## DataBase
Status | Agency | Project Title | Multi-Year/Multi-Year Partial Phase-out/One-off Phase-Out/Individual/RMP/RMP Update/RMP for Non-LVC/Halon Banking | Region | Country | Sector | Mtg | Type | Num | A/N | IRDX | Chemical | Consumption ODP to be Phased Out per Proposal | Consumption ODP Phased Out | Production ODP to be Phased Out per Proposal | Production ODP Phased Out | Date Approved | First Disbursment Date | Date of Compl per Proposal | Planned Date of Completion | Date Completed (Actual) | Date of Financial Completion | Approved Funding (US$) | Adjustment (US$) | Approved Funding plus Adjustments (US$) | Funds Disbursed (US$) | Per Cent of Funds Disbursed | Balance (US$) | Funds Committed (US$) | Estimated Disbursement in Current Year (US$) | Support Cost Approved (US$) | Support Cost Adjustment (US$) | Support Cost Disbursed (US$) | Support Cost Balance (US$) | Support Cost Committed (US$) | Remarks | Remarks (Latest information) | Year of Contribution | Latest Planned Date of Completion | Business Plan Allocation (Investment/Non-Investment) | Disbursements made to final beneficiaries from FECO/ MEP | Inplementation Delays/Status Report Decisions (77th Meeting)
FIN | Germany | National phase-out plan (1st tranche) | Multi-Year | ASP | AFG | PHA | 47 | INV | 06 | A | I | CFC | 28 | 28 | 0 |  | 2005-11-01 | 2016-05-01 | 2007-12-01 |  | 2008-08-01 | 2010-08-01 | 118438 | 0 | 118438 | 118438 | 100% | 0 | 0 | 0 | 15397 | 0 | 15397 | 0 | 0 | The foam sector was evaluated. A strategy was worked out based on the training of technicians for one foam company. A training was conducted for Afghan technicians in Tehran, Iran in April 2008. In addition, an inspection was carried out to the foam company in Afghanistan, Kabul in 2008.
FIN | UNEP | National phase-out plan (1st tranche) | Multi-year | ASP | AFG | PHA | 47 | TAS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-04-01 | 2009-12-01 |  | 2010-12-01 | 2011-12-01 | 305000 | 0 | 305000 | 305000 | 100% | 0 | 0 |  | 39650 | 0 | 39650 | 0 | 0
FIN | Germany | National phase-out plan (2nd tranche) | Multi-Year | ASP | AFG | PHA | 48 | INV | 07 | A | I | CFC | 151.8 | 151.8 | 0 |  | 2006-04-01 | 2006-05-01 | 2009-12-01 |  | 2009-12-01 | 2011-11-01 | 642368 | 0 | 642368 | 642368 | 100% | 0 | 0 | 0 | 83508 | 0 | 83508 | 0 | 0 | R&R equipment was delivered in Apr-2007, training and commissioning was accomplished in May 2007, 83 R&R units have been distributed until 12-2008, furhter 63 will be distributed in 2009. In addition, two train the trainer workshops were organized in 2007 and 2008.
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | AFG | PHA | 55 | PRP | 09 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-09-01 | 2009-07-01 |  | 2010-12-01 | 2011-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 |  | 11050 | 0 | 11050 | 0 | 0
FIN | Germany | Preparation of a HCFC phase-out management plan | Individual | ASP | AFG | PHA | 60 | PRP | 11 | A | I | HCFC | 0 |  | 0 |  | 2010-04-01 | 2010-04-01 | 2011-04-01 |  | 2011-03-01 | 2013-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | HPMP approved at 63rd meeting
TRF | Germany | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | AFG | PHA | 63 | INV | 13 | A | I | HCFC | 0 | 0 | 0 |  | 2011-04-01 | 2011-10-01 | 2012-03-01 |  |  | 2016-12-01 | 85000 | -47938 | 37062 | 37062 | 100% | 0 |  |  | 11050 | -6232 | 4132 | 686 |  | transferred to UNIDO at 77th Excom (November 2017) |  |  |  | INV
COM | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | ASP | AFG | PHA | 63 | TAS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-12-01 | 2012-03-01 |  | 2015-12-01 |  | 120000 | 0 | 120000 | 89321 | 74.43% | 30679 | 30679 | 30679 | 15600 | 0 | 11611.73 | 3988.27 | 3988.27 | Project completed | Project completed. The funds were transferred to the country but UNEP has not yet received the full expenditure report
TRF | Germany | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | ASP | AFG | PHA | 72 | INV | 17 | A | I | HCFC | 1 |  | 0 |  | 2014-05-01 | 2014-09-01 | 2017-05-01 |  |  | 2016-12-01 | 84000 | -84000 | 0 | 0 | #DIV/0! | 0 |  |  | 10920 | -10920 | 433 | -433 |  | transferred to UNIDO at 77th Excom (November 2017)
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | ASP | AFG | PHA | 72 | TAS | 16 | A | I | HCFC-22 | 1.4 |  | 0 |  | 2014-05-01 | 2015-11-01 | 2017-05-01 | 2017-12-01 |  |  | 118000 | 0 | 118000 | 68066.92 | 57.68% | 49933.08 | 49933.08 | 4993.308 | 15340 | 0 | 8848.6996 | 6491.3004 | 6491.3004 | Brief progress report (actual/planned): One stakeholder consultation on quota system in Oct 2016. Media campaigns and notification on quota reduction and Ozone issues. Labelling planned. Identifiers distributed. ToT for RAC technicians. Certification system planned Legal arrangements(actual/planned): More regorous adaption of quota system (10% reduction) and 7 importers allocated quota. Ban of HCFC equipment planned for Jan 2018 First mission (actual/planned): 2nd planned for June 2017 All funds disbursed (yes/no): No Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: due to funds transfer issue and general conditions in the country If Yes, will delay have impact on project completion date (yes/no): Yes | Brief progress report (actual/planned): Coordination between UNEP, NOU and UNIDO initiated in Jan 2017 and a joint mission planned for July 2017. ToR for the verification report for 2014-2015 prepared and consultant being recruited. Legal arrangements(actual/planned): Yes First mission (actual/planned): next mission in June 2017 TOR completed(actual/planned): ___ First disbursement date (actual/planned): Nov 2015 actual All funds disbursed (yes/no): NO Any delay? (yes/no): ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___ |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor the appointment of project management unit coordinator.
ONG | UNIDO | HCFC phase-out management plan (Stage I, first and second tranches) | Multi-Year | ASP | AFG | PHA | 77 | INV | 20 | A | I | HCFC | 1 | 0 |  |  | 2016-11-01 |  | 2019-12-01 | 2019-12-01 |  |  | 131938 | 0 | 131938 | 0 | 0% | 131938 | 0 | 20000 | 11874 | 0 | 0 | 11874 | 0 | The transfer of the project from the Government of Germany to UNIDO has been approved at the 77th EXCOM. | - Several conference calls with the NOU have been held to catch up with the project status and follow up actions. - JD has been drafted and job vacancy has been posted for recruiting international consultants as agreed by the Government. Candidates have been shortlisted and some interviewed. Actions towards next goals: - A mission is planned in June 2017 jointly with UNEP. During the mission, companies listed in the project document will be visited in Herat. - The Government of Afghanistan also requested adding some companies and training centers in Kabul in the investment qualified institution list. They will be also visited during the mission in June. - Equipment needs will be identified during the mission, TOR will be prepared and bidding will be conducted afterwards accordingly. - No delay - No recurring problem - No impact on project completion date - No action required by Executive Committee
FIN | UNEP | Preparation of the country programme/RMP project | Individual | ASP | AFG | SEV | 43 | CPG | 02 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-12-01 | 2005-03-01 |  | 2005-10-01 | 2011-12-01 | 60000 | -18155 | 41845 | 41845 | 100% | 0 | 0 |  | 7800 | -2360 | 5440 | 0 | 0
FIN | UNEP | Institutional strengthening project (phase I, start-up) | Individual | ASP | AFG | SEV | 43 | INS | 01 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-08-01 | 2005-07-01 |  | 2005-07-01 | 2007-04-01 | 40000 | -13 | 39987 | 39987 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Start up of institutional strengthening project | Individual | ASP | AFG | SEV | 46 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-08-01 | 2005-12-01 |  | 2005-10-01 | 2006-10-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Establishment of national ozone unit for implementing the phase-out of ODS (institutional strengthening) | Individual | ASP | AFG | SEV | 47 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-02-01 | 2007-12-01 |  | 2007-11-01 | 2007-12-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | ASP | AFG | SEV | 53 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-04-01 | 2009-11-01 |  | 2009-11-01 | 2009-11-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | ASP | AFG | SEV | 58 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2009-12-01 | 2011-11-01 |  | 2011-12-01 | 2012-12-01 | 81250 | 68750 | 150000 | 150000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase V: 12/2011-11/2013) | Individual | ASP | AFG | SEV | 64 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2011-12-01 | 2013-11-01 |  | 2013-12-01 | 2014-12-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of institutional strengthening project (phase VI: 12/2013-11/2015) | Individual | ASP | AFG | SEV | 70 | INS | 15 | A | I |  | 0 |  | 0 |  | 2013-07-01 | 2014-04-01 | 2015-11-01 | 2017-07-01 |  |  | 150000 | 0 | 150000 | 0 | 0% | 150000 | 150000 | 15000 | 0 | 0 | 0 | 0 | 0 | Final payment yet to be reported by partner | Final payment yet to be reported by partner
ONG | UNEP | Extension of institutional strengthening project (phase VII: 12/2015-11/2017) | Individual | ASP | AFG | SEV | 74 | INS | 18 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-08-01 | 2017-11-01 | 2017-12-01 |  |  | 150000 | 0 | 150000 | 66.92 | 0.04461% | 149933.08 | 149933.08 | 14993.308 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): a number of activities carried out and ongoing: quota distribution and monitoring, customs training for illegal trade issues, data reporting, mainstreaming ozone into NEPA structure, consultation for introduction of bans, certification programmes, and awareness raising. one customers training conducted. A7 and CP data submitted. Awareness raising events on 8th March and 16th Sept. Initial stages of project implementation(actual/planned): Intermediate goals achieved (actual/planned): Legal arrangements(actual/planned): SSFA in place First disbursement date (actual/planned): Aug 2016 All funds disbursed (yes/no): No Any delay?(yes/no): ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): CP and A7 data being prepared. Legal arrangements(actual/planned): SSFA in place Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): Aug 2016 All funds disbursed (yes/no): No Any delay?(yes/no): ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | ASP | AFG | SEV | 74 | TAS | 19 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-10-01 | 2016-05-01 | 2017-06-01 |  |  | 110000 | 0 | 110000 | 5108.93 | 4.644% | 104891.07 | 95093.07 | 10489.107 | 14300 | 0 | 664.1609 | 13635.8391 | 12362.0991 | Brief progress report (actual/planned): ToR developed and consultant recruited. Survey conducted. Stakeholder consultations meetings held, one during the mission by UNEP in Oct 2016. Full draft of the survey report submitted for review by UNEP. Legal arrangements(actual/planned): SSFA in place Initial stages of project implementation(actual/planned): Intermediate goals achieved (actual/planned): Yes survey completed Project completion and follow up: ___ First disbursement date (actual/planned): Oct 2016 All funds disbursed (yes/no): No Any delay?(yes/no): ___ If Yes, reasons for delay & action plan to resolve: Insufficient institutional capacity at national level to conduct the survey If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): Comments on the first draft sent by UNEP Feb 2017. Comments are currently being incorporated into the final draft of the survey report. Legal arrangements(actual/planned): SSFA in place Initial stages of project implementation(actual/planned): Intermediate goals achieved (actual/planned): Yes survey completed and first draft of the report produced Project completion and follow up: ___ First disbursement date (actual/planned): Oct 2016 All funds disbursed (yes/no): No Any delay?(yes/no): ___ If Yes, reasons for delay & action plan to resolve: Insufficient institutional capacity at national level to conduct the survey If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___
ONG | France | Strategy for disposal and destruction of ODS for five low-volume-consuming Central African countries (Burundi, Cameroon, Central African Republic, Congo and Guinea) | Individual | AFR | AFR | DES | 68 | TAS | 41 | A | I | CFC | 0 |  | 0 |  | 2012-12-01 | 2013-05-01 | 2013-12-01 | 2017-12-01 |  |  | 80000 | 0 | 80000 | 53159 | 66.45% | 26841 | 7750 | 26000 | 10400 | 0 | 6911 | 3489 | 1008 |  | The review of the Report for Policymakers by France and UNIDO still pending as well as the translation of the Report for Policymakers into French; Followig that, we will share the technical teport and the report for Policymakers with all five participating countries, asking them to provide their comments (with a focus on the Report for Policymakers).
FIN | UNEP | Regional workshop on methyl bromide for English-speaking African countries | Individual | AFR | AFR | FUM | 16 | TRA | 10 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-04-01 | 1996-03-01 |  | 1995-09-01 | 1999-04-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0
FIN | Australia | Replacement of methyl bromide with non-ozone depleting alternative in grain storage | Individual | AFR | AFR | FUM | 17 | TAS | 14 | A | D |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-10-01 | 1996-01-01 |  | 1995-10-01 | 1995-11-01 | 38896 | 0 | 38896 | 38896 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed |  | 1995
FIN | UNDP | Methyl bromide data collection for Africa | Individual | AFR | AFR | FUM | 17 | TAS | 15 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-09-01 | 1996-01-01 |  | 1998-04-01 | 2000-12-01 | 179850 | 0 | 179850 | 179850 | 100% | 0 | 0 | 0 | 23380.5 | 0 | 23380.5 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1995 |  | Non-Investment
FIN | UNEP | Regional survey and workshop on methyl bromide for French-speaking African countries | Individual | AFR | AFR | FUM | 21 | TRA | 18 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-04-01 | 1998-02-01 |  | 1998-04-01 | 1999-03-01 | 275000 | 0 | 275000 | 275000 | 100% | 0 | 0 |  | 35750 | 0 | 35750 | 0 | 0
FIN | UNEP | Regional training of trainer courses for extension workers | Individual | AFR | AFR | FUM | 27 | TRA | 23 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 2001-10-01 |  | 2001-12-01 | 2006-02-01 | 80000 | -16044 | 63956 | 63956 | 100% | 0 | 0 |  | 10400 | -2085.75 | 8314.25 | 0 | 0
FIN | UNEP | Regional training workshops on policy development | Individual | AFR | AFR | FUM | 27 | TRA | 24 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-06-01 | 2000-03-01 |  | 1999-12-01 | 2001-12-01 | 130000 | 0 | 130000 | 130000 | 100% | 0 | 0 |  | 16900 | 0 | 16900 | 0 | 0
FIN | UNEP | Regional workshop on the experiences of use of methyl bromide alternatives evaluated under the Multilateral Fund | Individual | AFR | AFR | FUM | 34 | TRA | 28 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2003-08-01 | 2002-07-01 |  | 2004-03-01 | 2009-07-01 | 80000 | -24177 | 55823 | 55823 | 100% | 0 | 0 |  | 10400 | -3142.71 | 7257.29 | 0 | 0 |  |  |  | 2003-09-01
FIN | UNDP | Technical assistance for methyl bromide reductions and formulation of regional phase-out strategies for low-volume consuming countries | Individual | AFR | AFR | FUM | 38 | TAS | 32 | A | I | MeBr | 1.5 | 1.5 | 0 | 0 | 2002-11-01 | 2003-02-01 | 2006-02-01 |  | 2011-12-01 | 2014-02-01 | 550000 | -2111.83 | 547888.17 | 547888 | 100% | 0.17 | 0 | 0 | 70500 | -270.7 | 70229.28 | 0.02 | 0 | Financially completed in 2014. | Some invoices still pending. | 2002 |  | Non-Investment
COM | UNIDO | Regional demonstration project on alternatives to the use of methyl bromide for treatment of high moisture dates (Algeria and Tunisia) | Individual | AFR | AFR | FUM | 54 | DEM | 40 | A | I |  | 0 | 0 |  |  | 2008-04-01 | 2008-06-01 | 2010-03-31 |  | 2016-12-01 |  | 306812 | 0 | 306812 | 259381.61 | 84.54% | 47430.39 | 12741.33 | 1 | 23011 | 0 | 19454 | 3557 | 956 | - In coordination with international experts and national expert from Tunisia, UNIDO has worked on the dissemination of project results. In particular, UNIDO managed to disseminate project results at several level, both national and in the region. - UNIDO has produced a video and a technical brochure on the PH3/CO2 technology and has organized a side event during the MOP in Vienna in 2016. - Final technical report was prepared, for further dissemination to the interested parties. - Project is completed by December 2016. - Financial completion is progress, balance will be returned. |  |  |  | INV |  | To request the submission of additional status report to the 79th meeting to monitor project completion by December 2016.
FIN | Germany | Establishment of a regional halon bank for Eastern and Southern African countries (Botswana, Ethiopia, Kenya, Lesotho, Namibia, Tanzania and Zimbabwe) | Halon banking | AFR | AFR | HAL | 35 | TAS | 29 | A | I | HAL | 27 | 27 | 0 |  | 2001-12-01 | 2002-08-01 | 2005-01-01 |  | 2010-12-01 | 2012-12-01 | 350000 | 0 | 350000 | 350000 | 100% | 0 | 0 | 0 | 45500 | 0 | 45500 | 0 | 0 | Many of the countries phased out halons through controls and awareness. Most recently Botswana successfully phased out approx 8MT of halons.
CLO | UNDP | Sectoral phase out programme: establishing a regional halon bank for West and Central Africa (Benin, Burkina Faso, Cameroon, Congo, Congo DR, and Guinea) | Individual | AFR | AFR | HAL | 37 | TAS | 31 | A | I | Halon | 61 | 44.2 | 0 | 0 | 2002-07-01 | 2003-02-01 | 2005-08-01 |  |  | 2008-11-01 | 300000 | -81518.81 | 218481.19 | 218481 | 100% | 0.19 | 0 | 0 | 39000 | -10597.45 | 28402.53 | 0.02 | 0 | Canceled in 2008. Funds will be returned to Excom in 2011. |  | 2002 |  | Non-Investment
TRF | UNDP | Training and demonstration programme in commercial/industrial refrigeration in West Africa (French) | Individual | AFR | AFR | REF | 06 | TRA | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1993-02-01 |  |  | 1993-06-01 | 40000 | -40000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 5200 | -5200 | 0 | 0 | 0 | Transferred in 1993. Financially Completed in 1993. |  | 1992 |  | Non-Investment
TRF | UNDP | Training and demonstration programme in commercial/industrial refrigeration in Africa (English-speaking countries) | Individual | AFR | AFR | REF | 06 | TRA | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1993-02-01 |  |  | 1993-06-01 | 40000 | -40000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 5200 | -5200 | 0 | 0 | 0 | Transferred in 1993. Financially Completed in 1993. |  | 1992 |  | Non-Investment
FIN | UNEP | Regional training course on refrigeration for Africa | Individual | AFR | AFR | REF | 06 | TRA | 04 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-12-01 | 1992-12-01 |  | 1992-12-01 | 1993-12-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 |  | 0
FIN | UNEP | Training and demonstration programme in commercial/industrial refrigeration in West Africa (French) | Individual | AFR | AFR | REF | 10 | TRA | 05 | A | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-07-01 | 1994-05-01 |  | 1995-07-01 | 1995-12-01 | 43400 | 0 | 43400 | 43400 | 100% | 0 | 0 |  | 5642 | 0 | 5642 | 0 | 0
FIN | UNEP | Training and demonstration programme in commercial/industrial refrigeration in Africa (English-speaking countries) | Individual | AFR | AFR | REF | 10 | TRA | 06 | A | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-08-01 | 1994-05-01 |  | 1994-09-01 | 1994-12-01 | 43400 | 0 | 43400 | 43400 | 100% | 0 | 0 |  | 5642 | 0 | 5642 | 0 | 0
FIN | UNIDO | Preparation of a recovery and recycling projects in Benin, Botswana, Burkina Faso, Gambia, Guinea, Namibia and Senegal | Individual | AFR | AFR | REF | 17 | PRP | 12 | A | I |  | 0 | 0 |  |  | 1995-07-01 | 1996-04-01 | 1996-01-01 |  | 1997-09-01 | 1999-08-01 | 45000 | -1119 | 43881 | 43881 | 100% | 0 | 0 |  | 5850 | -155 | 5695 | 0 | 0 | FIN
FIN | France | Refrigeration and global environment evaluation of equipment modernization study |  | AFR | AFR | REF | 32 | TAS | 26 | A | I |  | 0 |  | 0 |  | 2000-12-01 | 2001-07-01 | 2002-07-01 |  | 2002-12-01 | 2002-11-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 |  | 0 | 750 | 0 | 750 | 0 |  | Project completed. Final report sent to the Secretariat in Mai 2003.
FIN | Germany | Strategic demonstration project for accelerated conversion of CFC chillers in 5 African Countries (Cameroon, Egypt, Namibia, Nigeria and Sudan) | Individual | AFR | AFR | REF | 48 | DEM | 34 | A | I | CFC | 0 |  | 0 |  | 2006-04-01 | 2006-09-01 | 2009-09-01 |  | 2010-12-01 | 2011-12-01 | 192500 | 0 | 192500 | 192500 | 100% | 0 | 0 | 0 | 25025 | 0 | 25025 | 0 | 0 | Chiller has been delivered to Namibia and installed. Project and financial completion under way.
ONG | Japan | Strategic demonstration project for accelerated conversion of CFC chillers in 5 African Countries (Cameroon, Egypt, Namibia, Nigeria and Sudan) | Individual | AFR | AFR | REF | 48 | DEM | 35 | A | I | CFC | 0 |  | 0 |  | 2006-04-01 | 2007-06-01 | 2009-09-01 | 2017-12-01 |  |  | 700000 | 0 | 700000 | 464950.68 | 66.42% | 235049.32 | 234993.07 | 234993.07 | 91000 | 0 | 60443.5884 | 30556.4116 | 30549.0991 | - In 2016 the remaining funds have been disbursed in combination with the remaining funds from FFEM for procurement of five chillers for the Taxation Authority in Sudan. - The chillers have been delivered to the beneficiary but the supplier was unable to conduct installation and commissioning since the beneficiary did not complete the preparation of the site. - A mission to Sudan took place in August 2016 by the UNIDO project manager and a technical expert to assess the situation. - A workplan has been elaborated with the beneficiary in order to complete the site preparation by the end of 2016, immediately followed by the installation and commissioning. Activities planned but not implemented, reasons and strategy: The installation and commissioning of the equipment did not take place since the beneficiary did not complete the preparation of the site. Was there any delay during the reporting year? Yes Any recurring problem? No Any impact on project completion date:Yes Any action required by Executive Committee? No | - In 2017 the beneficiary (Taxation Authority Sudan) has made a local procurement for retrofit of their existing cooling system in the two buildings where the new chillers will be installed. - After completion of the local works, the supplier will perform installation and commissioning of the new chillers. - The activities are expected to be completed in 2017. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | 2006 |  | investment
ONG | France | Strategic demonstration project for accelerated conversion of CFC chillers in 5 African Countries (Cameroon, Egypt, Namibia, Nigeria and Sudan) | Individual | AFR | AFR | REF | 48 | DEM | 36 | A | I | CFC | 0 |  | 0 |  | 2006-04-01 | 2010-12-01 | 2009-09-01 | 2017-12-01 |  |  | 360000 | 0 | 360000 | 345530 | 95.98% | 14470 | 0 | 14470 | 46800 | 0 | 44919 | 1881 | 1881 |  | The agreed workplan required local works on the retrofit that had to be procured by local procurement organized by the beneficiary. After completion of the local procurement in early 2017, the beneficiary has awarded a contract to Petra company to complete the retrofit of the air conditioning infrastructure in the TA buildings. It is expected that the retrofit will be completed in the 4th Q 2017 and the commissioning of the chillers will follow immediately. Actions towards next goals: completion of the retrofit and commissioning of the chillers Was there any delay during the reporting year? No. Any recurring problem? No Any action required by Executive Committee? No
COM | UNIDO | Strategic demonstration project for accelerated conversion of CFC chillers in 5 African Countries (Cameroon, Egypt, Namibia, Nigeria and Sudan) | Individual | AFR | AFR | REF | 48 | DEM | 37 | A | I |  | 0 | 0 |  |  | 2006-04-01 | 2007-01-01 | 2009-09-01 |  | 2014-12-14 |  | 747500 | 0 | 747500 | 735058.49 | 98.34% | 12441.51 | 12233.43 | 1 | 56063 | 0 | 55129 | 934 | 918 | The project was operationally completed. |  |  |  | INV
FIN | UNEP | Regional workshop for Africa | Individual | AFR | AFR | SEV | 06 | TRA | 01 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-04-01 | 1993-02-01 |  | 1992-12-01 | 1993-12-01 | 210000 | 0 | 210000 | 210000 | 100% | 0 | 0 |  | 27300 | 0 | 27300 | 0 | 0
FIN | South Africa | Industry workshop on the practical implementation of the Protocol for English-speaking countries |  | AFR | AFR | SEV | 11 | TRA | 07 | A | D |  | 0 |  |  |  | 1993-11-01 |  | 1995-11-01 | 1994-09-01 | 1994-09-01 | 1994-09-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | [5 empty] | 0 |  |  |  | 94
FIN | UNEP | Support to regional network for ODS officers in Africa (1994) | Individual | AFR | AFR | SEV | 12 | TAS | 09 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-03-01 |  | 1996-03-01 | 2000-03-01 | 180000 | 0 | 180000 | 180000 | 100% | 0 | 0 |  | 23400 | 0 | 23400 | 0 | 0
FIN | UNEP | Follow-up on prior regional workshop and training activities | Individual | AFR | AFR | SEV | 12 | TRA | 08 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-06-01 | 1995-03-01 |  | 1997-06-01 | 1999-04-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Support to regional network for ODS officers in Africa (1995) | Individual | AFR | AFR | SEV | 16 | TAS | 20 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-07-01 | 1996-03-01 |  | 1996-03-01 | 1999-01-01 | 232200 | 0 | 232200 | 232200 | 100% | 0 | 0 |  | 30186 | 0 | 30186 | 0 | 0
FIN | France | Technology transfer workshop for African countries on practical implementation of the Montreal Protocol |  | AFR | AFR | SEV | 17 | TRA | 11 | A | D |  | 0 |  | 0 |  | 1995-07-01 | 1995-12-01 | 1996-01-01 |  | 1996-02-01 | 1996-02-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Exécuté en février 1996 en coopération ave le PNUE. Project completed.
FIN | UNEP | African Network (1996) | Individual | AFR | AFR | SEV | 19 | TAS | 17 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1997-05-01 |  | 1996-12-01 | 1999-12-01 | 299400 | 0 | 299400 | 299400 | 100% | 0 | 0 |  | 38922 | 0 | 38922 | 0 | 0
FIN | UNEP | Regional workshop on monitoring and control of ODS consumption for English-speaking Africa | Individual | AFR | AFR | SEV | 19 | TRA | 16 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1997-05-01 |  | 1997-07-01 | 1999-01-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 |  | 11050 | 0 | 11050 | 0 | 0
FIN | UNEP | African Region Network (1997) | Individual | AFR | AFR | SEV | 21 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-12-01 | 411000 | -33344 | 377656 | 377656 | 100% | 0 | 0 |  | 53430 | -4334.72 | 49095.28 | 0 | 0
FIN | UNEP | African regional networks for French-speaking and English-speaking countries (1998) | Individual | AFR | AFR | SEV | 23 | TAS | 21 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-01-01 |  | 1998-12-01 | 2000-03-01 | 431000 | -21369 | 409631 | 409631 | 100% | 0 | 0 |  | 56030 | -2777.97 | 53252.03 | 0 | 0
FIN | UNEP | Africa Region Network (French-speaking and English-speaking) | Individual | AFR | AFR | SEV | 26 | TAS | 22 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-12-01 | 431000 | -14398 | 416602 | 416602 | 100% | 0 | 0 |  | 56030 | -1871.74 | 54158.26 | 0 | 0
FIN | UNEP | African regional network (French-and English-speaking countries) (2000) | Individual | AFR | AFR | SEV | 29 | TAS | 25 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2005-01-01 | 452550 | -30254 | 422296 | 422296 | 100% | 0 | 0 |  | 58832 | -3933 | 54899 | 0 | 0
FIN | UNEP | African regional network (French-speaking, English-speaking) (2001) | Individual | AFR | AFR | SEV | 32 | TAS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2003-06-01 | 464000 | -36863 | 427137 | 427137 | 100% | 0 | 0 |  | 60320 | -4792.19 | 55527.81 | 0 | 0
FIN | UNEP | Harmonization of legislative and regulatory mechanisms to improve monitoring and control of ODS consumption in French-speaking African countries | Individual | AFR | AFR | SEV | 32 | TAS | 28 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2002-06-01 |  | 2004-11-01 | 2007-12-01 | 151500 | -22085 | 129415 | 129415 | 100% | 0 | 0 |  | 19695 | -2871 | 16824 | 0 | 0
FIN | UNDP | Regional surveys in halon and methyl bromide sector | Individual | AFR | AFR | SEV | 36 | TAS | 30 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-09-01 | 2003-04-01 |  | 2002-11-01 | 2005-10-01 | 30000 | -146 | 29854 | 29854 | 100% | 0 | 0 | 0 | 3900 | -18.98 | 3881.02 | 4.3e-05 | 0 | Completed in 2002. Financially completed in 2005. |  | 2002 |  | Non-Investment
FIN | UNEP | Sub-regional project on harmonization of legislative and regulatory mechanisms to improve monitoring and control of ODS consumption in English-speaking Africa | Individual | AFR | AFR | SEV | 45 | TAS | 33 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-02-01 | 2006-12-01 |  | 2011-06-01 | 2011-12-01 | 140000 | 0 | 140000 | 140000 | 100% | 0 | 0 |  | 18200 | 0 | 18200 | 0 | 0
FIN | UNEP | African customs enforcement networks for preventing illegal trade of ODS in the African sub-regional trade organizations (CEMAC, COMESA, SACU and UEMOA) | Individual | AFR | AFR | SEV | 53 | TAS | 38 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-11-01 |  | 2009-07-01 | 2013-12-01 | 160000 | -2684 | 157316 | 157316 | 100% | 0 | 0 |  | 20800 | -348.92 | 20451.08 | 0 | 0
CLO | France | African customs enforcement networks for preventing illegal trade of ODS in the African sub-regional trade organizations (CEMAC, COMESA, SACU and UEMOA) | Individual | AFR | AFR | SEV | 53 | TAS | 39 | A | I | CFC | 0 |  | 0 |  | 2007-11-01 |  | 2009-11-01 |  |  | 2014-12-01 | 75000 | -75000 | 0 | 0 |  | 0 |  | 0 | 9750 | -9750 |  | 0 |  | Cancelled by decision 70/8/(c). |  |  | 2010-12-01
FIN | UNIDO | Preparation of a national ODS phase-out plan | Individual | EUR | ALB | PHA | 36 | PRP | 03 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-06-01 | 2003-07-01 |  | 2003-12-01 | 2004-12-01 | 40000 | -458 | 39542 | 39541.55 | 100% | 0.45 | 0 |  | 5200 | -68 | 5132 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National ozone depleting substances phase-out plan: conversion of cleaning installations from carbon tetrachloride (CTC) to tetrachloroethylene (PER) at Energy Combinat Ltd., Elbasan | Multi-Year | EUR | ALB | PHA | 39 | INV | 10 | A | I | CTC | 2.3 | 2.3 |  |  | 2003-04-01 | 2005-09-01 | 2005-04-01 |  | 2005-12-01 | 2007-09-01 | 45000 | -192 | 44808 | 44807.85 | 100% | 0.15 | 0 |  | 3375 | -14 | 3361 | 0 | 0 | FIN
FIN | UNIDO | National ozone depleting substances phase-out plan: refrigerant recovery and recycling network | Multi-Year | EUR | ALB | PHA | 39 | TAS | 05 | A | I | CFC | 6.8 | 6.8 |  |  | 2003-04-01 | 2004-12-01 | 2006-04-01 |  | 2007-12-01 | 2008-09-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 7500 | 0 | 7500 | 0 | 0 | FIN |  |  | 2006-12-01 | INV
FIN | UNIDO | National ozone depleting substances phase-out plan: awareness workshop to prevent the introduction of methyl bromide | Multi-Year | EUR | ALB | PHA | 39 | TAS | 08 | A | I | MBR | 0 | 0 |  |  | 2003-04-01 | 2003-12-01 | 2004-04-01 |  | 2004-07-01 | 2005-09-01 | 20000 | -319 | 19681 | 19681.27 | 100% | -0.27 | 0 |  | 1500 | -26 | 1474 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | National ozone depleting substances phase-out plan: programme management and auditing | Multi-Year | EUR | ALB | PHA | 39 | TAS | 09 | A | I |  | 0 | 0 |  |  | 2003-04-01 | 2005-04-01 | 2009-12-01 |  | 2007-12-01 | 2008-07-01 | 16068 | 0 | 16068 | 16068 | 100% | 0 | 0 |  | 1205 | 0 | 1205 | 0 | 0 | FIN |  |  | 2009-12-01 | NON-INV
FIN | UNEP | National ODS phase-out plan: training of customs officers in monitoring of ODS | Multi-year | EUR | ALB | PHA | 39 | TRA | 06 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2004-01-01 | 2004-04-01 |  | 2005-08-01 | 2007-04-01 | 35700 | -278 | 35422 | 35422 | 100% | 0 | 0 |  | 4641 | -36 | 4605 | 0 | 0
FIN | UNEP | National ODS phase-out plan: training of trainers in good practices of refrigeration | Multi-year | EUR | ALB | PHA | 39 | TRA | 07 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2004-01-01 | 2004-04-01 |  | 2006-07-01 | 2010-12-01 | 82425 | -10163 | 72262 | 72262 | 100% | 0 | 0 |  | 10715 | -1322 | 9393 | 0 | 0 |  |  |  | 2005-07-01
FIN | UNIDO | National ODS phase out plan (2nd tranche) | Multi-Year | EUR | ALB | PHA | 46 | INV | 11 | A | I | CFC | 25 | 25 |  |  | 2005-07-01 | 2006-08-01 | 2006-07-01 |  | 2008-04-01 | 2010-12-01 | 172322 | 0 | 172322 | 172322.01 | 100% | -0.01 | 0 |  | 12924 | 0 | 12924 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National ODS phase out plan (3rd tranche) | Multi-Year | EUR | ALB | PHA | 50 | INV | 14 | A | I | CFC | 21 | 21 |  |  | 2006-11-01 | 2007-03-01 | 2007-11-01 |  | 2009-12-01 | 2010-12-01 | 72322 | 0 | 72322 | 72321.85 | 100% | 0.15 | 0 |  | 5424 | 0 | 5424 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National ODS phase out plan (fourth and fifth tranches) | Multi-Year | EUR | ALB | PHA | 54 | INV | 15 | A | I | CFC | 13 | 13 |  |  | 2008-04-01 | 2008-12-01 | 2009-03-31 |  | 2011-01-01 | 2012-05-01 | 64644 | -17 | 64627 | 64627.39 | 100% | -0.39 | 0 |  | 4848 | -1 | 4847 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | EUR | ALB | PHA | 55 | PRP | 17 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 |  | 2011-06-01 | 2011-12-01 | 30000 | -74 | 29926 | 29926.15 | 100% | -0.15 | 0 |  | 2250 | -6 | 2244 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan (additional funding) | Individual | EUR | ALB | PHA | 57 | PRP | 18 | A | I |  | 0 | 0 |  |  | 2009-04-01 | 2009-12-01 | 2010-03-31 |  | 2011-06-01 | 2012-10-01 | 55000 | -897 | 54103 | 54102.72 | 100% | 0.28 | 0 |  | 4125 | -67 | 4058 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | National ODS Phase out plan (sixth tranche) | Multi-Year | EUR | ALB | PHA | 58 | INV | 19 | A | I | CFC | 2.2 | 2.2 |  |  | 2009-07-01 | 2010-12-01 | 2010-07-31 |  | 2012-05-01 | 2012-12-01 | 22322 | -438 | 21884 | 21883.81 | 100% | 0.19 | 0 |  | 1674 | -33 | 1641 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National ODS Phase out plan (seventh tranche) | Multi-Year | EUR | ALB | PHA | 58 | INV | 20 | A | I |  | 0 | 0 |  |  | 2009-07-01 | 2010-12-01 | 2010-07-31 |  | 2012-09-01 | 2013-10-01 | 22322 | -867 | 21455 | 21454.56 | 100% | 0.44 | 0 |  | 1674 | -65 | 1609 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | EUR | ALB | PHA | 64 | INV | 22 | A | I |  | 0 | 0 |  |  | 2011-07-01 | 2012-03-01 | 2013-07-31 |  | 2015-03-01 | 2016-10-01 | 45000 | -989 | 44011 | 44011.13 | 100% | -0.13 | 0 |  | 4050 | -89 | 3961 | 0 | 0 | The project was financially completed and the balance was returned at the 77th ExCom. |  |  |  | INV
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | EUR | ALB | PHA | 64 | TAS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-01-01 | 2013-07-01 |  | 2013-07-01 | 2014-07-01 | 25000 | -46 | 24954 | 24954 | 100% | 0 | 0 |  | 3250 | -6 | 3244 | 0 | 0
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | EUR | ALB | PHA | 70 | INV | 25 | A | I | HCFC | 0.4 | 0.4 |  |  | 2013-07-01 | 2015-05-01 | 2015-07-31 | 2017-06-01 |  |  | 92000 | 0 | 92000 | 76453.85 | 83.1% | 15546.15 | 1783.98 | 15000 | 8280 | 0 | 6881 | 1399 | 160.5582 | Tranche II implementation: new legislation introducing certification scheme has been completed in 2016 and its implementation initiated. Training contractual arrangements have been concluded between UNIDO and counterpart to support certification scheme. Milestones achieved: Milestone 1: Equipment specification development - Yes Milestone 2: Specific legislation on certification scheme - Yes Milestone 3: Equipment delivery - Yes Activities planned but not implemented, reasons and strategy: The setting up of the Certification Commission was pending due to the time required for its component's approval at higher level in the Ministry. Actions towards next goals: NOU to report first quarter of 2017 on the status of the Commission for certification establishment. Training process in line with the new scheme has been initiated. Was there any delay during the reporting year? Yes If yes, reasons and action plan: The setting up of the Certification Commission was pending due the time required for its component's approval at higher level in the Ministry. Any recurring problem? No Any impact on project completion date: No Project completion scheduled for the year 2017 Any action required by Executive Committee? No | Operational completion will be achieved by June 2017 as planned. |  |  | INV |  | To request the submission of additional status report to the 79th meeting to monitor the completion of legislation for a new certification.
COM | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | EUR | ALB | PHA | 70 | TAS | 26 | A | I |  | 0.2 |  | 0 |  | 2013-07-01 | 2014-01-01 | 2015-07-01 |  | 2014-12-01 |  | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | Projectcompleted. | Project completed.
ONG | UNIDO | Verification report for stage I of HCFC phase-out management plan | Individual | EUR | ALB | PHA | 71 | TAS | 27 | A | I |  | 0 | 0 |  |  | 2013-12-01 | 2014-05-01 | 2015-05-01 | 2017-06-17 |  |  | 30000 | 0 | 30000 | 16526.69 | 55.09% | 13473.31 | 3359.25 | 10000 | 2700 | 0 | 1487 | 1213 | 302.3325 | NC for verification report on 2015 consumption was identified by NOU and contractual arrangements were initiated. Financial completion is foreseen in mid 2017. | NC for verification report was identified by NOU and contractual arrangements are under processing as of April 2017. The verification report budget will be executed as planned, until mid 2017. |  |  | NON-INV
ONG | UNIDO | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | EUR | ALB | PHA | 75 | INV | 30 | A | I |  | 0 | 0 |  |  | 2015-11-01 |  | 2018-12-01 | 2019-03-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 0 | 10000 | 3600 | 0 | 0 | 3600 | 0 | Tranche 3 budget became operational first quarter of 2016. Work plan to continue servicing sector activities and HPMP implementation has been agreed with NOU. Enhancement of recovery scheme and good practices in refrigeration is the main priority under tranche 3 and envisaged activities planned are the training of refrigeration technicians and environment inspectors. Workshops were planned and training execution was initiated during the second half of 2016. Milestones achieved: Milestone 1: Specific legislation on certification scheme - Yes Milestone 2: Equipment delivery - yes (equipment delivery purchased under tranche II was completed) Activities planned but not implemented, reasons and strategy: NA Actions towards next goals: NOU will continue to monitor enforcement of the training activities in line with the new certification scheme. Was there any delay during the reporting year? No If yes, reasons and action plan: The setting up of the Certification Commission was pending due the time required for its component's approval at higher level in the Ministry. Any recurring problem? No Any impact on project completion date: Yes Any action required by Executive Committee? No | Work plan for the year 2017 was developed by NOU. NCs for continuation of training activities were contracted for the period Jan - July 2017. Meeting with NOU to plan further tranche execution is scheduled for the week of 9 May 2017. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: Yes Any action required by Executive Committee? No |  |  | INV
ONG | UNEP | HCFC phase-out management plan (stage I, third tranche) | Multi-year | EUR | ALB | PHA | 75 | TAS | 31 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-03-01 | 2018-12-01 | 2018-12-01 |  |  | 23000 | 0 | 23000 | 205.73 | 0.8945% | 22794.27 | 22794.27 | 2279.427 | 2990 | 0 | 26.7449 | 2963.2551 | 2963.2551 | Brief progress report (actual/planned): Training materials for refrigeration technicians have been updated. Training of technicians on good practice in refrigeration took place in Tirana, 27–28 May 2016, in Durres, 28-30 April 2016 and in Vlore, 28-30 October 2016. In total, 87 technicians were trained and 69 received certifications of certification. Legal arrangements (actual/planned): SSFA with the Ministry of Environment established in February 2016. First mission (actual/planned): Yes - UNEP staff jointly with the Ozone Officer attended RILO ECE meeting in Tirana, 1-2 June 2016. TOR completed (actual/planned): N.a. First disbursement date (actual/planned): March 2016 All funds disbursed (yes/no): No Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: N.a. If Yes, will delay have impact on project completion date (yes/no): N.a. Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N.a | Brief progress report (actual/planned): NOU Albania submitted the report for Albania HPMP stage I tranche 3. Two training workshops of inspectors and enforcement officers are scheduled for 2017. Legal arrangements (actual/planned): SSFA with the Ministry of Environment established in February 2016. First mission (actual/planned): Yes - UNEP staff jointly with the Ozone Officer attended RILO ECE meeting in Tirana, 1-2 June 2016. TOR completed (actual/planned): N.a. First disbursement date (actual/planned): March 2016 All funds disbursed (yes/no): No Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: N.a. If Yes, will delay have impact on project completion date (yes/no): N.a. Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N.a
FIN | UNEP | Preparation of country programme | Individual | EUR | ALB | SEV | 30 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-04-01 | 2001-06-01 |  | 2002-06-01 | 2005-12-01 | 60000 | -29000 | 31000 | 31000 | 100% | 0 | 0 |  | 7800 | -3770 | 4030 | 0 | 0 |  |  |  | 2002-09-01
FIN | UNEP | Establishment of the Ozone Unit | Individual | EUR | ALB | SEV | 35 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-06-01 | 2002-12-01 |  | 2002-12-01 | 2004-01-01 | 42000 | 0 | 42000 | 42000 | 100% | 0 | 0 |  | 5460 | 0 | 5460 | 0 | 0
FIN | UNEP | Establishment of the Ozone Unit (second year) | Individual | EUR | ALB | SEV | 38 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2004-01-01 | 2003-12-01 |  | 2005-07-01 | 2007-06-01 | 54600 | 0 | 54600 | 54600 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase I, year 3) | Individual | EUR | ALB | SEV | 46 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-09-01 | 2007-07-01 |  | 2006-07-01 | 2008-03-01 | 54600 | 0 | 54600 | 54600 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase II) | Individual | EUR | ALB | SEV | 49 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2006-08-01 | 2008-06-01 |  | 2008-06-01 | 2010-12-01 | 109200 | 0 | 109200 | 109200 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase III) | Individual | EUR | ALB | SEV | 54 | INS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-08-01 | 2010-06-01 |  | 2011-06-01 | 2012-06-01 | 109200 | -63 | 109137 | 109137 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase IV) | Individual | EUR | ALB | SEV | 61 | INS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-01-01 | 2012-06-01 |  | 2012-12-01 | 2013-12-01 | 109200 | 0 | 109200 | 109200 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase V: 7/2012-6/2014) | Individual | EUR | ALB | SEV | 66 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 | 2012-12-01 | 2014-06-01 |  | 2014-06-01 | 2016-12-01 | 109200 | 0 | 109200 | 109200 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
ONG | UNEP | Renewal of institutional strengthening project (phase VI: 7/2014-6/2016) | Individual | EUR | ALB | SEV | 72 | INS | 28 | A | I |  | 0 |  | 0 |  | 2014-05-01 | 2014-10-01 | 2016-06-01 | 2017-12-01 |  |  | 109200 | 0 | 109200 | 80429.68 | 73.65% | 28770.32 | 28770.32 | 2877.032 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Reporting of Country Programme and Article 7 data for 2015, monitoring trade in ODS through the licensing system, quota allocation and iPIC, awareness raising through IOD celebrations and website, participation in ECA network meeting in Ashgabat, 24-27 May 2016, and Montreal Protocol meetings, approval of Albania IS phase 7 by ExCom 75, coordination and reporting on Montreal Protocol projects (HPMP, ODS alternatives survey). Legal arrangements (actual/planned): SSFA with the Ministry of Environment signed in August 2014. Initial stages of project implementation(actual/planned): N.a. Intermediate goals achieved (actual/planned): N.a. Project completion and follow up: September 2016 First disbursement date (actual/planned): October 2014 All funds disbursed (yes/no): Yes Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: Delay in releasing the third (final) disbursement due to slow payment processing. If Yes, will delay have impact on project completion date (yes/no): Yes Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N.a. | Project completed.
ONG | UNIDO | Survey of ODS alternatives at the national level | Individual | EUR | ALB | SEV | 74 | TAS | 29 | A | I |  | 0 | 0 |  |  | 2015-05-01 | 2016-07-01 | 2016-05-31 | 2017-06-16 |  |  | 40000 | 0 | 40000 | 38266.46 | 95.67% | 1733.54 | 2013.31 | 1 | 3600 | 0 | 0 | 3600 | 181.1979 | Two consultants were appointed to conduct the survey. Milestones achieved: Milestone 1: Submission of the preliminary results (Excel tables) Yes Milestone 2: ODS alternatives survey report completed - submission planned by 8 May 2017 Was there any delay during the reporting year? Yes, the project was implemented in timelines set by the NOU. Any impact on project completion date: Yes, completion is expected for Jun 17. | Milestones achieved: Milestone 1: Submission of the preliminary results (Excel tables) Yes Milestone 2: ODS alternatives survey report completed - submission planned by 8 May 2017. |  |  | NON-INV
ONG | UNEP | Renewal of institutional strengthening project (phase VII: 7/2016-6/2018) | Individual | EUR | ALB | SEV | 76 | INS | 32 | A | I |  | 0 |  | 0 |  | 2016-05-01 | 2016-09-01 | 2018-06-01 | 2018-06-01 |  |  | 139776 | 0 | 139776 | -4.5475e-12 | -3.253e-15% | 139776 | 139776 | 13977.6 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Monitoring trade in ODS through the licensing system, quota allocation and iPIC, awareness raising through the website and IOD celebrations, participation in ECA thematic meeting in Belgrade, 29 November - 1 December 2016, as well as Montreal Protocol meetings, coordination and reporting on Montreal Protocol projects (HPMP, ODS alternatives survey). Legal arrangements (actual/planned): SSFA with the Ministry of Environment signed by both parties in August 2016. Initial stages of project implementation(actual/planned): N.a. Intermediate goals achieved (actual/planned): N.a. Project completion and follow up: N.a. First disbursement date (actual/planned): September 2016 All funds disbursed (yes/no): No Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: N.a. If Yes, will delay have impact on project completion date (yes/no): N.a. Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N.a. | Brief progress report (actual/planned): NOU Albania has been preparing several project related reports required by different government authorities and the implementing agencies. Legal arrangements (actual/planned): SSFA with the Ministry of Environment signed by both parties in August 2016. Initial stages of project implementation(actual/planned): N.a. Intermediate goals achieved (actual/planned): N.a. Project completion and follow up: N.a. First disbursement date (actual/planned): September 2016 All funds disbursed (yes/no): No Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: N.a. If Yes, will delay have impact on project completion date (yes/no): N.a. Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N.a.
FIN | UNIDO | Phasing out of CFCs at Entreprise Nationale des Detergents (ENAD) | Individual | AFR | ALG | ARS | 18 | INV | 12 | A | I | CFC | 150 | 150 |  |  | 1995-11-01 | 1996-07-01 | 1997-05-01 |  | 1997-12-01 | 2002-05-01 | 614850 | 0 | 614850 | 614850.15 | 100% | -0.15 | 0 |  | 79931 | -46 | 79885 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Etablissement Has Mohamed | Individual | AFR | ALG | ARS | 20 | INV | 15 | A | I | CFC | 22.5 | 22.5 |  |  | 1996-10-01 | 1997-08-01 | 1997-10-01 |  | 1998-12-01 | 2000-12-01 | 82018 | 0 | 82018 | 82018 | 100% | 0 | 0 |  | 10662 | -2 | 10660 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Vague de Fraicheur | Individual | AFR | ALG | ARS | 20 | INV | 16 | A | I | CFC | 51.4 | 51.4 |  |  | 1996-10-01 | 1997-10-01 | 1997-10-01 |  | 1998-12-01 | 2001-12-01 | 164623 | 0 | 164623 | 164623.06 | 100% | -0.06 | 0 |  | 21401 | -13 | 21388 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Ets. Wouroud | Individual | AFR | ALG | ARS | 20 | INV | 17 | A | I | CFC | 47 | 47 |  |  | 1996-10-01 | 1997-10-01 | 1997-10-01 |  | 1998-12-01 | 2000-12-01 | 187772 | -420 | 187352 | 187352 | 100% | 0 | 0 |  | 24410 | -93 | 24317 | 0 | 0 | FIN
CLO | UNIDO | Phasing out CFCs at Laboratoire Bendi | Individual | AFR | ALG | ARS | 20 | INV | 18 | A | I | CFC | 19.2 | 19.2 |  |  | 1996-10-01 | 1997-10-01 | 1997-10-01 |  |  | 2002-05-01 | 56790 | -3005 | 53785 | 53785 | 100% | 0 | 0 |  | 7383 | -402 | 6981 | 0 | 0 | CLO
FIN | UNIDO | Phasing out CFCs at Ets. COPHYD | Individual | AFR | ALG | ARS | 20 | INV | 19 | A | I | CFC | 15 | 15 |  |  | 1996-10-01 | 1997-09-01 | 1997-10-01 |  | 1997-07-01 | 1999-08-01 | 53024 | -1291 | 51733 | 51733 | 100% | 0 | 0 |  | 6893 | -178 | 6715 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-11 and CFC-12 with hydrocarbons in the aerosol sector at Ets Djadir | Individual | AFR | ALG | ARS | 25 | INV | 28 | A | I | CFC | 38.4 | 38.4 |  |  | 1998-07-01 | 1999-11-01 | 1999-08-01 |  | 2000-12-01 | 2002-08-01 | 147807 | -316 | 147491 | 147490.52 | 100% | 0.48 | 0 |  | 19215 | -72 | 19143 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the aerosol sector | Individual | AFR | ALG | ARS | 27 | PRP | 36 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-05-01 | 1999-12-01 |  | 2000-11-01 | 2001-09-01 | 15000 | -598 | 14402 | 14402.12 | 100% | -0.12 | 0 |  | 1950 | -81 | 1869 | 0 | 0 | FIN
FIN | UNIDO | Phase out of CFC11/CFC12 by conversion to hydrocarbons technology in the manufacture of aerosols at Floreal | Individual | AFR | ALG | ARS | 28 | INV | 38 | A | I | CFC | 18.1 | 18.1 |  |  | 1999-07-01 | 2000-05-01 | 2000-08-01 |  | 2001-07-01 | 2002-09-01 | 77145 | -78 | 77067 | 77066.69 | 100% | 0.31 | 0 |  | 10029 | -26 | 10003 | 0 | 0 | FIN
FIN | UNIDO | Phase out of CFC-11/CFC-12 by conversion to hydrocarbon technology in the manufacture of aerosols at company Saco | Individual | AFR | ALG | ARS | 28 | INV | 41 | A | I | CFC | 19 | 19 |  |  | 1999-07-01 | 2000-05-01 | 2000-08-01 |  | 2002-02-01 | 2003-05-01 | 73691 | -74 | 73617 | 73617 | 100% | 0 | 0 |  | 9580 | -25 | 9555 | 0 | 0 | FIN |  |  | 2002-03-01
CLO | UNIDO | Preparation of 8 investment projects in the aerosol sector | Individual | AFR | ALG | ARS | 36 | PRP | 52 | A | I |  | 0 | 0 |  |  | 2002-03-01 |  | 2003-04-01 |  |  | 2003-05-01 | 25000 | -25000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 3250 | -3250 | 0 | 0 | 0 | CLO |  |  |  | INV
FIN | UNIDO | Preparation for pilot demonstration project on ODS waste management and disposal | Individual | AFR | ALG | DES | 59 | PRP | 74 | A | I |  | 0 | 0 |  |  | 2009-11-01 | 2009-12-01 | 2011-05-31 |  | 2014-12-31 | 2016-03-01 | 85000 | -5538 | 79462 | 79461.61 | 100% | 0.39 | 0 |  | 6375 | -415 | 5960 | 0 | 0 | The project was financially completed and the balance was returned at the 76th ExCom. |  |  |  | NON-INV
ONG | France | Pilot demonstration project on ODS waste management and disposal | Individual | AFR | ALG | DES | 72 | DEM | 78 | A | I | CFC | 0 |  | 0 |  | 2014-05-01 |  | 2016-05-01 | 2017-12-01 |  |  | 250000 | 0 | 250000 | 0 | 0% | 250000 |  |  | 32500 | 0 | 0 | 32500 |  |  | No progress occurred in 2017.
ONG | UNIDO | Pilot demonstration project on ODS waste management and disposal | Individual | AFR | ALG | DES | 72 | DEM | 79 | A | I |  | 0 | 0 |  |  | 2014-05-01 | 2015-04-01 | 2016-12-31 | 2017-12-01 |  |  | 375059 | 0 | 375059 | 13518.5 | 3.604% | 361540.5 | 0 | 1 | 26254 | 0 | 946 | 25308 | 0 | No progress and in the list to be cancelled. | No progress occurred. The project is suggested for cancellation. |  |  | INV
FIN | UNIDO | Preparation of an investment project for the phase-out of CFC-11 in the manufacture of sandwich panels at Prosider (Annaba-Algeria) | Individual | AFR | ALG | FOA | 15 | PRP | 06 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-05-01 | 1995-06-01 |  | 1995-11-01 | 1999-08-01 | 25000 | -1584 | 23416 | 23416 | 100% | 0 | 0 |  | 3250 | -211 | 3039 | 0 | 0 | FIN
FIN | UNIDO | Preparation of an investment project for CFC phase-out in the production of rigid foam at Batimetal | Individual | AFR | ALG | FOA | 15 | PRP | 08 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-05-01 | 1995-06-01 |  | 1995-11-01 | 1999-08-01 | 25000 | -4245 | 20755 | 20755 | 100% | 0 | 0 |  | 3250 | -556 | 2694 | 0 | 0 | FIN
CLO | UNIDO | Phasing out CFC-11 in the manufacture of sandwich panels by discontinuous method at Prosider Berrahal | Individual | AFR | ALG | FOA | 19 | INV | 13 | A | I | CFC | 82 | 82 |  |  | 1996-05-01 | 1997-07-01 | 1997-11-01 |  |  | 2003-03-01 | 434500 | -564 | 433936 | 433936.34 | 100% | -0.34 | 0 |  | 56485 | -163 | 56322 | 0 | 0 | CLO
FIN | UNIDO | Phasing out CFC-11 in the manufacture of sandwich panels at Batimetal Beni Mansour | Individual | AFR | ALG | FOA | 19 | INV | 14 | A | I | CFC | 110 | 110 |  |  | 1996-05-01 | 1997-07-01 | 1997-11-01 |  | 1998-12-01 | 2003-03-01 | 496650 | 0 | 496650 | 496649.82 | 100% | 0.18 | 0 |  | 64565 | -78 | 64487 | 0 | 0 | FIN
CLO | UNIDO | Phasing out CFC-11 at Ets Leulmi Essaid flexible polyurethane foam plant | Individual | AFR | ALG | FOA | 22 | INV | 21 | A | I | CFC | 0 | 0 |  |  | 1997-05-01 | 1997-06-01 | 1998-06-01 |  |  | 2002-09-01 | 61880 | -55372 | 6508 | 6508.1 | 100% | -0.1 | 0 |  | 8044 | -7199 | 845 | 0 | 0 | CLO
FIN | UNIDO | Phasing out CFC-11 at Snam flexible polyurethane foam plant | Individual | AFR | ALG | FOA | 22 | INV | 22 | A | I | CFC | 32 | 32 |  |  | 1997-05-01 | 1997-11-01 | 1998-06-01 |  | 1998-12-01 | 2002-08-01 | 88360 | -408 | 87952 | 87952.11 | 100% | -0.11 | 0 |  | 11487 | -71 | 11416 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Sammo flexible polyurethane foam plant | Individual | AFR | ALG | FOA | 22 | INV | 23 | A | I | CFC | 24 | 24 |  |  | 1997-05-01 | 1997-10-01 | 1998-06-01 |  | 1998-12-01 | 2002-08-01 | 98770 | -1411 | 97359 | 97359.2 | 100% | -0.2 | 0 |  | 12840 | -203 | 12637 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at La Mousse du Sud flexible polyurethane foam plant | Individual | AFR | ALG | FOA | 23 | INV | 25 | A | I | CFC | 95 | 95 |  |  | 1997-11-01 | 1998-06-01 | 1998-12-01 |  | 2002-10-01 | 2003-07-01 | 553480 | -1430 | 552050 | 552049.87 | 100% | 0.13 | 0 |  | 71952 | -299 | 71653 | 0 | 0 | FIN
FIN | UNIDO | Phase out of CFC-11 in the manufacture of flexible polyurethane foam through the use of methylene chloride technology at Ets. Matelas Djurdjura | Individual | AFR | ALG | FOA | 25 | INV | 27 | A | I | CFC | 28 | 28 |  |  | 1998-07-01 | 1998-12-01 | 1999-08-01 |  | 2001-07-01 | 2002-09-01 | 82608 | -753 | 81855 | 81855.45 | 100% | -0.45 | 0 |  | 10739 | -115 | 10624 | 0 | 0 | FIN
FIN | UNIDO | Phase out of CFC-11 in the manufacture of flexible polyurethane foam through the use of methylene chloride technology at Ets. Maghreb Mousse | Individual | AFR | ALG | FOA | 26 | INV | 29 | A | I | CFC | 24 | 24 |  |  | 1998-11-01 | 1999-02-01 | 1999-12-01 |  | 2001-07-01 | 2002-09-01 | 96492 | -500 | 95992 | 95992.28 | 100% | -0.28 | 0 |  | 12544 | -85 | 12459 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Matelas Atlas (Sam Atlas) | Individual | AFR | ALG | FOA | 27 | INV | 33 | A | I | CFC | 22 | 22 |  |  | 1999-03-01 | 1999-12-01 | 2000-04-01 |  | 2002-06-01 | 2004-03-01 | 120060 | 0 | 120060 | 120059.99 | 100% | 0.01 | 0 |  | 15608 | 0 | 15608 | 0 | 0 | FIN |  |  | 2001-07-01
FIN | UNIDO | Phasing out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at King's Matelas | Individual | AFR | ALG | FOA | 27 | INV | 34 | A | I | CFC | 20 | 20 |  |  | 1999-03-01 | 1999-12-01 | 2000-04-01 |  | 2002-06-01 | 2003-07-01 | 110179 | -38 | 110141 | 110140.55 | 100% | 0.45 | 0 |  | 14323 | -27 | 14296 | 0 | 0 | FIN |  |  | 2001-07-01
FIN | UNIDO | Project preparation in the foam sector (flexible) | Individual | AFR | ALG | FOA | 27 | PRP | 31 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-06-01 | 1999-12-01 |  | 2001-10-01 | 2002-12-01 | 18000 | -20 | 17980 | 17979.88 | 100% | 0.12 | 0 |  | 2340 | -6 | 2334 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by conversion of methylene chloride in the manufacture of flexible polyurethane slabstock foam at Matelas Mondial | Individual | AFR | ALG | FOA | 28 | INV | 37 | A | I | CFC | 20 | 20 |  |  | 1999-07-01 | 1999-12-01 | 2000-08-01 |  | 2002-06-01 | 2003-07-01 | 97986 | -66 | 97920 | 97919.63 | 100% | 0.37 | 0 |  | 12738 | -29 | 12709 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by conversion of methylene chloride in the manufacture of flexible polyurethane slabstock foam at Orania Mousse Ameublement (OMA) | Individual | AFR | ALG | FOA | 28 | INV | 39 | A | I | CFC | 18 | 18 |  |  | 1999-07-01 | 1999-12-01 | 2000-08-01 |  | 2002-06-01 | 2003-07-01 | 99477 | -104 | 99373 | 99373.32 | 100% | -0.32 | 0 |  | 12932 | -34 | 12898 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the flexible foam sector | Individual | AFR | ALG | FOA | 30 | PRP | 40 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-10-01 | 2001-04-01 |  | 2001-11-01 | 2002-12-01 | 20000 | -1 | 19999 | 19998.69 | 100% | 0.31 | 0 |  | 2600 | -4 | 2596 | 0 | 0 | FIN
FIN | Germany | Conversion of Algeria Mousse Polyurethane (AMP) | Individual | AFR | ALG | FOA | 31 | INV | 44 | A | I | CFC | 152 | 152 | 0 |  | 2000-07-01 | 2000-08-01 | 2003-08-01 |  | 2004-12-01 | 2007-12-01 | 565728 | 0 | 565728 | 565728 | 100% | 0 | 0 | 0 | 73545 | 0 | 73545 | 0 | 0 | Project completed. PCR has been submitted to the country
FIN | Germany | Conversion of SOFTPM, Choupot Oran, to LCD technology | Individual | AFR | ALG | FOA | 32 | INV | 45 | A | I | CFC | 80 | 80 | 0 |  | 2000-12-01 | 2001-01-01 | 2002-01-01 |  | 2004-12-01 | 2007-12-01 | 498400 | 0 | 498400 | 498400 | 100% | 0 | 0 | 0 | 64792 | 0 | 64792 | 0 | 0 | Project completed. PCR has been submitted to the country
FIN | Germany | Conversion of Matelas Souf to LCD technology | Individual | AFR | ALG | FOA | 32 | INV | 46 | A | I | CFC | 95 | 95 | 0 |  | 2000-12-01 | 2001-01-01 | 2002-01-01 |  | 2004-12-01 | 2007-12-01 | 561379 | 0 | 561379 | 561379 | 100% | 0 | 0 | 0 | 72979 | 0 | 72979 | 0 | 0 | Project completed. PCR has been submitted to the country
FIN | Germany | Project preparation for the phase out of ODS use in the flexible foam sub-sector | Individual | AFR | ALG | FOA | 33 | PRP | 49 | A | I |  | 0 |  | 0 |  | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2002-04-01 | 2007-12-01 | 30900 | 0 | 30900 | 30900 | 100% | 0 | 0 | 0 | 4017 | 0 | 4017 | 0 | 0 | Project completed. A report has been prepared and will be used in preparation of the terminal phase out plan.
FIN | UNIDO | Preparation for HCFC phase-out investment activities (polyurethane foam sector) | Individual | AFR | ALG | FOA | 59 | PRP | 73 | A | I |  | 0 | 0 |  |  | 2009-11-01 | 2010-04-01 | 2010-11-30 |  | 2010-12-01 | 2011-12-01 | 40000 | -1724 | 38276 | 38275.82 | 100% | 0.18 | 0 |  | 3000 | -129 | 2871 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | Conversion from HCFC-141b in the manufacture of polyurethane rigid insulation foam for domestic refrigerators at Cristor | Multi-Year | AFR | ALG | FOA | 62 | INV | 75 | A | I | HCFC | 2.4 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2012-12-31 | 2017-07-31 |  |  | 215380 | 0 | 215380 | 14423.18 | 6.697% | 200956.82 | 188891 | 200000 | 19384 | 0 | 1298 | 18086 | 17000 | -TOR for the purchase of the equipment was finalized and procurement exercise initiated. - Bidding conducted with 7 offers received. Milestones achieved: Milestone 1: Grant agreement submitted to beneficiary - Yes Milestone 3: Evaluation of offers ongoing - Yes Milestone 4: Contracts awarded - Yes Was there any delay during the reporting year? No Actions towards next goals: Finalize the conversion of the foaming line. Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Manufacturing of equipment completed and shipment of material being arranged. - Beneficiary is expected to complete the necessary civil works and other preparatory activities to be performed before the conversion takes place. - Tentative arrival of equipment to beneficiary is end of April 2017. Actions towards next goals: Finalize the conversion of the foaming line. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Project formulation in the methyl bromide sector | Individual | AFR | ALG | FUM | 22 | PRP | 24 | A | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-07-01 | 1998-06-01 |  | 2000-01-01 | 2000-07-01 | 8000 | -3793 | 4207 | 4207 | 100% | 0 | 0 |  | 1040 | -494 | 546 | 0 | 0 | FIN
FIN | UNIDO | Project preparation to replace methyl bromide in fumigation of dates in ten units | Individual | AFR | ALG | FUM | 34 | PRP | 50 | A | I |  | 0 | 0 |  |  | 2001-07-01 | 2001-09-01 | 2002-08-01 |  | 2011-12-01 | 2011-12-01 | 25000 | -11723 | 13277 | 13277.46 | 100% | -0.46 | 0 |  | 3250 | -1524 | 1726 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Technical assistance to phase out methyl bromide in pulses disinfestations | Individual | AFR | ALG | FUM | 50 | TAS | 65 | A | I | MBR | 1.6 | 1.6 |  |  | 2006-11-01 | 2007-12-01 | 2007-11-01 |  | 2008-12-01 | 2010-05-01 | 51000 | -1274 | 49726 | 49725.97 | 100% | 0.03 | 0 |  | 4590 | -115 | 4475 | 0 | 0 | FIN |  |  |  | INV
COM | UNIDO | Project preparation in the fumigants sector (high-moisture dates) | Individual | AFR | ALG | FUM | 72 | PRP | 80 | A | I |  | 0 | 0 |  |  | 2014-05-01 |  | 2015-05-31 |  | 2016-12-01 |  | 35000 | 0 | 35000 | 0 | 0% | 35000 | 0 | 1 | 2450 | 0 | 0 | 2450 | 0 | Project closed on 31 December 2016, as per ExCom Decision. |  |  |  | NON-INV
FIN | Germany | Project preparation, technical assistance in the halon sector | Individual | AFR | ALG | HAL | 31 | PRP | 42 | A | I |  | 0 |  | 0 |  | 2000-07-01 | 2001-01-01 | 2002-01-01 |  | 2001-06-01 | 2002-03-01 | 10520 | 0 | 10520 | 10520 | 100% | 0 | 0 | 0 | 1368 | 0 | 1368 | 0 | 0 | Project document submitted and approved.
FIN | Germany | Sectoral phase out programme: establishment of a halon bank | Individual | AFR | ALG | HAL | 35 | TAS | 51 | A | I | HAL | 392.3 | 392.3 | 0 |  | 2001-12-01 | 2002-10-01 | 2005-01-01 |  | 2010-07-01 | 2012-07-01 | 259500 | 0 | 259500 | 259500 | 100% | 0 | 0 | 0 | 33735 | 0 | 33735 | 0 | 0 | Project is completed, PCR has been sent to Algeria 10 months ago, so far no response.
CLO | Germany | Project preparation for terminal ODS phase out management plan, excluding the refrigeration sector | Individual | AFR | ALG | PHA | 37 | PRP | 57 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2002-10-01 | 2003-08-01 |  |  | 2007-09-01 | 42000 | 0 | 42000 | 42000 | 100% | 0 | 0 | 0 | 5460 | 0 | 5460 | 0 | 0 | The TPMP preparation was cancelled by the Government of Algeria long after the work was completely prepared. The results will be used by UNIDO.
FIN | UNIDO | Preparation of a national ODS phase-out plan | Individual | AFR | ALG | PHA | 46 | PRP | 63 | A | I |  | 0 | 0 |  |  | 2005-07-01 | 2007-04-01 | 2006-03-01 |  | 2008-04-01 | 2008-12-01 | 25000 | -1596 | 23404 | 23404.03 | 100% | -0.03 | 0 |  | 1875 | -120 | 1755 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Project preparation for an ODS phase-out management plan | Individual | AFR | ALG | PHA | 51 | PRP | 66 | A | I |  | 0 | 0 |  |  | 2007-03-01 | 2007-06-01 | 2008-03-01 |  | 2007-11-01 | 2007-12-01 | 15000 | -882 | 14118 | 14118.22 | 100% | -0.22 | 0 |  | 1125 | -66 | 1059 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | National phase-out plan (first tranche) | Multi-Year | AFR | ALG | PHA | 53 | INV | 67 | A | I | CFC TCA | 130.5 | 130.5 |  |  | 2007-11-01 | 2008-02-01 | 2009-03-01 |  | 2010-04-01 | 2012-07-01 | 723500 | 0 | 723500 | 723500.02 | 100% | -0.02 | 0 |  | 54263 | 0 | 54263 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | AFR | ALG | PHA | 55 | PRP | 68 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-09-01 | 2009-07-31 |  | 2010-12-01 | 2012-05-01 | 85000 | -255 | 84745 | 84744.79 | 100% | 0.21 | 0 |  | 6375 | -19 | 6356 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | National phase-out plan (second tranche) | Multi-Year | AFR | ALG | PHA | 58 | INV | 71 | A | I | CFC CTC TCA | 154 | 154 |  |  | 2009-07-01 | 2009-12-01 | 2010-07-31 |  | 2013-12-01 | 2014-07-01 | 198000 | -3610 | 194390 | 194390.16 | 100% | -0.16 | 0 |  | 14850 | -271 | 14579 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan (additional funding) | Individual | AFR | ALG | PHA | 58 | PRP | 70 | A | I |  | 0 | 0 |  |  | 2009-07-01 | 2009-11-01 | 2010-07-31 |  | 2012-12-01 | 2012-12-01 | 65000 | -22 | 64978 | 64978.26 | 100% | -0.26 | 0 |  | 4875 | -2 | 4873 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (conversion from HCFC-22 in the manufacture of room air conditioners at Condor) | Multi-Year | AFR | ALG | PHA | 66 | INV | 76 | A | I | HCFC | 8.3 | 0 |  |  | 2012-04-01 | 2013-01-01 | 2013-04-30 | 2018-06-01 |  |  | 1379460 | 0 | 1379460 | 30056.52 | 2.179% | 1349403.48 | 842731.5 | 600000 | 103460 | 0 | 2254 | 101206 | 63204.8625 | - Final TOR was agreed with the company in January and bidding started early February, which ended in March. Subsequently the offers were evaluated, several request for clarifications were sent to the bidders and the final evaluation of the offers was agreed end May. The contract for the selected supplier was signed by UNIDO early August and countersigned by the supplier in October after a visit to Condor where all technical details were agreed upon. The supplier started producing the equipment in 2016. Reasons for low disbursements: Slow progress in previous years due to new technology. Milestones achieved: First mission/working arrangements agreed: Yes; ToR for equipment purchase agreed upon: Yes, January 2016 Bids prepared & requested: Yes, February 2016 Contract awarded: Yes, early August 2016 Contract countersigned in October 2016 Equipment delivered & installed: No Commissioning & trial runs: No Activities planned but not implemented, reasons and strategy: Significant progress was made in 2016, everything as planned in December 2015. Actions towards next goals: Follow-up with supplier to accelerate delivery of equipment. Was there any delay during the reporting year? NO major delays in 2016. Any recurring problem? No. Any action required by Executive Committee? No. | - Equipment production was completed by February and the supplier started to arrange for shipping, however, some items were dangerous goods for which separate shipment had to be arranged. Draft shipping documents were provided to UNIDO, which were cleared. UNIDO initiated end March the process of tax exemption in Algeria, which is expected to take about 1 month. Shipment is expected to leave in April and arrive in May. Installation start date will be end August, which was agreed between Condor and the supplier due to peak production in the months before. Reasons for low disbursements: Equipment is not yet delivered. Milestones achieved: First mission/working arrangements agreed: Yes; ToR for equipment purchase agreed upon: Yes, January 2016 Bids prepared & requested: Yes, February 2016 Contract awarded: Yes, early August 2016 Contract countersigned in October 2016 Equipment delivered & installed: No Commissioning & trial runs: No Activities planned but not implemented, reasons and strategy: Delivery of equipment delayed due to peak production period at Condor. Actions towards next goals: Follow-up with supplier to accelerate delivery of equipment and subsequently installation and commissioning. Was there any delay during the reporting year? Yes, shipment was delayed by about 6 months. Any recurring problem? No. Any action required by Executive Committee? No. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (activities in the refrigeration servicing sector including phase-out of HCFC-141b used for flushing, and project monitoring) | Multi-Year | AFR | ALG | PHA | 66 | INV | 77 | A | I | HCFC | 2.8 | 0 |  |  | 2012-04-01 | 2012-10-01 | 2013-04-30 | 2019-03-01 |  |  | 214400 | 0 | 214400 | 36459.57 | 17.01% | 177940.43 | 0 | 20000 | 16080 | 0 | 2734 | 13346 | 0 | - Bidding for INV components of HPMP (Cristor and Condor) were finalized and conversions are ongoing. CONDOR: Shortly before the 75th ExCom, the company confirmed its readiness to start project implementation. UNIDO undertook a mission to Condor mid-December to discuss the details and the process of the bidding for equipment procurement. Final TOR was agreed with the company in January and bidding started early February and ended 18 March. Subsequently the offers will be evaluated and a contract is expected to be signed still in the 2nd quarter 2016. For this reason, disbursement level might not increase significantly by the 77th ExCom yet. CRISTOR: Bidding procedure for the purchase of one foaming line completed and conversion ongoing. UNIDO communicated to NOU about the necessity to prepare the consumption verification and plan other remaining activities. UNIDO is waiting for feedback from NOU on these activities. | Conversion of Cristor and Condor ongoing. UNIDO will follow-up with the NOU on the necessity to prepare the consumption verification and plan other remaining activities, including preparing the next tranche submission. |  |  | INV |  | To request the submission of additional status report to the 79th meeting to monitor no response from the national ozone unit on the training plan and verification exercise.
FIN | UNIDO | Investment project for phasing out CFCs at Entreprise Nationale des Industries de l'Electromenager, ENIEM | Individual | AFR | ALG | REF | 15 | INV | 09 | A | I | CFC | 425 | 425 |  |  | 1994-12-01 | 1995-12-01 | 1996-06-01 |  | 1996-12-01 | 2002-09-01 | 6589550 | -82919 | 6506631 | 6506630.78 | 100% | 0.22 | 0 |  | 856642 | -12121 | 844521 | 0 | 0 | FIN
FIN | UNIDO | Project formulation for establishment of a National Centre for recovery and recycling CFC-11, CFC-12 and CFC-502 | Individual | AFR | ALG | REF | 15 | PRP | 07 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1998-11-01 | 1995-06-01 |  | 1999-12-01 | 2001-11-01 | 25000 | -8254 | 16746 | 16746.19 | 100% | -0.19 | 0 |  | 3250 | -1077 | 2173 | 0 | 0 | FIN |  |  | 1999-12-01
FIN | UNIDO | Replacement of CFC-12 with HFC 134a for commercial refrigeration at Enapat | Individual | AFR | ALG | REF | 25 | INV | 26 | A | I | CFC | 9.2 | 9.2 |  |  | 1998-07-01 | 1999-03-01 | 1999-08-01 |  | 1998-12-01 | 2000-12-01 | 139932 | -16937 | 122995 | 122995 | 100% | 0 | 0 |  | 18191 | -2227 | 15964 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-12 with HFC-134a for domestic refrigeration at Enapem | Individual | AFR | ALG | REF | 26 | INV | 30 | A | I | CFC | 12.8 | 12.8 |  |  | 1998-11-01 | 1999-06-01 | 1999-12-01 |  | 1999-12-01 | 2002-05-01 | 167332 | -2890 | 164442 | 164441.7 | 100% | 0.3 | 0 |  | 21753 | -409 | 21343 | 1 | 0 | FIN
FIN | UNIDO | Project preparation in the commercial refrigeration sector (commercial) | Individual | AFR | ALG | REF | 27 | PRP | 35 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 2000-10-01 | 1999-12-01 |  | 2000-11-01 | 2001-07-01 | 15000 | -11980 | 3020 | 3019.87 | 100% | 0.13 | 0 |  | 1950 | -1558 | 392 | 0 | 0 | FIN
FIN | UNIDO | Strategy for the preparation of an RMP | Individual | AFR | ALG | REF | 31 | PRP | 43 | A | I |  | 0 | 0 |  |  | 2000-07-01 | 2001-06-01 | 2002-01-01 |  | 2003-01-01 | 2003-06-01 | 60000 | -1013 | 58987 | 58987.21 | 100% | -0.21 | 0 |  | 7800 | -144 | 7656 | 0 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration at the RCA (Société de Réfrigeration et de Conditionnement de l'air) | Individual | AFR | ALG | REF | 32 | INV | 47 | A | I | CFC | 27.3 | 27.3 |  |  | 2000-12-01 | 2001-07-01 | 2003-05-01 |  | 2003-12-01 | 2004-12-01 | 351768 | -5863 | 345905 | 345904.94 | 100% | 0.06 | 0 |  | 45730 | -834 | 44896 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a refrigeration sectoral phase-out plan | Individual | AFR | ALG | REF | 36 | PRP | 53 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-08-01 | 2003-07-01 |  | 2004-12-01 | 2005-11-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the first group of commercial refrigerator manufacturers | Individual | AFR | ALG | REF | 37 | INV | 56 | A | I | CFC | 18.6 | 18.6 |  |  | 2002-07-01 | 2002-12-01 | 2005-01-01 |  | 2004-12-01 | 2006-12-01 | 224320 | -22701 | 201619 | 201618.86 | 100% | 0.14 | 0 |  | 29162 | -2952 | 26210 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Refrigerant management plan to phase out the use of ODS in the refrigeration and air-conditioning sector (includes: training in good refrigerant management practices, training of customs officers, and national recovery and recycling) | Multi-Year | AFR | ALG | REF | 37 | TAS | 55 | A | I | CFC | 0 | 0 |  |  | 2002-07-01 | 2002-10-01 | 2003-12-01 |  | 2004-06-01 | 2004-07-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 |  | 26000 | -6 | 25994 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Refrigerant management plan to phase out the use of ODS in refrigeration and air-conditioning sector (including training in good refrigerant management practices, training of customs officers, and national recovery and recycling): Second tranche | Multi-Year | AFR | ALG | REF | 39 | TAS | 58 | A | I | CFC | 45 | 110 |  |  | 2003-04-01 | 2004-03-01 | 2004-04-01 |  | 2005-06-01 | 2007-05-01 | 700000 | 0 | 700000 | 699999.99 | 100% | 0.01 | 0 |  | 52500 | 0 | 52500 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan to phase out the use of ODS in refrigeration and air-conditioning sector: 2004 programme | Multi-Year | AFR | ALG | REF | 42 | TAS | 59 | A | I | CFC | 200 | 200 |  |  | 2004-04-01 | 2004-12-01 | 2005-04-01 |  | 2007-11-01 | 2008-12-01 | 524647 | -12543 | 512104 | 512104.16 | 100% | -0.16 | 0 |  | 39349 | -941 | 38408 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the last group of commercial refrigerator manufactures ( refrigeration sector terminal project) | Individual | AFR | ALG | REF | 44 | INV | 62 | A | I | CFC | 72.8 | 72.8 |  |  | 2004-12-01 | 2006-03-01 | 2007-04-01 |  | 2012-12-01 | 2014-07-01 | 589000 | -3630 | 585370 | 585370.14 | 100% | -0.14 | 0 |  | 44175 | -272 | 43903 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation for HCFC phase-out investment activities (refrigeration and air-to-air air-conditioning sector) | Individual | AFR | ALG | REF | 59 | PRP | 72 | A | I |  | 0 | 0 |  |  | 2009-11-01 | 2009-12-01 | 2010-11-30 |  | 2012-12-01 | 2012-12-01 | 60000 | -381 | 59619 | 59619.34 | 100% | -0.34 | 0 |  | 4500 | -29 | 4471 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNEP | Country programme preparation | Individual | AFR | ALG | SEV | 09 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1994-04-01 | 1993-06-01 |  | 1993-11-01 | 1994-12-01 | 15000 | 3000 | 18000 | 18000 | 100% | 0 | 0 |  | 1950 | 390 | 2340 | 0 | 0
FIN | UNEP | Institutional support for ODS phase-out | Individual | AFR | ALG | SEV | 11 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1995-01-01 | 1996-11-01 |  | 1999-03-01 | 2001-03-01 | 297000 | 0 | 297000 | 297000 | 100% | 0 | 0 |  | 38610 | 0 | 38610 | 0 | 0 |  |  |  | 1999-12-01
FIN | UNIDO | Preparatory assistance for phase out of ODS in the domestic refrigeration. production at ENIEM | Individual | AFR | ALG | SEV | 12 | PRP | 03 | A | I |  | 0 | 0 |  |  | 1994-03-01 | 1994-08-01 | 1994-09-01 |  | 1995-03-01 | 1998-08-01 | 25000 | -675 | 24325 | 24325 | 100% | 0 | 0 |  | 3250 | -93 | 3157 | 0 | 0 | FIN
FIN | UNIDO | Preparatory assistance for phase out of ODS in the aerosol production and solvent conversion at ENAD | Individual | AFR | ALG | SEV | 12 | PRP | 04 | A | I |  | 0 | 0 |  |  | 1994-03-01 | 1994-11-01 | 1994-09-01 |  | 1995-03-01 | 1998-08-01 | 25000 | -5049 | 19951 | 19951 | 100% | 0 | 0 |  | 3250 | -661 | 2589 | 0 | 0 | FIN
FIN | IBRD | Preparation of investment projects |  | AFR | ALG | SEV | 12 | PRP | 05 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 100000 | -93039 | 6961 | 6961 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | UNIDO | Project formulation for phasing out ODS in small- and medium-scale industries | Individual | AFR | ALG | SEV | 17 | PRP | 11 | A | I |  | 0 | 0 |  |  | 1995-07-01 | 1996-03-01 | 1996-01-01 |  | 1999-12-01 | 2001-03-01 | 50000 | -1409 | 48591 | 48591 | 100% | 0 | 0 |  | 6500 | -193 | 6307 | 0 | 0 | FIN |  |  | 1999-06-01
FIN | UNIDO | Project formulation of investment projects in the aerosol, foam and refrigeration sectors | Individual | AFR | ALG | SEV | 21 | PRP | 20 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-05-01 | 1997-08-01 |  | 1998-02-01 | 2002-09-01 | 50000 | -2690 | 47310 | 47309.6 | 100% | 0.4 | 0 |  | 6500 | -359 | 6140 | 1 | 0 | FIN
FIN | UNEP | Renewal of institutional strengthening | Individual | AFR | ALG | SEV | 27 | INS | 32 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2001-01-01 | 2001-04-01 |  | 2001-12-01 | 2003-06-01 | 90010 | 0 | 90010 | 90010 | 100% | 0 | 0 |  | 11701 | 0 | 11701 | 0 | 0 |  |  |  | 2002-06-01
FIN | UNEP | Renewal of institutional strengthening project (Phase 3) | Individual | AFR | ALG | SEV | 37 | INS | 54 | A | I | CFC | 21.2 | 21.2 | 0 | 0 | 2002-07-01 | 2004-01-01 | 2004-08-01 |  | 2006-07-01 | 2007-07-01 | 257000 | -1 | 256999 | 256999 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
CLO | Germany | Development of a country programme update | Individual | AFR | ALG | SEV | 43 | CPG | 60 | A | I |  | 0 |  | 0 |  | 2004-07-01 | 2004-09-01 | 2005-07-01 |  |  | 2007-09-01 | 13500 | 0 | 13500 | 13500 | 100% | 0 | 0 | 0 | 1215 | 0 | 1215 | 0 | 0 | The CPU update was cancelled by the Government of Algeria. The results have been used by UNIDO for the National Phase Out Plan.
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | ALG | SEV | 48 | INS | 64 | A | I | CFC | 21.3 | 21.3 | 0 | 0 | 2006-04-01 | 2006-12-01 | 2008-04-01 |  | 2008-12-01 | 2012-08-01 | 257400 | 0 | 257400 | 257400 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of the institutional strengthening project (phase V) | Individual | AFR | ALG | SEV | 57 | INS | 69 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-07-01 | 2011-03-01 |  | 2014-07-01 |  | 257400 | 0 | 257400 | 231660 | 90% | 25740 | 25740 | 25740 | 0 | 0 | 0 | 0 | 0 | Project completed | Project completed
ONG | UNEP | Extension of the institutional strengthening project (phase VI: 12/2014-11/2016) | Individual | AFR | ALG | SEV | 73 | INS | 81 | A | I |  | 0 |  | 0 |  | 2014-11-01 | 2016-02-01 | 2016-11-01 | 2017-11-01 |  |  | 257400 | 0 | 257400 | 0 | 0% | 257400 | 257400 | 25740 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Country received first payment in February 2016. Art5 data report for 2015 and CP data for 2015 have been provided in May 2016. Meeting of the steering Committee organized in February 2016 for the assessment of the licensing system and quota issued in 2015. Legal arrangements (actual/planned): Agreement signed in May 2015. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): CAP to agree with country for the mission date - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in February 2016__ All funds disbursed (yes/no): NO_ Final payment being _NO ___Any delay? (yes/no): YES___ If Yes, reasons for delay & action plan to resolve: due to changes in the Environment Ministry, project activities are slow down. If Yes, will delay have impact on project completion date (yes/no): _ If not addressed, the delay can affect timely and quality delivery of the project __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Brief progress report (actual/planned): Country received first payment in February 2016. Art5 data report for 2015 and CP data for 2015 have been provided in May 2016. Meeting of the steering Committee organized in February 2016 for the assessment of the licensing system and quota issued in 2015. Legal arrangements (actual/planned): Agreement signed in May 2015. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): CAP to agree with country for the mission date - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in February 2016__ All funds disbursed (yes/no): NO_ Final payment being _NO ___Any delay? (yes/no): YES___ If Yes, reasons for delay & action plan to resolve: due to changes in the Environment Ministry, project activities are slow down. If Yes, will delay have impact on project completion date (yes/no): _ If not addressed, the delay can affect timely and quality delivery of the project __ Any ongoing problems (yes/no): _ yes, NOO is on sick leave __ If Yes, is any action required by ExCom: _ n/a |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor project implementation progress and the disbursement rate of approved funds.
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | AFR | ALG | SEV | 74 | TAS | 82 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-05-01 | 2016-05-01 | 2017-05-01 |  |  | 110000 | 0 | 110000 | 60600 | 55.09% | 49400 | 49400 | 4940 | 14300 | 0 | 7878 | 6422 | 6422 | Brief progress report (actual/planned): Country received first payment in May 2016. Country is not ready to submit first draft of ODS Survey. Agreement signed in April 2016. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in May 16 __ All funds disbursed (yes/no): NO_ Final payment being _NO Any delay? (yes/no): YES ___ If Yes, reasons for delay & action plan to resolve: internal changes in the Environment Ministry, heavy administrative procedures, NOO on sick leave___ If Yes, will delay have impact on project completion date (yes/no): _ Yes, the country is already late in submitting its ODS report __ Any ongoing problems (yes/no): _ YES __ If Yes, is any action required by ExCom: _ n/a | Brief progress report (actual/planned): Country received first payment in May 2016. ODS Survey is delayed by the country beacause of changes in the government. Agreement signed in April 2016. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in May 16 __ All funds disbursed (yes/no): NO_ Final payment being _NO Any delay? (yes/no): YES ___ If Yes, reasons for delay & action plan to resolve: internal changes in the Environment Ministry, heavy administrative procedures. NOO on sick leave ___ If Yes, will delay have impact on project completion date (yes/no): _ Yes, the country seems not able to submitting its ODS report __ Any ongoing problems (yes/no): _ Yes, NOO on sick leave__ If Yes, is any action required by ExCom: _ n/a
FIN | UNIDO | Investment project for phasing out CFCs at Entreprise nationale des Detergents (ENAD-Lames) | Individual | AFR | ALG | SOL | 17 | INV | 10 | A | I | CFC | 5.6 | 5.6 |  |  | 1995-07-01 | 1996-03-01 | 1996-07-01 |  | 1996-06-01 | 2001-03-01 | 109900 | -606 | 109294 | 109294 | 100% | 0 | 0 |  | 14287 | -101 | 14186 | 0 | 0 | FIN
FIN | Germany | Project preparation in the solvent sector | Individual | AFR | ALG | SOL | 33 | PRP | 48 | A | I |  | 0 |  | 0 |  | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2002-04-01 | 2007-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project completed. Strategy will be included in NPP.
FIN | UNEP | Project preparation for a terminal phase-out management plan | Individual | AFR | ANG | PHA | 51 | PRP | 06 | A | I |  | 0 | 0 | 0 | 0 | 2007-03-01 | 2007-11-01 | 2008-03-01 |  | 2012-03-01 | 2013-12-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 |  | 2340 | 0 | 2340 | 0 | 0
FIN | UNDP | Project preparation for a terminal phase-out management plan in the servicing sector | Individual | AFR | ANG | PHA | 51 | PRP | 07 | A | I | CFC | 0 | 0 | 0 | 0 | 2007-03-01 | 2008-04-01 | 2008-03-01 |  | 2010-12-01 | 2012-12-01 | 12000 | -8195 | 3805 | 3805 | 100% | 0 | 0 | 0 | 900 | -614.63 | 285.375 | -0.005 | 0 | Financially completed in 2012. |  | 2007 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | AFR | ANG | PHA | 55 | PRP | 08 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2011-11-01 | 2013-12-01 | 85000 | -155.28 | 84844.72 | 84845 | 100% | -0.28 | 0 | 0 | 6375 | -11.65 | 6363.375 | -0.025 | 0 | Financially completed in 2013. | Completed in 2011. Only some final payments may need to be settled in 2012, including for holding of a series of customs training workshops to strengthen control capacities at ports of entry. | 2008 |  | Investment
FIN | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | AFR | ANG | PHA | 65 | INV | 10 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-06-01 | 2015-11-01 |  | 2015-12-01 | 2016-12-01 | 86222 | 0 | 86222 | 23758 | 27.55% | 62464 | 62464 | 0 | 7760 | 0 | 2138.2255 | 5621.7745 | 5621.7745 | Financially completed in 2016. | Since 2014, needs for tools and equipment were assessed and TOR completed. Government has approved procurement plan and UNDP is to start bidding in third quarter of 2015. | 2011 |  | Investment
COM | UNDP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | AFR | ANG | PHA | 72 | INV | 12 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 | 2014-11-01 | 2016-05-01 |  | 2016-10-01 |  | 39111 | 0 | 39111 | 39111 | 100% | 0 | 0 | 0 | 3520 | 0 | 3520 | 0 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): All purchase of the equipment was concluded. The equipment was delivered to the Country and will be distributed during last workshops to be performed in 2017. Prodoc signed (actual/planned, yes/no and date):Project document was signed prior to 2015. Missions undertaken (actual/planned):0 of 0 TOR for consultants/subcontracts completed (actual/planned): 0 of 0 Contract/PO/MOA agreements signed: 0 of 0 First disbursement date (actual/planned): Any delays/problems (yes/no):Yes. If Yes, reasons for delay & action plan to resolve:The delivery of part of the equipment had to be delayed due to import complications in the Country. The issue was resolved in 2016 and the equipment successfully entered the country. | - |  |  | Investment
COM | UNDP | Verification report for stage I of HCFC phase-out management plan | Individual | AFR | ANG | PHA | 73 | TAS | 13 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-11-01 | 2015-11-01 | 2016-11-01 |  | 2015-12-01 |  | 30000 | 0 | 30000 | 22476 | 74.92% | 7524 | 0 | 6395.4 | 2700 | 0 | 2022.84 | 677.16 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2015. |  | 2014 |  | Non-Investment
COM | UNDP | HCFC phase-out management plan (stage I, third tranche) | Multi-year | AFR | ANG | PHA | 75 | INV | 16 | N | I | HCFC | 1.6 | 0 | 0 | 0 | 2015-11-01 | 2016-03-01 | 2018-11-01 |  | 2016-11-01 |  | 31111 | 0 | 31111 | 28395 | 91.27% | 2716 | 0 | 2308.6 | 2800 | 0 | 2555.5591 | 244.4409 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): The international consultant performed two two-week missions for trainings in the provinces of Namibe and Luanda. Over 100 people have been trained (local government, professors, technicians). Prodoc signed (actual/planned, yes/no and date):Project document was signed prior to 2015. Missions undertaken (actual/planned):2 0f 2 for training in best practices TOR for consultants/subcontracts completed (actual/planned): 1 of 1 Contract/PO/MOA agreements signed: 0 of 0 First disbursement date (actual/planned): Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | Arrangements with the Ozone Unit for purchase of the past portion of the equipment corresponding to Tranche 4. A three-week mission from the International Consultant for additional trainings for technicians and customs officers is planned for September 2017. | 2015 |  | Investment
ONG | UNDP | Preparation of a HCFC phase-out management plan (stage II) | Individual | AFR | ANG | PHA | 75 | PRP | 17 | N | I | HCFC | 0 | 0 | 0 | 0 | 2015-11-01 | 2016-03-01 | 2016-12-01 | 2017-07-01 |  |  | 60000 | 0 | 60000 | 11574.78 | 19.29% | 48425.22 | 6300 | 19370.088 | 4200 | 0 | 810.2346 | 3389.7654 | 441 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): A consultant was hired for the development of the HPMP Phase II. Information was gathered throughout the year. Prodoc signed (actual/planned, yes/no and date):N/A Missions undertaken (actual/planned):0 of 0 TOR for consultants/subcontracts completed (actual/planned): 1 of 1 Contract/PO/MOA agreements signed: 0 of 0 First disbursement date (actual/planned): Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | Angola Phase 2 HPMP to be submitted on the July meeting. | 2015 |  | Non-Investment
ONG | UNDP | HCFC phase-out management plan (stage I, fourth tranche) | Multi-year | AFR | ANG | PHA | 77 | INV | 18 | N | I | HCFC | 0 | 0 | 0 | 0 | 2016-12-01 |  | 2017-12-01 | 2017-12-01 |  |  | 19556 | 0 | 19556 | 0 | 0% | 19556 | 0 | 7822.4 | 1760 | 0 | 0 | 1760 | 0 | Newly Approved | DoA sent in February 2017. ProDoc signed.Technical specifications of tools were prepared. | 2016 |  | Investment
FIN | Germany | Implementation of the RMP: enforcement of regulations, training of customs officers, training of refrigeration service technicians, recovery and recycling, incentive programme for end-users, and public awareness | RMP Update | AFR | ANG | REF | 39 | TAS | 04 | A | I | CFC | 97.6 | 97.8 | 0 | 0 | 2003-04-01 | 2003-11-01 | 2008-04-01 |  | 2009-12-01 | 2011-12-01 | 700000 | 0 | 700000 | 700000 | 100% | 0 | 0 | 0 | 87000 | 0 | 87000 | 0 | 0 | Additional Training courses in Refrigeration Sector were conducted in Huige and Huambo Provices.- A public awareness campaign has been launched in the provinces of Huila, Moxico, Huambo, Bie and Malange, with the additional aim of formation of interministerial support groups.- Working group of legal experts has been created in order to finalize and submit draft on ODS related legislation and regulations. - Survey has been undertaken in provinces and Luanda in order to identify ODS consuming companies which may qualify for Incentive programme. - R&R centre has been established in Huambo (Central Angola). 1st Customs Training was done in Luanda during January 08, 2nd & 03rd Customs Training in the towns of Namibe and Benguela respectively have been conducted during January /February 09. During Octover 2009 another R&R Centre has been established and inaugurated in Luanda.- Together with National Customs Identification Center for CFCs has been installed at Santa-Clara borderpost (border with Namibia) during November /December 09. During November 09 final training course in good refrigertion pracitses has been conducted in Ondjiva (Southern Angola) - Draft for ODS related legislation and regulation has been handed over to Council of Ministers of Angolan Government during November 2009. According to Angolan NOU approval can be expected for April /May 2010. All funds approved have been spent and project activities were terminated during December 2009, with PCR to be handed over during May/June 2010.
TRF | UNEP | Preparation of country programme | Individual | AFR | ANG | SEV | 32 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 |  | 2002-04-01 |  |  | 2002-04-01 | 60000 | -60000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 7800 | -7800 |  | 0
FIN | Germany | Country programme preparation | Individual | AFR | ANG | SEV | 34 | CPG | 02 | A | I |  | 0 |  | 0 |  | 2001-07-01 | 2001-08-01 | 2002-08-01 |  | 2002-08-01 | 2002-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | National consultants contracted, survey on ODS consump finalized, Country Programme prepared and submitted together with prop. for I.S. Angola. Aproved at 38th ExCom. (1st instalment of 1st tranche of IS funding of 81000) Request for 2nd instalment of IS
FIN | Germany | Establishment of the Ozone Unit | Individual | AFR | ANG | SEV | 38 | INS | 03 | N | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-04-01 | 2005-12-01 |  | 2006-12-01 | 2007-06-01 | 71682 | 141618 | 213300 | 213300 | 100% | 0 | 0 | 0 | 9319 | 18411 | 27730 | 0 | 0 | 1st phase of Institutional Strengthening project is completed. - the infrastructure of the NOU-office in Luanda has been completed, with internet and telepone / fax connection. - Regional support groups have been created in serveral of Angolas provinces in order to assist NOU in data collection, public awareness activities, etc.- ODS data up to reporting year 2006 have been submitted to both Ozone Secretariat and Multilateral Fund Secretariat. - Angola is in compliance with phase-out schedule and data reporting obligations.
FIN | Germany | Extension of the institutional strengthening project (phase II) | Individual | AFR | ANG | SEV | 50 | INS | 05 | N | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2008-11-01 |  | 2009-01-01 | 2011-01-01 | 134400 | 0 | 134400 | 134400 | 100% | 0 | 0 | 0 | 17472 | 0 | 17472 | 0 | 0 | NOU moved into the building of the Ministry (Urbanism & Environment). NOU collected and reported data for 2006, preparations for reporting of ODS data for 2007 has started. - After General elections in Angola restructuring of Government took place. Angolan NOU is now part of newly created Ministry of Environment. According to NOU ODS data for 2007 and 2008 have been reported to Ozone Secretariat and MFsecretariat. - All approved funds have been spent, with final payment done in January 2009. All project acitvities were completed in December 2008.
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | AFR | ANG | SEV | 63 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-09-01 | 2013-03-01 |  | 2013-01-01 | 2013-07-01 | 134400 | 0 | 134400 | 134400 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of the institutional strengthening project (phase IV: 4/2013-3/2015) | Individual | AFR | ANG | SEV | 69 | INS | 11 | A | I |  | 0 |  | 0 |  | 2013-04-01 | 2013-11-01 | 2015-03-01 |  | 2016-12-01 |  | 134400 | 0 | 134400 | 96723.27 | 71.97% | 37676.73 | 27078.47 | 37677 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The licensing and quota systems are in place and functioning. The NOU conducted a seminar on quota allocations in February, 2016, in Luanda, attended by 30 participants, to coordinate, analyze and allocate annual quotas. The NOU organized 4 custom enforcement workshops between January and June 2016, attended by 60 officers, and updated ODS alternatives on new customs tariff and illegal trade. The NOU conducted 3 monitoring visits on illegal trade. The NOU submitted 2015 Country Programme and Article 7 Data reports in June 2016. The NOU submitted IS Phase V Renewal Request to ExCom 74 which was approved. Legal arrangements(actual/planned): The SSFA was signed between the country and UNEP in July 2013____Initial stages of project implementation(actual/planned): __Yes_ Intermediate goals achieved (actual/planned): _Yes__ Project completion and follow up: _Yes__ First disbursement date (actual/planned): November 2013___ All funds disbursed (yes/no): _Yes__ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: __N/A_ | Project completed
ONG | UNEP | Extension of the institutional strengthening project (phase V: 7/2015-6/2017) | Individual | AFR | ANG | SEV | 74 | INS | 14 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-02-01 | 2017-03-01 | 2018-03-01 |  |  | 134400 | 0 | 134400 | 37731.74 | 28.07% | 96668.26 | 96668.26 | 9666.826 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The licensing and quota systems are in place and functioning. The NOU conducted a steering committee meeting, participated by 16 members, to monitor, and coordinate the operations and activities of the NOU. The NOU organized two RAC training workshops and two custom training workshops, and 65 technicians and 30 custom officers were trained respectively. The NOU conducted public awareness, attended by 60 participants, and distributed awareness materials. The NOU submitted 2015 Country Programme and Article 7 Data reports in June 2016. The NOU celebrated 2016 International Ozone Day, participated by more than 300 participants and conducted several awareness activities resulting in broad support for national Montreal Protocol policies and programmes. The NOU participated in all Montreal Protocol meetings organized in 2016, including Africa Joint Network meeting, 17 – 22 March 2016, Victoria Falls, Zimbabwe; 37th OEWG meeting, 4-8 April 2016, Geneva, Switzerland; 28 MOP Meeting, 10-14 October 2016, Kigali, Rwanda. Legal arrangements (actual/planned):The SSFA was drafted and signed by UNEP and the Government of Angola in March 2016. Initial stages of project implementation(actual/planned): __Yes_ Intermediate goals achieved (actual/planned): _Yes__ Project completion and follow up: _No__ First disbursement date (actual/planned): Feb 2016___ All funds disbursed (yes/no): _No__ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: __N/A_ | Brief progress report (actual/planned): The NOU continues to monitor imports and trade of ODS and ODS related equipment. Collection of the 2016 data on ODS imports and consumption has been completed and is being analyzed for submission. NOU commenced preparation of national legislative requirement processes in planning for ratification of Kigali amendment.
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | AFR | ANG | SEV | 74 | TAS | 15 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-05-01 | 2016-05-01 | 2017-05-01 |  |  | 70000 | 0 | 70000 | 5050 | 7.214% | 64950 | 64950 | 6495 | 9100 | 0 | 656.5 | 8443.5 | 8443.5 | Brief progress report (actual/planned): The first stakeholders meeting was organized by the NOU in June 2016 in Luanda and 40 participants from the ODS Alternative user sectors and importers attended. The main goal of the meeting was to sensitize the government and industry on the survey and agree on the plan for the Survey of ODS alternatives at the national level and obtain support of main national stakeholders. One National Consultant was hired in March 2016 by the NOU to support the data collection. The National Consultant assisted the NOU in the identification of the current use of ODS alternatives by substance/sector and collection of import/export data for the substances for the past a couple of years. The National Consultant also provided support in establishing growth patterns in use by substance/sector and in compiling data on available ODS alternatives for various applications.The NOU and the National Consultant drafted and cross checked the information to ensure the completion of end-user surveys, collection, analysis, and aggregation of consumption data. The various sections of the report were drafted. The second stakeholders meeting was organized by the NOU in September 2016 in Luanda with the main goal to organise consultations with representatives of the government and private sector to finalize the outcomes of the Survey of ODS alternatives and discuss potential opportunities for introduction of those alternatives in the country. A total of 40 participants were in attendance. The draft report was prepared by the NOU and the National Consultant. It was reviewed and finalized based on the format approved by ExCom decision 75/67 as contained in document UNEP/OzL.Pro/ExCom/75/77/Rev.1 after incorporating inputs/ comments raised during National Stakeholders’ workshop. The final report was submitted to UNEP in November 2016 for final review and submission to MLFS. The NOU participated in the ODS Alternative Thematic workshop held in December 2016 to refine the draft report according to the revised template for the report. The report has been finally submitted to UNEP. Legal arrangements(actual/planned): The SSFA was drafted and signed by UNEP and the Government of Angola in March 2016___ Initial stages of project implementation(actual/planned): _Yes__ Intermediate goals achieved (actual/planned): Yes___ Project completion and follow up: _Yes__ First disbursement date (actual/planned): _May 2016__ All funds disbursed (yes/no): Yes___ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): __N/A_ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): The NOU incorporated comments from UNEP ROA and Paris and re-submitted final ODS survey report.
FIN | IBRD | Preparation of a national CFC phase-out plan |  | LAC | ANT | PHA | 39 | PRP | 08 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2004-09-01 | 2004-09-01 |  | 2004-09-01 | 2004-09-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1125 | 0 | 1125 | 0 | 0 | Project prepared, submitted and then approved at the 44th ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | CFC phase-out management plan | Multiyear | LAC | ANT | PHA | 44 | INV | 10 | N | D | CFC | 2 | 3 | 0 | 0 | 2004-12-01 | 2012-05-01 | 2006-12-01 |  | 2011-12-01 | 2012-05-01 | 69400 | -6413 | 62987 | 62987 | 100% | 0 | 0 |  | 6246 | -577 | 5668.83 | 0.17 | 0.17 | Project operationally completed (Dec. 11) and financially closed (May 12). |  |  |  | INV | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | ANT | PHA | 55 | PRP | 12 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2010-08-01 | 2009-07-01 |  | 2013-03-01 | 2014-12-01 | 85000 | -8216 | 76784 | 76784 | 100% | 0 | 0 |  | 11050 | -1068.08 | 9981.92 | 0 | 0
FIN | IBRD | CFC phase-out management plan (second tranche) | Multiyear | LAC | ANT | PHA | 61 | INV | 13 | N | D |  | 0 | 0 | 0 | 0 | 2010-07-01 |  | 2011-12-31 |  | 2011-12-01 | 2012-05-01 | 27900 | -27900 | 0 | 0 | #DIV/0! | 0 | 0 |  | 2511 | -2511 | 0 | 0 | 0 | Project operationally completed (link to ANT/PHA/61/INV/13) Dec. 11 and financially closed May 12. |  |  |  | INV | 0
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | LAC | ANT | PHA | 66 | TAS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 | 2012-11-01 | 2015-04-01 | 2017-12-01 |  |  | 45850 | 0 | 45850 | 27235 | 59.4% | 18615 | 0 | 1861.5 | 5961 | 0 | 3540.847 | 2420.153 | 0 | Brief progress report (actual/planned): ___Mission to follow up on approval of Ministerial Order took place in Sep-16. Ministerial Order approved by Cabinet in Nov-16. Legal arrangements (actual/planned): Nov-13/Dec-12___ First mission (actual/planned): _Mar-16/Sep-16__ TOR completed (actual/planned): ___ First disbursement date (actual/planned): Nov-13/Dec-12___ All funds disbursed (yes/no): No___ Any delay? (yes/no): yes___ If Yes, reasons for delay & action plan to resolve: outstanding financial and progress reports to reprogramme funding; SSFA expired. During mission in Sep-16 NOU was requested to send outstanding reports. New SSFA to be discussed with country in 1Q of 2017 ___ If Yes, will delay have impact on project completion date (yes/no): yes. ___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): ___follow-up on outstanding progress and financial report in Feb-17. Updating of tranche request document undergoing. Legal arrangements (actual/planned): planned for 2Q of 2017 once reports are submitted and funds reprogrammed___ First mission (actual/planned): _Planned Aug-17__ TOR completed (actual/planned): ___ First disbursement date (actual/planned): Nov-13___ All funds disbursed (yes/no): No___ Any delay? (yes/no): yes___ If Yes, reasons for delay & action plan to resolve: outstanding financial and progress reports to reprogramme funding; SSFA expired. Follow-up on outstanding reports. New SSFA to be discussed with country in 2Q of 2017 ___ If Yes, will delay have impact on project completion date (yes/no): yes. The planned completion date has been revised to Dec-17 in order to accomodate reprogramming of funds, signature of SSFA and 100% disbursement of tranche 1. ___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___ |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor the signing of the endorsement letter from the Ministry.
ONG | UNEP | Preparation of a HCFC phase-out management plan (stage II) | Individual | LAC | ANT | PHA | 73 | PRP | 17 | A | I |  | 0 |  | 0 |  | 2014-11-01 | 2015-03-01 | 2015-11-01 | 2017-12-01 |  |  | 20000 | 0 | 20000 | 19812.2 | 99.06% | 187.8 | 0 | 18.78 | 2600 | 0 | 2575.586 | 24.414 | 0 | Brief progress report (actual/planned): Submission of second stage proposal subject to approval of Ministerial Order. Ministerial Order approved by Cabinet in Nov-16 ___. Legal arrangements (actual/planned):___ First mission (actual/planned): Mar-2016/Sep-2016 ___ TOR completed (actual/planned): Feb-2015/Mar-2015___ First disbursement date (actual/planned): Mar-2015/Mar-2015 ___ All funds disbursed (yes/no): yes___ Any delay? (yes/no): yes___ If Yes, reasons for delay & action plan to resolve: Approval of Ministerial Order formalizing the quota system was necessary condition of submission of Stage II proposal. Mission in Sep-16 to follow-up on approval of Ministerial Order. ___ If Yes, will delay have impact on project completion date (yes/no): yes___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): Updating of second stage proposal sby NOU as of Mar-17. Proposal planned to be submitted to last ExCom of 2017. ___. Legal arrangements (actual/planned):___ First mission (actual/planned): Mar-2016/Sep-2016 ___ TOR completed (actual/planned): Feb-2015/Mar-2015___ First disbursement date (actual/planned): Mar-2015/Mar-2015 ___ All funds disbursed (yes/no): yes___ Any delay? (yes/no): yes___ If Yes, reasons for delay & action plan to resolve: Approval of Ministerial Order formalizing the quota system was necessary condition of submission of Stage II proposal. ___ If Yes, will delay have impact on project completion date (yes/no): yes. Completion date revised to Dec-17 in order to accomodate submission of Stage II for the last ExCom in 2017.___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___
FIN | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | Individual | LAC | ANT | PHA | 73 | PRP | 18 | A | I |  | 0 | 0 |  |  | 2014-11-01 | 2014-12-01 | 2015-11-30 |  | 2015-09-01 | 2015-09-01 | 10000 | 0 | 10000 | 10000.1 | 100% | -0.1 | 0 |  | 700 | 0 | 700 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNEP | Assistance for formulation refrigeration management plan | RMP | LAC | ANT | REF | 21 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1998-03-01 |  | 1998-09-01 | 1999-04-01 | 30000 | -5000 | 25000 | 25000 | 100% | 0 | 0 |  | 3900 | -650 | 3250 | 0 | 0
FIN | Canada | Implementation of the RMP: national recovery and recycling | RMP | LAC | ANT | REF | 26 | TAS | 06 | A | I | CFC | 1 |  | 0 |  | 1998-11-01 | 2000-06-01 | 2000-11-01 |  | 2001-11-01 | 2001-12-01 | 34000 | 0 | 34000 | 34000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project Completed. PCR submitted. |  | 1998 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: training of customs | RMP | LAC | ANT | REF | 26 | TRA | 04 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-04-01 | 2000-11-01 |  | 2002-10-01 | 2002-12-01 | 42940 | 0 | 42940 | 42940 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project Complete. PCR submitted. |  | 1998 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: training the trainers in good refrigerant management practices | RMP | LAC | ANT | REF | 26 | TRA | 05 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-04-01 | 2000-11-01 |  | 2001-11-01 | 2001-12-01 | 47460 | 0 | 47460 | 47460 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project Completed PCR submitted. |  | 1998 |  | Non-Inv.
FIN | UNEP | Country programme preparation | Individual | LAC | ANT | SEV | 11 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1994-11-01 |  | 1998-09-01 | 1999-06-01 | 30000 | -969 | 29031 | 29031 | 100% | 0 | 0 |  | 3900 | -125.97 | 3774.03 | 0 | 0
FIN | UNEP | Establishment of an Ozone Protection Unit | Individual | LAC | ANT | SEV | 26 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-09-01 | 2001-12-01 |  | 2002-12-01 | 2004-10-01 | 36000 | 0 | 36000 | 36000 | 100% | 0 | 0 |  | 4680 | 0 | 4680 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project | Individual | LAC | ANT | SEV | 38 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2004-01-01 | 2004-12-01 |  | 2005-06-01 | 2009-06-01 | 31200 | -13 | 31187 | 31187 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | LAC | ANT | SEV | 44 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2006-10-01 | 2006-12-01 |  | 2012-12-01 | 2013-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of institutional strengthening project (phase IV: 1/2013-12/2014) | Individual | LAC | ANT | SEV | 68 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-09-01 | 2014-12-01 | 2017-12-01 |  |  | 60000 | 0 | 60000 | 30000 | 50% | 30000 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Mission in Sep-16 to discuss progress on legislation related to QS and outstanding reports on projects. Despite commitments from mission, country has not sent outstanding reports as of Dec-16. Country reported Art.7 data on time. NOO attended the Caribbean thematic meeting in ODS Alternatives Surveys in Barbados in Dec-2016. Celebration of International Ozone Day ___Legal arrangements (actual/planned): Nov-13/Jul-13___Initial stages of project implementation (actual/planned): NOU has been focused on approval of Ministerial Order by Cabinet to formalize QS throughout 2016 ___ Intermediate goals achieved (actual/planned): Policy instrument approved in Nov-16. 2015 CP data reporting and Art.7 Data reporting. Celebration of the Ozone day. Participation in Caribbean network meeting ___ Project completion and follow up: ___ First disbursement date (actual/planned): Nov-13/Jul-13.___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): yes___ If Yes, reasons for delay & action plan to resolve: pending submission of financial and progress report to process last disbursement. Periodic folllow-up and a mission undertaken in Sep-16 ___ If Yes, will delay have impact on project completion date (yes/no): yes. The completion date has been revised to accomodate submission of financial report and processing of last disbursement.___ Any ongoing problems (yes/no): no ___ If Yes, is any action required by ExCom: | Brief progress report (actual/planned): Country to submit outstanding report in 1Q of 2017 to process last disbursement. 2015 CP Data report is pending clicking on 'submission', NOU informed to submit in Feb-17__ Legal arrangements (actual/planned): Nov-13/Jul-13 ___Initial stages of project implementation (actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): Sep-13/Jul-13.___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): yes___ If Yes, reasons for delay & action plan to resolve: SSFA expired and pending submission of financial and progress report. Periodic follow up and a mission planned for 3Q of 2017 ___ If Yes, will delay have impact on project completion date (yes/no): yes. The completion date has been revised to accomodate submission of financial report and processing of last disbursement.___ Any ongoing problems (yes/no): no ___ If Yes, is any action required by ExCom: |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor project implementation progress and the disbursement rate of approved funds.
ONG | UNEP | Extension of institutional strengthening project (phase V: 1/2015-12/2016) | Individual | LAC | ANT | SEV | 73 | INS | 16 | A | I |  | 0 |  | 0 |  | 2014-11-01 |  | 2016-12-01 | 2018-12-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 60000 | 6000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): First disbursement subject to submission of financial report of the previous phase. Activities are undergoing with balance of previous phase and funding from Government ___Legal arrangements (actual/planned): Apr-15/Mar-15___Initial stages of project implementation (actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): Pending/Apr-15.___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): yes___ If Yes, reasons for delay & action plan to resolve: pending submission of financial report of previous phase to process first disbursement. Mission to country in Sep16 to follow-up on outstanding reports. As of Dec-16 NOU has not submitted financial report to release first disbursement ___ If Yes, will delay have impact on project completion date (yes/no): yes ___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: | Brief progress report (actual/planned): Activities are undergoing with funding from Government. Country to click on 'submit' the online 2015 CP data report. Follow-up on oustanding reports. Amendnment of SSFA to be prepared in Mar-17 to extend duration of SSFA___. Legal arrangements (actual/planned): Apr-15/Mar-15 ___Initial stages of project implementation (actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): Pending/Apr-2015.___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): yes___ If Yes, reasons for delay & action plan to resolve: pending submission of financial report of previous phase to process first disbursement. Periodic follow-up on outstanding reports with NOU. ___ If Yes, will delay have impact on project completion date (yes/no): yes. Completion date revised to Dec-2018 to accomodate for amendment of the SSFA and re-starting of activities under current phase.___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor project implementation progress and the disbursement rate of approved funds.
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | LAC | ANT | SEV | 74 | TAS | 19 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-10-01 | 2016-05-01 | 2017-06-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 35000 | 4000 | 5200 | 0 | 0 | 5200 | 4550 | Brief progress report (actual/planned): SSFA signed by UNEP in Apr-2016, and in Sep-16 by country. Regional Consultant selected and contract signed in Jul-16. National consultants hired in Nov-16 and assisting with collection of information ___. Legal arrangements (actual/planned): Sep-16/Dec-15 ___ First mission (actual/planned):Dec-16/Mar-16 ___ TOR completed (actual/planned): May-16/Feb-2016___ First disbursement date (actual/planned): Oct-16/Dec-15 ___ All funds disbursed (yes/no): No___ Any delay? (yes/no): no___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no):___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): National consultants to complete collection of information in 1Q 2017. Completion date revised to Jul-17 in order to allow submision of national data and finalization of the report ___. Legal arrangements (actual/planned): Sep-16/Dec-15 ___ First mission (actual/planned):Dec-16/Mar-16 ___ TOR completed (actual/planned): May-16/Feb-16___ First disbursement date (actual/planned): Oct-16/Dec-15 ___ All funds disbursed (yes/no): No___ Any delay? (yes/no): no___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no):___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___
FIN | IBRD | Conversion from CFC-11, CFC-12, CFC-113 and MCF into HCFC for technical aerosols at Electroquimica Delta | Individual | LAC | ARG | ARS | 36 | INV | 128 | N | I | CFC | 60 | 60 | 0 | 0 | 2002-03-01 | 2004-08-01 | 2005-04-01 |  | 2004-12-01 | 2006-07-01 | 264000 | 0 | 264000 | 264000 | 100% | 0 | 0 |  | 34320 | 0 | 34320 | 0 | 0 | Project physically and financially completed. |  |  |  | INV | 0
FIN | IBRD | Conversion from CFC-11, CFC-12, CFC-113 and MCF into HCFC for technical aerosols at Servex S.R.L. | Individual | LAC | ARG | ARS | 38 | INV | 131 | N | I | CFC | 36.4 | 36.4 | 0 | 0 | 2002-11-01 | 2004-08-01 | 2005-11-01 |  | 2005-02-01 | 2006-07-01 | 160160 | 0 | 160160 | 160160 | 100% | 0 | 0 |  | 20820.8 | 0 | 20820.8 | 0 | 0 | Project physically and financially completed. |  |  |  | INV | 0
CLO | IBRD | Preparation of one investment project in the aerosol filling industry |  | LAC | ARG | ARS | 39 | PRP | 135 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 |  | 2003-12-01 |  |  | 2005-11-01 | 10000 | -10000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 750 | -750 | 0 | 0 | 0 | Funds returned to the 47th ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of MDI phase-out plan |  | LAC | ARG | ARS | 45 | PRP | 142 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2008-12-01 | 2005-12-01 |  | 2008-12-01 | 2008-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 3750 | 0 | 3750 | 0 | 0 | With World Bank assistance an Argentinian Strategy for MDIs was prepared, presented to and approved at the 56th ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | Phase-out of CFC consumption in the manufacture of aerosol MDIs | Individual | LAC | ARG | ARS | 56 | INV | 159 | N | I | CFC | 118.4 | 118.4 | 0 | 0 | 2008-11-01 | 2009-12-01 | 2012-01-31 |  | 2014-12-01 | 2015-11-01 | 2806874 | -74889 | 2731985 | 2731985 | 100% | 0 | 0 |  | 210516 | -5616.69 | 204899.31 | 0 | 0 | Project completed. |  |  | 2014-12-01 | INV | 0
FIN | UNIDO | Preparatory assistance for phase out of ODS in the foam production at BANDEX, CELPACK & PRENSIPLANT | Individual | LAC | ARG | FOA | 11 | PRP | 05 | A | I |  | 0 | 0 |  |  | 1993-11-01 | 1994-03-01 | 1994-11-01 |  | 1995-12-01 | 1998-08-01 | 35000 | 8990 | 43990 | 43990 | 100% | 0 | 0 |  | 4550 | 1169 | 5719 | 0 | 0 | FIN
FIN | UNIDO | Investment project for phasing out of ODS at Bandex S.A. | Individual | LAC | ARG | FOA | 13 | INV | 09 | A | I | CFC | 214 | 214 |  |  | 1994-07-01 | 1995-01-01 | 1995-07-01 |  | 1995-11-01 | 1998-08-01 | 517630 | -555 | 517075 | 517075 | 100% | 0 | 0 |  | 67292 | -179 | 67113 | 0 | 0 | FIN
FIN | UNIDO | Phase out of ODS at CELPACK S.A. | Individual | LAC | ARG | FOA | 13 | INV | 10 | A | I | CFC | 135 | 135 |  |  | 1994-07-01 | 1994-12-01 | 1995-07-01 |  | 1995-12-01 | 1998-08-01 | 503094 | 377 | 503471 | 503471 | 100% | 0 | 0 |  | 65402 | 49 | 65451 | 0 | 0 | FIN
FIN | UNDP | Conversion to non-CFC technology in the manufacture of flexible and integral skin polyurethane foam at Prensiplast | Individual | LAC | ARG | FOA | 14 | INV | 13 | A | I | CFC | 30 | 30 | 0 | 0 | 1994-09-01 | 1995-12-01 | 1995-09-01 |  | 1999-11-01 | 2001-12-01 | 345000 | -5021 | 339979 | 339979 | 100% | 0 | 0 | 0 | 44850 | -653.13 | 44196.87 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1994 | 1999-07-01 | Investment
FIN | UNDP | Elimination of the use of CFC in the manufacture of sandwich polyurethane panels at Cinter, S.R.L. | Individual | LAC | ARG | FOA | 15 | INV | 14 | A | I | CFC | 45 | 45 | 0 | 0 | 1994-12-01 | 1995-12-01 | 1995-12-01 |  | 2001-12-01 | 2003-09-01 | 725000 | -32679 | 692321 | 692321 | 100% | 0 | 0 | 0 | 94250 | -4248.26 | 90001.74 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1994 | 1997-12-01 | Investment
FIN | UNDP | Conversion to non-CFC technology in the manufacture of flexible foam (slabstock) at Belmo Buenos Aires and Belmo San Luis | Individual | LAC | ARG | FOA | 18 | INV | 26 | A | I | CFC | 145 | 145 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 1998-12-01 | 2001-08-01 | 715000 | -10 | 714990 | 714990 | 100% | 0 | 0 | 0 | 92950 | -1.3 | 92948.7 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1995 |  | Investment
FIN | UNDP | Conversion to non-CFC technology in the manufacture of flexible foam (slabstock) at Nuvel Corp. S.A. | Individual | LAC | ARG | FOA | 18 | INV | 27 | A | I | CFC | 53 | 53 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 2002-11-01 | 2004-01-01 | 313500 | 0 | 313500 | 313500 | 100% | 0 | 0 | 0 | 40755 | 0 | 40755 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 1995 | 1999-06-01 | Investment
FIN | UNDP | Conversion to non-CFC technology in the manufacture of flexible foam (slabstock) at Mentvil S.A. | Individual | LAC | ARG | FOA | 18 | INV | 28 | A | I | CFC | 18.5 | 18.5 | 0 | 0 | 1995-11-01 | 1996-12-01 | 1996-11-01 |  | 1997-04-01 | 2001-12-01 | 115000 | -12796 | 102204 | 102204 | 100% | 0 | 0 | 0 | 14950 | -1663.13 | 13286.87 | 0 | 0 | Completed in 1997. Financially completed in 2001. |  | 1995 |  | Investment
FIN | UNDP | Conversion to non-CFC technology in the manufacture of flexible foam (slabstock) at Limansky | Individual | LAC | ARG | FOA | 18 | INV | 29 | A | I | CFC | 95 | 95 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 1998-12-01 | 2000-12-01 | 473000 | -364 | 472636 | 472636 | 100% | 0 | 0 | 0 | 61490 | -47.32 | 61442.68 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Conversion to non-CFC technology in the manufacture of flexible foam (slabstock) at Piero SAIC | Individual | LAC | ARG | FOA | 18 | INV | 30 | A | I | CFC | 64 | 64 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 2002-11-01 | 2004-01-01 | 341000 | -1708 | 339292 | 339292 | 100% | 0 | 0 | 0 | 44330 | -222.04 | 44107.96 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 1995 | 1999-06-01 | Investment
FIN | UNDP | Conversion to non CFC technology in the manufacture of flexible foam (slabstock) at Sueño Estelar S.A. and Estelar San Luis S.A. | Individual | LAC | ARG | FOA | 18 | INV | 31 | A | I | CFC | 128.6 | 128.6 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 1998-12-01 | 2000-12-01 | 690000 | -2837 | 687163 | 687163 | 100% | 0 | 0 | 0 | 89700 | -368.81 | 89331.19 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Elimination of the use of CFC's in the manufacture of sandwich panels and spray foams at Montisol Argentina S.A. and Art Nouveau Puntana, S.A. | Individual | LAC | ARG | FOA | 18 | INV | 33 | A | I | CFC | 36.5 | 36.5 | 0 | 0 | 1995-11-01 | 1997-07-01 | 1996-11-01 |  | 2001-12-01 | 2003-04-01 | 285000 | -631 | 284369 | 284369 | 100% | 0 | 0 | 0 | 37050 | -82.03 | 36967.97 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1995 | 1998-01-01 | Investment
FIN | UNIDO | Preparation of an investment project in the foam sector | Individual | LAC | ARG | FOA | 18 | PRP | 32 | A | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-02-01 | 1996-01-01 |  | 1996-12-01 | 1998-08-01 | 20000 | -492 | 19508 | 19508 | 100% | 0 | 0 |  | 2600 | -68 | 2532 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-12 at Mallol Saic | Individual | LAC | ARG | FOA | 20 | INV | 47 | A | I | CFC | 36.5 | 36.5 |  |  | 1996-10-01 | 1997-02-01 | 1998-04-01 |  | 2003-12-01 | 2004-03-01 | 299344 | 0 | 299344 | 299343.73 | 100% | 0.27 | 0 |  | 38915 | -53 | 38862 | 0 | 0 | FIN |  |  | 2000-06-01
FIN | UNDP | Conversion to non-CFC technology in the manufacture of flexible foam (slabstocks) at Suavestar S.A. | Individual | LAC | ARG | FOA | 20 | INV | 48 | A | I | CFC | 92.5 | 92.5 | 0 | 0 | 1996-10-01 | 1997-03-01 | 1998-09-01 |  | 2002-11-01 | 2004-01-01 | 561000 | 0 | 561000 | 561000 | 100% | 0 | 0 | 0 | 72930 | 0 | 72930 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 1996 | 1998-01-01 | Investment
FIN | UNIDO | Phasing out of CFC-12 at Multiespuma Saic | Individual | LAC | ARG | FOA | 20 | INV | 49 | A | I | CFC | 60 | 60 |  |  | 1996-10-01 | 1997-02-01 | 1998-04-01 |  | 2000-12-01 | 2001-11-01 | 282438 | -11981 | 270457 | 270457.47 | 100% | -0.47 | 0 |  | 36717 | -1613 | 35104 | 0 | 0 | FIN |  |  | 2000-06-01
FIN | UNDP | Project preparation in the foam sector | Individual | LAC | ARG | FOA | 21 | PRP | 50 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2000-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Eliminations of the use of CFCs in the manufacture of sandwich polyurethane panels and spray foams at Rheem S.A. | Individual | LAC | ARG | FOA | 22 | INV | 55 | A | I | CFC | 12 | 12 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1998-12-01 | 2001-12-01 | 76650 | 0 | 76650 | 76650 | 100% | 0 | 0 | 0 | 9964.5 | 0 | 9964.5 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to non CFC technology in the manufacture of flexible foam (slabstocks) at FPV S.A. | Individual | LAC | ARG | FOA | 22 | INV | 56 | A | I | CFC | 19 | 19 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 2000-05-01 | 2004-01-01 | 118000 | -34528 | 83472 | 83472 | 100% | 0 | 0 | 0 | 15340 | -4489 | 10851 | 0 | 0 | Completed in 2000. Financially completed in 2004. |  | 1997 |  | Investment
FIN | UNDP | Elimination of the use of CFCs in the manufacture of sandwich polyurethane panels and spray foams at Calofrig Asilaciones Jacobi S.A.I.C. | Individual | LAC | ARG | FOA | 22 | INV | 57 | A | I | CFC | 72 | 72 | 0 | 0 | 1997-05-01 | 1998-06-01 | 1999-06-01 |  | 2001-12-01 | 2003-04-01 | 563750 | 0 | 563750 | 563750 | 100% | 0 | 0 | 0 | 73287.5 | 0 | 73287.5 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Elimination of the use of CFCs in the manufacture of sandwich polyurethane panels and spray foams at Bonano | Individual | LAC | ARG | FOA | 23 | INV | 61 | A | I | CFC | 72 | 72 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1999-12-01 |  | 2001-12-01 | 2003-04-01 | 456500 | 0 | 456500 | 456500 | 100% | 0 | 0 | 0 | 59345 | 0 | 59345 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1997 |  | Investment
CLO | UNDP | Conversion to non CFC technology in the manufacture of integral skin and flexible moulded foam at Strapur | Individual | LAC | ARG | FOA | 23 | INV | 62 | A | I | CFC | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  |  | 2001-08-01 | 212500 | -162380 | 50120 | 50120 | 100% | 0 | 0 | 0 | 27625 | -21109.4 | 6515.6 | 0 | 0 | Canceled in 2001. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to non CFC technology in the manufacture of moulded foam at Cifor S.A. | Individual | LAC | ARG | FOA | 23 | INV | 63 | A | I | CFC | 8.2 | 8.2 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 2000-03-01 | 2001-12-01 | 132000 | -9838 | 122162 | 122162 | 100% | 0 | 0 | 0 | 17160 | -1279 | 15881 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1997 |  | Investment
CLO | UNDP | Elimination of the use of CFCs in the manufacture of rigid foam blocks for insulated trailers at Fruehauf | Individual | LAC | ARG | FOA | 23 | INV | 65 | A | I | CFC | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  |  | 2003-11-01 | 175000 | -40597 | 134403 | 134403 | 100% | 0 | 0 | 0 | 22750 | -5277.61 | 17472.39 | 0 | 0 | Canceled in 2002. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | LAC | ARG | FOA | 24 | PRP | 74 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1998 |  | Investment
FIN | UNDP | Conversion to low index additive technology in the manufacture of flexible boxfoam at Rozen S.R.L. | Individual | LAC | ARG | FOA | 25 | INV | 76 | A | I | CFC | 19.6 | 19.6 | 0 | 0 | 1998-07-01 | 2000-08-01 | 2000-08-01 |  | 2002-11-01 | 2004-01-01 | 122100 | 0 | 122100 | 122100 | 100% | 0 | 0 | 0 | 15873 | 0 | 15873 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam (spray) at Comenco | Individual | LAC | ARG | FOA | 26 | INV | 78 | A | I | CFC | 31.2 | 31.2 | 0 | 0 | 1998-11-01 | 1999-08-01 | 2000-12-01 |  | 2000-08-01 | 2001-12-01 | 210150 | -3022 | 207128 | 207128 | 100% | 0 | 0 | 0 | 27319.5 | -393 | 26926.5 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
FIN | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam in panels for thermal insulation at Arneg Raffo | Individual | LAC | ARG | FOA | 27 | INV | 81 | N | I | CFC | 67 | 67 | 0 | 0 | 1999-03-01 | 2001-02-20 | 2001-04-01 |  | 2002-07-01 | 2004-03-01 | 177960 | 0 | 177960 | 177960 | 100% | 0 | 0 |  | 23134.8 | 0 | 23134.8 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | UNDP | Preparation of two projects in the integral skin foam subsector | Individual | LAC | ARG | FOA | 27 | PRP | 83 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNIDO | Project preparation in the foam sector (general) | Individual | LAC | ARG | FOA | 27 | PRP | 84 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-06-01 | 1999-12-01 |  | 2000-09-01 | 2002-05-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 | FIN
FIN | UNDP | Preparation of an umbrella project and three other projects in the rigid foam subsector | Individual | LAC | ARG | FOA | 27 | PRP | 87 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2002-03-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNIDO | Phasing out CFC-11 by conversion to HCFC-141B as a blowing agent in the manufacture of P.U. blocks and tank spraying at Polwer S.R.L. | Individual | LAC | ARG | FOA | 28 | INV | 110 | A | I | CFC | 26.8 | 26.8 |  |  | 1999-07-01 | 1999-11-01 | 2001-02-01 |  | 2001-06-01 | 2002-11-01 | 111641 | -69 | 111572 | 111571.66 | 100% | 0.34 | 0 |  | 14513 | -32 | 14481 | 0 | 0 | FIN
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam (spray) at OSIR (Organización de Servicios Integrales Rosario) | Individual | LAC | ARG | FOA | 29 | INV | 94 | A | I | CFC | 17.8 | 17.8 | 0 | 0 | 1999-11-01 | 2000-08-01 | 2002-12-01 |  | 2001-12-01 | 2003-04-01 | 127392 | 0 | 127392 | 127392 | 100% | 0 | 0 | 0 | 16560.96 | 0 | 16560.96 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam (spray) at Obras de Ingenieria | Individual | LAC | ARG | FOA | 29 | INV | 95 | A | I | CFC | 16.5 | 16.5 | 0 | 0 | 1999-11-01 | 2000-08-01 | 2002-12-01 |  | 2000-12-01 | 2003-04-01 | 124025 | -221 | 123804 | 123804 | 100% | 0 | 0 | 0 | 16123.25 | -28.73 | 16094.52 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam (spray and boxfoam) at Mendoza de Poliuretanos | Individual | LAC | ARG | FOA | 29 | INV | 96 | A | I | CFC | 43.9 | 43.9 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2002-11-01 | 2004-01-01 | 234409 | 0 | 234409 | 234409 | 100% | 0 | 0 | 0 | 30473.17 | 0 | 30473.17 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b as a blowing agent in the manufacture of rigid P.U. foams: umbrella project (Tarco, Mondino, Schaum, Fadep, Occhipinti and Friolatina) | Individual | LAC | ARG | FOA | 29 | INV | 97 | A | I | CFC | 30.4 | 30.4 |  |  | 1999-11-01 | 2000-01-01 | 2001-06-01 |  | 2001-06-01 | 2002-09-01 | 227048 | 0 | 227048 | 227048.01 | 100% | -0.01 | 0 |  | 29516 | -7 | 29509 | 0 | 0 | FIN
FIN | UNDP | Conversion from CFC-11 to methylene chloride/LIA technology in the manufacture of flexible polyurethane boxfoam at Fasax | Individual | LAC | ARG | FOA | 30 | INV | 106 | A | I | CFC | 50 | 50 | 0 | 0 | 2000-03-01 | 2000-12-01 | 2003-04-01 |  | 2002-11-01 | 2004-01-01 | 252000 | 0 | 252000 | 252000 | 100% | 0 | 0 | 0 | 32760 | 0 | 32760 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Preparation of a project in the flexible foam subsector | Individual | LAC | ARG | FOA | 30 | PRP | 101 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-05-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Preparation of 4 projects in the rigid foam subsector | Individual | LAC | ARG | FOA | 30 | PRP | 102 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 2000 |  | Investment
FIN | IBRD | Project preparation in the rigid polyurethane foam sub-sector |  | LAC | ARG | FOA | 30 | PRP | 108 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-12-01 | 2001-06-01 |  | 2000-12-01 | 2000-12-01 | 7000 | 0 | 7000 | 7000 | 100% | 0 | 0 |  | 910 | 0 | 910 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Conversion from CFC-11 to LIA technology in the manufacture of flexible polyurethane boxfoam at four enterprises: Cosmos; La Cardeuse; Jovis; and Micropore | Individual | LAC | ARG | FOA | 31 | INV | 111 | A | I | CFC | 48.7 | 48.7 | 0 | 0 | 2000-07-01 | 2001-09-01 | 2003-08-01 |  | 2003-12-01 | 2005-09-01 | 295300 | -97042 | 198258 | 198258 | 100% | 0 | 0 | 0 | 38389 | -12615 | 25774 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam at 9 enterprises (Produmerc; Produnova; Carlos Masciotta; Elido Palermo; Carlos Castillo; Estanislao Kowcz; Constuctora Vimac; Gaspar Adragna; Placido Sandoval) | Individual | LAC | ARG | FOA | 32 | INV | 113 | A | I | CFC | 49.6 | 49.6 | 0 | 0 | 2000-12-01 | 2001-09-01 | 2004-01-01 |  | 2005-01-01 | 2007-03-01 | 320332 | -90 | 320242 | 320242 | 100% | 0 | 0 | 0 | 41643.16 | -11.7 | 41631.46 | 0 | 0 | Completed in 2005. Financially completed in 2007. |  | 2000 |  | Investment
FIN | UNIDO | Phasing out CFC-11 by conversion to HCFC-141b as a blowing agent in the manufacture of rigid polyurethane foams at 7 companies (Aislaciones y Servicios Maximo; Baduco D and D; Bolatti; Hi-Tec Poliuretano Alberto; Najera Jose; Stefanelli Vincer, SRL) | Individual | LAC | ARG | FOA | 32 | INV | 117 | A | I | CFC | 46.1 | 46.1 |  |  | 2000-12-01 | 2001-07-01 | 2003-01-01 |  | 2003-06-01 | 2004-09-01 | 329495 | 0 | 329495 | 329495.03 | 100% | -0.03 | 0 |  | 42834 | -36 | 42798 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the rigid foam sector | Individual | LAC | ARG | FOA | 33 | PRP | 118 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-06-01 | 2002-04-01 |  | 2003-10-01 | 2003-12-01 | 35000 | -900 | 34100 | 34099.99 | 100% | 0.01 | 0 |  | 4550 | -124 | 4426 | 0 | 0 | FIN |  |  |  | INV
FIN | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | LAC | ARG | FOA | 33 | PRP | 121 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam at 4 foam manufacturers (Artestamp, Paissan, Forever, Termica) | Individual | LAC | ARG | FOA | 34 | INV | 122 | A | I | CFC | 54.9 | 54.9 | 0 | 0 | 2001-07-01 | 2002-09-01 | 2004-08-01 |  | 2005-01-01 | 2007-01-01 | 352896 | -12969 | 339927 | 339927 | 100% | 0 | 0 | 0 | 45876.48 | -1685.95 | 44190.5276 | 0.0024 | 0 | Completed in 2005. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b in the manufacture of rigid foam insulation panels at Frio Star | Individual | LAC | ARG | FOA | 34 | INV | 123 | A | I | CFC | 18.9 | 18.9 | 0 | 0 | 2001-07-01 | 2002-12-01 | 2004-08-01 |  | 2003-12-01 | 2005-09-01 | 147987 | -53810 | 94177 | 94177 | 100% | 0 | 0 | 0 | 19238.31 | -6995 | 12243.31 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Preparation of a terminal programme in the foam sector | Individual | LAC | ARG | FOA | 36 | PRP | 126 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2005-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Completed in 2002. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Terminal umbrella project for phaseout of the use of CFC-11 in the manufacture of polyurethane foam | Individual | LAC | ARG | FOA | 38 | INV | 132 | A | I | CFC | 192.3 | 192.3 | 0 | 0 | 2002-11-01 | 2003-02-01 | 2005-12-01 |  | 2007-12-01 | 2013-01-01 | 1324843 | -17620.02 | 1307222.98 | 1307223 | 100% | -0.02 | 0 | 0 | 155732.7 | -2071.2 | 153661.5036 | -0.003551 | 0 | Financially completed in 2013. |  | 2002 |  | Investment
FIN | IBRD | Preparation for HCFC phase-out investment activities in the foam sector |  | LAC | ARG | FOA | 64 | PRP | 166 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2011-12-01 | 2012-07-31 |  | 2012-04-01 | 2012-04-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 2250 | 0 | 2250 | 0 | 0 | Project approved along with the Argentina HPMP (UNIDO) at the 66th ExCom in April. |  |  |  | Non-INV | 0
CLO | IBRD | Preparation for HCFC phase-out investment activities in the foam sector (additional funding) |  | LAC | ARG | FOA | 65 | PRP | 167 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-03-01 | 2012-06-30 |  |  | 2013-03-01 | 120000 | -108561 | 11439 | 11439 | 100% | 0 | 0 |  | 9000 | -8142 | 857.92 | 0.08 | 0.08 | Remainder of the preparatory funds returned to the 71st ExCom per Dec. 70/7. |  |  |  | Non-INV | 0
ONG | IBRD | Preparation for HCFC phase-out investment activities (stage II) (foam sector) |  | LAC | ARG | FOA | 76 | PRP | 176 | A | I |  | 0 | 0 | 0 | 0 | 2016-05-01 |  | 2017-05-31 | 2017-12-01 |  |  | 137500 | 0 | 137500 | 0 | 0% | 137500 | 137500 | 103300 | 9625 | 0 | 0 | 9625 | 9625 | Market data collection and overall Foam Sector Plan (FSP) preparation was initiated in Aug 16. Launch event organized at Ministry of Production, inviting representatives of system houses and individual foam enterprises. WB technical consultant presented available alternatives to ODS-free foam production. WB visited two system houses and two major HCFC-141b consumer companies to initiate respective project preparation. WB completed draft FSP in close collaboration with UEPRO by Dec 16. | Fine-tuning and completing information in the FSP continued during Jan-Feb 17, and a coordination meeting with OPROZ/NOU and UNIDO, the lead MP Implementing Agency in Argentina, was organized in Feb to complete the draft Argentine HPMP Stage II. Stage II HPMP submitted to the 79th ExCom. Bank preparation activities (including amending the WB-Argentina Grant Agreement) will continue into 2017. |  |  | Non-INV | 0
FIN | UNIDO | Demonstration Project: Open and closed circuit non-soil cultivation as main alternatives to the use of methyl bromide in tomato, cut flowers and strawberry production | Individual | LAC | ARG | FUM | 23 | DEM | 71 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-06-01 | 1999-12-01 |  | 2000-06-01 | 2002-09-01 | 481800 | -19112 | 462688 | 462687.69 | 100% | 0.31 | 0 |  | 62634 | -2580 | 60054 | 0 | 0 | FIN
FIN | UNDP | Project preparation for methyl bromide (tobacco) demonstration project | Individual | LAC | ARG | FUM | 24 | PRP | 73 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-08-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1998 |  | Investment
FIN | IBRD | Project preparation for methyl bromide (citrus and cotton) demonstration project |  | LAC | ARG | FUM | 25 | PRP | 75 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-03-30 | 1999-08-01 |  | 1999-06-30 | 1999-06-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Demonstration and training in viable alternatives, information dissemination and development of a national plan for phasing out methyl bromide in the tobacco sector | Individual | LAC | ARG | FUM | 26 | DEM | 79 | N | I | MeBr | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2000-12-01 |  | 2001-04-01 | 2003-11-01 | 273350 | -1493 | 271857 | 271857 | 100% | 0 | 0 | 0 | 35535.5 | -194.09 | 35341.41 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNIDO | Formulation of investment project in the methyl bromide sector (flowers) | Individual | LAC | ARG | FUM | 27 | PRP | 85 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-07-01 | 1999-12-01 |  | 2000-12-01 | 2002-09-01 | 40000 | -5622 | 34378 | 34378.04 | 100% | -0.04 | 0 |  | 5200 | -738 | 4462 | 0 | 0 | FIN
FIN | UNIDO | Formulation of investment project in the methyl bromide sector (strawberries, tomatoes) | Individual | LAC | ARG | FUM | 27 | PRP | 89 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-05-01 | 1999-12-01 |  | 2000-07-14 | 2000-11-09 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 | FIN
FIN | IBRD | Demonstration project for testing methyl bromide alternatives in post-harvest disinfestation for cotton and citrus (phase I) | Individual | LAC | ARG | FUM | 29 | DEM | 93 | N | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2004-08-01 | 2001-12-01 |  | 2013-06-01 | 2013-06-01 | 375000 | -62672 | 312328 | 312328 | 100% | 0 | 0 |  | 48750 | -8147.36 | 40602.64 | 0 | 0 | Project closed in 2013 following INTA's submission of a final report that clarified findings and informed of satisfactory results in both the cotton (phosphine and carbon disulfide) and citrus trials (phosphine and cold storage chambers). Despite positive results generated under lab conditions, it was determined that substitutes were not viable at commercial scale given toxicity and safety considerations and long periods of inactivity required for use of cold chambers. |  |  |  | Non-INV | 0
COM | UNIDO | Phase-out of methyl bromide in strawberry, protected vegetables and cut flower production | Individual | LAC | ARG | FUM | 30 | INV | 105 | A | I | MBR | 331 | 331 |  |  | 2000-03-01 | 2000-07-01 | 2015-01-01 |  | 2015-10-01 | 2016-04-01 | 3183390 | 0 | 3183390 | 3183261.2 | 100% | 128.8 | 0 | 1 | 360173 | 0 | 360159 | 14 | 0 | The project was operationally completed.
FIN | IBRD | Preparation of an investment project in methyl bromide sector |  | LAC | ARG | FUM | 30 | PRP | 100 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2001-12-01 |  | 2001-12-01 | 2001-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Project preparation in soil fumigation (tobacco) | Individual | LAC | ARG | FUM | 33 | PRP | 120 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-07-01 | 2003-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Methyl bromide phase-out in tobacco and non-protected vegetable seedbeds (2001 and 2002 tranches) | Multi-Year | LAC | ARG | FUM | 36 | INV | 129 | N | I | MeBr | 29 | 29 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2002-12-01 |  | 2004-12-01 | 2012-07-01 | 1720000 | 0 | 1720000 | 1720000 | 100% | 0 | 0 | 0 | 199200 | 0 | 199200 | 0 | 0 | Financially completed in 2012. |  | 2001 | 2004-03-01 | Investment
FIN | UNDP | Methyl bromide phase-out in tobacco and non-protected vegetable seedbeds (third tranche) | Multi-Year | LAC | ARG | FUM | 40 | INV | 136 | N | I | MeBr | 21 | 21 | 0 | 0 | 2003-07-01 | 2004-07-01 | 2004-03-01 |  | 2005-12-01 | 2012-07-01 | 467000 | 0 | 467000 | 467000 | 100% | 0 | 0 | 0 | 35025 | 0 | 35025 | 0 | 0 | Financially completed in 2012. |  | 2003 | 2005-07-01 | Investment
FIN | UNDP | Methyl bromide phase-out in tobacco and non-protected vegetable seedbeds (fourth tranche) | Multi-Year | LAC | ARG | FUM | 43 | INV | 139 | N | I | MeBr | 16 | 16 | 0 | 0 | 2004-07-01 | 2005-02-01 | 2005-07-01 |  | 2006-12-01 | 2012-07-01 | 467000 | 0 | 467000 | 467000 | 100% | 0 | 0 | 0 | 35025 | 0 | 35025 | 0 | 0 | Financially completed in 2012. |  | 2004 |  | Investment
FIN | UNDP | Methyl bromide phase-out in tobacco and non-protected vegetable seedbeds (fifth tranche) | Multi-Year | LAC | ARG | FUM | 46 | INV | 146 | N | I | MeBr | 33.3 | 33.3 | 0 | 0 | 2005-07-01 | 2006-01-01 | 2006-07-01 |  | 2007-12-01 | 2012-07-01 | 467000 | 0 | 467000 | 467000 | 100% | 0 | 0 | 0 | 35025 | 0 | 35025 | 0 | 0 | Financially completed in 2012. |  | 2005 |  | Investment
FIN | UNDP | Methyl bromide phase-out in tobacco and non-protected vegetable seedbeds (sixth tranche) | Multi-Year | LAC | ARG | FUM | 48 | INV | 149 | N | I | MeBr | 56.7 | 56.7 | 0 | 0 | 2006-04-01 | 2007-03-01 | 2007-04-01 |  | 2009-06-01 | 2012-07-01 | 467000 | -73.49 | 466926.51 | 466927 | 100% | -0.49 | 0 | 0 | 35025 | -5.51 | 35019.5249 | -0.03495 | 0 | Financially completed in 2012. |  | 2006 |  | Investment
FIN | UNDP | Technical assistance to prepare a national halon programme | Individual | LAC | ARG | HAL | 13 | TAS | 07 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-09-01 | 1995-01-01 |  | 1996-12-01 | 1997-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1996. Financially completed in 1997. |  | 1994 |  | Non-Investment
FIN | IBRD | National halon management programme to help eliminate the use of halon-1301 in new applications and to manage recovered halon-1301 | Individual | LAC | ARG | HAL | 26 | TAS | 80 | N | I | HAL | 200 | 200 | 0 | 0 | 1998-11-01 | 2002-02-01 | 2000-12-01 |  | 2010-12-31 | 2012-07-01 | 290620 | -112794.54 | 177825.46 | 177825.46 | 100% | 0 | 0 |  | 37780.6 | -14663.3 | 23117.3 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | UNIDO | National CFC phase-out plan (first tranche) | Multi-Year | LAC | ARG | PHA | 42 | INV | 138 | A | I | CFC | 0 | 0 |  |  | 2004-04-01 | 2004-06-01 | 2005-04-01 |  | 2008-12-01 | 2012-12-01 | 2740000 | 0 | 2740000 | 2740000.01 | 100% | -0.01 | 0 |  | 205500 | 0 | 205500 | 0 | 0 | FIN |  |  | 2006-12-01 | INV
COM | UNIDO | National CFC phase-out plan: 2006 work programme | Multi-Year | LAC | ARG | PHA | 47 | INV | 147 | A | I | CFC | 100 | 100 |  |  | 2005-11-01 | 2006-04-01 | 2006-12-01 |  | 2013-12-01 |  | 1850000 | 0 | 1850000 | 1843869.25 | 99.67% | 6130.75 | 0 | 1 | 138750 | 0 | 138290 | 460 | 0 | The project was operationally completed. |  |  |  | INV
FIN | IBRD | National CFC phase-out plan: 2006 work programme | Multiyear | LAC | ARG | PHA | 47 | INV | 148 | N | I | CFC | 1.5 | 1.5 | 0 | 0 | 2005-11-01 | 2009-12-01 | 2006-12-01 |  | 2013-12-01 | 2013-12-01 | 500000 | -368019.6 | 131980.4 | 131980.4 | 100% | 0 | 0 |  | 37500 | -27600 | 9900 | 0 | 0 | Given overall economic situation in Argentina and the requirement imposed by Dec. 70/7, it was not possible to initiate and finalize the chiller replacements that were planned during 2013. Only one chiller conversion agreement was finalized by the end of 2013: ALPARGATAS, 4 chillers. Project was closed 31 Dec. 2013. |  |  |  | INV | 0
FIN | UNIDO | National CFC phase-out plan: 2007 work programme | Multi-Year | LAC | ARG | PHA | 50 | INV | 150 | A | I | CFC | 200 | 200 |  |  | 2006-11-01 | 2007-09-01 | 2007-11-01 |  | 2015-10-01 | 2016-10-01 | 1103500 | -14 | 1103486 | 1103485.94 | 100% | 0.06 | 0 |  | 82763 | -1 | 82761 | 1 | 0 | The project was financially completed and the balance was returned at the 77th ExCom. |  |  |  | INV
COM | UNIDO | National CFC phase-out plan: 2008 work programme | Multi-Year | LAC | ARG | PHA | 53 | INV | 152 | A | I | CFC | 1509.5 | 1509.5 |  |  | 2007-11-01 | 2008-12-01 | 2009-12-31 |  | 2015-12-01 |  | 1167350 | 0 | 1167350 | 780619.49 | 66.87% | 386730.51 | 381459.21 | 1 | 87551 | 0 | 58546 | 29005 | 28609 | The project was operationally completed. |  |  |  | INV
TRF | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | ARG | PHA | 55 | PRP | 157 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-12-01 | 2009-07-01 |  |  | 2011-11-01 | 95750 | -43657 | 52093 | 52093 | 100% | 0 | 0 | 0 | 7181.25 | -3274 | 3907.25 | 0 | 0 | Project PRP transferred to UNIDO and remaining funds returned to MLF. | Project PRP transferred to UNIDO and remaining funds returned to MLF. | 2008 |  | Investment
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | LAC | ARG | PHA | 55 | PRP | 158 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 |  | 2011-06-01 | 2011-12-01 | 78000 | 0 | 78000 | 78000 | 100% | 0 | 0 |  | 5850 | 0 | 5850 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | LAC | ARG | PHA | 64 | PRP | 165 | A | I |  | 0 | 0 |  |  | 2011-07-01 | 2012-02-01 | 2012-07-01 |  | 2012-04-01 | 2013-04-01 | 43657 | -759 | 42898 | 42898.47 | 100% | -0.47 | 0 |  | 3274 | -57 | 3217 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | LAC | ARG | PHA | 66 | INV | 169 | A | I | HCFC | 7.1 | 7.1 |  |  | 2012-04-01 | 2013-05-01 | 2013-04-30 | 2018-05-31 |  |  | 685388 | 0 | 685388 | 565887.37 | 82.56% | 119500.63 | 63077.55 | 30000 | 51404 | 0 | 42442 | 8962 | 4730.8162 | - UNIDO continued the training all over the country. - The distribution of kits to technicians took place in September and November 2016. - No delay - No recurring problem - No impact on project completion date - No action required by Executive Committee | - Training continued and the distribution of kits is almost completed. - UNIDO has started a new set of training on natural alternatives: the firs two trainings are scheduled for April 2017 in Buenos Aires. - No delay - No recurring problem - No impact on project completion date - No action required by Executive Committee |  |  | INV
FIN | IBRD | HCFC phase-out management plan (stage I, first tranche) (phase-out of HCFC-141b in the production of polyurethane rigid insulation foam for domestic refrigerators at Mabe) | Multiyear | LAC | ARG | PHA | 66 | INV | 171 | N | I | HCFC | 18.46 | 18.46 | 0 | 0 | 2012-04-01 | 2015-11-01 | 2013-04-30 |  | 2015-04-01 | 2016-03-01 | 838612 | 0 | 838612 | 838612 | 100% | 0 | 0 | 0 | 62896 | 0 | 62896 | 0 | 0 | In Mar 16, WB disbursed third and final payment for the Mabe project, which was subsequently disbursed to Mabe by UEPRO, the Project Coordination Unit (PCU). Mabe provided UEPRO/WB all required technical documents e.g. on baseline equipment destruction, confirmation of compliance with necessary safety regulations for use of HC, and on environmental management and fiduciary compliance. | N/A |  |  | INV | 0
ONG | IBRD | HCFC phase-out management plan (stage I, first tranche) (monitoring and reporting of HCFC-22 production) | Multiyear | LAC | ARG | PHA | 66 | TAS | 170 | N | I |  | 0 | 0 | 0 | 0 | 2012-04-01 | 2016-11-01 | 2013-04-30 | 2018-06-01 |  |  | 76000 | 0 | 76000 | 12000 | 15.79% | 64000 | 64000 | 47000 | 5700 | 0 | 900 | 4800 | 4800 | UEPRO and consultant signed a contract on control and monitoring of HCFC-22 production by FIASA S.A. on Mar 1, 2016. Consultant first conducted retroactive monitoring of FIASA’s HCFC-22 production during 2015, and then proceeded with quarterly control and monitoring visits. In 2016, consultant prepared 4 reports: 2015 retroactive report and 3 quarterly reports. Said reports reviewed by UEPRO and WB and shared with OPROZ/NOU at Ministry of Environment and Sustainable Development (MAyDS), which used it to complete the information gathered through the national Import and Export Licensing System. Throughout monitoring period, FIASA was confirmed to produce less HCFC-22 than allowed by production quotas. FIASA vents by-product HFC-23, taken the costs of operating its existing incineration tower. Taken delayed start of monitoring and reporting suffered prior to Grant Agreement effectiveness, available funding will be sufficient to cover 2017 FIASA monitoring. New closing date for this activity is consequently proposed to be June 30, 2018. | Consultant conducted the final quarterly control and monitoring visit of 2016, covering the months of Oct-Dec, the key results being in line with those of the earlier reports. Reporting will continue throughout 2017. Available funding for monitoring will allow project activities to continue through 2017 into 2018. |  |  | Non-INV | 0 | To request the submission of additional status report to the 79th meeting to monitor the disbursement rate of approved funds.
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | Multi-Year | LAC | ARG | PHA | 74 | INV | 174 | A | I | HCFC | 3.3 | 0 |  |  | 2015-05-01 | 2015-09-01 | 2018-05-31 | 2018-05-31 |  |  | 314612 | 0 | 314612 | 20492.79 | 6.514% | 294119.21 | 61213.14 | 40000 | 22023 | 0 | 0 | 22023 | 4284.9198 | - UNIDO continue the support to local authorities with the coordination of the HPMP activities. - A review mission took place in November 2016. - Plans for workshop on refrigeration technologies applied to supermarkets have been discussed to be carried out in cooperation with Italian companies. - We have supported OPROZ (NOU of Argentina) in updating the new authorities on the activities of this project. - Negotiations with La Anonima as part of the demonstration project (financed apart) started. - No delay - No recurring problem - No impact on project completion date - No action required by Executive Committee | - UNIDO had a couple of meetings in February 2017 with the Argentinian authorities on the whole HCFC and HFC programme. - Some internal decisions at Ministry level have been taken, which seek to move OPROZ to the Ministry and under close coordination. - No delay - No recurring problem - No impact on project completion date - No action required by Executive Committee |  |  | INV
ONG | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | Individual | LAC | ARG | PHA | 77 | PRP | 177 | A | I |  | 0 | 0 |  |  | 2016-11-01 |  | 2018-06-30 | 2017-12-31 |  |  | 90000 | 0 | 90000 | 0 | 0% | 90000 | 0 | 50000 | 6300 | 0 | 0 | 6300 | 0 | The project was approved at the 77th Meeting of the ExCom in November 2016. | HPMP Stage II project document is being prepared and planned to be submitted to the next ExCom Meeting.
FIN | IBRD | Project preparation for the CFC production sector |  | LAC | ARG | PRO | 31 | PRP | 112 | A | I |  | 0 | 0 | 0 | 0 | 2000-07-01 | 2000-03-31 | 2001-01-01 |  | 2000-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | CFC production closure plan (first tranche) | Multiyear | LAC | ARG | PRO | 38 | INV | 133 | N | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2004-12-01 | 2003-12-01 |  | 2003-12-01 | 2010-11-01 | 500000 | 0 | 500000 | 500000 | 100% | 0 | 0 |  | 20000 | 0 | 20000 | 0 | 0 | An accounting and technical monitoring was carried out to verify that no CFCs were produced during 2009, and it was verified that the plant didn't operate during that period. The entire production sector project is 100% completed within expected deadlines, including destruction of equipment. Funds were fully disbursed according to the disbursement schedule and prior annual audits –technical and financial- according to UNEP’s regulations. Production cessation initially expected to be done by 2010 was done by 2007, when the company ceased definitely producing CFCs. |  |  |  | INV | 0
FIN | IBRD | Strategy for gradual phase-out of CFC-11 and CFC-12 production: 2004 annual programme | Multiyear | LAC | ARG | PRO | 44 | INV | 141 | N | I | CFC | 0 | 0 | 1373 | 1373 | 2004-12-01 | 2004-12-01 | 2005-12-01 |  | 2005-12-01 | 2010-11-01 | 3500000 | 0 | 3500000 | 3500000 | 100% | 0 | 0 |  | 200000 | 0 | 200000 | 0 | 0 | Accounting and technical monitoring was carried out to verify that no CFCs were produced during 2008, and it was verified that the plant did not operate during that period. All remaining CTC in storage was sold and exported. |  |  |  | INV | 0
FIN | IBRD | Strategy for gradual phase-out of CFC-11 and CFC-12 production: 2005 annual programme | Multiyear | LAC | ARG | PRO | 45 | INV | 143 | N | I | CFC | 0 | 0 | 1373 | 1373 | 2005-04-01 | 2007-09-01 | 2006-04-01 |  | 2006-04-01 | 2010-11-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 |  | 120000 | 0 | 120000 | 0 | 0 | Accounting and technical monitoring was carried out to verify that no CFCs were produced during 2008, and it was verified that the plant did not operate during that period. All remaining CTC in storage was sold and exported. |  |  |  | INV | 0
FIN | IBRD | Strategy for gradual phase-out of CFC-11 and CFC-12 production: 2006 annual programme | Multiyear | LAC | ARG | PRO | 50 | INV | 151 | N | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-09-01 | 2007-10-01 |  | 2007-10-01 | 2010-11-01 | 2000000 | 0 | 2000000 | 2000000 | 100% | 0 | 0 |  | 100000 | 0 | 100000 | 0 | 0 | Accounting and technical monitoring was carried out to verify that no CFCs were produced during 2008, and it was verified that the plant did not operate during that period. All remaining CTC in storage was sold and exported. |  |  |  | INV | 0
FIN | IBRD | Strategy for gradual phase-out of CFC-11 and CFC-12 production: 2007 annual programme | Multiyear | LAC | ARG | PRO | 53 | INV | 154 | N | I |  | 0 | 0 | 0 | 0 | 2007-11-01 |  | 2009-11-30 |  | 2008-03-01 | 2010-11-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 120000 | 0 | 120000 | 0 | 0 | Accounting and technical monitoring was carried out to verify that no CFCs were produced during 2008, and it was verified that the plant did not operate during that period. All remaining CTC in storage was sold and exported. |  |  |  | INV | 0
FIN | IBRD | Accelerated phase-out plan for CFC production | Multiyear | LAC | ARG | PRO | 53 | INV | 155 | N | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-11-01 |  | 2008-03-01 | 2010-11-01 | 2300000 | 0 | 2300000 | 2300000 | 100% | 0 | 0 |  | 172500 | 0 | 172500 | 0 | 0 | Accounting and technical monitoring was carried out to verify that no CFCs were produced during 2008, and it was verified that the plant did not operate during that period. All remaining CTC in storage was sold and exported. |  |  |  | INV | 0
FIN | IBRD | Strategy for gradual phase-out of CFC-11 and CFC-12 production: 2008 annual programme | Multiyear | LAC | ARG | PRO | 54 | INV | 156 | N | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-12-01 | 2009-03-31 |  | 2009-04-01 | 2010-11-01 | 1000000 | 0 | 1000000 | 1000000 | 100% | 0 | 0 |  | 120000 | 0 | 120000 | 0 | 0 | Completed. |  |  |  | INV | 0
FIN | IBRD | Strategy for gradual phase-out of CFC-11 and CFC-12 production: 2009 annual programme | Multiyear | LAC | ARG | PRO | 57 | INV | 160 | N | I | CFC | 0 | 0 | 274 | 274 | 2009-04-01 | 2009-12-31 | 2010-03-31 |  | 2009-12-31 | 2010-11-01 | 1000000 | 0 | 1000000 | 1000000 | 100% | 0 | 0 |  | 47000 | 0 | 47000 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Conversion to non-CFC technology in the production of heat exchangers for mobile air conditioning at Interclima, S.A. | Individual | LAC | ARG | REF | 15 | INV | 15 | N | I | CFC | 0 | 0 | 0 | 0 | 1994-12-01 | 1997-07-01 | 1995-12-01 |  | 1999-06-01 | 1999-11-01 | 1983430 | -314039 | 1669391 | 1669391 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. PCR was sent to ExCom. |  |  | 1999-08-01 | INV | 0
FIN | IBRD | Conversion to non-CFC technology in the production of condensers for mobile air conditioning at Simon Cachan, S.A. | Individual | LAC | ARG | REF | 15 | INV | 16 | N | I | CFC | 0 | 0 | 0 | 0 | 1994-12-01 | 1997-09-01 | 1995-12-01 |  | 2001-01-01 | 2002-03-01 | 2738217 | -459396 | 2278821 | 2278821 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  | 1999-11-01 | INV | 0
FIN | IBRD | Conversion to non-CFC technology in the production of complete mobile air conditioning systems at Mirgor, S.A. | Individual | LAC | ARG | REF | 15 | INV | 17 | N | I | CFC | 0 | 0 | 0 | 0 | 1994-12-01 | 1999-06-01 | 1995-12-01 |  | 1999-06-01 | 1999-06-01 | 35632 | -4082 | 31550 | 31550 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1999-08-01 | INV | 0
CLO | IBRD | Elimination of ODP in the production of household refrigerators at the Fribe La Rioja Plant | Individual | LAC | ARG | REF | 15 | INV | 18 | N | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1999-03-01 | 1997-06-01 |  |  | 1999-03-01 | 1488127 | -1444783 | 43344 | 43344 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project cancelled due to bankruptcy. Funds returned at 27th meeting. |  |  | 1997-06-01 | INV | 0
FIN | IBRD | Elimination of CFC in two manufacturing plants of domestic refrigerators at Helametal S.A., and Helametal Catamarca S.A. | Individual | LAC | ARG | REF | 15 | INV | 19 | N | I | CFC | 62 | 62 | 0 | 0 | 1994-12-01 | 1997-09-01 | 1996-12-01 |  | 2003-10-01 | 2004-07-01 | 2959085 | -59591.29 | 2899493.71 | 2899493.71 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1999-12-01 | INV | 0
CLO | IBRD | Elimination of ODS in the production of domestic refrigerators in the Fribe, S.A. plant | Individual | LAC | ARG | REF | 15 | INV | 20 | N | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1999-03-01 | 1997-06-01 |  |  | 1999-03-01 | 1822750 | -1769660 | 53090 | 53090 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project cancelled due to bankruptcy. Funds returned to 27th meeting. |  |  | 1997-06-01 | INV | 0
FIN | IBRD | Elimination of CFC in the domestic refrigerator manufacturing plant of McLean | Individual | LAC | ARG | REF | 15 | INV | 21 | N | I | CFC | 74 | 74 | 0 | 0 | 1994-12-01 | 1998-02-01 | 1996-12-01 |  | 2001-01-01 | 2001-05-01 | 2440570 | -1567990 | 872580 | 872580 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | All pending payments were effected by May 2001. The project is complete and the PCR has been submitted to EXCOM. |  |  | 2000-03-01 | INV | 0
FIN | USA | MAC servicing demonstration |  | LAC | ARG | REF | 16 | DEM | 22 | A | I | CFC | 20.4 | 20 | 0 |  | 1995-03-01 | 1995-09-01 | 1995-12-01 |  | 1997-06-01 | 1998-06-01 | 170000 | 0 | 170000 | 170000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1995 | 1997-06-01
FIN | Australia | Provision of training in leak reduction, emission control and recycling and management of non-CFC refrigerants in domestic and commercial refrigeration and air conditioning | Individual | LAC | ARG | REF | 17 | TAS | 24 | A | D |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-11-01 | 1995-11-01 |  | 1996-02-01 | 1996-03-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed |  | 1995
CLO | UNDP | Elimination of the use of CFCs in the manufacture of display cabinets and polyurethane panels for cold stores at Market Costan S.A. | Individual | LAC | ARG | REF | 18 | INV | 34 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1998-01-01 | 1997-05-01 |  |  | 1998-07-01 | 423000 | -421642 | 1358 | 1358 | 100% | 0 | 0 | 0 | 54990 | -54813.46 | 176.54 | 0 | 0 | Canceled in 1998. Financially completed in 1998. |  | 1995 |  | Investment
CLO | IBRD | Elimination of CFCs in domestic refrigerator production plants in Aurora S.A. | Individual | LAC | ARG | REF | 18 | INV | 35 | N | I |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1997-11-01 |  |  | 2000-12-01 | 567590 | -567590 | 0 | 0 | #DIV/0! | 0 | 0 |  | 73786.7 | -73786.7 | 0 | 0 | 0 | Project canceled at the 31st ExCom meeting. Funds returned at 32nd meeting. |  |  | 1998-05-01 | INV | 0
CLO | IBRD | Elimination of CFCs in 2 domestic refrigerator manufacturing plants at Piragua S.A., and Piragua San Luis | Individual | LAC | ARG | REF | 18 | INV | 36 | N | I |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1997-11-01 |  |  | 2000-12-01 | 1040264 | -1040264 | 0 | 0 | #DIV/0! | 0 | 0 |  | 135234.32 | -135234.32 | 0 | 0 | 0 | Project canceled at the 31st ExCom meeting. Funds returned at 32nd meeting. |  |  | 1998-05-01 | INV | 0
FIN | IBRD | Elimination of CFCs in domestic refrigerator production plant in Autosal, S.A. | Individual | LAC | ARG | REF | 18 | INV | 37 | N | I | CFC | 22 | 22 | 0 | 0 | 1995-11-01 | 1998-11-01 | 1997-11-01 |  | 2003-06-01 | 2004-03-01 | 797390 | 0 | 797390 | 797390 | 100% | 0 | 0 |  | 103660.7 | 0 | 103660.7 | 0 | 0 | Project completed. |  |  | 2001-09-01 | INV | 0
FIN | IBRD | Elimination of CFCs in the manufacturing plant of domestic refrigerators of Briket, S.A. | Individual | LAC | ARG | REF | 18 | INV | 38 | N | I | CFC | 30 | 30 | 0 | 0 | 1995-11-01 | 1998-02-01 | 1997-11-01 |  | 2001-10-01 | 2001-11-08 | 726400 | 0 | 726400 | 726400 | 100% | 0 | 0 |  | 94432 | 0 | 94432 | 0 | 0 | The company has been producing without CFCs since Aug. 2001. Destruction of old equipment was completed Oct. 2001. |  |  | 1999-10-01 | INV | 0
FIN | IBRD | Elimination of CFC in the manufacturing plant of domestic refrigerators of Neba, S.A. | Individual | LAC | ARG | REF | 18 | INV | 39 | N | I | CFC | 29 | 29 | 0 | 0 | 1995-11-01 | 1999-02-01 | 1997-11-01 |  | 2012-08-01 | 2012-08-01 | 686370 | 0 | 686370 | 686370 | 100% | 0 | 0 |  | 89228.1 | 0 | 89228.1 | 0 | 0 | On Aug. 22, 2012 a UEPRO representative visited Neba/Ikala and verified destruction of CFC-based equipment. With this verification action the project is completed. |  |  | 2001-09-01 | INV | 0
FIN | IBRD | Conversion to non-CFC technology in the production of mobile air conditioning systems at Sistemaire, S.A. | Individual | LAC | ARG | REF | 18 | INV | 40 | N | I | CFC | 0 | 0 | 0 | 0 | 1995-11-01 | 1998-08-01 | 1996-11-01 |  | 2000-09-01 | 2000-12-01 | 2370550 | -1400728 | 969822 | 969822 | 100% | 0 | 0 |  | 308171.5 | -182094.64 | 126076.5 | 0.36 | 0.36 | Completed. PCR submitted to ExCom. Savings returned to 34th ExCom. |  |  | 2000-11-01 | INV | 0
CLO | IBRD | Elimination of CFC in the manufacturing plant of domestic refrigerators at Adzen S.A. C.I.F. | Individual | LAC | ARG | REF | 19 | INV | 43 | N | I |  | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1997-05-01 |  |  | 2003-12-01 | 356970 | -356970 | 0 | 0 | #DIV/0! | 0 | 0 |  | 46406 | -41051.45 | 5354.55 | 0 | 0 | Project cancelled at the 40th ExCom. |  |  | 1997-11-01 | INV | 0
FIN | IBRD | Elimination of CFCs in the manufacturing plants of domestic refrigerators of Frimetal, Rosario | Individual | LAC | ARG | REF | 19 | INV | 44 | N | I | CFC | 89.7 | 89.7 | 0 | 0 | 1996-05-01 | 1998-03-01 | 1998-05-01 |  | 2004-09-01 | 2004-10-01 | 1855000 | 0 | 1855000 | 1855000 | 100% | 0 | 0 |  | 241150 | 0 | 241150 | 0 | 0 | Project financially and physically completed. |  |  | 2000-01-01 | INV | 0
FIN | UNDP | Elimination of the use of CFC's in the manufacture of display cabinet and walk-in freezers at Disthel | Individual | LAC | ARG | REF | 19 | INV | 45 | A | I | CFC | 10 | 10 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-05-01 |  | 1997-09-01 | 2000-12-01 | 196000 | -5726 | 190274 | 190274 | 100% | 0 | 0 | 0 | 25480 | -744.38 | 24735.62 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1996 |  | Investment
FIN | Switzerland | Technical assistance and training on safe designs of hydrocarbon based domestic and commercial refrigeration appliances | Individual | LAC | ARG | REF | 19 | TRA | 46 | A | D |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-08-01 | 1997-10-01 |  | 1997-08-01 | 1997-10-01 | 242600 | 0 | 242600 | 242600 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Balance has been compensated with separate Swiss funding |  | 1996
FIN | UNEP | National train the trainer programme on good practices in refrigeration | Individual | LAC | ARG | REF | 21 | TRA | 51 | A | I | CFC | 44.8 | 44.8 | 0 | 0 | 1997-02-01 | 1997-04-01 | 1998-02-01 |  | 1999-12-01 | 1999-12-01 | 215000 | 0 | 215000 | 215000 | 100% | 0 | 0 |  | 27950 | 0 | 27950 | 0 | 0 |  |  |  | 1999-12-01
CLO | UNIDO | Phasing out of CFCs in the manufacturing plant of domestic refrigerators of Radio Victoria Catamarca, S.A. | Individual | LAC | ARG | REF | 22 | INV | 58 | A | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-12-01 | 1999-06-01 |  |  | 2001-07-01 | 599896 | -454313 | 145583 | 145583 | 100% | 0 | 0 |  | 77986 | -59090 | 18896 | 0 | 0 | CLO
FIN | UNDP | Elimination of the use of CFCs in the manufacture of commercial refrigerators and display cabinets at Trevi | Individual | LAC | ARG | REF | 23 | INV | 60 | A | I | CFC | 3.5 | 3.5 | 0 | 0 | 1997-11-01 | 1999-06-01 | 1999-12-01 |  | 2000-11-01 | 2001-08-01 | 53850 | -4409 | 49441 | 49441 | 100% | 0 | 0 | 0 | 7000.5 | -573.17 | 6427.33 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNIDO | Elimination of CFCs in the manufacturing plant of domestic refrigerators of Frare S.A., Buenos Aires | Individual | LAC | ARG | REF | 23 | INV | 64 | A | I | CFC | 32 | 32 |  |  | 1997-11-01 | 1999-01-01 | 1999-12-01 |  | 2000-05-01 | 2002-09-01 | 514384 | -2300 | 512084 | 512084.45 | 100% | -0.45 | 0 |  | 66870 | -405 | 66465 | 0 | 0 | FIN
FIN | UNDP | Elimination of the use of CFCs in the manufacture of display cabinets and polyurethane panels for cold stores and walk-in coolers at Eurofrio | Individual | LAC | ARG | REF | 23 | INV | 66 | A | I | CFC | 26 | 26 | 0 | 0 | 1997-11-01 | 1999-01-01 | 1999-12-01 |  | 2002-11-01 | 2004-01-01 | 377350 | 0 | 377350 | 377350 | 100% | 0 | 0 | 0 | 49055.5 | 0 | 49055.5 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 1997 | 2001-05-01 | Investment
FIN | UNIDO | Elimination of CFCs in the manufacturing plant of domestic refrigerators of Bambi S.A., Santa Fe | Individual | LAC | ARG | REF | 23 | INV | 67 | A | I | CFC | 30.6 | 30.6 |  |  | 1997-11-01 | 1998-07-01 | 1999-12-01 |  | 1999-12-01 | 2002-05-01 | 515258 | 0 | 515258 | 515257.55 | 100% | 0.45 | 0 |  | 66984 | -24 | 66960 | 0 | 0 | FIN
FIN | IBRD | Elimination of CFCs in 1 manufacturing plant of domestic refrigerators of enterprise Whirlpool Argentina S.A. | Individual | LAC | ARG | REF | 23 | INV | 68 | N | I | CFC | 90.55 | 90.55 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-06-01 |  | 1999-12-01 | 2001-04-26 | 863879 | -99292 | 764587 | 764587 | 100% | 0 | 0 |  | 112304 | -12907.69 | 99396.31 | 0 | 0 | Project completed and funding disbursed. PCR submitted Dec. 01. |  |  |  | INV | 0
CLO | IBRD | Elimination of CFCs in the manufacturing plant of domestic refrigerators at Lobato San Luis S.A. | Individual | LAC | ARG | REF | 23 | INV | 69 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1998-12-01 |  |  | 2002-11-01 | 410683 | -410683 | 0 | 0 | #DIV/0! | 0 | 0 |  | 53389 | -47229 | 6160 | 0 | 0 | Cancelled - 37th ExCom |  |  |  | INV | 0
CLO | IBRD | Elimination of CFCs in the manufacturing plants of domestic refrigerators at Gepasa S.A. and Gesal S.R.L. | Individual | LAC | ARG | REF | 23 | INV | 70 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1999-12-01 |  |  | 2000-12-01 | 550400 | -550400 | 0 | 0 | #DIV/0! | 0 | 0 |  | 71552 | -71552 | 0 | 0 | 0 | Project cancelled at 31st ExCom. Funds returnd at 32nd ExCom. |  |  |  | INV | 0
FIN | IBRD | Substituting CFCs by HCFC-141b and HFC-134a in manufacturing of domestic and commercial refrigerators at El Dorado, S.A. | Individual | LAC | ARG | REF | 25 | INV | 77 | N | I | CFC | 12.8 | 12.8 | 0 | 0 | 1998-07-01 | 1999-06-01 | 2000-08-01 |  | 2000-09-01 | 2000-06-01 | 176000 | 0 | 176000 | 176000 | 100% | 0 | 0 |  | 22880 | 0 | 22880 | 0 | 0 | Completed. PCR has been sent |  |  |  | INV | 0
FIN | UNDP | Preparation of a project in the commercial refrigeration subsector | Individual | LAC | ARG | REF | 27 | PRP | 88 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-04-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology and of CFC-12 by conversion to HFC-134a in the manufacture of commercial refrigeration display cabinets and polyurethane panels for cold stores AT Perito Moreno Ref. | Individual | LAC | ARG | REF | 28 | INV | 92 | A | I | CFC | 31.1 | 31.1 | 0 | 0 | 1999-07-01 | 1999-09-01 | 2002-02-01 |  | 2001-12-01 | 2003-04-01 | 379605 | 0 | 379605 | 379605 | 100% | 0 | 0 | 0 | 49348.65 | 0 | 49348.65 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Preparation of one project in the commercial refrigeration subsector | Individual | LAC | ARG | REF | 30 | PRP | 103 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-05-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 2000 |  | Investment
FIN | IBRD | Project preparation in the commercial refrigeration sector |  | LAC | ARG | REF | 30 | PRP | 107 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Replacement of CFC-11 by HCFC-141b in the manufacture of rigid polyurethane foam for domestic refrigerators and sandwich panels at MTH S.R.L. | Individual | LAC | ARG | REF | 32 | INV | 116 | N | I | CFC | 8 | 8 | 0 | 0 | 2000-12-01 | 2001-05-30 | 2002-12-01 |  | 2002-10-01 | 2004-03-01 | 82695 | 0 | 82695 | 82695 | 100% | 0 | 0 |  | 10750.35 | 0 | 10750.35 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | UNEP | Training of customs officers | Individual | LAC | ARG | REF | 32 | TRA | 114 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2002-02-01 |  | 2007-11-01 | 2008-12-01 | 175000 | 0 | 175000 | 175000 | 100% | 0 | 0 |  | 22750 | 0 | 22750 | 0 | 0
FIN | UNEP | Training programme for the refrigeration servicing sector (Phase III) | Individual | LAC | ARG | REF | 32 | TRA | 115 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2003-12-01 |  | 2009-07-01 | 2010-12-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 |  | 39000 | 0 | 39000 | 0 | 0
FIN | UNDP | Project preparation in the commercial refrigeration sector | Individual | LAC | ARG | REF | 33 | PRP | 119 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNIDO | Preparation of umbrella project in the commercial refrigeration sector | Individual | LAC | ARG | REF | 36 | PRP | 124 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-05-01 | 2003-05-01 | 25000 | 0 | 25000 | 25000.04 | 100% | -0.04 | 0 |  | 3250 | -4 | 3246 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a refrigerant management plan | Individual | LAC | ARG | REF | 36 | PRP | 127 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-11-01 | 2004-08-01 |  | 2004-08-01 | 2004-08-01 | 100000 | 0 | 100000 | 99999.54 | 100% | 0.46 | 0 |  | 13000 | -11 | 12989 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation for HCFC phase-out investment activities (air-conditioning manufacturing sector) | Individual | LAC | ARG | REF | 57 | PRP | 161 | A | I |  | 0 | 0 |  |  | 2009-04-01 | 2009-08-01 | 2010-03-31 |  | 2010-07-01 | 2012-05-01 | 80000 | -5 | 79995 | 79994.57 | 100% | 0.43 | 0 |  | 6000 | 0 | 6000 | 0 | 0 | FIN |  |  |  | NON-INV
COM | Italy | Phase-out of HCFC-22 in the room and unitary air-conditioning equipment manufacturing sector | Multi-Year | LAC | ARG | REF | 61 | INV | 163 | A | I | HCFC | 0 | 0 | 0 |  | 2010-07-01 | 2011-06-01 | 2013-07-01 |  | 2016-12-01 |  | 300000 | 0 | 300000 | 122008 | 40.67% | 177992 | 0 | 0 | 39000 | 0 | 15861 | 23139 | 0 | - UNIDO continued following up with the supplier and the beneficiary company for the installation. - On the request of the beneficiary company, the installation was postponed to 2016 and was carried out in April. However, small technical problems were identified during the installation of some equipment. The equipment supplier has been committed to provide the required spare parts and solve the remaining technical issues. | - Based on the ExCom Decision 77/17, the remaining funds will be returned in 2017 by the 79th meeting; - the outstanding issues with the supplier are about to be completed, this however only affects the MLF-funded part of the project. | 2010 |  | Investment
ONG | UNIDO | Phase-out of HCFC-22 in the room and unitary airconditioning equipment manufacturing sector | Multi-Year | LAC | ARG | REF | 61 | INV | 164 | A | I | HCFC | 53.5 | 53.5 |  |  | 2010-07-01 | 2010-12-01 | 2013-07-31 | 2017-07-31 |  |  | 8435542 | 0 | 8435542 | 7136729.61 | 84.6% | 1298812.39 | 965543.14 | 10000 | 632666 | 0 | 535255 | 97411 | 72416 | - The installation was done in April 2016. Once some minor technical problems are solved, the project could be cleared completed. - Progress report submitted to the 78th Meeting of the ExCom and agreed to return funds from those companies that have not been converted due to bankruptcy. | - The project will be declare completed in July 2017 and funds will be returned as per ExCom decision. |  |  | INV
FIN | UNDP | Tecnical assistance for country programme preparation | Individual | LAC | ARG | SEV | 04 | CPG | 01 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1994-07-01 | 1993-02-01 |  | 1994-12-01 | 1997-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1991 |  | Non-Investment
FIN | IBRD | Country programme preparation | Individual | LAC | ARG | SEV | 06 | CPG | 02 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 149337 | -59619 | 89718 | 89718 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1993) |  | LAC | ARG | SEV | 09 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 63000 | -29084 | 33916 | 33916 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | User-sector project identification and preparation (1993) |  | LAC | ARG | SEV | 10 | PRP | 04 | A | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-06-30 | 1994-06-01 |  | 1993-12-01 | 1993-12-01 | 100000 | 65560 | 165560 | 165560 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Country programme preparation | Individual | LAC | ARG | SEV | 12 | CPG | 59 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The Country Program was completed and presented at the 13th E.C. meeting. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects in the refrigeration and foam sectors (1994) |  | LAC | ARG | SEV | 12 | PRP | 06 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 192929 | 4741 | 197670 | 197670 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | UNDP | Institutional strengthening (establishment of OPROZ) | Individual | LAC | ARG | SEV | 13 | INS | 11 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 | 1995-11-01 | 1997-07-01 |  | 1999-12-01 | 2000-12-01 | 359500 | 0 | 359500 | 359500 | 100% | 0 | 0 | 0 | 46735 | 0 | 46735 | 0 | 0 | Financially closed in 2000. |  | 1994 |  | Non-Investment
TRF | IBRD | Institutional strengthening (establishment of OPROZ) | Individual | LAC | ARG | SEV | 13 | INS | 11 | N | D |  | 0 | 0 | 0 | 0 | 1994-07-01 |  | 1997-07-01 |  |  | 1994-07-01 | 359500 | -359500 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Transfered to UNDP |  |  |  | Non-INV | 0
FIN | USA | Project preparation/technical assistance |  | LAC | ARG | SEV | 13 | PRP | 08 | A | I |  | 0 |  | 0 |  | 1994-07-01 |  | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 105000 | 0 | 105000 | 105000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | UNDP | Project preparation assistance (1994) | Individual | LAC | ARG | SEV | 14 | PRP | 12 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-09-01 | 1994-09-01 | 1995-09-01 |  | 1995-06-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Investment
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | LAC | ARG | SEV | 16 | PRP | 23 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-31 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 185000 | -4503 | 180497 | 180497 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | UNDP | Project preparation assistance | Individual | LAC | ARG | SEV | 17 | PRP | 25 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-07-01 | 1996-03-01 |  | 1996-07-01 | 1997-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Completed in 1996. Financially completed in 1997. |  | 1995 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | ARG | SEV | 18 | PRP | 41 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-12-01 | 1998-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | IBRD | Project preparation |  | LAC | ARG | SEV | 18 | PRP | 42 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 |  | 5850 | 0 | 5850 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | UNIDO | Project preparation in the refrigeration and methyl bromide sectors | Individual | LAC | ARG | SEV | 21 | PRP | 52 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-04-01 | 1998-02-01 |  | 2000-06-02 | 2002-05-01 | 32140 | 0 | 32140 | 32140.49 | 100% | -0.49 | 0 |  | 4178 | 0 | 4178 | 0 | 0 | FIN |  |  | 1999-06-01
FIN | IBRD | Project preparation |  | LAC | ARG | SEV | 21 | PRP | 53 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 |  | 5850 | 0 | 5850 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Project preparation | Individual | LAC | ARG | SEV | 22 | PRP | 54 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-04-01 | 2000-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | IBRD | Project preparation in the refrigeration, halon and MAC sectors |  | LAC | ARG | SEV | 24 | PRP | 72 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1998-12-01 | 1998-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects in the refrigeration and solvent cleaning sectors |  | LAC | ARG | SEV | 27 | PRP | 86 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-30 | 2001-01-01 |  | 1999-12-31 | 1999-12-01 | 16000 | 0 | 16000 | 16000 | 100% | 0 | 0 |  | 2080 | 0 | 2080 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Renewal of the institutional strengthening under the Montreal Protocol (Phase II) | Individual | LAC | ARG | SEV | 29 | INS | 98 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1999-11-01 | 1999-12-01 | 2001-12-01 |  | 2003-05-01 | 2013-12-01 | 239700 | 0 | 239700 | 239700 | 100% | 0 | 0 | 0 | 31161 | 0 | 31161 | 0 | 0 | Financially completed in 2013. |  | 1999 |  | Non-Investment
FIN | UNEP | Policy assistance for the design and implementation of an ODS import/export licensing system | Individual | LAC | ARG | SEV | 30 | TAS | 104 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2001-11-01 |  | 2007-12-01 | 2007-12-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 |  | 11700 | 0 | 11700 | 0 | 0 |  |  |  | 2003-10-01
FIN | UNDP | Extension of institutional strengthening project | Individual | LAC | ARG | SEV | 38 | INS | 130 | N | I | No_ODP | 25.7 | 25.7 | 0 | 0 | 2002-11-01 | 2003-05-01 | 2004-12-01 |  | 2005-12-01 | 2008-10-01 | 311610 | -197 | 311413 | 311413 | 100% | 0 | 0 | 0 | 40509.3 | -25.61 | 40483.69 | 0 | 0 | Completed in 2005. Financially completed in 2008. |  | 2002 |  | Non-Investment
CLO | UNIDO | Preparation of country programme update | Individual | LAC | ARG | SEV | 39 | CPG | 134 | A | I |  | 0 | 0 |  |  | 2003-04-01 |  | 2004-10-01 |  |  | 2005-08-01 | 50000 | -50000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 4500 | -4500 | 0 | 0 | 0 | CLO
FIN | UNDP | Assistance to carry out an HCFC survey | Individual | LAC | ARG | SEV | 45 | TAS | 144 | A | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-04-01 | 2006-12-01 |  | 2008-08-01 | 2009-12-01 | 68807 | -10271 | 58536 | 58536 | 100% | 0 | 0 | 0 | 6193 | -924.45 | 5268.5548 | -0.0048 | 0 | Completed in 2008. Financially completed in 2009. |  | 2005 |  | Non-Investment
FIN | UNDP | Extension for institutional strengthening project (phase IV) | Individual | LAC | ARG | SEV | 46 | INS | 145 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-12-01 | 2007-07-01 |  | 2008-05-01 | 2009-07-01 | 311567 | -521 | 311046 | 311046 | 100% | 0 | 0 | 0 | 23368 | -39.08 | 23328.9242 | -0.0042 | 0 | Completed in 2008.Financially completed in 2009. |  | 2005 |  | Non-Investment
FIN | UNDP | Extension for institutional strengthening project (phase V) | Individual | LAC | ARG | SEV | 53 | INS | 153 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-01-01 | 2009-11-01 |  | 2010-05-01 | 2011-12-01 | 311567 | 0 | 311567 | 311567 | 100% | 0 | 0 | 0 | 23368 | 0 | 23368 | 0 | 0 | Completed. National Ozone Unit monitoring elimination of use of CFCs in ARG.. Very strong licensing system allows country to have very reliable consumption data. Active public awareness programmes in place. Ozone Unit preparing for future challenges rela |  | 2007 |  | Non-Investment
FIN | UNDP | Extension for institutional strengthening project (phase VI) | Individual | LAC | ARG | SEV | 59 | INS | 162 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-03-01 | 2011-12-01 |  | 2012-05-01 | 2014-04-01 | 155784 | 155783 | 311567 | 311567 | 100% | 0 | 0 | 0 | 11684 | 11683.92 | 23367.925 | -0.0049987 | 0 | Financially completed in 2014. | Completed in 2012. | 2009 |  | Non-Investment
FIN | UNDP | Extension for institutional strengthening project (phase VII: 1/2012-12/2013) | Individual | LAC | ARG | SEV | 65 | INS | 168 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-09-01 | 2013-12-01 |  | 2014-11-01 | 2015-08-01 | 311567 | -214 | 311353 | 311353 | 100% | 0 | 0 | 0 | 23368 | -16.05 | 23351.9497 | 0.0003 | 0 | Financially Completed in 2015. | The review of imports of HCFCs in 2013 and preparation of reports to the MLFS are in progress as per the workplan. In addition, there has been follow up on existing MP funded projects in Argentina and the contract renewal of NOU's consultants. | 2011 |  | Non-investment
ONG | UNDP | Extension for institutional strengthening project (phase VIII: 1/2014-12/2015) | Individual | LAC | ARG | SEV | 71 | INS | 172 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2013-12-01 | 2015-02-01 | 2015-12-01 | 2017-12-01 |  |  | 311567 | 0 | 311567 | 269513.82 | 86.5% | 42053.18 | 0 | 16821.272 | 21810 | 0 | 18866.2356 | 2943.7644 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Institutional strengthening activities underway. ODS consumption reports prepared and submitted. Celebration of Ozone Day carried out. 2016 HCFC import quota set. Request for renewal of IS project was prepared. Prodoc signed (actual/planned, yes/no and date):The agreement has been signed earlier. Missions undertaken (actual/planned):0 of 0 TOR for consultants/subcontracts completed (actual/planned): TOR completed earlier. Contract/PO/MOA agreements signed: 0 of 0 First disbursement date (actual/planned): 42050Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:Due to devaluation of the Argentinian peso, budget implementation was slower than planned and renewal request was posponed to 2016. New phase was requested in the first meeting of 2016. | Annual work planned prepared and discussed. HCFC import quota for 2017 set. | 2013 |  | Non-Investment
ONG | UNIDO | Survey of ODS alternatives at the national level | Individual | LAC | ARG | SEV | 74 | TAS | 173 | A | I |  | 0 | 0 |  |  | 2015-05-01 | 2016-09-01 | 2016-05-31 | 2017-06-30 |  |  | 130000 | 0 | 130000 | 13167.27 | 10.13% | 116832.73 | 14800 | 90000 | 11700 | 0 | 0 | 11700 | 1332 | - National consultant was recruited and started the survey. - Most of the information were collected, the only pending issues were related to the consumption of chillers. - Slight impact on the project completion date. | - Draft survey and tables are prepared and have been submitted. - UNIDO is finalizing the survey and preparing the English translation. |  |  | NON-INV
ONG | UNDP | Extension for institutional strengthening project (phase IX: 7/2016-6/2018) | Individual | LAC | ARG | SEV | 76 | INS | 175 | N | I | HCFC | 0 | 0 | 0 | 0 | 2016-05-01 |  | 2019-06-01 | 2017-06-01 |  |  | 398806 | 0 | 398806 | 0 | 0% | 398806 | 0 | 159522.4 | 27916 | 0 | 0 | 27916 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): ProDoc signed on Dec 26, 2016, and implementation started up. Prodoc signed (actual/planned, yes/no and date):Dec 26 2016 Missions undertaken (actual/planned):0 of 0 TOR for consultants/subcontracts completed (actual/planned): 0 of 0 Contract/PO/MOA agreements signed: 0 of o First disbursement date (actual/planned): 42736Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:Signing of ProDoc took a little bit longer than anticipated. | Standaard IS activities implemented in Argentina. |  |  | Non-Investment
CLO | IBRD | Replacement of 1,1,1-trichloethane sheet steel cleaning system on the steel sheet-cutting table with an aqueous-mechanical system in the steel enterprise Siderar, SAIC | Individual | LAC | ARG | SOL | 28 | INV | 90 | N | I |  | 0 | 0 | 0 | 0 | 1999-07-01 |  | 2001-08-01 |  |  | 2003-04-01 | 105147 | -105147 | 0 | 0 | #DIV/0! | 0 | 0 |  | 13669.11 | -11566 | 2103 | 0.11 | 0.11 | Cancelled - 38th ExCom |  |  |  | INV | 0
FIN | IBRD | Conversion from MCF used as solvent to aqua based cleaning at Argelite La Rioja, SA; CIMCAM, SA; Grimoldi, SA; Heliodino SAIC; Integral Metalurgica, SA; Orbis Mertig SAIC; Trosh, SA Unisol, SA and Buffalo, S.A. | Individual | LAC | ARG | SOL | 28 | INV | 91 | N | I | TCA | 7.1 | 2.3 | 0 | 0 | 1999-07-01 | 2001-02-20 | 2000-08-01 |  | 2004-03-01 | 2004-03-01 | 272157 | -183607 | 88550 | 88550 | 100% | 0 | 0 |  | 35380.41 | -23868.91 | 11511.5 | 0 | 0 | Orbis and Buffalo have completed conversion. Argelite, Unisol and Cincam cancelled at the 39th ExCom. Grimoldi, Integral Metalurgica, Heliodino and Trosh were cancelled at the 44th ExCom. |  |  |  | INV | 0
FIN | IBRD | Project preparation in the solvent (TCA) sub-sector |  | LAC | ARG | SOL | 30 | PRP | 109 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2001-03-01 |  | 2001-12-01 | 2001-12-01 | 7000 | 0 | 7000 | 7000 | 100% | 0 | 0 |  | 910 | 0 | 910 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNIDO | Preparation of an investment project in the solvents sector (CFC-113 and TCA) | Individual | LAC | ARG | SOL | 36 | PRP | 125 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-12-01 | 2004-09-01 | 40000 | -1126 | 38874 | 38874 | 100% | 0 | 0 |  | 5200 | -154 | 5046 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Plan for phase-out of ODS in the solvent sector | Individual | LAC | ARG | SOL | 41 | INV | 137 | A | I | CFC CTC TCA | 42 | 54 |  |  | 2003-12-01 | 2004-04-01 | 2009-12-01 |  | 2013-12-01 | 2015-03-01 | 635986 | -6649 | 629337 | 629337.3 | 100% | -0.3 | 0 |  | 47699 | -499 | 47200 | 0 | 0 | FIN |  |  |  | INV
FIN | IBRD | Elimination of CFCs in sterilization via ETO at Asisthos SRL | Individual | LAC | ARG | STE | 27 | INV | 82 | N | I | CFC | 20.69 | 20.69 | 0 | 0 | 1999-03-01 | 1999-06-01 | 2001-04-01 |  | 2000-09-01 | 2001-03-01 | 395095 | 0 | 395095 | 395095 | 100% | 0 | 0 |  | 51362.35 | 0 | 51362.35 | 0 | 0 | Completed. PCR submitted Feb. 01. |  |  |  | INV | 0
CLO | UNEP | Preparation for a terminal phase-out management plan | Individual | EUR | ARM | PHA | 53 | PRP | 01 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 |  | 2008-11-01 |  |  | 2008-11-01 | 18000 | -18000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 2340 | -2340 |  | 0
CLO | UNDP | Preparation for a terminal phase-out management plan | Individual | EUR | ARM | PHA | 53 | PRP | 02 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2007-11-01 |  | 2008-11-01 |  |  | 2009-12-01 | 12000 | -12000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 900 | -900 | 0 | 0 | 0 | Canceled in 2008. Financially Completed in 2009. |  | 2007 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | EUR | ARM | PHA | 55 | PRP | 03 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2010-12-01 | 2011-09-01 | 85000 | -1548.67 | 83451.33 | 83451 | 100% | 0.33 | 0 | 0 | 6375 | -116.15 | 6258.825 | 0.02495 | 0 | Completed in 2010. Financially completed in 2011. |  | 2008 |  | Investment
FIN | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | EUR | ARM | PHA | 62 | INV | 06 | N | I | HCFC | 2.2 | 2.2 | 0 | 0 | 2010-12-01 | 2011-04-01 | 2012-12-01 |  | 2013-12-01 | 2014-08-01 | 265661 | 0 | 265661 | 170182.08 | 64.06% | 95478.92 | 0 | 0 | 19925 | 0 | 12763.9283 | 7161.0717 | 0 | Financially completed in 2014. | Completed in 2013. The planned milestone of conducting a mission to discuss progress over SAGA was achieved with a mission taking place in January 2014. Both, HPMP Stage I last tranche and PRP for Stage II have been prepared for submission to the 72nd Ex | 2010 |  | Investment
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | EUR | ARM | PHA | 62 | TAS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-05-01 | 2011-12-01 |  | 2013-12-01 | 2014-12-01 | 31515 | 0 | 31515 | 31515 | 100% | 0 | 0 |  | 4097 | 0 | 4097 | 0 | 0
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | EUR | ARM | PHA | 66 | INV | 09 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-04-01 | 2013-02-01 | 2015-04-01 | 2017-08-01 |  |  | 297177 | 0 | 297177 | 253354 | 85.25% | 43823 | 0 | 17529.2 | 22288 | 0 | 19001.3156 | 3286.6844 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): In February 2016, SAGA's equipment was transferred to a warehouse and safely stored until the bidding was announced in September 2016, and a winner selected in October 2016 correpondingly. Proceeds from the sale were returned to UNDP central accounts, and will further be transferred to the MLF. Assistance was provided to the winning company to find a transportation firm to deliver the equipment to final destination at the new client's cost. The equipment was shipped to Finland late December 2016. No more activities were underway in this period, except for continous monitoring on the HCFC re-use in the servicing sector which was carried out by two experts. 24 companies were subjected to such monitoring efforts. The project produced two 10 short videos on national HCFC control policies to faciliate awareness raising. Prodoc signed (actual/planned, yes/no and date):1/1. Yes. Agreement signed earlier. Missions undertaken (actual/planned):1/1: Mission fielded in 2016 to discuss HPMP-I progress and SAGA situation TOR for consultants/subcontracts completed (actual/planned): 1/1: One ITB was prepared for SAGA equipment and announced. Monitoring experts TORs were established in earlier reporting periods. Contract/PO/MOA agreements signed: 1/1: Tender was announced to financially dispose of SAGA equipment, with one company selected as recipient. First disbursement date (actual/planned): 41306Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:SAGA company wnet bankrupt earlier and NOU/UNDP were trying to find solution to the purchased equipment. Eventually, after all other options were exhausted, and in consultation with MLF Secretarait, NOU/UNDP announced a tender and found a new client from outside of Armenia for SAGA's equipment. Case solved. | No activities in 2017, except for operational closure of the project, including finalization of transactions on SAGA programme. | 2012 |  | Investment
FIN | UNEP | Preparation of a HCFC phase-out management plan (stage II) | Individual | EUR | ARM | PHA | 73 | PRP | 11 | A | I |  | 0 |  | 0 |  | 2014-11-01 | 2016-06-01 | 2016-11-01 |  | 2016-11-01 | 2016-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | Brief progress report (actual/planned): UNEP hired a national consultant to prepare a report on the non-investment components for HPMP stage II in April 2016. The consultant collected, reviewed, and finalized in cooperation with the NOU and UNEP the information regarding policy, legislation, application of standards and safety requirements, availability of low GWP alternatives, and training activities. An overview on the codes of goof servicing practice and standards for proper handling of flammable or toxic refrigerants currently in place or to be introduced was prepared and served as the basis for the development of Armenia HPMP stage II proposal. The proposal was first reviewed by the Ministry of Nature Protection of Armenia and then submitted to UNEP in May 2016. In coordination with UNDP as the lead agency and UNEP as the cooperating agency, it was submitted and approved by ExCom 77 in November 2016. Legal arrangements(actual/planned): SSA with a national consultant established in April 2016. First mission (actual/planned): N.a. TOR completed (actual/planned): Yes - TOR for national consultant First disbursement date (actual/planned): June 2016 All funds disbursed (yes/no): Yes Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: N.a. If Yes, will delay have impact on project completion date (yes/no): N.a. Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N.a. | Project financially completed
ONG | UNDP | Preparation of a HCFC phase-out management plan (stage II) | Individual | EUR | ARM | PHA | 73 | PRP | 12 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-11-01 | 2015-07-01 | 2016-11-01 | 2017-03-01 |  |  | 20000 | 0 | 20000 | 19989.91 | 99.95% | 10.09 | 0 | 4.036 | 1400 | 0 | 1399.2937 | 0.7063 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Project team was recruited to enable formulation of HPMP-II documentation. Required data collection processed and stakeholder workshops held to discuss HCFC control policies and HPMP-II design. HPMP-II was prepared, submitted and approved at the 77th ExCom Prodoc signed (actual/planned, yes/no and date): Missions undertaken (actual/planned):1/1: Mission fielded in 2016 to assist NOU with HPMP-II related stakeholder workshop. TOR for consultants/subcontracts completed (actual/planned): 2/2: Two experts were recruited to help with HCFC data collection and analysis Contract/PO/MOA agreements signed: 0/0: No procurement was expected in PRP stage First disbursement date (actual/planned): 42186Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | No activities due to completion of HPMP-II formulation process and its submission to the 77th ExCom. | 2014 |  | Non-Investment
COM | UNDP | Verification report for stage I of HCFC phase-out management plan | Individual | EUR | ARM | PHA | 73 | TAS | 13 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-11-01 | 2015-07-01 | 2015-05-01 |  | 2015-11-01 |  | 30000 | 0 | 30000 | 29909.18 | 99.7% | 90.82 | 0 | 77.197 | 2700 | 0 | 2691.8262 | 8.1738 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2015. |  | 2014 |  | Non-Investment
COM | UNEP | HCFC phase-out management plan (stage I, third tranche) | Multi-year | EUR | ARM | PHA | 74 | TAS | 15 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2015-11-01 | 2016-05-01 |  | 2016-05-01 |  | 7485 | 0 | 7485 | 7485 | 100% | 0 | 0 | 0 | 973 | 0 | 973 | 0 | 0 | Brief progress report (actual/planned): The verification report was submitted and accepted by the Fund Secretariat in February 2016 and subsequently the project funds were released to the implementing agencies. The SSFA with the Ministry of Nature Protection was signed in February 2016 . Consultants were hired to prepapare the training workshops and to up-date the training materials. The training of 30 customs and enforcement officers (environmental inspectors) took place in Yerevan on 17 May 2016 as a result of interagency cooperation between the Ministry and the Customs Service. The training of 21 refrigertion technicians took place in Yerevan on 18 May 2016 as a result of cooperation between the Ministry and the RAC Association of Armenia. Both trainings were opened and attended by the Deputy Minister highlighting the importance of the training activity in the respective fields. The participants of the refrigeration training were awarded with certificates. The monitoring activity within the project covered the period of February - May 2016. Project completed in May 2016. Legal arrangements(actual/planned): SSFA with the Ministry of Nature Protection signed by both parties in February 2016. First mission (actual/planned): N.a. TOR completed(actual/planned): N.a. First disbursement date (actual/planned): May 2016 All funds disbursed (yes/no): Yes Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: N.a. If Yes, will delay have impact on project completion date (yes/no): N.a. Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N.a. | Project completed.
ONG | UNDP | HCFC phase-out management plan (stage II, first tranche) | Multi-year | EUR | ARM | PHA | 77 | INV | 18 | N | I | HCFC | 0 | 0 | 0 | 0 | 2016-12-01 |  | 2019-12-01 | 2017-12-01 |  |  | 108000 | 0 | 108000 | 0 | 0% | 108000 | 0 | 43200 | 9720 | 0 | 0 | 9720 | 0 | Newly Approved | Once funds from the fund were received, DOA was prepared and sent to UNDP and NOU-Armenia in February 2017. UNDP Project document drafted, along with 2017 workplan, and submitted for signature with the Government. Signature expected in April/May 2017 to allow to start with implementation of workplans, TORs etc. | 2016 |  | Investment
ONG | UNEP | HCFC phase-out management plan (stage II, first tranche) | Multi-year | EUR | ARM | PHA | 77 | TAS | 19 | A | I |  | 0 |  | 0 |  | 2016-12-01 |  | 2018-12-01 | 2018-12-01 |  |  | 35000 | 0 | 35000 | 0 | 0% | 35000 | 0 | 3500 | 4550 | 0 | 0 | 4550 | 0 | Project newly approved by ExCom 77. | Brief progress report (actual/planned): Project newly approved by ExCom 77. Legal arrangements (actual/planned): SSFA with the Ministry of Nature Protection submitted for internal clearance and signature in December 2016. First mission (actual/planned): N.a. TOR completed (actual/planned): N.a. First disbursement date (actual/planned): Pending All funds disbursed (yes/no): No Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: Time is required to transfer and programming of project funds and the release of payments. If Yes, will delay have impact on project completion date (yes/no): No Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N.a.
FIN | UNDP | Preparation for HCFC phase-out investment activities (refrigeration sector) | Individual | EUR | ARM | REF | 57 | PRP | 04 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-05-01 | 2010-03-01 |  | 2010-12-01 | 2012-04-01 | 30000 | -3538.57 | 26461.43 | 26461 | 100% | 0.43 | 0 | 0 | 2250 | -265.39 | 1984.575 | 0.03495 | 0 | Financially completed in 2012. | Financially completed in 2012. | 2009 |  | Investment
FIN | UNIDO | Institutional strengthening (phase I) | Individual | EUR | ARM | SEV | 57 | INS | 05 | N | I |  | 0 | 0 |  |  | 2009-04-01 | 2009-11-01 | 2011-03-31 |  | 2010-12-01 | 2012-12-01 | 120000 | -1188 | 118812 | 118811.98 | 100% | 0.02 | 0 |  | 9000 | -89 | 8911 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Extension of institutional strengthening project (phase II) | Individual | EUR | ARM | SEV | 62 | INS | 08 | N | I |  | 0 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2013-03-31 |  | 2012-12-01 | 2014-07-01 | 120000 | 0 | 120000 | 120000.34 | 100% | -0.34 | 0 |  | 9000 | 0 | 9000 | 0 | 0 | FIN |  |  |  | NON-INV
COM | UNIDO | Extension of institutional strengthening project (phase III: 4/2013-3/2015) | Individual | EUR | ARM | SEV | 68 | INS | 10 | N | I |  | 0 | 0 |  |  | 2012-12-01 | 2013-06-01 | 2014-12-31 |  | 2014-12-01 | 2016-04-01 | 120000 | 0 | 120000 | 118452.15 | 98.71% | 1547.85 | 0 | 1 | 8400 | 0 | 8292 | 108 | 0 | The project was operationally completed. |  |  |  | NON-INV
ONG | UNIDO | Extension of institutional strengthening project (phase IV: 4/2015-3/2017) | Individual | EUR | ARM | SEV | 73 | INS | 14 | N | I |  | 0 | 0 |  |  | 2014-11-01 | 2015-04-01 | 2017-03-31 | 2017-04-17 |  |  | 120000 | 0 | 120000 | 111560.58 | 92.97% | 8439.42 | 481.35 | 7958 | 8400 | 0 | 7809 | 591 | 34 | - NOU is fully staffed and activities were executed in line with project document and annual work plan. There were no delays in activities execution. - The project activities are to be completed in 2017, as scheduled. Milestones achieved: Milestone 1: NOU staff contracts released - Yes Milestone 2: Public awareness activities organized - yes Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | Project activities were completed as of April 2017 |  |  | NON-INV
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | EUR | ARM | SEV | 74 | TAS | 16 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-02-01 | 2016-05-01 | 2017-03-01 |  |  | 70000 | 0 | 70000 | 23497.83 | 33.57% | 46502.17 | 0 | 4650.217 | 9100 | 0 | 3054.7179 | 6045.2821 | 0 | Brief progress report (actual/planned): Five local experts were recruited, priority sectors identified, working group created, survey questionnaires prepared and the first stakeholder consultation took place on 15 March 2016. Field trips and labor division took place according to geographic location of the selected enterprises. Desktop study and data collection completed in May 2016. Official communications were sent to the Ministry of Emergency Situations, Ministry of Internal Affairs / Road Police, State Revenue Committee, South Caucasus Railroad LLC, State Drug Service and Yerevan Chemical Plant LLC and the collected data analysed in the second half of 2016. The second stakeholder consultation took place on 23-24 December 2016. Legal arrangements(actual/planned): SSFA was amended in February 2016 to extend its validity and to include the funding previously retained for an international expert. Initial stages of project implementation(actual/planned): N.a. Intermediate goals achieved (actual/planned): N.a. Project completion and follow up: N.a. First disbursement date (actual/planned): February 2016 All funds disbursed (yes/no): No Any delay?(yes/no): Yes If Yes, reasons for delay & action plan to resolve: Delays in slow disbursement. If Yes, will delay have impact on project completion date (yes/no): Yes Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N.a. | Brief progress report (actual/planned): Following the recommendations of the second stakeholder consultation, data analysis was continued, additional data on MDIs collected to close data gaps and the draft report prepared in February 2017. Legal arrangements(actual/planned): SSFA was amended in February 2016 to extend its validity and to include the funding previously retained for an international expert. Initial stages of project implementation (actual/planned): N.a. Intermediate goals achieved (actual/planned): N.a. Project completion and follow up: N.a. First disbursement date (actual/planned): February 2016 All funds disbursed (yes/no): No Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: Delays due to slow disbursement. If Yes, will delay have impact on project completion date (yes/no): Yes Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N.a.
ONG | UNIDO | Extension of institutional strengthening project (phase V: 4/2017-3/2019) | Individual | EUR | ARM | SEV | 76 | INS | 17 | N | I |  | 0 | 0 |  |  | 2016-05-01 |  | 2019-03-31 | 2019-06-30 |  |  | 153600 | 0 | 153600 | 0 | 0% | 153600 | 0 | 20000 | 10752 | 0 | 0 | 10752 | 0 | - Project approved at the 76th Meeting of the ExCom in 2016. - The project activities are to be initiated in March 2017, in line with the approved project document (March 2017 - March 2019). | - Work plan for executing project activities for the year 2017 has been already developed by NOU. - NOU is fully staffed and bilateral consultations are scheduled 10- 12 May 2017. |  |  | NON-INV
FIN | UNEP | Regional workshop on aerosol conversion for the SEAP region | Individual | ASP | ASP | ARS | 16 | TRA | 16 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-04-01 | 1995-06-01 |  | 1995-05-01 | 1999-04-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 | 0 |  | 15600 | 0 | 15600 | 0 | 0
COM | Japan | Project preparation for a demonstration project on ODS disposal | Individual | ASP | ASP | DES | 54 | PRP | 53 | A | I |  | 0 |  | 0 |  | 2008-04-01 | 2009-04-01 | 2009-03-01 |  | 2014-05-01 |  | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | A project document was submitted twice but agreement to forward it to the ExCom (the 66th and the 72nd) for consideration was not reached with the Secretariat. According to the decision at the ExCom72, this project proposal will not be submitted again. Financially closed in |  | 2008
FIN | UNDP | Low-CFC foam training and demonstration programme in Asia | Individual | ASP | ASP | FOA | 06 | TRA | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-12-01 | 1994-02-01 |  | 1993-12-01 | 1997-12-01 | 52500 | -15672 | 36828 | 36828 | 100% | 0 | 0 | 0 | 6825 | -2037.36 | 4787.64 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Methyl bromide data collection for Asia and the Pacific | Individual | ASP | ASP | FUM | 17 | TAS | 19 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-08-01 | 1996-01-01 |  | 1996-03-01 | 2000-12-01 | 102000 | -64974 | 37026 | 37026 | 100% | 0 | 0 | 0 | 13260 | -8446.36 | 4813.64 | 0 | 0 | Completed in 1996. Financially completed in 2000. |  | 1995 |  | Non-Investment
FIN | UNEP | Regional workshop on methyl bromide for Asia and the Pacific | Individual | ASP | ASP | FUM | 17 | TRA | 18 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-10-01 | 1996-01-01 |  | 1995-11-01 | 1999-04-01 | 82500 | 0 | 82500 | 82500 | 100% | 0 | 0 |  | 10725 | 0 | 10725 | 0 | 0
FIN | UNEP | Regional workshop on the experiences of use of methyl bromide alternatives evaluated under the Multilateral Fund | Individual | ASP | ASP | FUM | 34 | TRA | 43 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-08-01 | 2002-06-01 |  | 2003-12-01 | 2005-12-01 | 80000 | -13239 | 66761 | 66761 | 100% | 0 | 0 |  | 10400 | -1721.07 | 8678.93 | 0 | 0
FIN | USA | South-east Asia halon-1211 training workshop in Japan |  | ASP | ASP | HAL | 08 | TRA | 07 | A | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1992-10-01 |  | 1992-10-01 | 1992-10-01 | 190000 | 0 | 190000 | 190000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1992
FIN | France | Survey for halon banking management plan in West Asia (Bahrain, Lebanon, Qatar and Yemen) |  | ASP | ASP | HAL | 28 | TAS | 29 | N | D |  | 0 |  | 0 |  | 1999-07-01 | 2002-05-01 | 2000-02-01 |  | 2000-02-01 | 2002-12-01 | 17500 | 0 | 17500 | 17500 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed.
FIN | Germany | Survey for halon banking management plan in West Asia: Bahrain, Lebanon, Qatar and Yemen | Halon banking | ASP | ASP | HAL | 28 | TAS | 39 | A | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-06-01 | 2000-02-01 |  | 2000-03-01 | 2000-09-01 | 17500 | 0 | 17500 | 17500 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation lead to project approved at 30th ExCom.
FIN | Germany | Halon banking management plan in West Asia countries: Bahrain, Lebanon, Qatar and Yemen (jointly implemented with France) | Halon banking | ASP | ASP | HAL | 30 | TAS | 36 | A | I |  | 0 |  | 0 |  | 2000-03-01 | 2001-02-01 | 2001-10-01 |  | 2005-04-01 | 2007-12-01 | 117500 | 0 | 117500 | 117500 | 100% | 0 | 0 | 0 | 15275 | 0 | 15275 | 0 | 0 | Evaluation meeting Beirut 31.5.-4.6.2004; Comment on Terms, Comment on evaluation report; Calculation of operational costs of halon R&R equipment; contact addresses and quotations received for storage cylinders; discussion of alternative strategies. Proje
FIN | France | Halon banking management plan in West Asia countries: Bahrain, Lebanon, Qatar and Yemen (jointly implemented with Germany) |  | ASP | ASP | HAL | 30 | TAS | 37 | A | I |  | 0 |  | 0 |  | 2000-03-01 | 2004-04-01 | 2001-10-01 |  | 2004-12-01 | 2005-01-01 | 117500 | 0 | 117500 | 117500 | 100% | 0 |  | 0 | 5875 | 0 | 5875 | 0 |  | Project completed. Final payment to GTZ in 2004.
FIN | UNEP | Workshop for halon banking management plan in West Asia countries: Bahrain, Lebanon, Qatar and Yemen | Individual | ASP | ASP | HAL | 30 | TRA | 38 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2002-10-01 | 2001-10-01 |  | 2004-12-01 | 2006-12-01 | 50000 | -2360 | 47640 | 47640 | 100% | 0 | 0 |  | 6500 | -307 | 6193 | 0 | 0
FIN | UNEP | Development of HCFC phase-out management plan for PIC countries through regional approach | Individual | ASP | ASP | PHA | 60 | PRP | 54 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-07-01 | 2011-09-01 |  | 2011-12-01 | 2013-12-01 | 494600 | 0 | 494600 | 494600 | 100% | 0 | 0 |  | 64298 | 0 | 64298 | 0 | 0
ONG | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, first tranche) | Multi-year | ASP | ASP | PHA | 63 | TAS | 55 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-09-01 | 2015-03-01 | 2017-04-01 |  |  | 134000 | 0 | 134000 | 134000 | 100% | 0 | 0 | 0 | 17420 | 0 | 17420 | 0 | 0 | Brief progress report (actual/planned): 500 copies of the draft "Quick Guide on Good Servicing Practices for Flammable Refrigerant” was publicized and distributed to the PICs technicians through the NOOs for feedback and comments. Based on the feedback obtained from countries as well as discussion during the Network Meeting in Fiji in 2016, the Quick Guide was finalized and processed for publication. As of December 2016, there is the balance from the SSFA with the Secretariat of the Pacific Regional Environment Programme (SPREP), which was anticipated to be fully utilized. UN Environment has therefore identified activities to support the implementation of the regional component, which will be implemented in 2017. Legal arrangement: The SSFA has been signed in May 2011 with OCO; August 2011 with SPREP; and December 2011 with SCT. First Mission: May 2011 TOR completed: Not applicable. First disbursement date: September 2011 All funds disbursed (yes/no): No Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned):To support the regional component, the regional component under the first tranche will be delivered through the support of resource persons and representatives from country with significant progress in the development of standards for labeling requirement for RAC appliance and low GWP refrigerants to participate in the PIC Network Meeting to be organized April 2017. This will set the stage for the PIC to synergize HPMP activities with their national on-going activities. The regional component of the first tranche will be completed by first half of 2017.
ONG | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, second tranche) | Multi-year | ASP | ASP | PHA | 74 | TAS | 58 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-06-01 | 2020-05-01 | 2020-12-01 |  |  | 106000 | 0 | 106000 | 0 | 0% | 106000 | 28270.5 | 10600 | 13780 | 0 | 0 | 13780 | 3675.165 | Brief progress report (actual/planned): UNEP continued to provide support to assist the countries to strengthen their existing legislation and regulations to effectively control imports and exports of HCFCs and HCFC-based equipment (licensing and quota system, iPIC, provision of policy advice, high level political support, development of legislation/regulations, training and capacity building, and synergy with others). A session on implementation of the HPMP stage 1 second tranche covering the regulations and certifictaion system was delivered during the Network Meeting in Suva, Fiji in June 2016. The regional component co-financed partipation of about 35 NOOs and PIC technicians in the back-to-back Train-the-Trainer Workshop on Good Servicing Practices for Longer-term, Low-GWP Alternatives in Refrigeration and Air-conditioning Sector fo the PIC from 20 June - 1 July 2016. Legal arrangement: Not applicable. First Mission: June 2016 TOR completed: Not applicable. First disbursement date: June 2016 All funds disbursed (yes/no): No Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): UNEP continues to provide support to assist the countries to strengthen their existing legislation, regulations, capacity and awarenes raising to effectively control imports and exports of HCFCs and HCFC-based equipment through regular communication with the NOOs.
TRF | UNDP | Training and demonstration programme in commercial/industrial refrigeration in East Asia | Individual | ASP | ASP | REF | 06 | TRA | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1993-02-01 |  |  | 1993-06-01 | 40000 | -40000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 5200 | -5200 | 0 | 0 | 0 | Transferred in 1993. Financially Completed in 1993. |  | 1992 |  | Non-Investment
FIN | UNDP | Training and demonstration programme in CFC recycling in MAC in Asia | RMP-Component | ASP | ASP | REF | 06 | TRA | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1996-06-01 | 1994-07-01 |  | 1996-08-01 | 1997-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Completed in 1996. Financially completed in 1997. |  | 1992 |  | Non-Investment
TRF | UNDP | Training and demonstration programme in commercial/industrial refrigeration in South Asia | Individual | ASP | ASP | REF | 06 | TRA | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1993-02-01 |  |  | 1993-06-01 | 40000 | -40000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 5200 | -5200 | 0 | 0 | 0 | Transferred in 1993. Financially Completed in 1993. |  | 1992 |  | Non-Investment
FIN | UNEP | Refrigeration training workshop for Asia and the Pacific | Individual | ASP | ASP | REF | 09 | TRA | 09 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-04-01 |  | 1994-04-01 | 1994-12-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 |  | 11700 | 0 | 11700 | 0 | 0
FIN | UNEP | Training and demonstration programme in commercial/industrial refrigeration in East Asia | Individual | ASP | ASP | REF | 10 | TRA | 10 | A | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1996-07-01 | 1994-06-01 |  | 1997-02-01 | 1999-04-01 | 43400 | 0 | 43400 | 43400 | 100% | 0 | 0 |  | 5642 | 0 | 5642 | 0 | 0
FIN | UNEP | Training and demonstration programme in commercial/industrial refrigeration in South Asia | Individual | ASP | ASP | REF | 10 | TRA | 11 | A | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-09-01 | 1994-05-01 |  | 1994-12-01 | 1995-12-01 | 43400 | 0 | 43400 | 43400 | 100% | 0 | 0 |  | 5642 | 0 | 5642 | 0 | 0
FIN | Australia | Support to participants to the regional workshop on refrigeration and air conditioning training programme | Individual | ASP | ASP | REF | 12 | TRA | 14 | A | D |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-03-01 |  | 1994-04-01 | 1994-05-01 | 66800 | 0 | 66800 | 66800 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed |  | 1994
FIN | Singapore | Training workshop on CFC-113 and methyl chloroform substitutes and alternative technologies in ASEAN countries |  | ASP | ASP | REF | 13 | TRA | 15 | A | D |  | 0 |  |  |  | 1994-07-01 |  | 1995-07-01 |  | 1995-12-01 |  | 40000 | 0 | 40000 | 40000 | 100% | 0 | [5 empty] | 0 |  |  |  | 94
FIN | UNEP | Implementation of the PIC Strategy: three thematic meetings on issues related to the implementation of the strategy | Individual | ASP | ASP | REF | 36 | TAS | 44 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-11-01 | 2005-04-01 |  | 2006-01-01 | 2006-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Implementation of the PIC Strategy: technical assistance for other countries not included in the strategy | Individual | ASP | ASP | REF | 36 | TAS | 45 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-03-01 | 2005-04-01 |  | 2006-01-01 | 2007-07-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Implementation of the PIC Strategy: policy assistance and guidance to countries for development of regulations | Individual | ASP | ASP | REF | 36 | TAS | 46 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-01-01 | 2003-10-01 |  | 2007-12-01 | 2007-12-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 |  | 11700 | 0 | 11700 | 0 | 0 |  |  |  | 2005-12-01
FIN | UNEP | Implementation of the PIC Strategy: technical assistance to countries and monitoring the implementation of the strategy | Individual | ASP | ASP | REF | 36 | TAS | 47 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-01-01 | 2005-12-01 |  | 2007-12-01 | 2007-12-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 | 0 |  | 15600 | 0 | 15600 | 0 | 0
FIN | UNEP | Implementation of the PIC strategy: technical assistance to countries and monitoring the implementation of the strategy | Individual | ASP | ASP | REF | 44 | TAS | 51 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2007-01-01 | 2006-12-01 |  | 2007-12-01 | 2008-12-01 | 30000 | -473 | 29527 | 29527 | 100% | 0 | 0 |  | 3900 | -61 | 3839 | 0 | 0
COM | UNEP | Promoting low-global warming potential refrigerants for air-conditioning sectors in high-ambient temperature countries in West Asia | Individual | ASP | ASP | REF | 69 | DEM | 56 | A | I |  | 0 |  | 0 |  | 2013-04-01 | 2013-08-01 | 2014-06-01 |  | 2016-12-01 |  | 155000 | 0 | 155000 | 146737.85 | 94.67% | 8262.15 | 1447.62 | 8262 | 20150 | 0 | 19075.9205 | 1074.0795 | 188.1906 | Brief progress report (actual/planned): - Final Review meeting for the International Technical Review Team is organized (Jan 2016). - International Seminar to release the project findings organized at ASHRAE Conference (Jan 2016). - Consultation with Industry and technology providers about findings and planned activities in next stage of the project is arranged in margins with AHR 2016 Expo (Jan 2016). - Final report is released and circulated to member states, industry and other stakeholders (March 2016) - Final report discussed and acknowledged by ExCom-76 - UNEP, and UNIDO, prepared and submitted stage-II of the project using the findings and consultation process took place during stage-I - Project is completed | Project is completed during 2016
ONG | UNIDO | Promoting low-global warming potential refrigerants for airconditioning sectors in high-ambient temperature countries in West Asia | Individual | ASP | ASP | REF | 69 | DEM | 57 | A | I |  | 0 | 0 |  |  | 2013-04-01 | 2013-08-01 | 2014-06-30 | 2017-05-01 |  |  | 365000 | 0 | 365000 | 339209.76 | 92.93% | 25790.24 | 11082.43 | 25000 | 25550 | 0 | 23745 | 1805 | 775.7701 | - The project was successfully completed and the final report was submitted together with the PRAHA II project concept to the 76th ExCom Meeting. - PRAHA II was approved at the 76th Meeting of the ExCom. '- The findings of PRAHA and other related testing projects; e.g. EGYPRA, US-DOE have been presented at several occasions; e.g. 38th OEWG/Vienna; Gustav Lorenzen conference/Edinburgh; CHEAA International workshop/Ningbo and UNEP network meetings. - A promotional video as well as additional documentation have been prepared targeting the presentation of the project's findings and challenges to a wider audience in a clear and understandable manner. | - The findings of PRAHA and other related testing projects; e.g. EGYPRA, US-DOE was continuously presented; e.g. at the AHR2017 Show in Las Vegas. - Promotional materials in multi-language has been finalized during Q1/2017. |  |  | INV
ONG | UNEP | Promoting alternative refrigerants in air-conditioning for high ambient countries in West Asia (PRAHA-II) | Individual | ASP | ASP | REF | 76 | DEM | 59 | A | I |  | 0 |  | 0 |  | 2016-05-01 | 2016-11-01 | 2017-11-01 | 2017-11-01 |  |  | 375000 | 0 | 375000 | 0 | 0% | 375000 | 0 | 37500 | 48750 | 0 | 0 | 48750 | 0 | Brief progress report (actual/planned): - Project approved at ExCom-76 (May 2016) - Countries consultation and planning meeting organized in margins of OEWG-July 2016 - All prototypes from PRAHA-I are transferred to ORNL (Oak Ridge) - Technical Consultation meetings with ORNL organized (two meetings- June and August) to set the scope of testing under PRAHA-II - Consultation meetings organized with AHRI support the testing process in conjunction with AREP high ambient testing methodology and guidelines - first technical capacity building training organized in cooperation with JRAIA during 28 Nov-2 Dec 2016. 16 experts from high ambient industry attended special workshop on designing and risk assessment of R-32 and A2L refrigerants, field trip to manufacturing facilities in Japan and attending the JRAIA International Symposium on Refrigerants & Environment | Brief progress report (actual/planned): - Contracting arrangements with ORNL and AHRI are concluded and contract is under signature - Support training of 10 experts from high ambient industry at ASHRAE Annual Conference (Jan-2017) for training on new safety and classification standards for refrigerants - Organize International Seminar, in margins of AHR Expo- Jan 2017, in cooperation with UNIDO, US-DOE (ORNL) and AHRI about international high ambient testing programs - Organize 2nd technical capacity building program for training on designing, production and installation with R-290 refrigerants in cooperation with government of China (25 experts from high ambient industry) during April 2017 including special workshop on R-290, field visit to manufacturing facilities and attending UNEP-China/CRAA Technology Round Table Meeting at China Expo 2017
ONG | UNIDO | Promoting alternative refrigerants in air-conditioning for high ambient countries in West Asia (PRAHA-II) | Individual | ASP | ASP | REF | 76 | DEM | 60 | A | I |  | 0 | 0 |  |  | 2016-05-01 | 2016-10-01 | 2018-12-31 | 2019-12-19 |  |  | 325000 | 0 | 325000 | 49197.36 | 15.14% | 275802.64 | 51299.97 | 70000 | 22750 | 0 | 3444 | 19306 | 3591 | - The project was approved at the 76th ExCom Meeting. - During 2nd half of 2016 working arrangements between stakeholders (OEM's, technology providers as well as governments) have been set-up. - A capacity building event on application of HFC-32 for an extended group of countries was conducted in Japan first week of December; arranged in cooperation with the Japanese Refrigeration Association (JRAIA). | - PRAHA-II outlook was presented at the AHR2017 Show in Las Vegas; at which also technology providers were consulted on recent development of low-GWP refrigerants. - A capacity building event on R-290 has been planned in China 2nd week of April; in cooperation with government of China as well as CHEAA. The number of countries attending this event has increased from the initial PRAHA-I countries to also include Egypt, Pakistan, Tunisia and Vietnam. |  |  | NON-INV
FIN | UNEP | Regional workshop for Asia and the Pacific | Individual | ASP | ASP | SEV | 04 | TRA | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-08-01 | 1991-11-01 |  | 1991-11-01 | 1992-12-01 | 246000 | 0 | 246000 | 246000 | 100% | 0 | 0 |  | 31980 | 0 | 31980 | 0 | 0
FIN | Australia | Support for delegates from six Asian countries to participate in regional workshop on alternatives to CFC | Individual | ASP | ASP | SEV | 07 | TRA | 06 | A | D |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1993-06-01 |  | 1993-06-01 | 1993-07-01 | 39394 | -4420 | 34974 | 34974 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed |  | 1992
FIN | Australia | Support to ASEAN regional conference on CFC and halons | Individual | ASP | ASP | SEV | 08 | TRA | 08 | A | D |  | 0 | 0 | 0 | 0 | 1992-10-01 |  | 1993-10-01 |  | 1993-10-01 | 1993-10-01 | 4420 | -103 | 4317 | 4317 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed |  | 1993
FIN | UNEP | Workshop for small and medium size enterprises on management of ODS phase-out | Individual | ASP | ASP | SEV | 12 | TRA | 13 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-01-01 | 1995-03-01 |  | 1995-02-01 | 1995-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0
FIN | UNEP | ODS officers network for Asia and the Pacific (1995) | Individual | ASP | ASP | SEV | 16 | TAS | 17 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-04-01 | 1996-03-01 |  | 1996-03-01 | 2000-03-01 | 62000 | 0 | 62000 | 62000 | 100% | 0 | 0 |  | 8060 | 0 | 8060 | 0 | 0
FIN | UNEP | Networking and Training (1996) | Individual | ASP | ASP | SEV | 19 | TAS | 21 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1997-05-01 |  | 1996-12-01 | 1999-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNEP | West Asian Network (1996) | Individual | ASP | ASP | SEV | 19 | TAS | 22 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1997-05-01 |  | 1997-05-01 | 1999-12-01 | 169200 | -24323 | 144877 | 144877 | 100% | 0 | 0 |  | 21996 | -3161.99 | 18834.01 | 0 | 0
FIN | UNEP | Regional workshop on monitoring and control of ODS consumption for West Asia | Individual | ASP | ASP | SEV | 19 | TRA | 20 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1997-05-01 |  | 1997-12-01 | 1999-03-01 | 80000 | -19056 | 60944 | 60944 | 100% | 0 | 0 |  | 10400 | -2477.28 | 7922.72 | 0 | 0
FIN | UNEP | West Asian Region Network (1997) | Individual | ASP | ASP | SEV | 21 | TAS | 23 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-12-01 | 110000 | 0 | 110000 | 110000 | 100% | 0 | 0 |  | 14300 | 0 | 14300 | 0 | 0
FIN | UNEP | South Asian Region Network (1997) | Individual | ASP | ASP | SEV | 21 | TAS | 24 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-12-01 | 199000 | -109950 | 89050 | 89050 | 100% | 0 | 0 |  | 25870 | -14293.5 | 11576.5 | 0 | 0
FIN | UNEP | Asia Regional Networks for SEAP and East Asia (1998) | Individual | ASP | ASP | SEV | 23 | TAS | 25 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-12-01 |  | 1998-12-01 | 1999-12-01 | 209000 | -48604 | 160396 | 160396 | 100% | 0 | 0 |  | 27170 | -6318.52 | 20851.48 | 0 | 0
FIN | UNEP | West Asian regional network (1998) | Individual | ASP | ASP | SEV | 23 | TAS | 26 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-12-01 |  | 1998-12-01 | 1999-12-01 | 115000 | 0 | 115000 | 115000 | 100% | 0 | 0 |  | 14950 | 0 | 14950 | 0 | 0
FIN | UNEP | Asia Regional Networks (South-East and Pacific and South Asia) | Individual | ASP | ASP | SEV | 26 | TAS | 27 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2001-12-01 | 209000 | 0 | 209000 | 209000 | 100% | 0 | 0 |  | 27170 | 0 | 27170 | 0 | 0
FIN | UNEP | West Asian Region Network (1999) | Individual | ASP | ASP | SEV | 26 | TAS | 28 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 1999-12-01 | 115000 | 0 | 115000 | 115000 | 100% | 0 | 0 |  | 14950 | 0 | 14950 | 0 | 0
FIN | UNEP | Asia and the Pacific Regional networks (South East Asia and Pacific and South Asia) (2000) | Individual | ASP | ASP | SEV | 29 | TAS | 30 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2001-01-01 | 2000-12-01 |  | 2000-12-01 | 2005-12-01 | 219450 | -18941 | 200509 | 200509 | 100% | 0 | 0 |  | 28529 | -2462.33 | 26066.67 | 0 | 0
FIN | UNEP | West Asian region network (2000) | Individual | ASP | ASP | SEV | 29 | TAS | 32 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2001-01-01 | 2005-12-01 | 120750 | -15000 | 105750 | 105750 | 100% | 0 | 0 |  | 15698 | -1950 | 13748 | 0 | 0
FIN | Sweden | Regional workshop on control and monitoring of ODS consumption for the South East Asia and the Pacific region | Individual | ASP | ASP | SEV | 29 | TRA | 31 | A | I |  | 0 |  | 0 |  | 1999-11-01 | 2000-04-01 | 2000-12-01 |  | 2001-02-01 | 2002-05-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 |  |  | 8450 | 0 | 8450 | 0 | 0 | Regional Workshop on Control and Monitoring of ODS Consumption for the Southeast Asia/Pacific Region (funded with equal bilateral contributions from Sweden and Japan and implemented through UNEP) was held 22-27 May 2000 and was attended by ozone and customs officers from ten countries in the region. The participating countries developed a joint set of declarations and drafted national action plans for further work in their respective country. The report from the workshop was prepared by Sweden in February 2001. The project completion report prepared in coordination with UNEP was submitted 1 May 2002. The project was financially completed 27 May 2002. |  | 1999
FIN | Japan | Regional workshop on control and monitoring of ODS consumption for the South East Asia and the Pacific region | Individual | ASP | ASP | SEV | 29 | TRA | 33 | A | I |  | 0 |  | 0 |  | 1999-11-01 | 2000-02-01 | 2000-12-01 |  | 2001-02-01 | 2002-06-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 | 0 | 7150 | 0 | 7150 | 0 | 0 | Project financially completed in June 2002. |  | 1999
FIN | Japan | Regional workshop on monitoring and control of ODS consumption for the South Asia region | Individual | ASP | ASP | SEV | 29 | TRA | 34 | A | I |  | 0 |  | 0 |  | 1999-11-01 | 2000-07-01 | 2001-06-01 |  | 2001-08-01 | 2002-06-01 | 95000 | 0 | 95000 | 95000 | 100% | 0 | 0 | 0 | 12350 | 0 | 12350 | 0 | 0 | Project financially completed in June 2002. |  | 1999
FIN | UNEP | West Asia military ODS workshop (to be held in conjunction with a global military environmental conference) | Individual | ASP | ASP | SEV | 30 | TRA | 35 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-01-01 | 2001-04-01 |  | 2001-05-01 | 2003-06-01 | 150000 | -15122 | 134878 | 134878 | 100% | 0 | 0 |  | 19500 | -1965.86 | 17534.14 | 0 | 0
FIN | UNEP | West Asian regional network (2001) | Individual | ASP | ASP | SEV | 32 | TAS | 40 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2003-06-01 | 124000 | -15001 | 108999 | 108999 | 100% | 0 | 0 |  | 16120 | -1950.13 | 14169.87 | 0 | 0
FIN | UNEP | South East Asia and the Pacific and South Asia regional networks (2001) | Individual | ASP | ASP | SEV | 32 | TAS | 48 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2002-06-01 | 2003-06-01 | 225000 | -20468 | 204532 | 204532 | 100% | 0 | 0 |  | 29250 | -2660.84 | 26589.16 | 0 | 0
FIN | Japan | Assistance for the implementation of strategic planning of the Multilateral Fund to promote compliance with the Montreal Protocol in the Asia and Pacific region | Individual | ASP | ASP | SEV | 34 | TAS | 41 | A | I |  | 0 |  | 0 |  | 2001-07-01 | 2001-10-01 | 2002-08-01 |  | 2003-05-01 | 2004-09-01 | 148500 | 0 | 148500 | 148500 | 100% | 0 | 0 | 0 | 19305 | 0 | 19305 | 0 | 0 | Project completed in May 2003. Balance of 25,000 USD transferred to Phase II for partly covering activities in Mongolia |  | 2001 |  | Non-Investment
FIN | Sweden | Regional cooperation for monitoring and control of ODS consumption | Individual | ASP | ASP | SEV | 34 | TAS | 42 | A | I |  | 0 |  | 0 |  | 2001-07-01 | 2002-03-01 | 2005-04-01 |  | 2006-12-01 | 2008-05-01 | 250000 | 155818 | 405818 | 405818 | 100% | 0 | 0 | 0 | 0 | 20256 | 20256 | 0 | 0 | The final financial report was received from UNEP in May 2008. The final report reported a balance of USD 49,926. In July 2008 the MLF confirmed the return of the same amount as part of the Swedish contribution to the MLF. |  | 2002
FIN | Japan | Assistance for the implementation of strategic planning of the Multilateral Fund to promote compliance with the Montreal Protocol in the Asia and Pacific region (phase 2) | Individual | ASP | ASP | SEV | 38 | TAS | 49 | A | I |  | 0 |  | 0 |  | 2002-11-01 | 2003-06-01 | 2003-11-01 |  | 2004-03-01 | 2005-11-01 | 125000 | 0 | 125000 | 125000 | 100% | 0 | 0 | 0 | 16250 | 0 | 16250 | 0 | 0 | Mongolia: Public awareness and IEC activities; Task Force Meeting China/Mongolia August 2003 / Iran: 15-02-04 National Consultation Meeting. Some funds were also used for building urgent capacity in the two new Parties Afghanistan and Bhutan as part of UN |  | 2002 |  | Non-Investment
FIN | Australia | Additional support for the regional strategy for 11 Article 5 countries in the Pacific (PIC strategy) | Individual | ASP | ASP | SEV | 50 | TAS | 52 | A | I |  | 0 |  | 0 |  | 2006-11-01 | 2007-07-01 | 2007-11-01 |  | 2011-03-01 | 2012-05-01 | 115000 | 0 | 115000 | 115000 | 100% | 0 | 0 | 0 | 14950 | 0 | 14950 | 0 | 0 | completed |  | 2007
FIN | Singapore | Regional methyl chloroform elimination programme for ASEAN countries |  | ASP | ASP | SOL | 11 | TAS | 12 | A | D |  | 0 |  |  |  | 1993-11-01 |  | 1995-11-01 |  | 1995-03-01 |  | 31976 | 0 | 31976 | 31976 | 100% | 0 | [5 empty] | 0 |  |  |  | 93
FIN | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | ASP | BAH | PHA | 50 | INV | 16 | N | I | CFC | 38.4 | 38.4 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2008-12-01 |  | 2008-12-01 | 2013-05-01 | 272500 | 0 | 272500 | 272500 | 100% | 0 | 0 | 0 | 20437 | 0 | 20437 | 0 | 0 | Financially completed in 2013. |  | 2006 |  | Investment
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-year | ASP | BAH | PHA | 50 | TAS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2010-06-01 | 2008-07-01 |  | 2014-12-01 | 2015-12-01 | 210000 | -120000 | 90000 | 90000 | 100% | 0 | 0 |  | 27300 | -15600 | 11700 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | BAH | PHA | 55 | PRP | 19 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2013-08-01 | 2014-05-01 | 105000 | -25917 | 79083 | 79083 | 100% | 0 | 0 |  | 13650 | -3369.21 | 10280.79 | 0 | 0
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | ASP | BAH | PHA | 55 | PRP | 20 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2009-04-01 | 2009-07-31 |  | 2012-12-01 | 2012-12-01 | 45000 | -291 | 44709 | 44708.92 | 100% | 0.08 | 0 |  | 3375 | -22 | 3353 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNDP | Terminal phase-out management plan (second tranche) | Multi-Year | ASP | BAH | PHA | 59 | INV | 22 | N | I | CFC | 20.3 | 20.3 | 0 | 0 | 2009-11-01 | 2011-01-01 | 2011-11-01 |  | 2012-12-01 | 2014-03-01 | 40000 | -6846 | 33154 | 33154 | 100% | 0 | 0 | 0 | 3000 | -513.45 | 2486.55 | 0 | 0 | Financially completed in 2014. | Completed in 2012. Some final payments pending. | 2009 |  | Investment
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | ASP | BAH | PHA | 59 | TAS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-12-01 | 2011-11-01 |  | 2014-12-01 | 2015-12-01 | 95000 | 0 | 95000 | 0 | 0% | 95000 | 95000 | 0 | 12350 | 0 | 0 | 12350 | 12350
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (phase-out of HCFC-22 from the manufacturing of central air conditioning and window air conditioning at Awal Gulf manufacturing company) | Multi-Year | ASP | BAH | PHA | 68 | INV | 27 | A | I | HCFC | 3.7 | 0 |  |  | 2012-12-01 | 2013-12-01 | 2014-12-31 | 2018-03-01 |  |  | 387855 | 0 | 387855 | 9622.17 | 2.481% | 378232.83 | 151767.5 | 150000 | 27150 | 0 | 674 | 26476 | 10623.725 | Supplier visited beneficiary premises and some adjustments to the list of equipment were suggested. The proposal was reviewed and bidders were requested to provide a quotation for the new items. The offers were evaluated and an amendment to the initial contract was subsequently issued. Equipment was delivered and installation and training completed. Activities planned but not implemented, reasons and strategy: No Any impact on project completion date: Yes If yes, implications: selection of alternative technology to be postponed. | Terms of reference for prototyping and testing prepared Contract to be issued shortly. |  |  | INV |  | To request the submission of additional status report to the 79th meeting to monitor the procurement and/or delivery of the equipment.
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (reclamation facility) | Multi-Year | ASP | BAH | PHA | 68 | TAS | 26 | A | I |  | 0 | 0 |  |  | 2012-12-01 | 2013-12-01 | 2020-12-31 | 2020-12-01 |  |  | 161600 | 0 | 161600 | 17521.17 | 10.84% | 144078.83 | 122355.5 | 50000 | 11312 | 0 | 1226 | 10086 | 8564.885 | Equipment arrived in Bahrain and was delivered to the NOU. | Awaiting selection of beneficiary company to conduct training. |  |  | INV
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) (policy, refrigeration servicing, monitoring and verification) | Multi-year | ASP | BAH | PHA | 68 | TAS | 28 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-09-01 | 2014-12-01 | 2017-12-01 |  |  | 120000 | 0 | 120000 | 4005 | 3.338% | 115995 | 66588 | 11599.5 | 15600 | 0 | 520.65 | 15079.35 | 8656.44 | Brief progress report (actual/planned): Implementation is progressing as planned with some delays in the certification program. - Legal arrangements (actual/planned): two legal contracts signed; one with Supreme Council for Environment (SCE) for the E-Licensing system & one with Bahrain Society of Engineers (BSE) for the rest of activities as requested by the government of Bahrain - Initial stages of project implementation (actual/planned): all initial stages completed including the contracting arrangements, planning of activities and kick-off of all programs - Intermediate goals achieved (actual/planned): Customs training achieved a target of 80 local officers trained plus 15 master trainers, national regulatory outreach campaign is ongoing with one training workshop conducted and three more to follow. Other two technical committees are progressing to finalize the national certification scheme and review local standards. E-Licensing system is developed and under testing before launch in 2017 - Project completion and follow up: Tranche related activities are expected to be completed by end of 2017 - All funds disbursed (yes/no): No - Project ongoing & delayed Any delay? (yes/no): Ongoing with some delays in the Certification program due to the movement of the training/certification mandate from Ministry of Labor to another local entity - If Yes, will delay have impact on project completion date (yes/no): No - AO136Any ongoing problems (yes/no): No | Brief progress report (actual/planned): - Agreement is made with international association to assist Bahrain to build national certification program for technicians. Plans is to start piloting the program by end of 2017 - Final payment and contract with SCE is concluded and all payments completed - Technical and financial report from BSE is received and subsequent payments processed. Contract to be completed and closed before end of 2017 - Local technical and legal team are working on developing the bylaws to support the national certification program and activities related to prevention of emissions and enforcement of R&R practices
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) (policy, refrigeration servicing, monitoring and verification) | Multi-year | ASP | BAH | PHA | 75 | TAS | 29 | A | I |  | 2.7 |  | 0 |  | 2015-11-01 |  | 2016-12-01 | 2017-12-01 |  |  | 145000 | 0 | 145000 | 0 | 0% | 145000 | 0 | 14500 | 18850 | 0 | 0 | 18850 | 0 | Brief progress report (actual/planned): Funds of 2nd tranche only released at 2nd half of 2016. UNEP and SCE drafted the TORs for the 2nd tranche • Legal arrangements(actual/planned): No • First mission (actual/planned): CAP team in West Asia is based in Bahrain allowing closer interaction and more support to HPMP activities • TOR completed(actual/planned): TORs for the project implementation is drafted • All funds disbursed (yes/no): No • Any delay? (yes/no): delay in starting 2nd tranche due to delay in reaching the 20% of first tranche because of pending payments for UNIDO’s shipment to the investment component. Also delay in some of tranche activities while led to delay in planning connected activities under tranche-2 • If Yes, reasons for delay & action plan to resolve: delay in starting 2nd tranche due to delay in reaching the 20% of first tranche because of pending payments for UNIDO’s shipment to the investment component. • If Yes, will delay have impact on project completion date (yes/no): Yes and submission of 3rd tranche will be delayed accordingly • If Yes, is any action required by ExCom: NO | Brief progress report (actual/planned): - 2nd tranche activities are continuation of 1st tranche of HPMP - New contract with SCE and BSE are under development and will be signed before mid of 2017 based on progress of tranche which is about to be completed - Resources under tranche-2 are already planned for immediate use once new contracts signed to support work started at first tranche including contract with international association to monitor and evaluate the certification program, contract with local training institute for training and certification implementation, national training program on the new bylaws to be issued within 2nd half of 2017 and the launch and operation of the E-Licensing system. |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor the signing of the agreement by the Government and UNEP.
FIN | UNDP | Project preparation in refrigeration recycling | Individual | ASP | BAH | REF | 21 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-12-01 | 2002-03-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | ASP | BAH | REF | 22 | TAS | 04 | A | I | CFC | 20.5 | 20.5 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1999-06-01 | 2001-12-01 | 242000 | -2849 | 239151 | 239151 | 100% | 0 | 0 | 0 | 31460 | -370 | 31090 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNEP | Implementation of the RMP: train the trainers programme in the refrigeration sector | Individual | ASP | BAH | REF | 26 | TRA | 05 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 2000-05-01 | 1999-12-01 |  | 2001-12-01 | 2001-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 |  | 5850 | 0 | 5850 | 0 | 0
FIN | UNEP | Implementation of the RMP: customs training | Individual | ASP | BAH | REF | 26 | TRA | 06 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 2000-12-01 | 2000-05-01 |  | 2001-12-01 | 2003-10-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 |  |  |  | 2001-05-01
FIN | UNDP | Preparation of two project proposals in the commercial refrigeration subsector | Individual | ASP | BAH | REF | 27 | PRP | 08 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-04-01 | 2004-01-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2000. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Al-Jazira Cooling and Heating Factory | Individual | ASP | BAH | REF | 29 | INV | 09 | A | I | CFC | 10.7 | 10.7 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2004-12-01 | 2011-12-01 | 173835 | 0 | 173835 | 173835 | 100% | 0 | 0 | 0 | 22598.55 | 0 | 22598.55 | 0 | 0 | Completed in 2004. Financially completed in 2011. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Awal Refrigeration and Air Conditioning | Individual | ASP | BAH | REF | 29 | INV | 10 | A | I | CFC | 6.3 | 6.3 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2004-12-01 | 2006-06-01 | 224478 | -51106 | 173372 | 173372 | 100% | 0 | 0 | 0 | 29182.14 | -6644 | 22538.14 | 0 | 0 | Completed in 2004. Financially completed in 2006. |  | 1999 |  | Investment
FIN | UNDP | Project preparation for a refrigerant management plan update | Individual | ASP | BAH | REF | 43 | PRP | 13 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-07-01 | 2005-02-01 | 2005-03-01 |  | 2006-12-01 | 2009-07-01 | 24000 | -1463 | 22537 | 22537 | 100% | 0 | 0 | 0 | 1800 | -109.73 | 1690.275 | -0.005 | 0 | Completed in 2006.Financially completed in 2009. |  | 2004 |  | Investment
FIN | UNIDO | Preparation for HCFC phase-out investment activities (air conditioning sector) | Individual | ASP | BAH | REF | 60 | PRP | 23 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-08-01 | 2011-04-30 |  | 2012-12-01 | 2012-12-01 | 30000 | -254 | 29746 | 29746.36 | 100% | -0.36 | 0 |  | 2250 | -19 | 2231 | 0 | 0 | FIN
FIN | UNEP | Country programme preparation | Individual | ASP | BAH | SEV | 12 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-06-01 | 1995-06-01 |  | 1996-06-01 | 1999-02-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Establishment of a National Ozone Office | Individual | ASP | BAH | SEV | 20 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-05-01 | 1999-10-01 |  | 2000-03-01 | 2001-03-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 |  | 8580 | 0 | 8580 | 0 | 0 |  |  |  | 2000-03-01
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | ASP | BAH | SEV | 31 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2000-07-01 | 2001-09-01 | 2002-08-01 |  | 2003-12-01 | 2004-12-01 | 44000 | 0 | 44000 | 44000 | 100% | 0 | 0 |  | 5720 | 0 | 5720 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project: phase 3 | Individual | ASP | BAH | SEV | 41 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-09-01 | 2005-12-01 |  | 2005-12-01 | 2006-12-01 | 57200 | 0 | 57200 | 57200 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | ASP | BAH | SEV | 47 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-07-01 | 2007-12-01 |  | 2007-12-01 | 2008-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase V) | Individual | ASP | BAH | SEV | 53 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-08-01 | 2009-11-01 |  | 2010-12-01 | 2012-04-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase VI) | Individual | ASP | BAH | SEV | 60 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2011-01-01 | 2011-12-01 |  | 2012-12-01 | 2013-12-01 | 52500 | 0 | 52500 | 52500 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of institutional strengthening project (phase VII: 1/2013-12/2014) | Individual | ASP | BAH | SEV | 68 | INS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2014-11-01 | 2014-11-01 |  | 2016-04-01 |  | 60000 | 0 | 60000 | 30000 | 50% | 30000 | 30000 | 30000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Implementation of phase complete and reports received. All payments complete and next phase was approved in May-16. Legal arrangements (actual/planned): closed Initial stages of project implementation (actual/planned): NOU submitted final reports end of Dec-16 Intermediate goals achieved (actual/planned): project complete and data reporting submitted on time Project completion and follow up: ISP completed. Audit report received. First disbursement date (actual/planned): Nov-14 All funds disbursed (yes/no): Yes. Project ongoing & delayed Any delay? (yes/no): COM, overall delay faced as justified by country in final terminal report If Yes, will delay have impact on project completion date (yes/no): n/a Any ongoing problems (yes/no): No | Project is completed but the status is COM as the final terminal report received Jan-17. The Expenditure is still to be cleared in UMOJA
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | ASP | BAH | SEV | 75 | TAS | 30 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-12-01 | 2016-12-01 | 2017-12-01 |  |  | 60000 | 0 | 60000 | -0.46 | -0.0007667% | 60000.46 | 60000.46 | 6000.046 | 7800 | 0 | -0.0598 | 7800.0598 | 7800.0598 | Brief progress report (actual/planned): TORs developed for the work under the survey, consultation meeting with NOU is arranged in margins of network meeting, detailed work-plan and sample documentation and forms sent to country for review and clearance, training for national expert arranged through regional workshop organized in back-to-back with the network meeting. Consultation meetings are organized with country and local experts to orient about the survey requirements. Another consultation meeting orgnized (for both surveys of Bahrain and Kuwait) • Legal arrangements(actual/planned): Legal instrument signed • Initial stages of project implementation(actual/planned): Started and all preparatory work arranged by UNEP • Intermediate goals achieved (actual/planned): Start of data collection delayed due to delay in finding the local consultant and forming the survey team • Project completion and follow up: Planned by mid of 2017 • First disbursement date (actual/planned): Paid during 4th quarter of 2016 • All funds disbursed (yes/no): No • Any delay?(yes/no): Yes • If Yes, reasons for delay & action plan to resolve: Due to delay in finding the local consultant and forming the survey team • If Yes, will delay have impact on project completion date (yes/no): Yes, completion planned by mid of 2017 instead of end of 2016 | Brief progress report (actual/planned): - National survey teams formed at end of 2016 and started collecting data - Several consultation meetings to review collected data orgnized with presence of UNEP - Data collection completed and NOU is currently validating the collected data - Final report under preparation and will be submitted by ExCom-79
ONG | UNIDO | Survey of ODS alternatives at the national level | Individual | ASP | BAH | SEV | 75 | TAS | 31 | A | I |  | 0 | 0 |  |  | 2015-11-01 | 2016-12-01 | 2017-12-01 | 2017-05-01 |  |  | 50000 | 0 | 50000 | 5135.59 | 10.27% | 44864.41 | 5146.53 | 35000 | 4500 | 0 | 0 | 4500 | 463.1877 | A meeting was held between the NOU and implementing agencies UNEP (lead) and UNIDO. A work plan was subsequently submitted to the NOU. ToR for the recruitment of consultant to conduct the survey has been prepared by UNIDO and handed to the NOU. Consultants were selected and recruited. Survey underway. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Late feedback from NOU. Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | The survey was conducted and will be submitted to 79th ExCom. Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | NON-INV
ONG | UNEP | Extension of institutional strengthening project (phase VIII: 5/2016-4/2018) | Individual | ASP | BAH | SEV | 76 | INS | 32 | A | I |  | 0 |  | 0 |  | 2016-05-01 |  | 2018-04-01 | 2018-04-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 25000 | 8500 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Newly approved Legal arrangements (actual/planned): SSFA drafting delayed due to country outstanding input, which was received by Dec-16. Initial stages of project implementation (actual/planned): NOU continued new cycle implementation during gap of signing legal instrument; Intermediate goals achieved (actual/planned): A7 data reporting completed on time; ozone national day celebration conducted; NOU supervised implementation of other MP projects; licensing system established and implemented Project completion and follow up: Audit report received for previous phase First disbursement date (actual/planned): none All funds disbursed (yes/no): no, awaiting legal instrument to be signed Project ongoing & delayed Any delay? (yes/no): ONG If Yes, will delay have impact on project completion date (yes/no): n/a Any ongoing problems (yes/no): No | Brief progress report (actual/planned): Implementation of new cycle on going Legal arrangements (actual/planned): SSFA signed Initial stages of project implementation (actual/planned): On going Intermediate goals achieved (actual/planned): country signed contract and continues to supervise work of other projects such as ODS alternatives survey Project completion and follow up: n/a First disbursement date (actual/planned): Mar-17 All funds disbursed (yes/no): No Project ongoing & delayed Any delay? (yes/no): ONG If Yes, will delay have impact on project completion date (yes/no): n/a Any ongoing problems (yes/no): No
FIN | UNIDO | Training and awareness workshop in the solvents and process agents (CTC and TCA) sector | Individual | ASP | BAH | SOL | 45 | TAS | 14 | A | I | CTC TCA | 1.7 | 1.7 |  |  | 2005-04-01 | 2006-07-01 | 2006-04-01 |  | 2007-12-01 | 2009-05-01 | 60000 | -15868 | 44132 | 44132.17 | 100% | -0.17 | 0 |  | 5400 | -1428 | 3972 | 0 | 0 | FIN |  |  | 2007-07-01 | INV
CLO | UNDP | Project preparation for a terminal phase-out management plan in the servicing sector | Individual | LAC | BAR | PHA | 54 | PRP | 14 | A | I | CFC | 0 | 0 | 0 | 0 | 2008-04-01 |  | 2009-03-01 |  |  | 2010-12-01 | 15000 | -15000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 1125 | -1125 | 0 | 0 | 0 | TPMP will not be prepared for Barbados and funds should be returned to the MLF. Project therefore canceled. Funds to be returned in 2011. |  | 2008 |  | Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan in the servicing sector | RMP | LAC | BAR | PHA | 54 | PRP | 17 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-06-01 | 2009-03-01 |  | 2010-10-01 | 2011-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | BAR | PHA | 55 | PRP | 18 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-01-01 | 2009-07-01 |  | 2013-12-01 | 2014-12-01 | 85000 | -33141 | 51859 | 51859 | 100% | 0 | 0 |  | 11050 | -4308.33 | 6741.67 | 0 | 0
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | LAC | BAR | PHA | 69 | INV | 21 | N | I | HCFC | 0 | 0 | 0 | 0 | 2013-04-01 |  | 2016-04-01 | 2017-04-01 |  |  | 50000 | 0 | 50000 | 0 | 0% | 50000 | 0 | 20000 | 4500 | 0 | 0 | 4500 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): PRODOC signed in october 2016. Planning of activities was started. Prodoc signed (actual/planned, yes/no and date):Yes, october 2016 Missions undertaken (actual/planned):0 of 0 TOR for consultants/subcontracts completed (actual/planned): 0 of 0 Contract/PO/MOA agreements signed: 0 of 0 First disbursement date (actual/planned): Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:Signing of the ProDoc has been delayed for a very long time. Activities are starting up now | TORs for experts being developed | 2013 |  | Investment |  | To request the submission of additional status report to the 79th meeting to monitor the signing of the agreement by the Government and UNDP.
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | LAC | BAR | PHA | 69 | TAS | 22 | A | I |  | 0 |  | 0 |  | 2013-04-01 | 2013-12-01 | 2016-04-01 | 2017-12-01 |  |  | 74000 | 0 | 74000 | 35374.75 | 47.8% | 38625.25 | 30000 | 3862.525 | 9620 | 0 | 4598.7175 | 5021.2825 | 3900 | Brief progress report (actual/planned): Mission in Mar-16 to follow-up on progress. Capacity building and Policy components contracts awarded in Sep-16. Curriculum review, development of guides for training of RAC technicians are progressing. Assignment of quotas until 2020. Policy on green building to start in 2nd half of 2017 ___ Legal arrangements (actual/planned): Dec-13/Oct-13___ First mission (actual/planned): ___ TOR completed (actual/planned): ___ First disbursement date (actual/planned): Dec-13/Oct-13___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): yes___ If Yes, reasons for delay & action plan to resolve: changes in government administrative processes have delayed national bidding processes. Mission undertook in Mar-16 to discuss progress___ If Yes, will delay have impact on project completion date (yes/no): yes.___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): SSFA expired. New draft to be discusssed with country in 1Q of 2017. Progress and financial reports in relation to first allotment sent to UN Environment. Reprogramming of funds in 2017 ___ Legal arrangements (actual/planned): not yet signed/May-17___ First mission (actual/planned): ___ TOR completed (actual/planned): ___ First disbursement date (actual/planned): not yet disbursed/Jun-2017___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): yes___ If Yes, reasons for delay & action plan to resolve: changes in government administrative processes have delayed implementation. Periodic follow-up with country___ If Yes, will delay have impact on project completion date (yes/no): yes. Completion date revised to Dec-17 to allow signature of new SSFA and expenditure of funds___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___ |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor the awarding of contracts for the HPMP.
ONG | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Individual | LAC | BAR | PHA | 75 | TAS | 25 | A | I |  | 0 |  | 0 |  | 2015-11-01 |  | 2017-03-01 | 2017-06-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 3000 | 3900 | 0 | 0 | 3900 | 0 | Brief progress report (actual/planned): Verification Consultant hired in Nov-16 ___ Legal arrangements (actual/planned): ___ First mission (actual/planned): ---/Dec-16___ TOR completed (actual/planned): Jun-16/Sep-16___ First disbursement date (actual/planned): --/Oct-16___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): no___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): no.___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): Mission took place in Jan-17. Information collected and draft report sent to country for comments. Report with comments from NOU sent to UN Environment for review in Feb-17. Review is undergoing. ___ Legal arrangements (actual/planned): ___ First mission (actual/planned): Jan-17/Dec-16___ TOR completed (actual/planned): Jun-16/Sep-16___ First disbursement date (actual/planned): Jan-17/Oct-16___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): no___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): no.___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___
FIN | UNIDO | Preparation of project for retrofitting in all ice-making systems, icebin compressor systems, blast freezers, cold storage and chiller rooms | Individual | LAC | BAR | REF | 15 | PRP | 02 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-06-01 | 1995-06-01 |  | 1995-12-01 | 1996-05-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | FIN
FIN | UNIDO | CFC-recovery, recycling and training in refrigeration | RMP | LAC | BAR | REF | 18 | TAS | 04 | A | I | CFC | 14 | 14 |  |  | 1995-11-01 | 1996-09-01 | 1998-11-01 |  | 1997-06-01 | 2000-07-01 | 165170 | -222 | 164948 | 164948 | 100% | 0 | 0 |  | 21472 | -63 | 21409 | 0 | 0 | FIN
FIN | UNEP | Development of RMP | RMP | LAC | BAR | REF | 30 | PRP | 06 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2001-04-01 |  | 2004-05-01 | 2005-07-01 | 30000 | -7982 | 22018 | 22018 | 100% | 0 | 0 |  | 3900 | -1037.66 | 2862.34 | 0 | 0
FIN | UNDP | Formulation of investment components of the RMP | Individual | LAC | BAR | REF | 39 | PRP | 07 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2005-07-01 | 2006-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1125 | 0 | 1125 | 0 | 0 | Completed in 2005. Financially completed in 2006. |  | 2003 |  | Investment
FIN | UNDP | Project preparation for the formulation of refrigerant management plan for end-users | Individual | LAC | BAR | REF | 42 | PRP | 09 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2004-10-01 |  | 2005-07-01 | 2006-12-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 | 0 | 0 | 600 | 0 | 600 | 0 | 0 | Completed in 2005. Financially completed in 2006. |  | 2004 |  | Investment
FIN | UNEP | Implementation of the RMP: import-export licensing system and establishment of refrigeration and air-conditioning association | Individual | LAC | BAR | REF | 43 | TAS | 10 | A | I | CFC | 5.2 | 0 | 0 | 0 | 2004-07-01 | 2005-03-01 | 2006-12-01 |  | 2011-03-01 | 2012-03-01 | 78000 | 0 | 78000 | 78000 | 100% | 0 | 0 |  | 10140 | 0 | 10140 | 0 | 0
FIN | UNDP | Implementation of the RMP: technical assistance project to the MAC and end-users sectors | RMP-Component | LAC | BAR | REF | 43 | TAS | 11 | N | I | CFC | 11.4 | 11.4 | 0 | 0 | 2004-07-01 | 2010-11-01 | 2006-12-01 |  | 2011-12-01 | 2014-02-01 | 172611 | -2925 | 169686 | 169686 | 100% | 0 | 0 | 0 | 15535 | -263.25 | 15271.75 | 0 | 0 | Financially completed in 2014. | Tools and equipment delivered to beneficiaries. Final invoices pending. | 2004 |  | Investment
FIN | UNDP | Implementation of the RMP: monitoring the activities in the RMP | RMP-Component | LAC | BAR | REF | 43 | TAS | 12 | N | I | CFC | 1.7 | 1.7 | 0 | 0 | 2004-07-01 |  | 2006-12-01 |  | 2013-12-01 | 2014-05-01 | 26150 | -26150 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 2354 | -2354 | 0 | 0 | 0 | Financially completed in 2014. | Completed in 2013. Project team is working in the PCR and the Financially closure of the Project. | 2004 |  | Non-Investment
FIN | UNEP | Country programme preparation | Individual | LAC | BAR | SEV | 09 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-05-01 | 1994-06-01 |  | 1994-12-01 | 1995-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Establishment of the Ozone Unit | Individual | LAC | BAR | SEV | 15 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1996-02-01 | 1997-12-01 |  | 1998-12-01 | 1999-10-01 | 136000 | -1050 | 134950 | 134950 | 100% | 0 | 0 |  | 17680 | -136.5 | 17543.5 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project | Individual | LAC | BAR | SEV | 26 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-10-01 | 2000-12-01 |  | 2005-12-01 | 2005-12-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 |  | 11700 | 0 | 11700 | 0 | 0
FIN | UNEP | Extension of Institutional strengthening project (phase III) | Individual | LAC | BAR | SEV | 42 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2005-12-01 | 2005-04-01 |  | 2007-11-01 | 2009-07-01 | 58500 | -560 | 57940 | 57940 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase III, year 2) | Individual | LAC | BAR | SEV | 46 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2008-01-01 | 2007-07-01 |  | 2011-03-01 | 2012-06-01 | 58500 | 0 | 58500 | 58500 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase IV) | Individual | LAC | BAR | SEV | 61 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-03-01 | 2012-06-01 |  | 2013-07-01 | 2013-12-01 | 117000 | -2760 | 114240 | 114240 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase V: 1/2013-12/2014) | Individual | LAC | BAR | SEV | 68 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-08-01 | 2015-02-01 |  | 2015-12-01 | 2016-12-01 | 117000 | 0 | 117000 | 117000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | LAC | BAR | SEV | 74 | TAS | 23 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-08-01 | 2016-05-01 | 2017-06-01 |  |  | 40000 | 0 | 40000 | 17312.62 | 43.28% | 22687.38 | 20717.38 | 2268.738 | 5200 | 0 | 2250.6406 | 2949.3594 | 2693.2594 | Brief progress report (actual/planned): SSFA signed in Aug-16. Regional Consultant selected and contract signed in Jul-16. National consultant hired in Aug-16. Stekeholders meeting held in Sep-16. Collection of information completed in Nov-16. Report sent in Dec-16 ___. Legal arrangements (actual/planned): Aug-16/Dec-15 ___ First mission (actual/planned):Dec-16/Aug-16 ___ TOR completed (actual/planned): May-16/Feb-16___ First disbursement date (actual/planned): Aug-16/Oct-16 ___ All funds disbursed (yes/no): No___ Any delay? (yes/no): no___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no):___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): Report review ongoing. Processing second disbursement in Mar-17. Completion date revised to Jul-17 to reflect submission of the report to the second ExCom in 2017 ___. Legal arrangements (actual/planned): Aug-16/Dec-15 ___ First mission (actual/planned):Dec-16/Aug-16 ___ TOR completed (actual/planned): May-16/Feb-16___ First disbursement date (actual/planned): Aug-16/Oct-16 ___ All funds disbursed (yes/no): No___ Any delay? (yes/no): no___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no):___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___
ONG | UNEP | Renewal of institutional strengthening project (phase VI: 11/2015-10/2017) | Individual | LAC | BAR | SEV | 75 | INS | 24 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-12-01 | 2017-10-01 | 2018-12-01 |  |  | 149760 | 0 | 149760 | 21233 | 14.18% | 128527 | 28744 | 12852.7 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Country requested adjustments to the draft SSFA in second half of 2016. SSFA signed in Nov-16. First disbursement processed. 2015 CP data and Article 7 data reported on time to the Multilateral Fund and Ozone Secretariats. NOU participated in the Joint Netwok meeting in Chile, May-2016 and hosted the Caribbean thematic meeting on ODS alternatives Surveys in Dec-16.___ Legal arrangements (actual/planned): Nov-16/Apr-16.___Initial stages of project implementation (actual/planned): ___ Intermediate goals achieved (actual/planned): ___ First disbursement date (actual/planned): Dec-16/Apr-16.___ All funds disbursed (yes/no): no___ Any delay? (yes/no): yes___ If Yes, reasons for delay & action plan to resolve: Adjustments to the SSFA requested from Country once the draft was agreed delayed signature and first disbursement processing. UN Environment addressed revisions promptly___ If Yes, will delay have impact on project completion date (yes/no): yes. The completion date has been revised to accomodate schedule of SSFA___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: | Brief progress report (actual/planned): Country collecting information for 2016 CP data report and Art. 7 Data report. Project management and monitoring implementation of HPMP and ODS alternatives Survey. Track transfer of first disbursement with NBO___ Legal arrangements (actual/planned): Nov-16/Apr-16.___Initial stages of project implementation (actual/planned): ___ Intermediate goals achieved (actual/planned): ___ First disbursement date (actual/planned): Dec-16/Apr-16.___ All funds disbursed (yes/no): no___ Any delay? (yes/no): yes___ If Yes, reasons for delay & action plan to resolve: Adjustments to the SSFA requested from Country once the draft was agreed delayed signature and first disbursement. UN Environment addressed revision promptly___ If Yes, will delay have impact on project completion date (yes/no): yes. The completion date has been revised to accomodate schedule of SSFA___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom:
FIN | UNDP | Project preparation in the aerosol sector | Individual | AFR | BDI | ARS | 33 | PRP | 07 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-09-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Phase-out of CFC-11 and CFC-12 mixture in the manufacture of insecticides by conversion to hydrocarbon propellant at Fadi, S.A. (Fabrication d'insecticide et de product chimique) | Individual | AFR | BDI | ARS | 35 | INV | 09 | A | I | CFC | 8.8 | 8.8 | 0 | 0 | 2001-12-01 | 2002-07-01 | 2004-12-01 |  | 2003-12-01 | 2011-12-01 | 128900 | -180 | 128720 | 128720 | 100% | 0 | 0 | 0 | 16757 | -23.4 | 16733.6 | 0 | 0 | Completed in 2003. Financially completed in 2011. |  | 2001 |  | Investment
FIN | UNDP | Project preparation in the flexible polyurethane foam sector | Individual | AFR | BDI | FOA | 33 | PRP | 08 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-09-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Exim, S.A. | Individual | AFR | BDI | FOA | 35 | INV | 10 | A | I | CFC | 26.3 | 26.3 | 0 | 0 | 2001-12-01 | 2002-07-01 | 2005-01-01 |  | 2003-12-01 | 2006-06-01 | 78262 | -8335 | 69927 | 69927 | 100% | 0 | 0 | 0 | 10174.06 | -1084 | 9090.06 | 0 | 0 | Completed in 2003. Financially completed in 2006. |  | 2001 |  | Investment
FIN | UNDP | Project preparation of a terminal phase-out management plan | Individual | AFR | BDI | PHA | 47 | PRP | 20 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-03-01 | 2006-12-01 |  | 2007-12-01 | 2009-12-01 | 30000 | -3963 | 26037 | 26037 | 100% | 0 | 0 | 0 | 2250 | -297.23 | 1952.775 | -0.005 | 0 | Completed in 2007. Financially completed in 2009. |  | 2005 |  | Investment
FIN | UNIDO | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | BDI | PHA | 55 | INV | 24 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2009-11-01 | 2009-12-31 |  | 2010-11-01 | 2012-05-01 | 76000 | 0 | 76000 | 76000 | 100% | 0 | 0 |  | 6840 | 0 | 6840 | 0 | 0 | FIN |  |  |  | INV
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | BDI | PHA | 55 | PRP | 23 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2011-12-01 | 2013-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 |  | 11050 | 0 | 11050 | 0 | 0
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | BDI | PHA | 55 | TAS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2010-08-01 | 2009-07-01 |  | 2011-12-01 | 2012-12-01 | 74000 | 0 | 74000 | 74000 | 100% | 0 | 0 |  | 9620 | 0 | 9620 | 0 | 0
FIN | UNIDO | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | BDI | PHA | 62 | INV | 27 | A | I | CFC | 3.1 | 3.1 |  |  | 2010-12-01 | 2010-12-01 | 2011-12-31 |  | 2013-12-01 | 2013-12-01 | 53000 | -201 | 52799 | 52799.48 | 100% | -0.48 | 0 |  | 4770 | -18 | 4752 | 0 | 0 | FIN |  |  |  | INV
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | BDI | PHA | 62 | TAS | 26 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-08-01 | 2011-12-01 |  | 2013-12-01 | 2014-12-01 | 41000 | -270 | 40730 | 40730 | 100% | 0 | 0 |  | 5330 | -35.1 | 5294.9 | 0 | 0
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | BDI | PHA | 65 | INV | 29 | A | I | HCFC | 0.4 | 0 |  |  | 2011-11-01 | 2012-02-01 | 2016-11-30 | 2018-07-01 |  |  | 80000 | 0 | 80000 | 73816.38 | 92.27% | 6183.62 | 0 | 1 | 7200 | 0 | 6643 | 557 | 0 | Meeting held with NOU. 'Request for next tranche planned to be submitted to next ExCom despite unstable situation in the country. Milestones achieved: Equipment procured, delivered and distributed: Yes Actions towards next goals: prepare next tranche with NOU Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: Yes (to use balance in combination with next tranche). Any action required by Executive Committee? No | Lead Implementing Agency deferred request of next tranche to 80th ExCom meeting. Hence completion date extended to use balance in combination with next tranche. |  |  | INV
COM | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | AFR | BDI | PHA | 65 | TAS | 28 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-06-01 | 2013-11-01 |  | 2013-11-01 |  | 45000 | 0 | 45000 | 43044 | 95.65% | 1956 | 1956 | 0 | 5850 | 0 | 5595.72 | 254.28 | 254.28
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | AFR | BDI | PHA | 73 | TAS | 31 | A | I |  | 0 |  | 0 |  | 2014-11-01 | 2015-06-01 | 2016-12-01 | 2017-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 30000 | 3000 | 3900 | 0 | 0 | 3900 | 3900 | Brief progress report (actual/planned): Country received first payment in January 2016. Country trained 23 customs officers and 35 RAC technicians in 2016. Legal arrangements (actual/planned): Agreement signed in April 2015. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in January 16 __ All funds disbursed (yes/no): NO_ Final payment being _NO Any delay? (yes/no): YES ___ If Yes, reasons for delay & action plan to resolve: No activity reported yet because of the civil unrest in the country ___ If Yes, will delay have impact on project completion date (yes/no): _ YES __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Brief progress report (actual/planned): Country received first payment in January 2016. Country trained 23 customs officers and 35 RAC technicians in 2016. Legal arrangements (actual/planned): Agreement signed in April 2015. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in January 16 __ All funds disbursed (yes/no): NO_ Final payment being _NO Any delay? (yes/no): YES ___ If Yes, reasons for delay & action plan to resolve: No activity reported yet because of the civil unrest in the country ___ If Yes, will delay have impact on project completion date (yes/no): _ YES __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
ONG | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Individual | AFR | BDI | PHA | 73 | TAS | 32 | A | I |  | 0 |  | 0 |  | 2014-11-01 |  | 2016-11-01 | 2017-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 13044 | 3000 | 3900 | 0 | 0 | 3900 | 1695.72 | Brief progress report (actual/planned):Consultant identified in 2016, but couldn't travel within the country because of the civil war in Burundi . No activity reported in 2016 because of the unrest in the country. Legal arrangements (actual/planned): All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in January 16 __ All funds disbursed (yes/no): NO_ Final payment being _NO Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Brief progress report (actual/planned): Consultant contract signed in January 2017. First Draft report send in March 2017. Legal arrangements (actual/planned): All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in January 17 __ All funds disbursed (yes/no): NO_ Final payment being _NO Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
FIN | UNDP | Implementation of the RMP: Monitoring the activities included in the RMP | RMP-Component | AFR | BDI | REF | 26 | TAS | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-11-01 | 2001-07-01 | 2000-12-01 |  | 2003-11-01 | 2003-11-01 | 10450 | -415 | 10035 | 10035 | 100% | 0 | 0 | 0 | 1358.5 | -54 | 1304.5 | 0 | 0 | Completed in 2003. Financially completed in 2003. |  | 1998 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: Implementation of a national programme for recovery and recycling of refrigerants | RMP-Component | AFR | BDI | REF | 26 | TAS | 05 | A | I | CFC | 5.4 | 5.4 | 0 | 0 | 1998-11-01 | 2001-05-01 | 2000-12-01 |  | 2003-11-01 | 2004-01-01 | 119577 | -3603 | 115974 | 115974 | 100% | 0 | 0 | 0 | 15545.01 | -468.39 | 15076.62 | 0 | 0 | Completed in 2003. Financially completed in 2004. |  | 1998 |  | Investment
FIN | UNEP | Implementation of the RMP: training for customs officers | Individual | AFR | BDI | REF | 26 | TRA | 03 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 2000-12-01 | 2000-05-01 |  | 2002-07-01 | 2003-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Implementation of the RMP: training technicians in good management practices | Individual | AFR | BDI | REF | 26 | TRA | 04 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-10-01 | 2000-05-01 |  | 2002-07-01 | 2003-06-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNDP | Project preparation for update of refrigerant management plan | Individual | AFR | BDI | REF | 40 | PRP | 12 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-07-01 | 2003-08-01 | 2004-07-01 |  | 2004-12-01 | 2005-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 1500 | 0 | 1500 | 0 | 0 | Completed in 2004. Financially Completed in 2005. |  | 2003 |  | Investment
FIN | UNDP | Implementation of the RMP: supplementary training and spares to the national programme for recovery and recycling of refrigerants | RMP-Component | AFR | BDI | REF | 41 | TAS | 13 | N | I | CFC | 4.7 | 4.7 | 0 | 0 | 2003-12-01 | 2004-01-01 | 2006-12-01 |  | 2006-12-01 | 2008-09-01 | 32500 | -153 | 32347 | 32347 | 100% | 0 | 0 | 0 | 2925 | -13.77 | 2911.23 | 0 | 0 | Completed in 2006. Financially Completed in 2008. |  | 2003 |  | Investment
FIN | UNDP | Implementation of the RMP: monitoring the activities in the RMP | RMP-Component | AFR | BDI | REF | 41 | TAS | 16 | N | I | CFC | 2.9 | 2.9 | 0 | 0 | 2003-12-01 | 2004-07-01 | 2006-12-01 |  | 2006-12-01 | 2008-09-01 | 20000 | -464 | 19536 | 19536 | 100% | 0 | 0 | 0 | 1800 | -41.76 | 1758.24 | 0 | 0 | Completed in 2006. Financially Completed in 2008. |  | 2003 |  | Non-Investment
FIN | UNEP | Implementation of the RMP: customs training programme (phase II) | Individual | AFR | BDI | REF | 41 | TRA | 14 | A | I | CFC | 4.3 | 4.3 | 0 | 0 | 2003-12-01 | 2004-09-01 | 2004-12-01 |  | 2006-07-01 | 2009-07-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Implementation of the RMP: training of refrigeration technicians (phase II) | Individual | AFR | BDI | REF | 41 | TRA | 15 | A | I | CFC | 3.2 | 3.2 | 0 | 0 | 2003-12-01 | 2004-09-01 | 2005-06-01 |  | 2006-07-01 | 2010-12-01 | 22500 | 0 | 22500 | 22500 | 100% | 0 | 0 |  | 2925 | 0 | 2925 | 0 | 0
FIN | UNEP | Preparation of country programme | Individual | AFR | BDI | SEV | 23 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1999-05-01 |  | 1998-09-01 | 1999-03-01 | 40000 | -10000 | 30000 | 30000 | 100% | 0 | 0 |  | 5200 | -1300 | 3900 | 0 | 0
FIN | UNEP | Establishment of an Ozone Unit | Individual | AFR | BDI | SEV | 26 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2001-12-01 |  | 2002-07-01 | 2003-07-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 |  | 8580 | 0 | 8580 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (Phase II) | Individual | AFR | BDI | SEV | 37 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2002-08-01 | 2004-08-01 |  | 2004-12-01 | 2005-12-01 | 57200 | 0 | 57200 | 57200 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | AFR | BDI | SEV | 44 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2006-12-01 |  | 2006-12-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | BDI | SEV | 50 | INS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-04-01 | 2008-11-01 |  | 2010-12-01 | 2011-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of the institutional strengthening project (phase V) | Individual | AFR | BDI | SEV | 57 | INS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-12-01 | 2011-03-01 |  | 2013-03-01 |  | 60000 | 0 | 60000 | 18000 | 30% | 42000 | 0 | 42000 | 0 | 0 | 0 | 0 | 0 | Some financial adjustments are needed. | Some financial adjustments are needed.
COM | UNEP | Extension of the institutional strengthening project (phase VI: 1/2014-12/2015) | Individual | AFR | BDI | SEV | 71 | INS | 30 | A | I |  | 0 |  | 0 |  | 2013-12-01 |  | 2015-12-01 | 2017-07-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | The project cannot be completed - there was no progress because of unrest in the country. IS new phase (VII) now is under implementation, SSFA signed and activities are progressing. | The project cannot be completed - there was no progress because of unrest in the country. IS new phase (VII) now is under implementation, SSFA signed and activities are progressing.
ONG | UNEP | Extension of the institutional strengthening project (phase VII: 1/2015-12/2017) | Individual | AFR | BDI | SEV | 75 | INS | 33 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-04-01 | 2017-12-01 | 2017-12-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 85000 | 8500 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Country received first payment in April 2016. A meeting of the steering committee was organized in December 2015 to allocate the 2016 quota. Legal arrangements (actual/planned): Agreement signed in March 2016. All activities under the SSFA are completed (as planned) NO___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in April 2016 __ All funds disbursed (yes/no): _ Final payment being _ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Brief progress report (actual/planned): Country received first payment in April 2016. A meeting of the steering committee was organized in December 2015 to allocate the 2016 quota. Legal arrangements (actual/planned): Agreement signed in March 2016. All activities under the SSFA are completed (as planned) NO___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in April 2016 __ All funds disbursed (yes/no): _ Final payment being _ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | AFR | BDI | SEV | 75 | TAS | 34 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-05-01 | 2016-12-01 | 2017-12-01 |  |  | 70000 | 0 | 70000 | 0 | 0% | 70000 | 70000 | 7000 | 9100 | 0 | 0 | 9100 | 9100 | Brief progress report (actual/planned): Country received first payment in May 2016 and prepared the Non ODS survey report. The advanced draft of ODS Survey sent to Paris. Legal arrangements (actual/planned): All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in May 2016__ All funds disbursed (yes/no): NO_ Final payment being _NO Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Brief progress report (actual/planned): Country received first payment in May 2016 and prepared the Non ODS survey report. The advanced draft of ODS Survey sent to Paris. Legal arrangements (actual/planned): All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in May 2016__ All funds disbursed (yes/no): NO_ Final payment being _NO Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
FIN | UNIDO | Training and awareness workshop in the process agents (TCA) sector | Individual | AFR | BDI | SOL | 45 | TAS | 19 | A | I | TCA | 0.1 | 0.1 |  |  | 2005-04-01 | 2005-12-01 | 2006-04-01 |  | 2007-12-01 | 2009-12-01 | 35000 | -2129 | 32871 | 32870.94 | 100% | 0.06 | 0 |  | 3150 | -192 | 2958 | 0 | 0 | FIN |  |  | 2007-07-01 | INV
CLO | UNIDO | Preparation of investment project for ODS phase-out in a foam producing plant (SIBAO) | Individual | AFR | BEN | FOA | 17 | PRP | 02 | A | I |  | 0 | 0 |  |  | 1995-07-01 |  | 1995-09-01 |  |  | 1998-08-01 | 15000 | -15000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 1950 | -1950 | 0 | 0 | 0 | CLO
FIN | UNDP | Preparation of two projects in the general foam subsector | Individual | AFR | BEN | FOA | 27 | PRP | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-01 | 2000-04-01 |  | 1999-11-01 | 2002-04-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Plastique Elastomeres du Benin (P.E.B.) | Individual | AFR | BEN | FOA | 32 | INV | 12 | A | I | CFC | 27.3 | 27.3 | 0 | 0 | 2000-12-01 | 2002-06-01 | 2003-07-01 |  | 2003-08-01 | 2005-09-01 | 143027 | -6481 | 136546 | 136546 | 100% | 0 | 0 | 0 | 18593.51 | -843 | 17750.51 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
CLO | Canada | Project preparation for a terminal phase-out management plan |  | AFR | BEN | PHA | 49 | PRP | 15 | A | I |  | 0 |  | 0 |  | 2006-07-01 |  | 2007-07-01 |  |  | 2009-07-01 | 12000 | -12000 | 0 | 0 |  | 0 |  | 0 | 1560 | -1560 | 0 | 0 |  | TPMP has been prepared by UNEP and approved at 55th meeting, without the need for the funds approved for Canada. Therefore, Canada will ask for cancellation of this project at the 58th meeting and return related funds. |  | 2006 |  | Non-Inv.
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | BEN | PHA | 49 | PRP | 16 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-02-01 | 2007-07-01 |  | 2007-10-01 | 2008-12-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 |  | 2340 | 0 | 2340 | 0 | 0
FIN | UNIDO | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | BEN | PHA | 55 | INV | 19 | A | I | CFC | 3.9 | 3.9 |  |  | 2008-07-01 | 2008-12-01 | 2009-12-31 |  | 2009-12-01 | 2011-12-01 | 106000 | -400 | 105600 | 105599.57 | 100% | 0.43 | 0 |  | 9540 | -36 | 9504 | 0 | 0 | FIN |  |  |  | INV
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | BEN | PHA | 55 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-10-01 | 2009-07-01 |  | 2009-07-01 | 2010-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 |  | 11050 | 0 | 11050 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | BEN | PHA | 57 | PRP | 21 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-08-01 | 2010-03-01 |  | 2011-12-01 | 2012-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 |  | 11050 | 0 | 11050 | 0 | 0
FIN | UNIDO | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | BEN | PHA | 59 | INV | 23 | A | I | CFC | 4 | 4 |  |  | 2009-11-01 | 2010-11-01 | 2010-11-30 |  | 2011-12-01 | 2012-12-01 | 69000 | 0 | 69000 | 68999.81 | 100% | 0.19 | 0 |  | 6210 | 0 | 6210 | 0 | 0 | FIN |  |  |  | INV
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | BEN | PHA | 59 | TAS | 22 | A | I |  | 0 | 0 | 0 |  | 2009-11-01 | 2009-12-01 | 2010-11-01 |  | 2010-11-01 | 2011-11-01 | 65000 | 0 | 65000 | 65000 | 100% | 0 | 0 |  | 8450 | 0 | 8450 | 0 | 0
FIN | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | BEN | PHA | 63 | INV | 26 | A | I |  | 0 | 0 |  |  | 2011-04-01 | 2012-04-01 | 2013-03-31 |  | 2014-12-01 | 2016-03-01 | 100000 | -90 | 99910 | 99910.34 | 100% | -0.34 | 0 |  | 7500 | -7 | 7493 | 0 | 0 | The project was financially completed and the balance was returned at the 76th ExCom. |  |  |  | INV
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | AFR | BEN | PHA | 63 | TAS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-12-01 | 2013-03-01 |  | 2013-03-01 | 2014-03-01 | 85000 | -3686 | 81314 | 81314 | 100% | 0 | 0 |  | 11050 | -479.18 | 10570.82 | 0 | 0
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) UNIDO | Multi-Year | AFR | BEN | PHA | 70 | INV | 27 | A | I | HCFC | 1 | 1 |  |  | 2013-07-01 | 2015-06-01 | 2016-07-31 | 2017-09-01 |  |  | 40000 | 0 | 40000 | 33774.59 | 84.44% | 6225.41 | 0 | 6000 | 3000 | 0 | 2533 | 467 | 0 | - UNIDO offered an alternative solution for the training, a bidding was organized for undertaking the training and the training was successfully organized in May 2016. The training had a special session on the proper installation and servicing of R290 air conditioners, which was done on the 3 AC units specifically designed for R290. The next tranche was approved at the 76th ExCom Meeting. Equipment distribution was planned for September 2016, however, no update has been received from the NOU. Milestones achieved: ToR for equipment purchase agreed upon: Yes, June 2014; Bids prepared & requested: Yes, September 2014; Contract awarded: Yes, December 2014; Equipment delivered: Yes, May 2015; Training of trainers organized: Yes, May 2016; Activities planned but not implemented, reasons and strategy: Distribution of equipment was planned for September, but did not take place based on recent information received. Actions towards next goals: Follow-up with the NOU for the distribution of equipment during 2017. Was there any delay during the reporting year? Yes, delay in equipment distribution. Any recurring problem? No Any impact on project completion date: Yes, the tranche is expected to be completed by September 2017. Any action required by Executive Committee? No | - In February, under the framework of the demonstration project in the service sector in East Africa, a training was organized by UNIDO in Tanzania. Benin was also invited for this workshop, since they are facing very similar problems on refrigerant quality like the countries involved in the demonstration project. During the joint network meeting in Abidjan in March 2017, UNIDO was approached and informed that a new ozone officer was appointed and UNIDO was also informed that equipment purchased under this tranche have not yet been distributed to beneficiaries. UNIDO will discuss with the new NOU on the possible way forward for the equipment distribution. Milestones achieved: ToR for equipment purchase agreed upon: Yes, June 2014; Bids prepared & requested: Yes, September 2014; Contract awarded: Yes, December 2014; Equipment delivered: Yes, May 2015; Training of trainers organized: Yes, May 2016; Activities planned but not implemented, reasons and strategy: Distribution of equipment was planned for September, but did not take place based on recent information received. UNIDO will liaise with the new NOU and agree on the modalities and timing of equipment distribution. Actions towards next goals: Follow-up with the NOU for the distribution of equipment during 2017. Was there any delay during the reporting year? Yes, delay in equipment distribution. Any recurring problem? No Any impact on project completion date: Yes, the tranche is expected to be completed by September 2017. Any action required by Executive Committee? No |  |  | INV
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | AFR | BEN | PHA | 70 | TAS | 28 | A | I |  | 1.4 |  | 0 |  | 2013-07-01 | 2014-06-01 | 2016-07-01 | 2017-12-01 |  |  | 85000 | 0 | 85000 | 29611 | 34.84% | 55389 | 55000 | 5538.9 | 11050 | 0 | 3849.43 | 7200.57 | 7150 | Brief progress report (actual/planned): Legal arrangements (actual/planned): Agreement signed in June 2014. Country organized 2 workshops training for refrigeration technicians in January-May 2016 in Cotonou (25 technicians), Porto Novo(25 ). A total of 50 technicians trained on Good practices and HCFC recovery and recycling. In June 2016 Country organized two workshops of 20 Customs officer in Djougou and Cotonou on control and identification of ODS and ODS based equipment including HCFCs and HCFCs based equipment. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in June 2014 __ All funds disbursed (yes/no): NO_ _ Any delay? (yes/no): Yes ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ Yes, the SSFA expired in June 2016, with a balance of US $ 40,000 Country appointed a new NOO, an extension will be needed to implement the remaining activities__ If Yes, is any action required by ExCom: | Brief progress report (actual/planned): Legal arrangements (actual/planned): Agreement signed in June 2014. Country organized 2 workshops training for refrigeration technicians in January-May 2016 in Cotonou (25 technicians), Porto Novo(25 ). A total of 50 technicians trained on Good practices and HCFC recovery and recycling. In June 2016 Country organized two workshops of 20 Customs officer in Djougou and Cotonou on control and identification of ODS and ODS based equipment including HCFCs and HCFCs based equipment. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in June 2014 __ All funds disbursed (yes/no): NO_ _ Any delay? (yes/no): Yes ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ Yes, the SSFA expired in June 2016, with a balance of US $ 40,000 Country appointed a new NOO, an extension will be needed to implement the remaining activities__ If Yes, is any action required by ExCom: |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor low disbursement rate of approved funds.
ONG | UNIDO | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | AFR | BEN | PHA | 76 | INV | 33 | A | I | HCFC | 2.4 | 0 |  |  | 2016-05-01 |  | 2020-05-31 | 2020-05-01 |  |  | 120000 | 0 | 120000 | 0 | 0% | 120000 | 0 | 10000 | 9000 | 0 | 0 | 9000 | 0 | - At the 76th ExCom Meeting the Executive Committee has decided to combine the last tranches for Benin to enable proper implementation of the tranche and the purchase and delivery of equipment at once. PAD was subsequently issued and the Government was informed on the approval. Milestones achieved: PAD issued: Yes, in May 2016 First mission undertaken/working arrangements agreed: No ToR for equipment purchase agreed upon: No; Bids prepared & requested: No; Contract awarded: No; Equipment delivered: No; Activities planned but not implemented, reasons and strategy: N/A Actions towards next goals: Contact new NOU and initiate discussions on the working arrangements and actions plans. Was there any delay during the reporting year? No, the project is going until 2020. Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - During the joint network meeting in Abidjan in March 2017, UNIDO was approached by Benin's representative and she informed UNIDO that she became the new NOU. No official communication has been received so far. Milestones achieved: PAD issued: Yes, in May 2016 First mission undertaken/working arrangements agreed: No ToR for equipment purchase agreed upon: No; Bids prepared & requested: No; Contract awarded: No; Equipment delivered: No; Activities planned but not implemented, reasons and strategy: No activities have been initiated due to lack of response from the previous NOU. Actions towards next goals: UNIDO will contact the new NOU and initiate discussions on the working arrangements and actions plans. Was there any delay during the reporting year? N/A Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
ONG | UNEP | HCFC phase-out management plan (stage I, third tranche) | Multi-year | AFR | BEN | PHA | 76 | TAS | 32 | A | I |  | 0 |  | 0 |  | 2016-05-01 |  | 2018-12-01 | 2018-12-01 |  |  | 75000 | 0 | 75000 | 0 | 0% | 75000 | 55000 | 7500 | 9750 | 0 | 0 | 9750 | 7150 | Newly approved project | Brief progress report (actual/planned): Legal arrangements (actual/planned): Agreement signed in January 2017. All activities under the SSFA are completed (as planned) NO___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _To be disbursed in February 17 __ All funds disbursed (yes/no): _ Final payment being _ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
ONG | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Individual | AFR | BEN | PHA | 77 | TAS | 34 | A | I |  | 0 |  | 0 |  | 2016-12-01 |  | 2018-06-01 | 2018-06-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 3000 | 3900 | 0 | 0 | 3900 | 0 | Newly approved project | Brief progress report (actual/planned): Newly approved. UNEP will help the country to hire an independent consultant and submit the report by ExCom 79. Legal arrangements (actual/planned): Agreement not signed yet. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement _no __ All funds disbursed (yes/no): _ Final payment _no_4.__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
FIN | UNIDO | Refrigerant recovery and recycling scheme | RMP | AFR | BEN | REF | 22 | TAS | 04 | A | I | CFC | 12.9 | 12.9 |  |  | 1997-05-01 | 1997-08-01 | 1999-06-01 |  | 1998-12-01 | 2000-12-01 | 114000 | 0 | 114000 | 114000 | 100% | 0 | 0 |  | 14820 | -13 | 14807 | 0 | 0 | FIN
FIN | UNEP | Preparation of a refrigerant management plan | RMP | AFR | BEN | REF | 27 | PRP | 06 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-10-01 | 2000-04-01 |  | 2000-12-01 | 2001-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | Canada | Implementation of the RMP: development of code of good practice for technicians | RMP Update | AFR | BEN | REF | 32 | TAS | 10 | A | I |  | 0.9 | 0.9 | 0 |  | 2000-12-01 | 2003-01-01 | 2002-12-01 |  | 2004-06-01 | 2004-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 |  | 0 | 1300 | 0 | 1300 | 0 |  | Final copies of Code of Good Practice received by Canada. |  | 2000 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: training of custom officials | RMP Update | AFR | BEN | REF | 32 | TRA | 08 | A | I |  | 5.2 | 5.2 | 0 |  | 2000-12-01 | 2003-01-01 | 2003-06-01 |  | 2006-08-01 | 2006-08-01 | 59900 | 0 | 59900 | 59900 | 100% | 0 |  | 0 | 7787 | 0 | 7787 | 0 |  | Project delayed until ODS import/export legislation was passed in April 2002. Train-the-Trainer Worshop held August 2003 and second phase followed in 2004. Canada asked that more customs officers be trained, as results are lower than under other comparabl |  | 2000 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: training of technicians in good refrigeration practices | RMP Update | AFR | BEN | REF | 32 | TRA | 09 | A | I |  | 12.6 | 12.6 | 0 |  | 2000-12-01 | 2001-10-01 | 2002-12-01 |  | 2003-12-01 | 2004-12-01 | 144000 | 0 | 144000 | 144000 | 100% | 0 |  | 0 | 18720 | 0 | 18720 | 0 |  | Train-the-Trainer workshop held in Jan. 2002. Phase II training and monitoring completed in 2003. |  | 2000 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: training of environmental inspectors and investigators | RMP Update | AFR | BEN | REF | 32 | TRA | 11 | A | I |  | 5 | 5 | 0 |  | 2000-12-01 | 2005-01-01 | 2003-12-01 |  | 2007-02-01 | 2007-02-01 | 57000 | 0 | 57000 | 57000 | 100% | 0 |  | 0 | 7410 | 0 | 7410 | 0 |  | Train-the-Trainer workshop for 25 environmental inspectors completed in March 2005 and second and final workshop held in June 2006. Small remaining balance was left and Canada agreed that it be used for an ODS survey. Benin submitted survey and final expenditure report. PCR was submitted Dec. 2007. |  | 2000 |  | Non-Inv.
FIN | UNEP | Country programme preparation | Individual | AFR | BEN | SEV | 13 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-12-01 | 1995-10-01 |  | 1995-10-01 | 1995-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 |  | 4550 | 0 | 4550 | 0 | 0
FIN | UNEP | Creation of an Ozone Bureau | Individual | AFR | BEN | SEV | 18 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-01-01 | 1998-11-01 |  | 1999-11-01 | 1999-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening (phase II) | Individual | AFR | BEN | SEV | 28 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 1999-11-01 | 2001-08-01 |  | 2001-09-01 | 2001-07-01 | 33333 | 0 | 33333 | 33333 | 100% | 0 | 0 |  | 4333 | 0 | 4333 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (Phase III) | Individual | AFR | BEN | SEV | 33 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-06-01 | 2003-04-01 |  | 2003-07-01 | 2004-07-01 | 33333 | 0 | 33333 | 33333 | 100% | 0 | 0 |  | 4333 | 0 | 4333 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project | Individual | AFR | BEN | SEV | 40 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2004-01-01 | 2005-07-01 |  | 2006-12-01 | 2007-12-01 | 43333 | 0 | 43333 | 43333 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase V) | Individual | AFR | BEN | SEV | 49 | INS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-06-01 | 2008-06-01 |  | 2008-12-01 | 2011-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase VI) | Individual | AFR | BEN | SEV | 56 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2010-03-01 | 2010-12-01 |  | 2011-12-01 |  | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase VII) | Individual | AFR | BEN | SEV | 62 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2012-04-01 | 2012-12-01 |  | 2013-12-01 | 2014-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed | Project financially completed
COM | UNEP | Renewal of institutional strengthening project (phase VIII: 1/2014-12/2015) | Individual | AFR | BEN | SEV | 71 | INS | 29 | A | I |  | 0 |  | 0 |  | 2013-12-01 | 2014-05-01 | 2015-12-01 |  | 2013-12-01 |  | 60000 | 0 | 60000 | 33000 | 55% | 27000 | 27000 |  | 0 | 0 | 0 | 0 | 0 | Project will not be completed the project was heavily delayed because of changes in the Government. IS new phase (IX) now is under implementation, SSFA signed and activities are progressing. | Project will not be completed the project was heavily delayed because of changes in the Government. IS new phase (IX) now is under implementation, SSFA signed and activities are progressing.
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | AFR | BEN | SEV | 74 | TAS | 30 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-06-01 | 2016-05-01 | 2017-10-01 |  |  | 55000 | 0 | 55000 | 0.3 | 0.0005455% | 54999.7 | 55000 | 5499.97 | 7150 | 0 | 0.039 | 7149.961 | 7150 | Brief progress report (actual/planned): Country signed the SSFA in May 2016 . First payment sent in June 2016. Consultants hired for ODS survey. Legal arrangements (actual/planned): Agreement signed in May 2016. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in June 2016 __ All funds disbursed (yes/no): _ n/a.__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Brief progress report (actual/planned): Country signed the SSFA in May 2016 . First payment sent in June 2016. Country sent the draft ODS survey report to UNEP. Legal arrangements (actual/planned): Agreement signed in May 2016. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in June 2016 __ All funds disbursed (yes/no): _ n/a.__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
ONG | UNEP | Renewal of institutional strengthening project (phase IX: 1/2016-12/2017) | Individual | AFR | BEN | SEV | 75 | INS | 31 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-04-01 | 2017-12-01 | 2017-12-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 85000 | 8500 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): __ SSFA signed in March 2016. First payment sent in April 2016. Art5 data report for 2015 and CP data for 2015 have been provided in May 2016. Legal arrangements (actual/planned): Agreement signed in March 2016. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in April 16 __ All funds disbursed (yes/no): NO_ Final payment being _NO Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/acompleted(actual/planned): _N/A__ First disbursement date (actual/planned): NO___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _YES_ If Yes, reasons for delay & action plan to resolve: NO__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): __ SSFA signed in March 2016. First payment sent in April 2016. Art5 data report for 2015 and CP data for 2015 have been provided in May 2016. Legal arrangements (actual/planned): Agreement signed in March 2016. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in April 16 __ All funds disbursed (yes/no): NO_ Final payment being _NO Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/acompleted(actual/planned): _N/A__ First disbursement date (actual/planned): NO___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _YES_ If Yes, reasons for delay & action plan to resolve: A new NOO is appointed by the government who will faster the implementation of the remaining activities__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__
FIN | UNDP | Conversion to CFC-free technology in the manufacture of aerosol at Advanced Chemical Industries Ltd. (ACI) | Individual | ASP | BGD | ARS | 17 | INV | 05 | N | I | CFC | 123.6 | 123.6 | 0 | 0 | 1995-07-01 | 1998-12-01 | 1996-07-01 |  | 2002-08-01 | 2003-10-01 | 322920 | -343 | 322577 | 322577 | 100% | 0 | 0 | 0 | 41979.6 | -45 | 41934.6 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1995 | 2001-05-01 | Investment
FIN | UNDP | Formulation of a phase-out project in the MDI sector | Individual | ASP | BGD | ARS | 50 | PRP | 24 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-03-01 | 2007-11-01 |  | 2007-04-01 | 2009-12-01 | 30000 | -7050 | 22950 | 22950 | 100% | 0 | 0 | 0 | 2250 | -528.75 | 1721.25 | 0 | 0 | Completed in 2007. Financially completed in 2009. |  | 2006 |  | Investment
FIN | UNEP | Formulation of a transition strategy for MDI | Individual | ASP | BGD | ARS | 50 | TAS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-06-01 | 2007-11-01 |  | 2007-12-01 | 2007-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNDP | Phase-out of CFC consumption in the manufacture of aerosol MDIs (Beximco, Square Pharmaceutical and Acme Pharmaceutical) | Individual | ASP | BGD | ARS | 52 | INV | 26 | N | I | CFC | 76.3 | 76.3 | 0 | 0 | 2007-07-01 | 2010-11-01 | 2011-07-01 |  | 2013-12-01 | 2015-01-01 | 2776778 | -14321.31 | 2762456.69 | 2762457 | 100% | -0.31 | 0 | 0 | 208258 | -1074.1 | 207183.9268 | -0.02685 | 0 | Financially Completed in 2015. | Completed in 2013. Verification of conversion in Square is proposed to be undertaken in May 2014. | 2007 | 2011-07-01 | Investment
FIN | UNEP | Transition strategy for phasing out use of CFCs in the manufacturing of MDIs | Individual | ASP | BGD | ARS | 52 | TAS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-11-01 | 2011-07-01 |  | 2011-12-01 | 2012-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0
FIN | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | ASP | BGD | FOA | 57 | PRP | 33 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 |  | 2010-03-01 |  | 2012-12-01 | 2013-12-01 | 50000 | -50000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 3750 | -3750 | 0 | 0 | 0 | Financially completed in 2013. | Completed in 2012. | 2009 |  | Investment
FIN | UNDP | Conversion from HCFC-141b to cyclopentane technology in manufacturing refrigeration equipment insulation foam at Walton Hi-Tech Industries Limited | Multi-year | ASP | BGD | FOA | 62 | INV | 38 | N | I | HCFC | 20.2 | 20.2 | 0 | 0 | 2010-12-01 | 2012-06-01 | 2012-12-01 |  | 2014-12-01 | 2015-12-01 | 1146074 | -4763 | 1141311 | 1141311 | 100% | 0 | 0 | 0 | 85956 | -357.23 | 85598.7731 | -0.0031 | 0 | Financially Completed in 2015. | Safety audit consultancy firm has been appointed and will complete the audit activity in April 2014. Verification of completion of project is also expected to be completed by May 2014. | 2010 |  | Investment
FIN | UNDP | Formulation of a national phase out plan | Individual | ASP | BGD | PHA | 39 | PRP | 15 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-04-01 | 2005-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 3000 | 0 | 3000 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2003 |  | Investment
FIN | UNEP | National ODS phase-out plan: public awareness and information dissemination to main stakeholders (2004 work programme) | Multi-Year | ASP | BGD | PHA | 42 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2006-05-01 | 2005-04-01 |  | 2008-12-01 | 2009-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 |  |  |  | 2007-12-01
FIN | UNDP | National ODS phase-out plan: technical assistance programme for the refrigeration servicing sub-sector (2004 work programme) | Multi-Year | ASP | BGD | PHA | 42 | TAS | 19 | N | I | CFC | 36 | 36 | 0 | 0 | 2004-04-01 | 2008-02-01 | 2005-04-01 |  | 2010-12-01 | 2013-10-01 | 96000 | 0 | 96000 | 96000 | 100% | 0 | 0 | 0 | 7200 | 0 | 7200 | 0 | 0 | Financially completed in 2013. |  | 2004 |  | Investment
FIN | UNDP | National ODS phase-out plan: technical assistance for the phase-out of ODS solvents (2004 work programme) | Multi-Year | ASP | BGD | PHA | 42 | TAS | 20 | N | I | CTC | 0 | 0 | 0 | 0 | 2004-04-01 | 2010-03-01 | 2005-04-01 |  | 2010-12-01 | 2013-10-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 1875 | 0 | 1875 | 0 | 0 | Financially completed in 2013. |  | 2004 |  | Investment
FIN | UNDP | National ODS phase-out plan: monitoring and management unit (2004 work programme) | Multi-Year | ASP | BGD | PHA | 42 | TAS | 21 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2010-03-01 | 2005-04-01 |  | 2010-12-01 | 2013-10-01 | 34000 | 0 | 34000 | 34000 | 100% | 0 | 0 | 0 | 2550 | 0 | 2550 | 0 | 0 | Financially completed in 2013. |  | 2004 |  | Non-Investment
FIN | UNEP | National ODS phase-out plan: training and certification programme for refrigeration service technicians, including development of a code of good practices (2004 work programme) | Multi-Year | ASP | BGD | PHA | 42 | TRA | 16 | A | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2006-05-01 | 2005-04-01 |  | 2008-04-01 | 2009-04-01 | 39500 | 0 | 39500 | 39500 | 100% | 0 | 0 |  | 5135 | 0 | 5135 | 0 | 0 |  |  |  | 2007-12-01
FIN | UNEP | National ODS phase-out plan: training programme for custom officers (2004 work programme) | Multi-Year | ASP | BGD | PHA | 42 | TRA | 17 | A | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2005-04-01 |  | 2008-12-01 | 2009-12-01 | 21000 | 0 | 21000 | 21000 | 100% | 0 | 0 |  | 2730 | 0 | 2730 | 0 | 0
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | ASP | BGD | PHA | 56 | PRP | 29 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-11-01 | 2011-04-01 | 2009-11-01 |  | 2012-12-01 | 2013-12-01 | 125000 | -102701.6 | 22298.4 | 22298 | 100% | 0.4 | 0 | 0 | 9375 | -7702.62 | 1672.35 | 0.03 | 0 | Financially completed in 2013. | Completed in 2012. | 2008 |  | Investment
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | BGD | PHA | 56 | PRP | 30 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2010-12-01 | 2009-11-01 |  | 2011-12-01 | 2012-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0
FIN | UNDP | National ODS phase-out plan (second, third and fourth tranches) | Multi-Year | ASP | BGD | PHA | 57 | TAS | 31 | N | I | CFC | 202.6 | 202.6 | 0 | 0 | 2009-04-01 | 2009-05-01 | 2011-03-01 |  | 2011-07-01 | 2013-10-01 | 669750 | 0 | 669750 | 669750 | 100% | 0 | 0 | 0 | 50231 | 0 | 50231 | 0 | 0 | Financially completed in 2013. | Completed in 2011. See BGD-36. | 2009 |  | Investment
FIN | UNEP | National ODS phase-out plan (second, third and fourth tranches) | Multi-Year | ASP | BGD | PHA | 57 | TRA | 32 | A | I |  | 0 | 0 | 0 |  | 2009-04-01 | 2009-07-01 | 2010-03-01 |  | 2011-12-01 | 2012-12-01 | 177175 | 0 | 177175 | 177175 | 100% | 0 | 0 |  | 23033 | 0 | 23033 | 0 | 0
FIN | UNDP | National ODS phase-out plan (fifth and sixth tranches) | Multi-year | ASP | BGD | PHA | 60 | INV | 36 | N | I | CFC | 21.9 | 21.9 | 0 | 0 | 2010-04-01 | 2011-01-01 | 2011-04-01 |  | 2012-12-01 | 2013-10-01 | 55000 | -4887.64 | 50112.36 | 50112 | 100% | 0.36 | 0 | 0 | 4125 | -366.57 | 3758.4 | 0.03 | 0 | Financially completed in 2013. | Completed in 2012. The project is expected to be financially closed by end of Q2 2013. | 2010 |  | Investment
FIN | UNEP | National ODS phase-out plan (fifth and sixth tranches) | Multi-Year | ASP | BGD | PHA | 60 | TAS | 35 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2011-06-01 | 2011-04-01 |  | 2011-12-01 | 2012-12-01 | 26500 | 0 | 26500 | 26500 | 100% | 0 | 0 |  | 3445 | 0 | 3445 | 0 | 0
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-year | ASP | BGD | PHA | 65 | INV | 40 | N | I | HCFC | 0.6 | 0 | 0 | 0 | 2011-11-01 |  | 2015-12-01 | 2017-12-01 |  |  | 55000 | 0 | 55000 | 0 | 0% | 55000 | 0 | 22000 | 4125 | 0 | 0 | 4125 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): In 2016 no progress has been done. Prodoc signed (actual/planned, yes/no and date):- Missions undertaken (actual/planned):- TOR for consultants/subcontracts completed (actual/planned): Contract/PO/MOA agreements signed: First disbursement date (actual/planned): 42842Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:Administrative delay due to delayed recruitment process of MPU Bangkok Team. As of March 2017 team is complete and communication with NY finance offcer and COO has now been facilitated to resolve financial issues. | Work will start after completion of internal procedures | 2011 |  | Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | ASP | BGD | PHA | 65 | TAS | 39 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2013-12-01 | 2013-11-01 | 2017-03-01 |  |  | 230000 | 0 | 230000 | 198382.75 | 86.25% | 31617.25 | 31617.25 | 3161.725 | 29900 | 0 | 25789.7575 | 4110.2425 | 4110.2425 | Brief progress report (actual/planned): Finalzing and launching RAC technicians training curriculum with vocational schools. 33 trainings and 1610 technicians trained overall. Border dialgogue held in Nepal in Dec 2016. Ozone day celebrations. Legal arrangement (actual/ planned): yes First mission (actual/ planned):____ TOR completed (actual/ planned): N/A. First disbursement date: actual Nov 2013 All funds disbursed (yes/no): no (final remaining) Any delay? (yes/no): yes. If Yes, reasons for delay & action plan to resolve: _________ If Yes, will delay have impact on project completion date (yes/no): __________ Any ongoing problems (yes/no): __________ If Yes, is any action required by ExCom: N/A. | Brief progress report (actual/planned): awaiting for the final and expenditure report to make the final payment and close SSFA
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | Multi-Year | ASP | BGD | PHA | 74 | TAS | 42 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-09-01 | 2016-06-01 | 2017-12-01 |  |  | 90000 | 0 | 90000 | 0 | 0% | 90000 | 90000 | 9000 | 11700 | 0 | 0 | 11700 | 11700 | Brief progress report (actual/planned): Launching training curriculum for technicians with vocational and technical schools, 850 technicians trained in 13 workshops, production of 1000 sets of training material Legal arrangements(actual/planned): SSFA still ongoing till Dec 2017 First mission (actual/planned): last mission in Sep 2016 TOR completed(actual/planned): First disbursement date (actual/planned): ___ All funds disbursed (yes/no): No Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: Internal administration processes If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): 79 technicians trained in 2 workshops Legal arrangements(actual/planned): SSFA still ongoing till Dec 2017 First mission (actual/planned): last mission in Sep 2016 TOR completed(actual/planned): First disbursement date (actual/planned): ___ All funds disbursed (yes/no): No Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: Internal administration processes If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___
ONG | UNDP | Preparation of a HCFC phase-out management plan (stage II) | Individual | ASP | BGD | PHA | 75 | PRP | 44 | N | I | HCFC | 0 | 0 | 0 | 0 | 2015-11-01 | 2016-12-01 | 2017-06-01 | 2017-06-01 |  |  | 30000 | 0 | 30000 | 14.35 | 0.04783% | 29985.65 | 0 | 11994.26 | 2100 | 0 | 1.0045 | 2098.9955 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): UNDP CO has finalized the process to recruit of International Consultant for Project Development. Expected to be on board by Q1, 2017 upon received ASL from MP Prodoc signed (actual/planned, yes/no and date):Letter of Authorisation sent 15 June 2016 Missions undertaken (actual/planned):- TOR for consultants/subcontracts completed (actual/planned): completed Contract/PO/MOA agreements signed: Not signed due to closure of financial year First disbursement date (actual/planned): 42872Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:Delay has been made for conducting of Confidental refrence check of the Selected Consultant. Resolved. Awaiting for 2017 ASL under Output ID 000100881 and Output ID 000100883 for issung Contrcat and PO | HPMP Stage II prepration work started and will be submitted in 80th ExCom | 2015 |  | Non-Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan (stage II) | Individual | ASP | BGD | PHA | 75 | PRP | 45 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-07-01 | 2016-12-01 | 2017-12-01 |  |  | 30000 | 0 | 30000 | 2455.97 | 8.187% | 27544.03 | 0 | 2754.403 | 3900 | 0 | 319.2761 | 3580.7239 | 0 | Brief progress report (actual/planned): One stakeholder consultation workshop on possible components for Stage 2. UNDP is still conducting the survey. Legal arrangements(actual/planned): SSFA is signed by UNEP and is now with NOU First mission (actual/planned): Sep 2016 TOR completed(actual/planned): not yet Funds disbursement date (actual/planned): Not yet All funds disbursed (yes/no): ___ Any delay? (yes/no): ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): UNDP as a lead agency is still conducting the survey/inventory. Legal arrangements(actual/planned): SSFA is signed by UNEP and it is now with NOU for signature First mission (actual/planned): TOR completed(actual/planned): not yet Funds disbursement date (actual/planned): Not yet All funds disbursed (yes/no): ___ Any delay? (yes/no): ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___
FIN | UNDP | Project preparation in refrigeration recycling | Individual | ASP | BGD | REF | 21 | PRP | 06 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1998-01-01 |  | 1999-09-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1997 | 1999-12-01 | Investment
FIN | UNDP | Implementation of the RMP: Implementation of a national recovery and recycling project | RMP-Component | ASP | BGD | REF | 29 | TAS | 10 | A | I | CFC | 12.6 | 12.6 | 0 | 0 | 1999-11-01 | 2001-12-01 | 2002-12-01 |  | 2005-07-01 | 2007-03-01 | 298270 | 0 | 298270 | 298270 | 100% | 0 | 0 | 0 | 38775.1 | 0 | 38775.1 | 0 | 0 | Completed in 2005. Financially completed in 2007. |  | 1999 |  | Investment
FIN | UNDP | Implementation of the RMP: Monitoring of the activities included in the RMP | RMP-Component | ASP | BGD | REF | 29 | TAS | 12 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-11-01 | 2003-02-01 | 2002-12-01 |  | 2005-12-01 | 2007-01-01 | 15455 | -69 | 15386 | 15386 | 100% | 0 | 0 | 0 | 2009.15 | -8.97 | 2000.1807 | -0.0007 | 0 | Completed in 2005. Financially completed in 2007. |  | 1999 |  | Non-Investment
FIN | UNEP | Implementation of the RMP: training programme for customs officers | Individual | ASP | BGD | REF | 29 | TRA | 08 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2002-04-01 | 2001-12-01 |  | 2004-07-01 | 2004-07-01 | 22500 | 0 | 22500 | 22500 | 100% | 0 | 0 |  | 2925 | 0 | 2925 | 0 | 0
FIN | UNEP | Implementation of the RMP: training of trainers in good refrigerant management practices and implementation of a national technicians training programme | Individual | ASP | BGD | REF | 29 | TRA | 11 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2002-03-01 | 2001-12-01 |  | 2004-12-01 | 2009-12-01 | 88000 | -24701 | 63299 | 63299 | 100% | 0 | 0 |  | 11440 | -3211.02 | 8228.98 | 0 | 0
FIN | UNDP | Preparation for HCFC phase-out investment activities (refrigeration sector) | Individual | ASP | BGD | REF | 57 | PRP | 34 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2011-12-01 | 2010-03-01 |  | 2012-09-01 | 2013-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 3750 | 0 | 3750 | 0 | 0 | Financially completed in 2013. |  | 2009 |  | Investment
ONG | UNDP | Preparation for HCFC phase-out investment activities (stage II) (refrigeration and air-conditioning sector) | Individual | ASP | BGD | REF | 75 | PRP | 43 | N | I | HCFC | 0 | 0 | 0 | 0 | 2015-11-01 | 2016-12-01 | 2017-06-01 | 2017-06-01 |  |  | 80000 | 0 | 80000 | 38.27 | 0.04784% | 79961.73 | 0 | 31984.692 | 5600 | 0 | 2.6789 | 5597.3211 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): UNDP CO has finalized the process to recruit of International Consultant for Project Development. Expected to be on board by Q1, 2017 upon received ASL from MP Prodoc signed (actual/planned, yes/no and date):Letter of Authorisation sent 15 June 2016 Missions undertaken (actual/planned):- TOR for consultants/subcontracts completed (actual/planned): completed Contract/PO/MOA agreements signed: Not signed due to closure of financial year First disbursement date (actual/planned): 42872Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:Delay has been made for conducting of Confidental refrence check of the Selected Consultant. Resolved. Awaiting for 2017 ASL under Output ID 000100881 and Output ID 000100883 for issung Contrcat and PO | HPMP Stage II prepration work started and will be submitted in 80th ExCom | 2015 |  | Non-Investment
CLO | IBRD | Country programme preparation |  | ASP | BGD | SEV | 04 | PRP | 07 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1992-06-01 |  |  | 1992-06-01 | 25564 | -25564 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Reconnaissance survey and training | Individual | ASP | BGD | SEV | 04 | TAS | 01 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1992-01-01 | 1992-06-01 |  | 1993-06-01 | 1997-12-01 | 55000 | -1150 | 53850 | 53850 | 100% | 0 | 0 | 0 | 7150 | -149.5 | 7000.5 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1991 |  | Non-Investment
FIN | UNDP | Country programme preparation | Individual | ASP | BGD | SEV | 06 | CPG | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-01-01 | 1993-06-01 |  | 1994-09-01 | 1997-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Institutional strengthening under the Multilateral Fund for the Implementation of the Montreal Protocol | Individual | ASP | BGD | SEV | 14 | INS | 04 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1994-09-01 | 1996-09-01 | 1997-09-01 |  | 1999-02-01 | 1999-12-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 | 0 | 19500 | 0 | 19500 | 0 | 0 | Completed in 1999. Financially completed in 1999. |  | 1994 | 1999-12-01 | Non-Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | BGD | SEV | 14 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-09-01 | 1994-11-01 | 1995-05-01 |  | 1996-12-01 | 1998-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Renewal of the institutional strengthening project for the phase-out of ODSs under the Montreal Protocol (Phase II) | Individual | ASP | BGD | SEV | 29 | INS | 09 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1999-11-01 | 1999-12-01 | 2001-12-01 |  | 2001-12-01 | 2008-08-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 2001. Financially completed in 2008. |  | 1999 |  | Non-Investment
FIN | UNDP | Renewal of the institutional strengthening project (phase III) | Individual | ASP | BGD | SEV | 35 | INS | 13 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2001-12-01 | 2003-02-01 | 2004-01-01 |  | 2004-12-01 | 2008-08-01 | 100000 | -2099 | 97901 | 97901 | 100% | 0 | 0 | 0 | 13000 | -272.87 | 12727.13 | 0 | 0 | Completed in 2004. Financially completed in 2008. |  | 2001 |  | Non-Investment
FIN | UNDP | Country programme update | Individual | ASP | BGD | SEV | 36 | CPG | 14 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2003-10-01 |  | 2006-12-01 | 2007-03-01 | 18750 | -202 | 18548 | 18548 | 100% | 0 | 0 | 0 | 2437.5 | -26 | 2411.5 | 0 | 0 | Completed in 2006. Financially completed in 2007. |  | 2002 |  | Non-Investment
FIN | UNDP | Renewal of the institutional strengthening project (phase IV) | Individual | ASP | BGD | SEV | 44 | INS | 23 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-12-01 | 2006-02-01 | 2006-12-01 |  | 2007-12-01 | 2009-08-01 | 130000 | -1588 | 128412 | 128412 | 100% | 0 | 0 | 0 | 9750 | -119.1 | 9630.9 | 0 | 0 | Completed in 2007.Financially completed in 2009. |  | 2004 |  | Non-Investment
FIN | UNDP | Renewal of the institutional strengthening project (phase V) | Individual | ASP | BGD | SEV | 53 | INS | 28 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-01-01 | 2009-11-01 |  | 2011-12-01 | 2012-07-01 | 130000 | -272.81 | 129727.19 | 129727 | 100% | 0.19 | 0 | 0 | 9750 | -20.46 | 9729.525 | 0.01505 | 0 | Financially completed in 2012. | The project is being financially closed by June 12. | 2007 |  | Non-Investment
FIN | UNDP | Renewal of the institutional strengthening project (phase VI) | Individual | ASP | BGD | SEV | 61 | INS | 37 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2010-07-01 | 2012-01-01 | 2012-06-01 |  | 2014-06-01 | 2015-12-01 | 130000 | -1140 | 128860 | 128860 | 100% | 0 | 0 | 0 | 9750 | -85.5 | 9664.5 | 0 | 0 | Financially Completed in 2015. | Monitoring of HPMP implementation and regulations, including licensing systems ongoing in Q1 of 2014. | 2010 |  | Non-Investment
ONG | UNDP | Renewal of the institutional strengthening project (phase VII: 1/2014-12/2015) | Individual | ASP | BGD | SEV | 71 | INS | 41 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2013-12-01 | 2015-03-01 | 2015-12-01 | 2017-06-01 |  |  | 130000 | 0 | 130000 | 113330.32 | 87.18% | 16669.68 | 0 | 6667.872 | 9100 | 0 | 7933.1224 | 1166.8776 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Progress was made as per the planned activities. Policy of ODS import for the year 2015 and 2016 was reviewed, data update survey was conducted for the year 2014 and 2015, CP and Article 7 data reported for the year 2014 and 2015, International Ozone day were observed during 2015 and 2016. Prodoc signed (actual/planned, yes/no and date):42064 Missions undertaken (actual/planned):- TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: signed earlier First disbursement date (actual/planned): 42064Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | Remaining amount will be utilized by Q2, 2017. ASL 2017 received. IS VIII will start after utalizing the previous balance. AWP finalized. | 2013 |  | Non-Investment
ONG | UNDP | Survey of ODS alternatives at the national level | Individual | ASP | BGD | SEV | 75 | TAS | 46 | N | I | HCFC | 0 | 0 | 0 | 0 | 2015-11-01 | 2016-09-01 | 2016-12-01 | 2017-03-01 |  |  | 55000 | 0 | 55000 | 35893.75 | 65.26% | 19106.25 | 9009.12 | 7642.5 | 4950 | 0 | 3230.4375 | 1719.5625 | 810.8208 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): The survey has been completed and draft report submitted to International Consultant for review. Prodoc signed (actual/planned, yes/no and date):Letter of Authorisation sent 15 June 2016 Missions undertaken (actual/planned):- TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: 28/09/2016 First disbursement date (actual/planned): 42614Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:ASL receipt, Resolved | Final version will be submitted after the review by International Consultant | 2015 |  | Non-Investment
ONG | UNDP | Renewal of the institutional strengthening project (phase VIII: 1/2017-12/2018) | Individual | ASP | BGD | SEV | 77 | INS | 47 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2016-12-01 |  | 2018-12-01 | 2017-12-01 |  |  | 166400 | 0 | 166400 | 0 | 0% | 166400 | 0 | 66560 | 11648 | 0 | 0 | 11648 | 0 | Newly Approved | DoA sent Feb 2017. Awaiting prodoc & AWP from CO for ASL request. | 2016 |  | Non-Investment
FIN | IBRD | Terminal phaseout management plan | Multiyear | LAC | BHA | PHA | 35 | INV | 08 | N | I | CFC | 18 | 18 | 0 | 0 | 2001-12-01 | 2004-11-01 | 2003-12-01 |  | 2003-12-01 | 2009-06-01 | 240000 | 0 | 240000 | 240000 | 100% | 0 | 0 |  | 31200 | 0 | 31200 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Terminal phase-out management plan: 2004-2005 biennial programme | Multiyear | LAC | BHA | PHA | 44 | INV | 12 | N | I | CFC | 23 | 23 | 0 | 0 | 2004-12-01 | 2008-01-01 | 2005-12-01 |  | 2005-12-01 | 2009-06-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 |  | 26000 | 0 | 26000 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Terminal phase-out management plan: 2006-2007 biennial programme | Multiyear | LAC | BHA | PHA | 51 | INV | 14 | N | I | CFC | 25 | 25 | 0 | 0 | 2007-03-01 | 2009-06-01 | 2009-03-01 |  | 2009-01-01 | 2009-06-01 | 120000 | -29054 | 90946 | 90946 | 100% | 0 | 0 |  | 15600 | -3777.02 | 11822.98 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | BHA | PHA | 55 | PRP | 15 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2010-11-01 | 2009-07-01 |  | 2013-12-01 | 2014-12-01 | 85000 | -5892 | 79108 | 79108 | 100% | 0 | 0 |  | 11050 | -765.96 | 10284.04 | 0 | 0
COM | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | BHA | PHA | 65 | INV | 18 | A | I |  | 0 | 0 |  |  | 2011-11-01 | 2013-05-01 | 2013-11-30 |  | 2015-12-01 |  | 105128 | 0 | 105128 | 105087.73 | 99.96% | 40.27 | 0 | 1 | 9462 | 0 | 9458 | 4 | 0 | The project was operationally completed. |  |  |  | INV
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | BHA | PHA | 65 | TAS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-06-01 | 2013-11-01 |  | 2013-12-01 | 2014-01-01 | 18200 | 0 | 18200 | 18200 | 100% | 0 | 0 |  | 2366 | 0 | 2366 | 0 | 0
COM | UNIDO | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | AFR | BHA | PHA | 71 | INV | 20 | A | I | HCFC | 0.2 | 0.2 |  |  | 2013-12-01 | 2015-08-01 | 2016-12-31 |  | 2015-12-01 |  | 10464 | 0 | 10464 | 10209.21 | 97.57% | 254.79 | 0 | 1 | 942 | 0 | 919 | 23 | 0 | The project was operationally completed. |  |  |  | INV
ONG | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Individual | LAC | BHA | PHA | 71 | TAS | 19 | A | I |  | 0 |  | 0 |  | 2013-12-01 |  | 2016-11-01 | 2017-03-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 30000 | 3000 | 3900 | 0 | 0 | 3900 | 3900 | Brief progress report (actual/planned): Verification Consultant hired in Nov-16 ___ Legal arrangements (actual/planned): ___ First mission (actual/planned): ---/Dec-16___ TOR completed (actual/planned): Jun-16/Sep-16___ First disbursement date (actual/planned): --/Oct-16___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): no___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): no.___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): Mission took place in Jan-17. Information collected and draft report sent to country for comments. Report with comments from NOU sent to UN Environment for review in Feb-17. Review is undergoing. Completion date revised to reflect actual completion of activities ___ Legal arrangements (actual/planned): ___ First mission (actual/planned): Jan-17/Dec-16___ TOR completed (actual/planned): Jun-16/Sep-16___ First disbursement date (actual/planned): Jan-17/Oct-16___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): no___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): no.___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | BHA | PHA | 71 | TAS | 21 | A | I |  | 0.2 |  | 0 |  | 2013-12-01 | 2014-10-01 | 2016-12-01 | 2017-09-01 |  |  | 49550 | 0 | 49550 | 1290.1 | 2.604% | 48259.9 | 48259.9 | 4825.99 | 6442 | 0 | 167.726 | 6274.274 | 6274.274 | Brief progress report (actual/planned): ___SSFA signed in Apr-16. First disbursement processed, transfer confirmed in Jul-16. Legal arrangements (actual/planned): Apr-16/Mar-15___ First mission (actual/planned): ___ TOR completed (actual/planned): ___ First disbursement date (actual/planned): Jul-16/Jun-15___ All funds disbursed (yes/no): No___ Any delay? (yes/no): yes___ If Yes, reasons for delay & action plan to resolve: changes in clearance processes of legal instruments in The Bahamas and requests to modify certain clauses that required legal department clearance delayed the signature of this agreement. UN Environment processed requests and clarifications promptly as they were raised ___ If Yes, will delay have impact on project completion date (yes/no): yes___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): ___Follow-up on progress and financial reports to process second installment of SSFA. Legal arrangements (actual/planned): Apr-16/Mar-15___ First mission (actual/planned): ___ TOR completed (actual/planned): ___ First disbursement date (actual/planned): Jul-16/Jun-15___ All funds disbursed (yes/no): No___ Any delay? (yes/no): yes___ If Yes, reasons for delay & action plan to resolve: changes in clearance processes of legal instruments in The Bahamas and requests to modify certain clauses that required legal department clearance delayed the signature of this agreement. UN Environment processed requests and clarifications promptly as they were raised ___ If Yes, will delay have impact on project completion date (yes/no): yes. Completion date revised to reflect timeframe of signed SSFA___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___
FIN | UNDP | Project preparation in refrigeration recycling | Individual | LAC | BHA | REF | 21 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2000-12-01 | 15000 | -2543 | 12457 | 12457 | 100% | 0 | 0 | 0 | 1950 | -330.59 | 1619.41 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Implementation of the RMP: Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | BHA | REF | 23 | TAS | 05 | A | I | CFC | 12.6 | 12.6 | 0 | 0 | 1997-11-01 | 1999-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-05-01 | 151400 | -12625 | 138775 | 138775 | 100% | 0 | 0 | 0 | 19682 | -1641.25 | 18040.75 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNEP | Implementation of the RMP: training in monitoring and controlling of ODSs | Individual | LAC | BHA | REF | 23 | TRA | 04 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 2002-08-01 | 1998-02-01 |  | 2005-09-01 | 2008-12-01 | 26500 | -8334 | 18166 | 18166 | 100% | 0 | 0 |  | 3445 | -1084 | 2361 | 0 | 0
FIN | UNEP | Implementation of the RMP: training the trainers of technicians in the refrigeration sector | Individual | LAC | BHA | REF | 23 | TRA | 06 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 2002-05-01 | 2003-11-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Country programme preparation | Individual | LAC | BHA | SEV | 11 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1995-02-01 |  | 1995-10-01 | 1995-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNEP | Institutional strengthening for the phase-out of ODSs under the Montreal Protocol | Individual | LAC | BHA | SEV | 19 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1997-05-01 | 1999-05-01 |  | 2000-03-01 | 2006-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Preparation of a terminal phase-out plan | RMP | LAC | BHA | SEV | 27 | PRP | 07 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-06-01 | 2000-04-01 |  | 2001-12-01 | 2002-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project: phase 2 (one year) | Individual | LAC | BHA | SEV | 39 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2004-12-01 | 2004-04-01 |  | 2006-07-01 | 2007-07-01 | 21666 | 0 | 21666 | 21666 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase II ) | Individual | LAC | BHA | SEV | 42 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-12-01 | 2005-04-01 |  | 2006-07-01 | 2009-07-01 | 21667 | 0 | 21667 | 21667 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase III ) | Individual | LAC | BHA | SEV | 50 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-06-01 | 2008-07-01 |  | 2010-07-01 | 2011-07-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | LAC | BHA | SEV | 61 | INS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2012-04-01 | 2012-06-01 |  | 2014-01-01 | 2014-12-01 | 60000 | -50 | 59950 | 59950 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of the institutional strengthening project (phase V: 4/2014-3/2016) | Individual | LAC | BHA | SEV | 72 | INS | 22 | A | I |  | 0 |  | 0 |  | 2014-05-01 | 2016-03-01 | 2016-03-01 | 2017-12-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 48387 | 6000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): 2015 CP Data and Art. 7 Data have been reported. Country managing implementation of HPMP, ODS alternatives Survey and HFC Inventories. NOU participated in the Joint Network Meeting in Chile May-16 and the Caribbean Thematic Meeting on ODS alternatives Surveys in Barbados, Dec-16. Preparation of next phase of IS and approval in ExCom 77__Legal arrangements (actual/planned): Dec-15/ Dec-14___Initial stages of project implementation (actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): Jan-16/ Dec-15.___ All funds disbursed (yes/no): NO ___ Any delay? (yes/no): yes___ If Yes, reasons for delay & action plan to resolve: Signature of SSFA by PS requires previous approval of Cabinet. Adjustments requested to the text were addressed by UN Environment as early as possible. ___ If Yes, will delay have impact on project completion date (yes/no): yes. ___ Any ongoing problems (yes/no): no. ___ If Yes, is any action required by ExCom: n/a. | Brief progress report (actual/planned):CP data for 2016 is being collected and analyzed. ODS alternatives survey is being coordinated towards completion. __Legal arrangements (actual/planned): Dec-15/ Dec-14___Initial stages of project implementation (actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): Jan-16/ Dec-15.___ All funds disbursed (yes/no): No ___ Any delay? (yes/no): yes___ If Yes, reasons for delay & action plan to resolve: Signature of SSFA by PS requires previous approval of Cabinet. Adjustments requested to the text were addressed by UN Environment as early as possible. ___ If Yes, will delay have impact on project completion date (yes/no): yes. ___ Any ongoing problems (yes/no): no. ___ If Yes, is any action required by ExCom: n/a. |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor project implementation progress and the disbursement rate of approved funds.
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | LAC | BHA | SEV | 75 | TAS | 23 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-05-01 | 2016-12-01 | 2017-06-01 |  |  | 20000 | 0 | 20000 | 0 | 0% | 20000 | 20000 | 2000 | 2600 | 0 | 0 | 2600 | 2600 | Brief progress report (actual/planned): SSFA signed by UN Environment in Apr-2016, and in May-16 by country. Regional Consultant selected and contract signed in Jul-16. National consultants hired in May-16 and assisting with collection of information ___. Legal arrangements (actual/planned): May-16/Jan-16 ___ First mission (actual/planned):Dec-16/Mar-16 ___ TOR completed (actual/planned): May-16/Feb-16___ First disbursement date (actual/planned): May-16/May-16 ___ All funds disbursed (yes/no): No___ Any delay? (yes/no): no___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no):___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): National consultants to finalize collection of information in 1Q of 2017. Completion date revised to reflect date of ExCom where Survey is to be submitted ___. Legal arrangements (actual/planned): May-16/Jan-16 ___ First mission (actual/planned):Dec-16/Mar-16 ___ TOR completed (actual/planned): May-16/Feb-16___ First disbursement date (actual/planned): May-16/May-16 ___ All funds disbursed (yes/no): No___ Any delay? (yes/no): no___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no):___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___
ONG | UNEP | Extension of the institutional strengthening project (phase VI: 11/2016-10/2018) | Individual | LAC | BHA | SEV | 77 | INS | 24 | A | I |  | 0 |  | 0 |  | 2016-12-01 |  | 2018-10-01 | 2018-10-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | Newly approved project | Brief progress report (actual/planned): NOU coordinating completion of ODS Alternatives Survey and HFC Inventory. NOU coordinated mission from Verification Consultant in Jan-17 to collect necessary data for the report. Draft SSFA of new phase to be discusssed with country in Mar-17. Country collecting information for 2016 CP data and Art. 7 data reports.___ Legal arrangements(actual/planned): ---/Apr-17.___Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): ---/May-17.___ All funds disbursed (yes/no): no ___ Any delay?(yes/no): no.___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): No.___ If Yes, is any action required by ExCom: ___
CLO | UNIDO | Project preparation in the aerosol sector | Individual | EUR | BHE | ARS | 30 | PRP | 03 | A | I |  | 0 | 0 |  |  | 2000-03-01 |  | 2001-04-01 |  |  | 2002-04-01 | 15000 | -15000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 1950 | -1950 | 0 | 0 | 0 | CLO
FIN | UNIDO | Project preparation in the flexible foam sector | Individual | EUR | BHE | FOA | 30 | PRP | 04 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2001-08-01 | 2001-04-01 |  | 2002-10-01 | 2003-06-01 | 15000 | -238 | 14762 | 14762.25 | 100% | -0.25 | 0 |  | 1950 | -34 | 1916 | 0 | 0 | FIN
FIN | UNIDO | Preparation of two investment projects in the flexible foam sector | Individual | EUR | BHE | FOA | 34 | PRP | 07 | A | I |  | 0 | 0 |  |  | 2001-07-01 | 2002-08-01 | 2002-08-01 |  | 2004-01-01 | 2004-04-01 | 15000 | -738 | 14262 | 14262.04 | 100% | -0.04 | 0 |  | 1950 | -99 | 1851 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to methylene chloride in the production of flexible slab stock foam at Inga Co. | Individual | EUR | BHE | FOA | 35 | INV | 08 | A | I | CFC | 21 | 21 |  |  | 2001-12-01 | 2002-03-01 | 2004-07-01 |  | 2005-12-01 | 2006-12-01 | 101950 | -1506 | 100444 | 100444.19 | 100% | -0.19 | 0 |  | 13254 | -196 | 13058 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of an investment project in the rigid foam sector | Individual | EUR | BHE | FOA | 36 | PRP | 12 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2003-09-01 | 2003-04-01 |  | 2004-01-01 | 2004-12-01 | 15000 | -417 | 14583 | 14583.12 | 100% | -0.12 | 0 |  | 1950 | -57 | 1893 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of CFC-11 by conversion to n-pentane in the manufacture of rigid foam products for insulating purposes at Stirokart Co. | Individual | EUR | BHE | FOA | 39 | INV | 15 | A | I | CFC | 33 | 33 |  |  | 2003-04-01 | 2004-04-01 | 2004-07-01 |  | 2006-12-01 | 2009-05-01 | 364650 | -15 | 364635 | 364634.54 | 100% | 0.46 | 0 |  | 27349 | -1 | 27348 | 0 | 0 | FIN
FIN | UNIDO | Preparation for HCFC phase-out investment activities (rigid polyurethane foam applications) | Individual | EUR | BHE | FOA | 63 | PRP | 24 | A | I |  | 0 | 0 |  |  | 2011-04-01 | 2011-07-01 | 2012-03-31 |  | 2012-12-01 | 2014-04-01 | 30000 | -355 | 29645 | 29644.89 | 100% | 0.11 | 0 |  | 2250 | -27 | 2223 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Phase-out of methyl bromide in tobacco seedling vegetables and flower production sector | Individual | EUR | BHE | FUM | 41 | INV | 17 | A | I | MBR | 11.8 | 11.8 |  |  | 2003-12-01 | 2004-08-01 | 2006-12-01 |  | 2006-12-01 | 2008-12-01 | 229000 | -3337 | 225663 | 225662.9 | 100% | 0.1 | 0 |  | 20610 | -300 | 20310 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of halon consumption | Individual | EUR | BHE | HAL | 42 | TAS | 18 | A | I | HAL | 4.1 | 4.1 |  |  | 2004-04-01 | 2004-06-01 | 2006-04-01 |  | 2010-12-01 | 2011-12-01 | 64600 | -403 | 64197 | 64196.77 | 100% | 0.23 | 0 |  | 5814 | -36 | 5778 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a national ODS phase-out plan | Individual | EUR | BHE | PHA | 36 | PRP | 13 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-09-01 | 2003-07-01 |  | 2003-12-01 | 2005-05-01 | 80000 | -1922 | 78078 | 78077.52 | 100% | 0.48 | 0 |  | 10400 | -266 | 10134 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National ODS phase-out plan (first trance) | Multi-Year | EUR | BHE | PHA | 41 | INV | 16 | A | I | CFC TCA | 0 | 27.3 |  |  | 2003-12-01 | 2004-04-01 | 2004-12-01 |  | 2006-12-01 | 2009-05-01 | 265300 | -1999 | 263301 | 263301.14 | 100% | -0.14 | 0 |  | 19898 | -150 | 19748 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National ODS Phase-out Plan: second tranche | Multi-Year | EUR | BHE | PHA | 44 | INV | 21 | A | I | CFC TCA | 0 | 31.1 |  |  | 2004-12-01 | 2005-12-01 | 2005-12-01 |  | 2013-12-01 | 2014-08-01 | 295860 | -8124 | 287736 | 287735.57 | 100% | 0.43 | 0 |  | 22190 | -609 | 21580 | 1 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National ODS phase-out plan (third tranche) | Multi-Year | EUR | BHE | PHA | 52 | INV | 22 | A | I | CFC | 121.1 | 121 |  |  | 2007-07-01 | 2008-12-01 | 2008-07-31 |  | 2013-12-01 | 2014-08-01 | 303000 | -15044 | 287956 | 287956.25 | 100% | -0.25 | 0 |  | 22725 | -1128 | 21597 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | EUR | BHE | PHA | 55 | PRP | 23 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2009-12-01 | 2009-07-31 |  | 2012-04-01 | 2013-10-01 | 150000 | -1728 | 148272 | 148272.01 | 100% | -0.01 | 0 |  | 11250 | -130 | 11120 | 0 | 0 | FIN |  |  |  | NON-INV
COM | UNIDO | HCFC phase-out management plan (stage I, first tranche) (activities in the refrigeration servicing sector including policy actions) | Multi-Year | EUR | BHE | PHA | 66 | INV | 26 | A | I | HCFC | 0.2 | 0.2 |  |  | 2012-04-01 | 2013-11-01 | 2013-04-30 |  | 2015-12-01 |  | 76070 | 0 | 76070 | 76079.82 | 100% | -9.82 | 0 |  | 5705 | 0 | 5706 | -1 | 0 | The project was operationally completed. |  |  |  | INV
COM | UNIDO | HCFC phase-out management plan (stage I, first tranche) (conversion to cyclopentane in the manufacture of panels at Alternativa, and conversion to methyl formate (foam) and non-HCFCs refrigerant in 6 manufacturers of commercial refrigeration equipment) | Multi-Year | EUR | BHE | PHA | 66 | INV | 27 | A | I | HCFC | 5.77 | 5.77 |  |  | 2012-04-01 | 2013-01-01 | 2013-04-30 |  | 2015-12-01 |  | 555212 | 0 | 555212 | 554924.4 | 99.95% | 287.6 | 0 | 1 | 41641 | 0 | 41619 | 22 | 0 | The project was operationally completed. |  |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) (activities in the refrigeration servicing sector including policy actions) | Multi-Year | EUR | BHE | PHA | 72 | INV | 29 | A | I |  | 0 | 0 |  |  | 2014-05-01 | 2015-03-01 | 2016-12-31 | 2018-06-16 |  |  | 128979 | 0 | 128979 | 45598.78 | 35.35% | 83380.22 | 4837.45 | 30000 | 9029 | 0 | 3192 | 5837 | 339 | Request for the 3rd tranche was submitted to the 76 ExCom and approved in May 2016. The work plan included establishment of the National Code of Good Practice in Refrigeration and Air–condition Sectors, Update of ODS legislation at level of entities (Federation BiH and Rep. Srpska) as well as initiation of the training programme for the RAC sector. Milestones achieved: Milestone 1: National Code of Practice in RAC: No Milestone 2: Update of ODS legislation at level of entities: No Milestone 3: Work plan for the training programme for RAC sector: No Milestone 4: Work plan for the training programme for the customs officers and maritime agents: No Activities planned but not implemented, reasons and strategy: The NOU started various activities on RAC but could do only consultation with the RAC association. Further progress was hampered by lack of support from the management of the Ministry (changes of 3 Ministers over the last 2 years) so the NOU decided to focus on completion of investment activities and postpone the non-investment activities. Actions towards next goals: Training activities for customs officers and maritime agents. Was there any delay during the reporting year? Yes, as above. Any recurring problem? No Any impact on project completion date: Yes Any action required by Executive Committee? No | Milestones achieved: Milestone 1: National Code of Practice in RAC: No Milestone 2: Update of ODS legislation at level of entities: No Milestone 3: Work plan for the training programme for RAC sector: No Milestone 4: Work plan for the training programme for the customs officers and maritime agents: No Activities planned but not implemented, reasons and strategy: The NOU started various activities on RAC but could do only consultation with the RAC association. Further progress was hampered by lack of support from the management of the Ministry (changes of 3 Ministers over the last 2 years) so the NOU decided to focus on completion of investment activities and postpone the non-investment activities. Actions towards next goals: The NOU expected to submit the work plan for the non-investment activities by the end of April. Was there any delay during the reporting year? Yes, as above. Any recurring problem? No Any impact on project completion date: Yes Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | Verification report for stage I of HCFC phase-out management plan | Individual | EUR | BHE | PHA | 75 | TAS | 32 | A | I |  | 0 | 0 |  |  | 2015-11-01 | 2016-03-01 | 2017-03-01 | 2018-06-16 |  |  | 30000 | 0 | 30000 | 4216.07 | 14.05% | 25783.93 | 0 | 1000 | 2700 | 0 | 0 | 2700 | 0 | Verification of achievement of 2014 and 2015 ODS consumption targets in BIH was initiated in January and completed in March 2016 and submitted as part of the 3rd tranche request to the 76 ExCom. Milestones achieved: Milestone 1: Appointing verification consultant Yes Milestone 2: Verification report completed Yes Milestone 3: Verification Report submitted Yes Activities planned but not implemented, reasons and strategy: N.A. . Actions towards next goals: N.A. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: Yes, completion date extended in order to use the funds for 2016 and 2017 verification. Any action required by Executive Committee? No | Verification of consumption targets for 2016 and 2017 will be conducted for the tranche submission in 2018. |  |  | NON-INV
ONG | UNIDO | HCFC phase-out management plan (stage I, third tranche) (activities in the refrigeration servicing sector including policy actions) | Multi-Year | EUR | BHE | PHA | 76 | INV | 33 | A | I |  | 0 | 0 |  |  | 2016-05-01 |  | 2019-05-31 | 2019-05-31 |  |  | 117692 | 0 | 117692 | 0 | 0% | 117692 | 0 | 20000 | 8238 | 0 | 0 | 8238 | 0 | As above under BHE/PHA/72/INV/29 | As above under BHE/PHA/72/INV/29 |  |  | INV
FIN | UNIDO | Project preparation in the commercial/ domestic refrigeration sector | Individual | EUR | BHE | REF | 33 | PRP | 05 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-08-01 | 2002-04-01 |  | 2003-07-01 | 2004-09-01 | 15000 | -8025 | 6975 | 6975.21 | 100% | -0.21 | 0 |  | 1950 | -1045 | 905 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project preparation in the commercial refrigeration sector | Individual | EUR | BHE | REF | 33 | PRP | 06 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-08-01 | 2002-04-01 |  | 2003-07-01 | 2004-04-01 | 15000 | -1613 | 13387 | 13387.29 | 100% | -0.29 | 0 |  | 1950 | -212 | 1738 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134 and foam blowing agent CFC-11 with cyclopentane in the manufacture of commercial refrigeration equipment at Bira, Bihac | Individual | EUR | BHE | REF | 35 | INV | 09 | A | I | CFC | 29 | 29 |  |  | 2001-12-01 | 2002-09-01 | 2004-05-01 |  | 2005-12-01 | 2006-12-01 | 536956 | -795 | 536161 | 536160.65 | 100% | 0.35 | 0 |  | 69065 | -87 | 68978 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Replacement of refrigerants CFC-12 and R-502 with HFC-134a and R-404A, and foam blowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment and cold refrigeration chambers at Soko | Individual | EUR | BHE | REF | 35 | INV | 10 | A | I | CFC | 17.4 | 17.4 |  |  | 2001-12-01 | 2002-12-01 | 2004-05-01 |  | 2004-06-01 | 2005-05-01 | 159707 | -818 | 158889 | 158888.79 | 100% | 0.21 | 0 |  | 20762 | -139 | 20623 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of two investment projects in the commercial refrigeration sector | Individual | EUR | BHE | REF | 36 | PRP | 11 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-10-01 | 2003-04-01 |  | 2003-07-01 | 2004-09-01 | 15000 | -3464 | 11536 | 11536.49 | 100% | -0.49 | 0 |  | 1950 | -453 | 1497 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Replacement of CFC-12 with HFC-134a, CFC-11 with HCFC-141b, and TCA with non-cleaning process in the manufacture of commercial refrigeration equipment, panels, and heat exchangers at three enterprises (Soko Paneli, Soko IPV and Kuca Leda) | Individual | EUR | BHE | REF | 39 | INV | 14 | A | I | CFC TCA | 13.7 | 13.7 |  |  | 2003-04-01 | 2003-11-01 | 2004-07-01 |  | 2005-12-01 | 2007-09-01 | 175283 | -5869 | 169414 | 169413.92 | 100% | 0.08 | 0 |  | 15775 | -528 | 15247 | 0 | 0 | FIN
FIN | UNIDO | Country Programme Preparation | Individual | EUR | BHE | SEV | 21 | CPG | 01 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-08-01 | 1998-02-01 |  | 1998-12-01 | 2000-07-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | -2 | 10398 | 0 | 0 | FIN
FIN | UNIDO | Establishment of an Ozone Unit | Individual | EUR | BHE | SEV | 27 | INS | 02 | N | I |  | 0 | 0 |  |  | 1999-03-01 | 2001-05-01 | 2002-04-01 |  | 2004-12-01 | 2005-12-01 | 110000 | -5291 | 104709 | 104708.57 | 100% | 0.43 | 0 |  | 14300 | -709 | 13591 | 0 | 0 | FIN |  |  | 2003-12-01 | NON-INV
FIN | UNIDO | Extension of institutional strengthening: phase II | Individual | EUR | BHE | SEV | 43 | INS | 19 | N | I |  | 0 | 0 |  |  | 2004-07-01 | 2008-12-01 | 2006-07-01 |  | 2011-12-01 | 2014-07-01 | 95333 | -1592 | 93741 | 93741.41 | 100% | -0.41 | 0 |  | 7150 | -119 | 7031 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Extension of the institutional strengthening project (phase III: 3/2012-2/2014) | Individual | EUR | BHE | SEV | 65 | INS | 25 | N | I |  | 0 | 0 |  |  | 2011-11-01 | 2012-04-01 | 2014-02-28 |  | 2013-12-01 | 2015-03-01 | 95333 | 0 | 95333 | 95333.27 | 100% | -0.27 | 0 |  | 7150 | 0 | 7150 | 0 | 0 | FIN |  |  |  | NON-INV
COM | UNIDO | Extension of the institutional strengthening project (phase IV: 3/2014-2/2016) | Individual | EUR | BHE | SEV | 71 | INS | 28 | N | I |  | 0 | 0 |  |  | 2013-12-01 | 2014-04-01 | 2016-02-29 |  | 2016-12-01 |  | 95333 | 0 | 95333 | 90974.11 | 95.43% | 4358.89 | 171.86 | 1 | 6673 | 0 | 6368 | 305 | 12.0302 | - NOU is fully staffed and activities are executed in line with project document and annual work plan. There are no delays in activities execution against work plan for the year 2016. - The project activities were committed as of end of 2016 and the project was completed. Milestone 1: NOU staff contracts released - Yes Milestone 2: Public awareness activities organized - yes Actions towards next goals: Operational completion was achieved. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | Financial closure is being initiated. |  |  | NON-INV
ONG | UNIDO | Extension of the institutional strengthening project (phase V: 3/2016-2/2018) | Individual | EUR | BHE | SEV | 74 | INS | 30 | N | I |  | 0 | 0 |  |  | 2015-05-01 | 2016-01-01 | 2018-02-28 | 2018-02-28 |  |  | 95333 | 0 | 95333 | 53493.06 | 56.11% | 41839.94 | 1730.1 | 30000 | 6673 | 0 | 0 | 6673 | 121.107 | - NOU is fully staffed and activities are executed in line with project document and annual work plan. There are no delays in activities execution against work plan. Milestone 1: NOU staff contracts released - Yes Milestone 2: Public awareness activities organized - yes Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Work plan for executing project activities for the year 2017 has been already developed by NOU. - NOU is fully staffed and bilateral consultations are scheduled 10- 12 May 2017. |  |  | NON-INV
ONG | UNIDO | Survey of ODS alternatives at the national level | Individual | EUR | BHE | SEV | 74 | TAS | 31 | A | I |  | 0 | 0 |  |  | 2015-05-01 | 2016-08-01 | 2016-05-31 | 2017-06-17 |  |  | 40000 | 0 | 40000 | 26320.23 | 65.8% | 13679.77 | 9419.15 | 13679.77 | 3600 | 0 | 0 | 3600 | 847.7235 | The green light from the NOU BIH to start the ODS surveys was received in June 2016. Three consultants were hired in July 2016. Milestones achieved: Milestone 1: Approval by the NOU to start the survey: Yes Milestone 2: Appointment of consultants: Yes Milestone 3: ODS alternatives survey report completed: No Activities planned but not implemented, reasons and strategy: N.A. . Actions towards next goals: N.A. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | Milestones achieved: Milestone 1: Submission of the preliminary results (Excel tables): Yes Milestone 2: ODS alternatives survey report completed - submission planned by 8 May 2017 Activities planned but not implemented, reasons and strategy: N.A. . Actions towards next goals: N.A. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | NON-INV |  | Continued Monitoring
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | ASP | BHU | PHA | 50 | PRP | 08 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-04-01 | 2007-11-01 |  | 2007-12-01 | 2007-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | ASP | BHU | PHA | 50 | PRP | 09 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2007-12-01 |  | 2007-03-01 | 2009-12-01 | 15000 | -10265 | 4735 | 4735 | 100% | 0 | 0 | 0 | 1125 | -769.88 | 355.125 | -0.005 | 0 | Completed in 2007. Financially completed in 2009. |  | 2006 |  | Investment
FIN | UNDP | Terminal phase-out management plan | One-off-Phaseout | ASP | BHU | PHA | 52 | INV | 11 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-02-01 | 2010-07-01 |  | 2009-12-01 | 2011-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 3150 | 0 | 3150 | 0 | 0 | Completed in 2009. Financially completed in 2011. |  | 2007 |  | Investment
FIN | UNEP | Terminal phase-out management plan | Individual | ASP | BHU | PHA | 52 | TAS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-05-01 | 2010-07-01 |  | 2010-12-01 | 2011-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | BHU | PHA | 55 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-05-01 | 2009-07-01 |  | 2010-12-01 | 2011-04-01 | 30000 | -4803 | 25197 | 25197 | 100% | 0 | 0 |  | 3900 | -624.39 | 3275.61 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan (additional) | RMP | ASP | BHU | PHA | 56 | PRP | 14 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-05-01 | 2009-11-01 |  | 2010-12-01 | 2011-04-01 | 55000 | -11314 | 43686 | 43686 | 100% | 0 | 0 |  | 7150 | -1470.82 | 5679.18 | 0 | 0
FIN | UNDP | HCFC phase-out management plan (first tranche) | Multi-Year | ASP | BHU | PHA | 63 | INV | 17 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-04-01 | 2013-01-01 | 2013-12-01 |  | 2013-12-01 | 2014-06-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 6300 | 0 | 6300 | 0 | 0 | Financially completed in 2014. | Completed in 2013. During Q1 of 2014, project activities are being monitored. | 2011 |  | Investment
FIN | UNEP | HCFC phase-out management plan (first tranche) | Multi-Year | ASP | BHU | PHA | 63 | TAS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2012-05-01 | 2013-12-01 |  | 2013-11-01 | 2016-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0 | Project financially completed | Project financially completed
COM | UNDP | HCFC phase-out management plan (second tranche) | Multi-year | ASP | BHU | PHA | 70 | INV | 19 | N | I | HCFC | 0 | 0 | 0 | 0 | 2013-07-01 | 2013-12-01 | 2016-07-01 |  | 2015-09-01 |  | 42000 | 0 | 42000 | 41259 | 98.24% | 741 | 0 | 629.85 | 3780 | 0 | 3713.31 | 66.69 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2015. |  | 2013 |  | Investment
FIN | UNEP | HCFC phase-out management plan (second tranche) | Multi-Year | ASP | BHU | PHA | 70 | TAS | 20 | A | I |  | 0 |  | 0 |  | 2013-07-01 | 2014-06-01 | 2016-07-01 |  | 2016-06-01 | 2016-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0 | Project financially completed | Project financially completed
COM | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Multi-Year | ASP | BHU | PHA | 73 | TAS | 22 | A | I |  | 0 |  | 0 |  | 2014-11-01 | 2016-08-01 | 2016-05-01 |  | 2016-12-01 |  | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project completed | Project completed
ONG | UNEP | HCFC phase-out management plan (third tranche) | Multi-Year | ASP | BHU | PHA | 76 | TAS | 25 | A | I |  | 0.2 |  | 0 |  | 2016-05-01 | 2016-10-01 | 2024-05-01 | 2024-05-01 |  |  | 84000 | 0 | 84000 | 16244.83 | 19.34% | 67755.17 | 67755.17 | 6775.517 | 10920 | 0 | 2111.8279 | 8808.1721 | 8808.1721 | Brief progress report (actual/planned): Newly approved. A technician training organized Legal arrangement (actual/ planned): SSFA signed in Sep 2016 First mission (actual/ planned): Not yet TOR completed (actual/ planned): n/a First disbursement date (actual/planned): actual Oct 2016 All funds disbursed (yes/no): no. Any delay? (yes/no): ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): Selection of the full time officer initiated. Criteria for GPP of airconditioning finalized. Legal arrangement (actual/ planned): SSFA signed in Sep 2016 First mission (actual/ planned): Not yet TOR completed (actual/ planned): n/a First disbursement date (actual/planned): actual Oct 2016 All funds disbursed (yes/no): no. Any delay? (yes/no): ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___
ONG | UNDP | HCFC phase-out management plan (third tranche) | Multi-Year | ASP | BHU | PHA | 76 | TAS | 26 | N | I | HCFC | 0.1 | 0 | 0 | 0 | 2016-05-01 |  | 2024-05-01 | 2017-05-01 |  |  | 57000 | 0 | 57000 | 0 | 0% | 57000 | 0 | 22800 | 5130 | 0 | 0 | 5130 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): ASL has been approved and work in progress Prodoc signed (actual/planned, yes/no and date):42736 Missions undertaken (actual/planned):- TOR for consultants/subcontracts completed (actual/planned): Contract/PO/MOA agreements signed: First disbursement date (actual/planned): 42856Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | AWP approved. |  |  | Investment
FIN | UNDP | Preparation of investment component of the refrigerant management plan | Individual | ASP | BHU | REF | 43 | PRP | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2004-07-01 | 2005-07-01 | 2006-07-01 |  | 2005-12-01 | 2006-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1125 | 0 | 1125 | 0 | 0 | Completed in 2005. Financially completed in 2006. |  | 2004 |  | Investment
FIN | UNDP | Implementation of the RMP: technical assistance in the refrigeration servicing sector | RMP-Component | ASP | BHU | REF | 45 | TAS | 06 | N | I | CFC | 0.1 | 0.1 | 0 | 0 | 2005-04-01 | 2005-07-01 | 2007-04-01 |  | 2006-12-01 | 2009-11-01 | 45000 | -41 | 44959 | 44959 | 100% | 0 | 0 | 0 | 4050 | -3.69 | 4046.31 | 0 | 0 | Completed in 2006.Financially completed in 2009. |  | 2005 |  | Non-Investment
FIN | UNEP | Implementation of the RMP: train the trainer programme for customs and enforcement officers | Individual | ASP | BHU | REF | 45 | TRA | 04 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-10-01 | 2006-04-01 |  | 2006-09-01 | 2007-09-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0
FIN | UNEP | Implementation of the RMP: train the trainer programme for refrigeration service technicians | Individual | ASP | BHU | REF | 45 | TRA | 05 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-11-01 | 2006-10-01 |  | 2006-09-01 | 2006-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0
FIN | UNEP | Preparation of country programme/RMP project | Individual | ASP | BHU | SEV | 43 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-12-01 | 2006-07-01 |  | 2005-07-01 | 2006-08-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 |  | 5850 | 0 | 5850 | 0 | 0
FIN | UNEP | Institutional strengthening project (phase I, start-up) | Individual | ASP | BHU | SEV | 43 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-12-01 | 2005-07-01 |  | 2005-07-01 | 2006-08-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Institutional strengthening project (phase I) | Individual | ASP | BHU | SEV | 46 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-11-01 | 2008-07-01 |  | 2007-07-01 | 2008-06-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase II) | Individual | ASP | BHU | SEV | 53 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-12-01 | 2009-11-01 |  | 2009-11-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | ASP | BHU | SEV | 58 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2010-06-01 | 2011-11-01 |  | 2011-12-01 | 2012-12-01 | 32500 | 27500 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase IV: 12/2011-11/2013) | Individual | ASP | BHU | SEV | 64 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-07-01 | 2013-11-01 |  | 2013-11-01 | 2014-03-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of institutional strengthening project (phase V: 12/2013-11/2015) | Individual | ASP | BHU | SEV | 71 | INS | 21 | A | I |  | 0 |  | 0 |  | 2013-12-01 | 2014-06-01 | 2015-11-01 |  | 2016-12-01 |  | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Brief progress report(actual/planned): The remaining activities were completed as the SSFA had to be extended. This project is now being closed as all outputs have been met. | Project completed
ONG | UNEP | Extension of institutional strengthening project (phase VI: 12/2015-11/2017) | Individual | ASP | BHU | SEV | 74 | INS | 23 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-09-01 | 2017-11-01 | 2017-12-01 |  |  | 60000 | 0 | 60000 | 30101.2 | 50.17% | 29898.8 | 29898.8 | 2989.88 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): No updates as the previous IS phase being finalized Legal arrangements(actual/planned): SSFA in place since Nov 2016 Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): Actual in Sep 2016 All funds disbursed (yes/no): No Any delay?(yes/no): ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): CP data and A7 data submitted Legal arrangements(actual/planned): SSFA in place since Nov 2016 Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): Actual in Sep 2016 All funds disbursed (yes/no): No Any delay?(yes/no): ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | ASP | BHU | SEV | 74 | TAS | 24 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-04-01 | 2016-05-01 | 2017-06-01 |  |  | 40000 | 0 | 40000 | 27.58 | 0.06895% | 39972.42 | 39972.42 | 3997.242 | 5200 | 0 | 3.5854 | 5196.4146 | 5196.4146 | Brief progress report (actual/planned): The final report submitted to Paris. Results and information about survey was shared in two stake holders’ workshops. Legal arrangements(actual/planned): Yes Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: SSFA amended to extend the duration First disbursement date (actual/planned): Apr 2016 All funds disbursed (yes/no): No Any delay?(yes/no): yes If Yes, reasons for delay & action plan to resolve: lack of expertise and relevant guidance on conducting the survey. If Yes, will delay have impact on project completion date (yes/no): No Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___ | Brief progress report: The final round of comments from UNEP submitted and the report is being reviewed
FIN | UNIDO | Workshop to raise awareness on use of methyl bromide in tobacco cultivation | Individual | AFR | BKF | FUM | 34 | TRA | 14 | A | I | MBR | 0 | 0 |  |  | 2001-07-01 | 2002-01-01 | 2002-08-01 |  | 2002-12-01 | 2003-06-01 | 30000 | -7497 | 22503 | 22503.12 | 100% | -0.12 | 0 |  | 3900 | -979 | 2921 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNEP | Project preparation request for TPMP | Individual | AFR | BKF | PHA | 47 | PRP | 18 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-03-01 | 2006-12-01 |  | 2006-09-01 | 2008-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0
FIN | Canada | Project preparation for the terminal phase-out management plan |  | AFR | BKF | PHA | 47 | PRP | 19 | A | I |  | 0 |  | 0 |  | 2005-11-01 | 2006-09-01 | 2006-12-01 |  | 2006-10-01 | 2006-10-01 | 10000 | -650 | 9350 | 9350 | 100% | 0 |  | 0 | 1300 | -100 | 1200 | 0 |  | TPMP prepared and submitted with UNEP at ExCom 50. Project completed. Remaining balance of $650 and associated support costs ($100) were returned to Fund. |  | 2005 |  | Non-Inv.
FIN | Canada | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | BKF | PHA | 50 | INV | 22 | A | I | CFC | 2 | 2 | 0 |  | 2006-11-01 | 2007-01-01 | 2008-03-01 |  | 2008-09-01 | 2008-10-01 | 98500 | 0 | 98500 | 98500 | 100% | 0 |  | 0 | 12805 | 0 | 12805 | 0 |  |  |  | 2006 |  | Investment
FIN | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-year | AFR | BKF | PHA | 50 | TAS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-07-01 | 2008-03-01 |  | 2008-03-01 | 2009-03-01 | 100900 | -631 | 100269 | 100269 | 100% | 0 | 0 |  | 13117 | -82.03 | 13034.97 | 0 | 0
FIN | Canada | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | BKF | PHA | 54 | INV | 24 | A | I | CFC | 5.4 | 5.4 | 0 |  | 2008-04-01 | 2008-10-01 | 2009-03-01 |  | 2010-12-01 | 2011-07-01 | 86500 | -3000 | 83500 | 83500 | 100% | 0 |  | 0 | 11245 | -495 | 10750 | 0 |  | Procurement of retrofit equipment and tools (2nd phase) completed in July 2009 ($57,481). $13,000 provided to Burkina Faso for awareness-raising activities and local purchase of tools. Additional technician training courses organized in 2009-beginning of 2010 by UNEP. Mission by EC in January 2010 revealed that tools had not yet been distributed to technicians, but this was subsequently reported by NOU to have been done. Project completed. $3,000 returned to the MLF with $495 in support costs, and noted at 64th ExCom meeting. |  | 2008 |  | Investment
FIN | UNEP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | BKF | PHA | 54 | TAS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-07-01 | 2009-03-01 |  | 2009-03-01 | 2010-12-01 | 102100 | 0 | 102100 | 102100 | 100% | 0 | 0 |  | 13273 | 0 | 13273 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | BKF | PHA | 55 | PRP | 25 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-02-01 | 2009-07-01 |  | 2010-12-01 | 2011-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan (additional) | RMP | AFR | BKF | PHA | 56 | PRP | 27 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-02-01 | 2009-11-01 |  | 2010-12-01 | 2011-12-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 |  | 7150 | 0 | 7150 | 0 | 0
FIN | UNEP | TPMP verification | Individual | AFR | BKF | PHA | 57 | TAS | 28 | A | I |  | 0 |  | 0 | 0 | 2009-04-01 | 2009-07-01 | 2010-03-01 |  | 2009-12-01 | 2010-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0
COM | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | BKF | PHA | 62 | INV | 30 | A | I |  | 0 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2013-12-31 |  | 2015-11-01 |  | 150000 | 0 | 150000 | 148785.97 | 99.19% | 1214.03 | 796.33 | 1 | 13500 | 0 | 13391 | 109 | 72 | The project was operationally completed. |  |  |  | INV
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | BKF | PHA | 62 | TAS | 29 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-04-01 | 2013-12-01 |  | 2013-12-01 |  | 120000 | 0 | 120000 | 119999.53 | 100% | 0.47 | -0.31 |  | 15600 | 0 | 15599.9389 | 0.0611 | -0.0403
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | AFR | BKF | PHA | 70 | TAS | 33 | A | I |  | 2 |  | 0 |  | 2013-07-01 | 2014-08-01 | 2016-07-01 | 2018-12-01 |  |  | 120000 | 0 | 120000 | 58446.73 | 48.71% | 61553.27 | 55499 | 6155.327 | 15600 | 0 | 7598.0749 | 8001.9251 | 7214.87 | Brief progress report (actual/planned): Country signed the SSFA in March 2014. Country trained 60 enforcement officers on identification of HCFC, 90 refrigeration technicians on recovery and recycling in 2016. Legal arrangements (actual/planned): Agreement signed in March 2014. Agreement split into two SSFA of $60,000 each. First payment of second SSFA sent on 12 January 2017. All activities under the SSFA are completed (as planned) YES___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _August 2014 __ All funds disbursed: Yes__ Any delay? (yes/no): Yes ___ If Yes, reasons for delay & action plan to resolve: __ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a __ | Brief progress report (actual/planned): Country signed the SSFA in March 2014. Country trained 60 enforcement officers on identification of HCFC, 90 refrigeration technicians on recovery and recycling in 2016. NOO trained 40enforcement officers and 55 RAC technicians in 2017. Project ongoing. Legal arrangements (actual/planned): Agreement signed in March 2014. Agreement split into two SSFA of $60,000 each. First payment of second SSFA sent on 12 January 2017. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _August 2014 __ All funds disbursed: no__ Any delay? (yes/no): No ___ If Yes, reasons for delay & action plan to resolve: __ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a __ |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor the signing of the second agreement between the Government and UNEP for the release of remaining funds.
FIN | UNEP | Training for refrigeration repair technicians | Individual | AFR | BKF | REF | 11 | TRA | 03 | A | I | CFC | 23 | 23 | 0 | 0 | 1993-11-01 | 1994-03-01 | 1996-11-01 |  | 1996-11-01 | 1999-04-01 | 41500 | 0 | 41500 | 41500 | 100% | 0 | 0 |  | 5395 | 0 | 5395 | 0 | 0
FIN | UNIDO | Refrigerant recovery and recycling scheme | RMP | AFR | BKF | REF | 22 | TAS | 05 | A | I | CFC | 15.48 | 15.48 |  |  | 1997-05-01 | 1997-08-01 | 1999-06-01 |  | 1998-12-01 | 2000-07-01 | 96000 | 0 | 96000 | 96000 | 100% | 0 | 0 |  | 12480 | 0 | 12480 | 0 | 0 | FIN
FIN | UNEP | Development of refrigerant management plan | RMP | AFR | BKF | REF | 24 | PRP | 07 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-05-01 | 1999-02-01 |  | 1999-10-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | Canada | Implementation of the RMP: training of customs officers programme | RMP | AFR | BKF | REF | 29 | TRA | 09 | A | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-03-01 | 2001-06-01 |  | 2002-08-01 | 2003-01-01 | 42500 | 0 | 42500 | 42500 | 100% | 0 |  | 0 | 5525 | 0 | 5525 | 0 |  | Project Complete. PCR submitted. |  | 1999 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: train the trainers and technicians in good refrigeration management practices | RMP | AFR | BKF | REF | 29 | TRA | 10 | A | I |  | 0 |  | 0 |  | 1999-11-01 | 2000-06-01 | 2001-06-01 |  | 2002-03-01 | 2002-03-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  | 0 | 5200 | 0 | 5200 | 0 |  | Training of technicians is completed as of March 2002. PCR submitted. |  | 1999 |  | Non-Inv.
FIN | UNDP | Implementation of the RMP: Incentive programme for the commercial and industrial refrigeration end-user sector | RMP-Component | AFR | BKF | REF | 32 | TAS | 11 | N | I | CFC | 27.5 | 27.5 | 0 | 0 | 2000-12-01 | 2001-04-01 | 2006-01-01 |  | 2006-12-01 | 2008-09-01 | 132250 | -7409 | 124841 | 124841 | 100% | 0 | 0 | 0 | 17192.5 | -963.2 | 16229.302 | -0.002 | 0 | Completed in 2006. Financially completed in 2008. |  | 2000 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: Monitoring the activities in the RMP | RMP-Component | AFR | BKF | REF | 34 | TAS | 13 | N | I | CFC | 3.4 | 3.4 | 0 | 0 | 2001-07-01 |  | 2007-08-01 |  | 2006-12-01 | 2008-09-01 | 16350 | -16350 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 2125.5 | -2126 | 0 | -0.5 | 0 | Completed in 2006. Financially completed in 2008. |  | 2001 |  | Non-Investment
FIN | UNEP | Country programme preparation | Individual | AFR | BKF | SEV | 06 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-01 | 1993-02-01 |  | 1993-11-01 | 1993-12-01 | 30000 | 3000 | 33000 | 33000 | 100% | 0 | 0 |  | 3900 | 390 | 4290 | 0 | 0
FIN | UNEP | Establishment of the Ozone Board | Individual | AFR | BKF | SEV | 11 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-12-01 | 1996-11-01 |  | 1997-06-01 | 1996-02-01 | 83500 | 0 | 83500 | 83500 | 100% | 0 | 0 |  | 10855 | 0 | 10855 | 0 | 0
FIN | UNEP | Workshop on monitoring and control of ODS consumption (customs training) | Individual | AFR | BKF | SEV | 11 | TRA | 04 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1994-11-01 |  | 1994-10-01 | 1994-12-01 | 14500 | 0 | 14500 | 14500 | 100% | 0 | 0 |  | 1885 | 0 | 1885 | 0 | 0
FIN | UNEP | Institutional strengthening renewal | Individual | AFR | BKF | SEV | 22 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1999-08-01 | 1999-12-01 | 55700 | 0 | 55700 | 55700 | 100% | 0 | 0 |  | 7241 | 0 | 7241 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening | Individual | AFR | BKF | SEV | 27 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-08-01 | 2001-04-01 |  | 2001-07-01 | 2001-12-01 | 55700 | 0 | 55700 | 55700 | 100% | 0 | 0 |  | 7241 | 0 | 7241 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (Phase IV) | Individual | AFR | BKF | SEV | 33 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-06-01 | 2003-04-01 |  | 2003-01-01 | 2003-12-01 | 55700 | 0 | 55700 | 55700 | 100% | 0 | 0 |  | 7241 | 0 | 7241 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase 5) | Individual | AFR | BKF | SEV | 38 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-02-01 | 2004-12-01 |  | 2004-12-01 | 2004-12-01 | 72410 | 0 | 72410 | 72410 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase VI) | Individual | AFR | BKF | SEV | 44 | INS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2006-12-01 |  | 2006-12-01 | 2008-12-01 | 72410 | 0 | 72410 | 72410 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VII) | Individual | AFR | BKF | SEV | 50 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-12-01 | 2008-11-01 |  | 2008-12-01 | 2009-12-01 | 72410 | 0 | 72410 | 72410 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VIII) | Individual | AFR | BKF | SEV | 56 | INS | 26 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-02-01 | 2010-12-01 |  | 2010-12-01 | 2012-12-01 | 72410 | 0 | 72410 | 72410 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IX) | Individual | AFR | BKF | SEV | 62 | INS | 31 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-02-01 | 2012-12-01 |  | 2012-12-01 | 2013-12-01 | 72410 | 0 | 72410 | 72410 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase X: 1/2013-12/2014) | Individual | AFR | BKF | SEV | 68 | INS | 32 | A | I |  | 0 |  | 0 | 0 | 2012-12-01 | 2013-03-01 | 2014-12-01 |  | 2015-12-01 | 2016-12-01 | 72410 | 0 | 72410 | 72410 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
ONG | UNEP | Extension of the institutional strengthening project (phase XI: 6/2015-5/2017) | Individual | AFR | BKF | SEV | 74 | INS | 34 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-04-01 | 2017-05-01 | 2017-12-01 |  |  | 72410 | 0 | 72410 | 36147.34 | 49.92% | 36262.66 | 36241.48 | 3626.266 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): SSFA signed in January 2016. Country reported 2015 Art. 7 and 2015 CP data. Country celebrated the 2016 Ozone day. Legal arrangements (actual/planned): Agreement signed in Jan. 2016. All activities under the SSFA are completed (as planned) __No_ First mission (actual/planned): August 2016 - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _April 2016. Second payment sent in Ocober 2016. All funds disbursed (yes/no): No_ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Brief progress report (actual/planned): SSFA signed in January 2016. Country reported 2015 Art. 7 and 2015 CP data. Country celebrated the 2016 Ozone day. Legal arrangements (actual/planned): Agreement signed in Jan. 2016. All activities under the SSFA are completed (as planned) __No_ First mission (actual/planned): August 2016 - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _April 2016. Second payment sent in Ocober 2016. All funds disbursed (yes/no): No_ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | AFR | BKF | SEV | 74 | TAS | 35 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-05-01 | 2016-05-01 | 2017-10-01 |  |  | 55000 | 0 | 55000 | 36.1 | 0.06564% | 54963.9 | 54963.9 | 5496.39 | 7150 | 0 | 4.693 | 7145.307 | 7145.307 | Brief progress report (actual/planned): Country signed the SSFA in April 2016 . First payment sent in May 2016. Local consultants hired in June 2016 and survey activities started in June 2016. Legal arrangements (actual/planned): Agreement signed in April 2016. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in May 2016 __ All funds disbursed (yes/no): _ n/a.__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Brief progress report (actual/planned): Country signed the SSFA in April 2016 . First payment sent in May 2016. Country submitted a draft of ODS survey report in January 2017. Legal arrangements (actual/planned): Agreement signed in April 2016. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in May 2016 __ All funds disbursed (yes/no): _ n/a.__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
FIN | UNDP | Project preparation in the foam sector | Individual | LAC | BOL | FOA | 21 | PRP | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1998-07-01 | 1997-12-01 |  | 1998-12-01 | 2000-12-01 | 25000 | -2187 | 22813 | 22813 | 100% | 0 | 0 | 0 | 3250 | -284.31 | 2965.69 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
CLO | Belgium | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Quimica Andina |  | LAC | BOL | FOA | 28 | INV | 10 | A | I |  | 5 | 0 |  |  | 1999-07-01 | 2000-01-01 | 2002-02-01 |  |  |  | 108480 | -108480 | 0 | 0 | 0% | 0 |  | 0 | 0 |  |  | 0 |  | Agreement between UNDP and the Belgian Government finally signed in September 2000. However, funds not yet received as of 31 December 2000. Info as of 31 May 2001: funds received in Feb. 2001. Project document not yet signed by Bolivian Govt. However, invitations to bid were sent out and bid analysi was done. However, we had to re-bid because offers did not meet specs for one machine. New bid analysis on-going. Info as of 31 December 2001: New ministry was undergoing some verification of the enterprises which were being considered for MLF funding since according to some new regulations, in order for Quimica Andina to qualify it needed to be one of the higher national consumers of CFC-11. Only if this was the case would the project be approved and the PRODOC signed. |  | 36923
FIN | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | LAC | BOL | FOA | 33 | PRP | 13 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Foam sector ODS phaseout (two enterprises: Isolcruz and Teplo) | Individual | LAC | BOL | FOA | 35 | INV | 15 | A | I | CFC | 4.9 | 4.9 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-01-01 |  | 2004-05-01 | 2007-01-01 | 161211 | -5875 | 155336 | 155336 | 100% | 0 | 0 | 0 | 20957.43 | -763.73 | 20193.6957 | 0.0043 | 0 | Completed in 2004. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | LAC | BOL | FOA | 57 | PRP | 34 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-03-01 | 2010-03-01 |  | 2014-12-01 | 2014-12-01 | 50000 | -34137 | 15863 | 15863 | 100% | 0 | 0 | 0 | 3750 | -2560 | 1190 | 0 | 0 | Financially Completed in 2015. | As planned, discussions were held with the local NOU to schedule activities for starting activities on foam sector. | 2009 |  | Investment
FIN | UNDP | Preparation of a methyl bromide alternative project in soil fumigation (cotton and soy) | Individual | LAC | BOL | FUM | 27 | PRP | 09 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2001-12-01 | 2003-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Project preparation in soil fumigation | Individual | LAC | BOL | FUM | 33 | PRP | 11 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Terminal methyl bromide phase-out, excluding QPS applications | One-off-Phaseout | LAC | BOL | FUM | 35 | INV | 16 | N | I | MeBr | 1.5 | 1.5 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-12-01 |  | 2007-12-01 | 2011-10-01 | 221032 | -1 | 221031 | 221031 | 100% | 0 | 0 | 0 | 28734.16 | -0.13 | 28734.03 | 0 | 0 | Completed in 2007. Financially completed in 2011. |  | 2001 |  | Investment
FIN | Canada | Project preparation for the terminal phase-out management plan |  | LAC | BOL | PHA | 47 | PRP | 27 | A | I |  | 0 |  | 0 |  | 2005-11-01 | 2006-09-01 | 2006-12-01 |  | 2007-02-01 | 2007-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  | 0 | 3900 | 0 | 3900 | 0 |  | TPMP prepared, submitted to ExCom 51 and approved. Project and last payment completed in February 2007. |  | 2005 |  | Non-Inv.
FIN | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | LAC | BOL | PHA | 51 | INV | 29 | N | I | CFC | 0.2 | 0.2 | 0 | 0 | 2007-03-01 | 2007-11-01 | 2010-03-01 |  | 2009-12-01 | 2013-02-01 | 151000 | 0 | 151000 | 151000 | 100% | 0 | 0 | 0 | 11325 | 0 | 11325 | 0 | 0 | Financially completed in 2013. |  | 2007 |  | Investment
FIN | Canada | Terminal phase-out management plan (first tranche) | Multi-Year | LAC | BOL | PHA | 51 | TAS | 28 | A | I | CFC,CTC | 15.3 | 15.3 | 0 |  | 2007-03-01 | 2007-06-01 | 2009-12-01 |  | 2009-03-01 | 2009-04-01 | 79000 | 0 | 79000 | 79000 | 100% | 0 |  | 0 | 10270 | 0 | 10270 | 0 |  | Completion of the revision of the legal framework, diffusion of awareness-raising material, training of 159 customs officers. Inspection visits to workshops and importers took place in several cities throughout 2009 to evaluate their compliance with national legislation and verify the consumption. Most project activities completed by March 2009. A CTC workshop with users was rescheduled under second tranche to September 2009 due to coordination issues. |  | 2007 |  | Investment
FIN | Germany | Preparation of a HCFC phase-out management plan (multiple sectors) | Individual | LAC | BOL | PHA | 55 | PRP | 31 | A | I | HCFC | 0 |  | 0 |  | 2008-07-01 | 2009-03-01 | 2009-07-01 |  | 2011-04-01 | 2012-12-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 | 0 | 19500 | 0 | 19500 | 0 | 0 | HPMP approved at 64th meeting
FIN | UNDP | Terminal phase-out management plan (second tranche) | Multi-Year | LAC | BOL | PHA | 57 | INV | 33 | N | I | CFC | 11.4 | 11.4 | 0 | 0 | 2009-04-01 | 2010-01-01 | 2011-03-01 |  | 2012-10-01 | 2014-04-01 | 222000 | -152 | 221848 | 221848 | 100% | 0 | 0 | 0 | 16650 | -11.4 | 16638.6 | 0 | 0 | Financially completed in 2014. | Completed in 2012. 5000 US$ from Environment Canada has been transferred to UNDP and will be implemented under this project.The remaining resources will be used for training of technicians in Bolivia. | 2009 |  | Investment
FIN | Canada | Terminal phase-out management plan (second tranche) | Multi-Year | LAC | BOL | PHA | 57 | TAS | 32 | A | I | CFC, CTC | 0 | 0 | 0 |  | 2009-04-01 | 2009-09-01 | 2010-03-01 |  | 2013-07-01 | 2013-07-01 | 88000 | -5000 | 83000 | 83000 | 100% | 0 |  | 0 | 11440 | -650 | 10790 | 0 |  | Activities undertaken consists of a CTC information workshop (including printing and distribution of report on alternatives to CTC for laboratories); 62 inspections of servicing workshops; modifications to ODS regulations and printing regulatory text; printing of 300 copies of customs training manual; various public awareness activities, and project management. In 2012, Bolivia advised that it still held about US $7,000 in funds advanced from Canada and proposed to use them for project management and awareness-raising activities. Despite repeated attempts, Canada never received a final report on the use of these funds, but considered the project closed as of July 2013. Note that ExCom 68 approved transfer of remaining funds not transferred from Canada (US $5,000) to UNDP for HCFC activities under UNDP's final tranche of the TPMP. | No additional information up to April 29 2013. | 2009 |  | Investment
FIN | Germany | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | BOL | PHA | 64 | INV | 36 | A | I | HCFC | 0 | 0 | 0 |  | 2011-07-01 | 2011-10-01 | 2015-07-01 |  | 2015-05-01 | 2015-06-01 | 94500 | 0 | 94500 | 94500 | 100% | 0 | 0 | 0 | 12285 | 0 | 12285 | 0 |  | Implementation of train the trainer and RAC training as well as dissemination activities. | financially completed
TRF | Germany | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | BOL | PHA | 72 | INV | 38 | A | I | HCFC | 0 |  | 0 |  | 2014-05-01 |  | 2016-05-01 |  |  | 2015-05-01 | 94500 | -94500 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 12285 | -12285 | 0 | 0 |  | Transferred to UNIDO at 74th Excom (May 2015)
COM | UNIDO | HCFC phase-out management plan (stage I, second tranche) (transfer of project) | Multi-Year | LAC | BOL | PHA | 74 | INV | 42 | A | I | HCFC | 0.5 | 0.5 |  |  | 2015-05-01 | 2015-08-01 | 2017-05-31 |  | 2016-12-01 |  | 94500 | 0 | 94500 | 67760.34 | 71.7% | 26739.66 | 26777.6 | 26000 | 8505 | 0 | 0 | 8505 | 2409.984 | Delivery and distribution of tools for training centers was carried out. Agreement to create new centers and distribution of tools to the centers was reached. Program for training purposes was established. -The implementation of the project is again jeopardized: the fifth National Ozone Officer since UNIDO is implementing the project was removed after two months. - Delay in project implementation: No - Recurring problem: continuous fluctuations at the National Ozone Unit - Impact on project completion date: No - No action required by Executive Committee. | Project completed, Financial closure is ongoing. |  |  | INV
TRF | Germany | Verification report for stage I of HCFC phase-out management plan |  | LAC | BOL | PHA | 74 | TAS | 40 | A | I |  | 0 |  | 0 |  | 2015-05-01 |  | 2015-05-01 |  |  | 2015-05-01 | 30000 | -30000 | 0 |  | #DIV/0! | 0 |  |  | 3900 | -3900 |  | 0 |  | Transferred at the 74th meeting to UNIDO (May 15)
COM | UNIDO | HCFC phase-out management plan (stage I, second tranche) (transfer of project) (a verification report) | Multi-Year | LAC | BOL | PHA | 74 | TAS | 43 | A | I |  | 0 | 0 |  |  | 2015-05-01 | 2015-08-01 | 2016-05-01 |  | 2015-12-01 |  | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 2700 | 0 | 0 | 2700 | 0 | The project was operationally completed. |  |  |  | NON-INV
ONG | UNIDO | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | LAC | BOL | PHA | 75 | INV | 44 | A | I |  | 0 | 0 |  |  | 2015-11-01 | 2016-01-01 | 2018-12-01 | 2018-12-31 |  |  | 64500 | 0 | 64500 | 16053.02 | 24.89% | 48446.98 | 26170.28 | 15000 | 5805 | 0 | 0 | 5805 | 2355.3252 | The National Ozone Officer was changed twice this year. Only monitoring and follow up activities. All related with the previous tranche. -The implementation of the project is again jeopardized: the fifth National Ozone Officer since UNIDO is implementing the project was removed after two months. - Delay in project implementation: Yes, as above. - Recurring problem: continuous fluctuations at the National Ozone Unit - Impact on project completion date: No - No action required by Executive Committee. | The implementation of the project is again jeopardized: the fifth National Ozone Officer since UNIDO is implementing the project was removed after two months. Since mid January 2017 there is no coordinator. In January an ambitious public awareness program was implemented taking advantage of the Rally Dakar which was crossing a City called Uyuni Bolivia. A ‘solmaforo’ (device designed to monitor the solar UVR intensity) has been installed and tourist guides and NOU officer were trained among others. The UV radiation is being measured daily. UNIDO and Ministry of Environment signed an Implementation Agreement in January 2017 however after that, the coordinator was removed. It is expected to have a new coordinator soon, the planning of all the activities are ready but stand by. - Delay in project implementation: Yes, as above. - Recurring problem: continuous fluctuations at the National Ozone Unit - Impact on project completion date: No - No action required by Executive Committee. |  |  | INV
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | BOL | REF | 20 | TAS | 04 | A | I | CFC | 13.8 | 13.8 | 0 | 0 | 1996-10-01 | 1997-05-01 | 1998-09-01 |  | 2001-12-01 | 2003-04-01 | 146000 | -691 | 145309 | 145309 | 100% | 0 | 0 | 0 | 18980 | -89.83 | 18890.17 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1996 | 1998-10-01 | Investment
FIN | UNDP | Project preparation for 2 projects in commercial refrigeration and one in domestic refrigeration sub-sectors | Individual | LAC | BOL | REF | 24 | PRP | 06 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 2001-11-01 | 2001-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 2001. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNEP | Development of refrigerant management plan | RMP | LAC | BOL | REF | 24 | PRP | 07 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 2001-01-01 | 1999-02-01 |  | 2001-12-01 | 2002-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNDP | Project preparation in the commercial refrigeration sector | Individual | LAC | BOL | REF | 33 | PRP | 12 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Project preparation in the commercial refrigeration (terminal phase-out) sector | Individual | LAC | BOL | REF | 36 | PRP | 18 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2004-09-01 | 2005-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2002 |  | Investment
FIN | Canada | Implementation of the RMP: assistance in preparation of regulations and technical norms | RMP | LAC | BOL | REF | 36 | TAS | 17 | A | I |  | 1.3 | 1.3 | 0 |  | 2002-03-01 | 2002-09-01 | 2003-06-01 |  | 2003-11-01 | 2003-12-01 | 13000 | 0 | 13000 | 13000 | 100% | 0 |  | 0 | 1690 | 0 | 1690 | 0 |  | Funds disbursed for legal consultant and workshops to develop legislation. Legislation approved in March 2004. Project completed. PCR submitted. |  | 2002 |  | Investment
FIN | Canada | Implementation of the RMP: public awareness programme on issues related to the ozone layer | RMP | LAC | BOL | REF | 36 | TAS | 20 | A | I |  | 5.4 | 5.4 | 0 |  | 2002-03-01 | 2002-09-01 | 2004-06-01 |  | 2008-03-01 | 2008-03-01 | 52000 | 0 | 52000 | 52000 | 100% | 0 |  | 0 | 6760 | 0 | 6760 | 0 |  | Last remaining activity, production of school texts on ozone depletion, was delayed due to administration difficulties - now completed. Final report was received in early 2008. |  | 2002 |  | Investment
FIN | Canada | Implementation of the RMP: monitoring the activities in the RMP project | RMP | LAC | BOL | REF | 36 | TAS | 22 | A | I |  | 5.9 | 5.9 | 0 |  | 2002-03-01 | 2002-09-01 | 2005-12-01 |  | 2008-03-01 | 2008-03-01 | 57000 | 0 | 57000 | 57000 | 100% | 0 |  | 0 | 7410 | 0 | 7410 | 0 |  | Monitoring database and information system installed and working, as well as ODS monitoring and reporting activities. Funds used principally for local project consultant to implement, monitor and report on project activities. All activities have been completed and final report received in early 2008. |  | 2002 |  | Investment
FIN | Canada | Implementation of the RMP: training programme for customs officers and technical staff in municipalities | RMP | LAC | BOL | REF | 36 | TRA | 19 | A | I |  | 5 | 5 | 0 |  | 2002-03-01 | 2002-09-01 | 2004-06-01 |  | 2005-04-01 | 2005-04-01 | 48000 | 0 | 48000 | 48000 | 100% | 0 |  | 0 | 6240 | 0 | 6240 | 0 |  | Train-the-trainers workshop completed in 2004. Phase II customs officers training completed in March 2005 with 83 officers trained. A total of $13,972 remained in funding after project completion and were used on other RMP components (principally the moni |  | 2002 |  | Investment
FIN | Canada | Implementation of the RMP: training programme for refrigeration technicians | RMP | LAC | BOL | REF | 36 | TRA | 21 | A | I |  | 5.7 | 5.7 | 0 |  | 2002-03-01 | 2002-09-01 | 2003-06-01 |  | 2005-06-01 | 2005-06-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 |  | 0 | 7150 | 0 | 7150 | 0 |  | Train-the Trainers workshop held in Sept. 2004. Training equipment purchased and distributed. Phase II training completed in May 2005 with 265 technicians trained. Remaining funds from 2005 were used in 2006 on other RMP components (mainly the monitoring) |  | 2002 |  | Investment
FIN | Canada | Implementation of the RMP: recovery and recycling | RMP | LAC | BOL | REF | 39 | TAS | 23 | A | I | CFC | 30.3 | 30.3 | 0 |  | 2003-04-01 | 2005-01-01 | 2005-12-01 |  | 2008-03-01 | 2008-03-01 | 292000 | 0 | 292000 | 292000 | 100% | 0 |  | 0 | 37960 | 0 | 37960 | 0 |  | 1st Phase of R&R equipment was shipped to Bolivia in April 2005 and 2nd Phase in Dec. 2005. The majority of the equipment has been distributed to technicians and training has been completed. A few batches of R&R machines have not been distributed due to administrative problems, but Bolivia expects to distribute them prior to end of April 2009. |  | 2003 |  | Investment
FIN | UNDP | Terminal umbrella project for the commercial refrigeration manufacturing sector | Individual | LAC | BOL | REF | 42 | INV | 25 | N | I | CFC | 5.8 | 5.8 | 0 | 0 | 2004-04-01 | 2005-01-01 | 2007-04-01 |  | 2007-12-01 | 2011-11-01 | 88840 | -130.13 | 88709.87 | 88710 | 100% | -0.13 | 0 | 0 | 7995 | -11.71 | 7983.3009 | -0.010899 | 0 | Completed in 2007. |  | 2004 |  | Investment
FIN | UNEP | Completion of country programme preparation | Individual | LAC | BOL | SEV | 16 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-04-01 | 1996-06-01 |  | 1995-10-01 | 1999-01-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0
FIN | UNEP | Establishment of the Ozone Governmental Commission (COGO) | Individual | LAC | BOL | SEV | 18 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-04-01 | 1998-11-01 |  | 1999-12-01 | 1999-12-01 | 91000 | 0 | 91000 | 91000 | 100% | 0 | 0 |  | 11830 | 0 | 11830 | 0 | 0
FIN | UNDP | Project preparation assistance | Individual | LAC | BOL | SEV | 18 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-05-01 | 1996-11-01 |  | 1996-11-01 | 1998-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNEP | Renewal of the institutional strengthening project | Individual | LAC | BOL | SEV | 26 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 2000-10-01 | 2000-12-01 |  | 2001-12-01 | 2003-12-01 | 60670 | 0 | 60670 | 60670 | 100% | 0 | 0 |  | 7887 | 0 | 7887 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project | Individual | LAC | BOL | SEV | 34 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-10-01 | 2003-08-01 |  | 2003-12-01 | 2004-12-01 | 60670 | 0 | 60670 | 60670 | 100% | 0 | 0 |  | 7887 | 0 | 7887 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project | Individual | LAC | BOL | SEV | 40 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2004-08-01 | 2005-07-01 |  | 2006-12-01 | 2007-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase V) | Individual | LAC | BOL | SEV | 47 | INS | 26 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-05-01 | 2007-12-01 |  | 2008-12-01 | 2009-12-01 | 78867 | 0 | 78867 | 78867 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase VI) | Individual | LAC | BOL | SEV | 53 | INS | 30 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-05-01 | 2009-11-01 |  | 2009-12-01 | 2010-12-01 | 78867 | 0 | 78867 | 78867 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase VII) | Individual | LAC | BOL | SEV | 59 | INS | 35 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2011-05-01 | 2011-12-01 |  | 2012-06-01 | 2013-12-01 | 39434 | 39434 | 78868 | 78868 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase VIII: 8/2012-7/2014) | Individual | LAC | BOL | SEV | 67 | INS | 37 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2012-11-01 | 2014-07-01 |  | 2014-12-01 | 2014-12-01 | 78867 | 0 | 78867 | 78867 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of institutional strengthening project (phase IX: 12/2014-11/2016) | Individual | LAC | BOL | SEV | 73 | INS | 39 | A | I |  | 0 |  | 0 |  | 2014-11-01 | 2015-12-01 | 2016-11-01 | 2017-11-01 |  |  | 78867 | 0 | 78867 | 31546 | 40% | 47321 | 47321 | 4732.1 | 0 | 0 | 0 | 0 | 0 | Brief Progress: A UNEP mission took place in November 2016 and the issues related to the consumption data, as identified at the 75th ExCom, were addressed and an induction to the new NOO took place. First cash advance of the SSFA was fully implemented and expenditures verified. Second cash advance was requested in December 2016. An Awareness Plan was prepared by the Government and will be implemented in 2017. Legal arrangements (actual/planned): July 2015 / Feb 2015. Initial stages of project implementation(actual/planned): July 2015 / Feb 2015. Intermediate goals achieved (actual/planned): 2015 country programme and Article 7 data reported. Action Plan established. Procurement plan prepared. First mission (actual/planned): 1/1 - TOR completed (actual/planned): 0/0. First disbursement date (actual/planned): August 2015/May 2015 - All funds disbursed? No. Any delay? No. Issues identified in 2015 seemed to be solved. Any ongoing problems? Not identified - If Yes, is any action required by ExCom: N/A | Brief Progress: Awareness Plan being implemented. A comprehensive awareness intervention over Ozone Layer, UV radiation and cross-cutting issues along with other Governmental Institutions was put in place during the 2017 Dakar Rally in the Uyuni Salar. Second cash advance was transferred to GOV in January/2017. Procurement plan for 2017 prepared and one mission to the country is envisaged for the second quarter of 2017. Legal arrangements (actual/planned): July 2015 / Feb 2015. Initial stages of project implementation(actual/planned): July 2015 / Feb 2015. Intermediate goals achieved (actual/planned): 2015 country programme and Article 7 data reported. Action Plan established. Procurement plan prepared. First mission (actual/planned): 0/0 - TOR completed (actual/planned): 0/0. First disbursement date (actual/planned): August 2015/May 2015 - All funds disbursed? No. Any delay? No. Issues identified in 2015 seemed to be solved. Any ongoing problems? Not identified - If Yes, is any action required by ExCom: N/A Any ongoing problems? Yes, the NOO hired in 2016 has been dismissed and a new recruitment process has been initiated by the GOV (post fully funded with Goverment co-finance). Whit the NOO position vacant some implementation decisions are likely to not be made and some delays in the implementation is anticipated. --- If Yes, is any action required by ExCom: No
ONG | UNIDO | Survey of ODS alternatives at the national level | Individual | LAC | BOL | SEV | 74 | TAS | 41 | A | I |  | 0 | 0 |  |  | 2015-05-01 | 2015-09-01 | 2016-05-31 | 2017-03-01 |  |  | 70000 | 0 | 70000 | 68656.36 | 98.08% | 1343.64 | 1165.66 | 1166 | 6300 | 0 | 0 | 6300 | 104.9094 | Survey was carried out by local supplier and following consultation and review of the documents by UNIDO. | Survey will be submitted in 2017, pending payments are being transferred. |  |  | NON-INV
FIN | UNIDO | Preparation of a demonstration project (grain fumigation) | Individual | AFR | BOT | FUM | 24 | PRP | 04 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-04-01 | 1999-04-01 |  | 1998-05-01 | 2001-07-01 | 25000 | -1950 | 23050 | 23050 | 100% | 0 | 0 |  | 3250 | -258 | 2992 | 0 | 0 | FIN
FIN | UNIDO | Three alternatives to the use of methyl bromide: non-soil cultivation techniques, bio-fumigation with solarization, and application of various mixtures of other chemicals in low doses in tomatoes and curcubits | Individual | AFR | BOT | FUM | 25 | DEM | 05 | A | I | MBR | 0 | 0 |  |  | 1998-07-01 | 1998-11-01 | 2000-08-01 |  | 2004-12-01 | 2005-12-01 | 146300 | 0 | 146300 | 146300.01 | 100% | -0.01 | 0 |  | 19019 | 0 | 19019 | 0 | 0 | FIN
FIN | Germany | Project preparation for a terminal phase-out management plan | Individual | AFR | BOT | PHA | 55 | PRP | 11 | A | I |  | 0 |  | 0 |  | 2008-07-01 | 2008-10-01 | 2009-01-01 |  | 2009-03-01 | 2009-04-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | TPMP project was approved at the 57th Excom.
FIN | Germany | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | BOT | PHA | 57 | INV | 12 | A | I | CFC | 1 |  | 0 |  | 2009-04-01 | 2009-06-01 | 2011-03-01 |  | 2010-12-01 | 2012-12-01 | 155000 | 0 | 155000 | 155000 | 100% | 0 | 0 | 0 | 20150 | 0 | 20150 | 0 | 0 | 7 customs training were realised, purchase of training equipment, major public awareness on phase out of CFCs was conducted
FIN | Germany | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | BOT | PHA | 60 | INV | 13 | A | I | CFC | 0 |  | 0 |  | 2010-04-01 | 2010-05-01 | 2011-04-01 |  | 2011-11-01 | 2012-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | 10 additional refrigerant identifiers were purchased following the request from the customs dept. This was followed by 3 customs training at remote border posts of Botswana.
FIN | Germany | Preparation of a HCFC phase-out management plan | Individual | AFR | BOT | PHA | 60 | PRP | 14 | A | I | HCFC | 0 |  | 0 |  | 2010-04-01 | 2010-11-01 | 2011-04-01 |  | 2014-03-01 | 2014-08-01 | 150000 | -1794 | 148206 | 148206 | 100% | 0 |  | 0 | 19500 | -195 | 19305 | 0 |  | The regulations were not approved in 2014 delaying any progress. | Regulations were approved in Feb 2015. The remaining funds will be offset against other project activities. Project transferred to UNEP. HPMP will be submitted to the 75th excom.
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | BOT | PHA | 75 | INV | 17 | A | I |  | 0.5 |  | 0 |  | 2015-11-01 | 2016-10-01 | 2018-12-01 | 2018-12-01 |  |  | 135000 | 0 | 135000 | 0 | 0% | 135000 | 65000 | 13500 | 17550 | 0 | 0 | 17550 | 8450 | Brief progress report (actual/planned): The NOU enforced HCFC licensing and quota system and conducted two training workshops for 60 Customs and other Law Enforcement Officers and strengthening the customs training school. The NOU conducted 2 RAC workshops and trained 40 refrigeration technicians. The main aim of the training is to equip refrigeration technicians with knowledge and necessary skills in hydrocarbon technologies and good refrigeration practices and to equip them with the minimum toolkits for a good servicing. The NOU conducted inspection visits at the markets and major entry points to monitor distribution of HCFCs to check compliance with the quotas allocated for that particular year.___ Legal arrangements(actual/planned): _ The SSFA was drafted and signed by UNEP and the Government of Botswana in September 2016_ First mission (actual/planned): yes___ TOR completed(actual/planned): __yes_ First disbursement date (actual/planned): October 2016__ All funds disbursed (yes/no): No__ Any delay? (yes/no): No___ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): N/A___ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: __No_ | Brief progress report (actual/planned): The NOU trained 20 participants from the Ministry of Environment, Wildlife and Tourism on the HCFC phase out management plan |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor the signing of the agreement by the Government and UNEP.
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | BOT | PHA | 75 | INV | 18 | A | I | HCFC | 0.6 | 0 |  |  | 2015-11-01 | 2016-10-01 | 2018-12-01 | 2018-12-19 |  |  | 140000 | 0 | 140000 | 4280.95 | 3.058% | 135719.05 | 227.42 | 10000 | 9800 | 0 | 0 | 9800 | 15.9194 | - PAD issued. - Fact finding mission undertaken in September 2016. Actions towards next goals: Purchase equipment as per HPMP Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Equipment scope is being defined and procurement process planned during Q2/2017 Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
FIN | UNDP | Project preparation in refrigeration recycling | Individual | AFR | BOT | REF | 21 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2002-03-01 | 20000 | -8880 | 11120 | 11120 | 100% | 0 | 0 | 0 | 2600 | -1154.4 | 1445.6 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1997 |  | Investment
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | BOT | REF | 26 | TAS | 06 | A | I | CFC | 1.5 | 1.7 | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2005-06-01 | 2006-06-01 | 70375 | 0 | 70375 | 70375 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted in 2006
FIN | Germany | Project preparation for an RMP update | RMP Update | AFR | BOT | REF | 39 | PRP | 07 | A | I |  | 0 |  | 0 |  | 2003-04-01 | 2003-06-01 | 2004-04-01 |  | 2004-12-01 | 2005-03-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project preparation completetd. RMP update to be submitted for approval at 45th Excom
FIN | Germany | Implementation of the RMP update | RMP Update | AFR | BOT | REF | 45 | TAS | 09 | A | I | CFC | 5.8 | 5.8 | 0 |  | 2005-04-01 | 2005-11-01 | 2008-04-01 |  | 2009-08-01 | 2011-11-01 | 64295 | 0 | 64295 | 64295 | 100% | 0 | 0 | 0 | 8358 | 0 | 8358 | 0 | 0 | Customs training was the only activity remaining under the project and with the approval of the ODS regulations these could be completed. 36 customs officiers were trained at the various border posts. The PCR will be submitted in 2010
FIN | UNEP | Country programme preparation | Individual | AFR | BOT | SEV | 06 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-04-01 | 1994-07-01 |  | 1994-06-01 | 1994-12-01 | 30000 | 10000 | 40000 | 40000 | 100% | 0 | 0 |  | 3900 | 1300 | 5200 | 0 | 0
FIN | UNEP | Institutional strengthening (establishment of the Ozone Office) | Individual | AFR | BOT | SEV | 13 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1996-05-01 | 1997-07-01 |  | 2003-12-01 | 2003-12-01 | 90200 | 0 | 90200 | 90200 | 100% | 0 | 0 |  | 11726 | 0 | 11726 | 0 | 0 |  |  |  | 1999-12-01
FIN | UNEP | Extension of institutional strengthening project: phase 2 | Individual | AFR | BOT | SEV | 41 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2006-06-01 | 2005-12-01 |  | 2008-02-01 | 2012-12-01 | 78173 | 0 | 78173 | 78173 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | AFR | BOT | SEV | 53 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2011-05-01 | 2009-11-01 |  | 2014-07-01 | 2016-12-01 | 78173 | 0 | 78173 | 78173 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed | Project financially completed
ONG | UNEP | Extension of institutional strengthening project (phase IV: 1/2013-12/2014) | Individual | AFR | BOT | SEV | 68 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2015-04-01 | 2014-11-01 | 2017-12-01 |  |  | 78173 | 0 | 78173 | 24527.57 | 31.38% | 53645.43 | 53645.43 | 5364.543 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The licensing and quota systems are in place and functioning. The NOU registered 5 importers of HCFCs and organized one stakeholders meeting in Feb 2016 to coordinate and allocate licenses and quotas. The NOU carried out 3 inspection visits to monitor distribution of HCFCs to check compliance with quotas allocated between June and November 2016. The NOU conducted two RAC training workshops and two custom training workshops, and trained 60 technicians and 30 custom officers respectively. The NOU conducted one steering committee meeting to monitor, and coordinate the operations of the NOU. Two public awareness meetings were organized and more than 100 participants in June and September, 2016. The NOU submitted 2015 Country Programme and Article 7 Data reports in June 2016. The NOU celebrated 2016 International Ozone Day and conducted several awareness activities. The NOU participated in all Montreal Protocol meetings organized in 2016. ___ Legal arrangements (actual/planned): The SSFA was drafted and signed by UNEP and the Government of Botswana in March 2015. ___Initial stages of project implementation (actual/planned): __Yes_ Intermediate goals achieved (actual/planned): _Yes__ Project completion and follow up: _Yes__ First disbursement date (actual/planned): April 2015. All funds disbursed (yes/no): Yes__ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: __N/A_ | Brief progress report (actual/planned): The NOU continues to monitor imports and trade of ODS and ODS related equipment. Collection of the 2016 data on ODS imports and consumption has been completed and is being analyzed for submission.
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | AFR | BOT | SEV | 74 | TAS | 16 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-05-01 | 2016-05-01 | 2017-05-01 |  |  | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Brief progress report (actual/planned): The first stakeholders meeting was organized by the NOU in May 2016 in Gaborone and 30 participants from the ODS alternative user sectors and importers attended. The main goal of the meeting was to sensitize the government and industry on the survey and agree on the plan for the Survey of ODS alternatives at the national level and obtain support of main national stakeholders. One National Consultant was hired in March 2016 by the NOU to support the data collection. The National Consultant assisted the NOU in the identification of the current use of ODS alternatives by substance/sector and collection of import/export data for the substances for the past a couple of years. The National Consultant also provided support in establishing growth patterns in use by substance/sector and in compiling data on available ODS alternatives for various applications.The NOU and the National Consultant drafted and cross checked the information to ensure the completion of end-user surveys, collection, analysis, and aggregation of consumption data. The various sections of the report were drafted. The second stakeholders meeting was organized by the NOU in November 2016 in Gaborone with the main goal to organise consultations with representatives of the government and private sector to finalize the outcomes of the Survey of ODS alternatives and discuss potential opportunities for introduction of those alternatives in the country. A total of 35 participants were in attendance. The draft report was prepared by the NOU and the National Consultant. It was reviewed and finalized based on the format approved by ExCom decision 75/67 as contained in document UNEP/OzL.Pro/ExCom/75/77/Rev.1 after incorporating inputs/ comments raised during National Stakeholders’ workshop. The final report was submitted to UNEP in December 2016 for final review and submission to MLFS. The NOU participated in the ODS Alternative Thematic workshop held in December 2016 to refine the draft report according to the revised template for the report. The report has been finally submitted to UNEP. Legal arrangements(actual/planned): The SSFA was drafted and signed by UNEP and the Government of Botswana in January 2016___ Initial stages of project implementation(actual/planned): _Yes__ Intermediate goals achieved (actual/planned): Yes___ Project completion and follow up: _Yes__ First disbursement date (actual/planned): _May 2016__ All funds disbursed (yes/no): No___ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): __N/A_ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): The NOU incorporated comments from UNEP ROA and Paris and re-submitted final ODS survey report.
ONG | UNEP | Extension of institutional strengthening project (phase V: 6/2016-7/2018) | Individual | AFR | BOT | SEV | 76 | INS | 19 | A | I |  | 0 |  | 0 |  | 2016-05-01 | 2016-07-01 | 2018-07-01 | 2018-07-01 |  |  | 100061 | 0 | 100061 | 180.5 | 0.1804% | 99880.5 | 99880.5 | 9988.05 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The licensing and quota systems are in place and functioning. The NOU registered importers of HCFCs and organized one stakeholders meeting in March 2016 to coordinate and allocate licenses and quotas. The NOU conducted one RAC training workshop and one custom training workshop, trained 20 technicians and 30 custom officers respectively. The NOU conducted one steering committee meeting to monitor, and coordinate the operations of the NOU. One public awareness meeting was organized with 30 participants in attendance. The NOU submitted 2015 Country Programme and Article 7 Data reports. The NOU celebrated 2016 International Ozone Day and conducted several awareness activities. The NOU participated in all Montreal Protocol meetings organized in 2016. ___ Legal arrangements (actual/planned): The SSFA was drafted by UNEP and sent to the Government of Botswana for signature in Nov 2016. ___Initial stages of project implementation (actual/planned): __Yes_ Intermediate goals achieved (actual/planned): _Yes__ Project completion and follow up: _Yes__ First disbursement date (actual/planned): __No____. All funds disbursed (yes/no): No__ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: __N/A_ | Brief progress report (actual/planned):The NOU continues to monitor imports and trade of ODS and ODS related equipment. Collection of the 2016 data on ODS imports and consumption has been completed and is being analyzed for submission. NOU commenced preparation of national legislative requirement processes in planning for ratification of Kigali amendment.
CLO | UNIDO | Project preparation in the aerosol sector | Individual | LAC | BRA | ARS | 27 | PRP | 127 | A | I |  | 0 | 0 |  |  | 1999-03-01 |  | 1999-12-01 |  |  | 1999-07-01 | 30000 | -30000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 3900 | -3900 | 0 | 0 | 0 | CLO
FIN | UNDP | Preparation for pilot demonstration project on ODS waste management and disposal | Individual | LAC | BRA | DES | 57 | PRP | 288 | N | I | ODS-Waste | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-02-01 | 2010-03-01 |  | 2014-10-01 | 2015-01-01 | 40000 | -6730 | 33270 | 33270 | 100% | 0 | 0 | 0 | 3000 | -504.75 | 2495.25 | 0 | 0 | Financially Completed in 2015. | The planned milestone of hiring the international expert has been completed and the project is being drafted. Submission is expected to the 72nd ExCom. | 2009 |  | Investment
ONG | UNDP | Pilot demonstration project on ODS waste management and disposal | Individual | LAC | BRA | DES | 72 | DEM | 305 | N | I | ODS-Waste | 0 | 0 | 0 | 0 | 2014-05-01 | 2015-06-01 | 2018-01-01 | 2017-01-01 |  |  | 1490600 | 0 | 1490600 | 166417.03 | 11.16% | 1324182.97 | 0 | 529673.188 | 104342 | 0 | 11649.1921 | 92692.8079 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Public process undertaken to identify the Recycling centers that will participate in the project. Each lab set up criteria to receive the funding. Technical specs developed for the purchase of cylinders to increase storage capacity. Prodoc signed (actual/planned, yes/no and date):Signed earlier Missions undertaken (actual/planned):1 of 1 TOR for consultants/subcontracts completed (actual/planned): 2 of 2 Contract/PO/MOA agreements signed: 0 of 0 First disbursement date (actual/planned): 42156Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | Public consultation process undertaken in Jan/Feb 2017 to identify eligible companies for the destruction plant. Results are currently being evaluated. |  |  | Investment
FIN | UNIDO | Preparation of investment projects for elimination of CFCs in the polymer foams manufacturing | Individual | LAC | BRA | FOA | 09 | PRP | 08 | A | I |  | 0 | 0 |  |  | 1993-03-01 | 1993-07-01 | 1993-09-01 |  | 1996-08-01 | 1999-08-01 | 150000 | -5144 | 144856 | 144856 | 100% | 0 | 0 |  | 19500 | -699 | 18801 | 0 | 0 | FIN
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (spray) at Therm-Jet (Belo Horizonte), Zenimont and Lavale (Sao Paulo) | Individual | LAC | BRA | FOA | 12 | INV | 13 | N | I | CFC | 72 | 72 | 0 | 0 | 1994-03-01 | 1996-02-01 | 1995-03-01 |  | 1997-07-01 | 2000-12-01 | 370000 | -15282 | 354718 | 354718 | 100% | 0 | 0 | 0 | 48100 | -1986.66 | 46113.34 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | IBRD | Conversion to reduced CFC technology in the manufacture of Refrigerators at Refrigeracao Parana S.A., Unidade Sao Carlos | Individual | LAC | BRA | FOA | 15 | INV | 16 | N | I | CFC | 96 | 96 | 0 | 0 | 1994-12-01 | 1996-01-01 | 1996-12-01 |  | 1999-06-01 | 1999-05-01 | 162603 | -12710 | 149893 | 149893 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. (Remaining "balance" has been disbursed to FA.) |  |  | 1999-06-01 | INV | 0
FIN | UNDP | Conversion to CFC-free technology in the manufacture of integral skin polyurethane foam for steering wheels at Plascar | Individual | LAC | BRA | FOA | 17 | INV | 21 | A | I | CFC | 15 | 15 | 0 | 0 | 1995-07-01 | 1997-01-01 | 1996-12-01 |  | 1997-10-01 | 2000-07-01 | 119400 | -25268 | 94132 | 94132 | 100% | 0 | 0 | 0 | 15522 | -3284.84 | 12237.16 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNIDO | Investment project for phasing out of ODS at Frisokar Equipamentos Plasticos Ltd. | Individual | LAC | BRA | FOA | 17 | INV | 26 | A | I | CFC | 42 | 42 |  |  | 1995-07-01 | 1996-11-01 | 1997-01-01 |  | 1997-10-01 | 2000-07-01 | 267948 | -13521 | 254427 | 254427 | 100% | 0 | 0 |  | 34833 | -1810 | 33023 | 0 | 0 | FIN
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Macform | Individual | LAC | BRA | FOA | 18 | INV | 27 | A | I | CFC | 25 | 25 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1997-05-01 |  | 1997-09-01 | 2000-12-01 | 243500 | -8086 | 235414 | 235414 | 100% | 0 | 0 | 0 | 31655 | -1051.18 | 30603.82 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Nacra | Individual | LAC | BRA | FOA | 18 | INV | 28 | A | I | CFC | 20 | 20 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1997-05-01 |  | 1997-10-01 | 2000-12-01 | 254500 | -47523.49 | 206976.51 | 206977 | 100% | -0.49 | 0 | 0 | 33085 | -6178.05 | 26907.01 | -0.06 | 0 | Completed in 1997. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at MBR | Individual | LAC | BRA | FOA | 18 | INV | 29 | A | I | CFC | 40 | 40 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1997-05-01 |  | 1997-10-01 | 2000-12-01 | 338500 | -44421 | 294079 | 294079 | 100% | 0 | 0 | 0 | 44005 | -5774.73 | 38230.27 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1995 |  | Investment
FIN | IBRD | Substitution of CFC-11 by HCFC-141b in the manufacture of polyurethane foams at Sao Rafael Ind. Com. | Individual | LAC | BRA | FOA | 18 | INV | 30 | N | I | CFC | 14 | 14 | 0 | 0 | 1995-11-01 | 1997-02-01 | 1996-10-01 |  | 1999-09-01 | 1998-02-01 | 82676 | -2016 | 80660 | 80660 | 100% | 0 | 0 |  | 10748 | -262.08 | 10485.8 | 0.12 | 0.12 | Complete. |  |  | 1998-07-01 | INV | 0
CLO | IBRD | Substitution of CFC-11 by HCFC-141b in the manufacture of polyurethane foams at Randon Implementos S.A. | Individual | LAC | BRA | FOA | 18 | INV | 31 | N | I |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1996-09-01 |  |  | 1999-07-01 | 92180 | -92180 | 0 | 0 | #DIV/0! | 0 | 0 |  | 11983 | -11983 | 0 | 0 | 0 | Cancelled. |  |  | 1999-06-01 | INV | 0
FIN | IBRD | Substitution of CFC-11 by HCFC-141b in the manufacture of polyurethane foams at Recrusul SEA | Individual | LAC | BRA | FOA | 18 | INV | 32 | N | I | CFC | 201 | 201 | 0 | 0 | 1995-11-01 | 1997-05-01 | 1996-11-01 |  | 1999-06-01 | 1999-08-01 | 1075650 | -121339 | 954311 | 954311 | 100% | 0 | 0 |  | 139835 | -15774.5 | 124060.5 | 0 | 0 | Complete. |  |  | 1999-06-01 | INV | 0
FIN | IBRD | Substitution of CFC-11 by HCFC-141b in the manufacture of polyurethane foams at M. Agostini, S.A. | Individual | LAC | BRA | FOA | 18 | INV | 33 | N | I | CFC | 11 | 11 | 0 | 0 | 1995-11-01 | 1999-02-01 | 1996-08-01 |  | 1999-09-01 | 1999-02-01 | 85217 | -2078 | 83139 | 83139 | 100% | 0 | 0 |  | 11078 | -269.93 | 10808.07 | 0 | 0 | All three foaming machines now installed and in routine operation. |  |  | 1999-06-01 | INV | 0
CLO | IBRD | Substitution of CFC-11 by HCFC-141b in the manufacture of polyurethane foams at Termolar, S.A. | Individual | LAC | BRA | FOA | 18 | INV | 34 | N | I |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1996-08-01 |  |  | 1996-09-01 | 61716 | -61716 | 0 | 0 | #DIV/0! | 0 | 0 |  | 8023 | -8023 | 0 | 0 | 0 | Cancelled. |  |  |  | INV | 0
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Madef/Isoltec | Individual | LAC | BRA | FOA | 19 | INV | 43 | A | I | CFC | 65.3 | 65.3 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  | 1998-12-01 | 2001-12-01 | 346000 | -64202 | 281798 | 281798 | 100% | 0 | 0 | 0 | 44980 | -8346.26 | 36633.74 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1996 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at three enterprises: Brafer, Invicta and Therm-Jet | Individual | LAC | BRA | FOA | 19 | INV | 44 | A | I | CFC | 38 | 38 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  | 1998-07-01 | 1999-12-01 | 275000 | 0 | 275000 | 275000 | 100% | 0 | 0 | 0 | 35750 | 0 | 35750 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1996 |  | Investment
FIN | UNDP | Umbrella project covering 6 companies for the conversion to CFC-free technology in the manufacture of integral rigid skin and flexible molded polyurethane foam (Rorispuma, Indek, Flexfom, Walrod, Rigi | Individual | LAC | BRA | FOA | 19 | INV | 45 | A | I | CFC | 51.8 | 51.8 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-05-01 |  | 1997-11-01 | 2000-07-01 | 746000 | 1.94 | 746001.94 | 746002 | 100% | -0.06 | 0 | 0 | 96980 | 0 | 96980.0078 | -0.0078 | 0 | Completed in 1997. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Conversion to CFC-free techcnology in the manufacture of polyurethane foam at Blitz Ind. Com. de Plasticos | Individual | LAC | BRA | FOA | 19 | INV | 46 | A | I | TCA/CFC | 9.8 | 9.8 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  | 1997-07-01 | 2000-07-01 | 120000 | -36822 | 83178 | 83178 | 100% | 0 | 0 | 0 | 15600 | -4786.86 | 10813.14 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Panisol, S.A. (Paineis Isolantes) | Individual | LAC | BRA | FOA | 20 | INV | 53 | A | I | CFC | 54.4 | 54.4 | 0 | 0 | 1996-10-01 | 1998-12-01 | 1998-09-01 |  | 1999-12-01 | 2003-11-01 | 315958 | -41 | 315917 | 315917 | 100% | 0 | 0 | 0 | 41074.54 | -5 | 41069.54 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  | 1996 | 1999-07-01 | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | LAC | BRA | FOA | 21 | PRP | 62 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2000-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Giroflex | Individual | LAC | BRA | FOA | 22 | INV | 64 | A | I | CFC | 23.4 | 23.4 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1999-08-01 | 2002-11-01 | 177500 | 0 | 177500 | 177500 | 100% | 0 | 0 | 0 | 23075 | 0 | 23075 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyethylene foam tubing at Polipex | Individual | LAC | BRA | FOA | 22 | INV | 65 | A | I | CFC | 28.5 | 28.5 | 0 | 0 | 1997-05-01 | 1998-12-01 | 1999-06-01 |  | 2002-01-01 | 2002-12-01 | 191000 | 0 | 191000 | 191000 | 100% | 0 | 0 | 0 | 24830 | 0 | 24830 | 0 | 0 | Completed in 2002. Financially completed in 2002. |  | 1997 | 1999-12-01 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Trambusti Naue | Individual | LAC | BRA | FOA | 22 | INV | 66 | A | I | CFC | 50 | 50 | 0 | 0 | 1997-05-01 | 1998-12-01 | 1999-06-01 |  | 2000-11-01 | 2001-11-01 | 763600 | -2355 | 761245 | 761245 | 100% | 0 | 0 | 0 | 99268 | -306.15 | 98961.85 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1997 | 1999-12-01 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Industrias Facchini, Ldta. | Individual | LAC | BRA | FOA | 22 | INV | 67 | A | I | CFC | 33 | 33 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 2000-03-01 | 2001-11-01 | 258000 | -85574 | 172426 | 172426 | 100% | 0 | 0 | 0 | 33540 | -11124.62 | 22415.38 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Dalla Rosa E Cia | Individual | LAC | BRA | FOA | 22 | INV | 68 | A | I | CFC | 9.1 | 9.1 | 0 | 0 | 1997-05-01 | 1998-12-01 | 1999-05-01 |  | 1999-12-01 | 2001-12-01 | 71600 | 0 | 71600 | 71600 | 100% | 0 | 0 | 0 | 9308 | 0 | 9308 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 | 1999-12-01 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Aquedores Cumulus S.A. | Individual | LAC | BRA | FOA | 22 | INV | 69 | A | I | CFC | 11 | 11 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1999-11-01 | 2001-12-01 | 86000 | -49 | 85951 | 85951 | 100% | 0 | 0 | 0 | 11180 | -6.37 | 11173.6296 | 0.0004 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Tekcor Utilidades Domesticas Ltd. | Individual | LAC | BRA | FOA | 22 | INV | 70 | A | I | CFC | 9.1 | 9.1 | 0 | 0 | 1997-05-01 | 1998-07-01 | 1999-06-01 |  | 1998-07-01 | 2003-05-01 | 71600 | -2957 | 68643 | 68643 | 100% | 0 | 0 | 0 | 9308 | -384.41 | 8923.59 | 0 | 0 | Completed in 1998. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Metallurgica Barra | Individual | LAC | BRA | FOA | 22 | INV | 71 | A | I | CFC | 36.3 | 36.3 | 0 | 0 | 1997-05-01 | 1997-07-01 | 1999-06-01 |  | 1997-07-01 | 2000-12-01 | 270000 | 0 | 270000 | 270000 | 100% | 0 | 0 | 0 | 35100 | 0 | 35100 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Isolenge | Individual | LAC | BRA | FOA | 22 | INV | 72 | A | I | CFC | 66 | 66 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1998-04-01 | 2000-12-01 | 516000 | -84186.38 | 431813.62 | 431814 | 100% | -0.38 | 0 | 0 | 67080 | -10944.23 | 56135.82 | -0.05 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | IBRD | Project preparation in the foam sector |  | LAC | BRA | FOA | 22 | PRP | 75 | A | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1999-03-31 | 1997-12-01 |  | 1999-12-01 | 1999-12-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 |  | 9750 | 0 | 9750 | 0 | 0 |  |  |  | 1999-12-01 | Non-INV | 0
FIN | UNDP | Conversion to CFC-free technlogy in the manufacture of polyurethane foam at Plasmold | Individual | LAC | BRA | FOA | 23 | INV | 77 | A | I | CFC | 11 | 11 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 1999-12-01 | 2001-12-01 | 161500 | -737.36 | 160762.64 | 160763 | 100% | -0.36 | 0 | 0 | 20995 | -95.91 | 20899.1392 | -0.0492 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polurethane foam at Bulltrade | Individual | LAC | BRA | FOA | 23 | INV | 78 | A | I | CFC | 30.8 | 30.8 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-12-01 | 2004-01-01 | 223000 | -358 | 222642 | 222642 | 100% | 0 | 0 | 0 | 28990 | -46.6 | 28943.4021 | -0.0021 | 0 | Completed in 1999. Financially completed in 2004. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at CMZ Poliuretanos | Individual | LAC | BRA | FOA | 23 | INV | 79 | A | I | CFC | 5.5 | 5.5 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-12-01 | 2001-12-01 | 92750 | -305.36 | 92444.64 | 92445 | 100% | -0.36 | 0 | 0 | 12057.5 | -39.71 | 12017.8348 | -0.0448 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polurethane foam at Bruzze | Individual | LAC | BRA | FOA | 23 | INV | 80 | A | I | CFC | 16.5 | 16.5 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-11-01 |  | 2000-11-01 | 2002-03-01 | 278190 | -456 | 277734 | 277734 | 100% | 0 | 0 | 0 | 36164.7 | -59.28 | 36105.42 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Bernini | Individual | LAC | BRA | FOA | 23 | INV | 82 | A | I | CFC | 22.9 | 22.9 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 1999-12-01 | 2002-11-01 | 135150 | 0 | 135150 | 135150 | 100% | 0 | 0 | 0 | 17569.5 | 0 | 17569.5 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Polistecom | Individual | LAC | BRA | FOA | 23 | INV | 84 | A | I | CFC | 42.6 | 42.6 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 2000-11-01 | 2001-12-01 | 303000 | 0 | 303000 | 303000 | 100% | 0 | 0 | 0 | 39390 | 0 | 39390 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Mikawa & Cia | Individual | LAC | BRA | FOA | 23 | INV | 87 | A | I | CFC | 7.5 | 7.5 | 0 | 0 | 1997-11-01 | 1998-04-01 | 1999-12-01 |  | 2000-11-01 | 2002-03-01 | 80600 | 0 | 80600 | 80600 | 100% | 0 | 0 | 0 | 10478 | 0 | 10478 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Kalf Calcados | Individual | LAC | BRA | FOA | 23 | INV | 89 | A | I | CFC | 15 | 15 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2000-11-01 | 2003-11-01 | 101100 | 0 | 101100 | 101100 | 100% | 0 | 0 | 0 | 13143 | 0 | 13143 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Fast Frio | Individual | LAC | BRA | FOA | 23 | INV | 92 | A | I | CFC | 14.5 | 14.5 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 1999-12-01 | 2002-03-01 | 72000 | 0 | 72000 | 72000 | 100% | 0 | 0 | 0 | 9360 | 0 | 9360 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at FJ Polymers | Individual | LAC | BRA | FOA | 23 | INV | 93 | A | I | CFC | 8.2 | 8.2 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 2000-11-01 | 2002-03-01 | 89500 | -992 | 88508 | 88508 | 100% | 0 | 0 | 0 | 11635 | -128.96 | 11506.04 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Espumatec | Individual | LAC | BRA | FOA | 23 | INV | 94 | A | I | CFC | 64.6 | 64.6 | 0 | 0 | 1997-11-01 | 1999-03-01 | 1999-12-01 |  | 2001-04-01 | 2003-04-01 | 372000 | -271 | 371729 | 371729 | 100% | 0 | 0 | 0 | 48360 | -35.23 | 48324.77 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Zenimont | Individual | LAC | BRA | FOA | 23 | INV | 95 | A | I | CFC | 38.1 | 38.1 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 2001-04-01 | 2002-03-01 | 298300 | 0 | 298300 | 298300 | 100% | 0 | 0 | 0 | 38779 | 0 | 38779 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Project preparation to prepare 16 projects in the foam sector | Individual | LAC | BRA | FOA | 24 | PRP | 98 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-08-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 70000 | -12756 | 57244 | 57244 | 100% | 0 | 0 | 0 | 9100 | -1658.28 | 7441.7213 | -0.0013 | 0 | Completed in 1998. Financially completed in 2000. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water technology in the manufacture of polyurethane foam at Injebank | Individual | LAC | BRA | FOA | 25 | INV | 101 | A | I | CFC | 6 | 6 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 1999-12-01 | 2002-04-01 | 86300 | -10846 | 75454 | 75454 | 100% | 0 | 0 | 0 | 11219 | -1409.98 | 9809.02 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Conversion to hexane and LCD technology in the manufacture of polyurethane foam at Herval | Individual | LAC | BRA | FOA | 25 | INV | 102 | A | I | CFC | 64.5 | 64.5 | 0 | 0 | 1998-07-01 | 2000-05-01 | 2000-08-01 |  | 2001-12-01 | 2003-11-01 | 637335 | 0 | 637335 | 637335 | 100% | 0 | 0 | 0 | 82853.55 | 0 | 82853.55 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNIDO | Phasing out CFC-11 with cyclopentane at Crios Industrial Ltd. (suppliers of Eletrofrio Company) | Individual | LAC | BRA | FOA | 25 | INV | 103 | A | I | CFC | 46 | 46 |  |  | 1998-07-01 | 1999-06-01 | 2000-08-01 |  | 2000-12-01 | 2002-09-01 | 357270 | 0 | 357270 | 357270.08 | 100% | -0.08 | 0 |  | 46445 | -50 | 46395 | 0 | 0 | FIN
FIN | UNDP | Conversion to water based technology in the manufacture of polyurethane foam at Refratarios Isolamentos e Pinturas (RIP) | Individual | LAC | BRA | FOA | 25 | INV | 104 | A | I | CFC | 12 | 12 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 2001-07-01 | 2003-04-01 | 94000 | -945 | 93055 | 93055 | 100% | 0 | 0 | 0 | 12220 | -122.85 | 12097.15 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water technology in the manufacture of polyurethane foam at Panther | Individual | LAC | BRA | FOA | 25 | INV | 105 | A | I | CFC | 18 | 18 | 0 | 0 | 1998-07-01 | 1999-12-01 | 2000-08-01 |  | 2000-11-01 | 2003-05-01 | 275805 | 0 | 275805 | 275805 | 100% | 0 | 0 | 0 | 35854.65 | 0 | 35854.65 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Conversion to HCFC-141b and water-blown technology in the manufacture of polyurethane foam at Gnatus | Individual | LAC | BRA | FOA | 25 | INV | 107 | A | I | CFC | 29.7 | 29.7 | 0 | 0 | 1998-07-01 | 1999-03-01 | 2000-08-01 |  | 2000-11-01 | 2003-04-01 | 207225 | -488 | 206737 | 206737 | 100% | 0 | 0 | 0 | 26939.25 | -63.44 | 26875.81 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Conversion to HCFC-141b and water-blown technology in the manufacture of polyurethane foam at Cougar | Individual | LAC | BRA | FOA | 25 | INV | 108 | A | I | CFC | 18.2 | 18.2 | 0 | 0 | 1998-07-01 | 1999-03-01 | 2000-08-01 |  | 2000-11-01 | 2003-11-01 | 154375 | 0 | 154375 | 154375 | 100% | 0 | 0 | 0 | 20068.75 | 0 | 20068.75 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Conversion to HCFC-141b in the manufacture of polyurethane foam at SSM Tecnologia | Individual | LAC | BRA | FOA | 25 | INV | 109 | A | I | CFC | 13.6 | 13.6 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 1999-12-01 | 2003-11-01 | 106500 | 0 | 106500 | 106500 | 100% | 0 | 0 | 0 | 13845 | 0 | 13845 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water and HCFC-141b technology in the manufacture of polyurethane foam at Delta Pack | Individual | LAC | BRA | FOA | 25 | INV | 110 | A | I | CFC | 27.5 | 27.5 | 0 | 0 | 1998-07-01 | 1999-03-01 | 2000-08-01 |  | 2000-11-01 | 2003-11-01 | 202500 | 0 | 202500 | 202500 | 100% | 0 | 0 | 0 | 26325 | 0 | 26325 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of insulation panels at Isoblock | Individual | LAC | BRA | FOA | 26 | INV | 112 | A | I | CFC | 13.6 | 13.6 | 0 | 0 | 1998-11-01 | 1999-03-01 | 2000-12-01 |  | 2000-11-01 | 2003-04-01 | 106500 | -132 | 106368 | 106368 | 100% | 0 | 0 | 0 | 13845 | -17 | 13828 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of insulation panels at C.A. Cunha | Individual | LAC | BRA | FOA | 26 | INV | 113 | A | I | CFC | 9.1 | 9.1 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 1999-12-01 | 2003-11-01 | 70100 | 0 | 70100 | 70100 | 100% | 0 | 0 | 0 | 9113 | 0 | 9113 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of insulation panels at P.F.I. Ind. E Com. Refrigeracao Ltd. (P.F.I.) | Individual | LAC | BRA | FOA | 26 | INV | 114 | A | I | CFC | 8.2 | 8.2 | 0 | 0 | 1998-11-01 | 1999-03-01 | 2000-12-01 |  | 2000-11-01 | 2003-11-01 | 64200 | 0 | 64200 | 64200 | 100% | 0 | 0 | 0 | 8346 | 0 | 8346 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by HCFC-141b in the manufacture of integral skin foam furniture and conversion from CFC-11 to methylene chloride in the manufacture of polyurethane boxfoam at Cantegril | Individual | LAC | BRA | FOA | 26 | INV | 116 | A | I | CFC | 27.1 | 27.1 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 1999-12-01 | 2003-05-01 | 154740 | -4476 | 150264 | 150264 | 100% | 0 | 0 | 0 | 20116.2 | -581.88 | 19534.32 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of integral skin foams (microcellular) at Bicicletos Caloi, S.A. | Individual | LAC | BRA | FOA | 27 | INV | 117 | A | I | CFC | 41 | 41 | 0 | 0 | 1999-03-01 | 2000-03-01 | 2001-10-01 |  | 2000-11-01 | 2003-04-01 | 227600 | -4765 | 222835 | 222835 | 100% | 0 | 0 | 0 | 29588 | -619.45 | 28968.55 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane boxfoam at Conter Ind. e Isolantes Termocos, Ltda. | Individual | LAC | BRA | FOA | 27 | INV | 120 | A | I | CFC | 10.9 | 10.9 | 0 | 0 | 1999-03-01 | 1999-12-01 | 2001-10-01 |  | 2000-11-01 | 2003-05-01 | 85347 | 0 | 85347 | 85347 | 100% | 0 | 0 | 0 | 11095.11 | 0 | 11095.11 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of integral skin foams at Spandy Peças em Poliuretano, Ltda. | Individual | LAC | BRA | FOA | 27 | INV | 125 | A | I | CFC | 17.8 | 17.8 | 0 | 0 | 1999-03-01 | 1999-12-01 | 2001-10-01 |  | 2000-11-01 | 2003-04-01 | 261400 | -4032 | 257368 | 257368 | 100% | 0 | 0 | 0 | 33982 | -524.16 | 33457.84 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Fabrica De Carrocerias Farage, Ltda. | Individual | LAC | BRA | FOA | 27 | INV | 129 | A | I | CFC | 10.9 | 10.9 | 0 | 0 | 1999-03-01 | 1999-12-01 | 2001-10-01 |  | 2000-11-01 | 2003-05-01 | 52770 | 0 | 52770 | 52770 | 100% | 0 | 0 | 0 | 6860.1 | 0 | 6860.1 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Posto de Molas Vivian, Ltda. (Posmovil) | Individual | LAC | BRA | FOA | 27 | INV | 130 | A | I | CFC | 9.1 | 9.1 | 0 | 0 | 1999-03-01 | 1999-12-01 | 2001-10-01 |  | 2000-11-01 | 2003-05-01 | 44700 | 0 | 44700 | 44700 | 100% | 0 | 0 | 0 | 5811 | 0 | 5811 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Preparation of four projects in the foam sector | Individual | LAC | BRA | FOA | 27 | PRP | 121 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2002-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Preparation of six projects in the rigid foam subsector | Individual | LAC | BRA | FOA | 27 | PRP | 123 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2002-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Preparation of five projects in integral skin foam subsector | Individual | LAC | BRA | FOA | 27 | PRP | 124 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 2000-04-01 |  | 2000-04-01 | 2002-03-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNIDO | Project preparation in the foam sector (general) | Individual | LAC | BRA | FOA | 27 | PRP | 126 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-11-01 | 1999-12-01 |  | 2000-12-01 | 2002-09-01 | 50000 | -9090 | 40910 | 40909.99 | 100% | 0.01 | 0 |  | 6500 | -1190 | 5310 | 0 | 0 | FIN
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane sprayfoam at Isotherm Tratamento Thermo Acoustico Ltda. | Individual | LAC | BRA | FOA | 28 | INV | 131 | A | I | CFC | 26.3 | 26.3 | 0 | 0 | 1999-07-01 | 2000-01-01 | 2002-02-01 |  | 2000-11-01 | 2003-11-01 | 116768 | 0 | 116768 | 116768 | 100% | 0 | 0 | 0 | 15179.84 | 0 | 15179.84 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and water based technology in the manufacture of rigid polyurethane foam at Polsul Group | Individual | LAC | BRA | FOA | 28 | INV | 135 | A | I | CFC | 55 | 55 | 0 | 0 | 1999-07-01 | 1999-12-01 | 2002-02-01 |  | 2002-11-01 | 2006-10-01 | 536892 | -24390 | 512502 | 512502 | 100% | 0 | 0 | 0 | 69058.12 | -2683 | 66375.12 | 0 | 0 | Completed in 2002. Financially completed in 2006. |  | 1999 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of rigid and flexible integral skin at Moldepol | Individual | LAC | BRA | FOA | 28 | INV | 136 | A | I | CFC | 34.8 | 34.8 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2002-02-01 |  | 2001-12-01 | 2003-11-01 | 421444 | -2 | 421442 | 421442 | 100% | 0 | 0 | 0 | 54787.72 | -0.26 | 54787.46 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Ananda | Individual | LAC | BRA | FOA | 28 | INV | 137 | A | I | CFC | 16 | 16 | 0 | 0 | 1999-07-01 | 1999-12-01 | 2002-02-01 |  | 1999-12-01 | 2002-04-01 | 37380 | -14147 | 23233 | 23233 | 100% | 0 | 0 | 0 | 4859.4 | -1839.11 | 3020.29 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in flexible molded foam, to water and methylene chloride technology in semi-rigid packaging foam, and to HCFC-141b in flexible integral skin foams at Espuma Oeste | Individual | LAC | BRA | FOA | 28 | INV | 138 | A | I | CFC | 16.9 | 16.9 | 0 | 0 | 1999-07-01 | 2000-05-01 | 2002-02-01 |  | 2000-11-01 | 2003-04-01 | 181616 | -5766 | 175850 | 175850 | 100% | 0 | 0 | 0 | 23610.08 | -749.58 | 22860.5 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and water based technology in the manufacture of rigid polyurethane foam and integral skin foam at JNP Group | Individual | LAC | BRA | FOA | 28 | INV | 140 | A | I | CFC | 80.3 | 80.3 | 0 | 0 | 1999-07-01 | 2000-01-01 | 2002-02-01 |  | 2002-12-01 | 2006-10-01 | 823867 | -22056 | 801811 | 801811 | 100% | 0 | 0 | 0 | 100625.4 | -2426 | 98199.4 | 0 | 0 | Completed in 2002. Financially completed in 2006. |  | 1999 |  | Investment
CLO | UNIDO | Phase-out of CFC-12 by conversion to n-butane as a blowing agent in the manufacture of extruded polyethylene foams for thermal insulation and food packaging purposes at Epex Co. | Individual | LAC | BRA | FOA | 28 | INV | 141 | A | I |  | 0 | 0 |  |  | 1999-07-01 |  | 2001-08-01 |  |  | 2001-07-01 | 632391 | -632391 | 0 | 0 | #DIV/0! | 0 | 0 |  | 79563 | -79563 | 0 | 0 | 0 | CLO
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in rigid polyurethane foam (spray and pour in place) at SIFC | Individual | LAC | BRA | FOA | 28 | INV | 143 | A | I | CFC | 9.5 | 9.5 | 0 | 0 | 1999-07-01 | 2000-02-01 | 2002-02-01 |  | 2000-11-01 | 2003-05-01 | 74385 | 0 | 74385 | 74385 | 100% | 0 | 0 | 0 | 9670.05 | 0 | 9670.05 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Fibrart | Individual | LAC | BRA | FOA | 29 | INV | 144 | A | I | CFC | 29.9 | 29.9 | 0 | 0 | 1999-11-01 | 2000-10-01 | 2002-12-01 |  | 2001-12-01 | 2003-11-01 | 111838 | 0 | 111838 | 111838 | 100% | 0 | 0 | 0 | 14538.94 | 0 | 14538.94 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water-blown technology in the manufacture of rigid integral skin foam at Durothan | Individual | LAC | BRA | FOA | 29 | INV | 145 | A | I | CFC | 30 | 30 | 0 | 0 | 1999-11-01 | 2001-02-01 | 2002-12-01 |  | 2001-12-01 | 2003-11-01 | 228625 | 0 | 228625 | 228625 | 100% | 0 | 0 | 0 | 29721.25 | 0 | 29721.25 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to water-based technology in the manufacture of rigid polyurethane foam at ACS Fibra | Individual | LAC | BRA | FOA | 29 | INV | 146 | A | I | CFC | 17.4 | 17.4 | 0 | 0 | 1999-11-01 | 2001-02-01 | 2002-12-01 |  | 2001-12-01 | 2004-01-01 | 119336 | -2316 | 117020 | 117020 | 100% | 0 | 0 | 0 | 15513.68 | -301.08 | 15212.6 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to water-based technology in the manufacture of rigid polyurethane foam for packaging and to HCFC-141b technology for insulation applications at World Pack da Amazonia, Ltd. | Individual | LAC | BRA | FOA | 29 | INV | 147 | A | I | CFC | 86.6 | 86.6 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2002-12-01 |  | 2001-12-01 | 2003-10-01 | 405610 | 0 | 405610 | 405610 | 100% | 0 | 0 | 0 | 52729.3 | 0 | 52729.3 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b in the manufacture of rigid polyurethane foam for display cabinets at Vacuum Systems | Individual | LAC | BRA | FOA | 29 | INV | 148 | A | I | CFC | 15 | 15 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2003-07-01 |  | 2001-12-01 | 2003-09-01 | 117450 | -1 | 117449 | 117449 | 100% | 0 | 0 | 0 | 15268.5 | -0.13 | 15268.37 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to water-based technology in the manufacture of rigid polyurethane foam at Plastwork Embalagens da Amazonia, Ltd. | Individual | LAC | BRA | FOA | 29 | INV | 149 | A | I | CFC | 18.5 | 18.5 | 0 | 0 | 1999-11-01 | 2001-02-01 | 2002-12-01 |  | 2001-12-01 | 2003-11-01 | 144855 | -1757 | 143098 | 143098 | 100% | 0 | 0 | 0 | 18831.15 | -228.41 | 18602.74 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Intertelhas | Individual | LAC | BRA | FOA | 29 | INV | 150 | A | I | CFC | 48.9 | 48.9 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2003-07-01 |  | 2000-12-01 | 2002-11-01 | 170074 | -62845 | 107229 | 107229 | 100% | 0 | 0 | 0 | 22109.62 | -8170 | 13939.62 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water-based technology in the manufacture of rigid integral skin foam at Spray | Individual | LAC | BRA | FOA | 29 | INV | 151 | A | I | CFC | 31.8 | 31.8 | 0 | 0 | 1999-11-01 | 2000-10-01 | 2002-12-01 |  | 2001-12-01 | 2003-04-01 | 211080 | -4717 | 206363 | 206363 | 100% | 0 | 0 | 0 | 27440.4 | -613.21 | 26827.19 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water-based technology in the manufacture of integral skin foams at Nicos do Brasil | Individual | LAC | BRA | FOA | 29 | INV | 152 | A | I | CFC | 16.5 | 16.5 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2002-12-01 |  | 2001-12-01 | 2003-11-01 | 160000 | 0 | 160000 | 160000 | 100% | 0 | 0 | 0 | 20800 | 0 | 20800 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Brasinj Ind. E Comm. | Individual | LAC | BRA | FOA | 29 | INV | 153 | A | I | CFC | 9.1 | 9.1 | 0 | 0 | 1999-11-01 | 2001-09-01 | 2003-07-01 |  | 2001-12-01 | 2003-04-01 | 71253 | 0 | 71253 | 71253 | 100% | 0 | 0 | 0 | 9262.89 | 0 | 9262.89 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane boxfoam and sprayfoam at Calorisol | Individual | LAC | BRA | FOA | 29 | INV | 154 | A | I | CFC | 19 | 19 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2002-12-01 |  | 2001-12-01 | 2003-04-01 | 91477 | -33 | 91444 | 91444 | 100% | 0 | 0 | 0 | 11892.01 | -4.29 | 11887.72 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water-blown technology in the manufacture of integral skin foams at ELV TEC Industria e Commercio Ltd. | Individual | LAC | BRA | FOA | 29 | INV | 155 | A | I | CFC | 14 | 14 | 0 | 0 | 1999-11-01 | 2001-02-01 | 2002-12-01 |  | 2001-12-01 | 2003-11-01 | 134265 | 0 | 134265 | 134265 | 100% | 0 | 0 | 0 | 17454.45 | 0 | 17454.45 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water-based technology in the manufacture of integral skin and flexible molded foams at Purtec | Individual | LAC | BRA | FOA | 29 | INV | 156 | A | I | CFC | 18.9 | 18.9 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2002-12-01 |  | 2001-12-01 | 2005-10-01 | 140769 | -3174 | 137595 | 137595 | 100% | 0 | 0 | 0 | 18299.97 | -412.62 | 17887.3493 | 0.000672 | 0 | Completed in 2001. Financially completed in 2005. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Isolamento Termico Brasfoam Ltd. | Individual | LAC | BRA | FOA | 29 | INV | 157 | A | I | CFC | 61.6 | 61.6 | 0 | 0 | 1999-11-01 | 2000-10-01 | 2002-12-01 |  | 2002-12-01 | 2004-01-01 | 110200 | -2358 | 107842 | 107842 | 100% | 0 | 0 | 0 | 14326 | -306.54 | 14019.46 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane boxfoam at Fibrasil Ind. Commercio de Carroceria Ltd. | Individual | LAC | BRA | FOA | 29 | INV | 158 | A | I | CFC | 15 | 15 | 0 | 0 | 1999-11-01 | 2001-09-01 | 2003-07-01 |  | 2002-05-01 | 2003-09-01 | 93425 | -32890 | 60535 | 60535 | 100% | 0 | 0 | 0 | 12145.25 | -4275.3 | 7869.95 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Preparation of 10 projects in the integral skin foam subsector | Individual | LAC | BRA | FOA | 30 | PRP | 160 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Preparation of 2 projects in the rigid foam subsector | Individual | LAC | BRA | FOA | 30 | PRP | 161 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Preparation of 2 projects in the rigid foam subsector (SMEs) | Individual | LAC | BRA | FOA | 30 | PRP | 163 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 2000 |  | Investment
CLO | UNDP | Preparation of 5 projects in the foam sector | Individual | LAC | BRA | FOA | 30 | PRP | 164 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 |  | 2001-04-01 |  |  | 2004-02-01 | 30000 | -30000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 3900 | -3900 | 0 | 0 | 0 | Canceled in 2000. Financially Completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of integral skin foam and flexible molded foam at Fabbrini | Individual | LAC | BRA | FOA | 31 | INV | 167 | A | I | CFC | 29 | 29 | 0 | 0 | 2000-07-01 | 2001-05-01 | 2003-08-01 |  | 2001-12-01 | 2002-11-01 | 124887 | -17316 | 107571 | 107571 | 100% | 0 | 0 | 0 | 16235.31 | -2251.08 | 13984.23 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of rigid integral skin foam at Menaf | Individual | LAC | BRA | FOA | 31 | INV | 168 | A | I | CFC | 10.7 | 10.7 | 0 | 0 | 2000-07-01 | 2001-05-01 | 2003-08-01 |  | 2001-12-01 | 2003-02-01 | 80994 | -11239 | 69755 | 69755 | 100% | 0 | 0 | 0 | 10529.22 | -1461.07 | 9068.15 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and water-based technology in the manufacture of rigid polyurethane foam at Polyfoam | Individual | LAC | BRA | FOA | 31 | INV | 169 | A | I | CFC | 41.9 | 41.9 | 0 | 0 | 2000-07-01 | 2001-05-01 | 2003-08-01 |  | 2003-10-01 | 2005-09-01 | 178873 | -23652 | 155221 | 155221 | 100% | 0 | 0 | 0 | 23253.49 | -3075 | 20178.49 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of flexible moulded foam at Massimo | Individual | LAC | BRA | FOA | 31 | INV | 173 | A | I | CFC | 8 | 8 | 0 | 0 | 2000-07-01 | 2001-05-01 | 2003-08-01 |  | 2002-09-01 | 2003-09-01 | 52279 | -5260 | 47019 | 47019 | 100% | 0 | 0 | 0 | 6796.27 | -683.8 | 6112.47 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of integral skin foam and rigid foam at Injepol | Individual | LAC | BRA | FOA | 31 | INV | 175 | A | I | CFC | 23 | 23 | 0 | 0 | 2000-07-01 | 2001-08-01 | 2003-08-01 |  | 2001-12-01 | 2003-04-01 | 107678 | -9727 | 97951 | 97951 | 100% | 0 | 0 | 0 | 13998.14 | -1264.51 | 12733.63 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown and HCFC-141b technology in the manufacture of integral skin and flexible molded foam at PPU | Individual | LAC | BRA | FOA | 31 | INV | 178 | A | I | CFC | 9.4 | 9.4 | 0 | 0 | 2000-07-01 | 2001-11-01 | 2003-08-01 |  | 2002-12-01 | 2003-09-01 | 64568 | -5159 | 59409 | 59409 | 100% | 0 | 0 | 0 | 8393.84 | -670.59 | 7723.25 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Packo Plurinox | Individual | LAC | BRA | FOA | 31 | INV | 179 | A | I | CFC | 13.4 | 13.4 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2000-12-01 | 2001-12-01 | 39750 | 0 | 39750 | 39750 | 100% | 0 | 0 | 0 | 5167.5 | 0 | 5167.5 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of integral skin foams at Mach-Plast | Individual | LAC | BRA | FOA | 31 | INV | 180 | A | I | CFC | 29.5 | 29.5 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-12-01 | 2003-04-01 | 188951 | -12871 | 176080 | 176080 | 100% | 0 | 0 | 0 | 24563.63 | -1673.23 | 22890.4 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of integral skin and rigid foam at Montreal | Individual | LAC | BRA | FOA | 31 | INV | 181 | A | I | CFC | 11.8 | 11.8 | 0 | 0 | 2000-07-01 | 2001-10-01 | 2003-08-01 |  | 2002-08-01 | 2003-09-01 | 83117 | 0 | 83117 | 83117 | 100% | 0 | 0 | 0 | 10805.21 | 0 | 10805.21 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Politermo | Individual | LAC | BRA | FOA | 31 | INV | 182 | A | I | CFC | 50.2 | 50.2 | 0 | 0 | 2000-07-01 | 2001-05-01 | 2003-08-01 |  | 2001-12-01 | 2003-02-01 | 219136 | -2808 | 216328 | 216328 | 100% | 0 | 0 | 0 | 28487.68 | -365.04 | 28122.64 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown and HCFC-141b technology in the manufacture of integral skin foam, flexible molded foam and rigid foam at Jetpol | Individual | LAC | BRA | FOA | 31 | INV | 183 | A | I | CFC | 29 | 29 | 0 | 0 | 2000-07-01 | 2001-12-01 | 2003-08-01 |  | 2002-05-01 | 2003-09-01 | 214600 | -9772 | 204828 | 204828 | 100% | 0 | 0 | 0 | 27898 | -1270.36 | 26627.64 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of flexible moulded foam and rigid foam at Trantor | Individual | LAC | BRA | FOA | 31 | INV | 184 | A | I | CFC | 19.6 | 19.6 | 0 | 0 | 2000-07-01 | 2001-03-01 | 2003-08-01 |  | 2001-12-01 | 2003-04-01 | 102234 | -5218 | 97016 | 97016 | 100% | 0 | 0 | 0 | 13290.42 | -678.34 | 12612.08 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Refripor | Individual | LAC | BRA | FOA | 31 | INV | 185 | A | I | CFC | 10.9 | 10.9 | 0 | 0 | 2000-07-01 | 2001-07-01 | 2003-08-01 |  | 2001-12-01 | 2004-01-01 | 85350 | -16916 | 68434 | 68434 | 100% | 0 | 0 | 0 | 11095.5 | -2198.95 | 8896.55 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNIDO | Phase-out of CFC-11 consumption by conversion to water-blown and HCFC-141b technology at Sector Co. in the manufacture of polyurethane integral skin and flexible moulded polyurethane foam | Individual | LAC | BRA | FOA | 31 | INV | 186 | A | I | CFC | 17.7 | 17.7 |  |  | 2000-07-01 | 2001-11-01 | 2003-01-01 |  | 2002-12-01 | 2003-02-01 | 130490 | 0 | 130490 | 130489.64 | 100% | 0.36 | 0 |  | 16964 | -7 | 16957 | 0 | 0 | FIN
FIN | UNDP | Conversion from CFC-11 to methylene chloride/LIA technology in the manufacture of flexible polyurethane boxfoam, from CFC-11 to water-blown foam in flexible molded foam, and from CFC-11 to HCFC-141b in flexible integral skin foam at Multispuma | Individual | LAC | BRA | FOA | 31 | INV | 187 | A | I | CFC | 24 | 24 | 0 | 0 | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2001-12-01 | 2003-04-01 | 123929 | 0 | 123929 | 123929 | 100% | 0 | 0 | 0 | 16110.77 | 0 | 16110.77 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-based technology in the manufacture of integral skin (shoesoles) at Prosola | Individual | LAC | BRA | FOA | 31 | INV | 188 | A | I | CFC | 18.1 | 18.1 | 0 | 0 | 2000-07-01 | 2001-02-01 | 2003-08-01 |  | 2004-12-01 | 2006-10-01 | 214118 | -165 | 213953 | 213953 | 100% | 0 | 0 | 0 | 27835.34 | -21 | 27814.34 | 0 | 0 | Completed in 2004. Financially completed in 2006. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and water based technology in the manufacture of rigid polyurethane foam and flexible molded/integral skin foam at 50 small enterprises centered around their systems house Plastquim | Individual | LAC | BRA | FOA | 31 | INV | 189 | A | I | CFC | 153.4 | 153.4 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2003-12-01 | 2005-12-01 | 931599 | -41480 | 890119 | 890119 | 100% | 0 | 0 | 0 | 112475.9 | -4563 | 107912.9 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of rigid foam at Rytpak | Individual | LAC | BRA | FOA | 32 | INV | 190 | A | I | CFC | 27 | 27 | 0 | 0 | 2000-12-01 | 2001-02-01 | 2004-01-01 |  | 2002-03-01 | 2003-04-01 | 211410 | -22300 | 189110 | 189110 | 100% | 0 | 0 | 0 | 27483.3 | -2899.05 | 24584.25 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-based technology in the manufacture of integral skin foams (shoesoles) at Megaflex | Individual | LAC | BRA | FOA | 32 | INV | 191 | A | I | CFC | 41.5 | 41.5 | 0 | 0 | 2000-12-01 | 2001-02-01 | 2004-01-01 |  | 2002-04-01 | 2003-05-01 | 205568 | -4726 | 200842 | 200842 | 100% | 0 | 0 | 0 | 26723.84 | -614.38 | 26109.46 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of rigid foam at Plastiron | Individual | LAC | BRA | FOA | 32 | INV | 192 | A | I | CFC | 32.4 | 32.4 | 0 | 0 | 2000-12-01 | 2001-03-01 | 2004-01-01 |  | 2002-08-01 | 2003-04-01 | 131768 | -5277 | 126491 | 126491 | 100% | 0 | 0 | 0 | 17129.84 | -686.01 | 16443.83 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Refri-Leste | Individual | LAC | BRA | FOA | 32 | INV | 193 | A | I | CFC | 30 | 30 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2002-09-01 | 2003-04-01 | 136840 | -232 | 136608 | 136608 | 100% | 0 | 0 | 0 | 17789.2 | -30.16 | 17759.04 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of rigid integral skin foam and to HCFC-141b for rigid polyurethane foam at Poliumetka | Individual | LAC | BRA | FOA | 32 | INV | 194 | A | I | CFC | 25.5 | 25.5 | 0 | 0 | 2000-12-01 | 2001-03-01 | 2004-01-01 |  | 2002-05-01 | 2003-09-01 | 136183 | -10263 | 125920 | 125920 | 100% | 0 | 0 | 0 | 17703.79 | -1334.06 | 16369.73 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Termobras | Individual | LAC | BRA | FOA | 32 | INV | 195 | A | I | CFC | 77 | 77 | 0 | 0 | 2000-12-01 | 2001-03-01 | 2004-01-01 |  | 2003-08-01 | 2005-09-01 | 294590 | -39496 | 255094 | 255094 | 100% | 0 | 0 | 0 | 38296.7 | -5135 | 33161.7 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-12 to isobutane technology in the manufacture of extruded polyethylene foam at Thermo-flex | Individual | LAC | BRA | FOA | 32 | INV | 196 | A | I | CFC | 15 | 15 | 0 | 0 | 2000-12-01 | 2001-07-01 | 2004-01-01 |  | 2003-12-01 | 2005-10-01 | 123300 | 0 | 123300 | 123300 | 100% | 0 | 0 | 0 | 16029 | 0 | 16029 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and water technology in the manufacture of rigid polyurethane foam at Ser Therm | Individual | LAC | BRA | FOA | 32 | INV | 197 | A | I | CFC | 72 | 72 | 0 | 0 | 2000-12-01 | 2001-07-01 | 2004-01-01 |  | 2003-12-01 | 2005-09-01 | 359791 | -76117 | 283674 | 283674 | 100% | 0 | 0 | 0 | 46772.83 | -9895 | 36877.83 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manfuacture of rigid polyurethane foam at Jose Sola | Individual | LAC | BRA | FOA | 32 | INV | 198 | A | I | CFC | 38.7 | 38.7 | 0 | 0 | 2000-12-01 | 2001-11-01 | 2004-01-01 |  | 2002-11-01 | 2005-09-01 | 150369 | -24740 | 125629 | 125629 | 100% | 0 | 0 | 0 | 19547.97 | -3216 | 16331.97 | 0 | 0 | Completed in 2002. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Frigs | Individual | LAC | BRA | FOA | 32 | INV | 201 | A | I | CFC | 90 | 90 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2002-08-01 | 2003-04-01 | 311056 | -73855 | 237201 | 237201 | 100% | 0 | 0 | 0 | 40437.28 | -9601.15 | 30836.13 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | LAC | BRA | FOA | 33 | PRP | 202 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNIDO | Project preparation for two projects in the integral skin sector | Individual | LAC | BRA | FOA | 33 | PRP | 204 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-05-01 | 2002-04-01 |  | 2002-06-01 | 2003-03-01 | 20000 | -615 | 19385 | 19384.52 | 100% | 0.48 | 0 |  | 2600 | -84 | 2516 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project preparation for two projects in the rigid foam sector | Individual | LAC | BRA | FOA | 33 | PRP | 206 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-10-01 | 2002-04-01 |  | 2002-06-01 | 2003-06-01 | 20000 | -130 | 19870 | 19870.32 | 100% | -0.32 | 0 |  | 2600 | -21 | 2579 | 0 | 0 | FIN |  |  |  | INV
FIN | UNDP | Project preparation in the flexible polyurethane foam sector | Individual | LAC | BRA | FOA | 33 | PRP | 207 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
CLO | UNDP | Project preparation in the foam sector | Individual | LAC | BRA | FOA | 33 | PRP | 209 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 |  | 2002-04-01 |  |  | 2003-12-01 | 15000 | -15000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 1950 | -1950 | 0 | 0 | 0 | Canceled in 2002. Financially Completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Project preparation in the integral skin foam sector | Individual | LAC | BRA | FOA | 33 | PRP | 210 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 | 0 | 10400 | 0 | 10400 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid integral skin foam at Juntafacil | Individual | LAC | BRA | FOA | 34 | INV | 211 | A | I | CFC | 12.2 | 12.2 | 0 | 0 | 2001-07-01 | 2002-02-01 | 2004-08-01 |  | 2002-09-01 | 2004-01-01 | 55204 | -3500 | 51704 | 51704 | 100% | 0 | 0 | 0 | 7176.52 | -455 | 6721.52 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 2001 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid integral skin foam at Ornati-Luce | Individual | LAC | BRA | FOA | 34 | INV | 212 | A | I | CFC | 14.1 | 14.1 | 0 | 0 | 2001-07-01 | 2002-02-01 | 2004-08-01 |  | 2002-09-01 | 2003-11-01 | 46292 | -1550 | 44742 | 44742 | 100% | 0 | 0 | 0 | 6017.96 | -201.5 | 5816.46 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of flexible molded foam at Paranoa | Individual | LAC | BRA | FOA | 34 | INV | 213 | A | I | CFC | 13 | 13 | 0 | 0 | 2001-07-01 | 2002-03-01 | 2004-08-01 |  | 2003-05-01 | 2004-01-01 | 84660 | -1 | 84659 | 84659 | 100% | 0 | 0 | 0 | 11005.8 | 0 | 11005.8 | 0 | 0 | Completed in 2003. Financially completed in 2004. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of rigid polyurethane foam and rigid integral skin foam at Piatex | Individual | LAC | BRA | FOA | 34 | INV | 214 | A | I | CFC | 15 | 15 | 0 | 0 | 2001-07-01 | 2002-08-01 | 2004-08-01 |  | 2003-05-01 | 2005-11-01 | 83075 | 0 | 83075 | 83075 | 100% | 0 | 0 | 0 | 10799.75 | 0 | 10799.75 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to water-based technology in the manufacture of flexible molded foam and to HCFC-141b for flexible integral skin foam at Rosil | Individual | LAC | BRA | FOA | 34 | INV | 215 | A | I | CFC | 5.2 | 5.2 | 0 | 0 | 2001-07-01 | 2002-08-01 | 2004-08-01 |  | 2002-12-01 | 2004-01-01 | 87672 | -2545 | 85127 | 85127 | 100% | 0 | 0 | 0 | 11397.36 | -330.98 | 11066.38 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 2001 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of flexible integral skin and flexible molded foams at Royal Rubber | Individual | LAC | BRA | FOA | 34 | INV | 216 | A | I | CFC | 15.3 | 15.3 | 0 | 0 | 2001-07-01 | 2002-08-01 | 2004-08-01 |  | 2002-12-01 | 2004-01-01 | 120795 | -3396 | 117399 | 117399 | 100% | 0 | 0 | 0 | 15703.35 | -441.48 | 15261.87 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of rigid polyurethane foam for electrical resistance floats at Taurus | Individual | LAC | BRA | FOA | 34 | INV | 217 | A | I | CFC | 12 | 12 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2002-10-01 | 2003-11-01 | 88075 | 0 | 88075 | 88075 | 100% | 0 | 0 | 0 | 11449.75 | 0 | 11449.75 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Thermoblock | Individual | LAC | BRA | FOA | 34 | INV | 218 | A | I | CFC | 41.1 | 41.1 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2002-10-01 | 2003-11-01 | 260592 | -36386 | 224206 | 224206 | 100% | 0 | 0 | 0 | 33876.96 | -4730.18 | 29146.78 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-based and HCFC-141b technology in the manufacture of rigid and flexible integral skin foam at VM | Individual | LAC | BRA | FOA | 34 | INV | 220 | A | I | CFC | 13.7 | 13.7 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2002-12-01 | 2003-11-01 | 83902 | 0 | 83902 | 83902 | 100% | 0 | 0 | 0 | 10907.26 | 0 | 10907.26 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of rigid polyurethane foam for surfboards at Jedda | Individual | LAC | BRA | FOA | 34 | INV | 221 | A | I | CFC | 54 | 54 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2002-10-01 | 2003-11-01 | 148272 | -32257 | 116015 | 116015 | 100% | 0 | 0 | 0 | 19275.36 | -4193.41 | 15081.95 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNIDO | Phase-out of CFC-11 consumption by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam for insulating purposes at Danica Co. | Individual | LAC | BRA | FOA | 34 | INV | 222 | A | I | CFC | 146.6 | 146.6 |  |  | 2001-07-01 | 2002-07-01 | 2004-02-01 |  | 2004-02-01 | 2004-06-01 | 616625 | 0 | 616625 | 616625.24 | 100% | -0.24 | 0 |  | 77829 | -84 | 77745 | 0 | 0 | FIN |  |  |  | INV
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Transen | Individual | LAC | BRA | FOA | 34 | INV | 224 | A | I | CFC | 18.9 | 18.9 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2004-08-01 |  | 2002-08-01 | 2003-11-01 | 61940 | -1800 | 60140 | 60140 | 100% | 0 | 0 | 0 | 8052.2 | -234 | 7818.2 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b in the manufacture of rigid foam for cold room panels, freezers and coolers at Central Equipment | Individual | LAC | BRA | FOA | 34 | INV | 225 | A | I | CFC | 15.1 | 15.1 | 0 | 0 | 2001-07-01 | 2002-07-01 | 2004-08-01 |  | 2002-12-01 | 2004-01-01 | 118233 | -8399 | 109834 | 109834 | 100% | 0 | 0 | 0 | 15370.29 | -1091.87 | 14278.42 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Isar | Individual | LAC | BRA | FOA | 34 | INV | 226 | A | I | CFC | 23 | 23 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2003-08-01 | 2005-09-01 | 174320 | -12870 | 161450 | 161450 | 100% | 0 | 0 | 0 | 22661.6 | -1673 | 20988.6 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Isoeste | Individual | LAC | BRA | FOA | 34 | INV | 227 | A | I | CFC | 64.9 | 64.9 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2003-08-01 | 2006-06-01 | 237296 | -33228 | 204068 | 204068 | 100% | 0 | 0 | 0 | 30848.48 | -4320 | 26528.48 | 0 | 0 | Completed in 2003. Financially completed in 2006. |  | 2001 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid and flexible integral skin foams at Air Micro | Individual | LAC | BRA | FOA | 34 | INV | 229 | A | I | CFC | 17.3 | 17.3 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2004-08-01 |  | 2002-08-01 | 2004-01-01 | 56490 | -2984 | 53506 | 53506 | 100% | 0 | 0 | 0 | 7343.7 | -387.66 | 6956.04 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 2001 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of rigid integral skin foam at Beneplast | Individual | LAC | BRA | FOA | 34 | INV | 230 | A | I | CFC | 11.7 | 11.7 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2002-12-01 | 2004-01-01 | 135176 | -12534 | 122642 | 122642 | 100% | 0 | 0 | 0 | 17572.88 | -1629.42 | 15943.46 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Korta Calhas | Individual | LAC | BRA | FOA | 34 | INV | 231 | A | I | CFC | 75.7 | 75.7 | 0 | 0 | 2001-07-01 | 2002-02-01 | 2004-08-01 |  | 2003-08-01 | 2005-10-01 | 151812 | 0 | 151812 | 151812 | 100% | 0 | 0 | 0 | 19735.56 | 0 | 19735.56 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of rigid integral skin foam, rigid foam and flexible molded foam at Carolinas | Individual | LAC | BRA | FOA | 34 | INV | 232 | A | I | CFC | 49.7 | 49.7 | 0 | 0 | 2001-07-01 | 2002-05-01 | 2004-08-01 |  | 2002-10-01 | 2003-11-01 | 237597 | -80 | 237517 | 237517 | 100% | 0 | 0 | 0 | 30887.61 | -10.4 | 30877.21 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of flexible molded foam and rigid integral skin foam, and to HCFC-141b for rigid, flexible integral skin and phenolic foams at J. Dal Ponte | Individual | LAC | BRA | FOA | 34 | INV | 233 | A | I | CFC | 97.6 | 97.6 | 0 | 0 | 2001-07-01 | 2002-07-01 | 2004-08-01 |  | 2002-12-01 | 2004-01-01 | 384134 | 0 | 384134 | 384134 | 100% | 0 | 0 | 0 | 49937.42 | 0 | 49937.42 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HFC-141b in the manufacture of rigid polyurethane foam at Danko | Individual | LAC | BRA | FOA | 34 | INV | 234 | A | I | CFC | 41.4 | 41.4 | 0 | 0 | 2001-07-01 | 2002-07-01 | 2004-08-01 |  | 2003-08-01 | 2005-10-01 | 199684 | -3329 | 196355 | 196355 | 100% | 0 | 0 | 0 | 25958.92 | -432.77 | 25526.1487 | 0.001343 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b in the manufacture of rigid polyurethane foam for truck bodies and panels at 9 enterprises (ABC Furgoes, Fricam Refri, Junges, Rafaeli, Refri Santos, Rondofrio, Tresmaiense, Trevosul Refrig, Verde Lago Furgoes) | Individual | LAC | BRA | FOA | 34 | INV | 235 | A | I | CFC | 65.3 | 65.3 | 0 | 0 | 2001-07-01 | 2002-08-01 | 2004-08-01 |  | 2003-05-01 | 2005-12-01 | 450479 | -69602 | 380877 | 380877 | 100% | 0 | 0 | 0 | 58562.27 | -9047.73 | 49514.54 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
CLO | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Grupo ACO | Individual | LAC | BRA | FOA | 34 | INV | 236 | A | I | CFC | 0 | 0 | 0 | 0 | 2001-07-01 |  | 2004-08-01 |  |  | 2002-07-01 | 174139 | -174139 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 22638.07 | -22638.07 | 0 | 0 | 0 | Canceled in 2002. Financially Completed in 2002. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Isoprice | Individual | LAC | BRA | FOA | 34 | INV | 237 | A | I | CFC | 16.2 | 16.2 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-08-01 |  | 2003-12-01 | 2006-10-01 | 126846 | -9673 | 117173 | 117173 | 100% | 0 | 0 | 0 | 16489.98 | -1257 | 15232.98 | 0 | 0 | Completed in 2003. Financially completed in 2006. |  | 2001 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water-blown technology in the manufacture of rigid and flexible microcellular foams at Hidroplas | Individual | LAC | BRA | FOA | 34 | INV | 238 | A | I | CFC | 33 | 33 | 0 | 0 | 2001-07-01 | 2002-07-01 | 2004-02-01 |  | 2002-11-01 | 2004-01-01 | 166211 | -5537 | 160674 | 160674 | 100% | 0 | 0 | 0 | 21607.43 | -719.81 | 20887.62 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam for ice cream makers and coolers at three enterprises (A.V. Bertollo, Citrocar, Systherm) | Individual | LAC | BRA | FOA | 34 | INV | 239 | A | I | CFC | 25.5 | 25.5 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2004-08-01 |  | 2002-10-01 | 2005-12-01 | 135345 | -2457 | 132888 | 132888 | 100% | 0 | 0 | 0 | 17594.85 | -319.41 | 17275.44 | 0 | 0 | Completed in 2002. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid integral skin foam at Injetec | Individual | LAC | BRA | FOA | 34 | INV | 240 | A | I | CFC | 11.7 | 11.7 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-08-01 |  | 2002-08-01 | 2003-11-01 | 43334 | -2371 | 40963 | 40963 | 100% | 0 | 0 | 0 | 5633.42 | -308.23 | 5325.19 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam and flexible integral skin foam at Pretty Glass | Individual | LAC | BRA | FOA | 36 | INV | 243 | A | I | CFC | 17.2 | 17.2 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-03-01 |  | 2003-12-01 | 2005-12-01 | 91508 | -6465 | 85043 | 85043 | 100% | 0 | 0 | 0 | 11896.04 | -840 | 11056.04 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam at Decorfrio | Individual | LAC | BRA | FOA | 36 | INV | 244 | A | I | CFC | 18 | 18 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-03-01 |  | 2005-12-01 | 2007-03-01 | 98416 | -3 | 98413 | 98413 | 100% | 0 | 0 | 0 | 12794.08 | -0.39 | 12793.69 | 0 | 0 | Completed in 2005. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam at Simonaggio | Individual | LAC | BRA | FOA | 36 | INV | 245 | A | I | CFC | 15.8 | 15.8 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-03-01 |  | 2003-12-01 | 2005-09-01 | 120383 | -10640 | 109743 | 109743 | 100% | 0 | 0 | 0 | 15649.79 | -1383 | 14266.79 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Heliotek | Individual | LAC | BRA | FOA | 36 | INV | 246 | A | I | CFC | 27.4 | 27.4 | 0 | 0 | 2002-03-01 | 2002-09-01 | 2004-03-01 |  | 2003-12-01 | 2005-12-01 | 127133 | -12221 | 114912 | 114912 | 100% | 0 | 0 | 0 | 16527.29 | -1588 | 14939.29 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Isojet | Individual | LAC | BRA | FOA | 36 | INV | 247 | A | I | CFC | 47.4 | 47.4 | 0 | 0 | 2002-03-01 | 2002-09-01 | 2004-03-01 |  | 2003-12-01 | 2005-12-01 | 130427 | 0 | 130427 | 130427 | 100% | 0 | 0 | 0 | 16955.51 | 0 | 16955.51 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to methylene chloride/LIA technology in the manufacture of flexible polyurethane boxfoam at Tecnosono | Individual | LAC | BRA | FOA | 36 | INV | 248 | A | I | CFC | 23 | 23 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-12-01 |  | 2003-07-01 | 2004-01-01 | 134718 | -4512.44 | 130205.56 | 130206 | 100% | -0.44 | 0 | 0 | 17513.34 | -586.61 | 16926.7914 | -0.0614 | 0 | Completed in 2003. Financially completed in 2004. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11to HCFC-141b technology in the manufacture of rigid polyurethane foam and flexible integral skin foam at Tolling Quimica | Individual | LAC | BRA | FOA | 36 | INV | 249 | A | I | CFC | 21.9 | 21.9 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-03-01 |  | 2003-08-01 | 2005-10-01 | 159662 | -1356 | 158306 | 158306 | 100% | 0 | 0 | 0 | 20756.06 | -176.28 | 20579.7805 | -0.000547 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water and HCFC-141b technology in the manufacture of rigid polyurethane foam at Fibral | Individual | LAC | BRA | FOA | 36 | INV | 250 | A | I | CFC | 47.5 | 47.5 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-09-01 |  | 2003-12-01 | 2007-03-01 | 197613 | -1856 | 195757 | 195757 | 100% | 0 | 0 | 0 | 25689.69 | -241.28 | 25448.4071 | 0.0029 | 0 | Completed in 2003. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of flexible integral skin foam, and water-blown technology for flexible moulded foam at Arquespuma | Individual | LAC | BRA | FOA | 36 | INV | 252 | A | I | CFC | 55.8 | 55.8 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-09-01 |  | 2003-12-01 | 2007-01-01 | 207741 | 0 | 207741 | 207741 | 100% | 0 | 0 | 0 | 27006.33 | 0 | 27006.33 | 0 | 0 | Completed in 2003. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Isosister | Individual | LAC | BRA | FOA | 36 | INV | 254 | A | I | CFC | 82.5 | 82.5 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-03-01 |  | 2004-12-01 | 2007-03-01 | 277668 | -6748 | 270920 | 270920 | 100% | 0 | 0 | 0 | 36096.84 | -877.24 | 35219.5961 | 0.0039 | 0 | Completed in 2004. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water/methylene chloride/hydrocarbon-blown technology in the manufacture of rigid and flexible foam at Toro | Individual | LAC | BRA | FOA | 36 | INV | 255 | A | I | CFC | 22.4 | 22.4 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2005-03-01 |  | 2004-12-01 | 2005-10-01 | 279477 | 0 | 279477 | 279477 | 100% | 0 | 0 | 0 | 36332.01 | 0 | 36332.01 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Repor | Individual | LAC | BRA | FOA | 36 | INV | 256 | A | I | CFC | 50.8 | 50.8 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-03-01 |  | 2004-12-01 | 2008-04-01 | 323201 | -35934 | 287267 | 287267 | 100% | 0 | 0 | 0 | 42016.13 | -4671.42 | 37344.71 | 0 | 0 | Completed in 2004. Financially completed in 2008. |  | 2001 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid foam and flexible integral skin foam and water-blown technology for flexible moulded foam and rigid integral skin foam at Ariston Polimeros | Individual | LAC | BRA | FOA | 36 | INV | 257 | A | I | CFC | 75.1 | 75.1 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2005-03-01 |  | 2003-08-01 | 2005-09-01 | 369242 | -12749 | 356493 | 356493 | 100% | 0 | 0 | 0 | 48001.46 | -1657 | 46344.46 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water-blown technology in the manufacture of flexible moulded foam at Indaru | Individual | LAC | BRA | FOA | 36 | INV | 258 | A | I | CFC | 93.8 | 93.8 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-12-01 |  | 2004-06-01 | 2007-03-01 | 423121 | 0 | 423121 | 423121 | 100% | 0 | 0 | 0 | 55005.73 | 0 | 55005.73 | 0 | 0 | Completed in 2004. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water-blown technology in the manufacture of flexible moulded foam, elastomers and integral skin foam for automotive applications and to HCFC-141b for furniture integral skin foam applications at Steel Plastik | Individual | LAC | BRA | FOA | 36 | INV | 259 | A | I | CFC | 46.7 | 46.7 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2005-03-01 |  | 2003-12-01 | 2005-11-01 | 247882 | 0 | 247882 | 247882 | 100% | 0 | 0 | 0 | 32224.66 | 0 | 32224.66 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Pilot project for validation of methyl formate as a blowing agent in the manufacture of polyurethane foam (phase I) | Individual | LAC | BRA | FOA | 56 | DEM | 285 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-06-01 | 2009-06-01 |  | 2010-12-01 | 2014-05-01 | 401500 | -25777.88 | 375722.12 | 375722 | 100% | 0.12 | 0 | 0 | 30113 | -1933.37 | 28179.6179 | 0.012102 | 0 | Financially completed in 2014. |  | 2008 | 2010-08-01 | Non-Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | LAC | BRA | FOA | 57 | PRP | 287 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-12-01 | 2010-03-01 |  | 2011-07-01 | 2012-06-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 | 0 | 11250 | 0 | 11250 | 0 | 0 | Financially completed in 2012. | Completed in 2011. Sector Foam projects approved by the 64th Executive Committee Meeting. Some remaining invoices pending. | 2009 |  | Investment
FIN | UNDP | Pilot project to validate methylal as blowing agent in the manufacture of polyurethane foams (phase I) | Individual | LAC | BRA | FOA | 58 | DEM | 292 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-07-01 | 2010-01-01 | 2010-07-01 |  | 2012-12-01 | 2014-02-01 | 464200 | -33805 | 430395 | 430395 | 100% | 0 | 0 | 0 | 34815 | -2535.38 | 32279.62 | 0 | 0 | Financially completed in 2014. | Completed in 2012. Final payments for Technical Assistance and commissioning in 2012 have been completed and will be reflected in 2013. | 2009 |  | Non-Investment
COM | UNDP | Preparation for HCFC phase-out investment activities (stage II) (foam sector) | Individual | LAC | BRA | FOA | 72 | PRP | 301 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 | 2014-11-01 | 2016-05-01 |  | 2016-11-01 |  | 150000 | 0 | 150000 | 95401.5 | 63.6% | 54598.5 | 29300.73 | 46408.725 | 10500 | 0 | 6678.105 | 3821.895 | 2051.0511 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Foam Sector planned approved by the ExCom. Follow-up activities with System Houses, individual Projects and end-users to gather additional information needed for the procurement processes and for the signing of the contracts in the project. Still some pending payments. Prodoc signed (actual/planned, yes/no and date):Signed earlier Missions undertaken (actual/planned):4 of 4 TOR for consultants/subcontracts completed (actual/planned): 1 of 1 Contract/PO/MOA agreements signed: 0 of 0 First disbursement date (actual/planned): 41944Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | All pending payments have been cleared. |  |  | Non-Investment
FIN | UNIDO | Demonstration project: three alternatives to the use of methyl bromide: non-soil cultivation, solarization and low-dose chemicals | Individual | LAC | BRA | FUM | 22 | DEM | 73 | A | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 2000-05-01 | 2002-09-01 | 393800 | -28111 | 365689 | 365689.05 | 100% | -0.05 | 0 |  | 51194 | -3730 | 47464 | 0 | 0 | FIN
CLO | UNDP | Project preparation for two methyl bromide demonstration projects (soil fumigation for flowers, tomatoes, cucumbers and strawberries) | Individual | LAC | BRA | FUM | 24 | PRP | 96 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-08-01 | 1998-12-01 |  |  | 2000-12-01 | 40000 | -31187 | 8813 | 8813 | 100% | 0 | 0 | 0 | 5200 | -4054.31 | 1145.69 | 0 | 0 | Canceled in 2000. Financially completed in 2000. |  | 1998 |  | Investment
FIN | UNIDO | Project preparation in the fumigant/ methyl bromide sector (tobacco) | Individual | LAC | BRA | FUM | 27 | PRP | 165 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-07-01 | 1999-12-01 |  | 2000-04-01 | 2001-07-01 | 50000 | -3855 | 46145 | 46145 | 100% | 0 | 0 |  | 6500 | -511 | 5989 | 0 | 0 | FIN
FIN | UNIDO | Phasing out methyl bromide in the entire Tobacco Sector | Individual | LAC | BRA | FUM | 28 | INV | 142 | A | I | MBR | 84.4 | 84.4 |  |  | 1999-07-01 | 2000-06-01 | 2002-08-01 |  | 2001-12-01 | 2002-10-01 | 2344440 | -19971 | 2324469 | 2324468.93 | 100% | 0.07 | 0 |  | 267888 | -2602 | 265286 | 0 | 0 | FIN
FIN | UNIDO | Assistance for the preparation of a survey on the consumption of methyl bromide | Individual | LAC | BRA | FUM | 38 | TAS | 263 | A | I | MBR | 0 | 0 |  |  | 2002-11-01 | 2004-04-01 | 2003-12-01 |  | 2005-09-01 | 2006-09-01 | 40000 | -862 | 39138 | 39137.91 | 100% | 0.09 | 0 |  | 5200 | -112 | 5088 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Project preparation in methyl bromide (tobacco, flowers, horticulture) | Individual | LAC | BRA | FUM | 44 | PRP | 269 | A | I |  | 0 | 0 |  |  | 2004-12-01 | 2005-04-01 | 2005-12-01 |  | 2005-12-01 | 2006-11-01 | 40000 | -1133 | 38867 | 38866.6 | 100% | 0.4 | 0 |  | 3000 | -85 | 2915 | 0 | 0 | FIN
FIN | Spain | Total phase-out of MB used in tobacco, flowers, ornamental plants, strawberries and other uses | Individual | LAC | BRA | FUM | 46 | INV | 272 | A | I | MBR | 65.4 | 65.4 | 0 |  | 2005-07-01 | 2006-10-01 | 2007-07-01 |  | 2008-12-01 | 2010-06-01 | 580390 | -212 | 580178 | 580178 | 100% | 0 | 0 | 0 | 75451 | -28 | 75423.14 | -0.14 | 0 | Financial completion in Jun 2010. Refund was reported to 61st ExCom, Jul 2010. FIN. |  |  |  | Investment
FIN | UNIDO | Total phase-out of MB used in tobacco, flowers, ornamentals, strawberries and other uses | Individual | LAC | BRA | FUM | 46 | INV | 273 | A | I | MBR | 153.2 | 153.2 |  |  | 2005-07-01 | 2005-10-01 | 2007-07-01 |  | 2008-12-01 | 2010-12-01 | 1450251 | -454 | 1449797 | 1449797.43 | 100% | -0.43 | 0 |  | 108769 | -34 | 108735 | 0 | 0 | FIN |  |  | 2008-12-01 | INV
FIN | Canada | Halon recycling and bank management | Halon Banking | LAC | BRA | HAL | 19 | TAS | 47 | A | I |  | 21.3 | 21.3 | 0 |  | 1996-05-01 | 1996-10-01 | 1998-05-01 |  | 1999-05-01 | 1999-05-01 | 499360 | -20031 | 479329 | 479329 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project successfully implemented although one year later than planned. Adjustment results of exchange rate fluctuations |  | 1996 | 1998-09-01 | Non-Inv.
FIN | IBRD | Project preparation in the process agent sub-sector |  | LAC | BRA | PAG | 36 | PRP | 242 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-12-01 | 2003-09-01 |  | 2003-09-01 | 2003-12-01 | 50000 | -14819 | 35181 | 35181 | 100% | 0 | 0 |  | 6500 | -1926 | 4573.53 | 0.47 | 0.47 | Upon confirmation of very low national CTC consumption, arrangements with Ministry of Environment are being made to transfer project to UNDP. |  |  |  | Non-INV | 0
FIN | UNDP | Phase-out of CTC as process agent in two applications at Braskem | Individual | LAC | BRA | PAG | 54 | INV | 281 | N | I | CTC | 0 | 0 | 0 | 0 | 2008-04-01 | 2009-04-01 | 2010-03-01 |  | 2010-12-01 | 2013-01-01 | 1178554 | -6110 | 1172444 | 1172444 | 100% | 0 | 0 | 0 | 88392 | -458.25 | 87933.7477 | 0.0023 | 0 | Financially completed in 2013. |  | 2008 |  | Investment
FIN | UNDP | Preparation of a CFC terminal phase-out programme | Individual | LAC | BRA | PHA | 36 | PRP | 251 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2005-12-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 26000 | 0 | 26000 | 0 | 0 | Completed in 2002. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | National CFC phase-out plan (first tranche) | Multi-Year | LAC | BRA | PHA | 37 | INV | 262 | N | I | CFC | 1251 | 1251 | 0 | 0 | 2002-07-01 | 2002-12-01 | 2003-12-01 |  | 2005-12-01 | 2013-12-01 | 7860000 | 0 | 7860000 | 7860000 | 100% | 0 | 0 | 0 | 687700 | 0 | 687700 | 0 | 0 | Financially completed in 2013. |  | 2002 |  | Investment
FIN | Germany | National CFC phase out plan: training of customs officers | Multi-Year | LAC | BRA | PHA | 37 | TRA | 260 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2002-08-01 | 2004-07-01 |  | 2007-12-01 | 2008-12-01 | 141200 | 0 | 141200 | 141200 | 100% | 0 | 0 | 0 | 18356 | 0 | 18356 | 0 | 0 | Training activities for 55 customs officers/instructors as well 9 staff members from the national environmental protection agency are completed. Refrigerant identifiers were purchased in 2007 and distributed to Customs officers. The project is completed.
FIN | Germany | National CFC phase-out plan: training of refrigeration mechanics in domestic and commercial refrigeration service sub-sectors (first tranche) | Multi-Year | LAC | BRA | PHA | 37 | TRA | 261 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2002-08-01 | 2004-07-01 |  | 2006-12-01 | 2007-12-01 | 435937 | 1062863 | 1498800 | 1498800 | 100% | 0 | 0 | 0 | 56672 | 95658 | 152330 | 0 | 0 | By end of 2006 7000 technicians had been trained under this tranche. A total of 27 mobile training units have been built and are used in the field. Production of 8,000 free books with photo-training on good practices for mechanics in the commercial and do
FIN | UNDP | National CFC phase-out plan: second tranche | Multi-Year | LAC | BRA | PHA | 41 | INV | 264 | N | I | CFC | 737 | 737 | 0 | 0 | 2003-12-01 | 2005-01-01 | 2004-12-01 |  | 2008-12-01 | 2013-05-01 | 5720000 | 0 | 5720000 | 5720000 | 100% | 0 | 0 | 0 | 500000 | 0 | 500000 | 0 | 0 | Financially completed in 2013. |  | 2003 |  | Investment
FIN | Germany | National CFC phase-out plan: second tranche | Multi-Year | LAC | BRA | PHA | 41 | INV | 265 | A | I | CFC | 0 | 0 | 0 |  | 2003-12-01 | 2005-04-01 | 2005-12-01 |  | 2008-12-01 | 2008-12-01 | 700000 | 0 | 700000 | 700000 | 100% | 0 | 0 | 0 | 63000 | 0 | 63000 | 0 | 0 | By end of 2008, more than 300 technicians had been trained under this tranche. One train the trainer course with 35 participants was conducted. A total of 12 mobile training units have been built and are used in the field. Continue to further distribute educational materials and public relation materials and to monitor and to follow up the success of training activities of technicians.
FIN | UNDP | National CFC phase-out plan: third tranche | Multi-Year | LAC | BRA | PHA | 45 | INV | 270 | N | I | CFC | 743 | 743 | 0 | 0 | 2005-04-01 | 2007-01-01 | 2006-04-01 |  | 2009-12-01 | 2013-02-01 | 3970000 | 0 | 3970000 | 3970000 | 100% | 0 | 0 | 0 | 342500 | 0 | 342500 | 0 | 0 | Financially completed in 2013. |  | 2005 |  | Investment
FIN | UNDP | National CFC phase-out plan: fourth tranche | Multi-Year | LAC | BRA | PHA | 47 | INV | 274 | N | I | CFC | 1020 | 1020 | 0 | 0 | 2005-11-01 | 2010-01-01 | 2006-12-01 |  | 2011-10-01 | 2013-12-01 | 2856400 | 0 | 2856400 | 2856400 | 100% | 0 | 0 | 0 | 242276 | 0 | 242276 | 0 | 0 | Financially completed in 2013. |  | 2005 |  | Investment
FIN | Germany | National CFC phase-out plan: third and fourth tranches | Multi-Year | LAC | BRA | PHA | 48 | INV | 277 | A | I | CFC | 0 |  | 0 |  | 2006-04-01 | 2006-12-01 | 2007-04-01 |  | 2011-04-01 | 2011-12-01 | 1543600 | 0 | 1543600 | 1543600 | 100% | 0 | 0 | 0 | 138924 | 0 | 138924 | 0 | 0 | Project completed
FIN | UNDP | National CFC phase-out plan (fifth tranche) | Multi-Year | LAC | BRA | PHA | 50 | INV | 278 | N | I | CFC | 1050 | 1050 | 0 | 0 | 2006-11-01 | 2011-04-01 | 2009-12-01 |  | 2012-09-01 | 2013-05-01 | 1190000 | 0 | 1190000 | 1190000 | 100% | 0 | 0 | 0 | 92300 | 0 | 92300 | 0 | 0 | Financially completed in 2013. |  | 2006 |  | Investment
FIN | UNDP | National CFC phase-out plan (sixth tranche) | Multi-Year | LAC | BRA | PHA | 53 | INV | 280 | N | I | CFC | 576 | 576 | 0 | 0 | 2007-11-01 | 2010-04-01 | 2009-11-01 |  | 2013-12-01 | 2013-12-01 | 870000 | 0 | 870000 | 870000 | 100% | 0 | 0 | 0 | 63500 | 0 | 63500 | 0 | 0 | Financially completed in 2013. |  | 2007 |  | Investment
FIN | Germany | Preparation of a HCFC phase-out management plan (multiple sectors) | Individual | LAC | BRA | PHA | 55 | PRP | 282 | A | I | HCFC | 0 |  | 0 |  | 2008-07-01 | 2009-09-01 | 2009-07-01 |  | 2011-04-01 | 2011-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | HPMP was approved based on a preperatory study
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | BRA | PHA | 55 | PRP | 283 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2011-07-01 | 2012-06-01 | 143750 | 0 | 143750 | 143750 | 100% | 0 | 0 | 0 | 10781.25 | 0 | 10781.25 | 0 | 0 | Financially completed in 2012. | Completed in 2011. HPMP approved by the 64th Executive Committee Meeting. | 2008 |  | Investment
FIN | UNDP | National CFC phase-out plan (seventh tranche) | Multi-Year | LAC | BRA | PHA | 56 | INV | 284 | N | I | CFC | 350 | 350 | 0 | 0 | 2008-11-01 | 2013-02-01 | 2009-11-01 |  | 2013-12-01 | 2013-12-01 | 250000 | 0 | 250000 | 250000 | 100% | 0 | 0 | 0 | 12500 | 0 | 12500 | 0 | 0 | Financially completed in 2013. |  | 2008 |  | Investment
FIN | Germany | Preparation of a HCFC phase-out management plan (extruded polystyrene foam sector) | Individual | LAC | BRA | PHA | 57 | PRP | 286 | A | I | HCFC | 0 |  | 0 |  | 2009-04-01 | 2009-12-01 | 2010-03-01 |  | 2011-04-01 | 2012-12-01 | 42000 | 0 | 42000 | 42000 | 100% | 0 | 0 | 0 | 5460 | 0 | 5460 | 0 | 0 | HPMP was approved based on a preperatory study
FIN | UNDP | National CFC phase-out plan (eighth tranche) | Multi-Year | LAC | BRA | PHA | 59 | INV | 293 | N | I | CFC | 74 | 74 | 0 | 0 | 2009-11-01 | 2013-02-01 | 2011-11-01 |  | 2013-12-01 | 2013-12-01 | 100000 | -13691 | 86309 | 86309 | 100% | 0 | 0 | 0 | 5000 | -685 | 4315 | 0 | 0 | Financially completed in 2013. |  | 2009 |  | Investment
FIN | UNDP | HCFC phase-out management plan (foam sector plan) (stage I, first tranche) | Multi-Year | LAC | BRA | PHA | 64 | INV | 295 | N | I | HCFC | 48.7 | 48.7 | 0 | 0 | 2011-07-01 | 2012-11-01 | 2012-07-01 |  | 2015-07-01 | 2016-07-01 | 4456257 | 0 | 4456257 | 4456257 | 100% | 0 | 0 | 0 | 334219 | 0 | 334219 | 0 | 0 | Financially completed in 2016. | Since 2014, implementation of continuous panels sector reconversions has progressed satisfactorily. Purcom and Arinos have advanced with the implementation of end-users trials and retrofits. | 2011 |  | Investment
FIN | Germany | HCFC phase-out management plan (refrigeration servicing sector) (stage I, first tranche) | Multi-Year | LAC | BRA | PHA | 64 | INV | 296 | A | I | HCFC | 14.8 | 2 | 0 |  | 2011-07-01 | 2011-10-01 | 2012-07-01 |  | 2015-09-01 | 2016-01-01 | 1209091 | 0 | 1209091 | 1209091 | 100% | 0 | 0 | 0 | 153000 | 0 | 153000 | 0 | 0 | Best practice Handbook for technician training developed & designed, training institutions selected and contracted, mobile training units assembled and distributed, technical standards elaborated, technical assistance programme for end users established, website and facebook fanpage published, regional outreach, 24 technical visits to supermarkets conducted, 4 case studies selected
FIN | UNDP | HCFC phase-out management plan (stage I, second tranche) (foam sector plan) | Multi-Year | LAC | BRA | PHA | 68 | INV | 298 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-12-01 | 2015-03-01 | 2014-12-01 |  | 2015-12-01 | 2016-12-01 | 3400000 | 0 | 3400000 | 3400000 | 100% | 0 | 0 | 0 | 255000 | 0 | 255000 | 0 | 0 | Financially completed in 2016. | Since 2014, implementation of integral skin sector reconversions has progressed satisfactorily. All IS System House suppliers have started initial trials at client level. | 2012 |  | Investment
ONG | Germany | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | Multi-Year | LAC | BRA | PHA | 68 | INV | 299 | A | I | HCFC | 0 | 0 | 0 |  | 2012-12-01 | 2013-12-01 | 2015-12-01 | 2017-12-01 |  |  | 2472727 | 0 | 2472727 | 1777607 | 71.89% | 695120 | 683226 | 695120 | 262000 | 0 | 188348 | 73652 | 73652 | Project Delay, 7 train-the-trainer courses carried out and 69 instructors trained, 4137 technicians in commercial refrigeration trained, demonstration tools purchased, identification, measurement and performance analysis equipment for refrigeration systems puchased, technical analysis of four case studies conducted, adaptation of online documentation system & introductory workshops conducted, test phase of online doc system, 2 technical publications and 3 best practice guidelines prepared, 100 technicians trained in best practices and better containment of HCFCs in split air conditioners, participation in sector workshops and fairs, 4 intervention plans and technical specifications for procurement prepared (tender is carried out in cooperation with UNDP), printing of info material and technical publications, operation of technical assistance programme for end users, operation and maintenance of project website and fanpage, monitoring visits to contracted training institutions, press officer contracted and intensive regional outreach with publication of articles in regional sector journals | Techncial and financial evaluation of offers for procurement of equipment and materials for implementation of the demo project in the first two supermarkets carried out and PO placed |  |  | INV
FIN | UNDP | Preparation of a HCFC phase-out management plan (stage II) | Individual | LAC | BRA | PHA | 72 | PRP | 300 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 | 2014-07-01 | 2016-05-01 |  | 2015-11-01 | 2016-11-01 | 50000 | 0 | 50000 | 49067 | 98.13% | 933 | 0 | 0 | 3500 | 0 | 3434.69 | 65.31 | 0 | Financially completed in 2016. | Since 2014, HCFC survey and drafted investment projects were reviewed in light of the new funding guidelines approved by the 74th ExCom. HPMP draft was put into public consultation to collect final inputs from private sector and civil society. |  |  | Investment
COM | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | Individual | LAC | BRA | PHA | 72 | PRP | 302 | A | I |  | 0 | 0 |  |  | 2014-05-01 | 2015-08-01 | 2015-12-31 |  | 2015-12-01 |  | 10000 | 0 | 10000 | 9999.99 | 100% | 0.01 | 0 |  | 700 | 0 | 700 | 0 | 0 | The project was operationally completed. |  |  |  | NON-INV
FIN | Germany | Preparation of a HCFC phase-out management plan (stage II) | Multi-Year | LAC | BRA | PHA | 72 | PRP | 303 | A | I | HCFC | 0 |  | 0 |  | 2014-05-01 | 2014-05-01 | 2015-09-01 |  | 2015-09-01 | 2016-01-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Servicing Sector Study prepared, data collection and processing, stakeholder consultations and agency meetings
ONG | UNDP | HCFC phase-out management plan (stage I, third tranche) (foam sector plan) | Multi-Year | LAC | BRA | PHA | 73 | INV | 306 | N | I | HCFC | 32.7 | 18.2 | 0 | 0 | 2014-11-01 | 2015-05-01 | 2016-11-01 | 2017-03-01 |  |  | 3000000 | 0 | 3000000 | 1770925.15 | 59.03% | 1229074.85 | -0.01 | 491629.94 | 225000 | 0 | 132819.3863 | 92180.6138 | -0.00075 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Successful completion of two umbrella projects, the conversion of one system house, technological reconversion of 86 downstream end users. Prodoc signed (actual/planned, yes/no and date):Signed earlier Missions undertaken (actual/planned):4 of 4 TOR for consultants/subcontracts completed (actual/planned): 4 of 4 Contract/PO/MOA agreements signed: 0 of 0 First disbursement date (actual/planned): Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:The difficult economic situation the country is facing currently is putting some delays on some key activities. | 1 mission undertaken to monitor progress in implementation. | 2014 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, fourth tranche) (foam sector plan) | Multi-year | LAC | BRA | PHA | 74 | INV | 307 | N | I | HCFC | 32.9 | 0 | 0 | 0 | 2015-05-01 |  | 2017-05-01 | 2017-05-01 |  |  | 3000000 | 0 | 3000000 | 0 | 0% | 3000000 | 0 | 1200000 | 225000 | 0 | 0 | 225000 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Successful completion of two umbrella projects, the conversion of one system house, technological reconversion of 86 downstream end users. Prodoc signed (actual/planned, yes/no and date):Signed earlier Missions undertaken (actual/planned):4 of 4 TOR for consultants/subcontracts completed (actual/planned): 4 of 4 Contract/PO/MOA agreements signed: 0 of 0 First disbursement date (actual/planned): Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:The difficult economic situation the country is facing currently is putting some delays on some key activities. | 1 mission undertaken to monitor progress in implementation. | 2015 |  | Investment
ONG | Germany | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | Multi-Year | LAC | BRA | PHA | 75 | INV | 309 | A | I | HCFC | 14.9 | 2 | 0 |  | 2015-11-01 | 2016-05-01 | 2017-12-01 | 2018-12-01 |  |  | 1299386 | 0 | 1299386 | 188428 | 14.5% | 1110958 | 89648 | 750191 | 144614 | 0 | 20971 | 123643 | 123643 | Project Delay: Agreement with Brazilian Government took more time than expected. Contracts with international consultancy established, specifications for training centre equipment and tools prepared (containment trainings), selection process of suitable training locations prepared and published, elaboration of sector communication plan, working on review and update of training materials (handbook and powerpoint presentations), 737 technicians trained in best practice for commercial refrigeration | Review of national safety standard for refrigeration system initiated according to latest version of EN378:2016, tender for contratcting of additional regional training institutions ongoing
ONG | Italy | HCFC phase-out management plan (stage II, first tranche) (foam sector) | Multi-Year | LAC | BRA | PHA | 75 | INV | 310 | A | I | HCFC | 5 |  | 0 |  | 2015-11-01 |  | 2017-12-01 | 2018-12-01 |  |  | 250000 | 0 | 250000 |  | 0% | 250000 |  | 100000 | 32500 | 0 | 0 | 32500 |  | The stage II launch took place on September 16th, 2016, and UNDP, which will act as executing agency on behalf of the Government of Italy for its component, is in the process of starting up the implementation of the foam sector plan. | The foam sector plan is under definition to start up the implementation of activities. The Government of Italy and UNDP are finalizing the trust fund agreement, which will be signed as soon as the foam sector plan will be completely defined. | 2015 | 2019-02-01 | Investment
ONG | UNIDO | HCFC phase-out management plan (stage II, first tranche) (commercial refrigeration and air-conditioning sector) | Multi-Year | LAC | BRA | PHA | 75 | INV | 311 | A | I | HCFC | 10.2 | 0 |  |  | 2015-11-01 |  | 2019-12-01 | 2019-12-01 |  |  | 1674275 | 0 | 1674275 | 0 | 0% | 1674275 | 0 | 50000 | 117199 | 0 | 0 | 117199 | 0 | Brief report: The project is ready for initial stage of implementation. Milestones achieved: Milestone 1: Working arrangements agreed – Yes Milestone 2: Local institutions identified - No Milestone 3: Legal arrangements – No Milestone 4: Initial stages of project implementation began – No Activities planned but not implemented: No Actions towards next goal: The approval of the agreement with the Government. Was any delay during the reporting year? Yes, due to the additional project approval required by the respective authorities in Brazil. Any recurring problem? No Any impact on project completion date: Yes Any actions required by Executive Committee? No | Brief report: The project is ready for initial stage of implementation. Milestones achieved: Milestone 1: Working arrangements agreed – Yes Milestone 2: Local institutions identified - No Milestone 3: Legal arrangements – Yes Milestone 4: Initial stages of project implementation began – No Activities planned but not implemented: No Actions towards next goal: Initial stages of project implementation Was any delay during the reporting year? Yes, due to the additional project approval required by the respective authorities in Brazil. Any recurring problem? No Any impact on project completion date: Yes Any actions required by Executive Committee? No |  |  | INV
ONG | UNDP | HCFC phase-out management plan (stage II, first tranche) (foam sector) | Multi-year | LAC | BRA | PHA | 75 | INV | 312 | N | I | HCFC | 40.8 | 0 | 0 | 0 | 2015-11-01 | 2016-10-01 | 2017-12-01 | 2017-12-01 |  |  | 2028900 | 0 | 2028900 | 1414.38 | 0.06971% | 2027485.62 | 0 | 810994.248 | 142023 | 0 | 99.0066 | 141923.9934 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Signing of contracts with 5 System Houses and 2 individual projects (all Methyl Formate). Agreements reached with 5 individual projects and 1 System House that opted for HFO and CO2 for the development of formulations. 1 individual enterprises agreed on TORs for industrial reconversion. Prodoc signed (actual/planned, yes/no and date):42583 Missions undertaken (actual/planned):2 of 2 TOR for consultants/subcontracts completed (actual/planned): 13 of 13 Contract/PO/MOA agreements signed: 7 of 7 First disbursement date (actual/planned): 42644Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | 1 contract signed with individual company. | 2015 |  | Investment |  | To request the submission of additional status report to the 79th meeting to monitor the signing of the agreement by the Government.
ONG | UNDP | HCFC phase-out management plan (stage I, fifth tranche) (foam sector) | Multi-year | LAC | BRA | PHA | 75 | INV | 315 | N | I | HCFC | 54.5 | 0 | 0 | 0 | 2015-11-01 |  | 2018-11-01 | 2017-11-01 |  |  | 1470700 | 0 | 1470700 | 0 | 0% | 1470700 | 0 | 588280 | 110303 | 0 | 0 | 110303 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Successful completion of two umbrella projects, the conversion of one system house, technological reconversion of 86 downstream end users. Prodoc signed (actual/planned, yes/no and date):Signed earlier Missions undertaken (actual/planned):4 of 4 TOR for consultants/subcontracts completed (actual/planned): 4 of 4 Contract/PO/MOA agreements signed: 0 of 0 First disbursement date (actual/planned): Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:The difficult economic situation the country is facing currently is putting some delays on some key activities. | 1 mission undertaken to monitor progress in implementation. | 2015 |  | Investment
ONG | Germany | HCFC phase-out management plan (stage I, fifth tranche) (refrigeration servicing sector) | Multi-Year | LAC | BRA | PHA | 75 | INV | 316 | A | I | HCFC | 36.7 | 31 | 0 |  | 2015-11-01 | 2016-01-01 | 2016-12-01 | 2017-12-01 |  |  | 409091 | 0 | 409091 | 198900 | 48.62% | 210191 | 115085 | 210191 | 45000 | 0 | 21879 | 23121 | 23121 | 663 technicians trained in better containment of HCFCs in supermarket installations, discussion and development of technical standards for the servicing sector, with participation of experts from the Brazilian Association of Technical Standards - ABNT in monthly meetings, technical assistance for users of the online documentation system, stakeholder meetings | Evaluation report of best practice training courses
ONG | UNIDO | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | Multi-Year | LAC | BRA | PHA | 75 | TAS | 308 | A | I |  | 0 | 0 |  |  | 2015-11-01 |  | 2018-12-01 | 2019-03-01 |  |  | 276000 | 0 | 276000 | 0 | 0% | 276000 | 0 | 30000 | 19320 | 0 | 0 | 19320 | 0 | Brief report: The project is ready for initial stage of implementation Milestones achieved: Milestone 1: Working arrangements agreed – Yes Milestone 2: Local institutions identified - No Milestone 3: Legal arrangements – No Milestone 4: Initial stages of project implementation began – No Activities planned but not implemented: No Actions towards next goal: The Agreement with the Government prepared, waiting approval. Was any delay during the reporting year? Yes, due to the additional project approval required by the respective authorities in Brazil. Any recurring problem? No Any impact on project completion date: No Any actions required by Executive Committee? No | Brief report: The project is ready for initial stage of implementation. Milestones achieved: Milestone 1: Working arrangements agreed – Yes Milestone 2: Local institutions identified - No Milestone 3: Legal arrangements – Yes Milestone 4: Initial stages of project implementation began – No Activities planned but not implemented: No Actions towards next goal: Initial stages of project implementation Was any delay during the reporting year? Yes, due to the additional project approval required by the respective authorities in Brazil. Any recurring problem? No Any impact on project completion date: No major impact Any actions required by Executive Committee? No |  |  | INV
ONG | UNDP | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing, regulatory actions and project monitoring) | Multi-year | LAC | BRA | PHA | 75 | TAS | 313 | N | I | HCFC | 4.4 | 0 | 0 | 0 | 2015-11-01 | 2016-10-01 | 2017-12-01 | 2017-12-01 |  |  | 1050000 | 0 | 1050000 | 32507.72 | 3.096% | 1017492.28 | 0 | 406996.912 | 73500 | 0 | 2275.5404 | 71224.4596 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Procurement process to procure equipment for the servicing sector component undertaken. Contract signed. Standard M&E activities carried out Prodoc signed (actual/planned, yes/no and date):42583 Missions undertaken (actual/planned):1 of 1 TOR for consultants/subcontracts completed (actual/planned): 1 of 1 Contract/PO/MOA agreements signed: 1 of 1 First disbursement date (actual/planned): 42644Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | PO signed for equipment delivery | 2015 |  | Non-Investment |  | To request the submission of additional status report to the 79th meeting to monitor the signing of the agreement by the Government.
FIN | UNDP | Demonstration programme to improve domestic refrigerator servicing and CFC recycling in service shops | Individual | LAC | BRA | REF | 06 | DEM | 04 | A | I | CFC | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-02-01 | 1993-12-01 |  | 1994-12-01 | 1997-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1992 |  | Non-Investment
CLO | IBRD | Assembly line refitting for HFC-134a refrigerator compressor, commercial production | Individual | LAC | BRA | REF | 07 | INV | 06 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1995-06-01 |  |  | 1995-07-01 | 530000 | -530000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Cancelled. |  |  | 1995-06-01 | INV | 0
FIN | IBRD | Project preparation on converting CFC-11 central air conditioning units with HCFC-123 or HFC-134a |  | LAC | BRA | REF | 07 | PRP | 05 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1992-12-01 | 1993-06-01 |  | 1995-12-01 | 1995-12-01 | 400000 | 0 | 400000 | 400000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. |  |  |  | Non-INV | 0
CLO | IBRD | CFC-12 collection, recycling and conservation programme for household refrigerator maintenance and repair shops | Individual | LAC | BRA | REF | 07 | TAS | 07 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1999-06-01 | 1995-06-01 |  |  | 2001-07-01 | 2000000 | -1980000 | 20000 | 20000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Cancelled. |  |  | 1999-12-01 | Non-INV | 0
FIN | Canada | Refrigeration training workshop in the state of Sao Paulo | Individual | LAC | BRA | REF | 11 | TRA | 11 | A | I |  | 0 |  | 0 |  | 1993-11-01 |  | 1994-11-01 |  | 1993-09-01 | 1994-11-01 | 172500 | 0 | 172500 | 172500 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project held in September 1993 and approved in retroactive funding in November 1993. |  | 1993 | 2000-01-01 | Non-Inv.
FIN | IBRD | Preparation of investment projects in the refrigeration sector (1994) |  | LAC | BRA | REF | 12 | PRP | 14 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 164380 | -53297 | 111083 | 111083 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | IBRD | System for storage and charging of ester oils used in the manufacture of HFC-134a compressors at Embraco | Individual | LAC | BRA | REF | 13 | INV | 15 | N | D | CFC | 0 | 0 | 0 | 0 | 1994-07-01 | 1995-05-01 | 1994-09-01 |  | 1994-07-01 | 1995-07-01 | 221200 | 0 | 221200 | 221200 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project fully implemented resulting in savings of 270 tons per year ODP. Project completed. |  |  | 1994-07-01 | INV | 0
FIN | IBRD | Replacement of CFC-11/12 to cyclopentane/HFC-134a foaming agent/refrigerant factory conversion at Metalfrio S.A. | Individual | LAC | BRA | REF | 15 | INV | 18 | N | I |  | 205.5 | 205.5 | 0 | 0 | 1994-12-01 | 1996-02-01 | 1996-06-01 |  | 1998-07-01 | 1999-05-01 | 2360360 | -776471 | 1583889 | 1583889 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Foaming process began operation in July 98 and refrigeration process in June 98. Final disbursement to Metalfrio was made on May 99. |  |  | 1999-05-01 | INV | 0
FIN | UNIDO | Conversion of the assembly of refrigeration compressors to phase out CFC-12 and CFC/HCFC-502 by using HFC-134a and R-404a at Elgin Maquinas SA | Individual | LAC | BRA | REF | 17 | INV | 20 | A | I |  | 0 | 0 |  |  | 1995-07-01 | 1996-10-01 | 1999-07-01 |  | 1998-12-01 | 2001-07-01 | 460339 | 0 | 460339 | 460339 | 100% | 0 | 0 |  | 59844 | 0 | 59844 | 0 | 0 | FIN
FIN | UNDP | Elimination of CFCs in the manufacture of domestic chest freezers at Multibras, S.A. Electrodomésticos | Individual | LAC | BRA | REF | 17 | INV | 24 | N | I | CFC | 165.9 | 165.9 | 0 | 0 | 1995-07-01 | 1997-07-01 | 1996-12-01 |  | 1997-12-01 | 1999-12-01 | 598499 | 0 | 598499 | 598499 | 100% | 0 | 0 | 0 | 77804.87 | 0 | 77804.87 | 0 | 0 | Completed in 1997. Financially completed in 1999. |  | 1995 |  | Investment
FIN | IBRD | Elimination of CFC-11 and CFC-12 in the manufacture of commercial chest freezers at Refrigeracao Parana S.A. Curitiba | Individual | LAC | BRA | REF | 18 | INV | 35 | N | I | CFC | 363 | 363 | 0 | 0 | 1995-11-01 | 1999-08-01 | 1996-11-01 |  | 1998-11-01 | 1999-08-01 | 1557613 | -210305.8 | 1347307.2 | 1347307 | 100% | 0.2 | 0.2 |  | 202490 | -27340.31 | 175149.69 | 0 | 0 | The firm went ahead with its own funds and completed one line (vertical freezers) in July 97; and the other line (horizontal freezers) in Nov. 98. FINEP reimbursed the firm retroactively for capital and operating costs. Final reimbursement made on August 2, 1999. |  |  | 1999-06-01 | INV | 0
FIN | UNIDO | Formulation of two investment projects in the commercial and domestic refrigerator sector | Individual | LAC | BRA | REF | 18 | PRP | 40 | A | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-02-01 | 1996-02-01 |  | 1997-12-01 | 1998-08-01 | 50000 | 87 | 50087 | 50087 | 100% | 0 | 0 |  | 6500 | 11 | 6511 | 0 | 0 | FIN
FIN | IBRD | Elimination of CFC-11 and CFC-12 in the production of commercial refrigeration equipment at Reubli, S.A. | Individual | LAC | BRA | REF | 19 | INV | 48 | N | I | CFC | 89.9 | 89.9 | 0 | 0 | 1996-05-01 | 1997-11-01 | 1997-11-01 |  | 1999-06-01 | 1999-06-01 | 901270 | -200188 | 701082 | 701082 | 100% | 0 | 0 |  | 117165 | -26024.34 | 91140.66 | 0 | 0 | Complete. |  |  | 1999-06-01 | INV | 0
FIN | IBRD | Elimination of CFC-11 and CFC-12 in the production of commercial refrigeration equipment at Geltec Comercio e Industria S.A. | Individual | LAC | BRA | REF | 19 | INV | 49 | N | I | CFC | 18.3 | 18.3 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  | 1998-02-01 | 1998-02-01 | 228250 | -93750 | 134500 | 134500 | 100% | 0 | 0 |  | 29673 | -12188 | 17485 | 0 | 0 | Refrigeration equipment installed and operating. |  |  | 1997-12-01 | INV | 0
FIN | IBRD | Conversion of CFC-11 to cyclopentane foam blowing agent and CFC-12 to HFC-134a refrigerant at Tecnomecanica Esmaltec Ltda. | Individual | LAC | BRA | REF | 19 | INV | 50 | N | I | CFC | 68.7 | 68.7 | 0 | 0 | 1996-05-01 | 1998-08-01 | 1997-11-01 |  | 2000-03-01 | 1999-06-01 | 924040 | 0 | 924040 | 924040 | 100% | 0 | 0 |  | 120125 | 0 | 120125 | 0 | 0 |  |  |  | 1999-06-01 | INV | 0
CLO | IBRD | Elimination of CFC-11 and CFC-12 in the production of commercial refrigeration equipment at Everest Refrigeracao Ind. e Comercio Ltda. | Individual | LAC | BRA | REF | 19 | INV | 51 | N | I |  | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1997-11-01 |  |  | 1998-07-01 | 149050 | -149050 | 0 | 0 | #DIV/0! | 0 | 0 |  | 19377 | -19377 | 0 | 0 | 0 | Cancelled. |  |  | 1998-06-01 | INV | 0
FIN | UNIDO | Phasing out of CFC-12 by HFC-134a as refrigerant and CFC-11 by cyclopentane as foam blowing agent in commercial refrigeration equipment for supermarkets at Eletrofrio S/A | Individual | LAC | BRA | REF | 20 | INV | 54 | A | I | CFC | 47 | 47 |  |  | 1996-10-01 | 1997-07-01 | 1998-10-01 |  | 1999-12-01 | 2001-12-01 | 610650 | 0 | 610650 | 610650.1 | 100% | -0.1 | 0 |  | 79385 | -63 | 79322 | 0 | 0 | FIN
FIN | IBRD | Elimination of CFC-11 and CFC-12 in the production of commercial refrigeration equipment at Gelopar | Individual | LAC | BRA | REF | 20 | INV | 55 | N | I | CFC | 13.14 | 13.14 | 0 | 0 | 1996-10-01 | 1997-12-01 | 1998-04-01 |  | 1998-05-01 | 1998-05-01 | 200200 | -145442 | 54758 | 54758 | 100% | 0 | 0 |  | 26026 | -18907.46 | 7118.54 | 0 | 0 | Refrigeration equipment acquired and installed. 134a production began May 98. |  |  |  | INV | 0
FIN | IBRD | Elimination of CFC-12 in the production of refrigeration equipment (drinking water fountains and coolers) at Industria Brasileira de Bebedouros Ltda. (IBBL) | Individual | LAC | BRA | REF | 20 | INV | 56 | N | I | CFC | 5.9 | 5.9 | 0 | 0 | 1996-10-01 | 1997-12-01 | 1998-04-01 |  | 1998-07-01 | 1998-05-01 | 82500 | -23113 | 59387 | 59387 | 100% | 0 | 0 |  | 10725 | -3004.69 | 7720.31 | 0 | 0 |  |  |  | 1999-06-01 | INV | 0
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators and freezers at Multibras, S.A. | Individual | LAC | BRA | REF | 20 | INV | 57 | N | I | CFC | 1068.8 | 1068.8 | 0 | 0 | 1996-10-01 | 1997-07-01 | 1999-09-01 |  | 2001-12-01 | 2013-12-01 | 4899790 | 0 | 4899790 | 4899790 | 100% | 0 | 0 | 0 | 636972.7 | 0 | 636972.7 | 0 | 0 | Financially completed in 2013. |  | 1996 | 1999-12-01 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Artico | Individual | LAC | BRA | REF | 23 | INV | 81 | A | I | CFC | 14.8 | 14.8 | 0 | 0 | 1997-11-01 | 1999-03-01 | 1999-12-01 |  | 2000-06-01 | 2001-12-01 | 225100 | -926.8 | 224173.2 | 224173 | 100% | 0.2 | 0 | 0 | 29263 | -120.41 | 29142.5627 | 0.0273 | 0 | Completed in 2000. Financially completed in 2001. |  | 1997 |  | Investment
CLO | UNIDO | Phasing out of CFC-12 by HFC-134a and CFC-11 by cyclopentane in the production of commercial refrigeration equipment at Refrigeracao Rubra | Individual | LAC | BRA | REF | 23 | INV | 83 | A | I | CFC | 21.8 | 0 |  |  | 1997-11-01 | 1998-12-01 | 1999-12-01 |  |  | 2002-10-01 | 320540 | -199780 | 120760 | 120760 | 100% | 0 | 0 |  | 41670 | -25996 | 15674 | 0 | 0 | CLO
FIN | UNDP | Elimination of CFCs in the manufacture of refrigerated trucks and trailers at Niju Ind. Com Implem Rodov Ltda. | Individual | LAC | BRA | REF | 23 | INV | 86 | A | I | CFC | 8.4 | 8.4 | 0 | 0 | 1997-11-01 | 1999-03-01 | 1999-12-01 |  | 2000-11-01 | 2001-12-01 | 111600 | 0 | 111600 | 111600 | 100% | 0 | 0 | 0 | 14508 | 0 | 14508 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Mais Frio | Individual | LAC | BRA | REF | 23 | INV | 88 | A | I | CFC | 10.1 | 10.1 | 0 | 0 | 1997-11-01 | 1998-07-01 | 1999-12-01 |  | 1999-12-01 | 2003-05-01 | 154400 | -25 | 154375 | 154375 | 100% | 0 | 0 | 0 | 20072 | -3.25 | 20068.75 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of refrigerated trucks and trailers at Increal Ltda. | Individual | LAC | BRA | REF | 23 | INV | 90 | A | I | CFC | 33 | 33 | 0 | 0 | 1997-11-01 | 1999-03-01 | 1999-12-01 |  | 2001-12-01 | 2003-04-01 | 418000 | -4 | 417996 | 417996 | 100% | 0 | 0 | 0 | 54340 | -0.52 | 54339.48 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Friar | Individual | LAC | BRA | REF | 23 | INV | 91 | A | I | CFC | 14.9 | 14.9 | 0 | 0 | 1997-11-01 | 1999-03-01 | 1999-12-01 |  | 2000-11-01 | 2003-04-01 | 185726 | -1023 | 184703 | 184703 | 100% | 0 | 0 | 0 | 24144.38 | -132.99 | 24011.39 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNIDO | Project preparation in the commercial refrigeration sector (Tecpur, Crios, Panamante and others) | Individual | LAC | BRA | REF | 24 | PRP | 97 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-08-01 | 1999-04-01 |  | 2000-07-01 | 2001-07-01 | 50000 | -2511 | 47489 | 47489 | 100% | 0 | 0 |  | 6500 | -336 | 6164 | 0 | 0 | FIN
FIN | UNDP | Project preparation for 4 projects in the commercial refrigeration subsector | Individual | LAC | BRA | REF | 24 | PRP | 99 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1999-07-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1998 |  | Investment
CLO | UNIDO | Phasing out CFC-12 with HFC-134a and CFC-11 with cyclopentane in the production of commercial refrigeration equipment at Panamante Refrigeracao | Individual | LAC | BRA | REF | 25 | INV | 106 | A | I | CFC | 34.3 | 0 |  |  | 1998-07-01 | 1999-06-01 | 2000-08-01 |  |  | 2002-09-01 | 377202 | -140248 | 236954 | 236954 | 100% | 0 | 0 |  | 49036 | -18281 | 30755 | 0 | 0 | CLO
FIN | UNDP | Phaseout of CFC-11 and CFC-12 by conversion to HCFC-141b (foam) and HFC-134a (refrigerant) technology in the manufacture of commercial refrigerators and display cases at Termisa | Individual | LAC | BRA | REF | 25 | INV | 111 | A | I | CFC | 27 | 27 | 0 | 0 | 1998-07-01 | 1999-03-01 | 2000-08-01 |  | 2000-11-01 | 2001-12-01 | 322205 | 0 | 322205 | 322205 | 100% | 0 | 0 | 0 | 41886.65 | 0 | 41886.65 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology and CFC-12 by conversion to HFC-134a in the manufacture of small commercial freezers and coolers at Bebber | Individual | LAC | BRA | REF | 26 | INV | 115 | A | I | CFC | 9.5 | 9.5 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 1999-12-01 | 2002-04-01 | 144500 | -3024 | 141476 | 141476 | 100% | 0 | 0 | 0 | 18785 | -393 | 18392 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 and CFC-12 by conversion to HCFC-141b technology (foam) and HFC-134a -134a technology (refrigerant) in the manufacture of refrigerated truck trailers at Artica | Individual | LAC | BRA | REF | 27 | INV | 118 | A | I | CFC | 22.3 | 22.3 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2001-10-01 |  | 2000-11-01 | 2003-10-01 | 183623 | -7277 | 176346 | 176346 | 100% | 0 | 0 | 0 | 23870.99 | -946.01 | 22924.98 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNIDO | Project preparation in the commercial refrigeration sector for four companies | Individual | LAC | BRA | REF | 27 | PRP | 119 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-12-01 | 1999-12-01 |  | 2001-03-01 | 2002-09-01 | 40000 | -8531 | 31469 | 31469.18 | 100% | -0.18 | 0 |  | 5200 | -1116 | 4084 | 0 | 0 | FIN
FIN | UNDP | Preparation of a project in the domestic refrigeration sector | Individual | LAC | BRA | REF | 27 | PRP | 122 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2002-03-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Preparation of four projects in the commercial refrigeration subsector | Individual | LAC | BRA | REF | 27 | PRP | 128 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2002-03-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 and CFC-12 in the manufacture of domestic refrigerators and freezers by conversion to cyclo-pentane and HCF-134a at Metalurgica Venan Ltda. | Individual | LAC | BRA | REF | 28 | INV | 132 | N | I | CFC | 36 | 36 | 0 | 0 | 1999-07-01 | 2000-09-01 | 2002-02-01 |  | 2004-03-01 | 2009-07-01 | 741800 | -6793 | 735007 | 735007 | 100% | 0 | 0 | 0 | 91598 | -838.8 | 90759.1955 | 0.0045 | 0 | Completed in 2004.Financially completed in 2009. |  | 1999 |  | Investment
FIN | UNDP | Phaseout of CFC-11, CFC-12 and R-502 by conversion to HCFC-141b technology (foam) and HFC-134a and R-404a technology (refrigerant) in the manufacture of milk coolers and display cabinets at Incomar | Individual | LAC | BRA | REF | 28 | INV | 133 | A | I | CFC | 4.9 | 4.9 | 0 | 0 | 1999-07-01 | 2000-05-01 | 2002-02-01 |  | 2000-11-01 | 2003-11-01 | 74529 | 0 | 74529 | 74529 | 100% | 0 | 0 | 0 | 9688.77 | 0 | 9688.77 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b, and from CFC-12 to HFC-134a and from R-502 to R-402a in the manufacture of commercial refrigeration products at General Icy | Individual | LAC | BRA | REF | 28 | INV | 134 | A | I | CFC | 27.9 | 27.9 | 0 | 0 | 1999-07-01 | 2000-03-01 | 2002-02-01 |  | 2001-12-01 | 2003-11-01 | 411139 | 0 | 411139 | 411139 | 100% | 0 | 0 | 0 | 53448.07 | 0 | 53448.07 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNIDO | Phasing out CFC-12 with HFC-134A and CFC-11 with HFC-141b at five commercial refrigeration companies (Arparna, Begel, Belliere, Genaredx and Katz Refrigeracao) (umbrella project) | Individual | LAC | BRA | REF | 28 | INV | 139 | A | I | CFC | 26 | 26 |  |  | 1999-07-01 | 2000-06-01 | 2001-08-01 |  | 2001-12-01 | 2002-12-01 | 485916 | -115476 | 370440 | 370440.15 | 100% | -0.15 | 0 |  | 63169 | -15088 | 48081 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the commercial refrigeration sector | Individual | LAC | BRA | REF | 30 | PRP | 159 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-05-01 | 2001-04-01 |  | 2002-08-01 | 2003-05-01 | 25000 | -409 | 24591 | 24590.56 | 100% | 0.44 | 0 |  | 3250 | -58 | 3192 | 0 | 0 | FIN
FIN | UNDP | Preparation of 3 projects in the commercial refrigeration subsector | Individual | LAC | BRA | REF | 30 | PRP | 162 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-01-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b, and from CFC-12 to HFC-134a and from R-502 to R-404a in the manufacture of freezer rooms and panels, and rigid foam at Schmit | Individual | LAC | BRA | REF | 31 | INV | 166 | A | I | CFC | 43.3 | 43.3 | 0 | 0 | 2000-07-01 | 2001-08-01 | 2003-08-01 |  | 2002-10-01 | 2003-11-01 | 288764 | -29918 | 258846 | 258846 | 100% | 0 | 0 | 0 | 37539.32 | -3889.21 | 33650.11 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNIDO | Phasing out CFC-12 with HFC-134a and CFC-11 with HCFC-141b at Ingecold Ltda. | Individual | LAC | BRA | REF | 31 | INV | 170 | A | I | CFC | 1.7 | 1.7 |  |  | 2000-07-01 | 2001-07-01 | 2003-08-01 |  | 2003-06-01 | 2003-06-01 | 25320 | -20 | 25300 | 25300.02 | 100% | -0.02 | 0 |  | 3292 | -8 | 3284 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-12 with HFC-134a and CFC-11 with HCFC-141b at Klima Ltda. | Individual | LAC | BRA | REF | 31 | INV | 171 | A | I | CFC | 5.7 | 5.7 |  |  | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2003-08-01 | 2004-09-01 | 86464 | -13509 | 72955 | 72955.26 | 100% | -0.26 | 0 |  | 11240 | -1771 | 9469 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-12 with HFC-134a and CFC-11 with HCFC-141b at Tecnigel Ltda | Individual | LAC | BRA | REF | 31 | INV | 172 | A | I | CFC | 2.5 | 2.5 |  |  | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2003-08-01 | 2004-09-01 | 34000 | -640 | 33360 | 33359.5 | 100% | 0.5 | 0 |  | 4420 | -90 | 4330 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-12 and R-502 with HFC-134a and HFC-404A as well as of CFC-11 with HCFC-141 at Kalten Ltd. | Individual | LAC | BRA | REF | 31 | INV | 174 | A | I | CFC | 8.1 | 8.1 |  |  | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2004-04-01 | 2004-09-01 | 122151 | -6158 | 115993 | 115993.1 | 100% | -0.1 | 0 |  | 15880 | -825 | 15055 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-12 with HFC-134a and CFC-11 with HCFC-141b at Metalplan Ltda. | Individual | LAC | BRA | REF | 31 | INV | 176 | A | I | CFC | 1.9 | 1.9 |  |  | 2000-07-01 | 2001-04-01 | 2003-08-01 |  | 2003-06-01 | 2003-06-01 | 28885 | 0 | 28885 | 28885.21 | 100% | -0.21 | 0 |  | 3755 | -3 | 3752 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-12 with HFC-134a and CFC-11 with HCFC-141b at Domnick Hunter Ltda. | Individual | LAC | BRA | REF | 31 | INV | 177 | A | I | CFC | 1.2 | 1.2 |  |  | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2003-06-01 | 2003-06-01 | 17971 | 0 | 17971 | 17971 | 100% | 0 | 0 |  | 2336 | 0 | 2336 | 0 | 0 | FIN
FIN | UNDP | Technical assistance for RMP survey and preparation | RMP-Component | LAC | BRA | REF | 32 | TAS | 200 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2003-01-01 |  | 2003-01-01 | 2003-07-01 | 100000 | -1 | 99999 | 99999 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 2003. Financially completed in 2003. |  | 2000 |  | Non-Investment
FIN | UNIDO | Project preparation for six projects in the commercial/domestic refrigeration sector | Individual | LAC | BRA | REF | 33 | PRP | 203 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-08-01 | 2002-04-01 |  | 2002-08-01 | 2003-06-01 | 25000 | -1663 | 23337 | 23337.28 | 100% | -0.28 | 0 |  | 3250 | -221 | 3029 | 0 | 0 | FIN |  |  |  | INV
FIN | UNDP | Project preparation in the commercial refrigeration sector | Individual | LAC | BRA | REF | 33 | PRP | 208 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNIDO | Umbrella project for four enterprises converting from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a at EZ Industria, Menoncin, Unifrio and from CFC-12 to HFC-134a at Croydon | Individual | LAC | BRA | REF | 34 | INV | 219 | A | I | CFC | 30.18 | 30.18 |  |  | 2001-07-01 | 2001-09-01 | 2004-02-01 |  | 2004-04-01 | 2004-12-01 | 469452 | -94888 | 374564 | 374564.24 | 100% | -0.24 | 0 |  | 61029 | -12413 | 48616 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of one investment project in the commercial refrigeration sector | Individual | LAC | BRA | REF | 34 | PRP | 223 | A | I |  | 0 | 0 |  |  | 2001-07-01 | 2002-06-01 | 2002-08-01 |  | 2002-08-01 | 2003-06-01 | 25000 | -4060 | 20940 | 20940.13 | 100% | -0.13 | 0 |  | 3250 | -532 | 2718 | 0 | 0 | FIN |  |  |  | INV
FIN | Germany | Pilot project: training programme for the refrigeration maintenance sector | Individual | LAC | BRA | REF | 34 | TRA | 228 | A | I |  | 0 |  | 0 |  | 2001-07-01 | 2001-08-01 | 2004-08-01 |  | 2004-08-01 | 2007-12-01 | 247400 | 0 | 247400 | 247400 | 100% | 0 | 0 | 0 | 32162 | 0 | 32162 | 0 | 0 | Project completed. Strategy derived from the demonstration project has been subvmitted with the National Phase Out Plan or Brazil
FIN | UNIDO | Umbrella project for two enterprises converting from CFC-11 and HCFC-141b and from CFC-12 to HFC-134a at Argi and Hornburg | Individual | LAC | BRA | REF | 35 | INV | 241 | A | I | CFC | 11.2 | 11.2 |  |  | 2001-12-01 | 2002-11-01 | 2004-05-01 |  | 2004-10-01 | 2005-05-01 | 108050 | -12441 | 95609 | 95608.63 | 100% | 0.37 | 0 |  | 14047 | -1638 | 12409 | 0 | 0 | FIN |  |  |  | INV
ONG | UNDP | Demonstration project for integrated management of the centrifugal chiller sub-sector, focusing on application of energy-efficient CFC-free technologies for replacement of CFC-based chillers. | Individual | LAC | BRA | REF | 47 | DEM | 275 | N | I | CFC | 0 | 0 | 0 | 0 | 2005-11-01 | 2013-04-01 | 2008-12-01 | 2017-01-01 |  |  | 1000000 | 0 | 1000000 | 770522.16 | 77.05% | 229477.84 | 0 | 91791.136 | 75000 | 0 | 57789.162 | 17210.838 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Two retrofits carried out in 2017 in two public buildings. One technical guide finalized. One technical manual with three volumens in the process of being developed. Prodoc signed (actual/planned, yes/no and date):Signed earlier Missions undertaken (actual/planned):1 of 1 TOR for consultants/subcontracts completed (actual/planned): 1 of 1 Contract/PO/MOA agreements signed: 2 of 2 First disbursement date (actual/planned): 41365Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | Technical manual finalized. Preparation for evaluation mission of the SMEO. | 2005 |  | Non-Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (refrigeration manufacturing sector) | Individual | LAC | BRA | REF | 57 | PRP | 289 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 |  | 2010-03-01 |  | 2011-07-01 | 2013-01-01 | 80000 | -80000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 6000 | -6000 | 0 | 0 | 0 | Financially completed in 2013. | Completed in 2011. HPMP approved by the 64th Executive Committee Meeting. It was decided that projects in the refrigeration manufacturing sector will not be included in phase I of the HPMP, priority will be given to foams. Some remaining invoices pending | 2009 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (air-conditioning manufacturing) | Individual | LAC | BRA | REF | 57 | PRP | 290 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 |  | 2010-03-01 |  | 2011-07-01 | 2013-01-01 | 80000 | -80000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 6000 | -6000 | 0 | 0 | 0 | Financially completed in 2013. | Completed in 2011. HPMP approved by the 64th Executive Committee Meeting. It was decided that projects in the air conditioning manufacturing sector will not be included in phase I of the HPMP, priority will be given to foams. Some remaining invoices pe | 2009 |  | Investment
COM | UNIDO | Preparation for HCFC phase-out investment activities (stage II) (refrigeration and air-conditioning manufacturing sector) | Individual | LAC | BRA | REF | 72 | PRP | 304 | A | I |  | 0 | 0 |  |  | 2014-05-01 | 2014-06-01 | 2015-12-31 |  | 2015-12-01 |  | 150000 | 0 | 150000 | 149932.88 | 99.96% | 67.12 | 12.79 | 1 | 10500 | 0 | 10495 | 5 | 1 | The project was operationally completed. |  |  |  | NON-INV
FIN | IBRD | Preparation of investment projects (1991) |  | LAC | BRA | SEV | 04 | PRP | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 114583 | -73761 | 40822 | 40822 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Country programme preparation | Individual | LAC | BRA | SEV | 06 | CPG | 02 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-03-31 | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 123788 | -122316 | 1472 | 1472 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1992) |  | LAC | BRA | SEV | 06 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 191878 | -89419 | 102459 | 102459 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1993) |  | LAC | BRA | SEV | 09 | PRP | 09 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 112000 | -20388 | 91612 | 91612 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Institutional strengthening support for the implementation of the Montreal Protocol | Individual | LAC | BRA | SEV | 10 | INS | 10 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-10-01 | 1996-06-01 |  | 1998-03-01 | 1999-12-01 | 403100 | 0 | 403100 | 403100 | 100% | 0 | 0 | 0 | 52403 | 0 | 52403 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1993 |  | Non-Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | BRA | SEV | 11 | PRP | 12 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-11-01 | 1994-11-01 |  | 1995-06-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1993 |  | Investment
FIN | IBRD | Country programme preparation | Individual | LAC | BRA | SEV | 12 | CPG | 76 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 49000 | -45000 | 4000 | 4000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Brazil Country Program was completed, presented and approved at the 13th Meeting of the Executive Committee. |  |  |  | Non-INV | 0
FIN | Canada | Montreal Protocol Technology Transfer Workshop on ODS (Phase II) | Individual | LAC | BRA | SEV | 15 | TRA | 17 | A | I |  | 0 |  | 0 |  | 1994-12-01 |  | 1995-12-01 |  | 1994-09-01 | 1995-12-01 | 58390 | 0 | 58390 | 58390 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project held in September 1994 and approved in retroactive funding in December 1994 |  | 1994 | 2000-01-01 | Non-Inv.
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | LAC | BRA | SEV | 16 | PRP | 19 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 235906 | 0 | 235906 | 235906 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | UNDP | Project preparation assistance | Individual | LAC | BRA | SEV | 17 | PRP | 22 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-07-01 | 1996-07-01 |  | 1996-01-01 | 1997-12-01 | 75000 | -2 | 74998 | 74998 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Completed in 1996. Financially completed in 1997. |  | 1995 |  | Investment
FIN | UNIDO | Preparation of investment project in a plant (Elgin) consuming 60 metric tons of TCA used as a degreasing agent in the production of compressors | Individual | LAC | BRA | SEV | 17 | PRP | 23 | A | I |  | 0 | 0 |  |  | 1995-07-01 | 1996-05-01 | 1995-09-01 |  | 1997-10-01 | 1998-08-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | FIN
FIN | UNDP | Project preparation assistance | Individual | LAC | BRA | SEV | 18 | PRP | 41 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-11-01 | 1996-11-01 |  | 1996-08-01 | 1997-12-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 | 0 | 7150 | 0 | 7150 | 0 | 0 | Completed in 1996. Financially completed in 1997. |  | 1995 |  | Investment
FIN | IBRD | Project preparation |  | LAC | BRA | SEV | 18 | PRP | 42 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | UNIDO | Project preparation in the refrigeration and methyl bromide sectors | Individual | LAC | BRA | SEV | 21 | PRP | 63 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-08-01 | 1998-02-01 |  | 1999-06-01 | 2000-12-01 | 57140 | -718 | 56422 | 56422 | 100% | 0 | 0 |  | 7428 | -105 | 7323 | 0 | 0 | FIN |  |  | 1999-06-01
FIN | UNDP | Project preparation | Individual | LAC | BRA | SEV | 22 | PRP | 74 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-04-01 | 2000-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Survey of ODS use in SMEs and approaches to ODS elimination | Individual | LAC | BRA | SEV | 23 | TAS | 85 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-02-01 | 1999-05-01 |  | 2000-07-01 | 2009-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 2000. Financially completed in 2009. |  | 1997 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening project for the phaseout of ozone depleting substances | Individual | LAC | BRA | SEV | 24 | INS | 100 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 2000-04-01 |  | 2000-11-01 | 2013-05-01 | 270000 | 0 | 270000 | 270000 | 100% | 0 | 0 | 0 | 35100 | 0 | 35100 | 0 | 0 | Financially completed in 2013. |  | 1998 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening (Phase III) | Individual | LAC | BRA | SEV | 32 | INS | 199 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2003-01-01 |  | 2006-07-01 | 2009-07-01 | 270000 | 0 | 270000 | 270000 | 100% | 0 | 0 | 0 | 35100 | 0 | 35100 | 0 | 0 | Completed in 2006.Financially completed in 2009. |  | 2000 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase IV) | Individual | LAC | BRA | SEV | 43 | INS | 267 | N | I | No_ODP | 29 | 29 | 0 | 0 | 2004-07-01 | 2006-01-01 | 2006-07-01 |  | 2007-12-01 | 2009-07-01 | 351000 | -76482 | 274518 | 274518 | 100% | 0 | 0 | 0 | 26325 | -5736.15 | 20588.85 | 0 | 0 | Completed in 2007.Financially completed in 2009. |  | 2004 |  | Non-Investment
FIN | UNDP | Assistance to carry out an HCFC survey | Individual | LAC | BRA | SEV | 45 | TAS | 271 | A | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-04-01 | 2006-12-01 |  | 2008-08-01 | 2009-12-01 | 183486 | -16859 | 166627 | 166627 | 100% | 0 | 0 | 0 | 16514 | -1517.33 | 14996.6661 | 0.0039 | 0 | Completed in 2008. Financially completed in 2009. |  | 2005 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase V) | Individual | LAC | BRA | SEV | 52 | INS | 279 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-01-01 | 2009-06-01 |  | 2010-12-01 | 2012-04-01 | 351000 | -49671.43 | 301328.57 | 301329 | 100% | -0.43 | 0 | 0 | 26325 | -3725.36 | 22599.6749 | -0.03495 | 0 | Financially completed in 2012. |  | 2007 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase VI) | Individual | LAC | BRA | SEV | 60 | INS | 294 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2010-04-01 | 2011-04-01 | 2011-12-01 |  | 2013-05-01 | 2014-12-01 | 307125 | -16641 | 290484 | 290484 | 100% | 0 | 0 | 0 | 23034 | -1248 | 21786 | 0 | 0 | Financially completed in 2014. | Completed in 2013. Project operationally completed as expected against milestones. Final payments related to publications are to take place in 2014. | 2010 |  | Non-Investment
COM | UNDP | Extension of institutional strengthening project (phase VII: 1/2012-12/2013) | Individual | LAC | BRA | SEV | 66 | INS | 297 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2012-04-01 | 2013-06-01 | 2013-12-01 |  | 2016-12-01 |  | 351000 | 0 | 351000 | 341408.37 | 97.27% | 9591.63 | 0 | 8152.8855 | 26325 | 0 | 25605.6277 | 719.3723 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Standard IS activities implemented. IBAMA publication of Norm #14. Improvements in the Federal Technical Registration system in IBAMA to improve the management of quotas. Prodoc signed (actual/planned, yes/no and date):Signed earlier Missions undertaken (actual/planned):1 of 1 TOR for consultants/subcontracts completed (actual/planned): 1 of 1 Contract/PO/MOA agreements signed: 2 of 2 First disbursement date (actual/planned): 41426Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:IS project was originally anticipated to be completed in 2013. However, GOV of Brazil has co-funded some activities that were initially foreseen in the budget. | - | 2012 |  | Non-Investment
ONG | UNDP | Extension of institutional strengthening project (phase VIII: 12/2015-11/2017) | Individual | LAC | BRA | SEV | 75 | INS | 314 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2015-11-01 |  | 2017-11-01 | 2017-11-01 |  |  | 449280 | 0 | 449280 | 0 | 0% | 449280 | 0 | 179712 | 31450 | 0 | 0 | 31450 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): ProDoc awaiting signature of the 3 parties (Min Env, Min Foreign Affairs and UNDP). Prodoc signed (actual/planned, yes/no and date):Expected to be signed by April 2017 Missions undertaken (actual/planned):0 of 0 TOR for consultants/subcontracts completed (actual/planned): 0 of 0 Contract/PO/MOA agreements signed: 0 of 0 First disbursement date (actual/planned): 42826Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:Signing of ProDoc delayed | Still awaiting signature of ProDoc | 2015 |  | Non-Investment
FIN | Canada | Ozone depleting solvents workshop in Brazil | Individual | LAC | BRA | SOL | 17 | TRA | 25 | A | I |  | 0 |  | 0 |  | 1995-07-01 |  | 1996-01-01 |  | 1994-05-01 | 1996-01-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project held in May 1994 and approved by retroactive funding in August 1995 |  | 1995 | 2000-01-01 | Non-Inv.
FIN | UNDP | Phase out of CFC-113 at DMG used in medical equipment parts cleaning | Individual | LAC | BRA | SOL | 18 | INV | 36 | N | I | CFC | 2 | 2 | 0 | 0 | 1995-11-01 | 1997-06-01 | 1996-11-01 |  | 1997-11-01 | 2000-12-01 | 38000 | -6 | 37994 | 37994 | 100% | 0 | 0 | 0 | 4940 | -0.78 | 4939.22 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Elimination of CFC-113 from the precision cleaning and drying process at Brasimet | Individual | LAC | BRA | SOL | 18 | INV | 37 | N | I | CFC | 1.6 | 1.6 | 0 | 0 | 1995-11-01 | 1999-05-01 | 1996-11-01 |  | 1999-12-01 | 2000-09-01 | 30400 | 0 | 30400 | 30400 | 100% | 0 | 0 | 0 | 3952 | 0 | 3952 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1995 | 1999-07-01 | Investment
CLO | IBRD | Phase out of CFC-113 and of MCF used in vapor degreasers to clean aircraft parts at Embraer | Individual | LAC | BRA | SOL | 18 | INV | 38 | N | I |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1997-05-01 |  |  | 1998-07-01 | 308215 | -308215 | 0 | 0 | #DIV/0! | 0 | 0 |  | 40068 | -40068 | 0 | 0 | 0 | Project cancelled. Enterprise unable to proceed with project as approved funding insufficient and no access to supplementary funds. |  |  | 1998-06-01 | INV | 0
FIN | UNIDO | Conversion of ODS cleaning processes from 1,1,1 TCA to aqueous cleaning and using trichlorethane at Elgin Maquinas SA | Individual | LAC | BRA | SOL | 18 | INV | 39 | A | I | TCA | 6 | 6 |  |  | 1995-11-01 | 1996-12-01 | 1997-02-01 |  | 1997-11-01 | 1999-08-01 | 156567 | -6049 | 150518 | 150518 | 100% | 0 | 0 |  | 20354 | -818 | 19536 | 0 | 0 | FIN
CLO | IBRD | Elimination of CFC-113 in medical parts cleaning and silicone deposition, and CFC-12 used in sterilization at Tecnobio | Individual | LAC | BRA | SOL | 19 | INV | 52 | N | I |  | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1997-05-01 |  |  | 1997-11-01 | 317492 | -317492 | 0 | 0 | #DIV/0! | 0 | 0 |  | 41274 | -41274 | 0 | 0 | 0 | Project cancelled. Enterprise unable to proceed with project as approved funding insufficient and no access to supplementary funds. |  |  | 1997-06-01 | INV | 0
CLO | UNIDO | Phase out of 1,1,1 TCA at Teperman | Individual | LAC | BRA | SOL | 20 | INV | 58 | A | R |  | 0 | 0 |  |  | 1996-10-01 |  | 1998-10-01 |  |  | 2000-06-01 | 152176 | -152176 | 0 | 0 | #DIV/0! | 0 | 0 |  | 19783 | -19783 | 0 | 0 | 0 | CLO
CLO | UNIDO | Elimination of 1,1,1 TCA used for autoparts cleaning at Brosol | Individual | LAC | BRA | SOL | 20 | INV | 59 | A | I |  | 0 | 0 |  |  | 1996-10-01 |  | 1997-10-01 |  |  | 1999-03-01 | 178361 | -178361 | 0 | 0 | #DIV/0! | 0 | 0 |  | 23187 | -23187 | 0 | 0 | 0 | CLO
FIN | UNIDO | Elimination of 1,1,1 TCA used as solvent at Rodabras | Individual | LAC | BRA | SOL | 20 | INV | 60 | A | I | TCA | 4.2 | 4.2 |  |  | 1996-10-01 | 1998-09-01 | 1997-10-01 |  | 1998-12-01 | 2000-07-01 | 151577 | -75 | 151502 | 151502 | 100% | 0 | 0 |  | 19705 | -41 | 19664 | 0 | 0 | FIN
FIN | UNIDO | Elimination of 1,1,1 TCA used for the formulation of tapping fluids at Tapmatic | Individual | LAC | BRA | SOL | 20 | INV | 61 | A | I | TCA | 9.9 | 9.9 |  |  | 1996-10-01 | 1997-08-01 | 1997-10-01 |  | 1997-12-01 | 2001-12-01 | 194500 | -27382 | 167118 | 167117.55 | 100% | 0.45 | 0 |  | 25285 | -3594 | 21691 | 0 | 0 | FIN
CLO | UNIDO | Project preparation for four projects in the solvents (CTC) sector | Individual | LAC | BRA | SOL | 33 | PRP | 205 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-06-01 | 2002-04-01 |  |  | 2003-05-01 | 30000 | -26812 | 3188 | 3188.15 | 100% | -0.15 | 0 |  | 3900 | -3486 | 414 | 0 | 0 | CLO |  |  |  | INV
FIN | UNDP | Project preparation for the formulation of CTC as a process agent | Individual | LAC | BRA | SOL | 42 | PRP | 266 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2005-04-01 |  | 2005-12-01 | 2006-12-01 | 32000 | 0 | 32000 | 32000 | 100% | 0 | 0 | 0 | 2400 | 0 | 2400 | 0 | 0 | Completed in 2005. Financially completed in 2006. |  | 2004 |  | Investment
FIN | UNDP | Project preparation for solvent and process agent sectors | Individual | LAC | BRA | SOL | 48 | PRP | 276 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-02-01 | 2007-04-01 |  | 2007-12-01 | 2011-11-01 | 50000 | -9426.22 | 40573.78 | 40574 | 100% | -0.22 | 0 | 0 | 3750 | -706.97 | 3043.05 | -0.02 | 0 | Completed in 2007. |  | 2006 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (solvent sector) | Individual | LAC | BRA | SOL | 57 | PRP | 291 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 |  | 2010-03-01 |  | 2011-07-01 | 2012-12-01 | 48000 | -48000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 3600 | -3600 | 0 | 0 | 0 | Financially completed in 2012. |  | 2009 |  | Investment
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | BRU | PHA | 55 | PRP | 11 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-10-01 | 2009-07-01 |  | 2011-06-01 | 2011-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 |  | 11050 | 0 | 11050 | 0 | 0
FIN | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | ASP | BRU | PHA | 66 | INV | 13 | N | I | HCFC | 0.2 | 0.2 | 0 | 0 | 2012-04-01 | 2013-03-01 | 2014-04-01 |  | 2015-05-01 | 2016-05-01 | 52800 | 0 | 52800 | 52800 | 100% | 0 | 0 | 0 | 4752 | 0 | 4752 | 0 | 0 | Financially completed in 2016. | In late February 2015, a joint mission with UNEP, to participate in the R&R training and to prepare the 2nd tranche request was conducted. The 2nd tranche request was submitted to and approved at the 74th ExCom. | 2012 |  | Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | BRU | PHA | 66 | TAS | 12 | A | I |  | 0.4 | 0 | 0 | 0 | 2012-04-01 | 2012-12-01 | 2014-04-01 | 2017-12-01 |  |  | 123000 | 0 | 123000 | 92251 | 75% | 30749 | 22000 | 3074.9 | 15990 | 0 | 11992.63 | 3997.37 | 2860 | Brief progress report (actual/planned): Activities agreed under the SSFA have been completed since 2015. The balance of the first tranche has been combined with the funds approved for the second tranche in the newly signed SSFA. Legal arrangements (actual/planned): The SSFA was signed in August 2012. First Mission: September 2012. TOR completed: Not applicable. First disbursement date: December 2012 All funds disbursed (yes/no): No, 22,000 US$ from the first tranche will be disbursed through the newly signed SSFA of the second tranche (as approved by the ExCom). Any delay? (yes/no): No. Any ongoing problems (yes/no): No. | The government is using the balance of the first tranche to conduct the RAC technician training and support the operation of the PMU. UNEP expects that the project will be completed by the end of 2017.
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | ASP | BRU | PHA | 74 | INV | 17 | N | I | HCFC | 0 | 0 | 0 | 0 | 2015-05-01 | 2016-02-01 | 2017-12-01 | 2017-12-01 |  |  | 39600 | 0 | 39600 | 15000 | 37.88% | 24600 | 19600 | 9840 | 3564 | 0 | 1350 | 2214 | 1764 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): In 2016, no further progress in procurement of equipment appears to have been made, based on the unliquidated obligation. Prodoc signed (actual/planned, yes/no and date):LoA 28 Jan 2016 Missions undertaken (actual/planned): TOR for consultants/subcontracts completed (actual/planned): - Contract/PO/MOA agreements signed: - First disbursement date (actual/planned): 42412Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:failure to submit the progress report on implementation of R&R program and replacement incentive programme. MPU-BKK is following up. | Procurement will be completed by December 2017 | 2015 |  | Investment
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | ASP | BRU | PHA | 74 | TAS | 16 | A | I |  | 0 |  | 0 |  | 2015-05-01 |  | 2017-05-01 | 2017-12-01 |  |  | 27500 | 0 | 27500 | 0 | 0% | 27500 | 27500 | 2750 | 3575 | 0 | 0 | 3575 | 3575 | Brief progress report (actual/planned): There was delay in the government signing of the SSFA due to the change of administrative procedures. The SSFA has been signed by the government and become effective since November 2016. Despite the delay in signing of SSFA, the Department of Environment, Park and Recreation (DEPR) regularly coordinated with the stakeholders to maintain the project implementation momentum especially the introduction of flammable and low GWP alternatives. The quota system and mandatory labeling requirement was implemented. The ban on import of HCFC-based equipment was in the final stage and presented to the Prime Minister's Office for approval. UNEP mission was conducted in December 2016 to plan the implementation of HPMP after signing of the SSFA. Brunei also attended the regional workshop on Environmentally Friendly Refrigerants in the Room Air Conditioners. 2015 CP data was submitted online. Legal arrangements (actual/planned): The SSFA was signed in November 2016. First Mission: December 2016. TOR completed: N/A First disbursement date: Processed but not yet transferred to country. All funds disbursed (yes/no): No. Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: The delay in signing SSFA affected the implementation of training programme. If Yes, will delay have impact on project completion date (yes/no): No. Any ongoing problems (yes/no): No. | Brief progress report (actual/planned): The training plan for customs and RAC technicians has been prepared. The first payment of the second tranche was relased to the country in February 2017. DEPR will organize the training of customs and RAC technician to catch up the planned implementation schedule. |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor the signing of the agreement by the Government.
ONG | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Individual | ASP | BRU | PHA | 75 | TAS | 19 | A | I |  | 0 |  | 0 |  | 2015-11-01 |  | 2017-03-01 | 2017-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 3000 | 3900 | 0 | 0 | 3900 | 0 | Brief progress report (actual/planned): There was the change in the process to transfer funds to the country. NOU recommended that the SSFA should be between UNEP and the Department of Economic Planning and Development, which has been recommended to conduct the verification of HCFC consumption. The SSFA was revised and submitted to the Department of Economic Planning and Development for their review and agreement. Due to the change in the administrative system, it would take some time to review and agree on the SSFA. Legal arrangements(actual/planned): Not yet. Initial stages of project implementation(actual/planned): Not yet. Intermediate goals achieved (actual/planned): Not applicable. Project completion and follow up: Not applicable. First disbursement date (actual/planned): not yet. All funds disbursed (yes/no): _No__ Any delay?(yes/no): Yes If Yes, reasons for delay & action plan to resolve: Delay in the review of the SSFA asigned to the Department of Economic Planning and Development. If Yes, will delay have impact on project completion date (yes/no): Yes, the report should be available in 2017. Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: No. | Brief progress report (actual/planned: UNEP coordinated with The Department of Environment, Park and Recreation (DEPR) on an urgent need to prepare the verification report, which is to be submitted to the 80th ExCom meeting. DEPR has closely follow-up with the Department of Economic Planning and Development on the progress.
FIN | UNEP | Development of RMP | RMP | ASP | BRU | REF | 30 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2001-04-01 |  | 2004-11-01 | 2009-12-01 | 30000 | -15500 | 14500 | 14500 | 100% | 0 | 0 |  | 3900 | -2015 | 1885 | 0 | 0
FIN | UNDP | Formulation of the investment components of the RMP | Individual | ASP | BRU | REF | 39 | PRP | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-12-01 | 2005-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 1875 | 0 | 1875 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2003 |  | Investment
FIN | UNEP | Implementation of the RMP: monitoring of the activities included in the RMP | Individual | ASP | BRU | REF | 44 | TAS | 09 | A | I | CFC | 2.9 | 2.9 | 0 | 0 | 2004-12-01 | 2008-05-01 | 2007-12-01 |  | 2010-12-01 | 2011-07-01 | 22000 | 0 | 22000 | 22000 | 100% | 0 | 0 |  | 2860 | 0 | 2860 | 0 | 0
COM | UNDP | Implementation of the RMP: technical assistance for the refrigeration service and MAC sectors | RMP-Component | ASP | BRU | REF | 44 | TAS | 10 | N | I | CFC | 52.3 | 52.3 | 0 | 0 | 2004-12-01 | 2011-12-01 | 2007-05-01 |  | 2014-07-01 |  | 390000 | -553 | 389447 | 389447 | 100% | 0 | 0 | 0 | 29250 | -41.48 | 29208.525 | -0.005 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2014. |  | 2004 |  | Investment
FIN | UNEP | Implementation of the RMP: training of trainers in good refrigerant management practices and national technicians training | Individual | ASP | BRU | REF | 44 | TRA | 07 | A | I | CFC | 6.7 | 6.7 | 0 | 0 | 2004-12-01 | 2008-06-01 | 2006-12-01 |  | 2010-12-01 | 2011-07-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Implementation of the RMP: customs training programme | Individual | ASP | BRU | REF | 44 | TRA | 08 | A | I | CFC | 4.6 | 4.6 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2006-12-01 |  | 2007-12-01 | 2008-12-01 | 34000 | 0 | 34000 | 34000 | 100% | 0 | 0 |  | 4420 | 0 | 4420 | 0 | 0
FIN | UNEP | Country programme preparation | Individual | ASP | BRU | SEV | 15 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-09-01 | 1996-03-01 |  | 1998-09-01 | 1999-06-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNEP | Creation of a Brunei Ozone Office | Individual | ASP | BRU | SEV | 26 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2001-12-01 |  | 2004-07-01 | 2010-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (phase II) | Individual | ASP | BRU | SEV | 43 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2011-06-01 | 2006-07-01 |  | 2012-12-01 | 2013-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (phase III: 1/2013-12/2014) | Individual | ASP | BRU | SEV | 67 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2014-08-01 | 2014-07-01 |  | 2014-12-01 | 2016-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
COM | UNEP | Renewal of the institutional strengthening project (phase IV: 1/2015-12/2016) | Individual | ASP | BRU | SEV | 73 | INS | 15 | A | I |  | 0 |  | 0 |  | 2014-11-01 | 2016-04-01 | 2016-12-01 |  | 2016-12-01 |  | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The NOU was operational normally, especially for the enforcement of the license/quota system and mandatory labelling requirement. In 2016, the quota remained unchanged from 2015 level at 75,250 Kg of HCFC-22, which were allocated to 16 registered companies. The licensing system was enforced and monitored through the National Single Window in close collaboration with the Customs. NOU also coordinated and facilitated the implementation of HPMP, ODS Alternative Survey and verification of HCFC consumption; The NOU also organized the 2016 ozone day celebration, and actively joined the regional and global ozone related meetings. As of December 2016, the activities were completed as planned. As the SSFA included retroactive finance provision from January 2015, the government advanced the expenditures befor the effectiveness of the SSFA and reimbursed from the project. As a result, all remaining payments as per the SSFA have been approved and awaiting for transfer. 2015 Article 7 and CP were submitted to the Ozone Secretariat and MLFS respectively. Legal arrangements(actual/planned): The SSFA was signed in October 2015._Initial stages of project implementation(actual/planned): Jan/Jan 2015_ Intermediate goals achieved (actual/planned): Yes. Project completion and follow up: Not applicable. First disbursement date (actual/planned): April 2016_ All funds disbursed (yes/no): No, but all remaining payments were being processed to transfer to country. Any delay?(yes/no): No | Project completed. The remaining payments as per the SSFA are being processed to transfer to the country. |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor project implementation progress and the disbursement rate of approved funds.
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | ASP | BRU | SEV | 74 | TAS | 18 | A | I |  | 0 |  | 0 |  | 2015-05-01 |  | 2016-05-01 | 2017-06-01 |  |  | 70000 | 0 | 70000 | 0 | 0% | 70000 | 0 | 7000 | 9100 | 0 | 0 | 9100 | 0 | Brief progress report (actual/planned): The SSFA was signed by the government and become effective in November 2016. Despite the delay in signing of SSFA, the Department of Environment, Park and Recreation (DEPR) had already identified and hire a local consultant to support the data collection. UNEP conducted a mission in December 2016 to meet the national stakeholders and local consultant to finalize the methodology and the national data collection started since then. Legal arrangements(actual/planned): The SSFA was signed in November 2016. Initial stages of project implementation(actual/planned): June / June 2015 Intermediate goals achieved (actual/planned): Not applicable. Project completion and follow up: Not applicable. First disbursement date (actual/planned): Not yet. All funds disbursed (yes/no): _No__ Any delay?(yes/no): Yes If Yes, reasons for delay & action plan to resolve: The delay in signing SSFA affected the kick-off the national data collection. If Yes, will delay have impact on project completion date (yes/no): Yes, the report should be available in 2017. Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): The national data collection is on-going. The local consultant has completed the data collection in 2 districts. The survey in remaining 2 districts is to be completed by end of March. The analysis and preparation of the report will commence after the national data collection with the assistance of UNEP and regional consultant. The first disbursement has been authorized in UMOJA and UNEP expects that the funds will be in the Government's account by the end of April of 2017.
ONG | UNEP | Renewal of the institutional strengthening project (phase V: 1/2017-12/2018) | Individual | ASP | BRU | SEV | 76 | INS | 20 | A | I |  | 0 |  | 0 |  | 2016-05-01 |  | 2018-12-01 | 2019-06-01 |  |  | 89600 | 0 | 89600 | 0 | 0% | 89600 | 0 | 8960 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The project was approved at the 76th ExCom Meeting in May 2016. The SSFA was drafted in consultation with the country. Following NOU confirmation on the agreement with the draft SSFA, it was processed for signing by the management. Legal arrangements(actual/planned): Not yet Initial stages of project implementation(actual/planned): Not yet Intermediate goals achieved (actual/planned): Not yet Project completion and follow up: Not applicable. First disbursement date (actual/planned): Not yet. All funds disbursed (yes/no): _No__ Any delay?(yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): The NOU is operating normally with support of DEPR even without the signed SSFA. NOU continues its enforcement of the licensing and quota system of HCFCs as well as mandatory labeling requirement for HCFC contriner. The SSFA was signed by UNEP in February 2017 and is being countersigned by the country following its procedure. The first payment will be made after signing of the SSFA.
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | LAC | BZE | PHA | 50 | PRP | 16 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-07-01 | 2007-11-01 |  | 2007-09-01 | 2007-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | LAC | BZE | PHA | 50 | PRP | 17 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-04-01 | 2007-11-01 |  | 2007-12-01 | 2010-12-01 | 15000 | -0.5 | 14999.5 | 15000 | 100% | -0.5 | 0 | 0 | 1125 | -0.04 | 1125 | -0.04 | 0 | Completed in 2007. |  | 2006 |  | Investment
FIN | UNDP | Terminal phase-out management plan for the phase-out of ODS in the refrigeration and air-conditioning sector (first tranche) | Multi-Year | LAC | BZE | PHA | 53 | INV | 20 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-09-01 | 2009-11-01 |  | 2009-11-01 | 2013-03-01 | 122000 | 0 | 122000 | 122000 | 100% | 0 | 0 | 0 | 10980 | 0 | 10980 | 0 | 0 | Financially completed in 2013. |  | 2007 |  | Investment
FIN | UNEP | Terminal phase-out management plan for the phase-out of ODS in the refrigeration and air-conditioning sector (first tranche) | Multi-year | LAC | BZE | PHA | 53 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-07-01 | 2009-03-01 |  | 2010-12-01 | 2011-12-01 | 53000 | 0 | 53000 | 53000 | 100% | 0 | 0 |  | 6890 | 0 | 6890 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | BZE | PHA | 55 | PRP | 21 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-10-01 | 2009-07-01 |  | 2011-12-01 | 2013-12-01 | 85000 | -4226 | 80774 | 80774 | 100% | 0 | 0 |  | 11050 | -549.38 | 10500.62 | 0 | 0
FIN | UNDP | Terminal phase-out management plan for the phase-out of ODS in the refrigeration and air-conditioning sector (second tranche) | Multi-Year | LAC | BZE | PHA | 57 | INV | 23 | N | I | CFC | 3.7 | 3.7 | 0 | 0 | 2009-04-01 | 2009-05-01 | 2011-03-01 |  | 2010-08-01 | 2013-03-01 | 72000 | -19.63 | 71980.37 | 71980 | 100% | 0.37 | 0 | 0 | 6480 | -1.77 | 6478.2 | 0.03 | 0 | Financially completed in 2013. |  | 2009 |  | Investment
FIN | UNEP | Terminal phase-out management plan for the phase-out of ODS in the refrigeration and air-conditioning sector (second tranche) | Multi-Year | LAC | BZE | PHA | 57 | TAS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-09-01 | 2010-03-01 |  | 2010-07-01 | 2011-07-01 | 48000 | 0 | 48000 | 48000 | 100% | 0 | 0 |  | 6240 | 0 | 6240 | 0 | 0
FIN | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | BZE | PHA | 62 | INV | 26 | N | I | HCFC | 0 | 0 | 0 | 0 | 2010-12-01 | 2012-07-01 | 2015-12-01 |  | 2015-01-01 | 2016-01-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 5400 | 0 | 5400 | 0 | 0 | Financially completed in 2016. | Since 2014, additional equipment (approx. 45% cumulative) has been delivered to final users. | 2010 |  | Investment
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | BZE | PHA | 62 | TAS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-06-01 | 2015-12-01 |  | 2014-05-01 | 2014-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0
FIN | Canada | Implementation of the RMP: monitoring and control of ODS and ODS based equipment and training programme for customs and other inspection officers | RMP | LAC | BZE | REF | 29 | TAS | 03 | A | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-03-01 | 2001-06-01 |  | 2003-12-01 | 2003-12-01 | 28000 | 0 | 28000 | 28000 | 100% | 0 |  | 0 | 3640 | 0 | 3640 | 0 |  | Train-the-trainer customs workshop held in March 2002. Phase II training completed in 2003. |  | 1999 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: policy dialogue programme and regulatory framework for phasing out ODSs | RMP | LAC | BZE | REF | 29 | TAS | 04 | A | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-03-01 | 2000-09-01 |  | 2001-11-01 | 2002-12-01 | 15500 | 0 | 15500 | 15500 | 100% | 0 |  | 0 | 2015 | 0 | 2015 | 0 |  | Planning and Policy Dialogue component completed Nov. 2001. Regulatory framework developed and adopted by Government. PCR submitted |  | 1999 | 2001-12-01 | Non-Inv.
FIN | UNDP | Implementation of the RMP: Implementation of a national programme for recovery and recycling of CFC-12 refrigerant | RMP-Component | LAC | BZE | REF | 29 | TAS | 05 | A | I | CFC | 1.7 | 1.7 | 0 | 0 | 1999-11-01 | 2002-06-01 | 2002-12-01 |  | 2002-12-01 | 2003-09-01 | 61125 | 0 | 61125 | 61125 | 100% | 0 | 0 | 0 | 7946.25 | 0 | 7946.25 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1999 |  | Investment
FIN | Canada | Implementation of the RMP: training of trainers and refrigeration technicians in good servicing practices | RMP | LAC | BZE | REF | 29 | TRA | 02 | A | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-03-01 | 2002-12-01 |  | 2003-12-01 | 2003-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 |  | 0 | 5850 | 0 | 5850 | 0 |  | Train the trainers workshop held in April 2001. Subsequent training took place in 2002 and finalized in 2003. |  | 1999 |  | Non-Inv.
FIN | UNEP | Preparation of the RMP update proposal | RMP Update | LAC | BZE | REF | 41 | PRP | 08 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-08-01 | 2004-12-01 |  | 2004-12-01 | 2005-06-01 | 15000 | -1250 | 13750 | 13750 | 100% | 0 | 0 |  | 1950 | -163 | 1787 | 0 | 0
FIN | UNDP | Project preparation for the formulation of refrigerant management plan update (investment component) | Individual | LAC | BZE | REF | 42 | PRP | 09 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2005-02-01 | 2005-04-01 |  | 2005-12-01 | 2007-06-01 | 20000 | -1164 | 18836 | 18836 | 100% | 0 | 0 | 0 | 1500 | -87.32 | 1412.6782 | 0.0018 | 0 | Completed in 2005. Financially completed in 2007. |  | 2004 |  | Investment
FIN | UNEP | Implementation of the RMP: certification and licensing of refrigeration technicians | Individual | LAC | BZE | REF | 44 | TAS | 11 | A | I | CFC | 5 | 5 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2007-12-01 |  | 2009-12-01 | 2010-12-01 | 33682 | 0 | 33682 | 33682 | 100% | 0 | 0 |  | 4379 | 0 | 4379 | 0 | 0
FIN | UNDP | Implementation of the RMP: technical assistance for the refrigeration servicing sector | RMP-Component | LAC | BZE | REF | 44 | TAS | 12 | N | I | CFC | 6.7 | 6.7 | 0 | 0 | 2004-12-01 | 2006-01-01 | 2007-12-01 |  | 2006-12-01 | 2007-06-01 | 44879 | -211 | 44668 | 44668 | 100% | 0 | 0 | 0 | 4039.11 | -19 | 4020.11 | 0 | 0 | Completed in 2006. Financially completed in 2007. |  | 2004 |  | Investment
FIN | UNEP | Implementation of the RMP: prevention of illegal trade of CFCs | Individual | LAC | BZE | REF | 44 | TAS | 13 | A | I | CFC | 3.4 | 3.4 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2007-12-01 |  | 2009-12-01 | 2010-12-01 | 22611 | 0 | 22611 | 22611 | 100% | 0 | 0 |  | 2939 | 0 | 2939 | 0 | 0
FIN | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | LAC | BZE | REF | 44 | TAS | 14 | A | I | CFC | 4 | 4 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2007-12-01 |  | 2009-12-01 | 2010-12-01 | 27140 | 0 | 27140 | 27140 | 100% | 0 | 0 |  | 3528 | 0 | 3528 | 0 | 0
FIN | UNEP | Country programme preparation | Individual | LAC | BZE | SEV | 24 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 1999-02-01 |  | 1999-11-01 | 2000-12-01 | 52000 | 0 | 52000 | 52000 | 100% | 0 | 0 |  | 6760 | 0 | 6760 | 0 | 0
FIN | UNEP | Creation of the national ozone unit | Individual | LAC | BZE | SEV | 29 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2002-12-01 |  | 2003-01-01 | 2004-10-01 | 88500 | 0 | 88500 | 88500 | 100% | 0 | 0 |  | 11505 | 0 | 11505 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project | Individual | LAC | BZE | SEV | 40 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2004-01-01 | 2005-07-01 |  | 2006-07-01 | 2007-07-01 | 76700 | 0 | 76700 | 76700 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase III) | Individual | LAC | BZE | SEV | 46 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2006-07-01 | 2007-07-01 |  | 2008-09-01 | 2009-09-01 | 76700 | 0 | 76700 | 76700 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase IV) | Individual | LAC | BZE | SEV | 53 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-07-01 | 2009-11-01 |  | 2010-07-01 | 2011-07-01 | 76700 | 0 | 76700 | 76700 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase V) | Individual | LAC | BZE | SEV | 59 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-08-01 | 2011-12-01 |  | 2013-03-01 | 2014-03-01 | 38350 | 38350 | 76700 | 76700 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase VI: 4/2012-3/2014) | Individual | LAC | BZE | SEV | 66 | INS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 | 2012-12-01 | 2014-03-01 |  | 2013-12-01 | 2014-12-01 | 76700 | 0 | 76700 | 76700 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Renewal of institutional strengthening project (phase VII: 4/2014-3/2016) | Individual | LAC | BZE | SEV | 72 | INS | 28 | A | I |  | 0 |  | 0 |  | 2014-05-01 | 2014-11-01 | 2016-03-01 |  | 2016-06-01 |  | 76700 | 0 | 76700 | 76700 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Final progress and financial reports submitted and approved. Last payment under SSFA disbursed. SSFA ended Sept 2016.___ Legal arrangements(actual/planned): N/A___Initial stages of project implementation(actual/planned): N/A___ Intermediate goals achieved (actual/planned): N/A___ Project completion and follow up: N/A___ First disbursement date (actual/planned): N/A___ All funds disbursed (yes/no): Yes ___ Any delay?(yes/no): Bi___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): No ___ If Yes, is any action required by ExCom: N/A___ | Project completed
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | LAC | BZE | SEV | 75 | TAS | 29 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-06-01 | 2016-12-01 | 2017-05-01 |  |  | 40000 | 0 | 40000 | 16778.48 | 41.95% | 23221.52 | 23221.52 | 2322.152 | 5200 | 0 | 2181.2024 | 3018.7976 | 3018.7976 | Brief progress report (actual/planned): The report is under final review and will be submitted to MLFS upon finalization.___ Legal arrangements(actual/planned): SSFA signed May-16___Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: 2nd disbursement being processed. Final to be processed upon acceptance of final report___ First disbursement date (actual/planned): Jun-16___ All funds disbursed (yes/no): No___ Any delay?(yes/no): No___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): No.___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): Final Report being reveiwed. Any comments or issues to be addressed will be forwarded to country, towards finalization.___ Legal arrangements(actual/planned): SignedMay-16.___Initial stages of project implementation(actual/planned): N/A___ Intermediate goals achieved (actual/planned): N/A___ Project completion and follow up: Finalize report with country and consultant. Process final disbursement.___ First disbursement date (actual/planned): Jun-16.___ All funds disbursed (yes/no): No.___ Any delay?(yes/no): No. ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): No. ___ If Yes, is any action required by ExCom: ___
ONG | UNEP | Renewal of institutional strengthening project (phase VIII: 4/2016-3/2018) | Individual | LAC | BZE | SEV | 76 | INS | 30 | A | I |  | 0 |  | 0 |  | 2016-05-01 | 2016-10-01 | 2016-03-01 | 2018-09-01 |  |  | 98176 | 0 | 98176 | 0 | 0% | 98176 | 98176 | 9817.6 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): NOU undertook training of importers and custom brokers on their Online Permit and Application Licensing system. NOU undertook inspections of each import/export of ODSs prior to granting licenses. 2016 Ozone Day celebrations held. NOU participated in Barbados Thematic Meeting in Dec-16. NOU supporting implementation of the ODS Alternatives Survey towards completion by 31 Dec-16. ___ Legal arrangements(actual/planned): SSFA signed Sep-16. __Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): Oct 2016___ All funds disbursed (yes/no): No ___ Any delay?(yes/no): No. ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no):No. ___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): NOU undertaking 2016 Article and CP data collection and verification.___ Legal arrangements(actual/planned): Sept-16.___Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): Oct-16.___ All funds disbursed (yes/no): ___ Any delay?(yes/no): No.___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): No.___ If Yes, is any action required by ExCom: ___
CLO | UNDP | Continuation of conversion to CFC-free technology in manufacturing of flexible polyurethane foam at Vita-Centrafrique | Individual | AFR | CAF | FOA | 19 | INV | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1996-05-01 | 1998-10-01 | 1997-05-01 |  |  | 2001-12-01 | 62000 | -30537 | 31463 | 31463 | 100% | 0 | 0 | 0 | 8060 | -3970 | 4090 | 0 | 0 | Canceled in 2001. Financially completed in 2001. |  | 1996 | 1998-04-01 | Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | CAF | PHA | 49 | PRP | 14 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-10-01 | 2007-07-01 |  | 2008-07-01 | 2009-07-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
COM | France | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | CAF | PHA | 55 | INV | 17 | A | I | CFC | 0.7 | 0.7 | 0 |  | 2008-07-01 | 2010-06-01 | 2009-12-01 |  | 2011-09-01 |  | 55000 | 0 | 55000 | 55000 | 100% | 0 |  | 0 | 7150 | 0 | 7150 | 0 |  | Project completed.
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | CAF | PHA | 55 | PRP | 16 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-03-01 | 2009-07-01 |  | 2011-12-01 | 2012-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 |  | 11050 | 0 | 11050 | 0 | 0
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | CAF | PHA | 55 | TAS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-04-01 | 2009-12-01 |  | 2011-01-01 | 2011-06-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0
COM | France | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | CAF | PHA | 61 | INV | 19 | A | I | CFC | 0.6 | 0.6 | 0 |  | 2010-07-01 | 2011-05-01 | 2011-07-01 |  | 2011-12-01 |  | 45000 | 0 | 45000 | 45000 | 100% | 0 |  | 0 | 5850 | 0 | 5850 | 0 |  | Project completed.
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | CAF | PHA | 61 | TAS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-04-01 | 2011-07-01 |  | 2012-12-01 | 2013-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 |  | 5850 | 0 | 5850 | 0 | 0
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | CAF | PHA | 64 | INV | 21 | A | I | HCFC | 0.5 | 0 |  |  | 2011-07-01 | 2012-09-01 | 2016-07-31 | 2019-12-01 |  |  | 125000 | 0 | 125000 | 19000.74 | 15.2% | 105999.26 | 87576.93 | 1 | 9375 | 0 | 1425 | 7950 | 6568 | Project activities suspended due to security situation in the country. | Project activities suspended due to security situation in the country. |  |  | INV |  | To request the submission of additional status report to the 79th meeting to monitor the resumption of activities due to security situations.
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | AFR | CAF | PHA | 64 | TAS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-04-01 | 2013-07-01 | 2017-12-01 |  |  | 75000 | 0 | 75000 | 44999.61 | 60% | 30000.39 | 0 | 3000.039 | 9750 | 0 | 5849.9493 | 3900.0507 | 0 | Brief progress report (actual/planned): _No activities undertaken in 2016 because of political unrest and travel restriction _ Legal arrangements(actual/planned): SSFA signed in May 2012___Initial stages of project implementation(actual/planned):N/a__ Intermediate goals achieved (actual/planned): _no__ Project completion and follow up:implementation stopped because of political unrest___ First disbursement date (actual/planned): First disbursment sent to the country in May 2012 ___ All funds disbursed (yes/no): _No__ Any delay?(yes/no): Yes___ If Yes, reasons for delay & action plan to resolve: __Political unrest_ If Yes, will delay have impact on project completion date (yes/no): __Yes_ Any ongoing problems (yes/no): _No National Ozone Coordinator appointed __ If Yes, is any action required by ExCom: _CAP contacted the Minister and is expexcting the Government to appoint a National Ozone _Coordinator_ | Brief progress report (actual/planned): _No activities undertaken in 2016 because of political unrest and travel restriction _ Legal arrangements(actual/planned): SSFA signed in May 2012___Initial stages of project implementation(actual/planned):N/a__ Intermediate goals achieved (actual/planned): _no__ Project completion and follow up :implementation stopped because of political unrest___ First disbursement date (actual/planned): First disbursement sent to the country in May 2012 ___ All funds disbursed (yes/no): _No__ Any delay?(yes/no): Yes___ If Yes, reasons for delay & action plan to resolve: __Political unrest_ If Yes, will delay have impact on project completion date (yes/no): __Yes_ Any ongoing problems (yes/no): _No National Ozone Coordinator appointed __ If Yes, is any action required by ExCom: _The Government appointed a National Ozone Officer who took part of the Network meeting in Abidjan in March 2017_ |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor the resumption of project implementation.
ONG | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Individual | AFR | CAF | PHA | 71 | TAS | 24 | A | I |  | 0 |  | 0 |  | 2013-12-01 |  | 2015-05-01 | 2017-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 3000 | 3900 | 0 | 0 | 3900 | 0 | Brief progress report (actual/planned): _No activities undertaken in 2016 because of political unrest and travel restriction _ Legal arrangements(actual/planned): SSFA signed in May 2012___Initial stages of project implementation(actual/planned):N/a__ Intermediate goals achieved (actual/planned): _no__ Project completion and follow up:implementation stopped because of political unrest___ First disbursement date (actual/planned): First disbursment sent to the country in May 2012 ___ All funds disbursed (yes/no): _No__ Any delay?(yes/no): Yes___ If Yes, reasons for delay & action plan to resolve: __Political unrest_ If Yes, will delay have impact on project completion date (yes/no): __Yes_ Any ongoing problems (yes/no): _No National Ozone Coordinator appointed __ If Yes, is any action required by ExCom: _CAP contacted the Minister and is expexcting the Government to appoint a National Ozone _Coordinator_ | Brief progress report (actual/planned): _No activities undertaken in 2016 because of political unrest and travel restriction _ Legal arrangements(actual/planned): SSFA signed in May 2012___Initial stages of project implementation(actual/planned):N/a__ Intermediate goals achieved (actual/planned): _no__ Project completion and follow up: implementation stopped because of political unrest___ First disbursement date (actual/planned): First disbursement sent to the country in May 2012 ___ All funds disbursed (yes/no): _No__ Any delay?(yes/no): Yes___ If Yes, reasons for delay & action plan to resolve: __Political unrest_ If Yes, will delay have impact on project completion date (yes/no): __Yes_ Any ongoing problems (yes/no): _No National Ozone Coordinator appointed __ If Yes, is any action required by ExCom: _ The Government appointed a National Ozone Officer who took part of the Network meeting in Abidjan in March 2017_
CLO | UNDP | Implementation of a national programme for recovery and recycling of refrigerants | RMP-Component | AFR | CAF | REF | 20 | TAS | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1996-10-01 | 1998-05-01 | 1998-09-01 |  |  | 2001-12-01 | 66441 | -923 | 65518 | 65518 | 100% | 0 | 0 | 0 | 8637.33 | -120.18 | 8517.146 | 0.004 | 0 | Canceled in 2001. Financially completed in 2001. |  | 1996 | 1999-06-01 | Investment
FIN | UNEP | Preparation of a refrigerant management plan | RMP | AFR | CAF | REF | 27 | PRP | 07 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-10-01 | 2000-04-01 |  | 2001-05-01 | 2002-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | France | Implementation of the RMP: development and implementation of a tax/incentive programme |  | AFR | CAF | REF | 34 | TAS | 10 | N | I |  | 0.3 | 0.1 | 0 |  | 2001-07-01 | 2003-09-01 | 2007-08-01 |  | 2008-07-01 | 2009-04-01 | 5500 | -3904 | 1596 | 1596 | 100% | 0 |  | 0 | 715 | -508 | 207 | 0 |  | Official statement on loss of funds was provided. Remaining activities were cancelled in favor of TPMP implementation (55 & 57 ExCom)
FIN | France | Implementation of the RMP: monitoring the activities of the RMP project, including registration of refrigeration service technicians, distributors and importers of CFCs |  | AFR | CAF | REF | 34 | TAS | 11 | A | I |  | 1.5 |  | 0 |  | 2001-07-01 | 2003-09-01 | 2007-08-01 |  | 2008-07-01 | 2009-04-01 | 26250 | -8986 | 17264 | 17264 | 100% | 0 |  |  | 3413 | -1168 | 2245 | 0
FIN | France | Implementation of the RMP: training programme for customs officers |  | AFR | CAF | REF | 34 | TRA | 08 | N | I |  | 4.4 | 2.9 | 0 |  | 2001-07-01 | 2003-09-01 | 2003-08-01 |  | 2008-07-01 | 2009-04-01 | 77440 | -26940 | 50500 | 50500 | 100% | 0 |  | 0 | 10067 | -3502 | 6565 | 0 |  | Official statement on loss of funds was provided. Remaining activities were cancelled in favor of TPMP implementation (55 & 57 ExCom).
FIN | France | Implementation of the RMP: train the trainers programme for refrigeration technicians in good management practices and a training programme to address technicians in the informal sector |  | AFR | CAF | REF | 34 | TRA | 09 | A | I |  | 3.4 | 2.4 | 0 |  | 2001-07-01 | 2003-09-01 | 2003-08-01 |  | 2008-07-01 | 2009-04-01 | 60900 | -17759 | 43141 | 43141 | 100% | 0 |  | 0 | 7917 | -2309 | 5608 | 0 |  | Official statement on loss of funds was provided. Remaining activities were cancelled in favor of TPMP implementation (55 & 57 ExCom).
FIN | UNEP | Country programme preparation | Individual | AFR | CAF | SEV | 12 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-11-01 | 1995-06-01 |  | 1995-10-01 | 1995-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Establishment of the National Technical Ozone Group (Ozone Unit) | Individual | AFR | CAF | SEV | 18 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-04-01 | 1998-11-01 |  | 1999-12-01 | 2000-06-01 | 45600 | 0 | 45600 | 45600 | 100% | 0 | 0 |  | 5928 | 0 | 5928 | 0 | 0
FIN | UNDP | Project preparation assistance | Individual | AFR | CAF | SEV | 18 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-02-01 | 1996-11-01 |  | 1996-11-01 | 1998-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNEP | Renewal of the institutional strengthening project | Individual | AFR | CAF | SEV | 26 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 2000-06-01 | 2000-12-01 |  | 2002-12-01 | 2004-10-01 | 30400 | 0 | 30400 | 30400 | 100% | 0 | 0 |  | 3952 | 0 | 3952 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project | Individual | AFR | CAF | SEV | 38 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2004-01-01 | 2004-12-01 |  | 2006-01-01 | 2007-04-01 | 39520 | 0 | 39520 | 39520 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | CAF | SEV | 45 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2007-06-01 | 2007-04-01 |  | 2009-03-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | AFR | CAF | SEV | 57 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2012-03-01 | 2011-03-01 |  | 2013-03-01 | 2014-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of the institutional strengthening project (phase VI: 1/2013-12/2014) | Individual | AFR | CAF | SEV | 68 | INS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2012-05-01 | 2014-12-01 | 2017-12-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 60000 | 6000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): _No activities undertaken in 2016 because of political unrest and travel restriction _ Legal arrangements(actual/planned): SSFA signed in May 2012___Initial stages of project implementation(actual/planned):N/a__ Intermediate goals achieved (actual/planned): _no__ Project completion and follow up:implementation stopped because of political unrest___ First disbursement date (actual/planned): First disbursment sent to the country in May 2012 ___ All funds disbursed (yes/no): _No__ Any delay?(yes/no): Yes___ If Yes, reasons for delay & action plan to resolve: __Political unrest_ If Yes, will delay have impact on project completion date (yes/no): __Yes_ Any ongoing problems (yes/no): _No National Ozone Coordinator appointed __ If Yes, is any action required by ExCom: _CAP contacted the Minister and is expexcting the Government to appoint a National Ozone _Coordinator_ | Brief progress report (actual/planned): _No activities undertaken in 2016 because of political unrest and travel restriction _ Legal arrangements(actual/planned): SSFA signed in May 2012___Initial stages of project implementation(actual/planned):N/a__ Intermediate goals achieved (actual/planned): _no__ Project completion and follow up:implementation stopped because of political unrest___ First disbursement date (actual/planned): First disbursment sent to the country in May 2012 ___ All funds disbursed (yes/no): _No__ Any delay?(yes/no): Yes___ If Yes, reasons for delay & action plan to resolve: __Political unrest_ If Yes, will delay have impact on project completion date (yes/no): __Yes_ Any ongoing problems (yes/no): _No National Ozone Coordinator appointed __ If Yes, is any action required by ExCom: _ The Government appointed a National Ozone Officer who took part of the Network meeting in Abidjan in March 2017_ |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor project implementation progress and the disbursement rate of approved funds.
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | CBI | PHA | 50 | PRP | 11 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-12-01 | 2007-11-01 |  | 2008-12-01 | 2011-01-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | CBI | PHA | 54 | TAS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-07-01 | 2010-03-01 |  | 2009-12-01 | 2011-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | CBI | PHA | 56 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-08-01 | 2009-11-01 |  | 2011-12-01 | 2011-12-01 | 85000 | -19552 | 65448 | 65448 | 100% | 0 | 0 |  | 11050 | -2541.76 | 8508.24 | 0 | 0
FIN | UNEP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | CBI | PHA | 59 | TAS | 15 | A | I | CFC-12 | 0.3 | 0 | 0 | 0 | 2009-11-01 | 2011-06-01 | 2010-11-01 |  | 2011-11-01 | 2012-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
COM | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | AFR | CBI | PHA | 64 | TAS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-04-01 | 2013-07-01 |  | 2016-12-01 |  | 44000 | -3710 | 40290 | 39991.65 | 99.26% | 298.35 | 298.35 | 298 | 5720 | -482.3 | 5198.9145 | 38.7855 | 38.7855 | The project returns to COM as the balance was committed through an SSFA amendment | The project returns to COM as the balance was committed through an SSFA amendment
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | AFR | CBI | PHA | 71 | TAS | 18 | A | I |  | 0 |  | 0 |  | 2013-12-01 | 2015-10-01 | 2016-12-01 | 2017-06-01 |  |  | 35000 | 0 | 35000 | -0.15 | -0.0004286% | 35000.15 | 35000.15 | 3500.015 | 4550 | 0 | -0.0195 | 4550.0195 | 4550.0195 | Brief progress report (actual/planned): Training of 25 refrigeration technicians on Good practices in refrigeration and 3 customs officer on ODS identification in April 2016_ in Praia. Legal arrangements (actual/planned): The SSFA signed in July 2015. Initial stages of project implementation(actual/planned): n/a__ Intermediate goals achieved (actual/planned): _yes__ Project completion and follow up:___ First disbursement date (actual/planned): First disbursement sent to the country in Oct 2015 ___ All funds disbursed (yes/no): _No__ Any delay?(yes/no): Yes___ If Yes, reasons for delay & action plan to resolve: __Political unrest_ If Yes, will delay have impact on project completion date (yes/no): __Yes_ Any ongoing problems (yes/no): _No __ If Yes, is any action required by ExCom: _ | Brief progress report (actual/planned): Legal arrangements (actual/planned): The SSFA signed in July 2015. Training of 25 refrigeration technicians on Good practices in refrigeration and 3 customs officer on ODS identification in April 2016_ in Praia. Project implementation(actual/planned): Yes__ (actual/planned): _yes__ Project completion and follow up:___ First disbursement date (actual/planned): First disbursement sent to the country in Oct 2015 ___ All funds disbursed (yes/no): _No__ Any delay?(yes/no): Yes___ If Yes, reasons for delay & action plan to resolve: _ If Yes, will delay have impact on project completion date (yes/no): __Yes_ Any ongoing problems (yes/no): _No __ If Yes, is any action required by ExCom: _
ONG | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Individual | AFR | CBI | PHA | 77 | TAS | 21 | A | I |  | 0 |  | 0 |  | 2016-12-01 |  | 2018-06-01 | 2018-06-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 3000 | 3900 | 0 | 0 | 3900 | 0 | Newly approved project | Brief progress report (actual/planned): Newly approved. UNEP will help the country to hire an independent consultant and submit the report by ExCom 79. Legal arrangements (actual/planned): Contract not signed yet. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement _no __ All funds disbursed (yes/no): _ Final payment _no_4.__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
ONG | UNEP | HCFC phase-out management plan (stage I, third tranche) | Multi-year | AFR | CBI | PHA | 77 | TAS | 22 | A | I |  | 0 |  | 0 |  | 2016-12-01 |  | 2018-12-01 | 2018-12-01 |  |  | 35000 | 0 | 35000 | 0 | 0% | 35000 | 0 | 3500 | 4550 | 0 | 0 | 4550 | 0 | Newly approved project | Brief progress report (actual/planned): Project newly approved. Agreement not signed yet. Legal arrangements (actual/planned): Agreement not signed yet. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement _no __ All funds disbursed (yes/no): _ Final payment _no_4.__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
FIN | UNDP | Project preparation for the formulation of refrigerant management plan (investment component) | Individual | AFR | CBI | REF | 42 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2005-04-01 |  | 2005-04-01 | 2006-12-01 | 24000 | 0 | 24000 | 24000 | 100% | 0 | 0 | 0 | 1800 | 0 | 1800 | 0 | 0 | Completed in 2005. Financially completed in 2006. |  | 2004 |  | Investment
FIN | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | AFR | CBI | REF | 44 | TAS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2007-12-01 |  | 2008-12-01 | 2011-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0
FIN | UNDP | Implementation of the RMP: technical assistance for the refrigeration servicing sector | RMP-Component | AFR | CBI | REF | 44 | TAS | 08 | N | I | CFC | 1.3 | 1.3 | 0 | 0 | 2004-12-01 | 2008-12-01 | 2007-06-01 |  | 2010-12-01 | 2013-01-01 | 75400 | -1335.75 | 74064.25 | 74064 | 100% | 0.25 | 0 | 0 | 6786 | -120.22 | 6665.76 | 0.02 | 0 | Financially completed in 2013. |  | 2004 |  | Investment
FIN | UNEP | Implementation of the RMP: training programme for refrigeration service technicians | Individual | AFR | CBI | REF | 44 | TRA | 05 | A | I | CFC | 0.7 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2006-12-01 |  | 2008-12-01 | 2011-11-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNEP | Implementation of the RMP: training programme for customs officers | Individual | AFR | CBI | REF | 44 | TRA | 07 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2006-12-01 |  | 2008-12-01 | 2011-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNEP | Formulation of national phase out strategy | Individual | AFR | CBI | SEV | 35 | TAS | 01 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2003-06-01 | 2003-08-01 |  | 2004-12-01 | 2011-07-01 | 40000 | -4983 | 35017 | 35017 | 100% | 0 | 0 |  | 5200 | -648 | 4552 | 0 | 0
FIN | UNEP | Establishment of the Ozone Unit | Individual | AFR | CBI | SEV | 36 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2005-06-01 | 2003-04-01 |  | 2007-11-01 | 2011-03-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Establishment of the Ozone Unit (institutional strengthening) | Individual | AFR | CBI | SEV | 44 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2006-12-01 |  | 2007-09-01 | 2011-01-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase II) | Individual | AFR | CBI | SEV | 50 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-02-01 | 2008-11-01 |  | 2008-11-01 | 2011-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | AFR | CBI | SEV | 57 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-06-01 | 2011-03-01 |  | 2013-03-01 | 2014-03-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of the institutional strengthening project (phase IV: 1/2014-12/2015) | Individual | AFR | CBI | SEV | 71 | INS | 17 | A | I |  | 0 |  | 0 |  | 2013-12-01 | 2014-08-01 | 2015-12-01 | 2017-12-01 |  |  | 60000 | 0 | 60000 | 30000 | 50% | 30000 | 30000 | 3000 | 0 | 0 | 0 | 0 | 0 | UNEP was to quick in putting COM as the new SSFA is needed to be signed to complete the work. The project is now ONG. | UNEP was to quick in putting COM as the new SSFA is needed to be signed to complete the work. The project is now ONG.
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | AFR | CBI | SEV | 74 | TAS | 19 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-03-01 | 2016-05-01 | 2017-10-01 |  |  | 40000 | 0 | 40000 | 189.26 | 0.4731% | 39810.74 | 28701.5 | 3981.074 | 5200 | 0 | 24.6038 | 5175.3962 | 3731.195 | Brief progress report (actual/planned): __ First payment sent to the Country in March 2016, country sent the first draft of ODS survey. Report to be finalized and translated. Legal arrangements (actual/planned): signed in November 2015 (Yes/No): No_ First mission (actual/planned): __n/a_ TOR completed (actual/planned): _N/A__ First disbursement date (actual/planned): March 2016___ All funds disbursed (yes/no): _NO__ any delay? (yes/no): _YES_ If Yes, reasons for delay & action plan to resolve: NO__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): __ First payment sent to the Country in March 2016, country sent the advanced draft of ODS survey in English. Legal arrangements (actual/planned): signed in November 2015 (Yes/No): No_ First mission (actual/planned): __n/a_ TOR completed (actual/planned): _N/A__ First disbursement date (actual/planned): March 2016___ All funds disbursed (yes/no): _NO__ any delay? (yes/no): _YES_ If Yes, reasons for delay & action plan to resolve: NO__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__
ONG | UNEP | Extension of the institutional strengthening project (phase V: 1/2016-12/2017) | Individual | AFR | CBI | SEV | 75 | INS | 20 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-04-01 | 2017-12-01 | 2017-12-01 |  |  | 85000 | 0 | 85000 | 32.49 | 0.03822% | 84967.51 | 84967.51 | 8496.751 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): SSFA signed in February 2016. First payment sent in April 2016. Art5 data report for 2015 and CP data for 2015 have been provided in May 2016. 2016 International Ozone Day celebrated. Legal arrangements (actual/planned): All activities under the SSFA are completed (as planned) NO___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _April 2016_ All funds disbursed (yes/no): _ _ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Brief progress report (actual/planned): SSFA signed in February 2016. First payment sent in April 2016. Art5 data report for 2015 and CP data for 2015 have been provided in May 2016. 2016 International Ozone Day celebrated. Legal arrangements (actual/planned): All activities under the SSFA are completed (as planned) NO___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _April 2016_ All funds disbursed (yes/no): _ _ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | CHD | PHA | 48 | PRP | 12 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-01-01 | 2007-04-01 |  | 2008-01-01 | 2011-10-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 |  | 2340 | 0 | 2340 | 0 | 0
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | AFR | CHD | PHA | 48 | PRP | 13 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-02-01 | 2007-04-01 |  | 2007-11-01 | 2008-12-01 | 12000 | 0 | 12000 | 12000 | 100% | 0 | 0 | 0 | 900 | 0 | 900 | 0 | 0 | Completed in 2007. Financially completed in 2008. |  | 2006 |  | Investment
FIN | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | CHD | PHA | 53 | INV | 16 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 | 2009-10-01 | 2009-11-01 |  | 2010-12-01 | 2013-08-01 | 92000 | 0 | 92000 | 92000 | 100% | 0 | 0 | 0 | 8280 | 0 | 8280 | 0 | 0 | Financially completed in 2013. |  | 2007 |  | Investment
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-year | AFR | CHD | PHA | 53 | TAS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-04-01 | 2009-03-01 |  | 2009-12-01 | 2011-12-01 | 94000 | 0 | 94000 | 94000 | 100% | 0 | 0 |  | 12220 | 0 | 12220 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | CHD | PHA | 55 | PRP | 17 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-10-01 | 2009-07-01 |  | 2012-12-01 | 2013-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 |  | 11050 | 0 | 11050 | 0 | 0
FIN | UNDP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | CHD | PHA | 57 | INV | 20 | N | I | CFC | 5.2 | 5.2 | 0 | 0 | 2009-04-01 | 2010-05-01 | 2011-03-01 |  | 2010-12-01 | 2013-08-01 | 82000 | -10981.89 | 71018.11 | 71018 | 100% | 0.11 | 0 | 0 | 7380 | -988.37 | 6391.62 | 0.01 | 0 | Financially completed in 2013. |  | 2009 |  | Investment
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | CHD | PHA | 57 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-10-01 | 2010-03-01 |  | 2010-03-01 | 2013-12-01 | 77000 | 0 | 77000 | 77000 | 100% | 0 | 0 |  | 10010 | 0 | 10010 | 0 | 0
COM | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | CHD | PHA | 62 | INV | 22 | A | I |  | 0 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2013-12-31 |  | 2015-12-01 | 2016-09-01 | 135000 | 0 | 135000 | 134541.74 | 99.66% | 458.26 | 0 | 1 | 10125 | 0 | 10091 | 34 | 0 | The project was operationally completed. |  |  |  | INV
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | CHD | PHA | 62 | TAS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-06-01 | 2013-12-01 |  | 2013-06-01 | 2014-06-01 | 100000 | -5000 | 95000 | 95000 | 100% | 0 | 0 |  | 13000 | -650 | 12350 | 0 | 0
COM | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | AFR | CHD | PHA | 70 | TAS | 24 | A | I |  | 1.6 |  | 0 |  | 2013-07-01 | 2015-12-01 | 2016-07-01 |  | 2016-12-01 |  | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Brief progress report (actual/planned): SSFA signed by the country in June 2014. Under the SSFA, country trained 151 refrigeration technicians and 70 enforcement officers. All funds disbursed. Agreement signed in June 2014. All activities under the SSFA are completed (as planned) YES___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement sent in July 2014. Last payment sent in September 2015.__ All funds disbursed (yes/no): _ Yes__ Any delay? (yes/no): no, SSFA expired in June 2016. ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a __ | Brief progress report (actual/planned): SSFA signed by the country in June 2014. Under the SSFA, country trained 151 refrigeration technicians and 70 enforcement officers. All funds disbursed. Agreement signed in June 2014. All activities under the SSFA are completed (as planned) YES___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement sent in July 2014. Last payment sent in September 2015.__ All funds disbursed (yes/no): _ Yes__ Any delay? (yes/no): no, SSFA expired in June 2016. ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a __
FIN | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Multi-Year | AFR | CHD | PHA | 73 | TAS | 26 | A | I |  | 0 |  | 0 |  | 2014-11-01 | 2016-01-01 | 2016-05-01 |  | 2016-12-01 | 2016-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | Project financially completed | Project financially completed
ONG | UNIDO | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | AFR | CHD | PHA | 76 | INV | 30 | A | I | HCFC | 2.4 | 0 |  |  | 2016-05-01 |  | 2020-05-31 | 2020-05-01 |  |  | 100000 | 0 | 100000 | 0 | 0% | 100000 | 97885.41 | 60000 | 7500 | 0 | 0 | 7500 | 7341 | Milestones achieved: TOR for purchase of equipment: prepared. Call for bids: published. Offers evaluated and supplier selected: Yes. Contract issued: Yes. Actions towards next goals: Plan training on the use of equipment Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | Equipment shipped and is on its way to N'Djamena. |  |  | INV
ONG | UNEP | HCFC phase-out management plan (stage I, third tranche) | Multi-year | AFR | CHD | PHA | 76 | TAS | 29 | A | I |  | 0 |  | 0 |  | 2016-05-01 | 2016-11-01 | 2018-12-01 | 2018-12-01 |  |  | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Brief progress report (actual/planned): SSFA signed in November 2016. First payment sent in November 2016. Country trained 20 RAC technicians and 13 customs officers in December 2016. Legal arrangements (actual/planned): All activities under the SSFA are completed (as planned) NO___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _November 2016_ All funds disbursed (yes/no): _ _ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Brief progress report (actual/planned): SSFA signed in November 2016. First payment sent in November 2016. Country trained 20 RAC technicians and 13 customs officers in December 2016. Country planning to organize 2 workshops training for 40 RAC technicians and 25 customs officers in March 2017. Legal arrangements (actual/planned): All activities under the SSFA are completed (as planned) NO___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _November 2016_ All funds disbursed (yes/no): _ _ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
ONG | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Individual | AFR | CHD | PHA | 77 | TAS | 31 | A | I |  | 0 |  | 0 |  | 2016-12-01 |  | 2018-06-01 | 2018-06-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 3000 | 3900 | 0 | 0 | 3900 | 0 | Newly approved project | Brief progress report (actual/planned): Newly approved. UNEP will help the country to hire an independent consultant and submit the report by ExCom 79. Legal arrangements (actual/planned): Agreement not signed yet. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement _no __ All funds disbursed (yes/no): _ Final payment _no_4.__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
FIN | UNDP | Preparation of a project in refrigerant recovery/recycling and RMP preparation | Individual | AFR | CHD | REF | 27 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 2000-04-01 |  | 1999-11-01 | 2002-04-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Implementation of the RMP: National programme for recovery and recycling of refrigerants | RMP-Component | AFR | CHD | REF | 29 | TAS | 04 | A | I | CFC | 12.6 | 12.6 | 0 | 0 | 1999-11-01 | 2001-05-01 | 2002-12-01 |  | 2001-12-01 | 2003-05-01 | 198252 | -36260 | 161992 | 161992 | 100% | 0 | 0 | 0 | 25772.76 | -4713.8 | 21058.96 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Implementation of the RMP: Monitoring of the activities included in the RMP | RMP-Component | AFR | CHD | REF | 29 | TAS | 07 | A | I | No_ODP | 1 | 1 | 0 | 0 | 1999-11-01 | 2001-09-01 | 2002-12-01 |  | 2003-07-01 | 2005-10-01 | 15455 | -4669 | 10786 | 10786 | 100% | 0 | 0 | 0 | 2009.15 | -607 | 1402.15 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 1999 |  | Non-Investment
FIN | UNEP | Implementation of the RMP: training the trainers of refrigeration technicians in good service practices | Individual | AFR | CHD | REF | 29 | TRA | 05 | A | I | CFC | 5.1 | 5.1 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2001-06-01 |  | 2002-08-01 | 2011-12-01 | 80125 | 0 | 80125 | 80125 | 100% | 0 | 0 |  | 10416 | 0 | 10416 | 0 | 0
FIN | UNEP | Implementation of the RMP: training programme for customs officers | Individual | AFR | CHD | REF | 29 | TRA | 06 | A | I | CFC | 4.8 | 4.8 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2001-06-01 |  | 2002-08-01 | 2011-11-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 |  | 9750 | 0 | 9750 | 0 | 0 |  |  |  | 2002-10-01
FIN | UNDP | Preparation of the refrigerant management plan update | Individual | AFR | CHD | REF | 37 | PRP | 08 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-07-01 | 2002-08-01 | 2003-07-01 |  | 2002-12-01 | 2005-12-01 | 12500 | 0 | 12500 | 12500 | 100% | 0 | 0 | 0 | 1625 | 0 | 1625 | 0 | 0 | Completed in 2002. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Incentive programme for commercial/industrial end-user sector | RMP-Component | AFR | CHD | REF | 38 | TAS | 09 | N | I | CFC | 6 | 6 | 0 | 0 | 2002-11-01 | 2005-02-01 | 2006-11-01 |  | 2010-12-01 | 2011-09-01 | 184416 | 0 | 184416 | 184416 | 100% | 0 | 0 | 0 | 23974.08 | 0 | 23974.08 | 0 | 0 | Completed in 2006. Financially completed in 2011. |  | 2002 |  | Non-Investment
FIN | UNEP | Country programme preparation | Individual | AFR | CHD | SEV | 15 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1996-05-01 | 1996-03-01 |  | 1998-05-01 | 2011-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNEP | Establishment of a National Ozone Unit | Individual | AFR | CHD | SEV | 25 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-01-01 | 2001-07-01 |  | 2004-12-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase II) | Individual | AFR | CHD | SEV | 44 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2006-12-01 |  | 2006-12-01 | 2009-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | AFR | CHD | SEV | 50 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-12-01 | 2008-11-01 |  | 2008-12-01 | 2011-03-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | CHD | SEV | 56 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2008-12-01 | 2010-12-01 |  | 2010-12-01 | 2006-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase V: 1/2012-12/2013) | Individual | AFR | CHD | SEV | 65 | INS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-05-01 | 2013-12-01 |  | 2013-08-01 | 2014-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of the institutional strengthening project (phase VI: 1/2014-12/2015) | Individual | AFR | CHD | SEV | 71 | INS | 25 | A | I |  | 0 |  | 0 |  | 2013-12-01 | 2014-08-01 | 2015-12-01 | 2017-12-01 |  |  | 60000 | 0 | 60000 | 18690 | 31.15% | 41310 | 41310 | 4131 | 0 | 0 | 0 | 0 | 0 | Project completed | Project completed
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | AFR | CHD | SEV | 74 | TAS | 27 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-03-01 | 2016-05-01 | 2017-10-01 |  |  | 70000 | 0 | 70000 | 15055.56 | 21.51% | 54944.44 | 54944.44 | 5494.444 | 9100 | 0 | 1957.2228 | 7142.7772 | 7142.7772 | Brief progress report (actual/planned): __ First payment sent to the Country in March 2016, country hired consultants to conduct the ODS survey. Legal arrangements (actual/planned): signed in November 2015 (Yes/No): No_ First mission (actual/planned): __n/a_ TOR completed (actual/planned): _N/A__ First disbursement date (actual/planned): March 2016___ All funds disbursed (yes/no): _NO__ any delay? (yes/no): _YES_ If Yes, reasons for delay & action plan to resolve: NO__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): __ First payment sent to the Country in March 2016, country sent the draft ODS survey report in January 2017. Legal arrangements (actual/planned): signed in November 2015 (Yes/No): No_ First mission (actual/planned): __n/a_ TOR completed (actual/planned): _N/A__ First disbursement date (actual/planned): March 2016___ All funds disbursed (yes/no): _NO__ any delay? (yes/no): _YES_ If Yes, reasons for delay & action plan to resolve: NO__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__
ONG | UNEP | Extension of the institutional strengthening project (phase VII: 1/2016-12/2017) | Individual | AFR | CHD | SEV | 75 | INS | 28 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-04-01 | 2017-12-01 | 2018-12-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 85000 | 8500 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Country signed the SSFA in March 2016. 2015 CP data and 2015 Art7 data reported. Legal arrangements (actual/planned): Agreement signed in March 2016.First payment: April 2016. All activities under the SSFA are completed (as planned) No__ First mission (actual/planned): _ N/A -TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in March 2016 __ All funds disbursed (yes/no): _ No__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Brief progress report (actual/planned): Country signed the SSFA in March 2016. 2015 CP data and 2015 Art7 data reported. Legal arrangements (actual/planned): Agreement signed in March 2016.First payment: April 2016. All activities under the SSFA are completed (as planned) No__ NOO trained 45 enforcement officers and 95 RAC technicians in 2016. First mission (actual/planned): _ April 2017 -TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in March 2016 __ All funds disbursed (yes/no): _ No__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
FIN | UNDP | Preparation of a project in the aerosol (sterilants) subsector | Individual | LAC | CHI | ARS | 30 | PRP | 140 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 2000 |  | Investment
FIN | IBRD | CFC phase out at Frigocar | Individual | LAC | CHI | FOA | 07 | INV | 19 | N | I | CFC | 0.6 | 0.6 | 0 | 0 | 1992-06-01 | 1996-10-01 | 1996-10-01 |  | 1996-10-01 | 1996-10-01 | 15784 | 0 | 15784 | 15784 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. Foam project |  |  | 1996-10-01 | INV | 0
FIN | IBRD | CFC phase out at Kifafi | Individual | LAC | CHI | FOA | 07 | INV | 20 | N | I | CFC | 0.9 | 0.8 | 0 | 0 | 1992-06-01 | 1997-05-01 | 1997-03-01 |  | 1997-02-01 | 1997-05-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1997-02-01 | INV | 0
FIN | IBRD | CFC phase out at Polimin | Individual | LAC | CHI | FOA | 07 | INV | 23 | N | I | CFC | 0.3 | 0.28 | 0 | 0 | 1992-06-01 | 1997-05-01 | 1997-03-01 |  | 1997-02-01 | 1997-05-01 | 9120 | 0 | 9120 | 9120 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1997-02-01 | INV | 0
CLO | IBRD | CFC phase out at Himmer & Himmer | Individual | LAC | CHI | FOA | 07 | INV | 28 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1997-03-01 |  |  | 1997-03-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Not funded. Eliminate from inventory |  |  | 1997-03-01 | INV | 0
CLO | IBRD | CFC phase out at SAAM, S.A. | Individual | LAC | CHI | FOA | 07 | INV | 29 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1997-03-01 |  |  | 1997-03-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Not funded. Eliminate from Inventory |  |  | 1997-03-01 | INV | 0
FIN | IBRD | CFC phase out at Instapanel (IPAC) | Individual | LAC | CHI | FOA | 07 | INV | 30 | N | I | CFC | 64.2 | 64.2 | 0 | 0 | 1992-06-01 | 1997-02-01 | 1997-03-01 |  | 1996-12-01 | 1997-02-01 | 131606.92 | 0 | 131606.92 | 131606.92 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1996-12-01 | INV | 0
FIN | IBRD | CFC phase out at Inversiones Overjuna (Metalcargo) | Individual | LAC | CHI | FOA | 07 | INV | 31 | N | I | CFC | 0.2 | 0.2 | 0 | 0 | 1992-06-01 | 1996-12-01 | 1997-03-01 |  | 1996-12-01 | 1996-12-01 | 4740 | 0 | 4740 | 4740 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1997-01-01 | INV | 0
FIN | UNDP | Terminal umbrella project for phase-out of the use of CFC-11 in the manufacture of polyurethane foam | Individual | LAC | CHI | FOA | 48 | INV | 161 | N | I | CFC | 51.4 | 51.4 | 0 | 0 | 2006-04-01 | 2007-07-01 | 2009-09-01 |  | 2010-12-01 | 2013-07-01 | 429962 | 0 | 429962 | 429962 | 100% | 0 | 0 | 0 | 32247 | 0 | 32247 | 0 | 0 | Financially completed in 2013. |  | 2006 | 2009-09-01 | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | LAC | CHI | FOA | 57 | PRP | 167 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-01-01 | 2010-03-01 |  | 2010-12-01 | 2012-12-01 | 50000 | -15796.29 | 34203.71 | 34204 | 100% | -0.29 | 0 | 0 | 3750 | -1184.72 | 2565.2999 | -0.01995 | 0 | Financially completed in 2012. |  | 2009 |  | Investment
COM | UNDP | Preparation for HCFC phase-out investment activities (stage II) (foam sector) | Individual | LAC | CHI | FOA | 73 | PRP | 183 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-11-01 | 2015-05-01 | 2016-11-01 |  | 2016-11-01 |  | 100000 | 0 | 100000 | 51494.11 | 51.49% | 48505.89 | 40414.8 | 41230.0065 | 7000 | 0 | 3604.5877 | 3395.4123 | 2829.036 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Final document prepared and submitted (as part of the complete HPMP Stage II project), comments by MLFS addressed. Discussion with stakeholders conducted to present approved funds. Prodoc signed (actual/planned, yes/no and date):The agreement has been signed earlier. Missions undertaken (actual/planned):1 of 1 TOR for consultants/subcontracts completed (actual/planned): TOR completed earlier. Contract/PO/MOA agreements signed: 0 of 0 First disbursement date (actual/planned): 42125Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | Pending payments cleared. | 2014 |  | Non-Investment
FIN | Canada | Bromosorb technology in commodity fumigation | Individual | LAC | CHI | FUM | 15 | DEM | 06 | A | I |  | 0 |  | 0 |  | 1994-12-01 |  | 1995-12-01 |  | 1997-04-01 | 1997-04-01 | 300000 | 17000 | 317000 | 317000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1994 | 1996-12-01 | Non-Inv.
FIN | UNDP | Project preparation for a methyl bromide alternative demonstration project for soil fumigation in nurseries and seed beds for apples and kiwis | Individual | LAC | CHI | FUM | 24 | PRP | 32 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-05-01 | 1998-12-01 |  | 2000-07-01 | 2003-12-01 | 25000 | -11504 | 13496 | 13496 | 100% | 0 | 0 | 0 | 3250 | -1495.52 | 1754.48 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1998 |  | Investment
FIN | IBRD | Project preparation in the methyl bromide sector for tomatoes |  | LAC | CHI | FUM | 24 | PRP | 33 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1998-12-01 | 1998-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Demonstration project for testing methyl bromide alternatives in soil treatment applications for tomatoes and peppers | Individual | LAC | CHI | FUM | 25 | DEM | 35 | N | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-06-01 | 2000-08-01 |  | 2006-12-01 | 2007-06-01 | 348130 | -73.55 | 348056.45 | 348056.45 | 100% | 0 | 0 |  | 45256.9 | -9.57 | 45247.33 | 0 | 0 | Project completed and closed. Reconciliation of all accounts concluded by the closing date of the whole umbrella project in Jun 07. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment project in the methyl bromide sector |  | LAC | CHI | FUM | 30 | PRP | 139 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2000-12-01 |  | 2001-12-01 | 2001-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organizations in methyl bromide communication | Individual | LAC | CHI | FUM | 30 | TAS | 141 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2011-12-01 | 25000 | -8217 | 16783 | 16783 | 100% | 0 | 0 |  | 3250 | -1068.21 | 2181.79 | 0 | 0
FIN | UNDP | Demonstration and phase-out project for methyl bromide soil fumigation for fruit tree production and replant | One-off-Phaseout | LAC | CHI | FUM | 32 | INV | 143 | N | I | MeBr | 76.2 | 76.2 | 0 | 0 | 2000-12-01 | 2001-07-01 | 2006-06-01 |  | 2007-12-01 | 2013-02-01 | 805000 | -453.72 | 804546.28 | 804545.99 | 100% | 0.29 | 0 | 0 | 98550 | -55.55 | 98494.419 | 0.031002 | 0 | Financially completed in 2013. |  | 2000 |  | Investment
FIN | IBRD | Project preparation for 2 projects in the methyl bromide sector |  | LAC | CHI | FUM | 33 | PRP | 145 | A | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-12-01 | 2002-09-01 |  | 2001-12-01 | 2001-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | The proposal is being prepare by the Bank and the INIA |  |  |  | Non-INV | 0
CLO | IBRD | Phase-out of all the remaining uses of methyl bromide in soil application pest control (first tranche) | Multiyear | LAC | CHI | FUM | 45 | INV | 158 | N | I | MBR | 1.3 | 0 | 0 | 0 | 2005-04-01 |  | 2006-04-01 |  |  | 2006-07-01 | 691703 | -691703 | 0 | 0 | #DIV/0! | 0 | 0 |  | 51878 | -51878 | 0 | 0 | 0 | Project cancelled. |  |  |  | INV | 0
FIN | UNIDO | Project preparation in the elimination of methyl bromide in soil fumigation | Individual | LAC | CHI | FUM | 57 | PRP | 169 | A | I |  | 0 | 0 |  |  | 2009-04-01 | 2009-05-01 | 2010-03-31 |  | 2010-12-01 | 2011-03-01 | 50000 | -152 | 49848 | 49847.63 | 100% | 0.37 | 0 |  | 3750 | -11 | 3739 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | National phase-out of methyl bromide - terminal project (first tranche) | Multi-Year | LAC | CHI | FUM | 60 | INV | 171 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-12-01 | 2014-04-30 |  | 2013-12-01 | 2013-12-01 | 1100000 | 0 | 1100000 | 1099999.5 | 100% | 0.5 | 0 |  | 82500 | 0 | 82500 | 0 | 0 | FIN
COM | UNEP | National phase-out of methyl bromide, terminal project (first tranche) | Multi-Year | LAC | CHI | FUM | 60 | TAS | 172 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-08-01 | 2014-04-01 |  | 2016-06-01 |  | 73000 | -188 | 72812 | 72812 | 100% | 0 | 0 | 0 | 9490 | -24.44 | 9465.56 | 0 | 0 | Project completed. | PCR being prepared.
COM | UNIDO | National phase-out of methyl bromide, terminal project (second tranche) | Multi-Year | LAC | CHI | FUM | 69 | INV | 178 | A | I | MBR | 0 | 0 |  |  | 2013-04-01 | 2013-08-01 | 2014-12-31 |  | 2015-12-01 |  | 557917 | 0 | 557917 | 556991.5 | 99.83% | 925.5 | 0 | 1 | 41844 | 0 | 41774 | 70 | 0 | The project was operationally completed. |  |  |  | INV
FIN | IBRD | Preparation of a national halon bank |  | LAC | CHI | HAL | 39 | PRP | 152 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-12-01 | 2003-12-01 |  | 2003-12-01 | 2003-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 3000 | 0 | 3000 | 0 | 0 | Proposal will be submitted to the 42nd ExCom Meeting. |  |  |  | Non-INV | 0
TRF | IBRD | Halon consumption phase-out: technical assistant programme and halon recycling and recovery equipment | Halon Banking | LAC | CHI | HAL | 42 | TAS | 156 | N | I |  | 0 | 0 | 0 | 0 | 2004-04-01 |  | 2006-10-01 |  |  | 2007-03-01 | 60000 | -60000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 4500 | -4500 | 0 | 0 | 0 | Project transferred to UNDP in 2007 at the 51st ExCom. |  |  |  | Non-INV | 0
FIN | UNDP | Halon consumption phase-out: technical assistant programme and halon recycling and recovery equipment | Individual | LAC | CHI | HAL | 51 | TAS | 164 | N | I | Halons | 0 | 0 | 0 | 0 | 2007-03-01 | 2010-01-01 | 2009-09-01 |  | 2014-03-01 | 2016-01-01 | 60000 | -1754.55 | 58245.45 | 58245 | 100% | 0.45 | 0 | 0 | 4500 | -131.59 | 4368.3751 | 0.03485 | 0 | Financially completed in 2016. | In 2014, the final report is being revised by NOU. | 2007 |  | Non-Investment
FIN | IBRD | Implementation of the Technology Conversion Financing Programme (Tecfin) | Individual | LAC | CHI | MUS | 07 | INV | 04 | N | I | CFC | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1996-06-01 |  | 1998-07-01 | 2000-03-01 | 69548 | -69548 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Part of $1,206,000 line-of-grant project. Funding returnd at the 30th ExCom. |  |  | 1997-04-01 | INV | 0
FIN | IBRD | Montreal Protocol implementation programme - phase II | Individual | LAC | CHI | MUS | 19 | INV | 14 | N | I | CFC | 400 | 216 | 0 | 0 | 1996-05-01 | 1998-12-01 | 2000-05-01 |  | 2004-12-01 | 2007-10-01 | 1000000 | 0 | 1000000 | 1000000 | 100% | 0 | 0 |  | 130000 | 0 | 130000 | 0 | 0 | Project completed and closed. Reconciliation of all accounts concluded by the closing date of whole umbrella project in Jun 07. |  |  | 2000-05-01 | INV | 0
FIN | IBRD | Montreal Protocol implementation programme (Phase II, second tranche) | Individual | LAC | CHI | MUS | 26 | INV | 37 | N | I | CFC | 270 | 202.6 | 0 | 0 | 1998-11-01 | 2000-12-01 | 2000-12-01 |  | 2004-12-01 | 2007-06-01 | 2800000 | -1512624 | 1287376 | 1287376 | 100% | 0 | 0 |  | 318000 | -166389 | 151611 | 0 | 0 | Project completed and closed. Reconciliation of all accounts concluded by the closing date of whole umbrella project in Jun 07. |  |  |  | INV | 0
FIN | Canada | Project preparation for a national phase-out plan |  | LAC | CHI | PHA | 50 | PRP | 162 | A | I |  | 0 |  | 0 |  | 2006-11-01 | 2007-10-01 | 2007-11-01 |  | 2008-04-01 | 2008-04-01 | 30000 | -1 | 29999 | 29999 | 100% | 0 |  | 0 | 3900 | 0 | 3900 | 0 |  | Chile servicing sector terminal phase-out plan preparation began in Oct 2007. Final proposal was completed by April 2008 and TPMP approved in July 2008. |  | 2006 |  | Non-Inv.
FIN | Canada | Servicing sector terminal CFC phase-out plan (first tranche) | Multi-Year | LAC | CHI | PHA | 55 | INV | 166 | A | I | CFC | 0 |  | 0 |  | 2008-07-01 | 2009-02-01 | 2011-07-01 |  | 2012-03-01 | 2012-03-01 | 176000 | 0 | 176000 | 176000 | 100% | 0 |  | 0 | 22880 | 0 | 22880 | 0 |  | Project was completed in March 2012. 107 conversions were undertaken and verified, 480 technicians received training in good practice, and a good practice standard was developed and officially published in June 2011 by the National Norm Institute. |  | 2008 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | CHI | PHA | 55 | PRP | 165 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-04-01 | 2009-07-01 |  | 2010-12-01 | 2014-05-01 | 150000 | -9.11 | 149990.89 | 149991 | 100% | -0.11 | 0 | 0 | 11250 | -0.68 | 11249.325 | -0.005 | 0 | Financially completed in 2014. |  | 2008 |  | Investment
FIN | Canada | Servicing sector terminal CFC phase-out plan (second tranche) | Multi-Year | LAC | CHI | PHA | 60 | INV | 173 | A | I | CFC | 32.9 | 32.9 | 0 |  | 2010-04-01 | 2011-01-01 | 2011-04-01 |  | 2013-03-01 | 2013-03-01 | 261500 | 0 | 261500 | 261500 | 100% | 0 |  | 0 | 33995 | 0 | 33995 | 0 |  | Project completed March 2013. Key results include: 125 refrigeration systems retrofitted; National Registry of refrigeration technicians established; Refrigeration servicing equipment supplied to training centres; 569 technicians trained in good practices. | Project completed in March 2013. Key results included: training of 569 technicians (in addition to those trained under Phase I); development of official certification system for technicians; 98 end-user conversions; procurement of equipment for training centres ($81,000) including tools, recovery machines and refrigerant identifiers. | 2010 |  | Investment
FIN | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | CHI | PHA | 63 | INV | 174 | N | I | HCFC | 5.7 | 5.7 | 0 | 0 | 2011-04-01 | 2012-12-01 | 2012-03-01 |  | 2015-11-01 | 2016-10-01 | 465566 | 0 | 465566 | 465566 | 100% | 0 | 0 | 0 | 34917 | 0 | 34917 | 0 | 0 | Financially completed in 2016. | Selection scheme for participating supermarkets was prepared by local consultant and is in final revision by NOU. A mission was conducted to review workplan and discuss implementation of the project. 2 local experts participated in specialized training on natural alternatives to HCFC in Germany. | 2011 |  | Investment
COM | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | CHI | PHA | 63 | TAS | 175 | A | I |  | 1.9 | 0 | 0 | 0 | 2011-04-01 | 2013-08-01 | 2012-03-01 |  | 2016-12-01 |  | 153217 | 0 | 153217 | 114417.79 | 74.68% | 38799.21 | 38799.21 | 38799 | 19918 | 0 | 14874.1559 | 5043.8441 | 5043.8441 | Brief progress: Project completed satisfactorily - 6 training classes delivered to 89 Officers, 2 local consultants hired and technical support on HCFCs Licensing and Quota System delivered to the NOU. Legal Arrangements: signed in May 2013 (but expired). - First mission: July 2013 TOR completed (actual/planned): N/a First disbursement date (actual/planned): August 2013/November 2011 - All funds disbursed? No. Any delay? N/A. If Yes, will delay have impact on project completion date? N/A | Project completed.
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | CHI | PHA | 71 | INV | 179 | N | I | HCFC | 6.6 | 4.2 | 0 | 0 | 2013-12-01 | 2014-03-01 | 2015-06-01 | 2017-12-01 |  |  | 537357 | 0 | 537357 | 75333.85 | 14.02% | 462023.15 | 0 | 184809.26 | 40302 | 0 | 5650.0703 | 34651.9297 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Consultancy for the identification of criteria to be used when applying subsidies to the certification process of RAC technicians was hired and conducted. Agreement with the Chilean chamber of refrigeration was updated. Prodoc signed (actual/planned, yes/no and date):The agreement has been signed earlier. Missions undertaken (actual/planned):1 of 1 TOR for consultants/subcontracts completed (actual/planned): 2 of 2 Contract/PO/MOA agreements signed: 2 of 2 First disbursement date (actual/planned): 41699Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:The hiring process of consultancies was declared empty, so it had to be relaunched, meetings with the NOU were conducted to adjuste TOR and work plan. | Review of annual work plan conducted. | 2013 |  | Investment
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | CHI | PHA | 71 | TAS | 180 | A | I |  | 0.5 |  | 0 |  | 2013-12-01 | 2016-12-01 | 2014-12-01 | 2017-12-01 |  |  | 40127 | 0 | 40127 | 0 | 0% | 40127 | 35225.55 | 4012.7 | 5217 | 0 | 0 | 5217 | 4579.7516 | Brief Report: The 2nd and 3rd tranches were approved together, so the implementation arrangements and Action Plan with the Government were agreed in order to undertake joint implementation of both tranches: part of funds through direct execution of UNEP (as requested by GOV and agreed by UNEP); and part by local execution (through a standard SSFA procedure). Two consultants (one for ODS Control and one for Awareness) had been recruited. HCFCs Quota System for 2016 was established and enforced by Customs and monitored by consultant. Consultant is also reviewing the training needs for Customs Officers in order to prepare a training programme. On Awareness, the Consultant has assessed all awareness interventions undertaken so far in order to propose a new Awareness Plan to fulfil Chilean needs. Legal arrangements (actual/planned): Dec 2016 / Mar 2014 TOR completed (actual/planned): 2/2 First disbursement date (actual/planned): Dec 2016 / Jun 2014 - All funds disbursed? No. Any delay? N/A - delays identified seemed to be resolved along 2016. If Yes, will delay have impact on project completion date? Yes. Delays on 2015 were incorporated at the Agreement ammended by the 76th ExCom. Any ongoing problems? No. - If Yes, is any action required by ExCom? N/A. | Brief Report: The 2nd and 3rd tranches were approved together, so the implementation arrangements and Action Plan with the Government were agreed in order to undertake joint implementation of both tranches: part of funds through direct execution of UNEP (as requested by GOV and agreed by UNEP); and part by local execution (through a standard SSFA procedure). 2017 HCFCs Quota System issued. Training programme for Customs Officers is being prepared. Issues related to the pre-blended polyols control are being assessed. Awareness Programme agreed with GOV and is being implemented. Legal arrangements (actual/planned): Dec 2016 / Mar 2014 TOR completed (actual/planned): N/a First disbursement date (actual/planned): Dec 2016 / Jun 2014 - All funds disbursed? No. Any delay? N/A - delays identified seemed to be resolved along 2016. If Yes, will delay have impact on project completion date? Yes. Delays on 2015 were incorporated at the Agreement ammended by the 76th ExCom. Any ongoing problems? No. - If Yes, is any action required by ExCom? N/A. |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor the signing of the agreement by the Government.
ONG | UNDP | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | LAC | CHI | PHA | 73 | INV | 184 | N | I | HCFC | 0.3 | 0 | 0 | 0 | 2014-11-01 |  | 2016-11-01 | 2017-12-01 |  |  | 295744 | 0 | 295744 | 0 | 0% | 295744 | 0 | 118297.6 | 22181 | 0 | 0 | 22181 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): 2 supermarkets were selected for the test of alternatives technologies to HCFC. 1 contract was prepared and submitted to the beneficiary company. Prodoc signed (actual/planned, yes/no and date):The agreement has been signed earlier. Missions undertaken (actual/planned):1 of 1 TOR for consultants/subcontracts completed (actual/planned): 2 pf 2 Contract/PO/MOA agreements signed: 0 fo 2 First disbursement date (actual/planned): 42125Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:One of the supermarket withdrew of the precess due to changes in the ownership, a new bidding process was planned for early 2017. | Review of TOR of the new bidding process. | 2014 |  | Investment |  | To request the submission of additional status report to the 79th meeting to monitor the disbursement rate of approved funds.
FIN | UNEP | Preparation of a HCFC phase-out management plan (stage II) | Multi-Year | LAC | CHI | PHA | 73 | PRP | 181 | A | I |  | 0 |  | 0 |  | 2014-11-01 |  | 2016-11-01 |  | 2016-11-01 | 2016-11-01 | 20000 | 0 | 20000 | 0 | 0% | 20000 | 0 |  | 2600 | 0 | 0 | 2600 | 0 | Brief Progress: HPMP Stage 2 approved at the 76th ExCom. Project completed. Legal arrangements: N/A - direct implementation, no agreement signed. TOR completed (actual/planned): 1/1 First disbursement date (actual/planned): 0 disbursed / May 2015 - All funds disbursed? No. Any delay? N/A - If Yes, will delay have impact on project completion date? N/A. Any ongoing problems? No. - If Yes, is any action required by ExCom? N/A. | Project completed. Because of UMOJA blackout period, UNEP could not hire consultant for project preparation. The project was prepared by UNDP, NOU and UNEP’s staff member.
COM | UNDP | Preparation of a HCFC phase-out management plan (stage II) | Individual | LAC | CHI | PHA | 73 | PRP | 182 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-11-01 |  | 2016-11-01 |  | 2016-11-01 |  | 50000 | -40000 | 10000 | 0 | 0% | 10000 | 0 | 8500 | 3500 | -2800 | 0 | 700 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Projec document prepared and submitted to ExCom. It was approved at the 76th ExCom meeting. After approval, the document was adjusted and discussed with stakeholders. Prodoc signed (actual/planned, yes/no and date):The agreement has been signed earlier. Missions undertaken (actual/planned):1 of 1 TOR for consultants/subcontracts completed (actual/planned): 1 of 1 Contract/PO/MOA agreements signed: 1 of 1 First disbursement date (actual/planned): 42752Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve:N/A | Final payments were done. | 2014 |  | Non-Investment
ONG | UNEP | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | LAC | CHI | PHA | 73 | TAS | 185 | A | I | CFC-22 | 2.1 |  | 0 |  | 2014-11-01 | 2016-12-01 | 2015-11-01 | 2017-12-01 |  |  | 27022 | 0 | 27022 | 0 | 0% | 27022 | 0 | 2702.2 | 3513 | 0 | 0 | 3513 | 0 | Brief Report: The 2nd and 3rd tranches were approved together, so the implementation arrangements and Action Plan with the Government were agreed in order to undertake joint implementation of both tranches: part of funds through direct execution of UNEP (as requested by GOV and agreed by UNEP); and part by local execution (through a standard SSFA procedure). Two consultants (one for ODS Control and one for Awareness) had been recruited. HCFCs Quota System for 2016 was established and been enforced by Customs and monitored by consultant. Consultant is also reviewing the training needs for Customs Officers in order to prepare a training programme. On Awareness, the Consultant has assessed all awareness interventions undertaken so far in order to propose a new Awareness Planto fulfill Chilean needs. Legal arrangements (actual/planned): Dec 2016 / Mar 2014 TOR completed (actual/planned): 2/2 First disbursement date (actual/planned): Dec 2016 / Jun 2014 - All funds disbursed? No. Any delay? N/A - delays identified seemed to be resolved along 2016. If Yes, will delay have impact on project completion date? Yes. Delays on 2015 were incorporated at the Agreement ammended by the 76th ExCom. Any ongoing problems? No. - If Yes, is any action required by ExCom? N/A. | Brief Report: The 2nd and 3rd tranches were approved together, so the implementation arrangements and Action Plan with the Government were agreed in order to undertake joint implementation of both tranches: part of funds through direct execution of UNEP (as requested by GOV and agreed by UNEP); and part by local execution (through a standard SSFA procedure). 2017 HCFCs Quota System issued. Training programme for Customs Officers is being prepared. Needs on the pre-blended polyols control being assessed. Awareness Programme agreed with GOV and being implemented. Legal arrangements (actual/planned): Dec 2016 / Mar 2014 TOR completed (actual/planned): 0 First disbursement date (actual/planned): Dec 2016 / Jun 2014 - All funds disbursed? No. Any delay? N/A - delays identified seemed to be resolved along 2016. If Yes, will delay have impact on project completion date? Yes. Delays on 2015 were incorporated at the Agreement ammended by the 76th ExCom. Any ongoing problems? No. - If Yes, is any action required by ExCom? N/A. |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor the signing of the agreement by the Government.
COM | UNIDO | Preparation of a HCFC phase-out management plan (stage II) (transfer of project) | Individual | LAC | CHI | PHA | 74 | PRP | 188 | A | I |  | 0 | 0 |  |  | 2015-05-01 | 2015-07-01 | 2016-11-30 |  | 2016-05-01 |  | 40000 | 0 | 40000 | 39441.93 | 98.6% | 558.07 | 0 | 1 | 2800 | 0 | 0 | 2800 | 0 | - Project completed. - HPMP Stage II project document prepared and approved at the 76th Executive Committee in 2016. | Balance will be returned to the 79th Meeting of the ExCom. |  |  | NON-INV
ONG | UNDP | HCFC phase-out management plan (stage II, first tranche) (foam sector ) | Multi-Year | LAC | CHI | PHA | 76 | INV | 190 | N | I | HCFC | 12 | 0 | 0 | 0 | 2016-05-01 |  | 2019-02-01 | 2017-02-01 |  |  | 700955 | 0 | 700955 | 0 | 0% | 700955 | 0 | 280382 | 49067 | 0 | 0 | 49067 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): ProDoc prepared and discussed with the stakeholders. The approved documents were adjusted and discussed with the beneficiary companies. Prodoc signed (actual/planned, yes/no and date):No, it is expected that the ProDoc will be signed on March 2017. Missions undertaken (actual/planned):0 of 0 TOR for consultants/subcontracts completed (actual/planned): 0 of 0 Contract/PO/MOA agreements signed: 0 of 0 First disbursement date (actual/planned): 42842Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve:N/A | Final draft under review by stakeholders. |  |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, fourth and fifth tranches) | Multi-Year | LAC | CHI | PHA | 76 | INV | 192 | N | I | HCFC | 5.9 | 0 | 0 | 0 | 2016-05-01 |  | 2017-12-01 | 2017-12-01 |  |  | 199299 | 0 | 199299 | 0 | 0% | 199299 | 0 | 79719.6 | 14947 | 0 | 0 | 14947 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Process to contract the regenaration center was launched and awarded. 2 technical experts were trained on natural alternatives to HCFC. 15 workshops on GRP were conducted, 290 technicians and 20 students were trained. Prodoc signed (actual/planned, yes/no and date): Missions undertaken (actual/planned):1 of 1 TOR for consultants/subcontracts completed (actual/planned): 2 of 2 Contract/PO/MOA agreements signed: 2 of 2 First disbursement date (actual/planned): Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve:N/A | Final draft under review by stakeholders. |  |  | Investment
ONG | UNIDO | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | Multi-Year | LAC | CHI | PHA | 76 | TAS | 189 | A | I |  | 0 | 0 |  |  | 2016-05-01 | 2016-08-01 | 2019-05-31 | 2019-05-01 |  |  | 309210 | 0 | 309210 | 19095.55 | 6.176% | 290114.45 | 4110.28 | 50000 | 21645 | 0 | 1337 | 20308 | 288 | - The project was approved at the 76th Meeting of the ExCom in May 2016. - Work plan was agreed. - A technical coordinator was recruited - Several awareness raising workshops have been carried out in Concepcion and Santiago Actions towards next goals: - Training on the certification - a certification programme based on Texas Institute is being prepared and adopted - Training programmes to be designed: on natural alternatives, on leakage monitoring, on best practices (updated) - No delay - No recurring problem - No impact on project completion date - No action required by Executive Committee | - A "train the trainers" workshop on alternatives have been organized in March 2017. - Participants, coming from different cities of Chile, were trained and updated on the latest technologies and alternatives refrigerants. Actions towards next goals: To continue with the training of trainers all over the country and the promotion and enlargement of the certification programme. - No delay - No recurring problem - No impact on project completion date - No action required by Executive Committee |  |  | INV
ONG | UNEP | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | Multi-Year | LAC | CHI | PHA | 76 | TAS | 191 | A | I |  | 0 |  | 0 |  | 2016-05-01 |  | 2018-05-01 | 2018-05-01 |  |  | 65481 | 0 | 65481 | 0 | 0% | 65481 | 0 | 6548.1 | 8513 | 0 | 0 | 8513 | 0 | Brief Report: Project approved in 2016, 76th ExCom. Legal arrangements: Agreement being negotiated. TOR completed (actual/planned): 0/0 First disbursement date (actual/planned): 0 disbursed / May 2017 - All funds disbursed? No. Any delay? No. --- If Yes, will delay have impact on project completion date? n/a Any ongoing problems? No. --- If Yes, is any action required by ExCom? N/A. | Brief Report: Agreement being negotiated and detailed action plan under preparation. Legal arrangements: Agreement being negotiated. TOR completed (actual/planned): 0/0 First disbursement date (actual/planned): 0 disbursed / May 2017 - All funds disbursed? No. Any delay? No. --- If Yes, will delay have impact on project completion date? n/a Any ongoing problems? No. --- If Yes, is any action required by ExCom? N/A.
ONG | UNEP | HCFC phase-out management plan (stage I, fourth and fifth tranches) | Multi-Year | LAC | CHI | PHA | 76 | TAS | 193 | A | I |  | 0 |  | 0 |  | 2016-05-01 |  | 2017-05-01 | 2017-12-01 |  |  | 68123 | 0 | 68123 | 0 | 0% | 68123 | 0 | 6812.3 | 8856 | 0 | 0 | 8856 | 0 | Brief Report: Project approved in 2016, 76th ExCom. As per Decisions 76/37 and 76/45, the Agreement for the Tranches 2 and 3 was signed in late December 2016, and therefore, the funding for the combined tranches 4 and 5 (4th Tranche) was released to UNEP by the MLFS on January 2017. Legal arrangements: n/a TOR completed (actual/planned): 0/0 First disbursement date (actual/planned): 0 disbursed / May 2017 - All funds disbursed? No. Any delay? Yes --- If Yes, will delay have impact on project completion date? Tranches 4 and 5 delayed due to the delay in the implementation of Tranches 2 and 3. Any ongoing problems? No. --- If Yes, is any action required by ExCom? N/A. | Brief Report: Funding received from the MLFS in January 2017, the Agreement is being negotiated and detailed action plan under preparation. Legal arrangements: n/a TOR completed (actual/planned): 0/0 First disbursement date (actual/planned): 0 disbursed / May 2017 - All funds disbursed? No. Any delay? Yes --- If Yes, will delay have impact on project completion date? Tranches 4 and 5 delayed due to the delay in the implementation of Tranches 2 and 3. Any ongoing problems? No. --- If Yes, is any action required by ExCom? N/A.
FIN | UNDP | Demonstration programme for service centre technicians on CFC-11 venting and leakage from refrigerators during operation and servicing | Individual | LAC | CHI | REF | 06 | DEM | 02 | A | I | CFC | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-06-01 | 1993-06-01 |  | 1993-09-01 | 1997-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | IBRD | Retrofit of freezing chambers at Frigorent Frigorifico Sociedad Limitada | Individual | LAC | CHI | REF | 07 | INV | 18 | N | I | CFC | 0.03 | 0.03 | 0 | 0 | 1992-06-01 | 1996-10-01 | 1996-09-01 |  | 1996-10-01 | 1996-10-01 | 20166.36 | 0 | 20166.36 | 20166.36 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1996-10-01 | INV | 0
FIN | IBRD | Replacement of CFCs at Mimet | Individual | LAC | CHI | REF | 07 | INV | 21 | N | I | CFC | 47.8 | 47.8 | 0 | 0 | 1992-06-01 | 1997-01-01 | 1996-12-01 |  | 1996-12-01 | 1997-01-01 | 93671.85 | 0 | 93671.85 | 93671.85 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1996-12-01 | INV | 0
CLO | IBRD | Replacement of ODS at Supermercado Gran Avenida | Individual | LAC | CHI | REF | 07 | INV | 24 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1997-03-01 |  |  | 1997-03-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Not funded. Eliminate from inventory |  |  | 1997-03-01 | INV | 0
FIN | IBRD | Replacement of ODS at Supermercado Vicuna McKenna | Individual | LAC | CHI | REF | 07 | INV | 25 | N | I | CFC | 0.64 | 0.05 | 0 | 0 | 1992-06-01 | 1997-06-01 | 1997-03-01 |  | 1997-02-01 | 1997-06-01 | 5558 | 0 | 5558 | 5558 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. Refrigeration subproject |  |  | 1997-03-01 | INV | 0
FIN | IBRD | Replacement of ODS at Supermercado Macul | Individual | LAC | CHI | REF | 07 | INV | 26 | N | I | CFC | 0.4 | 0.08 | 0 | 0 | 1992-06-01 | 1997-06-01 | 1997-03-01 |  | 1997-02-01 | 1997-06-01 | 2505 | 0 | 2505 | 2505 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. Refrigeration subproject |  |  | 1997-03-01 | INV | 0
FIN | IBRD | Replacement of ODS at Supermercado Plaza Egana | Individual | LAC | CHI | REF | 07 | INV | 27 | N | I | CFC | 0.32 | 0.03 | 0 | 0 | 1992-06-01 | 1997-06-01 | 1997-03-01 |  | 1997-02-01 | 1997-06-01 | 3300 | 0 | 3300 | 3300 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. Refrigeration subproject |  |  | 1997-03-01 | INV | 0
FIN | IBRD | Recovery and recycling programme at Central De Servicios Tecnicos (CST) | Individual | LAC | CHI | REF | 07 | TAS | 22 | N | I | CFC | 4 | 4 | 0 | 0 | 1992-06-01 | 1997-01-01 | 1997-03-01 |  | 1996-11-01 | 1997-05-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1997-02-01 | INV | 0
FIN | USA | Demonstration mobile air conditioning (MAC) and refrigerated transport (RT) |  | LAC | CHI | REF | 19 | DEM | 15 | A | I | CFC | 10 | 10 | 0 |  | 1996-05-01 | 1996-05-01 | 1997-12-01 |  | 1997-12-01 | 1999-10-01 | 140000 | 0 | 140000 | 140000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1995 | 1997-12-01
FIN | Canada | Refrigerant management plan formulation project | Individual | LAC | CHI | REF | 27 | TAS | 138 | A | I |  | 0 |  | 0 |  | 1999-03-01 | 1999-08-01 | 2001-04-01 |  | 2001-10-01 | 2001-12-01 | 33900 | 0 | 33900 | 33900 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project Completed. RMP was submitted to the 35th EXCOM and has been approved. |  | 1999 |  | Non-Inv.
FIN | UNEP | Implementation of the RMP: enabling a control and regulatory network | Individual | LAC | CHI | REF | 35 | TAS | 146 | A | I | CFC | 18.4 | 18.4 | 0 | 0 | 2001-12-01 | 2003-08-01 | 2002-09-01 |  | 2009-06-01 | 2011-04-01 | 111400 | 0 | 111400 | 111400 | 100% | 0 | 0 |  | 14482 | 0 | 14482 | 0 | 0
FIN | Canada | Implementation of the RMP: recovery and recycling programme | RMP | LAC | CHI | REF | 35 | TAS | 147 | A | I | CFC | 88 | 88 | 0 |  | 2001-12-01 | 2006-08-01 | 2005-04-01 |  | 2009-03-01 | 2010-07-01 | 531620 | -30 | 531590 | 531590 | 100% | 0 |  | 0 | 53162 | 0 | 53162 | 0 |  | All the R&R equipment has been procured and distributed, is in use. All related training activities have been completed. Monitoring of use of equipment was completed in early 2009. Project completed in Feb. 2009 and last payment to Chile was made in April 2009. $30 were remaining and returned to MLF at 61st Meeting, thus financially closing the project. |  | 2001 |  | Non-Inv.
FIN | UNEP | Implementation of the RMP: end-users and public awareness programme | Individual | LAC | CHI | REF | 35 | TAS | 148 | A | I | CFC | 28.5 | 28.5 | 0 | 0 | 2001-12-01 | 2004-01-01 | 2005-12-01 |  | 2009-06-01 | 2011-07-01 | 172000 | 0 | 172000 | 172000 | 100% | 0 | 0 |  | 22360 | 0 | 22360 | 0 | 0
FIN | UNEP | Implementation of the RMP: monitoring, evaluation and reporting of the activities in the RMP | Individual | LAC | CHI | REF | 35 | TAS | 149 | A | I | CFC | 8.6 | 8.6 | 0 | 0 | 2001-12-01 | 2004-01-01 | 2005-12-01 |  | 2009-06-01 | 2011-12-01 | 52000 | 0 | 52000 | 52000 | 100% | 0 | 0 |  | 6760 | 0 | 6760 | 0 | 0
FIN | Canada | Implementation of the RMP: training programme for technicians and establishment of refrigeration standards | RMP | LAC | CHI | REF | 35 | TRA | 150 | A | I |  | 43 | 43 | 0 |  | 2001-12-01 | 2002-09-01 | 2004-12-01 |  | 2006-12-01 | 2007-05-01 | 260000 | 0 | 260000 | 260000 | 100% | 0 |  | 0 | 33800 | 0 | 33800 | 0 |  | Refrigeration equipment purchased and distributed to training centres. 1650 technicians trained. Code/standard of good practices completed in July 2005. Retrofit demonstration strategy developed and demonstrations completed in 2006. |  | 2001 |  | Non-Inv.
FIN | UNDP | Project preparation for the formulation of commercial refrigeration project | Individual | LAC | CHI | REF | 42 | PRP | 155 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2005-01-01 | 2005-04-01 |  | 2006-12-01 | 2012-04-01 | 32000 | -328.68 | 31671.32 | 31671 | 100% | 0.32 | 0 | 0 | 2400 | -24.65 | 2375.325 | 0.025 | 0 | Financially completed in 2012. | Financially completed in 2012. | 2004 |  | Investment
FIN | UNDP | Terminal umbrella project for phase-out of the use of CFC-11, CFC-12 and R-502 (CFC-115) in the manufacture of refrigeration equipment | Individual | LAC | CHI | REF | 48 | INV | 160 | N | I | CFC | 21.7 | 21.7 | 0 | 0 | 2006-04-01 | 2007-03-01 | 2009-04-01 |  | 2012-07-01 | 2014-07-01 | 282025 | -2652 | 279373 | 279373 | 100% | 0 | 0 | 0 | 21152 | -198.9 | 20953.1 | 0 | 0 | Financially completed in 2014. | Completed in 2012. Some final payments pending. No activities in 2013. | 2006 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (refrigeration manufacturing) | Individual | LAC | CHI | REF | 57 | PRP | 170 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-01-01 | 2010-03-01 |  | 2010-12-01 | 2012-12-01 | 50000 | -38365.77 | 11634.23 | 11634 | 100% | 0.23 | 0 | 0 | 3750 | -2877.43 | 872.55 | 0.01995 | 0 | Financially completed in 2012. |  | 2009 |  | Investment
FIN | IBRD | Country programme preparation | Individual | LAC | CHI | SEV | 04 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 121166 | -115333 | 5833 | 5833 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1991) |  | LAC | CHI | SEV | 04 | PRP | 17 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 162736 | -134936 | 27800 | 27800 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1992) |  | LAC | CHI | SEV | 06 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 191878 | -134385 | 57493 | 57493 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Establishment of the Ozone Team | Individual | LAC | CHI | SEV | 07 | INS | 08 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1994-09-01 | 1996-06-01 |  | 1996-10-01 | 1996-11-01 | 213000.03 | -2093 | 210907.03 | 210906.86 | 100% | 0.17 | 0.17 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1996-10-01 | Non-INV | 0
FIN | IBRD | Ozone seal programme | Individual | LAC | CHI | SEV | 07 | TAS | 09 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1994-09-01 | 1993-06-01 |  | 1996-06-01 | 1996-06-01 | 8000 | -600 | 7400 | 7400 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1996-06-01 | Non-INV | 0
FIN | IBRD | Public awareness programme | Individual | LAC | CHI | SEV | 07 | TAS | 10 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1994-09-01 | 1996-06-01 |  | 1996-06-01 | 1996-07-01 | 378000 | -5932 | 372068 | 372067.8 | 100% | 0.2 | 0.2 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1996-07-01 | Non-INV | 0
FIN | IBRD | Implementation of a sector specific training programme | Individual | LAC | CHI | SEV | 07 | TRA | 11 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1996-01-01 | 1996-06-01 |  | 1997-10-01 | 1998-12-01 | 111000 | -14033 | 96967 | 96967 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed |  |  | 1997-06-01 | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1993) |  | LAC | CHI | SEV | 09 | PRP | 07 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 82890 | -10881 | 72009 | 72009 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Supervision of project implementation (approved at the 7th ExCom meeting) |  | LAC | CHI | SEV | 12 | PRP | 05 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 30208 | 2849 | 33057 | 33057 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation/supervision of investment projects for ODS I and ODS II (1995) |  | LAC | CHI | SEV | 16 | PRP | 12 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1995-12-01 |  | 1995-12-31 | 1995-12-31 | 130312 | 0 | 130312 | 130312 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation |  | LAC | CHI | SEV | 18 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1997-03-01 | 1997-03-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0 | Funds committed in CY96 were disbursed in CY97. |  |  |  | Non-INV | 0
FIN | IBRD | Institutional strengthening II | Individual | LAC | CHI | SEV | 20 | INS | 16 | N | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-03-01 | 1998-10-01 |  | 1998-10-01 | 1998-10-01 | 113500 | 0 | 113500 | 113500 | 100% | 0 | 0 |  | 14755 | 0 | 14755 | 0 | 0 | Completed |  |  | 1998-10-01 | Non-INV | 0
FIN | IBRD | Ozone protection and institutional strengthening project (renewal) | Individual | LAC | CHI | SEV | 25 | INS | 36 | N | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-01-01 | 2000-07-01 |  | 2000-12-01 | 2000-12-01 | 143500 | 0 | 143500 | 143500 | 100% | 0 | 0 |  | 18655 | 0 | 18655 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation for the Phase II auction scheme |  | LAC | CHI | SEV | 25 | PRP | 34 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-09-30 | 1999-08-01 |  | 1998-12-01 | 1998-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0 | Newly approved. |  |  |  | Non-INV | 0
FIN | IBRD | Renewal of institutional strengthening |  | LAC | CHI | SEV | 32 | INS | 142 | N | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2002-12-01 | 2003-01-01 |  | 2003-01-01 | 2003-01-01 | 143500 | 0 | 143500 | 143500 | 100% | 0 | 0 |  | 18655 | 0 | 18655 | 0 | 0 | NOU completed the IS tranche with work on several activities: the RMP, methyl bromide demo. project, sterilization project, and methyl bromide phase out in the tree sub-sector. New IS approved at the 38th ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | Extension of institutional strengthening project |  | LAC | CHI | SEV | 38 | INS | 52 | N | I | CFC | 15.42 | 15.42 | 0 | 0 | 2002-11-01 | 2003-12-01 | 2004-12-01 |  | 2005-12-01 | 2005-12-01 | 186550 | 0 | 186550 | 186550 | 100% | 0 | 0 |  | 46800 | 0 | 46800 | 0 | 0 | Phase V of the IS project completed. |  |  |  | Non-INV | 0
FIN | IBRD | Extension of the institutional strengthening project (phase VI, second year) | Individual | LAC | CHI | SEV | 45 | INS | 157 | N | I | CFC | 7.7 | 7.7 | 0 | 0 | 2005-04-01 | 2005-12-01 | 2006-04-01 |  | 2006-04-01 | 2007-06-01 | 93275 | 0 | 93275 | 93275 | 100% | 0 | 0 |  | 6996 | 0 | 6996 | 0 | 0 | All resources used. Newly approved IS transferred to UNDP in 2007. |  |  |  | Non-INV | 0
FIN | IBRD | Extension of institutional strengthening (phase VI, year 2) | Individual | LAC | CHI | SEV | 47 | INS | 159 | N | D | CFC | 7.7 | 7.7 | 0 | 0 | 2005-11-01 | 2006-12-01 | 2006-12-01 |  | 2006-12-01 | 2007-06-01 | 93275 | 0 | 93275 | 93275 | 100% | 0 | 0 |  | 6996 | 0 | 6996 | 0 | 0 | All resources used. Newly approved IS transferred to UNDP in 2007. |  |  |  | Non-INV | 0
FIN | UNDP | Extension of institutional strengthening (phase VII) | Individual | LAC | CHI | SEV | 51 | INS | 163 | N | I | No_ODP | 15.4 | 15.4 | 0 | 0 | 2007-03-01 | 2007-04-01 | 2009-03-01 |  | 2009-07-01 | 2011-09-01 | 186550 | -372.06 | 186177.94 | 186178 | 100% | -0.06 | 0 | 0 | 13991 | -27.9 | 13963.1005 | -0.00049992 | 0 | Completed in 2009. Financially completed in 2011. |  | 2007 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VIII) | Individual | LAC | CHI | SEV | 57 | INS | 168 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-08-01 | 2011-03-01 |  | 2011-09-01 | 2014-04-01 | 186550 | -17 | 186533 | 186533 | 100% | 0 | 0 | 0 | 13991 | -1.27 | 13989.73 | 0 | 0 | Financially completed in 2014. | NOU activily supporting the introduction of quota system for HCFCs. | 2009 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase IX) | Individual | LAC | CHI | SEV | 63 | INS | 176 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-10-01 | 2013-03-01 |  | 2013-03-01 | 2014-10-01 | 186550 | -51 | 186499 | 186499 | 100% | 0 | 0 | 0 | 13991 | -4 | 13987 | 0 | 0 | Financially completed in 2014. | Project completed in 2013. The IS renewal request (phase X) was presented and approved. | 2011 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase X: 4/2013-3/2015) | Individual | LAC | CHI | SEV | 69 | INS | 177 | N | I | non-HCFC | 0 | 0 | 0 | 0 | 2013-04-01 | 2013-08-01 | 2015-03-01 |  | 2015-03-01 | 2016-03-01 | 186550 | 0 | 186550 | 186550 | 100% | 0 | 0 | 0 | 13058 | 0 | 13058 | 0 | 0 | Financially completed in 2016. | In 2015, HCFC quota allocation was set and informed to importers. Information about 2014 HCFC consumption was gathered and Country Programme report submitted. | 2013 |  | Non-Investment
ONG | UNDP | Extension of the institutional strengthening project (phase XI: 4/2015-3/2017) | Individual | LAC | CHI | SEV | 74 | INS | 186 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2015-05-01 | 2015-09-01 | 2017-03-01 | 2017-03-01 |  |  | 186550 | 0 | 186550 | 92289.81 | 49.47% | 94260.19 | 0 | 37704.076 | 13058 | 0 | 6460.0393 | 6597.9607 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Institutional strengthening activities underway. ODS consumption reports prepared and submitted. Celebration of Ozone Day carried out. 2016 HCFC import quota set. Prodoc signed (actual/planned, yes/no and date):The agreement has been signed earlier. Missions undertaken (actual/planned):1 of 1 TOR for consultants/subcontracts completed (actual/planned): TOR completed earlier. Contract/PO/MOA agreements signed: 1 of 1 First disbursement date (actual/planned): 42248Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | Annual work planned prepared and discussed. HCFC import quota for 2017 set. | 2015 |  | Non-Investment
ONG | UNIDO | Survey of ODS alternatives at the national level | Individual | LAC | CHI | SEV | 74 | TAS | 187 | A | I |  | 0 | 0 |  |  | 2015-05-01 | 2016-03-01 | 2016-05-31 | 2017-07-31 |  |  | 55000 | 0 | 55000 | 36105.99 | 65.65% | 18894.01 | 2356.99 | 16000 | 4950 | 0 | 0 | 4950 | 212.1291 | - The work carried out by the National Consultant was not fully satisfactory. We have shortened the contract and recruited a new consultant to improve the data collection. - Slight impact on the project completion date. | Survey and tables submitted, finalization and English translation is being carried out. |  |  | NON-INV
FIN | UNDP | Formulation of solvent sectoral phase-out plan | Individual | LAC | CHI | SOL | 39 | PRP | 153 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-06-01 | 2004-04-01 |  | 2004-06-01 | 2005-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 1500 | 0 | 1500 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2003 |  | Investment
FIN | UNDP | Technical assistance to phase-out ozone depleting solvents | Individual | LAC | CHI | SOL | 41 | TAS | 154 | N | I | CFC/TCA/CTC | 17.1 | 17.1 | 0 | 0 | 2003-12-01 | 2005-01-01 | 2005-12-01 |  | 2009-12-01 | 2012-07-01 | 245690 | -15287.88 | 230402.12 | 230402 | 100% | 0.12 | 0 | 0 | 22112 | -1375.9 | 20736.0862 | 0.0138 | 0 | Financially completed in 2012. |  | 2003 |  | Non-Investment
FIN | UNDP | Project preparation in the sterilants sector | Individual | LAC | CHI | STE | 33 | PRP | 144 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 650 | 0 | 650 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Terminal conversion of ethylene oxide/CFC-12 mixtures to alternative non-ozone depleting technologies in 26 hospitals | Individual | LAC | CHI | STE | 35 | INV | 151 | A | I | CFC | 19.8 | 19.8 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2004-07-01 |  | 2005-12-01 | 2007-03-01 | 412741 | -113 | 412628 | 412628 | 100% | 0 | 0 | 0 | 53656.33 | -14.69 | 53641.6401 | -0.0001 | 0 | Completed in 2005. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, first tranche, Cook Islands) | Multi-Year | ASP | CKI | PHA | 63 | TAS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-12-01 | 2015-03-01 |  | 2015-05-01 | 2016-12-01 | 49250 | 0 | 49250 | 49250 | 100% | 0 | 0 |  | 6403 | 0 | 6403 | 0 | 0 | Project financially completed. | Project financially completed.
ONG | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, second tranche, Cook Islands) | Multi-year | ASP | CKI | PHA | 74 | TAS | 11 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-07-01 | 2020-05-01 | 2020-12-01 |  |  | 39850 | 0 | 39850 | 0 | 0% | 39850 | 27000 | 3985 | 5181 | 0 | 0 | 5181 | 3510.3388 | Brief progress report (actual/planned): The SSFA was signed by UNEP and the Government of Cook Islands in April 2016. The first payment under the second tranche was made to the country in July 2016. The licensing and quota system was implemented in 2016. UNEP conducted a misison in September 2016 to follow-up project implementation and jointly delivered update training workshop for customs and enforcement officers. An update customs and enforcement training workshop was organized on 20-21 September 2016 in Roratonga with participation of 13 participants to build awareness and local capacity in the prevention of smuggling and safe handling of flammable refrigerants, which has been available in the PIC region. UNEP worked closely with the NOU to engage multi-stakeholders in the implementation of HPMP, second tranche to synergize HPMP with other on-going environmental policies/projects e.g. PALS, Samoa Pathway. 2015 CP data was submitted to MLFS online. Legal arrangements (actual/planned): The SSFA was signed in April 2016 First Mission: September 2016. TOR completed: Not applicable First disbursement date: July 2016. All funds disbursed (yes/no): No. Any delay? (yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): UNEP keeps regular communications with the country (Head of Environment) to expedite HPMP implementation as per the agreed work plan. However, there has been no assigned NOO in the country since February 2017. UNEP is engaging the senior management level to agree on the way forward to expedite HPMP implementation and including filling of the NOO position
FIN | UNEP | Implementation of the PIC strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | CKI | REF | 44 | TAS | 01 | A | I | CFC | 0.9 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2006-12-01 |  | 2007-11-01 | 2010-12-01 | 14000 | -3277 | 10723 | 10723 | 100% | 0 | 0 |  | 1820 | -426.01 | 1393.99 | 0 | 0
FIN | UNEP | Implementation of the PIC strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | CKI | REF | 44 | TAS | 03 | A | I | CFC | 0.5 | 0.5 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2006-12-01 |  | 2010-07-01 | 2011-07-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 | 0 |  | 1040 | 0 | 1040 | 0 | 0
FIN | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | CKI | SEV | 44 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-10-01 | 2005-12-01 |  | 2007-01-01 | 2010-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase I) | Individual | ASP | CKI | SEV | 50 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2010-01-01 | 2007-11-01 |  | 2008-12-01 | 2010-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase II, first year) | Individual | ASP | CKI | SEV | 53 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2009-05-01 | 2008-11-01 |  | 2011-01-01 | 2011-06-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase II, second year) | Individual | ASP | CKI | SEV | 59 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-10-01 | 2010-12-01 |  | 2011-03-01 | 2011-06-01 | 32500 | 0 | 32500 | 32500 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | ASP | CKI | SEV | 62 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-09-01 | 2012-12-01 |  | 2012-12-01 | 2013-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV: 1/2013-12/2014) | Individual | ASP | CKI | SEV | 67 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2013-12-01 | 2014-12-01 |  | 2014-12-01 | 2015-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of the institutional strengthening project (phase V: 1/2015-12/2016) | Individual | ASP | CKI | SEV | 72 | INS | 10 | A | I |  | 0 |  | 0 |  | 2014-05-01 | 2015-07-01 | 2016-12-01 | 2017-06-01 |  |  | 60000 | 0 | 60000 | 44307.14 | 73.85% | 15692.86 | 15692.86 | 1569.286 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The NOU has been responsible for the management of all Montreal Protocol activities. The operation of the NOU was going on well. The license/quota system has been enforced in 2016. NOU also coordinated and facilitated the implementation of HPMP and ODS Alternative Survey. The NOU also organized the 2016 ozone day celebration, and actively joined the regional and global ozone related meetings e.g. the network meeting, OEWG and the MOP meetings. 2015 Article 7 and CP data were submitted to the Ozone Secretariat and MLFS respectively. Legal arrangements(actual/planned): The SSFA was signed April 2015. _Initial stages of project implementation(actual/planned): Jan/Apr 2015_ Intermediate goals achieved (actual/planned): _Project progressing Satisfactorily, Compliance (2015) sustained . Project completion and follow up: Not applicable. First disbursement date (actual/planned):July 2015. _ All funds disbursed (yes/no): No. Any delay?(yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): Only the fifth (final) payment is to be disbursed to the country upon completion of the IS project phase V. However, there has been no assigned NOO in the country since February 2017. UNEP is engaging the senior management level to agree on the way forward on the filling of NOO Post. IS was renewed at the 77 Ex. com
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | ASP | CKI | SEV | 75 | TAS | 12 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-07-01 | 2016-12-01 | 2017-06-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 25000 | 4000 | 5200 | 0 | 0 | 5200 | 3250 | Brief progress report (actual/planned): The SSFA was signed by UNEP and the Government of Cook Islands in April 2016. The first payment was made to the country in July 2016. NOO attended the training for conducting natiional surveys as part of Thematic workshop for Asia and the Pacific in June 2016. The national stakeholder workshop and a separate meeting with the Customs Department and Statistic Office were organzied during UNEP mission in September 2016. A regional expert was appointed by UNEP to provide support to the NOO in the planned, data collection and preparation of report. The survey methodology and questionnaire have been finalized and agreed. The data collection was on-going. Legal arrangements(actual/planned): The SSFA was signed in April 2016 Initial stages of project implementation(actual/planned): April 2016 . Intermediate goals achieved (actual/planned): Not applicable. Project completion and follow up: Not applicable. First disbursement date (actual/planned): July 2016. All funds disbursed (yes/no): No. Any delay?(yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): NOU with assistance of UNEP and regional consultant is conducting the data survey to identify the current use of ODS alternatives by substance/sector and collection of import/export data for the substances for the past a couple of years. The regional consultant conducted a mission in January 2017 to support the NOO to lead the data collection. However, there has been no assigned NOO in the country since February 2017. UNEP is engaging the senior management level to agree on the way forward to expedite implementation.
ONG | UNEP | Extension of the institutional strengthening project (phase VI: 1/2017-12/2018) | Individual | ASP | CKI | SEV | 77 | INS | 13 | A | I |  | 0 |  | 0 |  | 2016-12-01 |  | 2018-12-01 | 2018-12-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The project was approved at the 77th ExCom Meeting in December 2016. UNEP initiated the discussion with the NOU on the preparation of the SSFA. Legal arrangements(actual/planned): Not yet Initial stages of project implementation(actual/planned): Not yet Intermediate goals achieved (actual/planned): Not yet Project completion and follow up: Not applicable. First disbursement date (actual/planned): Not yet. All funds disbursed (yes/no): _No__ Any delay?(yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): There has been no assigned NOO in the country since February 2017. UNEP is engaging the senior management level to agree on the way forward to expedite implementation and including closure of old phase.
FIN | UNIDO | Phasing out CFC-11 at Scimpos | Individual | AFR | CMR | FOA | 23 | INV | 10 | A | I | CFC | 120 | 120 |  |  | 1997-11-01 | 1998-06-01 | 1998-12-01 |  | 2002-06-01 | 2003-06-01 | 541350 | -491 | 540859 | 540859.12 | 100% | -0.12 | 0 |  | 70376 | -176 | 70200 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Sonopol | Individual | AFR | CMR | FOA | 23 | INV | 11 | A | I | CFC | 130 | 130 |  |  | 1997-11-01 | 1998-06-01 | 1998-12-01 |  | 2002-06-01 | 2003-02-01 | 506310 | 0 | 506310 | 506309.62 | 100% | 0.38 | 0 |  | 65820 | -30 | 65790 | 0 | 0 | FIN
FIN | UNIDO | Preparation of demonstration project (tobacco, tomatoes, strawberries) | Individual | AFR | CMR | FUM | 24 | PRP | 13 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-05-01 | 1999-04-01 |  | 1998-05-01 | 2001-07-01 | 25000 | -1950 | 23050 | 23050 | 100% | 0 | 0 |  | 3250 | -258 | 2992 | 0 | 0 | FIN
FIN | UNIDO | Two alternatives to the use of methyl bromide: non-soil cultivation techniques and application of various mixtures of other chemicals in low doses in tobacco | Individual | AFR | CMR | FUM | 25 | DEM | 16 | A | I | MBR | 0 | 0 |  |  | 1998-07-01 | 1999-03-01 | 2000-08-01 |  | 2004-12-01 | 2005-12-01 | 160600 | -1033 | 159567 | 159566.82 | 100% | 0.18 | 0 |  | 20878 | -167 | 20711 | 0 | 0 | FIN
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organizations in methyl bromide communication | Individual | AFR | CMR | FUM | 34 | TAS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-01-01 | 2002-07-01 |  | 2003-07-01 | 2004-07-01 | 25000 | -10136 | 14864 | 14864 | 100% | 0 | 0 |  | 3250 | -1317.68 | 1932.32 | 0 | 0
FIN | UNIDO | Project preparation for the total phase-out of methyl bromide in all remaining uses | Individual | AFR | CMR | FUM | 50 | PRP | 25 | A | I |  | 0 | 0 |  |  | 2006-11-01 | 2007-03-01 | 2007-11-01 |  | 2007-12-01 | 2008-06-01 | 30000 | -60 | 29940 | 29939.69 | 100% | 0.31 | 0 |  | 2250 | -4 | 2245 | 1 | 0 | FIN |  |  |  | NON-INV
FIN | Italy | Total phase-out of methyl bromide used in stored commodities fumigation | Individual | AFR | CMR | FUM | 52 | INV | 27 | A | I | MBR | 14.5 | 14.5 | 0 |  | 2007-07-01 | 2008-04-01 | 2010-12-01 |  | 2011-12-01 | 2014-12-01 | 259713 | -2677 | 257036 | 257036 | 100% | 0 | 0 | 0 | 33763 | -348 | 33415 | 0 | 0 | Refund was reported to 74th ExCom, May 2015. FIN. | Balances (and interests accrued) have been reported to the 77th ExCom and have been returned in cash in April 2017 in light of ExCom decision 77/2(a)(iii) | 2007 |  | Investment
FIN | UNIDO | Project preparation for a terminal phase-out management plan | Individual | AFR | CMR | PHA | 49 | PRP | 24 | A | I |  | 0 | 0 |  |  | 2006-07-01 | 2006-08-01 | 2007-07-01 |  | 2006-11-01 | 2007-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 2250 | 0 | 2250 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Terminal CFC/TCA phase-out management plan (first tranche) | Multi-Year | AFR | CMR | PHA | 50 | INV | 26 | A | I | CFC TCA | 12.7 | 12.7 |  |  | 2006-11-01 | 2007-01-01 | 2008-07-01 |  | 2008-12-01 | 2011-12-01 | 600000 | -486 | 599514 | 599514.01 | 100% | -0.01 | 0 |  | 45000 | -36 | 44964 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal CFC/TCA phase-out management plan (second tranche) | Multi-Year | AFR | CMR | PHA | 54 | INV | 29 | A | I | CFC CTC | 13.9 | 13.9 |  |  | 2008-04-01 | 2009-02-01 | 2009-03-31 |  | 2009-12-01 | 2010-12-01 | 105000 | -1 | 104999 | 104999.08 | 100% | -0.08 | 0 |  | 7875 | 0 | 7875 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | AFR | CMR | PHA | 55 | PRP | 30 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 |  | 2011-12-01 | 2012-12-01 | 85000 | -3079 | 81921 | 81920.91 | 100% | 0.09 | 0 |  | 6375 | -231 | 6144 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Terminal CFC/TCA phase-out management plan (third tranche) | Multi-Year | AFR | CMR | PHA | 58 | INV | 31 | A | I | CFC TCA | 24 | 24 |  |  | 2009-07-01 | 2010-11-01 | 2010-07-31 |  | 2011-12-01 | 2012-12-01 | 95000 | -1572 | 93428 | 93428.21 | 100% | -0.21 | 0 |  | 7125 | -118 | 7007 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan (additional funding) | Individual | AFR | CMR | PHA | 58 | PRP | 32 | A | I |  | 0 | 0 |  |  | 2009-07-01 | 2010-09-01 | 2010-07-31 |  | 2011-12-01 | 2011-12-01 | 65000 | -364 | 64636 | 64636.28 | 100% | -0.28 | 0 |  | 4875 | -27 | 4848 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (foam sector plan) | Multi-Year | AFR | CMR | PHA | 64 | INV | 34 | A | I | HCFC | 15.7 | 15.7 |  |  | 2011-07-01 | 2012-04-01 | 2015-07-31 | 2017-12-17 |  |  | 310900 | 0 | 310900 | 288144.65 | 92.68% | 22755.35 | 12274.17 | 22000 | 23318 | 0 | 21611 | 1707 | 921 | The foam component project activities were completed, however, due to interrelation of the awareness activities on alternatives for the foam sector with the other tranches, the uncommitted balance will be used for such activities in 2017, using the flexibility principle of the HPMP implementation. Was there any delay during the reporting year? Yes, reason above Any recurring problem? No Any impact on project completion date: Yes Any action required by Executive Committee? No | Remaining available budget to be used for awareness activities in correlation with the other HPMPs tranches. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector plan) | Multi-Year | AFR | CMR | PHA | 64 | INV | 35 | A | I | HCFC | 6.4 | 6.4 |  |  | 2011-07-01 | 2011-12-01 | 2015-07-31 | 2017-12-17 |  |  | 573553 | 0 | 573553 | 506143.22 | 88.25% | 67409.78 | 6360.18 | 50000 | 43016 | 0 | 37961 | 5055 | 477 | - ToR for equipment purchase for servicing sector agreed with counterpart upon training activities outcome. - Bidding for contract with supplier for equipment purchase has been re-organized second half of 2016 - Equipment delivery was rescheduled to 2017 Milestones achieved: Milestone 1: Equipment purchase contract release - No Milestone 2: Equipment delivery - No Activities planned but not implemented, reasons and strategy: Purchasing process has been re-organized due to limited offers received. It is expected to expedite the purchase and the equipment and distribution in 2017. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Rebidding procedure caused 6 months delay in achieving equipment commissioning related training. Work plan was developed and tranche implementation will be completed first half of 2017. Any recurring problem? No Any impact on project completion date: No, the tranche will be operationally completed in 2017. Any action required by Executive Committee? No | ToR for equipment to be purchased has been reviewed in light of efficient use of the available budget for such purpose under tranches I and III. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No, the tranche will be operationally completed in 2017. Any action required by Executive Committee? No |  |  | INV |  | To request the submission of additional status report to the 79th meeting to monitor the procurement and/or delivery of the equipment.
ONG | UNIDO | HCFC phase-out management plan (refrigeration servicing sector plan) (stage I, second tranche) | Multi-Year | AFR | CMR | PHA | 71 | INV | 38 | A | I | HCFC | 2 | 0 |  |  | 2013-12-01 | 2014-11-01 | 2015-12-31 | 2017-12-17 |  |  | 180000 | 0 | 180000 | 166295.11 | 92.39% | 13704.89 | 0 | 13000 | 13500 | 0 | 12472 | 1028 | 0 | Tranche II activities were planned to cover mainly non-investment activities in servicing sector. Local contractual arrangements were executed in 2016, addressing training and certification of technicians in servicing sector, training of customs officers, legislation review, monitoring of quota system. Activities were executed successfully and operational completion has been achieved. Remaining funds will be used for conducting verification report in connection with 2016 consumption in view of submitting the request for the last tranche approval. Milestones achieved: Milestone 1: ToR for additional training in servicing sector - Yes Milestone 2: Training activities in servicing sector - Yes Milestone 3: Verification report for the consumption data for the years 2015 - 2016 - pending Activities planned but not implemented, reasons and strategy: data verification report for the year 2016 can be executed only in 2017, when the data for previous year becomes available. Actions towards next goals: NC contractual arrangement for data verification report to be settled first quarter 2017. Was there any delay during the reporting year? Yes, new planned completion date is in 2017, due to the need of compiling data verification report for the 2016 HCFCs consumption. Any impact on project completion date: Yes, slight delay as explained above. | NC for verification report was identified by NOU and contractual arrangements are in process as of April 2017. The verification report budget will be executed as planned, until mid 2017. Completion of the tranche II implementation will be achieved during 2017. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No, the tranche will be operationally completed in 2017. Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | Individual | AFR | CMR | PHA | 75 | PRP | 40 | A | I |  | 0 | 0 |  |  | 2015-11-01 | 2016-12-01 | 2017-12-01 | 2018-04-17 |  |  | 70000 | 0 | 70000 | 11403.31 | 16.29% | 58596.69 | 3153.37 | 30000 | 4900 | 0 | 0 | 4900 | 220.7359 | Substantial progress has been achieved in preparation of HPMP Stage II for Cameroon, that will cover the period 2018 - 2025. NCs were appointed for data collection. IC has been contracted to technically assist with the identification of priorities for HPMP Stage II. Draft of HPMP Stage II is completed and it is undergoing the review process with national relevant stakeholders. | Draft of HPMP Stage II is completed and has been submitted for review process to the national relevant stakeholders. |  |  | NON-INV
ONG | UNIDO | HCFC phase-out management plan (refrigeration servicing sector plan) (stage I, third tranche) | Multi-Year | AFR | CMR | PHA | 76 | INV | 42 | A | I |  | 0 | 0 |  |  | 2016-05-01 |  | 2019-05-31 | 2019-07-01 |  |  | 59136 | 0 | 59136 | 0 | 0% | 59136 | 0 | 10000 | 4435 | 0 | 0 | 4435 | 0 | The tranche was approved in 2016 at the 76th Meeting of the ExzCom. Third tranche activities were planned to purchase the equipment for trained and certified technicians/companies in servicing sector. ToR has been developed and reviewed in 2016, in order to efficiently use the funding jointly with the equipment component budget of the tranche I. List of end-users entitled to receive equipment (upon completion of certification) has been compiled by NOU and National Consultants. - Equipment delivery is scheduled third quarter of 2017 Milestones achieved: Milestone 1: Equipment purchase technical specification development - yes Milestone 2: Equipment delivery - No Activities planned but not implemented, reasons and strategy: equipment budget component of tranche one has been insufficient to cover the needs in the country. It has been decided to re-organize bidding using budget of tranche I and tranche III to compensate and efficiently organize the purchase. NOU compiled selection criteria for servicing sector companies to receive recovery/recycling equipment Was there any delay during the reporting year? Yes, If yes, reasons and action plan: Rebidding procedure caused delay in achieving equipment commissioning under tranche I. Any recurring problem? No Any impact on project completion date: No If yes, implications: No Instead of July 2015, the tranche will be operationally completed in 2017. | Revised technical specifications for equipment purchase and criteria for selecting servicing sector companies for receiving recovery/recycling equipment have been developed during the first quarter of 2017. Equipment delivery is scheduled third quarter of 2017. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No, the tranche will be operationally completed in 2017. Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Preparation of an investment project proposal for phase out of CFCs at FAEM, Cameroun | Individual | AFR | CMR | REF | 11 | PRP | 04 | A | I |  | 0 | 0 |  |  | 1993-11-01 | 1994-04-01 | 1994-11-01 |  | 1995-02-01 | 1998-08-01 | 20000 | -2046 | 17954 | 17954 | 100% | 0 | 0 |  | 2600 | -270 | 2330 | 0 | 0 | FIN
FIN | UNIDO | Phase out of CFC at FAEM.SA | Individual | AFR | CMR | REF | 13 | INV | 05 | A | I | CFC | 62 | 62 |  |  | 1994-07-01 | 1995-11-01 | 1996-01-01 |  | 1996-06-01 | 2000-04-01 | 1935860 | -42791 | 1893069 | 1893069 | 100% | 0 | 0 |  | 251662 | -5953 | 245709 | 0 | 0 | FIN
FIN | UNIDO | Preparation of project for phasing out CFC-11 in the manufacture of domestic refrigerators, freezers and air-conditioners at Union Camerounaise | Individual | AFR | CMR | REF | 15 | PRP | 06 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1996-02-01 | 1995-06-01 |  | 1996-06-01 | 1998-04-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs at Union Camerounaise d'Entreprise | Individual | AFR | CMR | REF | 18 | INV | 07 | A | I | CFC | 115.1 | 115.1 |  |  | 1995-11-01 | 1996-12-01 | 1997-03-01 |  | 2001-12-01 | 2002-12-01 | 1321400 | -20877 | 1300523 | 1300522.5 | 100% | 0.5 | 0 |  | 171782 | -2982 | 168800 | 0 | 0 | FIN
FIN | UNIDO | Preparation of refrigerant management plan | Individual | AFR | CMR | REF | 24 | PRP | 12 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1999-02-01 | 1999-04-01 |  | 2001-04-01 | 2001-11-01 | 30000 | -65 | 29935 | 29934.63 | 100% | 0.37 | 0 |  | 3900 | -15 | 3885 | 0 | 0 | FIN |  |  | 1999-05-01
FIN | UNIDO | Refrigerant management plan to phase out the use of ODS in the refrigeration servicing sector (includes: training in good refrigerant management practices, training of customs officers, and recovery and recycling programme) | Individual | AFR | CMR | REF | 38 | TAS | 18 | A | I | CFC | 218.4 | 218.4 |  |  | 2002-11-01 | 2003-03-01 | 2007-12-01 |  | 2007-06-01 | 2008-05-01 | 522982 | 0 | 522982 | 522982.01 | 100% | -0.01 | 0 |  | 67528 | 0 | 67528 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project preparation in the refrigeration sector | Individual | AFR | CMR | REF | 43 | PRP | 20 | A | I |  | 0 | 0 |  |  | 2004-07-01 | 2005-03-01 | 2005-07-01 |  | 2006-06-01 | 2006-12-01 | 25000 | -174 | 24826 | 24826.38 | 100% | -0.38 | 0 |  | 1875 | -13 | 1862 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNEP | Country programme preparation | Individual | AFR | CMR | SEV | 06 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-04-01 | 1993-06-01 |  | 1993-06-01 | 1993-12-01 | 30000 | 3000 | 33000 | 33000 | 100% | 0 | 0 |  | 3900 | 390 | 4290 | 0 | 0
FIN | UNEP | Workshop on monitoring and control of ODS consumption (customs officers) | Individual | AFR | CMR | SEV | 10 | TRA | 02 | A | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-08-01 | 1994-05-01 |  | 1994-08-01 | 1994-12-01 | 20200 | 0 | 20200 | 20200 | 100% | 0 | 0 |  | 2626 | 0 | 2626 | 0 | 0
FIN | UNEP | Establishment of the National Ozone Monitoring Commission | Individual | AFR | CMR | SEV | 11 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-10-01 | 1996-11-01 |  | 1997-10-01 | 1997-06-01 | 161000 | 0 | 161000 | 161000 | 100% | 0 | 0 |  | 20930 | 0 | 20930 | 0 | 0
CLO | UNIDO | Project formulation of investment projects in the foam and refrigeration sectors | Individual | AFR | CMR | SEV | 21 | PRP | 08 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-04-01 | 1998-02-01 |  |  | 2001-07-01 | 50000 | -23644 | 26356 | 26356.43 | 100% | -0.43 | 0 |  | 6500 | -3079 | 3421 | 0 | 0 | CLO
FIN | UNEP | Institutional strengthening renewal | Individual | AFR | CMR | SEV | 22 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-07-01 | 1999-06-01 |  | 1999-12-01 | 2000-01-01 | 107000 | 0 | 107000 | 107000 | 100% | 0 | 0 |  | 13910 | 0 | 13910 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening (phase III) | Individual | AFR | CMR | SEV | 28 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-01-01 | 2001-08-01 |  | 2003-12-01 | 2004-12-01 | 107000 | 0 | 107000 | 107000 | 100% | 0 | 0 |  | 13910 | 0 | 13910 | 0 | 0
FIN | UNEP | Policy and technical assistance | Individual | AFR | CMR | SEV | 37 | TAS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-05-01 | 2003-08-01 |  | 2004-07-01 | 2007-07-01 | 10000 | -1994 | 8006 | 8006 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project: phase 4 | Individual | AFR | CMR | SEV | 41 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-03-01 | 2004-12-01 |  | 2004-12-01 | 2005-12-01 | 69766 | 0 | 69766 | 69766 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (second year of phase IV) | Individual | AFR | CMR | SEV | 44 | INS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2005-12-01 |  | 2005-12-01 | 2007-02-01 | 69766 | 0 | 69766 | 69766 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project: phase V | Individual | AFR | CMR | SEV | 47 | INS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-03-01 | 2007-12-01 |  | 2007-12-01 | 2008-12-01 | 139532 | 0 | 139532 | 139532 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase VI) | Individual | AFR | CMR | SEV | 53 | INS | 28 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-11-01 |  | 2009-11-01 | 2010-12-01 | 139532 | 0 | 139532 | 139532 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase VII) | Individual | AFR | CMR | SEV | 59 | INS | 33 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-05-01 | 2011-12-01 |  | 2012-12-01 | 2013-12-01 | 69766 | 69766 | 139532 | 139532 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase VIII: 1/2012-12/2013) | Individual | AFR | CMR | SEV | 65 | INS | 36 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-05-01 | 2013-12-01 |  | 2013-12-01 | 2014-12-01 | 139532 | 0 | 139532 | 139532 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of institutional strengthening project (phase IX: 1/2014-12/2015) | Individual | AFR | CMR | SEV | 71 | INS | 37 | A | I |  | 0 |  | 0 |  | 2013-12-01 | 2014-05-01 | 2015-12-01 |  | 2015-12-01 |  | 139532 | 0 | 139532 | 109766 | 78.67% | 29766 | 29766 | 29766 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): All payments done. Final payment sent to the country in January 2016. Project financially closed. Art5 data report for 2015 and CP data for 2015 have been provided in May 2016. Legal arrangements (actual/planned): Agreement signed in April 2014. All activities under the SSFA are completed (as planned) YES___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in April 2014 __ All funds disbursed (yes/no): _ Final payment january 2016_ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Brief progress report (actual/planned): Legal arrangements (actual/planned): Agreement signed in April 2014. Final payment sent to the country in January 2016. Project completed. All payments done. Art5 data report for 2015 and CP data for 2015 have been provided in May 2016. All activities under the SSFA are completed (as planned) YES___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in April 2014 __ All funds disbursed (yes/no): _ Final payment january 2016_ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
ONG | UNEP | Extension of institutional strengthening project (phase X: 1/2016-12/2017) | Individual | AFR | CMR | SEV | 75 | INS | 39 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-04-01 | 2017-12-01 | 2017-12-01 |  |  | 178601 | 0 | 178601 | 0 | 0% | 178601 | 178601 | 17860.1 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Country signed the SSFA in March 2016. First payment sent in April 2016. Art5 data report for 2015 and CP data for 2015 have been provided in May 2016. Legal arrangements (actual/planned): Agreement signed in March 2016. All activities under the SSFA are completed (as planned) no___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in April 2016 __ All funds disbursed (yes/no): _ Final payment no_ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Brief progress report (actual/planned): Country signed the SSFA in March 2016. First payment sent in April 2016. Art5 data report for 2015 and CP data for 2015 have been provided in May 2016. Legal arrangements (actual/planned): Agreement signed in March 2016. NOU trained 60 enforcement officers and 270 RAC technicians. All activities under the SSFA are completed (as planned) no___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in April 2016 __ All funds disbursed (yes/no): _ Final payment no_ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
ONG | UNIDO | Survey of ODS alternatives at the national level | Individual | AFR | CMR | SEV | 75 | TAS | 41 | A | I |  | 0 | 0 |  |  | 2015-11-01 | 2016-05-01 | 2017-12-01 | 2017-12-01 |  |  | 110000 | 0 | 110000 | 18601.8 | 16.91% | 91398.2 | 30000 | 50000 | 9900 | 0 | 0 | 9900 | 2700 | Contract on national execution arrangement for data collection process was agreed with NOU. IC services to assist the data assessment process was concluded. Activities are under implementation and the project will be operationally completed until June 2017. | Draft Survey data were submitted for review to relevant stakeholders at national level. It is expected that project will be completed during the current year as planned. |  |  | NON-INV
FIN | UNEP | Project preparation for a TPMP | Individual | AFR | COI | PHA | 47 | PRP | 11 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2007-05-01 | 2006-12-01 |  | 2008-12-01 | 2009-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | COI | PHA | 52 | INV | 14 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-11-01 | 2009-07-01 |  | 2010-07-01 | 2013-01-01 | 43000 | 0 | 43000 | 43000 | 100% | 0 | 0 | 0 | 3870 | 0 | 3870 | 0 | 0 | Financially completed in 2013. |  | 2007 |  | Investment
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-year | AFR | COI | PHA | 52 | TAS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-10-01 | 2008-07-01 |  | 2009-07-01 | 2011-12-01 | 77000 | -5978 | 71022 | 71022 | 100% | 0 | 0 |  | 10010 | -777.14 | 9232.86 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | COI | PHA | 55 | PRP | 15 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-04-01 | 2009-07-01 |  | 2011-11-01 | 2012-11-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 |  | 11050 | 0 | 11050 | 0 | 0
FIN | UNDP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | COI | PHA | 56 | INV | 17 | N | I | CFC | 0.4 | 0.4 | 0 | 0 | 2008-11-01 | 2010-01-01 | 2009-11-01 |  | 2010-12-01 | 2013-01-01 | 32000 | -719.78 | 31280.22 | 31280 | 100% | 0.22 | 0 | 0 | 2880 | -64.78 | 2815.2 | 0.02 | 0 | Financially completed in 2013. |  | 2008 |  | Investment
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | COI | PHA | 56 | TAS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-08-01 | 2009-11-01 |  | 2011-12-01 | 2012-12-01 | 53000 | 0 | 53000 | 53000 | 100% | 0 | 0 |  | 6890 | 0 | 6890 | 0 | 0
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | AFR | COI | PHA | 64 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-07-01 | 2013-07-01 |  | 2013-09-01 | 2014-12-01 | 44000 | 0 | 44000 | 44000 | 100% | 0 | 0 |  | 5720 | 0 | 5720 | 0 | 0
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | AFR | COI | PHA | 70 | TAS | 21 | A | I |  | 0 |  | 0 |  | 2013-07-01 | 2016-01-01 | 2016-07-01 | 2017-12-01 |  |  | 35000 | 0 | 35000 | 29.85 | 0.08529% | 34970.15 | 21000 | 3497.015 | 4550 | 0 | 3.8805 | 4546.1195 | 2730 | Brief progress report (actual/planned): SSFA signed by the country in April 2015. First payment sent in January 2016. Country organized 2 workshop trainings for 50 refrigeration technicians in 2016. Country also organized 2 workshop trainings for 60 customs officers in 2016. Legal arrangements (actual/planned): Agreement signed in April 2015. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A _ TOR completed (actual/planned): _ N/A __ First disbursement date (actual/planned): _1st disbursement planned in Jan. 2016 __ All funds disbursed (yes/no): _ No__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a __ | Brief progress report (actual/planned): SSFA signed by the country in April 2015. First payment sent in January 2016. Country organized 2 workshop trainings for 50 refrigeration technicians in 2016. Country also organized 2 workshop trainings for 60 customs officers in 2016. Legal arrangements (actual/planned): Agreement signed in April 2015. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A _ TOR completed (actual/planned): _ N/A __ First disbursement date (actual/planned): _1st disbursement planned in Jan. 2016 __ All funds disbursed (yes/no): _ No__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a __
ONG | UNEP | HCFC phase-out management plan (stage I, third tranche) | Multi-year | AFR | COI | PHA | 77 | TAS | 25 | A | I |  | 0 |  | 0 |  | 2016-12-01 |  | 2018-12-01 | 2018-12-01 |  |  | 35000 | 0 | 35000 | 0 | 0% | 35000 | 0 | 3500 | 4550 | 0 | 0 | 4550 | 0 | Newly approved project | Brief progress report (actual/planned): Project newly approved. Agreement not signed yet. Legal arrangements (actual/planned): Agreement not signed yet. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement _no __ All funds disbursed (yes/no): _ Final payment _no_4.__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
FIN | UNEP | Preparation of a refrigerant management plan | RMP | AFR | COI | REF | 27 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-09-01 | 2000-04-01 |  | 2001-09-01 | 2001-07-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Implementation of the RMP: monitoring of RMP implementation and its impact in the service and end-users sectors | Individual | AFR | COI | REF | 35 | TAS | 05 | A | I | CFC | 0.3 | 0 | 0 | 0 | 2001-12-01 | 2005-04-01 | 2005-12-01 |  | 2006-07-01 | 2008-09-01 | 18000 | -2000 | 16000 | 16000 | 100% | 0 | 0 |  | 2340 | -260 | 2080 | 0 | 0
FIN | UNEP | Implementation of the RMP: assessment of the end-users subsector | Individual | AFR | COI | REF | 35 | TAS | 06 | A | I | CFC | 0.5 | 0 | 0 | 0 | 2001-12-01 | 2004-03-01 | 2005-12-01 |  | 2005-06-01 | 2006-06-01 | 30000 | -2218 | 27782 | 27782 | 100% | 0 | 0 |  | 3900 | -289 | 3611 | 0 | 0
FIN | UNEP | Implementation of the RMP: train the trainer and training of refrigeration service technicians | Individual | AFR | COI | REF | 35 | TRA | 07 | A | I | CFC | 0.8 | 0 | 0 | 0 | 2001-12-01 | 2002-10-01 | 2002-07-01 |  | 2003-12-01 | 2005-12-01 | 51000 | -7093 | 43907 | 43907 | 100% | 0 | 0 |  | 6630 | -922.09 | 5707.91 | 0 | 0
FIN | UNEP | Implementation of the RMP: training of customs officers in identification and control of ODS imports | Individual | AFR | COI | REF | 35 | TRA | 08 | A | I | CFC | 0.6 | 0 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2002-07-01 |  | 2003-12-01 | 2006-06-01 | 39000 | -13386 | 25614 | 25614 | 100% | 0 | 0 |  | 5070 | -1740 | 3330 | 0 | 0
FIN | UNEP | Country programme preparation | Individual | AFR | COI | SEV | 19 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-08-01 |  | 1997-11-01 | 1999-01-01 | 33000 | 0 | 33000 | 33000 | 100% | 0 | 0 |  | 4290 | 0 | 4290 | 0 | 0
FIN | UNEP | Establishment of the National Ozone Unit | Individual | AFR | COI | SEV | 23 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 2000-12-01 |  | 2001-03-01 | 2001-12-01 | 27800 | 0 | 27800 | 27800 | 100% | 0 | 0 |  | 3614 | 0 | 3614 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening | Individual | AFR | COI | SEV | 32 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2003-01-01 |  | 2003-04-01 | 2003-12-01 | 18533 | 0 | 18533 | 18533 | 100% | 0 | 0 |  | 2409 | 0 | 2409 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase 3) | Individual | AFR | COI | SEV | 39 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-07-01 | 2005-04-01 |  | 2005-04-01 | 2006-12-01 | 24093 | 0 | 24093 | 24093 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | COI | SEV | 45 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-07-01 | 2007-04-01 |  | 2008-04-01 | 2009-04-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | AFR | COI | SEV | 51 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2007-03-01 | 2007-05-01 | 2009-03-01 |  | 2009-03-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VI) | Individual | AFR | COI | SEV | 57 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-12-01 | 2011-03-01 |  | 2011-03-01 | 2011-07-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VII: 7/2011-6/2013) | Individual | AFR | COI | SEV | 64 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2011-11-01 | 2013-06-01 |  | 2013-07-01 |  | 60000 | 0 | 60000 | 59999.58 | 100% | 0.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of the institutional strengthening project (phase VIII: 7/2013-6/2015) | Individual | AFR | COI | SEV | 70 | INS | 22 | A | I |  | 0 |  | 0 |  | 2013-07-01 | 2014-06-01 | 2015-06-01 |  | 2015-12-01 |  | 60000 | 0 | 60000 | 10128 | 16.88% | 49872 | 36000 | 36000 | 0 | 0 | 0 | 0 | 0 | Project completed | Project completed
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | AFR | COI | SEV | 74 | TAS | 23 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-04-01 | 2016-05-01 | 2017-10-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 15000 | 4000 | 5200 | 0 | 0 | 5200 | 1950 | Brief progress report (actual/planned): SSFA signed in November 2015__ First payment sent to the Country in April 2016. Country hired consultants to conduct the ODS survey. Legal arrangements (actual/planned): signed in November 2015 (Yes/No): No_ First mission (actual/planned): __n/a_ TOR completed (actual/planned): _N/A__ First disbursement date (actual/planned): April 2016___ All funds disbursed (yes/no): _NO__ any delay? (yes/no): _YES_ If Yes, reasons for delay & action plan to resolve: NO__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): SSFA signed in November 2015__ First payment sent to the Country in April 2016. Country sent the draft ODS survey report in January 2017. Legal arrangements (actual/planned): signed in November 2015 (Yes/No): No_ First mission (actual/planned): __n/a_ TOR completed (actual/planned): _N/A__ First disbursement date (actual/planned): April 2016___ All funds disbursed (yes/no): _NO__ any delay? (yes/no): _YES_ If Yes, reasons for delay & action plan to resolve: NO__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__
ONG | UNEP | Extension of the institutional strengthening project (phase IX: 1/2016-6/2017) | Individual | AFR | COI | SEV | 75 | INS | 24 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-04-01 | 2017-12-01 | 2017-12-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 85000 | 8500 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Country signed the SSFA in February 2016; Country reported 2015 CP data and 2015 Art7 data r. Legal arrangements (actual/planned): Agreement signed in February 2016. First payment: April 2016. All activities under the SSFA are completed (as planned) _No _First mission (actual/planned): _ N/A -TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in April 2016__ All funds disbursed (yes/no): _ No__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Brief progress report (actual/planned): Country signed the SSFA in February 2016; Country reported 2016 CP data and 2016 Art7 data r. Legal arrangements (actual/planned): Agreement signed in February 2016. First payment: April 2016. All activities under the SSFA are completed (as planned) _No _First mission (actual/planned): _ N/A -TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in April 2016__ All funds disbursed (yes/no): _ No__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
FIN | UNDP | Project preparation for a MDI investment project | Individual | LAC | COL | ARS | 54 | PRP | 68 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-05-01 | 2009-03-01 |  | 2008-12-01 | 2011-11-01 | 30000 | -3478 | 26522 | 26522 | 100% | 0 | 0 | 0 | 2250 | -260.85 | 1989.15 | 0 | 0 | Completed in 2008. |  | 2008 |  | Investment
FIN | UNDP | Phase-out of CFC in the manufacturing of MDIs | Individual | LAC | COL | ARS | 56 | INV | 71 | N | I | CFC | 7.4 | 7.4 | 0 | 0 | 2008-11-01 | 2010-09-01 | 2011-11-01 |  | 2012-09-01 | 2013-07-01 | 409359 | -5.96 | 409353.04 | 409353 | 100% | 0.04 | 0 | 0 | 30701 | 0 | 30700.997 | 0.003 | 0 | Financially completed in 2013. | Completed in 2012. No activities in 2013. | 2008 |  | Investment
FIN | UNDP | Preparation for pilot demonstration project on ODS waste management and disposal | Individual | LAC | COL | DES | 59 | PRP | 74 | N | I | ODS-Waste | 0 | 0 | 0 | 0 | 2009-11-01 | 2011-04-01 | 2010-11-01 |  | 2011-12-01 | 2012-08-01 | 40000 | -8674.08 | 31325.92 | 31326 | 100% | -0.08 | 0 | 0 | 3000 | -650.56 | 2349.45 | -0.01 | 0 | Financially completed in 2012. | Project finalized and submitted to the 66th Executive Committee Meeting. Final invoices pending. | 2009 |  | Investment
ONG | UNDP | Demonstration project on end of life ODS management and destruction | Individual | LAC | COL | DES | 66 | DEM | 82 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-04-01 | 2012-09-01 | 2015-04-01 | 2017-10-01 |  |  | 1195000 | 0 | 1195000 | 787322.04 | 65.88% | 407677.96 | 0 | 163071.184 | 89625 | 0 | 59049.153 | 30575.847 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): The planned second burning test was conducted, collected data was analyzed by the international expert. Prodoc signed (actual/planned, yes/no and date):The agreement has been signed earlier. Missions undertaken (actual/planned):1 of 1 TOR for consultants/subcontracts completed (actual/planned): TOR completed earlier. Contract/PO/MOA agreements signed: The agreement has been signed earlier First disbursement date (actual/planned): 42990Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve:N/A | Work plan prepared, support requirements of the international expert were discussed. | 2012 |  | Investment
FIN | UNDP | Elimination of the use of CFC in the polystyrene foam sector at Manufacturas Ajover Ltda. | Individual | LAC | COL | FOA | 13 | INV | 09 | A | I | CFC | 190 | 190 | 0 | 0 | 1994-07-01 | 1995-09-01 | 1995-07-01 |  | 1998-12-01 | 2001-12-01 | 691500 | -22425 | 669075 | 669075 | 100% | 0 | 0 | 0 | 89895 | -2915 | 86980 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1994 |  | Investment
CLO | UNDP | Elimination of the use of CFC in the polystyrene foam sector at Industria Nacional de Desechables (Inaldes) | Individual | LAC | COL | FOA | 13 | INV | 10 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 | 1995-09-01 | 1995-07-01 |  |  | 2001-12-01 | 380500 | -373255 | 7245 | 7245 | 100% | 0 | 0 | 0 | 49465 | -48523 | 942 | 0 | 0 | Canceled in 2001. Financially completed in 2001. |  | 1994 | 2000-03-01 | Investment
FIN | UNDP | Project preparation for 2 projects in the foam sector | Individual | LAC | COL | FOA | 24 | PRP | 26 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-07-01 | 1998-12-01 |  | 1999-12-01 | 2000-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1998 |  | Investment
FIN | IBRD | Elimination of CFC-11 in the manufacture of rigid polyurethane foam through the use of HCFC-141b technology at Daniel J. Fernandez and Cia. Ltd. | Individual | LAC | COL | FOA | 26 | INV | 28 | N | I | CFC | 22.2 | 22.2 | 0 | 0 | 1998-11-01 | 2000-12-01 | 2000-12-01 |  | 2002-02-01 | 2002-05-01 | 173822 | 0 | 173822 | 173822 | 100% | 0 | 0 |  | 22596.86 | 0 | 22596.86 | 0 | 0 | Project has been fully executed. PCR is being revised for submission. |  |  |  | INV | 0
FIN | IBRD | Elimination of CFC-11 in manufacture of rigid polyurethane foam through the use of HCFC-141b technology at Friotermica S.A. | Individual | LAC | COL | FOA | 26 | INV | 29 | N | I | CFC | 8.6 | 8.6 | 0 | 0 | 1998-11-01 | 2001-12-01 | 2000-12-01 |  | 2002-09-01 | 2002-12-01 | 67338 | 0 | 67338 | 67338 | 100% | 0 | 0 |  | 8753.94 | 0 | 8753.94 | 0 | 0 | Project fully completed during the last trimester of 2002. PCR is being prepared. |  |  | 2002-12-01 | INV | 0
FIN | IBRD | Elimination of CFC in manufacture of rigid polyurethane foam through the use of HCFC-141b technology at Indufrio | Individual | LAC | COL | FOA | 26 | INV | 30 | N | I | CFC | 9.65 | 9.65 | 0 | 0 | 1998-11-01 | 2002-12-01 | 2000-12-01 |  | 2003-10-01 | 2003-12-01 | 75548 | 0 | 75548 | 75548 | 100% | 0 | 0 |  | 9821.24 | 0 | 9821.24 | 0 | 0 | Project has been financially completed. |  |  |  | INV | 0
CLO | IBRD | Elimination of CFC-11 in the manufacture of rigid polyurethane foam through the use of HCFC-22 technology at Master Cooler and Cia Ltd. | Individual | LAC | COL | FOA | 26 | INV | 31 | N | I |  | 0 | 0 | 0 | 0 | 1998-11-01 |  | 2000-12-01 |  |  | 2001-12-01 | 70862 | -70862 | 0 | 0 | #DIV/0! | 0 | 0 |  | 9212.06 | -9212 | 0 | 0.06 | 0.06 | Project cancelled and funds returned at the 35th ExCom. |  |  |  | INV | 0
FIN | IBRD | Elimination of CFC-11 in the manufacture of rigid polyurethane foam through the use of HCFC-141b technology at Rojas Hnos., Ltda. | Individual | LAC | COL | FOA | 28 | INV | 35 | N | R | CFC | 8.2 | 8.2 | 0 | 0 | 1999-07-01 | 2001-08-30 | 2001-08-01 |  | 2001-11-01 | 2001-12-01 | 64206 | 0 | 64206 | 64206 | 100% | 0 | 0 |  | 8346.78 | 0 | 8346.78 | 0 | 0 | The project is completed, equipment destroyed and funding disbursed. PCR is expected May 2002. |  |  |  | INV | 0
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam (panels and sprayfoam) at Manilit, S.A. | Individual | LAC | COL | FOA | 29 | INV | 36 | A | I | CFC | 15.4 | 15.4 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2000-12-01 | 2004-01-01 | 62230 | -679 | 61551 | 61551 | 100% | 0 | 0 | 0 | 8090 | -88 | 8002 | 0 | 0 | Completed in 2000. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Industrias Refridcol, Ltda. | Individual | LAC | COL | FOA | 29 | INV | 37 | A | I | CFC | 15 | 15 | 0 | 0 | 1999-11-01 | 2001-12-01 | 2002-12-01 |  | 2002-05-01 | 2003-09-01 | 117450 | 0 | 117450 | 117450 | 100% | 0 | 0 | 0 | 15268 | 0 | 15268 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Dinalsa | Individual | LAC | COL | FOA | 29 | INV | 38 | A | I | CFC | 10 | 10 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2002-12-01 |  | 2001-12-01 | 2004-01-01 | 78625 | 0 | 78625 | 78625 | 100% | 0 | 0 | 0 | 10221 | 0 | 10221 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 1999 |  | Investment
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam at 29 Colombian enterprises | Individual | LAC | COL | FOA | 29 | INV | 39 | N | I | CFC | 56.6 | 37.6 | 0 | 0 | 1999-11-01 | 2002-09-01 | 2002-06-01 |  | 2005-01-01 | 2005-08-01 | 584727 | -170557 | 414170 | 414170 | 100% | 0 | 0 |  | 74319.97 | -21678.14 | 52641.83 | 0 | 0 | Project is physically and financially completed. |  |  |  | INV | 0
FIN | UNDP | Preparation of a project in the rigid foam subsector | Individual | LAC | COL | FOA | 30 | PRP | 41 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and water based technology in the manufacture of various polyurethane foam applications at Olaflex with a technical assistance programme covering 10 small customers | Individual | LAC | COL | FOA | 32 | INV | 47 | A | I | CFC | 15 | 15 | 0 | 0 | 2000-12-01 | 2001-06-01 | 2004-01-01 |  | 2001-12-01 | 2003-10-01 | 191833 | 0 | 191833 | 191833 | 100% | 0 | 0 | 0 | 24938.29 | 0 | 24938.29 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion rom CFC-11 to HCFC-141b and water based technology in the manufacture of various polyurethane foam applications at 25 small enterprises centered around their systems house Espumlatex | Individual | LAC | COL | FOA | 32 | INV | 48 | A | I | CFC | 38.4 | 38.4 | 0 | 0 | 2000-12-01 | 2001-07-01 | 2004-01-01 |  | 2004-12-01 | 2004-12-01 | 332768 | 0 | 332768 | 332768 | 100% | 0 | 0 | 0 | 43259.84 | 0 | 43259.84 | 0 | 0 | Completed in 2004. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Retroactive funding for the conversion from CFC-11 to water-based technology in the manufacture of flexible molded and integral skin foam at Espumlatex-Promicolda | Individual | LAC | COL | FOA | 32 | INV | 49 | N | R | CFC | 11.5 | 11.5 | 0 | 0 | 2000-12-01 | 2001-05-01 | 2002-01-01 |  | 2001-05-01 | 2013-02-01 | 82020 | 0 | 82020 | 82020 | 100% | 0 | 0 | 0 | 4921 | 0 | 4921 | 0 | 0 | Financially completed in 2013. |  | 2000 |  | Investment
FIN | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | LAC | COL | FOA | 33 | PRP | 50 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Preparation of a terminal programme in the foam sector | Individual | LAC | COL | FOA | 36 | PRP | 55 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2005-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2002. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Terminal umbrella project for phaseout of the use of CFC-11 in the manufacture of polyurethane foam | Individual | LAC | COL | FOA | 38 | INV | 58 | A | I | CFC | 123.2 | 123.2 | 0 | 0 | 2002-11-01 | 2003-02-01 | 2005-12-01 |  | 2006-12-01 | 2008-04-01 | 840170 | 0 | 840170 | 840170 | 100% | 0 | 0 | 0 | 102418.7 | 0 | 102418.7 | 0 | 0 | Completed in 2006. Financially completed in 2008. |  | 2002 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | LAC | COL | FOA | 57 | PRP | 72 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-06-01 | 2010-03-01 |  | 2010-12-01 | 2012-05-01 | 150000 | -23032.64 | 126967.36 | 126967 | 100% | 0.36 | 0 | 0 | 11250 | -1727.45 | 9522.525 | 0.025 | 0 | Financially completed in 2012. |  | 2009 |  | Investment
COM | Japan | Demonstration project to validate the use of super-critical CO2 in the manufacture of sprayed polyurethane rigid foam | Individual | LAC | COL | FOA | 60 | DEM | 75 | A | I | HCFC-141b | 0 |  | 0 |  | 2010-04-01 |  | 2010-12-01 |  | 2014-12-01 |  | 441100 | -209 | 440891 | 440891 | 100% | 0 | 0 | 167 | 57343 | -27 | 57316 | 0 | 0 | Completed in 2014. | Completed in 2014. | 2010
FIN | UNDP | Conversion plan from HCFCs to hydrocarbons in the production of polyurethane rigid insulation foam in the domestic refrigeration subsector (Mabe Colombia, Industrias Haceb, Challenger and Indusel S.A.) | Multi-year | LAC | COL | FOA | 60 | INV | 76 | N | I | HCFC | 56 | 56 | 0 | 0 | 2010-04-01 | 2010-07-01 | 2013-04-01 |  | 2013-06-01 | 2014-01-01 | 5621483 | -256.84 | 5621226.16 | 5621226 | 100% | 0.16 | 0 | 0 | 421611 | -19.26 | 421591.725 | 0.015 | 0 | Financially Completed in 2014. | As planned, follow up to HCFC-free production and awareness activities among population promoting HCFC-free refrigerators are being conducted. | 2010 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (stage II) (foam sector) | Individual | LAC | COL | FOA | 72 | PRP | 87 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 | 2014-10-01 | 2016-05-01 |  | 2015-11-01 | 2016-11-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 | 0 | 10500 | 0 | 10500 | 0 | 0 | Financially completed in 2016. | First draft of projects were prepared and presented to beneficiary companies and system houses. A workshop with stakeholders from the foam sector was conducted to present the newly approved guidelines. 2 follow up missions were conducted. |  |  | Non-Investment
ONG | UNDP | Demonstration project to validate the use of hydrofluoro-olefins for discontinuous panels in Article 5 parties through the development of cost-effective formulations | Individual | LAC | COL | FOA | 76 | DEM | 100 | N | I | HCFC | 0 | 0 | 0 | 0 | 2016-05-01 | 2016-12-01 | 2017-05-17 | 2018-02-01 |  |  | 248380 | 0 | 248380 | 57500 | 23.15% | 190880 | 0 | 76352 | 22354 | 0 | 5174.9537 | 17179.0463 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): In 2016, the ProDoc was prepared and signed. a Collaboration Agreement between ESPUMLATEX and the Ministry of Environment and Sustainable Development has been drawn up and signed. Experimental protocol was prepared by the international expert. Prodoc signed (actual/planned, yes/no and date):Yes, on November 2016. Missions undertaken (actual/planned):0 of 0 TOR for consultants/subcontracts completed (actual/planned): 1 of 1 Contract/PO/MOA agreements signed: 1 of 1 First disbursement date (actual/planned): 43085Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve:N/A | The project is in the second stage oriented to the development of formulations with HFO, according to the experimental protocol designed with the accompaniment of the international expert. |  |  | Investment
FIN | UNIDO | Project formulation in the methyl bromide sector | Individual | LAC | COL | FUM | 21 | PRP | 23 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-06-01 | 1997-08-01 |  | 1998-01-01 | 2001-07-01 | 7140 | -558 | 6582 | 6582 | 100% | 0 | 0 |  | 928 | -74 | 854 | 0 | 0 | FIN
FIN | UNIDO | Demonstration project - alternatives to the use of methyl bromide in banana growing at Cenibanano | Individual | LAC | COL | FUM | 26 | DEM | 32 | A | I | MBR | 0 | 0 |  |  | 1998-11-01 | 1999-08-01 | 2000-12-01 |  | 2002-12-01 | 2003-06-01 | 123200 | -377 | 122823 | 122823.29 | 100% | -0.29 | 0 |  | 16016 | -74 | 15942 | 0 | 0 | FIN
FIN | UNIDO | Technical assistance in the methyl bromide sector | Individual | LAC | COL | FUM | 55 | TAS | 70 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2010-07-01 |  | 2009-12-01 | 2011-05-01 | 40000 | -620 | 39380 | 39380.46 | 100% | -0.46 | 0 |  | 3600 | -56 | 3544 | 0 | 0 | FIN |  |  |  | NON-INV
TRF | IBRD | Phase-out of CTC as process agent in the elimination of nitrogen trichloride during chlorine production at Prodesal S.A. | Individual | LAC | COL | PAG | 47 | INV | 64 | N | I |  | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2007-12-01 |  |  | 2006-04-01 | 114480 | -114480 | 0 | 0 | #DIV/0! | 0 | 0 |  | 10303 | -10303 | 0 | 0 | 0 | All project funds and support costs were transferred to UNDP at 48th Meeting. |  |  |  | INV | 0
FIN | UNDP | Phase-out of CTC as process agent in the elimination of nitrogen trichloride during chlorine production at Prodesal S.A. | Individual | LAC | COL | PAG | 48 | INV | 66 | N | I | CTC | 2 | 2 | 0 | 0 | 2006-04-01 | 2009-01-01 | 2007-12-01 |  | 2012-05-01 | 2013-07-01 | 114480 | -1.45 | 114478.55 | 114479 | 100% | -0.45 | 0 | 0 | 10303 | 0 | 10303.0405 | -0.0405 | 0 | Financially completed in 2013. | Completed in 2012. No activities in 2013. | 2006 |  | Investment
FIN | UNDP | National phase-out plan for Annex A (Group I and II) substances: first implementation programme | Multi-Year | LAC | COL | PHA | 41 | INV | 60 | N | I | CFC | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-07-01 | 2004-12-01 |  | 2008-12-01 | 2013-12-01 | 2146820 | 0 | 2146820 | 2146820 | 100% | 0 | 0 | 0 | 161011 | 0 | 161011 | 0 | 0 | Financially completed in 2013. |  | 2003 |  | Investment
FIN | UNDP | National phase-out plan for Annex A (Group I and II) substances: second implementation programme | Multi-Year | LAC | COL | PHA | 47 | INV | 63 | N | I | CFC | 805.9 | 805.9 | 0 | 0 | 2005-11-01 | 2006-05-01 | 2006-12-01 |  | 2011-12-01 | 2014-02-01 | 2353180 | -119 | 2353061 | 2353061 | 100% | 0 | 0 | 0 | 176488 | -8.92 | 176479.08 | 0 | 0 | Financially completed in 2014. | Final financial obligations being disbursed. | 2005 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | COL | PHA | 55 | PRP | 69 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-01-01 | 2009-07-01 |  | 2010-12-01 | 2012-04-01 | 173750 | -6849.95 | 166900.05 | 166900 | 100% | 0.05 | 0 | 0 | 13031 | -513.74 | 12517.2599 | 0.00014993 | 0 | Financially completed in 2012. | Financially completed in 2012. | 2008 |  | Investment
FIN | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | COL | PHA | 62 | INV | 77 | N | I | HCFC | 7.7 | 7.7 | 0 | 0 | 2010-12-01 | 2011-04-01 | 2012-12-01 |  | 2012-12-01 | 2013-05-01 | 400000 | 0 | 400000 | 400000 | 100% | 0 | 0 | 0 | 30000 | 0 | 30000 | 0 | 0 | Financially completed in 2013. |  | 2010 |  | Investment
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | COL | PHA | 62 | TAS | 78 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2012-06-01 | 2012-12-01 |  | 2014-12-01 | 2014-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNDP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | LAC | COL | PHA | 66 | INV | 81 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-04-01 | 2013-03-01 | 2014-04-01 |  | 2015-01-01 | 2016-03-01 | 550000 | 0 | 550000 | 550000 | 100% | 0 | 0 | 0 | 41250 | 0 | 41250 | 0 | 0 | Financially completed in 2016. | 4 workshops on good refrigeration practices conducted. 2 consultancies to standarize operation of reclaiming centers were initiated. 8 collection centers obtained their environmental license and operating in the R&R&R network. 2 follow up missions were conducted. | 2012 |  | Investment
COM | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | COL | PHA | 66 | TAS | 80 | A | I |  | 1.5 | 0 | 0 | 0 | 2012-04-01 | 2012-12-01 | 2014-04-01 |  | 2015-12-01 |  | 50000 | 0 | 50000 | 40907.78 | 81.82% | 9092.22 | 9092.22 | 9092 | 6500 | 0 | 5318.0114 | 1181.9886 | 1181.9886 | Project Completed in 2015. UNEP is waiting for UNDP Clearance Account to close this project's account. | Project Completed in 2015. UNEP can not put FIN as UNEP is waiting for UNDP Clearance Account to close this project's account.
COM | UNDP | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | LAC | COL | PHA | 72 | INV | 89 | N | I | HCFC | 2.9 | 2.9 | 0 | 0 | 2014-05-01 | 2014-11-01 | 2016-05-01 |  | 2016-12-01 |  | 150000 | 0 | 150000 | 142699.62 | 95.13% | 7300.38 | 0 | 6205.323 | 11250 | 0 | 10702.4715 | 547.5285 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): 2016 work plan was implemented as envisioned. Review of the certification rules were conducted with SENA and other stakeholders. Prodoc signed (actual/planned, yes/no and date):The agreement has been signed earlier. Missions undertaken (actual/planned):1 of 1 TOR for consultants/subcontracts completed (actual/planned): TOR completed earlier. Contract/PO/MOA agreements signed: The agreement has been signed earlier First disbursement date (actual/planned): 43053Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve:N/A | Completed project. |  |  | Investment
FIN | Germany | Preparation of a HCFC phase-out management plan (stage II) | Individual | LAC | COL | PHA | 72 | PRP | 85 | A | I | HCFC | 0 | 0 | 0 |  | 2014-05-01 | 2014-05-01 | 2016-05-01 |  | 2016-01-01 | 2016-01-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Data collection and processing, stakeholder consultations, visit to possible installations for natural refrigerants training centre, discussions with technical standard organization and sector study completed, final stage II proposal for the servicing sector prepared
COM | UNDP | Preparation of a HCFC phase-out management plan (stage II) | Individual | LAC | COL | PHA | 72 | PRP | 86 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 | 2014-11-01 | 2016-05-01 |  | 2015-10-01 |  | 75000 | 0 | 75000 | 74172 | 98.9% | 828 | 0 | 703.8 | 5250 | 0 | 5192.04 | 57.96 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2015. |  |  |  | Investment
ONG | Germany | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | Multi-Year | LAC | COL | PHA | 75 | INV | 95 | A | I | HCFC | 3.7 |  | 0 |  | 2015-11-01 | 2016-05-01 | 2018-11-01 | 2018-11-01 |  |  | 325800 | 0 | 325800 | 44345 | 13.61% | 281455 | 24500 | 200000 | 41838 | 0 | 5695 | 36143 | 36143 | Contracts with international consultancy established, specifications for training centre equipment prepared, selection process of suitable training locations undertaken (until now no suitable training center could be identified), work on review of standards and elaboration of training materials initiated, kick off workshop realized | work and progress for tender process for equipment, training materials and standard review
ONG | UNDP | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | Multi-year | LAC | COL | PHA | 75 | INV | 96 | N | I | HCFC | 6.9 | 0 | 0 | 0 | 2015-11-01 | 2016-11-01 | 2018-11-01 | 2019-02-01 |  |  | 605000 | 0 | 605000 | 4430.63 | 0.7323% | 600569.37 | 0 | 240227.748 | 42350 | 0 | 310.1441 | 42039.8559 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): ProDoc was prepared and signed. Consultant in charge of implementation of the project was hired. 1 workshop was conducted on alternatives to HCFC in the RAC sector. Meetings wiht stakeholders from the tourism and flower sectoes were conducted to identified possible alternatives of each sector. Prodoc signed (actual/planned, yes/no and date):Yes, 10/3/2016 Missions undertaken (actual/planned):0 of 0 TOR for consultants/subcontracts completed (actual/planned): 1 of 1 Contract/PO/MOA agreements signed: 1 of 1 First disbursement date (actual/planned): 43056Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve:N/A | Annual work plan prepared and discussed with stakeholders. | 2015 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage II, first tranche) (foam sector) | Multi-year | LAC | COL | PHA | 75 | INV | 98 | N | I | HCFC | 48.2 | 0 | 0 | 0 | 2015-11-01 | 2016-11-01 | 2018-11-01 | 2017-11-01 |  |  | 1279881 | 0 | 1279881 | 143113 | 11.18% | 1136768 | 0 | 454707.2 | 89592 | 0 | 10017.9469 | 79574.0531 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): ProDoc was prepared and signed.7 MoA with system houses and beneficiary companies prepared, 2 Moa have been signed. Discussions with providers of HFO and other technology providers have been conducted. Prodoc signed (actual/planned, yes/no and date):Yes, 10/3/2016 Missions undertaken (actual/planned):0 of 0 TOR for consultants/subcontracts completed (actual/planned): 7 of 7 Contract/PO/MOA agreements signed: 3 of 7 First disbursement date (actual/planned): 43055Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve:N/A | Discussion with system houses that are pending of signing their MoA were conducted. | 2015 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage II, first tranche) (project management, monitoring and coordination) | Multi-year | LAC | COL | PHA | 75 | TAS | 91 | N | I | HCFC | 0 | 0 | 0 | 0 | 2015-11-01 |  | 2018-11-01 | 2019-02-01 |  |  | 245325 | 0 | 245325 | 0 | 0% | 245325 | 0 | 98130 | 17173 | 0 | 0 | 17173 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): ProDoc was prepared and signed. Meeting for developing 2017 work plan was conducted. Prodoc signed (actual/planned, yes/no and date):Yes, 10/3/2016 Missions undertaken (actual/planned):0 of 0 TOR for consultants/subcontracts completed (actual/planned): 0 of 0 Contract/PO/MOA agreements signed: 0 of 0 First disbursement date (actual/planned): 42811Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve:N/A | Annual work plan share with stakeholders. | 2015 |  | Non-Investment
ONG | UNDP | HCFC phase-out management plan (stage II, first tranche) (technical assistance in policies formulation and implementation) | Multi-year | LAC | COL | PHA | 75 | TAS | 92 | N | I | HCFC | 1.6 | 0 | 0 | 0 | 2015-11-01 |  | 2018-11-01 | 2019-02-01 |  |  | 136485 | 0 | 136485 | 0 | 0% | 136485 | 0 | 54594 | 9554 | 0 | 0 | 9554 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): ProDoc was prepared and signed. Prodoc signed (actual/planned, yes/no and date):Yes, 10/3/2016 Missions undertaken (actual/planned):0 of 0 TOR for consultants/subcontracts completed (actual/planned): 0 of 0 Contract/PO/MOA agreements signed: 0 of 0 First disbursement date (actual/planned): 42811Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve:N/A | Annual work plan prepared. | 2015 |  | Non-Investment
ONG | UNEP | HCFC phase-out management plan (stage II, first tranche) (technical assistance in policies formulation and implementation) | Multi-Year | LAC | COL | PHA | 75 | TAS | 93 | A | I |  | 0.6 |  | 0 |  | 2015-11-01 |  | 2018-11-01 | 2017-12-01 |  |  | 50000 | 0 | 50000 | 0 | 0% | 50000 | 151.54 | 5000 | 6500 | 0 | 0 | 6500 | 19.7002 | Brief progress report: The implementation of the HPMP stage two, first tranche has been officially launched in June 2016. Legal arrangements (actual/planned): The SSFA to implement the stage two - first tranche was drafted. Initially planned for March 2016. First mission (actual/planned): June 2016 while no specific date was established in the project document. TOR completed (actual/planned): N/A. First disbursement date (actual/planned): No disbursement in 2016/ Planned for May 2016. All funds disbursed? (yes/no): No. Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: Administrative reasons, but they are now dully sorted out. If Yes, will delay have impact on project completion date: No. Any ongoing problems? (yes/no): No. If Yes, is any action required by ExCom: N/A | Brief progress report: The implementation of the HPMP stage two, first tranche has been officially launched in June 2016. Legal arrangements (actual/planned): The SSFA to implement the stage two - first tranche signed by UNEP in February 2017 and expected to be signed by the Government in April 2017. Initially planned for March 2016. First mission (actual/planned): June 2016 while no specific date was established in the project document. TOR completed (actual/planned): N/A. First disbursement date (actual/planned): Expected to May 2017/ Planned for May 2016. All funds disbursed? (yes/no): No. Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: Administrative reasons, but they are now dully sorted out. If Yes, will delay have impact on project completion date: No. Any ongoing problems? (yes/no): No. If Yes, is any action required by ExCom: N/A |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor the signing of the agreement by the Government and UNEP.
ONG | UNDP | HCFC phase-out management plan (stage II, first tranche) (technical assistance for fire protection sector) | Multi-year | LAC | COL | PHA | 75 | TAS | 94 | N | I | HCFC | 6.8 | 0 | 0 | 0 | 2015-11-01 |  | 2018-11-01 | 2019-02-01 |  |  | 75900 | 0 | 75900 | 0 | 0% | 75900 | 0 | 30360 | 5313 | 0 | 0 | 5313 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Prodoc prepared and signed. 2 TOR for consultancies in the sector prepared. Prodoc signed (actual/planned, yes/no and date):Yes, 10/3/2016 Missions undertaken (actual/planned):0 of 0 TOR for consultants/subcontracts completed (actual/planned): 2 pf 2 Contract/PO/MOA agreements signed: 0 of 2 First disbursement date (actual/planned): 42811Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve:N/A | Annual work plan prepared. | 2015 |  | Non-Investment
FIN | UNDP | Elimination of CFC in the manufacture of domestic refrigerators at Polarix Electrodomesticos, S.A. | Individual | LAC | COL | REF | 13 | INV | 04 | A | I | CFC | 63 | 63 | 0 | 0 | 1994-07-01 | 1995-05-01 | 1995-07-01 |  | 1997-10-01 | 2000-12-01 | 844824 | -205206 | 639618 | 639618 | 100% | 0 | 0 | 0 | 109827 | -26676.78 | 83150.22 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC in the manufacture of domestic refrigerators at Industrias Haceb, S.A. | Individual | LAC | COL | REF | 13 | INV | 05 | A | I | CFC | 69 | 69 | 0 | 0 | 1994-07-01 | 1995-05-01 | 1995-07-01 |  | 1997-10-01 | 2000-12-01 | 1386314 | -340578 | 1045736 | 1045736 | 100% | 0 | 0 | 0 | 180220.7 | -44275.14 | 135945.56 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC in the manufacture of domestic refrigerators at Icasa, S.A. | Individual | LAC | COL | REF | 13 | INV | 06 | A | I | CFC | 72 | 72 | 0 | 0 | 1994-07-01 | 1995-05-01 | 1995-07-01 |  | 1997-10-01 | 2000-12-01 | 1410680 | -358123 | 1052557 | 1052557 | 100% | 0 | 0 | 0 | 183388.4 | -46555.99 | 136832.41 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Conversion of CFC-12 to HFC-134a compresors at Compresores Andinos, S.A. | Individual | LAC | COL | REF | 13 | INV | 07 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 | 1995-05-01 | 1995-07-01 |  | 1997-10-01 | 2000-12-01 | 313650 | -23379 | 290271 | 290271 | 100% | 0 | 0 | 0 | 40774.37 | -3039.27 | 37735.1 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC in the manufacture of domestic refrigerators at Corporacion de Electrodomesticos, S.A. (Corelsa) | Individual | LAC | COL | REF | 13 | INV | 08 | A | I | CFC | 22 | 22 | 0 | 0 | 1994-07-01 | 1995-05-01 | 1995-07-01 |  | 1999-07-01 | 2000-12-01 | 853432 | -166101 | 687331 | 687331 | 100% | 0 | 0 | 0 | 110946.2 | -21593.13 | 89353.07 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1994 | 1999-02-01 | Investment
FIN | USA | MAC emissions reduction demonstration programme |  | LAC | COL | REF | 15 | DEM | 13 | A | I | CFC | 11.5 | 12 | 0 |  | 1994-12-01 | 1995-02-01 | 1995-06-01 |  | 1999-06-01 | 2000-05-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Final report will be submitted in May 2000. Project will be classified as financially complete at that time. |  | 1994
FIN | UNDP | Elimination of CFC 11 and 12 in the manufacture of unitary commercial refrigeration equipment at Industrias de Refrigeracion Comercial S.A. (Indufrial) | Individual | LAC | COL | REF | 15 | INV | 11 | A | I | CFC | 30 | 30 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  | 1997-10-01 | 2000-12-01 | 442644 | -8866 | 433778 | 433778 | 100% | 0 | 0 | 0 | 57543.72 | -1152.58 | 56391.14 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of unitary commercial refrigeration equipment at Industrias Wonder S.A. | Individual | LAC | COL | REF | 15 | INV | 12 | A | I | CFC | 7 | 7 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  | 1997-12-01 | 1999-12-01 | 251315 | 0 | 251315 | 251315 | 100% | 0 | 0 | 0 | 32670.95 | 0 | 32670.95 | 0 | 0 | Completed in 1997. Financially completed in 1999. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of unitary commercial refrigeration equipment at Industrial Colombia S.A. (Inducol) | Individual | LAC | COL | REF | 15 | INV | 14 | A | I | CFC | 16 | 16 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  | 1999-12-01 | 2001-12-01 | 381548 | -36480.18 | 345067.82 | 345068 | 100% | -0.18 | 0 | 0 | 49601.24 | -4742.76 | 44858.5 | -0.02 | 0 | Completed in 1999. Financially completed in 2001. |  | 1994 | 1999-02-01 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of unitary commercial refrigeration equipment at Friomix, S.A. | Individual | LAC | COL | REF | 17 | INV | 15 | A | D | CFC | 10 | 10 | 0 | 0 | 1995-07-01 | 1999-01-01 | 1996-07-01 |  | 1999-02-01 | 2000-12-01 | 11146 | 0 | 11146 | 11146 | 100% | 0 | 0 | 0 | 1448.98 | 0 | 1448.98 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1995 | 1999-02-01 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of unitary commercial refrigeration equipment at Industrias Westell Ltd. | Individual | LAC | COL | REF | 17 | INV | 16 | A | I | CFC | 20 | 20 | 0 | 0 | 1995-07-01 | 1997-05-01 | 1997-01-01 |  | 1999-12-01 | 2001-12-01 | 227602 | -2 | 227600 | 227600 | 100% | 0 | 0 | 0 | 29588.26 | 0 | 29588.26 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1995 | 1999-12-01 | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | COL | REF | 17 | TAS | 19 | N | I | CFC | 111 | 111 | 0 | 0 | 1995-07-01 | 1996-02-01 | 1996-07-01 |  | 1999-07-01 | 2013-08-01 | 787030 | -4.66 | 787025.34 | 787025 | 100% | 0.34 | 0 | 0 | 102313.9 | -0.85 | 102313.0058 | 0.0442 | 0 | Financially completed in 2013. |  | 1995 | 1999-06-01 | Investment
FIN | UNEP | Training programme in good practices in refrigeration | Individual | LAC | COL | REF | 17 | TRA | 18 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-09-01 | 1996-07-01 |  | 2003-12-01 | 2005-02-01 | 149100 | -42081.59 | 107018.41 | 107018.41 | 100% | 0 | 0 |  | 19383 | -5470.61 | 13912.39 | 0 | 0 |  |  |  | 1999-12-01
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Unilemh Ltd. (Challenger) | Individual | LAC | COL | REF | 18 | INV | 21 | A | I | CFC | 17 | 17 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1997-05-01 |  | 1997-10-01 | 2000-07-01 | 155350 | -1561 | 153789 | 153789 | 100% | 0 | 0 | 0 | 20195.5 | -202.93 | 19992.57 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of commercial refrigeration equipment at Refrigeracion Supernordico Ltda. | Individual | LAC | COL | REF | 19 | INV | 22 | A | I | CFC | 10.8 | 10.8 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  | 1999-12-01 | 2004-01-01 | 162500 | -1243 | 161257 | 161257 | 100% | 0 | 0 | 0 | 21125 | -162 | 20963 | 0 | 0 | Completed in 1999. Financially completed in 2004. |  | 1996 |  | Investment
FIN | IBRD | Project preparation in the commercial refrigeration sector |  | LAC | COL | REF | 24 | PRP | 27 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1999-06-01 | 1999-06-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 |  | 11700 | 0 | 11700 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | IBRD | Replacement of CFC-11 foam blowing agent with HCFC-141b and CFC-12 refrigerant with HFC-134a in the manufacture of commercial refrigerators and polyurethane sandwich panels at Polares Ltda. | Individual | LAC | COL | REF | 28 | INV | 34 | N | I | CFC | 4.64 | 4.64 | 0 | 0 | 1999-07-01 | 2001-09-11 | 2001-08-01 |  | 2002-03-01 | 2002-06-01 | 58109 | 0 | 58109 | 58109 | 100% | 0 | 0 |  | 7554.17 | 0 | 7554.17 | 0 | 0 | Project has been fully executed. PCR being prepared. |  |  |  | INV | 0
FIN | IBRD | Replacement of CFC-11 foam blowing agent with HCFC-141b and CFC-12 refrigerant with HFC-134a in the manufacture of commercial refrigerators and polyurethane sandwich panels at Industrias Supernórdico | Individual | LAC | COL | REF | 28 | INV | 44 | N | I | CFC | 9.6 | 9.7 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2001-08-01 |  | 2002-02-01 | 2002-06-01 | 128381 | 0 | 128381 | 128381 | 100% | 0 | 0 |  | 16689.53 | 0 | 16689.53 | 0 | 0 | Project has been fully executed. PCR has been prepared and is being evaluated. Actual phaseout as reported in the PCR and confirmed with enterprise, country and revised proposal. |  |  | 2002-12-01 | INV | 0
FIN | IBRD | Preparation of projects in the commercial refrigeration subsector |  | LAC | COL | REF | 30 | PRP | 40 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2001-12-01 |  | 2001-12-01 | 2001-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation in MACs and compressors project category |  | LAC | COL | REF | 30 | PRP | 43 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Technical assistance for RMP survey and preparation | RMP-Component | LAC | COL | REF | 32 | TAS | 46 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2002-07-01 | 2003-01-01 |  | 2003-12-01 | 2005-10-01 | 40000 | -2578 | 37422 | 37422 | 100% | 0 | 0 | 0 | 5200 | -335.14 | 4864.86 | -3.3e-05 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 | 2003-01-01 | Non-Investment
FIN | IBRD | Conversion of CFC-12 to HFC-134a technology in the production of MAC systems at Thermo-coil, Calaires, Auto Aires, and Servi Aires | Individual | LAC | COL | REF | 34 | INV | 51 | N | I | CFC | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-10-01 | 2003-08-01 |  | 2003-11-01 | 2003-12-01 | 1358647 | -13905 | 1344742 | 1344742.18 | 100% | -0.18 | -0.18 |  | 159451.17 | -1632 | 157819.3 | -0.13 | -0.13 | Project physically and financially completed. |  |  |  | INV | 0
FIN | Canada | Training programme for customs officers | Individual | LAC | COL | REF | 35 | TRA | 52 | A | I |  | 0 |  | 0 |  | 2001-12-01 | 2002-06-01 | 2004-07-01 |  | 2006-08-01 | 2006-08-01 | 106150 | 0 | 106150 | 106150 | 100% | 0 |  | 0 | 13799 | 0 | 13799 | 0 |  | 300 customs officers trained and monitoring and evaluation completed by June 2005. However, one final activity, reproduction of training manual was completed only by August 2006. PCR submitted in 2006. |  | 2000 |  | Non-Inv.
FIN | UNDP | Project preparation in the commercial refrigeration sector | Individual | LAC | COL | REF | 36 | PRP | 54 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2004-06-01 | 2005-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2002 |  | Investment
FIN | IBRD | Umbrella project designed to phase out of the refrigerant CFC-12 by conversion to HFC-134a and replacement of the blowing agent CFC-11 by HCFC-141b in the manufacture of commercial refrigeration systems in 17 enterprises | Individual | LAC | COL | REF | 38 | INV | 57 | N | I | CFC | 25.8 | 7.85 | 0 | 0 | 2002-11-01 | 2005-12-01 | 2004-12-01 |  | 2005-10-01 | 2005-12-01 | 211636 | -130071 | 81565 | 81565 | 100% | 0 | 0 |  | 27512.68 | -16909.24 | 10603.44 | 0 | 0 | Project is physically and financially completed. |  |  |  | INV | 0
COM | UNDP | Demonstration project for integrated management of the centrifugal chiller sub-sector, focusing on application of energy-efficient CFC-free technologies for replacement of CFC-based chillers | Individual | LAC | COL | REF | 47 | DEM | 65 | N | I | CFC | 0 | 0 | 0 | 0 | 2005-11-01 | 2010-01-01 | 2008-12-01 |  | 2015-12-01 |  | 1000000 | 0 | 1000000 | 994729.35 | 99.47% | 5270.65 | 0 | 4480.0525 | 75000 | 0 | 74604.7012 | 395.2988 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2015. |  | 2005 |  | Non-Investment
COM | UNDP | Preparation for HCFC phase-out investment activities (stage II) (commercial and industrial air-conditioning manufacturing sector) | Individual | LAC | COL | REF | 72 | PRP | 84 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 | 2014-11-01 | 2016-05-01 |  | 2015-10-01 |  | 25000 | 0 | 25000 | 24146 | 96.58% | 854 | 0 | 725.9 | 1750 | 0 | 1690.22 | 59.78 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2015. |  |  |  | Non-Investment
COM | UNDP | Preparation for HCFC phase-out investment activities (stage II) (commercial refrigeration manufacturing sector) | Individual | LAC | COL | REF | 72 | PRP | 88 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 | 2014-12-01 | 2016-05-01 |  | 2015-10-01 |  | 25000 | 0 | 25000 | 24540 | 98.16% | 460 | 0 | 391 | 1750 | 0 | 1717.8 | 32.2 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2015. |  |  |  | Non-Investment
ONG | UNDP | Demonstration of HC-290 (propane) as an alternative refrigerant in commercial air-conditioning manufacturing at Industrias Thermotar ltda | Individual | LAC | COL | REF | 75 | DEM | 97 | N | I | HCFC | 0.7 | 0 | 0 | 0 | 2015-11-01 | 2016-10-01 | 2017-06-01 | 2017-06-01 |  |  | 500000 | 0 | 500000 | 84486.82 | 16.9% | 415513.18 | 0 | 166205.272 | 35000 | 0 | 5914.0774 | 29085.9226 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Preliminary designs have been carried out by the company. The review of the designs has been carried out by the international expert. Also, the process of selecting the supplier of the technology for the modification of production line and the preparation of prototypes to carry out the tests of performance and security had been conducted. Prodoc signed (actual/planned, yes/no and date):Yes, on September 2016 Missions undertaken (actual/planned):1 of 1 TOR for consultants/subcontracts completed (actual/planned): 1 of 1 Contract/PO/MOA agreements signed: 1 of 1 First disbursement date (actual/planned): 42644Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve:N/A | Prototyes under evaluation, identification of suppliers of components is underway. | 2015 |  | Non-Investment
FIN | UNDP | Country programme preparation | Individual | LAC | COL | SEV | 12 | CPG | 01 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1994-03-01 |  | 1994-03-01 | 1994-03-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed in 1994. Financially Completed in 1994. |  | 1994 |  | Non-Investment
FIN | UNDP | Institutional strengthening for implementation of the Montreal Protocol in Colombia | Individual | LAC | COL | SEV | 12 | INS | 02 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-11-01 | 1997-03-01 |  | 1998-03-01 | 1999-12-01 | 317790 | 0 | 317790 | 317790 | 100% | 0 | 0 | 0 | 41312.7 | 0 | 41312.7 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1994 |  | Non-Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | COL | SEV | 12 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-01 | 1995-03-01 |  | 1995-06-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | COL | SEV | 17 | PRP | 17 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-07-01 | 1996-04-01 |  | 1996-03-01 | 1997-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1996. Financially completed in 1997. |  | 1995 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | COL | SEV | 18 | PRP | 20 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-11-01 | 1996-11-01 |  | 1996-11-01 | 1998-12-01 | 28000 | 0 | 28000 | 28000 | 100% | 0 | 0 | 0 | 3640 | 0 | 3640 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | IBRD | Project preparation identification |  | LAC | COL | SEV | 21 | PRP | 24 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Renewal of institutional strengthening project for the phaseout of ozone depleting substances | Individual | LAC | COL | SEV | 24 | INS | 25 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-05-01 | 2000-03-01 |  | 2000-03-01 | 2007-06-01 | 212000 | 0 | 212000 | 212000 | 100% | 0 | 0 | 0 | 27560 | 0 | 27560 | 0 | 0 | Completed in 2000. Financially completed in 2007. |  | 1998 |  | Non-Investment
FIN | IBRD | Preparation of projects in the foam, commercial refrigeration and solvent sectors |  | LAC | COL | SEV | 27 | PRP | 33 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-06-30 | 2000-01-01 |  | 2000-12-01 | 2000-12-01 | 38000 | 0 | 38000 | 38000 | 100% | 0 | 0 |  | 4940 | 0 | 4940 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Renewal of institutional strengthening: Phase 3 | Individual | LAC | COL | SEV | 30 | INS | 42 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2002-04-01 |  | 2003-05-01 | 2007-06-01 | 212000 | 0 | 212000 | 212000 | 100% | 0 | 0 | 0 | 27560 | 0 | 27560 | 0 | 0 | Completed in 2003. Financially completed in 2007. |  | 2000 |  | Non-Investment
FIN | UNDP | Country programme update | Individual | LAC | COL | SEV | 36 | CPG | 56 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-07-01 | 2003-10-01 |  | 2004-06-01 | 2005-11-01 | 30000 | -415 | 29585 | 29585 | 100% | 0 | 0 | 0 | 3900 | -54 | 3846 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2002 |  | Non-Investment
FIN | UNDP | Renewal of the institutional strengthening (phase 4) | Individual | LAC | COL | SEV | 38 | INS | 59 | N | I | No_ODP | 22.8 | 22.8 | 0 | 0 | 2002-11-01 | 2003-05-01 | 2004-12-01 |  | 2005-12-01 | 2010-10-01 | 275600 | -3.79 | 275596.21 | 275596 | 100% | 0.21 | 0 | 0 | 35828 | -0.49 | 35827.48 | 0.03 | 0 | Financially completed in 2010. |  | 2002 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase V) | Individual | LAC | COL | SEV | 45 | INS | 61 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-08-01 | 2007-04-01 |  | 2007-12-01 | 2010-10-01 | 275600 | -13.86 | 275586.14 | 275586 | 100% | 0.14 | 0 | 0 | 20670 | -1.04 | 20668.95 | 0.01 | 0 | Financially completed in 2010. |  | 2005 |  | Non-Investment
FIN | UNDP | Assistance to carry out an HCFC survey | Individual | LAC | COL | SEV | 45 | TAS | 62 | A | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-04-01 | 2006-12-01 |  | 2008-08-01 | 2009-12-01 | 68807 | -10271 | 58536 | 58536 | 100% | 0 | 0 | 0 | 6193 | -924.45 | 5268.5548 | -0.0048 | 0 | Completed in 2008. Financially completed in 2009. |  | 2005 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase VI) | Individual | LAC | COL | SEV | 52 | INS | 67 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-11-01 | 2009-10-01 |  | 2010-08-01 | 2011-10-01 | 275600 | -317.26 | 275282.74 | 275283 | 100% | -0.26 | 0 | 0 | 20670 | -23.79 | 20646.225 | -0.015 | 0 | Completed. See report on IS Colombia in COL/SEV/52/INS/73. |  | 2007 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase VII) | Individual | LAC | COL | SEV | 58 | INS | 73 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2009-07-01 | 2010-03-01 | 2011-10-01 |  | 2011-12-01 | 2013-07-01 | 160767 | 114820.23 | 275587.23 | 275587 | 100% | 0.23 | 0 | 0 | 12058 | 8611.04 | 20669.0249 | 0.01505 | 0 | Financially completed in 2013. | The NOU plays an active role in the implementation of MLF funded projects in Colombia. The NOU is in the process of establishing the qoutas for HCFCs for 2013 and include supporting legislation for HCFC phase out. Final invoices pending. | 2009 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase VIII: 11/2011-10/2013) | Individual | LAC | COL | SEV | 64 | INS | 79 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-04-01 | 2013-10-01 |  | 2013-12-01 | 2014-07-01 | 275600 | 0 | 275600 | 275600 | 100% | 0 | 0 | 0 | 20670 | 0 | 20670 | 0 | 0 | Financially completed in 2014. | The 2014 workplan and budget prepared and approved. As planned, the HCFC quotas for 2014 have been established. All pending payments were made. | 2011 |  | Non-Investment
COM | UNDP | Extension of institutional strengthening project (phase IX: 11/2013-10/2015) | Individual | LAC | COL | SEV | 70 | INS | 83 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2013-07-01 | 2013-12-01 | 2015-10-01 |  | 2016-03-01 |  | 275600 | 0 | 275600 | 275443.96 | 99.94% | 156.04 | 0 | 132.634 | 19292 | 0 | 19281.0772 | 10.9228 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): 2016 HCFC import quota established and distributed. ODS consumption reports prepared and submitted. Prodoc signed (actual/planned, yes/no and date):The agreement has been signed earlier. Missions undertaken (actual/planned):2 of 2 TOR for consultants/subcontracts completed (actual/planned): 0 of 0 Contract/PO/MOA agreements signed: The agreement has been signed earlier First disbursement date (actual/planned): 41609Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve:N/A | Completed project. | 2013 |  | Non-Investment
ONG | UNDP | Extension of institutional strengthening project (phase X: 11/2015-10/2017) | Individual | LAC | COL | SEV | 74 | INS | 90 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2015-05-01 | 2015-12-01 | 2017-10-01 | 2017-10-01 |  |  | 275600 | 0 | 275600 | 47742.35 | 17.32% | 227857.65 | 0 | 91143.06 | 19292 | 0 | 3341.9645 | 15950.0355 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Institutional strengthening activities underway. Celebration of Ozone Day carried out. 2016 HCFC import quota set. NOU attended regional and global meetings. Prodoc signed (actual/planned, yes/no and date):The agreement has been signed earlier. Missions undertaken (actual/planned):2 of 2 TOR for consultants/subcontracts completed (actual/planned): 3 of 3 Contract/PO/MOA agreements signed: 3 of 3 First disbursement date (actual/planned): 42339Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve:N/A | Annual work plan prepared. HCFC import quota set for 2017. | 2015 |  | Non-Investment
ONG | Germany | Survey of ODS alternatives at the national level | Individual | LAC | COL | SEV | 75 | TAS | 99 | A | I | HFC | 0 |  | 0 |  | 2015-11-01 | 2016-07-01 | 2016-11-01 | 2017-03-01 |  |  | 65000 | 0 | 65000 | 49500 | 76.15% | 15500 | 15500 | 15500 | 8450 | 0 | 6435 | 2015 | 2015 | Contracts with international and local consultancies completed, work on inventory and report | Project completed and report delivered to MLFS in Q1 2017
FIN | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | Individual | LAC | COL | SOL | 31 | INV | 45 | N | I | CFC | 7.6 | 7.6 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2002-08-01 |  | 2004-12-01 | 2004-12-01 | 81579 | 0 | 81579 | 81579 | 100% | 0 | 0 |  | 10605.27 | 0 | 10605.27 | 0 | 0 | Project is physically and financially completed. |  |  |  | INV | 0
FIN | IBRD | Project preparation in the CTC solvent sector |  | LAC | COL | SOL | 36 | PRP | 53 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-01-01 | 2003-01-01 | 20000 | -12000 | 8000 | 8000 | 100% | 0 | 0 |  | 2600 | -1560 | 1040 | 0 | 0 | Difficulties experienced in obtaining reliable CTC consumption data have significantly delayed potential project prep. efforts. National CTC consumption is reported to be minimal with the exception of one identified enterprise. |  |  |  | Non-INV | 0
FIN | UNDP | Seminar/workshop in the foam sector | Individual | LAC | COS | FOA | 08 | TRA | 05 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 2003-04-01 | 21120 | 0 | 21120 | 21120 | 100% | 0 | 0 | 0 | 2745.6 | 0 | 2745.6 | 0 | 0 | Completed in 1996. Financially completed in 2003. |  | 1992 |  | Non-Investment
FIN | UNDP | Project preparation for 2 methyl bromide alternative demonstration projects | Individual | LAC | COS | FUM | 24 | PRP | 12 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1998 |  | Investment
FIN | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican melons | Individual | LAC | COS | FUM | 27 | DEM | 14 | N | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 180500 | 0 | 180500 | 180500 | 100% | 0 | 0 | 0 | 23465 | 0 | 23465 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Alternatives to methyl bromide for soil fumigation on Costa Rican cut flowers | Individual | LAC | COS | FUM | 27 | DEM | 15 | N | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-10-01 |  | 2001-12-01 | 2003-06-01 | 193500 | -117 | 193383 | 193383 | 100% | 0 | 0 | 0 | 25155 | -15.21 | 25139.79 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | France | Project preparation for phase out of methyl bromide used in grain fumigation |  | LAC | COS | FUM | 29 | PRP | 21 | A | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-09-01 | 2000-12-01 |  | 2001-09-01 | 2001-09-01 | 30000 | -19257 | 10743 | 10743 | 100% | 0 |  | 0 | 1500 | -963 | 537 | 0 |  | Une première version du projet a été soumise par la FAO. Suite au projet par le Comité Exécutif visant à l'élimination du MBr au Costa Rica, il n'est plus possible de présenter d'autres projets. De fait le projet est annulé.
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organisations in methyl bromide communication | Individual | LAC | COS | FUM | 30 | TAS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9639 | 15361 | 15361 | 100% | 0 | 0 |  | 3250 | -1253.07 | 1996.93 | 0 | 0
FIN | UNDP | Project preparation in soil fumigation | Individual | LAC | COS | FUM | 33 | PRP | 24 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Total methyl bromide phase-out used as a fumigant in melons, cut flowers, bananas, tobacco seedbeds and nurseries, excluding QPS applications (first tranche) | Multi-Year | LAC | COS | FUM | 35 | INV | 25 | N | I | MeBr | 84.4 | 84.4 | 0 | 0 | 2001-12-01 | 2003-02-01 | 2002-12-01 |  | 2005-07-01 | 2013-05-01 | 1211321 | 0 | 1211321 | 1211321 | 100% | 0 | 0 | 0 | 143245.3 | 0 | 143245.3 | 0 | 0 | Financially completed in 2013. |  | 2001 | 2004-07-01 | Investment
FIN | UNDP | Total methyl bromide phase-out used as a fumigant in melons, cut flowers, bananas, tobacco seedbeds and nurseries, excluding QPS applications (tranches II and III) | Multi-Year | LAC | COS | FUM | 43 | INV | 33 | N | I | MeBr | 130.8 | 130.8 | 0 | 0 | 2004-07-01 | 2005-02-01 | 2005-12-01 |  | 2007-12-01 | 2013-02-01 | 1938114 | 0 | 1938114 | 1938114 | 100% | 0 | 0 | 0 | 145359 | 0 | 145359 | 0 | 0 | Financially completed in 2013. |  | 2004 |  | Investment
FIN | UNDP | Total methyl bromide phase-out used as a fumigant in melons, cut flowers, bananas, tobacco seedbeds and nurseries, excluding QPS applications (tranche IV) | Multi-Year | LAC | COS | FUM | 49 | INV | 36 | N | I | MeBr | 63.6 | 63.6 | 0 | 0 | 2006-07-01 | 2008-01-01 | 2008-12-01 |  | 2009-12-01 | 2013-12-01 | 969057 | 0 | 969057 | 969057 | 100% | 0 | 0 | 0 | 72679 | 0 | 72679 | 0 | 0 | Financially completed in 2013. |  | 2006 |  | Investment
FIN | UNDP | Total methyl bromide phase-out used as a fumigant in melons, cut flowers, bananas, tobacco seedbeds and nurseries, excluding QPS applications (tranche V) | Multi-Year | LAC | COS | FUM | 59 | INV | 43 | N | I | MeBr | 174 | 174 | 0 | 0 | 2009-11-01 | 2010-04-01 | 2013-11-01 |  | 2014-06-01 | 2015-10-01 | 726791 | -1587 | 725204 | 725204 | 100% | 0 | 0 | 0 | 54509 | -119.02 | 54389.9757 | 0.0043 | 0 | Financially Completed in 2015. | Follow up activities with farmers to maintain zero consumption of MB were continued. Technical assistance is provided in areas where farmers have encountered challenges with the alternatives. | 2009 |  | Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | LAC | COS | PHA | 48 | PRP | 35 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2006-10-01 | 2007-04-01 |  | 2007-07-01 | 2010-07-01 | 30000 | -2379.32 | 27620.68 | 27621 | 100% | -0.32 | 0 | 0 | 2250 | -178.45 | 2071.575 | -0.025 | 0 | Financially completed in 2010. |  | 2006 |  | Investment
FIN | UNDP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | COS | PHA | 52 | INV | 37 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-02-01 | 2009-07-01 |  | 2008-12-01 | 2013-02-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 15000 | 0 | 15000 | 0 | 0 | Financially completed in 2013. |  | 2007 |  | Investment
FIN | UNDP | Terminal phase-out management plan for Annex A Group I substances (second tranche) | Multi-year | LAC | COS | PHA | 55 | INV | 40 | N | I | CFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-05-01 | 2010-07-01 |  | 2010-08-01 | 2013-05-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 15000 | 0 | 15000 | 0 | 0 | Financially completed in 2013. |  | 2008 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | COS | PHA | 55 | PRP | 39 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2011-10-01 | 2014-04-01 | 150000 | -1958 | 148042 | 148042 | 100% | 0 | 0 | 0 | 11250 | -146.85 | 11103.15 | 0 | 0 | Financially completed in 2014. | Completed in 2011. HPMP approved by the 64th Executive Committee Meeting Some final invoices pending. | 2008 |  | Investment
FIN | UNDP | Terminal phase-out management plan for Annex A Group I substances (third tranche) | Multi-Year | LAC | COS | PHA | 58 | INV | 42 | N | I | CFC | 37.5 | 37.5 | 0 | 0 | 2009-07-01 | 2010-02-01 | 2011-07-01 |  | 2011-12-01 | 2013-05-01 | 165000 | 0 | 165000 | 165000 | 100% | 0 | 0 | 0 | 12375 | 0 | 12375 | 0 | 0 | Financially completed in 2013. |  | 2009 |  | Investment
FIN | UNDP | HCFC phase-out management plan (foam sector) (stage I, first tranche) | Multi-Year | LAC | COS | PHA | 64 | INV | 45 | N | I | HCFC | 14 | 14 | 0 | 0 | 2011-07-01 | 2012-04-01 | 2013-07-01 |  | 2013-07-01 | 2014-03-01 | 593523 | -1 | 593522 | 593522 | 100% | 0 | 0 | 0 | 44514 | -0.08 | 44513.925 | -0.005 | 0 | Financially Completed in 2014. | Completed in 2013. PCR is being finalized. HOPs are being finalized | 2011 |  | Investment
FIN | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | COS | PHA | 64 | INV | 46 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-04-01 | 2013-07-01 |  | 2014-06-01 | 2015-02-01 | 168000 | 0 | 168000 | 168000 | 100% | 0 | 0 | 0 | 12600 | 0 | 12600 | 0 | 0 | Financially Completed in 2015. | HPMP activities continue to be implemented. An agreement was made with SENAI in Brazil to provide south-south collaboration between training schools. | 2011 |  | Investment
COM | UNDP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | LAC | COS | PHA | 70 | INV | 48 | N | I | HCFC | 0 | 0 | 0 | 0 | 2013-07-01 | 2013-09-01 | 2015-07-01 |  | 2016-04-01 |  | 168000 | 0 | 168000 | 168000 | 100% | 0 | 0 | 0 | 12600 | 0 | 12600 | 0 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): 149 technicians trained in good practices. 90 technicians received the official certification provided by the National Education Institute. 8 University teachers trained in the use of "cool pack" software. Specialized training programme for 18 technicians in ICE with special needs. Prodoc signed (actual/planned, yes/no and date):Signed earlier Missions undertaken (actual/planned):1 of 1 TOR for consultants/subcontracts completed (actual/planned): 2 of 2 Contract/PO/MOA agreements signed: 1 of 1 First disbursement date (actual/planned): 41518Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | Continued training of technicians around the country. | 2013 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, third tranche) | Multi-year | LAC | COS | PHA | 74 | INV | 50 | N | I | HCFC | 1.4 | 0 | 0 | 0 | 2015-05-01 | 2015-11-01 | 2018-05-01 | 2017-05-01 |  |  | 62000 | 0 | 62000 | 11672.62 | 18.83% | 50327.38 | 0 | 20130.952 | 4650 | 0 | 875.4465 | 3774.5535 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): 149 technicians trained in good practices. 90 technicians received the official certification provided by the National Education Institute. 8 University teachers trained in the use of "cool pack" software. Specialized training programme for 18 technicians in ICE with special needs. Prodoc signed (actual/planned, yes/no and date):Signed earlier Missions undertaken (actual/planned):1 of 1 TOR for consultants/subcontracts completed (actual/planned): 2 of 2 Contract/PO/MOA agreements signed: 1 of 1 First disbursement date (actual/planned): Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | Continued training of technicians around the country. | 2015 |  | Investment
ONG | UNDP | Verification report for stage I of HCFC phase-out management plan | Individual | LAC | COS | PHA | 75 | TAS | 54 | N | I | HCFC | 0 | 0 | 0 | 0 | 2015-11-01 | 2016-05-01 | 2017-03-01 | 2017-03-01 |  |  | 30000 | 0 | 30000 | 13895.46 | 46.32% | 16104.54 | 0 | 6441.816 | 2700 | 0 | 1250.5914 | 1449.4086 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): First mission of int expert conducted. Prodoc signed (actual/planned, yes/no and date):42430 Missions undertaken (actual/planned):1 of 1 TOR for consultants/subcontracts completed (actual/planned): 1 of 1 Contract/PO/MOA agreements signed: NA First disbursement date (actual/planned): Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | Additional mission will take place to update verification report with latest figure prior to submission of next tranche request. | 2015 |  | Non-Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | COS | REF | 08 | TAS | 04 | A | I | CFC | 37.1 | 37.1 | 0 | 0 | 1992-10-01 | 1997-01-01 | 1998-09-01 |  | 2000-06-01 | 2004-03-01 | 88000 | 233693 | 321693 | 321693 | 100% | 0 | 0 | 0 | 11440 | 30380.09 | 41820.09 | 0 | 0 | Completed in 2000. Financially completed in 2004. |  | 1992 | 1999-08-01 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Atlas Eléctrica S.A. | Individual | LAC | COS | REF | 18 | INV | 08 | A | D | CFC | 27 | 27 | 0 | 0 | 1995-11-01 | 1997-02-01 | 1997-04-01 |  | 1998-05-01 | 1999-12-01 | 375000 | 0 | 375000 | 375000 | 100% | 0 | 0 | 0 | 48750 | 0 | 48750 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1995 |  | Investment
FIN | USA | Mobile air conditioning (MAC) and refrigerated transport (RT) |  | LAC | COS | REF | 19 | DEM | 09 | A | I | CFC | 10 |  | 0 |  | 1996-05-01 | 1996-09-01 | 1997-12-01 |  | 2000-05-01 | 2000-09-01 | 130000 | 0 | 130000 | 130000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Training workshop and equipment delivery are planned for May 2000. |  | 1995 | 1997-12-01
FIN | UNDP | Project preparation for 2 projects in commercial refrigeration subsector | Individual | LAC | COS | REF | 24 | PRP | 13 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-05-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 and CFC-12 by conversion to HCFC-141b and HFC-134a respectively in the manufacture of commercial refrigeration equipment at Refrigeración Omega, S.A. | Individual | LAC | COS | REF | 27 | INV | 17 | A | I | CFC | 4.3 | 4.3 | 0 | 0 | 1999-03-01 | 1999-09-01 | 2002-04-01 |  | 2001-12-01 | 2003-05-01 | 159883 | 0 | 159883 | 159883 | 100% | 0 | 0 | 0 | 20784.79 | 0 | 20784.79 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Phaseout of CFC-11 and CFC-12 by conversion to HCFC-141b and HFC-134a respectively in the manufacture of commercial refrigeration equipment at Refrigeración Wimmer Hnos., S.A. | Individual | LAC | COS | REF | 27 | INV | 18 | A | I | CFC | 4.6 | 4.6 | 0 | 0 | 1999-03-01 | 1999-09-01 | 2002-04-01 |  | 2001-12-01 | 2003-05-01 | 186217 | 0 | 186217 | 186217 | 100% | 0 | 0 | 0 | 24208.21 | 0 | 24208.21 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Phaseout of CFC-11 and CFC-12 by conversion to HCFC-141b and HFC-134a respectively in the manufacture of commercial refrigeration equipment at Refrigeración Hermanos González, S.A. | Individual | LAC | COS | REF | 27 | INV | 19 | A | I | CFC | 4.4 | 4.4 | 0 | 0 | 1999-03-01 | 1999-09-01 | 2002-04-01 |  | 2001-12-01 | 2003-04-01 | 185168 | 0 | 185168 | 185168 | 100% | 0 | 0 | 0 | 24071.84 | 0.09 | 24071.93 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
CLO | UNDP | Phaseout of CFC-11and CFC-12 by conversion to HCFC-141b and HFC-134a respectively in the manufacture of commercial refrigeration equipment at Quena S.A. | Individual | LAC | COS | REF | 27 | INV | 20 | A | I | CFC | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-09-01 | 2002-04-01 |  |  | 2002-11-01 | 219430 | -111322 | 108108 | 108108 | 100% | 0 | 0 | 0 | 28525.9 | -14471.86 | 14054.04 | 0 | 0 | Canceled in 2002. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Technical assistance for RMP survey and preparation | RMP-Component | LAC | COS | REF | 32 | TAS | 23 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2002-07-01 | 2003-01-01 |  | 2005-12-01 | 2010-10-01 | 40000 | -14642.37 | 25357.63 | 25358 | 100% | -0.37 | 0 | 0 | 5200 | -1903.51 | 3296.54 | -0.05 | 0 | Financially completed in 2010. |  | 2000 | 2003-01-01 | Non-Investment
FIN | UNDP | Implementation of the RMP: incentive programme for the commercial, industrial, and fishing fleet refrigeration end-user sub-sector | RMP-Component | LAC | COS | REF | 41 | TAS | 27 | N | I | CFC | 67.5 | 67.5 | 0 | 0 | 2003-12-01 | 2005-07-01 | 2006-12-01 |  | 2007-12-01 | 2010-07-01 | 200000 | -1012.02 | 198987.98 | 198988 | 100% | -0.02 | 0 | 0 | 18000 | -91.08 | 17908.92 | 0 | 0 | Financially completed in 2010. |  | 2003 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: technical assistance for the refrigeration servicing sub-sector | RMP-Component | LAC | COS | REF | 41 | TAS | 28 | N | I | CFC | 60.8 | 60.8 | 0 | 0 | 2003-12-01 | 2005-07-01 | 2006-12-01 |  | 2007-12-01 | 2010-07-01 | 180000 | -516.67 | 179483.33 | 179483 | 100% | 0.33 | 0 | 0 | 16200 | -46.5 | 16153.47 | 0.03 | 0 | Financially completed in 2010. |  | 2003 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: ensuring the effectiveness of all the project proposed with the RMP project | RMP-Component | LAC | COS | REF | 41 | TAS | 31 | N | I | CFC | 20.3 | 20.3 | 0 | 0 | 2003-12-01 | 2005-07-01 | 2007-12-01 |  | 2007-12-01 | 2010-07-01 | 60000 | -2685.69 | 57314.31 | 57314 | 100% | 0.31 | 0 | 0 | 5400 | -241.71 | 5158.26 | 0.03 | 0 | Financially completed in 2010. |  | 2003 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: technical assistance for certification and licensing of refrigeration technicians | RMP-Component | LAC | COS | REF | 41 | TRA | 29 | N | I | CFC | 33.8 | 33.8 | 0 | 0 | 2003-12-01 | 2005-07-01 | 2007-12-01 |  | 2007-12-01 | 2010-07-01 | 100000 | -796.64 | 99203.36 | 99203 | 100% | 0.36 | 0 | 0 | 9000 | -71.7 | 8928.27 | 0.03 | 0 | Financially completed in 2010. |  | 2003 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: technical assistance for training of customs officers | RMP-Component | LAC | COS | REF | 41 | TRA | 30 | N | I | CFC | 30.4 | 30.4 | 0 | 0 | 2003-12-01 | 2005-07-01 | 2005-12-01 |  | 2007-12-01 | 2010-07-01 | 90000 | -1004.24 | 88995.76 | 88996 | 100% | -0.24 | 0 | 0 | 8100 | -90.38 | 8009.64 | -0.02 | 0 | Financially completed in 2010. |  | 2003 |  | Non-Investment
ONG | UNDP | Preparation for HCFC phase-out investment activities (refrigeration manufacturing sector) | Individual | LAC | COS | REF | 57 | PRP | 41 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2011-04-01 | 2010-03-01 | 2017-01-01 |  |  | 60000 | 0 | 60000 | 25791 | 42.98% | 34209 | 0 | 13683.6 | 4500 | 0 | 1934.325 | 2565.675 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): No activities in 2016. Foam sector plan will be developed once System House projects have advanced implementation in the region. Prodoc signed (actual/planned, yes/no and date):Signed earlier Missions undertaken (actual/planned):0 of 0 TOR for consultants/subcontracts completed (actual/planned): 0 of 0 Contract/PO/MOA agreements signed: NA First disbursement date (actual/planned): 40634Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | NA | 2009 |  | Investment
COM | UNDP | Preparation of a demonstration project for the transition of HCFC-22-based refrigerant unit to NH3 system in cold chambers | Individual | LAC | COS | REF | 74 | PRP | 51 | N | I | HCFC | 0 | 0 | 0 | 0 | 2015-05-01 | 2015-11-01 | 2016-03-01 |  | 2016-12-01 |  | 40000 | 0 | 40000 | 16929.73 | 42.32% | 23070.27 | 5400 | 19609.7295 | 2800 | 0 | 1185.0811 | 1614.9189 | 378 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Two experts missions to Costa Rica. Two study tours to Ecuador and US to learn about new technology. Project approved by ExCom. Prodoc signed (actual/planned, yes/no and date):Signed earlier Missions undertaken (actual/planned):4 of 4 TOR for consultants/subcontracts completed (actual/planned): 1 of 1 Contract/PO/MOA agreements signed: NA First disbursement date (actual/planned): Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | Pending payments cleared. | 2015 |  | Non-Investment
ONG | UNDP | Demonstration of the application of an ammonia/carbon dioxide refrigeration system in replacement of HCFC-22 for the medium-sized producer and retail store of Premezclas Industriales S.A. | Individual | LAC | COS | REF | 76 | DEM | 55 | N | I | HCFC | 0 | 0 | 0 | 0 | 2016-05-01 | 2016-10-01 | 2017-07-17 | 2017-02-01 |  |  | 524000 | 0 | 524000 | 7964.24 | 1.52% | 516035.76 | 0 | 206414.304 | 36680 | 0 | 557.4968 | 36122.5032 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): During 2016, ProDoc was prepared and signed. Discussions on the work plan and implementation arreglements were conducted. Prodoc signed (actual/planned, yes/no and date):Yes, on September . Missions undertaken (actual/planned):0 of 0 TOR for consultants/subcontracts completed (actual/planned): 1 of 1 Contract/PO/MOA agreements signed: 1 of 1 First disbursement date (actual/planned): 42644Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve:N/A | The evaluation of proposal for supplying the equipment has been conducted, as well as the signing of the contract. |  |  | Investment
FIN | UNDP | ODS reconnaissance study | Individual | LAC | COS | SEV | 04 | TAS | 01 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-10-01 | 1992-06-01 |  | 1992-06-01 | 1997-12-01 | 20000 | 3422 | 23422 | 23422 | 100% | 0 | 0 | 0 | 2600 | 444.86 | 3044.86 | 0 | 0 | Completed in 1992. Financially completed in 1997. |  | 1991 |  | Non-Investment
FIN | UNDP | Country programme preparation | Individual | LAC | COS | SEV | 06 | CPG | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-01 | 1992-09-01 |  | 1992-09-01 | 1997-12-01 | 20000 | 2909 | 22909 | 22909 | 100% | 0 | 0 | 0 | 2600 | 378.17 | 2978.17 | 0 | 0 | Completed in 1992. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Institutional strengthening: Establishment of COGO | Individual | LAC | COS | SEV | 08 | INS | 03 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1993-08-01 | 1995-10-01 |  | 1996-12-01 | 1999-12-01 | 213160 | 0 | 213160 | 213160 | 100% | 0 | 0 | 0 | 27710.8 | 0 | 27710.8 | 0 | 0 | Completed in 1996. Financially completed in 1999. |  | 1992 |  | Non-Investment
FIN | UNDP | Assistance in project preparation | Individual | LAC | COS | SEV | 08 | PRP | 07 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1993-10-01 | 1995-10-01 |  | 1997-05-01 | 1998-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1997. Financially completed in 1998. |  | 1992 |  | Investment
FIN | UNDP | Renewal of institutional strengthening project (Phase II) | Individual | LAC | COS | SEV | 21 | INS | 10 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1999-02-01 |  | 1999-02-01 | 2000-12-01 | 108087 | 0 | 108087 | 108087 | 100% | 0 | 0 | 0 | 14051.31 | 0 | 14051.31 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1997 |  | Non-Investment
FIN | UNDP | Project preparation in the foam, refrigeration and solvent sectors | Individual | LAC | COS | SEV | 21 | PRP | 11 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1998-04-01 | 1997-12-01 |  | 1998-12-01 | 2000-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Renewal of institutional strengthening project for the phaseout of ozone depleting substance under the Montreal Protocol (Phase III) | Individual | LAC | COS | SEV | 27 | INS | 16 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2001-04-01 |  | 2001-12-01 | 2005-11-01 | 108087 | -2519 | 105568 | 105568 | 100% | 0 | 0 | 0 | 14051.31 | -327.46 | 13723.8472 | 0.0028 | 0 | Completed in 2001. Financially completed in 2005. |  | 1999 |  | Non-Investment
FIN | UNDP | Renewal of the institutional strengthening project | Individual | LAC | COS | SEV | 35 | INS | 26 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-02-01 | 2004-01-01 |  | 2004-12-01 | 2007-06-01 | 108087 | -3863 | 104224 | 104224 | 100% | 0 | 0 | 0 | 14051.31 | -502.23 | 13549.0843 | -0.0043 | 0 | Completed in 2004. Financially completed in 2007. |  | 2001 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project | Individual | LAC | COS | SEV | 41 | INS | 32 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-07-01 | 2005-12-01 |  | 2006-12-01 | 2008-08-01 | 140513 | -776 | 139737 | 139737 | 100% | 0 | 0 | 0 | 10538 | -58.2 | 10479.8026 | -0.0026 | 0 | Completed in 2006. Financially Completed in 2008. |  | 2003 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase VI) | Individual | LAC | COS | SEV | 47 | INS | 34 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-04-01 | 2008-12-01 |  | 2008-02-01 | 2009-07-01 | 140513 | -2445 | 138068 | 138068 | 100% | 0 | 0 | 0 | 10538 | -183.37 | 10354.6333 | -0.0033 | 0 | Completed in 2008.Financially completed in 2009. |  | 2005 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase VII) | Individual | LAC | COS | SEV | 53 | INS | 38 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-02-01 | 2009-11-01 |  | 2010-09-01 | 2011-08-01 | 140513 | -12595.67 | 127917.33 | 127917 | 100% | 0.33 | 0 | 0 | 10538 | -944.63 | 9593.3426 | 0.027449 | 0 | Completed in 2009. Financially completed in 2011. |  | 2007 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase VIII) | Individual | LAC | COS | SEV | 59 | INS | 44 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-03-01 | 2011-12-01 |  | 2011-12-01 | 2014-02-01 | 70257 | 70245 | 140502 | 140502 | 100% | 0 | 0 | 0 | 5269 | 5268.1 | 10537.1 | 0 | 0 | Financially completed in 2014. | Final invoices pending. | 2009 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase IX: 1/2012-12/2013) | Individual | LAC | COS | SEV | 65 | INS | 47 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-06-01 | 2013-12-01 |  | 2014-04-01 | 2015-11-01 | 140513 | 0 | 140513 | 140513 | 100% | 0 | 0 | 0 | 10538 | 0 | 10538 | 0 | 0 | Financially Completed in 2015. | As planned, 2013 data is being revised. | 2011 |  | Non-investment
COM | UNDP | Extension of institutional strengthening project (phase X: 1/2014-12/2015) | Individual | LAC | COS | SEV | 71 | INS | 49 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2013-12-01 | 2014-03-01 | 2015-12-01 |  | 2015-12-01 |  | 140513 | 0 | 140513 | 136185.96 | 96.92% | 4327.04 | 0 | 3677.984 | 9836 | 0 | 9533.1044 | 302.8956 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2015. |  | 2013 |  | Non-Investment
ONG | UNDP | Survey of ODS alternatives at the national level | Individual | LAC | COS | SEV | 74 | TAS | 52 | N | I | HFC | 0 | 0 | 0 | 0 | 2015-05-01 | 2016-02-01 | 2016-11-01 | 2017-02-01 |  |  | 70000 | 0 | 70000 | 52816.1 | 75.45% | 17183.9 | 0 | 6873.56 | 6300 | 0 | 4753.449 | 1546.551 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Project team hired. Methodology for conducting the survey was discussed and approved. Survey conducted and draft report prepared. Prodoc signed (actual/planned, yes/no and date):The agreement has been signed earlier. Missions undertaken (actual/planned):0 of 0 TOR for consultants/subcontracts completed (actual/planned): 1 of 1 Contract/PO/MOA agreements signed: 1 of 1 First disbursement date (actual/planned): 42401Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve:N/A | Final report prepared. Excel tables with survey's results completed and submitted. | 2015 |  | Non-Investment
ONG | UNDP | Extension of institutional strengthening project (phase XI: 1/2016-12/2017) | Individual | LAC | COS | SEV | 75 | INS | 53 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2015-11-01 | 2016-05-01 | 2017-12-01 | 2017-12-01 |  |  | 179857 | 0 | 179857 | 44990.46 | 25.01% | 134866.54 | 0 | 53946.616 | 12590 | 0 | 3149.3347 | 9440.6653 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Standard IS activities implemented. Celebration of Ozone day. Strong awareness raising component. Control of licenses and cuotas. Prodoc signed (actual/planned, yes/no and date):42430 Missions undertaken (actual/planned):1 of 1 TOR for consultants/subcontracts completed (actual/planned): 1 of 1 Contract/PO/MOA agreements signed: 1 of 1 First disbursement date (actual/planned): 42491Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | Standaard IS activities implemented in Costa Rica. | 2015 |  | Non-Investment
FIN | UNDP | Seminar/workshop in the solvent sector | Individual | LAC | COS | SOL | 08 | TRA | 06 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-11-01 | 1995-10-01 |  | 1996-11-01 | 2003-04-01 | 21120 | -3219 | 17901 | 17901 | 100% | 0 | 0 | 0 | 2745.6 | -418.47 | 2327.13 | 0 | 0 | Completed in 1996. Financially completed in 2003. |  | 1992 |  | Non-Investment
FIN | UNDP | Technical assistance for Guandong aerosols investment project and investigation of non-ODS filling technology and LPG purification | Individual | ASP | CPR | ARS | 06 | TAS | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1996-12-01 | 1998-12-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1992 |  | Non-Investment
FIN | IBRD | Shanghai CFC conversion to LPG propellant | Individual | ASP | CPR | ARS | 07 | INV | 14 | N | I | CFC | 6300 | 6300 | 0 | 0 | 1992-06-01 | 1994-05-01 | 1994-06-01 |  | 1996-09-01 | 1997-06-01 | 1900000 | 409000 | 2309000 | 2309000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | CFC consumption in aerosol banned as of Jan. 1, 1998. |  |  | 1997-06-01 | INV | 0
FIN | IBRD | Tianjin CFC conversion to LPG propellant | Individual | ASP | CPR | ARS | 07 | INV | 23 | N | I | CFC | 6300 | 6300 | 0 | 0 | 1992-06-01 | 1994-05-01 | 1994-06-01 |  | 1996-03-01 | 1997-06-01 | 2500000 | 270000 | 2770000 | 2770000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | CFC consumption in aerosol banned as of Jan. 1, 1998. |  |  | 1997-06-01 | INV | 0
FIN | IBRD | Zhongshan Fine Chemical Aerosol Filling Center CFC-12 substitution project | Individual | ASP | CPR | ARS | 13 | INV | 79 | N | I | CFC | 4067 | 4067 | 0 | 0 | 1994-07-01 | 1996-03-01 | 1996-07-01 |  | 1997-05-01 | 1998-10-01 | 1351360 | -319 | 1351041 | 1351041 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed; PCR submitted to 29th ExCom. |  |  | 1998-06-01 | INV | 0
FIN | IBRD | Umbrella project to complete CFC phaseout in general purpose aerosols at NCLI and Fujiang Light Industry Co. | Individual | ASP | CPR | ARS | 24 | INV | 244 | N | I | CFC | 1224 | 1224 | 0 | 0 | 1998-03-01 | 2000-03-01 | 2000-04-01 |  | 2002-12-01 | 2004-05-01 | 547675 | 0 | 547675 | 547675 | 100% | 0 | 0 |  | 71197.75 | 0 | 71197.75 | 0 | 0 | Project financially completed. |  |  | 2002-06-01 | INV | 0
FIN | IBRD | Project preparation for pharmaceutical aerosol |  | ASP | CPR | ARS | 43 | PRP | 415 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2006-02-01 | 2005-07-01 |  | 2007-03-01 | 2007-07-01 | 135500 | 0 | 135500 | 135500 | 100% | 0 | 0 |  | 10163 | 0 | 10163 | 0 | 0 | Completed technically and financially. |  |  |  | Non-INV | 0
FIN | UNIDO | Preparation of a MDI sector plan | Individual | ASP | CPR | ARS | 44 | PRP | 422 | A | I |  | 0 | 0 |  |  | 2004-12-01 | 2007-01-01 | 2005-12-01 |  | 2007-07-01 | 2009-05-01 | 90000 | -377 | 89623 | 89623.21 | 100% | -0.21 | 0 |  | 6750 | -28 | 6722 | 0 | 0 | FIN
FIN | IBRD | Phase-out of CFC consumption in the pharmaceutical aerosol sector (2007-2008 biennial programme) | One off phaseout | ASP | CPR | ARS | 51 | INV | 447 | N | I | CFC | 485.1 | 485.1 | 0 | 0 | 2007-03-01 | 2008-12-01 | 2011-03-01 |  | 2015-05-01 | 2015-06-01 | 6000000 | 0 | 6000000 | 6000000 | 100% | 0 | 0 |  | 450000 | 0 | 450000 | 0 | 0 | Project completed. Final payment for the calibration standard gas was made in Jun 15. All activities physically and financially completed by Jun 15. DIA has prepared a draft completion report which is under review and revision by SFDA. Final PCR will be ready in Sep 16. |  |  |  | INV | 0
ONG | UNIDO | Sector plan for phase-out of CFCs consumption in MDI sector | Individual | ASP | CPR | ARS | 56 | INV | 473 | A | I | CFC | 322.5 | 322.5 |  |  | 2008-11-01 | 2009-10-01 | 2013-12-31 | 2018-02-01 |  |  | 13500000 | 0 | 13500000 | 13178270.93 | 97.62% | 321729.07 | 270571.79 | 20000 | 1012500 | 0 | 988370 | 24130 | 20293 | (-) 33 ODS Phase-out contracts have been signed with 25 enterprises, whose CFC consumption is composed of 99.45% in baseline year 2007. (-) The amount of annual CFC consumption in 2015 has not been reported yet. (-) TA activities, public awareness and site supervision activities continue with sub-contracts signed with service providers. Milestones achieved: Milestone 3: Yes - ODS licensing system is operational and effective. Milestone 4: Yes - Implementation of monitoring system completed. Milestone 5: Yes - Public awareness is continued. Mission took place to discuss on plan of action for future activities. It was agreed to implement the following actions towards next goals: (-) Call for the national steering committee in 2016 and discuss on remaining activities. (-) To conduct the TA activity--Sites supervision of MDI manufactures for CFC consumption in 2017; (-) Preparation of new set of MDI standards, in particular reviewing the registration procedures for HFA MDI. | - Activities ongoing as planned: Steering committee decided on procedure to monitor all MDI manufacturers and assess their status and progresses with MDI-free products. - FECO, in cooperation with the health authority, will initiate an assessment on standards for HFA MDI. - Planned completion date is confirmed. |  | 2015-12-01 | INV |  | Continued Monitoring
FIN | IBRD | Verification of production of CFCs for essential use | Individual | ASP | CPR | ARS | 62 | TAS | 505 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-11-01 | 2011-05-31 |  | 2011-09-01 | 2011-11-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 4500 | 0 | 4500 | 0 | 0 | Verification of 2010 CFC production for EUN consumption was conducted in accordance with Dec. 60/47 at the only one remaining CFC producer starting in May 11. Report submitted to the 65th ExCom. |  |  |  | Non-INV | 0
FIN | UNIDO | Preparation for pilot demonstration project on ODS waste management and disposal | Individual | ASP | CPR | DES | 59 | PRP | 494 | A | I |  | 0 | 0 |  |  | 2009-11-01 | 2010-09-01 | 2011-05-31 |  | 2012-12-01 | 2012-12-01 | 85000 | -407 | 84593 | 84592.8 | 100% | 0.2 | 0 |  | 6375 | -31 | 6344 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | Pilot demonstration project on ODS waste management and disposal | Individual | ASP | CPR | DES | 67 | DEM | 520 | A | I |  | 0 | 0 |  |  | 2012-07-01 | 2014-10-01 | 2015-01-31 | 2017-12-01 |  |  | 1227885 | 0 | 1227885 | 1227885 | 100% | 0 | 0 |  | 85952 | 0 | 85952 | 0 | 0 | - In March 2016, a meeting was held between FECO and EPBs on the progress of activities. - The provinces of Shangai and Chongqing disposed first batches of ODS. Shanghai: 819.5 kg in 2015 and 1,308 kg in 2016. Chongqing: 5,144 kg in 2016. - In Jiangsu and Guangdong, the EPB has targeted a disposal company. - UNIDO organized a meeting to China in October to monitor project progressed. Out of the planned 192t, it was indicated that 18t have been disposed by the meeting date. - The municipality of Shanghai certified disposal of 12t of CFC11 and 0.87t of CFC12 in the year 2015. Furthermore, additional 12t of CFC11 and 0.4t of CFC11 were disposed as of October. - The city of Shandong planned to dispose a total of 20t in 2016 and progresses are encouraging: three centers for the disposal of appliances have been identified and agreement was reached with them to proceed with the ODS disposal from the refrigeration part as well as from the foam. The province of Tianjin completed the survey and could not start with the disposal activities. - FECO organized a meeting with the relevant municipalities and provinces to agree on a plan of action before the end of the year 2016. Actions towards next goals: (-) Receive latest progress Reports to be submitted by local EPBs (continuous monitoring); Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - UNIDO discussed with FECO on project development and agreed to place a monitoring visit to the relevant municipalities/provinces in the first half of 2017. - The project will be completed in 2017. |  |  | INV
ONG | Japan | Pilot demonstration project on ODS waste management and disposal | Individual | ASP | CPR | DES | 67 | DEM | 521 | A | I |  | 0 |  | 0 |  | 2012-07-01 | 2014-10-01 | 2015-01-01 | 2017-12-01 |  |  | 900000 | 0 | 900000 | 48846 | 5.427% | 851154 | 851154 | 851154 | 109000 | 0 | 5916 | 103084 | 103084 | - In March 2016, a meeting was held between FECO and EPBs on the progress of activities. - The provinces of Shangai and Chongqing disposed first batches of ODS. Shangai: 819.5 kg in 2015 and 1,308 kg in 2016. Chongqing: 5,144 kg in 2016. - In Jiangsu and Guangdong, the EPB has targeted a disposal company. - UNIDO organised a meeting to China in October to monitor project progressed. Out of the planned 192t, it was indicated that 18t have been disposed by the meeting date. - The municipality of Shanghai certified disposal of 12t of CFC11 and 0.87t of CFC12 in the year 2015. Furthermore, additional 12t of CFC11 and 0.4t of CFC11 were disposed as of October 2016. - The city of Shandong planned to dispose a total of 20t in 2016 and progresses are encouraging: three centres for the disposal of appliances have been identified and agreement was reached with them to proceed with the ODS disposal from the refrigeration part as well as from the foam. - The province of Tianjin completed the survey, but could not start with the disposal activities. - FECO organised a meeting with the relevant municipalities and provinces to agree on a plan of action before the end of the year 2016. Actions towards next goals: - Receive latest progress Reports to be submitted by local EPBs (continuous monitoring); - Disposal activities to get started in the province of Tianjin. Was there any delay during the reporting year? Yes Reason for the delay: Disposal activities in the province of Tianjin could not start yet. Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - UNIDO discussed with FECO on project development and agreed to place a monitoring visit to the relevant municipalities/provinces in the first half of 2017. - Disposal activities in the province of Tianjin start in 2017. - The project is planned to be completed before the end of 2017. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | 2013 |  | Investment
FIN | UNDP | Technical assistance for CFC-11 substitute technology in flexible polyurethane foam | Individual | ASP | CPR | FOA | 06 | TAS | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-07-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Quality control testing on adoption of CFC-11 substitutte technology in a production line for home refrigerators | Individual | ASP | CPR | FOA | 06 | TAS | 07 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 65000 | -4981 | 60019 | 60019 | 100% | 0 | 0 | 0 | 8450 | -647.53 | 7802.47 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Technical assistance for CFC-11 substitute technology in rigid polyurethane foam | Individual | ASP | CPR | FOA | 06 | TAS | 13 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-06-01 |  | 1993-09-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | IBRD | Zhejiang foam plant conversion to butane | Individual | ASP | CPR | FOA | 07 | INV | 15 | N | I | CFC | 400 | 400 | 0 | 0 | 1992-06-01 | 1994-04-01 | 1994-06-01 |  | 1995-09-01 | 1996-09-01 | 1042000 | -49000 | 993000 | 993000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. ODP phaseout target reached. |  |  | 1995-09-01 | INV | 0
FIN | IBRD | Project I: 50% CFC foam | Individual | ASP | CPR | FOA | 07 | INV | 16 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1994-06-01 | 1994-06-01 |  | 1996-06-01 | 1996-06-01 | 645000 | 0 | 645000 | 645000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Fully disbursed and distributed to 50% foam projects that were approved a year after this approval. Disbursed amount appeared to exceed grant by $1000. Thru Dec. 37/14, the Bank was able to return the $1,000 to the MLF in the context of the reconciliation of the Accounts of the Fund at the 38th ExCom (Dec. 38/9). |  |  | 1996-12-01 | INV | 0
FIN | UNDP | Technical assistance for the Beijing Household Electric Appliances Research Institute (Bheari) | Individual | ASP | CPR | FOA | 09 | TAS | 22 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1994-10-01 | 1995-06-01 |  | 1998-10-01 | 2003-07-01 | 0 | 444945 | 444945 | 444945 | 100% | 0 | 0 | 0 | 0 | 57843 | 57843 | 0 | 0 | Completed in 1998. Financially completed in 2003. |  | 1993 |  | Non-Investment
FIN | UNDP | Tianjin conversion to CFC-free technology in the manufacture of flexible polyurethane foam | Individual | ASP | CPR | FOA | 10 | INV | 32 | N | I | CFC | 180 | 180 | 0 | 0 | 1993-06-01 | 1993-10-01 | 1994-09-01 |  | 1995-04-01 | 1998-12-01 | 1080000 | -41407 | 1038593 | 1038593 | 100% | 0 | 0 | 0 | 140400 | -5383 | 135017 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1993 |  | Investment
FIN | IBRD | Liming Research and development of polyol and blended polyol production techniques for 50% reduced CFC foam | Individual | ASP | CPR | FOA | 10 | INV | 42 | N | D | CFC | 0 | 0 | 0 | 0 | 1993-06-01 | 1995-01-01 | 1995-06-01 |  | 1996-01-01 | 1996-09-01 | 457000 | 0 | 457000 | 457000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. |  |  | 1996-01-01 | INV | 0
FIN | IBRD | Wuxi production of blended polyol for 50% reduced CFC foam | Individual | ASP | CPR | FOA | 10 | INV | 43 | N | D | CFC | 0 | 0 | 0 | 0 | 1993-06-01 | 1994-11-01 | 1995-06-01 |  | 1995-09-01 | 1997-05-01 | 264000 | 0 | 264000 | 264000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. |  |  | 1995-09-01 | INV | 0
FIN | IBRD | Chengde conversion to 50% reduced CFC foam in insulation panel and in-situ foaming formulations | Individual | ASP | CPR | FOA | 10 | INV | 44 | N | D | CFC | 32 | 50 | 0 | 0 | 1993-06-01 | 1994-11-01 | 1997-06-01 |  | 1994-10-01 | 1996-09-01 | 163000 | 0 | 163000 | 163000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. Actual ODP phaseout exceeded target. |  |  | 1995-06-01 | INV | 0
FIN | IBRD | Dalian conversion to 50% CFC reduced foam in insulation panel | Individual | ASP | CPR | FOA | 10 | INV | 45 | N | D | CFC | 14 | 30 | 0 | 0 | 1993-06-01 | 1995-01-01 | 1995-06-01 |  | 1996-06-01 | 1997-06-01 | 275000 | 0 | 275000 | 275000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. Actual ODP phaseout exceeded target. |  |  | 1996-03-01 | INV | 0
TRF | IBRD | Tianjin conversion to 50% reduced CFC foam in insulation panel | Individual | ASP | CPR | FOA | 10 | INV | 46 | N | I |  | 0 | 0 | 0 | 0 | 1993-06-01 |  | 1995-06-01 |  |  | 1995-07-01 | 443000 | -443000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project Transferred to UNDP. $443,000 credited to the MLF at 17th Meeting. |  |  | 1995-06-01 | INV | 0
FIN | IBRD | Qindao Haier conversion to 50% reduced CFC foam in freezer cabinets | Individual | ASP | CPR | FOA | 10 | INV | 47 | N | D | CFC | 120 | 232 | 0 | 0 | 1993-06-01 | 1994-10-01 | 1995-06-01 |  | 1994-06-01 | 1997-06-01 | 476000 | 0 | 476000 | 476000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. Actual ODP phaseout exceeded target. The factory also began developing 100% CFC-free technology. |  |  | 1994-08-01 | INV | 0
FIN | IBRD | Henan Xinfei conversion to 50% reduced CFC foam in refrigerators | Individual | ASP | CPR | FOA | 10 | INV | 48 | N | D | CFC | 103 | 250 | 0 | 0 | 1993-06-01 | 1995-01-01 | 1995-06-01 |  | 1994-10-01 | 1997-06-01 | 1042000 | 0 | 1042000 | 1042000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. Actual ODP phaseout exceeded target. Funding approved for final conversion to non-ODS. |  |  | 1996-11-01 | INV | 0
FIN | IBRD | Shangling conversion to 50% reduced CFC foam in refrigerators | Individual | ASP | CPR | FOA | 10 | INV | 49 | N | I | CFC | 103 | 244.1 | 0 | 0 | 1993-06-01 | 1995-12-01 | 1995-06-01 |  | 1996-06-01 | 1997-06-01 | 958000 | 0 | 958000 | 958000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. Actual ODP phaseout exceeded target. The factory also began developing 100% CFC-free technology. |  |  | 1996-06-01 | INV | 0
FIN | IBRD | Shuangyan conversion to 50% reduced CFC foam in refrigerators | Individual | ASP | CPR | FOA | 10 | INV | 50 | N | D | CFC | 28 | 63 | 0 | 0 | 1993-06-01 | 1994-10-01 | 1995-06-01 |  | 1993-06-01 | 1997-03-01 | 485000 | 0 | 485000 | 485000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. Actual ODP phaseout exceeded target. |  |  | 1994-03-01 | INV | 0
FIN | IBRD | Shenyang production of blended polyol for 50% reduced CFC foam | Individual | ASP | CPR | FOA | 10 | INV | 51 | N | D | CFC | 0 | 0 | 0 | 0 | 1993-06-01 | 1994-09-01 | 1997-06-01 |  | 1994-08-01 | 1996-12-01 | 165000 | 0 | 165000 | 165000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and commissioned. By using the contingency fund, the factory went one step ahead to develop 100% CFC-free technology. |  |  | 1995-09-01 | INV | 0
FIN | UNDP | Strategy and action programme for the elimination of CFC in the manufacture of foams | Individual | ASP | CPR | FOA | 10 | TAS | 38 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1994-05-01 | 1994-06-01 |  | 1997-07-01 | 2000-06-01 | 200000 | -574 | 199426 | 199426 | 100% | 0 | 0 | 0 | 26000 | -75 | 25925 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1993 |  | Non-Investment
FIN | UNDP | Conversion to CFC free technology in the manufacture of rigid PUF (spray) at Beijing Commercial Machinery Factory (BCMF) | Individual | ASP | CPR | FOA | 11 | INV | 54 | A | I | CFC | 30 | 30 | 0 | 0 | 1993-11-01 | 1994-06-01 | 1994-11-01 |  | 1998-12-01 | 2000-12-01 | 435000 | -91690 | 343310 | 343310 | 100% | 0 | 0 | 0 | 56550 | -11919.7 | 44630.3 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1993 |  | Investment
CLO | UNDP | Conversion to non-CFC technology in the manufacture of flexible and integral skin polyurethane foam at Yanfeng | Individual | ASP | CPR | FOA | 13 | INV | 67 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 |  | 1995-07-01 |  |  | 1995-07-01 | 670000 | -670000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 87100 | -87100 | 0 | 0 | 0 | Canceled in 1995. Financially Completed in 1995. |  | 1994 |  | Investment
FIN | IBRD | Conversion to CFC-free technology in the manufacture of extruded polyethylene and polystyrene foam at Shanghai No. 18 Plastic Product Plant | Individual | ASP | CPR | FOA | 13 | INV | 72 | N | I | CFC | 200 | 200 | 0 | 0 | 1994-07-01 | 1996-09-01 | 1995-07-01 |  | 1998-09-01 | 1998-09-01 | 450000 | 0 | 450000 | 450000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed; PCR submitted to the 27th ExCom. |  |  | 1997-02-01 | INV | 0
FIN | UNDP | Elimination of CFC-12 used in the manufacture of EPE foam sheet at Danshui Huaya Plastics Industries Co. Ltd. | Individual | ASP | CPR | FOA | 13 | INV | 73 | A | R | CFC | 160 | 160 | 0 | 0 | 1994-07-01 | 1995-04-01 | 1995-07-01 |  | 1995-04-01 | 1997-12-01 | 241000 | 0 | 241000 | 241000 | 100% | 0 | 0 | 0 | 31330 | 0 | 31330 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-11 used in the manufacture of rigid polyurethane foam at Tianjin Polyurethane Plastic Plant | Individual | ASP | CPR | FOA | 13 | INV | 74 | N | I | CFC | 130 | 130 | 0 | 0 | 1994-07-01 | 1998-11-01 | 1995-07-01 |  | 2001-08-01 | 2003-07-01 | 690000 | -431333 | 258667 | 258667 | 100% | 0 | 0 | 0 | 89700 | -56073 | 33627 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1994 | 1999-12-01 | Investment
FIN | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at Shanghai No. 6 Plastic Product Plant | Individual | ASP | CPR | FOA | 13 | INV | 75 | N | I | CFC | 105 | 105 | 0 | 0 | 1994-07-01 | 1996-10-01 | 1995-07-01 |  | 1998-06-01 | 1998-12-01 | 687000 | -1292 | 685708 | 685708 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed; PCR submitted to 31th ExCom. |  |  | 1997-02-01 | INV | 0
FIN | UNDP | Elimination of CFC-12 in the manufacture of XPS foam sheet at Guizhou Jinchang Plastics Products Co. Ltd. | Individual | ASP | CPR | FOA | 15 | INV | 100 | A | I | CFC | 50 | 50 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1997-12-01 | 2002-04-01 | 390000 | -117155 | 272845 | 272845 | 100% | 0 | 0 | 0 | 50700 | -15230 | 35470 | 0 | 0 | Completed in 1997. Financially completed in 2002. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of XPS/XPE foam sheet at Hailun Plastic Packaging Material Factory | Individual | ASP | CPR | FOA | 15 | INV | 101 | A | I | CFC | 95 | 95 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1998-11-01 | 2002-04-01 | 321000 | -2 | 320998 | 320998 | 100% | 0 | 0 | 0 | 41730 | -0.26 | 41729.74 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of PE/PS foam sheet at Shanghai Jianhua Electro-Mechanical and Mechanical Company | Individual | ASP | CPR | FOA | 15 | INV | 102 | A | I | CFC | 100 | 100 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1999-11-01 | 2002-04-01 | 280000 | 0 | 280000 | 280000 | 100% | 0 | 0 | 0 | 36400 | 0 | 36400 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1994 | 1999-04-01 | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of XPS/XPE foam sheet at Foshan No. 3 Plastic Factory | Individual | ASP | CPR | FOA | 15 | INV | 103 | A | I | CFC | 360 | 360 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1998-12-01 | 2002-04-01 | 1065000 | -1 | 1064999 | 1064999 | 100% | 0 | 0 | 0 | 138450 | -0.13 | 138449.87 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1994 |  | Investment
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam (slabstock) in Gaofeng Plastic Plant | Individual | ASP | CPR | FOA | 15 | INV | 108 | N | I | CFC | 180 | 180 | 0 | 0 | 1994-12-01 | 1996-10-01 | 1995-12-01 |  | 1999-01-01 | 2002-09-01 | 458400 | 0 | 458400 | 458400 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1999-05-01 | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam (slabstock) at Hebei Dongfeng Plastic Plant | Individual | ASP | CPR | FOA | 15 | INV | 109 | N | I | CFC | 110 | 110 | 0 | 0 | 1994-12-01 | 1996-11-01 | 1995-12-01 |  | 1999-05-01 | 1999-03-01 | 268600 | 0 | 268600 | 268600 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted to 30th ExCom. |  |  | 1999-01-01 | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of extruded polyethylene and polystyrene foam sheet at Lanzhou Plastic Packing Material Factory | Individual | ASP | CPR | FOA | 15 | INV | 83 | N | I | CFC | 200 | 200 | 0 | 0 | 1994-12-01 | 1996-08-01 | 1995-12-01 |  | 1997-08-01 | 1997-11-01 | 222100 | -37 | 222063 | 222063 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed; PCR submitted to ExCom in January 1999. |  |  | 1997-03-01 | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of extruded polyethylene and polystyrene foam sheet at Cangzhou No. 2 Plastic Plant | Individual | ASP | CPR | FOA | 15 | INV | 84 | N | I | CFC | 140 | 140 | 0 | 0 | 1994-12-01 | 1996-08-01 | 1995-12-01 |  | 1998-11-01 | 1999-04-01 | 394000 | 0 | 394000 | 394000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted to the 30th ExCom. |  |  | 1997-03-01 | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam (slabstock) at Beijing Foam Plastic General Factory | Individual | ASP | CPR | FOA | 15 | INV | 85 | N | I | CFC | 100 | 100 | 0 | 0 | 1994-12-01 | 1996-10-01 | 1995-12-01 |  | 1999-11-01 | 1999-11-01 | 720000 | 0 | 720000 | 720000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted December 2000. |  |  | 1999-05-01 | INV | 0
FIN | IBRD | Conversion to CFC-free technology in manufacture of extruded polyethylene and polystyrene foam sheet at Zhengzhou Plastic Plant | Individual | ASP | CPR | FOA | 15 | INV | 86 | N | I | CFC | 260 | 260 | 0 | 0 | 1994-12-01 | 1996-08-01 | 1995-12-01 |  | 2003-04-01 | 2004-05-01 | 267100 | 0 | 267100 | 267100 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  | 1999-09-01 | INV | 0
FIN | UNDP | Elimination of CFC-12 in the manufacture of XPS foam sheet at Shijiazhuang Plastic Cement General Factory | Individual | ASP | CPR | FOA | 15 | INV | 87 | A | I | CFC | 160 | 160 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1998-12-01 | 2002-04-01 | 621000 | 0 | 621000 | 621000 | 100% | 0 | 0 | 0 | 80730 | 0 | 80730 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of PE foam tubing at Suzhou Plastic Works No. 7 | Individual | ASP | CPR | FOA | 15 | INV | 88 | A | I | CFC | 70 | 70 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1997-12-01 | 2002-04-01 | 358000 | -36690 | 321310 | 321310 | 100% | 0 | 0 | 0 | 46540 | -4769.7 | 41770.3 | 0 | 0 | Completed in 1997. Financially completed in 2002. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of EPS foam sheet at Sino-Foreign Joint Stock Shenyang Shenrong Co. | Individual | ASP | CPR | FOA | 15 | INV | 89 | A | I | CFC | 48 | 48 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1999-05-01 | 2002-04-01 | 166700 | -1 | 166699 | 166699 | 100% | 0 | 0 | 0 | 21671 | -0.13 | 21670.87 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1994 | 1999-06-01 | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of XPE foam sheet and netting at Feicheng Plastic Products Factory | Individual | ASP | CPR | FOA | 15 | INV | 90 | A | I | CFC | 150 | 150 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1999-04-01 | 2002-04-01 | 388000 | 0 | 388000 | 388000 | 100% | 0 | 0 | 0 | 50440 | 0 | 50440 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1994 | 1999-04-01 | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of XPS foam sheet at Guangxing Plastics Products Co., Hubei | Individual | ASP | CPR | FOA | 15 | INV | 91 | A | I | CFC | 36 | 36 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1998-12-01 | 2002-04-01 | 375000 | 0 | 375000 | 375000 | 100% | 0 | 0 | 0 | 48750 | 0 | 48750 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of XPS foam sheet at Shenzhen Shentie Plastics Tableware Products Company, Shenzhen | Individual | ASP | CPR | FOA | 15 | INV | 92 | A | I | CFC | 75 | 75 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1997-12-01 | 2002-04-01 | 345000 | 0 | 345000 | 345000 | 100% | 0 | 0 | 0 | 44850 | 0 | 44850 | 0 | 0 | Completed in 1997. Financially completed in 2002. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of XPE netting at Hebei Sixing Polypack Products Co. Ltd., Shijiazhuang | Individual | ASP | CPR | FOA | 15 | INV | 93 | A | I | CFC | 65 | 65 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1998-12-01 | 2002-04-01 | 436000 | -183121 | 252879 | 252879 | 100% | 0 | 0 | 0 | 56680 | -23805.73 | 32874.27 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1994 |  | Investment
FIN | UNDP | Conversion to non-CFC technology in the manufacture of flexible polyurethane foam at Beijing Yanxi | Individual | ASP | CPR | FOA | 15 | INV | 94 | A | I | CFC | 25 | 25 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1995-12-01 |  | 1998-11-01 | 2001-12-01 | 125000 | -31250 | 93750 | 93750 | 100% | 0 | 0 | 0 | 16250 | -4062.5 | 12187.5 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1994 |  | Investment
FIN | UNDP | Conversion to non-CFC technology in the manufacture of flexible polyurethane foam at Faw-Trim | Individual | ASP | CPR | FOA | 15 | INV | 95 | A | I | CFC | 28 | 28 | 0 | 0 | 1994-12-01 | 1996-02-01 | 1995-12-01 |  | 1997-12-01 | 2000-12-01 | 143000 | 0 | 143000 | 143000 | 100% | 0 | 0 | 0 | 18590 | 0 | 18590 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Conversion to non-CFC technology in the manufacture of integral skin polyurethane foam at Hubei Auto Engineering | Individual | ASP | CPR | FOA | 15 | INV | 96 | A | I | CFC | 20 | 20 | 0 | 0 | 1994-12-01 | 1996-02-01 | 1995-12-01 |  | 1997-12-01 | 2000-12-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 | 0 | 19500 | 0 | 19500 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
CLO | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam (slabstock) at Dalian No. 1 | Individual | ASP | CPR | FOA | 15 | INV | 97 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1998-12-01 |  |  | 2000-07-01 | 490000 | -457910 | 32090 | 32090 | 100% | 0 | 0 | 0 | 63700 | -59528 | 4172 | 0 | 0 | Canceled in 1999. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of extruded polystyrene foam sheet at Jinfeng | Individual | ASP | CPR | FOA | 15 | INV | 98 | A | R | CFC | 70 | 70 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1997-12-01 | 2002-04-01 | 235340 | 0 | 235340 | 235340 | 100% | 0 | 0 | 0 | 30594.2 | 0 | 30594.2 | 0 | 0 | Completed in 1997. Financially completed in 2002. |  | 1994 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of extruded polystyrene foam sheet at Jinan | Individual | ASP | CPR | FOA | 15 | INV | 99 | A | I | CFC | 30 | 30 | 0 | 0 | 1994-12-01 | 1995-06-01 | 1996-06-01 |  | 1998-11-01 | 2002-04-01 | 337000 | 0 | 337000 | 337000 | 100% | 0 | 0 | 0 | 43810 | 0 | 43810 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1994 |  | Investment
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam (slabstock) at Yifeng Polyurethane Plastic Plant | Individual | ASP | CPR | FOA | 17 | INV | 122 | N | I | CFC | 90 | 60 | 0 | 0 | 1995-07-01 | 1998-01-01 | 1997-01-01 |  | 1998-04-01 | 1998-08-01 | 214600 | 0 | 214600 | 214600 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project complete; PCR submitted to 29th ExCom. |  |  | 1998-12-01 | INV | 0
FIN | UNDP | Conversion to CFC-free technology in the manufacture of XPS foam at Cangzhou Foreign Trade Packaging Co. | Individual | ASP | CPR | FOA | 17 | INV | 125 | N | I | CFC | 75 | 75 | 0 | 0 | 1995-07-01 | 1999-05-01 | 1996-12-01 |  | 2000-10-01 | 2003-07-01 | 450800 | -445 | 450355 | 450355 | 100% | 0 | 0 | 0 | 58604 | -57.85 | 58546.15 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1995 | 1999-12-01 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of XPS foam at Handan No. 7 | Individual | ASP | CPR | FOA | 17 | INV | 126 | N | I | CFC | 60 | 60 | 0 | 0 | 1995-07-01 | 1999-05-01 | 1996-12-01 |  | 2000-10-01 | 2003-07-01 | 400950 | -446 | 400504 | 400504 | 100% | 0 | 0 | 0 | 52123.5 | -57.98 | 52065.52 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1995 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of XPS foam at Joint Industrial Plastic Corporation, Buotou | Individual | ASP | CPR | FOA | 17 | INV | 127 | N | I | CFC | 90 | 90 | 0 | 0 | 1995-07-01 | 1999-05-01 | 1996-12-01 |  | 2000-10-01 | 2001-05-01 | 604450 | -446 | 604004 | 604004 | 100% | 0 | 0 | 0 | 78578.5 | -57.98 | 78520.52 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1995 | 1999-12-01 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane products at Daimei | Individual | ASP | CPR | FOA | 17 | INV | 134 | N | I | CFC | 77 | 77 | 0 | 0 | 1995-07-01 | 1997-06-01 | 1996-12-01 |  | 1998-12-01 | 2001-12-01 | 362600 | -43425.16 | 319174.84 | 319175 | 100% | -0.16 | 0 | 0 | 47138 | -5644.39 | 41493.63 | -0.02 | 0 | Completed in 1998. Financially completed in 2001. |  | 1995 |  | Investment
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible (slabstock) polyurethane foam at Liangzhu | Individual | ASP | CPR | FOA | 17 | INV | 137 | N | I | CFC | 120 | 120 | 0 | 0 | 1995-07-01 | 1997-11-01 | 1997-01-01 |  | 2000-08-01 | 2002-09-01 | 167800 | 0 | 167800 | 167800 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed, PCR submitted to ExCom. |  |  | 1999-08-01 | INV | 0
CLO | IBRD | Conversion to CFC-free technology in the manufacture of flexible (slabstock) polyurethane foam at Zhenjiang No. 5 Plastic Factory | Individual | ASP | CPR | FOA | 17 | INV | 138 | N | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-12-01 | 1997-01-01 |  |  | 2001-03-01 | 276800 | -60003 | 216797 | 216797 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project cancelled. Remaining amount of $60,000 has been returned to ExCom. |  |  | 1998-12-01 | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam (slabstock) at Penglai Polyurethane Plastic Factory | Individual | ASP | CPR | FOA | 18 | INV | 140 | N | I | CFC | 70 | 70 | 0 | 0 | 1995-11-01 | 1998-01-01 | 1996-11-01 |  | 1998-06-01 | 1999-01-01 | 320583 | -83 | 320500 | 320500 | 100% | 0 | 0 |  | 41675.79 | -11 | 41665 | -0.21 | -0.21 | Project completed; PCR submitted to the 30th ExCom. |  |  | 1997-12-01 | INV | 0
FIN | UNDP | Elimination of CFC-11 in the manufacture of flexible slabstock PUF at Tianjin Daqui Foam Plant | Individual | ASP | CPR | FOA | 18 | INV | 141 | N | I | CFC | 190 | 190 | 0 | 0 | 1995-11-01 | 1997-06-01 | 1996-11-01 |  | 1998-12-01 | 2000-12-01 | 160000 | -60 | 159940 | 159940 | 100% | 0 | 0 | 0 | 20800 | -7.8 | 20792.2 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of integral skin and cold cured PUF moldings at Jiangxi Auto Engineering Plastic Plant | Individual | ASP | CPR | FOA | 18 | INV | 142 | N | I | CFC | 39 | 39 | 0 | 0 | 1995-11-01 | 1999-08-01 | 1996-11-01 |  | 2001-03-01 | 2003-07-01 | 170000 | -6784 | 163216 | 163216 | 100% | 0 | 0 | 0 | 22100 | -881.92 | 21218.08 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1995 | 1999-12-01 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of XPS foam at Tianjin Gangda | Individual | ASP | CPR | FOA | 18 | INV | 143 | N | I | CFC | 55 | 55 | 0 | 0 | 1995-11-01 | 1999-05-01 | 1997-05-01 |  | 2000-10-01 | 2003-07-01 | 404250 | -1033 | 403217 | 403217 | 100% | 0 | 0 | 0 | 52552.5 | -134.29 | 52418.21 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1995 | 1999-12-01 | Investment
FIN | IBRD | Conversion from CFC-11 foaming agent to cyclopentane at Chang Ling (Group) Co. Ltd. | Individual | ASP | CPR | FOA | 18 | INV | 146 | N | I | CFC | 190 | 190 | 0 | 0 | 1995-11-01 | 1997-12-01 | 1997-05-01 |  | 1999-12-01 | 1999-01-01 | 2062000 | 0 | 2062000 | 2062000 | 100% | 0 | 0 |  | 268060 | 0 | 268060 | 0 | 0 | Project completed; PCR submitted December 2000. |  |  | 1999-06-01 | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible (slabstock) polyurethane foam at Hangzhou Plastic Foam Factory | Individual | ASP | CPR | FOA | 19 | INV | 156 | N | I | CFC | 60 | 60 | 0 | 0 | 1996-05-01 | 1998-01-01 | 1997-11-01 |  | 1999-03-01 | 1999-08-01 | 317000 | 0 | 317000 | 317000 | 100% | 0 | 0 |  | 41210 | 0 | 41210 | 0 | 0 | Project complete; PCR submitted to 29th ExCom. |  |  | 1999-03-01 | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible (slabstock) polyurethane foam at Qingyang Chemical Corp. | Individual | ASP | CPR | FOA | 19 | INV | 157 | N | I | CFC | 90 | 90 | 0 | 0 | 1996-05-01 | 1999-08-01 | 1997-11-01 |  | 2001-09-01 | 2002-10-01 | 362000 | 0 | 362000 | 362000 | 100% | 0 | 0 |  | 47060 | 0 | 47060 | 0 | 0 | Project completed and PCR submitted to ExCom. |  |  | 1999-12-01 | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible (slabstock) polyurethane foam at Yinguang Chemical Group | Individual | ASP | CPR | FOA | 19 | INV | 158 | N | I | CFC | 85 | 85 | 0 | 0 | 1996-05-01 | 1997-10-01 | 1997-11-01 |  | 1999-05-01 | 2000-10-01 | 376000 | 0 | 376000 | 376000 | 100% | 0 | 0 |  | 48880 | 0 | 48880 | 0 | 0 | Project complete; PCR submitted to 29th ExCom. |  |  | 1999-06-01 | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible (slabstock) polyurethane foam at Qinhuangdao No. 3 Plastic Plant | Individual | ASP | CPR | FOA | 19 | INV | 159 | N | I | CFC | 60 | 60 | 0 | 0 | 1996-05-01 | 1998-06-01 | 1997-11-01 |  | 1999-08-01 | 1998-10-01 | 370000 | 0 | 370000 | 370000 | 100% | 0 | 0 |  | 48100 | 0 | 48100 | 0 | 0 | Project completed. PCR will be submitted in January 2001. |  |  | 1999-06-01 | INV | 0
FIN | IBRD | Phaseout of CFCs in the manufacture of flexible slabstock PUF at Jinan Shiyan Plastic Plant | Individual | ASP | CPR | FOA | 19 | INV | 160 | N | I | CFC | 35 | 35 | 0 | 0 | 1996-05-01 | 1998-04-01 | 1997-05-01 |  | 1999-01-01 | 2001-11-23 | 209300 | 0 | 209300 | 209300.29 | 100% | -0.29 | -0.29 |  | 27209 | 0 | 27209.03 | -0.03 | -0.03 | Project completed; PCR submitted. |  |  | 1998-12-01 | INV | 0
FIN | UNDP | Elimination of CFC-11 in the manufacture of flexible slabstock PUF at Jiangsu Jintan Insulation Material Plant | Individual | ASP | CPR | FOA | 19 | INV | 161 | N | I | CFC | 12 | 12 | 0 | 0 | 1996-05-01 | 1997-06-01 | 1997-05-01 |  | 1998-10-01 | 2000-12-01 | 66000 | -5638 | 60362 | 60362 | 100% | 0 | 0 | 0 | 8580 | -732.94 | 7847.06 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1996 |  | Investment
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible (slabstock) polyurethane foam at Zibo No. 3 Plastic Plant | Individual | ASP | CPR | FOA | 19 | INV | 162 | N | I | CFC | 100 | 55 | 0 | 0 | 1996-05-01 | 1997-12-01 | 1997-11-01 |  | 1999-01-01 | 2000-12-01 | 249000 | 0 | 249000 | 249000 | 100% | 0 | 0 |  | 32370 | 0 | 32370 | 0 | 0 | Project complete; PCR submitted to 29th ExCOM. |  |  | 1999-03-01 | INV | 0
FIN | IBRD | Conversion of manufacturing facilities from CFC-11 foaming agent to cyclopentane at Hua Yi Electrical Appliance General Company | Individual | ASP | CPR | FOA | 19 | INV | 166 | N | I | CFC | 170 | 170 | 0 | 0 | 1996-05-01 | 1997-10-01 | 1997-02-01 |  | 1998-05-01 | 1998-09-01 | 972490 | 0 | 972490 | 972490 | 100% | 0 | 0 |  | 126423.7 | 0 | 126423.7 | 0 | 0 | Project completed; PCR submitted to 29th ExCOM. |  |  | 1997-12-01 | INV | 0
CLO | IBRD | Conversion of manufacturing facilities from CFC-11 foaming agent to cyclopentane at Shanghai Shuanglu Electrical Appliance Co. Ltd. | Individual | ASP | CPR | FOA | 20 | INV | 174 | N | I |  | 0 | 0 | 0 | 0 | 1996-10-01 |  | 1997-07-01 |  |  | 1999-07-01 | 1899230 | -1899230 | 0 | 0 | #DIV/0! | 0 | 0 |  | 246899.9 | -246900 | 0 | -0.1 | -0.1 | Project cancelled. Company bankrupt. Funds returned at 27th meeting. |  |  | 1998-06-01 | INV | 0
FIN | IBRD | Elimination of CFCs in the manufacture of rigid PUF products at Handan Plastics No. 8 | Individual | ASP | CPR | FOA | 20 | INV | 177 | N | I | CFC | 101.64 | 101.64 | 0 | 0 | 1996-10-01 | 1998-05-01 | 1997-10-01 |  | 1999-05-01 | 2002-07-01 | 265000 | 0 | 265000 | 265000 | 100% | 0 | 0 |  | 34450 | 0 | 34450 | 0 | 0 |  |  |  | 1999-04-01 | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexibe (slabstock) polyurethane foam at Chengdu Plastics No. 7 | Individual | ASP | CPR | FOA | 20 | INV | 179 | N | I | CFC | 120 | 120 | 0 | 0 | 1996-10-01 | 2001-01-01 | 1998-04-01 |  | 2005-04-01 | 2005-01-01 | 301000 | 0 | 301000 | 301000 | 100% | 0 | 0 |  | 39130 | 0 | 39130 | 0 | 0 | Project completed. |  |  | 2000-12-01 | INV | 0
FIN | UNDP | Elimination of CFC-12 in the manufacture of EPS foam sheet at Zhejiang Wanpeng Clique Co., Ltd. | Individual | ASP | CPR | FOA | 22 | INV | 202 | N | I | CFC | 120 | 120 | 0 | 0 | 1997-05-01 | 1999-06-01 | 1999-06-01 |  | 2000-10-01 | 2002-06-01 | 412666 | -10472.44 | 402193.56 | 402194 | 100% | -0.44 | 0 | 0 | 53646.58 | -1361.82 | 52284.8172 | -0.0572 | 0 | Completed in 2000. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of EPS foam sheet at Zhoushan Fuchuan Plastic Products Factory | Individual | ASP | CPR | FOA | 22 | INV | 206 | N | I | CFC | 61 | 61 | 0 | 0 | 1997-05-01 | 1999-06-01 | 1999-06-01 |  | 2000-10-01 | 2002-06-01 | 403711 | -9044.73 | 394666.27 | 394666 | 100% | 0.27 | 0 | 0 | 52482.43 | -1175.46 | 51306.9349 | 0.0351 | 0 | Completed in 2000. Financially completed in 2002. |  | 1997 | 1999-12-01 | Investment
FIN | IBRD | Conversion of rigid and spray polyurethane foam manufacture from CFC-11 to HCFC-141b foam blowing agent at Yantai Moon Group Co. Ltd. | Individual | ASP | CPR | FOA | 23 | INV | 227 | N | I | CFC | 462.6 | 462.6 | 0 | 0 | 1997-11-01 | 2000-09-01 | 1999-12-01 |  | 2001-12-01 | 2002-11-01 | 1132682 | -2956 | 1129726 | 1129726 | 100% | 0 | 0 |  | 147249 | -370 | 146879 | 0 | 0 | Project completed. PCR submitted to ExCom. |  |  |  | INV | 0
FIN | UNDP | Elimination of the use of CFCs in the manufacture of sandwich polyurethane panels, pipes and spray foams at Baoding Oil Depot & Storage Engineering Company | Individual | ASP | CPR | FOA | 23 | INV | 228 | N | I | CFC | 75.5 | 75.5 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2001-08-01 | 2003-09-01 | 400960 | -34986.33 | 365973.67 | 365974 | 100% | -0.33 | 0 | 0 | 52124.8 | -4548.24 | 47576.5996 | -0.0396 | 0 | Completed in 2001. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of rigid and spray polyurethane foams at Xinjiang Tianye Co. Ltd. | Individual | ASP | CPR | FOA | 23 | INV | 229 | N | I | CFC | 92.3 | 92.3 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-11-01 |  | 2001-01-01 | 2004-01-01 | 300620 | -15937 | 284683 | 284683 | 100% | 0 | 0 | 0 | 39080.6 | -2072 | 37008.6 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 1997 |  | Investment
FIN | IBRD | Conversion of rigid and spray polyurethane foam manufacture from CFC-11 to HCFC-141b foam blowing agent at Shanghai General Machinery Company (SGMC) | Individual | ASP | CPR | FOA | 23 | INV | 230 | N | I | CFC | 88.3 | 88.3 | 0 | 0 | 1997-11-01 | 2000-09-01 | 1999-12-01 |  | 2002-12-01 | 2004-09-01 | 380300 | -1711.2 | 378588.8 | 378588.8 | 100% | 0 | 0 |  | 49439 | -171.12 | 49267.88 | 0 | 0 | Financially completed. |  |  |  | INV | 0
FIN | UNDP | Elimination of the use of CFCs in the manufacture of sandwich polyurethane panels at Luoyang Refrigeration Machinery Factory | Individual | ASP | CPR | FOA | 23 | INV | 236 | N | I | CFC | 117.8 | 117.8 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2001-01-01 | 2003-07-01 | 698595 | -41580 | 657015 | 657015 | 100% | 0 | 0 | 0 | 90817.35 | -5405.4 | 85411.95 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Conversion to cyclopentane in the manufacture of heating pipes at Jixi City Thermal Power Company | Individual | ASP | CPR | FOA | 24 | INV | 245 | N | I | CFC | 86 | 86 | 0 | 0 | 1998-03-01 | 2000-12-01 | 2000-04-01 |  | 2003-12-01 | 2008-10-01 | 673380 | -3133 | 670247 | 670247 | 100% | 0 | 0 | 0 | 87539.4 | -407.29 | 87132.1119 | -0.0019 | 0 | Completed in 2003. Financially completed in 2008. |  | 1998 |  | Investment
FIN | UNIDO | Preparation of investment projects (50 companies) in the foam sector (polysterene/polyethylene) | Individual | ASP | CPR | FOA | 24 | PRP | 240 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-06-01 | 1999-04-01 |  | 2000-06-01 | 2001-07-01 | 100000 | -2311 | 97689 | 97689 | 100% | 0 | 0 |  | 13000 | -321 | 12679 | 0 | 0 | FIN
FIN | UNDP | Project preparation for 10 projects in the rigid and integral skin foam sub-sectors | Individual | ASP | CPR | FOA | 24 | PRP | 241 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1999-12-01 | 2001-12-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 | 0 | 11700 | 0 | 11700 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Conversion to LCD technology int he manufacture of flexible (slabstock) polyurethane foam at Jinling Petrochemical Co. Plastics Factory | Individual | ASP | CPR | FOA | 25 | INV | 247 | N | I | CFC | 81 | 81 | 0 | 0 | 1998-07-01 | 2000-04-01 | 2000-08-01 |  | 2003-05-01 | 2005-02-01 | 504630 | -4472 | 500158 | 500158 | 100% | 0 | 0 | 0 | 65601.9 | -581 | 65020.9 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 1998 |  | Investment
FIN | UNIDO | Elimination of CFC-12 in manufacturing of EPE foam packaging nets at 25 enterprises (umbrella project) | Individual | ASP | CPR | FOA | 25 | INV | 248 | A | I | CFC | 1146 | 1146 |  |  | 1998-07-01 | 1998-12-01 | 2000-01-01 |  | 2000-12-01 | 2002-09-01 | 4488516 | 0 | 4488516 | 4488515.76 | 100% | 0.24 | 0 |  | 583507 | -341 | 583166 | 0 | 0 | FIN
FIN | UNDP | Conversion from CFC-11 to methylene chloride and forced cooling system in the manufacture of flexible polyurethane foam (slabstock) at Cangzhou New-Type Foam Decoration Material Plant | Individual | ASP | CPR | FOA | 25 | INV | 250 | N | I | CFC | 67 | 67 | 0 | 0 | 1998-07-01 | 1999-12-01 | 2000-08-01 |  | 2001-05-01 | 2003-09-01 | 417410 | -17009 | 400401 | 400401 | 100% | 0 | 0 | 0 | 54263.3 | -2211.29 | 52052.01 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | IBRD | Conversion of polyurethane slabstock manufacture to forced cooling and methylene chloride at Wuxi New Type Raw Material Plant | Individual | ASP | CPR | FOA | 25 | INV | 252 | N | I | CFC | 231 | 231 | 0 | 0 | 1998-07-01 | 1999-04-01 | 2001-08-01 |  | 1999-10-01 | 2002-08-01 | 488150 | 0 | 488150 | 488150 | 100% | 0 | 0 |  | 63459.5 | 0 | 63459.5 | 0 | 0 |  |  |  |  | INV | 0
FIN | UNDP | Conversion of rigid and spray polyurethane foam manufacture from CFC-11 to HCFC-141b foam blowing agent at Victory Petroleum Organization Bureau | Individual | ASP | CPR | FOA | 25 | INV | 254 | N | I | CFC | 72 | 72 | 0 | 0 | 1998-07-01 | 2001-11-01 | 2000-08-01 |  | 2003-11-01 | 2008-10-01 | 563760 | -273 | 563487 | 563487 | 100% | 0 | 0 | 0 | 73288.8 | -35.49 | 73253.3099 | 0.0001 | 0 | Completed in 2003. Financially completed in 2008. |  | 1998 |  | Investment
FIN | UNDP | Conversion to cyclopentane in the manufacture of PU-insulated heating pipes at Tianjin Pipeline Engineering Group Co. Ltd. | Individual | ASP | CPR | FOA | 26 | INV | 257 | N | I | CFC | 80 | 80 | 0 | 0 | 1998-11-01 | 2000-05-01 | 2000-12-01 |  | 2003-09-01 | 2005-03-01 | 626400 | -346 | 626054 | 626054 | 100% | 0 | 0 | 0 | 78904 | -44 | 78860 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 1998 |  | Investment
FIN | UNDP | Conversion to HCFC-141b in the manufacture of PU-sandwich panels and pour-in-place polyurethane foams at Guangdong Commercial Refrigeration Equipment Co. (GCREC) | Individual | ASP | CPR | FOA | 26 | INV | 258 | N | I | CFC | 60.3 | 60.3 | 0 | 0 | 1998-11-01 | 1999-12-01 | 2000-12-01 |  | 2001-10-01 | 2003-07-01 | 472150 | -18041 | 454109 | 454109 | 100% | 0 | 0 | 0 | 61379.5 | -2345.37 | 59034.13 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Conversion to HCFC-141b in the manufacture of PU-sandwich panels and pour-in-place polyurethane foams at Kaifeng Air Separation Group Ltd. (KFAS) | Individual | ASP | CPR | FOA | 26 | INV | 260 | N | I | CFC | 68.2 | 68.2 | 0 | 0 | 1998-11-01 | 2000-03-01 | 2000-12-01 |  | 2001-04-01 | 2001-11-01 | 534090 | -14357 | 519733 | 519733 | 100% | 0 | 0 | 0 | 68749.9 | -1579.38 | 67170.52 | 0 | 0 | Completed in 2001. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Conversion to HCFC-141b in the manufacture of rigid and pour-in-place polyurethane foams at Corrosionproof and Insulation Co., Ltd. | Individual | ASP | CPR | FOA | 26 | INV | 263 | N | I | CFC | 99.1 | 99.1 | 0 | 0 | 1998-11-01 | 2000-02-01 | 2000-12-01 |  | 2001-04-01 | 2004-01-01 | 776110 | -13913 | 762197 | 762197 | 100% | 0 | 0 | 0 | 95372.1 | -1530 | 93842.1 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 1998 |  | Investment
FIN | UNDP | Conversion of refrigerator manufacture in Zhenjiang Radio Factory from CFC-11 to N-pentane foam blowing agent in the production of PU insulation panels | Individual | ASP | CPR | FOA | 26 | INV | 264 | N | I | CFC | 120.5 | 120.5 | 0 | 0 | 1998-11-01 | 2000-02-01 | 2001-12-01 |  | 2003-09-01 | 2005-02-01 | 617860 | -4968 | 612892 | 612892 | 100% | 0 | 0 | 0 | 77964.6 | -627 | 77337.6 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 1998 |  | Investment
FIN | UNDP | Conversion to HCFC-141b in the manufacture of rigid and spray polyurethane foams at Daqing Petroleum Organization Bureau | Individual | ASP | CPR | FOA | 26 | INV | 265 | N | I | CFC | 167.8 | 167.8 | 0 | 0 | 1998-11-01 | 2001-11-01 | 2001-06-01 |  | 2003-11-01 | 2009-01-01 | 1124560 | -618 | 1123942 | 1123942 | 100% | 0 | 0 | 0 | 133701.6 | -73.48 | 133628.1243 | -0.0043 | 0 | Completed in 2003.Financially completed in 2009. |  | 1998 |  | Investment
FIN | UNDP | Conversion to LCD technology in the manufacture of flexible slabstock polyurethane foam at Ningbo Yongling Rubber and Plastic Co. | Individual | ASP | CPR | FOA | 26 | INV | 266 | N | I | CFC | 72 | 72 | 0 | 0 | 1998-11-01 | 2000-02-01 | 2001-12-01 |  | 2001-12-01 | 2003-07-01 | 448560 | -20224 | 428336 | 428336 | 100% | 0 | 0 | 0 | 58312.8 | -2628.62 | 55684.18 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | IBRD | Conversion of refrigerator manufacture from CFC-11 to pentane foam blowing agent in the production of PU insulation panels at Foshan Refrigeration Equipment General Factory | Individual | ASP | CPR | FOA | 26 | INV | 267 | N | I | CFC | 120.3 | 120.3 | 0 | 0 | 1998-11-01 | 2000-09-01 | 2001-12-01 |  | 2005-03-01 | 2005-08-01 | 743500 | 0 | 743500 | 743500 | 100% | 0 | 0 |  | 91785 | 0 | 91785 | 0 | 0 | Completed. |  |  |  | INV | 0
CLO | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Handan Fuyang Chemical Corporation | Individual | ASP | CPR | FOA | 27 | INV | 269 | N | I |  | 0 | 0 | 0 | 0 | 1999-03-01 |  | 2002-10-01 |  |  | 2001-12-01 | 436100 | -436100 | 0 | 0 | #DIV/0! | 0 | 0 |  | 56693 | -55842.6 | 850.4 | 0 | 0 | Project cancelled at the 35th ExCom. |  |  |  | INV | 0
FIN | IBRD | Phaseout of CFC-11 in the manufacture of rigid polyurethane foam through the use of HCFC-141b at Qingdao Changlong Commercial Machinery Co. Ltd. | Individual | ASP | CPR | FOA | 27 | INV | 270 | N | I | CFC | 57.7 | 57.7 | 0 | 0 | 1999-03-01 | 2000-06-01 | 2002-04-01 |  | 2002-02-01 | 2003-10-01 | 451791 | -3921.96 | 447869.04 | 447869.04 | 100% | 0 | 0 |  | 58732.83 | -490.25 | 58242.58 | 0 | 0 | Physically and financially completed. |  |  |  | INV | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology in Xiaoshan Polyurethane Foam Plant | Individual | ASP | CPR | FOA | 27 | INV | 271 | N | I | CFC | 111 | 111 | 0 | 0 | 1999-03-01 | 2001-01-01 | 2002-10-01 |  | 2003-12-01 | 2004-07-01 | 603058 | 0 | 603058 | 603058 | 100% | 0 | 0 |  | 76336.38 | 0 | 76336.38 | 0 | 0 | Project financially completed. |  |  |  | INV | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Shenyin Polyurethane Xinzhuang Plant | Individual | ASP | CPR | FOA | 27 | INV | 274 | N | I | CFC | 86.1 | 86.1 | 0 | 0 | 1999-03-01 | 2001-01-01 | 2002-10-01 |  | 2004-11-01 | 2005-04-01 | 536403 | 0 | 536403 | 536403 | 100% | 0 | 0 |  | 69004.33 | 0 | 69004.33 | 0 | 0 | Completed. |  |  |  | INV | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Henan Huojia Huashi Co. | Individual | ASP | CPR | FOA | 27 | INV | 275 | N | I | CFC | 109.5 | 109.5 | 0 | 0 | 1999-03-01 | 2001-01-01 | 2002-10-01 |  | 2003-12-01 | 2004-07-01 | 583186 | 0 | 583186 | 583186 | 100% | 0 | 0 |  | 74150.46 | 0 | 74150.46 | 0 | 0 | Project financially completed. |  |  |  | INV | 0
FIN | IBRD | Phaseout of CFC-11 in the manufacture of rigid polyurethane foam through the use of HCFC-141b at Zhenjiang Commercial Refrigeration Equipment General Plant | Individual | ASP | CPR | FOA | 27 | INV | 276 | N | I | CFC | 30.81 | 30.81 | 0 | 0 | 1999-03-01 | 2000-01-01 | 2002-04-01 |  | 2002-10-01 | 2003-10-01 | 145376 | -4908 | 140468 | 140468 | 100% | 0 | 0 |  | 18899 | -490.8 | 18408.2 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Jiangsu Haimen Foam plant | Individual | ASP | CPR | FOA | 27 | INV | 277 | N | I | CFC | 73 | 73 | 0 | 0 | 1999-03-01 | 2001-01-01 | 2002-04-01 |  | 2004-08-01 | 2004-12-01 | 454790 | 0 | 454790 | 454790 | 100% | 0 | 0 |  | 59122.7 | 0 | 59122.7 | 0 | 0 | Project financially completed. |  |  |  | INV | 0
FIN | UNDP | Phase-out of CFC-11 in the manufacture of rigid polyurethane foam through the use of water blown technology at Nanjing Kanglian Industrial Corporation | Individual | ASP | CPR | FOA | 27 | INV | 279 | N | I | CFC | 30 | 30 | 0 | 0 | 1999-03-01 | 2000-04-01 | 2001-10-01 |  | 2001-04-01 | 2002-06-01 | 234900 | -14525 | 220375 | 220375 | 100% | 0 | 0 | 0 | 30537 | -1888.49 | 28648.51 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1999 |  | Investment
FIN | IBRD | Phaseout of CFC-11 in the manufacture of rigid polyurethane foam through the use of HCFC-141b at Shanghai Haiou Electric Appliance General Factory | Individual | ASP | CPR | FOA | 27 | INV | 280 | N | I | CFC | 33.34 | 33.34 | 0 | 0 | 1999-03-01 | 2000-09-01 | 2002-04-01 |  | 2002-09-01 | 2004-04-01 | 261052 | 0 | 261052 | 261052 | 100% | 0 | 0 |  | 33936.76 | 0 | 33936.76 | 0 | 0 | Financially completed. |  |  |  | INV | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology in Putuo Zhujiajian Rubber and Plastic Plant | Individual | ASP | CPR | FOA | 27 | INV | 281 | N | I | CFC | 112 | 112 | 0 | 0 | 1999-03-01 | 2001-01-01 | 2002-10-01 |  | 2004-07-01 | 2005-03-01 | 525483 | 0 | 525483 | 525483 | 100% | 0 | 0 |  | 67803.13 | 0 | 67803.13 | 0 | 0 | Completed. |  |  |  | INV | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Shanghai Shenyin Polyurethane Baoshan Plant | Individual | ASP | CPR | FOA | 27 | INV | 284 | N | I | CFC | 76 | 76 | 0 | 0 | 1999-03-01 | 2001-01-01 | 2002-04-01 |  | 2004-10-01 | 2005-04-01 | 473480 | 0 | 473480 | 473480 | 100% | 0 | 0 |  | 61552.4 | 0 | 61552.4 | 0 | 0 | Completed. |  |  |  | INV | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Chengdu Jinjiang Foam General Plant | Individual | ASP | CPR | FOA | 27 | INV | 285 | N | I | CFC | 89 | 89 | 0 | 0 | 1999-03-01 | 2001-01-01 | 2002-10-01 |  | 2004-08-01 | 2004-11-01 | 554470 | 0 | 554470 | 554470 | 100% | 0 | 0 |  | 70991.7 | 0 | 70991.7 | 0 | 0 | Financially completed. |  |  |  | INV | 0
FIN | UNDP | Preparation of 16 projects in general foam subsector | Individual | ASP | CPR | FOA | 27 | PRP | 272 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2000-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1999 |  | Investment
FIN | UNDP | Preparation of ten projects in the integral skin foam subsector | Individual | ASP | CPR | FOA | 27 | PRP | 278 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 2000-04-01 |  | 2000-04-01 | 2005-12-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Completed in 2000. Financially completed in 2005. |  | 1999 |  | Investment
FIN | UNIDO | Preparation of investment project in the foam sector (rigid polyurethane) | Individual | ASP | CPR | FOA | 27 | PRP | 283 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-09-01 | 1999-12-01 |  | 2001-05-01 | 2002-09-01 | 50000 | -615 | 49385 | 49384.98 | 100% | 0.02 | 0 |  | 6500 | -90 | 6410 | 0 | 0 | FIN
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Hengfeng Polyurethane Spray Co. Ltd. | Individual | ASP | CPR | FOA | 28 | INV | 286 | N | I | CFC | 154.1 | 154.1 | 0 | 0 | 1999-07-01 | 2001-06-01 | 2002-02-01 |  | 2003-09-01 | 2005-02-01 | 1206600 | -101036 | 1105564 | 1105564 | 100% | 0 | 0 | 0 | 142726 | -11113.96 | 131612.04 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 1999 |  | Investment
FIN | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Wuhan Commercial Machinery Factory | Individual | ASP | CPR | FOA | 28 | INV | 288 | N | I | CFC | 29.3 | 29.3 | 0 | 0 | 1999-07-01 | 2000-09-01 | 2002-08-01 |  | 2003-11-01 | 2004-11-01 | 149195 | 0 | 149195 | 149195 | 100% | 0 | 0 |  | 19395.35 | 0 | 19395.35 | 0 | 0 | Project financially completed. |  |  |  | INV | 0
FIN | UNDP | Phase-out of CFC-11 in the manufacture of rigid polyurethane foam through the use of water blown technology at Jiangsu Chemical Research Institute | Individual | ASP | CPR | FOA | 28 | INV | 289 | N | I | CFC | 32.4 | 32.4 | 0 | 0 | 1999-07-01 | 2000-02-01 | 2002-02-01 |  | 2001-12-01 | 2004-06-01 | 253690 | -9289 | 244401 | 244401 | 100% | 0 | 0 | 0 | 32979.7 | -1207.57 | 31772.13 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Jiaxing Anti-Corrosion Factory | Individual | ASP | CPR | FOA | 28 | INV | 290 | N | I | CFC | 19.4 | 19.4 | 0 | 0 | 1999-07-01 | 2000-10-01 | 2002-02-01 |  | 2002-05-01 | 2004-06-01 | 151590 | -6492 | 145098 | 145098 | 100% | 0 | 0 | 0 | 19706.7 | -844 | 18862.7 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 1999 |  | Investment
CLO | UNDP | Phase-out of CFC-11 by conversion to n-pentane technology in the manufacture of rigid polyurethane insulation foam at Suzhou Purification Equipment Factory | Individual | ASP | CPR | FOA | 28 | INV | 291 | N | I | CFC | 66 | 66 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2002-02-01 |  |  | 2005-12-01 | 516780 | -259989.84 | 256790.16 | 256790 | 100% | 0.16 | 0 | 0 | 66845.8 | -33463 | 33382.7792 | 0.0208 | 0 | Canceled in 2004. Financially Completed in 2005. |  | 1999 |  | Investment
FIN | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Heilongjiang Commercial Installation Corporation | Individual | ASP | CPR | FOA | 28 | INV | 292 | N | I | CFC | 52.6 | 52.6 | 0 | 0 | 1999-07-01 | 2000-09-01 | 2002-08-01 |  | 2001-11-01 | 2003-02-01 | 411858 | 0 | 411858 | 411858 | 100% | 0 | 0 |  | 53541.54 | 0 | 53541.54 | 0 | 0 | Project physically and financially completed and PCR submitted. |  |  |  | INV | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology in Changzhou Huangfa Co. Ltd., Foam Plant | Individual | ASP | CPR | FOA | 28 | INV | 293 | N | I | CFC | 70.7 | 70.7 | 0 | 0 | 1999-07-01 | 2001-01-01 | 2002-08-01 |  | 2004-06-01 | 2005-04-01 | 440461 | 0 | 440461 | 440461 | 100% | 0 | 0 |  | 57259.93 | 0 | 57259.93 | 0 | 0 | Completed. |  |  |  | INV | 0
FIN | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Jiangsu Taizhou Commercial Machiner General Factory | Individual | ASP | CPR | FOA | 28 | INV | 294 | N | I | CFC | 28.3 | 28.3 | 0 | 0 | 1999-07-01 | 2000-09-01 | 2002-08-01 |  | 2003-05-01 | 2004-09-01 | 192890 | -106.2 | 192783.8 | 192783.8 | 100% | 0 | 0 |  | 25075.7 | -10.62 | 25065.08 | 0 | 0 | Project financially completed. |  |  |  | INV | 0
FIN | IBRD | Phaseout of CFC-11 by conversion to n-pentane technology in the manufacture of rigid polyurethane foam sandwich panels at Chengde Commercial Machinery Group Co. Ltd. | Individual | ASP | CPR | FOA | 28 | INV | 295 | N | I | CFC | 106 | 106 | 0 | 0 | 1999-07-01 | 2000-09-01 | 2002-08-01 |  | 2003-05-01 | 2004-07-01 | 829980 | 0 | 829980 | 829980 | 100% | 0 | 0 |  | 101297.8 | 0 | 101297.8 | 0 | 0 | Project financially completed. |  |  |  | INV | 0
CLO | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology in Shandong Tianhua (Group) Plastic Plant | Individual | ASP | CPR | FOA | 28 | INV | 296 | N | I |  | 0 | 0 | 0 | 0 | 1999-07-01 |  | 2002-08-01 |  |  | 2001-12-01 | 534534 | -534534 | 0 | 0 | #DIV/0! | 0 | 0 |  | 68798.74 | -67766.76 | 1031.98 | 1.0459e-11 | 0 | Project cancelled at the 35 th ExCom. |  |  |  | INV | 0
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Penglai Polyurethane Industry Co. | Individual | ASP | CPR | FOA | 28 | INV | 297 | N | I | CFC | 63.5 | 63.5 | 0 | 0 | 1999-07-01 | 1999-12-01 | 2002-02-01 |  | 2001-04-01 | 2003-07-01 | 497200 | -50527 | 446673 | 446673 | 100% | 0 | 0 | 0 | 64636 | -6568.51 | 58067.49 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam at Guangdong Zhujiang Refrigeration and Air Conditioning Co. | Individual | ASP | CPR | FOA | 28 | INV | 299 | N | I | CFC | 87.7 | 87.7 | 0 | 0 | 1999-07-01 | 2000-09-01 | 2002-08-01 |  | 2002-02-01 | 2003-06-01 | 581230 | 0 | 581230 | 581230 | 100% | 0 | 0 |  | 73935.3 | 0 | 73935.3 | 0 | 0 | Project completed. PCR submitted. |  |  |  | INV | 0
FIN | UNIDO | Elimination of CFC-12 in manufacturing of EPE foam packaging nets at 27 enterprises (Umbrella Project) | Individual | ASP | CPR | FOA | 28 | INV | 301 | A | I | CFC | 825.7 | 825.7 |  |  | 1999-07-01 | 1999-11-01 | 2001-08-01 |  | 2001-12-01 | 2002-12-01 | 5289441 | 0 | 5289441 | 5289440.76 | 100% | 0.24 | 0 |  | 591839 | -187 | 591652 | 0 | 0 | FIN |  |  | 2002-12-01
FIN | UNDP | Phaseout of CFC-11 by conversion to water blown and HCFC-141b in the manufacture of ISF at 4 SMEs (Ningbo Yongling Rubber & Plastic, Sichuan Mianyang Jinpan Automobile Parts, Zhenjiang Xingda Auto Par | Individual | ASP | CPR | FOA | 29 | INV | 304 | N | I | CFC | 17.6 | 17.6 | 0 | 0 | 1999-11-01 | 2001-05-01 | 2002-12-01 |  | 2003-09-01 | 2008-10-01 | 245710 | -19126.2 | 226583.8 | 226584 | 100% | -0.2 | 0 | 0 | 31942 | -2486.36 | 29455.6694 | -0.0294 | 0 | Completed in 2003. Financially completed in 2008. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water blown technology in the manufacture of flexible integral skin foam at Hangzhou Fanlong Steering Wheel, Co., Ltd. | Individual | ASP | CPR | FOA | 29 | INV | 305 | N | I | CFC | 10.5 | 10.5 | 0 | 0 | 1999-11-01 | 2002-02-01 | 2002-12-01 |  | 2003-09-01 | 2005-02-01 | 176520 | -4703 | 171817 | 171817 | 100% | 0 | 0 | 0 | 22948 | -612 | 22336 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 1999 |  | Investment
FIN | UNIDO | Elimination of CFC-11 in manufacturing of PU rigid foam for insulation at 31 enterprises | Individual | ASP | CPR | FOA | 29 | INV | 306 | A | I | CFC | 707.3 | 707.3 |  |  | 1999-11-01 | 2000-04-01 | 2002-06-01 |  | 2003-01-01 | 2004-04-01 | 5516900 | 0 | 5516900 | 5516900.42 | 100% | -0.42 | 0 |  | 616859 | -430 | 616429 | 0 | 0 | FIN
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Chengde Machinery Installation Co. Qinghuangdao Branch | Individual | ASP | CPR | FOA | 29 | INV | 310 | N | I | CFC | 19.99 | 19.99 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2002-12-01 |  | 2001-12-01 | 2004-04-01 | 156600 | -5284 | 151316 | 151316 | 100% | 0 | 0 |  | 20358 | -660.5 | 19697.5 | 0 | 0 | Project financially completed. |  |  |  | INV | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to methylene chloride and vertifoam from CFC-11 to liquid carbon dioxide technology at Shenzhou Foam Plant | Individual | ASP | CPR | FOA | 29 | INV | 311 | N | I | CFC | 134.9 | 134.9 | 0 | 0 | 1999-11-01 | 2001-10-01 | 2002-12-01 |  | 2005-05-01 | 2005-12-01 | 609616 | 0 | 609616 | 609616 | 100% | 0 | 0 |  | 77057.76 | 0 | 77057.76 | 0 | 0 | Completed. |  |  |  | INV | 0
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Beijing Hanfeng Polyurethane Company | Individual | ASP | CPR | FOA | 29 | INV | 312 | N | I | CFC | 56.3 | 56.3 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2002-12-01 |  | 2003-09-01 | 2005-03-01 | 440830 | -9007 | 431823 | 431823 | 100% | 0 | 0 | 0 | 57308 | -1171.19 | 56136.81 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 1999 | 2002-12-01 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Henan Bingxiong Refrigeration Truck Plant | Individual | ASP | CPR | FOA | 29 | INV | 313 | N | I | CFC | 56.3 | 56.3 | 0 | 0 | 1999-11-01 | 2001-09-01 | 2003-07-01 |  | 2002-10-01 | 2004-06-01 | 440780 | -97144 | 343636 | 343636 | 100% | 0 | 0 | 0 | 57301.4 | -12629.12 | 44672.2801 | -0.0001 | 0 | Completed in 2002. Financially completed in 2004. |  | 1999 | 2003-07-01 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam at Tianjin Relong Insulation Pipe Plant | Individual | ASP | CPR | FOA | 29 | INV | 314 | N | I | CFC | 11.9 | 11.9 | 0 | 0 | 1999-11-01 | 2001-09-01 | 2002-12-01 |  | 2003-09-01 | 2005-03-01 | 93190 | -5957 | 87233 | 87233 | 100% | 0 | 0 | 0 | 12115 | -774.43 | 11340.5708 | -0.0008 | 0 | Completed in 2003. Financially completed in 2005. |  | 1999 | 2002-12-01 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Zhenjiang Feichi Automobile Group, Co., Ltd. | Individual | ASP | CPR | FOA | 29 | INV | 315 | N | I | CFC | 31.7 | 31.7 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2002-12-01 |  | 2002-10-01 | 2004-06-01 | 223900 | -11388 | 212512 | 212512 | 100% | 0 | 0 | 0 | 29107 | -1480.66 | 27626.34 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 1999 | 2002-12-01 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Taiyuan No. 2 Plastic Factory | Individual | ASP | CPR | FOA | 29 | INV | 316 | N | I | CFC | 16.3 | 16.3 | 0 | 0 | 1999-11-01 | 2002-10-01 | 2002-12-01 |  | 2003-09-01 | 2005-02-01 | 127790 | -7057 | 120733 | 120733 | 100% | 0 | 0 | 0 | 16613 | -917.43 | 15695.5732 | -0.0032 | 0 | Completed in 2003. Financially completed in 2005. |  | 1999 |  | Investment
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Beijing Qianjin Polyurethane Corporation | Individual | ASP | CPR | FOA | 29 | INV | 317 | N | I | CFC | 64.77 | 64.77 | 0 | 0 | 1999-11-01 | 2002-12-01 | 2002-12-01 |  | 2002-08-01 | 2003-11-01 | 507109 | -79316 | 427793 | 427793 | 100% | 0 | 0 |  | 65781.99 | -10169 | 55613 | -0.01 | -0.01 | Project physically and financially completed. |  |  |  | INV | 0
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Harbin Dongguang Machinery Plant | Individual | ASP | CPR | FOA | 29 | INV | 318 | N | I | CFC | 57.1 | 57.1 | 0 | 0 | 1999-11-01 | 2001-06-01 | 2002-12-01 |  | 2002-10-01 | 2004-06-01 | 447170 | -23615.73 | 423554.27 | 423554 | 100% | 0.27 | 0 | 0 | 58132 | -3070.03 | 55061.9335 | 0.0365 | 0 | Completed in 2002. Financially completed in 2004. |  | 1999 | 2002-12-01 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water blown technology in the manufacture of flexible integral skin foam at Dongfeng Automobile Body Company | Individual | ASP | CPR | FOA | 29 | INV | 319 | N | I | CFC | 7.1 | 7.1 | 0 | 0 | 1999-11-01 | 2001-05-01 | 2002-12-01 |  | 2003-09-01 | 2005-02-01 | 111120 | -9255 | 101865 | 101865 | 100% | 0 | 0 | 0 | 14446 | -1203.18 | 13242.8167 | 0.0033 | 0 | Completed in 2003. Financially completed in 2005. |  | 1999 |  | Investment
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Beijing Hangxing Polyurethane Corporation | Individual | ASP | CPR | FOA | 29 | INV | 320 | N | I | CFC | 60.6 | 60.6 | 0 | 0 | 1999-11-01 | 2002-12-01 | 2002-12-01 |  | 2002-09-01 | 2004-09-01 | 471217 | -85471 | 385746 | 385746 | 100% | 0 | 0 |  | 61258.21 | -11111 | 50147.21 | 0 | 0 | Project financially completed. |  |  |  | INV | 0
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Yangzhou Tongli Refrigeration Container Co. Ltd. | Individual | ASP | CPR | FOA | 29 | INV | 321 | N | I | CFC | 14.63 | 14.63 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2002-12-01 |  | 2001-11-01 | 2003-06-01 | 114513 | 0 | 114513 | 114513 | 100% | 0 | 0 |  | 14886.69 | 0 | 14886.69 | 0 | 0 | Project physically and financially completed. |  |  |  | INV | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology in Handan Fuxing Jiahe Foam Plant | Individual | ASP | CPR | FOA | 29 | INV | 322 | N | I | CFC | 136.67 | 136.67 | 0 | 0 | 1999-11-01 | 2002-12-01 | 2002-12-01 |  | 2005-03-01 | 2005-07-01 | 515970 | 0 | 515970 | 515970 | 100% | 0 | 0 |  | 66756.7 | 0 | 66756.7 | 0 | 0 | Completed. |  |  |  | INV | 0
CLO | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology in Handan Huisheng Foam Plant | Individual | ASP | CPR | FOA | 29 | INV | 323 | N | I |  | 0 | 0 | 0 | 0 | 1999-11-01 |  | 2002-12-01 |  |  | 2003-12-01 | 522207 | -522207 | 0 | 0 | #DIV/0! | 0 | 0 |  | 67442.77 | -67443 | 0 | -0.23 | -0.23 | Project cancelled at the 40th ExCom. |  |  |  | INV | 0
CLO | IBRD | Conversion of polyurethane vertifoam manufacture from CFC-11 to liquid carbon dioxide technology in Tonxiang Shule Plastic Foam Plant | Individual | ASP | CPR | FOA | 29 | INV | 324 | N | I |  | 0 | 0 | 0 | 0 | 1999-11-01 |  | 2002-12-01 |  |  | 2001-12-01 | 498400 | -498400 | 0 | 0 | #DIV/0! | 0 | 0 |  | 64792 | -63820.12 | 971.88 | 0 | 0 | Project cancelled at the 35th ExCom. |  |  |  | INV | 0
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Shandong Zhifu Zhenxing Polyurethane Materials Plant | Individual | ASP | CPR | FOA | 29 | INV | 325 | N | I | CFC | 36.3 | 36.3 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2002-12-01 |  | 2002-08-01 | 2004-06-01 | 261480 | -24023 | 237457 | 237457 | 100% | 0 | 0 | 0 | 33992.4 | -3123 | 30869.4 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water blown technology in the manufacture of flexible molded foam at Hebei Tianye Automobile Group Co. Ltd. | Individual | ASP | CPR | FOA | 29 | INV | 326 | N | I | CFC | 19.7 | 19.7 | 0 | 0 | 1999-11-01 | 2002-05-01 | 2002-12-01 |  | 2002-08-01 | 2004-06-01 | 98800 | -21346 | 77454 | 77454 | 100% | 0 | 0 | 0 | 12844 | -2774.98 | 10069.0202 | -0.0002 | 0 | Completed in 2002. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water blown technology in the manufacture of integral skin foam at Guangzhou Haohua Automobile Carpet Plant | Individual | ASP | CPR | FOA | 29 | INV | 328 | N | I | CFC | 7.1 | 7.1 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2002-12-01 |  | 2002-09-01 | 2004-06-01 | 119540 | -8640 | 110900 | 110900 | 100% | 0 | 0 | 0 | 15540 | -1123 | 14417 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water blown technology in the manufacture of flexible integral skin foam at Ningxian Oriental Auto Parts Plant | Individual | ASP | CPR | FOA | 29 | INV | 329 | N | I | CFC | 7.3 | 7.3 | 0 | 0 | 1999-11-01 | 2001-09-01 | 2002-12-01 |  | 2003-09-01 | 2005-02-01 | 122235 | -6311 | 115924 | 115924 | 100% | 0 | 0 | 0 | 15891 | -820.45 | 15070.5474 | 0.0026 | 0 | Completed in 2003. Financially completed in 2005. |  | 1999 | 2002-12-01 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Fushan Anti-Corrosion Insulation Engineering Co. Ltd. | Individual | ASP | CPR | FOA | 29 | INV | 330 | N | I | CFC | 54.4 | 54.4 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2003-07-01 |  | 2002-08-01 | 2004-06-01 | 425950 | -15465 | 410485 | 410485 | 100% | 0 | 0 | 0 | 55373.5 | -2010.15 | 53363.35 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of flexible integral skin foam and flexible molded foam at Zhongqi Jinan Auto Parts Factory | Individual | ASP | CPR | FOA | 29 | INV | 331 | N | I | CFC | 21.6 | 21.6 | 0 | 0 | 1999-11-01 | 2001-05-01 | 2002-12-01 |  | 2002-08-01 | 2004-06-01 | 236130 | -8780.42 | 227349.58 | 227350 | 100% | -0.42 | 0 | 0 | 30697 | -1141.4 | 29555.6546 | -0.0546 | 0 | Completed in 2002. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Shandong Anqiu Polyurethane Materials Factory | Individual | ASP | CPR | FOA | 29 | INV | 332 | N | I | CFC | 63.5 | 63.5 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2002-12-01 |  | 2002-08-01 | 2004-06-01 | 497200 | -9710.12 | 487489.88 | 487490 | 100% | -0.12 | 0 | 0 | 64636 | -1262.28 | 63373.7356 | -0.0156 | 0 | Completed in 2002. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to water blown technology in the manufacture of flexible molded foam at Jizhou Beinei Automobile Cushion Plant | Individual | ASP | CPR | FOA | 29 | INV | 333 | N | I | CFC | 30 | 30 | 0 | 0 | 1999-11-01 | 2001-09-01 | 2002-12-01 |  | 2003-05-01 | 2005-03-01 | 484040 | -18030 | 466010 | 466010 | 100% | 0 | 0 | 0 | 62925 | -2343.89 | 60581.1074 | 0.0026 | 0 | Completed in 2003. Financially completed in 2005. |  | 1999 | 2002-12-01 | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Shandong Qingdao No. 10 Plastic Plant | Individual | ASP | CPR | FOA | 29 | INV | 334 | N | I | CFC | 38.1 | 38.1 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2002-12-01 |  | 2002-08-01 | 2004-06-01 | 298480 | -30327 | 268153 | 268153 | 100% | 0 | 0 | 0 | 38802 | -3942.51 | 34859.49 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 1999 |  | Investment
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Shanghai Furong Food Machinery Factory | Individual | ASP | CPR | FOA | 29 | INV | 335 | N | I | CFC | 23.1 | 23.1 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2002-12-01 |  | 2002-06-01 | 2003-09-01 | 139379 | 0 | 139379 | 139379 | 100% | 0 | 0 |  | 18119.27 | 0 | 18119.27 | 0 | 0 | Physically completed. Draft PCR under review. |  |  |  | INV | 0
FIN | UNIDO | Preparation of investment project in the polystyrene/ polyethylene foam sector | Individual | ASP | CPR | FOA | 30 | PRP | 337 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-07-01 | 2001-04-01 |  | 2002-03-01 | 2003-05-01 | 50000 | -2840 | 47160 | 47160.44 | 100% | -0.44 | 0 |  | 6500 | -379 | 6121 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the rigid foam sector | Individual | ASP | CPR | FOA | 30 | PRP | 338 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-07-01 | 2001-04-01 |  | 2002-03-01 | 2003-05-01 | 50000 | -2627 | 47373 | 47372.77 | 100% | 0.23 | 0 |  | 6500 | -351 | 6149 | 0 | 0 | FIN
FIN | IBRD | Project preparation in the flexible polyurethane foam subsector |  | ASP | CPR | FOA | 30 | PRP | 342 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 |  |  |  |  | Non-INV | 0
CLO | UNDP | Preparation of 7 projects in the rigid foam subsector | Individual | ASP | CPR | FOA | 30 | PRP | 343 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 |  | 2001-04-01 |  |  | 2003-01-01 | 35000 | -35000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 4550 | -4550 | 0 | 0 | 0 | Canceled in 2000. Financially Completed in 2003. |  | 2000 |  | Investment
CLO | UNDP | Preparation of 4 projects in the foam subsector | Individual | ASP | CPR | FOA | 30 | PRP | 345 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 |  | 2001-04-01 |  |  | 2003-01-01 | 40000 | -40000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 5200 | -5200 | 0 | 0 | 0 | Canceled in 2000. Financially Completed in 2003. |  | 2000 |  | Investment
CLO | UNDP | Preparation of 8 projects in the rigid foam subsector | Individual | ASP | CPR | FOA | 30 | PRP | 348 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 |  | 2001-04-01 |  |  | 2003-01-01 | 60000 | -60000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 7800 | -7800 | 0 | 0 | 0 | Canceled in 2000. Financially Completed in 2003. |  | 2000 |  | Investment
FIN | IBRD | Project preparation in the foam flexible subsector |  | ASP | CPR | FOA | 30 | PRP | 349 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation in the foam (general) sector |  | ASP | CPR | FOA | 30 | PRP | 350 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2001-12-01 | 2001-12-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 |  | 39000 | 0 | 39000 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation in the rigid polyurethane foam sub-sector |  | ASP | CPR | FOA | 30 | PRP | 353 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | Completed |  |  |  | Non-INV | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Qujing Plastic No. 2 Plant | Individual | ASP | CPR | FOA | 31 | INV | 358 | N | I | CFC | 99 | 99 | 0 | 0 | 2000-07-01 | 2003-04-01 | 2003-08-01 |  | 2004-09-01 | 2005-12-01 | 600066 | 0 | 600066 | 600066 | 100% | 0 | 0 |  | 76007.26 | 0 | 76007.26 | 0 | 0 | Completed. |  |  |  | INV | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Wuxian Polyurethane Foam Plant | Individual | ASP | CPR | FOA | 31 | INV | 361 | N | I | CFC | 80 | 80 | 0 | 0 | 2000-07-01 | 2003-12-01 | 2003-08-01 |  | 2004-10-01 | 2005-04-01 | 498400 | 0 | 498400 | 498400 | 100% | 0 | 0 |  | 64792 | 0 | 64792 | 0 | 0 | Completed. |  |  |  | INV | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Nantong Xinyuan Foam Plant | Individual | ASP | CPR | FOA | 31 | INV | 362 | N | I | CFC | 82 | 82 | 0 | 0 | 2000-07-01 | 2003-05-01 | 2003-08-01 |  | 2004-10-01 | 2004-12-01 | 510860 | 0 | 510860 | 510860 | 100% | 0 | 0 |  | 66194.6 | 0 | 66194.6 | 0 | 0 | Financially completed. |  |  |  | INV | 0
CLO | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Jintan Tiaoxi Shuya Foam Plant | Individual | ASP | CPR | FOA | 31 | INV | 363 | N | I |  | 0 | 0 | 0 | 0 | 2000-07-01 |  | 2003-08-01 |  |  | 2001-12-01 | 420525 | -420525 | 0 | 0 | #DIV/0! | 0 | 0 |  | 54668.25 | -53848.23 | 820.02 | -3.1832e-12 | 0 | Project cancelled at the 35th ExCom. |  |  |  | INV | 0
FIN | UNIDO | Replacement of CFC-11 with HCFC-141b in manufacturing of PU rigid spray foam for insulation at 26 enterprises | Individual | ASP | CPR | FOA | 32 | INV | 369 | A | I | CFC | 891.4 | 891.4 |  |  | 2000-12-01 | 2001-07-01 | 2003-07-01 |  | 2004-12-01 | 2006-09-01 | 3295600 | 2025174 | 5320774 | 5320774.18 | 100% | -0.18 | 0 |  | 372516 | 232769 | 605285 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project preparation for two umbrella projects in the polystyrene/polyethylene foam sector | Individual | ASP | CPR | FOA | 33 | PRP | 371 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-10-01 | 2002-10-01 |  | 2002-12-01 | 2003-12-01 | 100000 | -2686 | 97314 | 97314.17 | 100% | -0.17 | 0 |  | 13000 | -369 | 12631 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phasing out CFC-11 with HCFC-141b at six companies Hongyu, Longan, Songliao, Tianyun, Xinyang and Yizheng) and phasing out CFC-11 by conversion to water blown technology at one company (Yinxian) | Individual | ASP | CPR | FOA | 34 | INV | 375 | A | I | CFC | 191.6 | 191.6 |  |  | 2001-07-01 | 2001-09-01 | 2004-02-01 |  | 2004-07-01 | 2005-12-01 | 1087764 | -80453 | 1007311 | 1007310.63 | 100% | 0.37 | 0 |  | 129654 | -9025 | 120628 | 1 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase out of CFC-12 in the manufacture of extruded polystyrene foams to butane at 9 enterprises (umbrella) | Individual | ASP | CPR | FOA | 34 | INV | 376 | A | I | CFC | 750 | 750 |  |  | 2001-07-01 | 2002-02-01 | 2003-08-01 |  | 2004-12-01 | 2009-09-01 | 2808338 | 0 | 2808338 | 2808337.9 | 100% | 0.1 | 0 |  | 318917 | 0 | 318917 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase out of CFC-12 in the manufacturing of extruded polystyrene foams through the use of butane as a blowing agent at 7 enterprises (terminal umbrella project) | One-off Phase Out | ASP | CPR | FOA | 35 | INV | 379 | A | I | CFC | 359 | 359 |  |  | 2001-12-01 | 2002-12-01 | 2004-01-01 |  | 2007-12-01 | 2009-09-01 | 2450123 | -2605 | 2447518 | 2447518.19 | 100% | -0.19 | 0 |  | 279514 | -287 | 279227 | 0 | 0 | FIN |  |  |  | INV
FIN | IBRD | Sector plan for phase-out of CFC-11 in the China foam sector: 2002 annual programme | Multiyear | ASP | CPR | FOA | 35 | INV | 380 | N | I | CFC | 2000 | 2000 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2002-12-01 |  | 2002-12-01 | 2013-06-01 | 9940000 | 0 | 9940000 | 9940000 | 100% | 0 | 0 |  | 886600 | 0 | 886600 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | UNIDO | Terminal umbrella project for the elimination of CFC-12 in manufacturing of EPE foam packaging nets at 30 enterprises | One-off Phase Out | ASP | CPR | FOA | 36 | INV | 387 | A | I | CFC | 849.3 | 849.3 |  |  | 2002-03-01 | 2002-12-01 | 2004-09-01 |  | 2004-12-01 | 2010-04-01 | 1525648 | 2800061 | 4325709 | 4325709 | 100% | 0 | 0 |  | 171352 | 314476 | 485828 | 0 | 0 | FIN |  |  |  | INV
FIN | IBRD | Sector plan for phase-out of CFC-11 in the China foam sector: 2003 annual programme | Multiyear | ASP | CPR | FOA | 38 | INV | 396 | N | I | CFC | 2500 | 2721 | 0 | 0 | 2002-11-01 | 2003-06-01 | 2003-12-01 |  | 2003-12-01 | 2013-06-01 | 12570000 | 0 | 12570000 | 12570000 | 100% | 0 | 0 |  | 1115300 | 0 | 1115300 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for phase-out of CFC-11 in the China foam sector: 2004 annual programme | Multiyear | ASP | CPR | FOA | 41 | INV | 405 | N | I | CFC | 2500 | 2500 | 0 | 0 | 2003-12-01 | 2004-12-01 | 2004-12-01 |  | 2004-12-01 | 2013-06-01 | 10903000 | 0 | 10903000 | 10903000 | 100% | 0 | 0 |  | 961270 | 0 | 961270 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for phase-out of CFC-11 in the China foam sector: 2005 annual programme | Multiyear | ASP | CPR | FOA | 44 | INV | 424 | N | I | CFC | 2500 | 2500 | 0 | 0 | 2004-12-01 | 2007-09-01 | 2005-12-01 |  | 2005-12-01 | 2013-06-01 | 10903000 | 0 | 10903000 | 10903000 | 100% | 0 | 0 |  | 961270 | 0 | 961270 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for phase-out of CFC-11 in the China foam sector: 2006 annual programme | Multiyear | ASP | CPR | FOA | 47 | INV | 434 | N | I | CFC | 600 | 600 | 0 | 0 | 2005-11-01 | 2007-09-01 | 2006-12-01 |  | 2008-10-01 | 2013-06-01 | 3320000 | 0 | 3320000 | 3320000 | 100% | 0 | 0 |  | 282800 | 0 | 282800 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for phase-out of CFC-11 in the China foam sector: 2007 annual programme | Multiyear | ASP | CPR | FOA | 53 | INV | 454 | N | I | CFC | 551 | 551 | 0 | 0 | 2007-11-01 | 2008-12-01 | 2009-11-30 |  | 2009-11-01 | 2013-06-01 | 2676000 | 0 | 2676000 | 2676000 | 100% | 0 | 0 |  | 240840 | 0 | 240840 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for phase-out of CFC-11 in the China foam sector: 2008 annual programme | Multiyear | ASP | CPR | FOA | 53 | INV | 455 | N | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-12-01 | 2009-11-30 |  | 2010-01-01 | 2013-06-01 | 1767000 | 0 | 1767000 | 1767000 | 100% | 0 | 0 |  | 159030 | 0 | 159030 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for phase-out of CFC-11 in the China foam sector: 2009 annual programme | Multiyear | ASP | CPR | FOA | 56 | INV | 478 | N | I | CFC | 3492 | 3492 | 0 | 0 | 2008-11-01 | 2009-05-01 | 2009-11-30 |  | 2009-11-01 | 2013-06-01 | 1767000 | 0 | 1767000 | 1767000 | 100% | 0 | 0 |  | 159030 | 0 | 159030 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Preparation of a HCFC phase-out demonstration project (spray foam sector) |  | ASP | CPR | FOA | 57 | PRP | 484 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-12-01 | 2009-12-31 |  | 2009-11-01 | 2009-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 2250 | 0 | 2250 | 0 | 0 | Demo project approved in Nov 09. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of a HCFC phase-out demonstration project (foam insulation for water heaters) |  | ASP | CPR | FOA | 57 | PRP | 485 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-12-01 | 2009-12-31 |  | 2009-11-01 | 2009-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 2250 | 0 | 2250 | 0 | 0 | Demo project approved in Nov 09. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of a HCFC phase-out demonstration project (foam system house) |  | ASP | CPR | FOA | 57 | PRP | 486 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-12-01 | 2009-03-31 |  | 2009-11-01 | 2009-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 6000 | 0 | 6000 | 0 | 0 | Demo. project approved in Nov 09. |  |  |  | Non-INV | 0
ONG | IBRD | Conversion demonstration from HCFC-141b-based to cyclopentane-based pre-blended polyol in the manufacture of rigid polyurethane foam at Guangdong Wanhua Rongwei Polyurethane Co. Ltd | Individual | ASP | CPR | FOA | 59 | DEM | 491 | N | I | HCFC | 6.8 | 6.8 | 0 | 0 | 2009-11-01 | 2010-07-01 | 2011-11-30 | 2017-05-01 |  |  | 1214936 | 0 | 1214936 | 1193137 | 98.21% | 21799 | 21799 | 21799 | 91120 | 0 | 89485.07 | 1634.93 | 1634.93 | Vanward, with the assistance from Rongwei the System House, has completed mould retrofits and polyols optimization to meet the requirements of the new standard. | By Jan 17, Vanward completed physical conversion and stopped using ODS, started new production facilities, disposed of baseline equipment and received required environmental and safety approvals from local authorities. Vanward also applied for commissioning from FECO by Mar 17. FECO will organize experts to verify the project on Mar 28th. |  |  | INV | 0 | To request the submission of additional status report to the 79th meeting to monitor project completion.
FIN | IBRD | Conversion of the foam part of Jiangsu Huaiyin Huihuang Solar Co. Ltd. from HCFC-141b to cyclopentane | Individual | ASP | CPR | FOA | 59 | DEM | 492 | N | I | HCFC | 5.1 | 5.1 | 0 | 0 | 2009-11-01 | 2010-07-01 | 2011-11-30 |  | 2012-11-30 | 2012-11-30 | 786668 | 0 | 786668 | 786668 | 100% | 0 | 0 |  | 59000 | 0 | 59000 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Conversion from HCFC-141b-based to HFC-245fa-based spray polyurethane foam at Harbin Tianshuo Building Materials Co. Ltd. | Individual | ASP | CPR | FOA | 59 | INV | 493 | N | I | HCFC | 1.7 | 1.7 | 0 | 0 | 2009-11-01 | 2010-07-01 | 2010-11-30 |  | 2012-11-30 | 2013-06-01 | 193808 | 0 | 193808 | 193808 | 100% | 0 | 0 |  | 14536 | 0 | 14536 | 0 | 0 | Project fully completed. |  |  | 2011-12-01 | INV | 0
FIN | UNIDO | Preparation for technology demonstration project for hydrocarbon blowing agent in the extruded polystyrene (XPS) foam sector | Individual | ASP | CPR | FOA | 60 | PRP | 496 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-08-01 | 2011-04-30 |  | 2011-08-01 | 2011-12-01 | 30000 | 0 | 30000 | 30000.01 | 100% | -0.01 | 0 |  | 2250 | 0 | 2250 | 0 | 0 | FIN
FIN | UNDP | Preparation of a demonstration project for conversion from HCFC-142b and HCFC-22 technology to methyl formate and co-blowing technology in the manufacture of XPS foam at Feininger (Nanjing) Energy Saving Technology Co. Ltd. | Individual | ASP | CPR | FOA | 60 | PRP | 500 | N | I | HCFC | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-04-01 | 2011-04-01 |  | 2012-08-01 | 2013-04-01 | 30000 | -748.78 | 29251.22 | 29251 | 100% | 0.22 | 0 | 0 | 2250 | -56.16 | 2193.825 | 0.015 | 0 | Financially completed in 2013. | Completed in 2012. | 2010 |  | Investment
FIN | UNDP | Demonstration project for conversion from HCFC-22/HCFC-142b technology to CO2 with methyl formate co-blowing technology in the manufacture of extruded polystyrene foam at Feininger (Nanjing) Energy Saving Technology Co. Ltd. | Individual | ASP | CPR | FOA | 64 | DEM | 507 | N | X | HCFC | 12.3 | 12.3 | 0 | 0 | 2011-07-01 | 2011-09-01 | 2012-09-01 |  | 2014-12-01 | 2015-01-01 | 1973300 | 0 | 1973300 | 1973300 | 100% | 0 | 0 | 0 | 147998 | 0 | 147998 | 0 | 0 | Financially Completed in 2015. | Project completion activities are being closely monitored for completion of project by end of year 2014. | 2011 |  | Non-Investment | 933878
ONG | UNIDO | Preparation for HCFC phase-out investment activities (stage II) (extruded polystyrene foam sector) | Individual | ASP | CPR | FOA | 73 | PRP | 546 | A | I |  | 0 | 0 |  |  | 2014-11-01 | 2015-12-01 | 2016-06-01 | 2017-06-01 |  |  | 260000 | 0 | 260000 | 202244.16 | 77.79% | 57755.84 | 26600.55 | 57500 | 18200 | 0 | 14157 | 4043 | 1862 | - Preparation of Stage II HPMP in the XPS foam sector progressed as planned. - HPMP Stage II for XPS sector plan in China was approved at the 77th ExCom meeting. Milestones achieved: Milestone 1: Yes - Contract signed between FECO and UNIDO for implementation of the PRP. Milestone 2: Yes - Questionnaires distributed among a representative sample of companies, with a feedback ratio of about 70% so far. Milestone 3: Yes - 37 enterprises selected for field survey. Milestone 4: Yes - Coordination meetings of the preparation of Stage II HPMP held in Beijing, China (July and September 2015). Milestone 5: Yes. Project was approved by ExCom Actions towards next goals: (-) Ensure proper project implementation starting Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - UNIDO placed a mission to Beijing and agreed on modalities for project implementation as well as action plan. - Administrative actions have been initiated already. |  |  | NON-INV
COM | Germany | Preparation for HCFC phase-out investment activities (stage II) (extruded polystyrene foam sector) | Individual | ASP | CPR | FOA | 73 | PRP | 553 | A | I | HCFC | 0 |  | 0 |  | 2014-11-01 | 2016-02-01 | 2015-12-01 |  | 2016-12-01 |  | 44987 | 25013 | 70000 | 70000 | 100% | 0 | 0 | 0 | 5848 | 3252 | 9100 | 0 |  | update on submitted documents, Stage II XPS approved at 77th Excom | [5 empty] | To request the submission of additional status report to the 79th meeting to monitor the disbursement rate of approved funds.
ONG | IBRD | Preparation for HCFC phase-out investment activities (stage II) (polyurethane foam sector) |  | ASP | CPR | FOA | 73 | PRP | 558 | A | I |  | 0 | 0 | 0 | 0 | 2014-11-01 | 2015-12-01 | 2015-12-31 | 2017-06-01 |  |  | 400000 | 0 | 400000 | 276337 | 69.08% | 123663 | 123663 | 100000 | 28000 | 0 | 19343.59 | 8656.41 | 8656.41 | Stage II Foam Sector Plan completed by the end of Jan 16 and submitted to the ExCom for its consideration at its 76th Meeting. Clarifications provided to and discussions held with Secretariat. Project considered again in Nov 16 following discussions between China, IAs and ExCom on overall Stage II HPMP and approved. WB-required project documentation for the new grant agreement (GA) between China and the WB, including appraisal and safeguards documents were initiated and completed in draft form by end 2016. Drafts will be further developed in 2017 including project implementation manual. Bank appraisal expected in Aug 17, and new WB-China GA expected by end 2017. | SGAs for data collection for Stage II (CS-18) and preparation of HPMP Stage II (CS-19) are now completed. TOR for the project implementation manual prepared by FECO and submitted to Bank for review. |  |  | Non-INV | 0
FIN | UNDP | Survey of production and consumption of methyl bromide in China | Individual | ASP | CPR | FUM | 12 | TAS | 60 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-10-01 | 1995-03-01 |  | 1998-10-01 | 2001-12-01 | 87000 | -1791 | 85209 | 85209 | 100% | 0 | 0 | 0 | 11310 | -232.26 | 11077.74 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1994 |  | Non-Investment
FIN | Canada | Methyl bromide replacement demonstration programme | Individual | ASP | CPR | FUM | 22 | DEM | 199 | A | I |  | 0 |  | 0 |  | 1997-05-01 | 1997-06-01 | 1999-06-01 |  | 1998-10-01 | 1998-10-01 | 145000 | 0 | 145000 | 145000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project Completed |  | 1997 |  | Non-Inv.
FIN | UNIDO | Demonstration project on alternatives to the use of methyl bromide in soil fumigation | Individual | ASP | CPR | FUM | 22 | DEM | 201 | A | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-09-01 | 1999-06-01 |  | 1999-12-01 | 2001-08-01 | 443300 | -13942 | 429358 | 429358.46 | 100% | -0.46 | 0 |  | 57629 | -1901 | 55728 | 0 | 0 | FIN
FIN | UNEP | Sectoral policy plan for methyl bromide phase-out in China | Individual | ASP | CPR | FUM | 24 | TAS | 238 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 1999-01-01 |  | 1999-12-01 | 2001-12-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 |  | 19500 | 0 | 19500 | 0 | 0
FIN | UNEP | Awareness raising workshop to support ratification of the Copenhagen Amendment | Individual | ASP | CPR | FUM | 35 | TAS | 381 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-05-01 | 2002-12-01 |  | 2004-12-01 | 2010-12-01 | 100000 | -53818 | 46182 | 46182 | 100% | 0 | 0 |  | 13000 | -6996 | 6004 | 0 | 0 |  |  |  | 2004-06-01
FIN | UNEP | Techno-economic evaluation of methyl bromide alternatives | Individual | ASP | CPR | FUM | 35 | TAS | 382 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-05-01 | 2002-12-01 |  | 2004-12-01 | 2008-12-01 | 80000 | -9093 | 70907 | 70907 | 100% | 0 | 0 |  | 10400 | -1182 | 9218 | 0 | 0 |  |  |  | 2004-06-01
FIN | UNIDO | Preparation of a sectoral strategy in the methyl bromide sector | Individual | ASP | CPR | FUM | 36 | PRP | 386 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-12-01 | 2003-05-01 |  | 2003-12-01 | 2004-08-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | National phase-out of methyl bromide (first tranche) | Multi-Year | ASP | CPR | FUM | 41 | INV | 407 | A | I | MBR | 364 | 364 |  |  | 2003-12-01 | 2004-04-01 | 2007-03-01 |  | 2007-12-01 | 2008-09-01 | 4086600 | -1 | 4086599 | 4086599.43 | 100% | -0.43 | 0 |  | 306495 | 0 | 306495 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a methyl bromide consumption phase-out plan | Individual | ASP | CPR | FUM | 43 | PRP | 412 | A | I |  | 0 | 0 |  |  | 2004-07-01 | 2004-10-01 | 2005-07-01 |  | 2004-12-01 | 2005-05-01 | 20000 | -44 | 19956 | 19956.38 | 100% | -0.38 | 0 |  | 1500 | -6 | 1494 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of a production phase-out plan in the fumigants sector (methyl bromide) | Individual | ASP | CPR | FUM | 45 | PRP | 430 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-07-01 | 2006-04-01 |  | 2005-12-01 | 2006-02-01 | 40000 | -31 | 39969 | 39969.44 | 100% | -0.44 | 0 |  | 3000 | -7 | 2993 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | Italy | National phase-out of methyl bromide (phase II) | Multi-Year | ASP | CPR | FUM | 46 | INV | 431 | A | I | MBR | 534 | 534 | 0 |  | 2005-07-01 | 2007-03-01 | 2015-07-01 |  | 2009-12-01 | 2009-12-01 | 4000000 | 0 | 4000000 | 4000000 | 100% | 0 | 0 | 0 | 470000 | 0 | 470000 | 0 | 0 | FIN |  | 2005 |  | Investment
FIN | UNIDO | National phase-out of methyl bromide (phase II, second tranche) | Multi-Year | ASP | CPR | FUM | 52 | INV | 451 | A | I | MBR | 65.2 | 65.2 |  |  | 2007-07-01 | 2008-02-01 | 2008-07-31 |  | 2008-09-01 | 2008-09-01 | 1200000 | 0 | 1200000 | 1200000 | 100% | 0 | 0 |  | 90000 | 0 | 90000 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National phase-out of methyl bromide (phase II, third tranche) | Multi-Year | ASP | CPR | FUM | 55 | INV | 462 | A | I | MBR | 124.6 | 124.6 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 |  | 2009-12-01 | 2010-12-01 | 1800000 | 0 | 1800000 | 1800000 | 100% | 0 | 0 |  | 135000 | 0 | 135000 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National phase-out of methyl bromide (phase II, fourth tranche) | Multi-Year | ASP | CPR | FUM | 58 | INV | 489 | A | I |  | 0 | 0 |  |  | 2009-07-01 | 2009-11-01 | 2010-07-31 |  | 2010-12-01 | 2010-12-01 | 1300000 | 0 | 1300000 | 1300000 | 100% | 0 | 0 |  | 97500 | 0 | 97500 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National phase-out of methyl bromide (phase II, fifth tranche) | Multi-Year | ASP | CPR | FUM | 61 | INV | 501 | A | I |  | 0 | 0 |  |  | 2010-07-01 | 2010-12-01 | 2011-07-31 |  | 2011-12-01 | 2012-12-01 | 600000 | 0 | 600000 | 600000 | 100% | 0 | 0 |  | 45000 | 0 | 45000 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National phase-out of methyl bromide (phase II, sixth tranche) | Multi-Year | ASP | CPR | FUM | 64 | INV | 509 | A | I | MBR | 26 | 33 |  |  | 2011-07-01 | 2012-06-01 | 2012-07-31 |  | 2013-12-01 | 2015-03-01 | 500000 | -2 | 499998 | 499998.01 | 100% | -0.01 | 0 |  | 37500 | 0 | 37500 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National phase-out of methyl bromide (phase II, seventh tranche) | Multi-Year | ASP | CPR | FUM | 67 | INV | 522 | A | I | MBR | 50 | 76 |  |  | 2012-07-01 | 2013-06-01 | 2013-07-31 |  | 2013-12-01 | 2015-03-01 | 500000 | 0 | 500000 | 500000 | 100% | 0 | 0 |  | 37500 | 0 | 37500 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National phase-out of methyl bromide (phase II, eighth tranche) | Multi-Year | ASP | CPR | FUM | 71 | INV | 538 | A | I |  | 0 | 50 |  |  | 2013-12-01 | 2014-08-01 | 2014-12-31 |  | 2014-12-01 | 2016-03-01 | 500000 | 0 | 500000 | 500000 | 100% | 0 | 0 |  | 37500 | 0 | 37500 | 0 | 0 | The project was financially completed and the balance was returned at the 76th ExCom. |  |  |  | INV
ONG | UNIDO | National phase-out of methyl bromide (phase II, ninth tranche) | Multi-Year | ASP | CPR | FUM | 72 | INV | 542 | A | I | MBR | 50 | 50 |  |  | 2014-05-01 | 2015-01-01 | 2015-12-31 | 2018-12-01 |  |  | 302742 | 0 | 302742 | 242192 | 80% | 60550 | 60548.4 | 19000 | 22706 | 0 | 18164 | 4542 | 4541 | - Monitoring, technical assistance and awareness programme ongoing in conjunction with the remaining Technical Assistance activities due to the MB production sector plan. - Data collection for the compilation of the completion project report still ongoing. A detailed report was submitted for the consideration of the 77th Meeting of the ExCom. The extension of the project duration until December 2018 is suggested in line with the planned completion date of the sector plan for the methyl bromide production. Due the similarities and overlaps between the two projects, the combination of the completion reports is recommended, thus a single plan for data collection, analysis, etc. would be sufficient. | - The extension to Dec 2018 has been granted at the 77th ExCom: Monitoring, technical assistance and awareness programme is ongoing in conjunction with the remaining Technical Assistance activities due to the MB production sector plan. - Data collection for the compilation of the project completion report still ongoing. - No delay - No recurring problem - No impact on project completion date - No action required by Executive Committee |  |  | INV
FIN | UNDP | Technical study on halons usage and applications of halons substitutes | Individual | ASP | CPR | HAL | 06 | TAS | 09 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-04-01 | 1993-06-01 |  | 1993-06-01 | 1997-12-01 | 40000 | 3345 | 43345 | 43345 | 100% | 0 | 0 | 0 | 5200 | 434.85 | 5634.85 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | IBRD | Zhejiang halon extinguisher conversion | Individual | ASP | CPR | HAL | 07 | INV | 17 | N | I | HAL | 1200 | 1200 | 0 | 0 | 1992-06-01 | 1994-06-01 | 1993-12-01 |  | 1996-11-01 | 1996-01-01 | 797000 | -67000 | 730000 | 730000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and ODP phaseout target reached. The project was commissioned in May 97. |  |  | 1996-11-01 | INV | 0
FIN | IBRD | Beijing ABC powder production project | Individual | ASP | CPR | HAL | 07 | INV | 18 | N | I | HAL | 1200 | 1200 | 0 | 0 | 1992-06-01 | 1994-05-01 | 1993-06-01 |  | 1996-04-01 | 1996-08-01 | 403000 | 527000 | 930000 | 930000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project complete. |  |  |  | INV | 0
FIN | UNIDO | Substituting halon in fire fighting equipment at Nanjing | Individual | ASP | CPR | HAL | 09 | PRP | 194 | A | I |  | 0 | 0 |  |  | 1993-03-01 | 1994-04-01 | 1996-03-01 |  | 1995-03-01 | 1998-08-01 | 36000 | -6926 | 29074 | 29074 | 100% | 0 | 0 |  | 4680 | -906 | 3774 | 0 | 0 | FIN
FIN | UNDP | Implementation of the halon phase-out plan for China: current situation, revision of national codes, and education and training | Individual | ASP | CPR | HAL | 10 | TAS | 40 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1995-01-01 | 1996-06-01 |  | 1998-09-01 | 2000-12-01 | 280000 | -24125 | 255875 | 255875 | 100% | 0 | 0 | 0 | 36400 | -3136.25 | 33263.75 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1993 |  | Non-Investment
FIN | UNDP | Implementation of the halon phase-out plan for China: transfer of technology on alternatives to halon fire protection systems | Individual | ASP | CPR | HAL | 10 | TAS | 41 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1995-11-01 | 1996-06-01 |  | 1999-06-01 | 2000-12-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 | 0 | 39000 | 0 | 39000 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1993 | 1999-06-01 | Non-Investment
FIN | USA | Halon management resource manual |  | ASP | CPR | HAL | 11 | TAS | 53 | A | I |  | 0 |  | 0 |  | 1993-11-01 |  | 1994-11-01 |  | 1994-11-01 | 1994-11-01 | 32000 | 0 | 32000 | 32000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1993
FIN | USA | Halon-1211 recovery/recharge training workshops |  | ASP | CPR | HAL | 11 | TRA | 57 | A | I |  | 0 |  | 0 |  | 1993-11-01 |  | 1994-11-01 |  | 1994-11-01 | 1994-11-01 | 271000 | 0 | 271000 | 271000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1993
FIN | USA | Deployment of halon-1211 recovery/recharge machines |  | ASP | CPR | HAL | 12 | INV | 59 | A | I | HAL | 200 | 231 | 0 |  | 1994-03-01 |  | 1995-12-01 |  | 1995-12-01 | 1996-06-01 | 735000 | 72000 | 807000 | 807000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | UNDP | Acquisition of local air compressors for halon recycling machines | Individual | ASP | CPR | HAL | 12 | INV | 66 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-03-01 |  | 1996-12-01 | 1998-12-01 | 155000 | 0 | 155000 | 155000 | 100% | 0 | 0 | 0 | 20150 | 0 | 20150 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1994 |  | Investment
FIN | USA | Project preparation |  | ASP | CPR | HAL | 13 | PRP | 80 | A | I |  | 0 |  | 0 |  | 1994-07-01 |  | 1996-01-01 |  | 1997-12-01 | 1998-04-01 | 200000 | -68517 | 131483 | 131483 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. No further activities foreseen on this project with the approval of China's Halon Sector Strategy (23rd meeting). |  | 1994 | 1997-12-01
FIN | UNIDO | Conversion from halon 1211 to ABC dry powder and foam water spray at Nanjing Fire Fighting Equipment Factory | Individual | ASP | CPR | HAL | 15 | INV | 104 | A | I | HAL | 1110 | 1480 |  |  | 1994-12-01 | 1995-10-01 | 1996-12-01 |  | 1996-12-01 | 2000-12-01 | 496000 | 0 | 496000 | 496000 | 100% | 0 | 0 |  | 64480 | -53 | 64427 | 0 | 0 | FIN
FIN | USA | Halon leak reduction demonstration |  | ASP | CPR | HAL | 16 | DEM | 121 | A | I | HAL | 221.7 | 74 | 0 |  | 1995-03-01 | 1995-04-01 | 1996-03-01 |  | 1996-12-01 | 1998-06-01 | 90437 | 0 | 90437 | 90437 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1995
FIN | IBRD | Additional preparation of halon sector approach |  | ASP | CPR | HAL | 20 | PRP | 184 | A | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-03-31 | 1997-08-01 |  | 1997-09-30 | 1997-09-30 | 132500 | 0 | 132500 | 132500 | 100% | 0 | 0 |  | 17225 | 0 | 17225 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation in the halon sector |  | ASP | CPR | HAL | 21 | PRP | 187 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-31 | 1997-12-31 | 133000 | -500 | 132500 | 132500 | 100% | 0 | 0 |  | 17290 | -65 | 17225 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Sector plan for halon phaseout in China, 1998 Annual Programme | Multiyear | ASP | CPR | HAL | 23 | INV | 231 | N | I | HAL | 0 | 9939 | 0 | 11739 | 1997-11-01 | 1998-03-01 | 1998-12-01 |  | 1998-12-01 | 2013-06-01 | 12400000 | 0 | 12400000 | 12400000 | 100% | 0 | 0 |  | 1240000 | 0 | 1240000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for halon phaseout in China, 1999 Annual Programme | Multiyear | ASP | CPR | HAL | 26 | INV | 261 | N | I | HAL | 5370 | 5370 | 5970 | 5826 | 1998-11-01 | 1999-03-31 | 1999-12-01 |  | 1999-12-01 | 2013-06-01 | 9700000 | 0 | 9700000 | 9700000 | 100% | 0 | 0 |  | 970000 | 0 | 970000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for halon phaseout in China, 2000 Annual Programme | Multiyear | ASP | CPR | HAL | 29 | INV | 309 | N | I | HAL | 5370 | 3712 | 5970 | 5970 | 1999-11-01 | 2000-08-01 | 2000-12-01 |  | 2000-12-01 | 2013-06-01 | 10600000 | 0 | 10600000 | 10600000 | 100% | 0 | 0 |  | 1060000 | 0 | 1060000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for halon phaseout in China, 2001 Annual Programme | Multiyear | ASP | CPR | HAL | 32 | INV | 364 | N | I | HAL | 1389 | 1389 | 1989 | 1980 | 2000-12-01 | 2002-12-01 | 2001-12-01 |  | 2001-12-01 | 2013-06-01 | 4500000 | 0 | 4500000 | 4500000 | 100% | 0 | 0 |  | 450000 | 0 | 450000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for halon phaseout in China, 2002 Annual Programme | Multiyear | ASP | CPR | HAL | 35 | INV | 383 | N | I | HAL | 2889 | 2889 | 2169 | 2160 | 2001-12-01 | 2002-12-01 | 2002-12-01 |  | 2002-12-01 | 2013-06-01 | 3700000 | 0 | 3700000 | 3700000 | 100% | 0 | 0 |  | 370000 | 0 | 370000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for halon phaseout in China: 2003 annual programme | Multiyear | ASP | CPR | HAL | 38 | INV | 395 | N | I | HAL | 2292 | 2292 | 1992 | 1992 | 2002-11-01 | 2003-12-01 | 2003-12-01 |  | 2003-12-01 | 2013-06-01 | 5900000 | 0 | 5900000 | 5900000 | 100% | 0 | 0 |  | 442500 | 0 | 442500 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for halon phase-out in China: 2004 annual programme | Multiyear | ASP | CPR | HAL | 41 | INV | 404 | N | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-09-01 | 2004-12-01 |  | 2004-12-01 | 2013-06-01 | 1200000 | 0 | 1200000 | 1200000 | 100% | 0 | 0 |  | 90000 | 0 | 90000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for halon phase-out in China: 2005 annual programme | Multiyear | ASP | CPR | HAL | 44 | INV | 423 | N | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2006-06-01 | 2005-12-01 |  | 2005-11-01 | 2013-06-01 | 1800000 | 0 | 1800000 | 1800000 | 100% | 0 | 0 |  | 135000 | 0 | 135000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for halon phase-out in China: 2006 annual programme | Multiyear | ASP | CPR | HAL | 47 | INV | 433 | N | I | HAL | 6170 | 6170 | 10470 | 10470 | 2005-11-01 | 2006-06-01 | 2006-12-01 |  | 2007-11-01 | 2013-06-01 | 11400000 | 0 | 11400000 | 11400000 | 100% | 0 | 0 |  | 855000 | 0 | 855000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for halon phase-out in China: 2007 annual programme | Multiyear | ASP | CPR | HAL | 50 | INV | 445 | N | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-10-01 | 2007-11-01 |  | 2008-10-01 | 2013-06-01 | 400000 | 0 | 400000 | 400000 | 100% | 0 | 0 |  | 30000 | 0 | 30000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for halon phase-out in China: 2008 annual programme | Multiyear | ASP | CPR | HAL | 53 | INV | 456 | N | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-12-01 | 2009-11-30 |  | 2011-12-01 | 2013-06-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 |  | 22500 | 0 | 22500 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for halon phase-out in China: 2009 annual programme | Multiyear | ASP | CPR | HAL | 56 | INV | 481 | N | I | HAL | 1000 | 1000 | 1500 | 1500 | 2008-11-01 | 2011-06-01 | 2009-11-30 |  | 2009-11-01 | 2013-06-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 7500 | 0 | 7500 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | UNIDO | Preparatory assistance for phase out of ODS in tobacco expansion in China | Individual | ASP | CPR | OTH | 09 | TAS | 193 | A | I |  | 0 | 0 |  |  | 1993-03-01 | 1993-10-01 | 1996-03-01 |  | 1996-05-01 | 1998-08-01 | 72000 | 4499 | 76499 | 76499 | 100% | 0 | 0 |  | 9360 | 585 | 9945 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Formulation of investment projects in the tobacco sector | Individual | ASP | CPR | OTH | 18 | PRP | 144 | A | I |  | 0 | 0 |  |  | 1995-11-01 | 1997-03-01 | 1996-11-01 |  | 1999-12-01 | 2002-06-01 | 50000 | -1233 | 48767 | 48766.94 | 100% | 0.06 | 0 |  | 6500 | -170 | 6330 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNIDO | Preparation of a sectoral strategy in the tobacco sector | Individual | ASP | CPR | OTH | 24 | PRP | 237 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-09-01 | 1999-04-01 |  | 1999-11-01 | 2001-07-01 | 200000 | -8020 | 191980 | 191979.71 | 100% | 0.29 | 0 |  | 26000 | -1082 | 24918 | 0 | 0 | FIN |  |  | 1999-10-01
FIN | UNIDO | 2001 Annual work programme of the tobacco sector plan | Multi-Year | ASP | CPR | OTH | 32 | INV | 366 | A | I | CFC | 90 | 90 |  |  | 2000-12-01 | 2001-06-01 | 2001-12-01 |  | 2001-12-01 | 2004-02-01 | 2000000 | 0 | 2000000 | 2000000 | 100% | 0 | 0 |  | 180000 | 0 | 180000 | 0 | 0 | FIN
FIN | UNIDO | Tobacco sector plan for CFC-11 phase-out: 2002 workplan | Multi-Year | ASP | CPR | OTH | 36 | INV | 388 | A | I | CFC | 120 | 200 |  |  | 2002-03-01 | 2002-08-01 | 2003-03-01 |  | 2002-12-01 | 2003-07-01 | 2000000 | 0 | 2000000 | 2000000 | 100% | 0 | 0 |  | 180000 | 0 | 180000 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Tobacco sector plan: 2003 annual work programme | Multi-Year | ASP | CPR | OTH | 39 | INV | 400 | A | I | CFC | 180 | 180 |  |  | 2003-04-01 | 2003-10-01 | 2004-04-01 |  | 2003-12-01 | 2005-09-01 | 2000000 | 0 | 2000000 | 2000000 | 100% | 0 | 0 |  | 150000 | 0 | 150000 | 0 | 0 | FIN
FIN | UNIDO | Tobacco sector plan for CFC-11 phase-out: 2004 workplan | Multi-Year | ASP | CPR | OTH | 42 | INV | 409 | A | I | CFC | 200 | 200 |  |  | 2004-04-01 | 2004-08-01 | 2005-04-01 |  | 2005-04-01 | 2006-12-01 | 1800000 | 0 | 1800000 | 1800000 | 100% | 0 | 0 |  | 135000 | 0 | 135000 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Tobacco sector plan for CFC - 11 phase-out: annual programme for 2005 | Multi-Year | ASP | CPR | OTH | 45 | INV | 427 | A | I | CFC | 200 | 200 |  |  | 2005-04-01 | 2005-09-01 | 2006-04-01 |  | 2006-12-01 | 2007-03-01 | 1700000 | 0 | 1700000 | 1700000 | 100% | 0 | 0 |  | 127500 | 0 | 127500 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Tobacco sector plan for CFC - 11 phase-out: annual programme for 2006-2007 | Multi-Year | ASP | CPR | OTH | 48 | INV | 442 | A | I | CFC | 300 | 300 |  |  | 2006-04-01 | 2007-02-01 | 2007-12-01 |  | 2007-12-01 | 2008-05-01 | 1500000 | 0 | 1500000 | 1500000 | 100% | 0 | 0 |  | 112500 | 0 | 112500 | 0 | 0 | FIN |  |  |  | INV
FIN | IBRD | Project preparation in the solvent (process agent) sector |  | ASP | CPR | PAG | 30 | PRP | 354 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0 | Completed |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation for the process agent sector plan |  | ASP | CPR | PAG | 34 | PRP | 374 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2002-06-01 |  | 2001-12-01 | 2001-12-01 | 122000 | 0 | 122000 | 122000 | 100% | 0 | 0 |  | 15860 | 0 | 15860 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Phase out the production and consumption of CTC for process agent and other non-identified uses (phase I): First tranche | Multiyear | ASP | CPR | PAG | 38 | INV | 397 | N | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-10-01 | 2003-12-01 |  | 2003-12-01 | 2013-06-01 | 2000000 | 0 | 2000000 | 2000000 | 100% | 0 | 0 |  | 150000 | 0 | 150000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Phase out the production and consumption of CTC for process agent and other non-identified uses (phase I): 2003 annual programme | Multi-Year Partial Phase-out | ASP | CPR | PAG | 39 | INV | 402 | N | I | CTC | 0 | 0 | 2638 | 2638 | 2003-04-01 | 2003-10-01 | 2004-04-01 |  | 2004-04-01 | 2013-06-01 | 20000000 | 0 | 20000000 | 20000000 | 100% | 0 | 0 |  | 1500000 | 0 | 1500000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Project preparation for the second phase of process agents phase-out plan |  | ASP | CPR | PAG | 42 | PRP | 408 | A | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2005-12-01 | 2004-12-01 |  | 2006-04-01 | 2007-01-01 | 125000 | 0 | 125000 | 125000 | 100% | 0 | 0 |  | 9375 | 0 | 9375 | 0 | 0 | Completed technically and financially. |  |  |  | Non-INV | 0
FIN | IBRD | Phase out the production and consumption of CTC for process agent and other non-identified uses (phase I): 2004 annual programme | Multi-Year Partial Phase-out | ASP | CPR | PAG | 43 | INV | 416 | N | I | CTC | 0 | 0 | 6657 | 6657 | 2004-07-01 | 2004-10-01 | 2005-07-01 |  | 2005-07-01 | 2013-06-01 | 16000000 | 0 | 16000000 | 16000000 | 100% | 0 | 0 |  | 1200000 | 0 | 1200000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Process agent sector plan (phase I): 2005 annual programme | Multiyear | ASP | CPR | PAG | 46 | INV | 432 | N | I | CTC | 4556 | 4556 | 16171 | 16171 | 2005-07-01 | 2005-12-01 | 2006-07-01 |  | 2006-07-01 | 2013-06-01 | 2000000 | 0 | 2000000 | 2000000 | 100% | 0 | 0 |  | 150000 | 0 | 150000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for phase-out of ODS process agent applications (phase II) and corresponding CTC production (first tranche) | Multiyear | ASP | CPR | PAG | 47 | INV | 437 | N | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-08-01 | 2010-12-01 |  | 2007-09-01 | 2013-06-01 | 15000000 | 0 | 15000000 | 15000000 | 100% | 0 | 0 |  | 1125000 | 0 | 1125000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Phase-out of the production and consumption of CTC for process agent and other non-identified uses (phase I): 2006 annual programme | Multiyear | ASP | CPR | PAG | 48 | INV | 440 | N | I | CTC | 0 | 0 | 6642 | 6642 | 2006-04-01 | 2006-09-01 | 2007-04-01 |  | 2007-04-01 | 2013-06-01 | 16000000 | 0 | 16000000 | 16000000 | 100% | 0 | 0 |  | 1200000 | 0 | 1200000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for phase-out of ODS process agent applications (phase II) and corresponding CTC production: 2006 annual programme | Multiyear | ASP | CPR | PAG | 48 | INV | 441 | N | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-12-01 | 2007-04-01 |  | 2007-12-01 | 2013-06-01 | 10000000 | 0 | 10000000 | 10000000 | 100% | 0 | 0 |  | 750000 | 0 | 750000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Phase-out of the production and consumption of CTC for process agent and other non-identified uses (phase I): 2007 annual programme | Multiyear | ASP | CPR | PAG | 51 | INV | 448 | N | I | CTC | 0 | 0 | 6642 | 6642 | 2007-03-01 | 2007-08-01 | 2008-03-01 |  | 2008-03-01 | 2013-06-01 | 5000000 | 0 | 5000000 | 5000000 | 100% | 0 | 0 |  | 375000 | 0 | 375000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for phase-out of ODS process agent applications (phase II) and corresponding CTC production: 2007 annual programme | Multiyear | ASP | CPR | PAG | 52 | INV | 452 | N | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-09-01 | 2008-07-31 |  | 2008-07-01 | 2013-06-01 | 10000000 | 0 | 10000000 | 10000000 | 100% | 0 | 0 |  | 750000 | 0 | 750000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Phase-out of the production and consumption of CTC for process agent and other non-identified uses (phase I): 2008 annual programme | Multiyear | ASP | CPR | PAG | 54 | INV | 458 | N | I | CTC | 0 | 0 | 10594 | 10594 | 2008-04-01 | 2008-12-01 | 2009-03-31 |  | 2009-12-01 | 2013-06-01 | 3000000 | 0 | 3000000 | 3000000 | 100% | 0 | 0 |  | 225000 | 0 | 225000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for phase-out of ODS process agent applications (phase II) and corresponding CTC production: 2008 annual programme | Multiyear | ASP | CPR | PAG | 55 | INV | 463 | N | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-12-01 | 2009-07-31 |  | 2009-12-01 | 2013-06-01 | 10000000 | 0 | 10000000 | 10000000 | 100% | 0 | 0 |  | 750000 | 0 | 750000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Phase-out of the production and consumption of CTC for process agent and other non-identified uses (phase I): 2009 annual programme | Multiyear | ASP | CPR | PAG | 57 | INV | 483 | N | I | CTC | 6587 | 6587 | 2818 | 2818 | 2009-04-01 | 2010-01-01 | 2010-03-31 |  | 2011-12-01 | 2013-06-01 | 1000000 | 0 | 1000000 | 1000000 | 100% | 0 | 0 |  | 75000 | 0 | 75000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for phase-out of ODS process agent applications (phase II) and corresponding CTC production: 2009 annual programme | Multiyear | ASP | CPR | PAG | 58 | INV | 488 | N | I | CTC | 6896 | 6896 | 0 | 0 | 2009-07-01 | 2010-01-01 | 2010-07-31 |  | 2010-07-01 | 2013-06-01 | 1500000 | 0 | 1500000 | 1500000 | 100% | 0 | 0 |  | 112500 | 0 | 112500 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | UNDP | Preparation of a HCFC phase-out management plan: industrial and commercial refrigeration sub-sectors | Individual | ASP | CPR | PHA | 55 | PRP | 460 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2012-08-01 | 2014-03-01 | 604000 | -1449.93 | 602550.07 | 602550 | 100% | 0.07 | 0 | 0 | 45300 | -108.74 | 45191.25 | 0.01 | 0 | Financially completed in 2014. | Completed in 2012. | 2008 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan: solvent sector | Individual | ASP | CPR | PHA | 55 | PRP | 461 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2012-08-01 | 2014-02-01 | 432000 | -505 | 431495 | 431495 | 100% | 0 | 0 | 0 | 32400 | -37.88 | 32362.125 | -0.005 | 0 | Financially completed in 2014. | Completed in 2012. | 2008 |  | Investment
FIN | UNDP | Preparation of an overarching HPMP strategy | Individual | ASP | CPR | PHA | 55 | PRP | 464 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-08-01 | 2009-07-01 |  | 2012-08-01 | 2013-12-01 | 360000 | -5.98 | 359994.02 | 359994 | 100% | 0.02 | 0 | 0 | 27000 | -0.45 | 26999.55 | 0 | 0 | Financially completed in 2013. |  | 2008 |  | Investment
FIN | UNEP | Preparation of a HCFC phase-out management plan: refrigeration servicing sub-sector | RMP | ASP | CPR | PHA | 55 | PRP | 465 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-10-01 | 2009-07-01 |  | 2011-12-01 | 2012-12-01 | 375000 | 0 | 375000 | 375000 | 100% | 0 | 0 |  | 48750 | 0 | 48750 | 0 | 0
FIN | UNIDO | Preparation of a HCFC phase-out management plan (XPS foam sector) | Individual | ASP | CPR | PHA | 55 | PRP | 466 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2009-10-01 | 2009-07-31 |  | 2011-08-01 | 2011-12-01 | 84000 | 0 | 84000 | 84000.02 | 100% | -0.02 | 0 |  | 6300 | 0 | 6300 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | IBRD | Preparation of a HCFC phase-out management plan: HCFC production sector |  | ASP | CPR | PHA | 55 | PRP | 467 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-09-01 | 2009-12-31 |  | 2013-06-01 | 2013-06-01 | 473300 | 0 | 473300 | 473300 | 100% | 0 | 0 |  | 35498 | 0 | 35498 | 0 | 0 | Final disbursement was made in June 2013 after the ExCom approved the HCFC Production Sector Plan (Stage I). |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of a HCFC phase-out management plan: polyurethane foam sector |  | ASP | CPR | PHA | 55 | PRP | 468 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-12-01 | 2009-12-31 |  | 2011-07-01 | 2012-12-01 | 685900 | 0 | 685900 | 685900 | 100% | 0 | 0 |  | 51443 | 0 | 51443 | 0 | 0 | Last disbursement made in Dec. 2012. |  |  |  | Non-INV | 0
FIN | Germany | Preparation of a HCFC phase-out management plan: extruded polystyrene foam | Individual | ASP | CPR | PHA | 55 | PRP | 469 | A | I | HCFC | 0 |  | 0 |  | 2008-07-01 | 2008-09-01 | 2009-07-01 |  | 2011-04-01 | 2012-12-01 | 201369 | 0 | 201369 | 201369 | 100% | 0 | 0 | 0 | 26178 | 0 | 26178 | 0 | 0 | The XPS sector HPMP was completed and submitted. The HPMP has been approved in ExCom 64.
FIN | UNIDO | Preparation of a HCFC phase-out management plan (Room air-conditioning sector) | Individual | ASP | CPR | PHA | 55 | PRP | 470 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-09-01 | 2009-07-31 |  | 2011-08-01 | 2011-12-01 | 500000 | -2 | 499998 | 499997.65 | 100% | 0.35 | 0 |  | 37500 | 0 | 37500 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNDP | Preparation of a HCFC phase-out management plan: extruded polystyrene foam | Individual | ASP | CPR | PHA | 55 | PRP | 471 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2012-08-01 | 2014-02-01 | 84000 | -71.97 | 83928.03 | 83928 | 100% | 0.03 | 0 | 0 | 6300 | -5.4 | 6294.6 | 0 | 0 | Financially completed in 2014. | Completed in 2012. | 2008 |  | Investment
FIN | UNEP | Preparation of a HCFC phase-out management plan: enabling components | RMP | ASP | CPR | PHA | 55 | PRP | 472 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-09-01 | 2009-07-01 |  | 2011-12-01 | 2012-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0
FIN | Germany | Preparation of a HCFC phase-out management plan: extruded polystyrene foam (additional funding) | Individual | ASP | CPR | PHA | 57 | PRP | 482 | A | I | HCFC | 0 |  | 0 |  | 2009-04-01 | 2009-05-01 | 2010-03-01 |  | 2011-04-01 | 2012-12-01 | 201370 | 0 | 201370 | 201370 | 100% | 0 | 0 | 0 | 26178 | 0 | 26178 | 0 | 0 | The XPS sector HPMP was completed and submitted. The HPMP has been approved in ExCom 64.
ONG | IBRD | HCFC phase-out management plan (polyurethane rigid foam sector plan) (stage I, first tranche) | Multiyear | ASP | CPR | PHA | 64 | INV | 508 | N | X |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2013-11-01 | 2012-07-31 | 2017-12-01 |  |  | 38859000 | 0 | 38859000 | 38859000 | 100% | 0 | 0 | 0 | 2914000 | 0 | 2914000 | 0 | 0 | Out of 12,762.95 MT of HCFC-141b to be phased out thru agreements with 54 enterprises 80% achieved by end of 2016 at enterprise level. At the end of 2016, 28 projects total are verified to be completed - 7 of these done in 2016. Remaining 26 are at various stages of implementation and expected to complete before 2018. Ban of HCFC-141b use in the 3 priority subsectors (refrigerators & freezers, reefers, and small household appliances) will be put in place in 2017 which will take care of the balance of consumption expected under the Stage I foam sector plan (14,682 MT total). Out of 6 system house subprojects aimed to allow companies to mix and supply c-pentane pre-blended polyol, two are to complete by 1 Jul 17. Out of 10 TA contracts signed for the Stage I PU foam sector, 4 are completed. Cumulative disbursement of TA activities, including for workshops and travel and ongoing TA activities end-2016 is $1,073,903. An additional 16 TAs are planned; 9 of these are to have contracts signed by early 2017. The rest will be proposed to the WB once TORs are prepared. | Commissioning of most of the conversion beneficiaries is taking place by early 2017. 6 beneficiaries have completed commissioning by end Mar 17, contributing 5014 MT of HCFC phase-out impact. 2 out of the additional 16 TA contracts have been signed, the rest are still undergoing required procedures; 5 TA TORs have been completed and submitted for the WB to review. |  |  | INV | 35495652.4
FIN | UNDP | HCFC phase-out management plan (industrial and commercial refrigeration and air conditioning sector plan) (stage I, first tranche) | Multi-Year | ASP | CPR | PHA | 64 | INV | 512 | N | X | HCFC | 0 | 0 | 0 | 0 | 2011-07-01 | 2011-12-01 | 2012-07-01 |  | 2013-12-01 | 2013-12-01 | 25380000 | 0 | 25380000 | 25380000 | 100% | 0 | 0 | 0 | 1903500 | 0 | 1903500 | 0 | 0 | Financially completed in 2013. |  | 2011 |  | Investment | 12431236
ONG | UNIDO | HCFC-22 phase-out management plan for room air-conditioner manufacturing sector (stage I, first tranche) | Multi-Year | ASP | CPR | PHA | 64 | INV | 513 | A | X |  | 0 | 0 |  |  | 2011-07-01 | 2012-01-01 | 2012-07-31 | 2019-03-01 |  |  | 36430000 | 0 | 36430000 | 32786916.75 | 90% | 3643083.25 | 3643000 | 1 | 2732250 | 0 | 2459019 | 273231 | 273225 | - All lines were converted to R290 except one line in Midea Foshan. Milestones achieved: First mission undertaken/working arrangements agreed: Yes TOR completed/contract signed: Yes Equipment delivered to all beneficiaries: Yes Conversion completed: Yes partially (7 R290 lines and 7 R410A lines) TUV certification and national acceptance completed: Yes partially, ( 6 R290 lines and 5 R410a lines) Actions towards next goals: Complete conversions at all companies. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: Yes, planned completion date is estimated at March 2019. Any action required by Executive Committee? No | - The conversion to R290 at the second production line at Midea is in progress. Milestones achieved: First mission undertaken/working arrangements agreed: Yes TOR completed/contract signed: Yes Equipment delivered to all beneficiaries: Yes Conversion completed: Yes partially (7 R290 lines and 7 R410A lines) TUV certification and national acceptance completed: Yes partially, ( 6 R290 lines and 5 R410a lines) Actions towards next goals: Complete conversion to R290 at 1 line at Midea and complete national acceptance at the above line and for two R410A lines at Aux and Hisense. Furthermore, complete laboratory conversion at Linda compressor line. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: Yes, planned completion date is estimated at March 2019. Any action required by Executive Committee? No |  |  | INV | 11423055 | To request the submission of additional status report to the 79th meeting to monitor the completion of the disbursement of incremental operating costs.
ONG | UNIDO | Sector plan for phase-out of HCFCs in the extruded polystyrene foam sector (stage I, first tranche) | Multi-Year | ASP | CPR | PHA | 64 | INV | 514 | A | X |  | 0 | 0 |  |  | 2011-07-01 | 2012-01-01 | 2012-07-31 | 2018-05-31 |  |  | 21372000 | 0 | 21372000 | 19234716.65 | 90% | 2137283.35 | 2137200 | 1 | 1602900 | 0 | 1442604 | 160296 | 160290 | - All 11 beneficiaries under Tranche 1 have signed their agreement for conversion. Out of which: - 3 already finished their project and reached national acceptance - equipment procurement and signed contracts with suppliers. - 5 are in the process of commissioning their equipment. Milestones achieved: Milestone 1: Yes. All contracts have been signed Milestone 2: Yes. All equipment have been purchased Milestone 3: No. All equipment delivered. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - UNIDO and FECO monitor the status of conversion projects on a regular basis. - Action towards next goals: Finalize conversion of all companies under Tranche I Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV | 8786176
FIN | UNDP | HCFC phase-out management plan (national coordination) (stage I, first tranche) | Multi-year | ASP | CPR | PHA | 64 | INV | 515 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-02-01 | 2013-07-01 |  | 2015-05-01 | 2016-05-01 | 360000 | 0 | 360000 | 360000 | 100% | 0 | 0 | 0 | 27000 | 0 | 27000 | 0 | 0 | Financially completed in 2016. | Activities progressing satisfactorily. HPMP Stage-I tranche requests for consumption sector for all sub-sectors would be submitted to the 75th Excom. | 2011 |  | Investment
COM | Japan | HCFC phase-out management plan (refrigeration servicing sector including enabling programme) (stage I, first tranche) | Multi-Year | ASP | CPR | PHA | 64 | INV | 516 | A | I |  | 0 |  | 0 |  | 2011-07-01 | 2012-11-01 | 2013-07-01 |  | 2013-12-01 |  | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 | 0 | 10400 | 0 | 10400 | 0 | 0 | The launching meeting was held in Shanghai in December 2011, not only for the servicing sector but also for all the sectors.
FIN | Germany | HCFC phase-out management plan (extruded polystyrene foam sector plan) (stage I, first tranche) | Multi-Year | ASP | CPR | PHA | 64 | INV | 518 | A | I | HCFC | 0 | 0 | 0 |  | 2011-07-01 | 2011-07-01 | 2012-07-01 |  | 2013-11-01 | 2015-12-01 | 459023 | 0 | 459023 | 459023 | 100% | 0 | 0 | 0 | 51260 | 0 | 51260 | 0 |  | Finalised | All technical input completed
COM | UNEP | HCFC phase-out management plan (refrigeration servicing sector including enabling programme) (stage I, first tranche) | Multi-Year | ASP | CPR | PHA | 64 | TAS | 517 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-05-01 | 2013-07-01 |  | 2014-12-01 |  | 1579000 | 0 | 1579000 | 1579000 | 100% | 0 | -1 |  | 176703 | 0 | 176703 | 0 | -0.11191 | Project completed. | project completed
FIN | UNDP | Sector plan for phase-out of HCFCs in the solvent sector (stage I, first tranche) | Multi-year | ASP | CPR | PHA | 65 | INV | 519 | N | X | HCFC | 33 | 33 | 0 | 0 | 2011-11-01 | 2012-07-01 | 2016-10-01 |  | 2015-05-01 | 2016-05-01 | 2500000 | 0 | 2500000 | 2500000 | 100% | 0 | 0 | 0 | 187500 | 0 | 187500 | 0 | 0 | Financially completed in 2016. | Activities are progressing satisfactorily with most of the companies covered under solvent sector plan at advanced stages of project implementation. Last tranche request would be submitted along with necessary verification reports as per the HPMP agreement. | 2011 |  | Investment | 2500000
ONG | UNIDO | HCFC-22 phase-out management plan for room air-conditioner manufacturing sector (stage I, second tranche) | Multi-Year | ASP | CPR | PHA | 68 | INV | 524 | A | X | HCFC | 176 | 0 |  |  | 2012-12-01 | 2013-10-01 | 2013-12-31 | 2019-03-01 |  |  | 9200000 | 0 | 9200000 | 8280000 | 90% | 920000 | 920000 | 1 | 644000 | 0 | 579600 | 64400 | 64400 | - Conversion to R290 and national acceptance of 1 compressor production line at Qingan company was completed in 2016. Milestones achieved: First mission undertaken/working arrangements agreed: Yes TOR completed/contract signed: Yes Equipment delivered to all beneficiaries: Yes Conversion completed: Yes TUV certification and national acceptance completed: Yes, partially. Actions towards next goals: Completion of the national acceptance of one compressor line. Was there any delay during the reporting year? No. Any recurring problem? No Any action required by Executive Committee? No | - All lines under Tranche 2 completed national acceptance except one compressor line at Highly. Milestones achieved: First mission undertaken/working arrangements agreed: Yes TOR completed/contract signed: Yes Equipment delivered to all beneficiaries: Yes Conversion completed: Yes TUV certification and national acceptance completed: Yes, partially. Actions towards next goals: Completion of the national acceptance of one compressor line at Highly. Was there any delay during the reporting year? Yes, national acceptance. Project is extended until March 2019 to make sure that all activities under Tranche 2 can be completed. Any recurring problem? No Any action required by Executive Committee? No |  |  | INV | 2881428 | To request the submission of additional status report to the 79th meeting to monitor the completion of the conversion of the compressor line.
FIN | UNDP | HCFC phase-out management plan (stage I, second tranche) (industrial and commercial refrigeration and air conditioning sector plan) | Multi-Year | ASP | CPR | PHA | 68 | INV | 525 | N | X | HCFC | 44 | 44 | 0 | 0 | 2012-12-01 | 2013-02-01 | 2015-12-01 |  | 2015-12-01 | 2016-12-01 | 6900000 | 0 | 6900000 | 6900000 | 100% | 0 | 0 | 0 | 483000 | 0 | 483000 | 0 | 0 | Financially completed in 2016. | Activities are progressing satisfactorily with most of the companies covered under ICR sector plan at advanced stages of project implementation. Last tranche request would be submitted along with necessary verification reports as per the HPMP agreement. | 2012 |  | Investment | 4748500
ONG | IBRD | HCFC phase-out management plan (stage I, second tranche) (polyurethane rigid foam sector plan) | Multiyear | ASP | CPR | PHA | 68 | INV | 526 | N | X | HCFC | 103.8 | 103.8 | 0 | 0 | 2012-12-01 | 2013-11-01 | 2013-12-31 | 2017-12-01 |  |  | 5520000 | 0 | 5520000 | 5520000 | 100% | 0 | 0 | 0 | 386400 | 0 | 386400 | 0 | 0 | Out of 12,762.95 MT of HCFC-141b to be phased out thru agreements with 54 enterprises 80% achieved by end of 2016 at enterprise level. At the end of 2016, 28 projects total are verified to be completed - 7 of these done in 2016. Remaining 26 are at various stages of implementation and expected to complete before 2018. Ban of HCFC-141b use in the 3 priority subsectors (refrigerators & freezers, reefers, and small household appliances) will be put in place in 2017 which will take care of the balance of consumption expected under the Stage I foam sector plan (14,682 MT total). Out of 6 system house subprojects aimed to allow companies to mix and supply c-pentane pre-blended polyol, two are to complete by 1 Jul 17. Out of 10 TA contracts signed for the Stage I PU foam sector, 4 are completed. Cumulative disbursement of TA activities, including for workshops and travel and ongoing TA activities end-2016 is $1,073,903. An additional 16 TAs are planned; 9 of these are to have contracts signed by early 2017. Rest will be proposed to WB once TORs are prepared. | Commissioning of most of the conversion beneficiaries is taking place by early 2017. 6 beneficiaries have completed commissioning by end Mar 17, contributing 5014 MT of HCFC phase-out impact. 2 out of the additional 16 TA contracts have been signed, the rest are still undergoing required procedures; 5 TA TORs have been completed and submitted for the WB to review. |  |  | INV | 4927020
COM | Japan | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector including enabling programme) |  | ASP | CPR | PHA | 68 | INV | 527 | A | I |  | 0 |  | 0 |  | 2012-12-01 | 2013-11-01 | 2013-12-01 |  | 2014-12-01 |  | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 | 0 | 10400 | 0 | 10400 | 0 | 0 | The consultation meetings for code/standard development were organized.
COM | UNEP | HCFC phase-out management plan(stage I, second tranche) (refrigeration servicing sector including enabling programme) | Multi-year | ASP | CPR | PHA | 68 | TAS | 528 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-10-01 | 2013-12-01 |  | 2014-12-01 |  | 598000 | 0 | 598000 | 598000 | 100% | 0 | 0 |  | 66921 | 0 | 66921 | 0 | 0 | Project completed. | project completed
ONG | UNIDO | Sector plan for phase-out of HCFCs in the extruded polystyrene foam sector (stage I, second tranche) | Multi-Year | ASP | CPR | PHA | 69 | INV | 529 | A | X | HCFC | 0 | 0 |  |  | 2013-04-01 | 2013-10-01 | 2014-04-30 | 2018-05-31 |  |  | 10217000 | 0 | 10217000 | 9195300 | 90% | 1021700 | 1021700 | 1 | 715190 | 0 | 643671 | 71519 | 71519 | - All 6 beneficiaries under Tranche 2 have signed their agreement for conversion. Out of which: - 1 already finished project and reached national acceptance. - 4 are in the process of commissioning their equipment. Milestones achieved: Milestone 1: Yes. All contracts have been signed Milestone 2: Yes. All equipment have been purchased Milestone 3: No. All equipment delivered. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - UNIDO and FECO monitor the status of conversion projects on a regular basis. - Action towards next goals: Finalize conversion of all companies under Tranche II Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV | 2762856
COM | Germany | HCFC phase-out management plan (stage I, second tranche) (extruded polystyrene foam sector plan) | Multi-Year | ASP | CPR | PHA | 69 | INV | 532 | A | I | HCFC | 0 |  | 0 |  | 2013-04-01 | 2013-09-01 | 2014-04-01 |  | 2015-12-01 |  | 390977 | 0 | 390977 | 390977 | 100% | 0 | 0 | 0 | 47059 | 0 | 47059 | 0 |  | Review of results conversions phase I on-oing for phase II implementation |  |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, third tranche) (extruded polystyrene foam sector plan) | Multi-Year | ASP | CPR | PHA | 71 | INV | 533 | A | X | HCFC | 47.8 | 0 |  |  | 2013-12-01 | 2014-09-01 | 2016-06-01 | 2018-05-31 |  |  | 3998000 | 0 | 3998000 | 3598200 | 90% | 399800 | 399800 | 1 | 279860 | 0 | 251874 | 27986 | 27986 | -1 beneficiary under Tranche 3 has signed agreement for conversion and is in the process of receiving the equipment. Milestones achieved: Milestone 1: Yes. All contracts have been signed Milestone 2: Yes. All equipment have been purchased Milestone 3: Yes All equipment delivered. Milestone 4: No. All equipment commissioned Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - UNIDO and FECO monitor the status of conversion projects on a regular basis. Actions towards next goals: Finalize conversion national acceptance Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV | 812859
ONG | UNDP | HCFC phase-out management plan (stage I, third tranche) (industrial and commercial refrigeration and air conditioning sector plan) | Multi-Year | ASP | CPR | PHA | 71 | INV | 534 | N | X | HCFC | 224.5 | 200 | 0 | 0 | 2013-12-01 | 2014-06-01 | 2015-12-01 | 2017-12-01 |  |  | 8495000 | 0 | 8495000 | 8424373 | 99.17% | 70627 | 0 | 28250.8 | 594650 | 0 | 589706.11 | 4943.89 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Finished and commissioned 2 lines of total 8 lines. Prodoc signed (actual/planned, yes/no and date):41806 Missions undertaken (actual/planned):2 TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: signed earlier First disbursement date (actual/planned): 41791Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | Conversion activities are in process as planned. | 2013 |  | Investment | 3039064 | To request the submission of additional status report to the 79th meeting to monitor disbursement of operating costs.
ONG | IBRD | HCFC phase-out management plan (stage I, third tranche) (polyurethane rigid foam sector plan) | Multiyear | ASP | CPR | PHA | 71 | INV | 535 | N | X | HCFC | 255.6 | 255.6 | 0 | 0 | 2013-12-01 | 2014-12-01 | 2014-12-31 | 2017-12-01 |  |  | 13592000 | 0 | 13592000 | 13592000 | 100% | 0 | 0 | 0 | 951440 | 0 | 951440 | 0 | 0 | Out of 12,762.95 MT of HCFC-141b to be phased out thru agreements with 54 enterprises 80% achieved by end of 2016 at enterprise level. At the end of 2016, 28 projects total are verified to be completed - 7 of these done in 2016. Remaining 26 are at various stages of implementation and expected to complete before 2018. Ban of HCFC-141b use in the 3 priority subsectors (refrigerators & freezers, reefers, and small household appliances) will be put in place in 2017 which will take care of the balance of consumption expected under the Stage I foam sector plan (14,682 MT total). Out of 6 system house subprojects aimed to allow companies to mix and supply c-pentane pre-blended polyol, two are to complete by 1 Jul 17. Out of 10 TA contracts signed for the Stage I PU foam sector, 4 are completed. Cumulative disbursement of TA activities, including for workshops and travel and ongoing TA activities end-2016 is $1,073,903. An additional 16 TAs are planned; 9 of these are to have contracts signed by early 2017. Rest will be proposed to WB once TORs are prepared. | Commissioning of most of the conversion beneficiaries is taking place by early 2017. 6 beneficiaries have completed commissioning by end Mar 17, contributing 5014 MT of HCFC phase-out impact. 2 out of the additional 16 TA contracts have been signed, the rest are still undergoing required procedures; 5 TA TORs have been completed and submitted for the WB to review. |  |  | INV | 7426357.5
ONG | UNIDO | HCFC phase-out management plan (stage I, third tranche) (room air-conditioner manufacturing sector plan) | Multi-Year | ASP | CPR | PHA | 71 | INV | 536 | A | X | HCFC | 49.1 | 0 |  |  | 2013-12-01 | 2014-09-01 | 2016-06-01 | 2019-03-01 |  |  | 8495000 | 0 | 8495000 | 7651024.48 | 90.07% | 843975.52 | 843868.29 | 1 | 594650 | 0 | 535572 | 59078 | 59070.7803 | - Conversion to R290 at 3 enterprises’ 4 production lines were completed. National acceptance of one R290 line (Haier Qingdao) was completed in 2016. Milestones achieved: First mission undertaken/working arrangements agreed: Yes TOR completed/bidding organized: Yes Contract for equipment signed: Yes Equipment delivered and converted: Yes TUV certification and national acceptance completed: Yes, partially. Actions towards next goals: Completion of the national acceptance at the remaining 3 lines. Was there any delay during the reporting year? No. Any impact on project completion date: Yes, planned completion date is estimated at March 2019. Any recurring problem? No. | - National acceptance of an additional R290 line was completed and the national acceptance of the remaining 2 R290 lines was prepared and will be completed in 2017. Milestones achieved: First mission undertaken/working arrangements agreed: Yes TOR completed/bidding organized: Yes Contract for equipment signed: Yes Equipment delivered and converted: Yes TUV certification and national acceptance completed: Yes, partially. Actions towards next goals: Completion of the national acceptance at the remaining 2 lines. Was there any delay during the reporting year? No. Any impact on project completion date: Yes, planned completion date is estimated at March 2019. Any recurring problem? No. |  |  | INV | 1811644
FIN | UNDP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | ASP | CPR | PHA | 71 | INV | 537 | N | X | HCFC | 26.4 | 26.4 | 0 | 0 | 2013-12-01 | 2014-04-01 | 2015-12-01 |  | 2015-12-01 | 2016-12-01 | 2000000 | 0 | 2000000 | 1997711 | 99.89% | 2289 | 0 | 0 | 140000 | 0 | 139839.77 | 160.23 | 0 | Financially completed in 2016. | Activities are progressing satisfactorily with most of the companies covered under solvent sector plan at advanced stages of project implementation. Last tranche request would be submitted along with necessary verification reports as per the HPMP agreement. | 2013 |  | Investment | 1109377
COM | Japan | HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing sector including enabling programme) |  | ASP | CPR | PHA | 72 | INV | 539 | A | I |  | 0 |  | 0 |  | 2014-05-01 | 2014-10-01 | 2015-05-01 |  | 2015-12-01 |  | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 | 0 | 10400 | 0 | 10400 | 0 | 0 | The training materials were prepared.
COM | UNEP | HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing sector including enabling programme) | Multi-Year | ASP | CPR | PHA | 72 | TAS | 541 | A | I |  | 0 |  | 0 |  | 2014-05-01 | 2014-10-01 | 2015-05-01 |  | 2016-12-01 |  | 1104000 | 0 | 1104000 | 510299.45 | 46.22% | 593700.55 | 593700.55 | 593701 | 123547 | 0 | 57106.8534 | 66440.1466 | 66440.1466 | Project completed. | project completed
ONG | UNIDO | HCFC phase-out management plan (stage I, fourth tranche) (extruded polystyrene foam sector plan) | Multi-Year | ASP | CPR | PHA | 73 | INV | 547 | A | X | HCFC | 75 | 0 |  |  | 2014-11-01 | 2015-08-01 | 2017-12-31 | 2018-05-31 |  |  | 6330000 | 0 | 6330000 | 3165000 | 50% | 3165000 | 3165000 | 1 | 443100 | 0 | 221550 | 221550 | 221550 | - All 3 beneficiaries under Tranche 4 have signed their agreement for conversion. Out of which: - 1 finalized the bidding procedures and is expecting delivery of equipment. Milestones achieved: Milestone 1: Yes. All contracts have been signed Milestone 2: No. All equipment have been purchased Milestone 3: No. All equipment delivered. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | UNIDO and FECO monitor the status of conversion projects on a regular basis. Actions towards next goals: Finalize conversion of all companies under Tranche IV Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, fourth tranche) (room air-conditioner manufacturing sector plan) | Multi-Year | ASP | CPR | PHA | 73 | INV | 548 | A | X | HCFC | 44 | 0 |  |  | 2014-11-01 | 2015-11-01 | 2017-12-01 | 2019-06-01 |  |  | 9625000 | 0 | 9625000 | 4812500 | 50% | 4812500 | 0 | 1000000 | 673750 | 0 | 336875 | 336875 | 0 | - Bidding for equipment organized and procurement contracts for the conversion of 2 lines were signed. Two lines started conversion. Milestones achieved: First mission undertaken/working arrangements agreed: Yes TOR completed/bidding organized: Yes Contract for equipment signed: Yes, partially (for 2 lines) Equipment delivered and converted: No TUV certification issued: No Actions towards next goals: Sign procurement contracts for 2 lines and start conversion at the other lines Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: Currently we estimate tranche completion by June 2019. Any action required by Executive Committee? No | - Procurement contracts for the R290 conversion at Haier Jiaozhou signed. Milestones achieved: First mission undertaken/working arrangements agreed: Yes TOR completed/bidding organized: Yes Contract for equipment signed: Yes, partially (for 3 lines) Equipment delivered and converted: Yes, partially for 1 line TUV certification issued: No Actions towards next goals: Sign procurement contracts for 1 line and start conversion at the other lines Was there any delay during the reporting year? No major delays. Any recurring problem? No Any impact on project completion date: Currently we estimate tranche completion by June 2019. Any action required by Executive Committee? No |  |  | INV |  | To request the submission of additional status report to the 79th meeting to monitor the procurement and/or delivery of the equipment.
ONG | UNDP | HCFC phase-out management plan (stage I, fourth tranche) (industrial and commercial refrigeration and air conditioning sector plan) | Multi-Year | ASP | CPR | PHA | 73 | INV | 550 | N | X | HCFC | 27.5 | 8 | 0 | 0 | 2014-11-01 | 2015-06-01 | 2016-11-01 | 2017-12-01 |  |  | 11075000 | 0 | 11075000 | 10985999 | 99.2% | 89001 | 0 | 35600.4 | 775250 | 0 | 769019.93 | 6230.07 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): 4 conversion projects and 2 compressor projects under 4th tranche are in processing. Aux has finished equipment procurement and Shenzhou has finished new product design and started procurement activities as planned. Prodoc signed (actual/planned, yes/no and date):42164 Missions undertaken (actual/planned):2 TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: signed earlier First disbursement date (actual/planned): 42156Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | Conversion activities are in processing as planned. | 2014 |  | Investment | 3949453
ONG | IBRD | HCFC phase-out management plan (stage I, fourth tranche) (polyurethane rigid foam sector plan) | Multiyear | ASP | CPR | PHA | 73 | INV | 551 | N | X | HCFC | 76.7 | 76.7 | 0 | 0 | 2014-11-01 | 2015-07-01 | 2015-12-31 | 2017-12-01 |  |  | 4079000 | -5195 | 4073805 | 4073805 | 100% | 0 | 0 | 0 | 285530 | 0 | 285530 | 0 | 0 | Out of 12,762.95 MT of HCFC-141b to be phased out thru agreements with 54 enterprises 80% achieved by end of 2016 at enterprise level. At the end of 2016, 28 projects total are verified to be completed - 7 of these done in 2016. Remaining 26 are at various stages of implementation and expected to complete before 2018. Ban of HCFC-141b use in the 3 priority subsectors (refrigerators & freezers, reefers, and small household appliances) will be put in place in 2017 which will take care of the balance of consumption expected under the Stage I foam sector plan (14,682 MT total). Out of 6 system house subprojects aimed to allow companies to mix and supply c-pentane pre-blended polyol, two are to complete by 1 Jul 17. Out of 10 TA contracts signed for the Stage I PU foam sector, 4 are completed. Cumulative disbursement of TA activities, including for workshops and travel and ongoing TA activities end-2016 is $1,073,903. An additional 16 TAs are planned; 9 of these are to have contracts signed by early 2017. Rest will be proposed to WB once TORs are prepared. | Commissioning of most of the conversion beneficiaries is taking place by early 2017. 6 beneficiaries have completed commissioning by end Mar 17, contributing 5014 MT of HCFC phase-out impact. 2 out of the additional 16 TA contracts have been signed, the rest are still undergoing required procedures; 5 TA TORs have been completed and submitted for the WB to review. |  |  | INV | 2593406.3
ONG | UNDP | Preparation of a HCFC phase-out management plan (stage II) (overarching strategy) | Individual | ASP | CPR | PHA | 73 | PRP | 545 | N | X | HCFC | 0 | 0 | 0 | 0 | 2014-11-01 | 2015-06-01 | 2016-11-01 | 2017-05-01 |  |  | 200000 | 0 | 200000 | 199740.71 | 99.87% | 259.29 | 0 | 103.716 | 14000 | 0 | 13981.8497 | 18.1503 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Main activities under the project has been completed and all the remaining funding was committed Prodoc signed (actual/planned, yes/no and date):42048 Missions undertaken (actual/planned):2 TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: signed earlier First disbursement date (actual/planned): 42156Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | To complete the funds disbursement by 2nd Q of 2017. | 2014 |  | Non-Investment
COM | UNEP | Preparation of a HCFC phase-out management plan (stage II) (refrigeration servicing sector and enabling programme) | Individual | ASP | CPR | PHA | 73 | PRP | 555 | A | I |  | 0 |  | 0 |  | 2014-11-01 | 2016-05-01 | 2015-12-01 |  | 2016-12-01 |  | 217600 | 0 | 217600 | 0 | 0% | 217600 | 217600 | 217600 | 28288 | 0 | 0 | 28288 | 28288 | Brief progress report (actual/planned): The HPMP stage II was submitted and approved by the Excom at its 76th meeting. The first tranche was then approved by Excom at its 77th meeting. The payments under the signed SSFA with China is being processed. Legal arrangements(actual/planned):signed SSFA with FECO in May 2015. In Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): ___Project completion and follow up: ___ First disbursement date(actual/planned): May 2016. All funds disbursed (yes/no): No___ Any delay?(yes/no): ___ If Yes, reasons for delay & action plan to resolve: If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___ | The payment under signed SSFA is being processing.
COM | Japan | Preparation of a HCFC phase-out management plan (stage II) (refrigeration servicing sector and enabling programme) |  | ASP | CPR | PHA | 73 | PRP | 556 | A | I |  | 0 |  | 0 |  | 2014-11-01 | 2016-05-01 | 2015-12-01 |  | 2016-11-01 |  | 25500 | 0 | 25500 | 25500 | 100% | 0 | 0 | 0 | 3315 | 0 | 3315 | 0 | 0 | The final coordination meeting was held in mid-January 2016 in Beijing, and a proposal document of the China HPMP Stage II was submitted to the ExCom76. The RAC servicing sector and enabling programme component was approved in principle in ExCom76 and the 1st tranche was approved in ExCom77. The first disbusement was made by UNEP in May 2016 due to the Umoja system. | The project is completed.
COM | Japan | HCFC phase-out management plan (stage I, fourth tranche) (refrigeration servicing sector including enabling programme) |  | ASP | CPR | PHA | 74 | INV | 560 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-05-01 | 2016-05-01 |  | 2016-12-01 |  | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 | 0 | 10400 | 0 | 10400 | 0 | 0 | The project is completed. The first disbusement was made by UNEP in May 2016 due to the Umoja system. | the project is completed
COM | Germany | Preparation of a HCFC phase-out management plan (stage II) (refrigeration servicing sector and enabling programme) | Individual | ASP | CPR | PHA | 74 | PRP | 557 | A | I | HCFC | 0 |  | 0 |  | 2015-05-01 | 2016-01-01 | 2015-12-01 |  | 2016-04-01 |  | 46900 | 0 | 46900 | 46900 | 100% | 0 | 0 | 0 | 6097 | 0 | 6097 | 0 |  | Stage II Servicing approved at 77th Excom | [5 empty] | To request the submission of additional status report to the 79th meeting to monitor the disbursement rate of approved funds.
ONG | UNEP | HCFC phase-out management plan (stage I, fourth tranche) (refrigeration servicing sector including enabling programme) | Multi-Year | ASP | CPR | PHA | 74 | TAS | 559 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2015-12-01 | 2016-05-01 | 2017-12-01 |  |  | 1173000 | 0 | 1173000 | 0 | 0% | 1173000 | 1135377.23 | 117300 | 131269 | 0 | 0 | 131269 | 127058.6817 | Brief progress report (actual/planned): The 5th Ozone2Climate Technology Roadshow and Industry Roundtable, during the annual International Exhibition for Refrigeration, Air Conditioning, Heating and Ventilation, Frozen Food Processing, Packaging and Storage (commonly known as CRH) in Beijing, 7-9 April 2016. About eight regional/national training centers participated in the roadshow to outreach the good practices programme, and one parallel forum on training of servicing technicians were organized. The training activities of the regional/natioanl training centers are on-going, and 340 technicians/teachers have been trained. The Vocational Training and Qualification Certification Association of China completed their study on the current situation of the vocational training system in China and presented their findings in August 2016. Two standards were put into force, and ther others were further revised. Legal arrangements(actual/planned): July 2015. First mission (actual/planned): _July 2015__ First disbursement date (actual/planned): Dec 2015 | Brief progress report (actual/planned): FECO is coordinating with local EPBs for a workshop on the output, leasson from the Shenzhen pilot city Project.
ONG | IBRD | HCFC phase-out management plan (stage I, fifth tranche) (polyurethane rigid foam sector plan) | Multiyear | ASP | CPR | PHA | 75 | INV | 563 | N | X | HCFC | 448.36 | 448.36 | 0 | 0 | 2015-11-01 | 2016-12-01 | 2016-12-31 | 2017-12-01 |  |  | 10950000 | 0 | 10950000 | 5475000 | 50% | 5475000 | 5475000 | 3400000 | 766500 | 0 | 383250 | 383250 | 153300 | Out of 12,762.95 MT of HCFC-141b to be phased out thru agreements with 54 enterprises 80% achieved by end of 2016 at enterprise level. At the end of 2016, 28 projects total are verified to be completed - 7 of these done in 2016. Remaining 26 are at various stages of implementation and expected to complete before 2018. Ban of HCFC-141b use in the 3 priority subsectors (refrigerators & freezers, reefers, and small household appliances) will be put in place in 2017 which will take care of the balance of consumption expected under the Stage I foam sector plan (14,682 MT total). Out of 6 system house subprojects aimed to allow companies to mix and supply c-pentane pre-blended polyol, two are to complete by 1 Jul 17. Out of 10 TA contracts signed for the Stage I PU foam sector, 4 are completed. Cumulative disbursement of TA activities, including for workshops and travel and ongoing TA activities end-2016 is $1,073,903. An additional 16 TAs are planned; 9 of these are to have contracts signed by early 2017. Rest will be proposed to WB once TORs are prepared. | Commissioning of most of the conversion beneficiaries is taking place by early 2017. 6 beneficiaries have completed commissioning by end Mar 17, contributing 5014 MT of HCFC phase-out impact. 2 out of the additional 16 TA contracts have been signed, the rest are still undergoing required procedures; 5 TA TORs have been completed and submitted for the WB to review. |  |  | INV | 758997.2
ONG | UNIDO | HCFC phase-out management plan (stage I, fifth tranche) (room air-conditioner manufacturing sector plan) | Multi-Year | ASP | CPR | PHA | 75 | INV | 564 | A | X |  | 0 | 0 |  |  | 2015-11-01 | 2016-06-01 | 2018-12-01 | 2019-12-01 |  |  | 11250000 | 0 | 11250000 | 9360.64 | 0.08321% | 11240639.36 | 3347742.69 | 3000000 | 787500 | 0 | 0 | 787500 | 234341.9883 | - Working arrangements were agreed upon early 2016 and first mission was undertaken in June 2016. The current tranche will support China for the conversion of 1 line to R290 and cover cost of IOC for earlier signed conversion contracts. Applications for conversion received, lines verified. Proposal for production line conversion was approved. Milestones achieved: First mission undertaken/working arrangements agreed: Yes Contract signed with the beneficiary: No. TOR completed/bidding organized: No. Contract for equipment signed: No. Equipment delivered and converted: No TUV certification issued: No Actions towards next goals: Sign contracts with beneficiary and initiate bidding. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No. Any action required by Executive Committee? No | - Contract was signed with the beneficiary. Milestones achieved: First mission undertaken/working arrangements agreed: Yes Contract signed with the beneficiary: Yes TOR completed/bidding organized: Yes. Contract for equipment signed: No. Equipment delivered and converted: No TUV certification issued: No Actions towards next goals: Sign procurement contract for the conversion of the last line to R290 under Stage I. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No. Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, fifth tranche) (extruded polystyrene foam sector plan) | Multi-Year | ASP | CPR | PHA | 75 | INV | 565 | A | X | HCFC | 88.5 | 0 |  |  | 2015-11-01 |  | 2018-12-01 | 2018-05-31 |  |  | 6733000 | 0 | 6733000 | 0 | 0% | 6733000 | 3366500 | 2693200 | 471310 | 0 | 0 | 471310 | 235655 | - 4 beneficiaries under Tranche 5 have signed their agreement for conversion. Out of which: - 2 received the equipment and are expecting the commissioning; - 1 is expecting delivery of equipment Milestones achieved: Milestone 1: Yes. All contracts have been signed Milestone 2: No. All equipment have been purchased Milestone 3: No. All equipment delivered. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - UNIDO and FECO monitor the status of conversion projects on a regular basis. Actions towards next goals: Finalize conversion of all companies under Tranche V Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
ONG | Germany | HCFC phase-out management plan (stage I, fifth tranche) (extruded polystyrene foam sector plan) | Multi-Year | ASP | CPR | PHA | 75 | INV | 566 | A | I | HCFC | 0 |  | 0 |  | 2015-11-01 | 2016-01-01 | 2017-12-01 | 2017-03-01 |  |  | 500000 | 0 | 500000 | 92000 | 18.4% | 408000 | 408000 | 408000 | 60181 | 0 | 11073 | 49108 |  | 3 meetings held, 3 site visits, technical assistance with regard to verification of technology conversions | site visit in January 2017, monitoring of verfication of technology conversion ongoing
ONG | UNDP | HCFC phase-out management plan (stage I, fifth tranche) (industrial and commercial refrigeration and air conditioning sector plan) | Multi-year | ASP | CPR | PHA | 75 | INV | 567 | N | X | HCFC | 38.2 | 0 | 0 | 0 | 2015-11-01 | 2016-05-01 | 2019-12-01 | 2017-12-01 |  |  | 9150000 | 0 | 9150000 | 9097205.41 | 99.42% | 52794.59 | 0 | 21117.836 | 640500 | 0 | 636804.3787 | 3695.6213 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Two conversion projects are in process as planned. Prodoc signed (actual/planned, yes/no and date):42481 Missions undertaken (actual/planned):2 TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: signed earlier First disbursement date (actual/planned): 42494Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | Two conversion projects are in process as planned. Yantai Moon finished design and testing center. | 2015 |  | Investment | 288142
ONG | UNDP | HCFC phase-out management plan (stage I, third tranche) (solvent sector) | Multi-year | ASP | CPR | PHA | 75 | INV | 569 | N | X | HCFC | 0 | 0 | 0 | 0 | 2015-11-01 | 2016-11-01 | 2019-12-01 | 2017-12-01 |  |  | 500000 | 0 | 500000 | 400333.09 | 80.07% | 99666.91 | 0 | 39866.764 | 35000 | 0 | 28023.3163 | 6976.6837 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): All the nine companies have completed their conversion activities. USD 237,903, it is estimated to finish all the disbursement in December,2017 Prodoc signed (actual/planned, yes/no and date):42690 Missions undertaken (actual/planned):2 TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: signed earlier First disbursement date (actual/planned): 42675Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | it is estimated to finish all the disbursement by December,2017 | 2015 |  | Investment | 237903
ONG | Japan | HCFC phase-out management plan (stage I, fifth tranche) (refrigeration servicing sector including enabling programme) |  | ASP | CPR | PHA | 75 | INV | 572 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-05-01 | 2017-12-01 | 2017-12-01 |  |  | 80000 | 0 | 80000 | 0 | 0% | 80000 | 80000 | 80000 | 10400 | 0 | 0 | 10400 | 10400 | The PCA was finalized and signed by UNEP with China in Febuary 2016. FECO has contracted new regional training center following its internal procedure, and the trainining was conducted. | The training programem is still on going as planned.
ONG | UNEP | HCFC phase-out management plan (stage I, fifth tranche) (refrigeration servicing sector including enabling programme) | Multi-Year | ASP | CPR | PHA | 75 | TAS | 571 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-05-01 | 2017-12-01 | 2017-12-01 |  |  | 786000 | 0 | 786000 | 0 | 0% | 786000 | 0 | 78600 | 87960 | 0 | 0 | 87960 | 0 | Brief progress report (actual/planned): Trained about 1,500 currently-employed technicians/trainers, and 600 students who are studying to become refrigeration technicians; Operationalised 2 more new regional training centres; Further refined the training materials for publication; Organized two more specific training workshops on the R290-based room air conditioner which resulted in 200 technicians/trainers being trained; Conducted a performance evaluation of the 14 training centers; Organized an outreach event in Jiaxing in June 2016 for R290-based room air conditioners; facilitated the procurement of 1,062 units of R290-based room air conditioners by Jiaxing Nanyang Polytechnical Institute; Conducted consultations with servicing enterprises and finalized mainstreaming good practices into the qualification certificate system for servicing enterprises; Shenzhen continued its servicing sector management activities; Revised the Public Service Announcements for local display; Maintained daily contacts with the provincial ozone officers through social media to guide their work; Conducted capacity building workshops in Nanchang and Lanzhou for local EPBs from the surrounding provinces; Organized coordination meetings with relevant member ministries of the National Leading Group; Shanghai Customs Academy incorporated ozone issues into its training course and regular curriculum; Coordinated and organized a series of events for the 2016 Ozone Day celebration; Successfully enforced the ODS import/export licensing/quota system with active participation in iPIC; Also around 200 queries were raised/screened using iPIC to clarify questionable trade cases. About 20 cases were rejected. Initiated the update of the ODS import/export control system to allow for automatic approval of applications; Conducted a workshop on the prevention of illegal ODS trade and to share the experience of Ningbo and other Customs on supervision and monitoring of ODS; Conducted workshops for import & export companies. Legal arrangements(actual/planned): Feb 2016. First mission (actual/planned): Jan 2016__ First disbursement date (actual/planned): May 2016 | Brief progress report (actual/planned): The 6th Ozone2Climate Technology Roadshow and Industry Roundtable, during the annual International Exhibition for Refrigeration, Air Conditioning, Heating and Ventilation, Frozen Food Processing, Packaging and Storage (commonly known as CRH) in Shanghai, 12-14 April 2017; The process for contracting more regional/national training centers is on-going, and the training of the technicians by training center is continuing. The national level meeting on the capacity building of the local EPBs is being planned.
ONG | Italy | HCFC phase-out management plan (stage II, first tranche) (room air-conditioner manufacturing sector plan) | Multi-Year | ASP | CPR | PHA | 77 | INV | 574 | A | I | HCFC | 10.3 |  | 0 |  | 2016-12-01 |  | 2019-12-01 | 2019-12-01 |  |  | 891892 | 0 | 891892 | 0 | 0% | 891892 | 0 | 100000 | 108108 | 0 | 0 | 108108 |  | - The Stage II HPMP was approved at the 77th ExCom Meeting in December 2016. - The Government of Italy and UNIDO have started the preparation of a trust fund agreement (see latest remarks for details on the state of the art) | - The details of the Trust Fund Agreement were worked out and the TFA was signed with UNIDO in March 2017. Funds are expected to be transferred to UNIDO during May 2017. Milestones achieved: -Trust Fund Agreement signed/funds received/PAD issued: TFA signed in March. - Participation to the Stge II RAC Sector Inception meeting in Shanghai, 11 March 2017; - Work Plan Agreed with NOU: No Activities planned but not implemented, reasons and strategy: The work plan is under discussion with the NOU and will be presented to the 79th ExCom Meeting in 2017. Actions towards next goals: Transfer funds to UNIDO and agree on work plan with the NOU. Was there any delay during the reporting year? No. Any recurring problem? No Any action required by Executive Committee? No | 2016
ONG | UNIDO | HCFC phase-out management plan (Stage II, first tranche)(RAC sector) | Multi-Year | ASP | CPR | PHA | 77 | INV | 576 | A | X | HCFC | 169 | 0 |  |  | 2016-11-01 |  | 2020-12-31 | 2020-12-31 |  |  | 14671089 | 0 | 14671089 | 0 | 0% | 14671089 | 0 | 2900000 | 1026976 | 0 | 0 | 1026976 | 0 | - The project was approved at the 77th ExCom Meeting and it was noted that the Agreement between the Government and the Executive Committee would be considered at the 79th meeting. It was also approved on the understanding that at least 20 manufacturing lines for the production of RAC equipment to HC-290; three compressor manufacturing lines to HC-290; three HPWH manufacturing lines to HC-290 and two HPWH manufacturing lines to R-744 would be converted. The PAD was issued in December 2016. Milestones achieved: - PAD issued: Yes, in December 2016 - First mission undertaken: No. - Work Plan Agreed with NOU: No - TOR completed/bidding organized: No. - Contract for equipment signed: No. - Equipment delivered and converted: No - TUV certification/national acceptance issued: No Activities planned but not implemented, reasons and strategy: N/A. Actions towards next goals: Agree on work plan with the NOU. Was there any delay during the reporting year? No Any recurring problem? No Any action required by Executive Committee? No | - First mission was undertaken in March 2017 and the inception meeting was organized on 11 March. FECO submitted the draft work plan to UNIDO early March, which is currently under discussion. Milestones achieved: - PAD issued: Yes, in December 2016 - First mission undertaken: Yes, March 2017 - Inception meeting organized: Yes, 11 March 2017 - Work Plan Agreed with NOU: No - TOR completed/bidding organized: No. - Contract for equipment signed: No. - Equipment delivered and converted: No - TUV certification/national acceptance issued: No Activities planned but not implemented, reasons and strategy: The work plan is under discussion with the NOU and will be presented to the 79th ExCom Meeting in 2017. Actions towards next goals: Agree on work plan with the NOU and submit it to the 79th ExCom Meeting. Was there any delay during the reporting year? No Any recurring problem? No Any action required by Executive Committee? No
ONG | UNDP | HCFC phase-out management plan (stage II, first tranche) (industrial and commercial refrigeration and air-conditioning sector plan) | Multi-year | ASP | CPR | PHA | 77 | INV | 577 | N | I | HCFC | 72.1 | 0 | 0 | 0 | 2016-12-01 |  | 2019-12-01 | 2017-12-01 |  |  | 13368756 | 0 | 13368756 | 0 | 0% | 13368756 | 0 | 5347502.4 | 935813 | 0 | 0 | 935813 | 0 | Newly Approved | DoA sent March 2017. | 2016 |  | Investment
ONG | UNIDO | HCFC phase-out management plan (Stage II, first tranche)(XPS sector) | Multi-Year | ASP | CPR | PHA | 77 | INV | 578 | A | X | HCFC | 152.2 | 0 |  |  | 2016-11-01 |  | 2020-12-31 | 2020-12-31 |  |  | 7514867 | 0 | 7514867 | 0 | 0% | 7514867 | 0 | 1200000 | 526041 | 0 | 0 | 526041 | 0 | Approved in principle for the period 2016 to 2026 to complete phase out of all HCFCs in the XPS foam sector. Noted that the Agreement between the Government and the Executive Committee would be considered at the 79th meeting and agency support costs determined at a future meeting. The Government of China, UNIDO and the Government of Germany were requested to deduct 646 ODP tonnes of HCFC-142b and 1,640 ODP tonnes of HCFC-22 from the remaining HCFC consumption eligible for funding. | - Launching ceremony of the sector plan took place in March 2017. - UNIDO and FECO discussed arrangements for project execution and initiated the necessary administrative actions towards the selection of beneficiaries and starting the conversion projects. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No
ONG | IBRD | HCFC phase-out management plan (stage II, first tranche) (polyurethane rigid foam sector plan) | Multiyear | ASP | CPR | PHA | 77 | INV | 579 | N | X | HCFC | 186 | 0 | 0 | 0 | 2016-12-01 |  | 2017-12-31 | 2018-12-01 |  |  | 7045027 | 0 | 7045027 | 0 | 0% | 7045027 | 7045027 | 1500000 | 493152 | 0 | 0 | 493152 | 493152 | Stage II project newly approved. Bank appraisal expected in Aug 17, and new Bank-China agreement expected by end 2017 - upon which disbursement from the WB to China can start. | One-day launch workshop with foam sector stakeholders on 21 April expected to introduce the Stage II PU Foam Sector Plan, present implementation requirements, provide an update on the latest alternative technologies, and allow research institutes (10 TA recipients of Stage I) to present their findings. |  |  | INV | 0
ONG | UNDP | HCFC phase-out management plan (stage II, first tranche) (solvent sector plan) | Multi-year | ASP | CPR | PHA | 77 | INV | 580 | N | I | HCFC | 0 | 0 | 0 | 0 | 2016-12-01 |  | 2019-12-01 | 2017-12-01 |  |  | 2821937 | 0 | 2821937 | 0 | 0% | 2821937 | 0 | 1128774.8 | 197536 | 0 | 0 | 197536 | 0 | Newly Approved | DoA sent March 2017. | 2016 |  | Investment
ONG | UNEP | HCFC phase-out management plan (stage II, first tranche) (refrigeration and air-conditioning servicing sector plan and enabling component) | Multi-Year | ASP | CPR | PHA | 77 | TAS | 581 | A | I |  | 119.3 |  | 0 |  | 2016-12-01 |  | 2017-12-01 | 2017-12-01 |  |  | 3299132 | 0 | 3299132 | 0 | 0% | 3299132 | 0 | 329913.2 | 364651 | 0 | 0 | 364651 | 0 | Brief progress report (actual/planned): Newly approved project in Nov 2016. The discussion with FECO on the detail workplan was initiated, and the draft PCA was developed for comments. | Brief progress report (actual/planned): The implementation plan was discussed and agreed with the country, so the budget allocation. The PCA was agreed and finalized in Feb 2017 for signature. FECO is initiating the full implementation of the approved tranche 1 under stage II. Legal arrangements (actual/planned): The SSFA being signed with internal procedure, it is expected to be signed by middle of March 2017. First Mission: Feb 2017. TOR completed: some of them. First disbursement date: Not yet. All funds disbursed (yes/no): No. Any delay? (yes/no): No. Any ongoing problems (yes/no): No.
ONG | Japan | HCFC phase-out management plan (stage II, first tranche) (refrigeration and air-conditioning servicing sector plan and enabling component) |  | ASP | CPR | PHA | 77 | TAS | 582 | A | I |  | 2.9 |  | 0 |  | 2016-12-01 |  | 2017-12-01 | 2017-12-01 |  |  | 80000 | 0 | 80000 | 0 | 0% | 80000 |  |  | 10400 | 0 | 0 | 10400 | 0 | Newly approved project in Dec 2016. | The PCA is being finalized and fianlized between UNEP and FECO/China.
ONG | Germany | HCFC phase-out management plan (stage II, first tranche) (refrigeration and air-conditioning servicing sector plan and enabling component) |  | ASP | CPR | PHA | 77 | TAS | 583 | A | I | HCFC | 10.9 |  | 0 |  | 2016-12-01 |  | 2017-12-01 | 2018-05-01 |  |  | 300000 | 0 | 300000 |  | 0% | 300000 | 0 | 180000 | 36000 | 0 |  | 36000 |  | Approval at 77th meeting | kick-off meeting in March 2017 - implementation agreement in negotiation
FIN | IBRD | Production-sector pre-investment studies |  | ASP | CPR | PRO | 10 | PRP | 34 | N | D |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1994-06-28 | 1994-06-01 |  | 1996-03-01 | 1996-03-01 | 240000 | 80000 | 320000 | 320000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation activities are complete, including many proposals and six sector phaseout strategies. 26 foam projects, to be implemented by UNDP and the Bank, were prepared following first two workshops. |  |  |  | Non-INV | 0
FIN | IBRD | Halon 1211 production closure at Tongxiang Chemical Fertilizer Factory | Individual | ASP | CPR | PRO | 13 | INV | 76 | N | I | HAL | 0 | 0 | 1200 | 1200 | 1994-07-01 | 1996-08-01 | 1995-01-01 |  | 1994-12-01 | 1996-08-01 | 838000 | -730880 | 107120 | 107120 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed; PCR submitted to ExCom. |  |  | 1994-12-01 | INV | 0
FIN | IBRD | Preparation of investment projects in the production sector for 1998 submission |  | ASP | CPR | PRO | 22 | PRP | 205 | A | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-09-30 | 1998-12-01 |  | 1999-06-01 | 1999-06-01 | 350000 | 0 | 350000 | 350000 | 100% | 0 | 0 |  | 45500 | 0 | 45500 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | IBRD | Sector plan for CFC production phaseout: 1999 annual programme | Multiyear | ASP | CPR | PRO | 27 | INV | 356 | N | I | CFC | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-09-30 | 1999-12-01 |  | 1999-12-01 | 2013-06-01 | 10000000 | 10000000 | 20000000 | 20000000 | 100% | 0 | 0 |  | 900000 | 900000 | 1800000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for CFC production phaseout: 2000 annual programme | Multiyear | ASP | CPR | PRO | 30 | INV | 347 | N | I | CFC | 0 | 0 | 4931 | 4931 | 2000-03-01 | 2000-08-07 | 2000-12-01 |  | 2000-12-01 | 2013-06-01 | 13000000 | 0 | 13000000 | 13000000 | 100% | 0 | 0 |  | 1170000 | 0 | 1170000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for CFC production phaseout: 2001 annual programme | Multiyear | ASP | CPR | PRO | 33 | INV | 370 | N | I | CFC | 0 | 0 | 4320 | 4320 | 2001-03-01 | 2001-07-19 | 2001-12-01 |  | 2001-12-31 | 2013-06-01 | 6500000 | 6500000 | 13000000 | 13000000 | 100% | 0 | 0 |  | 585000 | 585000 | 1170000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for CFC production phase-out: 2002 annual programme | Multiyear | ASP | CPR | PRO | 36 | INV | 391 | N | I | CFC | 0 | 0 | 3568 | 3568 | 2002-03-01 | 2002-12-01 | 2002-12-01 |  | 2002-12-01 | 2013-06-01 | 13000000 | 0 | 13000000 | 13000000 | 100% | 0 | 0 |  | 910000 | 0 | 910000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Project preparation funds for CTC and TCA production closure plan |  | ASP | CPR | PRO | 38 | PRP | 399 | A | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-12-01 | 2003-12-01 |  | 2003-12-01 | 2003-12-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 |  | 19500 | 0 | 19500 | 0 | 0 | TCA Sector Plan will be submitted to the 43rd ExCom. CTC sector plan will be submitted for information purpose to the 42nd ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | CFC production sector: 2003 annual programme | Multiyear | ASP | CPR | PRO | 39 | INV | 401 | N | I | CFC | 0 | 0 | 2900 | 2900 | 2003-04-01 | 2003-11-01 | 2003-12-01 |  | 2003-12-01 | 2013-06-01 | 13000000 | 0 | 13000000 | 13000000 | 100% | 0 | 0 |  | 975000 | 0 | 975000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for CFC production phase-out: 2004 annual programme | Multiyear | ASP | CPR | PRO | 42 | INV | 411 | N | I | CFC | 0 | 0 | 4700 | 4700 | 2004-04-01 | 2005-11-01 | 2004-12-01 |  | 2005-04-01 | 2013-06-01 | 13000000 | 0 | 13000000 | 13000000 | 100% | 0 | 0 |  | 975000 | 0 | 975000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Strategy for gradual phase-out of 1,1,1-trichlorethane (TCA) production (first stage programme) | Multiyear | ASP | CPR | PRO | 43 | INV | 417 | N | I | TCA | 0 | 0 | 33.8 | 33.8 | 2004-07-01 | 2005-12-01 | 2008-07-01 |  | 2008-07-01 | 2010-11-01 | 1400000 | 0 | 1400000 | 1400000 | 100% | 0 | 0 |  | 105000 | 0 | 105000 | 0 | 0 | Fully completed. |  |  |  | INV | 0
COM | USA | CFCs, CTC and halon accelerated phase-out plan (first tranche) | Multi-Year | ASP | CPR | PRO | 44 | INV | 425 | A | I |  | 0 |  | 0 |  | 2004-12-01 | 2006-10-01 | 2005-12-01 |  | 2006-10-01 |  | 5000000 | 0 | 5000000 | 5000000 | 100% | 0 | 0 | 0 | 375000 | 0 | 375000 | 0 | 0 | Completed. Funds disbursed in Oct. 2006.
FIN | IBRD | Sector plan for CFC production phase-out: 2005 annual programme | Multiyear | ASP | CPR | PRO | 45 | INV | 428 | N | I | CFC | 0 | 0 | 6550 | 6550 | 2005-04-01 | 2005-12-01 | 2005-12-01 |  | 2006-04-01 | 2013-06-01 | 13000000 | 0 | 13000000 | 13000000 | 100% | 0 | 0 |  | 975000 | 0 | 975000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
COM | UNIDO | Sector plan for methyl bromide production sector (first tranche) | Multi-Year | ASP | CPR | PRO | 47 | INV | 436 | A | I | MBR | 0 | 0 | 231 | 231 | 2005-11-01 | 2006-06-01 | 2008-12-01 |  | 2015-12-01 |  | 3000000 | 0 | 3000000 | 2994397.03 | 99.81% | 5602.97 | 1659.08 | 1 | 225000 | 0 | 224580 | 420 | 124 | The project was operationally completed. |  |  |  | INV
COM | USA | CFCs, CTC and halon accelerated phase-out-plan (second tranche) | Multi-Year | ASP | CPR | PRO | 47 | INV | 439 | A | I |  | 0 |  | 0 |  | 2005-11-01 |  | 2007-12-01 |  | 2009-01-01 |  | 5000000 | 0 | 5000000 | 5000000 | 100% | 0 |  |  | 375000 | 0 | 375000 | 0 |  | Ongoing.
FIN | IBRD | Sector plan for CFC production phase-out: 2006 annual programme | Multiyear | ASP | CPR | PRO | 48 | INV | 443 | N | I | CFC | 0 | 0 | 5250 | 5250 | 2006-04-01 | 2006-10-01 | 2007-04-01 |  | 2007-04-01 | 2013-06-01 | 13000000 | 0 | 13000000 | 13000000 | 100% | 0 | 0 |  | 975000 | 0 | 975000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for CFC production phase-out: 2007 annual programme | Multiyear | ASP | CPR | PRO | 51 | INV | 449 | N | I | CFC | 0 | 0 | 6100 | 6100 | 2007-03-01 | 2007-09-01 | 2008-03-01 |  | 2008-03-01 | 2013-06-01 | 24000000 | 0 | 24000000 | 24000000 | 100% | 0 | 0 |  | 1800000 | 0 | 1800000 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for CFC production phase-out: 2008 annual programme | Multiyear | ASP | CPR | PRO | 54 | INV | 459 | N | I | CFC | 0 | 0 | 6850 | 6850 | 2008-04-01 | 2008-12-01 | 2009-03-31 |  | 2009-03-01 | 2013-06-01 | 7500000 | 0 | 7500000 | 7500000 | 100% | 0 | 0 |  | 562500 | 0 | 562500 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | UNIDO | Sector plan for methyl bromide production sector (second tranche) | Multi-Year | ASP | CPR | PRO | 56 | INV | 475 | A | I |  | 0 | 0 | 214 | 214 | 2008-11-01 | 2009-02-01 | 2011-11-30 |  | 2013-03-01 | 2015-03-01 | 3000000 | -2602 | 2997398 | 2997397.82 | 100% | 0.18 | 0 |  | 225000 | -195 | 224805 | 0 | 0 | FIN |  |  |  | INV
FIN | IBRD | Strategy for gradual phase-out of 1,1,1-trichloroethane (TCA) production (second stage programme) | Multiyear | ASP | CPR | PRO | 56 | INV | 480 | N | I | TCA | 0 | 0 | 79.2 | 79.2 | 2008-11-01 | 2010-11-01 | 2010-11-30 |  | 2010-11-01 | 2010-11-01 | 700000 | 0 | 700000 | 700000 | 100% | 0 | 0 |  | 52500 | 0 | 52500 | 0 | 0 | Fully completed. |  |  |  | INV | 0
FIN | IBRD | Sector plan for CFC production phase-out: 2009 annual programme | Multiyear | ASP | CPR | PRO | 57 | INV | 487 | N | I | CFC | 0 | 0 | 550 | 550 | 2009-04-01 | 2009-12-01 | 2010-03-31 |  | 2010-03-01 | 2013-06-01 | 7500000 | 0 | 7500000 | 7500000 | 100% | 0 | 0 |  | 562500 | 0 | 562500 | 0 | 0 | Sector plan completed. |  |  |  | INV | 0
FIN | UNIDO | Sector plan for methyl bromide production sector (third tranche) | Multi-Year | ASP | CPR | PRO | 64 | INV | 510 | A | I | MBR | 0 | 0 | 126 | 126 | 2011-07-01 | 2013-04-01 | 2014-07-31 |  | 2014-12-01 | 2016-03-01 | 2000000 | 0 | 2000000 | 2000000 | 100% | 0 | 0 |  | 150000 | 0 | 150000 | 0 | 0 | The project was financially completed and the balance was returned at the 76th ExCom. |  |  |  | INV
COM | IBRD | HCFC production phase-out management plan (stage I, first tranche) | Multiyear | ASP | CPR | PRO | 69 | INV | 530 | N | X |  | 0 | 0 | 1058 | 1058 | 2013-04-01 | 2014-12-01 | 2014-04-30 |  | 2015-12-01 |  | 24000000 | 0 | 24000000 | 24000000 | 100% | 0 | 0 | 0 | 0 | 1344000 | 1344000 | 0 | 0 | Tranche fully disbursed. |  |  |  | INV | 24000000
FIN | IBRD | Verification of production of CFCs for essential use |  | ASP | CPR | PRO | 69 | TAS | 531 | A | I |  | 0 | 0 | 0 | 0 | 2013-04-01 | 2013-08-01 | 2013-08-31 |  | 2013-08-01 | 2013-08-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 2800 | 0 | 2800 | 0 | 0 | Verification report submitted to the 71st ExCom Meeting as planned and was considered by the Subgroup on the Production Sector. |  |  |  | Non-INV | 0
ONG | IBRD | HCFC production phase-out management plan (stage I, second tranche) | Multiyear | ASP | CPR | PRO | 72 | INV | 540 | N | X |  | 0 | 0 | 0 | 0 | 2014-05-01 | 2014-09-01 | 2015-05-31 | 2017-06-01 |  |  | 23000000 | 0 | 23000000 | 23000000 | 100% | 0 | 0 | 0 | 1288000 | 0 | 1288000 | 0 | 0 | Tranche from WB to China fully disbursed. 2015 production data verified and accepted by the 77th ExCom. Production quotas issued for 2016 and for 2017 are for 23,930 ODP MT each. Due to closure contracts, China surpassed its 2015 performance target for HCFC production of 26,210 ODP MT by 8.7%. All environment mgmt. plans (EMPs) for dismantling closure production lines prepared by enterprises, and reviewed and approved by WB. All 5 production lines dismantled. FECO approved bids from four producers in 2016 to close idle production capacity. TA activities conducted in 2016 include training workshops of HCFC producers and dealers (170 persons total); verification of 2015 HCFC production and investigation of feedstock applications of HCFCs in 2015. 40 manufacturers were visited through this TA, and a 2016 financial audit conducted. | Tranche from WB to China fully disbursed. Four idle capacity closure contracts were signed in Jan 17 with the contract amount of US$2,670,969. A contract for the TA activity "HCFC Phase-out Stage II in China HCFC Production Sector and PU Foam Sector Environmental and Social Safeguard Framework" was signed in Mar 17 for an amount of US$20,000. |  |  | INV | 22194188 | To request the submission of additional status report to the 79th meeting to monitor ongoing project with 100 per cent of fund disbursement.
ONG | UNIDO | Sector plan for methyl bromide production sector (fourth tranche) | Multi-Year | ASP | CPR | PRO | 73 | INV | 552 | A | I |  | 0 | 0 |  |  | 2014-11-01 | 2015-07-01 | 2018-12-31 | 2018-12-01 |  |  | 1790000 | 0 | 1790000 | 1413835.69 | 78.99% | 376164.31 | 277200 | 40000 | 134000 | 0 | 105840 | 28160 | 20751 | - Implementation of (a) Technical Assistance component, in conjunction with MB phase-out plan, and (b) formulation of Policies and Regulation framework for QPS uses of MB. - Monitoring of MB production and consumption and data collection ongoing. - No delay - No recurring problem - No impact on project completion date - No action required by Executive Committee | - Implementation of (a) Technical Assistance component, in conjunction with MB phase-out plan, and (b) formulation of Policies and Regulation framework for QPS uses of MB. - Monitoring of MB production and consumption and data collection ongoing. - No delay - No recurring problem - No impact on project completion date - No action required by Executive Committee |  |  | INV
ONG | IBRD | HCFC production phase-out management plan (stage I, third tranche) | Multiyear | ASP | CPR | PRO | 74 | INV | 561 | N | X |  | 0 | 0 | 2912 | 2912 | 2015-05-01 | 2015-09-01 | 2016-05-31 | 2017-12-01 |  |  | 24000000 | 0 | 24000000 | 24000000 | 100% | 0 | 0 | 0 | 1344000 | 0 | 1344000 | 0 | 0 | 2015 production data verified and accepted by the 77th ExCom. Production quotas issued for 2016 and for 2017 are for 23,930 ODP MT each. Due to closure contracts, China surpassed its 2015 performance target for HCFC production of 26,210 ODP MT by 8.7%. All environment mgmt. plans (EMPs) for dismantling closure production lines prepared by enterprises, and reviewed and approved by WB. All 5 production lines dismantled. FECO approved bids from four producers in 2016 to close idle production capacity. TA activities conducted in 2016 include training workshops of HCFC producers and dealers (170 persons total); verification of 2015 HCFC production and investigation of feedstock applications of HCFCs in 2015. 40 manufacturers were visited through this TA, and a 2016 financial audit conducted. | Four idle capacity closure contracts were signed in Jan 17 with the contract amount of US$2,670,969. A contract for the TA activity "HCFC Phase-out Stage II in China HCFC Production Sector and PU Foam Sector Environmental and Social Safeguard Framework" was signed in Mar 17 for an amount of US$20,000. |  |  | INV | 22377792
ONG | IBRD | HCFC production phase-out management plan (stage I, fourth tranche) | Multiyear | ASP | CPR | PRO | 75 | INV | 568 | N | X |  | 0 | 0 | 0 | 0 | 2015-11-01 | 2016-04-01 | 2017-04-30 | 2017-12-01 |  |  | 24000000 | 0 | 24000000 | 7200000 | 30% | 16800000 | 16800000 | 16800000 | 1344000 | 0 | 403200 | 940800 | 940800 | 2015 production data verified and accepted by the 77th ExCom. Production quotas issued for 2016 and for 2017 are for 23,930 ODP MT each. Due to closure contracts, China surpassed its 2015 performance target for HCFC production of 26,210 ODP MT by 8.7%. All environment mgmt. plans (EMPs) for dismantling closure production lines prepared by enterprises, and reviewed and approved by WB. All 5 production lines dismantled. FECO approved bids from four producers in 2016 to close idle production capacity. TA activities conducted in 2016 include training workshops of HCFC producers and dealers (170 persons total); verification of 2015 HCFC production and investigation of feedstock applications of HCFCs in 2015. 40 manufacturers were visited through this TA, and a 2016 financial audit conducted. | Four idle capacity closure contracts were signed in Jan 17 with the contract amount of US$2,670,969. A contract for the TA activity "HCFC Phase-out Stage II in China HCFC Production Sector and PU Foam Sector Environmental and Social Safeguard Framework" was signed in Mar 17 for an amount of US$20,000. |  |  | INV | 6921889
ONG | IBRD | Preparation of a HCFC production phase-out management plan (stage II) |  | ASP | CPR | PRO | 75 | PRP | 570 | N | I |  | 0 | 0 | 0 | 0 | 2015-11-01 | 2016-12-01 | 2016-12-31 | 2017-06-01 |  |  | 254650 | 0 | 254650 | 77887 | 30.59% | 176763 | 176763 | 160000 | 17825 | 0 | 5451.93 | 12373.07 | 12373.07 | TOR prepared and contract for Stage II HCFC production sector data compilation and strategy issued with Peking University by Jul 16. Preparation initiated by mid-2016 and first draft report completed in Oct 16. | Revised draft of the Stage II HCFC production sector strategy prepared by the consultant and submitted to FECO and the Bank in Jan 17. Preparation (analyses and cost calculations) continued through Feb 17 and document finalized and submitted to the ExCom by end Mar 17. Preparation of new Grant Agreement between China and the WB to start with expected completion by Fall 2017. |  |  | Non-INV | 0
FIN | UNDP | Feasibility study on the application of HFC-134a technology in MACs and CFC recycling | RMP-Component | ASP | CPR | REF | 06 | TAS | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-11-01 | 1993-09-01 |  | 1993-12-01 | 1997-12-01 | 40000 | -15164 | 24836 | 24836 | 100% | 0 | 0 | 0 | 5200 | -1971.32 | 3228.68 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Establishment of a quality control testing plant for using CFC-12 substitute technology in refrigeration and rigid foams | Individual | ASP | CPR | REF | 06 | TAS | 06 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1996-12-01 | 1993-12-01 |  | 1998-06-01 | 1998-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Completed in 1998. Financially completed in 1998. |  | 1992 |  | Non-Investment
FIN | UNDP | Establishment of a training programme for centrifugal chillers and domestic refrigeration service managers and technicians | RMP-Component | ASP | CPR | REF | 06 | TRA | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-01-01 | 1993-09-01 |  | 1993-09-01 | 1997-12-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | IBRD | Pre-investment activities for Nanjing compressor and four refrigeration projects |  | ASP | CPR | REF | 08 | PRP | 24 | N | D | CFC | 0 | 0 | 0 | 0 | 1992-10-01 | 1993-09-30 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation activities are complete. In addition, a sector-wide phaseout strategy for the commercial refrigeration and air-conditioning sector was prepared (12,500 tons of CFCs). |  |  |  | Non-INV | 0
FIN | UNIDO | Elimination of ODS used in the production of compressors for household refrigerators at Jiaxipera Compressor Co. Ltd. | Individual | ASP | CPR | REF | 09 | PRP | 28 | A | I |  | 0 | 0 |  |  | 1993-03-01 | 1994-06-01 | 1996-03-01 |  | 1994-12-01 | 1998-08-01 | 36000 | 4294 | 40294 | 40294 | 100% | 0 | 0 |  | 4680 | 558 | 5238 | 0 | 0 | FIN
FIN | UNDP | Import and promotion of applications for CFC substitute chemicals in the refrigeration sector in Southern China | RMP-Component | ASP | CPR | REF | 09 | TAS | 27 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1995-12-01 | 1994-06-01 |  | 1995-12-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1993 |  | Non-Investment
FIN | USA | Staged project to produce CFC-free refrigerators in China (stage 1a: model prototype development and testing) |  | ASP | CPR | REF | 10 | TAS | 33 | A | I |  | 0 |  | 0 |  | 1993-06-01 |  | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 396110 | 0 | 396110 | 396110 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1993
FIN | UNDP | Revision of design standards for cold storage | RMP-Component | ASP | CPR | REF | 10 | TAS | 39 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1996-01-01 | 1994-09-01 |  | 1999-03-01 | 2000-12-01 | 200000 | -18764.2 | 181235.8 | 181236 | 100% | -0.2 | 0 | 0 | 26000 | -2439.35 | 23560.68 | -0.03 | 0 | Completed in 1999. Financially completed in 2000. |  | 1993 | 1999-03-01 | Non-Investment
FIN | UNDP | Survey on policy and planning measures to promote recycling of CFC | RMP-Component | ASP | CPR | REF | 11 | TAS | 55 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1996-05-01 | 1994-11-01 |  | 1997-12-01 | 2000-12-01 | 100000 | -19358 | 80642 | 80642 | 100% | 0 | 0 | 0 | 13000 | -2516.54 | 10483.46 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1993 |  | Investment
FIN | IBRD | Engineering assistance for conversion of refrigerator manufacture to use HFC-134a refrigerant with Tecumseh designed compressors at Hua Yi Electrical Appliances General Co. | Individual | ASP | CPR | REF | 13 | INV | 68 | N | I | CFC | 60 | 60 | 0 | 0 | 1994-07-01 | 1996-07-01 | 1996-07-01 |  | 1997-12-01 | 1998-09-01 | 1368000 | 0 | 1368000 | 1368000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project complete; PCR submitted to 29th ExCom. |  |  | 1997-12-01 | INV | 0
FIN | IBRD | Engineering assistance for conversion of refrigerator manufacture to use HFC-152a refrigerant in conventional compressors at Wanbao Electrical Appliances Industrial Corporation | Individual | ASP | CPR | REF | 13 | INV | 69 | N | I | CFC | 80 | 80 | 0 | 0 | 1994-07-01 | 1996-12-01 | 1996-07-01 |  | 1999-07-01 | 2002-09-01 | 1360000 | 0 | 1360000 | 1360000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted to ExCom. |  |  | 1999-06-01 | INV | 0
CLO | IBRD | Engineering assistance for conversion of refrigerator manufacture to a ternary blend refrigerant (MP-39) in conventional compressors at Shanghai Shuanglu Electrical Appliances Co. Ltd. | Individual | ASP | CPR | REF | 13 | INV | 70 | N | I | CFC | 70 | 64.3 | 0 | 0 | 1994-07-01 | 1996-05-01 | 1996-07-01 |  |  | 1998-09-01 | 1010000 | -82008 | 927992 | 927992 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project cancelled due to financial difficulties. Undisbursed balance of $82,007.65 has been returned to MLF at the 30th ExCom Meeting. Four charging machines are proposed to be transferred to the new Shanghai Shangling project. PCR submitted. |  |  |  | INV | 0
FIN | IBRD | Engineering assistance for conversion of refrigerator manufacture to HFC-152a/HCFC-22 blended refrigerant in conventional compressors at Chang Ling Co. Ltd. | Individual | ASP | CPR | REF | 13 | INV | 71 | N | I | CFC | 70 | 70 | 0 | 0 | 1994-07-01 | 1996-03-01 | 1996-07-01 |  | 1997-09-01 | 1997-03-01 | 853000 | -10 | 852990 | 852990 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project complete; PCR submitted to 26th ExCom. |  |  | 1997-09-01 | INV | 0
FIN | IBRD | Application development for conversion of compressor manufacturing to HFC-134a rotary compressor designs at Shanghai Refrigerator Compressor Co. Ltd. | Individual | ASP | CPR | REF | 13 | INV | 77 | N | I | CFC | 0 | 0 | 0 | 0 | 1994-07-01 | 1996-07-01 | 1996-07-01 |  | 1997-05-01 | 1997-06-01 | 1280000 | 0 | 1280000 | 1280000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed; PCR submitted to ExCOM. |  |  | 1998-06-01 | INV | 0
FIN | IBRD | Engineering assistance for conversion of refrigerator manufacture to HFC-134a with rotary compressor at Shanghai Shangling General Refrigerator Factory | Individual | ASP | CPR | REF | 13 | INV | 78 | N | I | CFC | 108 | 108 | 0 | 0 | 1994-07-01 | 1996-12-01 | 1996-07-01 |  | 2000-06-01 | 2002-09-01 | 1327000 | 0 | 1327000 | 1327000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1999-06-01 | INV | 0
CLO | Canada | Feasibility study to establish a refrigerant conservation programme in Sichuan Province | Individual | ASP | CPR | REF | 14 | TAS | 81 | A | I |  | 0 |  | 0 |  | 1994-09-01 |  | 1995-09-01 |  |  | 1997-06-01 | 58400 | -58400 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1994 | 2000-01-01 | Non-Inv.
FIN | IBRD | Conversion of medium sized semi-hermetic CFC-12 air conditioning compressor production to HCFC-22 at Beijing Refrigerating Machinery Factory | Individual | ASP | CPR | REF | 15 | INV | 107 | N | I | CFC | 233 | 233 | 0 | 0 | 1994-12-01 | 1996-07-01 | 1997-12-01 |  | 2000-08-01 | 2002-04-01 | 3098000 | -1000 | 3097000 | 3097000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted. |  |  | 1999-12-01 | INV | 0
FIN | UNIDO | Conversion of domestic refrigerator and freezer factories to phase out CFC-12 and CFC-11 at Hangzhou Xiling Holdings Co. | Individual | ASP | CPR | REF | 15 | PRP | 105 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1996-04-01 | 1995-06-01 |  | 1996-12-01 | 1998-08-01 | 25000 | -8988 | 16012 | 16012 | 100% | 0 | 0 |  | 3250 | -1172 | 2078 | 0 | 0 | FIN
FIN | USA | MAC servicing demonstration |  | ASP | CPR | REF | 16 | DEM | 117 | A | I | CFC | 7 | 11.4 | 0 |  | 1995-03-01 | 1995-04-01 | 1995-03-01 |  | 1996-03-01 | 1996-03-01 | 172500 | -6667 | 165833 | 165833 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Final report submitted October 1999. |  | 1995
FIN | IBRD | Conversion of medium sized open-type CFC-12 refrigeration compressor production to HCFC-22 at Shanghai Refrigerating Machine Works (SRMW) | Individual | ASP | CPR | REF | 16 | INV | 110 | N | I | CFC | 162 | 162 | 0 | 0 | 1995-03-01 | 1996-07-01 | 1998-03-01 |  | 1998-09-01 | 1999-09-01 | 2710000 | 0 | 2710000 | 2710000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted to the ExCom March 2000. |  |  | 1999-06-01 | INV | 0
FIN | IBRD | Conversion of small open-type CFC-12 refrigeration compressor production to HCFC-22 at Anhui Provincial Refrigerating Machinery Factory (APRMF) | Individual | ASP | CPR | REF | 16 | INV | 111 | N | I | CFC | 171 | 171 | 0 | 0 | 1995-03-01 | 1996-07-01 | 1998-03-01 |  | 2002-07-01 | 2004-04-01 | 2224000 | 0 | 2224000 | 2224000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. |  |  | 2001-06-01 | INV | 0
FIN | IBRD | Conversion of small semi-hermetic CFC-12 refrigeration compressor production to HCFC-22 at Jiangsu Taizhou Commercial Machinery Factory (JTCMF) | Individual | ASP | CPR | REF | 16 | INV | 112 | N | I | CFC | 285 | 285 | 0 | 0 | 1995-03-01 | 1996-10-01 | 1998-03-01 |  | 1999-12-01 | 2002-09-01 | 2797500 | 0 | 2797500 | 2797500 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1999-06-01 | INV | 0
FIN | IBRD | Conversion of small semi-hermetic CFC-12 refrigeration compressor production to HCFC-22 at Nanjing Refrigerator General Works (NRGW) | Individual | ASP | CPR | REF | 16 | INV | 113 | N | I | CFC | 242 | 242 | 0 | 0 | 1995-03-01 | 1996-04-01 | 1998-03-01 |  | 1999-05-01 | 2002-04-01 | 2890000 | -27 | 2889973 | 2889973 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted. |  |  | 1998-06-01 | INV | 0
FIN | IBRD | Production of small ammonia refrigerating compressor at Yantai Refrigerating Machinery Works (YRMW) | Individual | ASP | CPR | REF | 16 | INV | 114 | N | I | CFC | 240 | 240 | 0 | 0 | 1995-03-01 | 1996-12-01 | 1998-03-01 |  | 1999-05-01 | 2000-06-01 | 2874000 | 0 | 2874000 | 2874000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed.PCR and certificates were submitted to 30th ExCom Meeting. |  |  | 1999-12-01 | INV | 0
FIN | Germany | Staged project to produce CFC-free refrigerators in China (stage 1b: field testing, stage 2: changeover of foam blowing agent to cyclopentane and refrigerant to isobutane in Haier Refrigerator Factory) | Individual | ASP | CPR | REF | 16 | INV | 115 | N | I | CFC | 174 | 174 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1996-03-01 | 1996-03-01 | 1336918 | 0 | 1336918 | 1336918 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completion report submitted Oct 99 |  |  | 2000-01-01
FIN | USA | Staged project to produce CFC-free refrigerators in China (stage 1b: field testing, stage 2: changeover of foam blowing agent to cyclopentane and refrigerant to isobutane in Haier Refrigerator Factory) |  | ASP | CPR | REF | 16 | INV | 116 | N | I | CFC | 29 |  | 0 |  | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 2000-05-01 | 2000-05-01 | 1643865 | 0 | 1643865 | 1643865 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Conversion of line to produce cyclopentane-152a/22 refrigerators completed, certified Aug96; CFCs eliminated. Final funding to follow verification of old equipment destruction, review of receipts, final safety certification, and initial production. |  | 1995 | 1999-12-01
FIN | USA | Refrigeration management demonstration project preparation |  | ASP | CPR | REF | 16 | PRP | 118 | A | I |  | 0 |  | 0 |  | 1995-03-01 | 1995-04-01 | 1996-03-01 |  | 1996-03-01 | 1996-03-01 | 39000 | 0 | 39000 | 39000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1995
FIN | UNDP | Demonstration project (refrigeration - large food stores) | RMP-Component | ASP | CPR | REF | 17 | DEM | 131 | A | I | CFC | 10 | 10 | 0 | 0 | 1995-07-01 | 1996-12-01 | 1996-07-01 |  | 1997-06-01 | 2002-05-01 | 76000 | 0 | 76000 | 76000 | 100% | 0 | 0 | 0 | 9880 | 0 | 9880 | 0 | 0 | Completed in 1997. Financially completed in 2002. |  | 1995 |  | Non-Investment
FIN | USA | Demonstration project (refrigeration - large food stores) |  | ASP | CPR | REF | 17 | DEM | 135 | A | I |  | 0 |  | 0 |  | 1995-07-01 | 1995-10-01 | 1996-01-01 |  | 1998-01-01 | 1998-12-01 | 132000 | 26400 | 158400 | 158400 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Final report submitted October 1999. |  | 1995 | 1997-06-01
FIN | UNIDO | Conversion of domestic refrigerator and freezer factories to phase out CFC-12 and CFC-11 by hydrocarbon isobutane and cyclopentane at Hangzhou Xiling Holdings Co. | Individual | ASP | CPR | REF | 17 | INV | 119 | A | I | CFC | 360 | 360 |  |  | 1995-07-01 | 1996-03-01 | 1997-07-01 |  | 2003-12-01 | 2004-12-01 | 2790320 | 0 | 2790320 | 2790320.21 | 100% | -0.21 | 0 |  | 362742 | -1 | 362741 | 0 | 0 | FIN |  |  | 1999-12-01
FIN | UNDP | Elimination of CFCs in the manufacture of domestic refrigerators at Guangdong Kelon Electrical Holding Company Ltd. | Individual | ASP | CPR | REF | 17 | INV | 123 | N | I | CFC | 767.2 | 767.2 | 0 | 0 | 1995-07-01 | 1997-04-01 | 1997-01-01 |  | 1999-06-01 | 2003-07-01 | 4483050 | -6913 | 4476137 | 4476137 | 100% | 0 | 0 | 0 | 582796.5 | -898.62 | 581897.88 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  | 1995 | 1999-06-01 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of domestic refrigerators at Changsha Zhongyi Group Corp. Ltd. | Individual | ASP | CPR | REF | 17 | INV | 124 | A | I | CFC | 360.2 | 360.2 | 0 | 0 | 1995-07-01 | 1997-05-01 | 1997-01-01 |  | 2000-09-01 | 2004-01-01 | 2961000 | -2311 | 2958689 | 2958689 | 100% | 0 | 0 | 0 | 384930 | -300.43 | 384629.57 | 0 | 0 | Completed in 2000. Financially completed in 2004. |  | 1995 | 1999-12-01 | Investment
FIN | IBRD | Conversion from CFC-12 to HFC-134a MAC compressor at Shanghai Ek Chor General Machinery Co. Ltd. | Individual | ASP | CPR | REF | 17 | INV | 129 | N | I | CFC | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-12-01 | 1996-07-01 |  | 1996-01-01 | 1998-06-01 | 961000 | 0 | 961000 | 961000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed; PCR submitted to the 30th ExCom. |  |  | 1998-06-01 | INV | 0
FIN | Denmark | Establishment of a CFC recycling centre at Zhejiang Donggyang Chemical Factory |  | ASP | CPR | REF | 17 | TAS | 130 | N | I |  | 20 |  |  |  | 1995-07-01 | 1996-10-01 | 1996-07-01 | 1998-12-01 | 1998-12-01 |  | 205000 | -43947 | 161053 | 161053.25 | 100% | -0.25 |  | 0 |  |  |  | 0 |  | Completed. Project Document signed in March 1996. Procurement comtract initialed in August 1996 but contract was not signed until 1997. Major delay caused by disagreement on contractual terms. Building modification work completed by enterprise in May 1998 and equipment delivered and installed in June 1998. A seminar for evaluation and dissemination of work experience was held 15-16 December 1998. All project activities were completed in December 1998. More than 50 tons of CFC has been recovered. A few tons of CFC had further been recycled at the reclaim station. |  |  | 1996-12-01
FIN | UNIDO | Workshop on domestic and commercial refrigerator compressor conversion | Individual | ASP | CPR | REF | 17 | TRA | 133 | A | I |  | 0 | 0 |  |  | 1995-07-01 | 1995-10-01 | 1996-01-01 |  | 1995-11-01 | 1998-08-01 | 40000 | 237 | 40237 | 40237 | 100% | 0 | 0 |  | 5200 | 31 | 5231 | 0 | 0 | FIN
FIN | UNIDO | Conversion of compressor production for domestic refrigerators from CFC-12 to hydrocarbon refrigerant at Jiaxipera compressor factory | Individual | ASP | CPR | REF | 18 | INV | 145 | A | I | CFC | 96 | 96 |  |  | 1995-11-01 | 1996-12-01 | 1997-11-01 |  | 1999-12-01 | 2002-09-01 | 1490000 | 0 | 1490000 | 1490000.07 | 100% | -0.07 | 0 |  | 193700 | 0 | 193700 | 0 | 0 | FIN |  |  | 1999-12-01
FIN | UNIDO | Phasing out ODS at Hangzhou Huari Refrigerator Co. | Individual | ASP | CPR | REF | 18 | INV | 147 | A | I | CFC | 338 | 338 |  |  | 1995-11-01 | 1996-12-01 | 1997-11-01 |  | 1999-12-01 | 2002-09-01 | 2827911 | -13884 | 2814027 | 2814027.14 | 100% | -0.14 | 0 |  | 367628 | -2384 | 365244 | 0 | 0 | FIN |  |  | 1999-12-01
FIN | IBRD | Conversion from CFC-12 to HFC-134a MAC system at Yueyang Hengli Air Conditioning Equipment Co. Ltd. | Individual | ASP | CPR | REF | 18 | INV | 148 | N | I | CFC | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-12-01 | 1997-11-01 |  | 1999-05-01 | 2000-02-01 | 1767961 | 0 | 1767961 | 1767961 | 100% | 0 | 0 |  | 229834.93 | 0 | 229834.93 | 0 | 0 | Project completed; PCR submitted to the 31th ExCom. |  |  | 1998-12-01 | INV | 0
FIN | IBRD | Conversion from CFC-12 to HFC-134a MAC compressor at Guangzhou Haohua Automobile Parts Co. Ltd. | Individual | ASP | CPR | REF | 18 | INV | 149 | N | I |  | 0.65 | 0.65 | 0 | 0 | 1995-11-01 | 1996-11-01 | 1997-05-01 |  | 2001-03-01 | 2001-07-08 | 2212039 | -202829 | 2009210 | 2009210.43 | 100% | -0.43 | -0.43 |  | 287565.07 | -25353.62 | 262211.45 | 0 | 0 | Project completed; Draft PCR is under review. |  |  | 1999-12-01 | INV | 0
FIN | IBRD | Conversion from CFC-12 to HFC-134a MAC system at Shanghai Automobile Air Conditioner Co. (SAAC) | Individual | ASP | CPR | REF | 18 | INV | 150 | N | I | CFC | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-08-01 | 1996-11-01 |  | 1996-12-01 | 1997-03-01 | 1642330 | -30 | 1642300 | 1642300 | 100% | 0 | 0 |  | 213502.9 | -3.9 | 213499.15 | -0.15 | -0.15 | Project completed; PCR submitted to the 30th ExCom. |  |  | 1997-04-01 | INV | 0
FIN | UNIDO | Formulation of investment projects in the refrigeration sector with particular attention to domestic refrigeration and compressor manufacturing | Individual | ASP | CPR | REF | 18 | PRP | 151 | A | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-04-01 | 1996-11-01 |  | 1998-10-01 | 2000-07-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 |  | 7150 | 0 | 7150 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | USA | Refrigeration mobile air conditioning (MAC) servicing |  | ASP | CPR | REF | 19 | DEM | 163 | A | I | CFC | 11.4 |  | 0 |  | 1996-05-01 | 1996-07-01 | 1999-05-01 |  | 1998-11-01 | 1998-12-01 | 385000 | 77600 | 462600 | 462600 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Final report will be submitted May 2000. |  | 1995 | 1997-12-01
FIN | UNIDO | Phasing out ODS at the X'ian Yuan Dong Compressor Co., Xi'an | Individual | ASP | CPR | REF | 19 | INV | 164 | A | I |  | 0 | 0 |  |  | 1996-05-01 | 1996-12-01 | 1998-05-01 |  | 1999-06-01 | 2000-12-01 | 1599000 | -5860 | 1593140 | 1593140 | 100% | 0 | 0 |  | 207870 | -1090 | 206780 | 0 | 0 | FIN |  |  | 1999-06-01
FIN | UNIDO | Phasing out ODS at the compressor factory of the Huangshi Dongbei Refrigeration Co. | Individual | ASP | CPR | REF | 19 | INV | 165 | A | I | CFC | 60 | 60 |  |  | 1996-05-01 | 1996-12-01 | 1998-05-01 |  | 1998-12-01 | 2002-05-01 | 899030 | 0 | 899030 | 899030.28 | 100% | -0.28 | 0 |  | 116874 | -33 | 116841 | 0 | 0 | FIN
FIN | UNDP | Elimination of CFCs 11 and 12 in the manufacture of domestic freezers at Guingdao Haier General Freezer Company | Individual | ASP | CPR | REF | 19 | INV | 167 | N | I | CFC | 278.8 | 278.8 | 0 | 0 | 1996-05-01 | 1997-06-01 | 1997-11-01 |  | 2000-04-01 | 2003-07-01 | 2548280 | -22910 | 2525370 | 2525370 | 100% | 0 | 0 | 0 | 331276.4 | -2978.3 | 328298.1 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1996 | 1998-05-01 | Investment
FIN | UNDP | Elimination of CFCs 11 and 12 in the manufacture of domestic freezers at Henan Freezer Factory | Individual | ASP | CPR | REF | 19 | INV | 168 | N | I | CFC | 167.7 | 167.7 | 0 | 0 | 1996-05-01 | 1997-06-01 | 1997-11-01 |  | 2001-06-01 | 2003-09-01 | 2550605 | -54725 | 2495880 | 2495880 | 100% | 0 | 0 | 0 | 331578.7 | -7114.25 | 324464.45 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1996 | 1999-12-01 | Investment
FIN | UNIDO | Phasing out ODS at the refrigerator plant of Aucma Electric Appliances Group Co. | Individual | ASP | CPR | REF | 20 | INV | 173 | A | I | CFC | 708 | 708 |  |  | 1996-10-01 | 1997-05-01 | 1998-10-01 |  | 1998-12-01 | 2002-07-01 | 2914904 | 0 | 2914904 | 2914904.08 | 100% | -0.08 | 0 |  | 378938 | -192 | 378746 | 0 | 0 | FIN
FIN | IBRD | Conversion of medium-sized semi-hermetic CFC-12 refrigerating compressor production to HCFC-22 production at Tianjin Tian Shan Refrigeration Equipment Co. | Individual | ASP | CPR | REF | 20 | INV | 175 | N | I | CFC | 275.5 | 275.5 | 0 | 0 | 1996-10-01 | 1997-11-01 | 2000-04-01 |  | 2003-05-01 | 2004-09-01 | 2256000 | 0 | 2256000 | 2256000 | 100% | 0 | 0 |  | 293280 | 0 | 293280 | 0 | 0 | Project financially completed. |  |  | 2000-12-01 | INV | 0
FIN | IBRD | Conversion of manufacturing facilities from CFC-11 foaming agent to cyclopentane and CFC-12 refrigerant to HFC-134a at Gansu Changfeng Baoan Industry Co. Ltd. | Individual | ASP | CPR | REF | 20 | INV | 176 | N | I | CFC | 65.2 | 65.2 | 0 | 0 | 1996-10-01 | 1997-06-01 | 1998-10-01 |  | 2002-04-01 | 2004-07-01 | 634150 | 260000 | 894150 | 894150 | 100% | 0 | 0 |  | 82439.5 | 33800 | 116239.5 | 0 | 0 | Project financially completed. |  |  | 2000-08-01 | INV | 0
FIN | IBRD | Conversion of small semi-hermetic CFC-12 refrigerating compressor production at Shanghai General Machinery (Group) Corp. (SGMC) | Individual | ASP | CPR | REF | 20 | INV | 180 | N | I | CFC | 209 | 209 | 0 | 0 | 1996-10-01 | 1997-11-01 | 2000-04-01 |  | 2002-12-01 | 2004-04-01 | 2039800 | 0 | 2039800 | 2039800 | 100% | 0 | 0 |  | 265174 | 0 | 265174 | 0 | 0 | Project financially completed. |  |  | 2000-12-01 | INV | 0
FIN | IBRD | Conversion of CFC-11 and CFC-12 centrifugal refrigerating compressor to HFC-134a centrifugal technology at Chongqing General Machinery Factory (CGMF) | Individual | ASP | CPR | REF | 20 | INV | 182 | N | I | CFC | 220 | 220 | 0 | 0 | 1996-10-01 | 1998-01-01 | 2000-04-01 |  | 2000-08-01 | 2002-03-01 | 2632000 | 0 | 2632000 | 2632000 | 100% | 0 | 0 |  | 342160 | 0 | 342160 | 0 | 0 | Project completed. PCR submitted to ExCom. |  |  | 2000-12-01 | INV | 0
FIN | IBRD | Conversion of CFC-12 small open-type and semi-hermetic refrigerating compressor to HCFC-22 refrigerating compressor at Zhenjiang Refrigerating Equipment Factory (ZREF) | Individual | ASP | CPR | REF | 20 | INV | 183 | N | I | CFC | 108.5 | 108.5 | 0 | 0 | 1996-10-01 | 1997-11-01 | 2000-04-01 |  | 2002-12-01 | 2004-04-01 | 1974000 | 0 | 1974000 | 1974000 | 100% | 0 | 0 |  | 256620 | 0 | 256620 | 0 | 0 | Project financially completed. |  |  | 2000-12-01 | INV | 0
FIN | UNIDO | Phasing out ODS at the Household Refrigerator Compressor Factory of the Guangzhou Wanbao Compressor Group | Individual | ASP | CPR | REF | 20 | INV | 185 | A | I | CFC | 3 | 3 |  |  | 1996-10-01 | 1997-04-01 | 1999-10-01 |  | 1999-10-01 | 2002-09-01 | 2250000 | 0 | 2250000 | 2250000.13 | 100% | -0.13 | 0 |  | 292500 | -35 | 292465 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the refrigeration plant of Hefei Meiling | Individual | ASP | CPR | REF | 22 | INV | 196 | A | I | CFC | 849 | 849 |  |  | 1997-05-01 | 1997-10-01 | 1999-06-01 |  | 1998-12-01 | 2002-09-01 | 3247877 | -44594 | 3203283 | 3203282.91 | 100% | 0.09 | 0 |  | 422224 | -6457 | 415767 | 0 | 0 | FIN
FIN | IBRD | Conversion of CFC-12 medium open-type refrigerating compressor to HCFC-22 compressor at Guangzhou Refrigerating Machinery Factory | Individual | ASP | CPR | REF | 22 | INV | 198 | N | I | CFC | 190 | 190 | 0 | 0 | 1997-05-01 | 1999-06-01 | 2000-06-01 |  | 2003-04-01 | 2004-09-01 | 1904769 | 0 | 1904769 | 1904769 | 100% | 0 | 0 |  | 247619.97 | 0 | 247619.97 | 0 | 0 | Project financially completed. |  |  | 2002-06-01 | INV | 0
FIN | IBRD | Conversion of CFC-12 small open-type refrigerating compressor to HCFC-22 refrigerating compressor at Subei Refrigeration Machinery Factory | Individual | ASP | CPR | REF | 22 | INV | 200 | N | I | CFC | 171 | 171 | 0 | 0 | 1997-05-01 | 1999-06-01 | 2000-06-01 |  | 2003-01-01 | 2004-04-01 | 1806908 | 0 | 1806908 | 1806908 | 100% | 0 | 0 |  | 234898.04 | 0 | 234898.04 | 0 | 0 | Project financially completed. |  |  | 2000-06-01 | INV | 0
FIN | UNIDO | Phasing out ODS at the Hualing refrigerator plant | Individual | ASP | CPR | REF | 22 | INV | 204 | A | I | CFC | 280 | 280 |  |  | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1997-12-01 | 2000-04-01 | 879788 | -207466 | 672322 | 672322 | 100% | 0 | 0 |  | 114372 | -27109 | 87263 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the refrigerator plant of Zerowatt Electric Appliances Group | Individual | ASP | CPR | REF | 22 | INV | 207 | A | I | CFC | 423 | 423 |  |  | 1997-05-01 | 1997-10-01 | 1999-06-01 |  | 1999-12-01 | 2002-09-01 | 2394178 | -10688 | 2383490 | 2383489.52 | 100% | 0.48 | 0 |  | 311243 | -1880 | 309362 | 1 | 0 | FIN
FIN | IBRD | Conversion of CFC-12 medium open type refrigerating compressor at Wuhan New World Refrigeration Industrial Co. Ltd. | Individual | ASP | CPR | REF | 22 | INV | 208 | N | I | CFC | 209 | 209 | 0 | 0 | 1997-05-01 | 1999-09-01 | 2000-06-01 |  | 2003-08-01 | 2004-12-01 | 1459871 | 0 | 1459871 | 1459871 | 100% | 0 | 0 |  | 189783.23 | 0 | 189783.23 | 0 | 0 | Project financially completed. |  |  | 2000-06-01 | INV | 0
FIN | IBRD | Conversion of CFC-12 small open-type and semi-hermetic refrigerating compressor to HCFC-22 refrigerating compressor at Zhenjiang Refrigerating Equipment Factory (ZREF) | Individual | ASP | CPR | REF | 22 | INV | 209 | N | I | CFC | 186 | 186 | 0 | 0 | 1997-05-01 | 2001-12-31 | 2000-11-01 |  | 2002-12-01 | 2004-04-01 | 1048286 | 0 | 1048286 | 1048286 | 100% | 0 | 0 |  | 136277.18 | 0 | 136277.18 | 0 | 0 | Project financially completed. |  |  |  | INV | 0
FIN | IBRD | Conversion of CFC-12 small and medium open type refrigerating compressor production at Zhejiang Chunhui Company (Group) (ZCC) | Individual | ASP | CPR | REF | 22 | INV | 210 | N | I | CFC | 361 | 361 | 0 | 0 | 1997-05-01 | 1999-06-01 | 2000-06-01 |  | 2003-02-01 | 2004-05-01 | 3200394 | 0 | 3200394 | 3200394 | 100% | 0 | 0 |  | 416051.22 | 0 | 416051.22 | 0 | 0 | Project is financially completed. |  |  | 2002-06-01 | INV | 0
FIN | UNIDO | Phasing out ODS at the Zel Tianjin Compressor Co., Ltd. | Individual | ASP | CPR | REF | 22 | INV | 211 | A | I | CFC | 30 | 30 |  |  | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1998-12-01 | 1999-07-01 | 962175 | 0 | 962175 | 962175 | 100% | 0 | 0 |  | 125083 | 0 | 125083 | 0 | 0 | FIN
FIN | IBRD | Conversion of CFC-12 medium open type refrigerating compressor at Chongqing Bingyang Refrigerating Machine Co. | Individual | ASP | CPR | REF | 22 | INV | 214 | N | I | CFC | 190 | 190 | 0 | 0 | 1997-05-01 | 1999-06-01 | 2000-06-01 |  | 2003-12-01 | 2004-05-01 | 1805370 | 0 | 1805370 | 1805370 | 100% | 0 | 0 |  | 234698.1 | 0 | 234698.1 | 0 | 0 | Project financially completed. |  |  | 2000-06-01 | INV | 0
FIN | IBRD | Conversion of CFC-12 small open type refrigerating compressor production at Ningbo Refrigerating Machinery Factory | Individual | ASP | CPR | REF | 22 | INV | 215 | N | I | CFC | 171 | 171 | 0 | 0 | 1997-05-01 | 1999-06-01 | 2000-06-01 |  | 2002-10-01 | 2004-04-01 | 1786949 | 0 | 1786949 | 1786949 | 100% | 0 | 0 |  | 232303.37 | 0 | 232303.37 | 0 | 0 | Project financially completed. |  |  | 2000-06-01 | INV | 0
FIN | IBRD | Hefei General Machinery Research Institute (HGMRI): four technical assistance projects to support conversion of commercial refrigeration compressors | Individual | ASP | CPR | REF | 23 | INV | 218 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 2000-06-01 | 2001-11-01 |  | 2002-11-01 | 2002-11-01 | 692400 | -39141 | 653259 | 653259 | 100% | 0 | 0 |  | 90012 | -4892.63 | 85119.37 | 0 | 0 | Project completed. Draft PCR underway. Savings to be returned to the MLF. |  |  |  | INV | 0
FIN | UNIDO | Phasing out ODS at the Yuhuan Compressor Factory in Kanmen Town in Yuhuan County, South East China | Individual | ASP | CPR | REF | 23 | INV | 219 | A | I | CFC | 116 | 116 |  |  | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 2000-12-01 | 2002-09-01 | 1465155 | -9186 | 1455969 | 1455969.4 | 100% | -0.4 | 0 |  | 190470 | -1494 | 188976 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the refrigerator plant of Zhejiang Rongsheng Electric Co. Ltd., Zhejiang, Deqing Country | Individual | ASP | CPR | REF | 23 | INV | 220 | A | I | CFC | 177.8 | 177.8 |  |  | 1997-11-01 | 1998-07-01 | 1999-12-01 |  | 2000-12-01 | 2002-09-01 | 1053910 | -67809 | 986101 | 986101.04 | 100% | -0.04 | 0 |  | 137008 | -9018 | 127990 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the Changshu Refrigerating Equipment Works (Baixue), Changsu | Individual | ASP | CPR | REF | 23 | INV | 221 | A | I | CFC | 425.7 | 425.7 |  |  | 1997-11-01 | 1998-06-01 | 1999-12-01 |  | 2000-12-01 | 2002-09-01 | 3548775 | -521956 | 3026819 | 3026819.15 | 100% | -0.15 | 0 |  | 461341 | -68478 | 392863 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the refrigerator plant of Bole Electric Appliances Group | Individual | ASP | CPR | REF | 23 | INV | 222 | A | I | CFC | 132 | 132 |  |  | 1997-11-01 | 1998-09-01 | 2007-04-01 |  | 2006-12-01 | 2007-12-01 | 1469029 | -1564 | 1467465 | 1467464.62 | 100% | 0.38 | 0 |  | 190974 | -4672 | 186302 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the freezer plant of Xing Xing Electric Appliances Industrial Co. | Individual | ASP | CPR | REF | 23 | INV | 223 | A | I | CFC | 348 | 348 |  |  | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-12-01 | 2002-04-01 | 3346941 | -334438 | 3012503 | 3012503.12 | 100% | -0.12 | 0 |  | 435102 | -44097 | 391005 | 0 | 0 | FIN
CLO | UNDP | Elimination of CFCs 11 and 12 in the manufacture of domestic freezers at Jilin Jinouer Electric Appliances Group Co. | Individual | ASP | CPR | REF | 23 | INV | 225 | N | I | CFC | 0 | 0 | 0 | 0 | 1997-11-01 | 1999-07-01 | 1999-12-01 |  |  | 2003-09-01 | 2548360 | -1223403 | 1324957 | 1324957 | 100% | 0 | 0 | 0 | 331286.8 | -159041.85 | 172244.95 | 0 | 0 | Canceled in 2002. Financially completed in 2003. |  | 1997 | 2000-12-01 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of domestic refrigerators at Wanbao Electrical Appliance Industries Co. | Individual | ASP | CPR | REF | 23 | INV | 226 | N | I | CFC | 574.2 | 574.2 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2003-12-01 | 2009-07-01 | 4566985 | 0 | 4566985 | 4566985 | 100% | 0 | 0 | 0 | 593708.1 | 0 | 593708.1 | 0 | 0 | Completed in 2003.Financially completed in 2009. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFCs 11 and 12 in the manufacture of domestic freezers at Honxiang Group, Laizhou Freezer Plant | Individual | ASP | CPR | REF | 23 | INV | 232 | N | I | CFC | 301.5 | 301.5 | 0 | 0 | 1997-11-01 | 1998-06-01 | 1999-12-01 |  | 2003-09-01 | 2005-03-01 | 1339203 | -6776 | 1332427 | 1332427 | 100% | 0 | 0 | 0 | 174096.4 | -881 | 173215.4 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 1997 |  | Investment
CLO | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic freezers at DeBao Refrigeration Equipment Co. Ltd. | Individual | ASP | CPR | REF | 23 | INV | 233 | N | I | CFC | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  |  | 2002-06-01 | 1208176 | -683628 | 524548 | 524548 | 100% | 0 | 0 | 0 | 157062.9 | -88871.64 | 68191.26 | 0 | 0 | Canceled in 2002. Financially completed in 2002. |  | 1997 |  | Investment
FIN | IBRD | Conversion of refrigerator manufacture to HFC-134a refrigerant and cyclopentane foam blowing agent at Henan Xinfei Electric Co. Ltd. | Individual | ASP | CPR | REF | 23 | INV | 234 | N | I | CFC | 375 | 375 | 0 | 0 | 1997-11-01 | 1999-08-01 | 1999-12-01 |  | 1998-12-01 | 2000-09-01 | 1556490 | 0 | 1556490 | 1556490 | 100% | 0 | 0 |  | 202344 | 0 | 202344 | 0 | 0 | Project was completed; PCR submitted to 30th ExCOM. |  |  |  | INV | 0
CLO | IBRD | Conversion of refrigerator manufacture to HFC-134a refrigerant and cyclopentane foam blowing agent at Shanghai Shangling Chang-An Refrigerator Co., Ltd (former Shanghai Yuandong Refrigerator Co. Ltd.) | Individual | ASP | CPR | REF | 23 | INV | 235 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 |  | 2000-11-01 |  |  | 2000-12-01 | 1237663 | -1237663 | 0 | 0 | #DIV/0! | 0 | 0 |  | 160896 | -158482.56 | 2413.44 | 0 | 0 | Project cancelled due to financial difficulties. |  |  |  | INV | 0
FIN | UNDP | Conversion to cylopentane and R-134a in the manufacture of domestic freezers at Wanbao Freezer Industrial Corporation | Individual | ASP | CPR | REF | 24 | INV | 242 | N | I | CFC | 138.2 | 138.2 | 0 | 0 | 1998-03-01 | 1999-08-01 | 2000-04-01 |  | 2001-08-01 | 2004-06-01 | 1402370 | -52248 | 1350122 | 1350122 | 100% | 0 | 0 | 0 | 182308.1 | -6792.3 | 175515.8 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 1998 |  | Investment
FIN | UNDP | Project preparation for 2 projects in the domestic refrigeration (hydrocarbon) subsector | Individual | ASP | CPR | REF | 24 | PRP | 239 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1999-12-01 | 2001-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Conversion to cyclopentane and isobutane in the manufacture of domestic refrigerators at Hangzhou Household Electrical Appliance Industrial Corporation (HHEAIC) | Individual | ASP | CPR | REF | 25 | INV | 249 | N | I | CFC | 247.8 | 247.8 | 0 | 0 | 1998-07-01 | 1999-12-01 | 2000-08-01 |  | 2004-11-01 | 2008-10-01 | 2238580 | -1062 | 2237518 | 2237518 | 100% | 0 | 0 | 0 | 291015.4 | -138.06 | 290877.3402 | -0.0002 | 0 | Completed in 2004. Financially completed in 2008. |  | 1998 | 2001-12-01 | Investment
CLO | IBRD | Conversion of refrigerator manufacture in Changhe Group to HFC-134a as refrigerant and cyclopentane as foam blowing agent | Individual | ASP | CPR | REF | 25 | INV | 251 | N | I |  | 0 | 0 | 0 | 0 | 1998-07-01 |  | 2001-08-01 |  |  | 2001-12-31 | 1267638 | -1267638 | 0 | 0 | #DIV/0! | 0 | 0 |  | 164792.94 | -162321.05 | 2471.89 | 1.4097e-11 | 0 | Project has been cancelled. |  |  |  | INV | 0
FIN | UNIDO | Phasing out ODS at the refrigerator plant of Hefei Hualing Electronic Co., Ltd. | Individual | ASP | CPR | REF | 25 | INV | 253 | A | I | CFC | 82.8 | 82.8 |  |  | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 2000-12-01 | 2002-09-01 | 785984 | -8264 | 777720 | 777719.64 | 100% | 0.36 | 0 |  | 102178 | -1235 | 100943 | 0 | 0 | FIN
FIN | IBRD | MAC ODS phaseout sector plan | One off phaseout | ASP | CPR | REF | 26 | INV | 255 | N | I | CFC | 40 | 40 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2001-12-01 |  | 2001-12-01 | 2003-04-01 | 7700000 | 0 | 7700000 | 7700000 | 100% | 0 | 0 |  | 820000 | 0 | 820000 | 0 | 0 | Project completed. Completion report submitted. |  |  |  | INV | 0
CLO | UNIDO | Conversion from CFC-12 to isobutane technologies and products at the compressor factory of the Hangli Refrigeration Ltd., in Hangzhou, China | Individual | ASP | CPR | REF | 26 | INV | 256 | A | I | CFC | 0 | 0 |  |  | 1998-11-01 | 1999-11-01 | 2001-12-01 |  |  | 2003-12-01 | 861000 | -180793 | 680207 | 680207 | 100% | 0 | 0 |  | 104710 | -20006 | 84704 | 0 | 0 | CLO
FIN | UNIDO | Replacement of CFC-11 with HCFC-141b foam blowing agent and CFC-12 with HFC-134a in the manufacture of domestic refrigerators/ freezers at the Beijing Freezing Equipment Factory. | Individual | ASP | CPR | REF | 26 | INV | 259 | A | I | CFC | 35.3 | 35.3 |  |  | 1998-11-01 | 1999-09-01 | 2000-12-01 |  | 2000-12-01 | 2002-09-01 | 280901 | -8254 | 272647 | 272647.45 | 100% | -0.45 | 0 |  | 36517 | -1129 | 35388 | 0 | 0 | FIN
FIN | Germany | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators and freezers at China Aerospace Industry Corp. Kunming Refrigerator Factory | Individual | ASP | CPR | REF | 27 | INV | 282 | A | I | CFC | 95.5 |  | 0 |  | 1999-03-01 | 1999-07-01 | 2001-04-01 |  | 2004-12-01 | 2006-10-01 | 1451137 | 0 | 1451137 | 1451137 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. PCR has been submitted.
FIN | IBRD | Replacement of CFC-12 refrigerant with HCFC-22 in the manufacture of small open type compressors at Wuhan Commercial Machinery Factory | Individual | ASP | CPR | REF | 28 | INV | 298 | N | I | CFC | 104.2 | 104.2 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2002-08-01 |  | 2004-09-01 | 2004-09-01 | 1457583 | 0 | 1457583 | 1457583 | 100% | 0 | 0 |  | 170334.13 | 0 | 170334.13 | 0 | 0 | Project financially completed. |  |  |  | INV | 0
FIN | IBRD | Replacement of CFC-12 refrigerant with HCFC-22 in the manufacture of small and medium sized open type compressors at Zhejiang Commercial Machinery Factory | Individual | ASP | CPR | REF | 28 | INV | 300 | N | I | CFC | 251.7 | 251.7 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2002-08-01 |  | 2004-09-01 | 2004-09-01 | 1710295 | 0 | 1710295 | 1710295 | 100% | 0 | 0 |  | 198132.45 | 0 | 198132.45 | 0 | 0 | Project financially completed. |  |  |  | INV | 0
FIN | Japan | Phasing out ODS in the production of compressors at Changshu Refrigerating Equipment Works | Individual | ASP | CPR | REF | 28 | INV | 302 | A | I | CFC | 75 | 75 | 0 |  | 1999-07-01 | 2001-11-01 | 2002-12-01 |  | 2004-10-01 | 2005-12-01 | 2250000 | -3142 | 2246858 | 2246858 | 100% | 0 | 0 | 0 | 257500 | -9474 | 248026 | 0 | 0 | The project was successfully completed in October 2004. |  | 1999
FIN | IBRD | Replacement of CFC-12 refrigerant with HCFC-22 in the manufacture of semi-hermetic compressors at Yueyang Hengli Air-Cool Equipment Co. Ltd. | Individual | ASP | CPR | REF | 28 | INV | 303 | N | I | CFC | 220.2 | 220.2 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2002-08-01 |  | 2004-09-01 | 2004-09-01 | 1951757 | -291.22 | 1951465.78 | 1951465.78 | 100% | 0 | 0 |  | 224693.27 | -33.53 | 224659.74 | 0 | 0 | Financially completed. |  |  |  | INV | 0
FIN | UNIDO | Replacement of CFC-11 and CFC-12 with cyclopentane and isobutane in the production of refrigerators at Moganshan Electric Appliances Co. | Individual | ASP | CPR | REF | 29 | INV | 308 | A | I | CFC | 667.6 | 667.6 |  |  | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2002-12-01 | 2003-12-01 | 2769118 | -754390 | 2014728 | 2014727.99 | 100% | 0.01 | 0 |  | 314603 | -83334 | 231269 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-11 and CFC-12 with cyclopentane and isobutane in the production of refrigerators at Zhejian Electrical Equipment Co. | Individual | ASP | CPR | REF | 29 | INV | 336 | A | I | CFC | 199 | 199 |  |  | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2004-12-01 | 2006-09-01 | 2189782 | -42893 | 2146889 | 2146888.98 | 100% | 0.02 | 0 |  | 250876 | -4718 | 246158 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the domestic refrigeration (hydrocarbons) sector | Individual | ASP | CPR | REF | 30 | PRP | 339 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-07-01 | 2001-04-01 |  | 2002-06-01 | 2003-05-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the refrigeration compressor subsector | Individual | ASP | CPR | REF | 30 | PRP | 340 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-05-01 | 2001-04-01 |  | 2002-08-01 | 2003-05-01 | 50000 | -786 | 49214 | 49214.19 | 100% | -0.19 | 0 |  | 6500 | -112 | 6388 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the transportation refrigeration sector (foam component) | Individual | ASP | CPR | REF | 30 | PRP | 341 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-07-01 | 2001-04-01 |  | 2002-06-01 | 2003-05-01 | 40000 | 0 | 40000 | 39999.55 | 100% | 0.45 | 0 |  | 5200 | -1 | 5199 | 0 | 0 | FIN
FIN | UNDP | Preparation of a project in the domestic refrigeration subsector (hydrocarbons) | Individual | ASP | CPR | REF | 30 | PRP | 344 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-06-01 | 2001-04-01 |  | 2001-04-01 | 2003-01-01 | 35000 | -7211.96 | 27788.04 | 27788 | 100% | 0.04 | 0 | 0 | 4550 | -937.59 | 3612.4079 | 0.002148 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | IBRD | Project preparation in the commercial refrigeration sub-sector |  | ASP | CPR | REF | 30 | PRP | 351 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2001-12-01 |  | 2001-12-01 | 2001-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation in the domestic refrigeration subsector |  | ASP | CPR | REF | 30 | PRP | 352 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNIDO | Replacement of CFC-11 and CFC-12 with cyclopentane and HFC-134a in the production of refrigerators at Banshen Electric Appliances Co. | Individual | ASP | CPR | REF | 31 | INV | 357 | A | I | CFC | 563 | 563 |  |  | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2003-06-01 | 2005-04-01 | 2988840 | -196425 | 2792415 | 2792415.49 | 100% | -0.49 | 0 |  | 338772 | -22093 | 316679 | 0 | 0 | FIN
FIN | UNIDO | Preparation of 2 investment projects in the domestic (hydrocarbons) refrigeration sub-sector | Individual | ASP | CPR | REF | 31 | PRP | 360 | A | I |  | 0 | 0 |  |  | 2000-07-01 | 2001-03-01 | 2001-07-01 |  | 2001-08-01 | 2002-11-01 | 40000 | -17965 | 22035 | 22035 | 100% | 0 | 0 |  | 5200 | -2340 | 2860 | 0 | 0 | FIN
FIN | Japan | Develop a strategy for the refrigeration servicing sector | Individual | ASP | CPR | REF | 31 | TAS | 359 | A | I |  | 0 |  | 0 |  | 2000-07-01 | 2001-07-01 | 2001-12-01 |  | 2003-12-01 | 2005-06-01 | 350000 | -1376 | 348624 | 348624 | 100% | 0 | 0 | 0 | 45500 | -179 | 45321 | 0 | 0 | Completed the data survey for the four sub-sectors and developed the first draft strategy. The national workshop was organized in July 2002 to review the draft. The second draft is being prepared as per comments received from the workshop and other source |  | 2000
FIN | UNIDO | Replacement of CFC-11 and CFC-12 with cyclopentane and isobutane in the production of refrigerators at Little Swan Electric (Jingzhou) Co. Ltd. | Individual | ASP | CPR | REF | 32 | INV | 365 | A | I | CFC | 211.9 | 211.9 |  |  | 2000-12-01 | 2001-06-01 | 2003-12-01 |  | 2004-05-01 | 2005-09-01 | 2392316 | 0 | 2392316 | 2392316.08 | 100% | -0.08 | 0 |  | 273155 | -253 | 272902 | 0 | 0 | FIN
FIN | UNDP | Phaseout of CFC-11 by conversion to cyclopentane technology and CFC-12 by conversion to isobutane (600a) technology in the manufacture of domestic freezers at Qingdao Haier No. 2 Freezer Plant | Individual | ASP | CPR | REF | 32 | INV | 367 | N | I | CFC | 180.8 | 180.8 | 0 | 0 | 2000-12-01 | 2003-06-01 | 2004-01-01 |  | 2004-11-01 | 2011-08-01 | 788359 | -9293 | 779066 | 779066 | 100% | 0 | 0 | 0 | 96720 | -1140.11 | 95579.8862 | 0.0038 | 0 | Completed in 2004. |  | 2000 |  | Investment
FIN | IBRD | Replacement of CFC-11 foaming agent with cyclopentane and CFC-12 refrigerant with HFC-134a in the manufacture of domestic refrigerators at Shangling Electric Appliance (Group) Co. Ltd. | Individual | ASP | CPR | REF | 34 | INV | 378 | N | I | CFC | 174.2 | 174.2 | 0 | 0 | 2001-07-01 | 2003-05-01 | 2004-08-01 |  | 2005-12-01 | 2006-11-01 | 1400000 | 0 | 1400000 | 1400000 | 100% | 0 | 0 |  | 164000 | 0 | 164000 | 0 | 0 | Project is completed. |  |  |  | INV | 0
FIN | Germany | Conversion of the use of CFC-12 to HC in the manufacture of thermostats at Foshan Tongbao Co., Ltd. | Individual | ASP | CPR | REF | 35 | INV | 384 | A | I | CFC | 11.5 |  | 0 |  | 2001-12-01 | 2002-12-01 | 2004-05-01 |  | 2004-09-01 | 2006-10-01 | 213271 | 0 | 213271 | 213271 | 100% | 0 | 0 | 0 | 27725 | 0 | 27725 | 0 | 0 | Project completed. PCR has been submitted.
FIN | IBRD | Replacement of CFC-12 refrigerant with HCFC-22 in the manufacture of small and medium open compressors at 5 enterprises (Dalian No.2, Shanghai Minhang, Zhejiang Beifeng, Zhejiang Chunlian, Zhejiang Yuhuan) | One off phaseout | ASP | CPR | REF | 36 | INV | 389 | N | I | CFC | 764.9 | 764.9 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2005-03-01 |  | 2007-12-01 | 2008-05-01 | 5250852 | 0 | 5250852 | 5250852 | 100% | 0 | 0 |  | 587593.72 | 0 | 587593.72 | 0 | 0 | Project completed. PCR prepared. |  |  |  | INV | 0
FIN | UNIDO | Preparation of a sectoral phase-out plan in domestic refrigeration and compressor manufacturing | Individual | ASP | CPR | REF | 36 | PRP | 385 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-05-01 | 2003-07-01 |  | 2003-07-01 | 2004-04-01 | 70000 | 0 | 70000 | 70000.32 | 100% | -0.32 | 0 |  | 9100 | -12 | 9088 | 0 | 0 | FIN |  |  |  | INV
FIN | Italy | Sector plan CFC final phase-out: domestic refrigeration and domestic refrigeration compressors (first tranche) | Multi-Year | ASP | CPR | REF | 38 | INV | 393 | A | I | CFC | 181 | 181 | 0 |  | 2002-11-01 | 2003-09-01 | 2005-11-01 |  | 2005-10-01 | 2005-12-01 | 1788991 | 0 | 1788991 | 1788991 | 100% | 0 | 0 | 0 | 161009 | 0 | 161009 | 0 | 0 | FIN |  | 2003 |  | Investment
FIN | UNIDO | Sector plan CFC final phase-out: domestic refrigeration and domestic refrigeration compressors | Multi-Year | ASP | CPR | REF | 38 | INV | 394 | A | I | CFC | 600 | 600 |  |  | 2002-11-01 | 2003-09-01 | 2007-05-01 |  | 2007-06-01 | 2007-12-01 | 3400000 | 0 | 3400000 | 3399999.51 | 100% | 0.49 | 0 |  | 299200 | 0 | 299200 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Sector plan CFC final phase-out: domestic refrigeration and domestic refrigeration compressors (second tranche) | Multi-Year | ASP | CPR | REF | 41 | INV | 406 | A | I | CFC | 318 | 318 |  |  | 2003-12-01 | 2006-12-01 | 2007-12-01 |  | 2009-12-01 | 2010-04-01 | 2171539 | -27541 | 2143998 | 2143997.51 | 100% | 0.49 | 0 |  | 192239 | -2460 | 189779 | 0 | 0 | FIN |  |  |  | INV
FIN | Germany | Development of a suitable strategy for the long term management of HCFCs, in particular HCFC-22 | Individual | ASP | CPR | REF | 43 | TAS | 414 | A | I |  | 0 | 0 | 0 |  | 2004-07-01 | 2004-11-01 | 2005-12-01 |  | 2007-03-01 | 2008-12-01 | 300300 | -2.8 | 300297.2 | 300297 | 100% | 0.2 | 0 | 0 | 39039 | -0.36 | 39039 | -0.36 | 0 | Project was completed and approved by the Chinese authorities. Project report was submitted to 51st ExCom. PCR was submitted in December 2008.
FIN | UNIDO | Refrigeration servicing sector CFC phase-out plan (first tranche) | Multi-Year | ASP | CPR | REF | 44 | INV | 419 | A | I | CFC | 0 | 0 |  |  | 2004-12-01 | 2005-04-01 | 2006-12-01 |  | 2007-12-01 | 2010-04-01 | 1000000 | -450043 | 549957 | 549956.95 | 100% | 0.05 | 0 |  | 75000 | -33753 | 41247 | 0 | 0 | FIN |  |  |  | INV
FIN | Japan | Refrigeration servicing sector CFC phase-out plan (first tranche) | Multi-Year | ASP | CPR | REF | 44 | INV | 420 | A | I | CFC-12 | 0 |  | 0 |  | 2004-12-01 | 2005-09-01 | 2005-12-01 |  | 2005-12-01 | 2013-12-01 | 1000000 | 0 | 1000000 | 1000000 | 100% | 0 | 0 | 0 | 130000 | 0 | 130000 | 0 | 0 | Financial completion in Dec 2013. |  | 2004 |  | investment
FIN | UNEP | Refrigeration servicing sector CFC phase-out plan (revised 2005 annual implementation programme) | Multi-year | ASP | CPR | REF | 45 | TAS | 426 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-10-01 | 2007-12-01 |  | 2010-12-01 | 2013-12-01 | 450000 | 0 | 450000 | 450000 | 100% | 0 | 0 |  | 58500 | 0 | 58500 | 0 | 0
FIN | Japan | Refrigeration servicing sector CFC phase-out plan (second tranche) | Multi-Year | ASP | CPR | REF | 47 | INV | 438 | A | I | CFC-12 | 511 | 511 | 0 |  | 2005-11-01 | 2006-11-01 | 2006-12-01 |  | 2012-12-01 | 2014-12-01 | 3000000 | -1580 | 2998420 | 2998420 | 100% | 0 | 0 | 0 | 390000 | -205 | 389795 | 0 | 0 | Financial completion in Dec 2014. Refund was reported to 74th ExCom, May 2015. FIN. |  | 2005 |  | investment
FIN | UNIDO | Refrigeration servicing sector CFC phase-out plan (third tranche) | Multi-Year | ASP | CPR | REF | 51 | INV | 450 | A | I | CFC | 782 | 782 |  |  | 2007-03-01 | 2007-09-01 | 2008-03-01 |  | 2008-12-01 | 2010-05-01 | 700000 | 0 | 700000 | 700000 | 100% | 0 | 0 |  | 52500 | 0 | 52500 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Refrigeration servicing sector CFC phase-out plan (fourth tranche) | Multi-Year | ASP | CPR | REF | 53 | INV | 453 | A | I | CFC | 793 | 793 |  |  | 2007-11-01 | 2008-05-01 | 2008-11-30 |  | 2013-12-01 | 2014-07-01 | 700000 | -2861 | 697139 | 697138.75 | 100% | 0.25 | 0 |  | 52500 | -215 | 52285 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Refrigeration servicing sector CFC Phase-out Plan (fifth tranche) | Multi-Year | ASP | CPR | REF | 56 | INV | 474 | A | I | CFC | 680 | 680 |  |  | 2008-11-01 | 2008-12-01 | 2009-11-30 |  | 2011-12-01 | 2011-12-01 | 700000 | -104 | 699896 | 699895.84 | 100% | 0.16 | 0 |  | 52500 | -8 | 52492 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Refrigeration servicing sector CFC phase-out plan (sixth tranche) | Multi-Year | ASP | CPR | REF | 59 | INV | 490 | A | I | CFC | 1136 | 1136 |  |  | 2009-11-01 | 2010-10-01 | 2010-11-30 |  | 2013-12-01 | 2013-12-01 | 785000 | 0 | 785000 | 785000 | 100% | 0 | 0 |  | 58880 | 0 | 58880 | 0 | 0 | FIN |  |  |  | INV
FIN | UNDP | Demonstration project for conversion from HCFC-22 technology to HFC-32 technology in the manufacture of commercial air-source chillers/heat pumps at Tsinghua Tong Fang Artifical Environment Co. Ltd. | Individual | ASP | CPR | REF | 60 | DEM | 498 | N | X | HCFC | 3.4 | 3.4 | 0 | 0 | 2010-04-01 | 2011-03-01 | 2011-10-01 |  | 2014-12-01 | 2015-12-01 | 1229336 | -1 | 1229335 | 1229335 | 100% | 0 | 0 | 0 | 92200 | -0.08 | 92199.925 | -0.005 | 0 | Financially Completed in 2015. | Project completion activities are underway. The project is expected to be completed by Q4-2014. A detailed technical report provided for the consideration of 72 Excom. | 2010 |  | Investment | 681096
FIN | UNDP | Demonstration project for conversion from HCFC-22 technology to Ammonia/CO2 technology in the manufacture of two-stage refrigeration systems for cold storage and freezing applications at Yantai Moon Group Co. Ltd. | Individual | ASP | CPR | REF | 60 | DEM | 499 | N | X | HCFC | 13.8 | 13.8 | 0 | 0 | 2010-04-01 | 2011-03-01 | 2011-10-01 |  | 2014-12-01 | 2015-12-01 | 3964458 | 0 | 3964458 | 3964458 | 100% | 0 | 0 | 0 | 297334 | 0 | 297334 | 0 | 0 | Financially Completed in 2015. | Project completion activities are underway. The project is expected to be completed by Q4-2014. A detailed technical report provided for the consideration of 72 Excom. | 2010 |  | Investment | 2629145
FIN | UNIDO | Demonstration sub-project for conversion of room airconditioning compressor manufacturing from HCFC-22 to propane at Guangdong Meizhi Co. | Individual | ASP | CPR | REF | 61 | DEM | 502 | A | I |  | 0 | 0 |  |  | 2010-07-01 | 2010-12-01 | 2012-09-30 |  | 2013-12-01 | 2015-09-01 | 1875000 | -74 | 1874926 | 1874925.84 | 100% | 0.16 | 0 |  | 140625 | -6 | 140619 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Demonstration sub-project for conversion from HCFC-22 to propane at Midea Room Air-conditioning Manufacturing Company | Individual | ASP | CPR | REF | 61 | DEM | 503 | A | I | HCFC | 13.2 | 13.2 |  |  | 2010-07-01 | 2010-12-01 | 2012-09-30 |  | 2014-12-01 | 2016-03-01 | 4026507 | -1348 | 4025159 | 4025159.01 | 100% | -0.01 | 0 |  | 301988 | -101 | 301887 | 0 | 0 | The project was financially completed and the balance was returned at the 76th ExCom. |  |  |  | INV
ONG | UNDP | Preparation for HCFC phase-out investment activities (stage II) (industrial and commercial refrigeration sector) | Individual | ASP | CPR | REF | 73 | PRP | 543 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-11-01 | 2015-04-01 | 2016-11-01 | 2017-05-01 |  |  | 330000 | 0 | 330000 | 313738.08 | 95.07% | 16261.92 | 0 | 6504.768 | 23100 | 0 | 21961.6656 | 1138.3344 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): The submitted HPMP of ICR sector for stage II was approved in Dec 2016. Prodoc signed (actual/planned, yes/no and date):42095 Missions undertaken (actual/planned):2 TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: signed earlier First disbursement date (actual/planned): 42095Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | Main acitivities under the project has been completed and all the remaining funding was committed. | 2014 |  | Non-Investment
ONG | UNIDO | Preparation for HCFC phase-out investment activities (stage II) (room and air-conditioner and domestic heat pump sectors) | Individual | ASP | CPR | REF | 73 | PRP | 554 | A | I |  | 0 | 0 |  |  | 2014-11-01 | 2015-12-01 | 2016-06-01 | 2017-04-01 |  |  | 300000 | 0 | 300000 | 285262.39 | 95.09% | 14737.61 | 246.69 | 14000 | 21000 | 0 | 19968 | 1032 | 17 | - Third coordination meeting before submission took place in January 2016. Subsequently the HPMP was finalized and submitted to the 76th ExCom Meeting and resubmitted to the 77th ExCom Meeting. The HPMP was approved at the 77th ExCom Meeting. Milestones achieved: Working arrangements agreed: Yes, February 2015; ToR for the Stage II HPMP preparation prepared and agreed: Yes, March 2015; Contract signed: Yes, May 2015; HCFC survey completed: Yes All technical input completed: Yes Draft document completed: Yes Activities planned but not implemented, reasons and strategy: Everything as planned. Actions towards next goals: Preparation of work plan based on the approval. Was there any delay during the reporting year? No Any recurring problem? No Any action required by Executive Committee? No | The draft work plan has been prepared in line with the ExCom's request and the project has been operationally completed. Financial completion will follow after clearance of commitments. |  |  | NON-INV
ONG | UNDP | Preparation of a demonstration project of ammonia semi-hermetic frequency convertible screw refrigeration system in the industrial and commercial refrigeration industry | Individual | ASP | CPR | REF | 74 | PRP | 562 | N | I | HCFC | 0 | 0 | 0 | 0 | 2015-05-01 | 2015-08-01 | 2016-05-01 | 2017-05-01 |  |  | 24000 | 0 | 24000 | 11747 | 48.95% | 12253 | 0 | 4901.2 | 1680 | 0 | 822.29 | 857.71 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Prepared the document, submitted to ExCom 76th and got approved. Fujian Snowman Co. (18 months to complete the project). Prodoc signed (actual/planned, yes/no and date):Letter of Authorisation sent 23 July 2015 Missions undertaken (actual/planned):- TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: signed earlier First disbursement date (actual/planned): 42217Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | Remaining payment will be disbursedby May 17 | 2015 |  | Non-Investment
ONG | UNDP | Demonstration project for ammonia semi-hermetic frequency convertible screw refrigeration compression unit in the industrial and commercial refrigeration industry at Fujian Snowman Co. Ltd. | Individual | ASP | CPR | REF | 76 | DEM | 573 | N | I | HCFC | 0 | 0 | 0 | 0 | 2016-05-01 |  | 2017-11-17 | 2018-05-01 |  |  | 1026815 | 0 | 1026815 | 0 | 0% | 1026815 | 0 | 410726 | 71877 | 0 | 0 | 71877 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Doc signed Jan 17 and first payment released. Prodoc signed (actual/planned, yes/no and date):42675 Missions undertaken (actual/planned):2 TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: signed earlier First disbursement date (actual/planned): 42776Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | The payment to the Snowman is in process now, and hopefully can be made by the middle of March 2017 to start the work. |  |  | Investment
FIN | IBRD | Preparation of investment projects (1991) |  | ASP | CPR | SEV | 04 | PRP | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 184000 | -167746 | 16254 | 16254 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Country programme preparation | Individual | ASP | CPR | SEV | 06 | CPG | 11 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-01 | 1993-02-01 |  | 1993-03-01 | 1997-12-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 26000 | 0 | 26000 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | IBRD | Country programme studies | Individual | ASP | CPR | SEV | 06 | CPG | 12 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1992-12-01 |  | 1992-12-01 | 1992-12-01 | 180000 | -73841 | 106159 | 106159 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Institutional strengthening, including establishment of the Information Clearing-house at NEPA | Individual | ASP | CPR | SEV | 06 | INS | 10 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1994-04-01 | 1995-02-01 |  | 1996-12-01 | 1998-12-01 | 150000 | 299997 | 449997 | 449997 | 100% | 0 | 0 | 0 | 19500 | 38999.61 | 58499.61 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1992 |  | Non-Investment
FIN | IBRD | Project preparation advance for developing components of Project I (1992) |  | ASP | CPR | SEV | 07 | PRP | 21 | N | D |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | PPA I is complete. These funds were used to support implementation of the China ODS Projects I and II. No money was allocated, however $600,000 from ODS II and $900,000 from ODS I was used. |  |  |  | Non-INV | 0
FIN | USA | Support for the FESCAST international conference |  | ASP | CPR | SEV | 08 | TRA | 25 | A | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1993-10-01 |  | 1993-10-01 | 1994-04-01 | 87000 | 96000 | 183000 | 183000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Adjustment of US $96,000 credited against 1993 contributions (11th Meeting).
FIN | UNDP | Preparation of investment projects | Individual | ASP | CPR | SEV | 09 | PRP | 30 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1994-07-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1993 |  | Investment
FIN | IBRD | Preparation of investment projects (1993) |  | ASP | CPR | SEV | 09 | PRP | 31 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 326000 | -133667 | 192333 | 192333 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Survey and assessment of small CFC plant conversion possibilities | Individual | ASP | CPR | SEV | 09 | TAS | 26 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1995-05-01 | 1994-03-01 |  | 1998-10-01 | 2001-12-01 | 90000 | -701 | 89299 | 89299 | 100% | 0 | 0 | 0 | 11700 | -91.21 | 11608.7884 | 0.0016 | 0 | Completed in 1998. Financially completed in 2001. |  | 1993 |  | Non-Investment
FIN | IBRD | Financial agent fee for the implementation of approved projects (two aerosols, two foams, two halons) | Individual | ASP | CPR | SEV | 09 | TAS | 29 | N | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-06-01 | 1995-12-01 |  | 1996-12-01 | 1996-12-01 | 185000 | 0 | 185000 | 185000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The FA completed appraisal reports for all subprojects and all have been cleared by the Bank. PPA I has been fully disbursed. ODS II was disbursed, and its accounts closed in 1997. Project completion report for ODS I& II completed. |  |  | 1996-12-01 | Non-INV | 0
FIN | IBRD | User-sector pre-investment studies (1993) |  | ASP | CPR | SEV | 10 | PRP | 35 | A | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-06-30 | 1994-06-01 |  | 1993-12-01 | 1993-12-01 | 280000 | -131872 | 148128 | 148128 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Project preparation assistance | Individual | ASP | CPR | SEV | 11 | PRP | 58 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-01 | 1994-11-01 |  | 1994-12-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1993 |  | Investment
FIN | UNDP | National product qualification and standards evaluation for non-ODS alternatives to CFC applications | Individual | ASP | CPR | SEV | 11 | TAS | 56 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1995-11-01 | 1994-11-01 |  | 1998-03-01 | 2000-12-01 | 362500 | -29055 | 333445 | 333445 | 100% | 0 | 0 | 0 | 47125 | -3777.15 | 43347.85 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1993 |  | Non-Investment
FIN | Canada | Activities in Sichuan Province | Individual | ASP | CPR | SEV | 11 | TRA | 52 | A | I |  | 0 |  | 0 |  | 1993-11-01 |  | 1994-11-01 |  | 1993-10-01 | 1994-11-01 | 172500 | 0 | 172500 | 172500 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Workshop held in October 1993 and approved by retroactive funding in September 1994. |  | 1993 | 2000-01-01 | Non-Inv.
FIN | IBRD | Preparation of projects ODS III (1994) |  | ASP | CPR | SEV | 12 | PRP | 62 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 660000 | -138768 | 521232 | 521232 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Supervision of project implementation of China ODS I (1994) |  | ASP | CPR | SEV | 12 | PRP | 63 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 79000 | -35235 | 43765 | 43765 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Supervision of project implementation of China ODS II (1994) |  | ASP | CPR | SEV | 12 | PRP | 64 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 110000 | 10949 | 120949 | 120949 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Project preparation assistance | Individual | ASP | CPR | SEV | 15 | PRP | 106 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-01-01 | 1995-06-01 |  | 1995-06-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Investment
FIN | IBRD | Preparation/supervision of investment projects ODS II (1995) |  | ASP | CPR | SEV | 16 | PRP | 120 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 103131 | 0 | 103131 | 103131 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation/supervision of investment projects ODS III (1995) |  | ASP | CPR | SEV | 16 | PRP | 139 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 650000 | 0 | 650000 | 650000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Processing of the third ODS Phaseout project for China has been completed. Grant agreement was signed in June 1995. $50,000 was transferred from PPA-IV (China) (CPR/SEV/16/PRP/217) to this project preparation (ODS III - China). Thus, $700,000 was disbursed under this activity. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation/supervision of investment projects ODS IV (1995) |  | ASP | CPR | SEV | 16 | PRP | 217 | N | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1996-12-31 | 1997-12-01 |  | 1997-12-31 | 1997-12-01 | 250000 | 0 | 250000 | 250000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. Actual disbursement for PPA IV was $200,000. and the balance of $50,000 was utilized for project preparation under ODS III (CPR/SEV/16/PRP/139). |  |  |  | Non-INV | 0
FIN | IBRD | Preparation/supervision of investment projects ODS I (1995) |  | ASP | CPR | SEV | 16 | PRP | 246 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 68017 | 0 | 68017 | 68017 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | UNDP | Project preparation assistance | Individual | ASP | CPR | SEV | 17 | PRP | 128 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-08-01 | 1996-04-01 |  | 1996-03-01 | 2002-05-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1996. Financially completed in 2002. |  | 1995 |  | Investment
FIN | UNIDO | Project formulation of investment projects in the halon sector in the 3 fire equipment factories (Xiangshan, Xiangshan No. 1 and Dalian Jinzhou) and in domestic refrigeration sectors and solvents | Individual | ASP | CPR | SEV | 17 | PRP | 132 | A | I |  | 0 | 0 |  |  | 1995-07-01 | 1995-09-01 | 1996-07-01 |  | 1998-12-01 | 2000-07-01 | 100000 | -193 | 99807 | 99807 | 100% | 0 | 0 |  | 13000 | -46 | 12954 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | IBRD | Development of a cost effective sector based ODS phase out approach | Individual | ASP | CPR | SEV | 17 | TAS | 136 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-10-31 | 1996-12-01 |  | 1996-12-01 | 1996-12-01 | 350000 | -150000 | 200000 | 200000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | $100,000 transferred to PPA-V. |  |  |  | Non-INV | 0
FIN | UNDP | Project preparation assistance | Individual | ASP | CPR | SEV | 18 | PRP | 153 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-11-01 | 2002-05-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1996. Financially completed in 2002. |  | 1995 |  | Investment
FIN | IBRD | Project preparation |  | ASP | CPR | SEV | 18 | PRP | 154 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | Complete. |  |  |  | Non-INV | 0
FIN | UNEP | Training workshop on safety aspects of CFC substitutes | Individual | ASP | CPR | SEV | 18 | TRA | 155 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-01-01 | 1996-05-01 |  | 1996-05-01 | 1999-04-01 | 82400 | 0 | 82400 | 82400 | 100% | 0 | 0 |  | 10712 | 0 | 10712 | 0 | 0
FIN | UNDP | Institutional strengthening for the phaseout of ODS under the Montreal Protocol - Phase II | Individual | ASP | CPR | SEV | 20 | INS | 181 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1996-10-01 | 1996-11-01 | 1998-11-01 |  | 1998-12-01 | 1999-12-01 | 300000 | -1 | 299999 | 299999 | 100% | 0 | 0 | 0 | 39000 | -0.13 | 38999.87 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1996 |  | Non-Investment
FIN | UNDP | Update of the country programme and policy workshop | Individual | ASP | CPR | SEV | 21 | CPG | 188 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-04-01 | 1998-03-01 |  | 1998-12-01 | 2002-06-01 | 225000 | -17054 | 207946 | 207946 | 100% | 0 | 0 | 0 | 29250 | -2217.02 | 27032.98 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1997 |  | Non-Investment
FIN | IBRD | Project preparation |  | ASP | CPR | SEV | 21 | PRP | 189 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-31 | 1997-12-31 | 250000 | 0 | 250000 | 250000 | 100% | 0 | 0 |  | 32500 | 0 | 32500 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNIDO | Project preparation in the refrigeration (including compressors), solvents and methyl bromide sectors | Individual | ASP | CPR | SEV | 21 | PRP | 190 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-06-01 | 1998-02-01 |  | 1999-12-01 | 2002-09-01 | 182140 | -575 | 181565 | 181565.3 | 100% | -0.3 | 0 |  | 23678 | -112 | 23566 | 0 | 0 | FIN
FIN | UNDP | Project preparation in the foam, refrigeration and solvent sectors | Individual | ASP | CPR | SEV | 21 | PRP | 191 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1997-12-01 | 1999-12-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 26000 | 0 | 26000 | 0 | 0 | Completed in 1997. Financially completed in 1999. |  | 1997 |  | Investment
FIN | UNDP | Project preparation in the foam, refrigeration and solvent sectors | Individual | ASP | CPR | SEV | 22 | PRP | 197 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-02-01 | 1999-12-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 | 0 | 19500 | 0 | 19500 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1997 |  | Investment
FIN | IBRD | Project preparation in the aerosol, foam, MAC and commercial refrigeration sectors |  | ASP | CPR | SEV | 24 | PRP | 243 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1999-06-01 | 1999-06-01 | 600000 | 0 | 600000 | 600000 | 100% | 0 | 0 |  | 78000 | 0 | 78000 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | UNDP | Institutional strengthening for the phaseout of ODS under the Montreal Protocol (Phase III) | Individual | ASP | CPR | SEV | 26 | INS | 262 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-11-01 | 1998-12-01 | 2000-12-01 |  | 2000-12-01 | 2001-12-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 | 0 | 39000 | 0 | 39000 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Non-Investment
FIN | IBRD | Preparation of projects in the foam, commercial refrigeration and CFC production sectors |  | ASP | CPR | SEV | 27 | PRP | 273 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-31 | 2001-01-01 |  | 1999-12-31 | 1999-12-31 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 |  | 39000 | 0 | 39000 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | UNEP | Development of policy training strategy and plan for local authorities | Individual | ASP | CPR | SEV | 27 | TAS | 268 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-05-01 | 2000-04-01 |  | 2000-10-01 | 2001-02-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
TRF | UNEP | Evaluation and risk analysis of Montreal Protocol Implementation in China | Individual | ASP | CPR | SEV | 30 | TAS | 346 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 |  | 2001-04-01 |  |  | 2001-12-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 |  | 0
FIN | UNDP | Renewal of institutional strengthening (Phase IV) | Individual | ASP | CPR | SEV | 32 | INS | 368 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2002-03-01 | 2003-01-01 |  | 2003-06-01 | 2008-10-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 | 0 | 39000 | 0 | 39000 | 0 | 0 | Completed in 2003. Financially completed in 2008. |  | 2000 |  | Non-Investment
FIN | Germany | Project preparation/technical assistance in the refrigeration sector (thermostat) | Individual | ASP | CPR | SEV | 33 | PRP | 372 | A | I |  | 0 |  | 0 |  | 2001-03-01 | 2001-04-01 | 2001-12-01 |  | 2002-01-01 | 2002-07-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 650 | 0 | 650 | 0 | 0 | Completed; no PCR due to project preparation only
FIN | UNEP | Policy training for local authorities (first tranche for 2001) | Individual | ASP | CPR | SEV | 34 | TRA | 377 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2002-07-01 |  | 2003-12-01 | 2003-12-01 | 275000 | 0 | 275000 | 275000 | 100% | 0 | 0 |  | 35750 | 0 | 35750 | 0 | 0
FIN | UNEP | Policy training for local authorities (second tranche) | Individual | ASP | CPR | SEV | 37 | TRA | 392 | A | I | CFC | 16.5 | 0 | 0 | 0 | 2002-07-01 | 2003-06-01 | 2003-08-01 |  | 2005-09-01 | 2005-07-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 |  | 26000 | 0 | 26000 | 0 | 0
FIN | UNDP | Extension of institutional strengthening (phase 5) | Individual | ASP | CPR | SEV | 38 | INS | 398 | N | I | No_ODP | 32.2 | 32.2 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2004-12-01 |  | 2005-09-01 | 2008-10-01 | 390000 | 0 | 390000 | 390000 | 100% | 0 | 0 | 0 | 50700 | 0 | 50700 | 0 | 0 | Completed in 2005. Financially completed in 2008. |  | 2002 |  | Non-Investment
FIN | UNEP | Policy training for local authorities (third tranche) | Individual | ASP | CPR | SEV | 43 | TRA | 413 | A | I | CFC | 27.7 | 27.7 | 0 | 0 | 2004-07-01 | 2004-10-01 | 2007-12-01 |  | 2010-12-01 | 2011-12-01 | 335000 | 0 | 335000 | 335000 | 100% | 0 | 0 |  | 43550 | 0 | 43550 | 0 | 0
FIN | UNDP | Extension of institutional strengthening project (phase VI) | Individual | ASP | CPR | SEV | 44 | INS | 421 | N | I | No_ODP | 32.2 | 32.2 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2006-12-01 |  | 2006-12-01 | 2010-10-01 | 390000 | -129.12 | 389870.88 | 389871 | 100% | -0.12 | 0 | 0 | 29250 | -9.68 | 29240.325 | -0.005 | 0 | Financially completed in 2010. |  | 2004 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VII) | Individual | ASP | CPR | SEV | 50 | INS | 444 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-06-01 | 2008-11-01 |  | 2008-12-01 | 2010-10-01 | 390000 | -413.47 | 389586.53 | 389587 | 100% | -0.47 | 0 | 0 | 29250 | -31.01 | 29219.0251 | -0.03505 | 0 | Financially completed in 2010. |  | 2006 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VIII) | Individual | ASP | CPR | SEV | 56 | INS | 477 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-05-01 | 2010-12-01 |  | 2010-12-01 | 2011-07-01 | 390000 | 0 | 390000 | 390000 | 100% | 0 | 0 | 0 | 29250 | 0 | 29250 | 0 | 0 | Completed in 2010. Financially completed in 2011. |  | 2008 |  | Non-Investment
FIN | UNEP | Awareness/outreach activities on HCFC phase-out and its challenges during HPMP preparatory phase | Individual | ASP | CPR | SEV | 56 | TAS | 476 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-06-01 | 2010-12-01 |  | 2011-06-01 | 2012-06-01 | 140000 | 0 | 140000 | 140000 | 100% | 0 | 0 |  | 18200 | 0 | 18200 | 0 | 0
FIN | UNDP | Extension of the institutional strengthening project (phase IX) | Individual | ASP | CPR | SEV | 62 | INS | 504 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-06-01 | 2012-12-01 |  | 2013-06-01 | 2014-09-01 | 390000 | -572 | 389428 | 389428 | 100% | 0 | 0 | 0 | 29250 | -43 | 29207 | 0 | 0 | Financially completed in 2014. | Completed in 2013. | 2010 |  | Investment
FIN | UNDP | Extension of the institutional strengthening project (phase X: 1/2013-12/2014) | Individual | ASP | CPR | SEV | 68 | INS | 523 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-04-01 | 2015-03-01 |  | 2014-12-01 | 2015-12-01 | 390000 | 0 | 390000 | 390000 | 100% | 0 | 0 | 0 | 27300 | 0 | 27300 | 0 | 0 | Financially Completed in 2015. | Project activities are continuing to be being monitored. | 2012 |  | Non-investment
ONG | UNDP | Extension of the institutional strengthening project (phase XI: 1/2015-12/2016) | Individual | ASP | CPR | SEV | 73 | INS | 549 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-11-01 | 2015-04-01 | 2016-12-01 | 2017-01-01 |  |  | 390000 | 0 | 390000 | 388644.76 | 99.65% | 1355.24 | 0 | 542.096 | 27300 | 0 | 27205.1332 | 94.8668 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): The project completed all activities and funding disbursement. Prodoc signed (actual/planned, yes/no and date):42064 Missions undertaken (actual/planned):1 TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: signed earlier First disbursement date (actual/planned): 42095Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | Preparation for implementation of IS phase XII is ongoing. | 2014 |  | Non-Investment
ONG | UNDP | Extension of the institutional strengthening project (phase XII: 1/2017-12/2018) | Individual | ASP | CPR | SEV | 77 | INS | 575 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2016-12-01 |  | 2018-12-01 | 2017-12-01 |  |  | 499200 | 0 | 499200 | 0 | 0% | 499200 | 0 | 199680 | 34944 | 0 | 0 | 34944 | 0 | Newly Approved | DoA sent March 2017. Awaiting prodoc & AWP from CO for ASL request. | 2016 |  | Non-Investment
FIN | UNDP | Pre-feasibility study to phase-out CFC-113 in electronic cleaning in four production lines | Individual | ASP | CPR | SOL | 06 | TAS | 08 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-10-01 | 1993-02-01 |  | 1993-03-01 | 1997-12-01 | 40000 | 1829 | 41829 | 41829 | 100% | 0 | 0 | 0 | 5200 | 237.77 | 5437.77 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Dalian precision parts cleaning line demonstration project | Individual | ASP | CPR | SOL | 07 | INV | 19 | N | I | CFC | 69 | 69 | 0 | 0 | 1992-06-01 | 1996-04-01 | 1994-06-01 |  | 1996-09-01 | 1998-12-01 | 495000 | -34190.74 | 460809.26 | 460809 | 100% | 0.26 | 0 | 0 | 64350 | -4444.55 | 59905.42 | 0.03 | 0 | Completed in 1996. Financially completed in 1998. |  | 1992 |  | Investment
FIN | UNDP | Dandong electronic tuner aqueous cleaning line demonstration project | Individual | ASP | CPR | SOL | 07 | INV | 20 | N | I | CFC | 20 | 20 | 0 | 0 | 1992-06-01 | 1995-07-01 | 1994-06-01 |  | 1995-11-01 | 1998-12-01 | 495000 | -663 | 494337 | 494337 | 100% | 0 | 0 | 0 | 64350 | -86.13 | 64263.87 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1992 |  | Investment
FIN | UNDP | Elimination of CFC in cleaning operations at Nanjing Wire Works | Individual | ASP | CPR | SOL | 10 | INV | 36 | A | I | CFC | 8.8 | 8.8 | 0 | 0 | 1993-06-01 | 1996-08-01 | 1995-12-01 |  | 1997-12-01 | 2000-12-01 | 409000 | -511 | 408489 | 408489 | 100% | 0 | 0 | 0 | 53170 | -66.43 | 53103.57 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1993 |  | Investment
FIN | UNDP | Elimination of CFC in cleaning operations at the Chengdu Qianfeng Radio Instrument Factory | Individual | ASP | CPR | SOL | 10 | INV | 37 | N | I | CFC | 7.2 | 7.2 | 0 | 0 | 1993-06-01 | 1996-03-01 | 1995-12-01 |  | 1997-12-01 | 1999-12-01 | 394700 | -13224 | 381476 | 381476 | 100% | 0 | 0 | 0 | 51311 | -1719 | 49592 | 0 | 0 | Completed in 1997. Financially completed in 1999. |  | 1993 |  | Investment
FIN | UNDP | ODS-free cleaning equipment manufacturing center for phasing out ODS consuming solvents across China | Individual | ASP | CPR | SOL | 12 | INV | 65 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1997-06-01 | 1996-03-01 |  | 1999-11-01 | 2002-07-01 | 524734 | -50707 | 474027 | 474027 | 100% | 0 | 0 | 0 | 68215.42 | -6591.91 | 61623.51 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1994 | 1999-12-01 | Investment
FIN | UNDP | Cleaning applications deployment center for replication of ODS-free process across China | Individual | ASP | CPR | SOL | 12 | TAS | 61 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1996-03-01 | 1995-03-01 |  | 1998-05-01 | 2000-12-01 | 489400 | -66345.28 | 423054.72 | 423055 | 100% | -0.28 | 0 | 0 | 63622 | -8624.89 | 54997.15 | -0.04 | 0 | Completed in 1998. Financially completed in 2000. |  | 1994 |  | Non-Investment
FIN | Canada | No-clean technology programme | Individual | ASP | CPR | SOL | 14 | TAS | 82 | A | I |  | 0 |  | 0 |  | 1994-09-01 |  | 1995-09-01 |  | 1994-11-01 | 1995-09-01 | 51100 | 0 | 51100 | 51100 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1994 | 2000-01-01 | Non-Inv.
FIN | UNDP | Elimination of ODS (CFC-113) used in the production line at Hunan Computer Factory | Individual | ASP | CPR | SOL | 18 | INV | 152 | A | R | CFC | 21 | 21 | 0 | 0 | 1995-11-01 | 1997-05-01 | 1997-05-01 |  | 1997-12-01 | 2000-12-01 | 104700 | -18343 | 86357 | 86357 | 100% | 0 | 0 | 0 | 13611 | -2384.59 | 11226.41 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Elimination of CFC-113 used in the production line at Shanghai Sixth Radio Factory | Individual | ASP | CPR | SOL | 19 | INV | 169 | N | I | CFC | 4.5 | 4.5 | 0 | 0 | 1996-05-01 | 1999-09-01 | 1998-04-01 |  | 2001-08-01 | 2003-09-01 | 138400 | -14098 | 124302 | 124302 | 100% | 0 | 0 | 0 | 17992 | -1832.74 | 16159.26 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1996 | 1998-05-01 | Investment
CLO | UNDP | Elimination of the use of CFC-113 in the electron gun final cleaning processes at the Tianjin Picture Tube Factory | Individual | ASP | CPR | SOL | 19 | INV | 170 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1998-04-01 |  |  | 1999-03-01 | 132600 | -132600 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 17238 | -17238 | 0 | 0 | 0 | Canceled in 1999. Financially Completed in 1999. |  | 1996 |  | Investment
FIN | UNDP | Elimination of the use of CFC-113 and methyl chloroform in the color picture tube cleaning processes at the Shanghai Novel CPT. Corp. Factory | Individual | ASP | CPR | SOL | 19 | INV | 171 | N | I | CFC | 75 | 75 | 0 | 0 | 1996-05-01 | 1998-10-01 | 1998-04-01 |  | 2002-11-01 | 2008-10-01 | 849950 | -150442 | 699508 | 699508 | 100% | 0 | 0 | 0 | 110493.5 | -19558 | 90935.5 | 0 | 0 | Completed in 2002. Financially completed in 2008. |  | 1996 | 1998-05-01 | Investment
FIN | UNDP | Elimination of the use of TCA in the Baoshi Electronics Corporation Shijazhuang Manufacturing Operations | Individual | ASP | CPR | SOL | 19 | INV | 172 | N | I | TCA | 7.4 | 7.4 | 0 | 0 | 1996-05-01 | 1997-07-01 | 1998-04-01 |  | 2000-07-01 | 2003-03-01 | 284900 | -7138.15 | 277761.85 | 277762 | 100% | -0.15 | 0 | 0 | 37037 | -928.08 | 36108.9395 | -0.0195 | 0 | Completed in 2000. Financially completed in 2003. |  | 1996 | 1998-05-01 | Investment
FIN | UNDP | Elimination of ODS (CFC 113) used in the production line at Shanghai Automation Instrumentation Factory | Individual | ASP | CPR | SOL | 20 | INV | 178 | N | I | CFC | 16 | 16 | 0 | 0 | 1996-10-01 | 1999-08-01 | 1998-09-01 |  | 2001-03-01 | 2003-03-01 | 325000 | -5336 | 319664 | 319664 | 100% | 0 | 0 | 0 | 42250 | -693.68 | 41556.32 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1996 | 1998-10-01 | Investment
FIN | UNDP | Elimination of ODS (CFC 113) used in the production line at Shanghai No 8 Radio Factory | Individual | ASP | CPR | SOL | 20 | INV | 186 | N | I | CFC | 19.2 | 19.2 | 0 | 0 | 1996-10-01 | 2000-03-01 | 1998-09-01 |  | 2001-03-01 | 2003-09-01 | 378000 | -81073 | 296927 | 296927 | 100% | 0 | 0 | 0 | 49140 | -10539.49 | 38600.51 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1996 | 1998-10-01 | Investment
FIN | UNDP | Preparation of a sectoral financing plan for the solvents sector | Individual | ASP | CPR | SOL | 21 | TAS | 192 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-12-01 | 2003-07-01 | 200000 | -19236 | 180764 | 180764 | 100% | 0 | 0 | 0 | 26000 | -2500.68 | 23499.32 | 0 | 0 | Completed in 1998. Financially completed in 2003. |  | 1997 |  | Non-Investment
FIN | UNDP | Elimination of CFC-113 used in the production line at Shanghai Railway Communication Equipment Factory | Individual | ASP | CPR | SOL | 22 | INV | 195 | N | I | CFC | 14.4 | 14.4 | 0 | 0 | 1997-05-01 | 1999-09-01 | 1999-06-01 |  | 2001-03-01 | 2003-03-01 | 276287 | -1 | 276286 | 276286 | 100% | 0 | 0 | 0 | 35917.31 | -0.13 | 35917.18 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNIDO | Conversion of ODS precision cleaning processes from CFC-113 to aqueous cleaning at Jiaxipera compressor factory | Individual | ASP | CPR | SOL | 22 | INV | 203 | A | I | CFC | 76 | 76 |  |  | 1997-05-01 | 1998-10-01 | 1998-12-01 |  | 1999-05-01 | 2000-04-14 | 308604 | 0 | 308604 | 308604 | 100% | 0 | 0 |  | 40119 | 0 | 40119 | 0 | 0 | FIN
FIN | UNIDO | Conversion of ODS cleaning processes from CFC-113 to trichloroethylene at Hangli Refrigeration Ltd. | Individual | ASP | CPR | SOL | 22 | INV | 212 | A | I | CFC | 28.8 | 28.8 |  |  | 1997-05-01 | 1998-06-01 | 1998-12-01 |  | 1999-12-01 | 2001-03-01 | 217762 | 0 | 217762 | 217762 | 100% | 0 | 0 |  | 28309 | -8 | 28301 | 0 | 0 | FIN
FIN | UNIDO | Conversion of ODS precision cleaning processes from CFC-113 to aqueous cleaning at Huangshi Dongbei Refrigeration Co. | Individual | ASP | CPR | SOL | 22 | INV | 213 | A | I | CFC | 37.6 | 37.6 |  |  | 1997-05-01 | 1998-09-01 | 1998-12-01 |  | 1998-12-01 | 1999-07-01 | 236242 | 0 | 236242 | 236242 | 100% | 0 | 0 |  | 30711 | 0 | 30711 | 0 | 0 | FIN
FIN | UNDP | Elimination of CFC-113 used in the production line at Shanghai Computer Factory | Individual | ASP | CPR | SOL | 22 | INV | 216 | N | I | CFC | 6.3 | 6.3 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1999-06-01 |  | 1999-11-01 | 2003-08-01 | 116767 | -1 | 116766 | 116766 | 100% | 0 | 0 | 0 | 15179.71 | -0.13 | 15179.58 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Elimination of ODS (CFC-113) used in the production line at Fujian Putian Vikay Electronics Co. Ltd. | Individual | ASP | CPR | SOL | 23 | INV | 224 | N | I | CFC | 56 | 56 | 0 | 0 | 1997-11-01 | 2000-06-01 | 1999-12-01 |  | 2002-11-01 | 2008-10-01 | 619780 | -2356 | 617424 | 617424 | 100% | 0 | 0 | 0 | 80571.4 | -306.28 | 80265.1215 | -0.0015 | 0 | Completed in 2002. Financially completed in 2008. |  | 1997 |  | Investment
FIN | UNDP | Elimination of ODS used in the production lines at Irico (Caihong) Color Picture Tube Factory | Individual | ASP | CPR | SOL | 28 | INV | 287 | N | I | TCA/CFC | 202 | 202 | 0 | 0 | 1999-07-01 | 2000-05-01 | 2003-08-01 |  | 2002-10-01 | 2004-06-01 | 2853200 | -38805 | 2814395 | 2814395 | 100% | 0 | 0 | 0 | 323852 | -4405.37 | 319446.6325 | -0.0025 | 0 | Completed in 2002. Financially completed in 2004. |  | 1999 |  | Investment
FIN | Japan | Project preparation assistance for enterprises in the city of Shenzhen for the elimination of CFC-113 and TCA in the production lines of LC display and TV picture tube | Individual | ASP | CPR | SOL | 29 | PRP | 307 | A | I | CFC-113andCTA | 0 |  | 0 |  | 1999-11-01 | 2000-06-01 | 2000-12-01 |  | 2002-12-01 | 2003-07-01 | 50000 | -30916 | 19084 | 19084 | 100% | 0 |  | 0 | 6500 | -4019 | 2481 | 0 | 0 | Completed. Project proposal prepared but activities incorporated into China Solvent Sector Plan |  | 1999
FIN | France | Project preparation of phase out of use of ODS solvent in production of parts working in high voltage conditions |  | ASP | CPR | SOL | 29 | PRP | 327 | A | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-07-01 | 2000-12-01 |  | 2002-09-01 | 2002-09-01 | 27500 | 0 | 27500 | 27500 | 100% | 0 |  | 0 | 1375 | 0 | 1375 | 0 |  | Project completed.
FIN | UNDP | ODS phaseout in China solvent sector: 2000 annual programme | Multi-Year | ASP | CPR | SOL | 30 | INV | 355 | N | I | TCA/CTC/CFC | 382.8 | 382.8 | 0 | 0 | 2000-03-01 | 2000-12-01 | 2001-03-01 |  | 2003-05-01 | 2013-02-01 | 6750000 | 0 | 6750000 | 6750000 | 100% | 0 | 0 | 0 | 675000 | 0 | 675000 | 0 | 0 | Financially completed in 2013. |  | 2000 |  | Investment
FIN | UNDP | ODS phaseout in China solvent sector: 2000-2001 annual programme | Multi-Year | ASP | CPR | SOL | 33 | INV | 373 | N | I | TCA/CTC/CFC | 534 | 534 | 0 | 0 | 2001-03-01 | 2003-03-01 | 2002-03-01 |  | 2005-01-01 | 2013-09-01 | 6955000 | 0 | 6955000 | 6955000 | 100% | 0 | 0 | 0 | 695500 | 0 | 695500 | 0 | 0 | Financially completed in 2013. |  | 2001 | 2003-09-01 | Investment
FIN | UNDP | ODS phase-out in China solvent sector: 2002 annual programme | Multi-Year | ASP | CPR | SOL | 36 | INV | 390 | N | I | TCA/CTC/CFC | 580 | 580 | 0 | 0 | 2002-03-01 | 2005-01-01 | 2003-03-01 |  | 2005-09-01 | 2013-12-01 | 6330000 | 0 | 6330000 | 6330000 | 100% | 0 | 0 | 0 | 633000 | 0 | 633000 | 0 | 0 | Financially completed in 2013. |  | 2002 | 2004-06-01 | Investment
FIN | UNDP | ODS phase-out in China solvent sector: 2003 annual programme | Multi-Year | ASP | CPR | SOL | 40 | INV | 403 | N | I | CFC/TCA/CTC | 580 | 580 | 0 | 0 | 2003-07-01 | 2005-01-01 | 2004-03-01 |  | 2005-12-01 | 2013-03-01 | 5755000 | 0 | 5755000 | 5755000 | 100% | 0 | 0 | 0 | 431625 | 0 | 431625 | 0 | 0 | Financially completed in 2013. |  | 2003 | 2005-06-01 | Investment
FIN | UNDP | ODS phase-out in China solvent sector: 2004 annual programme | Multi-Year | ASP | CPR | SOL | 42 | INV | 410 | N | I | CFC | 733 | 733 | 0 | 0 | 2004-04-01 | 2006-01-01 | 2005-04-01 |  | 2006-12-01 | 2013-07-01 | 5555000 | 0 | 5555000 | 5555000 | 100% | 0 | 0 | 0 | 416625 | 0 | 416625 | 0 | 0 | Financially completed in 2013. |  | 2004 |  | Investment
FIN | UNDP | ODS phase-out in China solvent sector: 2005 annual programme | Multi-Year | ASP | CPR | SOL | 45 | INV | 429 | N | I | TCA/CTC | 635 | 635 | 0 | 0 | 2005-04-01 | 2007-02-01 | 2006-04-01 |  | 2009-12-01 | 2013-08-01 | 5680000 | 0 | 5680000 | 5680000 | 100% | 0 | 0 | 0 | 426000 | 0 | 426000 | 0 | 0 | Financially completed in 2013. |  | 2005 |  | Investment
FIN | UNDP | ODS phase-out in China solvent sector: 2006 annual programme | Multi-Year | ASP | CPR | SOL | 47 | INV | 435 | N | I | TCA/CTC | 85 | 85 | 0 | 0 | 2005-11-01 | 2009-05-01 | 2006-12-01 |  | 2009-12-01 | 2013-02-01 | 5055000 | 0 | 5055000 | 5055000 | 100% | 0 | 0 | 0 | 379125 | 0 | 379125 | 0 | 0 | Financially completed in 2013. |  | 2005 |  | Investment
FIN | UNDP | ODS phase-out in China solvent sector: 2007 annual programme | Multi-Year | ASP | CPR | SOL | 50 | INV | 446 | N | I | TCA/CTC | 85 | 85 | 0 | 0 | 2006-11-01 | 2009-05-01 | 2008-12-01 |  | 2009-12-01 | 2013-08-01 | 5480000 | 0 | 5480000 | 5480000 | 100% | 0 | 0 | 0 | 411000 | 0 | 411000 | 0 | 0 | Financially completed in 2013. |  | 2006 |  | Investment
FIN | UNDP | ODS phase-out in China solvent sector: 2008 annual programme | Multi-Year | ASP | CPR | SOL | 53 | INV | 457 | N | I | TCA | 85 | 85 | 0 | 0 | 2007-11-01 | 2009-10-01 | 2009-11-01 |  | 2009-12-01 | 2013-09-01 | 1480000 | 0 | 1480000 | 1480000 | 100% | 0 | 0 | 0 | 111000 | 0 | 111000 | 0 | 0 | Financially completed in 2013. |  | 2007 |  | Investment
FIN | UNDP | ODS phase-out in China solvent sector: 2009 annual programme | Multi-Year | ASP | CPR | SOL | 56 | INV | 479 | N | I | TCA | 84 | 84 | 0 | 0 | 2008-11-01 | 2009-10-01 | 2009-11-01 |  | 2009-12-01 | 2013-03-01 | 1480000 | 0 | 1480000 | 1480000 | 100% | 0 | 0 | 0 | 111000 | 0 | 111000 | 0 | 0 | Financially completed in 2013. |  | 2008 |  | Investment
FIN | UNDP | ODS phase-out in China solvent sector: 2010 annual programme | Multi-Year | ASP | CPR | SOL | 59 | INV | 495 | N | I | TCA | 85 | 85 | 0 | 0 | 2009-11-01 | 2009-12-01 | 2011-11-01 |  | 2012-12-01 | 2013-08-01 | 1480000 | 0 | 1480000 | 1480000 | 100% | 0 | 0 | 0 | 111000 | 0 | 111000 | 0 | 0 | Financially completed in 2013. |  | 2009 |  | Investment
FIN | UNDP | Preparation of a demonstration project for conversion from HCFC-141b to a combination of isopropyl alcohol and hydrocarbon-based compounds in solvent cleaning applications at Zhejiang KDL Medical Equipment Group Ltd. | Individual | ASP | CPR | SOL | 60 | PRP | 497 | N | I | HCFC | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-08-01 | 2011-04-01 |  | 2012-12-01 | 2013-04-01 | 30000 | -4914.96 | 25085.04 | 25085 | 100% | 0.04 | 0 | 0 | 2250 | -368.62 | 1881.375 | 0.005 | 0 | Financially completed in 2013. | Completed in 2012. | 2010 |  | Investment
ONG | Japan | Demonstration project for conversion from HCFC-141b based technology to iso-paraffin and siloxane (KC-6) technology for cleaning in the manufacture of medical devices at Zhejiang Kindly Medical Devices Co. Ltd. |  | ASP | CPR | SOL | 64 | DEM | 506 | A | I |  | 1.1 |  | 0 |  | 2011-07-01 |  | 2012-09-01 | 2013-12-01 |  |  | 205616 | 0 | 205616 | 0 | 0% | 205616 | 205616 | 205616 | 26730 | 0 |  | 26730 | 26730 | Project activities were completed in 2013 and the demonstration project outputs were shared with delegates during technology conference in June 2013. Detailed report on this project would be provided to the 73rd ExCom. | None. |  |  | Investment
FIN | UNDP | Demonstration project for conversion from HCFC-141b based technology to iso-paraffin and siloxane (KC-6) technology for cleaning in the manufacture of medical devices at Zhejiang Kindly Medical Devices Co. Ltd. | Individual | ASP | CPR | SOL | 64 | DEM | 511 | N | X | HCFC | 2 | 2 | 0 | 0 | 2011-07-01 | 2011-09-01 | 2012-09-01 |  | 2014-12-01 | 2015-12-01 | 352051 | -9 | 352042 | 352042 | 100% | 0 | 0 | 0 | 26404 | -0.68 | 26403.325 | -0.005 | 0 | Financially Completed in 2015. | Project targeted for completion in 2014. | 2011 |  | Non-Investment | 313647
ONG | UNDP | Preparation for HCFC phase-out investment activities (stage II) (solvents sector) | Individual | ASP | CPR | SOL | 73 | PRP | 544 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-11-01 | 2015-04-01 | 2016-11-01 | 2017-05-01 |  |  | 150000 | 0 | 150000 | 138171 | 92.11% | 11829 | 0 | 4731.6 | 10500 | 0 | 9671.97 | 828.03 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Document prepared and submitted in ExCom 77th and got approved. Prodoc signed (actual/planned, yes/no and date):42062 Missions undertaken (actual/planned):1 TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: signed earlier First disbursement date (actual/planned): 42095Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | it is estimated to finish all the disbursement in May,2017 | 2014 |  | Non-Investment
FIN | UNIDO | Phasing out CFCs at Pliva D.D. | Individual | EUR | CRO | ARS | 22 | INV | 05 | A | I | CFC | 10.6 | 10.6 |  |  | 1997-05-01 | 1997-10-01 | 1998-08-01 |  | 2000-10-01 | 2001-12-01 | 89779 | -2344 | 87435 | 87434.5 | 100% | 0.5 | 0 |  | 11671 | -323 | 11348 | 0 | 0 | FIN |  |  | 1999-12-01
TRF | Germany | Project preparation for phasing out ODS use in Pliva Pharmaceuticals | Individual | EUR | CRO | ARS | 36 | PRP | 16 | A | I |  | 0 |  | 0 |  | 2002-03-01 |  | 2003-04-01 |  |  | 2003-04-01 | 16500 | -16500 | 0 |  | #DIV/0! | 0 | 0 | 0 | 2145 | -2145 | 0 | 0 | 0 | Project was offset against Germany contributions at the 39th meeting. Project funds have been transferred to the Croatia Halon project preparation project.
FIN | UNIDO | Project formulation of investment projects in the foam sector | Individual | EUR | CRO | FOA | 21 | PRP | 03 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-04-01 | 1998-02-01 |  | 1999-12-01 | 2001-07-01 | 30000 | -686 | 29314 | 29314 | 100% | 0 | 0 |  | 3900 | -95 | 3805 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Oriolik Co. flexible polyurethane foam plant | Individual | EUR | CRO | FOA | 22 | INV | 04 | A | I | CFC | 25 | 25 |  |  | 1997-05-01 | 1997-08-01 | 1998-06-01 |  | 1998-11-01 | 2000-07-01 | 110780 | -24 | 110756 | 110756 | 100% | 0 | 0 |  | 14401 | -26 | 14375 | 0 | 0 | FIN
FIN | UNIDO | Project preparation for the phase-out of HCFC-141b in polyurethane foam production | Individual | EUR | CRO | FOA | 57 | PRP | 33 | A | I |  | 0 | 0 |  |  | 2009-04-01 | 2009-06-01 | 2010-03-31 |  | 2010-07-01 | 2010-12-01 | 40000 | -14 | 39986 | 39986.25 | 100% | -0.25 | 0 |  | 3000 | -1 | 2999 | 0 | 0 | FIN |  |  |  | NON-INV
CLO | UNIDO | Phase-out of HCFC-141b from the manufacturing of polyurethane rigid foam at Pavusin | Multi-Year | EUR | CRO | FOA | 59 | INV | 34 | A | I | HCFC | 2 | 0 |  |  | 2009-11-01 | 2010-06-01 | 2011-11-30 |  |  | 2012-05-01 | 271150 | -268988 | 2162 | 2162 | 100% | 0 | 0 |  | 20336 | -20174 | 162 | 0 | 0 | CLO |  |  |  | INV
FIN | Italy | Phase-out of HCFC-141b from the manufacturing of polyurethane rigid and integral skin foams at Poly-Mix | Multi-Year | EUR | CRO | FOA | 60 | INV | 35 | A | I | HCFC | 1.8 | 1.8 | 0 |  | 2010-04-01 | 2011-12-01 | 2012-04-01 |  | 2013-12-01 | 2014-12-01 | 210000 | -7455 | 202545 | 202545 | 100% | 0 | 0 | 0 | 27300 | -969 | 26331 | 0 | 0 | Project completed in Dec 2013. All obligations have been cleared and the project was financially completed. | Balances (and interests accrued) have been reported to the 77th ExCom and have been returned in cash in April 2017 in light of ExCom decision 77/2(a)(iii) | 2010 |  | Investment
FIN | UNIDO | Preparation of a demonstration project (tobacco, tomatoes) | Individual | EUR | CRO | FUM | 24 | PRP | 07 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-05-01 | 1999-04-01 |  | 1998-05-01 | 2001-07-01 | 20000 | -1561 | 18439 | 18439 | 100% | 0 | 0 |  | 2600 | -207 | 2393 | 0 | 0 | FIN
FIN | UNIDO | Two alternatives to the use of methyl bromide in tobacco production; namely: solarization plus bio-fumigation, the use of low-dose chemicals, and non-soil cultivation, in combination with an integrated pest management programme | Individual | EUR | CRO | FUM | 25 | DEM | 08 | A | I |  | 0 | 0 |  |  | 1998-07-01 | 1998-09-01 | 2000-08-01 |  | 2001-05-01 | 2003-03-01 | 288200 | -28165 | 260035 | 260034.82 | 100% | 0.18 | 0 |  | 37466 | -3715 | 33751 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the tobacco fumigation sector | Individual | EUR | CRO | FUM | 33 | PRP | 13 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-11-01 | 2002-04-01 |  | 2001-12-01 | 2002-12-01 | 30000 | -16341 | 13659 | 13658.86 | 100% | 0.14 | 0 |  | 3900 | -2127 | 1773 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase out of methyl bromide in tobacco seedlings | Individual | EUR | CRO | FUM | 35 | INV | 14 | A | I | MBR | 16.2 | 16.2 |  |  | 2001-12-01 | 2002-07-01 | 2007-01-01 |  | 2006-12-01 | 2007-12-01 | 476833 | -5789 | 471044 | 471044.2 | 100% | -0.2 | 0 |  | 61988 | -752 | 61236 | 0 | 0 | FIN |  |  |  | INV
FIN | Germany | Project preparation/technical assistance for the halon sector | Individual | EUR | CRO | HAL | 39 | PRP | 19 | A | I |  | 0 |  | 0 |  | 2003-04-01 | 2003-12-01 | 2004-04-01 |  | 2004-07-01 | 2004-07-01 | 16500 | 0 | 16500 | 16500 | 100% | 0 | 0 | 0 | 2145 | 0 | 2145 | 0 | 0 | Project preparation lead to project approval at 43rd Excom
FIN | Germany | Sectoral phase-out programme: establishment of a halon bank | Individual | EUR | CRO | HAL | 43 | TAS | 24 | A | I | HAL | 30.1 | 30.1 | 0 |  | 2004-07-01 | 2005-01-01 | 2007-07-01 |  | 2008-10-01 | 2008-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Having identified an enterprise, tender for Halonbank equipment has been finalized in december 2007, equipment will be delivered in May 2008. Project completed. PCR was submitted in December 2008.
FIN | UNIDO | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | EUR | CRO | PHA | 39 | INV | 20 | A | I | CFC | 0 | 33 |  |  | 2003-04-01 | 2003-12-01 | 2004-04-01 |  | 2005-04-01 | 2010-04-01 | 184000 | -446 | 183554 | 183554.19 | 100% | -0.19 | 0 |  | 13800 | -33 | 13767 | 0 | 0 | FIN
FIN | Sweden | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | EUR | CRO | PHA | 39 | TAS | 18 | A | I |  | 0 |  | 0 |  | 2003-04-01 | 2003-09-01 | 2004-12-01 |  | 2005-06-01 | 2005-09-01 | 46000 | 0 | 46000 | 46000 | 100% | 0 |  |  | 3450 | 0 | 3450 | 0 | 0 | Annual report submitted and approved at the 42nd ExCom meeting. |  | 2003
FIN | UNIDO | Terminal phase-out management plan: 2004 annual implementation programme | Multi-Year | EUR | CRO | PHA | 42 | TAS | 22 | A | I | CFC | 0 | 0 |  |  | 2004-04-01 | 2005-02-01 | 2005-04-01 |  | 2005-12-01 | 2011-05-01 | 48300 | 0 | 48300 | 48300 | 100% | 0 | 0 |  | 3623 | 0 | 3623 | 0 | 0 | FIN |  |  |  | INV
FIN | Sweden | Terminal phase-out management plan (second tranche) | Multi-Year | EUR | CRO | PHA | 42 | TAS | 23 | A | I |  | 0 |  | 0 |  | 2004-04-01 | 2004-08-01 | 2005-04-01 |  | 2005-12-01 | 2005-12-01 | 24700 | 0 | 24700 | 24700 | 100% | 0 |  |  | 1853 | 0 | 1853 | 0 | 0 | Annual report submitted and approved at the 46th ExCom meeting. |  | 2004
FIN | UNIDO | Terminal CFC phase-out management plan (third tranche) | Multi-Year | EUR | CRO | PHA | 46 | TAS | 26 | A | I | CFC | 20 | 20 |  |  | 2005-07-01 | 2005-12-01 | 2006-07-01 |  | 2007-12-01 | 2011-05-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 |  | 2625 | 0 | 2625 | 0 | 0 | FIN |  |  |  | INV
FIN | Sweden | Terminal CFC phase-out management plan (third tranche) | Multi-Year | EUR | CRO | PHA | 46 | TAS | 27 | A | I | CFC | 13 | 13 | 0 |  | 2005-07-01 | 2005-09-01 | 2006-07-01 |  | 2006-06-01 | 2006-06-01 | 21500 | 0 | 21500 | 21500 | 100% | 0 | 0 | 0 | 1613 | 0 | 1613 | 0 | 0 | The assistance to Croatia in the implementation of the TPMP was jointly implemented by UNIDO and Sweden, with UNIDO as the lead implementing agency. During 2004 and 2005, the national ODS regulation (By-law) was revised and adopted. The reclamation equipment was delivered during autumn 2004. A mission took place in March 2005. The IC participated in the training of the reclamation facilities in October 2005. The SEI and the IC met with UNIDO in Vienna in September 2005 to discuss some outstanding issues. In March 2006 SEI received the final report from the national consultant/PMU. The project was completed in June 2006. |  | 2005
FIN | UNIDO | Terminal CFC phase-out management plan (4th tranche) | Multi-Year | EUR | CRO | PHA | 49 | TAS | 29 | A | I | CFC | 65 | 65 |  |  | 2006-07-01 | 2008-02-01 | 2008-12-01 |  | 2008-12-01 | 2011-12-01 | 20200 | -2100 | 18100 | 18100 | 100% | 0 | 0 |  | 1515 | -157 | 1358 | 0 | -1 | FIN |  |  |  | INV
FIN | UNIDO | Monitoring and verification audit report | Individual | EUR | CRO | PHA | 52 | TAS | 30 | A | I |  | 0 | 0 |  |  | 2007-07-01 | 2007-12-01 | 2008-01-31 |  | 2008-09-01 | 2009-09-01 | 20000 | -3296 | 16704 | 16703.54 | 100% | 0.46 | 0 |  | 1800 | -297 | 1503 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | EUR | CRO | PHA | 55 | PRP | 31 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-11-01 | 2009-07-31 |  | 2011-06-01 | 2011-12-01 | 150000 | -456 | 149544 | 149543.63 | 100% | 0.37 | 0 |  | 11250 | -34 | 11216 | 0 | 0 | FIN |  |  |  | NON-INV
COM | UNIDO | HCFC phase-out management plan (phase I, first tranche) | Multi-Year | EUR | CRO | PHA | 61 | INV | 36 | A | I |  | 0 | 0 |  |  | 2010-07-01 | 2010-12-01 | 2014-12-31 |  | 2015-12-01 | 2016-05-01 | 180000 | 0 | 180000 | 179466.94 | 99.7% | 533.06 | 0 | 1 | 13500 | 0 | 13460 | 40 | 0 | The project was operationally completed. |  |  |  | INV
COM | UNIDO | HCFC phase-out management plan (stage I, second and third tranches) | Multi-Year | EUR | CRO | PHA | 66 | INV | 38 | A | I | HCFC | 4.3 | 4.3 |  |  | 2012-04-01 | 2013-01-01 | 2013-07-31 |  | 2015-12-01 | 2016-08-01 | 360000 | 0 | 360000 | 359930.39 | 99.98% | 69.61 | 0 | 1 | 27000 | 0 | 26995 | 5 | 0 | The project was operationally completed. |  |  |  | INV
FIN | UNIDO | HCFC phase-out management plan (fourth tranche) | Multi-Year | EUR | CRO | PHA | 71 | INV | 40 | A | I |  | 0 | 0 |  |  | 2013-12-01 | 2015-12-01 | 2014-12-31 |  | 2015-12-01 | 2016-03-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 4500 | 0 | 4500 | 0 | 0 | - The project was financially completed and the balance was returned at the 76th ExCom. |  |  |  | INV
FIN | UNIDO | Preparation of a refrigerant management plan | Individual | EUR | CRO | REF | 24 | PRP | 06 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-09-01 | 1999-04-01 |  | 1999-02-01 | 1999-09-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: national recovery and recycling project | RMP | EUR | CRO | REF | 28 | TAS | 10 | A | I | CFC | 15 | 15 |  |  | 1999-07-01 | 2000-01-01 | 2001-08-01 |  | 2001-12-01 | 2003-10-01 | 289910 | -3739 | 286171 | 286171.08 | 100% | -0.08 | 0 |  | 37688 | -545 | 37143 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: phase I: training of trainers in good refrigerant management practices; phase II: national technicians training | RMP | EUR | CRO | REF | 28 | TRA | 09 | A | I | CFC | 0 | 0 |  |  | 1999-07-01 | 1999-10-01 | 2001-08-01 |  | 2003-02-01 | 2003-07-01 | 70000 | -1483 | 68517 | 68517 | 100% | 0 | 0 |  | 9100 | -207 | 8893 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: customs training | RMP | EUR | CRO | REF | 28 | TRA | 12 | A | I |  | 0 | 0 |  |  | 1999-07-01 | 2001-04-01 | 2001-08-01 |  | 2002-06-01 | 2003-07-01 | 38250 | -2227 | 36023 | 36022.65 | 100% | 0.35 | 0 |  | 4973 | -297 | 4676 | 0 | 0 | FIN
FIN | Sweden | Assistance to prepare an RMP update | Individual | EUR | CRO | REF | 36 | PRP | 15 | A | I |  | 0 |  | 0 |  | 2002-03-01 | 2002-11-01 | 2003-04-01 |  | 2004-03-01 | 2004-04-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 |  |  | 1950 | 0 | 1950 | 0 | 0 | At the 36th meeting in March 2002 Sweden received approval for assisting the Government of Croatia in updating their Refrigerant Management Plan (RMP Update). International and National consultants were contracted in June 2002. A survey of current ODS consumption and use in the servicing sector were conducted followed by a desk study and sector review. Due to ExCom decision regarding Terminal Phase-out Management Plans (TPMP) the Update was submitted in January 2003 as a TPMP, with Sweden as co-implementing agency and UNIDO as lead Implementing Agency, and approved at the 39th ExCom meeting. |  | 2002
FIN | UNEP | Country programme preparation | Individual | EUR | CRO | SEV | 16 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-04-01 | 1996-06-01 |  | 1996-06-01 | 1997-05-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNEP | Establishment of a National Ozone Office | Individual | EUR | CRO | SEV | 20 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-05-01 | 1999-10-01 |  | 2000-03-01 | 2001-03-01 | 101200 | 0 | 101200 | 101200 | 100% | 0 | 0 |  | 13156 | 0 | 13156 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | EUR | CRO | SEV | 29 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-03-01 | 2001-12-01 |  | 2002-03-01 | 2003-06-01 | 67000 | 0 | 67000 | 67000 | 100% | 0 | 0 |  | 8710 | 0 | 8710 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening projects (phase III) | Individual | EUR | CRO | SEV | 36 | INS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-06-01 | 2004-04-01 |  | 2004-12-01 | 2007-05-01 | 87900 | 0 | 87900 | 87900 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project | Individual | EUR | CRO | SEV | 41 | INS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-11-01 | 2005-12-01 |  | 2006-12-01 | 2008-05-01 | 87707 | 0 | 87707 | 87707 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase V) | Individual | EUR | CRO | SEV | 47 | INS | 28 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-12-01 | 2008-04-01 |  | 2008-11-01 | 2009-11-01 | 87707 | 0 | 87707 | 87707 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase VI) | Individual | EUR | CRO | SEV | 56 | INS | 32 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-04-01 | 2011-01-01 |  | 2011-07-01 | 2012-07-01 | 87707 | 0 | 87707 | 87707 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase VII) | Individual | EUR | CRO | SEV | 63 | INS | 37 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2012-04-01 | 2013-03-01 |  | 2014-12-01 | 2016-12-01 | 87707 | 0 | 87707 | 87707 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
COM | UNEP | Extension of institutional strengthening project (phase VIII: 4/2013-3/2015) | Individual | EUR | CRO | SEV | 69 | INS | 39 | A | I |  | 0 |  | 0 |  | 2013-04-01 | 2014-04-01 | 2015-03-01 |  | 2016-05-01 |  | 87707 | 0 | 87707 | 87707 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Adoption of the Act on Implementing Regulation (EU) No 517/2014 of the European Parliament and of the Countcil on Fluorinated Greenhouse Gases of 16 April 2014 and repealing Regulation (EC) No 842/2006 (F-gas Regulation), monitoring trade in ODS and F-gases through the licensing system and quota, quota allocation and iPIC, information brochures for service technians, awareness raising materials including costumes for performances, a floor game for kids, T-shirts, Ozzy Ozone comics and an ozone website, participation in ECA customs cooperation and network meeting in Ashgabat, 24-27 May 2016 as well as Montreal Protocol meetings, coordination and reporting on Montreal Protocol projects (HPMP, ODS alternatives survey) and the purchase of IT equipment. Croatia's IS project has been completed in May 2016. Legal arrangements(actual/planned): SSFA with the Ministry of Environmental and Nature Protection signed in January 2014 and amended in November 2015 to extend validity to May 2016. Initial stages of project implementation (actual/planned): N.a. Intermediate goals achieved (actual/planned): N.a. Project completion and follow up: May 2016 First disbursement date (actual/planned): March 2014 All funds disbursed (yes/no): No - final payment under the SSFA not be released because the amended SSFA expired in May 2016. Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: Slow disbursement and parliamentary elections took place in 2016 in Croatia resulting in delayed activities . If Yes, will delay have impact on project completion date (yes/no): Yes Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N.a. | Project completed.
FIN | UNIDO | Training and awareness workshop in the solvents (CTC) sector | Individual | EUR | CRO | SOL | 45 | TAS | 25 | A | I | CTC | 2.3 | 2.3 |  |  | 2005-04-01 | 2005-09-01 | 2006-04-01 |  | 2006-12-01 | 2007-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 3600 | 0 | 3600 | 0 | 0 | FIN |  |  |  | INV
FIN | UNDP | Project preparation in the aerosol sector | Individual | LAC | CUB | ARS | 22 | PRP | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-04-01 | 2000-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Project preparation in the aerosol sector | Individual | LAC | CUB | ARS | 33 | PRP | 16 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Phaseout of CFC-12 in the manufacture of insecticides and technical aerosols by conversion to hydrocarbon propellant at CIDT aerosol plant | Individual | LAC | CUB | ARS | 34 | INV | 18 | A | I | CFC | 28.2 | 28.2 | 0 | 0 | 2001-07-01 | 2002-10-01 | 2003-05-01 |  | 2006-12-01 | 2008-04-01 | 124220 | 0 | 124220 | 124220 | 100% | 0 | 0 | 0 | 16148.6 | 0 | 16148.6 | 0 | 0 | Completed in 2006. Financially completed in 2008. |  | 2001 |  | Investment
FIN | UNDP | Project preparation in the MDI sector | Individual | LAC | CUB | ARS | 36 | PRP | 20 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-07-01 | 2004-04-01 |  | 2004-06-01 | 2005-12-01 | 30000 | 20000 | 50000 | 50000 | 100% | 0 | 0 | 0 | 3900 | 1500 | 5400 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Development of MDI transition strategies | Individual | LAC | CUB | ARS | 36 | TAS | 19 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-07-01 | 2003-04-01 |  | 2004-03-01 | 2008-08-01 | 30000 | -5998 | 24002 | 24002 | 100% | 0 | 0 | 0 | 3900 | -779.74 | 3120.26 | 0 | 0 | Completed in 2004. Financially completed in 2008. |  | 2002 |  | Non-Investment
FIN | UNDP | Phase-out of CFC consumption in the manufacture of aerosol metered dose inhalers (MDIs) | Individual | LAC | CUB | ARS | 41 | INV | 23 | N | I | CFC | 109.1 | 109.1 | 0 | 0 | 2003-12-01 | 2004-09-01 | 2006-09-01 |  | 2011-12-01 | 2014-05-01 | 5960000 | -373 | 5959627 | 5959627 | 100% | 0 | 0 | 0 | 447000 | -27.98 | 446972.02 | 0 | 0 | Financially completed in 2014. | One year stability test will be done in April 2012. Final registration will take place after that, if tests are successful. | 2003 | 2008-03-01 | Investment
FIN | UNDP | Preparation for pilot demonstration project on ODS waste management and disposal | Individual | LAC | CUB | DES | 59 | PRP | 45 | N | I | ODS-Waste | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-03-01 | 2010-11-01 |  | 2010-11-01 | 2012-04-01 | 40000 | -1261.09 | 38738.91 | 38739 | 100% | -0.09 | 0 | 0 | 3000 | -94.58 | 2905.4251 | -0.00505 | 0 | Financially completed in 2012. | Financially completed in 2012. | 2009 |  | Investment
COM | UNDP | Pilot demonstration project on ODS waste management and disposal | Individual | LAC | CUB | DES | 62 | DEM | 46 | N | I | No_ODP | 45.3 | 45.3 | 0 | 0 | 2010-12-01 | 2011-09-01 | 2013-12-01 |  | 2015-10-01 |  | 525200 | 0 | 525200 | 519268.05 | 98.87% | 5931.95 | 0 | 5042.1575 | 39390 | 0 | 38945.1038 | 444.8962 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2015. |  | 2010 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | LAC | CUB | FOA | 57 | PRP | 41 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-04-01 | 2010-03-01 |  | 2013-05-01 | 2014-02-01 | 50000 | -487 | 49513 | 49513 | 100% | 0 | 0 | 0 | 3750 | -36.53 | 3713.47 | 0 | 0 | Financially Completed in 2014. | Project completed in 2013. | 2009 |  | Investment
FIN | UNIDO | Preparation of a phase out project (tobacco) | Individual | LAC | CUB | FUM | 24 | PRP | 08 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-05-01 | 1999-04-01 |  | 1999-01-01 | 2001-07-01 | 20000 | -1561 | 18439 | 18439 | 100% | 0 | 0 |  | 2600 | -207 | 2393 | 0 | 0 | FIN
FIN | UNIDO | Phasing out methyl bromide in the tobacco sector | Individual | LAC | CUB | FUM | 26 | INV | 11 | A | I | MBR | 48 | 48 |  |  | 1998-11-01 | 1999-03-01 | 2002-12-01 |  | 2001-12-01 | 2003-12-01 | 1673324 | -294 | 1673030 | 1673030.39 | 100% | -0.39 | 0 |  | 194066 | -324 | 193742 | 0 | 0 | FIN
FIN | UNIDO | Project preparation to eliminate methyl bromide consumption (horticulture) | Individual | LAC | CUB | FUM | 43 | PRP | 24 | A | I |  | 0 | 0 |  |  | 2004-07-01 | 2004-10-01 | 2005-07-01 |  | 2005-07-01 | 2006-09-01 | 30000 | -1068 | 28932 | 28931.73 | 100% | 0.27 | 0 |  | 2250 | -80 | 2170 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Total phase-out of methyl bromide in soil, substrate, storage and structure fumigation | Individual | LAC | CUB | FUM | 44 | INV | 29 | A | I | MBR | 24.1 | 24.1 |  |  | 2004-12-01 | 2005-07-01 | 2008-12-01 |  | 2009-12-01 | 2012-12-01 | 537763 | -3543 | 534220 | 534220.49 | 100% | -0.49 | 0 |  | 40332 | -265 | 40067 | 0 | 0 | FIN |  |  |  | INV
FIN | Germany | Preparation of a CFC phase out management plan | Individual | LAC | CUB | PHA | 37 | PRP | 21 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2002-12-01 | 2003-08-01 |  | 2004-07-01 | 2004-07-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Project preparation lead to project approval at 43rd Excom
TRF | Germany | National CFC phase-out management plan: phase-out of ODS in the refrigeration and air-conditioning sector (first tranche) | Multi-Year | LAC | CUB | PHA | 43 | TAS | 25 | A | I | CFC | 0 |  | 0 |  | 2004-07-01 | 2004-10-01 | 2005-07-01 |  |  | 2006-04-01 | 120000 | -76547 | 43453 | 43453 | 100% | 0 | 0 | 0 | 15600 | -9951 | 5649 | 0 | 0 | Technicians studied retrofit systems and potentials and prepared a syllabus on emission reduction; conversion of one cold room to R409; Preparation to retrofit 15 commercial refrigeration systems; development and printing of 1000 retrofit manuals and emis
FIN | Canada | National CFC phase-out management plan: phase-out of ODS in the refrigeration and air-conditioning sector (first tranche) | Multi-Year | LAC | CUB | PHA | 43 | TAS | 26 | A | I |  | 0 |  | 0 |  | 2004-07-01 | 2005-01-01 | 2005-07-01 |  | 2008-01-01 | 2008-01-01 | 400000 | 0 | 400000 | 400000 | 100% | 0 |  | 0 | 52000 | 0 | 52000 | 0 |  | First phase of R&R equipment shipped in May 2005. Public awareness activities initiated in 2005 are continuing and include the production of technical pamphlets, videos, TV commercials, education workshops etc.. 2nd phase of R&R equipment and retrofit tools delivered in November 2007. 3rd phase completed in January 2008. Note that target and consumption indicated under columns BB and BC are for 2005. |  | 2004 |  | Investment
TRF | France | National CFC phase-out management plan: phase-out of ODS in the refrigeration and air-conditioning sector (first tranche) | Multi-Year | LAC | CUB | PHA | 43 | TAS | 27 | A | I | CFC | 0 |  | 0 |  | 2004-07-01 | 2004-10-01 | 2005-07-01 |  |  | 2006-06-01 | 200000 | -119681 | 80319 | 80319 | 100% | 0 |  | 0 | 26000 | -15559 | 10441 | 0 |  | The French contribution was implemented by GTZ-Proklima. Upon Cuba's request, the project remaining budget and activities was transferred to UNDP in Apr 06.
TRF | Germany | National ODS phase-out plan for CFCs: 2005 annual implementation plan | Multi-Year | LAC | CUB | PHA | 45 | INV | 30 | A | I | CFC | 0 |  | 0 |  | 2005-04-01 |  | 2006-04-01 |  |  | 2006-04-01 | 116000 | -116000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 15080 | -15080 | 0 | 0 | 0 | see remarks under MLF No. CUB/PHA/43/TAS/25. Transfer to UNDP completed.
TRF | France | National ODS phase-out plan for CFCs: 2005 annual implementation plan | Multi-Year | LAC | CUB | PHA | 45 | INV | 31 | A | I | CFC | 0 |  | 0 |  | 2005-04-01 |  | 2006-04-01 |  |  | 2006-06-01 | 200000 | -200000 | 0 | 0 |  | 0 |  | 0 | 26000 | -26000 | 0 | 0 |  | The French contribution was implemented by GTZ-Proklima. Upon Cuba's request, the project was transferred to UNDP in Apr 06.
FIN | Canada | National ODS phase-out plan for CFCs: 2005 annual implementation plan | Multi-Year | LAC | CUB | PHA | 45 | INV | 32 | A | I | CFC | 30 | 30 | 0 |  | 2005-04-01 | 2008-01-01 | 2007-04-01 |  | 2011-06-01 | 2012-05-01 | 62000 | 0 | 62000 | 62000 | 100% | 0 |  | 0 | 8060 | 0 | 8060 | 0 |  | Project completed in June 2011 but Canada was awaiting final financial report from Cuba. Funds spent principally on R&R training and provision of tools and materiasl for technicians. Final financial report received in May 2012. |  | 2005 |  | Investment
FIN | UNDP | National ODS phase-out plan for CFCs: 2005 annual implementation plan - UNDP Portion | Multi-Year | LAC | CUB | PHA | 45 | INV | 33 | N | I | CFC | 30 | 30 | 0 | 0 | 2005-04-01 | 2007-07-01 | 2006-04-01 |  | 2007-12-01 | 2013-08-01 | 250000 | 0 | 250000 | 250000 | 100% | 0 | 0 | 0 | 18750 | 0 | 18750 | 0 | 0 | Financially completed in 2013. |  | 2005 |  | Investment
FIN | UNDP | National ODS phase-out plan for CFCs: balance of the 2004 and 2005 annual programmes (France and Germany) | Multi-Year | LAC | CUB | PHA | 48 | INV | 37 | N | I | CFC | 79.7 | 79.7 | 0 | 0 | 2006-04-01 | 2008-02-01 | 2007-04-01 |  | 2009-07-01 | 2013-12-01 | 512228 | 0 | 512228 | 512228 | 100% | 0 | 0 | 0 | 38417 | 0 | 38417 | 0 | 0 | Financially completed in 2013. |  | 2006 |  | Investment
FIN | UNDP | National ODS phase-out plan for CFCs: 2006 and 2007 annual implementation plans | Multi-Year | LAC | CUB | PHA | 53 | INV | 39 | N | I | CFC | 166.2 | 166.2 | 0 | 0 | 2007-11-01 | 2009-10-01 | 2009-11-01 |  | 2010-12-01 | 2013-07-01 | 641000 | 0 | 641000 | 641000 | 100% | 0 | 0 | 0 | 48075 | 0 | 48075 | 0 | 0 | Financially completed in 2013. |  | 2007 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | CUB | PHA | 56 | PRP | 40 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-11-01 | 2011-04-01 | 2009-11-01 |  | 2012-12-01 | 2014-04-01 | 150000 | -1 | 149999 | 149999 | 100% | 0 | 0 | 0 | 11250 | -0.08 | 11249.92 | 0 | 0 | Financially completed in 2014. | Pending payments have been made. | 2008 |  | Investment
FIN | UNDP | National ODS phase-out plan for CFCs: 2009 and 2010 annual implementation plans | Multi-Year | LAC | CUB | PHA | 59 | INV | 44 | N | I | CFC | 53.8 | 53.8 | 0 | 0 | 2009-11-01 | 2011-04-01 | 2011-12-01 |  | 2013-12-01 | 2014-03-01 | 156000 | -1176.09 | 154823.91 | 154824 | 100% | -0.09 | 0 | 0 | 11700 | -88.21 | 11611.8 | -0.01 | 0 | Financially Completed in 2014. | Project activities completed in 2013. PCR under preparation. | 2009 |  | Investment
FIN | UNDP | HCFC phase-out management plan (stage I, first tranche) (phase-out of HCFC-141b contained in formulated polyols in the foam sector) | Multi-year | LAC | CUB | PHA | 65 | INV | 49 | N | I | HCFC | 13.4 | 13.4 | 0 | 0 | 2011-11-01 | 2013-07-01 | 2016-10-01 |  | 2015-07-01 | 2016-07-01 | 650000 | 0 | 650000 | 650000 | 100% | 0 | 0 | 0 | 48750 | 0 | 48750 | 0 | 0 | Financially completed in 2016. | Pending contract was signed and construction of equipment started, so equipment for both plants are currently under construction. Preparation of plants for conversion was conducted. 1 follow up mission was carried out. | 2011 |  | Investment
FIN | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | LAC | CUB | PHA | 65 | TAS | 48 | N | I | HCFC | 1.7 | 1.7 | 0 | 0 | 2011-11-01 | 2013-05-01 | 2016-10-01 |  | 2014-12-01 | 2015-06-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 7500 | 0 | 7500 | 0 | 0 | Financially Completed in 2015. | As planned, the 2014 workplan and budget was prepared and approved. The process for purchasing equipment for workshops and training facilities launched. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan ( stage I, second tranche) (phase-out of HCFC-141b contained in formulated polyols in the foam sector) | Multi-Year | LAC | CUB | PHA | 68 | INV | 50 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-12-01 | 2015-02-01 | 2014-12-01 | 2017-12-01 |  |  | 537527 | 0 | 537527 | 315238.98 | 58.65% | 222288.02 | 0 | 88915.208 | 40315 | 0 | 23643.2021 | 16671.7979 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Installation of 3 production lines were completed, although some minor problems ocurred most of they were solved satisfactorely. Trials were conducted in a third plan to adopt preblended HC in a third plant. Prodoc signed (actual/planned, yes/no and date):The agreement has been signed earlier. Missions undertaken (actual/planned):0 of 0 TOR for consultants/subcontracts completed (actual/planned): 1 of 1 Contract/PO/MOA agreements signed: 0 of 1 First disbursement date (actual/planned): 42036Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:Lack of alternative for smaller companies. Discussions have been conducted with the international expert and PU suppliers to identify possible alternatives. | Visits to production lines to follow up project implementation. | 2012 |  | Investment
FIN | UNDP | Verification report for stage I of HCFC phase-out management plan | Individual | LAC | CUB | PHA | 71 | TAS | 51 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2013-12-01 | 2014-09-01 | 2016-05-01 |  | 2014-12-01 | 2016-01-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 2700 | 0 | 2700 | 0 | 0 | Financially completed in 2016. | The initial stage of project implementation has begun. The workplan has been prepared. | 2013 |  | Non-Investment
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | CUB | PHA | 73 | INV | 53 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-11-01 | 2015-04-01 | 2017-11-01 | 2017-11-01 |  |  | 162473 | 0 | 162473 | 66872.42 | 41.16% | 95600.58 | 0 | 38240.232 | 12185 | 0 | 5015.236 | 7169.764 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): International training of specialists and engineers from the Technical Advisory Group were don, 6 specialized trainers trained and attended technical congress in Germany and Panama. 5 courses on procedures and criteria for conducting conversion of RAC systems. 25 workshops on GRP conducted, 500 RAC technicians trained. Prodoc signed (actual/planned, yes/no and date):The agreement has been signed earlier. Missions undertaken (actual/planned):0 of 0 TOR for consultants/subcontracts completed (actual/planned): TOR completed earlier. Contract/PO/MOA agreements signed: The agreement has been signed earlier First disbursement date (actual/planned): 42095Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve:N/A | 2017 work plan prepared. | 2014 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, third tranche) | Multi-year | LAC | CUB | PHA | 77 | INV | 56 | N | I | HCFC | 0 | 0 | 0 | 0 | 2016-12-01 |  | 2019-12-01 | 2017-12-01 |  |  | 141527 | 0 | 141527 | 0 | 0% | 141527 | 0 | 56610.8 | 10615 | 0 | 0 | 10615 | 0 | Newly Approved | DoA sent in February 2017. ProDoc is under preparation. | 2016 |  | Investment
FIN | UNDP | Development of an ODS phase out strategy in the refrigeration sector | RMP-Component | LAC | CUB | REF | 13 | TAS | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-09-01 | 1995-07-01 |  | 1997-09-01 | 1998-12-01 | 30000 | -10000 | 20000 | 20000 | 100% | 0 | 0 | 0 | 3900 | -1300 | 2600 | 0 | 0 | Completed in 1997. Financially completed in 1998. |  | 1994 |  | Non-Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | CUB | REF | 15 | TAS | 04 | A | I | CFC | 49 | 49 | 0 | 0 | 1994-12-01 | 1995-02-01 | 1995-12-01 |  | 1997-09-01 | 1998-12-01 | 169000 | -5167 | 163833 | 163833 | 100% | 0 | 0 | 0 | 21970 | -672 | 21298 | 0 | 0 | Completed in 1997. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Umbrella project for elimination of CFC-11 and CFC-12 in the manufacture of unitary commercial refrigeration equipment at Empco-Mincin and Segere-Sime "Dionisio Rodrigues" | Individual | LAC | CUB | REF | 23 | INV | 06 | A | I | CFC | 3.2 | 3.2 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2000-06-01 | 2002-03-01 | 119505 | -9086 | 110419 | 110419 | 100% | 0 | 0 | 0 | 15535.65 | -1181.18 | 14354.47 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNIDO | Preparation of an investment project (hospitals) in the commercial refrigeration sector | Individual | LAC | CUB | REF | 24 | PRP | 07 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-06-01 | 1999-04-01 |  | 2000-02-14 | 2001-07-01 | 50000 | -1874 | 48126 | 48126 | 100% | 0 | 0 |  | 6500 | -253 | 6247 | 0 | 0 | FIN |  |  | 1999-04-01
FIN | Canada | Project preparation for development of a refrigerant management plan | Individual | LAC | CUB | REF | 25 | PRP | 09 | A | I |  | 0 |  | 0 |  | 1998-07-01 | 1999-06-01 | 1999-01-01 |  | 1999-09-01 | 2000-09-01 | 22600 | 0 | 22600 | 22600 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Although previous reports indicated all funds had been disbursed in 2002, US $2,600 were found to be left-over and were returned to the MLF. See letter to Sectretariat. |  | 1998 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: implementation and enforcement of regulations on ODSs | RMP | LAC | CUB | REF | 29 | TAS | 14 | A | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-03-01 | 2001-12-01 |  | 2004-11-01 | 2004-11-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 |  | 0 | 2600 | 0 | 2600 | 0 |  | Policy workshop held May 2002. ODS regulations updated. Project errouneously reported as completed in 2003. Completion officially reported by Cuba in 2004 |  | 1999 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: training of technicians in good refrigeration practice | RMP | LAC | CUB | REF | 29 | TRA | 12 | A | I |  | 0 |  | 0 |  | 1999-11-01 | 2000-11-01 | 2001-12-01 |  | 2004-11-01 | 2004-11-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 |  | 0 | 10400 | 0 | 10400 | 0 |  | 2650 technicians trained. |  | 1999 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: training programme for customs officers | RMP | LAC | CUB | REF | 29 | TRA | 13 | A | I |  | 0 |  | 0 |  | 1999-11-01 | 2000-11-01 | 2001-12-01 |  | 2004-11-01 | 2004-11-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 |  | 0 | 7150 | 0 | 7150 | 0 |  | 667 customs officers trained. ODS Import database system established. |  | 1999 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: recovery and recycling of CFC-12 in the MAC sector (amendment to the RMP) | RMP | LAC | CUB | REF | 30 | TAS | 15 | A | I | CFC | 8 |  | 0 |  | 2000-03-01 | 2001-11-01 | 2002-04-01 |  | 2004-11-01 | 2004-11-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project erroneously reported as completed in 2003. Additional (final) training took place in 2004. Insufficient data to determine ODP phase-out. However, RMP as a whole is deemed to have contributed to a reduction in the servicing sector of about 90 ODP |  | 2000 |  | Non-Inv.
TRF | Canada | Demonstration project for integrated management of the centrifugal chiller sub-sector, focusing on application of energy-efficient CFC-free technologies for replacement of CFC-based chillers | Individual | LAC | CUB | REF | 47 | DEM | 35 | A | I |  | 0 |  | 0 |  | 2005-11-01 |  | 2008-12-01 |  |  | 2007-03-01 | 196871 | -196871 | 0 | 0 |  | 0 |  | 0 | 25593 | -25593 | 0 | 0 |  | Project was transferred to UNDP at ExCom 51 (March 2007). Therefore there is no planned date of completion. Progress report for 2007 will show adjustment of funding approved. |  | 2005 |  | Non-Inv.
FIN | UNDP | Demonstration project for integrated management of the centrifugal chiller sub-sector, focusing on application of energy-efficient CFC-free technologies for replacement of CFC-based chillers | Individual | LAC | CUB | REF | 47 | DEM | 36 | N | I | CFC | 0 | 0 | 0 | 0 | 2005-11-01 | 2008-01-01 | 2008-12-01 |  | 2010-12-01 | 2014-02-01 | 787482 | 196669.49 | 984151.49 | 984151 | 100% | 0.49 | 0 | 0 | 59061 | 17702.43 | 76763.3918 | 0.03822 | 0 | Financially completed in 2014. |  | 2005 |  | Non-Investment
ONG | UNDP | Preparation for HCFC phase-out investment activities (manufacturing sector) | Individual | LAC | CUB | REF | 58 | PRP | 42 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-07-01 |  | 2010-07-01 | 2017-01-01 |  |  | 50000 | 0 | 50000 | 0 | 0% | 50000 | 0 | 20000 | 3750 | 0 | 0 | 3750 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Discussion had been conducted with the company to evaluate actual alternatives. NOU staff attended a RAC fair to identify possible alternatives. Prodoc signed (actual/planned, yes/no and date):The agreement has been signed earlier. Missions undertaken (actual/planned):0 of 0 TOR for consultants/subcontracts completed (actual/planned): 0 of 0 Contract/PO/MOA agreements signed: 0 of 0 First disbursement date (actual/planned): 42856Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:A suitable alternative for the company has not been agreed yet. Meeting with the NOU and discussion with technology providers were conducted in order to reach a solution. | - | 2009 |  | Investment
FIN | UNDP | Country programme preparation | Individual | LAC | CUB | SEV | 08 | CPG | 01 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1992-11-01 | 1993-10-01 |  | 1993-06-01 | 1997-12-01 | 20000 | -5000 | 15000 | 15000 | 100% | 0 | 0 | 0 | 2600 | -650 | 1950 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Institutional strengthening: Establishment of OTOZ | Individual | LAC | CUB | SEV | 10 | INS | 02 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-10-01 | 1996-06-01 |  | 1998-10-01 | 2000-12-01 | 172000 | -5 | 171995 | 171995 | 100% | 0 | 0 | 0 | 22360 | -1.13 | 22358.87 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1993 |  | Non-Investment
FIN | UNDP | Renewal of the institutional strengthening project | Individual | LAC | CUB | SEV | 26 | INS | 10 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-11-01 | 1998-12-01 | 2000-12-01 |  | 2001-07-01 | 2002-11-01 | 114666 | 0 | 114666 | 114666 | 100% | 0 | 0 | 0 | 14906.58 | 0 | 14906.58 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1998 |  | Non-Investment
FIN | UNDP | Renewal of the institutional strengthening under Montreal Protocol (phase III) | Individual | LAC | CUB | SEV | 34 | INS | 17 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-08-01 | 2003-08-01 |  | 2003-09-01 | 2004-12-01 | 114666 | 0 | 114666 | 114666 | 100% | 0 | 0 | 0 | 14906.58 | 0 | 14906.58 | 0 | 0 | Completed in 2003. Financially completed in 2004. |  | 2001 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase 4) | Individual | LAC | CUB | SEV | 40 | INS | 22 | N | I | No_ODP | 12.3 | 12.3 | 0 | 0 | 2003-07-01 | 2003-10-01 | 2005-07-01 |  | 2006-12-01 | 2008-08-01 | 149066 | 0 | 149066 | 149066 | 100% | 0 | 0 | 0 | 11180 | 0 | 11180 | 0 | 0 | Completed in 2006. Financially completed in 2008. |  | 2003 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase V) | Individual | LAC | CUB | SEV | 47 | INS | 34 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-11-01 | 2007-12-01 |  | 2008-03-01 | 2009-07-01 | 149066 | 0 | 149066 | 149066 | 100% | 0 | 0 | 0 | 11180 | 0 | 11180 | 0 | 0 | Completed in 2008.Financially completed in 2009. |  | 2005 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VI) | Individual | LAC | CUB | SEV | 53 | INS | 38 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-04-01 | 2009-11-01 |  | 2010-03-01 | 2011-05-01 | 149066 | 0 | 149066 | 149066 | 100% | 0 | 0 | 0 | 11180 | 0 | 11180 | 0 | 0 | Completed in 2010. Financially completed in 2011. |  | 2007 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VII) | Individual | LAC | CUB | SEV | 59 | INS | 43 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-03-01 | 2011-12-01 |  | 2012-05-01 | 2013-02-01 | 74533 | 74533 | 149066 | 149066 | 100% | 0 | 0 | 0 | 5590 | 5590 | 11180 | 0 | 0 | Financially completed in 2013. |  | 2009 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase VIII: 1/2012-12/2013) | Individual | LAC | CUB | SEV | 65 | INS | 47 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-09-01 | 2013-12-01 |  | 2014-06-01 | 2015-12-01 | 149066 | -117 | 148949 | 148949 | 100% | 0 | 0 | 0 | 11180 | -8.78 | 11171.225 | -0.005 | 0 | Financially Completed in 2015. | 2014 workplan and budget prepared and approved. | 2011 |  | Non-investment
ONG | UNDP | Extension of institutional strengthening project (phase IX: 1/2014-12/2015) | Individual | LAC | CUB | SEV | 71 | INS | 52 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2013-12-01 | 2014-12-01 | 2015-12-01 | 2017-02-01 |  |  | 149066 | 0 | 149066 | 127445.45 | 85.5% | 21620.55 | 0 | 8648.22 | 10435 | 0 | 8921.5064 | 1513.4936 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Institutional strengthening activities underway. ODS consumption reports prepared and submitted. Celebration of Ozone Day carried out. 2016 HCFC import quota set. NOU attended regional and global meetings. Prodoc signed (actual/planned, yes/no and date):The agreement has been signed earlier. Missions undertaken (actual/planned):0 of 0 TOR for consultants/subcontracts completed (actual/planned): TOR completed earlier. Contract/PO/MOA agreements signed: The agreement has been signed earlier First disbursement date (actual/planned): 41974Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve:N/A | Annual work plan prepared. HCFC import quota set for 2017. | 2013 |  | Non-Investment
ONG | UNDP | Extension of institutional strengthening project (phase X: 1/2016-12/2017) | Individual | LAC | CUB | SEV | 75 | INS | 54 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2015-11-01 |  | 2017-12-01 | 2017-12-01 |  |  | 190804 | 0 | 190804 | 0 | 0% | 190804 | 0 | 76321.6 | 13356 | 0 | 0 | 13356 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Prodoc prepared and discussed with counterparts. Prodoc signed (actual/planned, yes/no and date):No, May 2017. Missions undertaken (actual/planned):0 of 0 TOR for consultants/subcontracts completed (actual/planned): 0 of 0 Contract/PO/MOA agreements signed: 0 of 0 First disbursement date (actual/planned): 42522Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:The project budget has to be included in the National Plan for the Economy, due to internal re-arrengements this process has taken longer than planned. Local CO has been in contact with local authorities to acelerate the adoption of the new plan. | No activities has been conducted. | 2015 |  | Non-Investment
ONG | UNDP | Survey of ODS alternatives at the national level | Individual | LAC | CUB | SEV | 75 | TAS | 55 | N | I | HCFC | 0 | 0 | 0 | 0 | 2015-11-01 | 2016-05-01 | 2016-12-01 | 2017-03-01 |  |  | 70000 | 0 | 70000 | 19880.9 | 28.4% | 50119.1 | 0 | 20047.64 | 6300 | 0 | 1789.281 | 4510.719 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Project team hired. Methodology for conducting the survey was discussed and approved. Prodoc signed (actual/planned, yes/no and date): Missions undertaken (actual/planned):0 of 1 TOR for consultants/subcontracts completed (actual/planned): 1 of 2 Contract/PO/MOA agreements signed: NA First disbursement date (actual/planned): Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:start-up of activities slower than what was originally anticipated. | Survey conducted and draft report prepared. | 2015 |  | Non-Investment
FIN | UNEP | Country programme | Individual | EUR | CYP | SEV | 22 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1997-05-01 |  | 1997-05-01 |  | 1997-05-01 | 1997-05-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 |  | 0
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | AFR | DJI | PHA | 48 | PRP | 10 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-02-01 | 2007-04-01 |  | 2007-11-01 | 2008-12-01 | 12000 | 0 | 12000 | 12000 | 100% | 0 | 0 | 0 | 900 | 0 | 900 | 0 | 0 | Completed in 2007. Financially completed in 2008. |  | 2006 |  | Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | DJI | PHA | 48 | PRP | 11 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-01-01 | 2007-04-01 |  | 2008-03-01 | 2009-12-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 |  | 2340 | 0 | 2340 | 0 | 0
FIN | UNDP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | DJI | PHA | 53 | INV | 13 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 | 2009-10-01 | 2009-11-01 |  | 2009-12-01 | 2013-01-01 | 147000 | -2150.88 | 144849.12 | 144849 | 100% | 0.12 | 0 | 0 | 13230 | -193.58 | 13036.41 | 0.01 | 0 | Financially completed in 2013. |  | 2007 |  | Investment
FIN | UNEP | Terminal phase out management plan for CFCs (first tranche) | Multi-year | AFR | DJI | PHA | 53 | TAS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-01-01 | 2009-03-01 |  | 2012-12-01 | 2013-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | DJI | PHA | 55 | PRP | 14 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-12-01 | 2009-07-01 |  | 2013-05-01 | 2014-05-01 | 30000 | -10747 | 19253 | 19253 | 100% | 0 | 0 |  | 3900 | -1397.11 | 2502.89 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan (additional funding) | RMP | AFR | DJI | PHA | 58 | PRP | 16 | A | I |  | 0 | 0 | 0 |  | 2009-07-01 | 2009-12-01 | 2010-07-01 |  | 2013-12-01 | 2014-12-01 | 55000 | -9987 | 45013 | 45013 | 100% | 0 | 0 |  | 7150 | -1298.31 | 5851.69 | 0 | 0
FIN | UNEP | Terminal phase out management plan for CFCs (second tranche) | Multi-Year | AFR | DJI | PHA | 59 | TAS | 17 | A | I | CFC-12 | 3.2 | 3.2 | 0 | 0 | 2009-11-01 | 2010-07-01 | 2010-11-01 |  | 2013-12-01 | 2014-12-01 | 58000 | 0 | 58000 | 58000 | 100% | 0 | 0 |  | 7540 | 0 | 7540 | 0 | 0
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | AFR | DJI | PHA | 66 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 | 2012-12-01 | 2016-04-01 | 2017-12-01 |  |  | 81000 | 0 | 81000 | 60100 | 74.2% | 20900 | 20900 | 2090 | 10530 | 0 | 7813 | 2717 | 2717 | Brief progress report (actual/planned): Country organized a training workshop for 25 refrigeration technicians in good practices in refrigeration and 22 enforcement officers on ODS identification in 2016. Legal arrangements (actual/planned): Agreement signed in August 2012. All activities under the SSFA are completed (as planned) YES___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in August 2012 __ All funds disbursed (yes/no): _ Final payment being processed in July 2014.__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Brief progress report (actual/planned): Country organized a training workshop for 25 refrigeration technicians in good practices in refrigeration and 22 enforcement officers on ODS identification in 2016. Legal arrangements (actual/planned): Agreement signed in August 2012. All activities under the SSFA are completed (as planned) YES___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in August 2012 __ All funds disbursed (yes/no): _ Final payment being processed in July 2014.__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | AFR | DJI | PHA | 76 | TAS | 23 | A | I |  | 0 |  | 0 |  | 2016-05-01 | 2016-12-01 | 2018-06-01 | 2018-06-01 |  |  | 18500 | 0 | 18500 | 64 | 0.3459% | 18436 | 5100 | 1843.6 | 2405 | 0 | 8.32 | 2396.68 | 663 | Newly approved project | Brief progress report (actual/planned): Newly approved. Legal arrangements (actual/planned): Agreement signed in February 2017. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement _no __ All funds disbursed (yes/no): _ Final payment _no_4.__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
FIN | UNDP | Project preparation in the recovery and recycling refrigeration sector | Individual | AFR | DJI | REF | 36 | PRP | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2003-01-01 | 2005-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Implementation of the RMP: monitoring the activities in the RMP | RMP-Component | AFR | DJI | REF | 37 | TAS | 03 | A | I | CFC | 1.6 | 1.6 | 0 | 0 | 2002-07-01 | 2004-07-01 | 2004-08-01 |  | 2007-12-01 | 2011-04-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2007. Financially completed in 2011. |  | 2002 |  | Investment
FIN | UNDP | Implementation of the RMP: recovery and recycling | RMP-Component | AFR | DJI | REF | 37 | TAS | 07 | A | I | CFC | 8.8 | 8.8 | 0 | 0 | 2002-07-01 | 2004-07-01 | 2004-08-01 |  | 2007-12-01 | 2011-07-01 | 136463 | -685.13 | 135777.87 | 135778 | 100% | -0.13 | 0 | 0 | 17740.19 | -89.07 | 17651.14 | -0.02 | 0 | Completed in 2007. |  | 2002 |  | Investment
FIN | UNEP | Implementation of the RMP: customs training | Individual | AFR | DJI | REF | 37 | TRA | 04 | A | I | CFC | 2.1 | 2.1 | 0 | 0 | 2002-07-01 | 2003-06-01 | 2003-08-01 |  | 2006-12-01 | 2009-06-01 | 33100 | 0 | 33100 | 33100 | 100% | 0 | 0 |  | 4303 | 0 | 4303 | 0 | 0
FIN | UNEP | Implementation of the RMP: training in good practices of refrigeration | Individual | AFR | DJI | REF | 37 | TRA | 05 | A | I | CFC | 4.8 | 4.8 | 0 | 0 | 2002-07-01 | 2004-08-01 | 2003-08-01 |  | 2006-12-01 | 2009-04-01 | 74200 | 0 | 74200 | 74200 | 100% | 0 | 0 |  | 9646 | 0 | 9646 | 0 | 0
FIN | UNEP | Implementation of the RMP: assistance to establish legislation | Individual | AFR | DJI | REF | 37 | TRA | 08 | A | I | CFC | 0.6 | 0 | 0 | 0 | 2002-07-01 | 2004-05-01 | 2003-08-01 |  | 2004-04-01 | 2009-03-01 | 9000 | 0 | 9000 | 9000 | 100% | 0 | 0 |  | 1170 | 0 | 1170 | 0 | 0
FIN | UNEP | Preparation of country programme | Individual | AFR | DJI | SEV | 30 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-04-01 | 2001-06-01 |  | 2002-07-01 | 2007-01-01 | 60000 | -34200 | 25800 | 25800 | 100% | 0 | 0 |  | 7800 | -4446 | 3354 | 0 | 0 |  |  |  | 2002-07-01
FIN | UNEP | Establishment of the Ozone Unit (institutional strengthening) | Individual | AFR | DJI | SEV | 37 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2004-01-01 | 2005-08-01 |  | 2006-04-01 | 2007-04-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase II) | Individual | AFR | DJI | SEV | 48 | INS | 09 | A | I |  | 0 | 0.9 | 0 | 0 | 2006-04-01 | 2007-07-01 | 2008-04-01 |  | 2009-04-01 | 2010-12-01 | 78000 | 0 | 78000 | 78000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | AFR | DJI | SEV | 57 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-01-01 | 2011-03-01 |  | 2011-07-01 | 2012-07-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV: 7/2011-6/2013) | Individual | AFR | DJI | SEV | 64 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2011-11-01 | 2013-06-01 |  | 2013-04-01 | 2014-04-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of the institutional strengthening project (phase V: 7/2013-6/2015) | Individual | AFR | DJI | SEV | 70 | INS | 20 | A | I |  | 0 |  | 0 |  | 2013-07-01 | 2014-06-01 | 2015-06-01 | 2017-12-01 |  |  | 60000 | 0 | 60000 | 35996.12 | 59.99% | 24003.88 | 24003.88 | 24004 | 0 | 0 | 0 | 0 | 0 | UNEP was to quick in putting COM as the new SSFA is needed to be signed to complete the work. The project is now ONG. | UNEP was to quick in putting COM as the new SSFA is needed to be signed to complete the work. The project is now ONG.
ONG | UNEP | Extension of the institutional strengthening project (phase VI: 6/2015-7/2017) | Individual | AFR | DJI | SEV | 74 | INS | 21 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-04-01 | 2017-07-01 | 2017-12-01 |  |  | 60000 | 0 | 60000 | 0.49 | 0.0008167% | 59999.51 | 60000 | 5999.951 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Country signed the SSFA in March 2016 and First payment sent in April 2016.Country reported 2015 Art5 data and 2015 CP data in May 2016. Country coordinated the implementation of 2016 activities under Djibouti HPMP. Legal arrangements (actual/planned): Agreement signed in March 2016. All activities under the SSFA are completed (as planned) NO___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in April 2016__ All funds disbursed (yes/no): _ Final payment _ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Brief progress report (actual/planned): Country signed the SSFA in March 2016 and First payment sent in April 2016.Country reported 2015 Art5 data and 2015 CP data in May 2016. Country coordinated the implementation of 2016 activities. Legal arrangements (actual/planned): Agreement signed in March 2016. All activities under the SSFA are completed (as planned) NO___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in April 2016__ All funds disbursed (yes/no): No_ Final payment _ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | AFR | DJI | SEV | 74 | TAS | 22 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-04-01 | 2016-05-01 | 2017-12-01 |  |  | 40000 | 0 | 40000 | 0.49 | 0.001225% | 39999.51 | 40000 | 3999.951 | 5200 | 0 | 0.0637 | 5199.9363 | 5200 | Brief progress report (actual/planned): Country signed the SSFA in March 2016.First payment sent in April 2016. Consultants recruited in May 2016 and National survey on the use of ODS alternatives started in June 2016. Legal arrangements (actual/planned): Agreement signed in Mach 2016. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in April 2016 __ All funds disbursed (yes/no): _ n/a.__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Brief progress report (actual/planned): Country signed the SSFA in March 2016.First payment sent in April 2016. Consultants sent the advanced draft ODS alternatives survey in February 2017. Legal arrangements (actual/planned): Agreement signed in Mach 2016. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in April 2016 __ All funds disbursed (yes/no): _ n/a.__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a |  |  |  |  | 12 months delays
FIN | UNDP | Terminal CFC phase-out management plan (first tranche) | Multi-Year | LAC | DMI | PHA | 48 | TAS | 09 | N | I | CFC | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-10-01 | 2009-12-01 |  | 2009-12-01 | 2013-08-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 3600 | 0 | 3600 | 0 | 0 | Financially completed in 2013. |  | 2006 |  | Investment
FIN | UNEP | Terminal CFC phase-out management plan (first tranche) | Multi-Year | LAC | DMI | PHA | 48 | TAS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-07-01 | 2009-12-01 |  | 2010-11-01 | 2011-11-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 |  | 4550 | 0 | 4550 | 0 | 0
FIN | UNDP | Terminal CFC phase-out management plan (second and third tranches) | Multi-Year | LAC | DMI | PHA | 56 | INV | 14 | N | I | CFC | 0 | 0 | 0 | 0 | 2008-11-01 | 2011-04-01 | 2009-11-01 |  | 2013-12-01 | 2014-03-01 | 57000 | -792 | 56208 | 56208 | 100% | 0 | 0 | 0 | 5130 | -71 | 5059 | 0 | 0 | Financially Completed in 2014. | Completed in 2013. No new activities have been undertaken after December 2013. However, due to a delay with the equipment suppliers, equipment was shipped only in Jan 2014 and is being cleared from customs now. This project is operationally completed. | 2008 |  | Investment
FIN | UNEP | Terminal CFC phase-out management plan (second and third tranches) | Multi-Year | LAC | DMI | PHA | 56 | TAS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-09-01 | 2009-11-01 |  | 2011-12-01 | 2011-12-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 |  | 8580 | 0 | 8580 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | DMI | PHA | 57 | PRP | 16 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-01-01 | 2010-03-01 |  | 2011-12-01 | 2011-12-01 | 85000 | -17869 | 67131 | 67131 | 100% | 0 | 0 |  | 11050 | -2322.97 | 8727.03 | 0 | 0
FIN | UNDP | Terminal CFC phase-out management plan (fourth tranche) | Multi-year | LAC | DMI | PHA | 61 | INV | 17 | N | I | CFC | 0.7 | 0.7 | 0 | 0 | 2010-07-01 |  | 2011-07-01 |  | 2013-12-01 | 2014-08-01 | 6000 | -6000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 540 | -540 | 0 | 0 | 0 | Financially completed in 2014. | Completed in 2013. Demurrage services have been initiated. No new activities have been undertaken after December 2013. However, due to a delay with the equipment suppliers, equipment was shipped only in Jan 2014 and is being cleared from customs now. T | 2010 |  | Investment
FIN | UNEP | Terminal CFC phase-out management plan (fourth tranche) | Multi-Year | LAC | DMI | PHA | 61 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-06-01 | 2011-07-01 |  | 2013-12-01 | 2013-12-01 | 13000 | 0 | 13000 | 13000 | 100% | 0 | 0 |  | 1690 | 0 | 1690 | 0 | 0
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | DMI | PHA | 62 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2013-04-01 | 2014-12-01 | 2018-10-01 |  |  | 82250 | 0 | 82250 | 10026.36 | 12.19% | 72223.64 | 0 | 7222.364 | 10693 | 0 | 1303.4878 | 9389.5122 | 0 | Brief progress report (actual/planned): Mission held Apr-16 finalized draft of new SSFA which was approved by NOU and Administration. Country requsted withholding of 21,000 to undertake: capacity building and training of technicians and law enforcement officers. Request approved by Administration and reflected in SSFA. ___ Legal arrangements(actual/planned): SSFA signed by RD Oct-16. SSFA not yet returned signed by Country.___ First mission (actual/planned): ___ TOR completed(actual/planned): General TORs for monitoring and evaluation consultant agreed upon. Workplan agreed upon. ___ First disbursement date (actual/planned): To be processed upon receipt of signed SSFA and HPMP Workplan___ All funds disbursed (yes/no): No.___ Any delay? (yes/no): ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): No. ___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): Awaiting receipt of signed SSFA to commence activities (new SSFA for remaining activities). ___ Legal arrangements(actual/planned): Country reminded to submit signed SSFA.___ First mission (actual/planned): Mission planned for 2nd half of 2017.___ TOR completed(actual/planned): TORs for Regional Trainer and Monitoring and Evaluation Consultant to be revised, finalized and consultants recruited by Sept-17. ___ First disbursement date (actual/planned): To be processed upon receipt of signed SSFA and HPMP Workplan.___ All funds disbursed (yes/no): No.___ Any delay? (yes/no): ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): No. ___ If Yes, is any action required by ExCom: ___
ONG | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Individual | LAC | DMI | PHA | 75 | TAS | 22 | A | I |  | 0 |  | 0 |  | 2015-11-01 |  | 2017-03-01 | 2017-08-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 3000 | 3900 | 0 | 0 | 3900 | 0 | Brief progress report (actual/planned): The Terms of Reference (ToR) for hiring the international consultant was prepared, cleared by the management and advertised on 15 Sep-16. No applicants were received by closing date of 22 Sep-16 . To be readvertised.___ Legal arrangements(actual/planned): N/A at this stage.___Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): ___ All funds disbursed (yes/no): No. ___ Any delay?(yes/no): No. ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): No.___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): The Terms of Reference (ToR) for hiring the international consultant was combined with the TORs for the Verification Report for Suriname upon approval from Administration. Vacancy readvertised 14-Feb-17. ___ Legal arrangements(actual/planned):SSA to be prepared for selected candidate. ___Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): ___ All funds disbursed (yes/no): No. ___ Any delay?(yes/no): No. ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): No.___ If Yes, is any action required by ExCom: ___
FIN | UNEP | Implementation of the RMP: custom training | Individual | LAC | DMI | REF | 26 | TRA | 02 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 2003-06-01 | 2000-11-01 |  | 2006-04-01 | 2008-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0
FIN | UNEP | Implementation of the RMP: training of trainers in good refrigerant management practices | Individual | LAC | DMI | REF | 26 | TRA | 03 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-04-01 | 2000-11-01 |  | 2006-06-01 | 2008-12-01 | 20000 | -3000 | 17000 | 17000 | 100% | 0 | 0 |  | 2600 | -390 | 2210 | 0 | 0
FIN | UNEP | Preparation of refrigerant management plan | RMP | LAC | DMI | REF | 44 | PRP | 07 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-08-01 | 2005-12-01 |  | 2006-08-01 | 2008-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0
FIN | UNEP | Country programme preparation | Individual | LAC | DMI | SEV | 21 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1998-08-01 |  | 1998-09-01 | 1999-07-01 | 40000 | -16000 | 24000 | 24000 | 100% | 0 | 0 |  | 5200 | -2080 | 3120 | 0 | 0
FIN | UNEP | Establishment of an Ozone Protection Unit | Individual | LAC | DMI | SEV | 26 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 2000-07-01 | 2001-12-01 |  | 2004-02-01 | 2005-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase II) | Individual | LAC | DMI | SEV | 42 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2005-12-01 | 2005-04-01 |  | 2005-12-01 | 2007-04-01 | 13000 | 0 | 13000 | 13000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase II, second year) | Individual | LAC | DMI | SEV | 45 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-06-01 | 2006-04-01 |  | 2007-10-01 | 2008-01-01 | 13000 | 0 | 13000 | 13000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | LAC | DMI | SEV | 50 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-06-01 | 2008-11-01 |  | 2008-12-01 | 2009-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | LAC | DMI | SEV | 56 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2010-05-01 | 2010-11-01 |  | 2011-12-01 | 2011-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | LAC | DMI | SEV | 62 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2012-08-01 | 2012-11-01 |  | 2014-02-01 | 2014-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of the institutional strengthening project (phase VI: 4/2014-3/2016 ) | Individual | LAC | DMI | SEV | 72 | INS | 21 | A | I |  | 0 |  | 0 |  | 2014-05-01 | 2016-06-01 | 2016-03-01 | 2018-04-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 60000 | 6000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned):Access to ASYCUDA granted to NOU to facilite efficient and accurate CP and Article 7 data collection, verification and reporting. NOU supporting recruitment of MER and Regional Trainer Consultants under the HPMP. NOU attended Barbados Thematic Network Meeting. HCFC quotas for 2017 issued. ___ Legal arrangements(actual/planned): SSFA signed Apr-16 ___Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): Jun-16___ All funds disbursed (yes/no): No. ___ Any delay?(yes/no): ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): No. ___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): NOU undertaking 2016 Article 7 and CP data collection and verification. NOU reported change in PS in Feb-16. NOU working on an information package to hire a decidated Ozone Officer-note that this post has been filled by an Officer who did not have the title of Ozone Officer. ___ Legal arrangements(actual/planned): SSFA signed Apr-16. ___Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): Jun-16___ All funds disbursed (yes/no): No. ___ Any delay?(yes/no): ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): No. ___ If Yes, is any action required by ExCom: ___
FIN | UNDP | Preparation of a project in the general foam subsector | Individual | LAC | DOM | FOA | 27 | PRP | 20 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-04-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (panels and sprayfoam) at Paredomi (Paneles Refrigerados Dominicanos, C.A.) | Individual | LAC | DOM | FOA | 29 | INV | 21 | A | I | CFC | 60.7 | 60.7 | 0 | 0 | 1999-11-01 | 2001-10-01 | 2002-12-01 |  | 2002-04-01 | 2003-09-01 | 177670 | 0 | 177670 | 177670 | 100% | 0 | 0 | 0 | 23097.1 | 0.42 | 23097.52 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to methylene chloride/LIA technology in the manufacture of flexible polyurethane foam (boxfoam) at Espumas del Cibao | Individual | LAC | DOM | FOA | 29 | INV | 22 | A | I | CFC | 14.4 | 14.4 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2000-12-01 | 2002-11-01 | 89712 | -1048 | 88664 | 88664 | 100% | 0 | 0 | 0 | 11662.56 | -136.24 | 11526.32 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to methylene chloride/LIA technology in the manufacture of flexible polyurethane foam (boxfoam) at Poquinsa (Poliuretano Químico Indutrial, S.A.) | Individual | LAC | DOM | FOA | 29 | INV | 24 | A | I | CFC | 4 | 4 | 0 | 0 | 1999-11-01 | 2001-03-01 | 2002-12-01 |  | 2001-12-01 | 2003-04-01 | 24920 | 0 | 24920 | 24920 | 100% | 0 | 0 | 0 | 3239.6 | 0 | 3239.6 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | LAC | DOM | FOA | 33 | PRP | 26 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Preparation of a terminal programme in the foam sector | Individual | LAC | DOM | FOA | 36 | PRP | 27 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-07-01 | 2003-04-01 |  | 2005-07-01 | 2006-06-01 | 7500 | 0 | 7500 | 7500 | 100% | 0 | 0 | 0 | 975 | 0 | 975 | 0 | 0 | Completed in 2005. Financially completed in 2006. |  | 2002 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | LAC | DOM | FOA | 57 | PRP | 44 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-05-01 | 2010-03-01 |  | 2012-06-01 | 2014-03-01 | 60000 | -210.43 | 59789.57 | 59790 | 100% | -0.43 | 0 | 0 | 4500 | -15.78 | 4484.25 | -0.03 | 0 | Financially completed in 2014. | Completed in 2012. Pending payments have been made. | 2009 |  | Investment
FIN | UNDP | Conversion from HCFC-141b in the manufacture of polyurethane rigid insulation foam for commercial refrigerators | Multi-year | LAC | DOM | FOA | 61 | INV | 46 | N | I | HCFC | 3.7 | 3.7 | 0 | 0 | 2010-07-01 | 2011-03-01 | 2012-01-01 |  | 2012-10-01 | 2014-02-01 | 332775 | -39 | 332736 | 332736 | 100% | 0 | 0 | 0 | 24958 | -3 | 24955.075 | -0.07503 | 0 | Financially completed in 2014. | Completed in 2012. Cyclopentane is now being used on a commercial scale in FARCO. | 2010 |  | Investment
FIN | UNIDO | Preparation of a demonstration project (tobacco, curcubits, flowers, tomatoes) | Individual | LAC | DOM | FUM | 25 | PRP | 18 | A | I |  | 0 | 0 |  |  | 1998-07-01 | 1998-08-01 | 1999-08-01 |  | 1998-09-01 | 2001-07-01 | 30000 | -2341 | 27659 | 27659 | 100% | 0 | 0 |  | 3900 | -310 | 3590 | 0 | 0 | FIN
FIN | UNIDO | Demonstration project: alternatives to the use of methyl bromide: soil pasteurization (steam), non soil cultivation, solarization with biofumigation and low dose chemicals all in combination with IPM system | Individual | LAC | DOM | FUM | 26 | DEM | 19 | A | I | MBR | 0 | 0 |  |  | 1998-11-01 | 1999-05-01 | 2000-12-01 |  | 2002-03-01 | 2003-05-01 | 324500 | -699 | 323801 | 323800.91 | 100% | 0.09 | 0 |  | 42185 | -158 | 42027 | 0 | 0 | FIN
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organizations in methyl bromide communication | Individual | LAC | DOM | FUM | 30 | TAS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-12-01 | 25000 | -9183 | 15817 | 15817 | 100% | 0 | 0 |  | 3250 | -1194 | 2056 | 0 | 0
FIN | UNIDO | Preparation of a phase-out project in the fumigants (methyl bromide) sector for TPO-soil fumigation | Individual | LAC | DOM | FUM | 36 | PRP | 30 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2003-04-01 | 2004-03-01 | 30000 | -2722 | 27278 | 27278.42 | 100% | -0.42 | 0 |  | 3900 | -359 | 3541 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of methyl bromide in melon, flowers and tobacco | Individual | LAC | DOM | FUM | 38 | INV | 33 | A | I | MBR | 141 | 141 |  |  | 2002-11-01 | 2003-01-01 | 2006-12-01 |  | 2010-12-01 | 2011-12-01 | 922900 | -886 | 922014 | 922014.19 | 100% | -0.19 | 0 |  | 111519 | -97 | 111422 | 0 | 0 | FIN |  |  |  | INV
FIN | UNDP | National halon bank management plan development | Individual | LAC | DOM | HAL | 38 | TAS | 32 | N | I | Halon | 3 | 3 | 0 | 0 | 2002-11-01 | 2003-09-01 | 2004-12-01 |  | 2007-12-01 | 2011-11-01 | 40000 | -6494.68 | 33505.32 | 33505 | 100% | 0.32 | 0 | 0 | 5200 | -844.31 | 4355.65 | 0.04 | 0 | Completed in 2007. |  | 2002 |  | Investment
FIN | UNDP | National halon bank management plan update | Individual | LAC | DOM | HAL | 51 | TAS | 39 | N | I | Halons | 1.2 | 1.2 | 0 | 0 | 2007-03-01 | 2013-03-01 | 2011-01-01 |  | 2013-12-01 | 2014-02-01 | 20000 | -47.51 | 19952.49 | 19952 | 100% | 0.49 | 0 | 0 | 1800 | -4.28 | 1795.68 | 0.04 | 0 | Financially completed in 2014. | Completed in 2013. Project has started procedures to be operationally closed. | 2007 |  | Non-Investment
FIN | UNDP | Project preparation for a terminal phase-out management plan | Individual | LAC | DOM | PHA | 42 | PRP | 35 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2004-10-01 |  | 2005-05-01 | 2006-12-01 | 7500 | 0 | 7500 | 7500 | 100% | 0 | 0 | 0 | 563 | 0 | 563 | 0 | 0 | Completed in 2005. Financially completed in 2006. |  | 2004 |  | Investment
FIN | UNDP | Terminal phase-out plan for Annex A (Group I) substances: 2005 annual implementation programme | Multi-Year | LAC | DOM | PHA | 45 | INV | 36 | N | I | CFC | 41.3 | 41.3 | 0 | 0 | 2005-04-01 | 2006-02-01 | 2006-04-01 |  | 2007-12-01 | 2013-03-01 | 500000 | 0 | 500000 | 500000 | 100% | 0 | 0 | 0 | 37500 | 0 | 37500 | 0 | 0 | Financially completed in 2013. |  | 2005 |  | Investment
FIN | UNDP | Terminal phase-out plan for Annex A (Group I) substances: (second tranche) | Multi-Year | LAC | DOM | PHA | 48 | INV | 38 | N | I | CFC | 171 | 171 | 0 | 0 | 2006-04-01 | 2007-02-01 | 2007-04-01 |  | 2008-07-01 | 2013-09-01 | 400000 | 0 | 400000 | 400000 | 100% | 0 | 0 | 0 | 30000 | 0 | 30000 | 0 | 0 | Financially completed in 2013. |  | 2006 |  | Investment
FIN | UNDP | Terminal phase-out plan for Annex A (Group I) substances: (third tranche) | Multi-Year | LAC | DOM | PHA | 51 | INV | 40 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-03-01 | 2008-01-01 | 2009-03-01 |  | 2008-12-01 | 2013-02-01 | 400000 | 0 | 400000 | 400000 | 100% | 0 | 0 | 0 | 30000 | 0 | 30000 | 0 | 0 | Financially completed in 2013. |  | 2007 |  | Investment
FIN | UNDP | Terminal phase-out plan for Annex A (Group I) substances: (fourth tranche) | Multi-Year | LAC | DOM | PHA | 54 | INV | 41 | N | I | CFC | 28 | 28 | 0 | 0 | 2008-04-01 | 2009-05-01 | 2010-03-01 |  | 2009-12-01 | 2013-08-01 | 211600 | 0 | 211600 | 211600 | 100% | 0 | 0 | 0 | 15870 | 0 | 15870 | 0 | 0 | Financially completed in 2013. |  | 2008 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | DOM | PHA | 55 | PRP | 42 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2010-04-01 | 2009-07-01 |  | 2012-05-01 | 2014-03-01 | 150000 | -1664.96 | 148335.04 | 148335 | 100% | 0.04 | 0 | 0 | 11250 | -124.87 | 11125.125 | 0.005 | 0 | Financially completed in 2014. | Completed in 2012. No activities in 2013. | 2008 |  | Investment
FIN | UNDP | Terminal phase-out plan for Annex A (Group I) substances: (fifth tranche) | Multi-Year | LAC | DOM | PHA | 58 | INV | 45 | N | I | CFC | 70.9 | 70.9 | 0 | 0 | 2009-07-01 | 2010-02-01 | 2011-07-01 |  | 2012-05-01 | 2014-02-01 | 200000 | -8158 | 191842 | 191842 | 100% | 0 | 0 | 0 | 15000 | -611.85 | 14388.15 | 0 | 0 | Financially completed in 2014. | Completed in 2012. Some final payments pending. No activities in 2013. | 2009 |  | Investment
FIN | UNDP | HCFC phase-out management plan (stage I, first tranche) (sector phase-out for the use of HCFCs in the foam manufacturing sector) | Multi-year | LAC | DOM | PHA | 65 | INV | 48 | N | I | HCFC | 8.2 | 8.2 | 0 | 0 | 2011-11-01 | 2012-05-01 | 2016-10-01 |  | 2014-11-01 | 2015-05-01 | 343468 | 0 | 343468 | 343468 | 100% | 0 | 0 | 0 | 25760 | 0 | 25760 | 0 | 0 | Financially Completed in 2015. | As planned, follow up to HCFC-free production on commercial refrigeration companies and installation of new equipment is being conducted. | 2011 |  | Investment
FIN | UNDP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector and monitoring) | Multi-year | LAC | DOM | PHA | 65 | INV | 49 | N | I | HCFC | 0.6 | 0.6 | 0 | 0 | 2011-11-01 | 2012-05-01 | 2016-10-01 |  | 2015-12-01 | 2016-12-01 | 336532 | 0 | 336532 | 336532 | 100% | 0 | 0 | 0 | 25240 | 0 | 25240 | 0 | 0 | Financially completed in 2016. | Third tranche requested and approved. Implementation of MOA with Infotep continues. 3 workshops to End-users and refrigeration technicians were conducted. | 2011 |  | Investment
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | LAC | DOM | PHA | 65 | TAS | 50 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2013-04-01 | 2013-11-01 |  | 2013-11-01 | 2013-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0
COM | UNDP | HCFC phase-out management plan (stage I, second tranche) (sector phase-out for the use of HCFCs in the foam manufacturing sector) | Multi-year | LAC | DOM | PHA | 69 | INV | 53 | N | I | HCFC | 0 | 0 | 0 | 0 | 2013-04-01 | 2013-12-01 | 2015-04-01 |  | 2015-09-01 |  | 319982 | 0 | 319982 | 313736.48 | 98.05% | 6245.52 | 0 | 5308.692 | 23999 | 0 | 23530.5792 | 468.4208 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2015. |  | 2013 |  | Investment
FIN | UNDP | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector and monitoring) | Multi-year | LAC | DOM | PHA | 69 | INV | 54 | N | I | HCFC | 0 | 0 | 0 | 0 | 2013-04-01 | 2015-03-01 | 2015-04-01 |  | 2015-09-01 | 2016-10-01 | 143468 | 0 | 143468 | 143468 | 100% | 0 | 0 | 0 | 10760 | 0 | 10760 | 0 | 0 | Financially completed in 2016. | Third tranche requested and approved. Implementation of MOA with Infotep continues. 3 workshops to End-users and refrigeration technicians were conducted. | 2013 |  | Investment
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | Multi-year | LAC | DOM | PHA | 69 | TAS | 52 | A | I |  | 0 |  | 0 |  | 2013-04-01 | 2015-09-01 | 2015-04-01 | 2017-12-01 |  |  | 25000 | 0 | 25000 | 30.61 | 0.1224% | 24969.39 | 0 | 2496.939 | 3250 | 0 | 3.9793 | 3246.0207 | 0 | Brief progress report: The Government continued to enforce the HCFCs quota system and banning of HCFCs-1141b and polyols pre-blended with HCFC-141b. The procurement of three ODS identifiers included in a global bidding calling. Legal arrangements: N/A. The Government asked to UNEP for direct administration of project funds. First mission (actual/planned): September 2014/No specific date according to the project document. TOR completed (actual/planned): N/A. First disbursement date (actual/planned): No disbursements/Planned for 2015. All funds disbursed? (yes/no): No. Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: The global bidding of ODSs identifiers needs various steps to be completed. If Yes, will delay have impact on project completion date? (yes/no): Yes. Any ongoing problems? (yes/no): No. If Yes, is any action required by ExCom? N/A. | Brief progress report: The Government continued to enforce the HCFCs quota system and banning of HCFCs-1141b and polyols pre-blended with HCFC-141b. The procurement of three ODS identifiers is under process and purchase order will be issued by June 2017. Legal arrangements: N/A. The Government asked to UNEP for direct administration of project funds. First mission (actual/planned): September 2014/No specific date according to the project document. TOR completed (actual/planned): N/A. First disbursement date (actual/planned): No disbursements/Planned for 2015. All funds disbursed? (yes/no): No. Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: The global bidding of ODSs identifiers needs various steps to be completed. If Yes, will delay have impact on project completion date? (yes/no): Yes. Any ongoing problems? (yes/no): No. If Yes, is any action required by ExCom? N/A. |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor the completion of the global bidding process.
FIN | UNDP | Preparation of a HCFC phase-out management plan (stage II) | Individual | LAC | DOM | PHA | 72 | PRP | 55 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 | 2015-02-01 | 2016-05-01 |  | 2015-12-01 | 2016-12-01 | 60000 | 0 | 60000 | 54867 | 91.44% | 5133 | 0 | 0 | 4200 | 0 | 3840.69 | 359.31 | 0 | Financially completed in 2016. | 2015 workplan is under implementation. Information on HCFC consumptions is being gathered, draft of 2nd stage HPMP strategy prepared and under discussion. |  |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing sector and monitoring) | Multi-year | LAC | DOM | PHA | 74 | INV | 58 | N | I | HCFC | 0 | 0 | 0 | 0 | 2015-05-01 | 2016-06-01 | 2017-05-01 | 2017-12-01 |  |  | 170000 | 0 | 170000 | 112011.23 | 65.89% | 57988.77 | 0 | 23195.508 | 12750 | 0 | 8400.8422 | 4349.1578 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): 2016 work plan was implemented as envisioned. An update train-the-trainers workshop was conducted; 13 workshops on safety use of hydrocarbons as refrigerants were conducted; 600 technicians were trained by INFOTEP on good refrigeration practices; A presidential decree regarding the mandatory certification of RAC technicians was signed. Prodoc signed (actual/planned, yes/no and date):Yes, on May 2016. Missions undertaken (actual/planned):2 of 2 TOR for consultants/subcontracts completed (actual/planned): 1 of 1 Contract/PO/MOA agreements signed: 1 of 1 First disbursement date (actual/planned): 42522Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve:N/A | Annual work plan prepared. | 2015 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage II, first tranche) | Multi-year | LAC | DOM | PHA | 77 | INV | 60 | N | I | HCFC | 0 | 0 | 0 | 0 | 2016-12-01 |  | 2019-12-01 | 2017-12-01 |  |  | 558800 | -39 | 558761 | 0 | 0% | 558761 | 0 | 199920 | 39116 | 0 | 0 | 39116 | 0 | Newly Approved | DoA sent in February 2017. ProDoc is under preparation. | 2016 |  | Investment
ONG | UNEP | HCFC phase-out management plan (stage II, first tranche) | Multi-Year | LAC | DOM | PHA | 77 | TAS | 61 | A | I |  | 0 |  | 0 |  | 2016-12-01 |  | 2019-12-01 | 2019-12-01 |  |  | 95000 | 0 | 95000 | 0 | 0% | 95000 | 0 | 9500 | 12350 | 0 | 0 | 12350 | 0 | Newly approved project | Brief progress report: Annual implementation plan drafted. Legal arrangements (actual/planned): The SSFA to implement the stage two - first tranche is being drafted. Initially planned for January 2017. First mission (actual/planned): Expected to May 2017 while no specific date was established in the project document. TOR completed (actual/planned): N/A. First disbursement date (actual/planned): Expected to be in May 2017/ Planned for April 2017. All funds disbursed? (yes/no): No. Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: Administrative reasons, but they are now dully sorted out. If Yes, will delay have impact on project completion date: No. Any ongoing problems? (yes/no): No. If Yes, is any action required by ExCom: N/A
FIN | USA | Demonstration project in MACs |  | LAC | DOM | REF | 17 | DEM | 03 | A | I |  | 0 | 10 | 0 |  | 1995-07-01 | 1995-09-01 | 1996-12-01 |  | 1997-12-01 | 1999-10-01 | 220000 | 0 | 220000 | 220000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Final report submitted October 1999. |  | 1995 | 1997-12-01
FIN | USA | Project preparation in commercial refrigeration |  | LAC | DOM | REF | 17 | PRP | 02 | A | I |  | 0 |  | 0 |  | 1995-07-01 |  | 1996-01-01 |  | 1995-09-01 | 1995-09-01 | 19000 | 0 | 19000 | 19000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1995
FIN | USA | Demonstration project in commercial refrigeration (food storage, distribution and retailing) |  | LAC | DOM | REF | 18 | DEM | 05 | A | I |  | 0 | 7 | 0 |  | 1995-11-01 | 1995-11-01 | 1996-12-01 |  | 1998-02-01 | 1999-10-01 | 74000 | 0 | 74000 | 74000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Final report submitted October 1999. |  | 1995 | 1997-12-01
FIN | UNDP | Demonstration project in commercial refrigeration (food storage, distribution and retailing) | RMP-Component | LAC | DOM | REF | 18 | TAS | 06 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-04-01 | 1996-11-01 |  | 1998-04-01 | 1999-05-01 | 78000 | 0 | 78000 | 78000 | 100% | 0 | 0 | 0 | 10140 | 0 | 10140 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1995 |  | Non-Investment
FIN | UNDP | Project preparation in refrigeration recycling | Individual | LAC | DOM | REF | 21 | PRP | 08 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-03-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFCs 11 and 12 in the manufacture of unitary commercial refrigeration equipment at Fabrica de Refrigeradores Comerciales, C.A. (Farco) | Individual | LAC | DOM | REF | 22 | INV | 09 | A | I | CFC | 31.8 | 31.8 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1998-11-01 | 2000-07-01 | 423209 | -2883 | 420326 | 420326 | 100% | 0 | 0 | 0 | 55017.17 | -374.79 | 54642.38 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Project preparation in the commercial refrigeration sub-sector | Individual | LAC | DOM | REF | 22 | PRP | 10 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-03-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 consumption in the manufacture of unitary commercial refrigeration equipment at Metalgas S.A. by replacement with HCFC-141b and HFC-134a respectively | Individual | LAC | DOM | REF | 24 | INV | 11 | A | I | CFC | 20.8 | 20.8 | 0 | 0 | 1998-03-01 | 1998-09-01 | 2000-04-01 |  | 1999-12-01 | 2001-12-01 | 316368 | -3741 | 312627 | 312627 | 100% | 0 | 0 | 0 | 41127.84 | -486 | 40641.84 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Project preparation for one project in commercial refrigeration subsector | Individual | LAC | DOM | REF | 24 | PRP | 12 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-07-01 | 2000-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1998 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 consumption in the manufacture of unitary commercial refrigeration equipment at Industria Continental, C.A. by replacement with HCFC-141b and HFC 134a respectively | Individual | LAC | DOM | REF | 25 | INV | 16 | A | I | CFC | 19.9 | 19.9 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 1999-12-01 | 2002-03-01 | 303200 | -2802 | 300398 | 300398 | 100% | 0 | 0 | 0 | 39416 | -364.26 | 39051.74 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Implementation of the RMP: Implementation of a national programme for recovery and recycling of refrigerants | RMP-Component | LAC | DOM | REF | 25 | TAS | 13 | A | I | CFC | 37.4 | 37.4 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 2001-12-01 | 2003-04-01 | 441482 | -49014 | 392468 | 392468 | 100% | 0 | 0 | 0 | 57392.66 | -6371.82 | 51020.84 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Implementation of the RMP: Monitoring of the activities included in the RMP | RMP-Component | LAC | DOM | REF | 25 | TAS | 15 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 2000-01-01 | 2000-08-01 |  | 2003-09-01 | 2003-10-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2003. Financially completed in 2003. |  | 1998 |  | Non-Investment
FIN | UNEP | Implementation of the RMP: training programme for customs officers | Individual | LAC | DOM | REF | 25 | TRA | 14 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-10-01 | 1999-08-01 |  | 2003-06-01 | 2005-01-01 | 38000 | -10000 | 28000 | 28000 | 100% | 0 | 0 |  | 4940 | -1300 | 3640 | 0 | 0
FIN | UNEP | Implementation of the RMP: train the trainers programme in the refrigeration sector | Individual | LAC | DOM | REF | 25 | TRA | 17 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-09-01 | 2000-02-01 |  | 2001-12-01 | 2003-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 |  | 5850 | 0 | 5850 | 0 | 0 |  |  |  | 2000-12-01
FIN | UNDP | Preparation of investment activities of the RMP | Individual | LAC | DOM | REF | 36 | PRP | 29 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-09-01 | 2003-04-01 |  | 2004-12-01 | 2005-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2002 |  | Investment
ONG | UNDP | Feasibility study for district cooling in Punta Cana | Individual | LAC | DOM | REF | 74 | TAS | 57 | N | I | HCFC | 0 | 0 | 0 | 0 | 2015-05-01 | 2015-08-01 | 2016-11-01 | 2017-11-01 |  |  | 91743 | 0 | 91743 | 90000 | 98.1% | 1743 | 0 | 1743 | 8257 | 0 | 8100 | 157 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Workshop to present the project results was conducted with main stakeholders. Draft of final report was prepared and submitted to MLF. Prodoc signed (actual/planned, yes/no and date):The agreement has been signed earlier. Missions undertaken (actual/planned):1 of 1 TOR for consultants/subcontracts completed (actual/planned): TOR completed earlier. Contract/PO/MOA agreements signed: The agreement has been signed earlier First disbursement date (actual/planned): 42217Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve:N/A | Final report under review. | 2015 |  | Non-Investment
FIN | UNEP | Country programme preparation | Individual | LAC | DOM | SEV | 15 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-03-01 | 1996-03-01 |  | 1995-07-01 | 1995-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0
FIN | UNEP | Establishment of the National Commission for the Ozone (Cogo) | Individual | LAC | DOM | SEV | 17 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-04-01 | 1998-10-01 |  | 2000-02-01 | 2001-12-01 | 155000 | 0 | 155000 | 155000 | 100% | 0 | 0 |  | 20150 | 0 | 20150 | 0 | 0 |  |  |  | 1998-10-01
FIN | UNDP | Project preparation assistance in foams and refrigeration | Individual | LAC | DOM | SEV | 18 | PRP | 07 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-01 | 1996-11-01 |  | 1996-11-01 | 1998-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | LAC | DOM | SEV | 29 | INS | 23 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-02-01 | 2001-12-01 |  | 2003-06-01 | 2003-12-01 | 103000 | 0 | 103000 | 103000 | 100% | 0 | 0 |  | 13390 | 0 | 13390 | 0 | 0
FIN | UNEP | Policy and technical assistance | Individual | LAC | DOM | SEV | 37 | TAS | 31 | A | I | CFC | 0.8 | 0.8 | 0 | 0 | 2002-07-01 | 2003-07-01 | 2003-08-01 |  | 2006-06-01 | 2007-03-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase 3) | Individual | LAC | DOM | SEV | 39 | INS | 34 | A | I | CFC | 17.1 | 17.1 | 0 | 0 | 2003-04-01 | 2003-08-01 | 2005-04-01 |  | 2006-11-01 | 2007-04-01 | 134333 | -1 | 134332 | 134332 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | LAC | DOM | SEV | 48 | INS | 37 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2006-12-01 | 2008-04-01 |  | 2008-12-01 | 2009-12-01 | 134333 | 0 | 134333 | 134333 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | LAC | DOM | SEV | 56 | INS | 43 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-03-01 | 2010-11-01 |  | 2011-04-01 | 2011-12-01 | 134333 | 0 | 134333 | 134333 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VI) | Individual | LAC | DOM | SEV | 62 | INS | 47 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-05-01 | 2012-12-01 |  | 2012-12-01 | 2013-12-01 | 134333 | 0 | 134333 | 134333 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VII: 1/2013-12/2014) | Individual | LAC | DOM | SEV | 68 | INS | 51 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-04-01 | 2014-12-01 |  | 2014-12-01 | 2016-12-01 | 134333 | 0 | 134333 | 134333 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed | Project financially completed
ONG | UNEP | Extension of the institutional strengthening project (phase VIII: 1/2015-12/2016) | Individual | LAC | DOM | SEV | 73 | INS | 56 | A | I |  | 0 |  | 0 |  | 2014-11-01 | 2014-11-01 | 2016-12-01 | 2017-06-01 |  |  | 134333 | 0 | 134333 | 91281.71 | 67.95% | 43051.29 | 24017.84 | 4305.129 | 0 | 0 | 0 | 0 | 0 | Brief progress report: Project is progressing satisfactorily. Total transferences represent more than 80 % of the project budget. Progress and financial reports received and recorded. Legal arrangement (actual/planned): signed in April 2015/initially planned for February 2015. Initial stages of project implementation (actual/planned): Project currently ongoing. Intermediate goals achieved (actual/planned): Goals are achieved as planned for the year: NOO has been collecting ODS data and cross-checking information to prepare the 2015 Country Programme and Article 7 reports, and the International Ozone Day celebrated. The HCFCs license system continues being managed by the NOU. ISP renewal was submitted and approved by the 77 ExCom meeting. Project completion and follow up: Project ongoing. First disbursement date (actual/planned): May 2015/May 2015. All funds disbursed? (yes/no): No. Any delay? (yes/no): Minor delays in signature of the agreement that would not affect the project implementation timetable. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date? (yes/no): No. Any ongoing problems? (yes/no): No. If Yes, is any action required by ExCom?N/A. | Brief progress report: Project is progressing satisfactorily. Last cash advance will be released in May 2017. After that, total transferences will represent 100 % of the project budget. Progress and financial reports to complete the project are awaited and expected by June 2017. Legal arrangement (actual/planned): signed in April 2015/initially planned for February 2015. Initial stages of project implementation (actual/planned): Project currently ongoing. Intermediate goals achieved (actual/planned): Goals are achieved as planned for the year: NOO has been collecting ODS data and cross-checking information to prepare the 2016 Country Programme and Article 7 reports. The HCFCs license system continues being managed by the NOU. Project completion and follow up: Project ongoing. First disbursement date (actual/planned): May 2015/May 2015. All funds disbursed? (yes/no): No. Any delay? (yes/no): Minor delays in signature of the agreement that would not affect the project implementation timetable. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date? (yes/no): No. Any ongoing problems? (yes/no): No. If Yes, is any action required by ExCom?N/A.
ONG | UNDP | Survey of ODS alternatives at the national level | Individual | LAC | DOM | SEV | 75 | TAS | 59 | N | I | HCFC | 0 | 0 | 0 | 0 | 2015-11-01 | 2016-04-01 | 2016-12-01 | 2017-12-01 |  |  | 55000 | 0 | 55000 | 25928.51 | 47.14% | 29071.49 | 14122.32 | 11628.596 | 4950 | 0 | 2333.5659 | 2616.4341 | 1271.0088 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Project team hired. Methodology for conducting the survey was discussed and approved. Survey conducted and draft report prepared. Prodoc signed (actual/planned, yes/no and date):Yes, on May 2016. Missions undertaken (actual/planned):2 of 2 TOR for consultants/subcontracts completed (actual/planned): 1 of 1 Contract/PO/MOA agreements signed: 1 of 1 First disbursement date (actual/planned): 42461Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve:N/A | Final report prepared. Excel tables with preliminary results completed and submitted. | 2015 |  | Non-Investment
ONG | UNEP | Extension of the institutional strengthening project (phase IX: 1/2017-12/2018) | Individual | LAC | DOM | SEV | 77 | INS | 62 | A | I |  | 0 |  | 0 |  | 2016-12-01 |  | 2018-12-01 | 2018-12-01 |  |  | 171946 | 0 | 171946 | 0 | 0% | 171946 | 0 | 17194.6 | 0 | 0 | 0 | 0 | 0 | Newly approved project | Brief progress report: Annual implementation plan drafted. Legal arrangement (actual/planned): to be signed in April 2017/initially planned for February 2017. Initial stages of project implementation (actual/planned): In progress. Intermediate goals achieved (actual/planned): N/A. Project completion and follow up: N/A. First disbursement date (actual/planned): None/May 2017. All funds disbursed? (yes/no): No. Any delay? (yes/no): Minor delays in signature of the agreement that would not affect the project implementation timetable. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date? (yes/no): No. Any ongoing problems? (yes/no): No. If Yes, is any action required by ExCom?N/A.
FIN | UNDP | Preparation of a terminal programme in the solvent sector | Individual | LAC | DOM | SOL | 36 | PRP | 28 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-09-01 | 2003-04-01 |  | 2004-12-01 | 2005-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Project preparation in the flexible polyurethane foam sector | Individual | AFR | DRC | FOA | 33 | PRP | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-09-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Complast SPRL | Individual | AFR | DRC | FOA | 35 | INV | 06 | A | I | CFC | 38 | 38 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-01-01 |  | 2006-11-01 | 2007-03-01 | 190820 | 0 | 190820 | 190820 | 100% | 0 | 0 | 0 | 24806.6 | 0 | 24806.6 | 0 | 0 | Completed in 2006. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slastock foam by conversion to methylene chloride at M.K. SPRL | Individual | AFR | DRC | FOA | 35 | INV | 07 | A | I | CFC | 26 | 26 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-01-01 |  | 2005-12-01 | 2008-04-01 | 149800 | 0 | 149800 | 149800 | 100% | 0 | 0 | 0 | 19474 | 0 | 19474 | 0 | 0 | Completed in 2005. Financially completed in 2008. |  | 2001 |  | Investment
FIN | UNDP | Project preparation for 3 projects in the flexible slabstock sector | Individual | AFR | DRC | FOA | 36 | PRP | 09 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2005-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2002. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam at Bek SPRL by convesion to methylene chloride | Individual | AFR | DRC | FOA | 37 | INV | 10 | A | I | CFC | 28 | 28 | 0 | 0 | 2002-07-01 | 2003-02-01 | 2005-09-01 |  | 2005-12-01 | 2011-11-01 | 165670 | -25705.47 | 139964.53 | 139965 | 100% | -0.47 | 0 | 0 | 21537.1 | -3341.71 | 18195.45 | -0.06 | 0 | Completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam at Ekanawe SPRL by conversion to methylene chloride | Individual | AFR | DRC | FOA | 37 | INV | 11 | A | I | CFC | 24 | 24 | 0 | 0 | 2002-07-01 | 2004-01-01 | 2005-09-01 |  | 2005-12-01 | 2007-03-01 | 75490 | 0 | 75490 | 75490 | 100% | 0 | 0 | 0 | 9813.7 | 0 | 9813.7 | 0 | 0 | Completed in 2005. Financially completed in 2007. |  | 2002 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam at Sokamo SPRL by conversion to methylene chloride | Individual | AFR | DRC | FOA | 37 | INV | 12 | A | I | CFC | 21 | 21 | 0 | 0 | 2002-07-01 | 2004-01-01 | 2005-09-01 |  | 2005-12-01 | 2007-03-01 | 69920 | 0 | 69920 | 69920 | 100% | 0 | 0 | 0 | 9089.6 | 0 | 9089.6 | 0 | 0 | Completed in 2005. Financially completed in 2007. |  | 2002 |  | Investment
FIN | UNDP | Formulation of terminal project in the foam sector | Individual | AFR | DRC | FOA | 39 | PRP | 14 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-12-01 | 2005-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 750 | 0 | 750 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2003 |  | Investment
FIN | UNDP | Terminal umbrella project for the foam sector | Individual | AFR | DRC | FOA | 41 | INV | 19 | N | I | CFC | 123 | 123 | 0 | 0 | 2003-12-01 | 2005-02-01 | 2006-12-01 |  | 2007-12-01 | 2012-07-01 | 640820 | -22461.21 | 618358.79 | 618359 | 100% | -0.21 | 0 | 0 | 48062 | -1684.61 | 46377.4075 | -0.01745 | 0 | Financially completed in 2012. |  | 2003 |  | Investment
FIN | UNDP | National CFC phase-out plan (first tranche) | Multi-Year | AFR | DRC | PHA | 49 | INV | 24 | N | I | CFC | 0 | 0 | 0 | 0 | 2006-07-01 | 2009-05-01 | 2007-12-01 |  | 2009-12-01 | 2013-02-01 | 193750 | 0 | 193750 | 193750 | 100% | 0 | 0 | 0 | 14531 | 0 | 14531 | 0 | 0 | Financially completed in 2013. |  | 2006 |  | Investment
FIN | UNEP | National CFC phase-out plan (first tranche) | Multi-year | AFR | DRC | PHA | 49 | TAS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-10-01 | 2007-12-01 |  | 2009-07-01 | 2010-12-01 | 143750 | 0 | 143750 | 143750 | 100% | 0 | 0 |  | 18688 | 0 | 18688 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | DRC | PHA | 55 | PRP | 27 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-08-01 | 2009-07-01 |  | 2011-03-01 | 2011-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 |  | 11050 | 0 | 11050 | 0 | 0
FIN | UNDP | National CFC phase-out plan (second tranche) | Multi-Year | AFR | DRC | PHA | 57 | INV | 30 | N | I | CFC | 5 | 5 | 0 | 0 | 2009-04-01 | 2010-01-01 | 2011-03-01 |  | 2010-07-01 | 2013-01-01 | 71875 | 0 | 71875 | 71875 | 100% | 0 | 0 | 0 | 5391 | 0 | 5391 | 0 | 0 | Financially completed in 2013. |  | 2009 |  | Investment
FIN | UNEP | National CFC phase-out plan (second tranche) | Multi-Year | AFR | DRC | PHA | 57 | TAS | 29 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-10-01 | 2010-03-01 |  | 2011-03-01 | 2011-12-01 | 71875 | 0 | 71875 | 71875 | 100% | 0 | 0 |  | 9344 | 0 | 9344 | 0 | 0
FIN | UNDP | National CFC phase-out plan (third tranche) | Multi-year | AFR | DRC | PHA | 61 | INV | 33 | N | I | CFC | 46.5 | 46.5 | 0 | 0 | 2010-07-01 | 2011-01-01 | 2011-07-01 |  | 2011-12-01 | 2012-07-01 | 71875 | -8316.03 | 63558.97 | 63559 | 100% | -0.03 | 0 | 0 | 5391 | -623.75 | 4767.2567 | -0.0066502 | 0 | Financially completed in 2012. | Completed in 2011. | 2010 |  | Investment
FIN | UNEP | National CFC phase-out plan (third tranche) | Multi-Year | AFR | DRC | PHA | 61 | TAS | 32 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-09-01 | 2011-07-01 |  | 2011-12-01 | 2011-12-01 | 71875 | 0 | 71875 | 71875 | 100% | 0 | 0 |  | 9344 | 0 | 9344 | 0 | 0
FIN | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | DRC | PHA | 63 | INV | 36 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-08-01 | 2013-03-01 |  | 2013-12-01 | 2014-08-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 9000 | 0 | 9000 | 0 | 0 | Financially completed in 2014. | Completed in 2013. The planned milestone of determining the activities under Tranche 2 of the HPMP has been completed. The planned milestones will include delivery of the equipment in other regions of DRC and a support mission by UNDP and the Internation | 2011 |  | Investment
COM | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | AFR | DRC | PHA | 63 | TAS | 35 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-09-01 | 2013-03-01 |  | 2013-03-01 |  | 95000 | 0 | 95000 | 95000 | 100% | 0 | 0 |  | 12350 | 0 | 12350 | 0 | 0 | Some financial adjustments are needed. | Some financial adjustments are needed.
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | AFR | DRC | PHA | 70 | INV | 37 | N | I | HCFC | 2.9 | 1.1 | 0 | 0 | 2013-07-01 | 2014-06-01 | 2015-07-01 | 2017-07-01 |  |  | 116000 | 0 | 116000 | 94337.06 | 81.33% | 21662.94 | 0 | 8665.176 | 10440 | 0 | 8490.3354 | 1949.6646 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): The equipment was received in the country in 2016. However, it could not be delivered to all regions immediately, the delay being due to a disagreement with the delivery component in charge of releasing and transporting of the equipment in each of the regions. This unfortunate delay was eventually resolved by the UNDP Country Office and beneficiaries have now received the equipment. There was one official ceremony for the delivery of the equipment in Lumumbashi and three other ones will happen in 2017. The equipment is now available for the other activities of the HPMP in the country. The pending HCFC verification report, which was pending for the ne tranche request, could still not be completed in 2016. Prodoc signed (actual/planned, yes/no and date):1/1. Yes. Agreement signed earlier. Missions undertaken (actual/planned):0/1 - No mission I 2016. It is planned in 2017 with the equipment now being delivered, the next tranche to be submitted at ExCom 79 and the PRP for Stage 2 to be launched. TOR for consultants/subcontracts completed (actual/planned): ToR completed earlier Contract/PO/MOA agreements signed: 0/0 No new procurement. First disbursement date (actual/planned): 41791Any delays/problems (yes/no):Yes. If Yes, reasons for delay & action plan to resolve:Delay due to the logistical difficulties for delivering equipment in the regions. Disagreement with the transport company was eventually solved by the UNDP Country Office. | The official ceremonies for the delivery of equipment in planning in 3 other regions. The work plan for the year includes printing of booklet for ODS importers. | 2013 |  | Investment
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | AFR | DRC | PHA | 70 | TAS | 38 | A | I |  | 2.9 |  | 0 |  | 2013-07-01 | 2014-02-01 | 2015-07-01 | 2017-12-01 |  |  | 116500 | 0 | 116500 | 40681.61 | 34.92% | 75818.39 | 75818.39 | 11859.581 | 15145 | 0 | 5288.6093 | 9856.3907 | 9856.3907 | Brief progress report (actual/planned): SSFA amended for extension until April 2017. Payment sent in October 2016. Legal arrangements (actual/planned): Amended agreement signed in August 2016. Country trained 30 RAC technicians and 20 custom officers in 2016. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in Oct. 16 __ All funds disbursed (yes/no): _ n/a.__ Any delay? (yes/no): YES___ If Yes, reasons for delay & action plan to resolve: Former NOO retired, a new one was appointed with delays ___ If Yes, will delay have impact on project completion date (yes/no): _ No the new officer is fully in board __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Brief progress report (actual/planned): SSFA amended for extension until August 2017. Payment after amendment sent in October 2016. Legal arrangements (actual/planned): Amended agreement signed in August 2016. Country trained 30 RAC technicians and 20 custom officers in 2016. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in Oct. 16 __ All funds disbursed (yes/no): _ n/a.__ Any delay? (yes/no): YES___ If Yes, reasons for delay & action plan to resolve: Former NOO retired, a new one was appointed with delays ___ If Yes, will delay have impact on project completion date (yes/no): _ No the new officer is fully in board __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor the completion of training for the new national ozone officer.
FIN | UNEP | Assistance in developing the RMP project proposal | Individual | AFR | DRC | REF | 32 | TAS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2002-07-01 | 2002-01-01 |  | 2003-12-01 | 2010-12-01 | 60000 | -16985 | 43015 | 43015 | 100% | 0 | 0 |  | 7800 | -2208.4 | 5591.6 | 0 | 0 |  |  |  | 2003-12-01
FIN | UNDP | Project preparation in recovery and recycling refrigeration sector | Individual | AFR | DRC | REF | 36 | PRP | 08 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-10-01 | 2003-04-01 |  | 2003-12-01 | 2005-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Formulation of the investment components of the RMP | Individual | AFR | DRC | REF | 39 | PRP | 13 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-12-01 | 2005-12-01 | 7500 | 0 | 7500 | 7500 | 100% | 0 | 0 | 0 | 562 | 0 | 562 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2003 |  | Investment
FIN | UNDP | Implementation of the RMP: centralized recovery and recycling of CFC-12 programme | RMP-Component | AFR | DRC | REF | 41 | TAS | 16 | N | I | CFC | 13.1 | 13.1 | 0 | 0 | 2003-12-01 | 2005-02-01 | 2006-12-01 |  | 2008-12-01 | 2012-07-01 | 437102 | -231.44 | 436870.56 | 436871 | 100% | -0.44 | 0 | 0 | 32783 | -17.36 | 32765.6748 | -0.0348 | 0 | Financially completed in 2012. |  | 2003 |  | Investment
FIN | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | AFR | DRC | REF | 41 | TAS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-06-01 | 2006-12-01 |  | 2006-12-01 | 2009-06-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNEP | Implementation of the RMP: training programme for technicians in the refrigeration sector | Individual | AFR | DRC | REF | 41 | TRA | 15 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-03-01 | 2004-10-01 |  | 2006-12-01 | 2010-12-01 | 115000 | 0 | 115000 | 115000 | 100% | 0 | 0 |  | 14950 | 0 | 14950 | 0 | 0
FIN | UNEP | Implementation of the RMP: customs training programme | Individual | AFR | DRC | REF | 41 | TRA | 18 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-06-01 | 2004-12-01 |  | 2006-12-01 | 2008-12-01 | 109000 | -208 | 108792 | 108792 | 100% | 0 | 0 |  | 14170 | -27.04 | 14142.96 | 0 | 0
FIN | UNDP | Project preparation for refrigeration end-user | Individual | AFR | DRC | REF | 45 | PRP | 21 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-05-01 | 2006-04-01 |  | 2006-07-01 | 2006-12-01 | 16870 | 0 | 16870 | 16870 | 100% | 0 | 0 | 0 | 1265 | 0 | 1265 | 0 | 0 | Completed in 2006. Financially completed in 2006. |  | 2005 |  | Investment
FIN | UNEP | Country programme preparation | Individual | AFR | DRC | SEV | 17 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-10-01 | 1996-10-01 |  | 2000-12-01 | 2001-12-01 | 43000 | 0 | 43000 | 43000 | 100% | 0 | 0 |  | 5590 | 0 | 5590 | 0 | 0 |  |  |  | 1999-03-01
FIN | UNEP | Creation of an Ozone Office | Individual | AFR | DRC | SEV | 27 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2003-06-01 | 2000-04-01 |  | 2000-12-01 | 2004-04-01 | 32270 | 0 | 32270 | 32270 | 100% | 0 | 0 |  | 4195 | 0 | 4195 | 0 | 0
FIN | UNEP | Institutional strengthening project (renewal) | Individual | AFR | DRC | SEV | 32 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2004-01-01 | 2003-01-01 |  | 2005-09-01 | 2005-12-01 | 64540 | 0 | 64540 | 64540 | 100% | 0 | 0 |  | 8390 | 0 | 8390 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase III) | Individual | AFR | DRC | SEV | 46 | INS | 22 | A | I | CFC | 5.2 | 5.2 | 0 | 0 | 2005-07-01 | 2007-01-01 | 2007-07-01 |  | 2007-07-01 | 2009-07-01 | 64540 | 0 | 64540 | 64540 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | AFR | DRC | SEV | 52 | INS | 26 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-10-01 | 2009-06-01 |  | 2009-06-01 | 2011-11-01 | 64540 | 0 | 64540 | 64540 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase V) | Individual | AFR | DRC | SEV | 58 | INS | 31 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2011-08-01 | 2010-12-01 |  | 2011-12-01 | 2011-12-01 | 48405 | 0 | 48405 | 48405 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase VI) | Individual | AFR | DRC | SEV | 62 | INS | 34 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-08-01 | 2012-12-01 |  | 2013-06-01 | 2014-06-01 | 64540 | 0 | 64540 | 64540 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of institutional strengthening project (phase VII: 1/2014-12/2015) | Individual | AFR | DRC | SEV | 71 | INS | 39 | A | I |  | 0 |  | 0 |  | 2013-12-01 | 2014-07-01 | 2015-12-01 | 2017-07-01 |  |  | 64540 | 0 | 64540 | 32062 | 49.68% | 32478 | 32478.21 | 3247.8 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Country signed the SSFA in July 2014. Art5 data report for 2015 and CP data for 2015 have been provided. 2016 Ozone day was celebrated. Awareness campaigns raised in schools in September 2016. Legal arrangements (actual/planned): Agreement signed in July 2014. All activities under the SSFA are completed (as planned) YES___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in July 2014 __ All funds disbursed (yes/no): _YES_ Final payment October 2016_ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Brief progress report (actual/planned): Country signed the SSFA in July 2014. Art5 data report for 2015 and CP data for 2015 have been provided. 2016 Ozone day was celebrated. Awareness campaigns raised in schools in September 2016. Legal arrangements (actual/planned): Agreement signed in July 2014. All activities under the SSFA are completed (as planned) YES___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in July 2014 __ All funds disbursed (yes/no): _YES_ Final payment October 2016_ Any delay? (yes/no): no SSFA expired in Jul 2016 with balance US$ 0___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | AFR | DRC | SEV | 75 | TAS | 40 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-09-01 | 2016-12-01 | 2017-10-01 |  |  | 110000 | 0 | 110000 | 59.26 | 0.05387% | 109940.74 | 109940.74 | 10994.074 | 14300 | 0 | 7.7038 | 14292.2962 | 14292.2962 | Brief progress report (actual/planned): __ SSFA signed in August 2016 and first payment sent in September 2016. Country submitted the report on Non ODS survey. Legal arrangements (actual/planned): signed in August 2016 (Yes/No): No_ First mission (actual/planned): __n/a_ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): Sept. 2016__ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _YES_ If Yes, reasons for delay & action plan to resolve: NO__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): __ SSFA signed in August 2016 and first payment sent in September 2016. Country submitted the advanced translated draft of Non ODS survey report. Legal arrangements (actual/planned): signed in August 2016 (Yes/No): No_ First mission (actual/planned): __n/a_ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): Sept. 2016__ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _YES_ If Yes, reasons for delay & action plan to resolve: NO__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__
ONG | UNEP | Extension of institutional strengthening project (phase VIII: 1/2017-12/2018) | Individual | AFR | DRC | SEV | 77 | INS | 41 | A | I |  | 0 |  | 0 |  | 2016-12-01 |  | 2018-12-01 | 2018-12-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | Newly approved project | Brief progress report (actual/planned): Project newly approved. Agreement not signed yet. Legal arrangements (actual/planned): Agreement not signed yet. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement _no __ All funds disbursed (yes/no): _ Final payment _no_4.__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
FIN | UNIDO | Preparation of a phase-out plan in the solvents (CTC) sector | Individual | AFR | DRC | SOL | 45 | PRP | 20 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-07-01 | 2006-04-01 |  | 2007-04-01 | 2009-12-01 | 30000 | -1605 | 28395 | 28394.89 | 100% | 0.11 | 0 |  | 2250 | -120 | 2130 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | Italy | Umbrella project for terminal phase-out of ODS in the solvent sector (first phase) | Individual | AFR | DRC | SOL | 51 | INV | 25 | A | I | CTC-TCA | 8.9 | 8.9 | 0 |  | 2007-03-01 | 2008-04-01 | 2008-03-01 |  | 2011-10-01 | 2012-08-01 | 288440 | 0 | 288440 | 288440 | 100% | 0 | 0 | 0 | 37497 | 0 | 37497 | 0 | 0 | Financial completion in Aug 2012. |  | 2007 | 2009-12-01 | Investment
FIN | Italy | Umbrella project for terminal phase-out of ODS in the solvent sector (second phase) | Individual | AFR | DRC | SOL | 56 | INV | 28 | A | I | CTC-TCA | 11.7 | 11.7 | 0 |  | 2008-11-01 | 2008-12-01 | 2009-11-01 |  | 2011-10-01 | 2012-08-01 | 144220 | -1253.81 | 142966.19 | 142966 | 100% | 0.19 | 0 | 0 | 18749 | -163 | 18586 | 0 | 0 | Financial completion in Aug 2012. Refund was reported to 68th ExCom, Nov 2012. FIN. |  | 2008 | 2011-12-01 | Investment
FIN | UNIDO | Phasing out CFC-11 at Hamhung Foam Factory, Hamgyong South Province | Individual | ASP | DRK | FOA | 23 | INV | 06 | A | I | CFC | 35 | 35 |  |  | 1997-11-01 | 1998-06-01 | 1998-12-01 |  | 1998-12-01 | 2001-03-01 | 102680 | -2145 | 100535 | 100535 | 100% | 0 | 0 |  | 13348 | -299 | 13049 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Pyongyang Foam Plant | Individual | ASP | DRK | FOA | 23 | INV | 07 | A | I | CFC | 83 | 83 |  |  | 1997-11-01 | 1998-06-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 103570 | -1984 | 101586 | 101585.63 | 100% | 0.37 | 0 |  | 13464 | -279 | 13185 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Chongjin Foam Factory, Hamgyong North Province | Individual | ASP | DRK | FOA | 23 | INV | 08 | A | I | CFC | 32 | 32 |  |  | 1997-11-01 | 1998-12-01 | 1998-12-01 |  | 1998-12-01 | 2001-03-01 | 103670 | -72 | 103598 | 103598 | 100% | 0 | 0 |  | 13477 | -31 | 13446 | 0 | 0 | FIN
COM | UNIDO | Preparation for HCFC phase-out investment activities (polyurethane foam sector) | Individual | ASP | DRK | FOA | 64 | PRP | 54 | A | I |  | 0 | 0 |  |  | 2011-07-01 | 2011-12-01 | 2012-07-31 |  | 2015-12-01 |  | 50000 | 0 | 50000 | 40074.16 | 80.15% | 9925.84 | 10064.02 | 1 | 3750 | 0 | 3006 | 744 | 755 | The project was operationally completed. |  |  |  | NON-INV
FIN | UNIDO | Preparation of a demonstration project in the methyl bromide sector | Individual | ASP | DRK | FUM | 23 | PRP | 04 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-01-01 | 1998-03-01 |  | 1998-01-01 | 2001-07-01 | 15000 | 8050 | 23050 | 23050 | 100% | 0 | 0 |  | 1950 | 1042 | 2992 | 0 | 0 | FIN
FIN | UNIDO | Non-investment project: promotion and information transfer of alternatives to the use of methyl bromide in the preparation of seedbeds for the cultivation of rice and maize | Individual | ASP | DRK | FUM | 25 | TAS | 09 | A | I |  | 0 | 0 |  |  | 1998-07-01 | 1999-03-01 | 1999-07-01 |  | 1999-11-01 | 2001-03-01 | 27500 | -153 | 27347 | 27347 | 100% | 0 | 0 |  | 3575 | -25 | 3550 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of investment projects in the solvents, process agents and fumigants sector (CTC) | Individual | ASP | DRK | MUS | 39 | PRP | 23 | A | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-04-01 | 2004-09-01 | 40000 | -22 | 39978 | 39977.88 | 100% | 0.12 | 0 |  | 3000 | -6 | 2994 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a process agent terminal umbrella project | Individual | ASP | DRK | PAG | 48 | PRP | 42 | A | I |  | 0 | 0 |  |  | 2006-04-01 | 2006-05-01 | 2007-04-01 |  | 2006-12-01 | 2007-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 2250 | 0 | 2250 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Supplementary plan for terminal phase-out of CTC as process agent | Individual | ASP | DRK | PAG | 49 | INV | 46 | A | I | CTC | 229.9 | 229.9 |  |  | 2006-07-01 | 2007-01-01 | 2007-12-01 |  | 2008-12-01 | 2009-12-01 | 884399 | -799 | 883600 | 883599.54 | 100% | 0.46 | 0 |  | 66330 | -60 | 66270 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Plan for terminal phase-out of CTC (first tranche) | Multi-Year | ASP | DRK | PHA | 41 | INV | 30 | A | I | CTC | 0 | 613.8 |  |  | 2003-12-01 | 2004-02-01 | 2004-12-01 |  | 2009-12-01 | 2011-05-01 | 3500000 | -2013 | 3497987 | 3497986.94 | 100% | 0.06 | 0 |  | 262500 | -151 | 262349 | 0 | 0 | FIN |  |  | 2006-12-01 | INV
FIN | UNIDO | Plan for terminal phase-out of CTC (third tranche) | Multi-Year | ASP | DRK | PHA | 46 | INV | 35 | A | I | CTC | 1441.4 | 597.7 |  |  | 2005-07-01 | 2006-04-01 | 2006-07-01 |  | 2008-07-01 | 2008-07-01 | 300000 | 0 | 300000 | 300000.01 | 100% | -0.01 | 0 |  | 22500 | 0 | 22500 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Plan for terminal phase-out of CTC (second tranche) | Multi-Year | ASP | DRK | PHA | 46 | INV | 36 | A | I | CTC | 0 | 0 |  |  | 2005-07-01 | 2006-08-01 | 2006-07-01 |  | 2008-07-01 | 2008-07-01 | 1000000 | -157 | 999843 | 999842.55 | 100% | 0.45 | 0 |  | 75000 | -12 | 74988 | 0 | 0 | FIN |  |  |  | INV
FIN | UNEP | Preparation of a terminal phase-out management plan | Individual | ASP | DRK | PHA | 46 | PRP | 34 | A | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-09-01 | 2006-07-01 |  | 2005-11-01 | 2006-02-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0
FIN | UNIDO | Preparation of a terminal phase-out management plan | Individual | ASP | DRK | PHA | 46 | PRP | 38 | A | I |  | 0 | 0 |  |  | 2005-07-01 | 2005-09-01 | 2006-07-01 |  | 2006-12-01 | 2006-12-01 | 15000 | -11196 | 3804 | 3804.13 | 100% | -0.13 | 0 |  | 1125 | -840 | 285 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNEP | Implementation of the NPP: regulations, training programme and monitoring (first tranche) | Multi-year | ASP | DRK | PHA | 47 | TAS | 39 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-03-01 | 2006-12-01 |  | 2008-07-01 | 2009-07-01 | 234600 | 0 | 234600 | 234600 | 100% | 0 | 0 |  | 30498 | 0 | 30498 | 0 | 0
FIN | UNIDO | Implementation of the NPP: recovery and recycling | Multi-Year | ASP | DRK | PHA | 47 | TAS | 40 | A | I | CFC | 121.7 | 163.7 |  |  | 2005-11-01 | 2006-07-01 | 2009-12-01 |  | 2010-12-01 | 2011-12-01 | 536000 | -7549 | 528451 | 528451 | 100% | 0 | 0 |  | 40200 | -566 | 39634 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Plan for terminal phase-out of CTC (fourth tranche) | Multi-Year | ASP | DRK | PHA | 49 | INV | 45 | A | I | CTC | 100 | 100 |  |  | 2006-07-01 | 2007-01-01 | 2007-12-01 |  | 2008-12-01 | 2009-12-01 | 500000 | 0 | 500000 | 500000 | 100% | 0 | 0 |  | 37500 | 0 | 37500 | 0 | 0 | FIN |  |  |  | INV
FIN | UNEP | Implementation of the NPP: regulations, training programme and monitoring (second tranche) | Multi-year | ASP | DRK | PHA | 49 | TAS | 44 | A | I | CFC | 54 | 54 | 0 | 0 | 2006-07-01 | 2008-02-01 | 2007-12-01 |  | 2008-03-01 | 2011-11-01 | 163400 | -16532 | 146868 | 146868 | 100% | 0 | 0 |  | 21242 | -2149.16 | 19092.84 | 0 | 0
FIN | UNEP | Implementation of the NPP: regulations, training programme and monitoring (third tranche) | Multi-Year | ASP | DRK | PHA | 51 | TAS | 47 | A | I | CFC | 18 | 18 | 0 |  | 2007-03-01 | 2009-04-01 | 2008-03-01 |  | 2011-03-01 | 2012-03-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0
FIN | UNIDO | Plan for terminal phase-out of CTC (fifth tranche) | Multi-Year | ASP | DRK | PHA | 52 | INV | 48 | A | I | CTC | 15 | 15 |  |  | 2007-07-01 | 2007-11-01 | 2008-07-31 |  | 2008-12-01 | 2009-05-01 | 284840 | -142 | 284698 | 284698.36 | 100% | -0.36 | 0 |  | 21363 | -11 | 21352 | 0 | 0 | FIN |  |  |  | INV
FIN | UNEP | Implementation of the NPP: regulations, training programme and monitoring (fourth tranche) | Multi-Year | ASP | DRK | PHA | 54 | TAS | 50 | A | I | CFC | 19 | 19 | 0 | 0 | 2008-04-01 | 2011-01-01 | 2009-03-01 |  | 2011-04-01 | 2011-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0
FIN | UNIDO | Plan for terminal phase-out of CTC (6th tranche) | Multi-Year | ASP | DRK | PHA | 55 | INV | 52 | A | I | CTC | 77.8 | 77.8 |  |  | 2008-07-01 | 2009-02-01 | 2009-07-31 |  | 2010-12-01 | 2012-10-01 | 100000 | -2024 | 97976 | 97975.55 | 100% | 0.45 | 0 |  | 7500 | -152 | 7348 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | ASP | DRK | PHA | 55 | PRP | 51 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-11-01 | 2009-07-31 |  | 2011-12-01 | 2013-10-01 | 50000 | -2026 | 47974 | 47974.03 | 100% | -0.03 | 0 |  | 3750 | -152 | 3598 | 0 | 0 | FIN |  |  |  | NON-INV
COM | UNIDO | Preparation of a HCFC phase-out management plan (additional funding) | Individual | ASP | DRK | PHA | 64 | PRP | 55 | A | I |  | 0 | 0 |  |  | 2011-07-01 | 2011-10-01 | 2012-07-31 |  | 2015-12-01 |  | 65000 | 0 | 65000 | 64580.4 | 99.35% | 419.6 | 0 | 1 | 4875 | 0 | 4844 | 31 | 0 | The project was operationally completed. |  |  |  | NON-INV
FIN | UNEP | Preparation of a HCFC phase-out management plan | Individual | ASP | DRK | PHA | 64 | PRP | 56 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2011-12-01 | 2012-07-01 |  | 2013-12-01 | 2014-12-01 | 35000 | -9000 | 26000 | 26000 | 100% | 0 | 0 |  | 4550 | -1170 | 3380 | 0 | 0
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (phase-out of HCFC-141b in polyurethane foam sector at Pyongyang Sonbong and Puhung Building Materials) | Multi-Year | ASP | DRK | PHA | 73 | INV | 59 | A | I | HCFC | 2.8 | 0 |  |  | 2014-11-01 | 2015-05-01 | 2016-12-31 | 2018-06-01 |  |  | 83517 | 0 | 83517 | 14639.12 | 17.53% | 68877.88 | 35979.67 | 15000 | 5846 | 0 | 1025 | 4821 | 2519 | Bids received for the PU foam equipment for the Sonbong factory opened in March 2016 and technical evaluation completed in April 2016. Further progress was slowed down by lack of the UNSCC clearance that was finally obtained in September 2016. Contract for PU foam equipment was awarded in November 2016. Auxiliary equipment for Puhung factory ordered in September 2016. Shipment delayed because the Chinese Customs required various confirmation/clearance documents regarding the equipment items. Milestones achieved: Milestone 1: Technical evaluation for the PU foam - Yes Milestone 2: Contract award for the PU foam - Yes Milestone 3: Clearance from the UNSCC - Yes Milestone 4: Auxiliary equipment procurement - Yes Milestone 5: Auxiliary equipment shipment - No Activities planned but not implemented, reasons and strategy: Although clearance from the UNSCC for the auxiliary equipment was obtained in September 2016, Chinese Customs refused to allow the shipment to proceed and requested various confirmation documents from UNIDO and Government of Italy. Actions towards next goals: Waiting for the shipment of auxiliary equipment. Was there any delay during the reporting year? Yes Any recurring problem? No Any impact on project completion date: Yes Any action required by Executive Committee? No | Execution of the contract for the PU foam equipment delayed because the supplier had to obtain a bank guarantee. Confirmation from Italian Government on expert of auxiliary equipment obtained in March 2017 and sent to Chinese customs. Milestones achieved: Milestone 1: - Pre-shipment inspection and training on PU foam at supplier - No Milestone 2: Shipment of the PU foam equipment - No Milestone 3: Shipment of auxiliary equipment-No Milestone 4: RAC training equipment procurement - Yes Milestone 5: RAC training equipment shipment - Yes Activities planned but not implemented, reasons and strategy: A letter was obtained from the UNSCC at the end of June asking UNIDO to perform technical assessment and comparison with applicable sanctions. The technical assessment done and submitted to UNSCC in July 2016. Actions towards next goals: Waiting for the shipment of PU equipment. Was there any delay during the reporting year? Yes Any recurring problem? No Any impact on project completion date: Yes Any action required by Executive Committee? No |  |  | INV |  | To request the submission of additional status report to the 79th meeting to monitor the procurement and/or delivery of the equipment.
TRF | UNEP | HCFC phase-out management plan (stage I, first tranche) (policy, and refrigeration servicing) | Multi-Year | ASP | DRK | PHA | 73 | TAS | 58 | A | I |  | 0 |  | 0 |  | 2014-11-01 | 2015-07-01 | 2017-12-01 |  | 2016-12-01 |  | 43500 | -33196.85 | 10303.15 | 10073.58 | 97.77% | 229.57 | 229.57 |  | 5655 | -4315.59 | 1309.5659 | 29.8441 | 29.8441 | The project is transferred | The project is transferred
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing and monitoring) | Multi-Year | ASP | DRK | PHA | 73 | TAS | 60 | A | I |  | 0 | 0 |  |  | 2014-11-01 | 2015-09-01 | 2016-12-31 | 2018-06-01 |  |  | 40183 | 0 | 40183 | 5910.28 | 14.71% | 34272.72 | 0 | 15000 | 2813 | 0 | 414 | 2399 | 0 | Monitoring mission for preparation of the 3rd tranche conducted in August/September 2016. Procurement of RAC training equipment initiated in April 2016, supplier selected in May and shipment delivered in August 2016. Pilot training workshop for RAC service technicians conducted in early September 2016. Milestones achieved: Milestone 1: Monitoring mission conducted - Yes Milestone 2: 3rd tranche request prepared - Yes Milestone 3: RAC training equipment procurement - Yes Milestone 4: RAC training equipment shipment - Yes Milestone 5: Pilot training workshop for RAC service technicians - Yes Actions towards next goals: Waiting for the re-opening of the funding channel. Was there any delay during the reporting year? Yes Any recurring problem? No Any impact on project completion date: Yes Any action required by Executive Committee? No | Technical specification for equipment for R&R network prepared in January 2017 but procurement delayed by lack of response from the NOU/NCCE. After opening of the financial channel to DPRK by UNDP, actions towards establishment of PMU initiated. Milestones achieved: Milestone 1: R&R network equipment procurement - No Milestone 2: R&R network equipment shipment - No Milestone 3: PMU establishment (recruiting 2 national experts) - Yes Milestone 4: Follow-up - Yes Actions towards next goals: Publish RFx for R&R equipment, technical evaluation of bids. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: Yes Any action required by Executive Committee? No |  |  | INV |  | To request the submission of additional status report to the 79th meeting to monitor the resolution of the issue of the funding disbursement mechanism.
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) (phase-out of HCFC-141b in polyurethane foam sector at Pyongyang Sonbong and Puhung Building Materials) | Multi-Year | ASP | DRK | PHA | 75 | INV | 62 | A | I | HCFC | 14.5 | 0 |  |  | 2015-11-01 | 2016-07-01 | 2018-12-01 | 2019-03-01 |  |  | 428180 | 0 | 428180 | 4411.65 | 1.03% | 423768.35 | 287102.99 | 50000 | 29973 | 0 | 0 | 29973 | 20097.2093 | As above for DRK/PHA/73/INV/59 | As above for DRK/PHA/73/INV/59 |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) (policy, refrigeration servicing and monitoring) | Multi-Year | ASP | DRK | PHA | 75 | TAS | 63 | A | I |  | 0 | 0 |  |  | 2015-11-01 | 2016-08-01 | 2018-12-01 | 2018-12-18 |  |  | 78500 | 0 | 78500 | 33955.73 | 43.26% | 44544.27 | 22656.09 | 15000 | 5495 | 0 | 0 | 5495 | 1585.9263 | As above for DRK/PHA/73/TAS/60 | As above for DRK/PHA/73/TAS/60 |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, third tranche) (policy, refrigeration servicing and monitoring) | Multi-Year | ASP | DRK | PHA | 77 | INV | 64 | A | I | HCFC | 2.1 | 0 |  |  | 2016-11-01 |  | 2019-12-31 | 2019-12-18 |  |  | 167867 | 0 | 167867 | 0 | 0% | 167867 | 0 | 30000 | 11751 | 0 | 0 | 11751 | 0 | Project approved at the 77th ExCom. | As above for DRK/PHA/73/TAS/60
FIN | UNIDO | Closure of ODS production plant | Multi-Year | ASP | DRK | PRO | 36 | INV | 17 | A | R | CFC | 0 | 0 | 500 | 500 | 2002-03-01 | 2002-10-01 | 2003-03-01 |  | 2002-10-01 | 2003-05-01 | 1344350 | 0 | 1344350 | 1344350 | 100% | 0 | 0 |  | 67217 | 0 | 67217 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Closure of ODS production plant: verification of complete closure of all CFC-11 and CFC-12 production facilities (second tranche) | Multi-Year | ASP | DRK | PRO | 42 | INV | 33 | A | I | CFC | 0 | 0 | 1250 | 1250 | 2004-04-01 | 2004-09-01 | 2005-04-01 |  | 2004-06-01 | 2004-12-01 | 733700 | 0 | 733700 | 733700 | 100% | 0 | 0 |  | 36685 | 0 | 36685 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Closure of ODS production plant (third tranche) | Multi-Year | ASP | DRK | PRO | 49 | INV | 43 | A | I |  | 0 | 0 | 2530 | 2530 | 2006-07-01 | 2006-11-01 | 2008-12-01 |  | 2006-12-01 | 2008-04-01 | 488750 | 0 | 488750 | 488750 | 100% | 0 | 0 |  | 24438 | 0 | 24438 | 0 | 0 | FIN |  |  |  | INV
FIN | UNEP | Development of a refrigerant management plan | RMP | ASP | DRK | REF | 35 | PRP | 15 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2003-03-01 | 2002-08-01 |  | 2003-06-01 | 2005-05-01 | 60000 | -13466 | 46534 | 46534 | 100% | 0 | 0 |  | 7800 | -1750.5 | 6049.5 | 0 | 0
FIN | UNIDO | Preparation of investment projects in the refrigeration sector (CFC) | Individual | ASP | DRK | REF | 39 | PRP | 24 | A | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-04-01 | 2004-09-01 | 20000 | -267 | 19733 | 19732.67 | 100% | 0.33 | 0 |  | 1500 | -22 | 1478 | 0 | 0 | FIN
FIN | UNIDO | Sectoral phase-out in domestic refrigeration sector by conversion of refrigeration and compressor manufacture at 5th October Electronic and Automation Company (first tranche) | Multi-Year | ASP | DRK | REF | 40 | INV | 26 | A | I | CFC | 0 | 0 |  |  | 2003-07-01 | 2003-10-01 | 2004-07-01 |  | 2004-12-01 | 2008-07-01 | 384000 | 0 | 384000 | 384000 | 100% | 0 | 0 |  | 28800 | 0 | 28800 | 0 | 0 | FIN
FIN | UNEP | Monitoring the activities in the refrigeration servicing subsector | Individual | ASP | DRK | REF | 40 | TAS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2003-09-01 | 2006-07-01 |  | 2004-12-01 | 2005-12-01 | 10000 | -5000 | 5000 | 5000 | 100% | 0 | 0 |  | 1300 | -650 | 650 | 0 | 0
FIN | UNIDO | Provision of basic tools for the registered service workshops | RMP Update | ASP | DRK | REF | 40 | TAS | 29 | A | I | CFC | 0 | 0 |  |  | 2003-07-01 | 2004-06-01 | 2006-07-01 |  | 2005-09-01 | 2006-09-01 | 100000 | -10480 | 89520 | 89519.9 | 100% | 0.1 | 0 |  | 9000 | -943 | 8057 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNEP | Training of refrigeration service technicians in good servicing practices | Individual | ASP | DRK | REF | 40 | TRA | 27 | A | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2003-09-01 | 2006-07-01 |  | 2004-12-01 | 2008-12-01 | 70000 | -2171 | 67829 | 67829 | 100% | 0 | 0 |  | 9100 | -282 | 8818 | 0 | 0
FIN | UNEP | Assistance for the development of a licensing system and training of customs officers | Individual | ASP | DRK | REF | 40 | TRA | 28 | A | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2004-06-01 | 2006-07-01 |  | 2005-08-01 | 2006-01-01 | 50000 | -5486 | 44514 | 44514 | 100% | 0 | 0 |  | 6500 | -713 | 5787 | 0 | 0
FIN | UNIDO | Sectoral phase-out in domestic refrigeration sector by conversion of refrigeration and compressor manufacture at 5th October Electronic and Automation Company (second tranche) | Multi-Year | ASP | DRK | REF | 42 | INV | 32 | A | I | CFC | 56 | 56 |  |  | 2004-04-01 | 2004-08-01 | 2005-12-01 |  | 2009-12-01 | 2010-12-01 | 981011 | -33 | 980978 | 980978.41 | 100% | -0.41 | 0 |  | 73576 | -3 | 73573 | 0 | 0 | FIN |  |  |  | INV
COM | UNIDO | Preparation for HCFC phase-out investment activities (commercial refrigeration sector) | Individual | ASP | DRK | REF | 64 | PRP | 53 | A | I |  | 0 | 0 |  |  | 2011-07-01 | 2011-11-01 | 2012-07-31 |  | 2015-12-01 |  | 30000 | 0 | 30000 | 29931.55 | 99.77% | 68.45 | 0 | 1 | 2250 | 0 | 2245 | 5 | 0 | The project was operationally completed. |  |  |  | NON-INV
FIN | UNEP | Country programme preparation | Individual | ASP | DRK | SEV | 17 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-10-01 | 1996-10-01 |  | 1996-10-01 | 1997-02-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNEP | Establishment of a National Ozone Cell | Individual | ASP | DRK | SEV | 21 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1998-03-01 | 2000-02-01 |  | 2000-12-01 | 2003-06-01 | 142560 | 0 | 142560 | 142560 | 100% | 0 | 0 |  | 18533 | 0 | 18533 | 0 | 0
FIN | UNIDO | Project formulation of investment projects in all sectors | Individual | ASP | DRK | SEV | 21 | PRP | 03 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-06-01 | 1998-02-01 |  | 2000-10-01 | 2001-07-01 | 70000 | -1720 | 68280 | 68280 | 100% | 0 | 0 |  | 9100 | -238 | 8862 | 0 | 0 | FIN
FIN | UNEP | Renewal of institutional strengthening | Individual | ASP | DRK | SEV | 32 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2003-08-01 | 2003-01-01 |  | 2003-10-01 | 2003-12-01 | 95040 | 0 | 95040 | 95040 | 100% | 0 | 0 |  | 12355 | 0 | 12355 | 0 | 0
FIN | UNEP | Preparation of country programme update | Individual | ASP | DRK | SEV | 36 | CPG | 16 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-03-01 | 2003-04-01 |  | 2003-10-01 | 2005-05-01 | 30000 | -684 | 29316 | 29316 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | ASP | DRK | SEV | 41 | INS | 31 | A | I | CFC | 10.2 | 9.8 | 0 | 0 | 2003-12-01 | 2004-04-01 | 2005-12-01 |  | 2005-12-01 | 2010-12-01 | 123552 | 0 | 123552 | 123552 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | ASP | DRK | SEV | 47 | INS | 41 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-02-01 | 2007-12-01 |  | 2008-12-01 | 2009-12-01 | 123552 | 0 | 123552 | 123552 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase V) | Individual | ASP | DRK | SEV | 53 | INS | 49 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2010-04-01 | 2009-11-01 |  | 2011-01-01 | 2011-07-01 | 130000 | 0 | 130000 | 130000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of institutional strengthening project (phases VI and VII: 1/2010-12/2013) | Individual | ASP | DRK | SEV | 68 | INS | 57 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2014-04-01 | 2013-12-01 | 2017-12-01 |  |  | 260000 | 0 | 260000 | 122275.99 | 47.03% | 137724.01 | 0 | 13772.401 | 0 | 0 | 0 | 0 | 0 | Brief progress report(actual/planned): Discussions took place in Dec 2016 with UNIDO and UN HQ on possible funds transfer. No progress. Needs ExCom guidance on the way forward. | Brief progress report(actual/planned): No progress. Needs ExCom guidance on the way forward |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor project implementation progress and the disbursement rate of approved funds.
COM | UNEP | Survey of ODS alternatives at the national level | Individual | ASP | DRK | SEV | 74 | TAS | 61 | A | I |  | 0 |  | 0 |  | 2015-05-01 |  | 2016-05-01 |  | 2016-12-01 |  | 110000 | 0 | 110000 | 0 | 0% | 110000 | 67.38 | 0 | 14300 | 0 | 0 | 14300 | 8.7594 | Funds to be returned due to inability to conduct the survey by the set deadlines. Needs ExCom guidance. | Funds to be returned due to inability to conduct the survey by the set deadlines. Needs ExCom guidance.
FIN | UNIDO | Conversion of metal cleaning processes from ODS solvents to vapour degreasing at Unsan Tools Factory (UTF) | Individual | ASP | DRK | SOL | 23 | INV | 05 | A | I | CTC | 110 | 110 |  |  | 1997-11-01 | 1999-06-01 | 1999-06-01 |  | 1998-12-01 | 2001-07-01 | 311922 | 0 | 311922 | 311922.08 | 100% | -0.08 | 0 |  | 40550 | 0 | 40550 | 0 | 0 | FIN
FIN | UNIDO | Conversion of metal cleaning processes from ODS solvent to vapour at Pyongyang September 18 Bearings Factory | Individual | ASP | DRK | SOL | 26 | INV | 10 | A | I | CTC | 121 | 121 |  |  | 1998-11-01 | 1999-06-01 | 2000-06-01 |  | 2000-12-01 | 2002-09-01 | 1081024 | -2425 | 1078599 | 1078598.62 | 100% | 0.38 | 0 |  | 128913 | -455 | 128458 | 0 | 0 | FIN
FIN | UNIDO | Conversion of remaining metal cleaning processes from ODS solvents to vapour degreasing at Unsan Tools Factory (UTF) | Individual | ASP | DRK | SOL | 26 | INV | 11 | A | I | CTC | 168 | 168 |  |  | 1998-11-01 | 1999-11-01 | 2000-06-01 |  | 2001-12-01 | 2002-12-01 | 490157 | -2198 | 487959 | 487958.96 | 100% | 0.04 | 0 |  | 63720 | -386 | 63334 | 0 | 0 | FIN
FIN | UNIDO | Conversion of metal cleaning processes from CTC solvent to TCE vapour degreasing at Ceramic Tools Factory (CTF) | Individual | ASP | DRK | SOL | 28 | INV | 12 | A | I | CTC | 19.8 | 19.8 |  |  | 1999-07-01 | 2000-08-01 | 2000-08-01 |  | 2001-12-01 | 2002-12-01 | 206657 | 0 | 206657 | 206657 | 100% | 0 | 0 |  | 26865 | 0 | 26865 | 0 | 0 | FIN
FIN | UNIDO | Preparation for four projects in the solvent (CTC) sector | Individual | ASP | DRK | SOL | 33 | PRP | 14 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-07-01 | 2002-10-01 |  | 2002-12-01 | 2003-05-01 | 70000 | -17 | 69983 | 69983.13 | 100% | -0.13 | 0 |  | 9100 | -17 | 9083 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of cleaning installations from carbon tetrachloride to aqueous cleaning techniques at the Gumsong Tractor Factory (GST) | Individual | ASP | DRK | SOL | 36 | INV | 18 | A | I | CTC | 198 | 198 |  |  | 2002-03-01 | 2002-06-01 | 2004-09-01 |  | 2004-12-01 | 2006-05-01 | 1932207 | 0 | 1932207 | 1932207.01 | 100% | -0.01 | 0 |  | 222543 | -1 | 222542 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of cleaning processes from CTC to aqueous and solvent cleaning techniques at Huichon February 26 Factory (HUI) | Individual | ASP | DRK | SOL | 37 | INV | 19 | A | I | CTC | 209 | 209 |  |  | 2002-07-01 | 2003-04-01 | 2005-01-01 |  | 2004-12-01 | 2006-05-01 | 1945477 | -950 | 1944527 | 1944527.06 | 100% | -0.06 | 0 |  | 224002 | -443 | 223559 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of methyl chloroform and CTC to non-ODS solvent cleaning in the plating workshop of the Taedong-gang Television Factory (PTV), Taedong-gang District, Pyongyang City | Individual | ASP | DRK | SOL | 38 | INV | 20 | A | I | CTC | 59.8 | 59.8 |  |  | 2002-11-01 | 2003-12-01 | 2004-12-01 |  | 2005-06-01 | 2006-07-01 | 597886 | -4408 | 593478 | 593477.81 | 100% | 0.19 | 0 |  | 75767 | -484 | 75283 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of Cleaning Processes from CTC to perchloroethylene cleaning at the galvanising workshop of the Pyongyang Illuminating Fixtures Factory (PIF) | Individual | ASP | DRK | SOL | 38 | INV | 21 | A | I | CTC | 29.7 | 29.7 |  |  | 2002-11-01 | 2004-06-01 | 2004-06-01 |  | 2004-12-01 | 2006-09-01 | 230172 | -59 | 230113 | 230112.94 | 100% | 0.06 | 0 |  | 29922 | -7 | 29915 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of cleaning processes from CTC (formerly methyl chloroform) to perchloroethylene cleaning at the Plating Workshop (PLT) of the refrigeration factory of the 5 October Automation Complex, Pyongchon District, Pyongyang City | Individual | ASP | DRK | SOL | 38 | INV | 22 | A | I | CTC | 69.3 | 69.3 |  |  | 2002-11-01 | 2004-07-01 | 2004-12-01 |  | 2004-12-01 | 2006-05-01 | 508068 | -1981 | 506087 | 506086.6 | 100% | 0.4 | 0 |  | 65887 | -306 | 65581 | 0 | 0 | FIN |  |  |  | INV
CLO | IBRD | Project preparation for the conversion of six aerosol plants from CFC-12 to LPG |  | LAC | ECU | ARS | 06 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1992-12-01 |  |  | 1992-12-01 | 300000 | -300000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | USA | Technical assistance in aerosol project preparation |  | LAC | ECU | ARS | 08 | PRP | 07 | A | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1993-04-01 |  | 1993-04-01 | 1993-04-01 | 6000 | 0 | 6000 | 6000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1992
FIN | IBRD | Conversion of 18 aerosol plants to hydrocarbon propellants (Laboratorios Windsor (60 ton CFC/year), Pro Quim (6 ton), Jabonería Nacional (50 ton), Camposa (5 ton) and 14 other plants (169 ton) | Individual | LAC | ECU | ARS | 09 | INV | 12 | N | I | CFC | 290 | 82 | 0 | 0 | 1993-03-01 | 1994-04-01 | 1995-03-01 |  | 1995-09-01 | 1995-10-01 | 697000 | -365172 | 331828 | 331828 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | A complete phaseout in the aerosol sector has been achieved through this project component. All small aerosol producers have agreed to have their cans filled by Windsor Laboratories, Ecuador's largest aerosol filler. Balance to be returned to MF by Nov/99. |  |  |  | INV | 0
CLO | IBRD | Project preparation for the reduction of CFC-11 use in foam insulation at three refrigerator manufacturing plants (Indurama, Durex, Ecasa) |  | LAC | ECU | FOA | 06 | PRP | 06 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1992-12-01 |  |  | 1992-12-01 | 100000 | -100000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | USA | Feasibility study for reduction of CFC-11 in rigid polyurethane foam insulation for refrigerators using water/CO2 formulation |  | LAC | ECU | FOA | 08 | PRP | 08 | A | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1993-03-01 |  | 1993-03-01 | 1993-03-01 | 41000 | 50000 | 91000 | 91000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Adjustment of US $50,000 credited against 1993 contributions (11th Meeting).
FIN | IBRD | Reduction of CFC-11 use in foam insulation at three refrigerator manufacturing plants: Indurama, Durex, and Ecasa | Individual | LAC | ECU | FOA | 09 | INV | 10 | N | I | CFC | 51 | 126.4 | 0 | 0 | 1993-03-01 | 1994-04-01 | 1994-03-01 |  | 1995-11-01 | 1997-12-01 | 665000 | 0 | 665000 | 665000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Enterprises have used funds to completely phaseout CFC-11 through adoption of HCFC-141b. PCR completed. |  |  | 1995-07-01 | INV | 0
FIN | IBRD | Elimination of CFC-11 in the fabrication of flexible foams by replacement with methylene chloride at an automobile and furniture component manufacturing plant belonging to Elasto S.A. | Individual | LAC | ECU | FOA | 26 | INV | 24 | N | I | CFC | 32 | 32 | 0 | 0 | 1998-11-01 | 2001-12-26 | 2000-06-01 |  | 2002-10-01 | 2002-11-01 | 187286 | 0 | 187286 | 187286 | 100% | 0 | 0 |  | 24347.18 | 0 | 24347.18 | 0 | 0 | Project successfully completed in both physical and financial terms, and total funding disbursed. PCR under preparation. |  |  |  | INV | 0
FIN | UNIDO | Preparation for HCFC phase-out investment activities (foam manufacturing sector) | Individual | LAC | ECU | FOA | 60 | PRP | 46 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-06-01 | 2011-04-30 |  | 2012-03-01 | 2012-05-01 | 60000 | 0 | 60000 | 59999.53 | 100% | 0.47 | 0 |  | 4500 | 0 | 4500 | 0 | 0 | FIN
FIN | IBRD | Project preparation in the methyl bromide sector for cut flowers and tobacco |  | LAC | ECU | FUM | 24 | PRP | 21 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-09-30 | 1998-12-01 |  | 1999-06-01 | 1999-06-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | IBRD | Demonstration project for testing methyl bromide alternatives in soil treatment for the flower growing industry | Individual | LAC | ECU | FUM | 26 | TAS | 23 | N | I | MBR | 15 | 15 | 0 | 0 | 1998-11-01 | 2003-12-01 | 2005-11-01 |  | 2009-06-01 | 2009-09-01 | 244244 | -20203.07 | 224040.93 | 224040.93 | 100% | 0 | 0 |  | 31751.72 | -2626.4 | 29125.32 | 0 | 0 | Second testing was completed in Jun 09. Results were positive, reconfirming that the alternative substance (Agrocelhone) is effective for pest control. National consumption of Methyl Bromide by the closing of the WB umbrella ODS project in Sep 09 was 51 ODP MT. |  |  |  | INV | 0
FIN | IBRD | Project preparation in the methyl bromide sector |  | LAC | ECU | FUM | 33 | PRP | 29 | A | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2002-11-01 | 2001-12-01 |  | 2002-11-01 | 2002-11-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 |  | 4550 | 0 | 4550 | 0 | 0 | MeBr phaseout plan for the rose plant nursery sector approved at the 38th ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | Technology change for the phase-out of methyl bromide in the rose plant nursery sector | Individual | LAC | ECU | FUM | 38 | INV | 31 | N | I | MBR | 37.2 | 37.2 | 0 | 0 | 2002-11-01 | 2003-12-01 | 2005-11-01 |  | 2005-01-01 | 2005-02-01 | 597945 | 0 | 597945 | 597945 | 100% | 0 | 0 |  | 75774 | 0 | 75774 | 0 | 0 | Project completed. |  |  |  | INV | 0
CLO | IBRD | Preparation of a methyl bromide project |  | LAC | ECU | FUM | 45 | PRP | 34 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 |  | 2005-12-01 |  |  | 2010-07-01 | 25000 | -25000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 1875 | -1875 | 0 | 0 | 0 | Funding returned to the MLF. |  |  |  | Non-INV | 0
FIN | UNIDO | Preparation of investment activities in cut-flowers production | Individual | LAC | ECU | FUM | 63 | PRP | 53 | A | I |  | 0 | 0 |  |  | 2011-04-01 | 2011-05-01 | 2012-03-31 |  | 2012-03-01 | 2012-05-01 | 45000 | -111 | 44889 | 44889.25 | 100% | -0.25 | 0 |  | 3375 | -8 | 3367 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Technical assistance to eliminate the remaining consumption of methyl bromide to be in compliance with the total phase-out | Individual | LAC | ECU | FUM | 65 | INV | 57 | A | I | MBR | 40.8 | 40.8 |  |  | 2011-11-01 | 2012-03-01 | 2014-11-30 |  | 2014-12-01 | 2015-03-01 | 317500 | -169 | 317331 | 317330.62 | 100% | 0.38 | 0 |  | 23813 | -13 | 23800 | 0 | 0 | FIN |  |  |  | INV
FIN | UNEP | Technical assistance to eliminate the remaining consumption of methyl bromide to be in compliance with the total phase-out | Individual | LAC | ECU | FUM | 65 | TAS | 56 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2014-07-01 | 2014-11-01 |  | 2014-12-01 | 2014-12-01 | 12500 | -950 | 11550 | 11550 | 100% | 0 | 0 |  | 1625 | -123.5 | 1501.5 | 0 | 0
FIN | USA | Halon-1211 management plan |  | LAC | ECU | HAL | 13 | TAS | 16 | A | I |  | 5.5 |  | 0 |  | 1994-07-01 |  | 1995-07-01 |  | 1995-07-01 | 1995-07-01 | 58000 | 0 | 58000 | 58000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | IBRD | National CFC phase-out plan: first tranche | Multiyear | LAC | ECU | PHA | 41 | INV | 32 | N | I | CFC | 11 | 11 | 0 | 0 | 2003-12-01 | 2004-12-01 | 2004-12-01 |  | 2005-04-01 | 2010-12-01 | 777326 | 0 | 777326 | 777326 | 100% | 0 | 0 |  | 58299.45 | 0 | 58299.44 | 0.01 | 0.01 | NCPP completed. Balances of subsequent tranches returned to the MLF at the 62nd ExCom. |  |  |  | INV | 0
FIN | IBRD | National CFC phase-out plan: 2005 annual programme | Multiyear | LAC | ECU | PHA | 45 | INV | 36 | N | I | CFC | 85 | 85 | 0 | 0 | 2005-04-01 | 2008-10-01 | 2006-04-01 |  | 2009-06-01 | 2010-12-01 | 439319 | -22174 | 417145 | 417145 | 100% | 0 | 0 |  | 32349 | -1632.77 | 30716.23 | 0 | 0 | NCPP completed. Balance of $22,174 returned to the 62nd ExCom (project transferred to UNIDO/UNEP at the 61st ExCom). |  |  |  | INV | 0
FIN | IBRD | National CFC phase-out plan: 2006 annual programme | Multiyear | LAC | ECU | PHA | 49 | INV | 37 | N | I | CFC | 70 | 70 | 0 | 0 | 2006-07-01 |  | 2007-12-01 |  | 2009-06-01 | 2010-12-01 | 227410 | -227410 | 0 | 0 | #DIV/0! | 0 | 0 |  | 17055 | -17055 | 0 | 0 | 0 | NCPP completed. Balance of $227,410 returned to the 62nd ExCom (project transferred to UNIDO/UNEP at the 61st ExCom). |  |  |  | INV | 0
FIN | IBRD | National CFC phase-out plan: 2007 annual programme | Multiyear | LAC | ECU | PHA | 52 | INV | 39 | N | I | CFC | 38 | 38 | 0 | 0 | 2007-07-01 |  | 2008-07-31 |  | 2009-06-01 | 2010-12-01 | 227411 | -227411 | 0 | 0 | #DIV/0! | 0 | 0 |  | 17056 | -17056 | 0 | 0 | 0 | NCPP completed. Balance of $227,411 returned to the 62nd ExCom (project transferred to UNIDO/UNEP at the 61st ExCom). |  |  |  | INV | 0
TRF | IBRD | Preparation of a HCFC phase-out management plan |  | LAC | ECU | PHA | 55 | PRP | 40 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2009-12-31 |  |  | 2009-11-01 | 150000 | -150000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 11250 | -11250 | 0 | 0 | 0 | Preparation activity transferred to UNEP and UNIDO at the 59th ExCom Meeting. |  |  |  | Non-INV | 0
FIN | IBRD | National CFC phase-out plan: 2008 annual programme | Multiyear | LAC | ECU | PHA | 56 | INV | 41 | N | I | CFC | 42 | 42 | 0 | 0 | 2008-11-01 |  | 2009-11-30 |  | 2009-09-01 | 2010-12-01 | 18334 | -18334 | 0 | 0 | #DIV/0! | 0 | 0 |  | 1375 | -1375 | 0 | 0 | 0 | Project completed. Balance of $18,334 returned to the 62nd ExCom (project transferred to UNIDO/UNEP at the 61st ExCom). |  |  |  | INV | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | ECU | PHA | 59 | PRP | 44 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-12-01 | 2010-12-01 |  | 2012-12-01 | 2013-12-01 | 75000 | -173 | 74827 | 74827 | 100% | 0 | 0 |  | 9750 | -22.49 | 9727.51 | 0 | 0
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | LAC | ECU | PHA | 59 | PRP | 45 | A | I |  | 0 | 0 |  |  | 2009-11-01 | 2010-03-01 | 2010-11-30 |  | 2012-03-01 | 2013-01-01 | 75000 | 0 | 75000 | 74999.87 | 100% | 0.13 | 0 |  | 5625 | 0 | 5625 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | National CFC phase-out plan (fifth tranche) | Multi-Year | LAC | ECU | PHA | 61 | INV | 47 | A | I | CFC | 42 | 42 |  |  | 2010-07-01 | 2010-10-01 | 2011-07-31 |  | 2011-12-01 | 2011-12-01 | 10849 | 0 | 10849 | 10848.65 | 100% | 0.35 | 0 |  | 814 | 0 | 814 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National CFC phase-out plan (third tranche) | Multi-Year | LAC | ECU | PHA | 61 | INV | 49 | A | I |  | 0 | 0 |  |  | 2010-07-01 | 2010-12-01 | 2011-07-31 |  | 2012-03-01 | 2013-04-01 | 134575 | -95 | 134480 | 134480.04 | 100% | -0.04 | 0 |  | 10093 | -7 | 10086 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National CFC phase-out plan (fourth tranche) | Multi-Year | LAC | ECU | PHA | 61 | INV | 51 | A | I |  | 0 | 0 |  |  | 2010-07-01 | 2010-12-01 | 2011-07-31 |  | 2012-03-01 | 2013-12-01 | 134576 | 0 | 134576 | 134576 | 100% | 0 | 0 |  | 10093 | 0 | 10093 | 0 | 0 | FIN |  |  |  | INV
FIN | UNEP | National CFC phase-out plan (third tranche) | Multi-Year | LAC | ECU | PHA | 61 | TAS | 48 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-06-01 | 2011-07-01 |  | 2013-12-01 | 2013-12-01 | 92835 | -75452 | 17383 | 17383 | 100% | 0 | 0 |  | 12069 | -9809.13 | 2259.87 | 0 | 0
FIN | UNEP | National CFC phase-out plan (fourth tranche) | Multi-Year | LAC | ECU | PHA | 61 | TAS | 50 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2013-05-01 | 2011-07-01 |  | 2013-12-01 | 2013-12-01 | 92835 | -38873 | 53962 | 53962 | 100% | 0 | 0 |  | 12069 | -5054.05 | 7014.95 | 0 | 0
FIN | UNEP | National CFC phase-out plan (fifth tranche) | Multi-Year | LAC | ECU | PHA | 61 | TAS | 52 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2012-09-01 | 2011-07-01 |  | 2013-12-01 | 2013-12-01 | 7485 | -272 | 7213 | 7213 | 100% | 0 | 0 |  | 973 | -35.36 | 937.64 | 0 | 0
COM | UNIDO | HCFC phase-out management plan (stage I, first tranche) (conversion of the foam manufacturing by Indurama) | Multi-Year | LAC | ECU | PHA | 65 | INV | 55 | A | I | HCFC | 15 | 15 |  |  | 2011-11-01 | 2012-03-01 | 2013-11-30 |  | 2015-12-01 |  | 1331440 | 0 | 1331440 | 1331302.73 | 99.99% | 137.27 | 44 | 1 | 99858 | 0 | 99848 | 10 | 3 | The project was operationally completed. |  |  |  | INV
FIN | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | ECU | PHA | 65 | INV | 58 | A | I |  | 0 | 0 |  |  | 2011-11-01 | 2012-08-01 | 2013-11-30 |  | 2014-08-15 | 2016-04-01 | 200500 | -31 | 200469 | 200469.43 | 100% | -0.43 | 0 |  | 15038 | -2 | 15035 | 1 | 0 | The project was financially completed and the balance was returned at the 76th ExCom. |  |  |  | INV
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | ECU | PHA | 65 | TAS | 54 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-06-01 | 2013-11-01 |  | 2012-12-01 | 2013-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
COM | UNIDO | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | ECU | PHA | 70 | INV | 60 | A | I | HCFC | 1.8 | 1.8 |  |  | 2013-07-01 | 2014-01-01 | 2016-07-31 |  | 2015-12-01 | 2016-04-01 | 86500 | 0 | 86500 | 85376.77 | 98.7% | 1123.23 | 0 | 1 | 6488 | 0 | 6403 | 85 | 0 | The project was operationally completed. |  |  |  | INV
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | LAC | ECU | PHA | 70 | TAS | 59 | A | I |  | 0.4 |  | 0 |  | 2013-07-01 | 2014-02-01 | 2016-07-01 | 2017-12-01 |  |  | 20000 | 0 | 20000 | 16786.57 | 83.93% | 3213.43 | 0 | 321.343 | 2600 | 0 | 2182.2541 | 417.7459 | 0 | Brief progress report: remaining funds (USD 8,814) committed to the procurement of ODS Identifiers. Legal arrangements: Direct Execution, no SSFA required First mission (actual/planned): n/a TOR completed (actual/planned): 0/0 First disbursement date (actual/planned): January 2014 / December 2013 - All funds disbursed? Yes. Any delay? No. - If Yes, reasons for delay & action plan to resolve: N/A - If Yes, will delay have impact on project completion date? N/A Any ongoing problems? No. If Yes, is any action required by ExCom? N/A. | Brief progress report: Purchase Order for the refrigerants identifier expected to be issued in June 2017. Legal arrangements: Direct Execution, no SSFA required First mission (actual/planned): n/a TOR completed (actual/planned): 0/0 First disbursement date (actual/planned): January 2014 / December 2013 - All funds disbursed? Yes. Any delay? No. - If Yes, reasons for delay & action plan to resolve: N/A - If Yes, will delay have impact on project completion date? N/A Any ongoing problems? No. If Yes, is any action required by ExCom? N/A.
ONG | UNIDO | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | LAC | ECU | PHA | 76 | INV | 63 | A | I |  | 0 | 0 |  |  | 2016-05-01 |  | 2018-12-31 | 2019-03-01 |  |  | 86500 | 0 | 86500 | 0 | 0% | 86500 | 3290 | 20000 | 6488 | 0 | 0 | 6488 | 247 | The project was approved in 2016 by the 76th Meeting of the ExCom. | Agreement was signed between UNIDO and MIPRO-NOU on implementation modalities. Since this is electoral year in Ecuador the project is slowed down, only the ODS destruction initiative is going on and it is expected the MoE to grant permission for the process soon. Project implementation plan was defined and will continue after second round of presidential elections. National expert to support the HPMP activities is on board. - No action required by Executive Committee |  |  | INV
ONG | UNEP | HCFC phase-out management plan (stage I, third tranche) | Multi-year | LAC | ECU | PHA | 76 | TAS | 64 | A | I |  | 0 |  | 0 |  | 2016-05-01 |  | 2018-05-01 | 2018-05-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 3000 | 3900 | 0 | 0 | 3900 | 0 | Brief Report: Project approved in 2016, 76th ExCom. Legal arrangements: Direct Execution, no SSFA required. TOR completed (actual/planned): 0/0 First disbursement date (actual/planned): 0 disbursed / May 2017 - All funds disbursed? No. Any delay? No. --- If Yes, will delay have impact on project completion date? n/a Any ongoing problems? No. --- If Yes, is any action required by ExCom? N/A. | Brief Report: Purchase Order for the acquisition of 3 refrigerant identifiers to be issued in June 2017. Detailed action plan under preparation to implement remaining funds. 2017 HCFCs Quota System issued. Legal arrangements: Direct Execution, no SSFA required. TOR completed (actual/planned): 0/0 First disbursement date (actual/planned): 0 disbursed / May 2017 - All funds disbursed? No. Any delay? No. --- If Yes, will delay have impact on project completion date? n/a Any ongoing problems? No. --- If Yes, is any action required by ExCom? N/A.
ONG | UNIDO | Verification report for stage I of HCFC phase-out management plan | Individual | LAC | ECU | PHA | 77 | TAS | 63 | A | I |  | 0 | 0 |  |  | 2016-11-01 |  | 2017-12-31 | 2017-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 20000 | 2700 | 0 | 0 | 2700 | 0 | Approved on the understanding that the verification reports should be submitted at least 60 days prior to the applicable Executive Committee meeting where the next funding tranche for its HPMP is being sought. | The verification report is being prepared and it will be submitted with the request for the fourth tranche in January 2018.
FIN | IBRD | Replacing CFC-12 refrigerant with HFC-134a at a manufacturing plant of domestic refrigerators belonging to Indurama S.A. | Individual | LAC | ECU | REF | 26 | INV | 25 | N | I | CFC | 28.38 | 28.38 | 0 | 0 | 1998-11-01 | 2002-09-01 | 2001-06-01 |  | 2002-09-01 | 2002-09-01 | 174792 | 0 | 174792 | 174792 | 100% | 0 | 0 |  | 22722.96 | 0 | 22722.96 | 0 | 0 | ODS free production started Jun. 02. Project successfully completed in both physical and financial terms and all funds disbursed. PCR is under preparation. |  |  |  | INV | 0
FIN | IBRD | Replacement of CFC-12 refrigerant with HFC-134a at a manufacturing plant of domestic refrigerators belonging to Ecuatoriana de Artefactos S.A. (ECASA) | Individual | LAC | ECU | REF | 26 | INV | 26 | N | I | CFC | 15.73 | 15.73 | 0 | 0 | 1998-11-01 | 2001-12-26 | 2000-02-01 |  | 2001-11-30 | 2002-03-01 | 188545 | 0 | 188545 | 188545 | 100% | 0 | 0 |  | 24510.85 | 0 | 24510.85 | 0 | 0 | Project successfully completed both in physical and financial terms, and all funding disbursed. PCR under preparation. |  |  |  | INV | 0
FIN | IBRD | Preparation of investment projects (1991) |  | LAC | ECU | SEV | 04 | PRP | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 92031 | -5365 | 86666 | 86666 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Country programme preparation |  | LAC | ECU | SEV | 04 | PRP | 20 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 40386 | -22201 | 18185 | 18185 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
CLO | IBRD | Country programme preparation | Individual | LAC | ECU | SEV | 06 | CPG | 04 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1993-02-01 |  |  | 1992-12-01 | 76100 | -76100 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1992) |  | LAC | ECU | SEV | 06 | PRP | 05 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 95026 | 76203 | 171229 | 171229 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Training programme for the Montreal Protocol Project Implementation Unit | Individual | LAC | ECU | SEV | 06 | TRA | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-01-01 | 1993-12-01 |  | 1994-06-01 | 1997-12-01 | 100000 | 40000 | 140000 | 140000 | 100% | 0 | 0 | 0 | 13000 | 5200 | 18200 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | USA | Support for country programme preparation |  | LAC | ECU | SEV | 07 | CPG | 09 | A | I |  | 0 |  | 0 |  | 1992-06-01 |  | 1993-09-01 |  | 1993-09-01 | 1993-09-01 | 50000 | 6000 | 56000 | 56000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Adjustment of US $6,000 credited against 1993 contributions (11th Meeting).
FIN | IBRD | Institutional strengthening | Individual | LAC | ECU | SEV | 09 | INS | 11 | N | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1994-12-01 | 1996-03-01 |  | 1997-05-01 | 1997-08-01 | 204000 | -33327 | 170673 | 170673 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Public awareness campaign has been successfully carried out. Ozone Team actively supporting project implementation. |  |  | 1997-06-01 | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1993) |  | LAC | ECU | SEV | 09 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 68000 | 13231 | 81231 | 81231 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | USA | Assistance in implementation of country programme |  | LAC | ECU | SEV | 11 | CPG | 14 | A | I |  | 0 |  | 0 |  | 1993-11-01 |  | 1994-11-01 |  | 1994-11-01 | 1994-11-01 | 11000 | 0 | 11000 | 11000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1993
FIN | IBRD | Supervision of project implementation (approved at the 9th ExCom Meeting) |  | LAC | ECU | SEV | 12 | PRP | 15 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 30000 | 15197 | 45197 | 45197 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project supervision on-going. Implementation is proceeding satisfactorily. A second phase of the Country Program is expected for CY95. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | LAC | ECU | SEV | 16 | PRP | 18 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 56745 | 0 | 56745 | 56745 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project supervision on-going. Implementation is proceeding satisfactorily. A second phase of the Country Program is expected for CY97. |  |  |  | Non-INV | 0
CLO | UNIDO | Preparation of an investment project in a plant (Elasta) for the production of polyurethane flexible foam for automotive industry | Individual | LAC | ECU | SEV | 17 | PRP | 17 | A | I |  | 0 | 0 |  |  | 1995-07-01 | 1995-10-01 | 1995-09-01 |  |  | 1999-12-01 | 15000 | -9243 | 5757 | 5757 | 100% | 0 | 0 |  | 1950 | -1203 | 747 | 0 | 0 | CLO
FIN | IBRD | Project preparation |  | LAC | ECU | SEV | 21 | PRP | 19 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1998-03-31 | 1997-12-01 |  | 1998-12-01 | 1998-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | Ongoing. |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation in the foam, refrigeration and halon sectors |  | LAC | ECU | SEV | 24 | PRP | 22 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-03-31 | 1998-12-01 |  | 1998-12-01 | 1998-12-01 | 49000 | 0 | 49000 | 49000 | 100% | 0 | 0 |  | 6370 | 0 | 6370 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects in the foam and commercial refrigeration sectors |  | LAC | ECU | SEV | 27 | PRP | 27 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-12-31 | 2001-01-01 |  | 2000-12-01 | 2000-12-01 | 24000 | 0 | 24000 | 24000 | 100% | 0 | 0 |  | 3120 | 0 | 3120 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Renewal of institutional strengthening (phase II) |  | LAC | ECU | SEV | 28 | INS | 28 | N | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2001-12-01 | 2001-08-01 |  | 2004-04-01 | 2004-04-01 | 97300 | 0 | 97300 | 97300 | 100% | 0 | 0 |  | 12649 | 0 | 12649 | 0 | 0 | NOU (MICIP) activities included work on the regulatory side, seeing thru a resolution that sets up import quotas for ODS in order to comply with the Protocol's control measures and additional agreed targets with ExCom. Public awareness activities included a series of seminars in schools in different regions of the country. |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation of a national CFC phase-out plan |  | LAC | ECU | SEV | 36 | PRP | 30 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-09-01 |  | 2003-09-01 | 2003-09-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0 | NCPP submitted and approved at the 41st ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | Extension of institutional strengthening project (phase III) | Individual | LAC | ECU | SEV | 42 | INS | 33 | N | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-12-01 | 2006-04-01 |  | 2007-02-01 | 2007-03-01 | 176800 | 0 | 176800 | 176800 | 100% | 0 | 0 |  | 13260 | 0 | 13260 | 0 | 0 | IS completed. |  |  |  | Non-INV | 0
FIN | IBRD | Extension of institutional strengthening project (phase IV, first year) | Individual | LAC | ECU | SEV | 51 | INS | 38 | N | I |  | 0 | 0 | 0 | 0 | 2007-03-01 | 2007-11-01 | 2008-03-01 |  | 2009-04-01 | 2009-09-01 | 88400 | 0 | 88400 | 88400 | 100% | 0 | 0 |  | 6630 | 0 | 6630 | 0 | 0 | Phase IV completed. ISP transferred to UNEP. |  |  |  | Non-INV | 0
FIN | IBRD | Extension of institutional strengthening project (phase IV, second year) | Individual | LAC | ECU | SEV | 56 | INS | 42 | N | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-09-01 | 2009-09-30 |  | 2009-09-01 | 2009-09-01 | 88400 | 0 | 88400 | 88400 | 100% | 0 | 0 |  | 6630 | 0 | 6630 | 0 | 0 | Ecuador has complied with all MP targets for Annex A substance phaseout and has been actively engaged in maintaining its compliance status with methyl bromide. The ISP was transferred to UNEP (starting with phase V). |  |  |  | Non-INV | 0
COM | UNEP | Extension of institutional strengthening project (phase V) | Individual | LAC | ECU | SEV | 59 | INS | 43 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2012-03-01 | 2011-11-01 |  | 2015-12-01 |  | 95767 | 81034 | 176801 | 167564.57 | 94.78% | 9236.43 | 9236.43 | 9236 | 0 | 0 | 0 | 0 | 0 | Project Completed in 2015. UNEP is waiting for UNDP Clearance Account to close this project's account. | Pending coordination of expenditure data migration from IMIS to UMOJA.
COM | UNIDO | Survey of ODS alternatives at the national level | Individual | LAC | ECU | SEV | 74 | TAS | 61 | A | I |  | 0 | 0 |  |  | 2015-05-01 | 2015-07-01 | 2016-05-31 |  | 2016-12-01 |  | 110000 | 0 | 110000 | 106184.33 | 96.53% | 3815.67 | 3440.96 | 3440.96 | 9900 | 0 | 0 | 9900 | 309.6864 | Survey was carried out by local supplier and following consultation and review of the documents by UNIDO, the report was submitted to the 77th ExCom. | The project is completed, financial closure takes place. |  |  | NON-INV
ONG | UNEP | Extension of institutional strengthening project (phase VI: 5/2016-4/2018) | Individual | LAC | ECU | SEV | 76 | INS | 62 | A | I |  | 0 |  | 0 |  | 2016-05-01 |  | 2018-04-01 | 2018-04-01 |  |  | 226305 | 0 | 226305 | 0 | 0% | 226305 | 14165.68 | 22630.5 | 0 | 0 | 0 | 0 | 0 | Brief progress Report: Project approved in 2016, 76th ExCom. Legal arrangements: Agreement being negotiated. TOR completed (actual/planned): 0/0 First disbursement date (actual/planned): 0 disbursed / Jan 2017 - All funds disbursed? No. Any delay? No. --- If Yes, will delay have impact on project completion date? n/a Any ongoing problems? No. --- If Yes, is any action required by ExCom? N/A. | Brief Report: Agreement draft and submitted for Governmental approval. National Ozone Assistant recruited. Detailed action plan under preparation. Legal arrangements: Agreement being negotiated. About 25% of funds to be directly executed by UNEP upon GOV´s request (no agreement). the first disbursment was done in January 2017 TOR completed (actual/planned): 1/1 (National Ozone Assistant position) First disbursement date (actual/planned): Jan 2017 / Jan 2017 - All funds disbursed? No.
FIN | IBRD | Preparation of a TCA phase-out project |  | LAC | ECU | SOL | 45 | PRP | 35 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-02-01 | 2005-12-01 |  | 2006-02-01 | 2006-02-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 1500 | 0 | 1500 | 0 | 0 | Results from the survey and seminar carried out in Jan 06 show that there is not enough consumption of TCA in the country, and remaining consumers are changing technologies on their own. A project will not be presented to MLF. |  |  |  | Non-INV | 0
FIN | UNIDO | Preparation of a MDI phase-out plan (CFC) | Individual | AFR | EGY | ARS | 45 | PRP | 90 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-11-01 | 2006-04-01 |  | 2006-12-01 | 2008-05-01 | 50000 | -337 | 49663 | 49663.07 | 100% | -0.07 | 0 |  | 3750 | -25 | 3725 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | Phase-out of CFC consumption in the manufacture of aerosol metered dose inhalers (MDIs) | Individual | AFR | EGY | ARS | 50 | INV | 92 | A | I | CFC | 159.5 | 159.5 |  |  | 2006-11-01 | 2007-01-01 | 2009-12-01 | 2018-07-01 |  |  | 5899000 | 0 | 5899000 | 5670508.15 | 96.13% | 228491.85 | 212359.58 | 40000 | 442425 | 0 | 425288 | 17137 | 15927 | An agreement was found for the supply of equipment and material required for the production of the test batch. The technology supplier's proposal to provide the required filling head against a commitment from the beneficiary to reimburse the cost has been approved in principal. The terms and modalities of the reimbursement have been finalized and agreement signed. Procurement of a vessel for MDIs underway. Milestones achieved: Beneficiary agreed to new test batch production: Yes Agreement terms finalized: Yes Agreement signed: Yes TOR for the purchase of a vessel for MDIs prepared Call for bids issued Offers evaluated and supplier selected Contract issued Was there any delay during the reporting year: Yes If yes, reasons and action plan: Lengthy discussions between technology supplier and beneficiary regarding the failed stability test. Lengthy negotiations on the terms and modalities of the reimbursement of required equipment. Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | Vessel under delivery to Egypt. |  |  | INV |  | Continued Monitoring
FIN | UNDP | Phase-out of CFC-11 in manufacture of flexible polyurethane foam at Misr Foam Co. | Individual | AFR | EGY | FOA | 08 | INV | 05 | A | I | CFC | 121 | 121 | 0 | 0 | 1992-10-01 | 1993-04-01 | 1993-10-01 |  | 1994-01-01 | 2003-04-01 | 497000 | 3489 | 500489 | 500489 | 100% | 0 | 0 | 0 | 64610 | 453.57 | 65063.57 | 0 | 0 | Completed in 1994. Financially completed in 2003. |  | 1992 |  | Investment
FIN | UNDP | Phase-out of CFC-11 in the manufacturing of moulded, flexible, semi-rigid and rigid polyurethane foam at Taki-Vita factory | Individual | AFR | EGY | FOA | 08 | INV | 06 | A | I | CFC | 50 | 50 | 0 | 0 | 1992-10-01 | 1993-04-01 | 1994-10-01 |  | 1995-04-01 | 2003-04-01 | 293950 | 58550 | 352500 | 352500 | 100% | 0 | 0 | 0 | 38213.5 | 7611.5 | 45825 | 0 | 0 | Completed in 1995. Financially completed in 2003. |  | 1992 |  | Investment
FIN | UNDP | Phase-out of CFC-11 in the manufacture of moulded polyurethane foams at Technopol Egypt SAE | Individual | AFR | EGY | FOA | 08 | INV | 07 | A | I | CFC | 55 | 55 | 0 | 0 | 1992-10-01 | 1993-04-01 | 1994-10-01 |  | 1994-04-01 | 2003-04-01 | 645000 | 31211 | 676211 | 676211 | 100% | 0 | 0 | 0 | 83850 | 4057.43 | 87907.43 | 0 | 0 | Completed in 1994. Financially completed in 2003. |  | 1992 |  | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of extruded polystyrene foam at Al-Sharif Plastic Factories | Individual | AFR | EGY | FOA | 09 | INV | 10 | A | I | CFC | 75 | 75 | 0 | 0 | 1993-03-01 | 1998-12-01 | 1994-06-01 |  | 2001-12-01 | 2003-04-01 | 498000 | -22472 | 475528 | 475528 | 100% | 0 | 0 | 0 | 64740 | -2921.36 | 61818.64 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1993 | 1999-12-01 | Investment
FIN | UNDP | Phase-out of CFC-11 in manufacture of molded foam at Misr Foam Co. | Individual | AFR | EGY | FOA | 09 | INV | 12 | A | I | CFC | 28 | 28 | 0 | 0 | 1993-03-01 | 1993-06-01 | 1994-03-01 |  | 1993-11-01 | 2003-04-01 | 275000 | 9431 | 284431 | 284431 | 100% | 0 | 0 | 0 | 35750 | 1226.03 | 36976.03 | 0 | 0 | Completed in 1993. Financially completed in 2003. |  | 1993 |  | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of molded flexible polyurethane foam at Modern Building Carpentry Co. (Mobica) | Individual | AFR | EGY | FOA | 10 | INV | 15 | A | I | CFC | 20 | 20 | 0 | 0 | 1993-06-01 | 1993-08-01 | 1994-06-01 |  | 1995-11-01 | 1998-12-01 | 434000 | 0 | 434000 | 434000 | 100% | 0 | 0 | 0 | 56420 | 0 | 56420 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1993 |  | Investment
FIN | UNIDO | Elimination of CFC-12 in the manufacture of extruded polystyrene foam at (ADVECHEMS) | Individual | AFR | EGY | FOA | 10 | INV | 16 | A | I | CFC | 196 | 183.3 |  |  | 1993-06-01 | 1994-03-01 | 1994-06-01 |  | 1994-12-01 | 2000-12-01 | 904000 | 0 | 904000 | 904000 | 100% | 0 | 0 |  | 117520 | -44 | 117476 | 0 | 0 | FIN
FIN | UNDP | Elimination of CFC-11 in the manufacture of molded rigid polyurethane foam at Cairo Light Industries Co. (Olympic Electric) | Individual | AFR | EGY | FOA | 10 | INV | 17 | A | I | CFC | 75 | 75 | 0 | 0 | 1993-06-01 | 1993-08-01 | 1994-12-01 |  | 1995-11-01 | 2000-12-01 | 940000 | -28083.76 | 911916.24 | 911916 | 100% | 0.24 | 0 | 0 | 122200 | -3650.89 | 118549.08 | 0.03 | 0 | Completed in 1995. Financially completed in 2000. |  | 1993 |  | Investment
FIN | UNDP | Conversion to CFC-11 free technology in the manufacture of rigid polyurethane foam (PUF) at Specialized Engineering Contracting Co. | Individual | AFR | EGY | FOA | 11 | INV | 18 | A | I | CFC | 15 | 15 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1994-05-01 |  | 1994-12-01 | 1998-12-01 | 85000 | -5398 | 79602 | 79602 | 100% | 0 | 0 | 0 | 11050 | -702 | 10348 | 0 | 0 | Completed in 1994. Financially completed in 1998. |  | 1993 |  | Investment
FIN | UNDP | Conversion to CFC-11 free technology in the manufacture of flexible polyurethane foam at Alex Foam (formerly Dekheila Chemical Industries Co.) | Individual | AFR | EGY | FOA | 11 | INV | 19 | A | I | CFC | 130 | 130 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1994-10-01 |  | 1995-11-01 | 1998-12-01 | 650000 | -82388 | 567612 | 567612 | 100% | 0 | 0 | 0 | 84500 | -10710 | 73790 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1993 |  | Investment
FIN | UNDP | Conversion to CFC-11 free technology in the manufacture of flexible polyurethane foam (PUF) at Horse Foam Co. | Individual | AFR | EGY | FOA | 11 | INV | 20 | A | I | CFC | 120 | 120 | 0 | 0 | 1993-11-01 | 1995-11-01 | 1994-08-01 |  | 1997-03-01 | 2000-07-01 | 385000 | -107636 | 277364 | 277364 | 100% | 0 | 0 | 0 | 50050 | -13992.68 | 36057.32 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1993 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | AFR | EGY | FOA | 11 | PRP | 21 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-01 | 1995-01-01 |  | 1994-12-01 | 1997-12-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1993 |  | Investment
FIN | UNDP | Conversion to CFC free-technology in the manufacture of flexible polyurethane foam at Foam Industrial and Hyma | Individual | AFR | EGY | FOA | 12 | INV | 22 | A | I | CFC | 170 | 170 | 0 | 0 | 1994-03-01 | 1995-10-01 | 1995-06-01 |  | 1997-03-01 | 2000-07-01 | 525000 | -11897.74 | 513102.26 | 513102 | 100% | 0.26 | 0 | 0 | 68250 | -1546.71 | 66703.26 | 0.03 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Conversion to CFC free-technology in the manufacture of rigid molded and miscellaneous PUF at 5 plants: Tiba Air, Egat Company, Solar Energy Company, Ismailia Aluminum Company, and Fu Tech Company | Individual | AFR | EGY | FOA | 12 | INV | 26 | A | I | CFC | 44.2 | 44.2 | 0 | 0 | 1994-03-01 | 1994-06-01 | 1995-03-01 |  | 1997-03-01 | 1997-11-01 | 870000 | -107668 | 762332 | 762332 | 100% | 0 | 0 | 0 | 113100 | -13997.13 | 99102.87 | 0 | 0 | Completed in 1997. Financially completed in 1997. |  | 1994 |  | Investment
FIN | UNDP | Conversion to CFC free-technology at Scib Chemical Company | Individual | AFR | EGY | FOA | 12 | INV | 27 | A | I | CFC | 12.4 | 12.4 | 0 | 0 | 1994-03-01 | 1995-11-01 | 1995-03-01 |  | 1995-11-01 | 2003-02-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | Completed in 1995. Financially completed in 2003. |  | 1994 |  | Investment
FIN | UNDP | Conversion to CFC free-technology at El Fateh | Individual | AFR | EGY | FOA | 12 | INV | 28 | A | I | CFC | 59 | 59 | 0 | 0 | 1994-03-01 | 1996-01-01 | 1995-03-01 |  | 2002-03-01 | 2003-01-01 | 496000 | -1 | 495999 | 495999 | 100% | 0 | 0 | 0 | 64480 | -0.13 | 64479.87 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1994 | 1997-09-01 | Investment
FIN | UNDP | Conversion to CFC free-technology at Industrial Engineering Company for Construction and Development (Icon) | Individual | AFR | EGY | FOA | 12 | INV | 29 | A | I | CFC | 51 | 51 | 0 | 0 | 1994-03-01 | 1996-01-01 | 1995-03-01 |  | 1999-10-01 | 2001-12-01 | 498000 | 0 | 498000 | 498000 | 100% | 0 | 0 | 0 | 64740 | 0 | 64740 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1994 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacturing of rigid PUF at seven enterprises: GMC, Petrojet, Modern Products, Cairo General Contractors Co., Egyptian Solar Energy, Tawifika, Helwan | Individual | AFR | EGY | FOA | 15 | INV | 36 | A | I | CFC | 69 | 69 | 0 | 0 | 1994-12-01 | 1995-05-01 | 1995-12-01 |  | 2000-12-01 | 2002-11-01 | 780000 | -292655 | 487345 | 487345 | 100% | 0 | 0 | 0 | 101400 | -38045.15 | 63354.85 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1994 | 1999-07-01 | Investment
CLO | UNDP | Conversion to CFC-free technology in the manufacture of flexible slabstock PUF at El-Tawil Manufacturing Company | Individual | AFR | EGY | FOA | 15 | INV | 46 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-10-01 | 1995-12-01 |  |  | 2000-12-01 | 121000 | -91977.38 | 29022.62 | 29023 | 100% | -0.38 | 0 | 0 | 15730 | -11956.79 | 3773.26 | -0.050004 | 0 | Canceled in 1999. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Conversion to CFC free technology in the manufacture of flexible molded PUF and integral skin foam at El Shabrawi | Individual | AFR | EGY | FOA | 18 | INV | 48 | A | I | CFC | 16 | 16 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1997-05-01 |  | 1998-09-01 | 1999-12-01 | 143000 | 0 | 143000 | 143000 | 100% | 0 | 0 | 0 | 18590 | 0 | 18590 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1995 |  | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | AFR | EGY | FOA | 21 | PRP | 60 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2002-03-01 | 40000 | -7520 | 32480 | 32480 | 100% | 0 | 0 | 0 | 5200 | -977.6 | 4222.4 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Phaseout of the remaining ODS consumption in the foam sector (11 enterprises) | Individual | AFR | EGY | FOA | 22 | INV | 64 | A | I | CFC | 319 | 319 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-05-01 |  | 2005-01-01 | 2007-01-01 | 1672000 | -18136 | 1653864 | 1653864 | 100% | 0 | 0 | 0 | 217360 | -2357.68 | 215002.32 | 0 | 0 | Completed in 2005. Financially completed in 2007. |  | 1997 | 2000-12-01 | Investment
FIN | UNDP | Preparation for validation of low-cost hydrocarbon in foams | Individual | AFR | EGY | FOA | 57 | PRP | 99 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-05-01 | 2010-03-01 |  | 2009-12-01 | 2012-04-01 | 30000 | -7208 | 22792 | 22792 | 100% | 0 | 0 | 0 | 2250 | -540.6 | 1709.4 | 0 | 0 | Financially completed in 2012. | Financially completed in 2012. | 2009 |  | Investment
FIN | UNDP | Validation/demonstration of low cost options for the use of hydrocarbons as foaming agent in the manufacture of polyurethane foams | Individual | AFR | EGY | FOA | 58 | DEM | 100 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-07-01 | 2010-05-01 | 2010-07-01 |  | 2015-12-01 | 2016-12-01 | 473000 | 0 | 473000 | 459257 | 97.09% | 13743 | 0 | 0 | 35475 | 0 | 34444.275 | 1030.725 | 0 | Financially completed in 2016. | Missions by senior foam expert held in April and May 2015. Due to yet unresolved difficulties with DOW institutional changes, no substantial progress had been achieved with additional tests to complete the complementary report's findings on additional operational costs savings. Currently, the complementary report is being finalized with existing data for submission to the 75th ExCom. The project is set for closure. | 2009 |  | Non-Investment
FIN | UNIDO | Preparation for HCFC phase-out investment activities (appliance foam sector) | Individual | AFR | EGY | FOA | 61 | PRP | 102 | A | I |  | 0 | 0 |  |  | 2010-07-01 | 2010-10-01 | 2011-07-31 |  | 2010-12-01 | 2012-12-01 | 100000 | -374 | 99626 | 99626.09 | 100% | -0.09 | 0 |  | 7500 | -28 | 7472 | 0 | 0 | FIN |  |  |  | NON-INV
COM | UNIDO | Phase-out of HCFC-141b from the manufacturing of polyurethane foam at Mondial Freezers Company | Multi-Year | AFR | EGY | FOA | 62 | INV | 104 | A | I | HCFC | 6.6 | 6.6 |  |  | 2010-12-01 | 2010-12-01 | 2012-12-31 |  | 2015-12-01 | 2016-09-01 | 436300 | 0 | 436300 | 436080.31 | 99.95% | 219.69 | 0 | 1 | 32723 | 0 | 32706 | 17 | 0 | The project was operationally completed. |  |  |  | INV
FIN | UNDP | Conversion from HCFC-141b to n-pentane in the manufacture of polyurethane rigid insulation foam panels at MOG for Engineering and Industry | Multi-year | AFR | EGY | FOA | 62 | INV | 105 | N | I | HCFC | 13.9 | 13.9 | 0 | 0 | 2010-12-01 | 2011-04-01 | 2012-06-01 |  | 2014-06-01 | 2015-04-01 | 790400 | 0 | 790400 | 788642 | 99.78% | 1758 | 1758 | 0 | 59280 | 0 | 59148.15 | 131.85 | 131.85 | Financially Completed in 2015. | MOG is awaiting instructions on local works from the technology supplier before starting. | 2010 |  | Investment
FIN | UNDP | Conversion from HCFC-141b to methyl formate in the manufacture of polyurethane rigid insulation foam for water heaters at Fresh Electric for Home Appliances | Multi-year | AFR | EGY | FOA | 62 | INV | 106 | N | I | HCFC | 2.4 | 2.4 | 0 | 0 | 2010-12-01 | 2013-03-01 | 2012-06-01 |  | 2013-12-01 | 2014-08-01 | 124500 | 0 | 124500 | 124500 | 100% | 0 | 0 | 0 | 11205 | 0 | 11205 | 0 | 0 | Financially completed in 2014. | Completed in 2013. Equipment has arrived to FRESH, and is expected for installation in April 2014. | 2010 |  | Investment
FIN | UNDP | Conversion from HCFC-141b to methyl formate in the manufacture of polyurethane spray foams at Specialized Engineering Contracting Co. | Multi-year | AFR | EGY | FOA | 62 | INV | 107 | N | I | HCFC | 11.2 | 11.2 | 0 | 0 | 2010-12-01 | 2013-03-01 | 2012-06-01 |  | 2014-09-01 | 2015-06-01 | 178000 | 0 | 178000 | 178000 | 100% | 0 | 0 | 0 | 16020 | 0 | 16020 | 0 | 0 | Financially Completed in 2015. | Project is expected for completion after the next milestone is completed, which is the next visit of international expert in Q2 2014. | 2010 |  | Investment
FIN | UNDP | Conversion from HCFC-141b to n-pentane in the manufacture of polyurethane rigid insulation foam panels at Cairo Foam | Multi-year | AFR | EGY | FOA | 62 | INV | 108 | N | I | HCFC | 9.9 | 9.9 | 0 | 0 | 2010-12-01 | 2013-03-01 | 2012-06-01 |  | 2014-09-01 | 2015-05-01 | 386100 | 0 | 386100 | 386100 | 100% | 0 | 0 | 0 | 28958 | 0 | 28958 | 0 | 0 | Financially Completed in 2015. | Technicians from the supplier are waiting for security clearance for travel to Egypt, before they can visit to oversee installation works. | 2010 |  | Investment
CLO | UNIDO | Phase-out of HCFC-141b from the manufacturing of polyurethane foam at Delta Electric Applicances | Individual | AFR | EGY | FOA | 62 | INV | 109 | A | I | HCFC | 8.9 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2012-12-31 |  |  | 2013-04-01 | 422740 | -406844 | 15896 | 15896 | 100% | 0 | 0 |  | 31706 | -30514 | 1192 | 0 | 0 | CLO |  |  |  | INV
COM | UNIDO | Phase-out of HCFC-141b from the manufacturing of polyurethane foam at El-Araby Co. for Engineering Industries | Multi-Year | AFR | EGY | FOA | 62 | INV | 110 | A | I | HCFC | 11 | 11 |  |  | 2010-12-01 | 2010-12-01 | 2012-12-31 |  | 2015-12-01 | 2016-09-01 | 456540 | 0 | 456540 | 456533.55 | 100% | 6.45 | 0 | 1 | 34241 | 0 | 34240 | 1 | 0 | The project was operationally completed. |  |  |  | INV
ONG | UNIDO | Preparation for HCFC phase-out investment activities (stage II) (foam sector) | Individual | AFR | EGY | FOA | 73 | PRP | 120 | A | I |  | 0 | 0 |  |  | 2014-11-01 | 2016-08-01 | 2015-11-30 | 2017-07-01 |  |  | 60000 | -20000 | 40000 | 34819.31 | 87.05% | 5180.69 | 5040 | 5000 | 4200 | -1400 | 2437 | 363 | 353 | International consultant recruited and design of project commenced. | Stage II will be submitted to the 79th ExCom. |  |  | NON-INV
ONG | UNDP | Preparation for HCFC phase-out investment activities (stage II) (extruded polystyrene foam sector) | Individual | AFR | EGY | FOA | 74 | PRP | 124 | N | I | HCFC | 0 | 0 | 0 | 0 | 2015-05-01 | 2016-01-01 | 2017-05-01 | 2017-10-01 |  |  | 20000 | 0 | 20000 | 7506 | 37.53% | 12494 | 0 | 4997.6 | 1400 | 0 | 525.42 | 874.58 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Stage II documentation formulated by August 2016, and after a stakeholder workshop, submitted to the 77th ExCom. The submission was eventually withdrawn as not being in IA business plan for 2016. The package will be submitted to the 78th ExCom after additional baseline data is obtained. Prodoc signed (actual/planned, yes/no and date):1/1. Yes. Agreement has been signed earlier Missions undertaken (actual/planned):1/1: Mission fielded in August 2016 to assist with programme formulation and stakeholder workshop TOR for consultants/subcontracts completed (actual/planned): 2/2: National coordinator and international expert were recruited Contract/PO/MOA agreements signed: 2/2: National coordinator and international expert were recruited First disbursement date (actual/planned): 42370Any delays/problems (yes/no):No. HPMP Stage-II prodoc was submitted ahead of time in 2016 If Yes, reasons for delay & action plan to resolve: | Baseline clarifications continued, and Stage II documentation was updated for submission to the 78th ExCom | 2015 |  | Non-Investment
ONG | UNDP | Preparation for HCFC phase-out investment activities (stage II) (foam sector) | Individual | AFR | EGY | FOA | 74 | PRP | 125 | N | I | HCFC | 0 | 0 | 0 | 0 | 2015-05-01 |  | 2017-05-01 | 2017-10-01 |  |  | 20000 | 0 | 20000 | 0 | 0% | 20000 | 0 | 8000 | 1400 | 0 | 0 | 1400 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Stage II documentation formulated by August 2016, and after a stakeholder workshop, submitted to the 77th ExCom. The submission was eventually withdrawn as not being in IA business plan for 2016. The package will be submitted to the 78th ExCom after additional baseline data is obtained. Prodoc signed (actual/planned, yes/no and date):1/1. Yes. Agreement has been signed earlier Missions undertaken (actual/planned):1/1: Mission fielded in August 2016 to assist with programme formulation and stakeholder workshop TOR for consultants/subcontracts completed (actual/planned): 2/2: National coordinator and international expert were recruited Contract/PO/MOA agreements signed: 2/2: National coordinator and international expert were recruited First disbursement date (actual/planned): 42370Any delays/problems (yes/no):No. HPMP Stage-II prodoc was submitted ahead of time in 2016 If Yes, reasons for delay & action plan to resolve: | Baseline clarifications continued, and Stage II documentation was updated for submission to the 78th ExCom | 2015 |  | Non-Investment
ONG | UNDP | Demonstration of low-cost options for the conversion to non-ODS technologies in polyurethane foams at very small users | Individual | AFR | EGY | FOA | 76 | DEM | 129 | N | I | HCFC | 4.4 | 0 | 0 | 0 | 2016-05-01 |  | 2017-05-01 | 2018-12-01 |  |  | 295000 | 0 | 295000 | 0 | 0% | 295000 | 0 | 118000 | 20650 | 0 | 0 | 20650 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): DOA prepared and dispatched to UNDP-Egypt. Budgets were set in the financial system, though the project document is awaiting clearance and signature from the Ministry of Foreign Affairs. Initial contacys established with technology manufacturers, with one plant visited by the project team in Italy to introduce the project in more details. Prodoc signed (actual/planned, yes/no and date):0/1: MFA is reviewing project documentation before clearance Missions undertaken (actual/planned):1/1: Mission fielded in August 2016 to discuss project plans TOR for consultants/subcontracts completed (actual/planned): 1/2: Project team is in place, and technical specifications for technology optimization will be prepared once the project is cleared by MFA. Contract/PO/MOA agreements signed: 0/1: International tender will be announced once prodoc is signed by the Government First disbursement date (actual/planned): N/A at this moment, as prodoc has not been signed yet.Any delays/problems (yes/no):Yes. Delayed clearance on the project document from MFA If Yes, reasons for delay & action plan to resolve:MFA is reviewing project documentation. UNDP and NOU have regular exchanges with MFA on project's specifics. | Project team has planned additional visits to technology manufacturers for April 2017 |  |  | Investment
CLO | UNDP | Project preparation for two methyl bromide alternative demonstration projects (strawberries, tomatoes and curcubits) | Individual | AFR | EGY | FUM | 24 | PRP | 66 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 |  | 1998-12-01 |  |  | 1998-07-01 | 40000 | -40000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 5200 | -5200 | 0 | 0 | 0 | Canceled in 1998. Financially Completed in 1998. |  | 1998 |  | Investment
FIN | Germany | Project preparation for two methyl bromide alternative demonstration projects (strawberries, tomatoes and cucurbits) | Individual | AFR | EGY | FUM | 25 | PRP | 68 | N | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-08-01 | 1998-12-01 |  | 1998-08-01 | 1998-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Implementation of the demonstration
FIN | Germany | Four alternatives to the use of methyl bromide in horticulture (strawberries, tomatoes, cucurbits) | Individual | AFR | EGY | FUM | 26 | DEM | 69 | N | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-07-01 | 2000-12-01 |  | 2000-12-01 | 2001-03-01 | 308000 | -81000 | 227000 | 227000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completion report submitted. Balance was offset against German contribution at the 40th Meeting.
FIN | Germany | Application of methyl bromide alternatives in grain storage | Individual | AFR | EGY | FUM | 26 | DEM | 70 | N | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2000-12-01 |  | 2001-03-01 | 2001-03-01 | 297000 | 0 | 297000 | 297000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completion report submitted.
FIN | UNIDO | Preparation of an investment project in the methyl bromide sector | Individual | AFR | EGY | FUM | 30 | PRP | 77 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2001-11-01 | 2001-04-01 |  | 2002-12-01 | 2003-05-01 | 25000 | -858 | 24142 | 24142.35 | 100% | -0.35 | 0 |  | 3250 | -116 | 3134 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the soil fumigation sector | Individual | AFR | EGY | FUM | 33 | PRP | 82 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-05-01 | 2002-04-01 |  | 2002-12-01 | 2003-05-01 | 30000 | -528 | 29472 | 29471.78 | 100% | 0.22 | 0 |  | 3900 | -75 | 3825 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National phase-out of methyl bromide in horticulture and commodities fumigation | Individual | AFR | EGY | FUM | 38 | INV | 86 | A | I | MBR | 185.6 | 185.6 |  |  | 2002-11-01 | 2003-09-01 | 2009-11-01 |  | 2009-06-01 | 2011-03-01 | 2750592 | -95 | 2750497 | 2750497.35 | 100% | -0.35 | 0 |  | 312565 | -10 | 312555 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National phase-out of methyl bromide in horticulture and commodities fumigation except in date use | Individual | AFR | EGY | FUM | 56 | INV | 98 | A | I | MBR | 184.2 | 184.2 |  |  | 2008-11-01 | 2009-04-01 | 2013-11-30 |  | 2014-12-01 | 2016-09-01 | 1934994 | -19618 | 1915376 | 1915375.56 | 100% | 0.44 | 0 |  | 145125 | -1471 | 143653 | 1 | 0 | The project was financially completed and the balance was returned at the 77th ExCom. |  |  |  | INV
ONG | UNIDO | Technical assistance on two alternatives to methyl bromide in the palm date sector | Individual | AFR | EGY | FUM | 74 | TAS | 123 | A | I | MBR | 6 | 0 |  |  | 2015-05-01 | 2015-10-01 | 2017-12-31 | 2018-06-01 |  |  | 282480 | 0 | 282480 | 94177.49 | 33.34% | 188302.51 | 43592.43 | 80000 | 19774 | 0 | 0 | 19774 | 3051.4701 | - Purchase of PH3 monitoring devices almost finalized. - Training plan was agreed to be executed in spring 2017. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - UNIDO and NOU delivered a set of hand-on training on the use of PH3 in March and agreed to have a continuous training program for other regions in the course of the year 2017. - Last training activities will take place in November 2017. - UNIDO and NOU discussed also on awareness campaign to be performed in the course of the year. - Closing ceremony planned towards the end of 2017. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV |  | To request the submission of additional status report to the 79th meeting to monitor the resumption of activities.
FIN | UNDP | Technical assistance to prepare a national halon action plan and project development | Individual | AFR | EGY | HAL | 12 | TAS | 23 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-01-01 |  | 1997-03-01 | 1998-12-01 | 25000 | 1730 | 26730 | 26730 | 100% | 0 | 0 | 0 | 3250 | 224.9 | 3474.9 | 0 | 0 | Completed in 1997. Financially completed in 1998. |  | 1994 |  | Non-Investment
FIN | UNDP | Project preparation to prepare one halon sector programme | Individual | AFR | EGY | HAL | 24 | PRP | 67 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-09-01 | 1998-12-01 |  | 2000-10-01 | 2002-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Halon management bank programme | Individual | AFR | EGY | HAL | 32 | TAS | 81 | N | I | Halon | 754 | 754 | 0 | 0 | 2000-12-01 | 2003-02-01 | 2004-01-01 |  | 2007-12-01 | 2009-09-01 | 405000 | -3894 | 401106 | 401106 | 100% | 0 | 0 | 0 | 52650 | -506.22 | 52143.78 | 0 | 0 | Completed in 2007.Financially completed in 2009. |  | 2000 |  | Investment
FIN | UNIDO | Preparation of a national ODS phase-out plan | Individual | AFR | EGY | PHA | 36 | PRP | 85 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-04-01 | 2003-09-01 |  | 2005-12-01 | 2006-12-01 | 75000 | -33 | 74967 | 74966.89 | 100% | 0.11 | 0 |  | 9750 | -4 | 9746 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National CFC phase-out plan (first tranche) | Multi-Year | AFR | EGY | PHA | 46 | INV | 91 | A | I | CFC | 190 | 190 |  |  | 2005-07-01 | 2005-08-01 | 2006-07-01 |  | 2007-12-01 | 2010-04-01 | 1000000 | -1043 | 998957 | 998956.56 | 100% | 0.44 | 0 |  | 75000 | -78 | 74922 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National CFC phase-out plan (second tranche) | Multi-Year | AFR | EGY | PHA | 50 | INV | 93 | A | I | CFC | 182 | 182 |  |  | 2006-11-01 | 2007-01-01 | 2007-11-01 |  | 2009-03-01 | 2010-12-01 | 1200000 | 0 | 1200000 | 1200000.08 | 100% | -0.08 | 0 |  | 90000 | 0 | 90000 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National CFC phase-out plan (third tranche) | Multi-Year | AFR | EGY | PHA | 54 | INV | 95 | A | I | CFC | 100 | 100 |  |  | 2008-04-01 | 2008-11-01 | 2009-03-31 |  | 2013-12-01 | 2015-03-01 | 600000 | -11344 | 588656 | 588655.76 | 100% | 0.24 | 0 |  | 45000 | -851 | 44149 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | AFR | EGY | PHA | 55 | PRP | 96 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 |  | 2011-08-01 | 2012-12-01 | 195000 | -834 | 194166 | 194166.18 | 100% | -0.18 | 0 |  | 14625 | -63 | 14562 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | National CFC phase-out plan (fourth and fifth tranches) | Multi-Year | AFR | EGY | PHA | 60 | INV | 101 | A | I |  | 65 | 65 |  |  | 2010-04-01 | 2010-05-01 | 2011-04-30 |  | 2013-12-01 | 2014-08-01 | 300000 | -2060 | 297940 | 297940.41 | 100% | -0.41 | 0 |  | 22500 | -155 | 22346 | -1 | 0 | FIN
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (phase-out of HCFC-141b in the manufacture of insulation foam for refrigeration equipment) | Multi-Year | AFR | EGY | PHA | 65 | INV | 112 | A | I | HCFC | 23.5 | 23.5 |  |  | 2011-11-01 | 2012-04-01 | 2012-11-30 | 2017-12-01 |  |  | 905700 | 0 | 905700 | 809700.17 | 89.4% | 95999.83 | 83634.31 | 50000 | 67928 | 0 | 60728 | 7200 | 6273 | Supplier visited beneficiary premises and requested some additional installation activities required prior the star up of new equipment. Activities for the preparation of the site for safe operation of the c-pentane production line are ongoing. It has been agreed to combine other activities in the servicing sector with those planned for Stage II Milestones achieved: Procurement of equipment (TOR, bidding, contract, delivery) completed: Yes Commissioning and start up completed: No Was there any delay during the reporting year? Yes If yes, reasons and action plan: delay in the safety installation activities by beneficiary Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | Installation, start up and training completed for the foam conversion component. |  |  | INV
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) (phase-out of HCFC-141b in the polyurethane foam sector) | Multi-year | AFR | EGY | PHA | 65 | INV | 113 | N | I | HCFC | 42.1 | 42.1 | 0 | 0 | 2011-11-01 | 2013-03-01 | 2015-11-01 | 2017-01-01 |  |  | 2000000 | 0 | 2000000 | 1113438.19 | 55.67% | 886561.81 | 0 | 354624.724 | 150000 | 0 | 83507.8642 | 66492.1358 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Reftruck and Al Fateh stand-alone projects singed hand-over protocols. Two technical missions in 2016 fielded for follow up and consultation. Three (3) system houses (Dow-MidEast, Technocom and Obegi) now signed the MoA agreements, and completed the first milestones on technology development at each, and the second milestone on system house's conversion in case of Technocom. DOW qualified water blown (WB) technology with some customers, and preparing to run other trials based on WB, HFC and LBA. Prodoc signed (actual/planned, yes/no and date):1/1. Yes. Agreement has been signed earlier Missions undertaken (actual/planned):2/2: Two missions fielded with technical oversight and support to the programme TOR for consultants/subcontracts completed (actual/planned): Contract/PO/MOA agreements signed: 5/5: Three agreements signed with system houses and two hand-over protocols with completed stand-alone projects First disbursement date (actual/planned): 41334Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:Resistance from system houses to move in parallel to technology conversions. NOU/Govt was involved in organizing separate talks on the HCFC phaseout plans in the PU foam sector which allowed progress. | Technological trials with new alternatives are ongoing. Additional technical missions are being planned. | 2011 |  | Investment
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (coordination and management) | Multi-Year | AFR | EGY | PHA | 65 | TAS | 111 | A | I |  | 0 | 0 |  |  | 2011-11-01 | 2013-11-01 | 2012-11-30 | 2017-12-01 |  |  | 20000 | 0 | 20000 | 1543.54 | 7.718% | 18456.46 | 0 | 10000 | 1500 | 0 | 116 | 1384 | 0 | - Funding under this component is reserved until installation activities under the FOAM components have been completed for verification proposes. Activities planned but not implemented, reasons and strategy: Verification delayed due to foam components not completed. To be conducted after the latter's completion Was there any delay during the reporting year?: Yes If yes, reasons and action plan: Foam components delayed due to security situation Any recurring problem? No Any impact on project completion date: Yes Any action required by Executive Committee? No | Foam activities just completed. Verification will be conducted this year. |  |  | INV
COM | UNIDO | HCFC phase-out management plan (stage I, first tranche) (enabling activities in the refrigeration and air-conditioning sector) | Multi-Year | AFR | EGY | PHA | 65 | TAS | 114 | A | I | HCFC | 0.3 | 0.3 |  |  | 2011-11-01 | 2013-05-01 | 2012-11-30 |  | 2016-12-01 |  | 24300 | 0 | 24300 | 21798.93 | 89.71% | 2501.07 | 0 | 1 | 1823 | 0 | 1635 | 188 | 0 | Contacts with stakeholders maintained. It has been agreed to combine the activities in the servicing sector under this component with those planned for Stage II. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | Project activities completed. HPMP ongoing with further tranches supporting EGYPRA activities. |  |  | INV
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) (phase-out of HCFC-141b in the polyurethane foam sector) | Multi-Year | AFR | EGY | PHA | 68 | INV | 117 | N | I | HCFC | 42.1 | 2 | 0 | 0 | 2012-12-01 |  | 2018-12-01 | 2017-12-01 |  |  | 2000000 | 0 | 2000000 | 0 | 0% | 2000000 | 0 | 800000 | 150000 | 0 | 0 | 150000 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Reftruck and Al Fateh stand-alone projects singed hand-over protocols. Two technical missions in 2016 fielded for follow up and consultation. Three (3) system houses (Dow-MidEast, Technocom and Obegi) now signed the MoA agreements, and completed the first milestones on technology development at each, and the second milestone on system house's conversion in case of Technocom. DOW qualified water blown (WB) technology with some customers, and preparing to run other trials based on WB, HFC and LBA. Prodoc signed (actual/planned, yes/no and date):1/1. Yes. Agreement has been signed earlier Missions undertaken (actual/planned):2/2: Two missions fielded with technical oversight and support to the programme TOR for consultants/subcontracts completed (actual/planned): Contract/PO/MOA agreements signed: 5/5: Three agreements signed with system houses and two hand-over protocols with completed stand-alone projects First disbursement date (actual/planned): 41334Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:Resistance from system houses to move in parallel to technology conversions. NOU/Govt was involved in organizing separate talks on the HCFC phaseout plans in the PU foam sector which allowed progress. | Technological trials with new alternatives are ongoing. Additional technical missions are being planned. | 2012 |  | Investment
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) (enabling activities in the refrigeration and air-conditioning sector) | Multi-Year | AFR | EGY | PHA | 68 | TAS | 116 | A | I | HCFC | 3.1 | 0 |  |  | 2012-12-01 | 2013-06-01 | 2018-12-31 | 2018-12-01 |  |  | 250000 | 0 | 250000 | 196786.95 | 78.71% | 53213.05 | 2499.75 | 20000 | 18750 | 0 | 14759 | 3991 | 187.4812 | Prototypes built using delivered components. Performance Testing of prototypes using low GWP refrigerants commenced. | Prototype testing is ongoing. |  |  | INV
ONG | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | Individual | AFR | EGY | PHA | 73 | PRP | 121 | A | I |  | 0 | 0 |  |  | 2014-11-01 | 2015-12-01 | 2015-11-30 | 2017-07-01 |  |  | 70000 | -20000 | 50000 | 42526.1 | 85.05% | 7473.9 | 6368 | 6000 | 4900 | -1400 | 2977 | 523 | 446 | An organization was contracted to conduct a survey on HCFC consumption. Coordination meeting between NOU and implementing agencies UNIDO, UNEP and UNDP took place in Cairo in Dec 2015 and a work plan was agreed upon. An international consultant has been recruited to prepare draft the overarching strategy. A stakeholders meeting took place early August. | Stage II will be submitted to 79th ExCom Meeting. |  |  | NON-INV
ONG | UNEP | Preparation of a HCFC phase-out management plan (stage II) | Multi-Year | AFR | EGY | PHA | 73 | PRP | 122 | A | I |  | 0 |  | 0 |  | 2014-11-01 |  | 2015-11-01 | 2017-05-01 |  |  | 20000 | 0 | 20000 | 0 | 0% | 20000 | 0 | 2000 | 2600 | 0 | 0 | 2600 | 0 | Brief progress report (actual/planned): The NOU with assistance of ASHRAE completed report on data collection and analysis. The country drafted HPMP stage project which is being reviewed and will be submitted to the 78 Excom for approval .___ Legal arrangements(actual/planned): _ The SSFA was drafted but not yet signed as it has to go through Due Diligence clearance since the agreement is with the NGO, ASHRAE_ First mission (actual/planned): yes___ TOR completed(actual/planned): __yes_ First disbursement date (actual/planned): N/A__ All funds disbursed (yes/no): No__ Any delay? (yes/no): No___ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): N/A___ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: __No_ | Brief progress report (actual/planned): The HPMP stage project document is being reviewed, especially on the investment component and it will be submitted to Ex-com 78 for consideration. The SSFA is under clearance and the first disbursement is expected by May 2017.
ONG | UNDP | Preparation of a HCFC phase-out management plan (stage II) | Individual | AFR | EGY | PHA | 74 | PRP | 126 | N | I | HCFC | 0 | 0 | 0 | 0 | 2015-05-01 |  | 2017-05-01 | 2017-10-01 |  |  | 20000 | 0 | 20000 | 0 | 0% | 20000 | 0 | 8000 | 1400 | 0 | 0 | 1400 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Stage II documentation formulated by August 2016, and after a stakeholder workshop, submitted to the 77th ExCom. The submission was eventually withdrawn as not being in IA business plan for 2016. The package will be submitted to the 78th ExCom after additional baseline data is obtained. Prodoc signed (actual/planned, yes/no and date):1/1. Yes. Agreement has been signed earlier Missions undertaken (actual/planned):1/1: Mission fielded in August 2016 to assist with programme formulation and stakeholder workshop TOR for consultants/subcontracts completed (actual/planned): 2/2: National coordinator and international expert were recruited Contract/PO/MOA agreements signed: 2/2: National coordinator and international expert were recruited First disbursement date (actual/planned): 42370Any delays/problems (yes/no):No. HPMP Stage-II prodoc was submitted ahead of time in 2016 If Yes, reasons for delay & action plan to resolve: | Baseline clarifications continued, and Stage II documentation was updated for submission to the 78th ExCom | 2015 |  | Investment
FIN | IBRD | Conversion of refrigeration compressor manufacturing to HFC-134a at MISR Compressors Manufacturing Co. (MCMC) | Individual | AFR | EGY | REF | 08 | INV | 08 | N | I | CFC | 0 | 0 | 0 | 0 | 1992-10-01 | 1995-11-01 | 1994-03-01 |  | 1997-07-01 | 2000-11-01 | 2800000 | -950000 | 1850000 | 1850000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. Savings of $250,000 to be returned to the 36th ExCom. |  |  | 1997-12-01 | INV | 0
FIN | UNDP | Phase-out of CFC in refrigeration at Koldair Company | Individual | AFR | EGY | REF | 08 | INV | 09 | A | I | CFC | 18 | 18 | 0 | 0 | 1992-10-01 | 1993-04-01 | 1994-10-01 |  | 1994-01-01 | 2003-04-01 | 272000 | -21979 | 250021 | 250021 | 100% | 0 | 0 | 0 | 35360 | -2857.27 | 32502.73 | 0 | 0 | Completed in 1994. Financially completed in 2003. |  | 1992 |  | Investment
FIN | UNIDO | Preparatory assistance for elimination of CFCs in manufacturing foams at Advechems and El Fateh | Individual | AFR | EGY | REF | 09 | TAS | 11 | A | I |  | 0 | 0 |  |  | 1993-03-01 | 1993-09-01 | 1993-06-01 |  | 1994-08-01 | 1998-08-01 | 50000 | -9289 | 40711 | 40711 | 100% | 0 | 0 |  | 6500 | -1216 | 5284 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparatory assistance for phase out of ODS in the production of household refrigerators at Electrostar & Kiriazi | Individual | AFR | EGY | REF | 09 | TAS | 63 | A | I |  | 0 | 0 |  |  | 1993-03-01 | 1993-09-01 | 1993-06-01 |  | 1994-03-01 | 1998-08-01 | 50000 | 6602 | 56602 | 56602 | 100% | 0 | 0 |  | 6500 | 858 | 7358 | 0 | 0 | FIN
FIN | UNDP | Conversion to CFC free-technology Reftruck Company | Individual | AFR | EGY | REF | 12 | INV | 30 | A | I | CFC | 25.1 | 25.1 | 0 | 0 | 1994-03-01 | 1996-01-01 | 1995-03-01 |  | 1998-09-01 | 2002-11-01 | 385000 | -2692 | 382308 | 382308 | 100% | 0 | 0 | 0 | 50050 | -349.96 | 49700.04 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1994 |  | Investment
FIN | UNDP | Conversion to CFC free-technology at Misr Panel (Egyptian Company for Cold Storage Industries) | Individual | AFR | EGY | REF | 12 | INV | 31 | A | I | CFC | 74.4 | 74.4 | 0 | 0 | 1994-03-01 | 1996-01-01 | 1995-03-01 |  | 2001-03-01 | 2002-03-01 | 636000 | 0 | 636000 | 636000 | 100% | 0 | 0 | 0 | 82680 | 0 | 82680 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1994 | 1997-09-01 | Investment
FIN | IBRD | Preparation of investment projects in the commercial and industrial refrigeration (1994) |  | AFR | EGY | REF | 12 | PRP | 24 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 25000 | -18884 | 6116 | 6116 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | UNIDO | Phasing out ODS at the refrigerator plants of Delta Industrial Co. | Individual | AFR | EGY | REF | 13 | INV | 32 | A | I | CFC | 97 | 117 |  |  | 1994-07-01 | 1995-03-01 | 1996-01-01 |  | 1997-05-01 | 2000-07-01 | 2611986 | -133089 | 2478897 | 2478897 | 100% | 0 | 0 |  | 339558 | -17812 | 321746 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the Electrostar for Refrigeration Co. | Individual | AFR | EGY | REF | 13 | INV | 33 | A | I | CFC | 46 | 51 |  |  | 1994-07-01 | 1995-02-01 | 1996-01-01 |  | 1996-12-01 | 2000-07-01 | 1450585 | -13996 | 1436589 | 1436589 | 100% | 0 | 0 |  | 188576 | -2115 | 186461 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at the Kiriazi Refrigerators Manufacturing Co. | Individual | AFR | EGY | REF | 13 | INV | 35 | A | I | CFC | 137 | 137 |  |  | 1994-07-01 | 1995-03-01 | 1996-01-01 |  | 1996-12-01 | 2000-07-01 | 1643040 | -52934 | 1590106 | 1590106 | 100% | 0 | 0 |  | 213595 | -7209 | 206386 | 0 | 0 | FIN
FIN | UNIDO | Preparatory assistance for phase out of ODS in production of household refrigeration at additional four companies | Individual | AFR | EGY | REF | 13 | PRP | 34 | A | I |  | 0 | 0 |  |  | 1994-07-01 | 1994-10-01 | 1994-10-01 |  | 1995-08-01 | 1998-08-01 | 15000 | 3364 | 18364 | 18364 | 100% | 0 | 0 |  | 1950 | 437 | 2387 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Helwan Company for Metallic Appliances domestic refrigeration plant | Individual | AFR | EGY | REF | 15 | INV | 38 | A | I | CFC | 7.5 | 7.5 |  |  | 1994-12-01 | 1996-04-01 | 1996-06-01 |  | 1998-12-01 | 2000-12-01 | 644239 | -29419 | 614820 | 614820 | 100% | 0 | 0 |  | 83751 | -3951 | 79800 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Super Bosh Factory domestic refrigeration plant | Individual | AFR | EGY | REF | 15 | INV | 39 | A | I | CFC | 13 | 13 |  |  | 1994-12-01 | 1996-04-01 | 1996-06-01 |  | 1998-12-01 | 2000-12-01 | 760066 | -34709 | 725357 | 725357 | 100% | 0 | 0 |  | 98809 | -4662 | 94147 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Islamic Company for Industrialization (Siltal) domestic refrigeration plant | Individual | AFR | EGY | REF | 15 | INV | 40 | A | I | CFC | 26 | 26 |  |  | 1994-12-01 | 1996-04-01 | 1996-06-01 |  | 1998-12-01 | 2000-12-01 | 866633 | -39576 | 827057 | 827057 | 100% | 0 | 0 |  | 112662 | -5315 | 107347 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Société Mondiale pour Refroidissement (Alaska) domestic refrigeration plant | Individual | AFR | EGY | REF | 15 | INV | 41 | A | I | CFC | 55 | 55 |  |  | 1994-12-01 | 1996-04-01 | 1996-06-01 |  | 1998-12-01 | 2000-12-01 | 1518606 | -69349 | 1449257 | 1449257 | 100% | 0 | 0 |  | 197419 | -9314 | 188105 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at International Co. for Refrigeration and Appliances (Iberna) domestic refrigeration plant | Individual | AFR | EGY | REF | 15 | INV | 42 | A | I | CFC | 19 | 19 |  |  | 1994-12-01 | 1996-04-01 | 1996-06-01 |  | 1998-12-01 | 2000-12-01 | 852738 | -38941 | 813797 | 813797 | 100% | 0 | 0 |  | 110856 | -5230 | 105626 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at El Nasr Company for Electric and Electronic Apparatus (Philips) domestic refrigeration plant | Individual | AFR | EGY | REF | 15 | INV | 43 | A | I | CFC | 22.5 | 22.5 |  |  | 1994-12-01 | 1996-04-01 | 1996-06-01 |  | 1998-12-01 | 2000-12-01 | 854690 | -39030 | 815660 | 815660 | 100% | 0 | 0 |  | 111110 | -5242 | 105868 | 0 | 0 | FIN
FIN | UNDP | Elimination of CFC in the manufacture of commercial refrigeration equipment at Royal Engineering, Co. | Individual | AFR | EGY | REF | 15 | INV | 44 | A | I | CFC | 20.3 | 20.3 | 0 | 0 | 1994-12-01 | 1996-07-01 | 1995-12-01 |  | 1998-11-01 | 2001-12-01 | 539000 | -1790 | 537210 | 537210 | 100% | 0 | 0 | 0 | 70070 | -232.79 | 69837.2108 | -0.0008 | 0 | Completed in 1998. Financially completed in 2001. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC in the manufacture of commercial refrigeration equipment at Port Said Metal Work, Co. (MOG) | Individual | AFR | EGY | REF | 15 | INV | 45 | A | I | CFC | 11.8 | 11.8 | 0 | 0 | 1994-12-01 | 1996-07-01 | 1995-12-01 |  | 1999-10-01 | 2003-02-01 | 484000 | 0 | 484000 | 484000 | 100% | 0 | 0 | 0 | 62920 | 0 | 62920 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  | 1994 | 1999-07-01 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of commercial refrigeration equipment at United Investment Corporation Inc. | Individual | AFR | EGY | REF | 18 | INV | 49 | A | I | CFC | 48.7 | 48.7 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1997-05-01 |  | 1999-11-01 | 2003-11-01 | 493350 | -32495 | 460855 | 460855 | 100% | 0 | 0 | 0 | 64135.5 | -4224.35 | 59911.15 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  | 1995 | 1999-12-01 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of commercial refrigeration equipment at Refcat Compnay Inc. | Individual | AFR | EGY | REF | 18 | INV | 50 | A | I | CFC | 26.8 | 26.8 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1997-05-01 |  | 1998-09-01 | 2000-12-01 | 409000 | -18.76 | 408981.24 | 408981 | 100% | 0.24 | 0 | 0 | 53170 | -2.44 | 53167.53 | 0.03 | 0 | Completed in 1998. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of commercial refrigeration equipment at El-Mohandes | Individual | AFR | EGY | REF | 20 | INV | 58 | A | I | CFC | 13 | 13 | 0 | 0 | 1996-10-01 | 1997-03-01 | 1998-09-01 |  | 2001-03-01 | 2003-11-01 | 190000 | 0 | 190000 | 190000 | 100% | 0 | 0 | 0 | 24700 | 0 | 24700 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1996 | 2000-06-01 | Investment
CLO | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of commercial refrigeration equipment at Amiral | Individual | AFR | EGY | REF | 20 | INV | 59 | A | I | CFC | 0 | 0 | 0 | 0 | 1996-10-01 | 1998-06-01 | 1998-09-01 |  |  | 2003-11-01 | 160000 | -70081 | 89919 | 89919 | 100% | 0 | 0 | 0 | 20800 | -9111 | 11689 | 0 | 0 | Canceled in 2001. Financially completed in 2003. |  | 1996 | 1998-10-01 | Investment
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | EGY | REF | 27 | PRP | 71 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-09-01 | 2000-04-01 |  | 1999-09-01 | 2002-01-01 | 28700 | 0 | 28700 | 28700 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation lead to project proposal for implementation
FIN | Germany | Implementation of the RMP: modification of legal provisions and information system | RMP | AFR | EGY | REF | 29 | TAS | 74 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-03-01 | 2002-12-01 |  | 2004-12-01 | 2007-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | UNIDO was subcontracted. Project completed. Draft PCR submitted in September 2005.
FIN | Germany | Implementation of the RMP: establishing a national recovery and recycling network | Individual | AFR | EGY | REF | 29 | TAS | 75 | A | I | CFC | 100 | 100 | 0 |  | 1999-11-01 | 2000-04-01 | 2002-12-01 |  | 2007-12-01 | 2008-10-01 | 599500 | 0 | 599500 | 599500 | 100% | 0 | 0 | 0 | 77935 | 0 | 77935 | 0 | 0 | Project is completed. A final monitoring and evaluation workshop was organized with NOU in August 2007 to establish a network for monitoring in the whole country. PCR was approved by NOU and was sent to MLF in October 2008.
FIN | Germany | Implementation of the RMP: implementation of measures to address the informal sector | RMP | AFR | EGY | REF | 29 | TAS | 76 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-07-01 | 2002-12-01 |  | 2004-12-01 | 2007-12-01 | 252500 | 0 | 252500 | 252500 | 100% | 0 | 0 | 0 | 32825 | 0 | 32825 | 0 | 0 | Unido was subcontracted, training courses have been carried out successfully. Project completed. Draft PCR submitted in September 2005.
TRF | UNDP | Project preparation in the manufacturing refrigeration (terminal phase-out) sector | Individual | AFR | EGY | REF | 36 | PRP | 84 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 |  | 2003-04-01 |  |  | 2006-12-01 | 20000 | -20000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 2600 | -2600 | 0 | 0 | 0 | Transferred in 2003. Financially Completed in 2006. |  | 2002 |  | Investment
ONG | UNIDO | Preparation for HCFC phase-out investment activities (stage II) (refrigeration sector) | Individual | AFR | EGY | REF | 73 | PRP | 119 | A | I |  | 0 | 0 |  |  | 2014-11-01 | 2016-05-01 | 2015-11-30 | 2017-12-01 |  |  | 150000 | 0 | 150000 | 63817 | 42.54% | 86183 | 15468.92 | 50000 | 10500 | 0 | 4467 | 6033 | 1083 | A mission was arranged during which A/C manufacturers were visited and the possibility of future conversion of their production line to low-GWP technologies was discussed. Questionnaires were provided to the manufacturers to provide relevant data for project design. A stakeholders meeting took place early August. Project document submitted to 77th ExCom and withdrew. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: Yes. Any action required by Executive Committee? No | Stage II will be submitted to the 79th ExCom Meeting. |  |  | NON-INV
ONG | UNIDO | Feasibility study addressing district cooling | Individual | AFR | EGY | REF | 75 | TAS | 127 | A | I |  | 0 | 0 |  |  | 2015-11-01 | 2016-09-01 | 2017-12-01 | 2017-12-18 |  |  | 63521 | 0 | 63521 | 6158.98 | 9.696% | 57362.02 | 412.18 | 40000 | 5717 | 0 | 0 | 5717 | 37.0962 | Participation of two national experts at the conference in Stockholm September 2016. Coordination meeting with cooperating agency UNEP held in November 2016. Work plan for the project prepared. Milestones achieved: Milestone 1: Participation at Stockholm conference - Yes Milestone 2: Coordination meeting - Yes Milestone 3: Work plan for 2017 - Yes Actions towards next goals: Establishment of a Preparatory Committee for the Conference. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | Participation of two national experts at meeting with EBRD in Jordan to discuss potential funding of a full size feasibility study for Egypt organize in Jordan in March 2017. Recruitment of two national experts (technical and financial). ASHRAE-UNIDO-UNEP-EBRD conference on DC and Urban Development planned for September 2017. Milestones achieved: Milestone 1: Participation at EBRD meeting - Yes Milestone 2: Recruitment of national experts - Yes Milestone 3: Conference on DC and Urban Development - No Actions towards next goals: Establishment of a Preparatory Committee for the Conference. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | NON-INV
ONG | UNEP | Feasibility study addressing district cooling | Individual | AFR | EGY | REF | 75 | TAS | 128 | A | I |  | 0 |  | 0 |  | 2015-11-01 |  | 2016-12-01 | 2017-05-01 |  |  | 27223 | 0 | 27223 | 0 | 0% | 27223 | 0 | 2722.3 | 3539 | 0 | 0 | 3539 | 0 | Brief progress report (actual/planned): Funds are being programmed. The SSFA has been drafted awiating programming of funds . Activities are under preparation on the ground. ___ Legal arrangements (actual/planned): _ The SSFA has been drafted awaiting programming of funds_ First mission (actual/planned):NO__ TOR completed(actual/planned): __NO_ First disbursement date (actual/planned): N/A__ All funds disbursed (yes/no): No__ Any delay? (yes/no): No___ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): N/A___ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: __No_ | Brief progress report (actual/planned): Funds are being programmed. The SSFA has been drafted awiating programming of funds .___ Legal arrangements(actual/planned): _ The SSFA has been drafted awaiting programming of funds_ First mission (actual/planned):NO__ TOR completed(actual/planned): __NO_ First disbursement date (actual/planned): N/A__ All funds disbursed (yes/no): No__ Any delay? (yes/no): No___ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): N/A___ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: __No_
FIN | IBRD | Country programme preparation | Individual | AFR | EGY | SEV | 04 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-12-01 |  | 1992-12-01 | 1992-12-01 | 68981 | 28539 | 97520 | 97520 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1991) |  | AFR | EGY | SEV | 04 | PRP | 65 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 131065 | -51944 | 79121 | 79121 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Study tours for officials from the Ministry of the Environment, and pre-feasibility study | Individual | AFR | EGY | SEV | 04 | TRA | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1992-06-01 | 1992-02-01 |  | 1992-06-01 | 1997-12-01 | 51000 | -6910 | 44090 | 44090 | 100% | 0 | 0 | 0 | 6630 | -898.3 | 5731.7 | 0 | 0 | Completed in 1992. Financially completed in 1997. |  | 1991 |  | Non-Investment
FIN | IBRD | Preparation of investment projects (1992) |  | AFR | EGY | SEV | 06 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 227827 | -219155 | 8672 | 8672 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Preparation of investment projects | Individual | AFR | EGY | SEV | 06 | PRP | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-07-01 | 1993-02-01 |  | 1993-09-01 | 2003-04-01 | 100000 | 319 | 100319 | 100319 | 100% | 0 | 0 | 0 | 13000 | 41.47 | 13041.47 | 0 | 0 | Completed in 1993. Financially completed in 2003. |  | 1992 |  | Investment
FIN | IBRD | Preparation of investment projects (1993) |  | AFR | EGY | SEV | 09 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 112200 | -69976 | 42224 | 42224 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNIDO | Institutional strengthening unit for the Montreal Protocol related activities | Individual | AFR | EGY | SEV | 10 | INS | 14 | N | I |  | 0 | 0 |  |  | 1993-06-01 | 1993-10-01 | 1996-05-01 |  | 1996-12-01 | 2000-07-01 | 263450 | 0 | 263450 | 263450 | 100% | 0 | 0 |  | 34249 | 0 | 34249 | 0 | 0 | FIN |  |  |  | NON-INV
CLO | IBRD | Supervision of project implementation (1994) |  | AFR | EGY | SEV | 12 | PRP | 25 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1995-03-01 |  |  | 1994-12-01 | 50000 | -50000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1995) |  | AFR | EGY | SEV | 16 | PRP | 47 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 65623 | 0 | 65623 | 65623 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The reconnaissance mission reported that the scope of refrigeration-sector projects would be limited to recovery and recycling activities. Project identification was then undertaken. This activity is now completed. |  |  |  | Non-INV | 0
FIN | UNDP | Project preparation assistance | Individual | AFR | EGY | SEV | 18 | PRP | 55 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-06-01 | 1997-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1996. Financially completed in 1997. |  | 1995 |  | Investment
FIN | UNIDO | Institutional strengthening project for the Montreal Protocol related activities (Phase II) | Individual | AFR | EGY | SEV | 21 | INS | 61 | N | I |  | 0 | 0 |  |  | 1995-11-01 | 1997-03-01 | 1999-02-01 |  | 1998-12-01 | 1999-09-01 | 43900 | 132009 | 175909 | 175909 | 100% | 0 | 0 |  | 5707 | 17125 | 22832 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Phase III: Institutional Strengthening Project for the Montreal Protocol Related Activities | Individual | AFR | EGY | SEV | 27 | INS | 73 | N | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-09-01 | 2001-04-01 |  | 2001-11-01 | 2002-05-01 | 175000 | 0 | 175000 | 175000.46 | 100% | -0.46 | 0 |  | 22750 | -1 | 22749 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Renewal of institutional strengthening project (phase IV) | Individual | AFR | EGY | SEV | 34 | INS | 83 | N | I |  | 0 | 0 |  |  | 2001-07-01 | 2001-11-01 | 2003-08-01 |  | 2002-12-01 | 2004-12-01 | 175000 | -8670 | 166330 | 166330.22 | 100% | -0.22 | 0 |  | 22750 | -1161 | 21589 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Extension of institutional strengthening project | Individual | AFR | EGY | SEV | 40 | INS | 87 | N | I |  | 18.9 | 18.9 |  |  | 2003-07-01 | 2004-08-01 | 2005-07-01 |  | 2006-12-01 | 2007-08-01 | 228323 | -1 | 228322 | 228322 | 100% | 0 | 0 |  | 17125 | -1 | 17124 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Extension of institutional strengthening project (phase VI) | Individual | AFR | EGY | SEV | 51 | INS | 94 | N | I |  | 0 | 0 |  |  | 2007-03-01 | 2007-07-01 | 2008-12-01 |  | 2008-12-01 | 2009-12-01 | 228323 | 0 | 228323 | 228323 | 100% | 0 | 0 |  | 17124 | 0 | 17124 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Extension of the institutional strengthening projects (phase VII) | Individual | AFR | EGY | SEV | 56 | INS | 97 | N | I |  | 0 | 0 |  |  | 2008-11-01 | 2009-08-01 | 2011-03-31 |  | 2010-12-01 | 2011-03-01 | 228323 | 0 | 228323 | 228323 | 100% | 0 | 0 |  | 17124 | 0 | 17124 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Extension of the institutional strengthening project (phase VIII) | Individual | AFR | EGY | SEV | 61 | INS | 103 | N | I |  | 0 | 0 |  |  | 2010-07-01 | 2011-02-01 | 2012-12-31 |  | 2011-12-01 | 2013-10-01 | 228323 | 0 | 228323 | 228323 | 100% | 0 | 0 |  | 17124 | 0 | 17124 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Extension of the institutional strengthening project (phase IX: 1/2013-12/2014) | Individual | AFR | EGY | SEV | 67 | INS | 115 | N | I |  | 0 | 0 |  |  | 2012-07-01 | 2013-06-01 | 2014-12-31 |  | 2014-12-01 | 2016-03-01 | 228323 | -323 | 228000 | 228000 | 100% | 0 | 0 |  | 15983 | -23 | 15960 | 0 | 0 | The project was financially completed and the balance was returned at the 76th ExCom. |  |  |  | NON-INV
COM | UNIDO | Extension of the institutional strengthening project (phase X: 1/2015-12/2016) | Individual | AFR | EGY | SEV | 72 | INS | 118 | N | I |  | 0 | 0 |  |  | 2014-05-01 | 2014-12-01 | 2016-12-31 |  | 2016-12-01 |  | 228323 | 0 | 228323 | 228221.64 | 99.96% | 101.36 | 0 | 1 | 15983 | 0 | 15976 | 7 | 0 | - NOU is fully staffed and activities were achieved through local contractual arrangements. - The project was completed as of December 2016, in line with the planning. Milestone 1: NOU staff contracts released - Yes Milestone 2: Public awareness activities organized - yes Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | Project completed |  |  | NON-INV
ONG | UNIDO | Extension of the institutional strengthening project (phase XI: 1/2017-12/2018) | Individual | AFR | EGY | SEV | 76 | INS | 130 | N | I |  | 0 | 0 |  |  | 2016-05-01 |  | 2018-12-31 | 2019-06-30 |  |  | 292253 | 0 | 292253 | 0 | 0% | 292253 | 0 | 30000 | 20458 | 0 | 0 | 20458 | 0 | - Project approved at 76th Meeting of the ExCom in 2016. - Project execution has been initiated and is progressing by local contractual arrangements. - NOU is fully staffed and work plan agreed. Milestone 1: NOU staff contracts released - Yes Milestone 2: Public awareness activities organized - yes Actions towards next goals: NA Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - NOU is fully staffed and work plan agreed. Milestone 1: NOU staff contracts released - Yes Milestone 2: Public awareness activities organized - yes Second payment under current contract was released first quarter 2017, upon progress report received from counterpart (the NOU). |  |  | NON-INV
CLO | UNIDO | Conversion of cleaning processes from CFC-113 to Aqueous Cleaning at Optica | Individual | AFR | EGY | SOL | 18 | INV | 51 | A | I |  | 0 | 0 |  |  | 1995-11-01 |  | 1996-06-01 |  |  | 1996-06-01 | 12043 | -12043 | 0 | 0 | #DIV/0! | 0 | 0 |  | 1566 | -1566 | 0 | 0 | 0 | CLO
FIN | UNIDO | Conversion of electronic cleaning processes from ODS solvents to non-ODS cleaning at 3 electronic companies | Individual | AFR | EGY | SOL | 18 | INV | 52 | A | I | CFC TCA | 13.7 | 13.7 |  |  | 1995-11-01 | 1997-10-01 | 1996-11-01 |  | 1998-10-01 | 1998-11-01 | 227203 | 0 | 227203 | 227203 | 100% | 0 | 0 |  | 29536 | 0 | 29536 | 0 | 0 | FIN
FIN | UNIDO | Conversion of cleaning processes from CFC-113 and 1,1,1 TCA to semi-aqueous cleaning at Arab International Optronics | Individual | AFR | EGY | SOL | 18 | INV | 53 | A | I | CFC TCA | 2.1 | 2.1 |  |  | 1995-11-01 | 1999-08-01 | 1996-11-01 |  | 1999-12-01 | 2000-03-01 | 48533 | 0 | 48533 | 48533 | 100% | 0 | 0 |  | 6309 | 0 | 6309 | 0 | 0 | FIN |  |  | 1999-07-01
FIN | UNIDO | Conversion of cleaning processes from 1,1,1 TCA to aqueous cleaning at Siltal | Individual | AFR | EGY | SOL | 18 | INV | 54 | A | I | TCA | 2 | 2 |  |  | 1995-11-01 | 1997-11-01 | 1996-06-01 |  | 1998-10-01 | 2000-07-01 | 48784 | -419 | 48365 | 48365 | 100% | 0 | 0 |  | 6342 | -65 | 6277 | 0 | 0 | FIN
FIN | UNIDO | Conversion of cleaning processes from 1,1,1 TCA to aqueous cleaning at Technopol | Individual | AFR | EGY | SOL | 19 | INV | 56 | A | I | TCA | 6 | 6 |  |  | 1996-05-01 | 1997-07-01 | 1997-05-01 |  | 1998-12-01 | 2000-05-01 | 125249 | 0 | 125249 | 125249 | 100% | 0 | 0 |  | 16282 | 0 | 16282 | 0 | 0 | FIN
FIN | UNIDO | Conversion of cleaning processes from 1,1,1 TCA to cleaning in perchloroethylene at Abbasol | Individual | AFR | EGY | SOL | 19 | INV | 57 | A | I | TCA | 8 | 8 |  |  | 1996-05-01 | 1998-10-01 | 1997-05-01 |  | 1998-12-01 | 1999-07-01 | 154544 | 0 | 154544 | 154544 | 100% | 0 | 0 |  | 20091 | 0 | 20091 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the solvent sector | Individual | AFR | EGY | SOL | 21 | PRP | 62 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-07-01 | 1997-06-01 |  | 2000-07-01 | 2000-11-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | FIN |  |  | 1999-06-01
FIN | UNIDO | Project preparation in the solvent sector (TCA) | Individual | AFR | EGY | SOL | 27 | PRP | 72 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-05-01 | 1999-12-01 |  | 2001-02-01 | 2001-03-01 | 15000 | 0 | 15000 | 14999.85 | 100% | 0.15 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | FIN
FIN | UNIDO | Conversion of TCA used for the formulation of degreasing and contact cleaners and crack detectors to new formulations with special hydrocarbons and heavy chlorinated ester at Sien | Individual | AFR | EGY | SOL | 28 | INV | 79 | A | I | TCA | 9 | 9 |  |  | 1999-07-01 | 2000-11-01 | 2000-08-01 |  | 2002-06-01 | 2003-10-01 | 231435 | 0 | 231435 | 231435.42 | 100% | -0.42 | 0 |  | 30087 | -34 | 30053 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the solvent sector (TCA) | Individual | AFR | EGY | SOL | 30 | PRP | 78 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-12-01 | 2001-04-01 |  | 2004-11-01 | 2004-12-01 | 15000 | 0 | 15000 | 15000.05 | 100% | -0.05 | 0 |  | 1950 | -1 | 1949 | 0 | 0 | FIN
FIN | UNIDO | Conversion of metal cleaning processes from TCA solvent to TCE degreasing at Maasara Co. for engineering industries | Individual | AFR | EGY | SOL | 31 | INV | 80 | A | I | TCA | 10.7 | 10.7 |  |  | 2000-07-01 | 2001-08-01 | 2002-01-01 |  | 2002-12-01 | 2004-03-01 | 294950 | 0 | 294950 | 294950.23 | 100% | -0.23 | 0 |  | 38344 | -4 | 38340 | 0 | 0 | FIN
FIN | UNIDO | Terminal solvent sector umbrella project | Individual | AFR | EGY | SOL | 44 | INV | 89 | A | I | CFC CTC TCA | 41 | 41 |  |  | 2004-12-01 | 2005-02-01 | 2006-06-01 |  | 2007-12-01 | 2009-05-01 | 778464 | -5845 | 772619 | 772619.45 | 100% | -0.45 | 0 |  | 58385 | -439 | 57946 | 0 | 0 | FIN |  |  | 2007-07-01 | INV
CLO | UNDP | Project preparation for 2 projects in the foam sector | Individual | LAC | ELS | FOA | 24 | PRP | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 |  | 1998-12-01 |  |  | 2000-12-01 | 20000 | -20000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 2600 | -2600 | 0 | 0 | 0 | Canceled in 2000. Financially Completed in 2000. |  | 1998 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | LAC | ELS | FOA | 57 | PRP | 25 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-04-01 | 2010-03-01 |  | 2012-05-01 | 2013-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 2250 | 0 | 2250 | 0 | 0 | Financially completed in 2013. | Completed in 2012. No activities in 2013. | 2009 |  | Investment
FIN | UNIDO | Training and awareness workshop in the fumigants sector (methyl bromide) | Individual | LAC | ELS | FUM | 45 | TAS | 18 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2006-06-01 | 2006-04-01 |  | 2007-09-01 | 2007-12-01 | 40000 | -2757 | 37243 | 37243.08 | 100% | -0.08 | 0 |  | 3600 | -248 | 3352 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | LAC | ELS | PHA | 48 | PRP | 19 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-04-01 | 2007-04-01 |  | 2007-12-01 | 2009-08-01 | 30000 | -4831 | 25169 | 25169 | 100% | 0 | 0 | 0 | 2250 | -362.35 | 1887.648 | 0.002 | 0 | Completed in 2007.Financially completed in 2009. Difference has been returned back to UNDP at 60th Meeting. 2010 PR will reflect correct amounts. |  | 2006 |  | Investment
FIN | UNDP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | ELS | PHA | 53 | INV | 21 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-02-01 | 2009-11-01 |  | 2009-11-01 | 2013-07-01 | 230000 | 0 | 230000 | 230000 | 100% | 0 | 0 | 0 | 17250 | 0 | 17250 | 0 | 0 | Financially completed in 2013. |  | 2007 |  | Investment
FIN | UNEP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-year | LAC | ELS | PHA | 53 | TAS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-06-01 | 2008-11-01 |  | 2009-06-01 | 2010-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | ELS | PHA | 55 | PRP | 23 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2012-06-01 | 2014-07-01 | 150000 | -135 | 149865 | 149865 | 100% | 0 | 0 | 0 | 11250 | -10.13 | 11239.87 | 0 | 0 | Financially completed in 2014. | Completed in 2012. No activities in 2013. Pending payments were made. | 2008 |  | Investment
FIN | UNDP | Terminal phase-out management plan for Annex A Group I substances (second and third tranches) | Multi-Year | LAC | ELS | PHA | 57 | INV | 26 | N | I | CFC | 46 | 46 | 0 | 0 | 2009-04-01 | 2010-03-01 | 2011-03-01 |  | 2011-06-01 | 2013-07-01 | 285000 | -4.56 | 284995.44 | 284995 | 100% | 0.44 | 0 | 0 | 21375 | -0.34 | 21374.625 | 0.035 | 0 | Financially completed in 2013. | Completed in 2011. Final activities under the TPMP completed. Follow up actions with hospitals and training institutions,. Training programme in the process of being updated to fully reflect requirements from HCFC phase out. Final invoices pending. | 2009 |  | Investment
FIN | UNEP | Terminal phase-out management plan for Annex A Group I substances (second and third tranches) | Multi-Year | LAC | ELS | PHA | 57 | TAS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2011-01-01 | 2010-03-01 |  | 2012-06-01 | 2013-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
COM | UNDP | HCFC phase-out management plan (stage I, first tranche) (phase out of HCFC-141b in imported pre-blended polyols used in the foam manufacturing sector) | Multi-year | LAC | ELS | PHA | 65 | INV | 29 | N | I | HCFC | 4.9 | 4.9 | 0 | 0 | 2011-11-01 | 2013-03-01 | 2015-11-01 |  | 2015-11-01 |  | 439277 | 0 | 439277 | 437600.61 | 99.62% | 1676.39 | 0 | 1424.9315 | 32946 | 0 | 32820.2699 | 125.7301 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2015. |  | 2011 |  | Investment
FIN | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | LAC | ELS | PHA | 65 | INV | 30 | N | I | HCFC | 0.9 | 0.9 | 0 | 0 | 2011-11-01 | 2013-03-01 | 2015-11-01 |  | 2015-11-01 | 2016-11-01 | 91072 | 0 | 91072 | 91072 | 100% | 0 | 0 | 0 | 6830 | 0 | 6830 | 0 | 0 | Financially completed in 2016. | 2015 work plan is under implementation. Training of technicians on good refrigeration practices continues. Second tranche requested and approved. | 2011 |  | Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | LAC | ELS | PHA | 65 | TAS | 28 | A | I |  | 0.7 | 0 | 0 | 0 | 2011-11-01 | 2012-06-01 | 2015-11-01 | 2018-12-01 |  |  | 166500 | 0 | 166500 | 59151.36 | 35.53% | 107348.64 | 0 | 10734.864 | 5850 | 0 | 2078.291 | 3771.709 | 0 | Brief progress report: New SSFA was cleared by the NOO and the NOU´s legal advisory and has been forwarded to Ministry of External Relations (co-signer). To maximize implementation effectiviness, remaining funds of 1st tranche + 2nd tranche approved in 2015 were joined under the SSFA. Action Plan for implementation was agreed. Legal arrangements (actual/planned): SSFA # 1 signed in November 2013 (expired in Nov. 2015) / Planned for Feb 2012 . New SSFA not signed. Expected to May 2017. First mission (actual/planned): July 2013/no specific date was planned. TOR completed (actual/planned): 0/0. First disbursement date (actual/planned): (for the expired SSFA) November 2013/February 2012. ---- All funds disbursed? No. Any delay? No. ---- If Yes, reasons for delay & action plan to resolve: Delays reported in 2015 were solved (which caused rain reaction and delayed the further tranches). ---- If Yes, will delay have impact on project completion date? N/A. Any ongoing problems? No. ----- If Yes, is any action required by ExCom: No. | Brief progress report: New SSFA awaiting the Ministry of External Relations approved in order to be signed. (To maximize implementation effectiveness, remaining funds of 1st tranche + 2nd tranche approved in 2015 were joined under the SSFA.) Legal arrangements (actual/planned): New SSFA not signed, expected to May 2017. First mission (actual/planned): July 2013/no specific date was planned. TOR completed (actual/planned): 0/0. First disbursement date (actual/planned): (for the expired SSFA) November 2013/February 2012. ---- All funds disbursed? No. Any delay? No. ---- If Yes, reasons for delay & action plan to resolve: Delays reported in 2015 were solved (which caused rain reaction and delayed the further tranches). ---- If Yes, will delay have impact on project completion date? N/A. Any ongoing problems? No. ----- If Yes, is any action required by ExCom: No. |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor the signing of the agreement by the Government and UNEP (original agreement expired).
COM | UNDP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | LAC | ELS | PHA | 74 | INV | 31 | N | I | HCFC | 0 | 0 | 0 | 0 | 2015-05-01 | 2015-08-01 | 2017-05-01 |  | 2016-12-01 |  | 58928 | 0 | 58928 | 57928.59 | 98.3% | 999.41 | 0 | 849.4985 | 4420 | 0 | 4345.0375 | 74.9625 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): ToR for hiring the international consultant were prepared and hiring process launched. International consultant hired. 2 train-the-trainers workshops to update their GRP knowledge, 20 trainers from across the country participated, and 2 workshops for refrigeration technicians, 160 technicians were trained. 160 basic kits for RAC technicians were bought. Prodoc signed (actual/planned, yes/no and date):The agreement has been signed earlier. Missions undertaken (actual/planned):1 of 1 TOR for consultants/subcontracts completed (actual/planned): 2 of 2 Contract/PO/MOA agreements signed: 2 of 2 First disbursement date (actual/planned): 42217Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve:N/A | Completion and follow up process underway. | 2015 |  | Investment
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | ELS | PHA | 74 | TAS | 32 | A | I |  | 0 |  | 0 |  | 2015-05-01 |  | 2016-05-01 | 2018-12-01 |  |  | 18500 | 0 | 18500 | 0 | 0% | 18500 | 0 | 1850 | 650 | 0 | 0 | 650 | 0 | Brief progress report: New SSFA was cleared by the NOO and the NOU´s legal advisory and has been forwarded to Ministry of External Relations (co-signer). To maximize implementation effectiviness, remaining funds of 1st tranche + 2nd tranche approved in 2015 were joined under the SSFA. Action Plan for implementation was agreed. Legal arrangements (actual/planned): (new SSFA) not signed / April 2017. First mission (actual/planned): July 2013/no specific date was planned. TOR completed (actual/planned): 0/0. First disbursement date (actual/planned): (new SSFA) no disbursement / July 2017. ---- All funds disbursed? No. Any delay? No. ---- If Yes, reasons for delay & action plan to resolve: Delays reported in 2015 were solved (which caused rain reaction and delayed the further tranches). ---- If Yes, will delay have impact on project completion date? N/A. Any ongoing problems? No. ----- If Yes, is any action required by ExCom: No. | Brief progress report: New SSFA awaiting the Ministry of External Relations approved in order to be signed. (To maximize implementation effectiveness, remaining funds of 1st tranche + 2nd tranche approved in 2015 were joined under the SSFA.) Legal arrangements (actual/planned): (new SSFA) not signed / April 2017. First mission (actual/planned): July 2013/no specific date was planned. TOR completed (actual/planned): 0/0. First disbursement date (actual/planned): (new SSFA) no disbursement / July 2017. ---- All funds disbursed? No. Any delay? No. ---- If Yes, reasons for delay & action plan to resolve: Delays reported in 2015 were solved (which caused rain reaction and delayed the further tranches). ---- If Yes, will delay have impact on project completion date? N/A. Any ongoing problems? No. ----- If Yes, is any action required by ExCom: No. |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor the signing of the agreement by the Government and UNEP.
ONG | UNDP | HCFC phase-out management plan (stage I, third tranche) | Multi-year | LAC | ELS | PHA | 77 | INV | 34 | N | I | HCFC | 2 | 0 | 0 | 0 | 2016-12-01 |  | 2020-12-01 | 2017-12-01 |  |  | 94000 | 0 | 94000 | 0 | 0% | 94000 | 0 | 37600 | 7050 | 0 | 0 | 7050 | 0 | Newly Approved | DoA sent in February 2017. ProDoc is under preparation. | 2016 |  | Investment
ONG | UNEP | HCFC phase-out management plan (stage I, third tranche) | Multi-year | LAC | ELS | PHA | 77 | TAS | 35 | A | I |  | 0.3 |  | 0 |  | 2016-12-01 |  | 2020-12-01 | 2020-12-01 |  |  | 171000 | 0 | 171000 | 0 | 0% | 171000 | 0 | 17100 | 4680 | 0 | 0 | 4680 | 0 | Brief Report: Project approved in 2016, 77th ExCom. Legal arrangements: Agreement being negotiated with GOV. TOR completed (actual/planned): 0/0 First disbursement date (actual/planned): 0 disbursed / Jan 2018 - All funds disbursed? No. Any delay? No. --- If Yes, will delay have impact on project completion date? n/a Any ongoing problems? No. --- If Yes, is any action required by ExCom? N/A. | Brief Report: Agreement being negotiated. Legal arrangements: Agreement being negotiated with GOV. TOR completed (actual/planned): 0/0 First disbursement date (actual/planned): 0 disbursed / Jan 2018 - All funds disbursed? No. Any delay? No. --- If Yes, will delay have impact on project completion date? n/a Any ongoing problems? No. --- If Yes, is any action required by ExCom? N/A.
FIN | UNDP | Project preparation in the refrigeration sectors | Individual | LAC | ELS | REF | 21 | PRP | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2000-12-01 | 45000 | -3239 | 41761 | 41761 | 100% | 0 | 0 | 0 | 5850 | -421.07 | 5428.93 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators and freezers at Prado, S.A. de C.V. | Individual | LAC | ELS | REF | 22 | INV | 03 | A | I | CFC | 22.4 | 22.4 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 2000-06-01 | 2001-12-01 | 306229 | 0 | 306229 | 306229 | 100% | 0 | 0 | 0 | 39809.77 | 0 | 39809.77 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Implementation of the RMP: Monitoring of the activities included in the RMP | RMP-Component | LAC | ELS | REF | 25 | TAS | 06 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 2002-01-01 | 2000-08-01 |  | 2003-06-01 | 2005-10-01 | 10500 | -1035 | 9465 | 9465 | 100% | 0 | 0 | 0 | 1365 | -135 | 1230 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 1998 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: Implementation of a national programme for recovery and recycling of refrigerants | RMP-Component | LAC | ELS | REF | 25 | TAS | 09 | A | I | CFC | 36.3 | 36.3 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 2001-12-01 | 2003-05-01 | 403925 | -26048 | 377877 | 377877 | 100% | 0 | 0 | 0 | 52510.25 | -3386.24 | 49124.01 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNEP | Implementation of the RMP: train the trainers programme in the refrigeration sector | Individual | LAC | ELS | REF | 25 | TRA | 07 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-10-01 | 2000-02-01 |  | 2001-12-01 | 2003-07-01 | 39000 | 0 | 39000 | 39000 | 100% | 0 | 0 |  | 5070 | 0 | 5070 | 0 | 0 |  |  |  | 2000-12-01
FIN | UNEP | Implementation of the RMP: customs training | Individual | LAC | ELS | REF | 25 | TRA | 08 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-10-01 | 1999-08-01 |  | 2004-03-01 | 2005-02-01 | 38000 | -14300 | 23700 | 23700 | 100% | 0 | 0 |  | 4940 | -1859 | 3081 | 0 | 0
FIN | UNDP | Preparation of the refrigerant management plan update | Individual | LAC | ELS | REF | 37 | PRP | 11 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-07-01 | 2002-11-01 | 2003-08-01 |  | 2004-12-01 | 2005-12-01 | 17500 | 0 | 17500 | 17500 | 100% | 0 | 0 | 0 | 2275 | 0 | 2275 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | RMP update: technical assistance for the refrigeration sector | Individual | LAC | ELS | REF | 42 | TAS | 13 | N | I | CFC | 172.5 | 172.5 | 0 | 0 | 2004-04-01 | 2005-12-01 | 2008-04-01 |  | 2007-12-01 | 2009-08-01 | 231700 | -1 | 231699 | 231699 | 100% | 0 | 0 | 0 | 20853 | -0.09 | 20852.91 | 0 | 0 | Completed in 2007.Financially completed in 2009. |  | 2004 |  | Investment
FIN | UNDP | RMP update: monitoring programme | Individual | LAC | ELS | REF | 42 | TAS | 15 | N | I | CFC | 30.5 | 30.5 | 0 | 0 | 2004-04-01 | 2005-12-01 | 2008-04-01 |  | 2008-04-01 | 2009-08-01 | 41000 | -485 | 40515 | 40515 | 100% | 0 | 0 | 0 | 3690 | -43.65 | 3646.35 | 0 | 0 | Completed in 2008.Financially completed in 2009. Difference has been returned back to UNDP at 60th Meeting. 2010 PR will reflect correct amounts. |  | 2004 |  | Investment
FIN | UNDP | RMP update: technical assistance for certification and licensing of refrigeration technicians | Individual | LAC | ELS | REF | 42 | TRA | 14 | N | I | CFC | 57.6 | 57.6 | 0 | 0 | 2004-04-01 | 2005-12-01 | 2008-04-01 |  | 2007-12-01 | 2009-08-01 | 77300 | -1 | 77299 | 77299 | 100% | 0 | 0 | 0 | 6957 | -0.09 | 6956.91 | 0 | 0 | Completed in 2007.Financially completed in 2009. |  | 2004 |  | Investment
FIN | UNEP | Country programme preparation | Individual | LAC | ELS | SEV | 16 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-06-01 | 1996-06-01 |  | 1997-03-01 | 1999-01-01 | 40000 | -5000 | 35000 | 35000 | 100% | 0 | 0 |  | 5200 | -650 | 4550 | 0 | 0
FIN | UNEP | Area of policies for the protection of the ozone layer (institutional strengthening) | Individual | LAC | ELS | SEV | 22 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-10-01 | 2000-05-01 |  | 2001-06-01 | 2001-12-01 | 66900 | 0 | 66900 | 66900 | 100% | 0 | 0 |  | 8697 | 0 | 8697 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening | Individual | LAC | ELS | SEV | 32 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-07-01 | 2003-01-01 |  | 2003-03-01 | 2004-05-01 | 44600 | 0 | 44600 | 44600 | 100% | 0 | 0 |  | 5798 | 0 | 5798 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project | Individual | LAC | ELS | SEV | 38 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2004-01-01 | 2004-12-01 |  | 2005-12-01 | 2006-10-01 | 57980 | 0 | 57980 | 57980 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | LAC | ELS | SEV | 44 | INS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-12-01 | 2006-12-01 |  | 2007-06-01 | 2009-01-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (year 1 of phase V) | Individual | LAC | ELS | SEV | 52 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-01-01 | 2009-09-01 |  | 2009-09-01 | 2010-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (year 2 of phase V) | Individual | LAC | ELS | SEV | 56 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-03-01 | 2009-11-01 |  | 2011-12-01 | 2013-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNDP | Survey of ODS alternatives at the national level | Individual | LAC | ELS | SEV | 74 | TAS | 33 | N | I | HFC | 0 | 0 | 0 | 0 | 2015-05-01 | 2016-03-01 | 2016-11-01 | 2017-03-01 |  |  | 70000 | 0 | 70000 | 26164.15 | 37.38% | 43835.85 | 3750 | 17534.34 | 6300 | 0 | 2354.7735 | 3945.2265 | 337.5 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Project team hired. Methodology for conducting the survey was discussed and approved. Survey conducted and draft report prepared. Prodoc signed (actual/planned, yes/no and date):Yes, on Jan 2016 Missions undertaken (actual/planned):1 of 1 TOR for consultants/subcontracts completed (actual/planned): 2 of 2 Contract/PO/MOA agreements signed: 2 of 2 First disbursement date (actual/planned): 42430Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve:N/A | Final report prepared. Excel tables with preliminary results completed and submitted. | 2015 |  | Non-Investment
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | EQG | PHA | 56 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-06-01 | 2009-11-01 |  | 2011-12-01 | 2012-12-01 | 85000 | -10528 | 74472 | 74472 | 100% | 0 | 0 |  | 11050 | -1368.64 | 9681.36 | 0 | 0
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | EQG | PHA | 57 | TAS | 04 | A | I | CFC-12 | 4.6 | 4.6 | 0 | 0 | 2009-04-01 | 2011-01-01 | 2010-09-01 |  | 2013-12-01 | 2014-12-01 | 105000 | -25000 | 80000 | 80000 | 100% | 0 | 0 |  | 13650 | -3250 | 10400 | 0 | 0
FIN | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | EQG | PHA | 65 | INV | 06 | A | I | HCFC | 0.3 | 0.3 |  |  | 2011-11-01 | 2012-09-01 | 2016-11-30 |  | 2014-12-31 | 2016-03-01 | 75000 | -38 | 74962 | 74961.69 | 100% | 0.31 | 0 |  | 6750 | -3 | 6747 | 0 | 0 | The project was financially completed and the balance was returned at the 76th ExCom. |  |  |  | INV
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | AFR | EQG | PHA | 65 | TAS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-06-01 | 2013-11-01 | 2017-12-01 |  |  | 40000 | 0 | 40000 | 22050.18 | 55.13% | 17949.82 | 17949.82 | 1794.982 | 5200 | 0 | 2866.5234 | 2333.4766 | 2333.4766 | Brief progress report (actual/planned): SSFA amended for extension. Country signed the amended SSFA in March 2016; NOU trained 18 RAC technicians and 14 custom officers in 2016. Legal arrangements (actual/planned): Agreement signed in March 2016 .First payment: Apr-16. All activities under the SSFA are completed (as planned) _No_First mission (actual/planned): _ N/A -TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement Apr-16__ All funds disbursed (yes/no): _ No__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Brief progress report (actual/planned): Legal arrangements (actual/planned): first agreement signed in February 2012. SSFA expired in Feb 2015 with a balance of SSFA amended for extension until March 2017. Country signed the amended SSFA in March 2016; NOU trained 18 RAC technicians and 14 custom officers in 2016. Legal arrangements (actual/planned): amended Agreement signed in March 2016 .First payment: Apr-16. All activities under the SSFA are completed (as planned) _No. _First mission (actual/planned): _ N/A -TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement Apr-16__ All funds disbursed (yes/no): _ No__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | AFR | EQG | PHA | 74 | TAS | 08 | A | I |  | 0.3 |  | 0 |  | 2015-05-01 | 2016-09-01 | 2016-12-01 | 2018-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 12050.18 | 3000 | 3900 | 0 | 0 | 3900 | 1566.5234 | Brief progress report (actual/planned): Country signed the SSFA in March 2016; Legal arrangements (actual/planned): Agreement signed in March 2016 .First payment: September 2016. Under this tranche, NOU has supervised the training of 20 RAC technicians’ trainers as well as the training of 16 customs officers’ trainers in 2016. All activities under the SSFA are completed (as planned) _No_First mission (actual/planned): _ N/A -TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement Sept. 2016__ All funds disbursed (yes/no): _ No__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Brief progress report (actual/planned): Country signed the SSFA in March 2016; Legal arrangements (actual/planned): Agreement signed in March 2016 .First payment: September 2016. Under this tranche, NOU has supervised the training of 20 RAC technicians’ trainers as well as the training of 16 customs officers’ trainers in 2016. All activities under the SSFA are completed (as planned) _No. _First mission (actual/planned): _ May 2017 -TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement Sept. 2016__ All funds disbursed (yes/no): _ No__ Any delay? (yes/no): Yes___ If Yes, reasons for delay & action plan to resolve: The NOO is hospitalized and couldn’t finalized the implementation of activities before end March 2017___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
ONG | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Individual | AFR | EQG | PHA | 75 | TAS | 11 | A | I |  | 0 |  | 0 |  | 2015-11-01 |  | 2017-03-01 | 2017-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 3000 | 3900 | 0 | 0 | 3900 | 0 | Brief progress report (actual/planned): Consultant identified and will start the exercise in May 2017. The mission is delayed because the NOO is currently hospitalized. Legal arrangements (actual/planned): All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): UNEP to hire and pay the consultant_ All funds disbursed (yes/no): NO Any delay? (yes/no): Yes ___ If Yes, reasons for delay & action plan to resolve: Difficulty to identify a consultant speaking both spanish and french___ If Yes, will delay have impact on project completion date (yes/no): _ No, the consultant is identified and will start in May __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Brief progress report (actual/planned): Consultant identified and will start the exercise in May 2017. The mission is delayed because the NOO is currently hospitalized. Legal arrangements (actual/planned): All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): UNEP to hire and pay the consultant_ All funds disbursed (yes/no): NO Any delay? (yes/no): Yes ___ If Yes, reasons for delay & action plan to resolve: Difficulty to identify a consultant speaking both spanish and french___ If Yes, will delay have impact on project completion date (yes/no): _ No, the consultant is identified and will start in May __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
FIN | UNEP | Project preparation for a country programme/refrigerant management plan | Individual | AFR | EQG | SEV | 49 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2008-03-01 | 2007-07-01 |  | 2010-12-01 | 2011-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0
FIN | UNEP | Start-up of institutional strengthening project | Individual | AFR | EQG | SEV | 49 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-12-01 | 2007-07-01 |  | 2009-03-01 | 2010-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Institutional strengthening (phase I) | Individual | AFR | EQG | SEV | 57 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2011-01-01 | 2011-03-01 | 2017-12-01 |  |  | 80000 | 0 | 80000 | 24282.49 | 30.35% | 55717.51 | 55717.51 | 5571.751 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): SSFA amended for extension till March 2017. Amended SSFA signed in March 2016. Payment sent in April 2016. Country reported 2015 Art. 7 and 2015 CP data as well. Country celebrated the 2016 Ozone day. Legal arrangements (actual/planned): Agreement signed in March 2016. All activities under the SSFA are completed (as planned) __No_ First mission (actual/planned): Project Completed _No_ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _April 2016. First payment after amendment April 2016. All funds disbursed (yes/no): No_ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Brief progress report (actual/planned): SSFA amended for extension till March 2017. Amended SSFA signed in March 2016. Payment sent in April 2016. Country reported 2015 Art. 7 and 2015 CP data as well. Country celebrated the 2016 Ozone day. Legal arrangements (actual/planned): Agreement signed in March 2016. All activities under the SSFA are completed (as planned) __No_ First mission (actual/planned): Project Completed _No_ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _April 2016. First payment after amendment sent April 2016. All funds disbursed (yes/no): No_ Any delay? (yes/no): Yes ___ If Yes, reasons for delay & action plan to resolve: The NOO is hospitalized and couldn’t finalized the implementation of activities before end March ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
ONG | UNEP | Renewal of the institutional strengthening project (phase II: 6/2015-5/2017) | Individual | AFR | EQG | SEV | 74 | INS | 09 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-05-01 | 2017-05-01 | 2018-07-01 |  |  | 80000 | 0 | 80000 | 0.49 | 0.0006125% | 79999.51 | 80000 | 7999.951 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): SSFA signed in February 2016. Country reported 2015 Art. 7 and 2015 CP data as well. Country celebrated the 2016 Ozone day. Legal arrangements (actual/planned): Agreement signed in February 2016. All activities under the SSFA are completed (as planned) __No_ First mission (actual/planned): Project Completed _No_ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): May 2016. All funds disbursed (yes/no): No_ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Brief progress report (actual/planned): SSFA signed in February 2016. Country reported 2015 Art. 7 and 2015 CP data as well. Country celebrated the 2016 Ozone day. Legal arrangements (actual/planned): Agreement signed in February 2016. All activities under the SSFA are completed (as planned) __No_ First mission (actual/planned): Project Completed _No_ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): May 2016. All funds disbursed (yes/no): No_ Any delay? (yes/no): Yes__ If Yes, reasons for delay & action plan to resolve: The NOO is currently hospitalized ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | AFR | EQG | SEV | 74 | TAS | 10 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-04-01 | 2016-05-01 | 2017-10-01 |  |  | 70000 | 0 | 70000 | 32.49 | 0.04641% | 69967.51 | 60000 | 6996.751 | 9100 | 0 | 4.2237 | 9095.7763 | 7800 | Brief progress report (actual/planned): Country signed the SSFA in December 2015. First payment sent in April 2016. NOO to seek for a consultant coming from Chad will lead the consultant’s team. Legal arrangements (actual/planned): Agreement signed in December 2015. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in April 2016 __ All funds disbursed (yes/no): _ n/a.__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Brief progress report (actual/planned): Country signed the SSFA in December 2015. First payment sent in April 2016. Local consultants hired in June 2016 and survey activities started in June 2016. A senior consultant coming from Chad will lead the consultant’s team. Country submitted the draft report in January 2017. Legal arrangements (actual/planned): Agreement signed in December 2015. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in April 2016 __ All funds disbursed (yes/no): _ n/a.__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
FIN | UNIDO | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | ERI | PHA | 54 | INV | 05 | A | I |  | 0 | 0 |  |  | 2008-04-01 | 2010-05-01 | 2010-03-31 |  | 2012-03-01 | 2012-04-01 | 100000 | -1 | 99999 | 99999.35 | 100% | -0.35 | 0 |  | 9000 | 0 | 9000 | 0 | 0 | FIN |  |  |  | INV
FIN | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | ERI | PHA | 54 | TAS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2011-02-01 | 2010-03-01 |  | 2014-12-01 | 2015-12-01 | 100000 | -20000 | 80000 | 80000 | 100% | 0 | 0 |  | 13000 | -2600 | 10400 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | ERI | PHA | 55 | PRP | 07 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-02-01 | 2009-07-01 |  | 2013-07-01 | 2014-07-01 | 85000 | -30000 | 55000 | 55000 | 100% | 0 | 0 |  | 11050 | -3900 | 7150 | 0 | 0
FIN | UNIDO | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | ERI | PHA | 63 | INV | 09 | A | I | CFC | 4.2 | 4.2 |  |  | 2011-04-01 | 2011-12-01 | 2012-03-31 |  | 2013-12-01 | 2014-08-01 | 75000 | -606 | 74394 | 74393.9 | 100% | 0.1 | 0 |  | 6750 | -55 | 6695 | 0 | 0 | FIN |  |  |  | INV
FIN | UNEP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | ERI | PHA | 63 | TAS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 |  | 2012-03-01 |  | 2014-12-01 | 2014-12-01 | 70000 | -70000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 9100 | -9100 |  | 0
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | ERI | PHA | 67 | INV | 10 | A | I |  | 0 | 0 |  |  | 2012-07-01 | 2014-04-01 | 2016-07-31 | 2017-06-17 |  |  | 40000 | 0 | 40000 | 26860.65 | 67.15% | 13139.35 | 0 | 13139 | 3600 | 0 | 2417 | 1183 | 0 | The new tranche was not submitted by UNEP, lead implementing agency, to the 76th ExCom. Since with the remaining funds it was not possible to implement the planned activities, no progress has taken place in 2016. The next tranche was submitted by UNEP to the 77th ExCom in Nov 2016. - Delay in implementation due to the above - No recurring problem - Impact on project completion date - No action required by Executive Committee | With the approval of the second tranche the tools to establish a reclaiming center and some required to upgrade the actual centers were purchased. The cost was divided between both tranches. The tools and reclaiming unit are expected to be in the country in May 2017. Action towards next goals: A reclaiming center will be established in Massawa training center aiming end-users as provision of refrigerant reclaiming service. - Delay in implementation due to the late submission of the second tranche request by lead IA, UNEP - No recurring problem - Impact on project completion date - No action required by Executive Committee |  |  | INV
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | AFR | ERI | PHA | 67 | TAS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2014-12-01 | 2016-07-01 | 2017-05-01 |  |  | 40000 | 0 | 40000 | 22868.75 | 57.17% | 17131.25 | 17131.25 | 1713.125 | 5200 | 0 | 2972.9375 | 2227.0625 | 2227.0625 | Brief progress report (actual/planned): The NOU trained 25 customs and law enforcement officers to carry out the enforcement of ODS control measures as well as combat illegal ODS trade in the country. Additional 30 Customs officers in Tesney were trained from 7-8 July, 2016 to enhance their capacity in conducting inspection of illegal entry of ODS. The NOU conducted one RAC training workshop for 30 technicians. The NOU conducted one steering committee meeting to monitor, coordinate and review operations of the NOU. The NOU submitted 2015 Country Programme and Article 7 Data reports in May 2016. The NOU celebrated 2016 International Ozone Day and conducted several awareness activities. The NOU participated in all Montreal Protocol meetings organized in 2016. ___ Legal arrangements (actual/planned): The SSFA was drafted and signed by Government and the Government of Eritrea in May 2015. ___Initial stages of project implementation (actual/planned): __Yes_ Intermediate goals achieved (actual/planned): _Yes__ Project completion and follow up: _Yes__ First disbursement date (actual/planned): __Jan 2016 ____. All funds disbursed (yes/no): No__ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: __N/A_ | Brief progress report (actual/planned): The NOU continues to monitor imports and trade of ODS and ODS related equipment
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | AFR | ERI | PHA | 77 | INV | 15 | A | I | HCFC | 0.2 | 0 |  |  | 2016-11-01 |  | 2020-12-31 | 2020-12-31 |  |  | 80000 | 0 | 80000 | 0 | 0% | 80000 | 0 | 15000 | 7200 | 0 | 0 | 7200 | 0 | Noted that the Agreement was updated based on the established HCFC baseline for compliance; and that the revised starting point for sustained aggregate reduction in HCFC consumption was 1.08 ODP tonnes, calculated using actual consumption of 1.05 ODP tonnes and 1.12 ODP tonnes reported for 2009 and 2010, respectively, under Article 7 of the Montreal Protocol and that the revised funding level for stage I of the HPMP for Eritrea was US$210,000 plus agency support costs, in accordance with decision 60/44(f)(xii). Approved on the understanding that if Eritrea were to decide to proceed with retrofits and associated servicing to flammable and toxic refrigerants in refrigeration and air-conditioning equipment originally designed for non-flammable substances, it would do so assuming all associated responsibilities and risks and only in accordance with the relevant standards and protocols. | As above. Activities are combined under first and second trance. - No delay in implementation - No recurring problem - No impact on project completion date - No action required by Executive Committee
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | AFR | ERI | PHA | 77 | TAS | 14 | A | I |  | 0.2 |  | 0 |  | 2016-12-01 |  | 2020-12-01 | 2020-12-01 |  |  | 29000 | 0 | 29000 | 0 | 0% | 29000 | 0 | 2900 | 3770 | 0 | 0 | 3770 | 0 | Newly approved | Brief progress report (actual/planned): The project was newly approved in Dec 2016. The NOU enforced HCFC licensing and quota system and conducted a steering committee meeting to discuss and coordinate the implementation of newly approved HPMP.___ Legal arrangements (actual/planned): _ The SSFA was drafted by UNEP in Feb 2017 and sent to the Government of Eritrea for signature _ First mission (actual/planned): No___ TOR completed(actual/planned): __No_ First disbursement date (actual/planned): No__ All funds disbursed (yes/no): No__ Any delay? (yes/no): No___ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): N/A___ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: __No_
CLO | UNDP | Project preparation of the investment components of the RMP | Individual | AFR | ERI | REF | 47 | PRP | 01 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2006-12-01 |  |  | 2007-12-01 | 20000 | -20000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 1500 | -1500 | 0 | 0 | 0 | Canceled in 2006. Financially completed in 2007. |  | 2005 |  | Investment
FIN | UNEP | Institutional strengthening project (start-up cost) | Individual | AFR | ERI | SEV | 47 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-04-01 | 2006-12-01 |  | 2008-02-01 | 2009-08-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Country programme/RMP project preparation | RMP | AFR | ERI | SEV | 47 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-04-01 | 2006-12-01 |  | 2006-09-01 | 2008-12-01 | 40000 | -2000 | 38000 | 38000 | 100% | 0 | 0 |  | 5200 | -260 | 4940 | 0 | 0
COM | UNEP | Institutional strengthening (phase I) | Individual | AFR | ERI | SEV | 54 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2010-05-01 | 2010-03-01 |  | 2016-11-01 |  | 40000 | 0 | 40000 | 22007.85 | 55.02% | 17992.15 | 0 | 17992 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The licensing and quota systems are in place and functioning. The NOU registered all importers of HCFCs and organized one stakeholders meeting in Feb 2016 to coordinate and allocate licenses and quotas. The NOU conducted two inspection visits on importers to assess compliance with allocated quotas. The NOU trained 30 custom officers and 40 RAC technicians. The NOU submitted 2015 Country Programme and Article 7 Data reports. The NOU celebrated 2016 International Ozone Day and conducted several awareness activities, printed 300 T shirts and organized Radio Talk-shows. The NOU also participated in all Montreal Protocol meetings organized in 2016.___ Legal arrangements(actual/planned): SSFA was signed between the country and UNEP in March 2010__Initial stages of project implementation(actual/planned): _Yes__ Intermediate goals achieved (actual/planned): _Yes__ Project completion and follow up: Yes___ First disbursement date (actual/planned): _May 2010__ All funds disbursed (yes/no): _Yes__ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: __N/A_ If Yes, will delay have impact on project completion date (yes/no): _Yes__ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: _N/A__ | Project Completed
ONG | UNEP | Institutional strengthening (phase II: 1/2013-12/2014) | Individual | AFR | ERI | SEV | 68 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2015-12-01 | 2014-11-01 | 2017-05-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 60000 | 6000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The licensing and quota systems are in place and operational. The NOU conducted stakeholder’s workshop to allocate HCFCs licenses and quotas. The NOU conducted regular inspection activities to ensure compliance and distributed tools to RAC technicians. The NOU conducted training for 30 RAC technicians from 3-4 Sept 2016, in Assab. The NOU trained 40 Custom officers in combating illegal trade. The NOU conducted public awareness activities at the city of Barentu and Akordat from 13-15 October 2016 to raise awareness on ODS and HPMP implementation. The NOU Posted Articles on National Newspaper and conducted a talk show on the national radio station on 16th of October 2016. | Brief progress report (actual/planned): The NOU continues to monitor imports and trade of ODS and ODS related equipment. Collection of the 2016 data on ODS imports and consumption has been completed and is being analyzed for submission. NOU commenced preparation of national legislative requirement processes in planning for ratification of Kigali amendment. |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor project implementation progress and the disbursement rate of approved funds.
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | AFR | ERI | SEV | 74 | TAS | 13 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-03-01 | 2016-05-01 | 2017-05-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 40000 | 4000 | 5200 | 0 | 0 | 5200 | 5200 | Brief progress report (actual/planned): The first stakeholders meeting was organized by the NOU on 1st August 2016 in Massawa and 40 participants from the ODS alternative user sectors and importers attended. The main goal of the meeting was to sensitize the government and industry on the survey and agree on the plan for the Survey of ODS alternatives at the national level and obtain support of main national stakeholders. One National Consultant was hired in March 2016 by the NOU to support the data collection. The National Consultant assisted the NOU in the identification of the current use of ODS alternatives by substance/sector and collection of import/export data for the substances for the past a couple of years. The National Consultant also provided support in establishing growth patterns in use by substance/sector and in compiling data on available ODS alternatives for various applications.The NOU and the National Consultant drafted and cross checked the information to ensure the completion of end-user surveys, collection, analysis, and aggregation of consumption data. The various sections of the report were drafted. The second stakeholders meeting was organized by the NOU in Asmara on 25th October 2016 with the main goal to organise consultations with representatives of the government and private sector to finalize the outcomes of the Survey of ODS alternatives and discuss potential opportunities for introduction of those alternatives in the country. A total of 40 participants were in attendance. The draft report was prepared by the NOU and the National Consultant. It was reviewed and finalized based on the format approved by ExCom decision 75/67 as contained in document UNEP/OzL.Pro/ExCom/75/77/Rev.1 after incorporating inputs/ comments raised during National Stakeholders’ workshop. The final report was submitted to UNEP in November 2016 for final review and submission to MLFS. The NOU participated in the ODS Alternative Thematic workshop held in December 2016 to refine the draft report according to the revised template for the report. The report has been finally submitted to UNEP. Legal arrangements(actual/planned): The SSFA was drafted and signed by UNEP and the Government of Eritrea in Jan 2016___Initial stages of project implementation(actual/planned): _Yes__ Intermediate goals achieved (actual/planned): Yes___ Project completion and follow up: _Yes__ First disbursement date (actual/planned): _March 2016__ All funds disbursed (yes/no): No___ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): __N/A_ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): The NOU incorporated comments from UNEP ROA and Paris and re-submitted final ODS survey report.
ONG | UNEP | Renewal of the institutional strengthening project (phase III: 12/2016-11/2018) | Individual | AFR | ERI | SEV | 77 | INS | 16 | A | I |  | 0 |  | 0 |  | 2016-12-01 |  | 2018-11-01 | 2018-11-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | Newly approved project. | Brief progress report (actual/planned): The newly approved project. The licensing and quota system are in place and operational. The NOU continues to monitor imports and trade of ODS and ODS related equipment. Collection of the 2016 data on ODS imports and consumption has been completed and is being analyzed for submission. NOU commenced preparation of national legislative requirement processes in planning for ratification of Kigali amendment. ___ Legal arrangements (actual/planned): The SSFA was drafted and sent to the Government of Eritrea for signature. ___Initial stages of project implementation (actual/planned): __Yes_ Intermediate goals achieved (actual/planned): _No__ Project completion and follow up: _Yes__ First disbursement date (actual/planned): __No ____. All funds disbursed (yes/no): No__ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: __N/A_
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organizations in methyl bromide communication | Individual | AFR | ETH | FUM | 30 | TAS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -7326 | 17674 | 17674 | 100% | 0 | 0 |  | 3250 | -952.38 | 2297.62 | 0 | 0
COM | UNIDO | Project preparation in the fumigant sector (flowers) | Individual | AFR | ETH | FUM | 54 | PRP | 18 | A | I |  | 0 | 0 |  |  | 2008-04-01 | 2008-12-01 | 2009-03-31 |  | 2015-12-01 |  | 35000 | 0 | 35000 | 24469.65 | 69.91% | 10530.35 | 95.9 | 1 | 2625 | 0 | 1835 | 790 | 7 | The project was operationally completed. |  |  |  | NON-INV
FIN | France | Project preparation for a terminal phase-out management plan in the servicing sector | Individual | AFR | ETH | PHA | 51 | PRP | 17 | A | I | CFC | 0 |  | 0 |  | 2007-03-01 | 2008-12-01 | 2008-03-01 |  | 2010-07-01 | 2010-07-01 | 30000 | -12400 | 17600 | 17600 | 100% | 0 |  | 0 | 3900 | -1612 | 2288 | 0 |  | The French contribution was implemented by GTZ-Proklima. The survey for the preparation of the TPMP has been completed but the continued lack of regulations prevents Ethiopia from submitting the TPMP. Funds will be returned to MLF.
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | ETH | PHA | 56 | PRP | 19 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-07-01 | 2009-11-01 |  | 2013-07-01 | 2014-07-01 | 85000 | -38581 | 46419 | 46419 | 100% | 0 | 0 |  | 11050 | -5016.53 | 6033.47 | 0 | 0
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | ETH | PHA | 68 | INV | 22 | A | I | HCFC | 0.2 | 0 |  |  | 2012-12-01 |  | 2016-12-31 | 2017-12-01 |  |  | 70000 | 0 | 70000 | 0 | 0% | 70000 | 56763 | 69000 | 6300 | 0 | 0 | 6300 | 5108.67 | - UNIDO received the feedback from NOU and TOR for the purchase of equipment was initiated and finalized. Technology provider selected and contract awarded. Milestones achieved: Milestone 1: First mission/Working arrangements (agreement/document signatures/PDA) agreed - Yes Activities planned but not implemented, reasons and strategy: None. Actions towards next goals: Finalize equipment delivery and installation. Was there any delay during the reporting year? No If yes, reasons and action plan: Any recurring problem? No If yes, description of the problem/s: Any impact on project completion date: No Any action required by Executive Committee? No | - Equipment delivered to NOU. - Verification, installation, commissioning and training for four training centers has been fixed in early April 2017. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | AFR | ETH | PHA | 68 | TAS | 21 | A | I |  | 0.3 | 0 | 0 | 0 | 2012-12-01 | 2013-06-01 | 2016-12-01 | 2017-10-01 |  |  | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 |  | 11050 | 0 | 11050 | 0 | 0 | Brief progress report (actual/planned): The licensing and quota systems are in place and operational. NOU registered all importers of HCFC for 2016, advertised for quota allocation for 2016 HCFC importation and conducted inspection visits to various boarders to check how customs officers are enforcing the control measures of HCFC importation. The Ministry, in close collaboration with the Ethiopian Customs and Revenue Authority, conducted training for 100 customs and other law enforcement officers in 2016 in Adama town 100 km from Addis Ababa. The NOU conducted one regional stakeholders’ meeting held in May 2016 for regional retrofit centres situated in regional towns of Addis Ababa and Adama which were attended by a total of 40 participants. Additional 40 refrigeration technicians and technical school teachers and 60 customs officers were trained in the train the trainer programmes in 2016 in the towns of Addis and Nazreth. The SSFA was drafted and signed by UNEP and the Government of Ethiopia in May 2013___Initial stages of project implementation(actual/planned): _Yes__ Intermediate goals achieved (actual/planned): Yes___ Project completion and follow up: _No__ First disbursement date (actual/planned): _June 2013__ All funds disbursed (yes/no): No___ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): __N/A_ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): The NOU continues to monitor imports and trade of ODS and ODS related equipment. Collection of the 2016 data on ODS imports and consumption has been completed and is being analyzed for submission. NOU commenced preparation of national legislative requirement processes in planning for ratification of Kigali amendment.
ONG | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Individual | AFR | ETH | PHA | 75 | TAS | 25 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-04-01 | 2017-03-01 | 2017-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 30000 | 3000 | 3900 | 0 | 0 | 3900 | 3900 | Brief progress report (actual/planned): The Terms of Reference (ToR) for hiring the international consultant was prepared, cleared by the management and advertised in Feb 2016. The international consultant was recruited by UNEP to verify the national consumption in relation to the targets as set out in the Agreement between ExCom and Government of Ethiopia, following the relevant decisions of the ExCom and guidelines for the verification of national consumption targets for the multi-year agreements. The consultant prepared and presented the draft work plan which included timeline for conducting the verification as well as tasks and roles and responsibilities of each concerned stakeholders in the verification process. The consultant also informed the NOU about support/cooperation that was required from various stakeholders. The consultant also reviewed official statistics on import and export maintained by different sources and analyzed and compare those statistics. In addition, the consultant conducted the necessary on-site visits and interviews, and analyzed and cross-check various data collected from different sources. The reports was produced in English and provides detailed data demonstrating and confirming whether the consumption targets in the Agreement were achieved, whether there is existence of an operational licensing and quota system for HCFC imports and exports and whether the system is capable to ensure the country's compliance with the targets as set out in the Agreement between Ethiopia and the ExCom.The verification report was finalised and submitted to Ex-com 77 | Brief progress report (actual/planned): The project was completed. NOU is implementing the recommendations from the verification report
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | AFR | ETH | PHA | 77 | INV | 28 | A | I | HCFC | 0.7 | 0 |  |  | 2016-11-01 |  | 2019-12-31 | 2019-12-31 |  |  | 70000 | 0 | 70000 | 0 | 0% | 70000 | 0 | 3500 | 6300 | 0 | 0 | 6300 | 0 | Approved on the understanding that UNEP would report on the progress in implementing the recommendations in the verification report in the next tranche submission; and if Ethiopia were to decide to proceed with retrofits and associated servicing to flammable and toxic refrigerants in refrigeration and air-conditioning equipment originally designed for non-flammable substances, it would do so assuming all associated responsibilities and risks and only in accordance with the relevant standards and protocols. | - UNIDO will undergo a mission to Ethiopia to discuss with the NOU on the best way to ensure an efficient identification of country's needs for tranche 2 in order to avoid the problems occurred during the implementation of tranche I, where UNIDO had to wait for years to receive a feedback from NOU and UNEP on the needs for training equipment. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | AFR | ETH | PHA | 77 | TAS | 27 | A | I |  | 0.8 |  | 0 |  | 2016-12-01 |  | 2019-12-01 | 2019-12-01 |  |  | 55000 | 0 | 55000 | 0 | 0% | 55000 | 0 | 5500 | 7150 | 0 | 0 | 7150 | 0 | Newly approved | Brief progress report (actual/planned): The project was approved in Dec 2016. The licensing and quota system are in place and operational. The NOU continues to monitor imports and trade of ODS and ODS related equipment. Collection of the 2016 data on ODS imports and consumption has been completed and is being analyzed for submission. NOU commenced preparation of national legislative requirement processes in planning for ratification of Kigali amendment. ___ Legal arrangements (actual/planned): The SSFA was drafted and sent to the Government of Ethiopia for signature. ___Initial stages of project implementation (actual/planned): __Yes_ Intermediate goals achieved (actual/planned): _No__ Project completion and follow up: _No__ First disbursement date (actual/planned): __No ____. All funds disbursed (yes/no): No__ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: __N/A_
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | ETH | REF | 23 | PRP | 05 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1998-03-01 |  | 1998-07-01 | 1999-07-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation lead to project proposal for implementation
TRF | Finland | Implementation of a training programme for recovery and recycling of refrigerants | Individual | AFR | ETH | REF | 23 | TRA | 04 | A | I |  | 0 |  | 0 |  | 1997-11-01 | 1998-01-01 | 1999-12-01 |  |  | 2000-03-01 | 93490 | -93490 | 0 |  |  | 0 |  | 0 | 0 | 0 |  | 0 |  | Project transferred to UNEP at ExCom 30
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | ETH | REF | 26 | TAS | 06 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2004-10-01 | 2005-09-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Completed. PCR submitted. RMP update approved in dec 2004
FIN | UNEP | Implementation of a training programme for recovery and recycling of refrigerants | Individual | AFR | ETH | REF | 30 | TRA | 09 | A | I | CFC | 11.1 | 11.1 | 0 | 0 | 2000-03-01 | 2001-11-01 | 2003-06-01 |  | 2003-06-01 | 2007-07-01 | 82735 | -24380 | 58355 | 58355 | 100% | 0 | 0 |  | 10755 | -3169.24 | 7585.76 | 0 | 0
FIN | Germany | Project preparation for a refrigerant management plan update | RMP Update | AFR | ETH | REF | 37 | PRP | 10 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-06-01 | 2003-08-01 |  | 2004-10-01 | 2004-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | RMP-update was approved at 44th ExCom
FIN | France | Implementation of the RMP update | RMP Update | AFR | ETH | REF | 44 | TAS | 14 | A | I | CFC | 12.3 |  | 0 |  | 2004-12-01 | 2005-11-01 | 2007-12-01 |  | 2010-12-01 | 2012-04-01 | 91300 | -40988.89 | 50311.11 | 50311 | 100% | 0.11 |  | 0 | 11869 | -5329 | 6791 | -251 |  | The French contribution was implemented by GIZ-Proklima. The ODS regulations were not approved despite all possible effort. However customs trainings was conducted on the use of identifiers. This project was stopped because of lack of progress.
FIN | UNEP | Country programme preparation | Individual | AFR | ETH | SEV | 16 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-09-01 | 1996-06-01 |  | 1996-12-01 | 1996-07-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0
CLO | UNDP | Project preparation assistance | Individual | AFR | ETH | SEV | 17 | PRP | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 |  | 1996-07-01 |  |  | 1997-05-01 | 30000 | -30000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 3900 | -3900 | 0 | 0 | 0 | Canceled in 1997. Financially Completed in 1997. |  | 1995 |  | Investment
FIN | UNEP | Establishment of national ozone cell for the implementation of Montreal Protocol in Ethiopia | Individual | AFR | ETH | SEV | 20 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-04-01 | 1999-10-01 |  | 2000-01-01 | 1999-11-01 | 60500 | 0 | 60500 | 60500 | 100% | 0 | 0 |  | 7865 | 0 | 7865 | 0 | 0 |  |  |  | 2000-03-01
FIN | UNEP | Renewal of institutional strengthening (phase 3 year 2) | Individual | AFR | ETH | SEV | 29 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2001-12-01 |  | 2003-06-01 | 2003-12-01 | 40300 | 0 | 40300 | 40300 | 100% | 0 | 0 |  | 5239 | 0 | 5239 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project for a one year period (phase 3) | Individual | AFR | ETH | SEV | 39 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-08-01 | 2004-04-01 |  | 2006-12-01 | 2009-05-01 | 26216 | 0 | 26216 | 26216 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | AFR | ETH | SEV | 41 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-12-01 | 2005-12-01 |  | 2008-12-01 | 2009-12-01 | 26216 | 0 | 26216 | 26216 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | ETH | SEV | 50 | INS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2009-07-01 | 2008-11-01 |  | 2013-12-01 | 2014-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of the institutional strengthening project (phase V) | Individual | AFR | ETH | SEV | 59 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2011-05-01 | 2011-11-01 | 2017-10-01 |  |  | 32500 | 27500 | 60000 | 33000 | 55% | 27000 | 27000 | 2700 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The licensing and quota systems are in place and operational. The NOU conducted stakeholder’s workshop to allocate HCFCs licenses and quotas. The NOU conducted two inspection activities to ensure compliance and distributed tools to RAC technicians. The NOU trained 30 custom officers and 40 RAC technicians. The NOU submitted 2015 Country Programme and Article 7 Data reports. The NOU celebrated 2016 International Ozone Day and conducted several awareness activities and participated in all Montreal Protocol meetings organized in 2016. __ Legal arrangements(actual/planned): The SSFA was drafted and signed by UNEP and the Government of Ethiopia March 2011___Initial stages of project implementation(actual/planned): _Yes__ Intermediate goals achieved (actual/planned): __Yes_ Project completion and follow up: _No__ First disbursement date (actual/planned): __May 2016_ All funds disbursed (yes/no): _No__ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: ___N/A If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: __N/A_ | Brief progress report (actual/planned): The NOU continues to monitor imports and trade of ODS and ODS related equipment. Collection of the 2016 data on ODS imports and consumption has been completed and is being analyzed for submission. NOU commenced preparation of national legislative requirement processes in planning for ratification of Kigali amendment.
ONG | UNEP | Extension of the institutional strengthening project (phase VI: 1/2015-12/2016) | Individual | AFR | ETH | SEV | 73 | INS | 23 | A | I |  | 0 |  | 0 |  | 2014-11-01 | 2016-05-01 | 2016-12-01 | 2018-04-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 60000 | 6000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The licensing and quota systems are in place and operational. The NOU registered all importers of HCFCs, coordinated the allocation of HCFC licenses and quotas, and conducted inspection visits to monitor distribution of HCFCs to check compliance with the quotas allocated. The NOU conducted two RAC training workshops and two custom training workshops, and trained 60 technicians and 30 custom officers respectively. | Brief progress report (actual/planned): The NOU continues to monitor imports and trade of ODS and ODS related equipment. Collection of the 2016 data on ODS imports and consumption has been completed and is being analyzed for submission. NOU commenced preparation of national legislative requirement processes in planning for ratification of Kigali amendment.
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | AFR | ETH | SEV | 74 | TAS | 24 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-04-01 | 2016-05-01 | 2017-05-01 |  |  | 40000 | 0 | 40000 | 15050 | 37.62% | 24950 | 24950 | 2495 | 5200 | 0 | 1956.5 | 3243.5 | 3243.5 | Brief progress report (actual/planned): The first stakeholders meeting was organized by the NOU on 19 June 2016 at the Ethiopian Environment and forest research institute and 40 participants from the ODS alternative user sectors and importers attended. The main goal of the meeting was to sensitize the government and industry on the survey and agree on the plan for the Survey of ODS alternatives at the national level and obtain support of main national stakeholders. The Research wing of the Ministry of the Ethiopian Environment and Forest Research Institute was hired in June 2016 by the NOU to support the data collection. The Research Wing assisted the NOU in the identification of the current use of ODS alternatives by substance/sector and collection of import/export data for the substances for the past a couple of years. The Research Wing also provided support in establishing growth patterns in use by substance/sector and in compiling data on available ODS alternatives for various applications.The NOU and the Research Wing drafted and cross checked the information to ensure the completion of end-user surveys, collection, analysis, and aggregation of consumption data. The various sections of the report were drafted. The second stakeholders meeting was organized by the NOU on 16 October 2016 at Harmony hotel with the main goal to organise consultations with representatives of the government and private sector to finalize the outcomes of the Survey of ODS alternatives and discuss potential opportunities for introduction of those alternatives in the country. A total of 30 participants were in attendance. The draft report was prepared by the NOU and the Research wing. It was reviewed and finalized based on the format approved by ExCom decision 75/67 as contained in document UNEP/OzL.Pro/ExCom/75/77/Rev.1 after incorporating inputs/ comments raised during National Stakeholders’ workshop. The final report was submitted to UNEP in December 2016 for final review and submission to MLFS. The NOU participated in the ODS Alternative Thematic workshop held in December 2016 to refine the draft report according to the revised template for the report. The report has been finally submitted to UNEP. Legal arrangements(actual/planned):The SSFA was drafted and signed by UNEP and the Government of Ethiopia in April 2016. ____Initial stages of project implementation(actual/planned): _Yes__ Intermediate goals achieved (actual/planned): Yes___ Project completion and follow up: _No__ First disbursement date (actual/planned): _May 2016__ All funds disbursed (yes/no): No___ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): __N/A_ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): The NOU incorporated comments from UNEP ROA and Paris and re-submitted final ODS survey report.
ONG | UNEP | Extension of the institutional strengthening project (phase VII 1/2017-12/2018) | Individual | AFR | ETH | SEV | 77 | INS | 26 | A | I |  | 0 |  | 0 |  | 2016-12-01 |  | 2018-12-01 | 2018-12-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | Newly approved project. | Brief progress report (actual/planned): The project was approved in Dec 2016. The licensing and quota system are in place and operational. The NOU continues to monitor imports and trade of ODS and ODS related equipment. Collection of the 2016 data on ODS imports and consumption has been completed and is being analyzed for submission. NOU commenced preparation of national legislative requirement processes in planning for ratification of Kigali amendment. ___ Legal arrangements (actual/planned): The SSFA was drafted and sent to the Government of Ethiopia for signature. ___Initial stages of project implementation (actual/planned): __Yes_ Intermediate goals achieved (actual/planned): _No__ Project completion and follow up: _Yes__ First disbursement date (actual/planned): __No ____. All funds disbursed (yes/no): No__ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: __N/A_
CLO | UNIDO | Training and awareness workshop in the solvents and process agents (CTC and TCA) sector | Individual | AFR | ETH | SOL | 45 | TAS | 15 | A | I | CTC TCA | 5.4 | 0 |  |  | 2005-04-01 | 2005-08-01 | 2006-04-01 |  |  | 2007-12-01 | 40000 | -35474 | 4526 | 4526.08 | 100% | -0.08 | 0 |  | 3600 | -3193 | 407 | 0 | 0 | CLO |  |  |  | INV
FIN | Czech Republic | Strategy for disposal and destruction of ODS for 4 LVC countries in the Europe and Central Asia region (Bosnia and Herzegovina, Croatia, Montenegro and Turkmenistan) |  | EUR | EUR | DES | 65 | PRP | 11 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-08-01 | 2012-11-01 |  | 2013-05-01 |  | 35000 | -5590 | 29410 | 29410.27 | 100% | -0.27 | 0 | 0 | 4550 | -727 | 3823.3351 | -0.3351 | 0 | Project preparation was completed in May 2013 and project proposal approved by ExCom 69. | Preparation project completed. | 2011 |  | 2011 | N.a.
COM | UNIDO | Strategy for disposal and destruction of ODS for 4 LVC countries in the Europe and Central Asia region (Bosnia and Herzegovina, Croatia, Montenegro and Turkmenistan) | Individual | EUR | EUR | DES | 65 | PRP | 12 | A | I |  | 0 | 0 |  |  | 2011-11-01 | 2012-04-01 | 2012-11-30 |  | 2014-05-31 |  | 35000 | 0 | 35000 | 35002.4 | 100% | -2.4 | 0 |  | 2625 | 0 | 2625 | 0 | 0 | The project was operationally completed. |  |  |  | NON-INV
ONG | UNEP | Demonstration of a regional strategy for ODS waste management and disposal in the Europe and Central Asia region | Individual | EUR | EUR | DES | 69 | DEM | 13 | A | I |  | 0 |  | 0 |  | 2013-04-01 | 2013-09-01 | 2015-04-01 | 2017-12-01 |  |  | 75000 | 0 | 75000 | 32839.95 | 43.79% | 42160.05 | 0 | 4216.005 | 9750 | 0 | 4269.1935 | 5480.8065 | 0 | Brief progress report (actual/planned): As part of UNIDO's component, the destruction of the third (and final) batch of ODS waste from Croatia and Montenegro has been contracted to a company in Poland. In order to increase cost efficiency, UNIDO combined the destruction of ODS waste under this project with the destruction of ODS waste from Turkey. Once the ODS waste from Turkey will have been destroyed by the Polish company, UNIDO will be able to complete the financial transactions. UNEP and UNIDO have initiated the preparation of the final report and leaflet, in cooperation with the participating countries. The leaflet will demonstrate both advantages and disadvantages of the regional approach and lessons learned for other Article 5 LVC countries. Legal arrangements(actual/planned): Direct implementation by UNEP. Initial stages of project implementation(actual/planned): N.a. Intermediate goals achieved (actual/planned): N.a. Project completion and follow up: N.a. First disbursement date (actual/planned): September 2013 All funds disbursed (yes/no): No Any delay?(yes/no): Yes If Yes, reasons for delay & action plan to resolve: Delay in the process of obtaining necessary permits and insurance for the shipment and destruction of the third (and final) batch of waste ODS from Croatia and Montenegro to the destruction facility in Poland (UNIDO component). In order to increase cost efficiency, UNIDO combined the destruction of ODS waste under this project with the destruction of ODS waste from Turkey. Once the ODS waste from Turkey will have been destroyed by the Polish company, UNIDO will be able to complete the financial transactions. If Yes, will delay have impact on project completion date (yes/no): Yes Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N.a. | Brief progress report (actual/planned): In order to increase cost efficiency, UNIDO combined the destruction of ODS waste under this project with the destruction of ODS waste from Turkey. Once the ODS waste from Turkey will have been destroyed by the Polish company, UNIDO will be able to complete the financial transactions and thereport and leaflet will be finanlized in cooperation with the participating countries. The leaflet will demonstrate both advantages and disadvantages of the regional approach and lessons learned for other Article 5 LVC countries. Legal arrangements(actual/planned): Direct implementation by UNEP. Initial stages of project implementation(actual/planned): N.a. Intermediate goals achieved (actual/planned): N.a. Project completion and follow up: N.a. First disbursement date (actual/planned): September 2013 All funds disbursed (yes/no): No Any delay?(yes/no): Yes If Yes, reasons for delay & action plan to resolve: Delay in the process of obtaining necessary permits and insurance for the shipment and destruction of the third (and final) batch of waste ODS from Croatia and Montenegro to the destruction facility in Poland (UNIDO component). In order to increase cost efficiency, UNIDO combined the destruction of ODS waste under this project with the destruction of ODS waste from Turkey. Once the ODS waste from Turkey will have been destroyed by the Polish company, UNIDO will be able to complete the financial transactions. If Yes, will delay have impact on project completion date (yes/no): Yes Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N.a. |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor project completion.
ONG | UNIDO | Demonstration of a regional strategy for ODS waste management and disposal in the Europe and Central Asia region | Individual | EUR | EUR | DES | 69 | DEM | 14 | A | I |  | 0 | 0 |  |  | 2013-04-01 | 2014-02-01 | 2015-04-30 | 2017-07-17 |  |  | 274480 | 0 | 274480 | 186314.23 | 67.88% | 88165.77 | 34066.2 | 50000 | 19214 | 0 | 13042 | 6172 | 2384.634 | The required authorization for the export of the last batch to be destroyed took longer than expected. Once this export and consequently destruction has taken place, we will be in a position to declare the project completed. Was there any delay during the reporting year? Yes, due to the delay in obtaining the authorization for the export. Any impact on project completion date: Yes, as above. Any action required by Executive Committee? No | The authorization for last batch shipment for destruction were obtained as of March 2017 and shipment will take place in April 2017. It is expected that project will be completed in the current year. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
COM | UNIDO | Demonstration project on the replacement of CFC centrifugal chillers (Croatia, Macedonia, Romania, and Serbia and Montenegro) | Individual | EUR | EUR | REF | 47 | DEM | 06 | A | I |  | 0 | 0 |  |  | 2005-11-01 | 2006-07-01 | 2008-12-01 |  | 2015-12-01 |  | 1069074 | 0 | 1069074 | 1035507.3 | 96.86% | 33566.7 | 0 | 1 | 80181 | 0 | 77663 | 2518 | 0 | The project was operationally completed. |  |  |  | INV
COM | UNIDO | Preparation of a regional centre of excellence for demonstration and training of low-global warming potential ozone-safe alternative technologies in the Europe and Central Asia region (ECA) | Individual | EUR | EUR | REF | 74 | PRP | 15 | A | I |  | 0 | 0 |  |  | 2015-05-01 | 2015-12-01 | 2016-05-31 |  | 2016-12-01 |  | 50000 | 0 | 50000 | 49708.85 | 99.42% | 291.15 | 789.09 | 200 | 3500 | 0 | 0 | 3500 | 55.2363 | Brief report: Preparation for the project was completed. The development of the project has been approved at the 76th ExCom. Milestones achieved: Milestone 1: Local institution identified - Yes Milestone 2: Grant agreement signature - Yes Milestone 3: Legal arrangements – Yes Milestone 4: Initial stages of project implementation began - Yes Activities planned but not implemented: No Actions towards next goal: Development of the project Was any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any actions required by Executive Committee? No | Preparation for the project was completed. Financial closure is ongoing. |  |  | NON-INV
ONG | Russian Federation | Development of a regional centre of excellence for training and certification and demonstration of low-global warming potential alternative refrigerants |  | EUR | EUR | REF | 76 | DEM | 16 | A | I |  | 0 |  | 0 |  | 2016-05-01 |  | 2019-05-01 | 2019-05-01 |  |  | 591600 | 0 | 591600 | 0 | 0% | 591600 | 0 |  | 75076 | 0 | 0 | 75076 | 0 | No funding was transferred to UNIDO in order to start the implementation.
FIN | Germany | Promoting compliance with the Montreal Protocol in countries with economies in transition (Croatia and Romania) | Individual | EUR | EUR | SEV | 28 | TAS | 01 | A | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2001-08-01 |  | 2001-08-01 | 2003-10-01 | 67800 | -6900 | 60900 | 60900 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
FIN | Hungary | Regional network for 11 article 5 countries in Eastern Europe and Central Asia (jointly implemented with the Czech Republic, the Slovak Republic and UNEP) |  | EUR | EUR | SEV | 39 | TAS | 02 | A | I |  | 0 |  | 0 |  | 2003-04-01 |  | 2003-12-01 |  |  |  | 41145 | 0 | 41145 | 41145 | 100% | 0 |  |  | 5349 | 0 | 5349 | 0
FIN | Slovak Republic | Regional network for 11 article 5 countries in Eastern Europe and Central Asia (jointly implemented with the Czech Republic, Hungary and UNEP) |  | EUR | EUR | SEV | 39 | TAS | 03 | A | I |  | 0 |  | 0 |  | 2003-04-01 |  | 2003-12-01 |  |  |  | 14622 | 0 | 14622 | 14622 | 100% | 0 |  |  | 1901 | 0 | 1901 | 0
FIN | Czech Republic | Regional network for 10 article 5 countries in Eastern Europe and Central Asia (jointly implemented with Hungary, the Slovak Republic and UNEP) |  | EUR | EUR | SEV | 39 | TAS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-09-01 | 2003-12-01 |  | 2005-02-01 | 2006-02-01 | 58487 | 0 | 58487 | 58487 | 100% | 0 | 0 | 0 | 7603 | 0 | 7603 | 0 | 0 | Financially completed. | Financially completed. | 2003 |  | 2003 | N.a.
FIN | UNEP | Regional network for 11 article 5 countries in Eastern Europe and Central Asia (jointly implemented with the Czech Republic, Hungary and the Slovak Republic) | Individual | EUR | EUR | SEV | 39 | TAS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-09-01 | 2003-12-01 |  | 2005-02-01 | 2006-02-01 | 53666 | 0 | 53666 | 53666 | 100% | 0 | 0 |  | 6977 | 0 | 6977 | 0 | 0
FIN | Czech Republic | Initiating regional cooperation to enforce ODS trade controls in Europe and Central Asia network countries (first tranche) | Multi-Year | EUR | EUR | SEV | 57 | TAS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-09-01 | 2011-03-01 |  | 2012-10-01 | 2013-12-01 | 80500 | 0 | 80500 | 80500 | 100% | 0 | 0 | 0 | 10465 | 0 | 10465 | 0 | 0 | Financially completed. | Financially completed. | 2009 |  | 2009 | N.a.
FIN | UNEP | Initiating regional cooperation to enforce ODS trade controls in Europe and Central Asia network countries (first tranche) | Individual | EUR | EUR | SEV | 57 | TAS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-09-01 | 2011-03-01 |  | 2012-10-01 | 2013-12-01 | 51250 | 0 | 51250 | 51250 | 100% | 0 | 0 |  | 6663 | 0 | 6663 | 0 | 0
FIN | UNEP | Initiating regional cooperation to enforce ODS trade controls in Europe and Central Asia network countries (second tranche) | Individual | EUR | EUR | SEV | 60 | TAS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2012-04-01 | 2011-04-01 |  | 2012-10-01 | 2013-12-01 | 27500 | 0 | 27500 | 27500 | 100% | 0 | 0 |  | 3575 | 0 | 3575 | 0 | 0
FIN | Czech Republic | Initiating regional cooperation to enforce ODS trade controls in Europe and Central Asia network countries (second tranche) | Multi-Year | EUR | EUR | SEV | 60 | TAS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-09-01 | 2011-04-01 |  | 2012-10-01 |  | 80500 | -3824 | 76676 | 76676.1 | 100% | -0.1 | 0 | 0 | 10465 | -497 | 9967.9424 | 0.057605 | 0 | Completed in October 2012. | Completed in October 2012. | 2010 |  | 2010 | N.a.
FIN | UNEP | Technical assistance project to install alternatives, achieve compliance and phase-out methyl bromide | Individual | ASP | FIJ | FUM | 47 | TAS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-05-01 | 2008-12-01 |  | 2009-12-01 | 2010-12-01 | 65000 | 0 | 65000 | 65000 | 100% | 0 | 0 |  | 8450 | 0 | 8450 | 0 | 0
FIN | UNDP | Technical assistance project to install alternatives, achieve compliance and phase-out methyl bromide | Individual | ASP | FIJ | FUM | 47 | TAS | 17 | N | I | MeBr | 2.1 | 2.1 | 0 | 0 | 2005-11-01 | 2006-09-01 | 2008-12-01 |  | 2011-10-01 | 2012-06-01 | 50000 | -1096.64 | 48903.36 | 48903 | 100% | 0.36 | 0 | 0 | 4500 | -98.7 | 4401.27 | 0.03 | 0 | Financially completed in 2012. | The project was financially closed at the end of February 12. | 2005 |  | Non-Investment
FIN | UNEP | Development of a total ODS phase out plan | Individual | ASP | FIJ | PHA | 45 | PRP | 11 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-07-01 | 2006-04-01 |  | 2005-11-01 | 2006-03-01 | 15000 | -83 | 14917 | 14917 | 100% | 0 | 0 |  | 1950 | -11 | 1939 | 0 | 0
FIN | UNDP | Project preparation for complete ODS phase-out plan | Individual | ASP | FIJ | PHA | 45 | PRP | 12 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-02-01 | 2006-04-01 |  | 2006-07-01 | 2009-12-01 | 16870 | -6870 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1265 | -515.15 | 749.8518 | -0.0018 | 0 | Completed in 2006. Financially completed in 2009. |  | 2005 |  | Investment
FIN | UNDP | Implementation of the TPMP (investment component) | One-off-Phaseout | ASP | FIJ | PHA | 47 | TAS | 15 | N | I | CFC | 0.5 | 0.5 | 0 | 0 | 2005-11-01 | 2008-01-01 | 2009-12-01 |  | 2008-12-01 | 2012-07-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 3600 | 0 | 3600 | 0 | 0 | Financially completed in 2012. |  | 2005 | 2009-12-01 | Investment
FIN | UNEP | Implementation of the TPMP (non-investment component) | Individual | ASP | FIJ | PHA | 47 | TAS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-05-01 | 2009-12-01 |  | 2010-01-01 | 2011-01-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | ASP | FIJ | PHA | 55 | PRP | 19 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2011-12-01 | 2013-04-01 | 85000 | -1243.87 | 83756.13 | 83756 | 100% | 0.13 | 0 | 0 | 6375 | -93.29 | 6281.7 | 0.01005 | 0 | Financially completed in 2013. | Project Targeted for Completion in 2012. | 2008 |  | Investment
FIN | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | ASP | FIJ | PHA | 65 | INV | 23 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-10-01 | 2014-11-01 |  | 2014-12-01 | 2015-06-01 | 71800 | 0 | 71800 | 71800 | 100% | 0 | 0 | 0 | 6462 | 0 | 6462 | 0 | 0 | Financially Completed in 2015. | Project activities are progressing satisfactorily. Second tranche preparation including verification targeted for completion by Q3 of 2014. | 2011 |  | Investment
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | FIJ | PHA | 65 | TAS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-09-01 | 2014-11-01 |  | 2014-12-01 | 2016-12-01 | 47900 | 0 | 47900 | 47900 | 100% | 0 | 0 |  | 6227 | 0 | 6227 | 0 | 0 | Project financially completed. | Project financially completed.
FIN | UNDP | Verification report for stage I of HCFC phase-out management plan | Individual | ASP | FIJ | PHA | 71 | TAS | 25 | N | I | HCFC | 0 | 0 | 0 | 0 | 2013-12-01 | 2014-04-01 | 2016-11-01 |  | 2014-12-01 | 2016-02-01 | 30000 | -10501 | 19499 | 19499 | 100% | 0 | 0 | 0 | 2700 | -945.09 | 1754.91 | 0 | 0 | Financially completed in 2016. | Implementation plan has been finalised and verification to be completed by Q3-2014 | 2013 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | ASP | FIJ | PHA | 73 | INV | 27 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-11-01 | 2015-02-01 | 2016-11-01 | 2017-06-01 |  |  | 37900 | 0 | 37900 | 29374.97 | 77.51% | 8525.03 | 0 | 3410.012 | 3411 | 0 | 2643.7473 | 767.2527 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): All the work near to completion. 3rd Tramche approved in 77th ExCom Prodoc signed (actual/planned, yes/no and date):42136 Missions undertaken (actual/planned):1 TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: signed earlier First disbursement date (actual/planned): 42156Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | It is estimated that by June 2017 all the activities will be completed. | 2014 |  | Investment
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | ASP | FIJ | PHA | 73 | TAS | 28 | A | I |  | 0 |  | 0 |  | 2014-11-01 | 2016-09-01 | 2016-12-01 | 2017-12-01 |  |  | 24400 | 0 | 24400 | 0 | 0% | 24400 | 24400 | 2440 | 3172 | 0 | 0 | 3172 | 3172 | Brief progress report (actual/planned): The project has been well implemented with progress. The NOU organized a five-days RAC training workshop on good practices with 30 participants in June 2016 and 2 three-days workshop in April and August 2016 (with 36 participation). A number of public awareness activities were conducted including awareness workshops, awareness program broadcasting and distribution of awareness materials including consultative meeting for revision of ODS Act and the draft ODS and Refrigerant Management Decree, proposed R&R system and so forth. Moreover, inline ministries, statutory bodies and Associations has also been engaged in consultative forums on empty refrigerant cylinder disposal and equipment distribution/ syllables change; Legal arrangements (actual/planned): December 15. TOR completed: Not appplicable. First disbursement date: September 2016. All funds disbursed (yes/no): No. Any delay? (yes/no): No. If Yes, reasons for delay & action plan to resolve: Delay in signing of the SSFA. If Yes, will delay have impact on project completion date (yes/no): Yes, the completion date was postponed to December 2017 Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): The Government continues to organize the training for customs and enforcement offiers and RAC technicians in different location in the country. UNEP is working with the government to prepare the interim progress report, which will be use for the disbursement of the second payment under the signed SSFA.
ONG | UNDP | HCFC phase-out management plan (stage I, third tranche) | Multi-year | ASP | FIJ | PHA | 77 | INV | 31 | N | I | HCFC | 1.2 | 0 | 0 | 0 | 2016-12-01 |  | 2020-12-01 | 2017-12-01 |  |  | 59850 | 0 | 59850 | 0 | 0% | 59850 | 0 | 23940 | 5387 | 0 | 0 | 5387 | 0 | Newly Approved | DoA sent March 2017. Awaiting AWP from CO for ASL request. | 2016 |  | Investment
ONG | UNEP | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | ASP | FIJ | PHA | 77 | TAS | 32 | A | I |  | 0.8 |  | 0 |  | 2016-12-01 |  | 2020-12-01 | 2020-12-01 |  |  | 41650 | 0 | 41650 | 0 | 0% | 41650 | 0 | 4165 | 5415 | 0 | 0 | 5415 | 0 | Brief progress report (actual/planned): The project was approved at the 77th ExCom Meeting in December 2016. UNEP initiated the discussion with the NOU on the preparation of the SSFA. Legal arrangements (actual/planned): Not Yet. First Mission: Not yet. TOR completed: Not applicable First disbursement date: Not Yet. All funds disbursed (yes/no): No. Any delay? (yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): UNEP is working with the NOU in the preparation of SSFA.
FIN | UNEP | Assistance for formulation refrigeration management plan | RMP | ASP | FIJ | REF | 21 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1998-03-01 |  | 1999-11-01 | 2002-01-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 |  |  |  | 1999-05-01
FIN | UNDP | Implementation of the RMP: National programme for recovery and recycling of refrigerants | RMP-Component | ASP | FIJ | REF | 29 | TAS | 04 | A | I | CFC | 13.1 | 13.1 | 0 | 0 | 1999-11-01 | 2001-03-01 | 2002-12-01 |  | 2003-12-01 | 2007-02-01 | 96755 | -500 | 96255 | 96255 | 100% | 0 | 0 | 0 | 12578.15 | -65 | 12513.1508 | -0.0008 | 0 | Completed in 2003. Financially completed in 2007. |  | 1999 |  | Investment
FIN | UNEP | Implementation of the RMP: train the trainer programme for refrigeration service technicians | Individual | ASP | FIJ | REF | 29 | TRA | 06 | A | I | CFC | 9.5 | 9.5 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2001-06-01 |  | 2003-01-01 | 2004-10-01 | 70500 | -24500 | 46000 | 46000 | 100% | 0 | 0 |  | 9165 | -3185 | 5980 | 0 | 0 |  |  |  | 2002-12-01
FIN | UNEP | Implementation of the RMP: training of custom officers, ODS inspectorate and NOU staff | Individual | ASP | FIJ | REF | 29 | TRA | 07 | A | I | CFC | 5.8 | 5.8 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2001-06-01 |  | 2004-07-01 | 2008-12-01 | 42500 | -1811 | 40689 | 40689 | 100% | 0 | 0 |  | 5525 | -235 | 5290 | 0 | 0 |  |  |  | 2002-12-01
FIN | UNEP | Country programme preparation | Individual | ASP | FIJ | SEV | 04 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-07-01 | 1992-09-01 |  | 1993-06-01 | 1993-12-01 | 25000 | -2165 | 22835 | 22835 | 100% | 0 | 0 |  | 3250 | -281.45 | 2968.55 | 0 | 0
FIN | UNEP | Institutional strengthening for the phase-out of ODS controlled under the Montreal Protocol | Individual | ASP | FIJ | SEV | 12 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-07-01 | 1997-03-01 |  | 2000-07-01 | 2001-12-01 | 65890 | 0 | 65890 | 65890 | 100% | 0 | 0 |  | 8566 | 0 | 8566 | 0 | 0 |  |  |  | 1999-12-01
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | ASP | FIJ | SEV | 29 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-07-01 | 2001-12-01 |  | 2002-05-01 | 2007-03-01 | 43930 | 0 | 43930 | 43930 | 100% | 0 | 0 |  | 5711 | 0 | 5711 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (Phase III) | Individual | ASP | FIJ | SEV | 37 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-06-01 | 2004-08-01 |  | 2004-08-01 | 2008-12-01 | 57000 | 0 | 57000 | 57000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | ASP | FIJ | SEV | 44 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-03-01 | 2005-12-01 |  | 2005-12-01 | 2006-08-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase IV- year 2) | Individual | ASP | FIJ | SEV | 47 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-03-01 | 2006-12-01 |  | 2006-12-01 | 2007-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | ASP | FIJ | SEV | 50 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-06-01 | 2008-11-01 |  | 2008-11-01 | 2008-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VI) | Individual | ASP | FIJ | SEV | 56 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2008-12-01 | 2010-11-01 |  | 2010-11-01 | 2011-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VII) | Individual | ASP | FIJ | SEV | 61 | INS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-02-01 | 2012-11-01 |  | 2012-11-01 | 2013-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VIII: 12/2012-11/2014) | Individual | ASP | FIJ | SEV | 67 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2013-07-01 | 2014-11-01 |  | 2014-12-01 | 2016-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
ONG | UNEP | Extension of the institutional strengthening project (phase IX: 12/2014-11/2016) | Individual | ASP | FIJ | SEV | 72 | INS | 26 | A | I |  | 0 |  | 0 |  | 2014-05-01 | 2015-05-01 | 2016-11-01 | 2017-11-01 |  |  | 60000 | 0 | 60000 | 30000 | 50% | 30000 | 30000 | 3000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The NOU has been responsible for the management of all Montreal Protocol activities. The operation of the NOU was going on well. Stable, continued NOU and functioning as part of the institutional system of Government. The license/quota system has been enforced in 2016. Fiji successfully hosted the 2016 Joint Asia and the Pacific Network meeting, Thematic Workshop on ODS alternatives and Training of RAC technicians (Pacific region) in longer term alternatives. NOU also coordinated and facilitated the implementation of HPMP and ODS Alternative Survey. The NOU also organized the 2016 ozone day celebration, and actively joined the regional and global ozone related meetings e.g. the network meeting, OEWG and the MOP meetings. 2015 Article 7 and CP data were submitted to the Ozone Secretariat and MLFS respectively. Legal arrangements(actual/planned): The SSFA was signed April 2015. _Initial stages of project implementation(actual/planned): Dec 2014/Apr 2015_ Intermediate goals achieved (actual/planned): _Project progressing satisfactorily, compliance (2015) sustained. Project completion and follow up: Not applicable. First disbursement date (actual/planned):May 2015. _ All funds disbursed (yes/no): No. Any delay?(yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): Country continues to enforce the licensing and quota system as well as conducting iPIC mechanism. Only the fifth (final) payment is to be disbursed to the country upon completion of the IS project phase IX.
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | ASP | FIJ | SEV | 75 | TAS | 29 | A | I |  | 0 |  | 0 |  | 2015-11-01 |  | 2016-12-01 | 2017-06-01 |  |  | 35000 | 0 | 35000 | 0 | 0% | 35000 | 0 | 3500 | 4550 | 0 | 0 | 4550 | 0 | Brief progress report (actual/planned): SSFA for the ODS Alternatives Survey was submitted to the government for review and agreement, but no confirmation has been received from the government. However, the stakeholder meetings were organized and draft survey foramts and local resource persons were identified. The survey methodology and questionnaire have been finalized and agreed. NOO attended the training for conducting natiional surveys as part of Thematic workshop for Asia and the Pacific in June 2016. NOU had already started the data collection. Legal arrangements(actual/planned): Not yet. Initial stages of project implementation(actual/planned): April 2016 . Intermediate goals achieved (actual/planned): Not applicable. Project completion and follow up: Not applicable. First disbursement date (actual/planned): Not yet. All funds disbursed (yes/no): No. Any delay?(yes/no): Yes If Yes, reasons for delay & action plan to resolve: Delay in signing of SSFA due to the internal administration process. If Yes, will delay have impact on project completion date (yes/no): No. Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): UNEP regularly communicates with the NOO on the status of reviewing the SSFA. The government informed that, due to complicate internal administrative procedures, the signing of SSFA might take loger time. Pursuant to this, UNEP is discussing with the NOU to explore the option to do direct implementation to aviod further delay. UNEP's consultant visited Fiji in the last week of February (2017) to obtain preliminary data collected by the NOO and to determine next steps.
ONG | UNEP | Extension of the institutional strengthening project (phase X: 1/2017-12/2018) | Individual | ASP | FIJ | SEV | 77 | INS | 30 | A | I |  | 0 |  | 0 |  | 2016-12-01 |  | 2018-12-01 | 2018-12-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The project was approved at the 77th ExCom Meeting in December 2016. UNEP initiated the discussion with the NOU on the preparation of the SSFA. Legal arrangements(actual/planned): Not yet Initial stages of project implementation(actual/planned): Not yet Intermediate goals achieved (actual/planned): Not yet Project completion and follow up: Not applicable. First disbursement date (actual/planned): Not yet. All funds disbursed (yes/no): _No__ Any delay?(yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): _No_ If Yes, is any action required by ExCom: N/A | rief progress report (actual/planned): UNEP is working with the NOU to finalize the SSFA for IS project phase X.
FIN | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, first tranche, Micronesia) | Multi-Year | ASP | FSM | PHA | 63 | TAS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2012-09-01 | 2015-03-01 |  | 2015-04-01 | 2016-12-01 | 53875 | 0 | 53875 | 53875 | 100% | 0 | 0 |  | 7004 | 0 | 7004 | 0 | 0 | Project financially completed. | Project financially completed.
ONG | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, second tranche, Federated States of Micronesia) | Multi-year | ASP | FSM | PHA | 74 | TAS | 10 | A | I |  | 0.1 |  | 0 |  | 2015-05-01 | 2016-05-01 | 2020-05-01 | 2020-12-01 |  |  | 46925 | 0 | 46925 | 3227.17 | 6.877% | 43697.83 | 28772.83 | 4369.783 | 6100 | 0 | 419.5149 | 5680.4851 | 3740.3146 | Brief progress report (actual/planned): The SSFA was signed by UNEP and the Government of FSM in May 2016. The first payment under the second tranche was also made to the country in May 2016. The licensing and quota system was implemented in 2016. Amendment to ODS regulation to ban importation of HCFC-based equipment still awaited President’s signature. A RAC expert was recruited to deliver the update RAC training, which was expected in early 2017. UNEP worked closely with the NOU to engage multi-stakeholders in the implementation of HPMP, second tranche to synergize HPMP with other on-going environmental policies/projects e.g. PALS, Samoa Pathway. 2015 CP data was submitted to MLFS online. Legal arrangements (actual/planned): The SSFA was signed in May 2016 First Mission: Not yet. TOR completed: Not applicable First disbursement date: May 2016. All funds disbursed (yes/no): No. Any delay? (yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): The update RAC training workshop was organized in January 2017 to strengthen RAC technician capacity in the safe handling of flammable refrigerants, which has been available in the PIC region. UNEP mission is planned in 2017.
FIN | Australia | Implementation of the PIC Strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | FSM | REF | 36 | TAS | 01 | A | I |  | 0.3 | 0 | 0 | 0 | 2002-03-01 | 2003-06-01 | 2005-04-01 |  | 2010-09-01 | 2012-05-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | completed |  | 2002
FIN | Australia | Implementation of the PIC Strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | FSM | REF | 36 | TAS | 02 | A | I |  | 0.7 | 0 | 0 | 0 | 2002-03-01 | 2003-06-01 | 2005-04-01 |  | 2008-06-01 | 2012-05-01 | 26000 | 0 | 26000 | 26000 | 100% | 0 | 0 | 0 | 3380 | 0 | 3380 | 0 | 0 | completed |  | 2002
FIN | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | FSM | SEV | 36 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2004-01-01 | 2005-04-01 |  | 2006-06-01 | 2010-12-01 | 34000 | -2761.13 | 31238.87 | 31238.87 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase II) | Individual | ASP | FSM | SEV | 49 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2010-01-01 | 2007-03-01 |  | 2008-07-01 | 2010-12-01 | 11333 | 0 | 11333 | 11333 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (2nd year of phase II) | Individual | ASP | FSM | SEV | 58 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2009-12-01 | 2010-12-01 |  | 2011-12-01 | 2011-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase III) | Individual | ASP | FSM | SEV | 61 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2010-12-01 | 2012-12-01 |  | 2012-12-01 | 2013-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase IV: 1/2013-12/2014) | Individual | ASP | FSM | SEV | 67 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2013-07-01 | 2014-12-01 |  | 2014-12-01 | 2016-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
ONG | UNEP | Renewal of institutional strengthening project (phase V: 1/2015-12/2016) | Individual | ASP | FSM | SEV | 72 | INS | 09 | A | I |  | 0 |  | 0 |  | 2014-05-01 | 2015-04-01 | 2016-12-01 | 2017-06-01 |  |  | 60000 | 0 | 60000 | 29058 | 48.43% | 30942 | 30942 | 3094.2 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The NOU has been responsible for the management of all Montreal Protocol activities. Stable, high skilled continued NOU and functioning as part of the institutional system of Government. The operation of the NOU was going on well. The license/quota system has been enforced in 2016. NOU also coordinated and facilitated the implementation of HPMP and ODS Alternative Survey. The NOU also organized the 2016 ozone day celebration, and actively joined the regional and global ozone related meetings e.g. the network meeting, OEWG and the MOP meetings.NOU also actively engaged in the OEWG and MOP. 2015 Article 7 and CP data were submitted to the Ozone Secretariat and MLFS respectively. NOU has been the lead focal officer working with the Pacific Islands Forum Fisheries Agency and UNEP OzonAction on the assessment of the ODS used in the marine fishing sectors. Legal arrangements(actual/planned): The SSFA was signed in March 2015. Initial stages of project implementation(actual/planned): Jan/Mar 2015. Intermediate goals achieved (actual/planned): _Project progressing Satisfactorily, Compliance (2015) sustained. Project completion and follow up: Not applicable. First disbursement date (actual/planned): April 2015. All funds disbursed (yes/no): No. Any delay?(yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): Country continues to enforce the licensing and quota system. There are 2 remaining payments to be disbursed to the country. Projecct will be completed in June 2017.
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | ASP | FSM | SEV | 74 | TAS | 11 | A | I |  | 0 |  | 0 |  | 2015-05-01 |  | 2016-05-01 | 2017-06-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 0 | 4000 | 5200 | 0 | 0 | 5200 | 0 | Brief progress report (actual/planned): It took longer time than other countries to develop and agreed on the draft SSFA because there was need to develop the SSFA so as it is not to replicate the work already conducted under the EC project. As of December 2016, the SSFA was signed by UNEP and awaiting for counter-signature from the Government. NOO attended the training for conducting natiional surveys as part of Thematic workshop for Asia and the Pacific in June 2016. The survey methodology and questionnaire have been finalized and agreed. Initial work on the survey has been carried out. Legal arrangements(actual/planned): Not yet. Initial stages of project implementation(actual/planned): June 2016. Intermediate goals achieved (actual/planned): Not applicable. Project completion and follow up: Not applicable. First disbursement date (actual/planned): Not yet. All funds disbursed (yes/no): No. Any delay?(yes/no): Yes. If Yes, reasons for delay & action plan to resolve: Delay in drafting and signing of SSFA which is not duplicate with the EC project. If Yes, will delay have impact on project completion date (yes/no): No. Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): The SSFA was signed by UNEP and the Government of FSM. The first payment was requested, but has not yet been transferred to the country. UNEP regularly communicate with the NOO on the way forward to complete the data collection, data analysis and preparation of the report.
ONG | UNEP | Renewal of institutional strengthening project (phase VI: 1/2017-12/2018) | Individual | ASP | FSM | SEV | 77 | INS | 12 | A | I |  | 0 |  | 0 |  | 2016-12-01 |  | 2018-12-01 | 2018-12-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The project was approved at the 77th ExCom Meeting in December 2016. UNEP initiated the discussion with the NOU on the preparation of the SSFA. Legal arrangements(actual/planned): Not yet Initial stages of project implementation(actual/planned): Not yet Intermediate goals achieved (actual/planned): Not yet Project completion and follow up: Not applicable. First disbursement date (actual/planned): Not yet. All funds disbursed (yes/no): _No__ Any delay?(yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): _No_ If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): UNEP is working with the NOU to finalize the SSFA for IS project phase VI.
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | AFR | GAB | PHA | 48 | PRP | 17 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-02-01 | 2007-04-01 |  | 2007-07-01 | 2008-12-01 | 12000 | 0 | 12000 | 12000 | 100% | 0 | 0 | 0 | 900 | 0 | 900 | 0 | 0 | Completed in 2007. Financially completed in 2008. |  | 2006 |  | Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | GAB | PHA | 48 | PRP | 18 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-12-01 | 2007-04-01 |  | 2008-05-01 | 2009-05-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 |  | 2340 | 0 | 2340 | 0 | 0
FIN | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | GAB | PHA | 52 | INV | 21 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-02-01 | 2009-07-01 |  | 2009-09-01 | 2011-11-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 4500 | 0 | 4500 | 0 | 0 | Completed in 2009. Financially completed in 2011. |  | 2007 |  | Investment
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | GAB | PHA | 52 | TAS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-10-01 | 2008-07-01 |  | 2010-07-01 | 2012-07-01 | 65000 | -2493 | 62507 | 62507 | 100% | 0 | 0 |  | 8450 | -324.09 | 8125.91 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | GAB | PHA | 55 | PRP | 22 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-05-01 | 2009-07-01 |  | 2011-01-01 | 2012-01-01 | 85000 | -4947 | 80053 | 80053 | 100% | 0 | 0 |  | 11050 | -643.11 | 10406.89 | 0 | 0
FIN | UNDP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | GAB | PHA | 57 | INV | 25 | N | I | CFC | 1.5 | 1.5 | 0 | 0 | 2009-04-01 | 2009-05-01 | 2011-03-01 |  | 2009-12-01 | 2011-11-01 | 40000 | -6716.7 | 33283.3 | 33283 | 100% | 0.3 | 0 | 0 | 3600 | -604.5 | 2995.47 | 0.03 | 0 | Completed in 2009. Financially completed in 2011. |  | 2009 |  | Investment
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | GAB | PHA | 57 | TAS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-07-01 | 2010-03-01 |  | 2011-12-01 | 2012-12-01 | 50000 | -15000 | 35000 | 35000 | 100% | 0 | 0 |  | 6500 | -1950.24 | 4549.76 | 0 | 0
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | GAB | PHA | 62 | INV | 27 | A | I |  | 0 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2013-12-31 | 2018-04-01 |  |  | 130000 | 0 | 130000 | 88003.43 | 67.69% | 41996.57 | 0 | 10000 | 11700 | 0 | 7920 | 3780 | 0 | Distribution of equipment has been partially completed. It was agreed with the NOU to conduct a mission before the end of 2016 to assess further equipment and training needs. The mission was postponed due to unrest in the country. Was there any delay during the reporting year? Yes. The scheduled mission could not take place due to unrest in the country. Any recurring problem? No Any impact on project completion date: Yes Any action required by Executive Committee? No | NOU met at a network meeting reported that the political situation has improved and a mission can be arranged. |  |  | INV
COM | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | GAB | PHA | 62 | TAS | 26 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2013-01-01 | 2013-12-01 |  | 2015-12-01 |  | 90000 | 0 | 90000 | 53310 | 59.23% | 36690 | 36690 | 36690 | 11700 | 0 | 6930.3 | 4769.7 | 4769.7 | Project completed. | Project completed.
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | AFR | GAB | PHA | 73 | TAS | 30 | A | I |  | 0 |  | 0 |  | 2014-11-01 | 2016-08-01 | 2016-09-01 | 2017-12-01 |  |  | 46000 | 0 | 46000 | 36.1 | 0.07848% | 45963.9 | 9370 | 4596.39 | 5980 | 0 | 4.693 | 5975.307 | 1218.1 | Brief progress report (actual/planned): Country signed the SSFA in March 2016. First payment sent in August 2016.__NOU trained 50 refrigeration technicians on Good practices including recovery and recycling of HCFC have been organized in 2016. NOU trained 30 Customs officers on identification and control of ODS and ODS based equipment in 2016. Legal arrangements (actual/planned): SSFA signed in March 2016. Any delay (Yes/No): Yes_ First mission (actual/planned): N/A_ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): August 2016___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _No_ If Yes, reasons for delay & action plan to resolve: N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): Country signed the SSFA in March 2016. First payment sent in August 2016.__NOU trained 50 refrigeration technicians on Good practices including recovery and recycling of HCFC. NOU trained 30 RAC technicians in 2017. NOU trained 30 Customs officers on identification and control of ODS and ODS based equipment in 2016. NOU also trained 15 enforcement officers in 2017. Legal arrangements (actual/planned): SSFA signed in March 2016. Any delay (Yes/No): Yes_ First mission (actual/planned): N/A_ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): August 2016___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _No_ If Yes, reasons for delay & action plan to resolve: N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__
FIN | UNDP | Project preparation in refrigeration recycling | Individual | AFR | GAB | REF | 21 | PRP | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-11-01 | 2002-03-01 | 20000 | -5395 | 14605 | 14605 | 100% | 0 | 0 | 0 | 2600 | -701.35 | 1898.65 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Implementation of the RMP: National programme for recovery and recycling of refrigerants | RMP-Component | AFR | GAB | REF | 26 | TAS | 06 | A | I | CFC | 12.2 | 12.2 | 0 | 0 | 1998-11-01 | 2001-06-01 | 2000-12-01 |  | 2001-12-01 | 2003-04-01 | 232470 | -36306 | 196164 | 196164 | 100% | 0 | 0 | 0 | 30221.1 | -4719.78 | 25501.32 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Implementation of the RMP: Monitoring of the activities included in the RMP | RMP-Component | AFR | GAB | REF | 26 | TAS | 07 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-11-01 | 2002-01-01 | 2000-12-01 |  | 2003-07-01 | 2003-08-01 | 12100 | -1600 | 10500 | 10500 | 100% | 0 | 0 | 0 | 1573 | -208 | 1365 | 0 | 0 | Completed in 2003. Financially completed in 2003. |  | 1998 |  | Non-Investment
FIN | UNEP | Implementation of the RMP: train the trainers programme in the refrigeration sector | Individual | AFR | GAB | REF | 26 | TRA | 04 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-10-01 | 2000-05-01 |  | 2002-09-01 | 2003-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 |  | 5850 | 0 | 5850 | 0 | 0
FIN | UNEP | Implementation of the RMP: customs training | Individual | AFR | GAB | REF | 26 | TRA | 05 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 2000-12-01 | 2000-05-01 |  | 2003-12-01 | 2005-01-01 | 31000 | -10000 | 21000 | 21000 | 100% | 0 | 0 |  | 4030 | -1300 | 2730 | 0 | 0
FIN | UNDP | Preparation of the refrigerant management plan update | Individual | AFR | GAB | REF | 37 | PRP | 09 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-07-01 | 2002-08-01 | 2003-08-01 |  | 2004-12-01 | 2005-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Implementation of the RMP: supplementary training and spares to the national programme for recovery and recycling of refrigerants | RMP-Component | AFR | GAB | REF | 41 | TAS | 11 | N | I | CFC | 3.3 | 3.3 | 0 | 0 | 2003-12-01 | 2006-01-01 | 2006-12-01 |  | 2007-07-01 | 2011-12-01 | 60277 | 0 | 60277 | 60277 | 100% | 0 | 0 | 0 | 5424.93 | 0 | 5424.93 | 0 | 0 | Completed in 2007. Financially completed in 2011. |  | 2003 |  | Investment
FIN | UNDP | Implementation of the RMP: monitoring the activities in the RMP | RMP-Component | AFR | GAB | REF | 41 | TAS | 14 | N | I | CFC | 0.8 | 0.8 | 0 | 0 | 2003-12-01 | 2007-01-01 | 2006-12-01 |  | 2007-12-01 | 2011-11-01 | 15000 | -772.32 | 14227.68 | 14228 | 100% | -0.32 | 0 | 0 | 1350 | -69.51 | 1280.52 | -0.03 | 0 | Completed in 2007. |  | 2003 |  | Non-Investment
FIN | UNEP | Implementation of the RMP: customs training programme ( phase II) | Individual | AFR | GAB | REF | 41 | TRA | 12 | A | I | CFC | 2.7 | 2.7 | 0 | 0 | 2003-12-01 | 2005-10-01 | 2004-12-01 |  | 2006-12-01 | 2008-12-01 | 50000 | -1985 | 48015 | 48015 | 100% | 0 | 0 |  | 6500 | -258.05 | 6241.95 | 0 | 0
FIN | UNEP | Implementation of the RMP: training of refrigeration technicians (phase II) | Individual | AFR | GAB | REF | 41 | TRA | 13 | A | I | CFC | 1.9 | 1.9 | 0 | 0 | 2003-12-01 | 2004-10-01 | 2005-07-01 |  | 2006-12-01 | 2007-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 |  | 4550 | 0 | 4550 | 0 | 0
FIN | UNEP | Country programme preparation | Individual | AFR | GAB | SEV | 15 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1996-02-01 | 1995-12-01 |  | 1997-05-01 | 1997-06-01 | 10000 | 33000 | 43000 | 43000 | 100% | 0 | 0 |  | 1300 | 4290 | 5590 | 0 | 0
FIN | UNEP | Creation of a National Ozone Technical Group | Individual | AFR | GAB | SEV | 22 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-02-01 | 2000-05-01 |  | 2000-12-01 | 2001-12-01 | 45600 | 0 | 45600 | 45600 | 100% | 0 | 0 |  | 5928 | 0 | 5928 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening | Individual | AFR | GAB | SEV | 32 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-03-01 | 2003-01-01 |  | 2002-12-01 | 2003-12-01 | 30400 | 0 | 30400 | 30400 | 100% | 0 | 0 |  | 3952 | 0 | 3952 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (Phase III) | Individual | AFR | GAB | SEV | 37 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-01-01 | 2004-08-01 |  | 2004-12-01 | 2005-02-01 | 39520 | 0 | 39520 | 39520 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | AFR | GAB | SEV | 44 | INS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2006-12-01 |  | 2006-12-01 | 2009-06-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | AFR | GAB | SEV | 50 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2008-11-01 |  | 2008-12-01 | 2009-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VI) | Individual | AFR | GAB | SEV | 56 | INS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2008-12-01 | 2010-12-01 |  | 2011-04-01 | 2012-04-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of the institutional strengthening project (phase VII) | Individual | AFR | GAB | SEV | 62 | INS | 28 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-03-01 | 2012-12-01 |  | 2013-12-01 |  | 60000 | 0 | 60000 | 22618.76 | 37.7% | 37381.24 | 27000 | 37381 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): SSFA signed in December 2011. Expired on December 2013 with a balance. Amended for extension until March 2017. Country signed the amended SSFA in January 2017. Art5 data report for 2015 and CP data for 2015 have been provided. 2016 Ozone day was celebrated. Legal arrangements (actual/planned): First agreement signed in December 2011. All activities under the SSFA are completed (as planned) NO___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in March 2012 __ All funds disbursed (yes/no): _NO_ Final payment -_ Any delay? (yes/no): Yes, amended SSFA expired with a balance of US $ 15,000 ___ If Yes, reasons for delay & action plan to resolve: NOU had 3 ongoing IS projects ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: Remaining balance to be returned to ExCom | Brief progress report (actual/planned): SSFA signed in December 2011. Expired on December 2013 with a balance. Amended for extension until March 2017. Country signed the amended SSFA in January 2017. Art5 data report for 2015 and CP data for 2015 have been provided. 2016 Ozone day was celebrated. Legal arrangements (actual/planned): First agreement signed in December 2011. All activities under the SSFA are completed (as planned) NO___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in March 2012 __ All funds disbursed (yes/no): _NO_ Final payment -_ Any delay? (yes/no): Yes, amended SSFA expired with a balance of US $ 15,000 ___ If Yes, reasons for delay & action plan to resolve: NOU had 3 ongoing IS projects ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: Remaining balance to be returned to ExCom
FIN | UNEP | Extension of the institutional strengthening project (phase VIII: 1/2014-12/2015) | Individual | AFR | GAB | SEV | 71 | INS | 29 | A | I |  | 0 |  | 0 |  | 2013-12-01 |  | 2015-12-01 |  | 2015-12-01 | 2016-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. Balances to be returned as the project was heavily delayed because of changes in the Government. IS new phase (IX) now is under implementation, SSFA signed and activities are progressing. | Project financially completed. Balances to be returned as the project was heavily delayed because of changes in the Government. IS new phase (IX) now is under implementation, SSFA signed and activities are progressing.
ONG | UNEP | Extension of the institutional strengthening project (phase IX: 1/2016-12/2017) | Individual | AFR | GAB | SEV | 75 | INS | 31 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-04-01 | 2017-12-01 | 2017-12-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 85000 | 8500 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): SSFA signed in March 2016._Legal arrangements (actual/planned): signed in March 2016. . Art5 data report for 2015 and CP data for 2015 have been provided. 2016 Ozone day was celebrated. NOU trained 50 refrigeration technicians on Good practices including recovery and recycling of HCFC. NOU trained 30 RAC technicians in 2017. NOU trained 30 Customs officers on identification and control of ODS and ODS based equipment in 2016. NOU also trained 15 enforcement officers in 2017. _ First mission (actual/planned): __ _ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): April 2016__ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _NO_ If Yes, reasons for delay & action plan to resolve: NO__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): SSFA signed in March 2016._Legal arrangements (actual/planned): signed in March 2016. . Art5 data report for 2015 and CP data for 2015 have been provided. 2016 Ozone day was celebrated. NOU trained 50 refrigeration technicians on Good practices including recovery and recycling of HCFC. NOU trained 30 RAC technicians in 2017. NOU trained 30 Customs officers on identification and control of ODS and ODS based equipment in 2016. NOU also trained 15 enforcement officers in 2017. _ First mission (actual/planned): __ _ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): April 2016__ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _NO_ If Yes, reasons for delay & action plan to resolve: NO__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | AFR | GAB | SEV | 75 | TAS | 32 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-05-01 | 2016-12-01 | 2017-10-01 |  |  | 110000 | 0 | 110000 | 110000 | 100% | 0 | 0 | 0 | 14300 | 0 | 14300 | 0 | 0 | Brief progress report (actual/planned): Country received first payment in May 2016. National consultants hired in July 2016. Country to submit the drafr report in January 2017. Agreement signed in April 2016. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in May 16 __ All funds disbursed (yes/no): NO_ Final payment being _NO Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Brief progress report (actual/planned): Country received first payment in May 2016. National consultants hired in July 2016. Country submitted the draft report in January 2017. Agreement signed in April 2016. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in May 16 __ All funds disbursed (yes/no): NO_ Final payment being _NO Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
FIN | UNDP | Project preparation in the foam sector | Individual | AFR | GAM | FOA | 21 | PRP | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1997-05-01 | 2002-03-01 | 20000 | -6548 | 13452 | 13452 | 100% | 0 | 0 | 0 | 2600 | -851.24 | 1748.76 | 0 | 0 | Completed in 1997. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Phase out of CFC in the manufacture of flexible foam (slabstock) at Karan Foam Manufacturing Ltd. | Individual | AFR | GAM | FOA | 22 | INV | 06 | A | I | CFC | 11 | 11 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1999-12-01 | 2000-12-01 | 63500 | -2619 | 60881 | 60881 | 100% | 0 | 0 | 0 | 8255 | -340.47 | 7914.53 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | GAM | PHA | 49 | PRP | 15 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2006-12-01 | 2007-07-01 |  | 2007-08-01 | 2008-12-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 |  | 2340 | 0 | 2340 | 0 | 0
FIN | UNDP | Project preparation for a terminal phase-out management plan | Individual | AFR | GAM | PHA | 49 | PRP | 16 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-04-01 | 2007-07-01 |  | 2007-12-01 | 2009-12-01 | 12000 | -240 | 11760 | 11760 | 100% | 0 | 0 | 0 | 900 | -18 | 882 | 0 | 0 | Completed in 2007. Financially completed in 2009. |  | 2006 |  | Investment
FIN | UNDP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | GAM | PHA | 53 | INV | 18 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-08-01 | 2009-11-01 |  | 2008-12-01 | 2013-11-01 | 99500 | 0 | 99500 | 99500 | 100% | 0 | 0 | 0 | 8955 | 0 | 8955 | 0 | 0 | Financially completed in 2013. |  | 2007 |  | Investment
FIN | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-year | AFR | GAM | PHA | 53 | TAS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-03-01 |  | 2009-03-01 | 2010-12-01 | 93000 | 0 | 93000 | 93000 | 100% | 0 | 0 |  | 12090 | 0 | 12090 | 0 | 0
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | AFR | GAM | PHA | 55 | PRP | 20 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2010-12-01 | 2013-11-01 | 85000 | -8939.46 | 76060.54 | 76061 | 100% | -0.46 | 0 | 0 | 6375 | -670.46 | 5704.575 | -0.035 | 0 | Financially completed in 2013. |  | 2008 |  | Investment
FIN | UNDP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | GAM | PHA | 57 | INV | 22 | N | I | CFC | 3.6 | 3.6 | 0 | 0 | 2009-04-01 | 2009-05-01 | 2011-03-01 |  | 2010-12-01 | 2013-11-01 | 30500 | -3000.54 | 27499.46 | 27499 | 100% | 0.46 | 0 | 0 | 2745 | -270.05 | 2474.91 | 0.04 | 0 | Financially completed in 2013. |  | 2009 |  | Investment
FIN | UNEP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | GAM | PHA | 57 | TAS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-08-01 | 2010-03-01 |  | 2011-03-01 | 2011-12-01 | 72000 | 0 | 72000 | 72000 | 100% | 0 | 0 |  | 9360 | 0 | 9360 | 0 | 0
COM | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | GAM | PHA | 65 | INV | 24 | A | I | HCFC | 0.1 | 0.1 |  |  | 2011-11-01 | 2012-07-01 | 2016-11-30 |  | 2016-02-01 |  | 50000 | 0 | 50000 | 49496.51 | 98.99% | 503.49 | 0 | 1 | 4500 | 0 | 4455 | 45 | 0 | Project completed in Feb 2016. | Project completed. Financial closure is being processed. Remaining funds will be returned to the 79th ExCom. |  |  | INV
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | GAM | PHA | 65 | TAS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-08-01 | 2013-11-01 |  | 2014-12-01 | 2016-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 | Project financially completed | Project financially completed
ONG | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Individual | AFR | GAM | PHA | 71 | TAS | 27 | A | I |  | 0 |  | 0 |  | 2013-12-01 | 2016-04-01 | 2016-11-01 | 2017-03-01 |  |  | 30000 | 0 | 30000 | 21094.84 | 70.32% | 8905.16 | 0 | 890.516 | 3900 | 0 | 2742.3292 | 1157.6708 | 0 | Brief progress report (actual/planned): The Terms of Reference (ToR) for hiring the international consultant was prepared, cleared by the management and advertised in Feb 2016. The international consultant was recruited by UNEP to verify the national consumption in relation to the targets as set out in the Agreement between ExCom and Government of Ethiopia, following the relevant decisions of the ExCom and guidelines for the verification of national consumption targets for the multi-year agreements. The consultant prepared and presented the draft work plan which included timeline for conducting the verification as well as tasks and roles and responsibilities of each concerned stakeholders in the verification process. The consultant also informed the NOU about support/cooperation that was required from various stakeholders. The consultant also reviewed official statistics on import and export maintained by different sources and analyzed and compare those statistics. In addition, the consultant conducted the necessary on-site visits and interviews, and analyzed and cross-check various data collected from different sources. The reports was produced in English and provides detailed data demonstrating and confirming whether the consumption targets in the Agreement were achieved, whether there is existence of an operational licensing and quota system for HCFC imports and exports and whether the system is capable to ensure the country's compliance with the targets as set out in the Agreement between Gambia and the ExCom.The verification report was finalised and submitted to Ex-com 77 | Brief progress report (actual/planned): The project was completed. NOU is implementing the recommendations from the verification report
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | AFR | GAM | PHA | 71 | TAS | 28 | A | I |  | 0.1 |  | 0 |  | 2013-12-01 | 2016-04-01 | 2016-12-01 | 2017-12-01 |  |  | 23000 | 0 | 23000 | 0.16 | 0.0006957% | 22999.84 | 23000 | 2299.984 | 2990 | 0 | 0.0208 | 2989.9792 | 2990 | Brief progress report (actual/planned): _ The NOU registered all importers of HCFC for 2016, advertised for quota allocation for 2016 HCFC importation and conducted inspection visits to various boarders to check how customs officers are enforcing the control measures of HCFC importation. Two stakeholders workshops were organized by the NOU in March and September 2016, with the main goal to sensitize major stakeholders about HCFC phase out schedule, data survey and the Government’s strategy for phasing out of HCFCs. The NOU developed a database of certified technicians for updating the general public on competent RAC technicians. The NOU conducted two inspection visits on importers to assess compliance with allocated quotas. The NOU trained 30 custom officers and 40 RAC technicians._ Legal arrangements(actual/planned): The SSFA was drafted and signed by UNEP and the Government of Gambia in December 2015___ First mission (actual/planned): _Yes__ TOR completed(actual/planned): _Yes__ First disbursement date (actual/planned): April 2016___ All funds disbursed (yes/no): No___ Any delay? (yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): No___ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): The NOU continues to monitor imports and trade of ODS and ODS related equipment.
ONG | UNIDO | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | AFR | GAM | PHA | 77 | INV | 33 | A | I | HCFC | 0.2 | 0 |  |  | 2016-11-01 |  | 2020-12-31 | 2020-12-31 |  |  | 50000 | 0 | 50000 | 0 | 0% | 50000 | 0 | 5000 | 4500 | 0 | 0 | 4500 | 0 | Approved on the understanding that if the Gambia were to decide to proceed with retrofits and associated servicing to flammable and toxic refrigerants in refrigeration and air-conditioning equipment originally designed for non-flammable substances, it would do so assuming all associated responsibilities and risks and only in accordance with the relevant standards and protocols. Was there any delay during the reporting year?: Yes If yes, reasons and action plan: (narrative): New ozone officers to be communicated. Any recurring problem? No Any action required by Executive Committee? No | Approved on the understanding that if the Gambia were to decide to proceed with retrofits and associated servicing to flammable and toxic refrigerants in refrigeration and air-conditioning equipment originally designed for non-flammable substances, it would do so assuming all associated responsibilities and risks and only in accordance with the relevant standards and protocols. Was there any delay during the reporting year?: Yes If yes, reasons and action plan: (narrative): New ozone officers to be communicated. Any recurring problem? No Any action required by Executive Committee? No
ONG | UNEP | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | AFR | GAM | PHA | 77 | TAS | 32 | A | I |  | 0 |  | 0 |  | 2016-12-01 |  | 2018-12-01 | 2018-12-01 |  |  | 20000 | 0 | 20000 | 0 | 0% | 20000 | 0 | 2000 | 2600 | 0 | 0 | 2600 | 0 | Newly approved project. | Brief progress report (actual/planned): The project was approved in Dec 2016. The licensing and quota system are in place and operational. The NOU continues to monitor imports and trade of ODS and ODS related equipment. Collection of the 2016 data on ODS imports and consumption has been completed and is being analyzed for submission. NOU commenced preparation of national legislative requirement processes in planning for ratification of Kigali amendment. ___ Legal arrangements (actual/planned): The SSFA was drafted and sent to the Government of Ethiopia for signature. ___Initial stages of project implementation (actual/planned): __Yes_ Intermediate goals achieved (actual/planned): _No__ Project completion and follow up: _Yes__ First disbursement date (actual/planned): __No ____. All funds disbursed (yes/no): No__ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: __N/A_
FIN | UNIDO | Refrigeration recovery and recycling scheme | RMP | AFR | GAM | REF | 22 | TAS | 05 | A | I | CFC | 7.7 | 7.7 |  |  | 1997-05-01 | 1997-09-01 | 1999-06-01 |  | 1998-12-01 | 2000-12-01 | 68000 | -243 | 67757 | 67757 | 100% | 0 | 0 |  | 8840 | -45 | 8795 | 0 | 0 | FIN
FIN | UNEP | Assistance for formulation of a refrigerant management plan | RMP | AFR | GAM | REF | 23 | PRP | 07 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-08-01 | 1998-11-01 |  | 1999-10-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Implementation of the RMP: policy development and related information dissemination | Individual | AFR | GAM | REF | 29 | TAS | 08 | A | I | CFC | 3.2 | 3.2 | 0 | 0 | 1999-11-01 | 2000-06-01 | 2000-12-01 |  | 2002-10-01 | 2003-10-01 | 22000 | 0 | 22000 | 22000 | 100% | 0 | 0 |  | 2860 | 0 | 2860 | 0 | 0
FIN | UNEP | Implementation of the RMP: training programme for technicians in good refrigeration practices | Individual | AFR | GAM | REF | 29 | TRA | 09 | A | I | CFC | 5.8 | 5.8 | 0 | 0 | 1999-11-01 | 2000-06-01 | 2001-06-01 |  | 2002-10-01 | 2003-10-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0
FIN | Germany | Project preparation for additional activities for Gambia RMP | RMP | AFR | GAM | REF | 32 | PRP | 11 | A | I |  | 0 |  | 0 |  | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2004-03-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Project completed and resultant RMP update is being implemented.
FIN | Germany | Implementation of the RMP update: phasing out ODS use in the refrigeration and air conditioning sector | Individual | AFR | GAM | REF | 37 | TAS | 12 | A | I |  | 11.2 | 11.2 | 0 |  | 2002-07-01 | 2003-03-01 | 2005-01-01 |  | 2007-09-01 | 2009-01-01 | 76700 | -30 | 76670 | 76670 | 100% | 0 | 0 | 0 | 9971 | -4 | 9967 | 0 | 0 | Project completed and PCR submitted.
FIN | UNEP | Country programme preparation | Individual | AFR | GAM | SEV | 06 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-03-01 | 1994-06-01 |  | 1995-10-01 | 1995-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Institutional strengthening | Individual | AFR | GAM | SEV | 19 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1997-05-01 | 1999-05-01 |  | 2000-09-01 | 2000-09-01 | 42200 | 0 | 42200 | 42200 | 100% | 0 | 0 |  | 5486 | 0 | 5486 | 0 | 0
FIN | UNEP | Training of customs officers | Individual | AFR | GAM | SEV | 19 | TRA | 03 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1999-12-01 | 1996-12-01 |  | 2002-10-01 | 2003-10-01 | 9500 | 0 | 9500 | 9500 | 100% | 0 | 0 |  | 1235 | 0 | 1235 | 0 | 0 |  |  |  | 1997-12-01
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | AFR | GAM | SEV | 30 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-09-01 | 2002-04-01 |  | 2003-12-01 | 2003-12-01 | 28000 | 0 | 28000 | 28000 | 100% | 0 | 0 |  | 3640 | 0 | 3640 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project: phase 3 | Individual | AFR | GAM | SEV | 41 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-04-01 | 2005-12-01 |  | 2006-03-01 | 2007-03-01 | 36573 | 0 | 36573 | 36573 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | GAM | SEV | 48 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2006-12-01 | 2008-04-01 |  | 2008-04-01 | 2009-04-01 | 60000 | -29 | 59971 | 59971 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | AFR | GAM | SEV | 54 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-08-01 | 2010-03-01 |  | 2010-08-01 | 2011-08-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VI) | Individual | AFR | GAM | SEV | 61 | INS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2010-10-01 | 2012-06-01 |  | 2012-10-01 | 2013-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VII: 8/2012-7/2014) | Individual | AFR | GAM | SEV | 67 | INS | 26 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2013-01-01 | 2014-06-01 |  | 2014-12-01 | 2016-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed | Project financially completed
ONG | UNEP | Extension of the institutional strengthening project (phase VIII: 7/2014-6/2016) | Individual | AFR | GAM | SEV | 72 | INS | 29 | A | I |  | 0 |  | 0 |  | 2014-05-01 | 2015-12-01 | 2016-06-01 | 2017-09-01 |  |  | 60000 | 0 | 60000 | 15000 | 25% | 45000 | 45000 | 4500 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): _ The licensing and quota system are in place and functioning. The NOU registered all importers of HCFCs and coordinated the allocation of HCFC licenses and quota. The NOU conducted two inspection visits to monitor distribution of HCFCs to check compliance with the quotas allocated. The NOU conducted training for 30 Custom Officers and 60 refrigeration technicians on control of HCFCs and other ODS. The NOU celebrated 2016 international ozone day, and implemented several awareness activities. The NOU collected, processed and submitted 2015 Country Programme and Article 7 Data reports. The NOU participated in all Montreal Protocol meetings organized in 2016._. __ Legal arrangements (actual/planned): __ The SSFA was drafted and signed by UNEP and the Government of Gambia in September 2015__Initial stages of project implementation(actual/planned): Yes___ Intermediate goals achieved (actual/planned): Yes___ Project completion and follow up: _No__ First disbursement date (actual/planned): _October 2015__ All funds disbursed (yes/no): No ___ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: N/A___ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): The NOU continues to monitor imports and trade of ODS and ODS related equipment. Collection of the 2016 data on ODS imports and consumption has been completed and is being analyzed for submission. NOU commenced preparation of national legislative requirement processes in planning for ratification of Kigali amendment.
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | AFR | GAM | SEV | 74 | TAS | 30 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-04-01 | 2016-05-01 | 2017-05-01 |  |  | 40000 | 0 | 40000 | 27.58 | 0.06895% | 39972.42 | 35000 | 3997.242 | 5200 | 0 | 3.5854 | 5196.4146 | 4550 | Brief progress report (actual/planned): The first stakeholders meeting was organized by the NOU in May 2016 in Banjul with the main goal to agree on the plan for the Survey of ODS alternatives at the national level and obtain support of main national stakeholders. The meeting was attended by 40 participants. One National Consultant as hired by the NOU to support the data collection. The National Consultant assisted the NOU in the identification of the current use of ODS alternatives by substance/sector and collection of import/export data for the substances for the past a couple of years. The National Consultant also provided support in establishing growth patterns in use by substance/sector and in compiling data on available ODS alternatives for various applications.The NOU and the National Consultant drafted and cross checked the information to ensure the completion of end-user surveys, collection, analysis, and aggregation of consumption data. The various sections of the report were drafted. The second stakeholders meeting was organized by the NOU in September 2016 in Banjul with the main goal to organise consultations with representatives of the government and private sector to finalize the outcomes of the Survey of ODS alternatives and discuss potential opportunities for introduction of those alternatives in the country. The draft report was prepared by the NOU and the National Consultant. It was reviewed and finalized based on the format approved by ExCom decision 75/67 as contained in document UNEP/OzL.Pro/ExCom/75/77/Rev.1 after incorporating inputs/ comments raised during National Stakeholders’ workshop. The final report has been submitted to UNEP for final review and submission to MLFS. . The NOU participated in the ODS Alternative Thematic workshop held in December 2016 to refine the draft report according to the revised template for the report. Legal arrangements(actual/planned): The SSFA was drafted and signed by UNEP and the Government of Gambia in Jan 2016___Initial stages of project implementation(actual/planned): _Yes__ Intermediate goals achieved (actual/planned): Yes___ Project completion and follow up: _No__ First disbursement date (actual/planned): _March 2016__ All funds disbursed (yes/no): No___ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): __N/A_ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): The NOU incorporated comments from UNEP ROA and Paris and re-submitted final ODS survey repor.
ONG | UNEP | Extension of the institutional strengthening project (phase IX: 12/2016-11/2018) | Individual | AFR | GAM | SEV | 77 | INS | 31 | A | I |  | 0 |  | 0 |  | 2016-12-01 |  | 2018-11-01 | 2018-11-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | Newly approved project. | Brief progress report (actual/planned): The project was approved in Dec 2016. The licensing and quota system are in place and operational. The NOU continues to monitor imports and trade of ODS and ODS related equipment. Collection of the 2016 data on ODS imports and consumption has been completed and is being analyzed for submission. NOU commenced preparation of national legislative requirement processes in planning for ratification of Kigali amendment. ___ Legal arrangements (actual/planned): The SSFA was drafted and sent to the Government of Gambia for signature. ___Initial stages of project implementation (actual/planned): __Yes_ Intermediate goals achieved (actual/planned): _No__ Project completion and follow up: _Yes__ First disbursement date (actual/planned): __No ____. All funds disbursed (yes/no): No__ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: __N/A_
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | GBS | PHA | 50 | PRP | 10 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-07-01 | 2007-11-01 |  | 2008-12-01 | 2009-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | GBS | PHA | 56 | TAS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-08-01 | 2010-03-01 |  | 2011-12-01 | 2013-12-01 | 62500 | -18 | 62482 | 62482 | 100% | 0 | 0 |  | 8125 | -2.34 | 8122.66 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | GBS | PHA | 57 | PRP | 12 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-07-01 | 2010-03-01 |  | 2013-12-01 | 2014-12-01 | 85000 | -18021 | 66979 | 66979 | 100% | 0 | 0 |  | 11050 | -2342.73 | 8707.27 | 0 | 0
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | GBS | PHA | 60 | TAS | 13 | A | I | CFC-12 | 3.9 | 0 | 0 | 0 | 2010-04-01 | 2010-07-01 | 2011-04-01 |  | 2011-12-01 | 2011-12-01 | 37500 | 0 | 37500 | 37500 | 100% | 0 | 0 |  | 4875 | 0 | 4875 | 0 | 0
COM | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | GBS | PHA | 65 | INV | 15 | A | I | HCFC | 0.1 | 0.1 |  |  | 2011-11-01 | 2013-05-01 | 2016-11-30 |  | 2015-12-01 |  | 40000 | 0 | 40000 | 39138.2 | 97.85% | 861.8 | 0 | 1 | 3600 | 0 | 3522 | 78 | 0 | The project was operationally completed. |  |  |  | INV
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | GBS | PHA | 65 | TAS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-08-01 | 2013-11-01 | 2017-12-01 |  |  | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 |  | 4550 | 0 | 4550 | 0 | 0 | Project returns to ONG as an amendment to an SSFA has been signed on Jan 2016 as requested by country. | Project returns to ONG as an amendment to an SSFA has been signed on Jan 2016 as requested by country.
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | AFR | GBS | PHA | 71 | TAS | 17 | A | I |  | 0 |  | 0 |  | 2013-12-01 | 2014-05-01 | 2016-12-01 | 2017-12-01 |  |  | 52000 | 0 | 52000 | 14134.22 | 27.18% | 37865.78 | 7270.03 | 3786.578 | 6760 | 0 | 1837.4486 | 4922.5514 | 945.1039 | Brief progress report (actual/planned): NOU supervised a training of 30 technicians each on recovery, recycling and HCFCs alternative in 2016 and a training workshop for 30 customs officers on ODS control in 2016. Legal arrangements (actual/planned): Agreement signed in May 2014. All activities under the SSFA are completed (as planned) YES___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in May 2014 __ All funds disbursed (yes/no): _ .__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Brief progress report (actual/planned): Legal arrangements (actual/planned): Agreement signed in May 2014. All activities under the SSFA are completed (as planned)_No. _NOU supervised a training of 30 technicians each on recovery, recycling and HCFCs alternative in 2016 and a training workshop for 30 customs officers on ODS control in 201___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in May 2014 __ All funds disbursed (yes/no): _ No__ Any delay? (yes/no): Yes_ If Yes, reasons for delay & action plan to resolve: SSFA expired on 2 April 2017 with a balance of US $ 22,000._ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: Balance to be returned as the 3rd Tranche of HPMP was approved
ONG | UNIDO | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | AFR | GBS | PHA | 77 | INV | 21 | A | I | HCFC | 0.3 | 0 |  |  | 2016-11-01 |  | 2019-12-01 | 2019-12-01 |  |  | 75000 | 0 | 75000 | 0 | 0% | 75000 | 0 | 15000 | 6750 | 0 | 0 | 6750 | 0 | Approved on the understanding that if Guinea-Bissau were to decide to proceed with retrofits and associated servicing to flammable and toxic refrigerants in refrigeration and air-conditioning equipment originally designed for non-flammable substances, it would do so assuming all associated responsibilities and risks and only in accordance with the relevant standards and protocols. | From the previous tranche the training for technicians in the proper use of the provided tools was pending. The training took place in the January 2017 in the premises of the supplier TST Stag in Spain and 4 technicians were trained. Action towards next goals: It is planned to visit the country to verify the requirements in May 2017. - No delay in implementation - No recurring problem - No impact on project completion date - No action required by Executive Committee
ONG | UNEP | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | AFR | GBS | PHA | 77 | TAS | 20 | A | I |  | 0.6 |  | 0 |  | 2016-12-01 |  | 2020-12-01 | 2020-12-01 |  |  | 50000 | 0 | 50000 | 0 | 0% | 50000 | 0 | 5000 | 6500 | 0 | 0 | 6500 | 0 | Newly approved project | Brief progress report (actual/planned): Project newly approved. Agreement not signed yet. Legal arrangements (actual/planned): Agreement not signed yet. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement _no __ All funds disbursed (yes/no): _ Final payment _no___ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
FIN | UNDP | Formulation of the investment components of the RMP | Individual | AFR | GBS | REF | 39 | PRP | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2005-04-01 | 2006-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 1875 | 0 | 1875 | 0 | 0 | Completed in 2005. Financially completed in 2006. |  | 2003 |  | Investment
FIN | UNEP | Implementation of the RMP: monitoring of the activities in the RMP | Individual | AFR | GBS | REF | 43 | TAS | 05 | A | I | CFC | 1 | 0 | 0 | 0 | 2004-07-01 | 2005-07-01 | 2007-07-01 |  | 2008-12-01 | 2009-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0
FIN | UNDP | Implementation of the RMP: technical assistance project for MAC and refrigeration service and end-user sub-sectors | RMP-Component | AFR | GBS | REF | 43 | TAS | 07 | N | I | CFC | 14.3 | 14.3 | 0 | 0 | 2004-07-01 | 2009-05-01 | 2006-07-01 |  | 2011-12-01 | 2014-03-01 | 282900 | -480 | 282420 | 282420 | 100% | 0 | 0 | 0 | 21217.5 | -36 | 21181.5 | 0 | 0 | Financially completed in 2014. | Final invoices pending. | 2004 |  | Investment
FIN | UNEP | Implementation of the RMP: training for customs officials, police, coast guards, border guards and commercial inspectors | Individual | AFR | GBS | REF | 43 | TRA | 06 | A | I | CFC | 3.5 | 3.5 | 0 | 0 | 2004-07-01 | 2004-08-01 | 2006-07-01 |  | 2007-12-01 | 2010-12-01 | 70000 | -1956 | 68044 | 68044 | 100% | 0 | 0 |  | 9100 | -254.28 | 8845.72 | 0 | 0
FIN | UNEP | Implementation of the RMP: training for refrigeration technicians | Individual | AFR | GBS | REF | 43 | TRA | 08 | A | I | CFC | 3.5 | 3.5 | 0 | 0 | 2004-07-01 | 2005-07-01 | 2006-07-01 |  | 2007-12-01 | 2009-12-01 | 70000 | -626 | 69374 | 69374 | 100% | 0 | 0 |  | 9100 | -81.38 | 9018.62 | 0 | 0
FIN | UNEP | Establishment of ozone unit | Individual | AFR | GBS | SEV | 39 | INS | 01 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2010-01-01 | 2004-04-01 |  | 2004-07-01 | 2010-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Formulation of the country programme/RMP | RMP | AFR | GBS | SEV | 39 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-06-01 | 2004-04-01 |  | 2004-07-01 | 2011-03-01 | 60000 | -14454 | 45546 | 45546 | 100% | 0 | 0 |  | 7800 | -1879.02 | 5920.98 | 0 | 0
FIN | UNEP | Establishment of the Ozone Unit (institutional strengthening project) | Individual | AFR | GBS | SEV | 43 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2005-12-01 | 2006-07-01 |  | 2007-12-01 | 2008-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase II) | Individual | AFR | GBS | SEV | 50 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-01-01 | 2008-11-01 |  | 2011-11-01 | 2012-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of the institutional strengthening project (phase III: 7/2102-6/2014) | Individual | AFR | GBS | SEV | 67 | INS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2012-12-01 | 2014-06-01 |  | 2015-12-01 |  | 60000 | 0 | 60000 | 32992.4 | 54.99% | 27007.6 | 27007.6 | 27008 | 0 | 0 | 0 | 0 | 0 | Project completed | Project completed
ONG | UNEP | Extension of the institutional strengthening project (phase IV: 12/2014-11/2016) | Individual | AFR | GBS | SEV | 73 | INS | 18 | A | I |  | 0 |  | 0 |  | 2014-11-01 | 2015-07-01 | 2016-11-01 | 2017-12-01 |  |  | 60000 | 0 | 60000 | 26830.16 | 44.72% | 33169.84 | 33169.84 | 3316.984 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): _SSFA signed in July 2015. First payment sent in October 2015_ Country reported 2015 Art5 data and 2015 CP data in May 2016. Country coordinated the implementation of 2016 activities under Bissau HPMP, Celebration of the Ozone day in September 2016. Legal arrangements (actual/planned): signed in July 2015 (Yes/No): No_ First mission (actual/planned): __July 2015_ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): October 2015___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _YES_ If Yes, reasons for delay & action plan to resolve: NO__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): _SSFA signed in July 2015. First payment sent in October 2015_ Country reported 2015 Art5 data and 2015 CP data in May 2016. Country coordinated the implementation of 2016 activities under Bissau HPMP. Celebration of the Ozone day in September held 2016. NOU trained 75 RAC technicians and 40 enforcement officers in 2016. Legal arrangements (actual/planned): signed in July 2015 (Yes/No): No_ First mission (actual/planned): __July 2015_ TOR completed (actual/planned): _N/A__ First disbursement date (actual/planned): October 2015___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _YES_ If Yes, reasons for delay & action plan to resolve: NO__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | AFR | GBS | SEV | 75 | TAS | 19 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-05-01 | 2016-12-01 | 2017-10-01 |  |  | 40000 | 0 | 40000 | -0.42 | -0.00105% | 40000.42 | 40000 | 4000.042 | 5200 | 0 | -0.0546 | 5200.0546 | 5200 | Brief progress report (actual/planned): SSFA signed in May 2016_ Country received first payment in May 2016. National consultants hired in July 2016. Legal arrangements (actual/planned): Agreement signed in May 2016. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in May 16 __ All funds disbursed (yes/no): NO_ Final payment being _NO Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Brief progress report (actual/planned): SSFA signed in May 2016_ Country received first payment in May 2016. National consultants hired in July 2016. First draft report sent in January 2017, returned by UNEP for additional data consolidation. Legal arrangements (actual/planned): Agreement signed in May 2016. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in May 16 __ All funds disbursed (yes/no): NO_ Final payment being _NO Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
ONG | UNEP | Extension of the institutional strengthening project (phase V: 12/2016-11/2018) | Individual | AFR | GBS | SEV | 77 | INS | 22 | A | I |  | 0 |  | 0 |  | 2016-12-01 |  | 2018-11-01 | 2018-11-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | Newly approved project | Brief progress report (actual/planned): Project newly approved. Agreement not signed yet. Legal arrangements (actual/planned): Agreement not signed yet. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement _no __ All funds disbursed (yes/no): _ Final payment _no___ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
FIN | UNDP | Preparation of an ODS bank management and destruction demonstration project | Individual | EUR | GEO | DES | 64 | PRP | 32 | N | I | ODS-Waste | 0 | 0 | 0 | 0 | 2011-07-01 | 2011-11-01 | 2012-07-01 |  | 2013-03-01 | 2014-10-01 | 30000 | -103 | 29897 | 29897 | 100% | 0 | 0 | 0 | 2250 | -7.72 | 2242.28 | 0 | 0 | Financially completed in 2014. | Completed in 2013. | 2011 |  | Non-Investment
FIN | UNDP | Pilot demonstration project on ODS waste management and disposal | Individual | EUR | GEO | DES | 69 | DEM | 33 | N | I | ODS-Waste | 0 | 0 | 0 | 0 | 2013-04-01 | 2014-04-01 | 2015-04-01 |  | 2015-12-01 | 2016-12-01 | 55264 | 0 | 55264 | 45385 | 82.12% | 9879 | 0 | 0 | 4974 | 0 | 4084.8471 | 889.1529 | 0 | Financially completed in 2016. | ODS waste destruction certificates received. NOU-Georgia and UNDP project team together will conduct a survey of available cement kilns which would be willing to upgrade their air-pollution control and ODS waste feed mechanisms to take such waste for disposal in future. Two storage cylinders are being purchased for the central R/R/R Center in Tbilisi to ensure additional waste has a place for accumulation and safe storage in future. Project will be closed after these two last activities. Final report will be completed in Q4 of 2015. | 2013 |  | Non-Investment
FIN | Canada | Initiating early phase-out of methyl bromide through awareness raising, policy development and demonstration/training activities | Individual | EUR | GEO | FUM | 30 | TAS | 07 | A | I |  | 0 |  | 0 |  | 2000-03-01 | 2001-04-01 | 2002-03-01 |  | 2004-01-01 | 2004-01-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed. PCR submitted. |  | 2000 |  | Non-Inv.
FIN | UNIDO | Project preparation in the soil fumigation sector | Individual | EUR | GEO | FUM | 33 | PRP | 09 | A | I | MBR | 0 | 0 |  |  | 2001-03-01 | 2001-11-01 | 2002-04-01 |  | 2002-05-01 | 2003-05-01 | 30000 | -1001 | 28999 | 28998.87 | 100% | 0.13 | 0 |  | 3900 | -136 | 3764 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Technical assistance for the phase-out of methyl bromide for soil fumigation | Individual | EUR | GEO | FUM | 37 | TAS | 13 | A | I | MBR | 6 | 6 |  |  | 2002-07-01 | 2003-02-01 | 2006-08-01 |  | 2006-12-01 | 2009-12-01 | 220000 | -957 | 219043 | 219043.42 | 100% | -0.42 | 0 |  | 28600 | -124 | 28476 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of structure in fumigation of commodities in mill factories and grain storage | Individual | EUR | GEO | FUM | 44 | PRP | 17 | A | I |  | 0 | 0 |  |  | 2004-12-01 | 2005-07-01 | 2005-12-01 |  | 2005-12-01 | 2006-12-01 | 30000 | -62 | 29938 | 29937.84 | 100% | 0.16 | 0 |  | 2250 | -5 | 2245 | 0 | 0 | FIN
FIN | UNIDO | Technical assistance for the elimination of methyl bromide in grain and storage facilities | Individual | EUR | GEO | FUM | 47 | INV | 20 | A | I | MBR | 7.2 | 7.2 |  |  | 2005-11-01 | 2006-07-01 | 2009-12-01 |  | 2010-12-01 | 2012-05-01 | 225500 | -2 | 225498 | 225498.11 | 100% | -0.11 | 0 |  | 20295 | 0 | 20295 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a national halon bank | Individual | EUR | GEO | HAL | 44 | PRP | 16 | A | I |  | 0 | 0 |  |  | 2004-12-01 | 2005-07-01 | 2005-12-01 |  | 2006-10-01 | 2007-09-01 | 15000 | -1438 | 13562 | 13561.63 | 100% | 0.37 | 0 |  | 1125 | -108 | 1017 | 0 | 0 | FIN
FIN | UNIDO | Halon banking management programme | Individual | EUR | GEO | HAL | 47 | TAS | 21 | A | I | HAL | 42.5 | 42.5 |  |  | 2005-11-01 | 2006-08-01 | 2008-12-01 |  | 2008-01-01 | 2008-09-01 | 64930 | -603 | 64327 | 64327.46 | 100% | -0.46 | 0 |  | 5844 | -55 | 5789 | 0 | 0 | FIN |  |  |  | INV
FIN | Sweden | Assistance to prepare a terminal phase-out management plan | Individual | EUR | GEO | PHA | 47 | PRP | 19 | A | I |  | 0 |  | 0 |  | 2005-11-01 | 2006-01-01 | 2006-12-01 |  | 2006-12-01 | 2006-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | In December 2005 at the 47th Meeting of the Executive Committee, the Government of Sweden received approval for the preparation of a Terminal phase-out management plan in Georgia. The final TPMP was submitted to the 50th ExCom meeting and approved. The TPMP is implemented by UNDP as sole implementing agency. |  | 2005
FIN | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | EUR | GEO | PHA | 50 | INV | 22 | N | I | CFC | 4.8 | 4.8 | 0 | 0 | 2006-11-01 | 2007-04-01 | 2009-11-01 |  | 2008-12-01 | 2011-10-01 | 216180 | 0 | 216180 | 216180 | 100% | 0 | 0 | 0 | 16214 | 0 | 16214 | 0 | 0 | Completed in 2008. Financially completed in 2011. |  | 2006 |  | Investment
FIN | UNDP | Terminal phase-out management plan (second tranche) | Multi-Year | EUR | GEO | PHA | 53 | INV | 25 | N | I | CFC | 3.4 | 3.4 | 0 | 0 | 2007-11-01 | 2009-10-01 | 2009-11-01 |  | 2009-12-01 | 2011-10-01 | 108820 | -81.94 | 108738.06 | 108738 | 100% | 0.06 | 0 | 0 | 8162 | -6.15 | 8155.8496 | 0.00040028 | 0 | Completed in 2009. Financially completed in 2011. |  | 2007 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | EUR | GEO | PHA | 55 | PRP | 26 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2010-12-01 | 2013-04-01 | 85000 | -1037.68 | 83962.32 | 83962 | 100% | 0.32 | 0 | 0 | 6375 | -77.83 | 6297.15 | 0.02 | 0 | Financially completed in 2013. |  | 2008 |  | Investment
FIN | UNDP | TPMP verification | Individual | EUR | GEO | PHA | 57 | TAS | 29 | N | I | CFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-02-01 | 2010-03-01 |  | 2010-08-01 | 2011-08-01 | 20000 | -136.13 | 19863.87 | 19864 | 100% | -0.13 | 0 | 0 | 1800 | -12.25 | 1787.76 | -0.01 | 0 | Completed. Fully formulated TPMP verification report was submitted to the MLF Secretariat in February 2010. Further, it was reviewed and approved at the 60th meeting of the Executive Committee (60/8). |  | 2009 |  | Non-Investment
FIN | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | EUR | GEO | PHA | 63 | INV | 30 | N | I | HCFC | 0.7 | 0.7 | 0 | 0 | 2011-04-01 | 2013-04-01 | 2014-03-01 |  | 2015-03-01 | 2016-03-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 15000 | 0 | 15000 | 0 | 0 | Financially completed in 2016. | The first tranche is complete as no funding is left. This project was operationally completed in March 2015. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | EUR | GEO | PHA | 72 | INV | 35 | N | I | HCFC | 0.5 | 0 | 0 | 0 | 2014-05-01 | 2015-04-01 | 2017-05-01 | 2017-12-01 |  |  | 150000 | 0 | 150000 | 89194.79 | 59.46% | 60805.21 | 0 | 24322.084 | 11250 | 0 | 6689.6093 | 4560.3907 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): In order to improve HCFC control skills and capacity for Customs office, the project organized special trainings in April 2016 for 40 officers in Tbilisi and Batumi. One tender held for two HCFC leak detectors and one multi-gas analyzer - this equipment was purchased for Customs. One Customs office represetnative was funded for participation in the regional network meeting in Turkmenistan in May 2016. Two experts were recruited to prepare materials for planned publication on Ozone Layer's protection - a scientific-educational book, intended for high school students and teachers. Prodoc signed (actual/planned, yes/no and date):1/1. Yes. Agreement signed earlier. Missions undertaken (actual/planned):1/1: Mission fielded in 2016 to assist NOU with workplaning and progress checking TOR for consultants/subcontracts completed (actual/planned): 3/3: One trainer for Customs, and two experts for publication were recruited. Contract/PO/MOA agreements signed: 1/1: One tender was announced and completed in 2016. First disbursement date (actual/planned): 42095Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:2015's change in project team postponed workplans into 2016. Currently all works are on track. | - |  |  | Investment
ONG | UNDP | Verification report for stage I of HCFC phase-out management plan | Individual | EUR | GEO | PHA | 75 | TAS | 38 | N | I | HCFC | 0 | 0 | 0 | 0 | 2015-11-01 | 2016-12-01 | 2017-03-01 | 2017-03-01 |  |  | 30000 | 0 | 30000 | 4604.6 | 15.35% | 25395.4 | 0 | 10158.16 | 2700 | 0 | 414.414 | 2285.586 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Project document signed by relevant parties in September 2016. A consultancy company was selected and contractual part was finalized. That contractor developed detailed steps and situation assessment procedures for the verification process; it further prepared and submitted summary of relevant national legislation, policies and procedures associated iwht HCFC controls; and a detailed analysis of national compliance situation. recommendations. Prodoc signed (actual/planned, yes/no and date):1/1. Yes, in November 2016 Missions undertaken (actual/planned):0/0: No mission required from NOU on verification process. TOR for consultants/subcontracts completed (actual/planned): 1/1: One sub-contract was established with a national consultancy company to process verification. Contract/PO/MOA agreements signed: 0/0: No procurement processes planned in the verification project First disbursement date (actual/planned): 42705Any delays/problems (yes/no):No. Verification schedule is on time If Yes, reasons for delay & action plan to resolve: | A final draft report with conclusions and recommendations was submitted to NOU. | 2015 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: Implementation of a national programme for recovery and recycling of refrigerants | RMP-Component | EUR | GEO | REF | 23 | TAS | 04 | A | I | CFC | 3.7 | 3.7 | 0 | 0 | 1997-11-01 | 1998-12-01 | 2000-12-01 |  | 2001-12-01 | 2003-04-01 | 106750 | -2348 | 104402 | 104402 | 100% | 0 | 0 | 0 | 13877.5 | -305.24 | 13572.26 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNEP | Implementation of the RMP: training in monitoring and controlling of ODS | Individual | EUR | GEO | REF | 23 | TRA | 02 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 2002-01-01 | 1998-02-01 |  | 2005-06-01 | 2006-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 |  | 4550 | 0 | 4550 | 0 | 0
FIN | UNEP | Implementation of the RMP: training of trainers in the refrigeration servicing sector | Individual | EUR | GEO | REF | 23 | TRA | 05 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1999-11-01 | 1998-11-01 |  | 2001-11-01 | 2006-12-01 | 50000 | -9800 | 40200 | 40200 | 100% | 0 | 0 |  | 6500 | -1274 | 5226 | 0 | 0
FIN | UNDP | Implementation of the RMP: incentive programme for the end-users in the commercial/industrial refrigeration and refrigerated transport sub-sectors | RMP-Component | EUR | GEO | REF | 35 | TAS | 10 | N | I | CFC | 14.1 | 14.1 | 0 | 0 | 2001-12-01 | 2002-06-01 | 2005-01-01 |  | 2005-01-01 | 2007-06-01 | 101000 | -553 | 100447 | 100447 | 100% | 0 | 0 | 0 | 13130 | -71.95 | 13058.0463 | 0.0037 | 0 | Completed in 2005. Financially completed in 2007. |  | 2001 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: monitoring the activities in the RMP | RMP-Component | EUR | GEO | REF | 35 | TAS | 11 | N | I | No_ODP | 2.3 | 2.3 | 0 | 0 | 2001-12-01 | 2002-06-01 | 2007-12-01 |  | 2005-12-01 | 2007-06-01 | 16350 | 0 | 16350 | 16350 | 100% | 0 | 0 | 0 | 2125.5 | 0 | 2125.5 | 0 | 0 | Completed in 2005. Financially completed in 2007. |  | 2001 |  | Non-Investment
FIN | UNEP | Implementation of the RMP: training programme in the refrigeration sector (phase III) | Individual | EUR | GEO | REF | 35 | TRA | 12 | A | I | CFC | 2.8 | 2.8 | 0 | 0 | 2001-12-01 | 2002-02-01 | 2003-01-01 |  | 2005-11-01 | 2008-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0
FIN | UNDP | Preparation for HCFC phase-out investment activities (refrigeration sector) | Individual | EUR | GEO | REF | 57 | PRP | 27 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-03-01 | 2010-03-01 |  | 2010-12-01 | 2011-08-01 | 30000 | -0.78 | 29999.22 | 29999 | 100% | 0.22 | 0 | 0 | 2250 | -0.06 | 2249.925 | 0.015 | 0 | Completed in 2010. Financially completed in 2011. |  | 2009 |  | Investment
FIN | UNEP | Country programme preparation | Individual | EUR | GEO | SEV | 23 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1997-11-01 |  | 1997-11-01 | 1997-11-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 |  | 0
FIN | UNEP | Establishment of a National Ozone Unit | Individual | EUR | GEO | SEV | 23 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-07-01 | 2000-12-01 |  | 2001-05-01 | 2001-07-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0
FIN | Canada | Promoting compliance with the Montreal Protocol in countries with economies in transition (CEITs) | Individual | EUR | GEO | SEV | 27 | TAS | 06 | A | I |  | 0 |  | 0 |  | 1999-03-01 | 1999-07-01 | 2001-03-01 |  | 2001-10-01 | 2002-06-01 | 33900 | 0 | 33900 | 33900 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed. PCR submitted. |  | 1999 |  | Non-Inv.
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | EUR | GEO | SEV | 32 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-08-01 | 2003-01-01 |  | 2003-02-01 | 2003-12-01 | 46700 | 0 | 46700 | 46700 | 100% | 0 | 0 |  | 6071 | 0 | 6071 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase 3) | Individual | EUR | GEO | SEV | 39 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-08-01 | 2005-04-01 |  | 2004-12-01 | 2008-12-01 | 60667 | 0 | 60667 | 60667 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project: phase IV | Individual | EUR | GEO | SEV | 45 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-07-01 | 2007-04-01 |  | 2007-04-01 | 2009-11-01 | 60667 | 0 | 60667 | 60667 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
TRF | UNEP | Extension of the institutional strengthening project (phase V) | Individual | EUR | GEO | SEV | 51 | INS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2007-03-01 |  | 2009-03-01 |  |  | 2007-12-01 | 60667 | -60667 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 |  | 0
FIN | UNDP | Extension of the institutional strengthening project (phase V) | Individual | EUR | GEO | SEV | 52 | INS | 24 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-11-01 | 2009-03-01 |  | 2009-12-01 | 2011-08-01 | 60667 | -39.95 | 60627.05 | 60627 | 100% | 0.05 | 0 | 0 | 4550 | -3 | 4547.0001 | -5.0021e-05 | 0 | Completed in 2009. |  | 2007 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VI) | Individual | EUR | GEO | SEV | 57 | INS | 28 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-03-01 | 2011-06-01 |  | 2011-12-01 | 2013-04-01 | 60667 | -47.15 | 60619.85 | 60620 | 100% | -0.15 | 0 | 0 | 4550 | -3.54 | 4546.475 | -0.01505 | 0 | Financially completed in 2013. | Completed in 2011. | 2009 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VII) | Individual | EUR | GEO | SEV | 63 | INS | 31 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2011-04-01 | 2012-05-01 | 2013-06-01 |  | 2013-06-01 | 2014-12-01 | 60667 | -148 | 60519 | 60519 | 100% | 0 | 0 | 0 | 4550 | -11.1 | 4538.9 | 0 | 0 | Financially completed in 2014. | Completed in 2013. Funds in this IS phase exhausted | 2011 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VIII: 7/2013-6/2015) | Individual | EUR | GEO | SEV | 69 | INS | 34 | N | I | non-HCFC | 0 | 0 | 0 | 0 | 2013-04-01 | 2014-03-01 | 2015-06-01 |  | 2015-12-01 | 2016-12-01 | 60667 | 0 | 60667 | 60586 | 99.87% | 81 | 0 | 0 | 4247 | 0 | 4241.3296 | 5.6704 | 0 | Financially completed in 2016. | A campaign was held with students of art colleges to produce a special greeting card with the Ozone Day theme which will not be for sale as other cards, but will be circulated to key ministries and other stakeholders to raise awareness. Winners will receive special gifts and souvenirs (palletes, brush sets). NOU-Georgia has prepared for the celebrations on the Ozone Day in September. In April 2015, 15 Customs officers were trained in Tbilisi, and 20 officers in Western Georgia (Kutaisi). Art 7 data collection has been supported to enable NOU-Georgia to report to the Ozone Secretariat on the HCFC consumption for 2014. | 2013 |  | Non-Investment
ONG | UNDP | Extension of the institutional strengthening project (phase IX: 7/2015-6/2017) | Individual | EUR | GEO | SEV | 74 | INS | 37 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2015-05-01 | 2015-11-01 | 2017-06-01 | 2017-12-01 |  |  | 60667 | 0 | 60667 | 18184.5 | 29.97% | 42482.5 | 0 | 16993 | 4247 | 0 | 1273.0079 | 2973.9921 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): In order to strengthen certification system, NOU arranged training for 100 technicians working in the refrigerating/air-conditioning sector and on thermal pumps. The project assisted Environmental Information and Education Center (EIEC) to build their capacity for conducting certification of technicians as required by the amended Law on Air Protection. Required test materials were formulated. Ozone.ge web-page is undergoing an update. Prodoc signed (actual/planned, yes/no and date):1/1. Yes. Agreement signed earlier. Missions undertaken (actual/planned):1/1: Mission fielded in 2016 to assist NOU with workplaning and progress checking TOR for consultants/subcontracts completed (actual/planned): 2/2: Refrigeration technician expert for test materials and web-page developer for software updates were recruited. Contract/PO/MOA agreements signed: 0/0: No procurement planned in this project's cycle except other personnel sub-contracts. First disbursement date (actual/planned): 42309Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:2015's change in project team postponed workplans into 2016. Currently all works are on track. | Currently, electronic test and certification software is being developed to assist the training center. | 2015 |  | Non-Investment
ONG | UNIDO | Survey of ODS alternatives at the national level | Individual | EUR | GEO | SEV | 74 | TAS | 36 | A | I |  | 0 | 0 |  |  | 2015-05-01 | 2016-01-01 | 2016-05-31 | 2017-05-17 |  |  | 40000 | 0 | 40000 | 10905.56 | 27.26% | 29094.44 | 0 | 20000 | 3600 | 0 | 0 | 3600 | 0 | Collection of data has been completed and related draft report received. This is followed by data verification and preparation of the completion of the format agreed by the ExCom. Project is planned to completed by February 2017. | Report has been reviewed and revision/update will take place during April 2017. Submission of final report is scheduled for May/2017. |  |  | NON-INV
FIN | UNDP | MDI transition strategy | Individual | AFR | GHA | ARS | 56 | TAS | 28 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-05-01 | 2010-05-01 |  | 2009-12-01 | 2011-09-01 | 30000 | -40.56 | 29959.44 | 29959 | 100% | 0.44 | 0 | 0 | 2700 | -3.65 | 2696.31 | 0.04 | 0 | Completed in 2009. |  | 2008 |  | Non-Investment
FIN | UNDP | Preparation for pilot demonstration project on ODS waste management and disposal | Individual | AFR | GHA | DES | 57 | PRP | 29 | N | I | ODS-Waste | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-05-01 | 2010-03-01 |  | 2011-04-01 | 2012-05-01 | 30000 | -4400 | 25600 | 25600 | 100% | 0 | 0 | 0 | 2250 | -330 | 1920 | 0 | 0 | Financially completed in 2012. | Completed in 2011. | 2009 |  | Investment
COM | UNDP | Pilot demonstration project on ODS waste management and disposal | Individual | AFR | GHA | DES | 63 | DEM | 33 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-11-01 | 2014-03-01 |  | 2016-12-01 |  | 198000 | 0 | 198000 | 197193.74 | 99.59% | 806.26 | 0 | 322.504 | 17820 | 0 | 17747.4366 | 72.5634 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): This project was almost completed by the end of 2015. The last remaining item was to address the remaining collected foam from the refrigerators through best environmental practices. Cooperation with the GIZ-funded project addressing ODS waste in Ghana allowed to find a technological solution avoiding the release of ODSs from the collected foam. Prodoc signed (actual/planned, yes/no and date):1/1. Yes. Agreement signed earlier. Missions undertaken (actual/planned):0/0 No mission required at this stage. HPMP monitoring missions allow to follow up on the sustainability and replication of the demonstration project. TOR for consultants/subcontracts completed (actual/planned): ToR completed earlier Contract/PO/MOA agreements signed: 0/0 No procurement at this stage. First disbursement date (actual/planned): 40848Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | NA | 2011 |  | Non-Investment
FIN | UNDP | Technical assistance for technology transfer for phase-out of CFC-11 in flexible foam | Individual | AFR | GHA | FOA | 08 | TAS | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1994-01-01 | 1994-10-01 |  | 1995-06-01 | 1997-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Umbrella project for continuation of CFC free-technology in the manufacture of flexible polyurethane foam at Ashanti, Latex Foam, Nsawam and Prestige Foam | Individual | AFR | GHA | FOA | 12 | INV | 07 | A | I | CFC | 316 | 316 | 0 | 0 | 1994-03-01 | 1997-12-01 | 1994-12-01 |  | 2000-06-01 | 2001-12-01 | 345000 | -53650 | 291350 | 291350 | 100% | 0 | 0 | 0 | 44850 | -6974.13 | 37875.87 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1994 | 1999-08-01 | Investment
FIN | UNDP | Project preparation in soil fumigation (curcubits) | Individual | AFR | GHA | FUM | 33 | PRP | 17 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-11-01 | 2002-04-01 |  | 2002-12-01 | 2003-09-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Training programme for terminal phase-out of methyl bromide use, excluding QPS applications | One-off-Phaseout | AFR | GHA | FUM | 37 | TRA | 18 | N | I | MeBr | 6.3 | 6.3 | 0 | 0 | 2002-07-01 | 2003-02-01 | 2005-08-01 |  | 2006-12-01 | 2009-08-01 | 101550 | -799 | 100751 | 100751 | 100% | 0 | 0 | 0 | 13201.5 | -103.87 | 13097.63 | 0 | 0 | Completed in 2006.Financially completed in 2009. |  | 2002 |  | Non-Investment
FIN | UNDP | Project preparation of a terminal phase-out management plan | Individual | AFR | GHA | PHA | 47 | PRP | 23 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-02-01 | 2006-12-01 |  | 2006-12-01 | 2008-08-01 | 30000 | -609 | 29391 | 29391 | 100% | 0 | 0 | 0 | 2250 | -45.68 | 2204.325 | -0.005 | 0 | Completed in 2006. Financially Completed in 2008. |  | 2005 |  | Investment
FIN | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | GHA | PHA | 50 | INV | 24 | N | I | CFC | 12.2 | 12.2 | 0 | 0 | 2006-11-01 | 2007-03-01 | 2009-11-01 |  | 2008-11-01 | 2011-06-01 | 204394 | 0 | 204394 | 204394 | 100% | 0 | 0 | 0 | 15330 | 0 | 15330 | 0 | 0 | Completed in 2008. Financially completed in 2011. |  | 2006 |  | Investment
FIN | UNDP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | GHA | PHA | 53 | INV | 26 | N | I | CFC | 5.3 | 5.3 | 0 | 0 | 2007-11-01 | 2008-01-01 | 2009-11-01 |  | 2009-11-01 | 2011-06-01 | 140500 | 0 | 140500 | 140500 | 100% | 0 | 0 | 0 | 10538 | 0 | 10538 | 0 | 0 | Completed in 2009. Financially completed in 2011. |  | 2007 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | AFR | GHA | PHA | 55 | PRP | 27 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2010-07-01 | 2011-02-01 | 85000 | -2468.29 | 82531.71 | 82532 | 100% | -0.29 | 0 | 0 | 6375 | -185.12 | 6189.9001 | -0.02005 | 0 | Completed. HPMP submitted and approved at 61st meeting. |  | 2008 |  | Investment
FIN | UNDP | HCFC phase-out management plan (phase I, first tranche) | Multi-year | AFR | GHA | PHA | 61 | INV | 30 | N | I | HCFC | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-01-01 | 2014-12-01 |  | 2012-12-01 | 2013-07-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 15000 | 0 | 15000 | 0 | 0 | Financially completed in 2013. |  | 2010 |  | Investment
FIN | Italy | HCFC phase-out management plan (phase I, first tranche) | Multi-Year | AFR | GHA | PHA | 61 | TAS | 31 | N | I | HCFC | 0 | 0 | 0 | 0 | 2010-07-01 | 2012-04-01 | 2014-12-01 | 2014-12-01 | 2012-12-01 | 2015-08-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Financially completed in 2015. | Financially completed in 2015. | 2010 |  | Investment
COM | UNDP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | AFR | GHA | PHA | 67 | INV | 34 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-07-01 | 2013-03-01 | 2014-07-01 |  | 2016-12-01 |  | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 15000 | 0 | 15000 | 0 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): The final activities under this tranche were completed in 2016, including in relation to the full launch of the Centre of Excellence at the national level for refrigeration technicians; and the continuation of the support to the certified service centres for the refrigerant recovery/retrofit project. As several activities in second tranche were linked to the third tranche, details are further given in the report of the third tranche. Prodoc signed (actual/planned, yes/no and date):1/1. Yes. Agreement signed earlier. Missions undertaken (actual/planned):0/0 No mission for this year, but planned for early 2017. TOR for consultants/subcontracts completed (actual/planned): ToR completed earlier Contract/PO/MOA agreements signed: No new procurement for this tranche. First disbursement date (actual/planned): 41334Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | NA | 2012 |  | Investment |  | To request the submission of additional status report to the 79th meeting to monitor the delivery of the equipment.
COM | Italy | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | AFR | GHA | PHA | 67 | INV | 35 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-07-01 | 2013-03-01 | 2014-07-01 | 2016-09-01 | 2016-10-01 |  | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | This tranche was fully operationally completed by October 2016. The international consultant for legal background component related to the strengthening of the regulatory environment delivered his second report, "Ghana HPMP - Phase II - Legal projects component" in 2016 which was reviewed and shared with national stakeholders, and fully integrated in the work of a new national Committee for a Regulatory Framework for Hydrocarbon Refrigerants in Ghana; after a review meeting of the Guidelines for Hydrocarbons use in Ghana held on 14 July 2016, these Guidelines were completed and shared with the MLF Secretariat and, more importantly, are now implemented by industry and Ghana EPA. These guidelines represented one of the 2 conditions of the release of the funds for the 4th tranche (the other condition, the provision of a verification report, was also completed). Finally, the procurement of the identifiers to be used in Ghana was succesfully completed and equipment received in October 2016, allowing now for distribution of these identifiers to customs officers and training on those. | This tranche was fully operationally completed by October 2016. The international consultant for legal background component related to the strengthening of the regulatory environment delivered his second report, "Ghana HPMP - Phase II - Legal projects component" in 2016 which was reviewed and shared with national stakeholders, and fully integrated in the work of a new national Committee for a Regulatory Framework for Hydrocarbon Refrigerants in Ghana; after a review meeting of the Guidelines for Hydrocarbons use in Ghana held on 14 July 2016, these Guidelines were completed and shared with the MLF Secretariat and, more importantly, are now implemented by industry and Ghana EPA. These guidelines represented one of the 2 conditions of the release of the funds for the 4th tranche (the other condition, the provision of a verification report, was also completed). Finally, the procurement of the identifiers to be used in Ghana was succesfully completed and equipment received in October 2016, allowing now for distribution of these identifiers to customs officers and training on those. | 2012 |  | Investment
ONG | Italy | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | AFR | GHA | PHA | 72 | INV | 37 | N | I | HCFC | 1.4 | 0 | 0 |  | 2014-05-01 |  | 2016-05-01 | 2016-05-01 | 2016-12-01 |  | 70000 | 0 | 70000 | 15517 | 22.17% | 54483 | 54483 | 28000 | 9100 | 0 | 2017 | 7083 | 0 | Activities under this tranche have been initiated, although in 2016 they have been mostly focusing on the monitoring of the HPMP by the international consultant, and the planning of the main set of activities: customs training, with the use of the newly received identifiers; and procurement of the reclaim machines, which will be complemented by training of technicians for optimal use of the new equipment. | The national plan for customs training is being completed by the NOU; the procurement of the reclaim machines will be launched shortly, through the UNDP Country Office. The training for this equipment will be attached to this procurement process. | 2014 | 2017-12-01 | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | AFR | GHA | PHA | 72 | INV | 39 | N | I | HCFC | 4.4 | 2.2 | 0 | 0 | 2014-05-01 | 2015-03-01 | 2016-05-01 | 2017-11-01 |  |  | 190000 | 0 | 190000 | 170520.86 | 89.75% | 19479.14 | 0 | 7791.656 | 14250 | 0 | 12789.0645 | 1460.9355 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Several trainings took place at the Centre of Excellence: in April 2016, a GIZ consultant provided forty (40) A/C practitioners theoretical and practical hands-on training with emphasis on hydrocarbon safety, handling, the EU codes and standards, welding and brazing, instrumentation, charging. Two training Workshops for Forty (40) selected Personnel from Factory Inspectorate, the Fire Service and some Importers and Distributors of refrigerant were held at Takoradi & Kumasi 27th September & 4th October, 2016. Regrading the Refrigerant Recovery Recycling Project (RRRP) : tools and equipment which the HPMP project purchased for the 11 RR centres are being put to good use. Equipment assets register has been opened for all the equipment and all the equipment have been labelled and verified. The Converted A/Cs running on HC 290 have all been verified. 2630 AC units were converted in 2016, and 5158 kg of refrigerants have been recovered. Guidelines for the use of HC refrigerants were approved by Ghana EPA with the approval of industry stakeholders and are being implemented. Prodoc signed (actual/planned, yes/no and date):1/1. Yes. Agreement signed earlier. Missions undertaken (actual/planned):0/0 No Mission TOR for consultants/subcontracts completed (actual/planned): ToR completed earlier Contract/PO/MOA agreements signed: NA First disbursement date (actual/planned): 42064Any delays/problems (yes/no):Yes: procurement for the the equipment for the Northern Sector Centre of Excellence for Refrigeration Training has ben complete with delays and will be delivered shortly in 2017 (one item was difficult to identify by the e supplier, this was solve through regular contacts from UNDP. The process started in 2015 for the end user programme could not be completed yet in 2016, due to the thorough review being analysed for the alternate proposed technology. If Yes, reasons for delay & action plan to resolve:Delay was eventually solved through regular contacts between the Country Office and the supplier. | New analysis on the end user applications was prepared and submitted by the NOU in March 2017. |  |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, fourth tranche) | Multi-Year | AFR | GHA | PHA | 76 | INV | 42 | N | I | HCFC | 0 | 0 | 0 | 0 | 2016-05-01 |  | 2018-06-18 | 2017-12-01 |  |  | 195000 | 0 | 195000 | 0 | 0% | 195000 | 0 | 78000 | 14625 | 0 | 0 | 14625 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): The tranche was approved conditionally, with the requirement to provide a Verification report and develop and adopt the Guidelines for the use of HC refrigerants. This only happened in the last quarter of 2016. Prodoc signed (actual/planned, yes/no and date):0/1. No, due to the conditions put for the approval. Missions undertaken (actual/planned):No TOR for consultants/subcontracts completed (actual/planned): No Contract/PO/MOA agreements signed: No First disbursement date (actual/planned): Any delays/problems (yes/no):This was due to the tie that was needed to prepare the two reports noted in the conditional approval. If Yes, reasons for delay & action plan to resolve:Eventually resolved after final reviews and clearances. | Activities are now about to start under this tranche. |  |  | Investment
ONG | Italy | HCFC phase-out management plan (stage I, fourth tranche) | Multi-Year | AFR | GHA | PHA | 76 | INV | 43 | N | I | HCFC | 0 |  | 0 |  | 2016-05-01 |  | 2018-06-01 |  |  |  | 65000 | 0 | 65000 | 0 | 0% | 65000 | 0 | 0 | 8450 | 0 | 0 | 8450 | 0 | The activities of this tranche approved could not be initiated in 2016 due to the necessary fulfillment of the 2 main conditions set in ExCom decision 76/46. With the fulfillment of these two conditions by end of 2016, the funds could be transferred to UNDP which acts as executing agency on behalf of the Government of Italy for this bilateral component) in January 2017. | While activities of Tranche 3 are being completed. Tthe plan of work for activities has been integrated in the overall work plan for implementation of HPMP in Ghana in 2017 | 2016 |  | Investment
TRF | UNDP | Refrigeration training programme for servicing technicians | RMP-Component | AFR | GHA | REF | 04 | TRA | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1992-06-01 | 1992-06-01 |  |  | 1993-06-01 | 99000 | -93800 | 5200 | 5200 | 100% | 0 | 0 | 0 | 12870 | -12194 | 676 | 0 | 0 | Transferred in 1993. Financially completed in 1993. |  | 1991 |  | Non-Investment
FIN | UNDP | Improved servicing and maintenance within the refrigeration sector | RMP-Component | AFR | GHA | REF | 08 | TAS | 04 | A | I | CFC | 50 | 50 | 0 | 0 | 1992-10-01 | 1993-10-01 | 1995-10-01 |  | 1997-04-01 | 1998-12-01 | 328000 | 0 | 328000 | 328000 | 100% | 0 | 0 | 0 | 42640 | 0 | 42640 | 0 | 0 | Completed in 1997. Financially completed in 1998. |  | 1992 |  | Investment
FIN | UNEP | Implementation of train the trainer programme and national demonstration programme | Individual | AFR | GHA | REF | 10 | TRA | 06 | A | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-07-01 | 1995-06-01 |  | 1995-12-01 | 1999-04-01 | 99000 | 0 | 99000 | 99000 | 100% | 0 | 0 |  | 12870 | 0 | 12870 | 0 | 0
FIN | France | Technical assistance in air conditioning |  | AFR | GHA | REF | 27 | TAS | 11 | A | I |  | 0 |  | 0 |  | 1999-03-01 | 2000-01-01 | 2000-04-01 |  | 2001-04-01 | 2001-04-01 | 31500 | -5121 | 26379 | 26379 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed. Le Ghana a présenté avec l'aide du PNUD un projet utilisant les 50% restant dans le cadre du Plan de Gestion des Réfrigérants. Il n'est donc plus possible de présenter de projets avant 2007 dans ce pays.
FIN | UNDP | Implementation of the RMP: Mobile air conditioning recovery and recycling of CFC-12 | RMP-Component | AFR | GHA | REF | 32 | TAS | 12 | A | I | CFC | 7.7 | 7.7 | 0 | 0 | 2000-12-01 | 2001-10-01 | 2003-01-01 |  | 2003-12-01 | 2006-10-01 | 98902 | -45 | 98857 | 98857 | 100% | 0 | 0 | 0 | 12857.26 | -6 | 12851.26 | 0 | 0 | Completed in 2003. Financially completed in 2006. |  | 2000 |  | Investment
FIN | UNDP | Implementation of the RMP: Incentive programme for the commercial/industrial refrigeration end-user sector | RMP-Component | AFR | GHA | REF | 32 | TAS | 14 | N | I | CFC | 15.3 | 15.3 | 0 | 0 | 2000-12-01 | 2001-06-01 | 2006-01-01 |  | 2006-12-01 | 2009-08-01 | 198000 | -1419 | 196581 | 196581 | 100% | 0 | 0 | 0 | 25740 | -184.47 | 25555.53 | 0 | 0 | Completed in 2006.Financially completed in 2009. |  | 2000 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: Monitoring of the activities included in the RMP | RMP-Component | AFR | GHA | REF | 32 | TAS | 16 | N | I | CFC | 1.2 | 1.2 | 0 | 0 | 2000-12-01 | 2001-06-01 | 2002-01-01 |  | 2007-12-01 | 2009-08-01 | 15455 | -11257 | 4198 | 4198 | 100% | 0 | 0 | 0 | 2009.15 | -1463.3 | 545.8493 | 0.0007 | 0 | Completed in 2007.Financially completed in 2009. |  | 2000 |  | Non-Investment
FIN | UNEP | Implementation of the RMP: customs training programme | Individual | AFR | GHA | REF | 32 | TRA | 13 | A | I | CFC | 6.3 | 0 | 0 | 0 | 2000-12-01 | 2001-05-01 | 2002-01-01 |  | 2003-01-01 | 2007-04-01 | 81000 | -18194 | 62806 | 62806 | 100% | 0 | 0 |  | 10530 | -2365.22 | 8164.78 | 0 | 0 |  |  |  | 2003-06-01
FIN | UNEP | Country programme preparation | Individual | AFR | GHA | SEV | 04 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-07-01 | 1992-09-01 |  | 1992-10-01 | 1992-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0
FIN | IBRD | Country programme preparation |  | AFR | GHA | SEV | 04 | PRP | 09 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 29362 | -11448 | 17914 | 17914 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Institutional strengthening | Individual | AFR | GHA | SEV | 08 | INS | 05 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1993-06-01 | 1996-12-01 |  | 1996-12-01 | 1999-12-01 | 160000 | 23200 | 183200 | 183200 | 100% | 0 | 0 | 0 | 20800 | 3016 | 23816 | 0 | 0 | Completed in 1996. Financially completed in 1999. |  | 1992 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening | Individual | AFR | GHA | SEV | 20 | INS | 08 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1996-10-01 | 1996-11-01 | 1998-10-01 |  | 1998-12-01 | 1999-12-01 | 107000 | 0 | 107000 | 107000 | 100% | 0 | 0 | 0 | 13910 | 0 | 13910 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1996 |  | Non-Investment
FIN | UNDP | Renewal of the institutional strengthening project | Individual | AFR | GHA | SEV | 26 | INS | 10 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 2000-12-01 |  | 2000-12-01 | 2011-12-01 | 107000 | -7725 | 99275 | 99275 | 100% | 0 | 0 | 0 | 13910 | -1004.25 | 12905.75 | 0 | 0 | Completed in 2000. Financially completed in 2011. |  | 1998 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening (Phase IV) | Individual | AFR | GHA | SEV | 32 | INS | 15 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-04-01 | 2003-01-01 |  | 2003-02-01 | 2013-03-01 | 107000 | 0 | 107000 | 107000 | 100% | 0 | 0 | 0 | 13910 | 0 | 13910 | 0 | 0 | Financially completed in 2013. |  | 2000 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening (phase 5) | Individual | AFR | GHA | SEV | 38 | INS | 19 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-02-01 | 2004-12-01 |  | 2004-12-01 | 2009-08-01 | 139100 | -860 | 138240 | 138240 | 100% | 0 | 0 | 0 | 18083 | -111.8 | 17971.2 | 0 | 0 | Completed in 2004.Financially completed in 2009. |  | 2002 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VI) | Individual | AFR | GHA | SEV | 43 | INS | 20 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-07-01 | 2006-07-01 |  | 2006-12-01 | 2008-08-01 | 139100 | -272 | 138828 | 138828 | 100% | 0 | 0 | 0 | 10433 | -20.4 | 10412.599 | 0.001 | 0 | Completed in 2006. Financially Completed in 2008. |  | 2004 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VII) | Individual | AFR | GHA | SEV | 50 | INS | 25 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-01-01 | 2008-11-01 |  | 2008-11-01 | 2011-09-01 | 139100 | -70.57 | 139029.43 | 139029 | 100% | 0.43 | 0 | 0 | 10433 | -5.29 | 10427.6747 | 0.035252 | 0 | Completed in 2008. |  | 2006 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VIII) | Individual | AFR | GHA | SEV | 56 | INS | 29 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-11-01 | 2009-12-01 |  | 2010-12-01 | 2012-01-01 | 139100 | -116.65 | 138983.35 | 138983 | 100% | 0.35 | 0 | 0 | 10433 | -8.75 | 10424.2245 | 0.025451 | 0 | Financially completed in 2012. |  | 2008 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase IX) | Individual | AFR | GHA | SEV | 62 | INS | 32 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-02-01 | 2012-12-01 |  | 2012-12-01 | 2014-10-01 | 139100 | -1666 | 137434 | 137434 | 100% | 0 | 0 | 0 | 10433 | -124.96 | 10308.04 | 0 | 0 | Financially completed in 2014. | Completed in 2012. Some pending payments remaining. | 2010 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase X: 1/2013-12/2014) | Individual | AFR | GHA | SEV | 67 | INS | 36 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2012-07-01 | 2013-02-01 | 2014-12-01 |  | 2014-12-01 | 2016-02-01 | 139100 | 0 | 139100 | 139100 | 100% | 0 | 0 | 0 | 9737 | 0 | 9737 | 0 | 0 | Financially completed in 2016. | Work programme was agreed for 2014. Planned activities ongoing. Report on Phase 10 and Request for Phase 11 submitted for the consideration of ExCom 72. | 2012 |  | Non-Investment
COM | UNDP | Extension of the institutional strengthening project (phase XI: 1/2015-12/2016) | Individual | AFR | GHA | SEV | 72 | INS | 38 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2014-05-01 | 2015-03-01 | 2016-12-01 |  | 2016-12-01 |  | 139100 | 0 | 139100 | 121604.19 | 87.42% | 17495.81 | 0 | 14871.4385 | 9737 | 0 | 8512.2933 | 1224.7067 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): The National Ozone Unit successfully collected data for Article 7 data as well as reporting to the MFS, which were communicated to the Secretariats. The NOU also conducted a survey to identify the different brands of refrigerants on the Ghanaian market. Sensitize customs officers at border points and refrigerant dealers on detection of fake/ mislabeled /adulterated refrigerants; ca. 200 kg of such refrigerants were confiscated and awareness raising was conducted during visits and a radio programme. A seminar for second cycle institutions on ODS in the Ashanti Region of Ghana. Awareness raising was conducted at the time of the international ozone day in particular with secondary schools. NOU conducted monitoring of converted AC units (running on Hydrocarbon R290) in selected regional/district capitals. Prodoc signed (actual/planned, yes/no and date):1/1. Yes. Agreement signed earlier. Missions undertaken (actual/planned):No TOR for consultants/subcontracts completed (actual/planned): ToR completed earlier Contract/PO/MOA agreements signed: 0/0 No. First disbursement date (actual/planned): 42064Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | New phase initiated. |  |  | Non-Investment
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | AFR | GHA | SEV | 74 | TAS | 40 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-08-01 | 2016-05-01 | 2017-05-01 |  |  | 55000 | 0 | 55000 | 50500 | 91.82% | 4500 | 0 | 450 | 7150 | 0 | 6565 | 585 | 0 | Brief progress report (actual/planned): The first stakeholders meeting was organized by the NOU in May 2016 in Accra with the main goal to agree on the plan for the Survey of ODS alternatives at the national level and obtain support of main national stakeholders. The meeting was attended by 40 participants. One National Consultant was hired by the NOU to support the data collection. The National Consultant assisted the NOU in the identification of the current use of ODS alternatives by substance/sector and collection of import/export data for the substances for the past a couple of years. The National Consultant also provided support in establishing growth patterns in use by substance/sector and in compiling data on available ODS alternatives for various applications. The NOU and the National Consultant drafted and cross checked the information to ensure the completion of end-user surveys, collection, analysis, and aggregation of consumption data. The various sections of the report were drafted. The second stakeholders meeting was organized by the NOU in November 2016 in Accra with the main goal to organise consultations with representatives of the government and private sector to finalize the outcomes of the Survey of ODS alternatives and discuss potential opportunities for introduction of those alternatives in the country. The draft report was prepared by the NOU and the National Consultant. It was reviewed and finalized based on the format approved by ExCom decision 75/67 as contained in document UNEP/OzL.Pro/ExCom/75/77/Rev.1 after incorporating inputs/ comments raised during National Stakeholders’ workshop. The final report has been submitted to UNEP for final review and submission to MLFS. The NOU participated in the ODS Alternative Thematic workshop held in December 2016 to refine the draft report according to the revised template for the report. ___ Legal arrangements(actual/planned):N/A. ____Initial stages of project implementation(actual/planned): _Yes__ Intermediate goals achieved (actual/planned): Yes___ Project completion and follow up: _No__ First disbursement date (actual/planned): _N/A__ All funds disbursed (yes/no): YES__ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): __N/A_ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): The NOU incorporated comments from UNEP ROA and Paris and re-submitted final ODS survey report. The report is ready for submission
ONG | UNDP | Extension of the institutional strengthening project (phase XII: 1/2017-12/2018) | Individual | AFR | GHA | SEV | 76 | INS | 41 | N | I | HCFC | 0 | 0 | 0 | 0 | 2016-05-01 |  | 2018-12-18 | 2017-12-01 |  |  | 178048 | 0 | 178048 | 0 | 0% | 178048 | 0 | 71219.2 | 12463 | 0 | 0 | 12463 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): The project was set to start in January 2017 (as per ExCom decision). Prodoc signed (actual/planned, yes/no and date):0/0 Missions undertaken (actual/planned):0/0 TOR for consultants/subcontracts completed (actual/planned): 0/0 Contract/PO/MOA agreements signed: 0/0 First disbursement date (actual/planned): Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | Project now started. |  |  | Non-Investment
FIN | UNDP | Technical assistance for the CTC sector | Individual | AFR | GHA | SOL | 44 | TAS | 22 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2005-12-01 |  | 2006-12-01 | 2008-08-01 | 20000 | -284 | 19716 | 19716 | 100% | 0 | 0 | 0 | 1800 | -25.56 | 1774.44 | 0 | 0 | Completed in 2006. Financially Completed in 2008. |  | 2004 |  | Non-Investment
FIN | UNDP | Technical assistance in aerosol sector | Individual | GLO | GLO | ARS | 06 | TAS | 24 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-03-01 | 1994-02-01 |  | 1996-07-01 | 1997-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Completed in 1996. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNEP | Preparation of training material for aerosol sector | Individual | GLO | GLO | ARS | 09 | TAS | 32 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-06-01 | 1994-03-01 |  | 1994-06-01 | 1994-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNEP | Aerosol training workshop | Individual | GLO | GLO | ARS | 09 | TRA | 34 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1994-03-01 | 1994-12-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 |  | 11700 | 0 | 11700 | 0 | 0
FIN | IBRD | Global aerosol project | Individual | GLO | GLO | ARS | 10 | TAS | 44 | A | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-06-30 | 1994-12-01 |  | 1995-12-01 | 1995-12-01 | 350000 | -196423 | 153577 | 153577 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The Global Aerosol Phase I report has been received and is under consideration. It is most likely that the Phase II component will be implemented by UNEP. Discussions have been initiated. |  |  |  | Non-INV | 0
CLO | IBRD | Supervision of project implementation (1994) |  | GLO | GLO | ARS | 12 | PRP | 66 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1995-03-01 |  |  | 1994-12-01 | 349931 | -349931 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNEP | Produce sector-specific video for aerosol sector | Individual | GLO | GLO | ARS | 19 | TAS | 91 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1998-01-01 | 1996-12-01 |  | 1999-12-01 | 2000-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0 |  |  |  | 1999-03-01
FIN | UNEP | Development of guidelines to promote safety an aerosol conversions | Individual | GLO | GLO | ARS | 39 | TAS | 246 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-08-01 | 2003-12-01 |  | 2010-04-01 | 2011-04-01 | 52000 | 0 | 52000 | 52000 | 100% | 0 | 0 |  | 6760 | 0 | 6760 | 0 | 0
FIN | UNEP | MDI regional workshops/CAP | Individual | GLO | GLO | ARS | 52 | TAS | 282 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-01-01 | 2008-07-01 |  | 2009-12-01 | 2012-06-01 | 200000 | -49311 | 150689 | 150689 | 100% | 0 | 0 |  | 16000 | -3944.88 | 12055.12 | 0 | 0
FIN | IBRD | Development of strategy/methodology for ODS disposal |  | GLO | GLO | DES | 55 | TAS | 291 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-12-01 | 2009-07-31 |  | 2010-05-01 | 2010-09-01 | 250000 | 0 | 250000 | 250000 | 100% | 0 | 0 |  | 22500 | 0 | 22500 | 0 | 0 | Final study completed by the consultant, printed, distributed and posted on the internet. Companion piece drawing from the study that targets ozone nnits also completed. |  |  |  | Non-INV | 0
FIN | UNDP | Technical assistance in flexible polyurethane foam sector | Individual | GLO | GLO | FOA | 06 | TAS | 08 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-07-01 | 1994-02-01 |  | 1993-12-01 | 1997-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Technical assistance in rigid polyurethane foam sector | Individual | GLO | GLO | FOA | 06 | TAS | 19 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-07-01 | 1994-01-01 |  | 1993-12-01 | 1997-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Low-CFC foam training and demonstration programme in the Middle East/Africa | Individual | GLO | GLO | FOA | 06 | TRA | 17 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-06-01 | 1993-12-01 |  | 1993-12-01 | 1997-12-01 | 52500 | -14413 | 38087 | 38087 | 100% | 0 | 0 | 0 | 6825 | -1873.69 | 4951.31 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Safety pre-assessment and post-assessment of foam and solvent projects implemented by UNDP | Individual | GLO | GLO | FOA | 12 | TAS | 63 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-06-01 | 1995-03-01 |  | 1995-06-01 | 1997-12-01 | 25000 | 3000 | 28000 | 28000 | 100% | 0 | 0 | 0 | 3250 | 390 | 3640 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Non-Investment
FIN | UNDP | Determination of cost-effective phase-out approaches for enterprises with relatively small ODS use in foams | Individual | GLO | GLO | FOA | 14 | TAS | 71 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-09-01 | 1994-11-01 | 1995-09-01 |  | 1995-12-01 | 1997-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Non-Investment
FIN | UNEP | Produce a video on methyl bromide alternatives | Individual | GLO | GLO | FUM | 19 | TAS | 93 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1996-12-01 |  | 1999-03-01 | 2000-06-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0 |  |  |  | 1999-03-01
FIN | UNEP | Develop a technical brochure on methyl bromide | Individual | GLO | GLO | FUM | 19 | TRA | 94 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1996-12-01 |  | 1998-12-01 | 1999-06-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 |  |  |  | 1999-12-01
FIN | UNEP | Technical sourcebook of methyl bromide alternatives | Individual | GLO | GLO | FUM | 23 | TAS | 150 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1998-11-01 |  | 2001-12-01 | 2002-06-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0
FIN | UNEP | Handbook for NOUs reducing reliance on methyl bromide | Individual | GLO | GLO | FUM | 23 | TAS | 151 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-06-01 | 1998-11-01 |  | 1999-02-01 | 1999-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0
FIN | UNEP | Compilation of legislations for regulatory authorities from Article 5 countries that discourage methyl bromide use and promote alternatives | Individual | GLO | GLO | FUM | 24 | TAS | 155 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 1999-06-01 |  | 1999-12-01 | 1999-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Technical and institutional resources for methyl bromide alternatives projects | Individual | GLO | GLO | FUM | 24 | TAS | 156 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 1998-10-01 |  | 1999-09-01 | 1999-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Methyl bromide information kit | Individual | GLO | GLO | FUM | 24 | TAS | 157 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 1999-03-01 |  | 1998-12-01 | 1999-06-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0
FIN | UNEP | Compilation of case studies on commercial, low-impact methyl bromide alternatives successfully implemented | Individual | GLO | GLO | FUM | 24 | TAS | 160 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 1999-03-01 |  | 2000-09-01 | 2001-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0
FIN | Germany | Travel expenses for participants to attend a regional workshop on methyl bromide alternatives for North African countries (Algeria, Egypt, Jordan, Lebanon, Morocco, Syria, Tunisia) | Individual | GLO | GLO | FUM | 25 | TRA | 161 | N | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-05-01 | 1999-06-01 |  | 1998-06-01 | 1999-07-01 | 33000 | 0 | 33000 | 33000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Compl report submitted Oct 99
FIN | UNEP | Development of training manuals for extension workers | Individual | GLO | GLO | FUM | 27 | TRA | 178 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 2001-10-01 |  | 2001-12-01 | 2003-02-01 | 50000 | -4000 | 46000 | 46000 | 100% | 0 | 0 |  | 6500 | -520 | 5980 | 0 | 0
FIN | UNEP | National farmer's training and establishment of Farmer's Field School (FFS) | Individual | GLO | GLO | FUM | 27 | TRA | 179 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 2001-04-01 |  | 2001-12-01 | 2003-12-01 | 60000 | -4000 | 56000 | 56000 | 100% | 0 | 0 |  | 7800 | -520 | 7280 | 0 | 0
FIN | UNEP | Preparation of how-to crop manual on adopting methyl bromide alternatives for cut flowers | Individual | GLO | GLO | FUM | 29 | TAS | 187 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-07-01 | 2000-11-01 |  | 2001-12-01 | 2002-06-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0
FIN | UNEP | Policy development assistance to prevent future methyl bromide growth in low methyl bromide-consuming countries | Individual | GLO | GLO | FUM | 30 | TAS | 211 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-05-01 | 2001-03-01 |  | 2001-05-01 | 2002-12-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 |  | 26000 | 0 | 26000 | 0 | 0
FIN | Israel | International methyl bromide compliance assistance workshop (Bahamas, Barbados, Bosnia, Congo, Ecuador, Ethiopia, Moldova, Mexico, and Zambia) | Individual | GLO | GLO | FUM | 37 | TRA | 240 | A | D |  | 0 |  | 0 |  | 2002-07-01 |  | 2003-03-01 |  | 2002-12-01 |  | 98300 | -64177 | 34123 | 34123 | 100% | 0 | 0 | 0 | 9830 | -5847 | 3983 | 0 | 0 | The workshop was completed as planned. The goals were achieved and feedback from participants was very positive. The numbers of participants were lower than the maximum potential cited in the proposal. Costs were lower than expected. Two countries, Bahamas and Barbados, did not send participants. Participants from Ethiopia did not arrive due to logistical problems. Please see extended summary for further details of workshop content and outputs. * In addition to estimated disbursement stated, there will be support costs at 10%. |  | 2002 |  | 2002
COM | Israel | International methyl bromide compliance assistance workshop | Individual | GLO | GLO | FUM | 56 | TAS | 296 | A | D |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-02-01 |  | 2008-12-01 |  | 101200 | 0 | 101200 | 32347.25 | 31.96% | 68852.75 | 0 | 0 | 13156 | 0 | 0 | 13156 | 0 | The workshop was fully implemented to the satisfaction of participants and organisers. |  |  |  | 2008
FIN | UNDP | Technical assistance in halons | Individual | GLO | GLO | HAL | 06 | TAS | 10 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-03-01 | 1994-01-01 |  | 1994-06-01 | 1997-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Training and demonstration programmes in halon reduction in the Middle East | Individual | GLO | GLO | HAL | 06 | TRA | 16 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-03-01 | 1993-02-01 |  | 1993-12-01 | 1997-12-01 | 60000 | -20988 | 39012 | 39012 | 100% | 0 | 0 | 0 | 7800 | -2728.44 | 5071.56 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Procurement of 40 halon recycling machines for demonstration | Individual | GLO | GLO | HAL | 07 | DEM | 25 | A | I | HAL | 0 | 0 | 0 | 0 | 1992-06-01 | 1993-09-01 | 1993-07-01 |  | 1993-09-01 | 1997-12-01 | 250000 | 0 | 250000 | 250000 | 100% | 0 | 0 | 0 | 32500 | 0 | 32500 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Global halon project | Individual | GLO | GLO | HAL | 08 | TAS | 27 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1993-03-01 | 1995-10-01 |  | 1997-12-01 | 1999-05-01 | 345133 | 0 | 345133 | 345133 | 100% | 0 | 0 | 0 | 44867.29 | 0 | 44867.29 | 0 | 0 | Completed in 1997. Financially completed in 1999. |  | 1992 |  | Non-Investment
FIN | USA | Regional workshops in halon-1211 training |  | GLO | GLO | HAL | 08 | TRA | 30 | A | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1993-10-01 |  | 1993-10-01 | 1993-10-01 | 429000 | 0 | 429000 | 429000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1992
FIN | UNEP | International halon bank clearing-house function | Individual | GLO | GLO | HAL | 09 | TAS | 37 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1996-05-01 | 1996-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0
FIN | UNEP | Halon bank management information collection and dissemination (1994) | Individual | GLO | GLO | HAL | 12 | TAS | 55 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-05-01 | 1995-03-01 |  | 1995-03-01 | 1995-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Halon bank management case study logbook | Individual | GLO | GLO | HAL | 12 | TAS | 56 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1998-07-01 | 1995-03-01 |  | 2001-10-01 | 2001-10-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 |  |  |  | 1999-03-01
FIN | UNEP | Translate the halon management: banking for the future information kit | Individual | GLO | GLO | HAL | 12 | TAS | 57 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-06-01 | 1995-03-01 |  | 1996-03-01 | 1999-03-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0
FIN | UNDP | Analysis and formulation of a halon action plan and phase out strategy for small consuming countries | Individual | GLO | GLO | HAL | 13 | TAS | 69 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-10-01 | 1995-07-01 |  | 1995-06-01 | 1997-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Non-Investment
FIN | UNEP | Halon bank management query response, information collection and dissemination (1995) | Individual | GLO | GLO | HAL | 16 | TAS | 81 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1995-07-01 |  | 1996-03-01 | 1999-02-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 |  | 4550 | 0 | 4550 | 0 | 0
FIN | UNEP | Meeting of halon bank managers | Individual | GLO | GLO | HAL | 16 | TAS | 84 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-10-01 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Development of a "self-help" guide for small halon-consuming countries | Individual | GLO | GLO | HAL | 16 | TAS | 85 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1998-08-01 | 1996-12-01 |  | 1999-12-01 | 1999-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 |  |  |  | 1999-03-01
FIN | UNEP | Dissemination of the existing halon banking awareness flyer | Individual | GLO | GLO | HAL | 16 | TAS | 86 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 |  | 1995-09-01 |  | 1997-11-01 | 1997-11-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 |  | 0
FIN | UNEP | Provide halon bank management query response, information collection and dissemination | Individual | GLO | GLO | HAL | 19 | TAS | 95 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1996-12-01 |  | 1996-12-01 | 1999-01-01 | 29000 | 0 | 29000 | 29000 | 100% | 0 | 0 |  | 3770 | 0 | 3770 | 0 | 0
FIN | UNEP | Provide international halon bank management information clearinghouse services | Individual | GLO | GLO | HAL | 21 | TAS | 115 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 |  | 11050 | 0 | 11050 | 0 | 0
FIN | UNEP | Provide international halon bank management information clearinghouse services (1998) | Individual | GLO | GLO | HAL | 23 | TAS | 145 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 1999-01-01 | 89000 | 0 | 89000 | 89000 | 100% | 0 | 0 |  | 11570 | 0 | 11570 | 0 | 0
FIN | UNEP | Development of a handbook on standards and codes of good practice for halon sector | Individual | GLO | GLO | HAL | 27 | TAS | 181 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-06-01 | 2000-04-01 |  | 2001-09-01 | 2002-01-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 |  | 9750 | 0 | 9750 | 0 | 0
FIN | UNEP | Study on challenges associated with halon banking in developing countries | Individual | GLO | GLO | HAL | 52 | TAS | 281 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-02-01 | 2008-07-01 |  | 2013-07-01 | 2014-12-01 | 40000 | -4000 | 36000 | 36000 | 100% | 0 | 0 |  | 5200 | -520 | 4680 | 0 | 0
FIN | IBRD | Assessment of CTC phase-out in the chlo-alkali sector | Individual | GLO | GLO | PHA | 52 | TAS | 280 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-07-01 | 2008-09-30 |  | 2008-06-01 | 2008-07-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 9000 | 0 | 9000 | 0 | 0 | Study completed and presented to the 55th ExCom. |  |  |  | Non-INV | 0
CLO | UNIDO | Advance for preparation of HPMPs | Individual | GLO | GLO | PHA | 54 | PRP | 288 | A | I |  | 0 | 0 |  |  | 2008-04-01 |  | 2008-07-01 |  |  | 2008-09-01 | 390000 | -390000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 29250 | -29250 | 0 | 0 | 0 | CLO |  |  |  | NON-INV
CLO | UNDP | Advance for preparation of HPMPs | Individual | GLO | GLO | PHA | 54 | PRP | 289 | A | I | HCFC | 0 | 0 | 0 | 0 | 2008-04-01 |  | 2008-07-01 |  |  | 2008-11-01 | 257000 | -257000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 19275 | -19275 | 0 | 0 | 0 | Canceled in 2008. Financially Completed in 2008. |  | 2008 |  | Investment
CLO | UNEP | Advance for preparation of HPMPs | RMP | GLO | GLO | PHA | 54 | PRP | 290 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 |  | 2008-07-01 |  |  | 2008-12-01 | 408000 | -408000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 53040 | -53040 |  | 0
FIN | UNDP | Technical assistance in MAC | RMP-Component | GLO | GLO | REF | 06 | TAS | 06 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-12-01 | 1994-02-01 |  | 1998-01-01 | 1998-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1998. Financially completed in 1998. |  | 1992 |  | Non-Investment
FIN | UNDP | Technical assistance in refrigeration sector | RMP-Component | GLO | GLO | REF | 06 | TAS | 07 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-01-01 | 1994-02-01 |  | 1994-09-01 | 1997-12-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 | 0 | 11700 | 0 | 11700 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Training and demonstration programme in CFC recycling in MAC in the Middle East | RMP-Component | GLO | GLO | REF | 06 | TRA | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1996-06-01 | 1992-12-01 |  | 1996-06-01 | 1997-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Completed in 1996. Financially completed in 1997. |  | 1992 |  | Non-Investment
TRF | UNDP | Training and demonstration programme in commercial and industrial refrigeration in the Middle East | Individual | GLO | GLO | REF | 06 | TRA | 18 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1993-02-01 |  |  | 1993-06-01 | 40000 | -40000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 5200 | -5200 | 0 | 0 | 0 | Transferred in 1993. Financially Completed in 1993. |  | 1992 |  | Non-Investment
FIN | UNDP | Global MAC project | RMP-Component | GLO | GLO | REF | 08 | TAS | 28 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1994-01-01 | 1995-10-01 |  | 1995-12-01 | 1997-12-01 | 318584 | 0 | 318584 | 318584 | 100% | 0 | 0 | 0 | 41415.92 | 0 | 41415.92 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | IBRD | Global refrigeration project | Individual | GLO | GLO | REF | 08 | TAS | 29 | A | I |  | 0 | 0 | 0 | 0 | 1992-10-01 | 1992-12-31 | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 60000 | -6681 | 53319 | 53319 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The original Global Refrigeration project is completed. The final activity, the preparation of a template for the domestic refrigeration sector utilizing hydrocarbon refrigerant, has been completed. |  |  |  | Non-INV | 0
FIN | UNEP | Preparation of training material for refrigeration sector | Individual | GLO | GLO | REF | 09 | TAS | 41 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-09-01 | 1994-03-01 |  | 1995-03-01 | 1995-12-01 | 160000 | 0 | 160000 | 160000 | 100% | 0 | 0 |  | 20800 | 0 | 20800 | 0 | 0
FIN | UNEP | Training and demonstration programme in commercial/industrial refrigeration in the Middle East | Individual | GLO | GLO | REF | 10 | TRA | 45 | A | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-07-01 | 1994-05-01 |  | 1994-12-01 | 1995-12-01 | 43400 | 0 | 43400 | 43400 | 100% | 0 | 0 |  | 5642 | 0 | 5642 | 0 | 0
FIN | UNIDO | Strategy for phasing out of ODS in low ODS-consuming countries | Individual | GLO | GLO | REF | 11 | TAS | 46 | A | I |  | 0 | 0 |  |  | 1993-11-01 | 1994-09-01 | 1994-11-01 |  | 1996-06-01 | 1998-08-01 | 100000 | -159 | 99841 | 99841 | 100% | 0 | 0 |  | 13000 | -41 | 12959 | 0 | 0 | FIN |  |  |  | NON-INV
CLO | IBRD | Supervision of project implementation (1994) |  | GLO | GLO | REF | 12 | PRP | 65 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1995-03-01 |  |  | 1994-12-01 | 156750 | -156750 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNEP | Compilation of recommendations for a Code of Good Practices in refrigeration in Article 5 countries | Individual | GLO | GLO | REF | 16 | TAS | 87 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1996-07-01 | 1995-09-01 |  | 1998-07-01 | 1999-04-01 | 38000 | 0 | 38000 | 38000 | 100% | 0 | 0 |  | 4940 | 0 | 4940 | 0 | 0
FIN | UNEP | Translation of "Training Manual on Good Practices in Refrigeration" and "Training Manual on Chillers and Refrigerant Management" into Chinese, French and Spanish | Individual | GLO | GLO | REF | 16 | TRA | 73 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-10-01 | 1995-09-01 |  | 1997-12-01 | 1999-04-01 | 264000 | 0 | 264000 | 264000 | 100% | 0 | 0 |  | 34320 | 0 | 34320 | 0 | 0
FIN | UNDP | Global MACs project: Phase 2 | RMP-Component | GLO | GLO | REF | 18 | TAS | 90 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-01-01 | 1997-11-01 |  | 1999-05-01 | 2004-01-01 | 500000 | -1 | 499999 | 499999 | 100% | 0 | 0 | 0 | 65000 | 0 | 65000 | 0 | 0 | Completed in 1999. Financially completed in 2004. |  | 1995 | 1999-07-01 | Non-Investment
FIN | UNEP | Guidelines for the establishment of recovery and recycling systems and related legislation for low volume ODS consuming countries | Individual | GLO | GLO | REF | 19 | TAS | 96 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1997-05-01 |  | 2000-06-01 | 2000-12-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 |  | 7150 | 0 | 7150 | 0 | 0 |  |  |  | 1999-07-01
FIN | UNEP | Training modules for national training courses on good practices in refrigeration | Individual | GLO | GLO | REF | 19 | TRA | 97 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1997-05-01 |  | 2002-05-01 | 2003-06-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 |  |  |  | 2002-06-01
FIN | UNEP | Prepare guidance to assist hotel industry in LVCs to avoid, replace, or eliminate ODS | Individual | GLO | GLO | REF | 19 | TRA | 98 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1997-07-01 | 1996-12-01 |  | 1998-04-01 | 1999-01-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Study on drop-in substitutes for domestic refrigeration | Individual | GLO | GLO | REF | 21 | TAS | 116 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1999-08-01 | 2000-06-01 | 80000 | -21000 | 59000 | 59000 | 100% | 0 | 0 |  | 10400 | -2730 | 7670 | 0 | 0 |  |  |  | 1999-05-01
FIN | UNDP | Preparation of refrigerant management plans (Bahamas, Bangladesh, Botswana, Dominican Republic, El Salvador, Gabon, Mozambique, Niger, Lesotho, Trinidad and Tobago) | Individual | GLO | GLO | REF | 22 | PRP | 133 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-04-01 | 2002-03-01 | 140000 | -2 | 139998 | 139998 | 100% | 0 | 0 | 0 | 18200 | 0 | 18200 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNIDO | Development of Refrigeration Management Plans | Individual | GLO | GLO | REF | 22 | PRP | 134 | A | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-09-01 | 1997-12-01 |  | 2001-04-01 | 2001-09-01 | 60000 | -23740 | 36260 | 36260.31 | 100% | -0.31 | 0 |  | 7800 | -3094 | 4706 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | Switzerland | International workshop on potential for hydrocarbon-based refrigerant as replacements in existing domestic and small commercial refrigeration appliances | Individual | GLO | GLO | REF | 23 | TRA | 137 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1997-12-01 | 1997-12-01 |  | 1997-09-01 | 1997-12-01 | 33900 | 0 | 33900 | 33900 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1997
FIN | Germany | Information video: working safely with hydrocarbons in domestic and small scale commercial refrigeration | Individual | GLO | GLO | REF | 23 | TRA | 138 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-07-01 | 1998-08-01 |  | 2001-01-01 | 2002-12-01 | 322050 | 0 | 322050 | 322050 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completion report submitted Dec 2003
FIN | UNDP | Global MAC project: Phase III | RMP-Component | GLO | GLO | REF | 24 | TAS | 159 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-09-01 | 1999-04-01 |  | 2002-12-01 | 2003-12-01 | 250000 | -63356 | 186644 | 186644 | 100% | 0 | 0 | 0 | 32500 | -8236.28 | 24263.72 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1998 |  | Non-Investment
FIN | Germany | Implementation of RMPs for 14 low volume consuming countries in eastern and southern Africa | RMP | GLO | GLO | REF | 26 | TAS | 172 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2004-11-01 | 2005-09-01 | 815000 | 0 | 815000 | 815000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | All countries completed the activities under this project. PCR is to be submitted
FIN | UNDP | Preparation of 6 projects in the recovery/recycling refrigeration subsector | Individual | GLO | GLO | REF | 30 | PRP | 204 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2003-09-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Preparation of 6 projects in the end-user commercial refrigeration subsector | Individual | GLO | GLO | REF | 30 | PRP | 205 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2003-09-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNEP | Project preparation in the chiller sector | Individual | GLO | GLO | REF | 46 | PRP | 264 | A | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-11-01 | 2005-11-01 |  | 2007-02-01 | 2011-03-01 | 40000 | -8548 | 31452 | 31452 | 100% | 0 | 0 |  | 5200 | -1111.24 | 4088.76 | 0 | 0
FIN | UNIDO | Project preparation in the chiller sector | Individual | GLO | GLO | REF | 46 | PRP | 265 | A | I |  | 0 | 0 |  |  | 2005-07-01 | 2005-08-01 | 2005-11-01 |  | 2006-06-01 | 2007-12-01 | 119000 | -640 | 118360 | 118360.18 | 100% | -0.18 | 0 |  | 8925 | -48 | 8877 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNDP | Project preparation in the chiller sector | Individual | GLO | GLO | REF | 46 | PRP | 266 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-09-01 | 2005-11-01 |  | 2005-12-01 | 2010-10-01 | 122000 | -919.35 | 121080.65 | 121081 | 100% | -0.35 | 0 | 0 | 9150 | -68.95 | 9081.0749 | -0.02495 | 0 | Financially completed in 2010. |  | 2005 |  | Investment
FIN | IBRD | Project preparation in the chiller sector and organization of a workshop |  | GLO | GLO | REF | 46 | PRP | 267 | A | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-11-01 | 2005-11-01 |  | 2005-11-01 | 2005-11-01 | 195000 | 0 | 195000 | 195000 | 100% | 0 | 0 |  | 14625 | 0 | 14625 | 0 | 0 | Chiller Workshop held Sep 05. Findings were used as a basis for development of IA chiller projects, including the Bank's Global Chiller Project. The Global Chiller Project was submitted for ExCom consideration in Nov 05 and US$6.88 million was approved out of the $15 million window. |  |  |  | Non-INV | 0
ONG | IBRD | Global chiller replacement project (China, India, Indonesia, Malaysia and Philippines) | Individual | GLO | GLO | REF | 47 | DEM | 268 | N | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2010-12-01 | 2013-12-01 | 2017-12-01 |  |  | 6884612 | -3630684 | 3253928 | 2058264 | 63.25% | 1195664 | 1195664 | 270000 | 516346 | -272301 | 133810.15 | 110234.85 | 110234.85 | India: Project financially completed and balance of $481,628 returned May 16. Philippines: Project completed 31 Dec 16. A total 38 SGAs signed to replace old chillers with 72 new chillers of which 67 were installed and commissioned. Disbursement made in CY16 is $232,849. Target of 53 chillers was exceeded by 26%. It is expected that combined disbursement of the $3.6 million total MLF and GEF grants will be at 73% upon financial completion; Argentina: During 2016, UEPRO (PCU) signed 2 SGAs for CFC chiller replacements; the first with Fundación Favaloro - Hospital Universitario y de Investigación Médica for two chiller units of 350 TR each, and the second with a consortium of building owners for a chiller unit of 400 TR. One of the 350 TR and the 400 TR chillers was destroyed, after proper capturing the CFC, and replaced in 2016. Replacement of the other 350 TR chiller is postponed to 2017 as the equipment delivery was belated and it was impossible to leave the hospital without sufficient cooling over the summer. SGA execution will be completed in Apr 17. During the Aug 2016 mid-term project review, the WB agreed to a request by Ministry of Production to increase chiller replacement subsidy to 33%, as per the allowable maximum set out in the global chiller project rules. Two SGAs are worth $141,562. Jordan: Project completed. | Philippines: All 72 chillers have been installed and commissioned as planned. Another $21,000 was disbursed under the Philippines Chiller EE Project in Mar 17. Payment of subsidies for all remaining chillers to be completed. Financial completion expected by Apr 17. Implementation completion report (ICR) for the entire MLF/GEF project is under preparation and will be completed by Jun 17. Argentina: During the first months of 2017, UEPRO initiated discussions on 2 further chiller replacements, one of an 800 TR unit. UEPRO is to open a call for chiller replacement proposals in Apr 17. |  |  | Non-INV | 0
FIN | UNEP | Global technical assistance programme in the chiller sector | Individual | GLO | GLO | REF | 48 | TAS | 275 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2010-09-01 | 2009-04-01 |  | 2013-07-01 | 2015-05-01 | 200000 | -111412 | 88588 | 88588 | 100% | 0 | 0 |  | 26000 | -14484.2 | 11515.8 | 0 | 0
COM | UNIDO | Preparation of a demonstration project in the refrigeration assembly sector | Individual | GLO | GLO | REF | 74 | PRP | 327 | A | I |  | 0 | 0 |  |  | 2015-05-01 | 2015-12-01 | 2016-05-29 |  | 2016-12-01 |  | 60000 | 0 | 60000 | 59013.99 | 98.36% | 986.01 | 160.8 | 1 | 4200 | 0 | 0 | 4200 | 11.256 | - Project completed. - Demonstration project approved at the 76th Meeting of the ExCom. |  |  |  | NON-INV
COM | UNIDO | Project preparation for a demonstration project | Individual | GLO | GLO | REF | 74 | PRP | 328 | A | I |  | 0 | 0 |  |  | 2015-05-01 | 2015-07-01 | 2016-05-31 |  | 2016-12-01 |  | 150000 | 0 | 150000 | 138518.22 | 92.35% | 11481.78 | 11669.2 | 11000 | 10500 | 0 | 0 | 10500 | 816.844 | Several field visits were undertaken and with the help of national and international experts, the project was prepared and finalized. Project was submitted to the 76th ExCom Meeting and 2 components were approved (East Africa and the Caribbean). The project was operationally completed. | Project will be financially completed upon clearance of the commitments. |  |  | NON-INV
ONG | UNIDO | Demonstration project on refrigerant quality, containment and introduction of low-global warming potential alternatives (Eastern Africa and Caribbean regions) | Individual | GLO | GLO | REF | 76 | DEM | 333 | A | I |  | 0 | 0 |  |  | 2016-05-01 | 2016-09-01 | 2018-05-31 | 2018-05-31 |  |  | 345000 | 0 | 345000 | 4251 | 1.232% | 340749 | 104895 | 100000 | 24150 | 0 | 298 | 23852 | 7343 | The project was approved in May 2016 at the 76th Meeting of the ExCom with two sub-components: Eastern Africa and Caribbean regions. Eastern Africa: - The project promotes quality refrigerants through standards, training of technicians and awareness raising activities. - PAD issued: Yes - First mission undertaken/working arrangements agreed: Yes - National experts contracted, surveys initiated Caribbean: - The project equips a training center and certify technicians to train on flammables Milestone 1: Inception meeting held Milestone 2: Bids prepared and requested Activities planned but not implemented, reasons and strategy: N/A Actions towards next goals: complete surveys, organize trainings, contract national experts Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | Eastern Africa: - National experts contracted in all the countries - Survey completed on quality of refrigerant available in Tanzania / Uganda and Kenya – advanced / Zambia and Eritrea – pending - ID Pro refrigerant identifiers purchased for all countries in the project, some already delivered - Regional training Tanzania organized for refrigeration technicians/trainers (Tanzania, 20-23 February 2017) - Training organized for the National Ozone Unit of Tanzania, Tanzanian Bureau of Standards (TBS), customs officers, importers, environmental inspectors (Tanzania, 24-25 February 2017) Actions towards next goals: - Tanzanian Bureau of Standards to be contracted for the identification of gaps between imports and actual market of refrigerant - Local trainings to be organized in Eritrea, Kenya, Uganda and Zambia by UN Environment - Awareness raising activities to be carried out by UN Environment Caribbean: Milestone 1: Inception meeting held -Milestone 2: Bids prepared and requested Milestone 3: Contracts awarded Actions towards next goals: - The delivery of equipment is expected in 2nd quarter 2017 Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | NON-INV
ONG | UNEP | Demonstration project on refrigerant quality, containment and introduction of low-global warming potential alternatives (Eastern Africa and Caribbean regions) | Individual | GLO | GLO | REF | 76 | DEM | 334 | A | I |  | 0 |  | 0 |  | 2016-05-01 |  | 2018-05-01 | 2018-05-01 |  |  | 50000 | 0 | 50000 | 0 | 0% | 50000 | 0 | 5000 | 6500 | 0 | 0 | 6500 | 0 | Newly approved project. | Brief progress report (actual/planned): The plan for implementation of the initial stage of the project was developed and discussed with countries and UNIDO. The ___ Legal arrangements (actual/planned): the modality for implementation is still under discussion ___Initial stages of project implementation (actual/planned): __Yes_ Intermediate goals achieved (actual/planned): _No__ Project completion and follow up: _Yes__ First disbursement date (actual/planned): __No ____. All funds disbursed (yes/no): No__ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: __N/A_
ONG | UNIDO | Demonstration project for the introduction of trans-critical CO2 refrigeration technology for supermarkets (Argentina and Tunisia) | Individual | GLO | GLO | REF | 76 | DEM | 335 | A | I |  | 0 | 0 |  |  | 2016-05-01 |  | 2018-11-30 | 2018-11-30 |  |  | 846300 | 0 | 846300 | 0 | 0% | 846300 | 0 | 30000 | 59241 | 0 | 0 | 59241 | 0 | -The project was approved at the 76th Meeting of the ExCom in 2016. - Beneficiaries were selected. - TOR for Argentina finalized and bidding process initiated. - Technical guide on CO2 transcritical prepared and distributed in Tunisia. Milestones achieved: 1- Grant agreement submitted to beneficiary: Ongoing 2- Bids prepared and requested: No 3- Contracts awarded 4- Equipment delivered 5- Commissioning and trial runs 6- De-commissioning and/or destruction of redundant baseline equipment Actions towards next goals: (-) Proceed with bidding process (ToR, selection of supplier and contract award) Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Mission to Tunisia took place to select the supermarket for conversion. - Agreement on TOR was finalized. - Contract awarded for the supply of the system to Argentina. Actions towards next goals: - Award contract for the supply of equipment to Tunisia - Carry out the conversions in both countries Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | NON-INV
FIN | UNEP | Information exchange and technology transfer (1991-1992) | Individual | GLO | GLO | SEV | 04 | TAS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-07-01 | 1992-12-01 |  | 1993-06-01 | 1993-12-01 | 526000 | 0 | 526000 | 526000 | 100% | 0 | 0 |  | 68380 | 0 | 68380 | 0 | 0
FIN | UNEP | Advisory group meeting (1991) | Individual | GLO | GLO | SEV | 04 | TAS | 03 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-07-01 | 1992-06-01 |  | 1992-03-01 | 1992-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0
FIN | IBRD | Administration, coordination, financial, legal (1991) | Individual | GLO | GLO | SEV | 04 | TAS | 04 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 320000 | -34564 | 285436 | 0 | 0 |  |  |  |  | Non-INV | 0
CLO | IBRD | Initial work programme for 1991 | Individual | GLO | GLO | SEV | 04 | TAS | 135 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1991-12-01 |  |  | 1991-12-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 500000 | -500000 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Initial start-up costs | Individual | GLO | GLO | SEV | 04 | TAS | 256 | A | I | CFC | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-09-01 | 1991-12-01 |  | 1992-12-01 | 2004-07-01 | 596500 | 0 | 596500 | 596500 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed in 1992. Financially completed in 2004. |  | 2004 |  | Investment
FIN | UNEP | Regional workshop for Arabic speaking countries | Individual | GLO | GLO | SEV | 04 | TRA | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-08-01 | 1991-12-01 |  | 1991-12-01 | 1992-12-01 | 246000 | -104000 | 142000 | 142000 | 100% | 0 | 0 |  | 31980 | -13520 | 18460 | 0 | 0
FIN | UNEP | OzonAction Information Clearing-house (1992) | Individual | GLO | GLO | SEV | 06 | TAS | 14 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-01 | 1993-02-01 |  | 1993-02-01 | 1993-12-01 | 430000 | 0 | 430000 | 430000 | 100% | 0 | 0 |  | 55900 | 0 | 55900 | 0 | 0
FIN | UNEP | Preparation of technical documents and newsletter | Individual | GLO | GLO | SEV | 06 | TAS | 15 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-04-01 | 1993-02-01 |  | 1993-02-01 | 1993-12-01 | 320000 | 0 | 320000 | 320000 | 100% | 0 | 0 |  | 41600 | 0 | 41600 | 0 | 0
FIN | UNEP | Advisory group meeting (1992) | Individual | GLO | GLO | SEV | 06 | TAS | 21 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-06-01 | 1993-02-01 |  | 1993-03-01 | 1993-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 |  | 4550 | 0 | 4550 | 0 | 0
FIN | UNEP | Travel (1992) | Individual | GLO | GLO | SEV | 06 | TAS | 22 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-01 | 1993-02-01 |  | 1993-02-01 | 1993-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0
FIN | IBRD | Administration, coordination, financial, legal (1992) | Individual | GLO | GLO | SEV | 06 | TAS | 23 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1992-12-01 |  | 1992-12-01 | 1992-12-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 1347550 | -396573 | 950977 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Three national policy workshops | Individual | GLO | GLO | SEV | 06 | TRA | 11 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-10-01 | 1993-10-01 |  | 1996-12-01 | 1997-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Completed in 1996. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Two study-tours for officials and industry representatives | Individual | GLO | GLO | SEV | 06 | TRA | 12 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-10-01 | 1993-10-01 |  | 1998-04-01 | 1998-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1998. Financially completed in 1998. |  | 1992 |  | Non-Investment
FIN | UNDP | Participation at workshops and key metings | Individual | GLO | GLO | SEV | 06 | TRA | 13 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-11-01 | 1993-10-01 |  | 1995-09-01 | 1997-12-01 | 140000 | 0 | 140000 | 140000 | 100% | 0 | 0 | 0 | 18200 | 0 | 18200 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNEP | Support to training activities by UNEP | Individual | GLO | GLO | SEV | 06 | TRA | 20 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-04-01 | 1993-02-01 |  | 1994-03-01 | 1994-12-01 | 365000 | 0 | 365000 | 365000 | 100% | 0 | 0 |  | 47450 | 0 | 47450 | 0 | 0
FIN | Germany | Support to attend the Alternatives to CFC and Halons Technologies and Substances conference | Individual | GLO | GLO | SEV | 07 | TRA | 26 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1992-10-01 | 1992-10-01 |  | 1992-10-01 | 1994-10-01 | 18378 | 0 | 18378 | 18378 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Compl report submitted Oct 99
CLO | IBRD | Preparation of investment projects (1993) |  | GLO | GLO | SEV | 09 | PRP | 38 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 |  | 1995-03-01 |  |  | 1993-12-01 | 455000 | -455000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNEP | Support to networking activities | Individual | GLO | GLO | SEV | 09 | TAS | 33 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-05-01 | 1994-03-01 |  | 1993-12-01 | 1994-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Travel (1993) | Individual | GLO | GLO | SEV | 09 | TAS | 39 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1994-03-01 | 1994-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0
FIN | UNEP | Advisory group meeting (1993) | Individual | GLO | GLO | SEV | 09 | TAS | 40 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-05-01 | 1994-03-01 |  | 1994-03-01 | 1994-12-01 | 110000 | 0 | 110000 | 110000 | 100% | 0 | 0 |  | 14300 | 0 | 14300 | 0 | 0
FIN | UNEP | Information Exchange Clearing-house System (1993) | Individual | GLO | GLO | SEV | 09 | TAS | 42 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1996-06-01 | 1996-07-01 | 705000 | 0 | 705000 | 705000 | 100% | 0 | 0 |  | 91650 | 0 | 91650 | 0 | 0
FIN | IBRD | Administration, coordination, financial, legal and OORG meetings (1993) | Individual | GLO | GLO | SEV | 09 | TAS | 43 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 |  | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 1179000 | -309745 | 869355 | -100 | -100 |  |  |  |  | Non-INV | 0
FIN | UNEP | Support to other national training activities | Individual | GLO | GLO | SEV | 09 | TRA | 35 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1994-03-01 | 1994-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Development of a training strategy | Individual | GLO | GLO | SEV | 09 | TRA | 36 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-06-01 | 1994-03-01 |  | 1995-03-01 | 1995-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0
FIN | UNEP | Updating OAIC diskette and on-line system (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 47 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-06-01 | 1995-03-01 |  | 1995-02-01 | 1995-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0
FIN | UNEP | Outreach at conferences and workshops (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 48 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-07-01 | 1995-03-01 |  | 1995-02-01 | 1995-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Information dissemination (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 49 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-01 | 1995-03-01 |  | 1996-03-01 | 1999-02-01 | 380000 | 0 | 380000 | 380000 | 100% | 0 | 0 |  | 49400 | 0 | 49400 | 0 | 0
FIN | UNEP | Sectoral data collection (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 50 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-03-01 |  | 1997-03-01 | 1999-02-01 | 215000 | 0 | 215000 | 215000 | 100% | 0 | 0 |  | 27950 | 0 | 27950 | 0 | 0
FIN | UNEP | Quality review technology catalogs | Individual | GLO | GLO | SEV | 12 | TAS | 51 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-05-01 | 1994-09-01 |  | 1995-04-01 | 1995-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | IBRD | Administration, coordination, financial, legal and OORG meetings (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 52 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 1418963 | -47607 | 1371356 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNEP | Information papers and fact sheets for evaluation of technical options to replace ODS | Individual | GLO | GLO | SEV | 12 | TAS | 53 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-08-01 | 1995-03-01 |  | 1999-12-01 | 2000-01-01 | 60000 | -3500 | 56500 | 56500 | 100% | 0 | 0 |  | 7800 | -455 | 7345 | 0 | 0 |  |  |  | 1998-12-01
FIN | UNEP | Translation of the "Protecting the Ozone Layer" sectoral technical brochures | Individual | GLO | GLO | SEV | 12 | TAS | 54 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-06-01 | 1995-03-01 |  | 1997-09-01 | 1999-02-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNEP | Informal Advisory Group meeting (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 58 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-01-01 | 1995-03-01 |  | 1996-03-01 | 1999-02-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Ad hoc Group meetings (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 59 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-03-01 |  | 1995-02-01 | 1995-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0
FIN | UNEP | Meeting of the consultants (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 60 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-07-01 | 1995-03-01 |  | 1995-07-01 | 1995-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0
FIN | UNEP | Travel (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 61 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-03-01 |  | 1995-03-01 | 1995-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0
FIN | UNIDO | Joint UNIDO/UNEP preparation of country programmes | Individual | GLO | GLO | SEV | 12 | TAS | 62 | A | I |  | 0 | 0 |  |  | 1994-03-01 | 1994-11-01 | 1995-03-01 |  | 1996-06-01 | 1998-08-01 | 75000 | -3155 | 71845 | 71845 | 100% | 0 | 0 |  | 9750 | -425 | 9325 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNEP | Query-response service (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 67 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-05-01 | 1995-03-01 |  | 1995-02-01 | 1995-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0
FIN | UNEP | OzonAction newsletter and special supplements (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 68 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-05-01 | 1995-03-01 |  | 1995-02-01 | 1995-12-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 |  | 19500 | 0 | 19500 | 0 | 0
FIN | UNEP | Support to national training activities (1994) | Individual | GLO | GLO | SEV | 13 | TRA | 70 | A | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-10-01 | 1995-07-01 |  | 1996-07-01 | 1999-04-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0
FIN | IBRD | Administration, coordination, financial, legal (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 212 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 |  | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 1450646 | 0 | 1450646 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNEP | Update the OAIC diskette version (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 72 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-06-01 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0
FIN | UNEP | Information papers and fact sheets to assist evaluation of technical options to replace ODS (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 74 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-06-01 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0
FIN | UNEP | Develop sector specific videos | Individual | GLO | GLO | SEV | 16 | TAS | 75 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1996-05-01 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 |  | 11700 | 0 | 11700 | 0 | 0
FIN | UNEP | Update Technology Sourcebooks and quality review updated material | Individual | GLO | GLO | SEV | 16 | TAS | 76 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-06-01 | 1996-03-01 |  | 2003-12-01 | 2003-12-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 |  | 11700 | 0 | 11700 | 0 | 0 |  |  |  | 2002-04-01
FIN | UNEP | Disseminate information (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 77 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-04-01 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 |  | 26000 | 0 | 26000 | 0 | 0
FIN | UNEP | Publish the OzonAction newsletter and special supplements (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 78 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-04-01 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 245000 | 0 | 245000 | 245000 | 100% | 0 | 0 |  | 31850 | 0 | 31850 | 0 | 0
FIN | UNEP | Provide direct query-response service (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 79 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 |  | 4550 | 0 | 4550 | 0 | 0
FIN | UNEP | Conduct outreach at conferences and workshops (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 80 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-04-01 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0
FIN | UNEP | Collect sectoral data from worldwide sources (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 82 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-08-01 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 180000 | 0 | 180000 | 180000 | 100% | 0 | 0 |  | 23400 | 0 | 23400 | 0 | 0
FIN | UNEP | Informal advisory group meeting (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 83 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-07-01 | 1996-03-01 |  | 1996-03-01 | 1999-02-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Ad hoc group meetings (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 88 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-07-01 | 1996-03-01 |  | 1997-06-01 | 1999-02-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0
FIN | UNEP | Travel (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 89 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-04-01 | 1996-03-01 |  | 1996-09-01 | 1999-02-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0
FIN | IBRD | OORG workshops and meetings (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 92 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 |  | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 183399 | 0 | 183399 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNEP | Collect sectoral data from worldwide sources | Individual | GLO | GLO | SEV | 19 | TAS | 100 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1996-12-01 |  | 1997-12-01 | 1999-01-01 | 104500 | 0 | 104500 | 104500 | 100% | 0 | 0 |  | 13585 | 0 | 13585 | 0 | 0
FIN | UNEP | Provide direct query-response service (1996) | Individual | GLO | GLO | SEV | 19 | TAS | 101 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1996-12-01 |  | 1996-12-01 | 1999-01-01 | 48000 | 0 | 48000 | 48000 | 100% | 0 | 0 |  | 6240 | 0 | 6240 | 0 | 0
FIN | UNEP | Support to national activities (1996) | Individual | GLO | GLO | SEV | 19 | TAS | 102 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1996-12-01 |  | 1997-05-01 | 1999-02-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Ad hoc Group meetings | Individual | GLO | GLO | SEV | 19 | TAS | 103 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1996-12-01 |  | 1997-06-01 | 1999-01-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Deliver OAIC-DV and other OzonAction Programme information through World Wide Web home page site on a one year trial basis | Individual | GLO | GLO | SEV | 19 | TAS | 104 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1997-05-01 |  | 1997-07-01 | 1999-01-01 | 14500 | 0 | 14500 | 14500 | 100% | 0 | 0 |  | 1885 | 0 | 1885 | 0 | 0
FIN | UNEP | Continue to maintain contact data base of experts and mailing list for OzonAction Programme publications | Individual | GLO | GLO | SEV | 19 | TAS | 105 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1996-12-01 |  | 1997-06-01 | 1999-01-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Prepare an inventory and assessment of environmentally sound and economically viable technologies and know-how conducive to phase out of ODS | Individual | GLO | GLO | SEV | 19 | TAS | 106 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 2000-12-01 | 1996-08-01 |  | 2004-04-01 | 2005-12-01 | 50000 | -27500 | 22500 | 22500 | 100% | 0 | 0 |  | 6500 | -3575 | 2925 | 0 | 0 |  |  |  | 2000-03-01
FIN | UNEP | Travel (1996) | Individual | GLO | GLO | SEV | 19 | TAS | 107 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1997-05-01 |  | 1997-05-01 | 1999-01-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 |  | 9750 | 0 | 9750 | 0 | 0
FIN | UNEP | Publish the OzonAction newsletter and special supplements | Individual | GLO | GLO | SEV | 19 | TAS | 108 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1996-12-01 |  | 1996-12-01 | 1999-01-01 | 245000 | 0 | 245000 | 245000 | 100% | 0 | 0 |  | 31850 | 0 | 31850 | 0 | 0
FIN | UNEP | Conduct outreach at conferences and workshops (1996) | Individual | GLO | GLO | SEV | 19 | TAS | 110 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1996-12-01 |  | 1996-12-01 | 1999-01-01 | 24000 | 0 | 24000 | 24000 | 100% | 0 | 0 |  | 3120 | 0 | 3120 | 0 | 0
CLO | UNEP | Training modules on management of ODS phase out in SMEs | Individual | GLO | GLO | SEV | 19 | TAS | 112 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1999-12-01 | 1996-12-01 |  |  | 2006-12-01 | 40000 | -19000 | 21000 | 21000 | 100% | 0 | 0 | 0 | 5200 | -2470 | 2730 | 0 | 0 |  |  |  | 1999-12-01
FIN | UNEP | Update the OAIC diskette version | Individual | GLO | GLO | SEV | 19 | TAS | 99 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1996-12-01 |  | 1997-04-01 | 1999-01-01 | 28000 | 0 | 28000 | 28000 | 100% | 0 | 0 |  | 3640 | 0 | 3640 | 0 | 0
FIN | UNEP | Prepare information papers and case studies | Individual | GLO | GLO | SEV | 19 | TRA | 109 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1996-12-01 |  | 2001-09-01 | 2001-09-01 | 46000 | 0 | 46000 | 46000 | 100% | 0 | 0 |  | 5980 | 0 | 5980 | 0 | 0 |  |  |  | 1999-03-01
FIN | UNEP | Produce handbook on technology options especially for SMEs | Individual | GLO | GLO | SEV | 19 | TRA | 111 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1996-12-01 |  | 1999-11-01 | 1999-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 |  |  |  | 1999-07-01
FIN | UNEP | Disseminate information | Individual | GLO | GLO | SEV | 19 | TRA | 113 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-05-01 | 1996-12-01 |  | 1999-12-01 | 1999-12-01 | 270000 | 0 | 270000 | 270000 | 100% | 0 | 0 |  | 35100 | 0 | 35100 | 0 | 0 |  |  |  | 1999-12-01
FIN | UNEP | Training modules on policy design and setting up of legislation | Individual | GLO | GLO | SEV | 19 | TRA | 114 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1997-05-01 |  | 1998-07-01 | 1999-04-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0
FIN | IBRD | IFC concessional financing study |  | GLO | GLO | SEV | 21 | PRP | 117 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-31 | 1997-12-31 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNEP | Disseminate awareness materials, technical and policy information | Individual | GLO | GLO | SEV | 21 | TAS | 118 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 340000 | 0 | 340000 | 340000 | 100% | 0 | 0 |  | 44200 | 0 | 44200 | 0 | 0
FIN | UNEP | Provide direct query-response service (1997) | Individual | GLO | GLO | SEV | 21 | TAS | 119 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0
FIN | UNEP | Collect prioritized sectoral data from worldwide sources | Individual | GLO | GLO | SEV | 21 | TAS | 120 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-02-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 107000 | 0 | 107000 | 107000 | 100% | 0 | 0 |  | 13910 | 0 | 13910 | 0 | 0
FIN | UNEP | Publish the OzonAction newsletter and special supplements | Individual | GLO | GLO | SEV | 21 | TAS | 121 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1998-01-01 |  | 1997-12-01 | 1999-01-01 | 335000 | 0 | 335000 | 335000 | 100% | 0 | 0 |  | 43550 | 0 | 43550 | 0 | 0
FIN | UNEP | Advisory and expert group meetings | Individual | GLO | GLO | SEV | 21 | TAS | 122 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-06-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 |  | 9750 | 0 | 9750 | 0 | 0
FIN | UNEP | Conduct outreach at conferences and workshops (1997) | Individual | GLO | GLO | SEV | 21 | TAS | 123 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Travel (1997) | Individual | GLO | GLO | SEV | 21 | TAS | 124 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-06-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 |  | 9750 | 0 | 9750 | 0 | 0
FIN | UNEP | Update the OAIC diskette version including "Simple Search" versions of prioritized OzonAction publications | Individual | GLO | GLO | SEV | 21 | TAS | 125 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1998-07-01 | 1997-12-01 |  | 1998-10-01 | 2000-06-01 | 63000 | -15400 | 47600 | 47600 | 100% | 0 | 0 |  | 8190 | -2002 | 6188 | 0 | 0
FIN | UNEP | Deliver OzonAction newsletter and other information through the World Wide Web home page | Individual | GLO | GLO | SEV | 21 | TAS | 126 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0
FIN | UNEP | Update existing technical brochure series to include 1994/95 TOC data | Individual | GLO | GLO | SEV | 21 | TAS | 127 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 2001-01-01 | 2002-06-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 |  |  |  | 1999-12-01
FIN | UNEP | Develop awareness materials for 1999 freeze to support national initiatives on awareness raising | Individual | GLO | GLO | SEV | 21 | TAS | 128 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-06-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Translate prioritized OzonAction Programme documents into French and Spanish | Individual | GLO | GLO | SEV | 21 | TAS | 129 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-04-01 | 1997-12-01 |  | 1998-12-01 | 1999-08-01 | 40000 | -1191 | 38809 | 38809 | 100% | 0 | 0 |  | 5200 | -154.83 | 5045.17 | 0 | 0
FIN | UNEP | Develop a handbook on the practical use of policy instruments | Individual | GLO | GLO | SEV | 21 | TAS | 130 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1998-11-01 | 1997-12-01 |  | 2003-06-01 | 2005-12-01 | 50000 | -10000 | 40000 | 40000 | 100% | 0 | 0 |  | 6500 | -1300 | 5200 | 0 | 0 |  |  |  | 1999-07-01
FIN | UNEP | Maintain contact data base of experts and mailing list for OzonAction Programme publications | Individual | GLO | GLO | SEV | 21 | TAS | 131 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-01-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNEP | Preparation of refrigerant management plans/country programmes for VLVC/LVC | Individual | GLO | GLO | SEV | 22 | CPG | 132 | A | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-05-01 | 1997-12-01 |  | 2002-03-01 | 2007-01-01 | 200000 | -73040 | 126960 | 126960 | 100% | 0 | 0 |  | 26000 | -9495.2 | 16504.8 | 0 | 0 |  |  |  | 1999-12-01
CLO | IBRD | Advance for project preparation as indicated in the 1998 business plan |  | GLO | GLO | SEV | 23 | PRP | 149 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1998-12-01 |  |  | 1998-12-01 | 275600 | -275600 | 0 | 0 | #DIV/0! | 0 | 0 |  | 35828 | -35828 | 0 | 0 | 0 | The resources allocated for this project were granted to The World Bank as an advance for project preparation for the Year 1998. During the 24th meeting the resources were taken out of the total project prepartion approvals. To indicate this transaction a negative entry with the same ID is created in 24th meeting. |  |  |  | Non-INV | 0
CLO | UNDP | Advance for project preparation as indicated in the 1998 business plan | Individual | GLO | GLO | SEV | 23 | PRP | 154 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1998-03-01 |  |  | 1998-03-01 | 256000 | -256000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 33280 | -33280 | 0 | 0 | 0 | Canceled in 1998. Financially Completed in 1998. |  | 1998 |  | Investment
FIN | UNEP | Maintain contact data base of experts and mailing list for OzonAction Programme publications | Individual | GLO | GLO | SEV | 23 | TAS | 136 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 1999-08-01 | 42000 | 0 | 42000 | 42000 | 100% | 0 | 0 |  | 5460 | 0 | 5460 | 0 | 0
FIN | UNEP | Collect prioritized sectoral data from worldwide sources | Individual | GLO | GLO | SEV | 23 | TAS | 139 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 1999-12-01 | 112000 | 0 | 112000 | 112000 | 100% | 0 | 0 |  | 14560 | 0 | 14560 | 0 | 0
FIN | UNEP | Update the OAIC diskette version (1998) | Individual | GLO | GLO | SEV | 23 | TAS | 140 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1999-12-01 | 2000-01-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 |  | 8580 | 0 | 8580 | 0 | 0
FIN | UNEP | Disseminate awareness materials, technical and policy information | Individual | GLO | GLO | SEV | 23 | TAS | 141 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 1999-12-01 | 340000 | 0 | 340000 | 340000 | 100% | 0 | 0 |  | 44200 | 0 | 44200 | 0 | 0
FIN | UNEP | Provide direct query-response service (1998) | Individual | GLO | GLO | SEV | 23 | TAS | 142 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 1999-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0
FIN | UNEP | Deliver the OzonAction newsletter and other information through World Wide Web home page site | Individual | GLO | GLO | SEV | 23 | TAS | 143 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 1999-06-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0
FIN | UNEP | Advisory and expert group meetings (1998) | Individual | GLO | GLO | SEV | 23 | TAS | 144 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 2000-06-01 | 75000 | -10000 | 65000 | 65000 | 100% | 0 | 0 |  | 9750 | -1300 | 8450 | 0 | 0
FIN | UNEP | Travel (1998) | Individual | GLO | GLO | SEV | 23 | TAS | 146 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 2000-06-01 | 75000 | -2950 | 72050 | 72050 | 100% | 0 | 0 |  | 9750 | -383 | 9367 | 0 | 0
FIN | UNEP | Publish the OzonAction newsletter and special supplements | Individual | GLO | GLO | SEV | 23 | TAS | 147 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 1999-07-01 | 347000 | -1750 | 345250 | 345250 | 100% | 0 | 0 |  | 45110 | -227.5 | 44882.5 | 0 | 0
FIN | UNEP | Conduct outreach at conferences and workshops (1998) | Individual | GLO | GLO | SEV | 23 | TAS | 152 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 1998-12-01 | 1999-06-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Translate and print three guidelines and training modules into Arabic, Chinese, French and Spanish | Individual | GLO | GLO | SEV | 23 | TAS | 153 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1999-07-01 |  | 2002-12-01 | 2003-08-01 | 360000 | 0 | 360000 | 360000 | 100% | 0 | 0 |  | 46800 | 0 | 46800 | 0 | 0
FIN | UNEP | Support to national activities (1998) | Individual | GLO | GLO | SEV | 23 | TRA | 148 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-02-01 | 1998-10-01 |  | 1998-10-01 | 1999-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Data reporting handbook to provide information to Article 5 countries and assist them with their data reporting | Individual | GLO | GLO | SEV | 24 | TAS | 158 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 1999-03-01 |  | 2000-09-01 | 2001-01-01 | 110000 | 0 | 110000 | 110000 | 100% | 0 | 0 |  | 14300 | 0 | 14300 | 0 | 0
FIN | UNIDO | Project preparation advance | Individual | GLO | GLO | SEV | 26 | PRP | 175 | A | I |  | 0 | 0 |  |  | 1998-11-01 |  | 1999-12-01 |  | 1999-12-01 | 2001-02-01 | 169000 | -169000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 21970 | -21970 | 0 | 0 | 0 | FIN
CLO | UNDP | Project preparation advance | Individual | GLO | GLO | SEV | 26 | PRP | 176 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-11-01 |  | 1999-03-01 |  |  | 1999-03-01 | 299000 | -299000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 38870 | -38870 | 0 | 0 | 0 | Canceled in 1999. Financially Completed in 1999. |  | 1998 |  | Investment
FIN | IBRD | Project preparation advance |  | GLO | GLO | SEV | 26 | PRP | 177 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 2000-03-31 | 1999-12-01 |  | 2000-12-01 | 1999-12-01 | 140000 | 0 | 140000 | 140000 | 100% | 0 | 0 |  | 18200 | 0 | 18200 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNEP | Deliver the OzonAction newsletter and other information through world wide web home page site (1999) | Individual | GLO | GLO | SEV | 26 | TAS | 162 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-01-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0
FIN | UNEP | Collect prioritized sectoral data from worldwide sources (1999) | Individual | GLO | GLO | SEV | 26 | TAS | 163 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-01-01 | 112000 | 0 | 112000 | 112000 | 100% | 0 | 0 |  | 14560 | 0 | 14560 | 0 | 0
FIN | UNEP | Provide international halon bank management information clearinghouse services (1999) | Individual | GLO | GLO | SEV | 26 | TAS | 164 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-01-01 | 89000 | 0 | 89000 | 89000 | 100% | 0 | 0 |  | 11570 | 0 | 11570 | 0 | 0
FIN | UNEP | Disseminate awareness materials, technical and policy information (1999) | Individual | GLO | GLO | SEV | 26 | TAS | 165 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-12-01 | 340000 | 0 | 340000 | 340000 | 100% | 0 | 0 |  | 44200 | 0 | 44200 | 0 | 0
FIN | UNEP | Maintain contact data base of experts and mailing list for OzonAction Programme publications | Individual | GLO | GLO | SEV | 26 | TAS | 166 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-12-01 | 42000 | 0 | 42000 | 42000 | 100% | 0 | 0 |  | 5460 | 0 | 5460 | 0 | 0
FIN | UNEP | Update the OAIC diskette version | Individual | GLO | GLO | SEV | 26 | TAS | 167 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-01-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 |  | 8580 | 0 | 8580 | 0 | 0
FIN | UNEP | Provide direct query-response service (1999) | Individual | GLO | GLO | SEV | 26 | TAS | 168 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-01-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0
FIN | UNEP | Advisory and expert group meetings (1999) | Individual | GLO | GLO | SEV | 26 | TAS | 169 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-01-01 | 75000 | -3500 | 71500 | 71500 | 100% | 0 | 0 |  | 9750 | -455 | 9295 | 0 | 0
FIN | UNEP | Conduct outreach at conferences and workshops (1999) | Individual | GLO | GLO | SEV | 26 | TAS | 170 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-01-01 | 55000 | -6300 | 48700 | 48700 | 100% | 0 | 0 |  | 7150 | -819 | 6331 | 0 | 0
FIN | UNEP | Travel (1999) | Individual | GLO | GLO | SEV | 26 | TAS | 171 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-02-01 | 1999-12-01 |  | 1999-12-01 | 2000-12-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 |  | 9750 | 0 | 9750 | 0 | 0
FIN | UNEP | Support to national activities for 1999 | Individual | GLO | GLO | SEV | 26 | TAS | 173 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Publish the OzonAction newsletter and special supplements | Individual | GLO | GLO | SEV | 26 | TAS | 174 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-12-01 | 2000-12-01 | 347000 | 0 | 347000 | 347000 | 100% | 0 | 0 |  | 45110 | 0 | 45110 | 0 | 0
FIN | IBRD | Unallocated project preparation funds |  | GLO | GLO | SEV | 27 | PRP | 185 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-12-31 | 2001-01-01 |  | 2000-12-01 | 2000-12-01 | 162000 | 0 | 162000 | 162000 | 100% | 0 | 0 |  | 21060 | 0 | 21060 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNEP | Develop fact sheet describing win-win technology options relative to Kyoto and Montreal Protocols | Individual | GLO | GLO | SEV | 27 | TAS | 182 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2001-05-01 | 2000-04-01 |  | 2002-12-01 | 2003-01-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Update regulations to control ozone depleting substances | Individual | GLO | GLO | SEV | 27 | TAS | 183 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-12-01 | 2000-08-01 |  | 2001-09-01 | 2001-09-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0
FIN | Canada | Customs training manual | Individual | GLO | GLO | SEV | 27 | TRA | 180 | A | I |  | 0 |  | 0 |  | 1999-03-01 | 2000-02-01 | 2000-04-01 |  | 2001-07-01 | 2002-03-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | English version of manual completed in April 2001. Printing and dissemination has been completed. |  | 1999 |  | Non-Inv.
FIN | Finland | Customs training manual | Individual | GLO | GLO | SEV | 27 | TRA | 184 | A | I |  | 0 |  | 0 |  | 1999-03-01 | 1999-05-01 | 2000-04-01 |  | 2001-11-01 | 2002-02-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed |  | 1999 | 2001-06-01
FIN | UNIDO | Project preparation advance for 2000 | Individual | GLO | GLO | SEV | 29 | PRP | 189 | A | I |  | 0 | 0 |  |  | 1999-11-01 |  | 2000-04-01 |  | 2000-12-01 | 2003-05-01 | 170000 | -170000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 22100 | -22100 | 0 | 0 | 0 | FIN
CLO | UNDP | Project preparation advance for the year 2000 | Individual | GLO | GLO | SEV | 29 | PRP | 190 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-11-01 |  | 2000-04-01 |  |  | 2003-09-01 | 250000 | -250000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 32500 | -32500 | 0 | 0 | 0 | Canceled in 2000. Financially Completed in 2003. |  | 2000 |  | Investment
CLO | IBRD | Project preparation advance for 2000 |  | GLO | GLO | SEV | 29 | PRP | 191 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 |  | 2000-04-01 |  |  | 2000-03-01 | 357450 | -357450 | 0 | 0 | #DIV/0! | 0 | 0 |  | 46468.5 | -46468.5 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNEP | Update the OAIC CD-Rom | Individual | GLO | GLO | SEV | 29 | TAS | 186 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-10-01 | 2000-12-01 |  | 2001-01-01 | 2002-01-01 | 69300 | 0 | 69300 | 69300 | 100% | 0 | 0 |  | 9009 | 0 | 9009 | 0 | 0
FIN | UNEP | Support to national activities (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 188 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2001-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Conduct outreach at conferences and workshops (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 192 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-01-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 |  | 7150 | 0 | 7150 | 0 | 0
FIN | UNEP | Collect prioritized sectoral data from worldwide sources | Individual | GLO | GLO | SEV | 29 | TAS | 193 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-01-01 | 117600 | 0 | 117600 | 117600 | 100% | 0 | 0 |  | 15288 | 0 | 15288 | 0 | 0
FIN | UNEP | Travel (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 194 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-03-01 | 2000-12-01 |  | 2000-12-01 | 2001-12-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 |  | 9750 | 0 | 9750 | 0 | 0
FIN | UNEP | Disseminate awareness materials, technical and policy information (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 195 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-12-01 | 357000 | 0 | 357000 | 357000 | 100% | 0 | 0 |  | 46410 | 0 | 46410 | 0 | 0
FIN | UNEP | Provide international halon bank management information clearinghouse services (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 196 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-01-01 | 93450 | 0 | 93450 | 93450 | 100% | 0 | 0 |  | 12149 | 0 | 12149 | 0 | 0
FIN | UNEP | Provide direct query-response service (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 197 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-01-01 | 84000 | 0 | 84000 | 84000 | 100% | 0 | 0 |  | 10920 | 0 | 10920 | 0 | 0
FIN | UNEP | Complement for translation and printing of four guidelines and training modules into Arabic, Chinese, French and Spanish | Individual | GLO | GLO | SEV | 29 | TAS | 198 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2001-01-01 | 2000-12-01 |  | 2005-04-01 | 2007-07-01 | 120000 | -22000 | 98000 | 98000 | 100% | 0 | 0 |  | 15600 | -2860 | 12740 | 0 | 0 |  |  |  | 2002-12-01
FIN | UNEP | Advisory and expert group meetings (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 199 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-01-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 |  | 9750 | 0 | 9750 | 0 | 0
FIN | UNEP | Publish the OzonAction newsletter and special supplements (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 200 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2001-01-01 | 2002-03-01 | 364000 | 0 | 364000 | 364000 | 100% | 0 | 0 |  | 47320 | 0 | 47320 | 0 | 0
FIN | UNEP | Maintain contact data base of experts and mailing list for OzonAction Programme publications (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 201 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-12-01 | 44000 | 0 | 44000 | 44000 | 100% | 0 | 0 |  | 5720 | 0 | 5720 | 0 | 0
FIN | UNEP | Deliver the OzonAction newsletter and other information through worldwide web home page site (2000) | Individual | GLO | GLO | SEV | 29 | TAS | 202 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2001-01-01 | 26250 | 0 | 26250 | 26250 | 100% | 0 | 0 |  | 3413 | 0 | 3413 | 0 | 0
CLO | IBRD | Project preparation (unallocated) |  | GLO | GLO | SEV | 30 | PRP | 203 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 |  | 2000-12-01 |  |  | 2001-12-01 | 70000 | -70000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 9100 | -9100 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNEP | Organizing a global video competition on ozone layer protection | Individual | GLO | GLO | SEV | 30 | TAS | 206 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-05-01 | 2000-09-01 |  | 2002-11-01 | 2006-01-01 | 60000 | -42676 | 17324 | 17324 | 100% | 0 | 0 |  | 7800 | -5547.92 | 2252.08 | 0 | 0 |  |  |  | 2001-10-01
FIN | UNEP | Translation and printing of OzonAction documents into French, Spanish and Arabic | Individual | GLO | GLO | SEV | 30 | TAS | 207 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-05-01 | 2001-03-01 |  | 2001-12-01 | 2002-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNEP | Adapting existing audiovisual materials to promote control of illegal trade in ODS | Individual | GLO | GLO | SEV | 30 | TAS | 208 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2003-06-01 | 2003-10-01 | 50000 | -2353 | 47647 | 47647 | 100% | 0 | 0 |  | 6500 | -306 | 6194 | 0 | 0
FIN | UNEP | New awareness raising activities and materials for dissemination to the general public | Individual | GLO | GLO | SEV | 30 | TAS | 209 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-02-01 |  | 2001-12-01 | 2002-02-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Develop materials to educate children on ozone layer protection | Individual | GLO | GLO | SEV | 30 | TAS | 210 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-05-01 | 2001-03-01 |  | 2004-07-01 | 2006-02-01 | 100000 | -10448 | 89552 | 89552 | 100% | 0 | 0 |  | 13000 | -1359 | 11641 | 0 | 0 |  |  |  | 2003-07-01
FIN | UNIDO | Project preparation advance (2001) | Individual | GLO | GLO | SEV | 32 | PRP | 216 | A | I |  | 0 | 0 |  |  | 2000-12-01 |  | 2001-12-01 |  | 2001-03-01 | 2001-03-01 | 139500 | -139500 | 0 | 0 | #DIV/0! | 0 | 0 |  | 18135 | -18135 | 0 | 0 | 0 | FIN
CLO | UNDP | Project preparation advance (2001) | Individual | GLO | GLO | SEV | 32 | PRP | 227 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 |  | 2001-12-01 |  |  | 2001-03-01 | 200000 | -200000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 26000 | -26000 | 0 | 0 | 0 | Canceled in 2001. Financially Completed in 2001. |  | 2001 |  | Investment
FIN | Canada | Translation, in French and Spanish, of the approved manual on Customs Officer Training on Substances that Deplete the Ozone Layer | Individual | GLO | GLO | SEV | 32 | TAS | 213 | A | I |  | 0 |  | 0 |  | 2000-12-01 | 2001-04-01 | 2001-07-01 |  | 2002-02-01 | 2002-03-01 | 36000 | 0 | 36000 | 36000 | 100% | 0 |  | 0 | 1440 | 0 | 1440 | 0 |  | Translation of manual into Spanish and French completed in early 2002. Both manuals were printed and disseminated in 2002. Project Completed. |  | 2000 |  | Non-Inv.
FIN | UNEP | Provide international halon bank management information clearinghouse services in 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 214 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2002-01-01 | 76000 | 0 | 76000 | 76000 | 100% | 0 | 0 |  | 9880 | 0 | 9880 | 0 | 0
FIN | UNEP | Travel for 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 215 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2002-12-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 |  | 9750 | 0 | 9750 | 0 | 0
FIN | UNEP | Provide direct query-response service in 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 217 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2003-06-01 | 86000 | 0 | 86000 | 86000 | 100% | 0 | 0 |  | 11180 | 0 | 11180 | 0 | 0
FIN | UNEP | Disseminate awareness material, technical, and policy information in 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 219 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2003-06-01 | 346000 | -13916 | 332084 | 332084 | 100% | 0 | 0 |  | 44980 | -1809.08 | 43170.92 | 0 | 0
FIN | UNEP | Deliver OzonAction Newsletter and other information through world wide web home page site in 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 220 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2002-01-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNEP | Publish the OzonAction newsletter and special supplements in 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 221 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2003-06-01 | 280000 | -5051 | 274949 | 274949 | 100% | 0 | 0 |  | 36400 | -656.63 | 35743.37 | 0 | 0
FIN | UNEP | Advisory and expert group meetings for 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 223 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2003-06-01 | 75000 | -7392 | 67608 | 67608 | 100% | 0 | 0 |  | 9750 | -960.96 | 8789.04 | 0 | 0
FIN | UNEP | Regional awareness raising and South-South assistance | Individual | GLO | GLO | SEV | 32 | TAS | 224 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-10-01 | 2001-12-01 |  | 2004-12-01 | 2006-01-01 | 191000 | -26212 | 164788 | 164788 | 100% | 0 | 0 |  | 24830 | -3408 | 21422 | 0 | 0 |  |  |  | 2003-07-01
FIN | UNEP | Maintain contact database of experts and mailing list for OzonAction programme publications in 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 225 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2002-03-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 |  | 5850 | 0 | 5850 | 0 | 0
FIN | UNEP | Conduct outreach at conferences and workshops in 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 226 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-03-01 | 2001-12-01 |  | 2001-12-01 | 2002-01-01 | 55000 | -5 | 54995 | 54995 | 100% | 0 | 0 |  | 7150 | -1 | 7149 | 0 | 0
FIN | UNEP | Prioritized sectoral data from worldwide sources in 2001 | Individual | GLO | GLO | SEV | 32 | TAS | 228 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2002-01-01 | 121000 | 0 | 121000 | 121000 | 100% | 0 | 0 |  | 15730 | 0 | 15730 | 0 | 0
FIN | UNEP | Global enabling activity for customs training | Individual | GLO | GLO | SEV | 32 | TRA | 218 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2002-01-01 |  | 2002-03-01 | 2003-06-01 | 165400 | -13971 | 151429 | 151429 | 100% | 0 | 0 |  | 21502 | -1816.23 | 19685.77 | 0 | 0
FIN | UNEP | Support to national activities for 2001 | Individual | GLO | GLO | SEV | 32 | TRA | 222 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2003-02-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Preparation of a booklet on data reporting for methyl bromide | Individual | GLO | GLO | SEV | 33 | TAS | 229 | A | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-06-01 | 2001-12-01 |  | 2001-11-01 | 2003-06-01 | 42500 | -2002 | 40498 | 40498 | 100% | 0 | 0 |  | 5525 | -260.26 | 5264.74 | 0 | 0
FIN | UNEP | Study on development of ODS phase-out strategy for SMEs | Individual | GLO | GLO | SEV | 34 | TAS | 230 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2004-09-01 | 2002-12-01 |  | 2005-12-01 | 2009-09-01 | 100000 | -10000 | 90000 | 90000 | 100% | 0 | 0 |  | 13000 | -1300 | 11700 | 0 | 0
FIN | UNEP | Global public awareness and education campaign to sustain the phase out (first tranche) | Individual | GLO | GLO | SEV | 34 | TAS | 231 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2002-08-01 |  | 2003-01-01 | 2003-01-01 | 60000 | -11755 | 48245 | 48245 | 100% | 0 | 0 |  | 7800 | -1528.15 | 6271.85 | 0 | 0
CLO | UNEP | Development of tracking system for ODS and ODS-based equipment | Individual | GLO | GLO | SEV | 34 | TAS | 232 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 |  | 2002-12-01 |  |  | 2005-03-01 | 40000 | -40000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 5200 | -5200 |  | 0
FIN | UNIDO | Project preparation advance | Individual | GLO | GLO | SEV | 35 | PRP | 234 | A | I |  | 0 | 0 |  |  | 2001-12-01 |  | 2002-03-01 |  | 2002-03-01 | 2002-03-01 | 176250 | -176250 | 0 | 0 | #DIV/0! | 0 | 0 |  | 22913 | -22913 | 0 | 0 | 0 | FIN |  |  |  | INV
CLO | IBRD | Project preparation advance (2002) |  | GLO | GLO | SEV | 35 | PRP | 235 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 |  | 2002-03-01 |  |  | 2001-12-01 | 180000 | -180000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 23400 | -23400 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
CLO | UNDP | Project preparation advance (2002) | Individual | GLO | GLO | SEV | 35 | PRP | 236 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-12-01 |  | 2002-03-01 |  |  | 2002-03-01 | 200000 | -200000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 26000 | -26000 | 0 | 0 | 0 | Canceled in 2002. Financially Completed in 2002. |  | 2002 |  | Investment
FIN | UNEP | Compliance Assistance Programme: 2002 budget | Individual | GLO | GLO | SEV | 35 | TAS | 237 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-01-01 | 2002-12-01 |  | 2002-12-01 | 2005-01-01 | 5351450 | -1500591.3 | 3850858.7 | 3850858.7 | 100% | 0 | 0 |  | 428116 | -120046.9 | 308069.1 | 0 | 0
FIN | Japan | Workshop on concessional lending | Individual | GLO | GLO | SEV | 35 | TRA | 233 | A | I |  | 0 |  | 0 |  | 2001-12-01 | 2002-06-01 | 2002-12-01 |  | 2003-03-01 | 2006-07-01 | 75000 | -17294 | 57706 | 57706 | 100% | 0 | 0 | 0 | 9750 | -2248 | 7502 | 0 | 0 | Project financially completed in July 2006. |  | 2001
FIN | IBRD | Unallocated project preparation |  | GLO | GLO | SEV | 36 | PRP | 239 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 |  | 2003-04-01 |  | 2002-12-01 | 2002-12-01 | 180000 | -180000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 23400 | -23400 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNEP | Translation of OzonAction publications into other UN languages | Individual | GLO | GLO | SEV | 36 | TAS | 238 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-09-01 | 2002-11-01 |  | 2006-11-01 | 2007-12-01 | 93000 | -34067 | 58933 | 58933 | 100% | 0 | 0 |  | 12090 | -4429 | 7661 | 0 | 0 |  |  |  | 2004-07-01
FIN | UNEP | Assistance for regional awareness raising | Individual | GLO | GLO | SEV | 37 | TAS | 241 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-08-01 | 2003-08-01 |  | 2005-12-01 | 2006-01-01 | 200000 | -33111 | 166889 | 166889 | 100% | 0 | 0 |  | 26000 | -4304 | 21696 | 0 | 0 |  |  |  | 2004-12-01
FIN | UNEP | Compliance Assistance Programme: 2003 budget | Individual | GLO | GLO | SEV | 38 | TAS | 242 | A | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-01-01 | 2003-12-01 |  | 2003-12-01 | 2005-07-01 | 5830885 | -466383 | 5364502 | 5364502 | 100% | 0 | 0 |  | 466471 | -37310.84 | 429160.16 | 0 | 0
FIN | UNDP | Core Unit Support (2003) | Individual | GLO | GLO | SEV | 38 | TAS | 243 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2002-11-01 |  | 2003-12-01 |  | 2003-12-01 | 2007-01-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 1500000 | 0 | 1500000 | 0 | 0 | Completed in 2003. Financially completed in 2007. |  | 2002 |  | Non-Investment
FIN | UNIDO | Core unit (2003) | Individual | GLO | GLO | SEV | 38 | TAS | 244 | A | I |  | 0 | 0 |  |  | 2002-11-01 |  | 2003-12-01 |  | 2003-12-01 | 2003-12-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 1500000 | 0 | 1500000 | 0 | 0 | FIN
FIN | IBRD | Core unit (2003) |  | GLO | GLO | SEV | 38 | TAS | 245 | A | I |  | 0 | 0 | 0 | 0 | 2002-11-01 |  | 2003-12-01 |  | 2003-12-01 | 2003-12-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 1500000 | 0 | 1500000 | 0 | 0 | Core unit activities included support/travel of core staff; annual FI workshop and OORG meeting; attendance at ExCom and interagency mtgs; 15th MOP and UNEP regional meetings; and publication of MP case study and flyer. |  |  |  | Non-INV | 0
FIN | UNEP | Assistance for regional awareness raising | Individual | GLO | GLO | SEV | 39 | TAS | 247 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2004-02-01 | 2004-04-01 |  | 2006-04-01 | 2007-12-01 | 200000 | -77956 | 122044 | 122044 | 100% | 0 | 0 |  | 26000 | -10134 | 15866 | 0 | 0
FIN | UNEP | Production of OzonAction Newsletter in Russian, translation of 4 refrigeration/customs training modules into Russian, and reprinting and updating existing publications | Individual | GLO | GLO | SEV | 39 | TAS | 248 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-03-01 |  | 2008-05-01 | 2009-05-01 | 75000 | -8215 | 66785 | 66785 | 100% | 0 | 0 |  | 9750 | -1067.95 | 8682.05 | 0 | 0 |  |  |  | 2005-09-01
FIN | UNDP | Core Unit Support (2004) | Individual | GLO | GLO | SEV | 41 | TAS | 249 | N | I | No-ODP | 0 | 0 | 0 | 0 | 2003-12-01 |  | 2004-12-01 |  | 2004-12-01 | 2007-01-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 1500000 | 0 | 1500000 | 0 | 0 | Completed in 2004. Financially completed in 2007. |  | 2003 |  | Non-Investment
FIN | UNIDO | Core unit (2004) | Individual | GLO | GLO | SEV | 41 | TAS | 250 | A | I |  | 0 | 0 |  |  | 2003-12-01 |  | 2004-12-01 |  | 2004-12-01 | 2004-12-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 1500000 | 0 | 1500000 | 0 | 0 | FIN
FIN | IBRD | Core unit (2004) |  | GLO | GLO | SEV | 41 | TAS | 251 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 |  | 2004-12-01 |  | 2004-12-01 | 2004-12-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 1500000 | 0 | 1500000 | 0 | 0 | Core unit activities included travel to MP-related meetings; support of core unit staff; hosting of three MP events and development of select knowledge material. |  |  |  | Non-INV | 0
FIN | UNEP | Compliance Assistance Programme: 2004 budget | Individual | GLO | GLO | SEV | 41 | TAS | 252 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-01-01 | 2004-12-01 |  | 2004-12-01 | 2006-12-01 | 6757900 | -190217 | 6567683 | 6567683 | 100% | 0 | 0 |  | 540632 | -15218 | 525414 | 0 | 0
FIN | Sweden | Development of handbook on industry operated systems for recovery and reuse of ozone depleting substances | Individual | GLO | GLO | SEV | 41 | TAS | 253 | A | I |  | 0 |  | 0 |  | 2003-12-01 | 2004-11-01 | 2004-10-01 |  | 2006-02-01 | 2006-12-01 | 33874 | 0 | 33874 | 33874 | 100% | 0 | 0 | 0 | 4404 | 0 | 4404 | 0 | 0 | At the 41st meeting of the Executive Committee, the Government of Sweden in collaboration with the Government of Japan received approval for developing a Handbook related to the servicing sector. A Draft outline of the Handbook with a broader perspective in accordance with the ExCom decision was developed in March 04. Two consultants were recruited and a first full Draft was developed in Feb. 2005. The Draft was revised substantially twice before the text was sent for a review by UNEP/DTIE, Japan and the NOUs of Croatia and the Philippines in June 2005. Responses were received in Aug-Sept 2005. After taking into account the comments received, the layout and printing was organised. The printed version was received in February 2006 and the distribution to all NOUs and relevant agencies was organised by UNEP. The Handbook is available at the UNEP and SEI web pages for down load. |  | 2003
FIN | Japan | Development of handbook on industry operated systems for recovery and reuse of ozone depleting substances | Individual | GLO | GLO | SEV | 41 | TAS | 254 | A | I |  | 0 |  | 0 |  | 2003-12-01 | 2004-11-01 | 2004-12-01 |  | 2004-11-01 | 2004-11-01 | 33874 | 0 | 33874 | 33874 | 100% | 0 | 0 | 0 | 4404 | 0 | 4404 | 0 | 0 | PCR is expected to be submitted by Sweden Government in early autumn 2007. |  | 2003
FIN | UNEP | Assistance for regional awareness raising | Individual | GLO | GLO | SEV | 42 | TAS | 255 | A | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2005-04-01 |  | 2006-04-01 | 2009-12-01 | 200000 | -32056 | 167944 | 167944 | 100% | 0 | 0 |  | 26000 | -4166.94 | 21833.06 | 0 | 0
FIN | UNIDO | Core unit budget for 2005 | Individual | GLO | GLO | SEV | 44 | TAS | 258 | A | I |  | 0 | 0 |  |  | 2004-12-01 |  | 2005-12-01 |  | 2005-12-01 | 2005-12-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 1500000 | 0 | 1500000 | 0 | 0 | FIN
FIN | UNDP | Core unit (2005) | Individual | GLO | GLO | SEV | 44 | TAS | 259 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2005-12-01 |  | 2005-12-01 | 2007-01-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 1500000 | 0 | 1500000 | 0 | 0 | Completed in 2005. Financially completed in 2007. |  | 2004 |  | Non-Investment
FIN | UNEP | Compliance Assistance Programme: 2005 budget | Individual | GLO | GLO | SEV | 44 | TAS | 260 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-01-01 | 2005-12-01 |  | 2005-12-01 | 2008-12-01 | 7157544 | -304536 | 6853008 | 6853008 | 100% | 0 | 0 |  | 572604 | -24362.84 | 548241.16 | 0 | 0
FIN | IBRD | Core unit (2005) |  | GLO | GLO | SEV | 44 | TAS | 261 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2005-12-01 |  | 2005-12-01 | 2005-12-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 1500000 | 0 | 1500000 | 0 | 0 | Core unit activities included travel to MP-related meetings; support of core unit staff; hosting of two MP events and completion of reports and responses. |  |  |  | Non-INV | 0
FIN | UNEP | Assistance for regional awareness raising (2005) | Individual | GLO | GLO | SEV | 45 | TAS | 262 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-11-01 | 2006-04-01 |  | 2008-12-01 | 2012-11-01 | 200000 | -60190 | 139810 | 139810 | 100% | 0 | 0 |  | 26000 | -7824.7 | 18175.3 | 0 | 0
FIN | UNEP | Development of effective awareness materials | Individual | GLO | GLO | SEV | 45 | TAS | 263 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-07-01 | 2006-04-01 |  | 2006-01-01 | 2007-12-01 | 120000 | -13267 | 106733 | 106733 | 100% | 0 | 0 |  | 15600 | -1725 | 13875 | 0 | 0
COM | Portugal | Communication and cooperation support to Portuguese speaking countries (Angola, Cape Verde, East Timor, Guinea Bissau, Mozambique and Sao Tome and Principe) | Individual | GLO | GLO | SEV | 47 | TAS | 269 | A | I |  | 0 |  | 0 |  | 2005-11-01 |  | 2007-12-01 |  | 2011-07-01 |  | 90000 | 0 | 90000 | 47743 | 53.05% | 42257 | 31324 | 10933 | 11700 | 0 | 0 | 11700 | 0 | The education pack for primary schools were distributed to all Portuguese-speaking African countries in March 2011, The OzonAction Education pack for Secondary Schools will be translated and it will be distributed electronically in June 2011.
FIN | UNEP | Compliance Assistance Programme: 2006 budget | Individual | GLO | GLO | SEV | 47 | TAS | 270 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-02-01 | 2006-12-01 |  | 2006-12-01 | 2009-04-01 | 7770000 | -364599 | 7405401 | 7405401 | 100% | 0 | 0 |  | 621600 | -29167.44 | 592432.56 | 0 | 0
FIN | UNDP | Core unit budget (2006) | Individual | GLO | GLO | SEV | 47 | TAS | 271 | N | I | No-ODP | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2006-12-01 |  | 2006-12-01 | 2007-01-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 1700000 | 0 | 1700000 | 0 | 0 | Completed in 2006. Financially completed in 2007. |  | 2005 |  | Non-Investment
FIN | UNIDO | Core unit budget (2006) | Individual | GLO | GLO | SEV | 47 | TAS | 272 | A | I |  | 0 | 0 |  |  | 2005-11-01 |  | 2006-12-01 |  | 2006-12-01 | 2006-12-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 1700000 | 0 | 1700000 | 0 | 0 | FIN
FIN | IBRD | Core unit budget (2006) |  | GLO | GLO | SEV | 47 | TAS | 273 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2006-12-01 |  | 2006-12-01 | 2006-12-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 1500000 | 0 | 1500000 | 0 | 0 | Core unit activities included travel to ExCom, MP and UNEP regional meetings; support of core unit staff; hosting of two MP events and completion of reports and responses. |  |  |  | Non-INV | 0
FIN | UNEP | Updating the customs training manual | Individual | GLO | GLO | SEV | 48 | TRA | 274 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2006-12-01 | 2007-04-01 |  | 2008-08-01 | 2009-08-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0
FIN | UNEP | Compliance Assistance Programme: 2007 budget | Individual | GLO | GLO | SEV | 50 | TAS | 276 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-01-01 | 2007-12-01 |  | 2007-12-01 | 2009-12-01 | 8003000 | -409308 | 7593692 | 7593692 | 100% | 0 | 0 |  | 640240 | -32744.64 | 607495.36 | 0 | 0
FIN | UNIDO | Core unit budget (2007) | Individual | GLO | GLO | SEV | 50 | TAS | 277 | A | I |  | 0 | 0 |  |  | 2006-11-01 |  | 2007-11-01 |  | 2007-12-01 | 2007-12-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 1751000 | 0 | 1751000 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNDP | Core unit budget (2007) | Individual | GLO | GLO | SEV | 50 | TAS | 278 | N | I | CFC | 0 | 0 | 0 | 0 | 2006-11-01 |  | 2007-11-01 |  | 2007-12-01 | 2013-08-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 1751000 | 0 | 1751000 | 0 | 0 | Financially completed in 2013. |  | 2006 |  | Non-Investment
FIN | IBRD | Core unit budget (2007) |  | GLO | GLO | SEV | 50 | TAS | 279 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 |  | 2007-11-01 |  | 2007-11-01 | 2007-11-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 1580000 | -17251 | 1562749 | 0 | 0 | Core unit activities included travel to ExCom, MP and UNEP regional meetings; support of core unit staff; hosting of one MP event and completion of reports and responses. Two pamphlets completed for the 20th MP Anniversary. |  |  |  | Non-INV | 0
FIN | UNEP | Integrated enforcement training under the Montreal Protocol through green customs initiative | Individual | GLO | GLO | SEV | 52 | TAS | 283 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2009-09-01 | 2010-06-01 |  | 2010-12-01 | 2012-07-01 | 62000 | 0 | 62000 | 62000 | 100% | 0 | 0 |  | 8060 | 0 | 8060 | 0 | 0
FIN | UNEP | Compliance Assistance Programme: 2008 budget | Individual | GLO | GLO | SEV | 53 | TAS | 284 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-01-01 | 2008-12-01 |  | 2008-12-01 | 2009-12-01 | 8243090 | 0 | 8243090 | 8243090 | 100% | 0 | 0 |  | 659447 | 0 | 659447 | 0 | 0
FIN | UNDP | Core unit budget (2008) | Individual | GLO | GLO | SEV | 53 | TAS | 285 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2007-11-01 |  | 2008-11-01 |  | 2008-12-01 | 2013-08-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 1803530 | 0 | 1803530 | 0 | 0 | Financially completed in 2013. |  | 2007 |  | Non-Investment
FIN | IBRD | Core unit budget (2008) |  | GLO | GLO | SEV | 53 | TAS | 286 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 |  | 2008-11-30 |  | 2008-11-01 | 2008-11-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 1614900 | -360069 | 1254831 | 0 | 0 | Activities included travel to MP-related meetings; support of core unit staff; hosting the MP annual workshop for FIs and staff; reconvening the OORG (with 2 meetings held in 2008); an analytical piece on HCFC and related side-event; commissioning of a "foam decision tree," for HCFC alternatives; completion of reports and responses and providing required data and information needed for preparing ExCom documentation. |  |  |  | Non-INV | 0
FIN | UNIDO | Core unit budget (2008) | Individual | GLO | GLO | SEV | 53 | TAS | 287 | A | I |  | 0 | 0 |  |  | 2007-11-01 |  | 2008-11-01 |  | 2008-12-01 | 2008-12-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 1803530 | 0 | 1803530 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNEP | Compliance Assistance Programme: 2009 budget | Individual | GLO | GLO | SEV | 56 | TAS | 292 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-01-01 | 2009-12-01 |  | 2009-12-01 | 2011-02-01 | 8490000 | -3520.35 | 8486479.65 | 8486479.65 | 100% | 0 | 0 |  | 679200 | -281.6 | 678918.4 | 0 | 0
FIN | UNIDO | Core unit budget (2009) | Individual | GLO | GLO | SEV | 56 | TAS | 293 | A | I |  | 0 | 0 |  |  | 2008-11-01 |  | 2009-12-31 |  | 2009-12-01 | 2009-12-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 1857636 | 0 | 1857636 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | IBRD | Core unit budget (2009) |  | GLO | GLO | SEV | 56 | TAS | 294 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-12-31 |  | 2009-12-01 | 2009-12-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 1663347 | -204863 | 1458484 | 0 | 0 | Activities included travel to MP-related meetings; support of core unit staff; hosting the 13th annual workshop for FIs and staff as well as the new OORG meeting; strategic business development; completion of draft foam decision-tree report; and providing required monitoring, data collection and information for ExCom reporting. |  |  |  | Non-INV | 0
FIN | UNDP | Core unit budget (2009) | Individual | GLO | GLO | SEV | 56 | TAS | 295 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-12-01 |  | 2009-12-01 | 2013-03-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 1857636 | 0 | 1857636 | 0 | 0 | Financially completed in 2013. |  | 2008 |  | Non-Investment
FIN | IBRD | Core unit budget (2010) |  | GLO | GLO | SEV | 59 | TAS | 298 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 |  | 2010-12-01 |  | 2010-12-01 | 2010-12-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 1701466 | -390706 | 1310760 | 0 | 0 | Activities included travel to MP-related meetings; support of core unit staff; hosting of the 14th annual workshop for FIs and staff, the 5th new OORG meeting and two technology roundtable meetings; strategic business development and completion of reports and responses and providing any required data and information needed for preparing ExCom documentation. |  |  |  | Non-INV | 0
FIN | UNEP | Compliance Assistance Programme: 2010 budget | Individual | GLO | GLO | SEV | 59 | TAS | 299 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-01-01 | 2010-12-01 |  | 2010-12-01 | 2013-12-01 | 8745000 | -169753 | 8575247 | 8575247 | 100% | 0 | 0 |  | 699600 | -13580.24 | 686019.76 | 0 | 0
FIN | UNIDO | Core unit budget (2010) | Individual | GLO | GLO | SEV | 59 | TAS | 300 | A | I |  | 0 | 0 |  |  | 2009-11-01 |  | 2010-12-31 |  | 2010-12-01 | 2010-12-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 1913365 | 0 | 1913365 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNDP | Core unit budget (2010) | Individual | GLO | GLO | SEV | 59 | TAS | 301 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2009-11-01 |  | 2010-12-01 |  | 2010-12-01 | 2013-12-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 1913365 | 0 | 1913365 | 0 | 0 | Financially completed in 2013. |  | 2009 |  | Non-Investment
FIN | Japan | Training on alternative technologies to HCFCs | Individual | GLO | GLO | SEV | 59 | TRA | 297 | A | I |  | 0 |  | 0 |  | 2009-11-01 | 2010-03-01 | 2010-05-01 |  | 2011-03-01 | 2013-12-01 | 141750 | -335 | 141415 | 141415 | 100% | 0 | 0 | 0 | 18428 | -44 | 18384 | 0 | 0 | Financial completion in Dec 2013. Refund was reported to 71st ExCom, Dec 2013. FIN. |  | 2009 |  | Non-Investment
FIN | UNEP | Compliance Assistance Programme: 2011 budget | Individual | GLO | GLO | SEV | 62 | TAS | 302 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-01-01 | 2011-12-01 |  | 2011-12-01 | 2013-12-01 | 9007000 | -585999 | 8421001 | 8421001 | 100% | 0 | 0 |  | 720560 | -46879.92 | 673680.08 | 0 | 0
FIN | UNIDO | Core unit budget (2011) | Individual | GLO | GLO | SEV | 62 | TAS | 303 | A | I |  | 0 | 0 |  |  | 2010-12-01 |  | 2011-12-31 |  | 2011-12-01 | 2011-12-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 1970766 | 0 | 1970766 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNDP | Core unit budget (2011) | Individual | GLO | GLO | SEV | 62 | TAS | 304 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2010-12-01 |  | 2011-12-01 |  | 2011-12-01 | 2013-07-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 1970766 | 0 | 1970766 | 0 | 0 | Financially completed in 2013. |  | 2010 |  | Non-Investment
FIN | IBRD | Core unit budget (2011) |  | GLO | GLO | SEV | 62 | TAS | 305 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 |  | 2011-12-31 |  | 2011-12-01 | 2012-06-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 1713000 | -390685 | 1322315 | 0 | 0 | Activities included travel to MP-related meetings; support of core unit staff; hosting of the 15th annual workshop for FIs and staff and the 6th new OORG meeting; and coordination of WB-MP activities, completion of reports and responses and providing info |  |  |  | Non-INV | 0
FIN | UNDP | Resource mobilization to maximize climate co-benefits | Individual | GLO | GLO | SEV | 63 | TAS | 306 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-04-01 | 2012-03-01 |  | 2013-12-01 | 2014-06-01 | 200000 | -135101 | 64899 | 64899 | 100% | 0 | 0 | 0 | 18000 | -12159 | 5841 | 0 | 0 | Financially completed in 2014. | Completed in 2013. | 2011 |  | Non-Investment
FIN | UNIDO | Mobilizing co-financing for Multilateral Fund funded projects based on the "Monetization" of their climate benefits | Individual | GLO | GLO | SEV | 63 | TAS | 307 | A | I |  | 0 | 0 |  |  | 2011-04-01 | 2011-12-01 | 2012-09-30 |  | 2014-12-23 | 2016-03-01 | 200000 | -728 | 199272 | 199271.99 | 100% | 0.01 | 0 |  | 18000 | -66 | 17934 | 0 | 0 | The project was financially completed and the balance was returned at the 76th ExCom. |  |  |  | NON-INV
COM | UNEP | Resource mobilization to address climate co-benefits for HCFC phase-out in low-volume-consuming countries with servicing sector only, in cooperation with other agencies | Individual | GLO | GLO | SEV | 63 | TAS | 308 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2013-04-01 | 2013-03-01 |  | 2014-12-01 |  | 100000 | 0 | 100000 | 77968 | 77.97% | 22032 | 0 | 22032 | 13000 | 0 | 10135.84 | 2864.16 | 0 | Project financially completed | Project financially completed. PCR submitted. |  | 2014-12-01
FIN | IBRD | Resource mobilization for HCFC phase-out co-benefits study |  | GLO | GLO | SEV | 63 | TAS | 309 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2012-12-01 | 2012-03-31 |  | 2013-12-01 | 2014-11-01 | 180000 | -61165.34 | 118834.66 | 118834.66 | 100% | 0 | 0 |  | 16200 | -5505 | 10695.12 | -0.12 | -0.12 | Study completed. |  |  |  | Non-INV | 0
FIN | UNDP | Core unit budget (2012) | Individual | GLO | GLO | SEV | 65 | TAS | 310 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2011-11-01 |  | 2012-12-01 |  | 2012-12-01 | 2013-03-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 1984561 | 0 | 1984561 | 0 | 0 | Financially completed in 2013. |  | 2011 |  | Non-investment
FIN | UNIDO | Core unit budget (2012) | Individual | GLO | GLO | SEV | 65 | TAS | 311 | A | I |  | 0 | 0 |  |  | 2011-11-01 |  | 2012-12-31 |  | 2012-12-01 | 2012-12-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 1984561 | 0 | 1984561 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | IBRD | Core unit budget (2012) |  | GLO | GLO | SEV | 65 | TAS | 312 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 |  | 2012-12-31 |  | 2012-12-01 | 2013-05-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 1724644 | -3981 | 1720663 | 0 | 0 | Activities included travel to MP-related meetings; support of core unit staff; holding a 7th new OORG meeting; hosting a regional ODS workshop for countries and WB staff as well as ozone day celebrations for the 25th MP anniversary, incl. a roundtable discussion and technology fair; and, coordination of WB-MP activities, completion of reports and responses and providing information needed for preparing ExCom reports. |  |  |  | Non-INV | 0
COM | UNEP | Compliance Assistance Programme: 2012 budget | Individual | GLO | GLO | SEV | 65 | TAS | 313 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-01-01 | 2012-12-01 |  | 2012-12-01 |  | 8987000 | -452976.38 | 8534023.62 | 8534023.62 | 100% | 0 | 0 | 0 | 718960 | -36237.75 | 682722.25 | 0 | 0
FIN | UNEP | Development of a guide for sustainable refrigerated facilities and systems, in cooperation with the American Society of Heating, Refrigeration and Air Conditioning Engineers (ASHRAE) | Individual | GLO | GLO | SEV | 66 | TAS | 314 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 |  | 2014-04-01 |  | 2014-12-01 | 2014-12-01 | 200000 | -200000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 26000 | -26000 |  | 0 |  | Project financially completed. PCR submitted. | Project financially completed. PCR submitted.
COM | UNEP | Compliance Assistance Programme: 2013 budget | Individual | GLO | GLO | SEV | 68 | TAS | 315 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-01-01 | 2013-12-01 |  | 2013-12-01 |  | 9158000 | -1030264 | 8127736 | 8107735.9958 | 99.75% | 20000.0042 | 20000.0042 |  | 732640 | -82421.12 | 648618.8797 | 1600.0003 | 1600.0003
FIN | UNDP | Core unit budget (2013) | Individual | GLO | GLO | SEV | 68 | TAS | 316 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2013-12-01 |  | 2013-12-01 | 2013-12-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 1998453 | 0 | 1998453 | 0 | 0 | Financially completed in 2013. |  | 2012 |  | Non-investment
FIN | UNIDO | Core unit budget (2013) | Individual | GLO | GLO | SEV | 68 | TAS | 317 | A | I |  | 0 | 0 |  |  | 2012-12-01 |  | 2013-12-31 |  | 2013-12-01 | 2013-12-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 1998453 | 0 | 1998453 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | IBRD | Core unit budget (2013) |  | GLO | GLO | SEV | 68 | TAS | 318 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2013-12-31 |  | 2013-12-01 | 2014-11-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 1725000 | -414405 | 1310595 | 0 | 0 | Activities included travel to MP-related meetings including ozone officer network meetings; support of core unit staff; internal liaison and coordination on MP matters and policy; a regional MP workshop for clients and project teams; strategic business development and completion of reports and responses and providing data and information needed for preparing ExCom documentation. |  |  |  | Non-INV | 0
FIN | UNIDO | Core unit budget (2014) | Individual | GLO | GLO | SEV | 71 | TAS | 319 | A | I |  | 0 | 0 |  |  | 2013-12-01 |  | 2014-12-31 |  | 2014-12-01 | 2014-12-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 2012442 | 0 | 2012442 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | IBRD | Core unit budget (2014) |  | GLO | GLO | SEV | 71 | TAS | 320 | A | I |  | 0 | 0 | 0 | 0 | 2013-12-01 |  | 2014-12-31 |  | 2014-12-01 | 2015-11-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 1725000 | -341953 | 1383047 | 0 | 0 | Activities included travel to MP-related meetings including 4 network meetings; support of core unit staff; internal liaison and coordination on MP matters and policy; hosting an MP workshop in Jun 14; strategic business development and completion of reports and responses and providing any required data and information needed for preparing ExCom documentation. Balance of $ returned to the 75th ExCom. |  |  |  | Non-INV | 0
COM | UNEP | Compliance Assistance Programme: 2014 budget | Individual | GLO | GLO | SEV | 71 | TAS | 321 | A | I |  | 0 | 0 | 0 | 0 | 2013-12-01 | 2014-01-01 | 2014-12-01 |  | 2015-12-01 |  | 9338000 | -1519371.62 | 7818628.38 | 7603596.9312 | 97.25% | 215031.4488 | 215031.4488 | 215031 | 747040 | -121549.73 | 608287.7541 | 17202.5159 | 17202.5159
FIN | UNDP | Core unit budget (2014) | Individual | GLO | GLO | SEV | 71 | TAS | 322 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2013-12-01 |  | 2014-12-01 |  | 2014-12-01 | 2016-02-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 2012442 | 0 | 2012442 | 0 | 0 | Financially completed in 2016. |  | 2013 |  | Non-Investment
ONG | UNEP | Compliance Assistance Programme: 2015 budget | Individual | GLO | GLO | SEV | 73 | TAS | 323 | A | I |  | 0 | 0 | 0 | 0 | 2014-11-01 | 2015-01-01 | 2015-12-01 | 2016-12-01 |  |  | 9459000 | 0 | 9459000 | 7105110.85 | 75.11% | 2353889.15 | 512758.6425 | 235388.915 | 756720 | 0 | 568408.868 | 188311.132 | 41020.6914 | [6 empty] | 12 months delays
FIN | UNDP | Core unit budget (2015) | Individual | GLO | GLO | SEV | 73 | TAS | 324 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-11-01 |  | 2015-12-01 |  | 2015-12-01 | 2016-12-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 2026529 | 0 | 2026529 | 0 | 0 | Financially completed in 2016. |  | 2014 |  | Non-Investment
FIN | UNIDO | Core unit budget (2015) | Individual | GLO | GLO | SEV | 73 | TAS | 325 | A | I |  | 0 | 0 |  |  | 2014-11-01 |  | 2015-12-31 |  | 2015-12-01 | 2015-12-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 2026529 | 0 | 2026529 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | IBRD | Core unit budget (2015) |  | GLO | GLO | SEV | 73 | TAS | 326 | A | I |  | 0 | 0 | 0 | 0 | 2014-11-01 |  | 2015-12-31 |  | 2015-12-01 | 2016-12-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 1725000 | -411441 | 1313559 | 0 | 0 | Completed. A savings of $411,441 was returned to the 77th ExCom Meeting. |  |  |  | Non-INV | 0
ONG | UNEP | Compliance Assistance Programme: 2016 budget | Individual | GLO | GLO | SEV | 75 | TAS | 329 | A | I |  | 0 | 0 | 0 | 0 | 2015-11-01 | 2016-01-01 | 2016-12-01 | 2017-12-01 |  |  | 9540000 | 0 | 9540000 | 7214826.75 | 75.63% | 2325173.25 | 800495.64 | 232517.325 | 763200 | 0 | 577186.14 | 186013.86 | 64039.6512
FIN | UNIDO | Core unit budget (2016) | Individual | GLO | GLO | SEV | 75 | TAS | 330 | A | I |  | 0 | 0 |  |  | 2015-11-01 |  | 2016-12-01 |  | 2016-12-01 | 2016-12-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 2040715 | 0 | 2040715 | 0 | 0 | Core unit functionalities are being undertaken, next report will be submitted to the 77th ExCom Meeting. |  |  |  | NON-INV
COM | UNDP | Core unit budget (2016) | Individual | GLO | GLO | SEV | 75 | TAS | 331 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2015-11-01 |  | 2016-12-01 |  | 2016-12-30 |  | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 2040715 | 0 | 2040715 | 0 | 0 | Will be financially completed in 2017. |  | 2015 |  | Non-Investment
COM | IBRD | Core unit budget (2016) |  | GLO | GLO | SEV | 75 | TAS | 332 | A | I |  | 0 | 0 | 0 | 0 | 2015-11-01 |  | 2016-12-31 | 13.2 | 2016-12-01 |  | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 1725000 | 0 | 1725000 | 0 | 0 | Activities included travel to MP-related meetings (76-77th ExCom Meetings,37th/38th OEWG, ExMOP and 28th MP Meetings, IA coordination meetings in Feb/Mar/Sep, ozone network meetings, E. Asia regional workshop for WB clients and project teams); managed submissions and reporting; supported core unit staff; internal liaison and coordination on MP matters and policy; internal knowledge work; hosted an MP workshop in Dec 16; and completed reports and responses and provided required data and information needed for ExCom documentation. | Financial completion expected in the first half of 2017. |  |  | Non-INV | 0
ONG | UNEP | Compliance Assistance Programme: 2017 budget | Individual | GLO | GLO | SEV | 77 | TAS | 336 | A | I |  | 0 | 0 | 0 | 0 | 2016-12-01 |  | 2017-12-01 | 2017-12-01 |  |  | 9776000 | 0 | 9776000 | 0 | 0% | 9776000 | 0 | 8500000 | 782080 | 0 | 0 | 782080 | 0
ONG | IBRD | Core unit budget (2017) |  | GLO | GLO | SEV | 77 | TAS | 337 | A | I |  | 0 | 0 | 0 | 0 | 2016-12-01 |  | 2017-12-31 | 2017-12-31 |  |  | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 1725000 | 0 | 0 | 1725000 | 1725000 | Activities to include travel to MP-related meetings; support of core unit staff; internal liaison and coordination on MP matters and policy; internal knowledge work; hosting an MP workshop; strategic business development and completion of reports and responses and providing any required data and information needed for preparing ExCom documentation. | Core unit attended the first 2017 interagency coordination meeting in Feb, managed submissions (to the 79th Meeting) and collected data for the 2016 progress report and project completion reports, and hosted an E. Asia regional workshop in Feb-Mar 17 for WB clients and project teams. Core unit continued to develop new internal MP operations platform as a resource to MP project managers. |  |  | Non-INV | 0
ONG | UNIDO | Core unit budget (2017) | Individual | GLO | GLO | SEV | 77 | TAS | 338 | A | I |  | 0 | 0 |  |  | 2016-11-01 |  | 2017-12-31 | 2017-12-01 |  |  | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 2055000 | 0 | 0 | 2055000 | 0 | It was approved at the 77th ExCom Meeting in 2016. |  |  |  | NON-INV
ONG | UNDP | Core unit budget (2017) | Individual | GLO | GLO | SEV | 77 | TAS | 339 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2016-12-01 |  | 2017-12-01 | 2017-12-01 |  |  | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 2055000 | 0 | 0 | 2055000 | 0 | Newly Approved |  | 2016 |  | Non-Investment
FIN | UNDP | Technical assistance in solvents | Individual | GLO | GLO | SOL | 06 | TAS | 09 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-06-01 | 1993-07-01 |  | 1993-09-01 | 1997-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | IBRD | Global solvent project |  | GLO | GLO | SOL | 08 | PRP | 31 | A | I |  | 0 | 0 | 0 | 0 | 1992-10-01 | 1992-12-31 | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 260000 | 21754 | 281754 | 281754 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | This activity is completed Final report to be issued shortly. |  |  |  | Non-INV | 0
CLO | IBRD | Supervision of project implementation (1994) |  | GLO | GLO | SOL | 12 | PRP | 64 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1995-03-01 |  |  | 1994-12-01 | 156750 | -156750 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | LAC | GRN | PHA | 49 | INV | 10 | N | I | CFC | 0 | 0 | 0 | 0 | 2006-07-01 | 2009-05-01 | 2007-12-01 |  | 2009-07-01 | 2013-02-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 3600 | 0 | 3600 | 0 | 0 | Financially completed in 2013. |  | 2006 |  | Investment
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-year | LAC | GRN | PHA | 49 | TAS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-01-01 | 2007-12-01 |  | 2010-12-01 | 2011-12-01 | 37000 | 0 | 37000 | 37000 | 100% | 0 | 0 |  | 4810 | 0 | 4810 | 0 | 0
FIN | UNDP | Terminal phase-out management plan (second tranche) | Multi-year | LAC | GRN | PHA | 55 | INV | 14 | N | I | CFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-05-01 | 2010-07-01 |  | 2009-12-01 | 2013-09-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 4500 | 0 | 4500 | 0 | 0 | Financially completed in 2013. |  | 2008 |  | Investment
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | GRN | PHA | 55 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2010-04-01 | 2009-07-01 |  | 2013-06-01 | 2013-06-01 | 85000 | -2650 | 82350 | 82350 | 100% | 0 | 0 |  | 11050 | -344.5 | 10705.5 | 0 | 0
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | LAC | GRN | PHA | 55 | TAS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-11-01 | 2009-07-01 |  | 2010-12-01 | 2011-12-01 | 48000 | 0 | 48000 | 48000 | 100% | 0 | 0 |  | 6240 | 0 | 6240 | 0 | 0
FIN | UNDP | Terminal phase-out management plan (third tranche) | Multi-Year | LAC | GRN | PHA | 59 | INV | 16 | N | I | CFC | 3 | 3 | 0 | 0 | 2009-11-01 | 2011-04-01 | 2011-11-01 |  | 2011-11-01 | 2014-05-01 | 30000 | -663 | 29337 | 29337 | 100% | 0 | 0 | 0 | 2700 | -59.67 | 2640.33 | 0 | 0 | Financially completed in 2014. | Completed in 2011. Equipment to support CFC phase-out procured and delivered to beneficiaries. | 2009 |  | Investment
FIN | UNEP | Terminal phase-out management plan (third tranche) | Multi-Year | LAC | GRN | PHA | 59 | TAS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-08-01 | 2011-11-01 |  | 2013-12-01 | 2013-12-01 | 32500 | -8528 | 23972 | 23972 | 100% | 0 | 0 |  | 4225 | -1108.64 | 3116.36 | 0 | 0
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | GRN | PHA | 62 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-06-01 | 2013-12-01 | 2018-07-01 |  |  | 105000 | 0 | 105000 | 52071.54 | 49.59% | 52928.46 | 52928 | 5292.846 | 13650 | 0 | 6769.3002 | 6880.6998 | 6880.64 | Brief progress report (actual/planned): Following some challenges described in 2015 progress, SSFA for remaining Tranche 1 balance signed 12 Jul 2016. 55 Customs Trainees trained in the Monitoring and Control of Trade in ODS. Training of 77 new technicians. Development of draft Standards for the Labeling of refrigerant containers. ___ Legal arrangements(actual/planned): New SSFA signed Jul-16. ___ First mission (actual/planned): Planned for first half of 2017.___ TOR completed(actual/planned): ___ First disbursement date (actual/planned): done___ All funds disbursed (yes/no): No. ___ Any delay? (yes/no): ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no):No. ___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): NOU held meetings with the Bureau of Standards to discuss the finalization of Standards for labelling of refrigerant containers and draft standards for use, storage, transportation and handling of refrigerants including flammable refrigerants. NOU held meetings with the TA Marryshow Community College and the National Training Agency to discuss integration of ODS alternatives and good refrigeration practices into their curricula (Caribbean Vocational Qualification (CVQ) for the National Training Agency). NOU also held discussions with GRENCASE (an NGO) with a view of partnering with them under the training component. ___ Legal arrangements(actual/planned):SSFA signed Jul-16. ___ First mission (actual/planned):planned for first half of 2017. ___ TOR completed(actual/planned): ___ First disbursement date (actual/planned): done___ All funds disbursed (yes/no): No. ___ Any delay? (yes/no): ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): No. ___ If Yes, is any action required by ExCom: ___ |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor the transfer of investment to non investment activities.
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | GRN | PHA | 77 | INV | 23 | A | I | HCFC | 0.1 | 0 |  |  | 2016-11-01 |  | 2020-12-31 | 2020-12-31 |  |  | 75000 | 0 | 75000 | 0 | 0% | 75000 | 0 | 10000 | 6750 | 0 | 0 | 6750 | 0 | Approved on the understanding that if Grenada were to decide to proceed with retrofits and associated servicing to flammable and toxic refrigerants in refrigeration and air-conditioning equipment originally designed for non flammable substances, it would do so assuming all associated responsibilities and risks and only in accordance with the relevant standards and protocols. Noted that UNIDO had been added as a cooperating agency for the implementation of the second tranche of stage I of the HPMP; that the Agreement between the Government and the Executive Committee had been updated based on the established HCFC baseline for compliance and the revised starting point, and the inclusion of UNIDO as cooperating agency; that the revised starting point for sustained aggregate reduction in HCFC consumption was 0.58 ODP tonnes, estimated based on the historical consumption; that the revised funding level for stage I of the HPMP for Grenada was US $164,500, plus agency support costs, in accordance with decision 60/44(f)(xii); and that the deduction of US $45,500 would be applied when stage II of the HPMP was approved. '- -Milestone 1: Bids prepared and requested | Approved on the understanding that if Grenada were to decide to proceed with retrofits and associated servicing to flammable and toxic refrigerants in refrigeration and air-conditioning equipment originally designed for non flammable substances, it would do so assuming all associated responsibilities and risks and only in accordance with the relevant standards and protocols. Noted that UNIDO had been added as a cooperating agency for the implementation of the second tranche of stage I of the HPMP; that the Agreement between the Government and the Executive Committee had been updated based on the established HCFC baseline for compliance and the revised starting point, and the inclusion of UNIDO as cooperating agency; that the revised starting point for sustained aggregate reduction in HCFC consumption was 0.58 ODP tonnes, estimated based on the historical consumption; that the revised funding level for stage I of the HPMP for Grenada was US $164,500, plus agency support costs, in accordance with decision 60/44(f)(xii); and that the deduction of US $45,500 would be applied when stage II of the HPMP was approved. '-Milestone 1: Bids prepared and requested - Milestone 2: Contracts awarded - Delivery of equipment expected in 2nd quarter 2017
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | GRN | PHA | 77 | TAS | 22 | A | I |  | 0.2 |  | 0 |  | 2016-12-01 |  | 2020-12-01 | 2020-12-01 |  |  | 9000 | 0 | 9000 | 0 | 0% | 9000 | 0 | 900 | 1170 | 0 | 0 | 1170 | 0 | Newly approved project | Funds to be programmed for later 2017 depending on level of disbursement with HPMP Tranche 1 and in consultation with Country.
FIN | UNDP | Implementation of the RMP: National recovery recycling project | RMP-Component | LAC | GRN | REF | 30 | TAS | 05 | A | I | CFC | 1.4 | 1.4 | 0 | 0 | 2000-03-01 | 2002-06-01 | 2001-10-01 |  | 2002-12-01 | 2003-11-01 | 33400 | 0 | 33400 | 33400 | 100% | 0 | 0 | 0 | 4342 | 0 | 4342 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNEP | Implementation of the RMP: train the trainer programme for refrigeration service technicians | Individual | LAC | GRN | REF | 30 | TRA | 03 | A | I | CFC | 2.2 | 2.2 | 0 | 0 | 2000-03-01 | 2000-12-01 | 2000-10-01 |  | 2007-01-01 | 2008-12-01 | 52000 | 0 | 52000 | 52000 | 100% | 0 | 0 |  | 6760 | 0 | 6760 | 0 | 0 |  |  |  | 2002-06-01
FIN | UNEP | Implementation of the RMP: training of custom officers, ODS inspectorate and Ozone Unit staff | Individual | LAC | GRN | REF | 30 | TRA | 04 | A | I | CFC | 1.5 | 1.5 | 0 | 0 | 2000-03-01 | 2000-12-01 | 2001-10-01 |  | 2007-01-01 | 2009-12-01 | 36700 | -13787 | 22913 | 22913 | 100% | 0 | 0 |  | 4771 | -1792.31 | 2978.69 | 0 | 0 |  |  |  | 2002-12-01
FIN | UNEP | Preparation of refrigerant management plan update | RMP update | LAC | GRN | REF | 46 | PRP | 08 | A | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-12-01 | 2006-07-01 |  | 2006-09-01 | 2009-12-01 | 15000 | -337 | 14663 | 14663 | 100% | 0 | 0 |  | 1950 | -43.81 | 1906.19 | 0 | 0
FIN | UNEP | Country programme preparation | Individual | LAC | GRN | SEV | 21 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1998-08-01 |  | 1999-10-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 |  |  |  | 1999-12-01
FIN | UNEP | Creation of a National Ozone Unit | Individual | LAC | GRN | SEV | 30 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2003-06-01 | 2003-04-01 |  | 2006-08-01 | 2014-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Institutional strengthening project | Individual | LAC | GRN | SEV | 44 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2006-06-01 | 2005-12-01 |  | 2007-12-01 | 2008-12-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase II) | Individual | LAC | GRN | SEV | 50 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-07-01 | 2008-11-01 |  | 2010-06-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | LAC | GRN | SEV | 60 | INS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-09-01 | 2011-12-01 |  | 2013-12-01 | 2013-12-01 | 52500 | 0 | 52500 | 52500 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of the institutional strengthening project (phase IV: 8/2012-7/2014) | Individual | LAC | GRN | SEV | 67 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2013-08-01 | 2014-07-01 |  | 2015-08-01 |  | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. All funds are disbursed. The country needs to send the final expenditure report. | Project completed. All funds are disbursed. The country needs to send the final expenditure report.
ONG | UNEP | Extension of the institutional strengthening project (phase V: 1/2016-12/2017) | Individual | LAC | GRN | SEV | 75 | INS | 21 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-07-01 | 2017-12-01 | 2018-08-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 85000 | 8500 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Ozone Day 2016 celebrated which included a donation of Tools and Equipment to the Boca Secondary School and seminars at schools. Training under the HPMP also delivered during the Ozone Day Celebrations. NOU participated in Caribbean Thematic Meeting in Dec-16. Country hosted an inception workshop for the UNIDO sub-regional Regional Demonstration Project on Safe Handling of low GWP Refrigerants 31 Aug to 1 Sep-16. Monitored and issued of pre-approval certificates for the e-licensing system to import refrigerants. Country Co-chaired the OWEG38 and resumed meetings. ___ Legal arrangements(actual/planned): SSFA signed May-16. ___Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): Jul-16.___ All funds disbursed (yes/no): No. ___ Any delay?(yes/no): No.___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): No.___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): 2016 Article 7 and CP data collection and verification underway. Country hosting a workshop for technicians through UNIDO's sub-regional Demonstration Project on the Safe Handling of low GWP Refrigerants to ODS in April/May-17. ___ Legal arrangements(actual/planned): SSFA signed May-16. ___Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): Jul-16.___ All funds disbursed (yes/no): No. ___ Any delay?(yes/no): No.___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): No.___ If Yes, is any action required by ExCom: ___
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | LAC | GRN | SEV | 75 | TAS | 20 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-06-01 | 2016-12-01 | 2017-05-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 40000 | 4000 | 5200 | 0 | 0 | 5200 | 5200 | Brief progress report (actual/planned): National Consultant identified. Country experiencing difficulties with gettiing the contract for consultant signed as there were 2 changes in Permanant Secretaries during the last half of 2016 prohibiting signing off on the contract. Counry pariticipated in Thematic Network Meeting on ODS Alternatives Surveys in Barbados, Dec-16.___ Legal arrangements(actual/planned):The SSFA was drafted and signed by UNEP and the Government of Grenada on May 2016. ___Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: follow-up on final recruitment of consultant and survey report due 31 Dec-16.___ First disbursement date (actual/planned): Jun-16.___ All funds disbursed (yes/no): No. ___ Any delay?(yes/no): ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): No. ___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): Country reported another change in Permanant Secretary. NOU to present full programme of activities to new adminstration and gain contract signature. NOU indicated committment to completing the survey submitting the report in the shortest time possible. ___ Legal arrangements(actual/planned):SSFA signed May-16. ___Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: follow-up on final recruitment of consultant and survey report.___ First disbursement date (actual/planned): Jun-16.___ All funds disbursed (yes/no): No. ___ Any delay?(yes/no): ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): No. ___ If Yes, is any action required by ExCom: ___
FIN | UNDP | Project preparation in the foam sector | Individual | LAC | GUA | FOA | 21 | PRP | 11 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 1999-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1997 |  | Investment
FIN | UNDP | Terminal umbrella project: Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at Construservicios, Aplitex, and Fiberglas & Plasticos | Individual | LAC | GUA | FOA | 23 | INV | 17 | A | I | CFC | 12.6 | 12.6 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 1999-11-01 | 2003-05-01 | 128500 | -15778 | 112722 | 112722 | 100% | 0 | 0 | 0 | 16705 | -2051.14 | 14653.86 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNIDO | Preparation for HCFC phase-out investment activities (foam sector) | Individual | LAC | GUA | FOA | 60 | PRP | 40 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-10-01 | 2011-04-30 |  | 2012-03-01 | 2013-04-01 | 60000 | -364 | 59636 | 59635.53 | 100% | 0.47 | 0 |  | 4500 | -27 | 4473 | 0 | 0 | FIN
FIN | UNIDO | Project formulation of demonstraton project in the methyl bromide sector | Individual | LAC | GUA | FUM | 21 | PRP | 12 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-03-01 | 1997-08-01 |  | 1999-01-01 | 2001-07-01 | 7140 | -558 | 6582 | 6582 | 100% | 0 | 0 |  | 928 | -74 | 854 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNIDO | Demonstration project: four alternatives to the use of methyl bromide: steam pasteurization, non-soil cultivation, solarization, and low-dose chemicals in combination with an IPM system | Individual | LAC | GUA | FUM | 22 | DEM | 15 | A | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-09-01 | 1999-06-01 |  | 1999-12-01 | 2001-07-01 | 440000 | -57777 | 382223 | 382222.67 | 100% | 0.33 | 0 |  | 57200 | -7590 | 49610 | 0 | 0 | FIN
FIN | UNIDO | Project preparation for the phase out of 800 tonnes in the methyl bromide sector (melon) | Individual | LAC | GUA | FUM | 29 | PRP | 21 | A | I |  | 0 | 0 |  |  | 1999-11-01 | 2002-04-01 | 2000-12-01 |  | 2002-12-01 | 2003-12-01 | 45000 | -1164 | 43836 | 43836.4 | 100% | -0.4 | 0 |  | 5850 | -160 | 5690 | 0 | 0 | FIN
FIN | UNIDO | National phase out of methyl bromide | Individual | LAC | GUA | FUM | 38 | INV | 29 | A | I | MBR | 502.6 | 502.6 |  |  | 2002-11-01 | 2003-03-01 | 2008-11-01 |  | 2008-12-01 | 2011-08-01 | 3257377 | 0 | 3257377 | 3257376.85 | 100% | 0.15 | 0 |  | 368311 | 0 | 368311 | 0 | 0 | FIN |  |  |  | INV
COM | UNIDO | National phase-out of methyl bromide (phase II, first tranche) | Multi-Year | LAC | GUA | FUM | 59 | INV | 38 | A | I | MBR | 48 | 48 |  |  | 2009-11-01 | 2010-12-01 | 2013-11-30 |  | 2015-12-01 |  | 1300000 | -210000 | 1090000 | 1089705.53 | 99.97% | 294.47 | 0 | 1 | 97500 | -15750 | 81728 | 22 | 0 | The project was operationally completed. |  |  |  | INV
FIN | UNEP | National phase-out of methyl bromide (phase II, first tranche) | Multi-Year | LAC | GUA | FUM | 59 | TAS | 39 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 |  | 2013-11-01 |  | 2014-12-01 | 2014-12-01 | 70000 | -70000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 9100 | -9100 |  | 0
ONG | UNIDO | National phase-out of methyl bromide (phase II, second tranche) | Multi-Year | LAC | GUA | FUM | 68 | INV | 46 | A | I | MBR | 217.7 | 217.7 |  |  | 2012-12-01 | 2013-07-01 | 2014-12-31 | 2018-03-31 |  |  | 943047 | 0 | 943047 | 725539.78 | 76.94% | 217507.22 | 3809.91 | 140000 | 70729 | 0 | 54415 | 16314 | 285.7432 | - Order delivered in March 2016 and all the equipment transferred to the respective beneficiaries. - Installation of the cultivation units for pre-grafted plants was carried out in September 2016. - The training programme and the plan to guarantee the sustainability of alternatives were rediscussed with the new authorities. (Elections took place end 2015.) - Reason for the delay: The installation of the equipment was delayed due to the civil work to be done by the beneficiary. - Slight impact on the project completion date. - No recurring problem - No action required by Executive Committee | - Based on the discussions with the authorities, UNIDO is supporting national training and education institute to sustain the use of methyl bromide alternatives in the country. - No delay - No recurring problem - No impact on project completion date - No action required by Executive Committee |  |  | INV
FIN | UNDP | Project preparation for a terminal phase-out management plan | Individual | LAC | GUA | PHA | 50 | PRP | 31 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-03-01 | 2007-11-01 |  | 2008-11-01 | 2009-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1125 | 0 | 1125 | 0 | 0 | Completed in 2008. Financially completed in 2009. |  | 2006 |  | Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | LAC | GUA | PHA | 50 | PRP | 32 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-11-01 | 2007-11-01 |  | 2009-12-01 | 2010-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0
FIN | UNDP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | GUA | PHA | 56 | INV | 35 | N | I | CFC | 5.9 | 5.9 | 0 | 0 | 2008-11-01 | 2011-04-01 | 2010-11-01 |  | 2013-12-01 | 2014-02-01 | 249000 | -43768.05 | 205231.95 | 205232 | 100% | -0.05 | 0 | 0 | 22410 | -3939.12 | 18470.88 | 0 | 0 | Financially completed in 2014. | Completed in 2013. Project team is preparing the PCR and the financial closure of the project. | 2008 |  | Investment
FIN | UNEP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | GUA | PHA | 56 | TAS | 34 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-07-01 | 2008-11-01 |  | 2012-12-01 | 2013-12-01 | 33000 | 0 | 33000 | 33000 | 100% | 0 | 0 |  | 4290 | 0 | 4290 | 0 | 0
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | LAC | GUA | PHA | 57 | PRP | 36 | A | I |  | 0 | 0 |  |  | 2009-04-01 | 2009-07-01 | 2010-03-31 |  | 2012-03-01 | 2013-04-01 | 75000 | -1370 | 73630 | 73630.11 | 100% | -0.11 | 0 |  | 5625 | -103 | 5522 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | GUA | PHA | 57 | PRP | 37 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-11-01 | 2010-03-01 |  | 2013-12-01 | 2013-12-01 | 75000 | -49373 | 25627 | 25627 | 100% | 0 | 0 |  | 9750 | -6418.49 | 3331.51 | 0 | 0
FIN | UNIDO | HCFC phase-out management plan (foam sector) (stage I, first tranche) | Multi-Year | LAC | GUA | PHA | 64 | INV | 43 | A | I | HCFC | 1.7 | 1.7 |  |  | 2011-07-01 | 2012-10-01 | 2013-07-31 |  | 2013-07-01 | 2014-07-01 | 109637 | -348 | 109289 | 109289.01 | 100% | -0.01 | 0 |  | 8223 | -26 | 8197 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | GUA | PHA | 64 | INV | 44 | A | I |  | 0 | 0 |  |  | 2011-07-01 | 2012-06-01 | 2013-07-31 |  | 2013-07-01 | 2014-07-01 | 8450 | -18 | 8432 | 8431.63 | 100% | 0.37 | 0 |  | 634 | -1 | 632 | 1 | 0 | FIN |  |  |  | INV
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | LAC | GUA | PHA | 64 | TAS | 42 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 |  | 2013-07-01 | 2017-12-01 |  |  | 28250 | 0 | 28250 | 0 | 0% | 28250 | 0 | 2825 | 3673 | 0 | 0 | 3673 | 0 | Brief progress report: Some progress. Legal arrangements (actual/planned): June 2016/Planned for Dec 2011. The Agreement with the Government has been signed in June 2016. Government of Guatemala asked for UNEP administrative support in the HPMP implementation. First mission (actual/planned): Dec 2013/No specific date established in the project document. TOR completed (actual/planned): N/A. First disbursement date (actual/planned): No disbursement/Planned for January 2012. All funds disbursed? (yes/no): No. Any delay? (yes/no): Yes, mainly at the disbursement rate level. If Yes, reasons for delay & action plan to resolve: Delays are due to an inadequate project management of the former NOO. Currently, there is a new NOO on board since middle 2015. An official meeting with the NOO and his supervisor was conducted in December 2015 to agree on a 2016 work plan. A country mission to meet high level authorities and train the new NOO was carried out by end of April 2016. If Yes, will delay have impact on project completion date? Yes. Any ongoing problems? (yes/no): No. If Yes, is any action required by ExCom? No | Brief progress report: Some progress. Legal arrangements (actual/planned): June 2016/Planned for Dec 2011. Government of Guatemala asked for UNEP administrative support in the HPMP implementation. A Customs train the trainers is planned to the second quarter of 2017. First mission (actual/planned): Dec 2013/No specific date established in the project document. TOR completed (actual/planned): An International Consultant to conduct the Customs train the trainers' workshop is being recruited. First disbursement date (actual/planned): No disbursement/Planned for January 2012. All funds disbursed? (yes/no): No. Any delay? (yes/no): Yes, mainly at the disbursement rate level. If Yes, reasons for delay & action plan to resolve: Delays are due to an inadequate project management of the former NOO. Currently, there is a new NOO on board since middle 2015. An official meeting with the NOO and his supervisor was conducted in December 2015 to agree on a 2016 work plan. A country mission to meet high level authorities and train the new NOO was carried out by end of April 2016. If Yes, will delay have impact on project completion date? Yes. Any ongoing problems? (yes/no): No. If Yes, is any action required by ExCom? No
FIN | UNIDO | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | GUA | PHA | 68 | INV | 45 | A | I | HCFC | 0.6 | 0.6 |  |  | 2012-12-01 | 2013-07-01 | 2015-07-31 |  | 2015-12-01 | 2016-05-01 | 97925 | -526 | 97399 | 97339.43 | 99.94% | 59.57 | 0 |  | 7344 | -39 | 7300 | 5 | 0 | The project was financially completed and the balance was returned at the 76th ExCom. |  |  |  | INV
COM | UNIDO | Verification report for stage I of HCFC phase-out management plan | Individual | LAC | GUA | PHA | 73 | TAS | 47 | A | I |  | 0 | 0 |  |  | 2014-11-01 | 2014-12-01 | 2015-11-30 |  | 2015-12-01 |  | 30000 | 0 | 30000 | 29917.49 | 99.72% | 82.51 | 0 | 1 | 2700 | 0 | 2693 | 7 | 0 | The project was operationally completed. |  |  |  | NON-INV
ONG | UNIDO | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | LAC | GUA | PHA | 75 | INV | 49 | A | I |  | 0 | 0 |  |  | 2015-11-01 | 2016-02-01 | 2018-12-01 | 2018-12-01 |  |  | 53775 | 0 | 53775 | 23260.13 | 43.25% | 30514.87 | 554.26 | 10000 | 4033 | 0 | 0 | 4033 | 41.5695 | Project manager visited the country and defined the implementing activities. Training of trainers of INTECAP carried out first week July 2016 with trainers, importers, trainees, 5 days training with 70 average daily attendance. Tools were purchased and delivered for the reclaiming center established in Guatemala City. | Tools received and distributed to the training centers. A program for end users and refrigerant reclaim is being implemented. - No delay in implementation - No recurring problem - Project completion date was set as original. - No action required by Executive Committee |  |  | INV
ONG | UNEP | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | LAC | GUA | PHA | 75 | TAS | 50 | A | I |  | 0.6 |  | 0 |  | 2015-11-01 |  | 2017-12-01 | 2017-12-01 |  |  | 45000 | -14816 | 30184 | 0 | 0% | 30184 | 0 | 3018.4 | 5850 | -1926 | 0 | 3924 | 0 | Brief progress report: Some progress. Government of Guatemala asked for UNEP administrative support in the HPMP implementation, particularly to hire a consultant to conduct a review of national legislation in the RAC service sector. Legal arrangements (actual/planned): N/A. First mission (actual/planned): No specific date established in the project document. TOR completed (actual/planned): N/A. First disbursement date (actual/planned): No disbursement/Planned for May 2016. All funds disbursed? (yes/no): No. Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: Project Funds were not transferred to UNEP until conditions of the approval were met. The action taken was to speed up the signature of the agreement for the first tranche. If Yes, will delay have impact on project completion date? Yes. Any ongoing problems? (yes/no): No. If Yes, is any action required by ExCom? No | Brief progress report: Some progress. Government of Guatemala asked for UNEP administrative support in the HPMP implementation, particularly to hire a consultant to conduct a review of national legislation in the RAC service sector. Legal arrangements (actual/planned): July 2016/Planned for March 2016. First mission (actual/planned): No specific date established in the project document. TOR completed(actual/planned): TOR for hiring a Regional consultant to support the country for reviewing RAC sector legislation is being drafted. First disbursement date (actual/planned): No disbursement/Planned for May 2016. All funds disbursed? (yes/no): No. Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: ExCom decision approval/Already met. If Yes, will delay have impact on project completion date? Yes. Any ongoing problems? (yes/no): No. If Yes, is any action required by ExCom? No
FIN | UNDP | Elimination of CFC 11 and 12 in the manufacture of unitary commercial refrigeration equipment at Industria Metalurgica Centroamericana S.A. (Imca) | Individual | LAC | GUA | REF | 15 | INV | 07 | A | I | CFC | 4 | 4 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  | 1997-07-01 | 2000-07-01 | 155017 | -5823 | 149194 | 149194 | 100% | 0 | 0 | 0 | 20152.21 | -756.99 | 19395.22 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC 11 and 12 in the manufacture of unitary commercial refrigeration equipment at Refrigeradores de Guatemala S.A. (Refrigua) | Individual | LAC | GUA | REF | 15 | INV | 08 | A | I | CFC | 24.4 | 24.4 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  | 1996-10-01 | 1999-12-01 | 194866 | 0 | 194866 | 194866 | 100% | 0 | 0 | 0 | 25332.58 | 0 | 25332.58 | 0 | 0 | Completed in 1996. Financially completed in 1999. |  | 1994 |  | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | GUA | REF | 18 | TAS | 09 | A | I | CFC | 26 | 26 | 0 | 0 | 1995-11-01 | 1996-02-01 | 1997-05-01 |  | 1999-12-01 | 2002-03-01 | 256780 | -19649 | 237131 | 237131 | 100% | 0 | 0 | 0 | 33381.4 | -2554.37 | 30827.03 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1995 |  | Investment
FIN | USA | Refrigeration: mobile air conditioning (MAC) and refrigerated transport (RT) |  | LAC | GUA | REF | 19 | DEM | 10 | A | I | CFC | 10 |  | 0 |  | 1996-05-01 | 1996-09-01 | 1997-12-01 |  | 1998-08-01 | 2000-05-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Final report will be submitted in May 2000. |  | 1995 | 1997-12-01
FIN | UNEP | National train the trainer programme on refrigeration management plan and good practices in refrigeration | Individual | LAC | GUA | REF | 21 | TRA | 13 | A | I | CFC | 68.3 | 68.3 | 0 | 0 | 1997-02-01 | 1997-04-01 | 1999-02-01 |  | 2001-12-01 | 2002-03-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0
FIN | UNDP | Conversion to CFC-free technology in the manufacture of commercial refrigeration equipment at four enterprises (Exea S.A., Productos American Vitas S.A., Termomecanica S.A., Unirefri S.A.) | Individual | LAC | GUA | REF | 23 | INV | 16 | A | I | CFC | 14 | 14 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 1999-11-01 | 2002-03-01 | 212000 | -24132 | 187868 | 187868 | 100% | 0 | 0 | 0 | 27560 | -3136.67 | 24423.33 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNEP | Implementation of the RMP: code of good practices in refrigeration | Individual | LAC | GUA | REF | 27 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2001-07-01 | 2000-10-01 |  | 2002-08-01 | 2003-08-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 |  |  |  | 2001-12-01
FIN | UNEP | Implementation of the RMP: licensing system | Individual | LAC | GUA | REF | 27 | TAS | 20 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2001-07-01 | 2000-10-01 |  | 2002-08-01 | 2003-08-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0
FIN | UNEP | Implementation of the RMP: custom officers training programme | Individual | LAC | GUA | REF | 27 | TRA | 18 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2001-06-01 | 2000-10-01 |  | 2002-11-01 | 2003-11-01 | 34000 | 0 | 34000 | 34000 | 100% | 0 | 0 |  | 4420 | 0 | 4420 | 0 | 0 |  |  |  | 2001-12-01
FIN | UNEP | Implementation of the RMP: establishment of licensing system | Individual | LAC | GUA | REF | 35 | TAS | 23 | A | I | CFC | 19.2 | 19.2 | 0 | 0 | 2001-12-01 | 2003-04-01 | 2007-12-01 |  | 2009-06-01 | 2009-12-01 | 23200 | 0 | 23200 | 23200 | 100% | 0 | 0 |  | 3016 | 0 | 3016 | 0 | 0
FIN | UNEP | Implementation of the RMP: alternatives to the use of CFC-12 in the refrigeration sector | Individual | LAC | GUA | REF | 35 | TAS | 24 | A | I | CFC | 47.9 | 47.9 | 0 | 0 | 2001-12-01 | 2004-01-01 | 2007-12-01 |  | 2009-03-01 | 2009-12-01 | 58000 | 0 | 58000 | 58000 | 100% | 0 | 0 |  | 7540 | 0 | 7540 | 0 | 0
FIN | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | LAC | GUA | REF | 35 | TAS | 25 | A | I | CFC | 26.3 | 26.3 | 0 | 0 | 2001-12-01 | 2007-11-01 | 2007-12-01 |  | 2009-06-01 | 2009-12-01 | 31800 | 0 | 31800 | 31800 | 100% | 0 | 0 |  | 4134 | 0 | 4134 | 0 | 0
FIN | UNEP | Implementation of the RMP: establishment and enforcement of legislation | Individual | LAC | GUA | REF | 35 | TAS | 26 | A | I | CFC | 51.2 | 51.2 | 0 | 0 | 2001-12-01 | 2004-01-01 | 2007-12-01 |  | 2009-06-01 | 2009-12-01 | 62000 | 0 | 62000 | 62000 | 100% | 0 | 0 |  | 8060 | 0 | 8060 | 0 | 0
FIN | UNEP | Implementation of the RMP: customs training programme | Individual | LAC | GUA | REF | 35 | TRA | 27 | A | I | CFC | 46.3 | 46.3 | 0 | 0 | 2001-12-01 | 2003-06-01 | 2007-12-01 |  | 2009-03-01 | 2009-03-01 | 56000 | 0 | 56000 | 56000 | 100% | 0 | 0 |  | 7280 | 0 | 7280 | 0 | 0
FIN | UNEP | Country programme preparation | Individual | LAC | GUA | SEV | 06 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-03-01 | 1993-05-01 |  | 1993-06-01 | 1993-12-01 | 30000 | 3000 | 33000 | 33000 | 100% | 0 | 0 |  | 3900 | 390 | 4290 | 0 | 0
FIN | IBRD | Preparation of investment projects (1992) |  | LAC | GUA | SEV | 08 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 1992-10-01 | 1992-12-31 | 1993-10-01 |  | 1992-12-01 | 1992-12-01 | 25000 | -13641 | 11359 | 11359 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1993) |  | LAC | GUA | SEV | 09 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 47000 | -13488 | 33512 | 33512 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNEP | Institutional strengthening: establishment of COGO | Individual | LAC | GUA | SEV | 10 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1994-12-01 | 1996-10-01 |  | 1997-10-01 | 1999-05-01 | 172000 | 0 | 172000 | 172000 | 100% | 0 | 0 |  | 22360 | 0 | 22360 | 0 | 0
FIN | UNDP | Project preparation assistance | Individual | LAC | GUA | SEV | 11 | PRP | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1994-05-01 |  | 1995-06-01 | 1997-12-01 | 30000 | 257 | 30257 | 30257 | 100% | 0 | 0 | 0 | 3900 | 33.41 | 3933.41 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1993 |  | Investment
FIN | IBRD | Preparation of investment projects (1994) |  | LAC | GUA | SEV | 12 | PRP | 06 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 55000 | -47098 | 7902 | 7902 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNEP | Renewal of institutional strengthening | Individual | LAC | GUA | SEV | 22 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-10-01 | 1999-11-01 |  | 2000-05-01 | 2000-12-01 | 96000 | 0 | 96000 | 96000 | 100% | 0 | 0 |  | 12480 | 0 | 12480 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening (phase III) | Individual | LAC | GUA | SEV | 28 | INS | 22 | A | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-05-01 | 2001-08-01 |  | 2001-12-01 | 2003-12-01 | 96000 | 0 | 96000 | 96000 | 100% | 0 | 0 |  | 12480 | 0 | 12480 | 0 | 0 |  |  |  | 2002-06-01
FIN | UNEP | Renewal of the institutional strengthening project | Individual | LAC | GUA | SEV | 35 | INS | 28 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-09-01 | 2004-01-01 |  | 2004-03-01 | 2007-12-01 | 96000 | 0 | 96000 | 96000 | 100% | 0 | 0 |  | 12480 | 0 | 12480 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (phase V) | Individual | LAC | GUA | SEV | 43 | INS | 30 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-08-01 | 2005-07-01 |  | 2010-06-01 | 2010-12-01 | 62400 | 0 | 62400 | 62400 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (phase VI) | Individual | LAC | GUA | SEV | 53 | INS | 33 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2009-04-01 | 2009-11-01 |  | 2011-04-01 | 2011-12-01 | 124800 | 0 | 124800 | 124800 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Renewal of the institutional strengthening project (phase VII) | Individual | LAC | GUA | SEV | 61 | INS | 41 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-11-01 | 2012-06-01 | 2018-07-01 |  |  | 124800 | 0 | 124800 | 19681.34 | 15.77% | 105118.66 | 105118.27 | 10511.866 | 0 | 0 | 0 | 0 | 0 | Brief progress report: Some Progress. 15% of project budget registered as spent. Legal arrangements: Signed in December 2011 as planned. The Agreement expired without exhausting the total budget. Initial stages of project implementation (actual/planned): A new agreement was drafted for Government consideration in 2015 and fully signed in June 2016. Second cash advance released in: September 2016. Intermediate goals achieved (actual/planned): Some goals achieved as planned. HCFC quota system is enforced. 2015 Article 7 and Country Programme Report submitted. International Ozone Day celebrated with specific activities for schools. Project completion and follow up: Project ongoing. First disbursement date (actual/planned): December 2011/Planned for January 2012. All funds disbursed? No. Any delay? Yes, mainly at the disbursement rate level. If Yes, reasons for delay & action plan to resolve: Delays are due to an inadequate project management of the former NOO. Currently, there is a new NOO on board since middle 2015. Two training sessions to NOO carried out by UNEP in 2016. A country mission was conducted in April 2016 to meet high level authorities and monitoring of activities. If Yes, will delay have impact on project completion date? Yes. Any ongoing problems? No. If Yes, is any action required by ExCom? No | Brief progress report: Project is progressing according to the adjusted work plan. Legal arrangements: Signed in December 2011 as planned. The Agreement expired without exhausting the total budget. Initial stages of project implementation (actual/planned): A new agreement was drafted for Government consideration in 2015 and fully signed in June 2016. Second cash advance released in: 2016. Intermediate goals achieved (actual/planned): Some goals achieved as planned. HCFC quota system is enforced. 2016 Article 7 and Country Programme Report being prepared. Public awareness activities are in progress. Project completion and follow up: Project ongoing. First disbursement date (actual/planned): December 2011/Planned for January 2012. All funds disbursed? No. Any delay? Yes, mainly at the disbursement rate level. If Yes, reasons for delay & action plan to resolve: Delays are due to an inadequate project management of the former NOO. Currently, there is a new NOO on board since middle 2015. Two training sessions to the NOO carried out by UNEP in 2016. A country mission was conducted in April 2016 to meet high level authorities and monitoring of activities. If Yes, will delay have impact on project completion date? Yes. Any ongoing problems? No. If Yes, is any action required by ExCom? No
COM | UNIDO | Survey of ODS alternatives at the national level | Individual | LAC | GUA | SEV | 74 | TAS | 48 | A | I |  | 0 | 0 |  |  | 2015-05-01 | 2016-02-01 | 2016-05-31 |  | 2016-12-01 |  | 70000 | 0 | 70000 | 40994.84 | 58.56% | 29005.16 | 27646.8 | 27647 | 6300 | 0 | 0 | 6300 | 2488.212 | Survey was carried out by local supplier, consultations and review of the documents by UNIDO took place in 2016. | Survey was submitted to the 78th ExCom. |  |  | NON-INV
FIN | UNIDO | Project formulation of investment projects in the foam sector | Individual | AFR | GUI | FOA | 21 | PRP | 04 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-09-01 | 1997-08-01 |  | 2000-12-01 | 2002-05-01 | 20000 | -8983 | 11017 | 11017 | 100% | 0 | 0 |  | 2600 | -1170 | 1430 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | GUI | PHA | 49 | PRP | 16 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-04-01 | 2007-07-01 |  | 2008-07-01 | 2009-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0
FIN | UNIDO | Project preparation for a terminal phase-out management plan | Individual | AFR | GUI | PHA | 49 | PRP | 17 | A | I |  | 0 | 0 |  |  | 2006-07-01 | 2007-04-01 | 2007-07-01 |  | 2008-06-01 | 2009-03-01 | 15000 | -2888 | 12112 | 12111.6 | 100% | 0.4 | 0 |  | 1125 | -217 | 908 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | GUI | PHA | 55 | INV | 20 | A | I | CFC | 1.4 | 1.4 |  |  | 2008-07-01 | 2009-06-01 | 2009-12-31 |  | 2012-02-01 | 2013-04-01 | 140000 | -62 | 139938 | 139937.85 | 100% | 0.15 | 0 |  | 12600 | -6 | 12594 | 0 | 0 | FIN |  |  |  | INV
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | GUI | PHA | 55 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-10-01 | 2009-12-01 |  | 2010-12-01 | 2011-12-01 | 74000 | 0 | 74000 | 74000 | 100% | 0 | 0 |  | 9620 | 0 | 9620 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | GUI | PHA | 56 | PRP | 21 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-07-01 | 2009-11-01 |  | 2011-12-01 | 2012-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 |  | 11050 | 0 | 11050 | 0 | 0
FIN | UNIDO | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | GUI | PHA | 60 | INV | 24 | A | I |  | 1.5 | 1.5 |  |  | 2010-04-01 | 2010-12-01 | 2011-04-30 |  | 2013-12-01 | 2013-12-01 | 60000 | -3523 | 56477 | 56476.78 | 100% | 0.22 | 0 |  | 5400 | -317 | 5083 | 0 | 0 | FIN
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | GUI | PHA | 60 | TAS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-08-01 | 2011-04-01 |  | 2011-12-01 | 2012-12-01 | 58000 | -1000 | 57000 | 57000 | 100% | 0 | 0 |  | 7540 | -130 | 7410 | 0 | 0
COM | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | GUI | PHA | 66 | INV | 26 | A | I | HCFC | 1.2 | 1.2 |  |  | 2012-04-01 | 2013-05-01 | 2016-04-30 |  | 2016-12-01 |  | 160000 | 0 | 160000 | 158839.6 | 99.27% | 1160.4 | 0 | 1 | 12000 | 0 | 11913 | 87 | 0 | Project completed. | Project completed. Financial closure is ongoing. |  |  | INV
COM | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | AFR | GUI | PHA | 66 | TAS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 | 2012-12-01 | 2014-04-01 |  | 2015-12-01 |  | 85000 | 0 | 85000 | 79072 | 93.03% | 5928 | 5928 | 5928 | 11050 | 0 | 10279.36 | 770.64 | 770.64 | Brief progress report (actual/planned): In February 2016 a refrigeration workshop for 25 experts on recovery and recycling as well as safe handling of hydrocarbon organized in Conakry. One workshop for 15 customs officers and 10 forestry guards on identification of ODS and ODS based equipment organized in Conakry, in April 2016 ___ Legal arrangements (actual/planned): Agreement signed in June 2012. All activities under the SSFA are completed (as planned) YES___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in July 2012 __ All funds disbursed (yes/no): _ No. SSFA has a balance of US$5,000.__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Project financially completed. Balances to be returned.
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | AFR | GUI | PHA | 72 | TAS | 29 | A | I |  | 0 |  | 0 |  | 2014-05-01 | 2016-10-01 | 2016-05-01 | 2018-12-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 60000 | 6000 | 7800 | 0 | 0 | 7800 | 7800 | Brief progress report (actual/planned): 25 RAC technicians and 25 enforcement officers trained in 2016. Legal arrangements (actual/planned): signed in August 2016 (Yes/No): No_ First mission (actual/planned): __n/a_ TOR completed (actual/planned): _N/A__ First disbursement date (actual/planned): Oct- 2016__ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _YES_ If Yes, reasons for delay & action plan to resolve: Country delayed the verification report submission due to Ebola outbreak__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): Legal arrangements (actual/planned): signed in August 2016 . NOU trained 25 RAC technicians and 25 enforcement officers in 2016. (Yes/No): No_ First mission (actual/planned): __n/a_ TOR completed (actual/planned): _N/A__ First disbursement date (actual/planned): Oct- 2016__ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _YES_ If Yes, reasons for delay & action plan to resolve: Country delayed the verification report submission due to Ebola outbreak__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__
FIN | UNEP | Development of a refrigerant management plan | RMP | AFR | GUI | REF | 21 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1998-03-01 |  | 2000-01-01 | 2001-06-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 |  |  |  | 1999-05-01
FIN | UNIDO | Refrigerant recovery and recycling scheme | RMP | AFR | GUI | REF | 22 | TAS | 05 | A | I | CFC | 12.9 | 12.9 |  |  | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1998-12-01 | 2000-04-01 | 80780 | 0 | 80780 | 80780 | 100% | 0 | 0 |  | 10501 | 0 | 10501 | 0 | 0 | FIN
FIN | UNEP | Implementation of the RMP: training for customs officers | Individual | AFR | GUI | REF | 30 | TRA | 06 | A | I | CFC | 6.7 | 6.7 | 0 | 0 | 2000-03-01 | 2001-03-01 | 2001-04-01 |  | 2003-03-01 | 2007-06-01 | 42500 | -23512 | 18988 | 18988 | 100% | 0 | 0 |  | 5525 | -3056.56 | 2468.44 | 0 | 0 |  |  |  | 2003-03-01
FIN | UNEP | Implementation of the RMP: train the trainer programme in the refrigeration servicing sector | Individual | AFR | GUI | REF | 30 | TRA | 07 | A | I | CFC | 10.5 | 10.5 | 0 | 0 | 2000-03-01 | 2000-12-01 | 2001-10-01 |  | 2002-09-01 | 2003-09-01 | 66500 | 0 | 66500 | 66500 | 100% | 0 | 0 |  | 8645 | 0 | 8645 | 0 | 0 |  |  |  | 2002-12-01
FIN | UNEP | Preparation of a country programme/RMP | RMP | AFR | GUI | REF | 39 | PRP | 09 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2004-01-01 | 2004-04-01 |  | 2004-11-01 | 2004-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0
FIN | UNDP | Project preparation for the formulation of refrigerant management plan update (investment components) | Individual | AFR | GUI | REF | 42 | PRP | 11 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2005-04-01 |  | 2005-04-01 | 2006-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 1500 | 0 | 1500 | 0 | 0 | Completed in 2005. Financially completed in 2006. |  | 2004 |  | Investment
FIN | UNEP | Implementation of the RMP: monitoring the activities of the RMP | Individual | AFR | GUI | REF | 45 | TAS | 14 | A | I | CFC | 3.1 | 3.1 | 0 | 0 | 2005-04-01 | 2005-08-01 | 2007-04-01 |  | 2008-12-01 | 2009-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0
FIN | UNDP | Implementation of the RMP: recovery and recycling programme (phase II) | RMP-Component | AFR | GUI | REF | 45 | TAS | 15 | N | I | CFC | 7.9 | 7.9 | 0 | 0 | 2005-04-01 | 2006-04-01 | 2007-04-01 |  | 2007-10-01 | 2011-12-01 | 49890 | -6010.66 | 43879.34 | 43879 | 100% | 0.34 | 0 | 0 | 4490 | -540.95 | 3949.022 | 0.027999 | 0 | Completed in 2007. |  | 2005 |  | Investment
FIN | UNEP | Implementation of the RMP: customs officers training in monitoring and control of ODS (phase II) | Individual | AFR | GUI | REF | 45 | TRA | 12 | A | I | CFC | 3.9 | 3.9 | 0 | 0 | 2005-04-01 | 2006-01-01 | 2006-04-01 |  | 2006-12-01 | 2009-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0
FIN | UNEP | Implementation of the RMP: training programme for refrigeration technicians (phase II) | Individual | AFR | GUI | REF | 45 | TRA | 13 | A | I | CFC | 3.9 | 3.9 | 0 | 0 | 2005-04-01 | 2006-01-01 | 2006-10-01 |  | 2006-12-01 | 2008-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0
FIN | UNEP | Country programme preparation | Individual | AFR | GUI | SEV | 11 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-03-01 | 1994-11-01 |  | 1995-10-01 | 1995-12-01 | 43000 | 0 | 43000 | 43000 | 100% | 0 | 0 |  | 5590 | 0 | 5590 | 0 | 0
FIN | UNEP | Creation of an Ozone Bureau | Individual | AFR | GUI | SEV | 18 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-04-01 | 1998-11-01 |  | 1999-11-01 | 1999-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening (phase II) | Individual | AFR | GUI | SEV | 28 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 1999-11-01 | 2001-08-01 |  | 2001-11-01 | 2001-12-01 | 33333 | 0 | 33333 | 33333 | 100% | 0 | 0 |  | 4333 | 0 | 4333 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project | Individual | AFR | GUI | SEV | 34 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2003-08-01 |  | 2003-12-01 | 2004-12-01 | 33333 | 0 | 33333 | 33333 | 100% | 0 | 0 |  | 4333 | 0 | 4333 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project: phase 4 | Individual | AFR | GUI | SEV | 41 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-03-01 | 2005-12-01 |  | 2006-12-01 | 2007-12-01 | 43333 | 0 | 43333 | 43333 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project: (phase V) | Individual | AFR | GUI | SEV | 50 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-03-01 | 2008-11-01 |  | 2009-02-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project: (phase VI) | Individual | AFR | GUI | SEV | 56 | INS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2008-12-01 | 2010-12-01 |  | 2010-06-01 | 2011-06-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VII) | Individual | AFR | GUI | SEV | 63 | INS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-11-01 | 2013-03-01 |  | 2013-03-01 | 2014-03-01 | 60000 | -121 | 59879 | 59879 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of the institutional strengthening project (phase VIII: 7/2013-6/2015) | Individual | AFR | GUI | SEV | 70 | INS | 28 | A | I |  | 0 |  | 0 |  | 2013-07-01 | 2014-01-01 | 2015-06-01 |  | 2015-12-01 |  | 60000 | 0 | 60000 | 32794.48 | 54.66% | 27205.52 | 27205.52 | 27206 | 0 | 0 | 0 | 0 | 0 | Project completed | Project completed
ONG | UNEP | Extension of the institutional strengthening project (phase IX: 7/2015-6/2017) | Individual | AFR | GUI | SEV | 74 | INS | 30 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-03-01 | 2017-06-01 | 2017-10-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 30000 | 6000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Legal arrangements (actual/planned): Agreement signed in January 2016. First payment sent in March 2016. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in March 2016 __ All funds disbursed (yes/no): _No_ Any delay? (yes/no): _No___ If Yes, reasons for delay & action plan to resolve: _n/a_ If Yes, will delay have impact on project completion date (yes/no): _ n/a__ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Brief progress report (actual/planned): Legal arrangements (actual/planned): Agreement signed in January 2016. First payment sent in March 2016. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in March 2016 __ All funds disbursed (yes/no): _No_ Any delay? (yes/no): _No___ If Yes, reasons for delay & action plan to resolve: _n/a_ If Yes, will delay have impact on project completion date (yes/no): _ n/a__ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | AFR | GUI | SEV | 74 | TAS | 31 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-05-01 | 2016-05-01 | 2017-12-01 |  |  | 110000 | 0 | 110000 | -0.08 | -7.273e-05% | 110000.08 | 110000 | 11000.008 | 14300 | 0 | -0.0104 | 14300.0104 | 14300 | Brief progress report (actual/planned): Legal arrangements (actual/planned): Agreement signed in May 2016. Country received first payment in May 2016. National consultants hired in July 2016. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in May 16 __ All funds disbursed (yes/no): NO_ Final payment being _NO Any delay? (yes/no): _YES__ If Yes, reasons for delay & action plan to resolve: Delay in submitting Non ODS survey report. UNEP to insist in order to get the report finalized.__ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Brief progress report (actual/planned): Country received first payment in May 2016. National consultants hired in July 2016. Report not sent yet by country. Legal arrangements (actual/planned): Agreement signed in May 2016. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in May 16 __ All funds disbursed (yes/no): NO_ Final payment being _NO Any delay? (yes/no): _YES__ If Yes, reasons for delay & action plan to resolve: Low responsiveness of NOU. Delay in submitting Non ODS survey report. UNEP to insist in order to get the report finalized.__ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a |  |  |  |  | 12 months delays
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | LAC | GUY | PHA | 48 | PRP | 11 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-05-01 | 2007-04-01 |  | 2009-06-01 | 2010-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | LAC | GUY | PHA | 48 | PRP | 12 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-04-01 | 2007-04-01 |  | 2007-12-01 | 2009-07-01 | 15000 | -12 | 14988 | 14988 | 100% | 0 | 0 | 0 | 1125 | -0.9 | 1124.1 | 0 | 0 | Completed in 2007.Financially completed in 2009. |  | 2006 |  | Investment
FIN | UNDP | Terminal phase-out management plan for the phase-out of ODS in the refrigeration and air-conditioning sector (first tranche) | Multi-Year | LAC | GUY | PHA | 53 | INV | 15 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-05-01 | 2009-11-01 |  | 2009-11-01 | 2013-02-01 | 124000 | 0 | 124000 | 124000 | 100% | 0 | 0 | 0 | 11160 | 0 | 11160 | 0 | 0 | Financially completed in 2013. |  | 2007 |  | Investment
FIN | UNEP | Terminal phase-out management plan for the phase-out of ODS in the refrigeration and air-conditioning sector (first tranche) | Multi-year | LAC | GUY | PHA | 53 | TAS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-06-01 | 2009-03-01 |  | 2010-05-01 | 2011-05-01 | 58000 | 0 | 58000 | 58000 | 100% | 0 | 0 |  | 7540 | 0 | 7540 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | GUY | PHA | 55 | PRP | 16 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-12-01 | 2009-07-01 |  | 2011-12-01 | 2011-12-01 | 85000 | -17218 | 67782 | 67782 | 100% | 0 | 0 |  | 11050 | -2238.34 | 8811.66 | 0 | 0
FIN | UNDP | Terminal phase-out management plan for the phase-out of ODS in the refrigeration and air-conditioning sector (second tranche) | Multi-Year | LAC | GUY | PHA | 59 | INV | 19 | N | I | CFC | 8 | 8 | 0 | 0 | 2009-11-01 | 2010-11-01 | 2011-11-01 |  | 2011-11-01 | 2012-07-01 | 91000 | -476.32 | 90523.68 | 90524 | 100% | -0.32 | 0 | 0 | 8190 | -42.87 | 8147.16 | -0.03 | 0 | Financially completed in 2012. | Completed in 2011. Equipment procured and delivered to final beneficiaries. | 2009 |  | Investment
FIN | UNEP | Terminal phase-out management plan for the phase-out of ODS in the refrigeration and air-conditioning sector (second tranche) | Multi-Year | LAC | GUY | PHA | 59 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-05-01 | 2011-11-01 |  | 2011-12-01 | 2011-12-01 | 72000 | -18566 | 53434 | 53434 | 100% | 0 | 0 |  | 9360 | -2413.58 | 6946.42 | 0 | 0
FIN | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | GUY | PHA | 63 | INV | 21 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-04-01 | 2012-08-01 | 2012-03-01 |  | 2014-12-01 | 2015-12-01 | 48000 | -2 | 47998 | 47998 | 100% | 0 | 0 | 0 | 4320 | -0.18 | 4319.82 | 0 | 0 | Financially Completed in 2015. | Clarifications were requested for the bidders. Purchase Order is expected to be issued soon. | 2011 |  | Investment
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | GUY | PHA | 63 | TAS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2013-03-01 | 2012-03-01 |  | 2014-12-01 | 2014-12-01 | 11000 | -68 | 10932 | 10932 | 100% | 0 | 0 |  | 1430 | -9 | 1421 | 0 | 0
COM | UNEP | Preparation of a HCFC phase-out management plan (stage II) | Multi-Year | LAC | GUY | PHA | 73 | PRP | 23 | A | I |  | 0 |  | 0 |  | 2014-11-01 | 2015-04-01 | 2015-11-01 |  | 2015-12-01 |  | 30000 | 0 | 30000 | 20200 | 67.33% | 9800 | 0 |  | 3900 | 0 | 2626 | 1274 | 0 | Project completed | Project completed
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | GUY | PHA | 74 | TAS | 24 | A | I |  | 0 |  | 0 |  | 2015-05-01 |  | 2016-05-01 | 2017-12-01 |  |  | 7000 | 0 | 7000 | 0 | 0% | 7000 | 0 | 700 | 910 | 0 | 0 | 910 | 0 | Brief progress report (actual/planned): ___No suitable candidate applied in re-advertizement of training consultancy in Jun-16. Legal arrangements (actual/planned): ___ First mission (actual/planned): ___ TOR completed (actual/planned): Feb-16/Oct-15___ First disbursement date (actual/planned): pending/Oct-2015___ All funds disbursed (yes/no): No___ Any delay? (yes/no): yes___ If Yes, reasons for delay & action plan to resolve: no suitable candidate applied for national training consultancy services. Agreement with country to focus on Stage II implementation and revisit this consultancy in 1Q of 2017 ___ If Yes, will delay have impact on project completion date (yes/no): yes. Completion date revised to accomodate a new contracting process in 2017 and completion of activities___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): ___Revised ToRs to be discussed with country in Mar-17. Legal arrangements (actual/planned): ___ First mission (actual/planned): ___ TOR completed (actual/planned): ---/Mar-17___ First disbursement date (actual/planned): ---/Mar-17___ All funds disbursed (yes/no): No___ Any delay? (yes/no): yes___ If Yes, reasons for delay & action plan to resolve: no suitable candidate applied for national training consultancy services. Agreement with country to focus on Stage II implementation. Consultancy to be revisited in Mar-17 ___ If Yes, will delay have impact on project completion date (yes/no): yes. Completion date revised to accomodate a new contracting process in 2017 and completionf of activities___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___
ONG | UNDP | HCFC phase-out management plan (stage II, first tranche) | Multi-year | LAC | GUY | PHA | 75 | INV | 28 | N | I | HCFC | 0.2 | 0 | 0 | 0 | 2015-11-01 | 2016-10-01 | 2018-12-01 | 2017-12-01 |  |  | 159750 | 0 | 159750 | 10450.56 | 6.542% | 149299.44 | 0 | 59719.776 | 11183 | 0 | 731.5719 | 10451.4281 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): ProDoc signed. Project team establish Launch of stage II HPMP in Guyana. TORs developed Prodoc signed (actual/planned, yes/no and date):42644 Missions undertaken (actual/planned):0 of 0 TOR for consultants/subcontracts completed (actual/planned): 1 of 1 Contract/PO/MOA agreements signed: NA First disbursement date (actual/planned): 42644Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | Specs in the process of being developed for procurement process of tools | 2015 |  | Investment
ONG | UNEP | HCFC phase-out management plan (stage II, first tranche) | Multi-Year | LAC | GUY | PHA | 75 | TAS | 27 | A | I |  | 0.1 |  | 0 |  | 2015-11-01 |  | 2018-12-01 | 2018-12-01 |  |  | 55500 | 0 | 55500 | 0 | 0% | 55500 | 55500 | 5550 | 7215 | 0 | 0 | 7215 | 7215 | Brief progress report (actual/planned): First disbursement processed in Oct-16, pending confirmation from country. Advancing discussion with academic stakeholders to introduce refrigeration programmes in their syllabus, both at the technical and terciary levels. ___. Legal arrangements (actual/planned): Oct-16/Mar-16 ___ First mission (actual/planned): ___ TOR completed (actual/planned): ___ First disbursement date (actual/planned): ---/Oct-16___ All funds disbursed (yes/no): No___ Any delay? (yes/no): yes___ If Yes, reasons for delay & action plan to resolve: country focused in finalizing Stage I during first half of 2016. This process couldn't be completed in two tries and delayed discussions and signature of SSFA ___ If Yes, will delay have impact on project completion date (yes/no): no___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): Tracking of first disbursement processed in Oct-16. Country requesting confirmation in Feb-17. Programming of training activities during 2017 ___. Legal arrangements (actual/planned): Oct-16/Mar-16 ___ First mission (actual/planned): ___ TOR completed (actual/planned): ___ First disbursement date (actual/planned): ---/Oct-16___ All funds disbursed (yes/no): No___ Any delay? (yes/no): yes___ If Yes, reasons for delay & action plan to resolve: country focused in finalizing Stage I during first half of 2016. This process couldn't be completed in two tries and delayed discussions and signature of SSFA ___ If Yes, will delay have impact on project completion date (yes/no): no___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___
ONG | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Individual | LAC | GUY | PHA | 77 | TAS | 29 | A | I |  | 0 |  | 0 |  | 2016-12-01 |  | 2018-06-01 | 2018-06-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 3000 | 3900 | 0 | 0 | 3900 | 0 | Newly approved project | Brief progress report (actual/planned): Contracting process of verification consultant will start 6 months before next tranche submission in 2018 ___. Legal arrangements (actual/planned):___ First mission (actual/planned): ___ TOR completed (actual/planned): ---/Jan-18___ First disbursement date (actual/planned): ---/Jan-18___ All funds disbursed (yes/no): No___ Any delay? (yes/no): no___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___
FIN | UNIDO | ODS phase out at a domestic refrigeration plant (Guyana Refrigeration Ltd.) | Individual | LAC | GUY | REF | 17 | PRP | 02 | A | I |  | 0 | 0 |  |  | 1995-07-01 | 1996-03-01 | 1995-09-01 |  | 1998-01-01 | 1999-08-01 | 15000 | -659 | 14341 | 14341 | 100% | 0 | 0 |  | 1950 | -89 | 1861 | 0 | 0 | FIN
FIN | UNEP | Assistance for formulation refrigeration management plan | RMP | LAC | GUY | REF | 21 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1998-03-01 |  | 1997-10-01 | 1999-12-01 | 30000 | -4000 | 26000 | 26000 | 100% | 0 | 0 |  | 3900 | -520 | 3380 | 0 | 0
FIN | UNIDO | Phasing out ODS at Guyana Refrigerator Ltd., Guyana (GRL) | Individual | LAC | GUY | REF | 23 | INV | 05 | A | I | CFC | 7.2 | 7.2 |  |  | 1997-11-01 | 1998-08-01 | 1999-06-01 |  | 2001-04-01 | 2002-09-01 | 461000 | 0 | 461000 | 461000.01 | 100% | -0.01 | 0 |  | 59930 | -6 | 59924 | 0 | 0 | FIN
FIN | Canada | Implementation of the RMP: national recovery and recycling programme | RMP | LAC | GUY | REF | 23 | TAS | 08 | A | I | CFC | 6.5 |  | 0 |  | 1997-11-01 | 1998-04-01 | 2000-12-01 |  | 2003-05-01 | 2003-05-01 | 73450 | 0 | 73450 | 73450 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project Completion Report submitted. |  | 1997 |  | Non-Inv.
FIN | UNEP | Implementation of the RMP: training of trainers for good refrigeration servicing practices | Individual | LAC | GUY | REF | 23 | TRA | 06 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-12-01 |  | 2001-04-01 | 2001-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Implementation of the RMP: training on monitoring and control of ODS and ODS using equipment | Individual | LAC | GUY | REF | 23 | TRA | 07 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1999-06-01 |  | 2003-08-01 | 2003-09-01 | 16000 | 0 | 16000 | 16000 | 100% | 0 | 0 |  | 2080 | 0 | 2080 | 0 | 0
FIN | UNEP | Implementation of the RMP: assistance for implementation of additional activities in the RMP | Individual | LAC | GUY | REF | 35 | TAS | 10 | A | I | CFC | 45.2 | 45.2 | 0 | 0 | 2001-12-01 | 2003-04-01 | 2007-12-01 |  | 2008-01-01 | 2009-04-01 | 65500 | 0 | 65500 | 65500 | 100% | 0 | 0 |  | 8515 | 0 | 8515 | 0 | 0
FIN | UNEP | Country programme preparation | Individual | LAC | GUY | SEV | 17 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-02-01 | 1996-10-01 |  | 1997-10-01 | 1999-05-01 | 40000 | -5000 | 35000 | 35000 | 100% | 0 | 0 |  | 5200 | -650 | 4550 | 0 | 0
FIN | UNEP | Creation of the National Ozone Action Unit | Individual | LAC | GUY | SEV | 23 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-02-01 | 2000-11-01 |  | 2001-08-01 | 2007-03-01 | 65000 | 0 | 65000 | 65000 | 100% | 0 | 0 |  | 8450 | 0 | 8450 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project | Individual | LAC | GUY | SEV | 34 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2005-02-01 | 2003-08-01 |  | 2008-09-01 | 2009-09-01 | 43400 | 0 | 43400 | 43400 | 100% | 0 | 0 |  | 5642 | 0 | 5642 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | LAC | GUY | SEV | 48 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-10-01 | 2008-04-01 |  | 2009-06-01 | 2010-12-01 | 56333 | 0 | 56333 | 56333 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | LAC | GUY | SEV | 59 | INS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-07-01 | 2011-11-01 |  | 2012-12-01 | 2013-12-01 | 32500 | 27500 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase V: 1/2013-12/2014) | Individual | LAC | GUY | SEV | 68 | INS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-11-01 | 2014-12-01 |  | 2014-12-01 | 2014-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of the institutional strengthening project (phase VI: 11/2015-10/2017) | Individual | LAC | GUY | SEV | 74 | INS | 25 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-05-01 | 2017-10-01 | 2017-12-01 |  |  | 60000 | 0 | 60000 | 51486.81 | 85.81% | 8513.19 | 8513.19 | 851.319 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Licensing and quotas have been implemented during 2016. Monitoring importation of HCFC-based equipment. 2015 CP Data and Art.7 Data reported on time. Meetings with steering committe to guide implementation of HPMP and collection of information for the ODS Alternatives Survey. Public awareness activities mainly during IOD celebrations. Management of the of HPMP-II and the ODS Alternatives Survey ___Legal arrangements (actual/planned): Apr-16/ Dec-15.___Initial stages of project implementation (actual/planned):___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): May-16/ Dec-15.___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): yes___ If Yes, reasons for delay & action plan to resolve: Signature of SSFA delayed in order to allow full expeditures of balance from previous phase. UN Environment reprogrammed related funding into 2016 and processed signature of SSFA . ___ If Yes, will delay have impact on project completion date (yes/no): no. ___ Any ongoing problems (yes/no): no. ___ If Yes, is any action required by ExCom: ___. | Brief progress report (actual/planned): Country collecting data to report 2016 CP Data on time. Processing of last disbursement in Feb-17. Draft renewal document prepared and commented by UN Environment. Renewal to be presented to last ExCom in 2017. ___Legal arrangements (actual/planned): Apr-16/ Dec-15.___Initial stages of project implementation (actual/planned):___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): May-16/ Dec-15.___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): no___ If Yes, reasons for delay & action plan to resolve: . ___ If Yes, will delay have impact on project completion date (yes/no): . ___ Any ongoing problems (yes/no): no. ___ If Yes, is any action required by ExCom: ___.
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | LAC | GUY | SEV | 74 | TAS | 26 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-04-01 | 2016-05-01 | 2017-12-01 |  |  | 40000 | 0 | 40000 | 16010 | 40.02% | 23990 | 20000 | 2399 | 5200 | 0 | 2081.3 | 3118.7 | 2600 | Brief progress report (actual/planned): SSFA signed in Dec-15. Regional Consultant selected and contract signed in Jul-16. National consultant hired in Sep-16. Stakeholders meeting held in Jul-16. Collection of information completed in Nov-16. Report sent in Dec-16 ___. Legal arrangements (actual/planned): Dec-15/Dec-2015 ___ First mission (actual/planned):Dec-16/Mar-16 ___ TOR completed (actual/planned): May-16/Feb-2016___ First disbursement date (actual/planned): Apr-16/Oct-15 ___ All funds disbursed (yes/no): No___ Any delay? (yes/no): no___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no):___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): Report review ongoing. Processing second disbursement in Mar-17. Completion date revised to Jul-17 to reflect submission of the report to the second ExCom in 2017 ___. Legal arrangements (actual/planned): Dec-15/Dec-2015 ___ First mission (actual/planned):Dec-16/Mar-16 ___ TOR completed (actual/planned): May-16/Feb-2016___ First disbursement date (actual/planned): Apr-16/Oct-15 ___ All funds disbursed (yes/no): No___ Any delay? (yes/no): no___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no):___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___
FIN | UNEP | Sectoral phase-out programme: Establishing a halon management plan | Individual | LAC | HAI | HAL | 50 | TAS | 10 | A | I | Halon | 1.5 | 1.5 | 0 | 0 | 2006-11-01 | 2007-07-01 | 2009-11-01 |  | 2008-11-01 | 2009-11-01 | 25000 | -9000 | 16000 | 16000 | 100% | 0 | 0 |  | 3250 | -1170 | 2080 | 0 | 0
FIN | UNDP | Project preparation for a terminal phase-out management plan in the servicing sector | Individual | LAC | HAI | PHA | 54 | PRP | 11 | A | I | CFC | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-12-01 | 2009-03-01 |  | 2009-07-01 | 2011-11-01 | 15000 | -1826 | 13174 | 13174 | 100% | 0 | 0 | 0 | 1125 | -136.95 | 988.05 | 0 | 0 | Completed in 2009. |  | 2008 |  | Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan in the servicing sector | RMP | LAC | HAI | PHA | 54 | PRP | 12 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-09-01 | 2009-03-01 |  | 2010-12-01 | 2012-04-01 | 15000 | -2038 | 12962 | 12962 | 100% | 0 | 0 |  | 1950 | -264.94 | 1685.06 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | HAI | PHA | 57 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2011-01-01 | 2010-03-01 |  | 2013-12-01 | 2013-12-01 | 85000 | -31082 | 53918 | 53918 | 100% | 0 | 0 |  | 11050 | -4040.61 | 7009.39 | 0 | 0
COM | UNDP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | HAI | PHA | 58 | INV | 14 | N | I | CFC | 2.3 | 2.3 | 0 | 0 | 2009-07-01 | 2013-12-01 | 2011-07-01 |  | 2014-12-01 |  | 150000 | -757 | 149243 | 149243 | 100% | 0 | 0 | 0 | 13500 | -68.13 | 13431.87 | 0 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2014. |  | 2009 |  | Investment
FIN | UNEP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | HAI | PHA | 58 | TAS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2009-12-01 | 2010-06-01 |  | 2013-06-01 | 2013-06-01 | 125000 | -14649 | 110351 | 110351 | 100% | 0 | 0 |  | 16250 | -1904.67 | 14345.33 | 0 | 0
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | HAI | PHA | 68 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2014-06-01 | 2015-12-01 | 2017-12-01 |  |  | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 | Brief progress report (actual/planned): political instability remained during 2016. Frequent change of Minister of Environment prevented signature of new agreement(s). Second tranche submitted to ExCom 76 and approved. Releasing of funds subject to submission of verification report. Mission in Aug-16 to discuss Montreal Protocol implementation: it was agreed that balance of first tranche will be used for training. The legal instrument is yet to be decided ___ Legal arrangements (actual/planned): ___ First mission (actual/planned): ___TOR completed (actual/planned): ___ First disbursement date (actual/planned): ___All funds disbursed (yes/no): no. ___ Any delay? (yes/no): yes. ___ If Yes, reasons for delay & action plan to resolve: political instability in the country remained througout the year. UN Environment provided support in the preparation of the second tranche request. ___ If Yes, will delay have impact on project completion date (yes/no): yes. ___ Any ongoing problems (yes/no): yes. ___ If Yes, is any action required by ExCom: no. ___ | Brief progress report (actual/planned): new Minister appointed in Feb-17. A new SSFA for completion of training activities will be discussed with country in Mar-17 ___ Legal arrangements (actual/planned): ---/Apr-17___ First mission (actual/planned): ___TOR completed (actual/planned): _____First disbursement date (actual/planned): ---/Jan-18___ All funds disbursed (yes/no): no. ___ Any delay? (yes/no): yes. ___ If Yes, reasons for delay & action plan to resolve: political instability in the country remained througout 2016. UN Environment will continue providing support in the advancement of Montreal Protocol under current administration. ___ If Yes, will delay have impact on project completion date (yes/no): yes. Completion date revised to accomodate for signature of new SSFA and completion of activities___ Any ongoing problems (yes/no): yes. ___ If Yes, is any action required by ExCom: no. ___ |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor the signing of a new agreement and the appointment of legal assistance to development of regulations.
ONG | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Multi-Year | LAC | HAI | PHA | 73 | TAS | 19 | A | I |  | 0 |  | 0 |  | 2014-11-01 | 2016-04-01 | 2015-05-01 | 2017-06-01 |  |  | 30000 | 0 | 30000 | 9590.98 | 31.97% | 20409.02 | 0 | 2040.902 | 3900 | 0 | 1246.8274 | 2653.1726 | 0 | Brief progress report (actual/planned): Additional information was requested from Consultant in Apr-16 in order to complete the report. Draft report sent to Country for comments. Mission in Aug-16 to follow-up on reviewing and commenting the report by NOU. Comments to the report sent by NOO in Sep-16. Additional but incomplete information was sent to consultant in Nov-16 by NOO. The report taking into account this partial information will be sent by consultant in Feb-17 ___ Legal arrangements (actual/planned): ___ First mission (actual/planned): Apr-16/Apr-15___ TOR completed (actual/planned): Jan-16/Jan-15___ First disbursement date (actual/planned): Apr-16/Apr-15___ All funds disbursed (yes/no): yes ___ Any delay? (yes/no): yes___ If Yes, reasons for delay & action plan to resolve: NOU have reviewed and sent comments to the report in Sep-16, and information requested by consultant in Nov-16; these have prevented the finalization of the report by Verificator. UN Environment has been supporting Haiti and following-up periodically with NOO in order to send required information___ If Yes, will delay have impact on project completion date (yes/no): yes.___ Any ongoing problems (yes/no): yes___ If Yes, is any action required by ExCom: no___ | Brief progress report (actual/planned): Verificator Consultant sent final report to NOU and to UN Environment in Feb-17. The final report will be sent to next ExCom in order to relase funds of second tranche. Project completed. ___ Legal arrangements (actual/planned): ___ First mission (actual/planned): Apr-16/Apr-15___ TOR completed (actual/planned): Jan-16/Jan-15___ First disbursement date (actual/planned): Apr-16/Apr-15___ All funds disbursed (yes/no): yes ___ Any delay? (yes/no): yes. ___ If Yes, reasons for delay & action plan to resolve: NOU have reviewed and sent comments to the report in Sep-16, and information requested by consultant in Nov-16; these have prevented the finalization of the report by Verificator. UN Environment has been supporting Haiti and following-up periodically with NOO in order to send required information___ If Yes, will delay have impact on project completion date (yes/no): yes. Completion date has been revised to reflect actual completion of project___ Any ongoing problems (yes/no): yes___ If Yes, is any action required by ExCom: no___
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | HAI | PHA | 76 | INV | 22 | N | I | HCFC | 0.4 | 0 | 0 | 0 | 2016-05-01 |  | 2020-05-01 | 2017-05-01 |  |  | 97119 | 0 | 97119 | 0 | 0% | 97119 | 0 | 38847.6 | 8741 | 0 | 0 | 8741 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Discussion with NOU and international consultant on work plan and scope of activiites. Prodoc signed (actual/planned, yes/no and date):No, April 2017 Missions undertaken (actual/planned):0 of 0 TOR for consultants/subcontracts completed (actual/planned): 0 of 0 Contract/PO/MOA agreements signed: 0 of 0 First disbursement date (actual/planned): 42856Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:There were delays in the implementation of the tranche as the verification report approval took longer than initially planned. | Funding not yet released to UNDP because of lack of verification report. |  |  | Investment
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | HAI | PHA | 76 | TAS | 21 | A | I |  | 0 |  | 0 |  | 2016-05-01 |  | 2018-05-01 | 2018-05-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 3000 | 3900 | 0 | 0 | 3900 | 0 | Brief progress report (actual/planned): Releasing of funds subject to submission of verification report. Mission in Aug-16 to discuss Montreal Protocol implementation: it was agreed that NOU will review and comment Verification report as well as provide additional information as requested by consultant at the soonest. Report reviewed and commented in Sep-16. Additional but incomplete information sent by NOU to the Verificator in Nov-16 ___ Legal arrangements (actual/planned): ---/Dec-16 ___ First mission (actual/planned): Aug-16/Aug-16 ___TOR completed (actual/planned): ___First disbursement date (actual/planned): ---/Dec-16___ All funds disbursed (yes/no): no. ___ Any delay? (yes/no): yes. ___ If Yes, reasons for delay & action plan to resolve: political instability in the country remained througout the year. UN Environment provided support in the preparation of the second tranche request and follow-up periodically with NOU to submit relevant information to Verificator ___ If Yes, will delay have impact on project completion date (yes/no): yes. ___ Any ongoing problems (yes/no): yes. ___ If Yes, is any action required by ExCom: no. ___ | Brief progress report (actual/planned): Releasing of funds subject to submission of verification report. Final report sent in Feb-17 by Verificator ___ Legal arrangements (actual/planned): ---/Dec-16 ___ First mission (actual/planned): ___TOR completed (actual/planned): ___First disbursement date (actual/planned): ---/Dec-16___ All funds disbursed (yes/no): no. ___ Any delay? (yes/no): yes. ___ If Yes, reasons for delay & action plan to resolve: political instability in the country remained througout 2016. New Minister appointed in Feb-17. UN Environment will continue providing support and follow-up periodically with NOU to advance progress ___ If Yes, will delay have impact on project completion date (yes/no): no. ___ Any ongoing problems (yes/no): yes. ___ If Yes, is any action required by ExCom: no. ___
FIN | UNDP | Project preparation in the recovery and recycling refrigeration sector | Individual | LAC | HAI | REF | 36 | PRP | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2005-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2002. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Implementation of the refrigerant management plan: recovery and recycling of CFC-12 refrigerant | RMP-Component | LAC | HAI | REF | 39 | TAS | 04 | A | I | CFC | 88.6 | 88.6 | 0 | 0 | 2003-04-01 | 2007-04-01 | 2006-04-01 |  | 2011-10-01 | 2014-03-01 | 220256 | -3239 | 217017 | 217017 | 100% | 0 | 0 | 0 | 19823.04 | -291.51 | 19531.53 | 0 | 0 | Financially completed in 2014. | Completed in 2011. Tools and equipment will be delivered to technicians once they have finalized training of local technicians organized by UNEP. | 2003 |  | Investment
FIN | UNDP | Implementation of the refrigerant management plan: monitoring the activities in the RMP | RMP-Component | LAC | HAI | REF | 39 | TAS | 06 | N | I | CFC | 11.8 | 11.8 | 0 | 0 | 2003-04-01 | 2008-02-01 | 2006-04-01 |  | 2010-08-01 | 2011-09-01 | 29400 | -2220.48 | 27179.52 | 27180 | 100% | -0.48 | 0 | 0 | 2646 | -199.84 | 2446.2 | -0.04 | 0 | Completed in 2006. Financially completed in 2011. |  | 2003 |  | Non-Investment
FIN | UNEP | Implementation of the RMP: train the technicians on good practices in refrigeration | Individual | LAC | HAI | REF | 39 | TRA | 05 | A | I | CFC | 29.9 | 29.9 | 0 | 0 | 2003-04-01 | 2004-01-01 | 2004-04-01 |  | 2008-12-01 | 2009-12-01 | 74200 | 0 | 74200 | 74200 | 100% | 0 | 0 |  | 9646 | 0 | 9646 | 0 | 0
FIN | UNEP | Implementation of the RMP: training for customs officers | Individual | LAC | HAI | REF | 39 | TRA | 07 | A | I | CFC | 13.3 | 13.3 | 0 | 0 | 2003-04-01 | 2003-12-01 | 2004-04-01 |  | 2010-12-01 | 2012-04-01 | 33100 | 0 | 33100 | 33100 | 100% | 0 | 0 |  | 4303 | 0 | 4303 | 0 | 0
FIN | UNEP | Preparation of country programme | Individual | LAC | HAI | SEV | 32 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-06-01 | 2002-04-01 |  | 2003-07-01 | 2005-06-01 | 60000 | -29000 | 31000 | 31000 | 100% | 0 | 0 |  | 7800 | -3770 | 4030 | 0 | 0
FIN | UNEP | Establishment of the Ozone Unit | Individual | LAC | HAI | SEV | 38 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-07-01 | 2003-12-01 |  | 2004-08-01 | 2004-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (phase I, years 2 and 3) | Individual | LAC | HAI | SEV | 43 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-10-01 | 2006-07-01 |  | 2006-09-01 | 2008-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase II) | Individual | LAC | HAI | SEV | 50 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-07-01 | 2008-11-01 |  | 2010-09-01 | 2011-09-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of the institutional strengthening project (phase III) | Individual | LAC | HAI | SEV | 59 | INS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-09-01 | 2011-11-01 | 2017-12-01 |  |  | 54167 | 45834 | 100001 | 70863 | 70.86% | 29138 | 0 | 2913.8 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Country reported CP data and Article 7 data. Haiti attended the Joint Network meeting of Latin America and the Caribbean in Chile in May-16, and the Caribbean Thematic meeting on ODS Alternatives Surveys in Barbados, Dec-16. HCFC quotas have been managed through Ministerial Order. Mission in Aug-16 to discuss Montreal Protocol implementation: it was agreed that the balance of this phase be used to hire a legal consultant in 2017 in order to enhance current quota system. Legal arrangements(actual/planned): . ___Initial stages of project implementation (actual/planned): ___ Intermediate goals achieved (actual/planned): ___ First disbursement date (actual/planned): ___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): yes___ If Yes, reasons for delay & action plan to resolve: political unrest have prevented discussion/signature of legal instruments. Frequent turn-over of Minister of Environment. UN Environment has provided frequent support and guidance to NOU in order to advance progress ___ If Yes, will delay have impact on project completion date (yes/no): yes___ Any ongoing problems (yes/no): yes ___ If Yes, is any action required by ExCom: no. ___ | Brief progress report (actual/planned): Draft ToR of legal consultant will be discussed in Mar-16. Reprogramming of balance into 2017. Advertisement in Inspira planned for Apr-17. Legal arrangements(actual/planned): ---/May-17. ___Initial stages of project implementation (actual/planned): ___ Intermediate goals achieved (actual/planned): ___ First disbursement date (actual/planned): ___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): yes___ If Yes, reasons for delay & action plan to resolve: political unrest have prevented discussion/signature of legal instruments. Frequent turn-over of Minister of Environment. UN Environment has provided frequent support and guidance to NOU in order to advance progress. Agreement -derived from mission in Aug-16, to hire a legal consultant to enhance the current Ministerial Order (quota system) with balance of IS ___ If Yes, will delay have impact on project completion date (yes/no): yes. Completion date has been revised to accomodate contracting process of legal consultant and finalization of activities___ Any ongoing problems (yes/no): yes ___ If Yes, is any action required by ExCom: no. ___
FIN | UNEP | Additional emergency assistance for institutional strengthening | Individual | LAC | HAI | SEV | 61 | INS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2012-04-01 | 2011-06-01 |  | 2014-12-01 | 2014-12-01 | 20000 | -1936 | 18064 | 17063.84 | 94.46% | 1000.16 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of the institutional strengthening project (phase IV: 11/2015-10/2017) | Individual | LAC | HAI | SEV | 75 | INS | 20 | A | I |  | 0 |  | 0 |  | 2015-11-01 |  | 2017-10-01 | 2018-10-01 |  |  | 128000 | 0 | 128000 | 0 | 0% | 128000 | 0 | 12800 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): SSFA text agreed in Nov-16. Translation into French in Dec.16 was necessary for the Minister to be able to sign the agreement. Funds to be reprogrammed into 2017. Legal arrangements(actual/planned): ---/Mar-16. ___Initial stages of project implementation (actual/planned): ___ Intermediate goals achieved (actual/planned): ___ First disbursement date (actual/planned): ---/Mar-16.___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): yes___ If Yes, reasons for delay & action plan to resolve: political unrest have prevented discussion/signature of legal instruments. Frequent turn-over of Minister of Environment. Interchange on text of SSFA and translation delayed signature in 2016. UN Environment has provided prompt responses/comments to SSFA. ___ If Yes, will delay have impact on project completion date (yes/no): yes.___ Any ongoing problems (yes/no): yes ___ If Yes, is any action required by ExCom: no. ___ | Brief progress report (actual/planned): Reprogramming of funds into 2017 completed in Jan-17. SSFA signed by UN Environment in Feb-17. Legal arrangements(actual/planned): Feb-17/Mar-16. ___Initial stages of project implementation (actual/planned): ___ Intermediate goals achieved (actual/planned): ___ First disbursement date (actual/planned): ---/Mar-16.___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): yes___ If Yes, reasons for delay & action plan to resolve: political unrest have prevented discussion/signature of legal instruments. Frequent turn-over of Minister of Environment. UN Environment has provided prompt responses/comments to SSFA. ___ If Yes, will delay have impact on project completion date (yes/no): yes. Completion date has been revised to reflect actual implementation timeframe___ Any ongoing problems (yes/no): yes ___ If Yes, is any action required by ExCom: no. ___
FIN | UNIDO | Project formulation of investment projects in the foam sector | Individual | LAC | HON | FOA | 21 | PRP | 03 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1998-04-01 | 1997-05-01 |  | 2000-12-01 | 2001-09-01 | 30000 | -11403 | 18597 | 18597.21 | 100% | -0.21 | 0 |  | 3900 | -1486 | 2414 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNIDO | Project preparation in the soil fumigation sector | Individual | LAC | HON | FUM | 33 | PRP | 09 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-03-01 | 2002-04-01 |  | 2002-11-01 | 2003-05-01 | 30000 | -482 | 29518 | 29517.96 | 100% | 0.04 | 0 |  | 3900 | -69 | 3831 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of methyl bromide in melon and banana production sector and tobacco seedling | Individual | LAC | HON | FUM | 37 | INV | 10 | A | I | MBR | 213 | 213 |  |  | 2002-07-01 | 2002-11-01 | 2008-12-01 |  | 2006-12-01 | 2007-09-01 | 1977454 | -6 | 1977448 | 1977448.01 | 100% | -0.01 | 0 |  | 227519 | 0 | 227519 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National methyl bromide phase-out plan, phase II (first tranche) | Multi-Year | LAC | HON | FUM | 50 | INV | 21 | A | I | MBR | 31.8 | 31.8 |  |  | 2006-11-01 | 2007-02-01 | 2007-11-01 |  | 2008-09-01 | 2008-12-01 | 600000 | 0 | 600000 | 600000.02 | 100% | -0.02 | 0 |  | 45000 | 0 | 45000 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National methyl bromide phase-out plan, phase II (second tranche) | Multi-Year | LAC | HON | FUM | 53 | INV | 24 | A | I | MBR | 47.5 | 47.5 |  |  | 2007-11-01 | 2007-12-01 | 2008-11-30 |  | 2009-10-01 | 2010-09-01 | 800000 | 0 | 800000 | 799999.95 | 100% | 0.05 | 0 |  | 60000 | 0 | 60000 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National methyl bromide phase-out plan, phase II (third tranche) | Multi-Year | LAC | HON | FUM | 56 | INV | 29 | A | I | MBR | 23.9 | 23.9 |  |  | 2008-11-01 | 2009-05-01 | 2009-11-30 |  | 2011-12-01 | 2012-05-01 | 300000 | -200 | 299800 | 299800.08 | 100% | -0.08 | 0 |  | 22500 | -15 | 22485 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National methyl bromide phase-out plan, phase II (fourth tranche) | Multi-Year | LAC | HON | FUM | 59 | INV | 31 | A | I | MBR | 20.4 | 20.4 |  |  | 2009-11-01 | 2010-07-01 | 2010-11-30 |  | 2011-12-01 | 2012-05-01 | 106301 | -45 | 106256 | 106255.65 | 100% | 0.35 | 0 |  | 7973 | -4 | 7969 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project preparation for a terminal phase-out management plan | Individual | LAC | HON | PHA | 51 | PRP | 22 | A | I |  | 0 | 0 |  |  | 2007-03-01 | 2007-08-01 | 2008-03-01 |  | 2008-09-01 | 2008-09-01 | 15000 | -95 | 14905 | 14904.8 | 100% | 0.2 | 0 |  | 1125 | -7 | 1118 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNEP | Project preparation for a terminal phase-out management plan | Individual | LAC | HON | PHA | 51 | PRP | 23 | A | I |  | 0 | 0 | 0 | 0 | 2007-03-01 | 2007-08-01 | 2008-03-01 |  | 2008-03-01 | 2010-12-01 | 15000 | -2500 | 12500 | 12500 | 100% | 0 | 0 |  | 1950 | -325 | 1625 | 0 | 0
FIN | UNIDO | Terminal phase-out management plan (first tranche) | Multi-Year | LAC | HON | PHA | 55 | INV | 26 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-10-01 | 2009-12-31 |  | 2010-12-01 | 2011-12-01 | 301000 | -229 | 300771 | 300771.18 | 100% | -0.18 | 0 |  | 22575 | -17 | 22558 | 0 | 0 | FIN |  |  |  | INV
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | HON | PHA | 55 | PRP | 25 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-02-01 | 2009-07-01 |  | 2011-12-01 | 2011-12-01 | 35000 | -17884 | 17116 | 17116 | 100% | 0 | 0 |  | 4550 | -2325.33 | 2224.67 | 0 | 0
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | LAC | HON | PHA | 55 | PRP | 28 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 |  | 2011-12-01 | 2011-12-01 | 115000 | -82 | 114918 | 114917.64 | 100% | 0.36 | 0 |  | 8625 | -6 | 8619 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | LAC | HON | PHA | 55 | TAS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-02-01 | 2009-12-01 |  | 2011-12-01 | 2011-12-01 | 146000 | 0 | 146000 | 146000 | 100% | 0 | 0 |  | 18980 | 0 | 18980 | 0 | 0
FIN | UNIDO | Terminal phase-out management plan (second tranche) | Multi-Year | LAC | HON | PHA | 59 | INV | 33 | A | I | CFC | 39.7 | 39.7 |  |  | 2009-11-01 | 2009-12-01 | 2010-11-30 |  | 2010-12-01 | 2011-12-01 | 37500 | -271 | 37229 | 37228.69 | 100% | 0.31 | 0 |  | 2813 | -21 | 2792 | 0 | 0 | FIN |  |  |  | INV
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | LAC | HON | PHA | 59 | TAS | 32 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2011-05-01 | 2010-11-01 |  | 2013-12-01 | 2014-12-01 | 52000 | -8732 | 43268 | 43268 | 100% | 0 | 0 |  | 6760 | -1135 | 5625 | 0 | 0
FIN | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | HON | PHA | 63 | INV | 34 | A | I |  | 0 | 0 |  |  | 2011-04-01 | 2011-09-01 | 2014-03-31 |  | 2014-07-01 | 2015-09-01 | 100000 | -165 | 99835 | 99834.79 | 100% | 0.21 | 0 |  | 7500 | -12 | 7488 | 0 | 0 | FIN |  |  |  | INV
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | HON | PHA | 63 | TAS | 35 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2012-04-01 | 2014-03-01 | 2018-12-01 |  |  | 75000 | 0 | 75000 | 5216 | 6.955% | 69784 | 0 | 6978.4 | 9750 | 0 | 678.08 | 9071.92 | 0 | Brief progress report (actual/planned): The NOU controls the ODSs trade, promotes the use of ODSs alternatives and conducts the monitoring of the R&R network. Legal arrangements (actual/planned): August 2013/Planned for May 2013. The SSFA expired in July 2015. The SSFA to implement activities belonging to HPMP (first and second tranche) signed in December 2016. First mission (actual/planned): March 2014/No specific date planned in the project document. TOR completed (actual/planned): N/A. First disbursement date (actual/planned): done. All funds disbursed (yes/no): No. Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: Delay is due to administrative reasons and changes at the high level authorities of the Ministry. RNC carried out two official missions (Mach 2014 and May 2016) to coordinate actions for speed up project implementation. If Yes, will delay have impact on project completion date (yes/no): Yes. Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: N/A. | Brief progress report (actual/planned): Monitoring the illegal trade, promoting the use of ODSs alternatives and the monitoring of the R&R network implemented as planned. Legal arrangements (actual/planned): August 2013/Planned for May 2013. The SSFA expired in July 2015. The SSFA to implement activities belonging to HPMP (first and second tranche) signed in December 2016. First mission (actual/planned): March 2014/No specific date planned in the project document. TOR completed (actual/planned): N/A. First disbursement date (actual/planned): Done. All funds disbursed (yes/no): No. Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: Delay is due to administrative reasons and changes at the high level authorities of the Ministry. RNC carried out two official missions (Mach 2014 and May 2016) to coordinate actions for speed up project implementation. If Yes, will delay have impact on project completion date (yes/no): Yes. Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: N/A. |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor the signing of the agreement by the Government and UNEP.
COM | UNIDO | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | HON | PHA | 70 | INV | 37 | A | I | HCFC | 1.2 | 0.8 |  |  | 2013-07-01 | 2013-09-01 | 2016-07-31 |  | 2015-12-01 | 2016-04-01 | 90000 | 0 | 90000 | 83787.83 | 93.1% | 6212.17 | 0 | 1 | 6750 | 0 | 6284 | 466 | 0 | The project was operationally completed. |  |  |  | INV
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | LAC | HON | PHA | 70 | TAS | 38 | A | I |  | 0.8 |  | 0 |  | 2013-07-01 |  | 2016-07-01 | 2018-12-01 |  |  | 50000 | 0 | 50000 | 0 | 0% | 50000 | 0 | 5000 | 6500 | 0 | 0 | 6500 | 0 | Brief progress report: The NOU has updated technical material for distribution among different stakeholders and guide the public institutions and consumers towards the selection of products, equipment and services free of HCFCs. Legal arrangements (actual/planned): Signed in December 2016/Initially planned for November 2013. The SSFA to implement HPMP I - first and second tranche was dully signed in December 2016. First mission (actual/planned): March 2014/No specific date planned in the project document. TOR completed (actual/planned): N/A. First disbursement date (actual/planned): No disbursement in 2016/Planned for December 2013. All funds disbursed (yes/no): No. Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: Delay is due to administrative reasons and changes at the high level authorities of the Ministry of Environment. RNC carried out two official missions (Mach 2014 and May 2016) to coordinate actions for speed up project implementation, including a meeting with the Minister of Environment. If Yes, will delay have impact on project completion date (yes/no): Yes. Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom? No. | Brief progress report: Some progress. Government of Honduras asked for UNEP administrative support to hire an international consultant to design an electronic data base for managing certified technician registers' lists and and ODSs trade data provided by suppliers. The TORs are already draft. Legal arrangements (actual/planned): Signed in December 2016/Initially planned for November 2013. The SSFA to implement HPMP I - first and second tranche was dully signed in December 2016. First cash advance of the new agreement released in March 2017. First mission (actual/planned): March 2014/No specific date planned in the project document. TOR completed (actual/planned): TOR of the consultant are drafted/no specific date. First disbursement date (actual/planned):March 2017/Planned for December 2013. All funds disbursed (yes/no): No. Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: Delay is due to administrative reasons and changes at the high level authorities of the Ministry of Environment. RNC carried out two official missions (Mach 2014 and May 2016) to coordinate actions for speed up project implementation, including a meeting with the Minister of Environment. If Yes, will delay have impact on project completion date (yes/no): Yes. Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom? No. |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor the signing of the agreement by the Government and UNEP.
COM | UNIDO | Verification report for stage I of HCFC phase-out management plan | Individual | LAC | HON | PHA | 73 | TAS | 39 | A | I |  | 0 | 0 |  |  | 2014-11-01 | 2014-12-01 | 2016-05-30 |  | 2015-12-01 |  | 30000 | 0 | 30000 | 29487.93 | 98.29% | 512.07 | 0 | 1 | 2700 | 0 | 2654 | 46 | 0 | The project was operationally completed. |  |  |  | NON-INV
ONG | UNIDO | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | LAC | HON | PHA | 76 | INV | 42 | A | I |  | 0 | 0 |  |  | 2016-05-01 | 2016-08-01 | 2018-12-31 | 2018-12-31 |  |  | 90000 | 0 | 90000 | 18665.07 | 20.74% | 71334.93 | 28975.35 | 30000 | 6750 | 0 | 1400 | 5350 | 2173 | - The project was approved in 2016 by the 76th Meeting of the ExCom. - Activities carried out in 2016: a) Monitoring the ODS (non-ODS) refrigerant consumption in the country. The country has very strict monitoring regime on the import of used equipment containing HCFCs and controls all the borders. b) Public awareness program. c) Good refrigeration practices training program continuation. d) Establishment of program for end users and e) establishment of a refrigerant reclaiming center. - No delay in implementation - No recurring problem - No impact on project completion date - No action required by Executive Committee | - Tools to establish a reclaiming center and some required to upgrade the actual centers were purchased. - National expert was hired to support the project implementation activities. Action towards next goals: - The tools and reclaiming unit is expected to be in the country in May 2017. - A reclaiming center will be established in Tegucigalpa training center aiming end users as provision of refrigerant reclaiming service. - No delay in implementation - No recurring problem - No impact on project completion date - No action required by Executive Committee |  |  | INV
ONG | UNEP | HCFC phase-out management plan (stage I, third tranche) | Multi-year | LAC | HON | PHA | 76 | TAS | 43 | A | I |  | 0 |  | 0 |  | 2016-05-01 |  | 2018-05-01 | 2018-12-01 |  |  | 50000 | 0 | 50000 | 0 | 0% | 50000 | 0 | 5000 | 6500 | 0 | 0 | 6500 | 0 | Brief progress report: Newly approved. Legal arrangements (actual/planned): No/September 2016. First mission (actual/planned): No specific date established in the project document. TOR completed (actual/planned): N/A. First disbursement date (actual/planned): No disbursement/Planned for December 2016. All funds disbursed? (yes/no): No. Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: Project Funds were not be transferred to UNEP until conditions of the approval were met. Action taken was to speed up the signature of the agreement for the HPMP second tranche. If Yes, will delay have impact on project completion date? Yes. Any ongoing problems? (yes/no): No. If Yes, is any action required by ExCom? No | Brief progress report: UNEP is awaiting for funds releasing since conditions are met in December 2016. Legal arrangements (actual/planned): No/September 2016. First mission (actual/planned): No specific date established in the project document. TOR completed (actual/planned): N/A. First disbursement date (actual/planned): No disbursement/Planned for December 2016. All funds disbursed? (yes/no): No. Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: In 2016, Project Funds were not transferred to UNEP until conditions of the approval were met. Currently, conditions are met. If Yes, will delay have impact on project completion date? Yes. Any ongoing problems? (yes/no): No. If Yes, is any action required by ExCom? No
FIN | UNIDO | Preparation of a refrigerant management plan | Individual | LAC | HON | REF | 24 | PRP | 04 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-06-01 | 1999-04-01 |  | 1998-11-01 | 2000-07-01 | 30000 | -7251 | 22749 | 22749 | 100% | 0 | 0 |  | 3900 | -947 | 2953 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: national recovery and recycling project | RMP | LAC | HON | REF | 28 | TAS | 07 | A | I | CFC | 14.2 | 14.2 |  |  | 1999-07-01 | 2000-01-01 | 2001-08-01 |  | 2003-12-01 | 2004-12-01 | 245900 | -951 | 244949 | 244949.04 | 100% | -0.04 | 0 |  | 31967 | -174 | 31793 | 0 | 0 | FIN |  |  | 2003-06-01 | INV
FIN | UNIDO | Refrigerant management plan: customs training | RMP | LAC | HON | REF | 28 | TRA | 05 | A | I | CFC | 0 | 0 |  |  | 1999-07-01 | 2002-04-01 | 2001-08-01 |  | 2003-12-01 | 2004-09-01 | 38250 | 0 | 38250 | 38250 | 100% | 0 | 0 |  | 4973 | 0 | 4973 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: phase I: training of trainers in good refrigerant management practices; phase II: national technicians training | RMP | LAC | HON | REF | 28 | TRA | 06 | A | I | CFC | 0 | 0 |  |  | 1999-07-01 | 2000-01-01 | 2001-08-01 |  | 2003-12-01 | 2004-09-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0 | FIN
FIN | UNEP | Preparation of the RMP update proposal | RMP Update | LAC | HON | REF | 41 | PRP | 12 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-08-01 | 2004-12-01 |  | 2004-12-01 | 2008-12-01 | 15000 | -628 | 14372 | 14372 | 100% | 0 | 0 |  | 1950 | -82 | 1868 | 0 | 0
FIN | UNDP | Preparation of the RMP update proposal | RMP-Component | LAC | HON | REF | 41 | PRP | 13 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-07-01 | 2004-12-01 |  | 2005-12-01 | 2008-09-01 | 15000 | -2000 | 13000 | 13000 | 100% | 0 | 0 | 0 | 1125 | -150 | 975 | 0 | 0 | Completed in 2005. Financially Completed in 2008. |  | 2003 |  | Investment
FIN | UNDP | Implementation of the RMP: technical assistance programme for the promotion of good practices and recovery and recycling | RMP-Component | LAC | HON | REF | 44 | TAS | 15 | N | I | CFC | 138.6 | 138.6 | 0 | 0 | 2004-12-01 | 2007-11-01 | 2007-12-01 |  | 2009-11-01 | 2011-11-01 | 150000 | -71.56 | 149928.44 | 149928 | 100% | 0.44 | 0 | 0 | 13500 | -6.44 | 13493.52 | 0.04 | 0 | Completed in 2009. |  | 2004 |  | Investment
FIN | UNEP | Implementation of the RMP update: programme for prevention of illegal ODS trade | Individual | LAC | HON | REF | 44 | TAS | 17 | A | I | CFC | 21.3 | 21 | 0 | 0 | 2004-12-01 | 2006-08-01 | 2007-12-01 |  | 2009-06-01 | 2009-12-01 | 23000 | 0 | 23000 | 23000 | 100% | 0 | 0 |  | 2990 | 0 | 2990 | 0 | 0
FIN | UNEP | Implementation of the RMP update: programme for permanent monitoring of the RMP | Individual | LAC | HON | REF | 44 | TAS | 18 | A | I | CFC | 35.1 | 35.1 | 0 | 0 | 2004-12-01 | 2006-08-01 | 2007-12-01 |  | 2009-12-01 | 2011-03-01 | 38000 | -5630 | 32370 | 32370 | 100% | 0 | 0 |  | 4940 | -731.9 | 4208.1 | 0 | 0
FIN | UNEP | Implementation of the RMP update: programme for certification and licensing of refrigeration technicians | Individual | LAC | HON | REF | 44 | TRA | 16 | A | I | CFC | 86.9 | 86.9 | 0 | 0 | 2004-12-01 | 2007-09-01 | 2007-12-01 |  | 2009-12-01 | 2010-12-01 | 94000 | 0 | 94000 | 94000 | 100% | 0 | 0 |  | 12220 | 0 | 12220 | 0 | 0
FIN | UNEP | Country programme preparation | Individual | LAC | HON | SEV | 13 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-12-01 | 1995-10-01 |  | 1996-06-01 | 1999-03-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNEP | Establishment of the Ozone Unit Cell for the institutional strengthening programme | Individual | LAC | HON | SEV | 20 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-06-01 | 1999-10-01 |  | 2001-06-01 | 2001-12-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 |  | 8580 | 0 | 8580 | 0 | 0 |  |  |  | 2000-03-01
FIN | UNEP | Renewal of institutional strengthening | Individual | LAC | HON | SEV | 32 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-07-01 | 2003-01-01 |  | 2003-05-01 | 2003-12-01 | 44000 | 0 | 44000 | 44000 | 100% | 0 | 0 |  | 5720 | 0 | 5720 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project | Individual | LAC | HON | SEV | 40 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2003-07-01 | 2005-07-01 |  | 2005-07-01 | 2007-02-01 | 57200 | -1 | 57199 | 57199 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | LAC | HON | SEV | 45 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-07-01 | 2007-04-01 |  | 2007-05-01 | 2008-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | LAC | HON | SEV | 50 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-07-01 | 2008-11-01 |  | 2010-06-01 | 2011-06-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VI) | Individual | LAC | HON | SEV | 57 | INS | 30 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-09-01 | 2011-03-01 |  | 2012-12-01 | 2013-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of the institutional strengthening project (phase VII: 1/2013-12/2014) | Individual | LAC | HON | SEV | 68 | INS | 36 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-08-01 | 2014-02-01 | 2017-12-01 |  |  | 60000 | 0 | 60000 | 26407 | 44.01% | 33593 | 33593 | 3359.3 | 0 | 0 | 0 | 0 | 0 | Brief progress report: The SSFA (agreement) implementation is progressing with some delays. More than 90% of funds were transferred to the country. Expenditure and progress reports are due by the Government to issue the last cash advance. Legal arrangements (actual/planned): August 2013/Planned for May 2013. Initial stages of project implementation (actual/planned): N/A since Project currently ongoing. Intermediate goals achieved (actual/planned): Goals are achieved as planned for the year. NOO has been collecting ODS data and cross-checking information to prepare the 2015 Country Programme and Article 7 reports. Celebration of International Ozone Day and other public awareness events carried out. The HCFCs license system continues being managed by the NOU. NOU is responsible for the HPMP implementation. Project completion and follow up: Project ongoing. First disbursement date (actual/planned): September 2013/June 2013. All funds disbursed? (yes/no): No. Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: Changes of high level authorities in the Ministry of Environment (which happens at least twice per each presidential mandate) caused an impact in the NOU performance. Although the NOU has not been changed with new authorities, the changes in the management lines demanded the re-introduction/re-launch of the Multilateral Fund projects implementation. Furthermore, approval procedures for procurement and contracts are revised when new authorities are on board. Consequently, due to administrative reasons, delays have been accumulated. In order to provide support; RNC met the new Minister of Environment in March 2014 and May 2016. If Yes, will delay have impact on project completion date? Yes, late start of the project and administrative changes will result in a delayed project completion date. Any ongoing problems? (yes/no): No. If Yes, is any action required by ExCom? N/A. | Brief progress report: The SSFA (agreement) implementation is progressing with some delays. More than 90% of funds were transferred to the country. Expenditure and progress reports submitted by the Government. UNEP is processing reports to issue the last cash advance. Legal arrangements (actual/planned): August 2013/Planned for May 2013. Initial stages of project implementation (actual/planned): N/A since Project currently ongoing. Intermediate goals achieved (actual/planned): N/A. Project completion and follow up: Project ongoing. First disbursement date (actual/planned): September 2013/June 2013. All funds disbursed? (yes/no): No. Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: Changes of high level authorities in the Ministry of Environment (which happens at least twice per each presidential mandate) caused an impact in the NOU performance. Although the NOU has not been changed with new authorities, the changes in the management lines demanded the re-introduction/re-launch of the Multilateral Fund projects implementation. Furthermore, approval procedures for procurement and contracts are revised when new authorities are on board. Consequently, due to administrative reasons, delays have been accumulated. In order to provide support; RNC met the new Minister of Environment in March 2014 and May 2016. If Yes, will delay have impact on project completion date? Yes, late start of the project and administrative changes will result in a delayed project completion date. Any ongoing problems? (yes/no): No. If Yes, is any action required by ExCom? N/A.
ONG | UNIDO | Survey of ODS alternatives at the national level | Individual | LAC | HON | SEV | 74 | TAS | 40 | A | I |  | 0 | 0 |  |  | 2015-05-01 | 2016-02-01 | 2016-05-31 | 2017-11-17 |  |  | 70000 | 0 | 70000 | 19075.63 | 27.25% | 50924.37 | 1233.56 | 50900 | 6300 | 0 | 0 | 6300 | 111.0204 | International bidding took place, the offers were received in August 2016. Contract was awarded in September 2016 and the preparation of the survey got started. Delay in implementation: Yes, delay in the survey carry out activities due to non availability of good service suppliers in the country. - Impact on project completion date: Yes | Survey was carried out and final report is under preparation. The final report is expected to be submitted to the 79th ExCom. |  |  | NON-INV
ONG | UNEP | Extension of the institutional strengthening project (phase VIII: 1/2016-12/2017) | Individual | LAC | HON | SEV | 75 | INS | 41 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-09-01 | 2017-12-01 | 2018-12-01 |  |  | 85000 | 0 | 85000 | 19768 | 23.26% | 65232 | 65232 | 6523.2 | 0 | 0 | 0 | 0 | 0 | Brief progress report: Some progress. Legal arrangements (actual/planned): July 2017/March 2016. Initial stages of project implementation (actual/planned): Project implementation has been re-scheduled in order to start during the last quarter of 2016. Intermediate goals achieved (actual/planned): Application of the national ODS's legislative framework to keep country in compliance with phase-out targets. Project completion and follow up: N/A. First disbursement date (actual/planned): Sep 2016/May 2016. All funds disbursed (yes/no): No. Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: There were funds available from the IS Project phase VII. NOU accelerated the report of those resources and did follow up with the new agreement signature. If Yes, will delay have impact on project completion date (yes/no): Yes. Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: N/A. | Brief progress report: Some progress. Legal arrangements (actual/planned): July 2017/March 2016. Initial stages of project implementation (actual/planned): Project implementation has been re-scheduled in order to start during the last quarter of 2016. Intermediate goals achieved (actual/planned): Goals are achieved as planned for the year. NOO has been collecting ODS data and cross-checking information to prepare the 2016 Country Programme and Article 7 reports. The HCFCs license system continues being managed by the NOU. NOU is responsible for the HPMP implementation. Project completion and follow up: N/A. First disbursement date (actual/planned): Sep 2016/May 2016. All funds disbursed (yes/no): No. Any delay?(yes/no): Yes. If Yes, reasons for delay & action plan to resolve: There were funds available from the IS Project phase VII. NOU accelerated the report of those resources and did follow up with the new agreement signature. If Yes, will delay have impact on project completion date (yes/no): Yes. Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: N/A.
FIN | IBRD | Safety and technical programme to assist manufacturers of hydrocarbon propelled aerosol products | Individual | ASP | IDS | ARS | 11 | TAS | 10 | N | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1996-07-01 | 1995-11-01 |  | 1998-11-01 | 1998-11-01 | 238000 | -18915 | 219085 | 219085 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Activities on Work program had been completed. Technical audit has been carried out. Draft PCR has been submitted. Remaining grant returned to trust fund. Project completed and closed. 3% agency fee incl. |  |  | 1997-06-01 | Non-INV | 0
FIN | IBRD | Conversion and aerosol filling center at PT Candi Swadaya Sentosa | Individual | ASP | IDS | ARS | 22 | INV | 61 | N | I | CFC | 460 | 460 | 0 | 0 | 1997-05-01 | 2001-07-01 | 1999-06-01 |  | 2005-05-01 | 2004-10-01 | 1175340 | 0 | 1175340 | 1175340 | 100% | 0 | 0 |  | 152794 | 0 | 152794 | 0 | 0 | Project financially and physically completed. |  |  | 2002-06-01 | INV | 0
FIN | IBRD | National strategy for phasing out the use of CFC in the aerosol sector: Policies and actions, technical assistance, and enterprise investment initiatives | Multiyear | ASP | IDS | ARS | 44 | INV | 166 | N | I | CFC | 70 | 70 | 0 | 0 | 2004-12-01 | 2005-12-01 | 2008-05-01 |  | 2010-06-01 | 2010-06-01 | 371910 | 0 | 371910 | 371910 | 100% | 0 | 0 |  | 27893 | 0 | 27893 | 0 | 0 | Project successfully completed and closed in Jun 2010. |  |  |  | INV | 0
FIN | UNDP | National strategy for phasing out the use of CFC in the aerosol: conversion from CFC to hydrocarbon aerosol propellants at P.T Yulia | Multi-year | ASP | IDS | ARS | 44 | INV | 167 | N | I | CFC | 80 | 80 | 0 | 0 | 2004-12-01 | 2005-11-01 | 2005-12-01 |  | 2006-06-01 | 2011-12-01 | 224000 | -42113 | 181887 | 181887 | 100% | 0 | 0 | 0 | 13440 | -2526.78 | 10913.22 | 0 | 0 | Completed in 2006. Financially completed in 2011. |  | 2004 |  | Investment
FIN | IBRD | Project preparation funds for the development of a phase-out plan for the MDI sector |  | ASP | IDS | ARS | 46 | PRP | 170 | A | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2006-09-01 | 2006-07-01 |  | 2008-11-01 | 2008-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 |  | 3375 | 0 | 3375 | 0 | 0 | TA for an MDI strategy submitted and approved at the 56th ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | Technical assistance to implement national transition strategy to CFC-free MDI | Individual | ASP | IDS | ARS | 56 | TAS | 184 | N | I | CFC | 16.3 | 16.3 | 0 | 0 | 2008-11-01 | 2009-12-01 | 2010-12-31 |  | 2010-12-01 | 2010-12-01 | 155000 | 0 | 155000 | 155000 | 100% | 0 | 0 |  | 13950 | 0 | 13950 | 0 | 0 | Project completed as scheduled on the basis of workplan including development of database for registration of products, review of relevant policy and regulations within Agency for Drug and Food Control, preparation of a guideline for using CFC-free MDIs; workshop held for stakeholders and relevant leaflets produced. |  |  |  | INV | 0
FIN | IBRD | Preparation for pilot demonstration project on ODS waste management and disposal |  | ASP | IDS | DES | 57 | PRP | 187 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2013-12-01 | 2010-12-31 |  | 2014-06-01 | 2014-06-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 3750 | 0 | 3750 | 0 | 0 | A study on 'The Establishment of a Public-Private Financing System for Disposal of ODS for Indonesia' was completed and accepted by the client in Jun 2014. The report was submitted to the 71st ExCom as an information document. |  |  |  | Non-INV | 0
ONG | UNDP | Preparation for HCFC phase-out investment activities (stage II) (fire-fighting manufacturing sector) | Individual | ASP | IDS | FFI | 72 | PRP | 205 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 | 2016-01-01 | 2016-05-01 | 2017-05-01 |  |  | 50000 | 0 | 50000 | 1738.97 | 3.478% | 48261.03 | 0 | 19304.412 | 3500 | 0 | 121.7279 | 3378.2721 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): As per AWP work completed.In terms of ATLAS it is still going on. Prodoc signed (actual/planned, yes/no and date):Letter of Authorisation sent 4 Nov 2014 Missions undertaken (actual/planned):1 TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: signed earlier First disbursement date (actual/planned): 42387Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | Project is still ON-GOING, to be Operationally and Financially Closed, by HQ. |  |  | Non-Investment
FIN | IBRD | Elimination of CFC-11/12 in the manufacture of extruded polystyrene and polyethylene foam sheet at P.T. Tulus Bakti Sempurna | Individual | ASP | IDS | FOA | 11 | INV | 07 | N | I | CFC | 95 | 95 | 0 | 0 | 1993-11-01 | 1997-01-01 | 1994-11-01 |  | 1998-09-01 | 1998-12-01 | 416000 | -22725 | 393275 | 393275 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Financial and technical requirements of the project have been completed. PCR had been submitted. Project is closed. 3% agency fee incl. |  |  | 1997-12-01 | INV | 0
FIN | IBRD | Elimination of CFC-12 in the manufacture of extruded polystyrene and polyethylene foam sheet at P.T. Intitri Muliatama | Individual | ASP | IDS | FOA | 11 | INV | 08 | N | I | CFC | 119 | 119 | 0 | 0 | 1993-11-01 | 1996-12-01 | 1994-11-01 |  | 1998-09-01 | 1998-09-01 | 387000 | -62963 | 324037 | 324037 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Financial and technical requirements of the project have been completed. PCR had been submitted. Project is closed. 3% agency fee incl. |  |  | 1997-12-01 | INV | 0
FIN | IBRD | Elimination of CFC-11 in the manufacture of polyurethane foams at P.T. Dasa Windu Agung | Individual | ASP | IDS | FOA | 11 | INV | 09 | N | I | CFC | 122 | 122 | 0 | 0 | 1993-11-01 | 1995-12-01 | 1995-04-01 |  | 1998-08-01 | 1998-08-01 | 1733000 | 0 | 1733000 | 1733000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Run commercially. Technical audit had been completed and equipment disposal had been carried out. Project is closed. 3% agency fee incl. |  |  | 1997-06-01 | INV | 0
FIN | IBRD | Elimination of CFC-11 in the manufacture of polyurethane foams at P.T. Foamindo Industri Uretan | Individual | ASP | IDS | FOA | 11 | INV | 12 | N | I | CFC | 80 | 80 | 0 | 0 | 1993-11-01 | 1998-01-01 | 1994-11-01 |  | 2002-04-01 | 2002-04-01 | 176000 | 0 | 176000 | 176000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed in Apr. 02. Draft PCR submitted to WB for review. |  |  | 2000-12-01 | INV | 0
FIN | IBRD | Technical assistance programme for small CFC users in the flexible polyurethane foam sector | Individual | ASP | IDS | FOA | 11 | TAS | 11 | N | I | CFC | 100 | 286 | 0 | 0 | 1993-11-01 | 1996-11-01 | 1995-11-01 |  | 1998-05-01 | 1998-05-01 | 1600000 | -1987 | 1598013 | 1598013 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project technically and financial completed and closed. PCR had been submitted. 3% agency fee incl. |  |  | 1997-12-01 | INV | 0
FIN | IBRD | Elimination of CFC-11 in the manufacture of flexible polyurethane foam at P.T. Erlangga Trimanunggal Kusumah | Individual | ASP | IDS | FOA | 13 | INV | 16 | N | I | CFC | 100 | 100 | 0 | 0 | 1994-07-01 | 1997-10-01 | 1995-07-01 |  | 2002-04-01 | 2002-04-01 | 379000 | 0 | 379000 | 379000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project was completed in April 2002. Draft PCR has been submitted to WB for review. |  |  | 2000-12-01 | INV | 0
FIN | IBRD | Elimination of CFC-11 in the manufacture of flexible polyurethane foam at P.T. Royal Abadi Sejahtera | Individual | ASP | IDS | FOA | 13 | INV | 18 | N | I | CFC | 120 | 120 | 0 | 0 | 1994-07-01 | 1997-06-01 | 1995-07-01 |  | 1997-06-01 | 1997-06-01 | 237500 | -3846 | 233654 | 233654 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and closed. PCR had been submitted. 3% agency fee incl. |  |  | 1997-12-01 | INV | 0
FIN | IBRD | Elimination of CFC-11 in the manufacture of polyurethane foam sheet at Positive Foam Industry | Individual | ASP | IDS | FOA | 15 | INV | 19 | N | I | CFC | 90 | 90 | 0 | 0 | 1994-12-01 | 1997-10-01 | 1995-12-01 |  | 2002-04-01 | 2002-04-01 | 449000 | 0 | 449000 | 449000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed in April 2002. Draft PCR had been submitted to WB for review. |  |  | 2000-12-01 | INV | 0
FIN | IBRD | Elimination of CFC-11 in the manufacture of polyurethane foam sheet at Multi Karya Makmur | Individual | ASP | IDS | FOA | 15 | INV | 20 | N | I | CFC | 200 | 200 | 0 | 0 | 1994-12-01 | 1997-03-01 | 1995-12-01 |  | 2003-06-01 | 2003-07-01 | 123700 | -768 | 122932 | 122932.14 | 100% | -0.14 | -0.14 |  | 0 | 0 | 0 | 0 | 0 | Project physically and financially completed. |  |  | 1999-12-01 | INV | 0
FIN | IBRD | Elimination of CFC-12 in the manufacture of extruded polyethylene and polystyrene foam sheet at PT Inter Foamindosentra | Individual | ASP | IDS | FOA | 15 | INV | 21 | N | I | CFC | 120 | 120 | 0 | 0 | 1994-12-01 | 1997-03-01 | 1995-12-01 |  | 1998-09-01 | 2000-10-01 | 390000 | -154145 | 235855 | 235855 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted. Balance returned to the MLF at the 33rd ExCom. |  |  | 1997-12-01 | INV | 0
CLO | IBRD | Elimination of CFC-11 in the manufacture of polyurethane foam sheet at Musimassejahtera Abadi | Individual | ASP | IDS | FOA | 15 | INV | 30 | N | I | CFC | 114 | 50 | 0 | 0 | 1994-12-01 | 1996-11-01 | 1995-12-01 |  |  | 2000-12-01 | 390000 | -356351 | 33649 | 33649 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project cancelled at 31st meeting and $154,145 returned at the 32nd meeting. |  |  | 1997-12-01 | INV | 0
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF foam for cold storage at P.T. Fibrindo Carsa Pratama | Individual | ASP | IDS | FOA | 17 | INV | 32 | A | I | CFC | 11 | 11 | 0 | 0 | 1995-07-01 | 1997-03-01 | 1996-06-01 |  | 1997-12-01 | 2000-07-01 | 55000 | -5382 | 49618 | 49618 | 100% | 0 | 0 | 0 | 7150 | -699.66 | 6450.34 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF for coolers/thermoware at P.T. Perdana Merah Delima | Individual | ASP | IDS | FOA | 18 | INV | 34 | A | R | CFC | 27 | 27 | 0 | 0 | 1995-11-01 | 1996-10-01 | 1996-11-01 |  | 1996-10-01 | 1999-12-01 | 173000 | -1 | 172999 | 172999 | 100% | 0 | 0 | 0 | 22490 | -0.13 | 22489.87 | 0 | 0 | Completed in 1996. Financially completed in 1999. |  | 1995 |  | Investment
FIN | UNIDO | Investment project for phasing out ODS at PT Naviri Kencana Perdana | Individual | ASP | IDS | FOA | 19 | INV | 43 | A | I | CFC | 47.8 | 47.8 |  |  | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1998-12-01 | 2000-12-01 | 377382 | -402 | 376980 | 376980 | 100% | 0 | 0 |  | 49060 | -130 | 48930 | 0 | 0 | FIN
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PU foam sandwich panels at P.T. Alpine Cool | Individual | ASP | IDS | FOA | 20 | INV | 44 | A | I | CFC | 13.8 | 13.8 | 0 | 0 | 1996-10-01 | 1998-11-01 | 1998-09-01 |  | 2001-12-01 | 2003-04-01 | 84000 | -268 | 83732 | 83732 | 100% | 0 | 0 | 0 | 10920 | -34.84 | 10885.16 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1996 | 1999-12-01 | Investment
CLO | IBRD | Elimination of CFC-12 in the manufacture of extruded polyethylene foam sheet at PT. Toha Kencana Mas | Individual | ASP | IDS | FOA | 20 | INV | 45 | N | I |  | 0 | 0 | 0 | 0 | 1996-10-01 |  | 1997-10-01 |  |  | 1999-07-01 | 109930 | -109930 | 0 | 0 | #DIV/0! | 0 | 0 |  | 14290.9 | -14291 | 0 | -0.1 | -0.1 | Project is cancelled. Funds returned to 28th meeting. |  |  | 1997-10-01 | INV | 0
FIN | UNDP | Conversion to CFC free technology in the manufacture of integral skin molded polyurethane foam at PT Dithon Urethane | Individual | ASP | IDS | FOA | 20 | INV | 46 | A | I | CFC | 16.5 | 16.5 | 0 | 0 | 1996-10-01 | 1997-03-01 | 1998-09-01 |  | 1998-02-01 | 2000-07-01 | 184000 | -295 | 183705 | 183705 | 100% | 0 | 0 | 0 | 23920 | -38.35 | 23881.65 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PU foam sandwich panels at P.T. Mentari Metal Pratama | Individual | ASP | IDS | FOA | 20 | INV | 47 | A | I | CFC | 8.8 | 8.8 | 0 | 0 | 1996-10-01 | 1996-11-01 | 1998-09-01 |  | 1999-11-01 | 2001-12-01 | 47000 | -693 | 46307 | 46307 | 100% | 0 | 0 | 0 | 6110 | -90.25 | 6019.7549 | -0.0049 | 0 | Completed in 1999. Financially completed in 2001. |  | 1996 |  | Investment
FIN | UNIDO | Phasing out CFC-11 at PT Winnerfoam Abadi | Individual | ASP | IDS | FOA | 22 | INV | 56 | A | I | CFC | 40 | 40 |  |  | 1997-05-01 | 1997-09-01 | 1998-10-01 |  | 1998-12-01 | 2000-12-01 | 79472 | -1287 | 78185 | 78185 | 100% | 0 | 0 |  | 10331 | -183 | 10148 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Panca Duta foam industry | Individual | ASP | IDS | FOA | 22 | INV | 57 | A | I | CFC | 45 | 45 |  |  | 1997-05-01 | 1997-09-01 | 1998-10-01 |  | 1998-12-01 | 2001-12-01 | 86955 | -621 | 86334 | 86334.05 | 100% | -0.05 | 0 |  | 11304 | -98 | 11206 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at PT Elastino Satyajaya flexible polyurethane foam plant | Individual | ASP | IDS | FOA | 22 | INV | 58 | A | I | CFC | 18 | 18 |  |  | 1997-05-01 | 1997-09-01 | 1998-10-01 |  | 1998-12-01 | 2000-12-01 | 75943 | 0 | 75943 | 75943 | 100% | 0 | 0 |  | 9873 | -5 | 9868 | 0 | 0 | FIN
FIN | UNDP | Conversion to CFC free technology in the manufacture of integral skin molded polyurethane foam at Plysindo Inter Mouldi (PIM) | Individual | ASP | IDS | FOA | 22 | INV | 60 | A | I | CFC | 4.5 | 4.5 | 0 | 0 | 1997-05-01 | 1997-09-01 | 1999-06-01 |  | 1997-09-01 | 2001-12-01 | 75870 | -1848 | 74022 | 74022 | 100% | 0 | 0 | 0 | 9863.1 | -240.24 | 9622.86 | 0 | 0 | Completed in 1997. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid PUF insulated products at UD Samrow Foam | Individual | ASP | IDS | FOA | 23 | INV | 63 | A | I | CFC | 22.7 | 22.7 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2000-10-01 | 2001-12-01 | 110000 | 0 | 110000 | 110000 | 100% | 0 | 0 | 0 | 14300 | 0 | 14300 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC -free technology in the manufacture of rigid polyurethane foam (panels, blocks) at PT Aneka Cool Citratama | Individual | ASP | IDS | FOA | 23 | INV | 65 | A | I | CFC | 32.7 | 32.7 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 2001-12-01 | 2003-04-01 | 232225 | -10678 | 221547 | 221547 | 100% | 0 | 0 | 0 | 30189.25 | -1388.14 | 28801.11 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (thermoware) at PT Dilihan Glory | Individual | ASP | IDS | FOA | 23 | INV | 67 | A | I | CFC | 13.1 | 13.1 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 1999-11-01 | 2000-12-01 | 102200 | -14362 | 87838 | 87838 | 100% | 0 | 0 | 0 | 13286 | -1867.06 | 11418.94 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (spray foam) at PT Ferrarindo Multi Sarana | Individual | ASP | IDS | FOA | 23 | INV | 68 | A | I | CFC | 7.7 | 7.7 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1999-12-01 |  | 1998-03-01 | 2000-07-01 | 32900 | -315.94 | 32584.06 | 32584 | 100% | 0.06 | 0 | 0 | 4277 | -41.07 | 4235.92 | 0.01 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
CLO | UNDP | Conversion to CFC-free techology in the manufacture of rigid PUF insulated thermoware at PT Langgeng Makmur Plastic Industry Ltd. | Individual | ASP | IDS | FOA | 23 | INV | 70 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1999-12-01 |  |  | 2001-12-01 | 142000 | -142000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 18460 | -18460 | 0 | 0 | 0 | Canceled in 1999. Financially Completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible cold cured moulded and integral skin PUF at PT Archigramma | Individual | ASP | IDS | FOA | 23 | INV | 71 | A | I | CFC | 16.5 | 16.5 | 0 | 0 | 1997-11-01 | 1999-12-01 | 1999-12-01 |  | 2001-12-01 | 2003-04-01 | 106625 | -14881 | 91744 | 91744 | 100% | 0 | 0 | 0 | 13861.25 | -1934.53 | 11926.72 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1997 |  | Investment
FIN | IBRD | Elimination of CFC-12 in the manufacture of extruded polethylene foam sheet at PT. Tara Guna Foam | Individual | ASP | IDS | FOA | 23 | INV | 73 | N | I | CFC | 35 | 35 | 0 | 0 | 1997-11-01 | 2001-10-01 | 1999-12-01 |  | 2001-12-01 | 2002-10-01 | 287700 | -34630.97 | 253069.03 | 253069.03 | 100% | 0 | 0 |  | 37401 | -4502.03 | 32898.97 | 0 | 0 | Project technically and financially completed. PCR submitted to WB. |  |  | 2001-02-01 | INV | 0
CLO | IBRD | Elimination of CFC-11 in the manufacture of flexible polyurethane foam (slabstock) at PT. Irc Inoac Indonesia | Individual | ASP | IDS | FOA | 23 | INV | 75 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1999-12-01 |  |  | 2003-04-01 | 412900 | -412900 | 0 | 0 | #DIV/0! | 0 | 0 |  | 53677 | -53677 | 0 | 0 | 0 | Cancelled - 38th ExCom |  |  |  | INV | 0
CLO | IBRD | Elimination of CFC-11 in the manufacture of flexible polyurethane foam (slabstock) at PT Sea Horse Maspion Indonesia | Individual | ASP | IDS | FOA | 23 | INV | 76 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1999-12-01 |  |  | 2001-12-01 | 532200 | -532200 | 0 | 0 | #DIV/0! | 0 | 0 |  | 69186 | -63864 | 5322 | 0 | 0 | Project cancelled at the 35th ExCom and funds to be returned at the 36th ExCom. |  |  |  | INV | 0
FIN | IBRD | Flexible boxfoam. Technical assistance programme for SMEs at Indonesian Foam Association (AFI) | Individual | ASP | IDS | FOA | 23 | INV | 77 | N | I | CFC | 954 | 954 | 0 | 0 | 1997-11-01 | 2002-12-01 | 1999-12-01 |  | 2007-01-01 | 2007-03-01 | 4060640 | -467626.72 | 3593013.28 | 3593013.28 | 100% | 0 | 0 |  | 527883 | -60791.46 | 467091.54 | 0 | 0 | Project is physically and financially completed |  |  | 2002-12-01 | INV | 0
FIN | IBRD | Technical assistance programme for SMEs for flexible polyurethane foam at Indonesian Foam Association (AFI) | Individual | ASP | IDS | FOA | 23 | INV | 78 | N | I | CFC | 370 | 370 | 0 | 0 | 1997-11-01 | 2002-12-01 | 1999-12-01 |  | 2005-04-01 | 2005-12-01 | 3538400 | -1983523.96 | 1554876.04 | 1554876.04 | 100% | 0 | 0 |  | 459992 | -257858.12 | 202133.88 | 0 | 0 | Project completed. |  |  | 2002-12-01 | INV | 0
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid PUF spray insulation at Karya Cipta Semesta | Individual | ASP | IDS | FOA | 23 | INV | 81 | A | I | CFC | 16.4 | 16.4 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1999-12-01 |  | 1998-03-01 | 2000-12-01 | 68000 | 0 | 68000 | 68000 | 100% | 0 | 0 | 0 | 8840 | 0 | 8840 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible cold cured moulded PUF at Ciptaindah Jokindo | Individual | ASP | IDS | FOA | 23 | INV | 82 | A | I | CFC | 9 | 9 | 0 | 0 | 1997-11-01 | 2000-04-01 | 1999-12-01 |  | 2000-12-01 | 2002-03-01 | 77125 | -58 | 77067 | 77067 | 100% | 0 | 0 | 0 | 10026.25 | -7.32 | 10018.93 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Project preparation for 4 projects in the rigid foam subsector | Individual | ASP | IDS | FOA | 24 | PRP | 84 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-09-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam (spray foam) at PT Sentras Varitima | Individual | ASP | IDS | FOA | 25 | INV | 86 | A | I | CFC | 18.1 | 18.1 | 0 | 0 | 1998-07-01 | 1999-07-01 | 2000-08-01 |  | 2000-07-01 | 2002-03-01 | 125000 | -5780 | 119220 | 119220 | 100% | 0 | 0 | 0 | 16250 | -751.4 | 15498.6 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Converstion to CFC-free technology in the manufacture of rigid polyurethane spray foam at Metal Tunggal Prakarsamandiri | Individual | ASP | IDS | FOA | 25 | INV | 89 | A | I | CFC | 8 | 8 | 0 | 0 | 1998-07-01 | 1999-05-01 | 2000-08-01 |  | 1999-11-01 | 2002-10-01 | 43330 | 0 | 43330 | 43330 | 100% | 0 | 0 | 0 | 5632.9 | 0 | 5632.9 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Converstion to CFC-free technolgoy in the manufacture of rigid polyurethane spray foam at Karya Sempati Sarana | Individual | ASP | IDS | FOA | 25 | INV | 91 | A | I | CFC | 8.8 | 8.8 | 0 | 0 | 1998-07-01 | 1999-05-01 | 2000-08-01 |  | 1999-11-01 | 2004-01-01 | 45550 | 0 | 45550 | 45550 | 100% | 0 | 0 | 0 | 5921.5 | 0 | 5921.5 | 0 | 0 | Completed in 1999. Financially completed in 2004. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam spray insulation at PT Karoseri Trisakti | Individual | ASP | IDS | FOA | 26 | INV | 100 | A | I | CFC | 11.1 | 11.1 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2000-12-01 |  | 1999-11-01 | 2003-03-01 | 80037 | -6557 | 73480 | 73480 | 100% | 0 | 0 | 0 | 10404.81 | -852.41 | 9552.4 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam at Mentari Adi Fayar | Individual | ASP | IDS | FOA | 26 | INV | 101 | A | I | CFC | 22.4 | 22.4 | 0 | 0 | 1998-11-01 | 1999-07-01 | 2000-12-01 |  | 2003-01-01 | 2004-01-01 | 111517 | 0 | 111517 | 111517 | 100% | 0 | 0 | 0 | 14497.21 | 0 | 14497.21 | 0 | 0 | Completed in 2003. Financially completed in 2004. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (panels) at Irama Sejuk Santosa | Individual | ASP | IDS | FOA | 26 | INV | 103 | A | I | CFC | 7 | 7 | 0 | 0 | 1998-11-01 | 1999-12-01 | 2000-12-01 |  | 2000-12-01 | 2002-03-01 | 54800 | -4604 | 50196 | 50196 | 100% | 0 | 0 | 0 | 7124 | -598.52 | 6525.48 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of insulated boxes at P.T. Polidaya Fiberindo Indah | Individual | ASP | IDS | FOA | 26 | INV | 106 | A | I | CFC | 9.3 | 9.3 | 0 | 0 | 1998-11-01 | 1999-12-01 | 2000-12-01 |  | 2000-12-01 | 2002-03-01 | 72800 | -8363 | 64437 | 64437 | 100% | 0 | 0 | 0 | 9464 | -1087.19 | 8376.81 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation products at PT Hanaria Indah | Individual | ASP | IDS | FOA | 26 | INV | 93 | A | I | CFC | 12.9 | 12.9 | 0 | 0 | 1998-11-01 | 1999-11-01 | 2000-12-01 |  | 2000-10-01 | 2002-03-01 | 101352 | -18169 | 83183 | 83183 | 100% | 0 | 0 | 0 | 13175.76 | -2361.97 | 10813.79 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of insulated panels at P.T. Panendra Sejati | Individual | ASP | IDS | FOA | 26 | INV | 95 | A | I | CFC | 20 | 20 | 0 | 0 | 1998-11-01 | 2000-03-01 | 2000-12-01 |  | 2000-12-01 | 2002-03-01 | 156600 | -46830 | 109770 | 109770 | 100% | 0 | 0 | 0 | 20358 | -6087.9 | 14270.1 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam at Indoklima Sarana Engineering | Individual | ASP | IDS | FOA | 26 | INV | 96 | A | I | CFC | 27.1 | 27.1 | 0 | 0 | 1998-11-01 | 1999-07-01 | 2000-12-01 |  | 2000-10-01 | 2002-03-01 | 212193 | -43243 | 168950 | 168950 | 100% | 0 | 0 | 0 | 27585.09 | -5621.59 | 21963.5 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam spray insulation at PT Karoseri Laksana | Individual | ASP | IDS | FOA | 26 | INV | 97 | A | I | CFC | 21.3 | 21.3 | 0 | 0 | 1998-11-01 | 1999-07-01 | 2000-12-01 |  | 1999-11-01 | 2004-01-01 | 122885 | -3 | 122882 | 122882 | 100% | 0 | 0 | 0 | 15975.05 | 0 | 15975.05 | 0 | 0 | Completed in 1999. Financially completed in 2004. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam spray insulation at PT Mekar Armada Jaya | Individual | ASP | IDS | FOA | 26 | INV | 98 | A | I | CFC | 24.9 | 24.9 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2000-12-01 |  | 1999-11-01 | 2001-12-01 | 149357 | -6055 | 143302 | 143302 | 100% | 0 | 0 | 0 | 19416.41 | -787.15 | 18629.26 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1998 |  | Investment
FIN | IBRD | Preparation of projects in the foam sector |  | ASP | IDS | FOA | 27 | PRP | 108 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-06-30 | 2000-01-01 |  | 2000-12-01 | 2000-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNIDO | Preparation of investment project in the foam sector (flexible polyurethane) | Individual | ASP | IDS | FOA | 27 | PRP | 109 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-10-01 | 1999-12-01 |  | 2002-01-01 | 2003-05-01 | 50000 | -177 | 49823 | 49822.81 | 100% | 0.19 | 0 |  | 6500 | -33 | 6467 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of CFC-11 consumption by conversion to water-blown technology and HCFC-141b at P.T. Nirwana in the manufacture of polyurethane integral skin and flexible moulded polyurethane foam | Individual | ASP | IDS | FOA | 29 | INV | 110 | A | I | CFC | 32.6 | 32.6 |  |  | 1999-11-01 | 2000-11-01 | 2001-12-01 |  | 2001-10-01 | 2002-12-01 | 206911 | 0 | 206911 | 206911.12 | 100% | -0.12 | 0 |  | 26898 | -27 | 26871 | 0 | 0 | FIN
FIN | IBRD | Phase-out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (sprayfoam) at CV Sumber Logam | Individual | ASP | IDS | FOA | 29 | INV | 111 | N | I | CFC | 12.1 | 12.1 | 0 | 0 | 1999-11-01 | 2001-09-01 | 2002-12-01 |  | 2001-12-01 | 2002-05-01 | 56118 | -30157 | 25961 | 25961 | 100% | 0 | 0 |  | 7295.34 | -3920.41 | 3374.93 | 0 | 0 | Project technically and financially completed. PCR submitted to WB. |  |  |  | INV | 0
FIN | UNDP | Phase-out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (sprayfoam, panels, blocks) at Tansri Gani | Individual | ASP | IDS | FOA | 29 | INV | 112 | A | I | CFC | 45.3 | 45.3 | 0 | 0 | 1999-11-01 | 2001-08-01 | 2003-07-01 |  | 2003-03-01 | 2005-09-01 | 354700 | -5045 | 349655 | 349655 | 100% | 0 | 0 | 0 | 46111 | -656 | 45455 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 1999 | 2003-07-01 | Investment
FIN | UNIDO | Phase-out of CFC-11 consumption by conversion to water-blown technology and HCFC-141b at P.T. Meta Presindo Utama in the manufacture of polyurethane integral skin and moulded polyurethane foam | Individual | ASP | IDS | FOA | 29 | INV | 113 | A | I | CFC | 21.8 | 21.8 |  |  | 1999-11-01 | 2000-08-01 | 2001-12-01 |  | 2001-10-01 | 2002-12-01 | 213603 | 0 | 213603 | 213603.43 | 100% | -0.43 | 0 |  | 27768 | -15 | 27753 | 0 | 0 | FIN
FIN | UNDP | Phase-out of CFC-11 by conversion to water-based systems and HCFC-141b in the manufacture of polyurethane foam for automotive and furniture applications at P.T. Yoska Prima Inti | Individual | ASP | IDS | FOA | 29 | INV | 114 | A | I | CFC | 49.5 | 49.5 | 0 | 0 | 1999-11-01 | 2001-05-01 | 2003-07-01 |  | 2001-12-01 | 2003-04-01 | 368868 | -221866 | 147002 | 147002 | 100% | 0 | 0 | 0 | 47952.84 | -28842.59 | 19110.25 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
CLO | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (sprayfoam) at PT Sentra Sukses Selalu | Individual | ASP | IDS | FOA | 29 | INV | 115 | N | I |  | 0 | 0 | 0 | 0 | 1999-11-01 |  | 2002-12-01 |  |  | 2003-04-01 | 539579 | -539579 | 0 | 0 | #DIV/0! | 0 | 0 |  | 69353.69 | -69353.69 | 0 | 0 | 0 | Cancelled - 38th ExCom |  |  |  | INV | 0
FIN | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (boxfoam and sprayfoam) at PT Intimas Chemindo | Individual | ASP | IDS | FOA | 29 | INV | 116 | N | I | CFC | 74.3 | 74.3 | 0 | 0 | 1999-11-01 | 2003-10-01 | 2002-12-01 |  | 2003-03-01 | 2004-09-01 | 290294 | -163063.56 | 127230.44 | 127230.44 | 100% | 0 | 0 |  | 37738.22 | -21198.04 | 16539.96 | 0.22 | 0.22 | Project technically and financially completed. |  |  |  | INV | 0
FIN | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (panels) at PT Dawamiba Engineering | Individual | ASP | IDS | FOA | 29 | INV | 117 | N | I | CFC | 31.6 | 31.6 | 0 | 0 | 1999-11-01 | 2001-11-01 | 2002-12-01 |  | 2003-06-01 | 2003-10-01 | 156500 | -2750 | 153750 | 153750 | 100% | 0 | 0 |  | 20345 | -357.5 | 19987.5 | 0 | 0 | Project technically and financially completed. PCR draft being finalized. |  |  |  | INV | 0
FIN | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (sprayfoam) at Kimura Fiberglass | Individual | ASP | IDS | FOA | 29 | INV | 118 | N | I | CFC | 21.1 | 21.1 | 0 | 0 | 1999-11-01 | 2001-10-01 | 2002-12-01 |  | 2001-12-01 | 2002-07-01 | 69385 | -36556.41 | 32828.59 | 32828.59 | 100% | 0 | 0 |  | 9020.05 | -4752.34 | 4267.71 | 0 | 0 | Project technically and financially completed. PCR submitted to WB. |  |  |  | INV | 0
FIN | UNIDO | Phase-out of CFC-11 by conversion to water blown technology in the manufacturing of polyurethane integral skin shoe soles at P.T. Trias Rantai Mas | Individual | ASP | IDS | FOA | 31 | INV | 119 | A | I | CFC | 18.4 | 18.4 |  |  | 2000-07-01 | 2000-11-01 | 2003-01-01 |  | 2003-01-01 | 2003-12-01 | 141319 | 0 | 141319 | 141319.29 | 100% | -0.29 | 0 |  | 18371 | 0 | 18371 | 0 | 0 | FIN
FIN | IBRD | Phaseout of CFC-11 by conversion to water based technology and LCD technology in the manufacture of flexible moulded foam and to HCFC-141b in the manufacture of molded integral skin polyurethane foam at Anto Indo Foam | Individual | ASP | IDS | FOA | 31 | INV | 120 | N | I | CFC | 51.75 | 51.75 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2003-08-01 |  | 2003-03-01 | 2003-10-01 | 249645 | -244 | 249401 | 249400.86 | 100% | 0.14 | 0.14 |  | 32453.85 | -32 | 32422.11 | -0.26 | -0.26 | Project technically and financially completed. |  |  |  | INV | 0
FIN | UNIDO | Project preparation in the rigid foam sector | Individual | ASP | IDS | FOA | 33 | PRP | 122 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-10-01 | 2002-04-01 |  | 2002-10-01 | 2003-10-01 | 25000 | -2204 | 22796 | 22796.41 | 100% | -0.41 | 0 |  | 3250 | -291 | 2959 | 0 | 0 | FIN |  |  |  | INV
FIN | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | ASP | IDS | FOA | 33 | PRP | 124 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-05-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible molded polyurethane foam at PT Kemenangan | Individual | ASP | IDS | FOA | 35 | INV | 126 | A | I | CFC | 13.1 | 13.1 | 0 | 0 | 2001-12-01 | 2003-01-01 | 2004-07-01 |  | 2003-11-01 | 2005-10-01 | 104817 | -2098 | 102719 | 102719 | 100% | 0 | 0 | 0 | 13626.21 | -273 | 13353.21 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (steel door) at PT Bostinco | Individual | ASP | IDS | FOA | 35 | INV | 127 | N | I | CFC | 11.3 | 11.3 | 0 | 0 | 2001-12-01 | 2003-08-01 | 2004-01-01 |  | 2003-10-01 | 2004-05-01 | 88479 | 0 | 88479 | 88479 | 100% | 0 | 0 |  | 11502.27 | 0 | 11502.27 | 0 | 0 | Project physically and financially completed. |  |  |  | INV | 0
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (cooler box products) at Dua Roda Industrial Co. | Individual | ASP | IDS | FOA | 35 | INV | 128 | N | I | CFC | 11.2 | 11.2 | 0 | 0 | 2001-12-01 | 2003-10-01 | 2004-01-01 |  | 2003-05-01 | 2003-10-01 | 52457 | -5800 | 46657 | 46657 | 100% | 0 | 0 |  | 6819.41 | -754 | 6065.41 | 0 | 0 | Project physically and financially completed. |  |  |  | INV | 0
FIN | IBRD | Phase out of CFC-11 by conversion to 100% water based technology in the manufacture of polyurethane integral skin shoe soles at PT Udapana Swasti | Individual | ASP | IDS | FOA | 35 | INV | 129 | N | I | CFC | 28 | 28 | 0 | 0 | 2001-12-01 | 2003-12-01 | 2004-10-01 |  | 2005-12-01 | 2005-12-01 | 165201 | -20510.44 | 144690.56 | 144690.56 | 100% | 0 | 0 |  | 21476.13 | -2666.36 | 18809.77 | 0 | 0 | Project financially and technically completed. |  |  |  | INV | 0
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (house ware products) at PT Maspion Plastic and Metal Industry | Individual | ASP | IDS | FOA | 35 | INV | 130 | N | I | CFC | 18.1 | 18.1 | 0 | 0 | 2001-12-01 | 2003-10-01 | 2004-01-01 |  | 2003-11-01 | 2004-09-01 | 141723 | 0 | 141723 | 141723 | 100% | 0 | 0 |  | 18423.99 | 0 | 18423.99 | 0 | 0 | Project physically and financially completed |  |  |  | INV | 0
FIN | UNIDO | Phase-out of CFC-11 by conversion to HCFC-141b in the manufacture of integral skin automotive parts at PT Wulansari Raharja | Individual | ASP | IDS | FOA | 36 | INV | 141 | A | I | CFC | 10.8 | 10.8 |  |  | 2002-03-01 | 2004-02-01 | 2004-09-01 |  | 2004-09-01 | 2004-12-01 | 101301 | -632 | 100669 | 100668.52 | 100% | 0.48 | 0 |  | 13169 | -103 | 13066 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid insulation foam parts at two companies: PT Morodadi Prima and PT Tentrem Industri Karosseri | Individual | ASP | IDS | FOA | 36 | INV | 143 | A | I | CFC | 25.5 | 25.5 |  |  | 2002-03-01 | 2002-12-01 | 2004-09-01 |  | 2004-11-01 | 2007-04-01 | 164947 | -567 | 164380 | 164379.96 | 100% | 0.04 | 0 |  | 21443 | -74 | 21369 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of CFC-11 by conversion to water blown in the manufacture of integral skin shoe soles at PT Solindah Kita | Individual | ASP | IDS | FOA | 36 | INV | 144 | A | I | CFC | 48 | 48 |  |  | 2002-03-01 | 2002-08-01 | 2004-09-01 |  | 2005-12-01 | 2006-12-01 | 390760 | -5753 | 385007 | 385007.42 | 100% | -0.42 | 0 |  | 50799 | -748 | 50051 | 0 | 0 | FIN |  |  |  | INV
FIN | Japan | Phase-out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam for insulating purposes at Aneka Citra Refrigeratama Co. | Individual | ASP | IDS | FOA | 37 | INV | 145 | A | I | CFC-11 | 18.2 | 18.2 | 0 |  | 2002-07-01 | 2004-11-01 | 2004-09-01 |  | 2005-12-01 | 2006-03-01 | 142506 | -377 | 142129 | 142129 | 100% | 0 | 0 | 0 | 18526 | -49 | 18477 | 0 | 0 | Project completed. |  | 2002 |  | investment
FIN | Japan | Phase-out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam for insulating purposes at Bina Teknik Co. | Individual | ASP | IDS | FOA | 37 | INV | 146 | A | I | CFC-11 | 22.8 |  | 0 |  | 2002-07-01 | 2003-12-01 | 2005-03-01 |  | 2006-03-01 | 2006-03-01 | 117889 | -541 | 117348 | 117348 | 100% | 0 | 0 | 0 | 15326 | -71 | 15255 | 0 | 0 | Project completed in March 2006. |  | 2002 |  | investment
FIN | UNIDO | Phase-out of CFC-11 by conversion to water blown in the manufacture of integral skin shoe soles at PT. Accurai | Individual | ASP | IDS | FOA | 37 | INV | 147 | A | I | CFC | 50 | 50 |  |  | 2002-07-01 | 2003-12-01 | 2005-03-01 |  | 2005-06-01 | 2006-09-01 | 523943 | -656 | 523287 | 523287.38 | 100% | -0.38 | 0 |  | 67634 | -72 | 67562 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project to phase-out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam for insulating purposes at Ganesha Rattesko and Sindari Nusatama | Individual | ASP | IDS | FOA | 38 | INV | 150 | A | I | CFC | 52 | 52 |  |  | 2002-11-01 | 2003-12-01 | 2005-06-01 |  | 2005-12-01 | 2006-12-01 | 283490 | -101 | 283389 | 283389.34 | 100% | -0.34 | 0 |  | 36854 | -13 | 36841 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam for insulating purposes at Delta Atlantik and Samudra Plastics | Individual | ASP | IDS | FOA | 38 | INV | 152 | A | I | CFC | 18.8 | 18.8 |  |  | 2002-11-01 | 2003-12-01 | 2004-12-01 |  | 2004-11-01 | 2006-05-01 | 146388 | 0 | 146388 | 146387.89 | 100% | 0.11 | 0 |  | 19030 | -10 | 19020 | 0 | 0 | FIN |  |  |  | INV
FIN | IBRD | Phase-out of residual CFCs in the foam sector (advancement) | Multiyear | ASP | IDS | FOA | 42 | INV | 160 | N | I | CFC | 130 | 130 | 0 | 0 | 2004-04-01 | 2004-12-01 | 2005-12-01 |  | 2005-12-01 | 2007-12-01 | 100000 | 1625000 | 1725000 | 1725000 | 100% | 0 | 0 |  | 7500 | 121875 | 129375 | 0 | 0 | Project is physically and financially completed |  |  |  | INV | 0
FIN | IBRD | Phase-out of residual CFCs in the foam sector (second tranche) | Multiyear | ASP | IDS | FOA | 48 | INV | 172 | N | I | CFC | 130 | 130 | 0 | 0 | 2006-04-01 | 2007-11-01 | 2007-04-01 |  | 2008-12-01 | 2010-12-01 | 1050000 | 0 | 1050000 | 1050000 | 100% | 0 | 0 |  | 78750 | 0 | 78750 | 0 | 0 | Completed. |  |  |  | INV | 0
FIN | IBRD | Phase-out of residual CFCs in the foam sector (third tranche) | Multiyear | ASP | IDS | FOA | 51 | INV | 176 | N | I | CFC | 156 | 156 | 0 | 0 | 2007-03-01 | 2008-12-01 | 2008-03-01 |  | 2010-06-01 | 2010-12-01 | 147564 | 0 | 147564 | 147564 | 100% | 0 | 0 |  | 11067 | 0 | 11067 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Phase-out of residual CFCs in the foam sector (fourth tranche) | Multiyear | ASP | IDS | FOA | 54 | INV | 182 | N | I | CFC | 66 | 66 | 0 | 0 | 2008-04-01 | 2010-06-01 | 2009-03-31 |  | 2010-06-01 | 2010-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 |  | 2625 | 0 | 2625 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Preparation for HCFC phase-out investment activities (stage II) (foam sector) |  | ASP | IDS | FOA | 72 | PRP | 203 | A | I |  | 0 | 0 | 0 | 0 | 2014-05-01 | 2014-12-01 | 2016-05-31 |  | 2016-05-01 | 2016-05-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 | 0 | 10500 | 0 | 10500 | 0 | 0 | Project completion done by end Jan 16 and submitted to the ExCom. Stage II foam sector plan approved in May 16. | Not applicable. |  |  | Non-INV | 0
FIN | UNIDO | Preparation of a demonstration project in the methyl bromide sector (tobacco, tomatoes, pepper) | Individual | ASP | IDS | FUM | 23 | PRP | 69 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-01-01 | 1999-07-01 |  | 1998-09-01 | 2001-07-01 | 10000 | 17659 | 27659 | 27659 | 100% | 0 | 0 |  | 1300 | 2290 | 3590 | 0 | 0 | FIN
FIN | UNIDO | Demonstration project - alternatives to the use of methyl bromide in store products (rice, coffee and corn) | Individual | ASP | IDS | FUM | 26 | DEM | 94 | A | I |  | 0 | 0 |  |  | 1998-11-01 | 1999-03-01 | 2000-12-01 |  | 2001-12-01 | 2003-10-01 | 332200 | -5985 | 326215 | 326214.65 | 100% | 0.35 | 0 |  | 43186 | -845 | 42341 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a phase-out project in the fumigant (methyl bromide) sector in TPO-grain fumigation | Individual | ASP | IDS | FUM | 36 | PRP | 139 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-07-01 | 2003-04-01 |  | 2003-12-01 | 2005-05-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 | FIN |  |  |  | INV
TRF | Canada | Phase-out of the use of methyl bromide in grain storage | Individual | ASP | IDS | FUM | 41 | INV | 158 | A | I |  | 0 |  | 0 |  | 2003-12-01 |  | 2007-12-01 |  |  | 2004-12-01 | 350000 | -350000 | 0 | 0 |  | 0 |  | 0 | 45500 | -45500 | 0 | 0 |  | Project transferred to UNIDO. |  | 2003 |  | Non-Inv.
FIN | UNIDO | Phase-out of the use of methyl bromide in grain storage | Individual | ASP | IDS | FUM | 44 | INV | 168 | A | I | MBR | 37.8 | 37.8 |  |  | 2004-12-01 | 2005-04-01 | 2007-12-01 |  | 2008-09-01 | 2009-09-01 | 350000 | -372 | 349628 | 349628.38 | 100% | -0.38 | 0 |  | 26250 | -28 | 26222 | 0 | 0 | FIN |  |  |  | INV
FIN | IBRD | Elimination in production of halon-1211 fire protection extinguishers at Dahlia Cahaya, Bayu Sentosa Agung and Chubb Lips | Individual | ASP | IDS | HAL | 15 | INV | 27 | N | I | HAL | 465 | 682.4 | 0 | 0 | 1994-12-01 | 1996-06-01 | 1995-12-01 |  | 1997-11-01 | 1997-11-01 | 500000 | 0 | 500000 | 500000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | PCR has been submitted. Project is closed. 3% agency fee incl. |  |  | 1997-06-01 | INV | 0
FIN | IBRD | Project preparation in the halon recycling sector |  | ASP | IDS | HAL | 24 | PRP | 85 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1999-03-31 | 1998-12-01 |  | 1999-06-01 | 1999-06-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 |  | 2340 | 0 | 2340 | 0 | 0 | Complete. |  |  |  | Non-INV | 0
FIN | IBRD | Halon management programme, halon recovery, recycling and banking | Halon Banking | ASP | IDS | HAL | 27 | TAS | 107 | N | I | HAL | 972 | 972 | 0 | 0 | 1999-03-01 | 2001-05-01 | 2003-04-01 |  | 2007-01-01 | 2007-06-01 | 486200 | -11076.12 | 475123.88 | 475123.88 | 100% | 0 | 0 |  | 63206 | -1439.9 | 61766.1 | 0 | 0 | Project is physically and financially completed |  |  |  | INV | 0
FIN | IBRD | Conversion of tobacco expansion process from CFC-11 to carbon dioxide at PT Hanjaya Mandal Sampoerna and P.T. Djarum | Individual | ASP | IDS | OTH | 21 | INV | 51 | N | I | CFC | 90 | 54 | 0 | 0 | 1997-02-01 | 1998-08-01 | 1999-02-01 |  | 1997-06-01 | 1998-08-01 | 1214000 | -607000 | 607000 | 607000 | 100% | 0 | 0 |  | 157820 | -78910 | 78910 | 0 | 0 | PT Sampoerna - grant was fully disbursed. Completed technical audit and disposal plan. PCR has been submitted and project is closed. PT Djarum - steam-based technology proposed was refused, project cancelled. |  |  |  | INV | 0
FIN | UNIDO | Preparation of a sector phase-out plan in process agents sector | Individual | ASP | IDS | PAG | 36 | PRP | 140 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-09-01 | 2003-07-01 |  | 2004-12-01 | 2004-12-01 | 60000 | -1890 | 58110 | 58109.61 | 100% | 0.39 | 0 |  | 7800 | -258 | 7542 | 0 | 0 | FIN |  |  |  | INV
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | ASP | IDS | PHA | 55 | PRP | 183 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2010-12-01 | 2011-09-01 | 173750 | 0 | 173750 | 173750 | 100% | 0 | 0 | 0 | 13031.25 | 0 | 13031.25 | 0 | 0 | Completed in 2009. Financially completed in 2011. |  | 2008 |  | Investment
FIN | IBRD | Preparation of a HCFC phase-out management plan (foam sector) |  | ASP | IDS | PHA | 57 | PRP | 186 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-12-01 | 2010-12-31 |  | 2011-07-01 | 2011-07-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 7500 | 0 | 7500 | 0 | 0 | HPMP foam sector plan prepared and approved at the 64th ExCom Meeting. |  |  |  | Non-INV | 0
ONG | IBRD | HCFC phase-out management plan (foam sector plan) (stage I, first tranche) | Multiyear | ASP | IDS | PHA | 64 | INV | 191 | A | I | HCFC | 18.9 | 18.9 | 0 | 0 | 2011-07-01 | 2013-12-01 | 2013-03-31 | 2017-12-01 |  |  | 1500000 | 0 | 1500000 | 1132000 | 75.47% | 368000 | 368000 | 368000 | 112500 | 0 | 84900 | 27600 | 27600 | By end 2016, out of 26 targeted foam enterprises, 9 foam manufacturers had completed their phase-out of 197,208 kg (2009 consumption) of HCFC-141b; three of these companies converted to HC and 6 to HFC-245fa. One company will convert in 2017 (1100 kg in 2009) and two companies are still pending (12,460 kg in 2009). Remaining 15 companies declined to participate for various business reasons, but must nevertheless abide by the HCFC quota and use ban. In May 2016, ExCom approved redirecting funds to support two foam system houses develop low-GWP formulation under Stage 1. System houses signed agreements in 2016 and are expected to complete subprojects by 2019. Import quota system continues to be applied and a ban on HCFC use in targeted subsectors is in place. | Implementation continued as planned between Jan-Mar 17. Completion of Tranche 1 is expected in Oct 17. |  |  | INV | 0
FIN | UNDP | HCFC phase-out management plan (refrigeration sector plan) (stage I, first tranche) | Multi-Year | ASP | IDS | PHA | 64 | INV | 193 | N | I | HCFC | 24.4 | 24.4 | 0 | 0 | 2011-07-01 | 2012-05-01 | 2013-03-01 |  | 2014-12-01 | 2015-03-01 | 1802807 | -1211416 | 591391 | 591391 | 100% | 0 | 0 | 0 | 135210 | -90856 | 44354 | 0 | 0 | Financially completed in 2015. | As planned, the project activities are continued to be monitored. Technical consultations on availability of key components were held in Feburary 2014. | 2011 |  | Investment
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (Umbrella project to phase-out HCFC-141b from the manufacturing of rigid polyurethane foam at Isotech Jaya Makmur, Airtekindo, Sinar Lentera Kencana and Mayer Jaya) | Multi-Year | ASP | IDS | PHA | 64 | INV | 194 | A | I | HCFC | 11.01 | 11.01 |  |  | 2011-07-01 | 2012-02-01 | 2012-03-31 | 2017-01-31 |  |  | 777395 | 0 | 777395 | 500021.1 | 64.32% | 277373.9 | 269375 | 277000 | 58305 | 0 | 37502 | 20803 | 20203 | - Equipment delivered installed and commissioned. Final production tests and prototyping have been finalized at three beneficiaries in October 2016. Milestone 1: Grant agreement submitted to beneficiary - Yes Milestone 2: Grant agreement signature - Yes Milestone 3: Bids prepared and requested - Yes Milestone 4: Contracts awarded - Yes Milestone 5: Equipment delivered - Yes Milestone 6: Commissioning and trial runs - Yes Milestone 7: De-commissioning and/or destruction of redundant baseline equipment - Yes Activities planned but not implemented, reasons and strategy: No Actions towards next goals: decommissioning and project completion procedures. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Partially burned down company put extreme efforts and resources to catch up. Any recurring problem? No Any impact on project completion date: N/A. If yes, implications: N/A Any action required by Executive Committee? No | - Final works; purchase of cyclopentane for commissioning and commissioning itself at one counterpart took place in January 2017. - Project is completed, financial completion in process. |  |  | INV
FIN | UNDP | HCFC phase-out management plan (air conditioning sector plan) (stage I, first tranche) | Multi-Year | ASP | IDS | PHA | 64 | INV | 195 | N | I | HCFC | 14.5 | 14.5 | 0 | 0 | 2011-07-01 | 2012-11-01 | 2013-03-01 |  | 2015-05-01 | 2016-05-01 | 1995519 | -1922800 | 72719 | 72719 | 100% | 0 | 0 | 0 | 149664 | -144210 | 5454 | 0 | 0 | Financially completed in 2016. | Government has successfully implemented regulations for prohibiting use of HCFCs in RAC manufacturing from 1 Jan 2015. Monitoring of HCFC consumption is ongoing satisfactorily. Third tranche would be submitted to the 75th Excom | 2011 |  | Investment
FIN | UNDP | HCFC phase-out management plan (project management and coordination) (stage I, first tranche) | Multi-Year | ASP | IDS | PHA | 64 | TAS | 192 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-11-01 | 2013-03-01 |  | 2015-05-01 | 2016-05-01 | 201674 | 0 | 201674 | 201674 | 100% | 0 | 0 | 0 | 15126 | 0 | 15126 | 0 | 0 | Financially completed in 2016. | PMU activities are progressing satisfactorily. PMU continues to support project implementation and monitoirng. Verification for 2013 and 2014 are expected to be completed by August 2015. | 2011 |  | Non-Investment
ONG | Australia | HCFC phase-out management plan (technical assistance for refrigerant management) (stage I, first tranche) | Multi-Year | ASP | IDS | PHA | 64 | TAS | 196 | A | I |  | 3.7 |  | 0 |  | 2011-07-01 | 2013-08-01 | 2014-12-01 | 2017-12-01 |  |  | 300000 | 0 | 300000 | 128920 | 42.97% | 171080 | 0 | 45000 | 39000 | 0 | 18330 | 20670 | 0 | Ongoing | During the year 2016, main activities initiated includes development of (a) Training Curricula and Materials for RAC Technician (b) manual or guidelines able to guide technicians on how to handle flammable refrigerants in coordination with relevant expert (c) draft of a ministerial decree to revise the decree of Minister of Environment No. 2 year 2007 regarding Technical Guidelines and Competency Requirement for Retrofit and Recycle on Refrigeration System (d) Android Mobile and Web based application to monitor service workshop in Indonesia | 2011
ONG | UNDP | HCFC phase-out management plan (refrigeration sector plan) (stage I, second tranche) | Multi-Year | ASP | IDS | PHA | 71 | INV | 198 | N | I | HCFC | 24.4 | 18.2 | 0 | 0 | 2013-12-01 | 2015-05-01 | 2015-12-01 | 2017-01-01 |  |  | 1802807 | 0 | 1802807 | 1802807 | 100% | 0 | 0 | 0 | 135210 | 0 | 135210 | 0 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): As per AWP work completed.In terms of ATLAS it is still going on. Prodoc signed (actual/planned, yes/no and date):41821 Missions undertaken (actual/planned):1 TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: signed earlier First disbursement date (actual/planned): 42125Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | Project is still ON-GOING and operating. | 2013 |  | Investment
ONG | UNDP | HCFC phase-out management plan (air conditioning sector plan) (stage I, second tranche) | Multi-Year | ASP | IDS | PHA | 71 | INV | 199 | N | I | HCFC | 14.5 | 1.8 | 0 | 0 | 2013-12-01 | 2015-05-01 | 2015-12-01 | 2017-01-01 |  |  | 1995519 | 0 | 1995519 | 1659091 | 83.14% | 336428 | 28635.37 | 53865.684 | 149664 | 0 | 124432 | 25232 | 2147.6538 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): In term of activities, it has completed its plan. In term of ATLAS, it is still ON GOING Prodoc signed (actual/planned, yes/no and date):41821 Missions undertaken (actual/planned):1 TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: signed earlier First disbursement date (actual/planned): 42125Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | Project is still ON-GOING and operating. | 2013 |  | Investment
ONG | IBRD | HCFC phase-out management plan (foam sector plan) (stage I, second tranche) | Multiyear | ASP | IDS | PHA | 71 | INV | 202 | N | I | HCFC | 11.9 | 11.9 | 0 | 0 | 2013-12-01 | 2015-12-01 | 2015-12-31 | 2017-12-01 |  |  | 942767 | 0 | 942767 | 856677.9 | 90.87% | 86089.1 | 86089.1 | 86089.1 | 70708 | 0 | 64251.27 | 6456.73 | 6456.73 | By end 2016, out of 26 targeted foam enterprises, 9 foam manufacturers had completed their phase-out of 197,208 kg (2009 consumption) of HCFC-141b; three of these companies converted to HC and 6 to HFC-245fa. One company will convert in 2017 (1100 kg in 2009) and two companies are still pending (12,460 kg in 2009). Remaining 15 companies declined to participate for various business reasons, but must nevertheless abide by the HCFC quota and use ban. In May 2016, ExCom approved redirecting funds to support two foam system houses develop low-GWP formulation under Stage 1. System houses signed agreements in 2016 and are expected to complete subprojects by 2019. Import quota system continues to be applied and a ban on HCFC use in targeted subsectors is in place. | Two foam subprojects are still pending as of Mar. 17. Two system houses have started implementation of subprojects. |  |  | INV | 0
ONG | UNDP | HCFC phase-out management plan (project management and coordination) (stage I, second tranche) | Multi-Year | ASP | IDS | PHA | 71 | TAS | 200 | N | I | HCFC | 0 | 0 | 0 | 0 | 2013-12-01 |  | 2015-12-01 | 2017-01-01 |  |  | 201674 | 0 | 201674 | 201764 | 100% | -90 | 0 | 0 | 15126 | 0 | 15126 | 0 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): In term of activities, it has completed its plan. In term of ATLAS, it is still ON GOING Prodoc signed (actual/planned, yes/no and date):41821 Missions undertaken (actual/planned):1 TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: signed earlier First disbursement date (actual/planned): Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | Project is still ON-GOING and operating. | 2013 |  | Investment
ONG | UNDP | Preparation of a HCFC phase-out management plan (stage II) | Individual | ASP | IDS | PHA | 72 | PRP | 204 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 | 2015-04-01 | 2016-05-01 | 2017-05-01 |  |  | 90000 | 0 | 90000 | 46612.19 | 51.79% | 43387.81 | 5867.31 | 17355.124 | 6300 | 0 | 3262.8533 | 3037.1467 | 410.7117 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): In term of activities, it has completed its plan. In term of ATLAS, it is still ON GOING Prodoc signed (actual/planned, yes/no and date):Letter of Authorisation sent 4 Nov 2014 Missions undertaken (actual/planned):1 TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: signed earlier First disbursement date (actual/planned): 42297Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | Project is still ON-GOING, to be Operationally and Financially Closed, by HQ. |  |  | Investment
ONG | IBRD | HCFC phase-out management plan (stage I, third tranche) (foam sector) | Multiyear | ASP | IDS | PHA | 76 | INV | 207 | N | I | HCFC | 3.32 | 0 | 0 | 0 | 2016-05-01 |  | 2017-12-31 | 2018-12-01 |  |  | 271420 | 0 | 271420 | 0 | 0% | 271420 | 271420 | 30000 | 20356 | 0 | 0 | 20356 | 20356 | Final tranche approved in May 2016. By end 2016, out of 26 targeted foam enterprises, 9 foam manufacturers had completed their phase-out of 197,208 kg (2009 consumption) of HCFC-141b; three of these companies converted to HC and 6 to HFC-245fa. One company will convert in 2017 (1100 kg in 2009) and two companies are still pending (12,460 kg in 2009). Remaining 15 companies declined to participate for various business reasons, but must nevertheless abide by the HCFC quota and use ban. In May 2016, ExCom approved redirecting funds to support two foam system houses develop low-GWP formulation under Stage 1. System houses signed agreements in 2016 and are expected to complete subprojects by 2019. Import quota system continues to be applied and a ban on HCFC use in targeted subsectors is in place. | Two foam subprojects are still pending as of Mar. 17. Two system houses have started implementation of subprojects. The tranche implementation plan was for a two-year duration, not one as reflected in the Secretariat's Inventory. Moreover, country reduction commitments extend through 2018. Thus, planned completion date should be end 2018. |  |  | INV | 0
ONG | UNDP | HCFC phase-out management plan (stage I, third tranche) (refrigeration and air-conditioning sector) | Multi-Year | ASP | IDS | PHA | 76 | INV | 208 | N | I | HCFC | 9 | 0 | 0 | 0 | 2016-05-01 |  | 2018-05-01 | 2017-05-01 |  |  | 901102 | 0 | 901102 | 0 | 0% | 901102 | 0 | 360440.8 | 67583 | 0 | 0 | 67583 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): The draft of prodoc was prepared. It is currently under review by the National Ozone Unit (Ministry of Environment and Forestry) Prodoc signed (actual/planned, yes/no and date):42736 Missions undertaken (actual/planned):1 TOR for consultants/subcontracts completed (actual/planned): Contract/PO/MOA agreements signed: First disbursement date (actual/planned): Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | NOU will complete its review this quarter for further process with UNDP |  |  | Investment
ONG | IBRD | HCFC phase-out management plan (stage II, first tranche) (foam sector) | Multiyear | ASP | IDS | PHA | 76 | INV | 209 | N | I | HCFC | 19.94 | 0 | 0 | 0 | 2016-05-01 |  | 2018-12-31 | 2018-12-31 |  |  | 1985743 | 0 | 1985743 | 0 | 0% | 1985743 | 1985743 | 504646 | 139002 | 0 | 0 | 139002 | 139002 | Preparation of required documentation for amendment and additional financing of the current grant agreement between Indonesia and the WB initiated. | Amendment to the existing grant agreement to allow Stage II disbursement to commence expected in Q2 of 2017. |  |  | INV | 0
ONG | UNDP | HCFC phase-out management plan (stage II, first tranche) (fire fighting sector) | Multi-Year | ASP | IDS | PHA | 76 | INV | 211 | N | I | HCFC | 0 | 0 | 0 | 0 | 2016-05-01 |  | 2019-12-01 | 2017-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 12000 | 2100 | 0 | 0 | 2100 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): The draft of prodoc was prepared. It is currently under review by the National Ozone Unit (Ministry of Environment and Forestry) Prodoc signed (actual/planned, yes/no and date):No prodoc yet. DoA sent Nov 2016. Missions undertaken (actual/planned):1 TOR for consultants/subcontracts completed (actual/planned): Contract/PO/MOA agreements signed: First disbursement date (actual/planned): Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | NOU will complete its review this quarter for further process with UNDP |  |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | Multi-Year | ASP | IDS | PHA | 76 | TAS | 210 | N | I | HCFC | 0 | 0 | 0 | 0 | 2016-05-01 |  | 2019-12-01 | 2017-12-01 |  |  | 2203114 | 0 | 2203114 | 0 | 0% | 2203114 | 0 | 881245.6 | 154218 | 0 | 0 | 154218 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): The draft of prodoc was prepared. It is currently under review by the National Ozone Unit (Ministry of Environment and Forestry) Prodoc signed (actual/planned, yes/no and date):No prodoc yet. DoA sent Nov 2016. Missions undertaken (actual/planned):1 TOR for consultants/subcontracts completed (actual/planned): Contract/PO/MOA agreements signed: First disbursement date (actual/planned): Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | NOU will complete its review this quarter for further process with UNDP |  |  | Investment
FIN | IBRD | Elimination of ODS used in the production of household refrigerators at P.T. Sharp Yasonta, Indonesia | Individual | ASP | IDS | REF | 15 | INV | 22 | N | I | CFC | 172.7 | 172.7 | 0 | 0 | 1994-12-01 | 1997-05-01 | 1997-12-01 |  | 1998-05-01 | 1998-05-01 | 346000 | 502910 | 848910 | 848910.25 | 100% | -0.25 | -0.25 |  | 0 | 78000 | 78000 | 0 | 0 | PCR has been submitted. Project is physically and financially completed. |  |  | 1997-12-01 | INV | 0
FIN | IBRD | Elimination of ODS used in the production of household refrigerators at P.T. Lippo Melco Manufacturing | Individual | ASP | IDS | REF | 15 | INV | 23 | N | I | CFC | 47.02 | 47.02 | 0 | 0 | 1994-12-01 | 1996-12-01 | 1998-10-01 |  | 1998-06-01 | 1999-03-01 | 382000 | 234452.23 | 616452.23 | 616452.23 | 100% | 0 | 0 |  | 0 | 32455.02 | 32455.42 | -0.4 | -0.4 | Conversion of refrigerant to 134a is finished. Technical audit done on Feb. '98. Completed ODS phaseout in Jun. '98. Disposal plan was carried out in Nov. 19, '98. IOC has been disbursed. Project is technically and financially closed. |  |  | 1997-12-01 | INV | 0
FIN | IBRD | Elimination of ODS used in the manufacturing of household refrigerators at P.T. Sanyo Industries Indonesia, Jakarta | Individual | ASP | IDS | REF | 15 | INV | 26 | N | I | CFC | 72.3 | 72.3 | 0 | 0 | 1994-12-01 | 1996-04-01 | 1998-12-01 |  | 1998-03-01 | 1998-12-01 | 558000 | -30847.24 | 527152.76 | 527152.76 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project is completed. PCR had been submitted, project is closed. Unused funds returned to 32nd meeting. 3% agency fee incl. |  |  | 1997-12-01 | INV | 0
FIN | IBRD | Reduction of CFC-12 emission during service of MAC by use of recycling equipment | Individual | ASP | IDS | REF | 15 | TAS | 29 | N | I | CFC | 41 | 41 | 0 | 0 | 1994-12-01 | 2000-03-01 | 1996-12-01 |  | 2002-04-01 | 2002-04-01 | 327000 | -51593.01 | 275406.99 | 275406.99 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. Draft PCR submitted to the Bank. Savings are to be returned to the MLF. |  |  | 2001-12-01 | INV | 0
FIN | UNIDO | Phasing out of ODS at P.T. Air Tech. Co. Ltd. | Individual | ASP | IDS | REF | 18 | INV | 35 | A | I | CFC | 30.1 | 30.1 |  |  | 1995-11-01 | 1996-11-01 | 1997-05-01 |  | 1997-12-01 | 1999-05-01 | 409850 | 0 | 409850 | 409850 | 100% | 0 | 0 |  | 53281 | 0 | 53281 | 0 | 0 | FIN
FIN | IBRD | Elimination of ODSs used in the production of household refrigerators at P.T. Topjaya Antariksa Electronics | Individual | ASP | IDS | REF | 18 | INV | 36 | N | I | CFC | 51 | 69 | 0 | 0 | 1995-11-01 | 1996-11-01 | 2002-12-02 |  | 1998-05-01 | 2000-02-01 | 702000 | -2674 | 699326 | 699326 | 100% | 0 | 0 |  | 91260 | -347 | 90913 | 0 | 0 | Project is completed. PCR has been submitted. Unused fund is returned to 32nd Ex.Com. |  |  | 1997-12-01 | INV | 0
FIN | IBRD | Elimination of ODSs used in the production of household refrigerators at P.T. National Gobel (Nabel) | Individual | ASP | IDS | REF | 18 | INV | 37 | N | I | CFC | 90 | 100.57 | 0 | 0 | 1995-11-01 | 1996-07-01 | 2000-12-01 |  | 1998-03-01 | 2000-03-01 | 856500 | 0 | 856500 | 856500 | 100% | 0 | 0 |  | 111345 | 0 | 111345 | 0 | 0 | Project is completed. PCR has been submitted. |  |  | 1997-03-01 | INV | 0
FIN | IBRD | Engineering assistance for the elimination of ODS used in the production of household refrigerators at PT. Goldstar Astra Electronics (GSA) | Individual | ASP | IDS | REF | 20 | INV | 48 | N | I | CFC | 38.1 | 35.04 | 0 | 0 | 1996-10-01 | 1998-02-01 | 1999-04-01 |  | 1999-12-01 | 2001-03-01 | 512730 | -163820 | 348910 | 348910.32 | 100% | -0.32 | -0.32 |  | 66654.9 | -21297 | 45358 | -0.1 | -0.1 | Project is technically and financially closed. IOC has been disbursed. Balance returned to the MLF at the 35th ExCom. |  |  | 1999-04-01 | INV | 0
FIN | IBRD | Engineering assistance for the elimination of ODS used in the production of household refrigerators at PT. Samsung Maspion Indonesia (SMI) | Individual | ASP | IDS | REF | 21 | INV | 52 | N | I | CFC | 104.3 | 98.24 | 0 | 0 | 1997-02-01 | 1997-12-01 | 1999-08-01 |  | 2001-10-01 | 2001-11-01 | 537226 | -320243 | 216983 | 216983 | 100% | 0 | 0 |  | 69839.38 | -41632 | 28206.97 | 0.41 | 0.41 | Enterprise decided not to proceed to c-pentane due to current unfavorable economic conditions causing a high upfront investment costs for technology, and stopped at HCFC-141b. Disposal of old equipment done and IOC disbursed. Unused funds returned to the MLF at 35th and 36th Meetings. PCR under preparation. |  |  |  | INV | 0
FIN | UNDP | Project preparation in the refrigeration sector | Individual | ASP | IDS | REF | 21 | PRP | 53 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 1999-12-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1997 |  | Investment
FIN | UNIDO | Phasing out ODS at P.T. Jalur Sejuk | Individual | ASP | IDS | REF | 22 | INV | 59 | A | I | CFC | 30.85 | 30.85 |  |  | 1997-05-01 | 1997-09-01 | 1998-11-01 |  | 1999-06-01 | 2001-07-01 | 171470 | 0 | 171470 | 171470 | 100% | 0 | 0 |  | 22291 | -17 | 22274 | 0 | 0 | FIN |  |  | 1999-12-01
FIN | UNDP | Conversion to CFC-free technology in the manufacture of commercial refrigeration equipment at C.V. Kulkasindo | Individual | ASP | IDS | REF | 23 | INV | 66 | A | I | CFC | 9.4 | 9.4 | 0 | 0 | 1997-11-01 | 1998-08-01 | 1999-12-01 |  | 1999-11-01 | 2000-12-01 | 136000 | -18593.63 | 117406.37 | 117406 | 100% | 0.37 | 0 | 0 | 17680 | -2417.17 | 15262.78 | 0.05 | 0 | Completed in 1999. Financially completed in 2000. |  | 1997 |  | Investment
FIN | IBRD | Conversion of CFC-12 commercial refrigeration to HFC-134a at PT Maspion | Individual | ASP | IDS | REF | 23 | INV | 72 | N | I | CFC | 9 | 9 | 0 | 0 | 1997-11-01 | 1998-07-01 | 1999-12-01 |  | 1999-12-01 | 2000-11-01 | 136890 | -11703 | 125187 | 125187.38 | 100% | -0.38 | -0.38 |  | 17796 | -1521.39 | 16274.31 | 0.3 | 0.3 | Project completed. Disposal of old equipment has been carried out. PCR will be submitted January 2001. Project is closed. |  |  |  | INV | 0
FIN | IBRD | Conversion of CFC-12 commercial refrigeration to HFC-134a at PT Porkka Indonesia | Individual | ASP | IDS | REF | 23 | INV | 74 | N | I | CFC | 3.96 | 3.96 | 0 | 0 | 1997-11-01 | 2000-10-01 | 1999-12-01 |  | 1998-08-01 | 2001-03-01 | 58517 | -9377 | 49140 | 49140 | 100% | 0 | 0 |  | 7607 | -1219.01 | 6387.99 | 0 | 0 | Project completed and PCR to be submitted Mar. 02. Savings returned to the 35th ExCom. |  |  |  | INV | 0
FIN | IBRD | Conversion of CFC-12 refrigerant to HFC-134a, and CFC-11 to HCFC-141b as the blowing agent for foam insulation in the manufacture of commercial refrigeration units at PT Wahana Derby Sejati | Individual | ASP | IDS | REF | 23 | INV | 79 | N | I | CFC | 10.28 | 10.28 | 0 | 0 | 1997-11-01 | 1998-07-01 | 1999-12-01 |  | 1997-11-01 | 1998-07-01 | 139233 | -77613 | 61620 | 61620 | 100% | 0 | 0 |  | 18100 | -10089.69 | 8010.31 | 0 | 0 | Project completed, PCR submitted Mar. 99 and balance returned to the 32nd ExCom. |  |  |  | INV | 0
FIN | UNDP | Project preparation for 5 projects in commercial refrigeration subsector | Individual | ASP | IDS | REF | 24 | PRP | 83 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Supply conversion project to CFC-free technology in the manufacture of commercial refrigeration equipment at PT Gaya Teknik | Individual | ASP | IDS | REF | 25 | INV | 88 | A | I | CFC | 10 | 10 | 0 | 0 | 1998-07-01 | 2000-06-01 | 2000-08-01 |  | 2001-12-01 | 2003-12-01 | 147880 | -2358 | 145522 | 145522 | 100% | 0 | 0 | 0 | 19224.4 | -306.54 | 18917.86 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Conversion project to CFC-free technology in the manufacture of commercial refrigeration equipment at PT Aneka Froze Citratama | Individual | ASP | IDS | REF | 25 | INV | 90 | A | I | CFC | 13.1 | 13.1 | 0 | 0 | 1998-07-01 | 2000-06-01 | 2000-08-01 |  | 2001-12-01 | 2003-11-01 | 174255 | -17790 | 156465 | 156465 | 100% | 0 | 0 | 0 | 22653.15 | -2312.7 | 20340.45 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Conversion of CFC-11 and CFC-12/R-502 to HCFC-141b (foam) and HFC-134a/R404a (refrigerant) technology in the manufacture of commercial refrigerators and display cases at P.T. Intermas Pacific | Individual | ASP | IDS | REF | 25 | INV | 92 | A | I | CFC | 17.9 | 17.9 | 0 | 0 | 1998-07-01 | 1999-11-01 | 2000-08-01 |  | 2001-12-01 | 2003-04-01 | 209300 | -20993 | 188307 | 188307 | 100% | 0 | 0 | 0 | 27209 | -2729.5 | 24479.5 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at PT Herry Alter's | Individual | ASP | IDS | REF | 26 | INV | 102 | A | I | CFC | 32.4 | 32.4 | 0 | 0 | 1998-11-01 | 1999-12-01 | 2000-12-01 |  | 2001-07-01 | 2003-04-01 | 438060 | -15658 | 422402 | 422402 | 100% | 0 | 0 | 0 | 56947.8 | -2035.54 | 54912.26 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at 3 enterprises: Bali Cool, Centrum Cool and Ever Cool | Individual | ASP | IDS | REF | 26 | INV | 104 | A | I | CFC | 15.2 | 15.2 | 0 | 0 | 1998-11-01 | 2000-06-01 | 2000-12-01 |  | 2001-12-01 | 2003-12-01 | 231800 | -1729 | 230071 | 230071 | 100% | 0 | 0 | 0 | 30134 | -224.77 | 29909.23 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b, CFC-12 to HFC-134a and R-502 to R-404A technology in the manufacture of commercial refrigeration equipment at PT Algron | Individual | ASP | IDS | REF | 26 | INV | 105 | A | I | CFC | 10.4 | 10.4 | 0 | 0 | 1998-11-01 | 2000-06-01 | 2000-12-01 |  | 2001-12-01 | 2003-11-01 | 158210 | 0 | 158210 | 158210 | 100% | 0 | 0 | 0 | 20567.3 | 0 | 20567.3 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at PT Tesaguna Sejati | Individual | ASP | IDS | REF | 26 | INV | 99 | A | I | CFC | 9.7 | 9.7 | 0 | 0 | 1998-11-01 | 2000-06-01 | 2000-12-01 |  | 2001-12-01 | 2003-12-01 | 147900 | 0 | 147900 | 147900 | 100% | 0 | 0 | 0 | 19227 | 0 | 19227 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Project preparation in the commercial refrigeration sector | Individual | ASP | IDS | REF | 33 | PRP | 123 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment and rigid foam at PT Nikoteknik | Individual | ASP | IDS | REF | 35 | INV | 131 | A | I | CFC | 27.9 | 27.9 | 0 | 0 | 2001-12-01 | 2003-01-01 | 2004-07-01 |  | 2003-11-01 | 2005-10-01 | 238903 | -19314 | 219589 | 219589 | 100% | 0 | 0 | 0 | 31057.39 | -2511 | 28546.39 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at PT Sapporo Mestika | Individual | ASP | IDS | REF | 35 | INV | 132 | A | I | CFC | 11.2 | 11.2 | 0 | 0 | 2001-12-01 | 2003-01-01 | 2004-07-01 |  | 2003-10-01 | 2005-10-01 | 153768 | -4603 | 149165 | 149165 | 100% | 0 | 0 | 0 | 19989.84 | -598 | 19391.84 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at PT Hatindo Metal Utama | Individual | ASP | IDS | REF | 35 | INV | 133 | A | I | CFC | 9.6 | 9.6 | 0 | 0 | 2001-12-01 | 2003-01-01 | 2004-07-01 |  | 2003-10-01 | 2006-10-01 | 145894 | 0 | 145894 | 145894 | 100% | 0 | 0 | 0 | 18966.22 | 0 | 18966.22 | 0 | 0 | Completed in 2003. Financially completed in 2006. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment and rigid foam at PT Leoindo Kreasi | Individual | ASP | IDS | REF | 35 | INV | 134 | A | I | CFC | 15.7 | 15.7 | 0 | 0 | 2001-12-01 | 2003-01-01 | 2004-07-01 |  | 2003-10-01 | 2005-10-01 | 119394 | -4838 | 114556 | 114556 | 100% | 0 | 0 | 0 | 15521.22 | -629 | 14892.22 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at PT Alfa Metalindo Agra | Individual | ASP | IDS | REF | 35 | INV | 135 | A | I | CFC | 9.7 | 9.7 | 0 | 0 | 2001-12-01 | 2003-01-01 | 2004-07-01 |  | 2003-10-01 | 2005-10-01 | 146960 | -3500 | 143460 | 143460 | 100% | 0 | 0 | 0 | 19104.8 | -455 | 18649.8 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at PT Gastro Gizi Sarana | Individual | ASP | IDS | REF | 35 | INV | 136 | A | I | CFC | 15.5 | 15.5 | 0 | 0 | 2001-12-01 | 2002-11-01 | 2004-07-01 |  | 2003-11-01 | 2005-10-01 | 221049 | -6055 | 214994 | 214994 | 100% | 0 | 0 | 0 | 28736.37 | -787 | 27949.37 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Project preparation in the manufacturing refrigeration sector (terminal phase-out) | Individual | ASP | IDS | REF | 36 | PRP | 137 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2003-04-01 | 2005-11-01 | 20000 | -2740 | 17260 | 17260 | 100% | 0 | 0 | 0 | 2600 | -356.2 | 2243.8 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Preparation of a refrigerant management plan | Individual | ASP | IDS | REF | 36 | PRP | 138 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2003-04-01 | 2005-11-01 | 35000 | -5430 | 29570 | 29570 | 100% | 0 | 0 | 0 | 4550 | -705.9 | 3844.1 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Sector phase-out plan for elimination of CFCs in the refrigeration (manufacturing) sector (first tranche) | Multi-Year | ASP | IDS | REF | 37 | INV | 148 | N | I | CFC | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-10-01 | 2002-12-01 |  | 2004-12-01 | 2013-04-01 | 1288000 | 0 | 1288000 | 1288000 | 100% | 0 | 0 | 0 | 111920 | 0 | 111920 | 0 | 0 | Financially completed in 2013. |  | 2002 | 2004-12-01 | Investment
FIN | UNDP | Refrigeration sector phase-out plan: refrigeration servicing | Multi-Year | ASP | IDS | REF | 38 | INV | 151 | N | I | CFC | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-11-01 | 2003-12-01 |  | 2005-12-01 | 2013-01-01 | 2196758 | 0 | 2196758 | 2196758 | 100% | 0 | 0 | 0 | 195708 | 0 | 195708 | 0 | 0 | Financially completed in 2013. |  | 2002 |  | Investment
FIN | IBRD | Refrigeration sector phase-out plan: MAC servicing sector | Multiyear | ASP | IDS | REF | 38 | INV | 153 | N | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-12-01 | 2003-12-01 |  | 2003-12-01 | 2010-05-01 | 1369800 | 0 | 1369800 | 1369800 | 100% | 0 | 0 |  | 121962 | 0 | 121962 | 0 | 0 | 2003 annual plan completed successfully. |  |  |  | INV | 0
FIN | UNDP | Sector phase-out plan for elimination of CFCs in the refrigeration (manufacturing) sector ( 2nd tranche) | Multi-Year | ASP | IDS | REF | 40 | INV | 154 | N | I | CFC | 150 | 150 | 0 | 0 | 2003-07-01 | 2004-12-01 | 2004-12-01 |  | 2004-12-01 | 2013-04-01 | 600000 | 0 | 600000 | 600000 | 100% | 0 | 0 | 0 | 52900 | 0 | 52900 | 0 | 0 | Financially completed in 2013. |  | 2003 |  | Investment
FIN | UNDP | Sector phase-out plan for elimination of CFCs in the refrigeration (manufacturing) sector (balance of second tranche) | Multi-Year | ASP | IDS | REF | 41 | INV | 155 | N | I | CFC | 150 | 150 | 0 | 0 | 2003-12-01 | 2005-01-01 | 2004-12-01 |  | 2006-06-01 | 2013-04-01 | 1600000 | 0 | 1600000 | 1600000 | 100% | 0 | 0 | 0 | 141100 | 0 | 141100 | 0 | 0 | Financially completed in 2013. |  | 2003 |  | Investment
FIN | IBRD | Sector phase-out plan for elimination of CFCs in the refrigeration (MAC servicing) sector: 2004 annual programme | Multiyear | ASP | IDS | REF | 41 | INV | 156 | N | I | CFC | 110 | 110 | 0 | 0 | 2003-12-01 | 2005-12-01 | 2004-12-01 |  | 2004-12-01 | 2010-05-01 | 1347300 | 0 | 1347300 | 1347300 | 100% | 0 | 0 |  | 119937 | 0 | 119937 | 0 | 0 | 2004 annual plan completed sucessfully. |  |  |  | INV | 0
FIN | UNDP | Sector phase-out plan for elimination of CFCs in the refrigeration (servicing) sector (second tranche) | Multi-Year | ASP | IDS | REF | 41 | INV | 157 | N | I | CFC | 200 | 200 | 0 | 0 | 2003-12-01 | 2006-01-01 | 2004-12-01 |  | 2006-12-01 | 2013-02-01 | 1805987 | 0 | 1805987 | 1805987 | 100% | 0 | 0 | 0 | 160939 | 0 | 160939 | 0 | 0 | Financially completed in 2013. |  | 2003 | 2006-12-01 | Investment
FIN | UNDP | Phase-out of CFCs in the refrigeration sector (manufacturing) (third tranche) | Multi-Year | ASP | IDS | REF | 44 | INV | 163 | N | I | CFC | 300 | 300 | 0 | 0 | 2004-12-01 | 2007-01-01 | 2005-12-01 |  | 2007-12-01 | 2013-04-01 | 1762000 | 0 | 1762000 | 1762000 | 100% | 0 | 0 | 0 | 156900 | 0 | 156900 | 0 | 0 | Financially completed in 2013. |  | 2004 |  | Investment
FIN | UNDP | Phase-out of CFCs in the refrigeration sector (servicing) (third tranche) | Multi-Year | ASP | IDS | REF | 44 | INV | 164 | N | I | CFC | 200 | 200 | 0 | 0 | 2004-12-01 | 2008-01-01 | 2005-12-01 |  | 2008-12-01 | 2013-01-01 | 500000 | 0 | 500000 | 500000 | 100% | 0 | 0 | 0 | 43400 | 0 | 43400 | 0 | 0 | Financially completed in 2013. |  | 2004 |  | Investment
FIN | IBRD | Phase-out of CFCs in the refrigeration sector (MAC) (third tranche) | Multiyear | ASP | IDS | REF | 44 | INV | 165 | N | I | CFC | 110 | 110 | 0 | 0 | 2004-12-01 | 2006-11-01 | 2005-12-01 |  | 2005-12-01 | 2010-05-01 | 1347300 | 0 | 1347300 | 1347300 | 100% | 0 | 0 |  | 119937 | 0 | 119937 | 0 | 0 | 2005 consumption reduction target was achieved. |  |  |  | INV | 0
FIN | IBRD | Phase-out of CFCs in the refrigeration sector (MAC) (fourth tranche) | Multiyear | ASP | IDS | REF | 48 | INV | 173 | N | I | CFC | 110 | 110 | 0 | 0 | 2006-04-01 | 2008-12-01 | 2007-04-01 |  | 2008-12-01 | 2010-05-01 | 126800 | 0 | 126800 | 126800 | 100% | 0 | 0 |  | 10092 | 0 | 10092 | 0 | 0 | Completed. |  |  |  | INV | 0
FIN | UNDP | Phase-out of CFCs in the refrigeration sector (manufacturing) (fourth tranche) | Multi-Year | ASP | IDS | REF | 48 | INV | 174 | N | I | CFC | 300 | 300 | 0 | 0 | 2006-04-01 | 2008-02-01 | 2007-04-01 |  | 2009-12-01 | 2013-04-01 | 750000 | 0 | 750000 | 750000 | 100% | 0 | 0 | 0 | 67500 | 0 | 67500 | 0 | 0 | Financially completed in 2013. |  | 2006 |  | Investment
FIN | UNDP | Phase-out of CFCs in the refrigeration sector (servicing) (fourth tranche) | Multi-Year | ASP | IDS | REF | 48 | INV | 175 | N | I | CFC | 200 | 200 | 0 | 0 | 2006-04-01 | 2008-11-01 | 2007-04-01 |  | 2008-12-01 | 2013-01-01 | 250000 | 0 | 250000 | 250000 | 100% | 0 | 0 | 0 | 21300 | 0 | 21300 | 0 | 0 | Financially completed in 2013. |  | 2006 |  | Investment
FIN | UNDP | Phase-out of CFCs in the refrigeration sector (manufacturing) (fifth tranche) | Multi-Year | ASP | IDS | REF | 51 | INV | 177 | N | I | CFC | 300 | 300 | 0 | 0 | 2007-03-01 | 2009-01-01 | 2009-03-01 |  | 2010-12-01 | 2013-04-01 | 217000 | 0 | 217000 | 217000 | 100% | 0 | 0 | 0 | 19530 | 0 | 19530 | 0 | 0 | Financially completed in 2013. |  | 2007 |  | Investment
FIN | IBRD | Phase-out of CFCs in the refrigeration sector (MAC) (fifth tranche) | Multiyear | ASP | IDS | REF | 51 | INV | 178 | N | I | CFC | 110 | 110 | 0 | 0 | 2007-03-01 | 2008-12-01 | 2008-03-01 |  | 2010-03-01 | 2010-05-01 | 125800 | 0 | 125800 | 125800 | 100% | 0 | 0 |  | 10002 | 0 | 10002 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | UNDP | Phase-out of CFCs in the refrigeration sector (servicing) (fifth tranche) | Multi-Year | ASP | IDS | REF | 51 | INV | 179 | N | I | CFC | 172 | 172 | 0 | 0 | 2007-03-01 | 2009-02-01 | 2009-03-01 |  | 2010-12-01 | 2013-02-01 | 159555 | -9048.14 | 150506.86 | 150507 | 100% | -0.14 | 0 | 0 | 13160 | -746.29 | 12413.7264 | -0.016447 | 0 | Financially completed in 2013. |  | 2007 |  | Investment
FIN | UNDP | Phase-out of CFCs in the refrigeration sector (manufacturing) (sixth tranche) | Multi-Year | ASP | IDS | REF | 54 | INV | 181 | N | I | CFC | 241 | 241 | 0 | 0 | 2008-04-01 | 2008-05-01 | 2010-03-01 |  | 2011-12-01 | 2013-04-01 | 181000 | -6640.07 | 174359.93 | 174360 | 100% | -0.07 | 0 | 0 | 16290 | -597.61 | 15692.4 | -0.01 | 0 | Financially completed in 2013. | Project targeted for financial closure in 2012 | 2008 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (refrigeration manufacturing sector except air-to-air air-conditioning) | Individual | ASP | IDS | REF | 57 | PRP | 185 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-05-01 | 2010-03-01 |  | 2010-12-01 | 2012-06-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 5250 | 0 | 5250 | 0 | 0 | Financially completed in 2012. |  | 2009 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (air-to-air air-conditioning sector) | Individual | ASP | IDS | REF | 57 | PRP | 188 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-05-01 | 2010-03-01 |  | 2012-06-01 | 2013-02-01 | 20000 | -3482.96 | 16517.04 | 16517 | 100% | 0.04 | 0 | 0 | 1500 | -261.22 | 1238.775 | 0.005 | 0 | Financially completed in 2013. |  | 2009 |  | Investment
FIN | UNDP | Country programme preparation | Individual | ASP | IDS | SEV | 08 | CPG | 01 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1992-11-01 | 1993-10-01 |  | 1994-03-01 | 1997-12-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 26000 | 0 | 26000 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | IBRD | Country programme preparation | Individual | ASP | IDS | SEV | 08 | CPG | 02 | A | I |  | 0 | 0 | 0 | 0 | 1992-10-01 | 1992-12-31 | 1993-10-01 |  | 1992-12-01 | 1992-12-01 | 54000 | -12931 | 41069 | 41069 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation advance I (1993) |  | ASP | IDS | SEV | 09 | PRP | 03 | N | D |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-09-30 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 250000 | 0 | 250000 | 250000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation activities are complete. 14 subproject proposals were prepared. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1993) |  | ASP | IDS | SEV | 09 | PRP | 04 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 206000 | 1805 | 207805 | 207805 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Institutional strengthening of the Ozone Layer Protection and Ozone Depleting Substances Phase-out Unit | Individual | ASP | IDS | SEV | 10 | INS | 05 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1994-04-01 | 1996-06-01 |  | 1997-06-01 | 2003-04-01 | 314780 | 0 | 314780 | 314780 | 100% | 0 | 0 | 0 | 40921.4 | 0 | 40921.4 | 0 | 0 | Completed in 1997. Financially completed in 2003. |  | 1993 |  | Non-Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | IDS | SEV | 11 | PRP | 06 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-01 | 1995-02-01 |  | 1994-11-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1993 |  | Investment
FIN | IBRD | Completion of processing of investment projects approved at the 11th ExCom Meeting |  | ASP | IDS | SEV | 12 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 128899 | 43396 | 172295 | 172295 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation and processing complete. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1994) |  | ASP | IDS | SEV | 12 | PRP | 15 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-09-30 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 117312 | -81569 | 35743 | 35743 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Training of the Financial Intermediary on Multilateral Fund and World Bank project processing procedures | Individual | ASP | IDS | SEV | 12 | TRA | 14 | N | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1996-07-01 | 1995-03-01 |  | 1998-08-01 | 1998-08-01 | 50000 | -701 | 49299 | 49299 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | TA Uppindo project is closed. PCR submitted. 3% agency fee incl. |  |  | 1997-12-01 | Non-INV | 0
FIN | IBRD | ODS phase out investment project preparation (1994) |  | ASP | IDS | SEV | 13 | PRP | 17 | N | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1996-08-08 | 1996-08-01 |  | 1996-08-01 | 1996-08-01 | 170000 | 0 | 170000 | 170000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | UNIDO | Project formulation for phasing out ODS in small and medium scale industries | Individual | ASP | IDS | SEV | 15 | PRP | 24 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-03-01 | 1995-06-01 |  | 2000-01-01 | 2002-05-01 | 80000 | -2803 | 77197 | 77197.25 | 100% | -0.25 | 0 |  | 10400 | -380 | 10020 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNDP | Project preparation assistance in solvent, halon and refrigeration sectors | Individual | ASP | IDS | SEV | 15 | PRP | 28 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-01-01 | 1995-06-01 |  | 1996-03-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1996. Financially completed in 1997. |  | 1994 |  | Investment
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | ASP | IDS | SEV | 16 | PRP | 31 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 108824 | 0 | 108824 | 108824 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation/supervision of investment projects ODS II (1995) |  | ASP | IDS | SEV | 16 | PRP | 62 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-31 | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 50000 | -32695 | 17305 | 17305 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | Australia | Indonesian ODS control policy | Individual | ASP | IDS | SEV | 17 | TAS | 33 | A | D |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-05-01 | 1996-01-01 |  | 1996-01-01 | 1996-01-01 | 42000 | 0 | 42000 | 42000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed |  | 1995
FIN | UNDP | Project preparation assistance | Individual | ASP | IDS | SEV | 18 | PRP | 41 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-11-01 | 2002-05-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1996. Financially completed in 2002. |  | 1995 |  | Investment
FIN | IBRD | Project preparation |  | ASP | IDS | SEV | 18 | PRP | 42 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNIDO | Project formulation of investment projects in the aerosol and foam sectors | Individual | ASP | IDS | SEV | 21 | PRP | 54 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-04-01 | 1997-08-01 |  | 2000-10-01 | 2001-07-01 | 20000 | -4478 | 15522 | 15522 | 100% | 0 | 0 |  | 2600 | -585 | 2015 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | IBRD | Project preparation |  | ASP | IDS | SEV | 21 | PRP | 55 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 179000 | -150000 | 29000 | 29000 | 100% | 0 | 0 |  | 23270 | -19500 | 3770 | 0 | 0 | For IDS/SEV/21/PRP/55 $179,000 was approved of which $29,000 was expensed, and the remaining $150,000 was transferred to Indonesia PPA III. |  |  |  | Non-INV | 0
FIN | UNDP | Renewal of institutional strengthening | Individual | ASP | IDS | SEV | 23 | INS | 80 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-07-01 | 1999-12-01 |  | 2000-12-01 | 2003-04-01 | 208650 | -265 | 208385 | 208385 | 100% | 0 | 0 | 0 | 27124.5 | -34.45 | 27090.05 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1997 |  | Non-Investment
FIN | UNIDO | Preparation of an investment project for phasing out ODS at three enterprises including the companies Nirwana and P.T. Success | Individual | ASP | IDS | SEV | 23 | PRP | 64 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-09-01 | 1998-03-01 |  | 2000-10-01 | 2001-07-01 | 10000 | 9025 | 19025 | 19024.96 | 100% | 0.04 | 0 |  | 1300 | 1169 | 2469 | 0 | 0 | FIN
FIN | UNDP | Extension of institutional strengthening project (Phase III) | Individual | ASP | IDS | SEV | 32 | INS | 121 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2002-05-01 | 2003-01-01 |  | 2004-09-01 | 2006-08-01 | 208650 | -86 | 208564 | 208564 | 100% | 0 | 0 | 0 | 27124.5 | -11.13 | 27113.37 | 0 | 0 | Completed in 2004. Financially completed in 2006. |  | 2000 |  | Non-Investment
FIN | IBRD | Project preparation for 3 projects in the foam sector and one in the refrigeration sector |  | ASP | IDS | SEV | 33 | PRP | 125 | A | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-12-01 | 2001-12-01 |  | 2001-12-01 | 2001-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of two sector plans in the aerosol sector and in the foam sector |  | ASP | IDS | SEV | 36 | PRP | 142 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-09-01 |  | 2003-09-01 | 2003-09-01 | 130000 | 0 | 130000 | 130000 | 100% | 0 | 0 |  | 16900 | 0 | 16900 | 0 | 0 | Foam and aerosol proposals prepared and submitted to Excom. |  |  |  | Non-INV | 0
FIN | IBRD | Strengthening of import/export control | Individual | ASP | IDS | SEV | 37 | TAS | 149 | N | I | CFC | 9.1 | 9.1 | 0 | 0 | 2002-07-01 | 2003-12-01 | 2004-08-01 |  | 2006-12-01 | 2006-12-01 | 110000 | 0 | 110000 | 110000 | 100% | 0 | 0 |  | 14300 | 0 | 14300 | 0 | 0 | Gov. of Indonesia made great progress in improving import licensing and quota system to monitor and control ODS import. Revised draft to existing regulation agreed upon by Ministry of Trade and other relevant government depts. New regulation adopted on June 22, 2006. Old regulation with provision that only one company can import ODS declared void. Standard Operating Procedures drafted to provide guidance for implementation of new regulation. Project completed. |  |  |  | INV | 0
FIN | UNDP | Extension of institutional strengthening project | Individual | ASP | IDS | SEV | 41 | INS | 159 | N | I | No_ODP | 22.4 | 22.4 | 0 | 0 | 2003-12-01 | 2005-02-01 | 2005-12-01 |  | 2006-12-01 | 2011-11-01 | 271245 | -702.61 | 270542.39 | 270542 | 100% | 0.39 | 0 | 0 | 20343 | -52.69 | 20290.276 | 0.034049 | 0 | Completed in 2006. |  | 2003 |  | Non-Investment
FIN | UNDP | Assistance to carry out an HCFC survey | Individual | ASP | IDS | SEV | 45 | TAS | 169 | A | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-07-01 | 2006-12-01 |  | 2008-08-01 | 2009-12-01 | 114679 | -17119 | 97560 | 97560 | 100% | 0 | 0 | 0 | 10321 | -1540.69 | 8780.3064 | 0.0036 | 0 | Completed in 2008. Financially completed in 2009. |  | 2005 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase V) | Individual | ASP | IDS | SEV | 47 | INS | 171 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-12-01 | 2007-12-01 |  | 2007-12-01 | 2011-11-01 | 271245 | -100.7 | 271144.3 | 271144 | 100% | 0.3 | 0 | 0 | 20343 | -7.55 | 20335.4251 | 0.0249 | 0 | Completed in 2007. |  | 2005 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase VI) | Individual | ASP | IDS | SEV | 53 | INS | 180 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-01-01 | 2009-11-01 |  | 2009-12-01 | 2012-07-01 | 271245 | 0 | 271245 | 271245 | 100% | 0 | 0 | 0 | 20343 | 0 | 20343 | 0 | 0 | Financially completed in 2012. |  | 2007 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase VII) | Individual | ASP | IDS | SEV | 59 | INS | 189 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-04-01 | 2011-12-01 |  | 2011-12-01 | 2013-04-01 | 135623 | 134546.26 | 270169.26 | 270169 | 100% | 0.26 | 0 | 0 | 10172 | 10091.24 | 20263.2228 | 0.017201 | 0 | Financially completed in 2013. | The project is being financially closed by June 12, and activities will continue under IS-VIII. | 2009 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase VIII: 1/2012-12/2013) | Individual | ASP | IDS | SEV | 65 | INS | 197 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-03-01 | 2013-12-01 |  | 2013-12-01 | 2015-12-01 | 271246 | -1517 | 269729 | 269729 | 100% | 0 | 0 | 0 | 20343 | -113.77 | 20229.2275 | 0.0025 | 0 | Financially completed in 2015. | Completed in 2013. | 2011 |  | Non-investment
COM | UNDP | Extension of institutional strengthening project (phase IX: 1/2014-12/2015) | Individual | ASP | IDS | SEV | 71 | INS | 201 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2013-12-01 | 2014-07-01 | 2015-12-01 |  | 2015-12-01 |  | 271246 | 0 | 271246 | 271106.43 | 99.95% | 139.57 | 0 | 118.6345 | 18987 | 0 | 18977.2302 | 9.7698 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2015. |  | 2013 |  | Non-Investment
ONG | UNDP | Extension of institutional strengthening project (phase X: 1/2016-12/2017) | Individual | ASP | IDS | SEV | 75 | INS | 206 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2015-11-01 | 2016-06-01 | 2017-12-01 | 2017-12-01 |  |  | 347194 | 0 | 347194 | 132826.06 | 38.26% | 214367.94 | 0 | 85747.176 | 24304 | 0 | 9297.9849 | 15006.0151 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): DoA has been issued, on going Prodoc signed (actual/planned, yes/no and date):42461 Missions undertaken (actual/planned):- TOR for consultants/subcontracts completed (actual/planned): Contract/PO/MOA agreements signed: First disbursement date (actual/planned): 42522Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | on progress | 2015 |  | Non-Investment
CLO | UNDP | Elimination of the use of 111 TCA and CFC-113 in the manufacture of metal and plastic motorcycle parts at PT KGD Indonesia, Inc. | Individual | ASP | IDS | SOL | 15 | INV | 25 | A | R | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 |  | 1996-02-01 |  |  | 1997-05-01 | 88000 | -88000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 11440 | -11440 | 0 | 0 | 0 | Canceled in 1997. Financially Completed in 1997. |  | 1994 |  | Investment
FIN | IBRD | Conversion of metal cleaning processes from 1.1.1 TCA to aqueous cleaning at PT INTI (Industri Telekomunikasi Indonesia) | Individual | ASP | IDS | SOL | 18 | INV | 38 | N | I | TCA | 0.97 | 1 | 0 | 0 | 1995-11-01 | 1996-07-01 | 1996-11-01 |  | 1996-06-01 | 1996-08-01 | 37380 | 0 | 37380 | 37380 | 100% | 0 | 0 |  | 4859.4 | 0 | 4859.4 | 0 | 0 | Project is completed and closed. PCR submitted. |  |  | 1996-08-01 | INV | 0
FIN | IBRD | Conversion of metal cleaning processes from 1,1,1 TCA to aqueous cleaning at PT. Garuda Indonesia | Individual | ASP | IDS | SOL | 18 | INV | 39 | N | I | TCA | 0.86 | 2.67 | 0 | 0 | 1995-11-01 | 1997-10-01 | 1996-11-01 |  | 1998-11-01 | 1998-11-01 | 33264 | -169 | 33095 | 33095 | 100% | 0 | 0 |  | 4324.32 | -21.97 | 4302.35 | 0 | 0 | The project is completed. Technical audit has been done with satisfactory result. PCR had been submitted. Project is closed. |  |  | 1997-12-01 | INV | 0
CLO | IBRD | Conversion of metal cleaning processes from 1,1,1 TCA to aqueous cleaning at PT. Markindo Theco | Individual | ASP | IDS | SOL | 18 | INV | 40 | N | I |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1996-11-01 |  |  | 1999-03-01 | 83200 | -83200 | 0 | 0 | #DIV/0! | 0 | 0 |  | 10816 | -10816 | 0 | 0 | 0 | CANCELLED. Funds returned to 27th meeting. |  |  | 1996-11-01 | INV | 0
FIN | IBRD | Conversion of correction fluid manufacturing process from 1,1,1 TCA to non-ODS solvent at PT Cahaya Biru Sakti | Individual | ASP | IDS | SOL | 20 | INV | 50 | N | I | TCA | 18.2 | 18.2 | 0 | 0 | 1996-10-01 | 1997-09-01 | 1997-10-01 |  | 1998-06-01 | 2000-10-01 | 700700 | -125383 | 575317 | 575317 | 100% | 0 | 0 |  | 91091 | -16299.79 | 74791.21 | 0 | 0 | Project completed and PCR submitted Jan. 01. |  |  | 1999-06-01 | INV | 0
FIN | UNIDO | Plan for terminal phase-out of ODS in the solvent sector | Multi-Year | ASP | IDS | SOL | 44 | INV | 162 | A | I | CFC CTC TCA | 100.1 | 100.1 |  |  | 2004-12-01 | 2005-02-01 | 2006-12-01 |  | 2008-10-01 | 2009-09-01 | 1464733 | -670 | 1464063 | 1464062.74 | 100% | 0.26 | 0 |  | 108974 | -50 | 108924 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation for HCFC phase-out investment activities (solvent sector) | Individual | ASP | IDS | SOL | 61 | PRP | 190 | A | I |  | 0 | 0 |  |  | 2010-07-01 | 2010-10-01 | 2011-07-31 |  | 2010-12-01 | 2012-05-01 | 10000 | -353 | 9647 | 9647.1 | 100% | -0.1 | 0 |  | 750 | -26 | 724 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | IBRD | Aero Pharma aerosol conversion | Individual | ASP | IND | ARS | 11 | INV | 10 | N | I | CFC | 36 | 36 | 0 | 0 | 1993-11-01 | 1996-08-01 | 1994-11-01 |  | 2000-10-01 | 1998-06-01 | 62520 | 0 | 62520 | 62520 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | No change in previous status |  |  | 1999-06-01 | INV | 0
TRF | IBRD | Conversion of 5 aerosol filling installations to manual filling equipment using HAP | Individual | ASP | IND | ARS | 17 | DEM | 50 | N | I |  | 0 | 0 | 0 | 0 | 1995-07-01 |  | 1996-07-01 |  |  | 1995-07-01 | 181550 | -181550 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project implementation has been transferred to UNDP. |  |  | 1996-06-01 | Non-INV | 0
CLO | UNIDO | Preparation of umbrella project for ODS phase out in the Aerosol sector (small-scale industries) | Individual | ASP | IND | ARS | 18 | PRP | 53 | A | I |  | 0 | 0 |  |  | 1995-11-01 |  | 1996-05-01 |  |  | 1997-06-01 | 20000 | -20000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 2600 | -2600 | 0 | 0 | 0 | CLO
FIN | UNDP | Conversion of 5 aerosol filling installations to manual filling equipment using HAP | Individual | ASP | IND | ARS | 19 | DEM | 69 | A | I | CFC | 0 | 0 | 0 | 0 | 1996-05-01 | 1998-09-01 | 1997-06-01 |  | 2001-11-01 | 2002-03-01 | 0 | 168783 | 168783 | 168783 | 100% | 0 | 0 | 0 | 0 | 21941.79 | 21941.79 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1996 | 1998-04-01 | Non-Investment
FIN | IBRD | Stella Industries aerosol conversion | Individual | ASP | IND | ARS | 22 | INV | 113 | N | I | CFC | 105 | 105 | 0 | 0 | 1997-05-01 | 1997-08-01 | 1998-06-01 |  | 1998-09-01 | 1998-09-01 | 269175 | 0 | 269175 | 269175 | 100% | 0 | 0 |  | 34992.75 | 0 | 34992.75 | 0 | 0 | Project completed. PCR submitted. |  |  |  | INV | 0
FIN | IBRD | Accra Pack India Pvt. Ltd. aerosol conversion | Individual | ASP | IND | ARS | 22 | INV | 114 | N | I | CFC | 52 | 52 | 0 | 0 | 1997-05-01 | 1999-02-01 | 1998-06-01 |  | 2001-07-01 | 2002-04-01 | 129690 | -7545 | 122145 | 122145 | 100% | 0 | 0 |  | 16859.7 | -980.85 | 15878.85 | 0 | 0 | PCR to be finalized and submitted in 2003. |  |  | 1999-06-01 | INV | 0
FIN | UNDP | Ultra Tech Specialty Chemicals Pvt. Ltd. aerosol conversion | Individual | ASP | IND | ARS | 22 | INV | 115 | A | I | CFC | 30.8 | 30.8 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1998-06-01 |  | 1999-11-01 | 2002-03-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1997 | 1999-09-01 | Investment
FIN | UNDP | Texas Enterprises aerosol conversion, Bombay | Individual | ASP | IND | ARS | 22 | INV | 117 | A | I | CFC | 31.2 | 31.2 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1998-06-01 |  | 1999-11-01 | 2001-12-01 | 70000 | -4903 | 65097 | 65097 | 100% | 0 | 0 | 0 | 9100 | -637.13 | 8462.87 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 | 1999-09-01 | Investment
FIN | UNDP | Aerol Formulations aerosol conversion | Individual | ASP | IND | ARS | 22 | INV | 118 | A | I | CFC | 31 | 31 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1998-06-01 |  | 1999-11-01 | 2001-12-01 | 69450 | -790.74 | 68659.26 | 68659 | 100% | 0.26 | 0 | 0 | 9028.5 | -102.8 | 8925.67 | 0.03 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 | 1999-09-01 | Investment
FIN | IBRD | My Fair Lady aerosol conversion, Delhi | Individual | ASP | IND | ARS | 22 | INV | 119 | N | I | CFC | 59.4 | 59.4 | 0 | 0 | 1997-05-01 | 1999-06-01 | 1998-06-01 |  | 2000-12-01 | 2002-09-01 | 113975 | -16195 | 97780 | 97780.37 | 100% | -0.37 | -0.37 |  | 14816.75 | -2105.35 | 12711.4 | 0 | 0 | PCR finalized and submitted to ExCom. |  |  | 1999-06-01 | INV | 0
FIN | UNDP | Aerosols D'Asia Pvt. Ltd. aerosol conversion | Individual | ASP | IND | ARS | 22 | INV | 135 | A | I | CFC | 18 | 18 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1998-06-01 |  | 1999-11-01 | 2001-12-01 | 69450 | -2379 | 67071 | 67071 | 100% | 0 | 0 | 0 | 9028.5 | -309 | 8719.5 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 | 1999-09-01 | Investment
FIN | UNDP | Asian Aerosols Pvt. Ltd. aerosol conversion | Individual | ASP | IND | ARS | 22 | INV | 136 | A | I | CFC | 25 | 25 | 0 | 0 | 1997-05-01 | 1998-12-01 | 1998-06-01 |  | 1999-11-01 | 2001-12-01 | 90890 | -7767 | 83123 | 83123 | 100% | 0 | 0 | 0 | 11815.7 | -1010 | 10805.7 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 | 1999-09-01 | Investment
FIN | IBRD | Attarwala and Co. Pvt. Ltd. aerosol conversion, Bombay | Individual | ASP | IND | ARS | 22 | INV | 137 | N | I | CFC | 30.6 | 30.6 | 0 | 0 | 1997-05-01 | 2001-07-01 | 1998-06-01 |  | 2002-12-01 | 2005-01-01 | 134250 | -12102 | 122148 | 122148 | 100% | 0 | 0 |  | 17452.5 | -1573.26 | 15879.24 | 0 | 0 | Project financially completed and balance funds returned to ExCom. PCR submitted. |  |  | 1999-12-01 | INV | 0
FIN | UNDP | Aero Pack Products aerosol conversion | Individual | ASP | IND | ARS | 22 | INV | 138 | A | I | CFC | 20.4 | 20.4 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1998-06-01 |  | 1999-11-01 | 2002-04-01 | 69450 | 0 | 69450 | 69450 | 100% | 0 | 0 | 0 | 9028.5 | 0 | 9028.5 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1997 | 1999-09-01 | Investment
FIN | IBRD | Aero Industries aerosol conversion, Vapi | Individual | ASP | IND | ARS | 22 | INV | 139 | N | I | CFC | 27.6 | 27.6 | 0 | 0 | 1997-05-01 | 1998-05-01 | 1998-06-01 |  | 1999-06-01 | 1999-05-01 | 121735 | -3903 | 117832 | 117832 | 100% | 0 | 0 |  | 15825.55 | -507.39 | 15318.16 | 0 | 0 | Project completed and PCR submitted. |  |  |  | INV | 0
CLO | UNDP | Meenakshi aerosol and cosmetics conversion, Delhi | Individual | ASP | IND | ARS | 22 | INV | 140 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 |  | 1998-06-01 |  |  | 1998-07-01 | 98940 | -98940 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 12862.2 | -12862.2 | 0 | 0 | 0 | Canceled in 1998. Financially Completed in 1998. |  | 1997 |  | Investment
FIN | IBRD | Aeropres aerosol conversion, Vapi | Individual | ASP | IND | ARS | 22 | INV | 141 | N | I | CFC | 50 | 50 | 0 | 0 | 1997-05-01 | 1998-05-01 | 1998-06-01 |  | 1999-06-01 | 2000-10-01 | 146860 | -4040 | 142820 | 142819.81 | 100% | 0.19 | 0.19 |  | 19091.8 | -525.2 | 18566.6 | 0 | 0 | Project completed and PCR submitted. |  |  |  | INV | 0
FIN | UNDP | Aerosol conversion at Sunder Chemical | Individual | ASP | IND | ARS | 24 | INV | 167 | A | I | CFC | 15 | 15 | 0 | 0 | 1998-03-01 | 1998-12-01 | 2000-04-01 |  | 2000-06-01 | 2001-12-01 | 59892 | -3617 | 56275 | 56275 | 100% | 0 | 0 | 0 | 7785.96 | -470 | 7315.96 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Aerosol conversion at Sara-Chem Pvt. Ltd. | Individual | ASP | IND | ARS | 24 | INV | 171 | A | I | CFC | 23.3 | 23.3 | 0 | 0 | 1998-03-01 | 1998-11-01 | 2000-04-01 |  | 2001-03-01 | 2002-03-01 | 89164 | -29723 | 59441 | 59441 | 100% | 0 | 0 | 0 | 11591.32 | -3863.99 | 7727.33 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Aerosol conversion at Maja Cosmetics Pvt. Ltd. | Individual | ASP | IND | ARS | 24 | INV | 172 | A | I | CFC | 31.3 | 31.3 | 0 | 0 | 1998-03-01 | 1998-12-01 | 2000-04-01 |  | 2001-03-01 | 2002-03-01 | 125240 | -705 | 124535 | 124535 | 100% | 0 | 0 | 0 | 16281.2 | -91.65 | 16189.55 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Aerosol conversion at Spray Products | Individual | ASP | IND | ARS | 24 | INV | 173 | A | I | CFC | 16.8 | 16.8 | 0 | 0 | 1998-03-01 | 1998-11-01 | 2000-04-01 |  | 1999-11-01 | 2001-12-01 | 65486 | -2975 | 62511 | 62511 | 100% | 0 | 0 | 0 | 8513.18 | -387 | 8126.18 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Aerosol conversion at Chem-Verse Consultants | Individual | ASP | IND | ARS | 24 | INV | 174 | A | I | CFC | 18 | 18 | 0 | 0 | 1998-03-01 | 1998-12-01 | 2000-04-01 |  | 2000-06-01 | 2001-12-01 | 67324 | -1872 | 65452 | 65452 | 100% | 0 | 0 | 0 | 8752.12 | -243 | 8509.12 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Aerosol Conversion at Midas Care Pharmaceuticals | Individual | ASP | IND | ARS | 24 | INV | 179 | A | I | CFC | 25.2 | 25.2 | 0 | 0 | 1998-03-01 | 1998-12-01 | 2000-04-01 |  | 1999-11-01 | 2001-12-01 | 110880 | -2729 | 108151 | 108151 | 100% | 0 | 0 | 0 | 14414.4 | -355 | 14059.4 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Project preparation for 3 projects in the aerosol sector | Individual | ASP | IND | ARS | 24 | PRP | 161 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1999-06-01 | 2001-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Preparation of two projects in aerosol sector | Individual | ASP | IND | ARS | 27 | PRP | 201 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-11-01 | 2000-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1999 |  | Investment
FIN | UNDP | Phaseout of CFC-12 and CTC at Vimsons Aerosol by substituting with HAPs | Individual | ASP | IND | ARS | 28 | INV | 213 | A | I | CTC/CFC | 18.2 | 18.2 | 0 | 0 | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2001-03-01 | 2002-11-01 | 66500 | -18505 | 47995 | 47995 | 100% | 0 | 0 | 0 | 8645 | -2406 | 6239 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Phaseout of CFC by substituting HAPs at Syncaps | Individual | ASP | IND | ARS | 28 | INV | 221 | A | I | CFC | 53.5 | 53.5 | 0 | 0 | 1999-07-01 | 2001-05-01 | 2002-02-01 |  | 2005-09-01 | 2007-01-01 | 161518 | -15270 | 146248 | 146248 | 100% | 0 | 0 | 0 | 20997.34 | -1985.07 | 19012.2721 | -0.0021 | 0 | Completed in 2005. Financially completed in 2007. |  | 1999 |  | Investment
FIN | UNDP | Phaseout of CFC-12 and CTC by substituting with HAPs at Ruby Aerosols | Individual | ASP | IND | ARS | 28 | INV | 227 | A | I | CTC/CFC | 22.2 | 22.2 | 0 | 0 | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2002-01-01 | 2005-11-01 | 45800 | -16 | 45784 | 45784 | 100% | 0 | 0 | 0 | 5954 | -2.08 | 5951.92 | -2.8e-05 | 0 | Completed in 2002. Financially completed in 2005. |  | 1999 |  | Investment
FIN | UNDP | Technical assistance for safety and technical programme to assist SME's manufacturing aerosol products (Phase I) | Individual | ASP | IND | ARS | 29 | TAS | 244 | A | I | CFC | 125 | 125 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2002-12-01 |  | 2004-09-01 | 2008-04-01 | 155000 | -16537 | 138463 | 138463 | 100% | 0 | 0 | 0 | 20150 | -2149.81 | 18000.19 | 0 | 0 | Completed in 2004. Financially completed in 2008. |  | 1999 |  | Non-Investment
FIN | UNDP | Project preparation in the aerosol sector | Individual | ASP | IND | ARS | 33 | PRP | 298 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Preparation of a terminal programme in the aerosol sector | Individual | ASP | IND | ARS | 36 | PRP | 345 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2005-11-01 | 25000 | -3638 | 21362 | 21362 | 100% | 0 | 0 | 0 | 3250 | -472.94 | 2777.06 | 0 | 0 | Completed in 2002. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Terminal umbrella project in the aerosol sector | Individual | ASP | IND | ARS | 38 | INV | 358 | A | I | CTC/CFC | 132.5 | 132.5 | 0 | 0 | 2002-11-01 | 2003-02-01 | 2004-11-01 |  | 2007-03-01 | 2013-08-01 | 583000 | 0 | 583000 | 583000 | 100% | 0 | 0 | 0 | 74130 | 0 | 74130 | 0 | 0 | Financially completed in 2013. |  | 2002 |  | Investment
FIN | UNDP | MDI Transitional Strategy | Individual | ASP | IND | ARS | 41 | TAS | 368 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2003-12-01 |  | 2004-12-01 |  | 2008-07-01 | 2011-11-01 | 30000 | -30000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 2250 | -2250 | 0 | 0 | 0 | Completed in 2008. |  | 2003 |  | Non-Investment
FIN | UNDP | Project preparation for a MDI investment project | Individual | ASP | IND | ARS | 52 | PRP | 411 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-02-01 | 2008-07-01 |  | 2008-07-01 | 2010-01-01 | 100000 | -23585.72 | 76414.28 | 76414 | 100% | 0.28 | 0 | 0 | 7500 | -1768.93 | 5731.05 | 0.02 | 0 | Financially completed in 2010. |  | 2007 |  | Investment
FIN | UNDP | Plan for phase-out of CFCs in the manufacture of pharmaceutical MDIs | Individual | ASP | IND | ARS | 56 | INV | 423 | N | I | CFC | 564.6 | 564.6 | 0 | 0 | 2008-11-01 | 2009-05-01 | 2013-11-01 |  | 2015-12-01 | 2016-12-01 | 8082267 | -242277 | 7839990 | 7839990 | 100% | 0 | 0 | 0 | 606170 | -18170.77 | 587999.2257 | 0.0043 | 0 | Financially completed in 2016. | All major project activities have been completed and only a few verification and administrative steps remaining for completion. Discussions were held on completion of pending activities and plan finalised in Jan 2015 for completing the projects by end of the year 2015. | 2008 |  | Investment
COM | Italy | Plan for phase-out of CFCs in the manufacture of pharmaceutical MDIs | Individual | ASP | IND | ARS | 56 | INV | 424 | N | I | CFC | 139.7 | 139.7 | 0 |  | 2008-11-01 | 2011-03-01 | 2013-11-01 | 2015-12-01 | 2015-12-01 | 2016-07-01 | 2000000 | -59486 | 1940514 | 1940514 | 100% | 0 | 0 | 0 | 230000 | -6544 | 223159 | 297 | 0 | Activities completed in 2015 and unspent balance will be returned in 2016. | Unspent balances have been returned to the MLF in July 2016 and this has also been reported to the 77th meeting. |  | 2013-11-01
FIN | UNEP | National strategy for transition to non-CFC MDIs | Individual | ASP | IND | ARS | 56 | TAS | 425 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-08-01 | 2013-11-01 |  | 2014-12-01 | 2016-12-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 | 0 |  | 15600 | 0 | 15600 | 0 | 0 | Project financially completed | Project financially completed
FIN | IBRD | Verification of production of CFCs for essential use | Individual | ASP | IND | ARS | 62 | TAS | 438 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-11-01 | 2011-05-31 |  | 2011-08-01 | 2011-11-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 4500 | 0 | 4500 | 0 | 0 | Independent audit submitted to the 65th ExCom in Nov 11. Report shows that CFC producers produced less CFCs than approved by the Parties for essential use, and that these pharma grade CFCs were sold to 2 MDI manufacturers authorized by GoI to produce MDIs according to EUN Process. |  |  |  | Non-INV | 0
FIN | UNDP | Preparation of a project for demonstration of a sustainable technological, financial and management model for disposal of ODS | Individual | ASP | IND | DES | 61 | PRP | 437 | N | I | ODS-Waste | 0 | 0 | 0 | 0 | 2010-07-01 |  | 2011-07-01 |  | 2013-12-01 | 2014-07-01 | 80000 | -80000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 6000 | -6000 | 0 | 0 | 0 | Financially completed in 2014. | Completed in 2013. Funds to be returned to MFS in 72 Excom. | 2010 |  | Investment
FIN | IBRD | Application development for the conversion of CFC-11/polyol systems to low non-ODS formulations at UB Petroproducts Ltd. | Individual | ASP | IND | FOA | 11 | INV | 13 | N | I | CFC | 0 | 0 | 0 | 0 | 1993-11-01 | 1999-02-01 | 1996-11-01 |  | 1999-08-01 | 2000-08-01 | 200000 | 291817 | 491817 | 491817.37 | 100% | -0.37 | -0.37 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted |  |  | 1999-03-01 | INV | 0
FIN | IBRD | Application development for the conversion of CFC-11/polyol systems to low non-ODS formulations at Manali Petrochemical Ltd. | Individual | ASP | IND | FOA | 11 | INV | 14 | N | I | CFC | 0 | 0 | 0 | 0 | 1993-11-01 | 1997-02-01 | 1996-11-01 |  | 1998-01-01 | 2000-08-01 | 219000 | 211348 | 430348 | 430347.63 | 100% | 0.37 | 0.37 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted |  |  | 1999-03-01 | INV | 0
FIN | UNDP | Phase-out of the use of CFC in the manufacture of extruded polyethylene foam sheet at Camphor and Allied Products Ltd. | Individual | ASP | IND | FOA | 12 | INV | 16 | A | R | CFC | 120 | 120 | 0 | 0 | 1994-03-01 | 1995-12-01 | 1994-09-01 |  | 1995-12-01 | 1997-12-01 | 280000 | 0 | 280000 | 280000 | 100% | 0 | 0 | 0 | 36400 | 0 | 36400 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Investment
FIN | UNDP | Phase-out of the use of CFC in the manufacture of rigid PUF panels at Sunpra Ltd. | Individual | ASP | IND | FOA | 12 | INV | 17 | A | I | CFC | 20 | 20 | 0 | 0 | 1994-03-01 | 1996-04-01 | 1995-03-01 |  | 1996-06-01 | 1998-12-01 | 414000 | -43773 | 370227 | 370227 | 100% | 0 | 0 | 0 | 53820 | -5690 | 48130 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Phase-out of the use of CFC in the manufacture of rigid PUF for thermoware at Eagle Flasks Industries Ltd. | Individual | ASP | IND | FOA | 12 | INV | 18 | A | I | CFC | 20 | 20 | 0 | 0 | 1994-03-01 | 1996-05-01 | 1995-03-01 |  | 1996-09-01 | 2000-12-01 | 365000 | -3745.35 | 361254.65 | 361255 | 100% | -0.35 | 0 | 0 | 47450 | -486.9 | 46963.15 | -0.05 | 0 | Completed in 1996. Financially completed in 2000. |  | 1994 |  | Investment
FIN | IBRD | Replacement of CFC-11 as blowing agent in polyurethane foam systems with low and non-ODS materials at Expanded Incorporation | Individual | ASP | IND | FOA | 13 | INV | 23 | N | I | CFC | 72 | 72 | 0 | 0 | 1994-07-01 | 1997-04-01 | 1998-07-01 |  | 2000-09-01 | 2000-09-01 | 502130 | -8064 | 494066 | 494066 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted |  |  | 1999-03-01 | INV | 0
FIN | UNDP | Phase out of CFC-11 in the manufacture of phenolic foam at Bakelite Hylam Ltd. | Individual | ASP | IND | FOA | 13 | INV | 27 | A | I | CFC | 58 | 58 | 0 | 0 | 1994-07-01 | 1996-03-01 | 1995-07-01 |  | 1998-11-01 | 1999-12-01 | 367000 | 0 | 367000 | 367000 | 100% | 0 | 0 | 0 | 47710 | 0 | 47710 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1994 |  | Investment
FIN | UNDP | Phase out of CFC-11 in the manufacture of polyurethane foam at U-Foam Private Ltd. | Individual | ASP | IND | FOA | 13 | INV | 30 | A | I | CFC | 35 | 35 | 0 | 0 | 1994-07-01 | 1996-07-01 | 1995-07-01 |  | 1997-11-01 | 2000-12-01 | 328500 | -77822 | 250678 | 250678 | 100% | 0 | 0 | 0 | 42705 | -10116.86 | 32588.14 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Strategy and action programme for the elimination of CFC in the manufacture of foams | Individual | ASP | IND | FOA | 13 | TAS | 29 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 | 1998-07-01 | 1995-07-01 |  | 1999-12-01 | 2003-05-01 | 200000 | -1396 | 198604 | 198604 | 100% | 0 | 0 | 0 | 26000 | -181.48 | 25818.52 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  | 1994 | 1999-12-01 | Non-Investment
FIN | IBRD | Phase out of CFC-11 in the manufacture of flexible slabstock PUF at Duroflex Coir Industries P. Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 34 | N | I | CFC | 10 | 10 | 0 | 0 | 1995-07-01 | 1996-04-01 | 1997-01-01 |  | 1997-08-01 | 1998-03-01 | 100800 | -7422 | 93378 | 93378 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. |  |  | 1997-03-01 | INV | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of rigid PUF at Industrial Foams Pvt. Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 35 | N | I | CFC | 35 | 35 | 0 | 0 | 1995-07-01 | 1996-05-01 | 1997-01-01 |  | 1997-08-01 | 1997-06-01 | 320000 | -9500 | 310500 | 310500 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. |  |  | 1997-03-01 | INV | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of rigid PUF thermoware at Ishwar Arts (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 36 | N | I | CFC | 8 | 8 | 0 | 0 | 1995-07-01 | 1996-11-01 | 1997-01-01 |  | 1998-10-01 | 2000-08-01 | 120950 | -29077 | 91873 | 91873 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. |  |  | 1997-05-01 | INV | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of rigid PUF thermoware at Ishwar Ashish Plastics P. Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 37 | N | I | CFC | 8 | 8 | 0 | 0 | 1995-07-01 | 1996-11-01 | 1997-01-01 |  | 1998-10-01 | 2000-08-01 | 120950 | -29077 | 91873 | 91873 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. |  |  | 1997-04-01 | INV | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of flexible polyurtehane foams at Karnataka Consumer Products Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 38 | N | I | CFC | 27 | 27 | 0 | 0 | 1995-07-01 | 1999-06-01 | 1997-01-01 |  | 2000-03-01 | 2001-07-01 | 253200 | -103341 | 149859 | 149859 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. |  |  | 1999-09-01 | INV | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of moulded PUF at Madras Polymoulds (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 39 | N | I | CFC | 10 | 10 | 0 | 0 | 1995-07-01 | 1997-10-01 | 1997-01-01 |  | 1998-10-01 | 2000-07-01 | 167700 | -57255 | 110445 | 110445 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. |  |  | 1999-01-01 | INV | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of rigid PUF thermoware at Milton Plastics Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 40 | N | I | CFC | 30 | 30 | 0 | 0 | 1995-07-01 | 1996-11-01 | 1997-01-01 |  | 1998-10-01 | 2000-07-01 | 456500 | -81683 | 374817 | 374817 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. |  |  | 1997-04-01 | INV | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of rigid PUF thermoware at Milton Polyplas (India) Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 41 | N | I | CFC | 15 | 15 | 0 | 0 | 1995-07-01 | 1996-11-01 | 1997-01-01 |  | 1998-10-01 | 2000-07-01 | 236000 | -52332 | 183668 | 183668 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. |  |  | 1997-04-01 | INV | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of rigid PUF thermoware at Panorama Plastics (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 42 | N | I | CFC | 8 | 8 | 0 | 0 | 1995-07-01 | 1996-11-01 | 1997-01-01 |  | 1998-10-01 | 2000-08-01 | 120950 | -29077 | 91873 | 91873 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. |  |  | 1997-04-01 | INV | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of PUF sandwich panels at Polynate Foams Pvt. Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 43 | N | I | CFC | 20 | 20 | 0 | 0 | 1995-07-01 | 1997-11-01 | 1997-01-01 |  | 2000-02-01 | 2001-10-01 | 278000 | -1057 | 276943 | 276943 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted |  |  | 1999-02-01 | INV | 0
CLO | IBRD | Phase out of CFC-11 in the manufacture of PUF sandwich panels at Sree Precoated Steels Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 44 | N | I |  | 0 | 0 | 0 | 0 | 1995-07-01 |  | 1997-01-01 |  |  | 1999-11-01 | 224000 | -224000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Cancelled |  |  | 1998-01-01 | INV | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of rigid PUF thermoware at Vikram Plastics (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 45 | N | I | CFC | 15 | 15 | 0 | 0 | 1995-07-01 | 1996-11-01 | 1997-01-01 |  | 1998-10-01 | 2000-08-01 | 236000 | -52312 | 183688 | 183688 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted. |  |  | 1997-04-01 | INV | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of molded PUF at Tranquil Rubber Sales Pvt. Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 46 | N | I | CFC | 17 | 17 | 0 | 0 | 1995-07-01 | 1996-05-01 | 1997-01-01 |  | 1998-04-01 | 2000-07-01 | 215250 | -79521 | 135729 | 135729 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted. |  |  | 1997-07-01 | INV | 0
FIN | IBRD | Phase-out of CFCs in the manufacture of extruded polyethylene foam at Real Polymers | Individual | ASP | IND | FOA | 17 | INV | 47 | N | I | CFC | 35 | 35 | 0 | 0 | 1995-07-01 | 1996-12-01 | 1997-01-01 |  | 1998-09-01 | 1998-07-01 | 276200 | -51275 | 224925 | 224925 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted. |  |  | 1997-06-01 | INV | 0
FIN | IBRD | Phase out of CFCs in the manufacture of PUF moldings at Vijayjyot Seats Ltd. | Individual | ASP | IND | FOA | 17 | INV | 48 | N | I | CFC | 49 | 49 | 0 | 0 | 1995-07-01 | 1997-07-01 | 1997-01-01 |  | 1998-09-01 | 1999-12-01 | 335500 | -25979 | 309521 | 309521 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. |  |  | 1997-12-01 | INV | 0
FIN | IBRD | Phase out of CFCs in the manufacture of molded PUF automotive seats at Polyflex (India) P. Ltd. | Individual | ASP | IND | FOA | 17 | INV | 49 | N | I | CFC | 40 | 40 | 0 | 0 | 1995-07-01 | 1998-03-01 | 1997-01-01 |  | 1998-09-01 | 2002-01-01 | 222400 | -6000 | 216400 | 216400 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. |  |  | 1997-06-01 | INV | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of molded PUF at Alfa Foams (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 51 | N | I | CFC | 19 | 19 | 0 | 0 | 1995-07-01 | 1997-07-01 | 1997-01-01 |  | 1997-10-01 | 2000-11-01 | 219900 | -27875 | 192025 | 192025.49 | 100% | -0.49 | -0.49 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted. |  |  | 1997-12-01 | INV | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of PUF sandwich panels at Blue Star Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 52 | N | I | CFC | 13 | 13 | 0 | 0 | 1995-07-01 | 1997-05-01 | 1997-01-01 |  | 1998-06-01 | 2000-12-01 | 224000 | -55898 | 168102 | 168102 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted. |  |  | 1997-06-01 | INV | 0
FIN | IBRD | Phase out of CFCs in the manufacture of integral skin PUF moldings at Pfeda Synthetics (P) Ltd. | Individual | ASP | IND | FOA | 18 | INV | 54 | N | I | CFC | 30 | 30 | 0 | 0 | 1995-11-01 | 1997-02-01 | 1997-05-01 |  | 1998-04-01 | 1999-09-01 | 335728 | -14893 | 320835 | 320834.93 | 100% | 0.07 | 0.07 |  | 43644.64 | -1936.09 | 41708.55 | 0 | 0 | Complete. |  |  | 1997-09-01 | INV | 0
FIN | IBRD | Phase out of CFCs in the manufacture of molded PUF at Bharat Seats Ltd. | Individual | ASP | IND | FOA | 18 | INV | 55 | N | R | CFC | 55 | 55 | 0 | 0 | 1995-11-01 | 1996-12-01 | 1996-03-01 |  | 1993-07-01 | 1996-12-01 | 514563 | -563 | 514000 | 514000 | 100% | 0 | 0 |  | 66893.19 | -73.19 | 66820 | 0 | 0 | Complete. |  |  | 1993-07-01 | INV | 0
FIN | IBRD | Phase out of CFCs in the manufacture of molded PUF at PUR Polyurethane Products P. Ltd. | Individual | ASP | IND | FOA | 18 | INV | 56 | N | I | CFC | 17 | 17 | 0 | 0 | 1995-11-01 | 1997-12-01 | 1997-05-01 |  | 2002-03-01 | 2005-01-01 | 187864 | -41523 | 146341 | 146341 | 100% | 0 | 0 |  | 24422.32 | -5397.99 | 19024.33 | 0 | 0 | Project financially completed and balance funds returned. PCR submitted to ExCom. |  |  | 2000-12-01 | INV | 0
CLO | IBRD | Phase out of CFCs in the manufacture of extruded polyethylene foam at Kunstoff Polymers Ltd. | Individual | ASP | IND | FOA | 18 | INV | 57 | N | I |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1997-05-01 |  |  | 1997-02-01 | 239320 | -239320 | 0 | 0 | #DIV/0! | 0 | 0 |  | 31111.6 | -31111.6 | 0 | 0 | 0 | Cancelled |  |  | 1997-09-01 | INV | 0
FIN | IBRD | Phase-out of CFCs in the manufacture of extruded polyethylene foam at Shroff Textiles Ltd. | Individual | ASP | IND | FOA | 18 | INV | 58 | N | I | CFC | 25 | 25 | 0 | 0 | 1995-11-01 | 1998-05-01 | 1997-05-01 |  | 2000-06-01 | 2001-01-01 | 197200 | 0 | 197200 | 197200 | 100% | 0 | 0 |  | 25636 | 0 | 25636 | 0 | 0 | Project completed and PCR submitted |  |  | 1999-03-01 | INV | 0
FIN | IBRD | Phase out of CFCs in the manufacture of rigid PUF products at SDC Polyurethane Products Ltd. | Individual | ASP | IND | FOA | 18 | INV | 59 | N | I | CFC | 24 | 24 | 0 | 0 | 1995-11-01 | 1998-03-01 | 1997-05-01 |  | 1998-06-01 | 2000-07-01 | 160971 | 0 | 160971 | 160970.73 | 100% | 0.27 | 0.27 |  | 20926.23 | 0 | 20926.19 | 0.04 | 0.04 | Project completed and PCR submitted. |  |  | 1997-06-01 | INV | 0
CLO | UNDP | Phase out of CFCs in the manufacture of cold cured molded PUF products at Autofit P., Ltd. | Individual | ASP | IND | FOA | 19 | INV | 70 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1997-11-01 |  |  | 1998-07-01 | 103125 | -103125 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 13406.25 | -13406.25 | 0 | 0 | 0 | Canceled in 1998. Financially Completed in 1998. |  | 1996 |  | Investment
FIN | UNDP | Phase out of CFCs in the manufacture of rigid PUF insulated thermoware at Bharat Plastic Products | Individual | ASP | IND | FOA | 19 | INV | 71 | A | I | CFC | 25 | 25 | 0 | 0 | 1996-05-01 | 1997-03-01 | 1997-11-01 |  | 2000-12-01 | 2002-03-01 | 96000 | -889 | 95111 | 95111 | 100% | 0 | 0 | 0 | 12480 | -115.57 | 12364.43 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1996 | 1999-06-01 | Investment
FIN | UNDP | Phase out of CFCs in the manufacture of rigid PUF products in Inalsa Ltd. | Individual | ASP | IND | FOA | 19 | INV | 72 | A | I | CFC | 28.9 | 28.9 | 0 | 0 | 1996-05-01 | 1997-09-01 | 1997-11-01 |  | 1998-09-01 | 2000-12-01 | 123000 | -4222 | 118778 | 118778 | 100% | 0 | 0 | 0 | 15990 | -548.86 | 15441.14 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Phase out of CFCs in the manufacture of rigid PUF products at Omkar PUF Insulation | Individual | ASP | IND | FOA | 19 | INV | 73 | A | I | CFC | 10.6 | 10.6 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1997-06-01 | 2000-12-01 | 59000 | -151.48 | 58848.52 | 58849 | 100% | -0.48 | 0 | 0 | 7670 | -19.69 | 7650.37 | -0.06 | 0 | Completed in 1997. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Phase out of CFCs in the manufacture of cold cured molded and integral skin PUF products at Kaygee Foams P., Ltd. | Individual | ASP | IND | FOA | 19 | INV | 74 | A | I | CFC | 33 | 33 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1997-06-01 | 2000-12-01 | 217250 | -1198 | 216052 | 216052 | 100% | 0 | 0 | 0 | 28242.5 | -155.74 | 28086.76 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Phase out of CFCs in the manufacture of rigid PUF insulated thermoware at Mahavir Enterprises | Individual | ASP | IND | FOA | 19 | INV | 75 | A | I | CFC | 19.4 | 19.4 | 0 | 0 | 1996-05-01 | 1997-04-01 | 1997-11-01 |  | 2000-08-01 | 2001-12-01 | 94500 | -220 | 94280 | 94280 | 100% | 0 | 0 | 0 | 12285 | -28.61 | 12256.3924 | -0.0024 | 0 | Completed in 2000. Financially completed in 2001. |  | 1996 | 1999-07-01 | Investment
FIN | UNDP | Phase out of the CFCs in the manufacture of cold cured molded and integral skin PUF products at Preto Foams | Individual | ASP | IND | FOA | 19 | INV | 76 | A | I | CFC | 11.4 | 11.4 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1997-11-01 | 2000-12-01 | 167100 | -17268 | 149832 | 149832 | 100% | 0 | 0 | 0 | 21723 | -2244.84 | 19478.16 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1996 |  | Investment
FIN | IBRD | Phase-out of CFCs in the manufacture of molded PUF automotive seat cushions at Roloforms Polymer Ltd. | Individual | ASP | IND | FOA | 19 | INV | 77 | N | I | CFC | 26 | 26 | 0 | 0 | 1996-05-01 | 1998-03-01 | 1997-11-01 |  | 1999-06-01 | 2000-03-01 | 162400 | -38657 | 123743 | 123743 | 100% | 0 | 0 |  | 21112 | -5025.41 | 16086.59 | 0 | 0 | Project completed and PCR submitted. |  |  | 1999-06-01 | INV | 0
FIN | UNDP | Phase-out of CFCs in the manufacture of rigid PUF insulated thermoware at Asha Handicrafts (formerly Asian Advertisers) | Individual | ASP | IND | FOA | 19 | INV | 78 | A | I | CFC | 19.4 | 19.4 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  | 1997-06-01 | 2000-12-01 | 122500 | -6656 | 115844 | 115844 | 100% | 0 | 0 | 0 | 15925 | -865.28 | 15059.72 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Phase-out of CFCs in the manufacture of cold cured and integral skin PUF moldings at Amit Polyseats Ltd. | Individual | ASP | IND | FOA | 19 | INV | 79 | A | I | CFC | 19.3 | 19.3 | 0 | 0 | 1996-05-01 | 1996-10-01 | 1997-11-01 |  | 1997-06-01 | 2000-07-01 | 243000 | -28744 | 214256 | 214256 | 100% | 0 | 0 | 0 | 31590 | -3736.72 | 27853.28 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Phase-out of CFCs in the manufacture of rigid PUF spray insulation at Beardsell Ltd. | Individual | ASP | IND | FOA | 19 | INV | 80 | A | I | CFC | 21.2 | 21.2 | 0 | 0 | 1996-05-01 | 2000-05-01 | 1997-11-01 |  | 2000-11-01 | 2002-03-01 | 129000 | -19305 | 109695 | 109695 | 100% | 0 | 0 | 0 | 16770 | -2509.65 | 14260.35 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1996 | 1999-12-01 | Investment
FIN | UNDP | Phase-out of CFCs in the manufacture of rigid PUF products at Lloyd Insulations and Polyproducts | Individual | ASP | IND | FOA | 19 | INV | 81 | A | I | CFC | 76.7 | 76.7 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1997-09-01 | 2000-12-01 | 500000 | -35882.96 | 464117.04 | 464117 | 100% | 0.04 | 0 | 0 | 65000 | -4664.78 | 60335.21 | 0.01 | 0 | Completed in 1997. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Phase-out of CFCs in the manufacture of cold cured PUF moldings at Meenakshi Polymers Pvt. Ltd. | Individual | ASP | IND | FOA | 19 | INV | 82 | A | I | CFC | 15 | 15 | 0 | 0 | 1996-05-01 | 1996-11-01 | 1997-11-01 |  | 1997-06-01 | 2000-12-01 | 214000 | -38836 | 175164 | 175164 | 100% | 0 | 0 | 0 | 27820 | -5048.68 | 22771.32 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Phase-out of CFCs in the manufacture of cold cured PUF moldings at Punjab Scooters Ltd. | Individual | ASP | IND | FOA | 19 | INV | 83 | A | I | CFC | 39 | 39 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1998-12-01 | 2000-12-01 | 312200 | -23972 | 288228 | 288228 | 100% | 0 | 0 | 0 | 40586 | -3116.36 | 37469.64 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1996 |  | Investment
FIN | IBRD | Phase-out of CFC-11 in the manufacture of rigid PUF products at Polyproducts | Individual | ASP | IND | FOA | 19 | INV | 84 | N | I | CFC | 18.5 | 18.5 | 0 | 0 | 1996-05-01 | 1997-09-01 | 1997-11-01 |  | 1998-09-01 | 2001-03-01 | 140190 | -26 | 140164 | 140164 | 100% | 0 | 0 |  | 18224.7 | -3.38 | 18221.32 | 0 | 0 | Project completed and PCR submitted. |  |  | 1998-01-01 | INV | 0
CLO | IBRD | Phase-out of CFC-11 in the manufacture of rigid PUF for insulated thermoware at Arihant Thermoware Ltd. | Individual | ASP | IND | FOA | 19 | INV | 85 | N | I |  | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1997-11-01 |  |  | 1998-07-01 | 146450 | -146450 | 0 | 0 | #DIV/0! | 0 | 0 |  | 19038.5 | -19038.5 | 0 | 0 | 0 | Cancelled. |  |  | 1998-01-01 | INV | 0
FIN | IBRD | Phase-out of CFC-11 in the manufacture of rigid PUF insulated thermoware at Cello Plast | Individual | ASP | IND | FOA | 19 | INV | 86 | N | I | CFC | 21 | 21 | 0 | 0 | 1996-05-01 | 1998-02-01 | 1997-11-01 |  | 1999-06-01 | 2000-09-01 | 141320 | -546 | 140774 | 140773.84 | 100% | 0.16 | 0.16 |  | 18372 | -70.98 | 18301.02 | 0 | 0 | Project completed and PCR submitted |  |  | 1998-01-01 | INV | 0
FIN | IBRD | Phase-out of CFC-11 in the manufacture of rigid PUF insulated thermoware at Cello Thermoware Ltd. | Individual | ASP | IND | FOA | 19 | INV | 87 | N | I | CFC | 17.4 | 17.4 | 0 | 0 | 1996-05-01 | 1998-02-01 | 1997-11-01 |  | 1999-06-01 | 2000-09-01 | 129420 | 0 | 129420 | 129420 | 100% | 0 | 0 |  | 16824.6 | 0 | 16824.6 | 0 | 0 | Project completed and PCR submitted |  |  | 1998-01-01 | INV | 0
FIN | IBRD | Phase-out of CFC-11 in the manufacture of rigid PUF insulated thermoware at Wimco Pen Co. | Individual | ASP | IND | FOA | 19 | INV | 88 | N | I | CFC | 18.5 | 18.5 | 0 | 0 | 1996-05-01 | 1998-03-01 | 1997-11-01 |  | 1999-06-01 | 2000-09-01 | 119290 | -4225 | 115065 | 115065 | 100% | 0 | 0 |  | 15507.7 | -549.25 | 14958.45 | 0 | 0 | Project completed and PCR submitted |  |  | 1999-03-01 | INV | 0
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF products at Deccan Engineering Enterprises | Individual | ASP | IND | FOA | 20 | INV | 100 | A | I | CFC | 8.3 | 8.3 | 0 | 0 | 1996-10-01 | 1997-09-01 | 1998-09-01 |  | 1998-11-01 | 2000-12-01 | 64000 | -3303 | 60697 | 60697 | 100% | 0 | 0 | 0 | 8320 | -429.39 | 7890.61 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of EPE foam products at Vora Cork Industries | Individual | ASP | IND | FOA | 20 | INV | 101 | A | I | CFC | 39.6 | 39.6 | 0 | 0 | 1996-10-01 | 1998-12-01 | 1998-09-01 |  | 2003-07-01 | 2005-09-01 | 264500 | -52153 | 212347 | 212347 | 100% | 0 | 0 | 0 | 34385 | -6780 | 27605 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 1996 | 1999-09-01 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF products at Best Plastronics P. Ltd. | Individual | ASP | IND | FOA | 20 | INV | 102 | A | I | CFC | 19.5 | 19.5 | 0 | 0 | 1996-10-01 | 1998-11-01 | 1998-09-01 |  | 1999-08-01 | 2001-12-01 | 129000 | -35002 | 93998 | 93998 | 100% | 0 | 0 | 0 | 16770 | -4550 | 12220 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1996 | 1999-09-01 | Investment
FIN | UNDP | Phase-out of CFCs in the manufacture of cold cured molded PUF products at Krishna Fabrications Ltd. | Individual | ASP | IND | FOA | 20 | INV | 103 | A | I | CFC | 13 | 13 | 0 | 0 | 1996-10-01 | 1997-09-01 | 1998-09-01 |  | 1998-08-01 | 2000-12-01 | 164000 | -21543 | 142457 | 142457 | 100% | 0 | 0 | 0 | 21320 | -2800.59 | 18519.41 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1996 |  | Investment
FIN | IBRD | Conversion of domestic refrigerator manufacture to cyclopentane blowing agent at Godrej - GE Appliances Ltd. (GGEAL) | Individual | ASP | IND | FOA | 20 | INV | 104 | N | I | CFC | 568 | 568 | 0 | 0 | 1996-10-01 | 1999-01-01 | 1999-02-01 |  | 1999-07-01 | 2003-10-01 | 2691570 | -27265 | 2664305 | 2664305 | 100% | 0 | 0 |  | 349904.1 | -3544.45 | 346359.55 | 0.1 | 0.1 | Project completed. |  |  | 2000-06-01 | INV | 0
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF insulated thermoware at Amar Enterprises | Individual | ASP | IND | FOA | 20 | INV | 96 | A | I | CFC | 16.2 | 16.2 | 0 | 0 | 1996-10-01 | 1997-11-01 | 1998-09-01 |  | 1999-08-01 | 2001-12-01 | 120000 | -57 | 119943 | 119943 | 100% | 0 | 0 | 0 | 15600 | -7.41 | 15592.5896 | 0.0004 | 0 | Completed in 1999. Financially completed in 2001. |  | 1996 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF insulated thermoware at Bharat Plast | Individual | ASP | IND | FOA | 20 | INV | 97 | A | I | CFC | 10.6 | 10.6 | 0 | 0 | 1996-10-01 | 1997-12-01 | 1998-09-01 |  | 1998-08-01 | 2000-12-01 | 71000 | -104 | 70896 | 70896 | 100% | 0 | 0 | 0 | 9230 | -13.52 | 9216.48 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF insulated thermoware at Bharat Cottage Industries | Individual | ASP | IND | FOA | 20 | INV | 98 | A | I | CFC | 7.8 | 7.8 | 0 | 0 | 1996-10-01 | 1997-09-01 | 1998-09-01 |  | 1998-08-01 | 2000-12-01 | 61000 | -2047 | 58953 | 58953 | 100% | 0 | 0 | 0 | 7930 | -266.11 | 7663.89 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Phase-out of CFCs in the manufacture of cold cured molded PUF products at K.B. Poly Industries P. Ltd. | Individual | ASP | IND | FOA | 20 | INV | 99 | A | I | CFC | 10 | 10 | 0 | 0 | 1996-10-01 | 1997-12-01 | 1998-09-01 |  | 1999-08-01 | 2001-12-01 | 149000 | -19595 | 129405 | 129405 | 100% | 0 | 0 | 0 | 19370 | -2547 | 16823 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1996 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid polyurethane foam chemical systems at Polymermann (Asia) P.Ltd. | Individual | ASP | IND | FOA | 22 | INV | 111 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-05-01 |  | 2001-12-01 | 2003-11-01 | 385000 | -4930 | 380070 | 380070 | 100% | 0 | 0 | 0 | 50050 | -640.9 | 49409.1 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1997 | 1999-07-01 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PU foam insulation at Blowkings | Individual | ASP | IND | FOA | 22 | INV | 128 | A | I | CFC | 17.6 | 17.6 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1998-12-01 | 2000-12-01 | 132000 | -14394 | 117606 | 117606 | 100% | 0 | 0 | 0 | 17160 | -1871.22 | 15288.78 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PU foam insulation at Delta Foams Engineering Co. | Individual | ASP | IND | FOA | 22 | INV | 130 | A | I | CFC | 12 | 12 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1999-08-01 | 2001-12-01 | 85000 | -15226 | 69774 | 69774 | 100% | 0 | 0 | 0 | 11050 | -1979.13 | 9070.87 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PU foam insulation at Super Urethane Products P. Ltd. | Individual | ASP | IND | FOA | 22 | INV | 132 | A | I | CFC | 39.1 | 39.1 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1999-12-01 | 2001-12-01 | 284000 | -36531.9 | 247468.1 | 247468 | 100% | 0.1 | 0 | 0 | 36920 | -4748.86 | 32171.13 | 0.01 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid polyurethane foam in small and medium-sized enterprises (SMEs) | Individual | ASP | IND | FOA | 22 | INV | 133 | A | I | CFC | 290 | 290 | 0 | 0 | 1997-05-01 | 1997-12-01 | 2000-06-01 |  | 2001-12-01 | 2003-03-01 | 1404000 | -79 | 1403921 | 1403921 | 100% | 0 | 0 | 0 | 182520 | -10 | 182510 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1997 | 2000-06-01 | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF insulated thermoware at Nissan Thermoware P. Ltd. | Individual | ASP | IND | FOA | 23 | INV | 143 | A | I | CFC | 15.4 | 15.4 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 2000-08-01 | 2004-01-01 | 111000 | -706 | 110294 | 110294 | 100% | 0 | 0 | 0 | 14430 | -91.85 | 14338.1524 | -0.0024 | 0 | Completed in 2000. Financially completed in 2004. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid polyurethane foam insulation products at Viral Corporation | Individual | ASP | IND | FOA | 23 | INV | 146 | A | I | CFC | 11.8 | 11.8 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 2000-08-01 | 2001-12-01 | 84000 | -2736 | 81264 | 81264 | 100% | 0 | 0 | 0 | 10920 | -356 | 10564 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of flexible moulded cold-cured and integral skin PU foam at Venus Auto P. Ltd. | Individual | ASP | IND | FOA | 23 | INV | 147 | A | I | CFC | 21 | 21 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-11-01 | 2001-12-01 | 137250 | -1155 | 136095 | 136095 | 100% | 0 | 0 | 0 | 17842.5 | -150.3 | 17692.2034 | -0.0034 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of flexible cold-cured moulded PU foam at Siddhi Polymer P. Ltd. | Individual | ASP | IND | FOA | 23 | INV | 148 | A | I | CFC | 7.5 | 7.5 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 1999-12-01 | 2001-12-01 | 75250 | -737 | 74513 | 74513 | 100% | 0 | 0 | 0 | 9782.5 | -95.92 | 9686.581 | -0.001 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Phase-out of CFCs in the manufacture of cold cured moulded and integral skin at Shri Krishna Polyurethane Industries P. Ltd. | Individual | ASP | IND | FOA | 23 | INV | 149 | A | I | CFC | 19.1 | 19.1 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 1999-08-01 | 2002-11-01 | 192875 | -486 | 192389 | 192389 | 100% | 0 | 0 | 0 | 25073.75 | -63 | 25010.75 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid polyurethane foam insulation products at Reliable Rotomoulders P. Ltd. | Individual | ASP | IND | FOA | 23 | INV | 150 | A | I | CFC | 8.7 | 8.7 | 0 | 0 | 1997-11-01 | 1998-08-01 | 1999-12-01 |  | 1999-11-01 | 2001-12-01 | 63000 | -769 | 62231 | 62231 | 100% | 0 | 0 | 0 | 8190 | -100.11 | 8089.8879 | 0.0021 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid polyurethane foam insulation products at Panna International | Individual | ASP | IND | FOA | 23 | INV | 151 | A | I | CFC | 9.7 | 9.7 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 1998-12-01 | 2000-12-01 | 48000 | -19370 | 28630 | 28630 | 100% | 0 | 0 | 0 | 6240 | -2518.1 | 3721.9 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid polyurethane foam insulation products at Malanpur Entech P. Ltd. | Individual | ASP | IND | FOA | 23 | INV | 153 | A | I | CFC | 18.9 | 18.9 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 1999-12-01 | 2001-12-01 | 148000 | -12388 | 135612 | 135612 | 100% | 0 | 0 | 0 | 19240 | -1610 | 17630 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Phase-out of CFCs in the manufacture of integral skin PUF products at Legend Interiors | Individual | ASP | IND | FOA | 23 | INV | 154 | A | I | CFC | 9 | 9 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-12-01 | 2001-12-01 | 124000 | -14125 | 109875 | 109875 | 100% | 0 | 0 | 0 | 16120 | -1836 | 14284 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of flexible cold-cured moulded PU foam at K. J. Polymers P. Ltd. | Individual | ASP | IND | FOA | 23 | INV | 155 | A | I | CFC | 30 | 30 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 1999-12-01 | 2001-12-01 | 127550 | -353 | 127197 | 127197 | 100% | 0 | 0 | 0 | 16581.5 | -45.9 | 16535.5953 | 0.0047 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF insulated thermoware at Bluplast Corporation | Individual | ASP | IND | FOA | 23 | INV | 156 | A | I | CFC | 10.1 | 10.1 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 2000-06-01 | 2001-12-01 | 76000 | 0 | 76000 | 76000 | 100% | 0 | 0 | 0 | 9880 | 0 | 9880 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF insulated thermoware at Alaska Industries | Individual | ASP | IND | FOA | 23 | INV | 157 | A | I | CFC | 17.6 | 17.6 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-12-01 | 2001-12-01 | 128000 | -18370 | 109630 | 109630 | 100% | 0 | 0 | 0 | 16640 | -2388 | 14252 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid polyurethane foam at Ras Polybuild Products P. Ltd. | Individual | ASP | IND | FOA | 23 | INV | 158 | A | I | CFC | 17.7 | 17.7 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-11-01 | 2001-12-01 | 128000 | -136 | 127864 | 127864 | 100% | 0 | 0 | 0 | 16640 | -17.68 | 16622.3178 | 0.0022 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Project preparation to prepare 10 projects in the foam sector | Individual | ASP | IND | FOA | 24 | PRP | 164 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Elimination of CFCs with HCFC-141b and partial water based systems in the manufacture of rigid polyurethane foam at Puff Insulators | Individual | ASP | IND | FOA | 26 | INV | 184 | A | I | CFC | 10.6 | 10.6 | 0 | 0 | 1998-11-01 | 2000-02-01 | 2000-12-01 |  | 2000-11-01 | 2002-03-01 | 83150 | 0 | 83150 | 83150 | 100% | 0 | 0 | 0 | 10809.5 | 0 | 10809.5 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam and integral skin foam products to water blown systems in flexible molded polyurethane foam at Joti Foam Pr | Individual | ASP | IND | FOA | 26 | INV | 185 | A | I | CFC | 37.5 | 37.5 | 0 | 0 | 1998-11-01 | 2000-03-01 | 2000-12-01 |  | 2000-12-01 | 2002-03-01 | 174290 | -287 | 174003 | 174003 | 100% | 0 | 0 | 0 | 22657.7 | -37.31 | 22620.39 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Elimination of CFCs with HCFC-141b (and partial water) based systems, in the manufacture of rigid polyurethane foam insulated termoware at Jaypee Technoplast P. Ltd. | Individual | ASP | IND | FOA | 26 | INV | 186 | A | I | CFC | 18.5 | 18.5 | 0 | 0 | 1998-11-01 | 2000-04-01 | 2000-12-01 |  | 2000-10-01 | 2001-12-01 | 139860 | -966 | 138894 | 138894 | 100% | 0 | 0 | 0 | 18181.8 | -125.68 | 18056.1195 | 0.0005 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Elimination of CFCs with HCFC-141b (and partial water) based systems, in the manufacture of rigid polyurethane foam insulation products at Sintex Industries Ltd. | Individual | ASP | IND | FOA | 26 | INV | 187 | A | D | CFC | 10.9 | 10.9 | 0 | 0 | 1998-11-01 | 2000-12-01 | 2000-12-01 |  | 2001-11-01 | 2003-04-01 | 62980 | -1589 | 61391 | 61391 | 100% | 0 | 0 | 0 | 8187.4 | -206.57 | 7980.83 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Elimination of CFCs with HCFC-141b (and partial water) based systems, in the manufacture of rigid polyurethane foam insulated thermoware at National Flask Industries Ltd. | Individual | ASP | IND | FOA | 26 | INV | 188 | A | I | CFC | 36.9 | 36.9 | 0 | 0 | 1998-11-01 | 2000-02-01 | 2000-12-01 |  | 2000-08-01 | 2002-03-01 | 203870 | -16186 | 187684 | 187684 | 100% | 0 | 0 | 0 | 26503.1 | -2104.18 | 24398.92 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Elimination of CFCs with HCFC-141b (and partial water) based systems, in the manufacture of rigid polyurethane foam insulated thermoware at Jayson Industries | Individual | ASP | IND | FOA | 26 | INV | 189 | A | I | CFC | 12.9 | 12.9 | 0 | 0 | 1998-11-01 | 2000-02-01 | 2000-12-01 |  | 2000-10-01 | 2001-12-01 | 88900 | -840 | 88060 | 88060 | 100% | 0 | 0 | 0 | 11557 | -109.32 | 11447.6802 | -0.0002 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Elimination of CFCs with HCFC -141b (and partial water) based systems, in the manufacture of rigid polyurethane foam insulation products at Duab International | Individual | ASP | IND | FOA | 26 | INV | 190 | A | I | CFC | 13.4 | 13.4 | 0 | 0 | 1998-11-01 | 1999-07-01 | 2000-12-01 |  | 1999-12-01 | 2001-12-01 | 104490 | 0 | 104490 | 104490 | 100% | 0 | 0 | 0 | 13583.7 | 0 | 13583.7 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation products at Galaxy FRP P. Ltd. | Individual | ASP | IND | FOA | 26 | INV | 192 | A | I | CFC | 18.5 | 18.5 | 0 | 0 | 1998-11-01 | 1999-08-01 | 2000-12-01 |  | 2000-06-01 | 2002-03-01 | 144808 | -1805 | 143003 | 143003 | 100% | 0 | 0 | 0 | 18825.04 | -234.65 | 18590.39 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Elimination of CFCs with HCFC-141b and partial water based systems in the manufacture of rigid polyurethane foam insulated thermoware at Ajay Corrugating and Plastics P. Ltd. | Individual | ASP | IND | FOA | 26 | INV | 193 | A | I | CFC | 10.3 | 10.3 | 0 | 0 | 1998-11-01 | 1999-12-01 | 2000-12-01 |  | 2000-06-01 | 2002-03-01 | 80805 | 0 | 80805 | 80805 | 100% | 0 | 0 | 0 | 10504.65 | 0 | 10504.65 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam in situ and spray insulation at P.K. Construction Co. | Individual | ASP | IND | FOA | 27 | INV | 196 | A | D | CFC | 10.6 | 10.6 | 0 | 0 | 1999-03-01 | 1999-12-01 | 2001-10-01 |  | 1999-12-01 | 2001-12-01 | 74172 | -3275 | 70897 | 70897 | 100% | 0 | 0 | 0 | 9642.36 | -426 | 9216.36 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Ganga Thermoware | Individual | ASP | IND | FOA | 27 | INV | 197 | A | I | CFC | 10.1 | 10.1 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2001-10-01 |  | 2000-06-01 | 2002-03-01 | 78864 | -5388 | 73476 | 73476 | 100% | 0 | 0 | 0 | 10252.32 | -700.44 | 9551.88 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Bansal Plastic Industries | Individual | ASP | IND | FOA | 27 | INV | 198 | A | I | CFC | 20.4 | 20.4 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2001-10-01 |  | 2000-06-01 | 2002-03-01 | 68829 | -6240 | 62589 | 62589 | 100% | 0 | 0 | 0 | 8947.77 | -811.2 | 8136.57 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation products at Baba Insulator | Individual | ASP | IND | FOA | 27 | INV | 202 | A | I | CFC | 14.4 | 14.4 | 0 | 0 | 1999-03-01 | 1999-08-01 | 2001-10-01 |  | 2000-06-01 | 2002-03-01 | 59096 | -10468 | 48628 | 48628 | 100% | 0 | 0 | 0 | 7682.48 | -1360.84 | 6321.64 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation at R.S. Insulators | Individual | ASP | IND | FOA | 27 | INV | 205 | A | I | CFC | 10.3 | 10.3 | 0 | 0 | 1999-03-01 | 1999-08-01 | 2001-10-01 |  | 2000-06-01 | 2002-03-01 | 54800 | -10912 | 43888 | 43888 | 100% | 0 | 0 | 0 | 7124 | -1418.56 | 5705.44 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Shree Nath Plastics | Individual | ASP | IND | FOA | 27 | INV | 207 | A | I | CFC | 13.9 | 13.9 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2001-10-01 |  | 2000-06-01 | 2002-03-01 | 61370 | -7114 | 54256 | 54256 | 100% | 0 | 0 | 0 | 7978.1 | -924.82 | 7053.28 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Preparation of ten projects in general foam subsector | Individual | ASP | IND | FOA | 27 | PRP | 194 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2000-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1999 |  | Investment
FIN | UNDP | Preparation of seven projects in rigid foam subsector | Individual | ASP | IND | FOA | 27 | PRP | 206 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2000-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Varivar Plast Products P., Ltd. | Individual | ASP | IND | FOA | 28 | INV | 210 | A | I | CFC | 12.3 | 12.3 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2002-02-01 |  | 2000-11-01 | 2002-11-01 | 96184 | -1 | 96183 | 96183 | 100% | 0 | 0 | 0 | 12503.92 | -0.13 | 12503.79 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation at Supertek International | Individual | ASP | IND | FOA | 28 | INV | 211 | A | I | CFC | 10.6 | 10.6 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2002-02-01 |  | 2000-11-01 | 2003-04-01 | 83202 | 0 | 83202 | 83202 | 100% | 0 | 0 | 0 | 10816.26 | 0 | 10816.26 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation at Standard Electric Appliances | Individual | ASP | IND | FOA | 28 | INV | 212 | A | I | CFC | 10 | 10 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2002-02-01 |  | 2000-11-01 | 2002-03-01 | 78136 | 0 | 78136 | 78136 | 100% | 0 | 0 | 0 | 10157.68 | 0 | 10157.68 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at O.K. Industries | Individual | ASP | IND | FOA | 28 | INV | 214 | A | I | CFC | 10.7 | 10.7 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2002-02-01 |  | 2000-11-01 | 2002-11-01 | 66227 | -2012 | 64215 | 64215 | 100% | 0 | 0 | 0 | 8609.51 | -262 | 8347.51 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of integral skin polyurethane foam at Primrose Multiplast P. Ltd. | Individual | ASP | IND | FOA | 28 | INV | 215 | A | D | CFC | 9.6 | 9.6 | 0 | 0 | 1999-07-01 | 1999-12-01 | 2002-02-01 |  | 1999-12-01 | 2001-12-01 | 117105 | -1131 | 115974 | 115974 | 100% | 0 | 0 | 0 | 15223.65 | -147.2 | 15076.455 | -0.005 | 0 | Completed in 1999. Financially completed in 2001. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to CFC-free technology in the manufacture of rigid polyurethane foam chemical systems at Shivathene Linopack | Individual | ASP | IND | FOA | 28 | INV | 218 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2002-02-01 |  | 2000-11-01 | 2002-03-01 | 209000 | -16227 | 192773 | 192773 | 100% | 0 | 0 | 0 | 27170 | -2109.51 | 25060.49 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Devisons P. Ltd. | Individual | ASP | IND | FOA | 28 | INV | 219 | A | I | CFC | 15.3 | 15.3 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2002-02-01 |  | 2000-11-01 | 2002-11-01 | 114940 | -5215 | 109725 | 109725 | 100% | 0 | 0 | 0 | 14942.2 | -678 | 14264.2 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation at Nav Texfeb P. Ltd. | Individual | ASP | IND | FOA | 28 | INV | 224 | A | I | CFC | 32.4 | 32.4 | 0 | 0 | 1999-07-01 | 1999-12-01 | 2002-02-01 |  | 1999-12-01 | 2001-12-01 | 163982 | -3561 | 160421 | 160421 | 100% | 0 | 0 | 0 | 21317.66 | -463 | 20854.66 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at N.D. Plastics | Individual | ASP | IND | FOA | 28 | INV | 226 | A | I | CFC | 12.9 | 12.9 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2002-02-01 |  | 2000-10-01 | 2001-12-01 | 101289 | -802 | 100487 | 100487 | 100% | 0 | 0 | 0 | 13167.57 | -104.36 | 13063.2143 | -0.0043 | 0 | Completed in 2000. Financially completed in 2001. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Ashoka Metals | Individual | ASP | IND | FOA | 28 | INV | 228 | A | I | CFC | 12.5 | 12.5 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2002-02-01 |  | 2000-10-01 | 2002-03-01 | 68066 | -1587 | 66479 | 66479 | 100% | 0 | 0 | 0 | 8848.58 | -206.31 | 8642.27 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation at 28 small and medium-sized enterprises | Individual | ASP | IND | FOA | 28 | INV | 229 | A | I | CFC | 105.7 | 105.7 | 0 | 0 | 1999-07-01 | 2000-05-01 | 2002-02-01 |  | 2002-12-01 | 2005-09-01 | 699139 | -39114 | 660025 | 660025 | 100% | 0 | 0 | 0 | 86905.29 | -4862 | 82043.29 | 0 | 0 | Completed in 2002. Financially completed in 2005. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Tokyo Plast International, Ltd. | Individual | ASP | IND | FOA | 29 | INV | 231 | A | I | CFC | 30.5 | 30.5 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2003-07-01 |  | 2002-06-01 | 2003-11-01 | 196394 | -37676 | 158718 | 158718 | 100% | 0 | 0 | 0 | 25531.22 | -4897.63 | 20633.59 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation at Santech Industries | Individual | ASP | IND | FOA | 29 | INV | 232 | A | I | CFC | 14.7 | 14.7 | 0 | 0 | 1999-11-01 | 2001-05-01 | 2003-07-01 |  | 2001-11-01 | 2003-07-01 | 115101 | -9 | 115092 | 115092 | 100% | 0 | 0 | 0 | 14963.13 | -1.52 | 14961.61 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation at Saddle Poly Products P., Ltd. | Individual | ASP | IND | FOA | 29 | INV | 233 | A | I | CFC | 15.2 | 15.2 | 0 | 0 | 1999-11-01 | 2001-05-01 | 2003-07-01 |  | 2001-11-01 | 2003-07-01 | 119087 | -44 | 119043 | 119043 | 100% | 0 | 0 | 0 | 15481.31 | -5.59 | 15475.72 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of integral skin polyurethane foam at Coolwels Automobile Engineers | Individual | ASP | IND | FOA | 29 | INV | 234 | A | I | CFC | 15.8 | 15.8 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2001-12-01 | 2003-04-01 | 133221 | -669 | 132552 | 132552 | 100% | 0 | 0 | 0 | 17319 | -86.97 | 17232.03 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Mayur Jugs P., Ltd. | Individual | ASP | IND | FOA | 29 | INV | 235 | A | I | CFC | 16.9 | 16.9 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2003-07-01 |  | 2001-11-01 | 2003-04-01 | 119412 | -16905 | 102507 | 102507 | 100% | 0 | 0 | 0 | 15523.56 | -2198.04 | 13325.52 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of integral skin polyurethane foam at Premium Mouldings and Pressings P., Ltd. | Individual | ASP | IND | FOA | 29 | INV | 236 | A | I | CFC | 17.7 | 17.7 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2001-12-01 | 2003-11-01 | 138432 | -87 | 138345 | 138345 | 100% | 0 | 0 | 0 | 17996 | -11.31 | 17984.69 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Crystal Electronics and Plastics | Individual | ASP | IND | FOA | 29 | INV | 237 | A | I | CFC | 18.3 | 18.3 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2003-07-01 |  | 2001-11-01 | 2003-04-01 | 123343 | -20723 | 102620 | 102620 | 100% | 0 | 0 | 0 | 16034.59 | -2695 | 13339.59 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at National Plastics | Individual | ASP | IND | FOA | 29 | INV | 239 | A | I | CFC | 36.2 | 36.2 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2003-07-01 |  | 2001-11-01 | 2003-04-01 | 212481 | -39605 | 172876 | 172876 | 100% | 0 | 0 | 0 | 27622.53 | -5148.75 | 22473.78 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible molded polyurethane foam and from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Reactive Polymers Ltd. | Individual | ASP | IND | FOA | 29 | INV | 240 | A | I | CFC | 29.6 | 29.6 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2003-07-01 |  | 2001-11-01 | 2003-04-01 | 354175 | -56621 | 297554 | 297554 | 100% | 0 | 0 | 0 | 46042.75 | -7360.63 | 38682.12 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of integral skin polyurethane foam at Jaiswal Industries | Individual | ASP | IND | FOA | 29 | INV | 241 | A | I | CFC | 13.1 | 13.1 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2001-11-01 | 2003-04-01 | 152070 | -14822 | 137248 | 137248 | 100% | 0 | 0 | 0 | 19769 | -1926.86 | 17842.14 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation at 24 SMEs | Individual | ASP | IND | FOA | 29 | INV | 242 | A | I | CFC | 97.7 | 97.7 | 0 | 0 | 1999-11-01 | 2001-05-01 | 2003-07-01 |  | 2003-04-01 | 2006-10-01 | 886584 | -127666 | 758918 | 758918 | 100% | 0 | 0 | 0 | 107524.2 | -8865 | 98659.2 | 0 | 0 | Completed in 2003. Financially completed in 2006. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible molded polyurethane foam at Delite Foam and Polymers | Individual | ASP | IND | FOA | 29 | INV | 245 | A | I | CFC | 11.2 | 11.2 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2003-07-01 |  | 2001-11-01 | 2003-04-01 | 188832 | -2784 | 186048 | 186048 | 100% | 0 | 0 | 0 | 24548.16 | -361.92 | 24186.24 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam and from CFC-11 to HCFC-141b technology in the manufacture of integral skin polyurethane foam at Harjas Plastic and Metal Components P. Ltd. | Individual | ASP | IND | FOA | 29 | INV | 246 | A | I | CFC | 20.2 | 20.2 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2003-07-01 |  | 2002-05-01 | 2003-07-01 | 246386 | -30539 | 215847 | 215847 | 100% | 0 | 0 | 0 | 32030.18 | -3969.76 | 28060.42 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Preparation of 6 projects in the integral skin foam subsector | Individual | ASP | IND | FOA | 30 | PRP | 250 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-04-01 | 2003-01-01 | 30000 | -6577 | 23423 | 23423 | 100% | 0 | 0 | 0 | 3900 | -855.16 | 3044.84 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Preparation of an umbrella project in the rigid foam subsector | Individual | ASP | IND | FOA | 30 | PRP | 251 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-04-01 | 2003-01-01 | 30000 | -6577 | 23423 | 23423 | 100% | 0 | 0 | 0 | 3900 | -855.11 | 3044.89 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
CLO | UNDP | Preparation of 2 projects in the rigid foam subsector | Individual | ASP | IND | FOA | 30 | PRP | 252 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 |  | 2001-04-01 |  |  | 2003-01-01 | 30000 | -30000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 3900 | -3900 | 0 | 0 | 0 | Canceled in 2000. Financially Completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Ramakrishna Moulders | Individual | ASP | IND | FOA | 31 | INV | 258 | A | I | CFC | 15.7 | 15.7 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2002-12-01 | 2003-04-01 | 78479 | -1311 | 77168 | 77168 | 100% | 0 | 0 | 0 | 10202.27 | -170 | 10032.27 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at M-Plast | Individual | ASP | IND | FOA | 31 | INV | 259 | A | I | CFC | 13 | 13 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-12-01 | 2003-04-01 | 93279 | -451 | 92828 | 92828 | 100% | 0 | 0 | 0 | 12126.27 | -58.63 | 12067.64 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Naorang Plast | Individual | ASP | IND | FOA | 31 | INV | 260 | A | I | CFC | 13.5 | 13.5 | 0 | 0 | 2000-07-01 | 2001-07-01 | 2003-08-01 |  | 2002-06-01 | 2003-11-01 | 53171 | -563 | 52608 | 52608 | 100% | 0 | 0 | 0 | 6912 | -73.19 | 6838.81 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Sanjay Industries | Individual | ASP | IND | FOA | 31 | INV | 261 | A | I | CFC | 15.7 | 15.7 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2002-06-01 | 2003-11-01 | 99277 | -2381 | 96896 | 96896 | 100% | 0 | 0 | 0 | 12906.01 | -309.53 | 12596.48 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Crown Industries | Individual | ASP | IND | FOA | 31 | INV | 263 | A | I | CFC | 22.5 | 22.5 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-12-01 | 2003-11-01 | 113110 | -4382 | 108728 | 108728 | 100% | 0 | 0 | 0 | 14704.3 | -569.66 | 14134.64 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam spray and insitu insulation at sixteen enterprises | Individual | ASP | IND | FOA | 31 | INV | 267 | A | I | CFC | 211.1 | 211.1 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-11-01 | 2003-04-01 | 1094567 | -75293 | 1019274 | 1019274 | 100% | 0 | 0 | 0 | 130402.4 | -8282.23 | 122120.17 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulation at Enertech Engineering P. Ltd. | Individual | ASP | IND | FOA | 31 | INV | 268 | A | I | CFC | 15.8 | 15.8 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-11-01 | 2004-01-01 | 123109 | -86 | 123023 | 123023 | 100% | 0 | 0 | 0 | 16004.17 | -11 | 15993.17 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible moulded polyurethane foam at Raipur Agencies | Individual | ASP | IND | FOA | 31 | INV | 269 | A | I | CFC | 16.3 | 16.3 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-11-01 | 2003-04-01 | 144567 | -2814 | 141753 | 141753 | 100% | 0 | 0 | 0 | 18793.71 | -365.82 | 18427.89 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible moulded polyurethane foam at Pyarelal Coir Products Ltd. | Individual | ASP | IND | FOA | 31 | INV | 270 | A | I | CFC | 18.5 | 18.5 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-11-01 | 2003-04-01 | 167381 | -2886 | 164495 | 164495 | 100% | 0 | 0 | 0 | 21759.53 | -375.18 | 21384.35 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible moulded polyurethane foam at R.H. Industries | Individual | ASP | IND | FOA | 31 | INV | 271 | A | I | CFC | 11.3 | 11.3 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-11-01 | 2003-04-01 | 153895 | -2700 | 151195 | 151195 | 100% | 0 | 0 | 0 | 20006.35 | -351 | 19655.35 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible moulded polyurethane foam at Pinnacle Industries Ltd. | Individual | ASP | IND | FOA | 31 | INV | 272 | A | I | CFC | 13 | 13 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2002-06-01 | 2003-11-01 | 186392 | 0 | 186392 | 186392 | 100% | 0 | 0 | 0 | 24230.96 | 0 | 24230.96 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible moulded polyurethane foam at Nindra Foams | Individual | ASP | IND | FOA | 31 | INV | 273 | A | I | CFC | 11 | 11 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-12-01 | 2003-04-01 | 148804 | -2244 | 146560 | 146560 | 100% | 0 | 0 | 0 | 19344.52 | -291.59 | 19052.93 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible moulded polyurethane foam at SR Poly-steel P. Ltd. | Individual | ASP | IND | FOA | 31 | INV | 274 | A | I | CFC | 14.9 | 14.9 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2002-06-01 | 2003-11-01 | 144299 | -1 | 144298 | 144298 | 100% | 0 | 0 | 0 | 18758.87 | 0 | 18758.87 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible moulded and from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Enkay Foam P., Ltd. | Individual | ASP | IND | FOA | 31 | INV | 275 | A | I | CFC | 16.6 | 16.6 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-12-01 | 2003-11-01 | 162339 | -4442 | 157897 | 157897 | 100% | 0 | 0 | 0 | 21104.07 | -577.33 | 20526.74 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible moulded polyurethane foam at Alka International Ltd. | Individual | ASP | IND | FOA | 31 | INV | 276 | A | I | CFC | 18.5 | 18.5 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-12-01 | 2003-04-01 | 173155 | -6690 | 166465 | 166465 | 100% | 0 | 0 | 0 | 22510.15 | -869.7 | 21640.45 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Evershine Plastic Industry | Individual | ASP | IND | FOA | 31 | INV | 277 | A | I | CFC | 16.2 | 16.2 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-12-01 | 2003-11-01 | 80060 | -2410 | 77650 | 77650 | 100% | 0 | 0 | 0 | 10407.8 | -313.3 | 10094.5 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam at Netplast Ltd. | Individual | ASP | IND | FOA | 32 | INV | 280 | A | I | CFC | 18 | 18 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2003-09-01 | 2005-09-01 | 177224 | -2199 | 175025 | 175025 | 100% | 0 | 0 | 0 | 23039.12 | -286 | 22753.12 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of integral skin polyurethane foam at Sun Steering Wheels, Ltd. | Individual | ASP | IND | FOA | 32 | INV | 285 | A | I | CFC | 15.6 | 15.6 | 0 | 0 | 2000-12-01 | 2002-03-01 | 2004-01-01 |  | 2003-02-01 | 2005-10-01 | 144379 | -2997 | 141382 | 141382 | 100% | 0 | 0 | 0 | 18769.27 | -390 | 18379.27 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam and from CFC-11 to HCFC-141b technology in the manufacture of integral skin polyurethane foam at Sawhney Seating Systems | Individual | ASP | IND | FOA | 32 | INV | 289 | A | I | CFC | 28 | 28 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2003-07-01 | 2005-09-01 | 241619 | -3124 | 238495 | 238495 | 100% | 0 | 0 | 0 | 31410.47 | -406 | 31004.47 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
CLO | UNDP | Project preparation in the foam sector | Individual | ASP | IND | FOA | 33 | PRP | 296 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 |  | 2002-04-01 |  |  | 2003-07-01 | 15000 | -15000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 1950 | -1950 | 0 | 0 | 0 | Canceled in 2002. Financially Completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Project preparation in the integral skin foam sector | Individual | ASP | IND | FOA | 33 | PRP | 297 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | ASP | IND | FOA | 33 | PRP | 299 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at UNC Plast Industries | Individual | ASP | IND | FOA | 34 | INV | 304 | A | I | CFC | 11.4 | 11.4 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2004-06-01 | 2007-02-01 | 89607 | -1142 | 88465 | 88465 | 100% | 0 | 0 | 0 | 11648.91 | -148.46 | 11500.4489 | 0.0011 | 0 | Completed in 2004. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam at Viking Engineers P. Ltd. | Individual | ASP | IND | FOA | 34 | INV | 305 | A | I | CFC | 13.3 | 13.3 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-05-01 |  | 2004-06-01 | 2005-10-01 | 144900 | -2745 | 142155 | 142155 | 100% | 0 | 0 | 0 | 18837 | -356.85 | 18480.15 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | Italy | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam at Flexo Foam P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 307 | A | I | CFC | 19.4 | 19.4 | 0 |  | 2001-07-01 | 2002-12-01 | 2004-05-01 |  | 2004-03-01 | 2004-03-01 | 185241 | 0 | 185241 | 185241 | 100% | 0 | 0 |  | 24081 | 0 | 24081 | 0 |  | Trials, site preparation and balance of Incremental Operating Costs (IOC) paid in Dec-03. Handover Protocol and project completion took place in March 04. | Estimated Disbursement in Current Year (US$) was submitted as "n.a." | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Roome Plastics P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 312 | A | I | CFC | 18.1 | 18.1 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2003-11-01 | 2005-10-01 | 100546 | -2008 | 98538 | 98538 | 100% | 0 | 0 | 0 | 13070.98 | -261 | 12809.98 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Essa Aircons Ltd. | Individual | ASP | IND | FOA | 34 | INV | 317 | A | I | CFC | 13.9 | 13.9 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2004-06-01 | 2005-10-01 | 108837 | -2996 | 105841 | 105841 | 100% | 0 | 0 | 0 | 14148.81 | -389.49 | 13759.3248 | -0.004753 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | Italy | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam at Sutlej Coach Products P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 318 | A | I | CFC | 18 | 18 | 0 |  | 2001-07-01 | 2002-12-01 | 2004-05-01 |  | 2004-09-01 | 2004-09-01 | 187400 | 0 | 187400 | 187400 | 100% | 0 | 0 |  | 24362 | 0 | 24362 | 0 |  | Trials, site preparation and balance of Incremental Operating Costs (IOC) paid in Dec-03. Handover Protocol and project completion took place in June 04. | Estimated Disbursement in Current Year (US$) was submitted as "n.a." | 2001 |  | Investment
FIN | Italy | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam at Malvika Polymers | Individual | ASP | IND | FOA | 34 | INV | 319 | A | I | CFC | 20 | 20 | 0 |  | 2001-07-01 | 2002-12-01 | 2004-05-01 |  | 2004-03-01 | 2004-03-01 | 196610 | -295 | 196315 | 196315 | 100% | 0 | 0 |  | 25559 | -38 | 25521 | 0 |  | Trials, site preparation and balance of Incremental Operating Costs (IOC) paid in Dec-03. Handover Protocol and project completion took place in March 04. | Estimated Disbursement in Current Year (US$) was submitted as "n.a." | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCF-141b technology in the manufacture of rigid polyurethane foam spray and insitu insulation at 14 enterprises | Individual | ASP | IND | FOA | 34 | INV | 321 | A | I | CFC | 178.4 | 178.4 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-08-01 |  | 2003-09-01 | 2005-11-01 | 759165 | -12566 | 746599 | 746599 | 100% | 0 | 0 | 0 | 93508.15 | -1382 | 92126.15 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at 17 small and medium-sized enterprises | Individual | ASP | IND | FOA | 34 | INV | 322 | A | I | CFC | 55.8 | 55.8 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2004-03-01 | 2004-12-01 | 417740 | 0 | 417740 | 417740 | 100% | 0 | 0 | 0 | 54306.2 | 0 | 54306.2 | 0 | 0 | Completed in 2004. Financially completed in 2004. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Apollo Steelcrafts | Individual | ASP | IND | FOA | 34 | INV | 324 | A | I | CFC | 13.7 | 13.7 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2003-11-01 | 2005-10-01 | 76925 | -3129 | 73796 | 73796 | 100% | 0 | 0 | 0 | 10000.25 | -407 | 9593.25 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at SR Polymers and Printers | Individual | ASP | IND | FOA | 34 | INV | 325 | A | I | CFC | 19.6 | 19.6 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2004-06-01 | 2005-10-01 | 95002 | -2970 | 92032 | 92032 | 100% | 0 | 0 | 0 | 12350.26 | -386.09 | 11964.1681 | 0.001895 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Caryaire Equipments India P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 326 | A | I | CFC | 17 | 17 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2004-07-01 | 2005-11-01 | 133509 | 0 | 133509 | 133509 | 100% | 0 | 0 | 0 | 17356.17 | 0 | 17356.17 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Lear Insulation Engineering P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 328 | A | I | CFC | 10.6 | 10.6 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2004-06-01 | 2005-10-01 | 82567 | -1581 | 80986 | 80986 | 100% | 0 | 0 | 0 | 10733.71 | -205.54 | 10528.1745 | -0.004481 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Nandadeep Fibrotech P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 329 | A | I | CFC | 11.3 | 11.3 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2004-06-01 | 2005-10-01 | 88526 | -3278 | 85248 | 85248 | 100% | 0 | 0 | 0 | 11508.38 | -426.13 | 11082.2541 | -0.004071 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam at Nu-Foam Rubber Industries P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 330 | A | I | CFC | 15.6 | 15.6 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-05-01 |  | 2003-02-01 | 2005-10-01 | 160150 | -1115 | 159035 | 159035 | 100% | 0 | 0 | 0 | 20819.5 | -144.95 | 20674.5465 | 0.003524 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Poly Glass Fibre Industries P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 331 | A | I | CFC | 17.1 | 17.1 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2004-03-01 | 2005-10-01 | 134238 | -2571 | 131667 | 131667 | 100% | 0 | 0 | 0 | 17450.94 | -334.23 | 17116.7089 | 0.001147 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Polyrub Industries | Individual | ASP | IND | FOA | 34 | INV | 332 | A | I | CFC | 12.5 | 12.5 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2004-06-01 | 2005-10-01 | 97953 | -3144 | 94809 | 94809 | 100% | 0 | 0 | 0 | 12733.89 | -408.72 | 12325.1664 | 0.003572 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Prince Plastoware Ltd. | Individual | ASP | IND | FOA | 34 | INV | 333 | A | I | CFC | 9.4 | 9.4 | 0 | 0 | 2001-07-01 | 2002-01-01 | 2004-08-01 |  | 2002-06-01 | 2003-11-01 | 74010 | -3392 | 70618 | 70618 | 100% | 0 | 0 | 0 | 9621.3 | -440.96 | 9180.34 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Solvay Moulding P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 334 | A | I | CFC | 26.1 | 26.1 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-02-01 |  | 2003-07-01 | 2005-09-01 | 196885 | -15868 | 181017 | 181017 | 100% | 0 | 0 | 0 | 25595.05 | -2063 | 23532.05 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam insulated thermoware at Bhatia Plastics | Individual | ASP | IND | FOA | 34 | INV | 335 | A | I | CFC | 11.1 | 11.1 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-08-01 |  | 2004-03-01 | 2005-10-01 | 87070 | -5398 | 81672 | 81672 | 100% | 0 | 0 | 0 | 11319.1 | -701.73 | 10617.3662 | 0.003819 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | Italy | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam at Oto Industries P., Ltd. | Individual | ASP | IND | FOA | 34 | INV | 336 | A | I | CFC | 12.7 | 12.7 | 0 |  | 2001-07-01 | 2002-12-01 | 2004-05-01 |  | 2004-03-01 | 2004-03-01 | 139716 | -381 | 139335 | 139335 | 100% | 0 | 0 |  | 18163 | -47 | 18116 | 0 |  | Trials, site preparation and balance of Incremental Operating Costs (IOC) paid in Dec-03. Handover Protocol and project completion took place in March 04. | Estimated Disbursement in Current Year (US$) was submitted as "n.a." | 2001 |  | Investment
FIN | Germany | Project preparation for the phase out of ODS use in the flexible molded foam sub-sector in 5 enterprises | Individual | ASP | IND | FOA | 34 | PRP | 309 | A | I |  | 0 |  | 0 |  | 2001-07-01 | 2001-08-01 | 2002-08-01 |  | 2002-08-01 | 2002-10-01 | 23750 | 0 | 23750 | 23750 | 100% | 0 | 0 | 0 | 3088 | 0 | 3088 | 0 | 0 | 2 resultant investment projects were submitted and approved in Mar-02
FIN | Germany | Conversion from CFC-11 to water-based technology at Precision Engineering Tools and Components | Individual | ASP | IND | FOA | 36 | INV | 350 | A | I | CFC | 22 | 22 | 0 |  | 2002-03-01 | 2002-11-01 | 2003-09-01 |  | 2005-12-01 | 2006-06-01 | 200282 | -26 | 200256 | 200256 | 100% | 0 | 0 | 0 | 26037 | -3 | 26034 | 0 | 0 | Project has been completed. PCR submitted in 2006. Remaining funds will be returned. |  |  | 2004-12-01
FIN | Germany | Conversion from CFC-11 to water-based technology at Pramukh Poly-Products | Individual | ASP | IND | FOA | 36 | INV | 351 | A | I | CFC | 27 | 27 | 0 |  | 2002-03-01 | 2002-11-01 | 2003-09-01 |  | 2005-12-01 | 2006-06-01 | 224812 | -9 | 224803 | 224803 | 100% | 0 | 0 | 0 | 29226 | -1 | 29225 | 0 | 0 | Project has been completed. PCR submitted in 2006 |  |  | 2004-12-01
FIN | UNDP | Preparation of a terminal programme in the foam sector | Individual | ASP | IND | FOA | 36 | PRP | 348 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2005-11-01 | 40000 | -6328 | 33672 | 33672 | 100% | 0 | 0 | 0 | 5200 | -822.64 | 4377.36 | 0 | 0 | Completed in 2002. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Sectoral phase-out plan for elimination of CFCs in the foam sector (first tranche) | Multi-Year | ASP | IND | FOA | 37 | INV | 353 | N | I | CFC | 162.5 | 162.5 | 0 | 0 | 2002-07-01 | 2003-11-01 | 2003-12-01 |  | 2004-12-01 | 2013-10-01 | 1500000 | 0 | 1500000 | 1500000 | 100% | 0 | 0 | 0 | 131000 | 0 | 131000 | 0 | 0 | Financially completed in 2013. |  | 2002 |  | Investment
FIN | UNDP | Sectoral phase-out plan for elimination of CFCs in the foam sector (second tranche) | Multi-Year | ASP | IND | FOA | 41 | INV | 365 | N | I | CFC | 210 | 210 | 0 | 0 | 2003-12-01 | 2005-01-01 | 2004-12-01 |  | 2006-07-01 | 2013-10-01 | 1750000 | 0 | 1750000 | 1750000 | 100% | 0 | 0 | 0 | 153500 | 0 | 153500 | 0 | 0 | Financially completed in 2013. |  | 2003 |  | Investment
FIN | UNDP | Sectoral phase-out plan for elimination of CFCs in the foam sector (third tranche) | Multi-Year | ASP | IND | FOA | 44 | INV | 384 | N | I | CFC | 301 | 301 | 0 | 0 | 2004-12-01 | 2006-05-01 | 2005-12-01 |  | 2006-12-01 | 2013-10-01 | 1500000 | 0 | 1500000 | 1500000 | 100% | 0 | 0 | 0 | 131000 | 0 | 131000 | 0 | 0 | Financially completed in 2013. |  | 2004 |  | Investment
ONG | UNDP | Preparation for HCFC phase-out investment activities (stage II) (extruded polystyrene foam sector) | Individual | ASP | IND | FOA | 72 | PRP | 455 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 | 2015-06-01 | 2016-05-01 | 2017-06-01 |  |  | 40000 | 0 | 40000 | 8313 | 20.78% | 31687 | 0 | 12674.8 | 2800 | 0 | 581.91 | 2218.09 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Survery of enterprises in foam sector completed. Sectoral data analysed. HPMP Stage II Plan submitted and approved at 77th ExCom. Prodoc signed (actual/planned, yes/no and date):Letter of Authorisation sent 6 February 2015 Missions undertaken (actual/planned):3 TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: signed earlier First disbursement date (actual/planned): 42278Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | The process for selection of agency for verification of enterpises is initiated. After verification balance payment will be released to enterprises by June 2017 |  |  | Non-Investment
ONG | UNDP | Preparation for HCFC phase-out investment activities (stage II) (polyurethane foam sector) | Individual | ASP | IND | FOA | 72 | PRP | 458 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 | 2015-06-01 | 2016-05-01 | 2017-06-01 |  |  | 120000 | 0 | 120000 | 60221.94 | 50.18% | 59778.06 | 7383.26 | 23911.224 | 8400 | 0 | 4215.5358 | 4184.4642 | 516.8282 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Survery of enterprises in foam sector completed. Sectoral data analysed and HPMP II Plan prepared. HPMP Stage II Plan submitted and approved at 77th ExCom. Prodoc signed (actual/planned, yes/no and date):Letter of Authorisation sent 6 February 2015 Missions undertaken (actual/planned):3 TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: signed earlier First disbursement date (actual/planned): 42278Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | The process for selection of agency for verification of enterpises is initiated. After verification balance payment will be released to enterprises by June 2017 |  |  | Non-Investment
ONG | UNDP | Preparation of a demonstration project for development and evaluation of spray foam polyol systems for buildings using HFOs as blowing agent | Individual | ASP | IND | FOA | 74 | PRP | 460 | N | I | HCFC | 0 | 0 | 0 | 0 | 2015-05-01 | 2015-09-01 | 2016-05-01 | 2017-12-01 |  |  | 30000 | 0 | 30000 | 11071.41 | 36.9% | 18928.59 | 3469.16 | 7571.436 | 2100 | 0 | 774.9987 | 1325.0013 | 242.8412 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): The project was submitted along with HPMP II proposal as suggested by ExCom Prodoc signed (actual/planned, yes/no and date):Letter of Authorisation sent 6 February 2015 Missions undertaken (actual/planned):3 TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: signed earlier First disbursement date (actual/planned): 42248Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | Preparation for organising two workshops on low GWP technologies initiated | 2015 |  | Non-Investment
CLO | UNIDO | Preparation of an investment project in the fumigant sector | Individual | ASP | IND | FUM | 39 | PRP | 360 | A | I |  | 0 | 0 |  |  | 2003-04-01 | 2004-07-01 | 2004-04-01 |  |  | 2005-12-01 | 35000 | -34038 | 962 | 962.37 | 100% | -0.37 | 0 |  | 2625 | -2553 | 72 | 0 | 0 | CLO
FIN | UNDP | Demonstration and evaluation of alternative technology for halon fire protection system and technical assistance for sectoral strategy for ODS phase out | Individual | ASP | IND | HAL | 13 | DEM | 28 | N | I | HAL | 0 | 0 | 0 | 0 | 1994-07-01 | 1996-08-01 | 1997-07-01 |  | 1999-12-01 | 2003-02-01 | 309000 | -44111 | 264889 | 264889 | 100% | 0 | 0 | 0 | 40170 | -5734.43 | 34435.57 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  | 1994 | 1999-06-01 | Non-Investment
CLO | IBRD | Conversion from halon-1211 to ABC dry chemical power (ABC-DCP) and carbon dioxide (CO2) in portable extinguishers at Real Value Appliances Ltd. | Individual | ASP | IND | HAL | 18 | INV | 60 | N | I | HAL | 462 | 462 | 0 | 0 | 1995-11-01 |  | 1997-05-01 |  |  | 2003-07-01 | 251736 | -251736 | 0 | 0 | #DIV/0! | 0 | 0 |  | 32725.68 | -32725.68 | 0 | 0 | 0 | Project cancelled at the 39th ExCom. |  |  | 2000-12-01 | INV | 0
FIN | UNDP | Conversion of halon-1211 fire extinguisher production and elimination of its consumption of virgin halon-1301 at Steelage Industries Limited Minimax Division/ Chennai | Individual | ASP | IND | HAL | 24 | INV | 163 | A | I | Halon | 116 | 116 | 0 | 0 | 1998-03-01 | 2000-05-01 | 2000-04-01 |  | 2002-01-01 | 2003-04-01 | 131915 | -41454 | 90461 | 90461 | 100% | 0 | 0 | 0 | 17148.95 | -5389.02 | 11759.93 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher production and elimination of its consumption of virgin halon-1301 at Vijay Fire Protection Systems Ltd. | Individual | ASP | IND | HAL | 24 | INV | 165 | A | I | Halon | 292 | 292 | 0 | 0 | 1998-03-01 | 1999-08-01 | 2000-04-01 |  | 2000-12-01 | 2002-03-01 | 219152 | 0 | 219152 | 219152 | 100% | 0 | 0 | 0 | 28489.76 | 0 | 28489.76 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher production and elimination of its consumption of virgin halon-1301 at Nitin Fire Protection Industries Ltd., Bombay | Individual | ASP | IND | HAL | 24 | INV | 168 | A | I | Halon | 212 | 212 | 0 | 0 | 1998-03-01 | 1999-08-01 | 2000-04-01 |  | 2000-12-01 | 2002-03-01 | 165818 | 0 | 165818 | 165818 | 100% | 0 | 0 | 0 | 21556.34 | 0 | 21556.34 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Conversion of production halon-1211 fire extinguishers at Atkins, New Delhi | Individual | ASP | IND | HAL | 24 | INV | 170 | A | I | Halon | 37 | 37 | 0 | 0 | 1998-03-01 | 2000-04-01 | 2000-04-01 |  | 2001-05-01 | 2002-03-01 | 54760 | -739 | 54021 | 54021 | 100% | 0 | 0 | 0 | 7118.8 | -96.07 | 7022.73 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher production and elimination of its consumption of virgin halon-1301 at New Age Industries, Bombay | Individual | ASP | IND | HAL | 24 | INV | 175 | A | I | Halon | 133 | 133 | 0 | 0 | 1998-03-01 | 2000-04-01 | 2000-04-01 |  | 2000-12-01 | 2002-03-01 | 132248 | -292 | 131956 | 131956 | 100% | 0 | 0 | 0 | 17192.24 | -37.96 | 17154.28 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher production and elimination of its consumption of virgin halon-1301 at Vimal Industrial Safety Equipment Corporation Baroda, Gujrat | Individual | ASP | IND | HAL | 24 | INV | 176 | A | I | Halon | 133 | 133 | 0 | 0 | 1998-03-01 | 1999-08-01 | 2000-04-01 |  | 2000-12-01 | 2002-03-01 | 186152 | 0 | 186152 | 186152 | 100% | 0 | 0 | 0 | 24199.76 | 0 | 24199.76 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher production and elimination of its consumption of virgin halon-1301 at Ashoka Engineering Co., New Delhi | Individual | ASP | IND | HAL | 24 | INV | 177 | A | I | Halon | 34 | 34 | 0 | 0 | 1998-03-01 | 1999-08-01 | 2000-04-01 |  | 2000-12-01 | 2002-03-01 | 50320 | 0 | 50320 | 50320 | 100% | 0 | 0 | 0 | 6541.6 | 0 | 6541.6 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Project preparation for 5 halon extinguisher projects | Individual | ASP | IND | HAL | 24 | PRP | 166 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1999-12-01 | 2001-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher production to ABC powder and CO2 units at Cascade Counsel Ltd. New Delhi | Individual | ASP | IND | HAL | 28 | INV | 208 | A | I | Halon | 54 | 54 | 0 | 0 | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2000-12-01 | 2002-03-01 | 79920 | 0 | 79920 | 79920 | 100% | 0 | 0 | 0 | 10389.6 | 0 | 10389.6 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher production to ABC powder and CO2 units at Bharat Engineering Works, Mumbai | Individual | ASP | IND | HAL | 28 | INV | 209 | A | I | Halon | 49.5 | 49.5 | 0 | 0 | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2000-12-01 | 2002-03-01 | 73260 | -7751 | 65509 | 65509 | 100% | 0 | 0 | 0 | 9523.8 | -1007.63 | 8516.17 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher production to ABC powder and CO2 units at Zenith Fire Services, Mumbai | Individual | ASP | IND | HAL | 28 | INV | 216 | A | I | Halon | 36 | 36 | 0 | 0 | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2000-12-01 | 2002-03-01 | 53280 | -3309 | 49971 | 49971 | 100% | 0 | 0 | 0 | 6926.4 | -430.17 | 6496.23 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Extinguisher production and elimination of its consumption of virgin halon-1301 at New Fire Engineers Pvt. Ltd. Mumbai | Individual | ASP | IND | HAL | 28 | INV | 220 | A | I | Halon | 120 | 120 | 0 | 0 | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2000-12-01 | 2002-03-01 | 130000 | 0 | 130000 | 130000 | 100% | 0 | 0 | 0 | 16900 | 0 | 16900 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher to ABC powder and CO2 units together with the use of recycled halon-1301 in lieu of virgin product at Standard Castings Pvt. Ltd. New Delhi, under the name of Pyrosafety | Individual | ASP | IND | HAL | 28 | INV | 222 | A | I | Halon | 64.1 | 64.1 | 0 | 0 | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2000-12-01 | 2002-11-01 | 92000 | -23084 | 68916 | 68916 | 100% | 0 | 0 | 0 | 11960 | -3001 | 8959 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Conversion of halon-1211 fire extinguisher production to ABC powder and CO2 units at M/s Kooverji Devshi and Co. Pvt. Ltd., Mumbai | Individual | ASP | IND | HAL | 28 | INV | 256 | A | I | Halon | 25.5 | 25.5 | 0 | 0 | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2001-05-01 | 2002-03-01 | 37740 | 0 | 37740 | 37740 | 100% | 0 | 0 | 0 | 4906.2 | 0 | 4906.2 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Technical assistance for revision, preparation and introduction of national fire codes/standards for use of halon alternative technologies in India | Individual | ASP | IND | HAL | 29 | TAS | 243 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2002-12-01 |  | 2005-12-01 | 2007-03-01 | 88000 | -3435 | 84565 | 84565 | 100% | 0 | 0 | 0 | 11440 | -446.55 | 10993.45 | 0 | 0 | Completed in 2005. Financially completed in 2007. |  | 1999 |  | Non-Investment
FIN | Canada | National halon management and banking programme | Halon Banking | ASP | IND | HAL | 32 | TAS | 278 | A | I | HAL | 197.2 | 197.2 | 0 |  | 2000-12-01 | 2002-10-01 | 2004-01-01 |  | 2007-03-01 | 2007-03-01 | 245700 | 0 | 245700 | 245700 | 100% | 0 |  | 0 | 24570 | 0 | 24570 | 0 |  | Halon reclamation facility established in 2003. Canadian component annd Australian component of project completed |  | 2000 |  | Investment
FIN | Australia | National halon management and banking programme | Individual | ASP | IND | HAL | 32 | TAS | 281 | A | I | HAL | 197.2 | 197.2 | 0 | 0 | 2000-12-01 | 2002-02-01 | 2004-01-01 |  | 2007-05-01 | 2008-05-01 | 245700 | -24100 | 221600 | 221600 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Completed. |  | 2000
FIN | UNDP | Project preparation in the non-recycling halon sector | Individual | ASP | IND | HAL | 33 | PRP | 294 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2002-02-01 | 2002-04-01 |  | 2003-06-01 | 2003-07-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 2003. Financially completed in 2003. |  | 2001 |  | Investment
FIN | IBRD | Halon production and consumption sector phase out plan | One off phaseout | ASP | IND | HAL | 34 | INV | 315 | N | I | HAL | 556 | 556 | 321 | 321 | 2001-07-01 | 2003-08-01 | 2002-08-01 |  | 2003-10-01 | 2008-01-30 | 2600000 | 0 | 2600000 | 2600000 | 100% | 0 | 0 |  | 234000 | 0 | 234000 | 0 | 0 | UNDP has confirmed that project has been completed. Final completion report still pending from UNDP. |  |  |  | INV | 0
FIN | IBRD | Phaseout of use of carbon tetrachloride as process agent in the production of endosulphan by Excel Industries Limited | Individual | ASP | IND | PAG | 28 | INV | 217 | N | I | CTC | 375 | 375 | 0 | 0 | 1999-07-01 | 2000-11-01 | 2001-08-01 |  | 2001-12-01 | 2002-03-01 | 366000 | 0 | 366000 | 366000 | 100% | 0 | 0 |  | 47580 | 0 | 47580 | 0 | 0 | PCR to be finalized and submitted in 2003. |  |  |  | INV | 0
FIN | UNIDO | Conversion of carbon tetrachloride (CTC) as process solvent to trichloromethane at M/S Alpha Drugs India Ltd., Patiala | Individual | ASP | IND | PAG | 32 | INV | 283 | A | I | CTC | 69.7 | 69.7 |  |  | 2000-12-01 | 2001-11-01 | 2002-06-01 |  | 2003-03-01 | 2004-04-01 | 145866 | -130 | 145736 | 145735.54 | 100% | 0.46 | 0 |  | 15453 | -38 | 15415 | 0 | 0 | FIN
FIN | UNIDO | Conversion of carbon tetrachloride (CTC) as process solvent to ethylene dichloride at Svis Labs Ltd., Ranipet | Individual | ASP | IND | PAG | 32 | INV | 284 | A | R | CTC | 54.2 | 54.2 |  |  | 2000-12-01 | 2001-06-01 | 2002-01-01 |  | 2002-06-01 | 2003-07-01 | 249547 | 0 | 249547 | 249547.11 | 100% | -0.11 | 0 |  | 25352 | -9 | 25343 | 0 | 0 | FIN
FIN | UNIDO | Conversion of carbon tetrachloride (CTC) as process solvent to ethylene dichloride at Satya Deeptha Pharmaceuticals Ltd., Humnabad | Individual | ASP | IND | PAG | 32 | INV | 287 | A | I | CTC | 27.9 | 27.9 |  |  | 2000-12-01 | 2001-11-01 | 2002-07-01 |  | 2002-12-01 | 2004-12-01 | 260133 | -659 | 259474 | 259473.58 | 100% | 0.42 | 0 |  | 33817 | -139 | 33678 | 0 | 0 | FIN
FIN | UNIDO | Conversion of carbon tetrachloride (CTC) as process solvent to ethylene dichloride at Doctors Organic Chemicals Ltd., Tanuku | Individual | ASP | IND | PAG | 32 | INV | 291 | A | I | CTC | 94.6 | 94.6 |  |  | 2000-12-01 | 2002-01-01 | 2002-06-01 |  | 2002-12-01 | 2003-12-01 | 288809 | -171 | 288638 | 288638.31 | 100% | -0.31 | 0 |  | 37545 | -82 | 37463 | 0 | 0 | FIN
FIN | IBRD | Preparation of a sector plan for the process agent sector |  | ASP | IND | PAG | 33 | PRP | 301 | A | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-12-31 | 2001-12-01 |  | 2003-04-01 | 2003-12-01 | 130000 | 0 | 130000 | 130000 | 100% | 0 | 0 |  | 16900 | 0 | 16900 | 0 | 0 | Sector Plan completed and project document prepared for submission to the ExCom. |  |  |  | Non-INV | 0
FIN | UNIDO | Project preparation in the process agent (pharmaceutical) sector | Individual | ASP | IND | PAG | 33 | PRP | 302 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-06-01 | 2002-10-01 |  | 2003-10-01 | 2004-09-01 | 70000 | -5813 | 64187 | 64186.69 | 100% | 0.31 | 0 |  | 9100 | -769 | 8331 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of carbon tetrachloride as process agent to monochlorobenzene at M/S Benzo Chemical Industries, Tarapore | Individual | ASP | IND | PAG | 34 | INV | 303 | A | I | CTC | 23 | 23 |  |  | 2001-07-01 | 2003-03-01 | 2003-08-01 |  | 2004-12-01 | 2006-09-01 | 136786 | -3906 | 132880 | 132880.22 | 100% | -0.22 | 0 |  | 17782 | -508 | 17274 | 0 | 0 | FIN |  |  | 2004-12-01 | INV
FIN | UNIDO | Conversion of carbon tetrachloride as process agent to monochlorobenzene at Praddep Shetye Ltd., Alibagh | Individual | ASP | IND | PAG | 34 | INV | 311 | A | I | CTC | 133.9 | 133.9 |  |  | 2001-07-01 | 2002-12-01 | 2003-08-01 |  | 2004-12-01 | 2006-09-01 | 279001 | -10 | 278991 | 278991.21 | 100% | -0.21 | 0 |  | 36270 | -1 | 36269 | 0 | 0 | FIN |  |  | 2004-12-01 | INV
FIN | UNIDO | Conversion of carbon tetrachloride as process agent to ethylene dichloride at Chiplun Fine Chemicals Ltd., Ratnagiri | Individual | ASP | IND | PAG | 34 | INV | 313 | A | I | CTC | 16.7 | 16.7 |  |  | 2001-07-01 | 2002-02-01 | 2003-02-01 |  | 2003-07-01 | 2004-09-01 | 155830 | 0 | 155830 | 155829.82 | 100% | 0.18 | 0 |  | 20258 | -2 | 20256 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of carbon tetrachloride as process agent to monochlorobenzene at FDC Limited, Roha | Individual | ASP | IND | PAG | 34 | INV | 314 | A | I | CTC | 34.1 | 34.1 |  |  | 2001-07-01 | 2002-12-01 | 2003-08-01 |  | 2004-12-01 | 2008-05-01 | 238371 | -191 | 238180 | 238179.69 | 100% | 0.31 | 0 |  | 30988 | -25 | 30963 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of carbon tetrachloride as process agent to monochlorobenzene at GRD Chemicals Ltd., Indore, M.P. | Individual | ASP | IND | PAG | 34 | INV | 316 | A | I | CTC | 17.9 | 17.9 |  |  | 2001-07-01 | 2002-12-01 | 2003-08-01 |  | 2003-12-01 | 2005-04-01 | 127667 | 0 | 127667 | 127667.03 | 100% | -0.03 | 0 |  | 16597 | -9 | 16588 | 0 | 0 | FIN |  |  |  | INV
FIN | IBRD | Conversion of chlorinated rubber manufacture from carbon tetrachloride to non-ODS process at Rishiroop Organics Pvt. Ltd. | Individual | ASP | IND | PAG | 34 | INV | 320 | N | I | CTC | 248.8 | 248.8 | 0 | 0 | 2001-07-01 | 2002-12-01 | 2004-08-01 |  | 2003-10-01 | 2005-01-01 | 2074300 | -109984 | 1964316 | 1964315.95 | 100% | 0.05 | 0.05 |  | 238173 | -12098.24 | 226074.76 | 0 | 0 | Project financially completed and balance funds returned. PCR submitted to ExCom. |  |  |  | INV | 0
FIN | UNIDO | Conversion of carbon tetrachloride as process agent to cyclohexane at Amoli Organics Ltd., Mumbai | Individual | ASP | IND | PAG | 35 | INV | 338 | A | I | CTC | 38.5 | 38.5 |  |  | 2001-12-01 | 2002-03-01 | 2004-01-01 |  | 2004-08-01 | 2007-01-01 | 385367 | -1454 | 383913 | 383912.67 | 100% | 0.33 | 0 |  | 50098 | -189 | 49909 | 0 | 0 | FIN |  |  |  | INV
FIN | IBRD | CTC phase-out plan for the consumption and production sectors (first tranche) | Multiyear | ASP | IND | PHA | 40 | INV | 363 | N | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2005-12-01 | 2004-07-01 |  | 2004-07-01 | 2015-11-01 | 5000000 | 3520843 | 8520843 | 8520843 | 100% | 0 | 0 |  | 375000 | 264063 | 639063 | 0 | 0 | Tranche is completed. |  |  |  | INV | 0
FIN | IBRD | CTC phase-out plan for the consumption and production sectors: 2004 work programme | Multiyear | ASP | IND | PHA | 42 | INV | 373 | N | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2005-12-01 | 2005-04-01 |  | 2005-04-01 | 2015-11-01 | 9180112 | 0 | 9180112 | 9180112 | 100% | 0 | 0 |  | 688508 | 0 | 688508 | 0 | 0 | Targets met, tranche completed. |  |  |  | INV | 0
FIN | France | CTC phase-out plan for the consumption and production sectors: 2004 work programme | Multi-Year | ASP | IND | PHA | 42 | INV | 374 | A | I | CTC | 0 |  | 0 |  | 2004-04-01 | 2006-01-01 | 2005-04-01 |  | 2008-07-01 | 2010-10-01 | 1000000 | 0 | 1000000 | 1000000 | 100% | 0 |  | 0 | 85000 | 0 | 85000 | 0 |  | The French contribution is implemented by GIZ. All activities planned under this tranche have been completed. |  |  | 2007-04-01
FIN | Germany | CTC phase-out plan for the consumption and production sectors: 2004 work programme | Multi-Year | ASP | IND | PHA | 42 | INV | 375 | A | I | CTC | 0 |  | 0 |  | 2004-04-01 | 2004-06-01 | 2005-04-01 |  | 2007-12-01 | 2007-12-01 | 700000 | 0 | 700000 | 700000 | 100% | 0 | 0 | 0 | 57500 | 0 | 57500 | 0 | 0 | All activities planned with the funds from this tranche have been accomplished.
COM | Japan | CTC phase-out plan for the consumption and production sectors: 2004 work programme | Multi-Year | ASP | IND | PHA | 42 | INV | 376 | N | I | CTC | 0 |  | 0 |  | 2004-04-01 | 2005-11-01 | 2005-04-01 | 2014-12-01 | 2016-12-01 |  | 2500000 | 0 | 2500000 | 2500000 | 100% | 0 | 0 | 0 | 280000 | 0 | 280000 | 0 | 0 | CTC consumption phaseout in beneficiaries achieved before 2010. Remaining activities completed 31 Decembr 2016. | None. |  | 2016-12-01
FIN | UNIDO | CTC phase-out for the consumption and production sectors: 2005 annual programme | Multi-Year | ASP | IND | PHA | 45 | INV | 385 | A | I | CTC | 733 | 733 |  |  | 2005-04-01 | 2005-06-01 | 2006-04-01 |  | 2013-12-01 | 2014-08-01 | 3500000 | -79174 | 3420826 | 3420825.69 | 100% | 0.31 | 0 |  | 262500 | -5938 | 256562 | 0 | 0 | FIN |  |  |  | INV
FIN | IBRD | CTC phase-out for the consumption and production sectors: 2005 annual programme | Multiyear | ASP | IND | PHA | 45 | INV | 386 | N | I | CTC | 6158 | 9848 | 9827 | 9896 | 2005-04-01 | 2007-04-01 | 2006-04-01 |  | 2006-07-01 | 2015-11-01 | 399045 | 0 | 399045 | 399045 | 100% | 0 | 0 |  | 29928 | 0 | 29928 | 0 | 0 | Tranche completed. |  |  |  | INV | 0
FIN | France | CTC phase-out plan for the consumption and production sectors: 2005 annual programme | Multi-Year | ASP | IND | PHA | 45 | INV | 387 | A | I | CTC | 0 |  | 0 |  | 2005-04-01 | 2008-01-01 | 2006-04-01 |  | 2009-07-01 | 2010-10-01 | 1000000 | 0 | 1000000 | 1000000 | 100% | 0 |  | 0 | 85000 | 0 | 85000 | 0 |  | The French contribution was implemented by GTZ-Proklima. All activities have been completed. During 2009 the main focus of activities has been on training and technical assistance/information dissemination to industries. 3 dyes intermediaries manufacturers which had converted to ODS free technology had been found eligible for funding. The grant agreements have been signed and the subprojects have been completed in August 2009. |  |  | 2008-04-01
FIN | Germany | CTC phase-out plan for the consumption and production sectors: 2005 annual programme | Multi-Year | ASP | IND | PHA | 45 | INV | 388 | A | I | CTC | 0 | 970 | 0 |  | 2005-04-01 | 2006-01-01 | 2006-07-01 |  | 2008-12-01 | 2010-07-01 | 700000 | 0 | 700000 | 700000 | 100% | 0 | 0 | 0 | 57500 | 0 | 57500 | 0 | 0 | All activities planned under this tranche have been accomplished during implementation of the 2008 work plan.
ONG | Japan | CTC phase-out plan for the consumption and production sectors: 2005 annual programme | Multi-Year | ASP | IND | PHA | 45 | INV | 389 | N | I | CTC | 0 |  | 0 |  | 2005-04-01 | 2004-01-01 | 2008-04-01 | 2017-11-01 |  |  | 2500000 | 0 | 2500000 | 1686357 | 67.45% | 813643 | 0 | 325457 | 280000 | 0 | 188872 | 91128 | 0 | CTC consumption phaseout in beneficiaries achieved before 2010. Planning for remaining activities was in progress in 2016, remaining activities scheduled to be completed by Nov 2017 | None. |  | 2017-11-01
FIN | France | CTC phase-out plan for the consumption and production sectors: 2006 annual programme | Multi-Year | ASP | IND | PHA | 49 | INV | 399 | A | I | CTC | 0 |  | 0 |  | 2006-07-01 | 2009-01-01 | 2007-07-01 |  | 2009-12-01 | 2010-10-01 | 500000 | 0 | 500000 | 500000 | 100% | 0 |  | 0 | 85000 | 0 | 85000 | 0 |  | The French contribution was implemented by GTZ-Proklima. All activities have been completed. During 2009 the main focus of activities has been on training and technical assistance/information dissemination to industries. 3 dyes intermediaries manufacturers which had converted to ODS free technology had been found eligible for funding. The grant agreements have been signed and the subprojects have been completed in August 2009.
FIN | IBRD | CTC phase-out plan for the consumption and production sectors: 2006 annual programme | Multiyear | ASP | IND | PHA | 49 | INV | 400 | N | I | CTC | 232 | 232 | 232 | 232 | 2006-07-01 | 2007-11-01 | 2007-07-01 |  | 2007-07-01 | 2015-11-01 | 9556267 | 0 | 9556267 | 9556267 | 100% | 0 | 0 |  | 716720 | 0 | 716720 | 0 | 0 | Tranche fully disbursed. |  |  |  | INV | 0
FIN | Germany | CTC phase-out plan for the consumption and production sectors: 2006 annual programme | Multi-Year | ASP | IND | PHA | 49 | INV | 401 | A | I | CTC | 0 | 0 | 0 |  | 2006-07-01 | 2008-01-01 | 2007-07-01 |  | 2008-12-01 | 2010-07-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 | 0 | 57500 | 0 | 57500 | 0 | 0 | All activities planned under this tranche have been accomplished during implementation of the 2008 work plan.
FIN | UNIDO | CTC phase-out for the consumption and production sectors: 2006 annual programme | Multi-Year | ASP | IND | PHA | 49 | INV | 402 | A | I | CTC | 347 | 347 | 347 |  | 2006-07-01 | 2007-06-01 | 2007-07-01 |  | 2013-12-01 | 2013-12-01 | 399046 | -150288 | 248758 | 248757.81 | 100% | 0.19 | 0 |  | 29928 | -11272 | 18657 | -1 | 0 | FIN |  |  |  | INV
FIN | IBRD | CTC phase-out plan for the consumption and production sectors: 2007 annual programme | Multiyear | ASP | IND | PHA | 52 | INV | 408 | N | I | CTC | 420 | 420 | 420 | 420 | 2007-07-01 | 2007-11-01 | 2008-07-31 |  | 2008-07-01 | 2015-11-01 | 4020938 | 0 | 4020938 | 4020938 | 100% | 0 | 0 |  | 301570 | 0 | 301570 | 0 | 0 | Tranche completed. |  |  |  | INV | 0
FIN | France | CTC phase-out plan for the consumption and production sectors: 2007 annual programme | Multi-Year | ASP | IND | PHA | 52 | TAS | 409 | A | I | CTC | 0 |  | 0 |  | 2007-07-01 | 2009-01-01 | 2008-07-01 |  | 2009-12-01 | 2010-10-01 | 500000 | 0 | 500000 | 500000 | 100% | 0 |  | 0 | 85000 | 0 | 85000 | 0 |  | The French contribution was implemented by GTZ-Proklima. All activities have been completed. During 2009 the main focus of activities has been on training and technical assistance/information dissemination to industries. 3 dyes intermediaries manufacturers which had converted to ODS free technology had been found eligible for funding. The grant agreements have been signed and the subprojects have been completed in August 2009.
FIN | Germany | CTC phase-out plan for the consumption and production sectors: 2007 annual programme | Multi-Year | ASP | IND | PHA | 52 | TAS | 410 | A | I | CTC | 0 |  | 0 |  | 2007-07-01 | 2008-12-01 | 2008-07-01 |  | 2010-12-01 | 2012-12-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 | 0 | 57500 | 0 | 57500 | 0 | 0 | The environment, health and safety material has been completed and capacity building with institutional stakeholders from the power sector has taken place. All project activities have been completed now.
FIN | IBRD | CTC phase-out plan for the consumption and production sectors: 2008 annual programme | Multiyear | ASP | IND | PHA | 55 | INV | 422 | N | I | CTC | 440 | 440 | 440 | 440 | 2008-07-01 | 2008-12-01 | 2009-07-31 |  | 2009-12-01 | 2015-11-01 | 3211875 | 0 | 3211875 | 3211875 | 100% | 0 | 0 |  | 240891 | 0 | 240891 | 0 | 0 | All funds disbursed and tranche completed |  |  |  | INV | 0
FIN | Germany | Preparation of a HCFC phase-out management plan (overarching strategy) | Individual | ASP | IND | PHA | 56 | PRP | 426 | A | I | CFC | 0 |  | 0 |  | 2008-11-01 | 2009-09-01 | 2009-11-01 |  | 2010-12-01 | 2012-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | HPMP has been drafted and submitted to the NOU.
FIN | UNIDO | Preparation of a HCFC phase-out management plan (transportation refrigeration and air-conditioning sectors) | Individual | ASP | IND | PHA | 56 | PRP | 427 | A | I |  | 0 | 0 |  |  | 2008-11-01 | 2009-05-01 | 2009-11-30 |  | 2011-05-01 | 2011-05-01 | 70000 | -170 | 69830 | 69829.97 | 100% | 0.03 | 0 |  | 5250 | -13 | 5237 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNDP | Preparation of a HCFC phase-out management plan (overarching strategy) | Individual | ASP | IND | PHA | 56 | PRP | 428 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-11-01 | 2010-05-01 | 2009-11-01 |  | 2011-12-01 | 2013-05-01 | 113750 | 0 | 113750 | 113750 | 100% | 0 | 0 | 0 | 8531 | 0 | 8531 | 0 | 0 | Financially completed in 2013. | HPMP Stage-I submitted early January for the 66th Excom meeting. Project targeted for financial completion in 2012. | 2008 |  | Investment
FIN | UNEP | Preparation of a HCFC phase-out management plan (overarching strategy) | RMP | ASP | IND | PHA | 56 | PRP | 429 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-05-01 | 2009-11-01 |  | 2011-12-01 | 2012-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNDP | Preparation of a HCFC phase-out management plan (fire fighting and solvent sectors) | Individual | ASP | IND | PHA | 56 | PRP | 430 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-01 |  | 2011-12-01 | 2013-03-01 | 20000 | -20000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 1500 | -1500 | 0 | 0 | 0 | Financially completed in 2013. | Project targeted for financial closure in 2012 | 2008 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan (foam sector) | Individual | ASP | IND | PHA | 56 | PRP | 431 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-11-01 | 2010-05-01 | 2009-11-01 |  | 2011-12-01 | 2014-03-01 | 105000 | -26033.58 | 78966.42 | 78966 | 100% | 0.42 | 0 | 0 | 7875 | -1952.52 | 5922.45 | 0.03 | 0 | Financially completed in 2014. |  | 2008 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan (air conditioning sector) | Individual | ASP | IND | PHA | 56 | PRP | 432 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-11-01 | 2010-05-01 | 2009-11-01 |  | 2011-12-01 | 2013-03-01 | 125000 | -69173.6 | 55826.4 | 55826 | 100% | 0.4 | 0 | 0 | 9375 | -5188.02 | 4186.95 | 0.03 | 0 | Financially completed in 2013. | Project targeted for financial closure in 2012 | 2008 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan (refrigeration sector) | Individual | ASP | IND | PHA | 56 | PRP | 433 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-11-01 | 2010-05-01 | 2009-11-01 |  | 2011-12-01 | 2013-03-01 | 80000 | -35945.7 | 44054.3 | 44054 | 100% | 0.3 | 0 | 0 | 6000 | -2695.93 | 3304.05 | 0.02 | 0 | Financially completed in 2013. | Project targeted for financial closure in 2012 | 2008 |  | Investment
TRF | IBRD | CTC phase-out plan for the consumption and production sectors: 2009 annual programme | Multiyear | ASP | IND | PHA | 58 | INV | 434 | N | I | CTC | 268 | 268 | 0 | 0 | 2009-07-01 | 2009-12-01 | 2010-07-31 |  |  | 2015-11-01 | 3211874 | -806967 | 2404907 | 2404907 | 100% | 0 | 0 |  | 240891 | -60523 | 180368 | 0 | 0 | Project and balance of funds transferred to UNDP at the 75th Meeting. |  |  |  | INV | 0
FIN | UNDP | HCFC phase-out management plan (stage I, first tranche) (polyurethane foam sector plan) | Multi-year | ASP | IND | PHA | 66 | INV | 441 | N | I | HCFC | 145.4 | 145.4 | 0 | 0 | 2012-04-01 | 2013-03-01 | 2013-04-01 |  | 2015-05-01 | 2016-05-01 | 9400000 | 0 | 9400000 | 9400000 | 100% | 0 | 0 | 0 | 705000 | 0 | 705000 | 0 | 0 | Financially completed in 2016. | Activities progressing satisfactorily and most of the enterprises are at advanced stages of implementation of HCFC phase-out projects. Third tranche woul dbe submitted to the 75th Excom. | 2012 |  | Investment
COM | Germany | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | ASP | IND | PHA | 66 | INV | 442 | A | I | HCFC | 0 |  | 0 |  | 2012-04-01 | 2012-05-01 | 2013-04-01 |  | 2014-12-01 |  | 925452 | 0 | 925452 | 925452 | 100% | 0 | 0 | 0 | 106440 | 0 | 106440 | 0 |  | 1. RAC Technicians Training in Installation & Servicing Room Air conditioners up to 2 ton. 2. Training of Trainers (ToT) condcuted. 3. Contact established / initiated and meetings done with Instituional users - Defence and Railways for conducting training for their RAC technical staff. 4. One training for Defence - Technical staff conducted in Secunderabad. 5. Discussions with Reclamation Centre entreprenuers and preparing of action plan . 6. Discussions and proposal to DGET for Training RAC Trainers and syllabus revision. 7. IA and Core Group Meetings. 8. Planning and Co-ordination with the consultants and training partners in the field on a ongoing process. 9. PMU - Servicing Sector - management ongoing, coordination with UNEP ongoing. 11. Participation and Presentation at Awareness Workshops | 1. RAC Technicians Training in Installation & Servicing Room Air conditioners up to 2 ton. 2. Follow up meetings with Instituional users - Defence and Railways for conducting training for their RAC technical staff . 3. Two training programs for Railways - Technical staff one each in Lucknow and Ghaziabad. 4. Meeting with Reclamation centre entreprenuers. 5. Reclamation Centre awareness workshops one each at Ludhiana and Ahemdabad. 6. Discussions and proposal to DGET for Training RAC Trainers 7. IA and Core Group Meetings in August 2015. 8. Planning and Co-ordination with the consultants and training partners in the field on a ongoing process. 9. Printing of additional copies of Technicians Handbooks 10. PMU - Servicing Sector - management ongoing, coordination with UNEP ongoing 11. Participation and Presentation at Awareness Workshops. Activites to be completed - 1. Capacity building for Training Partners, 2. Insitutional training Railways and Defence RAC Techncial Staff 3. Training of RAC Teaching staff from ITI - that will require close follow up with DGET 4. Impact Monitoring - this activity will be completed early 2016 5. PMU - Servicing Sector - management ongoing, co-ordination with UNEP ongoing. 6. Participation and Presentation at Awareness Workshops
FIN | UNDP | HCFC phase-out management plan (stage I, first tranche) (project management component) | Multi-year | ASP | IND | PHA | 66 | TAS | 440 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-04-01 | 2013-05-01 | 2013-04-01 |  | 2015-11-01 | 2016-12-01 | 600000 | 0 | 600000 | 580000 | 96.67% | 20000 | 20000 | 0 | 45000 | 0 | 43500 | 1500 | 1500 | Financially completed in 2016. | Activities progressing satisfactorily and most of the enterprises are at advanced stages of implementation of HCFC phase-out projects. Third tranche would be submitted to the 75th Excom. PMU is coordinating project implementation monitoring in a satisfactory manner. | 2012 |  | Investment
COM | UNEP | HCFC phase-out management plan (stage I, first tranche) (enabling activities) | Multi-year | ASP | IND | PHA | 66 | TAS | 443 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 | 2012-12-01 | 2013-04-01 |  | 2016-12-01 |  | 250000 | 0 | 250000 | 250000 | 100% | 0 | 0 |  | 30402 | 0 | 30402 | 0 | 0 | Brief progress report (actual/planned): 12 awareness workshops with 1100 + stakeholders, Developed knowledge products (information, videos, flyers etc) Established association for RAC servicing sector in India (RASSS); 4 states in India Developed a website www.hpmp-ss.in Legal arrangements(actual/planned): Yes First mission (actual/planned): few missions undertaken TOR completed(actual/planned): ___ First disbursement date (actual/planned): Mar 2016 All funds disbursed (yes/no): No Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: New NOU and the focus more on investment component. Next Stage will recruit a consultant to coordinate UNEP's component If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): Materials prepared as a country handbook for customs training distributed to relevant stakeholders. Timetable for 15 workshops for supervisory officers of customs and other enforcement agencies finalized and initiated and will be completed by Nov 2017. Meetings to finalize the enforcement studies organized with NACEN and DRI in February 2017. Legal arrangements(actual/planned): Yes First mission (actual/planned): Feb 2017 TOR completed(actual/planned): ___ First disbursement date (actual/planned): Mar 2016 All funds disbursed (yes/no): No Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: New NOU and the focus more on investment component. Next Stage will recruit a consultant to coordinate UNEP's component If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___
COM | UNEP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-year | ASP | IND | PHA | 66 | TAS | 445 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 | 2013-08-01 | 2013-04-01 |  | 2016-12-01 |  | 180800 | 0 | 180800 | 180800 | 100% | 0 | 0 |  | 21986 | 0 | 21986 | 0 | 0 | Brief progress report (actual/planned): Training material developed in collaboration with NACEN. Capacity building of Custom Officers and Trainers ongoing. Refrigerant Identifiers at priority customs ports. Customs and enforcement officers and Directorate of Revenue Intelligence (DRI) received Ozone protection award for 2013-2015 for seizure of illegal HCFCs. Building Sector Intervention- curriculum for architects. Legal arrangements(actual/planned): Yes First mission (actual/planned): Few missions undertaken TOR completed(actual/planned): ___ First disbursement date (actual/planned): Mar 2016 All funds disbursed (yes/no): No Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: New NOU and the focus more on investment component. Next Stage will recruit a consultant to coordinate UNEP's component at national level If Yes, will delay have impact on project completion date (yes/no): Yes Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): The Agreement between NOU and Vigyan Prasar sighed to develop promotional videos and newsletter. Legal arrangements(actual/planned): Yes First mission (actual/planned): Few missions undertaken TOR completed(actual/planned): ___ First disbursement date (actual/planned): Mar 2016 All funds disbursed (yes/no): No Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: New NOU and the focus more on investment component. Next Stage will recruit a consultant to coordinate UNEP's component at national level If Yes, will delay have impact on project completion date (yes/no): Yes Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___
ONG | Germany | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | Multi-Year | ASP | IND | PHA | 71 | INV | 449 | A | I | HCFC | 0 |  | 0 |  | 2013-12-01 | 2014-01-01 | 2015-12-01 | 2017-12-01 |  |  | 869508 | 0 | 869508 | 699984 | 80.5% | 169524 | 169524 | 169524 | 100006 | 0 | 80508 | 19498 |  | Technicians Training for Residential (Room) Air-conditioners up to 2 ton completed - Institutional Strengthening - ToT for ITI instructors completed - Training for Defence and Railways one program for each completed - Reclamation centres workshops and review completed - PMU - Servicing Sector - management ongoing, co-ordination with UNEP ongoing. Partners meeting in December 2016 | Training Partners meeting will be organised Sept or Oct 2017 - Institutional Strengthening coordination with the staff at Defence and railwys to conduct one training program for each - PMU - Servicing Sector - management ongoing, co-ordination with UNEP ongoing |  |  | INV
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) (polyurethane foam sector plan) | Multi-Year | ASP | IND | PHA | 71 | INV | 451 | N | I | HCFC | 117.3 | 90.1 | 0 | 0 | 2013-12-01 | 2015-02-01 | 2015-12-01 | 2017-01-01 |  |  | 6580000 | 0 | 6580000 | 5380967.18 | 81.78% | 1199032.82 | 0 | 479613.128 | 460600 | 0 | 376667.7026 | 83932.2974 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): HPMP Stage-I activities in foam sector continued to be implemented in a satisfactory manner taking it to a completion stage. Industry conversion happened and 15 foam enterprises stopped consuming HCFC-141b. Verification completed for all 15 enterprises. Financial closure made for 10 enterprises. Only last installment is pending for payment for 5 enterprises which will happen in 2017. Prodoc signed (actual/planned, yes/no and date):41306 Missions undertaken (actual/planned):3 TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: signed earlier First disbursement date (actual/planned): 42036Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | The process for selection of agency for verification of enterpises initiated. After verification balance payment will be released to enterprises by June 2017 | 2013 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) (project management component) | Multi-Year | ASP | IND | PHA | 71 | TAS | 448 | N | I | HCFC | 0 | 0 | 0 | 0 | 2013-12-01 | 2013-03-01 | 2015-12-01 | 2017-01-01 |  |  | 420000 | 0 | 420000 | 198646.22 | 47.3% | 221353.78 | 0 | 88541.512 | 29400 | 0 | 13905.2354 | 15494.7646 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Project Management activities progressed satisfactorily. The project management unit contributed to preparation of HPMP II proposal as well as HPMP I implementation activities as required. Prodoc signed (actual/planned, yes/no and date):41365 Missions undertaken (actual/planned):3 TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: signed earlier First disbursement date (actual/planned): 41334Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | The project management unit contributed to preparation of project document and launch of the project | 2013 |  | Investment
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector and enabling activities) | Multi-year | ASP | IND | PHA | 71 | TAS | 450 | A | I |  | 3.6 |  | 0 |  | 2013-12-01 |  | 2015-12-01 | 2017-12-01 |  |  | 344640 | 0 | 344640 | 0 | 0% | 344640 | 299767.2 | 34464 | 41910 | 0 | 0 | 41910 | 36453.2363 | Brief progress report (actual/planned): Training material developed in collaboration with NACEN. Capacity building of Custom Officers and Trainers ongoing. Refrigerant Identifiers at priority customs ports. Customs and enforcement officers and Directorate of Revenue Intelligence (DRI) received Ozone protection award for 2013-2015 for seizure of illegal HCFCs. Building Sector Intervention- curriculum for architects. 12 awareness workshops with 1100 + stakeholders, Developed knowledge products (information, videos, flyers etc). Established association for RAC servicing sector in India (RASSS); 4 states in India. Developed a website www.hpmp-ss.in Legal arrangements(actual/planned): Yes First mission (actual/planned): Few missions undertaken TOR completed(actual/planned): ___ First disbursement date (actual/planned): Not yet (new bank details not confirmed) All funds disbursed (yes/no): No Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: New NOU and the focus more on investment component. Next Stage will recruit a consultant to coordinate UNEP's component If Yes, will delay have impact on project completion date (yes/no): Yes Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): Ministry contracted EESL (Energy Energy Services limited) to implement the activities related to the building sector. Draft training module/curriculum and awareness booklet on HPMP and building sector developed and finalized. Legal arrangements(actual/planned): Yes. The amendment was signed till Dec 2017 First mission (actual/planned): Few missions undertaken TOR completed(actual/planned): ___ First disbursement date (actual/planned): Not yet (new bank details not confirmed) All funds disbursed (yes/no): No Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: New NOU and the focus more on investment component. Next Stage will recruit a consultant to coordinate UNEP's component If Yes, will delay have impact on project completion date (yes/no): Yes Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___ |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor the signing of the amendment to the agreement.
ONG | UNDP | Preparation of a HCFC phase-out management plan (stage II) | Individual | ASP | IND | PHA | 72 | PRP | 452 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 | 2015-03-01 | 2016-05-01 | 2017-06-01 |  |  | 50000 | 0 | 50000 | 20000 | 40% | 30000 | 30000 | 12000 | 3500 | 0 | 1400 | 2100 | 2100 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): HPMP Stage-II survey was completed and overarching plan was made. One national stakeholder consultation was held in August 2016. The proposal was submitted and approved at the 77th ExCom. Prodoc signed (actual/planned, yes/no and date):LoA signed Nov 2015 Missions undertaken (actual/planned):3 TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: signed earlier First disbursement date (actual/planned): 42339Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | The process for selection of agency for verification of enterpises is initiated. |  |  | Investment
COM | Germany | Preparation of a HCFC phase-out management plan (stage II) | Individual | ASP | IND | PHA | 72 | PRP | 454 | A | I | HCFC | 0 |  | 0 |  | 2014-05-01 | 2015-06-01 | 2016-05-01 |  | 2016-10-01 |  | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 |  | HPMP - Stage II document prepared and submitted.
COM | UNEP | Preparation of a HCFC phase-out management plan (stage II) | Multi-Year | ASP | IND | PHA | 72 | PRP | 456 | A | I |  | 0 |  | 0 |  | 2014-05-01 | 2015-12-01 | 2016-05-01 |  | 2016-10-01 |  | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Project completed | Project completed
ONG | UNDP | CTC phase-out plan for the consumption and production sectors: 2009 annual programme | Multi-year | ASP | IND | PHA | 75 | INV | 463 | N | I | CTC | 0 | 0 | 0 | 0 | 2015-11-01 | 2016-07-01 | 2017-11-01 | 2017-11-01 |  |  | 750093 | 0 | 750093 | 83290.65 | 11.1% | 666802.35 | 41027.9 | 266720.94 | 56257 | 0 | 6246.8015 | 50010.1985 | 3077.0939 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): CTC activities as per approved plan was initiated. Two contracts were awarded for publication and study. Activities were also initiated for developing MIS, a online system for Ozone cell. The extension for project was received upto Nov 2017 in Excom. The project activities will be completed by Nov 2017 Prodoc signed (actual/planned, yes/no and date):42522 Missions undertaken (actual/planned):3 TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: signed earlier First disbursement date (actual/planned): 42552Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | The process for selection of consultant for MIS completed. Both agency (Study and publication) submitted inception report and initited work | 2015 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, third tranche) (polyurethane foam sector plan and project monitoring) | Multi-year | ASP | IND | PHA | 75 | INV | 464 | N | I | HCFC | 47.8 | 0 | 0 | 0 | 2015-11-01 |  | 2017-11-01 | 2017-11-01 |  |  | 1438490 | 0 | 1438490 | 0 | 0% | 1438490 | 0 | 575396 | 100694 | 0 | 0 | 100694 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): HPMP Stage-I activities in foam sector continued to be implemented in a satisfactory manner taking it to a completion stage. Industry conversion happened and 15 foam enterprises stopped consuming HCFC-141b. Verification completed for all 15 enterprises. Financial closure made for 10 enterprises. Only last installment is pending for payment for 5 enterprises which will happen in 2017. Prodoc signed (actual/planned, yes/no and date):42461 Missions undertaken (actual/planned):3 TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: signed earlier First disbursement date (actual/planned): 42461Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | The process for selection of agency for verification of enterpises is initiated. | 2015 |  | Investment
ONG | Germany | HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing sector) | Multi-Year | ASP | IND | PHA | 75 | INV | 465 | A | I | HCFC | 24.4 |  | 0 |  | 2015-11-01 | 2016-04-01 | 2016-12-01 | Dec-17 |  |  | 199440 | 0 | 199440 | 57000 | 28.58% | 142440 | 87000 | 125000 | 22938 | 0 | 22938 | 0 |  | Institutional Strengthening coordination with the officers at Defence and Railways - Impact Monitoring field work being done - PMU - Servicing Sector - management ongoing, co-ordination with UNEP ongoing. | Training Partners meeting proposed to be organised in Sept or Oct 2017 - Impact monitoring report writing ongoing - PMU - Servicing Sector - management ongoing, co-ordination with UNEP ongoing
ONG | UNEP | HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing sector and enabling activities) | Multi-Year | ASP | IND | PHA | 75 | TAS | 466 | A | I |  | 3.3 |  | 0 |  | 2015-11-01 | 2016-07-01 | 2016-12-01 | 2017-12-01 |  |  | 86160 | 0 | 86160 | 799.22 | 0.9276% | 85360.78 | 0 | 8536.078 | 10478 | 0 | 97.1939 | 10380.8061 | 0 | Brief progress report (actual/planned): Training material developed in collaboration with NACEN. Capacity building of Custom Officers and Trainers ongoing. Refrigerant Identifiers at priority customs ports. Customs and enforcement officers and Directorate of Revenue Intelligence (DRI) received Ozone protection award for 2013-2015 for seizure of illegal HCFCs. Building Sector Intervention- curriculum for architects. 12 awareness workshops with 1100 + stakeholders, Developed knowledge products (information, videos, flyers etc). Established association for RAC servicing sector in India (RASSS); 4 states in India. Developed a website www.hpmp-ss.in Legal arrangements(actual/planned): Yes First mission (actual/planned): Few missions undertaken TOR completed(actual/planned): ___ First disbursement date (actual/planned): Not yet (new bank details not confirmed) All funds disbursed (yes/no): No Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: New NOU and the focus more on investment component. Next Stage will recruit a consultant to coordinate UNEP's component If Yes, will delay have impact on project completion date (yes/no): Yes Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): 2 RAC services enterprises and association awarness raising workshops will be finalized by June 2017. Legal arrangements(actual/planned): Yes, amendment signed to extend till Dec 2017 First mission (actual/planned): Feb 2017 TOR completed(actual/planned): ___ First disbursement date (actual/planned): Not yet (new bank details not confirmed) All funds disbursed (yes/no): No Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: New NOU and the focus more on investment component. Next Stage will recruit a consultant to coordinate UNEP's component If Yes, will delay have impact on project completion date (yes/no): Yes Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___ |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor the signing of the agreement by the Government and UNEP.
ONG | UNDP | HCFC phase-out management plan (stage II, first tranche) (polyurethane foam sector plan) | Multi-year | ASP | IND | PHA | 77 | INV | 468 | N | I | HCFC | 114 | 0 | 0 | 0 | 2016-12-01 |  | 2019-12-01 | 2017-12-01 |  |  | 4500000 | 0 | 4500000 | 0 | 0% | 4500000 | 0 | 1800000 | 315000 | 0 | 0 | 315000 | 0 | Newly Approved | DoA sent March 2017. | 2016 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage II, first tranche) (air-conditioning manufacturing sector plan) | Multi-year | ASP | IND | PHA | 77 | INV | 469 | N | I | HCFC | 25 | 0 | 0 | 0 | 2016-12-01 |  | 2019-12-01 | 2017-12-01 |  |  | 4500000 | 0 | 4500000 | 0 | 0% | 4500000 | 0 | 1800000 | 315000 | 0 | 0 | 315000 | 0 | Newly Approved | DoA sent March 2017. | 2016 |  | Investment
ONG | Germany | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector plan) |  | ASP | IND | PHA | 77 | INV | 471 | A | I | HCFC | 4 |  | 0 |  | 2016-12-01 |  | 2018-12-01 | 2018-12-01 |  |  | 345000 | 0 | 345000 | 0 | 0% | 345000 | 0 | 200000 | 38626 | 0 | 38626 | 0 |  | The project was approved at 77th Excom | Draft a work plan for implementation of HPMP Stage - II - Participation in Stakeholders workshop / Launch event for HPMP Stage - II - Dialogue with NOU / MoEF&CC, RAC Industry other stakeholders - contracting with training partners and external experts - Technicians training - primarily the preparation work to facilitate conduct of technicians training is in progress - Technicians Training material finalised - Training network (TP and trainers ) functional - Training of trainers (ToT ) - Training initiated - PMU - Servicing Sector - management ongoing, co-ordination with UNEP ongoing
ONG | UNEP | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector plan) | Multi-Year | ASP | IND | PHA | 77 | TAS | 470 | A | I |  | 3.4 |  | 0 |  | 2016-12-01 |  | 2018-12-01 | 2018-12-01 |  |  | 300000 | 0 | 300000 | 0 | 0% | 300000 | 0 | 30000 | 36333 | 0 | 0 | 36333 | 0 | Newly approved project | Brief progress report: SSFA is under development.
ONG | UNDP | HCFC phase-out management plan (stage II, first tranche) (project management and monitoring) | Multi-year | ASP | IND | PHA | 77 | TAS | 472 | N | I | HCFC | 0 | 0 | 0 | 0 | 2016-12-01 |  | 2019-12-01 | 2017-12-01 |  |  | 256000 | 0 | 256000 | 0 | 0% | 256000 | 0 | 102400 | 17920 | 0 | 0 | 17920 | 0 | Newly Approved | DoA sent March 2017. | 2016 |  | Investment
FIN | IBRD | CFC production sector gradual phase-out project: 1999 annual programme | Multiyear | ASP | IND | PRO | 29 | INV | 238 | N | I | CFC | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-08-01 | 2000-11-01 |  | 2000-11-01 | 2011-11-01 | 12000000 | 0 | 12000000 | 12000000 | 100% | 0 | 0 |  | 960000 | 0 | 960000 | 0 | 0 | Production sector plan fully completed. |  |  |  | INV | 0
FIN | IBRD | Preparation of projects in halon production sector |  | ASP | IND | PRO | 30 | PRP | 249 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | CFC production sector gradual phase-out project: 2000 annual programme | Multiyear | ASP | IND | PRO | 31 | INV | 262 | N | I | CFC | 0 | 0 | 1882 | 1882 | 2000-07-01 | 2000-09-01 | 2000-12-01 |  | 2000-12-01 | 2011-11-01 | 11000000 | 0 | 11000000 | 11000000 | 100% | 0 | 0 |  | 880000 | 0 | 880000 | 0 | 0 | Production sector plan fully completed. |  |  |  | INV | 0
FIN | IBRD | CFC production sector gradual phase-out project: 2001 annual programme | Multiyear | ASP | IND | PRO | 33 | INV | 295 | N | I | CFC | 0 | 0 | 1583 | 1583 | 2001-03-01 | 2001-04-30 | 2001-12-01 |  | 2001-12-01 | 2011-11-01 | 11000000 | 0 | 11000000 | 11000000 | 100% | 0 | 0 |  | 880000 | 0 | 880000 | 0 | 0 | Production sector plan fully completed. |  |  |  | INV | 0
FIN | IBRD | CFC production sector gradual phase-out project: 2002 annual programme | Multiyear | ASP | IND | PRO | 36 | INV | 352 | N | I | CFC | 0 | 0 | 1883 | 1883 | 2002-03-01 | 2002-12-01 | 2002-12-01 |  | 2002-12-01 | 2011-11-01 | 6000000 | 0 | 6000000 | 6000000 | 100% | 0 | 0 |  | 480000 | 0 | 480000 | 0 | 0 | Production sector plan fully completed. |  |  |  | INV | 0
FIN | IBRD | Project preparation funds for CTC production closure plan |  | ASP | IND | PRO | 38 | PRP | 355 | A | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-12-01 | 2003-12-01 |  | 2003-12-01 | 2003-12-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 |  | 11700 | 0 | 11700 | 0 | 0 | Completed and submitted to ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | CFC production sector gradual phase-out: 2003 annual programme | Multiyear | ASP | IND | PRO | 39 | INV | 361 | N | I | CFC | 0 | 0 | 1883 | 1883 | 2003-04-01 | 2003-12-01 | 2004-04-01 |  | 2004-04-01 | 2011-11-01 | 6000000 | 0 | 6000000 | 6000000 | 100% | 0 | 0 |  | 450000 | 0 | 450000 | 0 | 0 | Production sector plan fully completed. |  |  |  | INV | 0
FIN | IBRD | CFC production sector gradual phase-out: 2004 annual programme | Multiyear | ASP | IND | PRO | 42 | INV | 372 | N | I | CFC | 0 | 0 | 1832 | 1832 | 2004-04-01 | 2004-06-01 | 2005-04-01 |  | 2005-01-01 | 2011-11-01 | 6000000 | 0 | 6000000 | 6000000 | 100% | 0 | 0 |  | 450000 | 0 | 450000 | 0 | 0 | Production sector plan fully completed. |  |  |  | INV | 0
FIN | IBRD | CFC production sector gradual phase-out: 2005 annual implementation plan | Multiyear | ASP | IND | PRO | 45 | INV | 390 | N | I | CFC | 0 | 0 | 1882 | 1882 | 2005-04-01 | 2005-11-01 | 2006-04-01 |  | 2006-04-01 | 2011-11-01 | 5850000 | 0 | 5850000 | 5850000 | 100% | 0 | 0 |  | 438750 | 0 | 438750 | 0 | 0 | Production sector plan fully completed. |  |  |  | INV | 0
FIN | IBRD | CFC production sector gradual phase-out: 2006 annual implementation plan | Multiyear | ASP | IND | PRO | 48 | INV | 397 | N | I | CFC | 0 | 0 | 3389 | 3389 | 2006-04-01 | 2006-08-01 | 2007-04-01 |  | 2007-04-01 | 2011-11-01 | 6000000 | 0 | 6000000 | 6000000 | 100% | 0 | 0 |  | 450000 | 0 | 450000 | 0 | 0 | Production sector plan fully completed. |  |  |  | INV | 0
FIN | IBRD | CFC production sector gradual phase-out: balance from the 2005 annual implementation plan | Multiyear | ASP | IND | PRO | 48 | INV | 398 | N | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2008-05-01 | 2007-04-01 |  | 2008-07-01 | 2011-11-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 |  | 11250 | 0 | 11250 | 0 | 0 | Production sector plan fully completed. |  |  |  | INV | 0
FIN | IBRD | CFC production sector gradual phase-out: 2007 annual implementation plan | Multiyear | ASP | IND | PRO | 51 | INV | 407 | N | I | CFC | 0 | 0 | 3953 | 3953 | 2007-03-01 | 2007-11-01 | 2008-03-01 |  | 2008-04-01 | 2011-11-01 | 6000000 | 0 | 6000000 | 6000000 | 100% | 0 | 0 |  | 450000 | 0 | 450000 | 0 | 0 | Production sector plan fully completed. |  |  |  | INV | 0
FIN | IBRD | CFC production sector gradual phase-out: 2008 annual implementation plan | Multiyear | ASP | IND | PRO | 54 | INV | 417 | N | I | CFC | 0 | 0 | 1130 | 1130 | 2008-04-01 | 2008-12-01 | 2009-03-31 |  | 2009-12-01 | 2011-11-01 | 6000000 | 0 | 6000000 | 6000000 | 100% | 0 | 0 |  | 450000 | 0 | 450000 | 0 | 0 | Production sector plan fully completed. |  |  |  | INV | 0
FIN | IBRD | CFC production sector gradual phase-out: 2009 annual implementation plan | Multiyear | ASP | IND | PRO | 59 | INV | 434 | N | I | CFC | 0 | 0 | 3171 | 3171 | 2009-11-01 | 2010-12-01 | 2010-11-30 |  | 2011-04-01 | 2011-11-01 | 6000000 | 0 | 6000000 | 6000000 | 100% | 0 | 0 |  | 450000 | 0 | 450000 | 0 | 0 | Production sector plan fully completed. |  |  |  | INV | 0
FIN | IBRD | Accelerated CFC production phase-out (first tranche) | Multiyear | ASP | IND | PRO | 59 | INV | 435 | N | I | CFC | 0 | 0 | 690 | 690 | 2009-11-01 | 2012-01-01 | 2010-11-30 |  | 2011-12-01 | 2015-11-01 | 2113000 | 0 | 2113000 | 2113000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Funding disbursed to the country in Jan 2012. |  |  |  | INV | 0
TRF | IBRD | Accelerated CFC production phase-out (second tranche) | Multiyear | ASP | IND | PRO | 67 | INV | 446 | N | I |  | 0 | 0 | 0 | 0 | 2012-07-01 |  | 2013-07-31 |  |  | 2015-11-01 | 739900 | -739900 | 0 | 0 | #DIV/0! | 0 | 0 |  | 213968 | -213968 | 0 | 0 | 0 | Project and balance of funds transferred to UNDP at the 75th Meeting. |  |  |  | INV | 0
TRF | IBRD | Accelerated CFC production phase-out (remaining of the second tranche) | Multiyear | ASP | IND | PRO | 69 | INV | 447 | N | I |  | 0 | 0 | 0 | 0 | 2013-04-01 |  | 2014-04-30 |  |  | 2015-11-01 | 317000 | -317000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 24032 | -24032 | 0 | 0 | 0 | Project and balance of funds transferred to UNDP at the 75th Meeting. |  |  |  | INV | 0
ONG | UNDP | Accelerated CFC production phase-out (second tranche) | Multi-year | ASP | IND | PRO | 75 | INV | 447 | N | I | CFC | 0 | 0 | 0 | 0 | 2015-11-01 | 2016-02-01 | 2017-11-01 | 2017-11-01 |  |  | 1056900 | 0 | 1056900 | 1056000 | 99.91% | 900 | 0 | 360 | 79268 | 0 | 79200.4996 | 67.5004 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Consultant was appointed and verification of four enterprises were made. Financial closure was done for all four enterprises and project was completed. Prodoc signed (actual/planned, yes/no and date):42401 Missions undertaken (actual/planned):3 TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: signed earlier First disbursement date (actual/planned): 42416Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | completed in 2016 | 2015 |  | Investment
FIN | IBRD | Substitution of CFC-11 refrigerant by HCFC-123 in centrifugal chillers (Blue Star) | Individual | ASP | IND | REF | 10 | INV | 08 | N | I | CFC | 36 | 36 | 0 | 0 | 1993-06-01 | 1995-07-01 | 1996-06-01 |  | 1997-12-01 | 1997-12-01 | 567000 | -146504 | 420496 | 420496 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. (Remaining "balance" has been disbursed to FA.) |  |  | 1997-06-01 | INV | 0
FIN | IBRD | Conversion of compressor manufacture from CFC-12 to HFC-134a designs at Shriram Industries | Individual | ASP | IND | REF | 10 | INV | 09 | N | I | CFC | 0 | 0 | 0 | 0 | 1993-06-01 | 1995-05-01 | 1995-06-01 |  | 1997-12-01 | 1997-07-01 | 685000 | -309549 | 375451 | 375451 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. (Remaining "balance" has been disbursed to FA.) |  |  | 1997-03-01 | INV | 0
FIN | UNIDO | Feasibility study for recovery/recycling of CFC refrigerants | RMP | ASP | IND | REF | 10 | TAS | 05 | A | I |  | 0 | 0 |  |  | 1993-06-01 | 1994-02-01 | 1993-10-01 |  | 1998-06-01 | 1999-08-01 | 55000 | -42920 | 12080 | 12080 | 100% | 0 | 0 |  | 7150 | -5582 | 1568 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | IBRD | Modification of CFC-12 MAC manufacturing for HFC-134a at Subros Ltd. | Individual | ASP | IND | REF | 11 | INV | 12 | N | I | CFC | 0 | 0 | 0 | 0 | 1993-11-01 | 1995-07-01 | 1995-11-01 |  | 1998-11-01 | 2003-05-01 | 1710000 | -55496 | 1654504 | 1654504 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted. |  |  | 1997-03-01 | INV | 0
FIN | IBRD | Conversion of compressor designs for refrigeration and appliances from CFC-12 to HFC-134a at Kirloskar Copeland Ltd. | Individual | ASP | IND | REF | 12 | INV | 15 | N | I | CFC | 0 | 0 | 0 | 0 | 1994-03-01 | 1996-05-01 | 1998-03-01 |  | 1999-03-01 | 1999-11-01 | 547900 | -16905 | 530995 | 530994.85 | 100% | 0.15 | 0.15 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted |  |  | 1999-03-01 | INV | 0
FIN | IBRD | Conversion of CFC-12 open-type compressor designs for use with HCFC-22 refrigerant at Freezeking Industries Pvt., Ltd. | Individual | ASP | IND | REF | 13 | INV | 24 | N | I | CFC | 0 | 0 | 0 | 0 | 1994-07-01 | 1996-03-01 | 1997-07-01 |  | 1999-11-01 | 2000-12-01 | 240500 | -25806 | 214694 | 214694.04 | 100% | -0.04 | -0.04 |  | 0 | 0 | 0 | 0 | 0 | Project completed and PCR submitted |  |  | 1998-07-01 | INV | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Meghdoot Refrigeration Industries | Individual | ASP | IND | REF | 18 | INV | 61 | N | I | CFC | 18 | 18 | 0 | 0 | 1995-11-01 | 1997-12-01 | 1997-05-01 |  | 1999-01-01 | 2000-07-01 | 164590 | -5660 | 158930 | 158929.9 | 100% | 0.1 | 0.1 |  | 21396.7 | -735.8 | 20660.9 | 0 | 0 | Project completed and PCR submitted. |  |  | 1999-05-01 | INV | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at V. Krishna & Co. | Individual | ASP | IND | REF | 18 | INV | 62 | N | I | CFC | 14.8 | 14.8 | 0 | 0 | 1995-11-01 | 1997-12-01 | 1997-05-01 |  | 1999-06-01 | 2001-06-01 | 147020 | -11574 | 135446 | 135446 | 100% | 0 | 0 |  | 19112.6 | -1504.62 | 17607.98 | 0 | 0 | Project completed and PCR submitted |  |  | 1997-08-01 | INV | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at V. Krishna Engineers P. Ltd. | Individual | ASP | IND | REF | 18 | INV | 63 | N | I | CFC | 17 | 17 | 0 | 0 | 1995-11-01 | 1997-12-01 | 1997-05-01 |  | 2001-04-01 | 2003-10-01 | 202790 | -81830 | 120960 | 120960 | 100% | 0 | 0 |  | 26362.7 | -10637.87 | 15725.13 | -0.3 | -0.3 | Project completed. |  |  | 1997-08-01 | INV | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Friz-Tech P. Ltd. | Individual | ASP | IND | REF | 18 | INV | 64 | N | I | CFC | 12 | 11.5 | 0 | 0 | 1995-11-01 | 1997-11-01 | 1997-05-01 |  | 2000-03-01 | 2002-07-01 | 132920 | 0 | 132920 | 132920 | 100% | 0 | 0 |  | 17279.6 | 0 | 17279.6 | 0 | 0 |  |  |  | 1997-08-01 | INV | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Rabi-Run Refrigeration P., Ltd. | Individual | ASP | IND | REF | 19 | INV | 89 | N | I | CFC | 14 | 14 | 0 | 0 | 1996-05-01 | 1997-10-01 | 1997-11-01 |  | 2001-01-01 | 2002-09-01 | 142622 | -2428 | 140194 | 140194.28 | 100% | -0.28 | -0.28 |  | 18541 | -315.64 | 18225.36 | 0 | 0 | PCR to be finalized and submitted in 2003. |  |  | 2000-06-01 | INV | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Seepra Refrigeration P., Ltd. | Individual | ASP | IND | REF | 19 | INV | 90 | N | I | CFC | 15 | 15 | 0 | 0 | 1996-05-01 | 1997-10-01 | 1997-11-01 |  | 1998-08-01 | 1999-12-01 | 171910 | -10400 | 161510 | 161510 | 100% | 0 | 0 |  | 22348 | -1352 | 20996 | 0 | 0 | Complete. |  |  | 1998-02-01 | INV | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Shakti Fabricators | Individual | ASP | IND | REF | 19 | INV | 91 | N | I | CFC | 13.5 | 13.5 | 0 | 0 | 1996-05-01 | 1997-07-01 | 1997-11-01 |  | 2001-11-01 | 2003-10-01 | 159230 | -926 | 158304 | 158304 | 100% | 0 | 0 |  | 20699.9 | -120.42 | 20579.58 | -0.1 | -0.1 | Project completed. |  |  | 1999-06-01 | INV | 0
CLO | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Chandra Frig Co. P., Ltd. | Individual | ASP | IND | REF | 19 | INV | 92 | N | I | CFC | 9.4 | 4.8 | 0 | 0 | 1996-05-01 | 1998-03-01 | 1997-11-01 |  |  | 2004-04-01 | 130984 | -64197 | 66787 | 66787.07 | 100% | -0.07 | -0.07 |  | 17028 | -8346 | 8682.32 | -0.32 | -0.32 | Project cancelled at the 42nd ExCom and balance returned at the 43rd ExCom. Bank has requested FI to examine the SGA to find out appropriate course of action for recuperation of equipment. Process underway. |  |  | 1998-02-01 | INV | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Rockwell Devices P., Ltd. | Individual | ASP | IND | REF | 19 | INV | 93 | N | I | CFC | 18 | 18 | 0 | 0 | 1996-05-01 | 1998-06-01 | 1997-11-01 |  | 1999-07-01 | 2000-09-01 | 181004 | -9611 | 171393 | 171392.74 | 100% | 0.26 | 0.26 |  | 23530.52 | -1249.43 | 22281.09 | 0 | 0 | Project completed and PCR submitted |  |  | 1998-02-01 | INV | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Sethia Appliances P., Ltd. | Individual | ASP | IND | REF | 19 | INV | 94 | N | I | CFC | 16 | 16 | 0 | 0 | 1996-05-01 | 1997-11-01 | 1997-11-01 |  | 1999-06-01 | 2000-08-01 | 173384 | -6586 | 166798 | 166798.3 | 100% | -0.3 | -0.3 |  | 22540 | -856.18 | 21683.82 | 0 | 0 | Project completed and PCR submitted |  |  | 1998-02-01 | INV | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Supercold Refrigeration Systems P. Ltd. | Individual | ASP | IND | REF | 20 | INV | 105 | N | I | CFC | 11 | 11 | 0 | 0 | 1996-10-01 | 2000-12-01 | 1998-04-01 |  | 2001-04-01 | 2002-05-01 | 133770 | -3495 | 130275 | 130275 | 100% | 0 | 0 |  | 17390.1 | -454.35 | 16935.75 | 0 | 0 | Enterprise has submitted the draft PCR which will be sent to the Bank by April 15, 2003. |  |  | 1999-12-01 | INV | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Murali Refrigeration and Engineering Co. | Individual | ASP | IND | REF | 20 | INV | 106 | N | I | CFC | 9 | 9 | 0 | 0 | 1996-10-01 | 1998-03-01 | 1998-04-01 |  | 1999-06-01 | 2000-10-01 | 126485 | -1539 | 124946 | 124945.52 | 100% | 0.48 | 0.48 |  | 16443.05 | -200.07 | 16242.98 | 0 | 0 | Project completed and PCR submitted |  |  |  | INV | 0
FIN | IBRD | Project preparation in the refrigeration sector |  | ASP | IND | REF | 21 | PRP | 108 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1998-06-01 | 1998-06-01 | 243000 | 0 | 243000 | 243000 | 100% | 0 | 0 |  | 31590 | 0 | 31590 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Refrigeration Components and Accessories | Individual | ASP | IND | REF | 22 | INV | 110 | N | I | CFC | 9.5 | 9.5 | 0 | 0 | 1997-05-01 | 2001-08-01 | 1999-06-01 |  | 2004-03-01 | 2005-01-01 | 125370 | -75182.45 | 50187.55 | 50187.55 | 100% | 0 | 0 |  | 16298.1 | -9773.72 | 6524.38 | 0 | 0 | Project financially completed and balance funds returned. |  |  | 2000-12-01 | INV | 0
FIN | IBRD | Conversion to non-CFC technology in the production of MAC systems at Pranav Vikas India Ltd. | Individual | ASP | IND | REF | 22 | INV | 116 | N | I | CFC | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-01-01 | 1999-06-01 |  | 2002-03-01 | 2002-12-01 | 944914 | -90669 | 854245 | 854245 | 100% | 0 | 0 |  | 122838.82 | -11786.97 | 111051.85 | 0 | 0 | Draft PCR submitted to ExCom Sep. 02. PCR to be finalized and resubmitted in 2003. |  |  |  | INV | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Standard Refrigeration Appliances | Individual | ASP | IND | REF | 22 | INV | 120 | N | I | CFC | 18.8 | 18.8 | 0 | 0 | 1997-05-01 | 1998-05-01 | 1998-11-01 |  | 2000-08-01 | 2000-12-01 | 170180 | -166 | 170014 | 170014 | 100% | 0 | 0 |  | 22123.4 | -21.58 | 22101.82 | 0 | 0 | Project completed and PCR submitted |  |  |  | INV | 0
FIN | IBRD | Conversion to non-CFC technology in the production of MAC systems at Sanden Vikas India Ltd. | Individual | ASP | IND | REF | 22 | INV | 121 | N | I | CFC | 8.36 | 8.36 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 2002-03-01 | 2002-04-01 | 490820 | -111557 | 379263 | 379263 | 100% | 0 | 0 |  | 63806.6 | -14502.41 | 49304.19 | 0 | 0 | Draft PCR submitted to the ExCom Sep. 02. PCR to be finalized and resubmitted in 2003. |  |  |  | INV | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Sheetal Engineering Works P. Ltd. | Individual | ASP | IND | REF | 22 | INV | 122 | N | I | CFC | 8.7 | 8.7 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1999-06-01 |  | 1999-02-01 | 2001-06-01 | 127630 | -28297 | 99333 | 99333 | 100% | 0 | 0 |  | 16591.9 | -3678.61 | 12913.29 | 0 | 0 | Project completed. PCR will be submitted January 2001. |  |  |  | INV | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Hindustan Refrigeration Industries | Individual | ASP | IND | REF | 22 | INV | 123 | N | I | CFC | 10.1 | 10.1 | 0 | 0 | 1997-05-01 | 2002-12-01 | 1999-06-01 |  | 2004-03-01 | 2005-01-01 | 132320 | -81327 | 50993 | 50993 | 100% | 0 | 0 |  | 17201.6 | -10572.51 | 6629.09 | 0 | 0 | Project financially completed and balance funds returned. |  |  |  | INV | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Refrigerators and Home Appliances P. Ltd. | Individual | ASP | IND | REF | 22 | INV | 124 | N | I | CFC | 11.3 | 11.3 | 0 | 0 | 1997-05-01 | 2001-08-01 | 1999-06-01 |  | 2004-03-01 | 2005-01-01 | 147300 | -95904.45 | 51395.55 | 51395.55 | 100% | 0 | 0 |  | 19149 | -12467.58 | 6681.42 | 0 | 0 | Project financially completed and balance funds returned. |  |  | 2000-12-01 | INV | 0
FIN | IBRD | Elimination of CFCs in the manufacture of domestic refrigerators at Maharaja International Ltd. | Individual | ASP | IND | REF | 22 | INV | 125 | N | I | CFC | 59.8 | 59.8 | 0 | 0 | 1997-05-01 | 2002-12-01 | 1999-11-01 |  | 2004-01-01 | 2005-01-01 | 510000 | -261775.31 | 248224.69 | 248224.69 | 100% | 0 | 0 |  | 66300 | -34030.79 | 32269.21 | 0 | 0 | Project financially completed and balance funds returned. PCR submitted to ExCom. |  |  | 2001-12-01 | INV | 0
FIN | IBRD | Conversion of domestic refrigerator manufacture to cyclopentane blowing agent and either R-600a or HCF-134a refrigerant at Voltas Ltd. | Individual | ASP | IND | REF | 22 | INV | 126 | N | I | CFC | 379.83 | 379.83 | 0 | 0 | 1997-05-01 | 2000-07-01 | 2001-12-01 |  | 2003-11-01 | 2005-01-01 | 2724378 | -1093985 | 1630393 | 1630393 | 100% | 0 | 0 |  | 354169.14 | -142218 | 211951 | 0.14 | 0.14 | Project financially completed and balance funds returned. |  |  | 1999-11-01 | INV | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Polar Enterprises | Individual | ASP | IND | REF | 22 | INV | 131 | N | I | CFC | 10.8 | 10.8 | 0 | 0 | 1997-05-01 | 1998-07-01 | 1999-06-01 |  | 1999-09-01 | 2001-07-01 | 138190 | -189 | 138001 | 138001 | 100% | 0 | 0 |  | 17964.7 | -24.57 | 17940.13 | 0 | 0 | Project completed and PCR submitted |  |  |  | INV | 0
FIN | IBRD | Conversion of refrigerator manufacture to cyclopentane foam blowing agent and to HCF-134a refrigerant at Videocon Appliances Ltd. | Individual | ASP | IND | REF | 22 | INV | 134 | N | I | CFC | 351.7 | 351.7 | 0 | 0 | 1997-05-01 | 1999-10-01 | 1999-11-01 |  | 2001-12-01 | 2002-08-01 | 1835115 | 524053.41 | 2359168.41 | 2359168.41 | 100% | 0 | 0 |  | 238564.95 | 61500.14 | 300065.09 | 0 | 0 | Project physically completed in 2001, however, was not reported as such by FI in time for the 2001 progress report. Subsequent draft PCR has confirmed correct date of completion. |  |  | 1999-11-01 | INV | 0
FIN | IBRD | Preparation of investment projects for submission in 1997 and 1998 |  | ASP | IND | REF | 22 | PRP | 127 | A | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-03-31 | 1997-12-01 |  | 1998-12-01 | 1998-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Aarkay Industries | Individual | ASP | IND | REF | 23 | INV | 144 | N | I | CFC | 19.8 | 19.8 | 0 | 0 | 1997-11-01 | 1999-07-01 | 1999-06-01 |  | 2000-09-01 | 2001-01-01 | 135798 | 15128 | 150926 | 150926 | 100% | 0 | 0 |  | 17654 | 1967 | 19621 | 0 | 0 | PCR is being finalized for submission in 2003. |  |  |  | INV | 0
FIN | IBRD | Eliminationof CFCs in the manufacture of commercial refrigeration equipment at Saikrupa Industries | Individual | ASP | IND | REF | 23 | INV | 145 | N | I | CFC | 14.8 | 14.8 | 0 | 0 | 1997-11-01 | 1999-02-01 | 1999-06-01 |  | 2000-09-01 | 2001-01-01 | 125618 | 10524 | 136142 | 136142 | 100% | 0 | 0 |  | 16330.34 | 1368.12 | 17698.46 | 0 | 0 | PCR is being finalized for submission in 2003. |  |  |  | INV | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Sarkar Refrigeration Industries | Individual | ASP | IND | REF | 23 | INV | 152 | N | I | CFC | 12 | 12 | 0 | 0 | 1997-11-01 | 2000-02-01 | 1999-06-01 |  | 2000-11-01 | 2002-06-01 | 117100 | -1955 | 115145 | 115145 | 100% | 0 | 0 |  | 15223 | -287 | 14936 | 0 | 0 | PCR is being finalized for submission in 2003. |  |  | 2000-09-01 | INV | 0
FIN | IBRD | Eliminationof CFCs in the manufacture of commercial refrigeration equipment at Sidwal Refrigeration Industries P. Ltd. | Individual | ASP | IND | REF | 23 | INV | 160 | N | I | CFC | 11.7 | 14.1 | 0 | 0 | 1997-11-01 | 1999-10-01 | 1999-06-01 |  | 2000-09-01 | 2002-05-01 | 169744 | 5038 | 174782 | 174782 | 100% | 0 | 0 |  | 22067 | 655.32 | 22722.32 | 0 | 0 |  |  |  |  | INV | 0
FIN | UNIDO | Preparation of an investment project for phasing out ODS in the refrigeration sector (project under identification | Individual | ASP | IND | REF | 23 | PRP | 159 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-06-01 | 1998-03-01 |  | 2000-12-01 | 2002-05-01 | 25000 | 24369 | 49369 | 49369.43 | 100% | -0.43 | 0 |  | 3250 | 3158 | 6408 | 0 | 0 | FIN
FIN | UNDP | Project preparation for 5 projects in commercial refrigeration subsector | Individual | ASP | IND | REF | 24 | PRP | 169 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 1998-12-01 |  | 2000-12-01 | 2001-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Sandeep Refrigeration | Individual | ASP | IND | REF | 25 | INV | 180 | N | I | CFC | 9.9 | 9.9 | 0 | 0 | 1998-07-01 | 1999-08-01 | 2000-08-01 |  | 2000-08-01 | 2001-04-01 | 107684 | -773 | 106911 | 106911 | 100% | 0 | 0 |  | 13998.92 | -100.49 | 13898.43 | 0 | 0 | Project completed and PCR submitted |  |  |  | INV | 0
CLO | IBRD | Elimination of CFC-11 and CFC-12 converting to HCFC-141b and HFC-134a in the manufacture of commercial refrigeration equipment at Prashant Refrigeration Appliances | Individual | ASP | IND | REF | 25 | INV | 182 | N | I |  | 0 | 0 | 0 | 0 | 1998-07-01 |  | 2000-08-01 |  |  | 1999-12-01 | 104058 | -104058 | 0 | 0 | #DIV/0! | 0 | 0 |  | 13527.54 | -13528 | 0 | -0.46 | -0.46 | Project has been cancelled. |  |  |  | INV | 0
FIN | IBRD | Elimination of CFC-11 and CFC-12 by converting to HCFC-141b and HFC-134a in the manufacture of domestic refrigerators at BPL Refrigeration Ltd. | Individual | ASP | IND | REF | 25 | INV | 183 | N | I | CFC | 136 | 136 | 0 | 0 | 1998-07-01 | 2002-12-01 | 2001-08-01 |  | 2002-12-01 | 2005-01-01 | 722906 | 302123 | 1025029 | 1025029 | 100% | 0 | 0 |  | 93977.78 | 35611.19 | 129588.97 | 0 | 0 | Project financially completed and balance funds returned. PCR submitted to ExCom. |  |  |  | INV | 0
FIN | IBRD | Elimination of CFCs in the manufacture of domestic refrigerators at Whirlpool of India Ltd. | Individual | ASP | IND | REF | 27 | INV | 204 | N | I | CFC | 200.6 | 200.6 | 0 | 0 | 1999-03-01 | 2002-12-01 | 2002-04-01 |  | 2002-12-01 | 2005-01-01 | 675165 | -276756 | 398409 | 398409 | 100% | 0 | 0 |  | 84268.15 | -39407.54 | 44860.61 | 0 | 0 | Project financially completed and balance funds returned. PCR submitted to ExCom. |  |  |  | INV | 0
FIN | UNDP | Preparation of five projects in the commercial refrigeration subsector | Individual | ASP | IND | REF | 27 | PRP | 200 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-12-01 | 2004-01-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Completed in 2000. Financially completed in 2004. |  | 1999 |  | Investment
FIN | IBRD | Conversion of domestic refrigerator manufacture to either R600a or HFC-134a refrigerant at Godrej - GE Appliances Ltd. (GGEAL) | Individual | ASP | IND | REF | 30 | INV | 337 | N | I | CFC | 71.7 | 71.7 | 0 | 0 | 2000-03-01 | 2003-07-01 | 2002-04-01 |  | 2002-12-01 | 2005-01-01 | 2050000 | -250684.64 | 1799315.36 | 1799315.36 | 100% | 0 | 0 |  | 235500 | -28798.16 | 206701.84 | 0 | 0 | Project financially completed and balance funds returned. PCR submitted to ExCom. |  |  |  | INV | 0
FIN | UNIDO | Preparation of an investment project in the commercial refrigeration sector | Individual | ASP | IND | REF | 30 | PRP | 248 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2001-07-01 | 2001-04-01 |  | 2002-06-01 | 2003-05-01 | 20000 | -703 | 19297 | 19297.01 | 100% | -0.01 | 0 |  | 2600 | -95 | 2505 | 0 | 0 | FIN
CLO | UNDP | Preparation of 2 projects in the commercial refrigeration subsector | Individual | ASP | IND | REF | 30 | PRP | 254 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 |  | 2001-04-01 |  |  | 2003-01-01 | 10000 | -10000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 1300 | -1300 | 0 | 0 | 0 | Canceled in 2000. Financially Completed in 2003. |  | 2000 |  | Investment
FIN | IBRD | Preparation of projects in the industrial and chiller refrigeration subsectors |  | ASP | IND | REF | 30 | PRP | 255 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2001-12-01 |  | 2001-12-01 | 2001-12-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 |  | 19500 | 0 | 19500 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Fedders Lloyd Corporation Ltd. | Individual | ASP | IND | REF | 31 | INV | 257 | A | I | CFC | 21.2 | 21.2 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2001-11-01 | 2003-04-01 | 257428 | -2616 | 254812 | 254812 | 100% | 0 | 0 | 0 | 33465.64 | -340.08 | 33125.56 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Sandlas Air-Con Systems P. Ltd. | Individual | ASP | IND | REF | 32 | INV | 282 | A | I | CFC | 23.3 | 23.3 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2003-12-01 | 2005-09-01 | 228517 | -9527 | 218990 | 218990 | 100% | 0 | 0 | 0 | 29707.21 | -1239 | 28468.21 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at nine enterprises | Individual | ASP | IND | REF | 32 | INV | 286 | A | I | CFC | 53.5 | 53.5 | 0 | 0 | 2000-12-01 | 2001-11-01 | 2004-01-01 |  | 2003-11-01 | 2005-10-01 | 789425 | -20719 | 768706 | 768706 | 100% | 0 | 0 | 0 | 96836.75 | -2279 | 94557.75 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNIDO | Umbrella project for the conversion of three commercial refrigeration enterprises in New Delhi (Gaurav Controls, Thermoking and Western Engineering) | Individual | ASP | IND | REF | 32 | INV | 290 | A | I | CFC | 27.3 | 27.3 |  |  | 2000-12-01 | 2001-01-01 | 2003-02-01 |  | 2004-08-01 | 2005-09-01 | 328894 | -49284 | 279610 | 279609.93 | 100% | 0.07 | 0 |  | 42756 | -6464 | 36292 | 0 | 0 | FIN
FIN | UNDP | Technical assistance to Ozone Cell, MOEF during the preparation of a refrigeration and air conditioning servicing sector strategy | RMP-Component | ASP | IND | REF | 32 | TAS | 279 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-11-01 | 2003-01-01 |  | 2003-07-01 | 2005-09-01 | 30000 | -3675 | 26325 | 26325 | 100% | 0 | 0 | 0 | 3900 | -478 | 3422 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Non-Investment
FIN | Germany | Preparation of a national strategy to reduce and eliminate the use of CFC refrigerants in the servicing sector | Individual | ASP | IND | REF | 32 | TAS | 288 | A | I |  | 0 |  | 0 |  | 2000-12-01 | 2001-01-01 | 2003-01-01 |  | 2004-04-01 | 2004-04-01 | 240200 | 0 | 240200 | 240200 | 100% | 0 | 0 | 0 | 31226 | 0 | 31226 | 0 | 0 | India's National CFC consumption Phase-Out Plan with special refeence to the Refrigeration Service Sector was approved at the 42nd ExCom (IND/REF/42/INV/369).
FIN | Switzerland | Preparation of a national strategy to reduce and eliminate the use of CFC refrigerants in the servicing sector | Individual | ASP | IND | REF | 32 | TAS | 292 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-10-01 | 2003-01-01 |  | 2003-04-01 | 2003-04-01 | 70796 | 0 | 70796 | 70796 | 100% | 0 | 0 | 0 | 9204 | 0 | 9204 | 0 | 0 |  |  | 2000
FIN | UNDP | Project preparation in the commercial refrigeration sector | Individual | ASP | IND | REF | 33 | PRP | 293 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | IBRD | Project preparation in the MAC sector |  | ASP | IND | REF | 33 | PRP | 300 | A | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2002-09-01 | 2001-12-01 |  | 2002-09-01 | 2002-09-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 | Project submitted to and approved at the 38th ExCom. |  |  |  | Non-INV | 0
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a in the manufacture of commercial refrigeration equipment at 5 enterprises (Ahmedabad Low Temp, Kalkura Cooling Machines, Mechelec Steel Products, Polfrost Aircon and Shri Ambica Engineering) | Individual | ASP | IND | REF | 34 | INV | 323 | A | I | CFC | 22 | 22 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2004-08-01 |  | 2003-11-01 | 2005-11-01 | 323627 | -7398 | 316229 | 316229 | 100% | 0 | 0 | 0 | 42071.51 | -962 | 41109.51 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at fourteen enterprises | Individual | ASP | IND | REF | 35 | INV | 339 | A | I | CFC | 68 | 68 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-01-01 |  | 2003-11-01 | 2005-10-01 | 960097 | -5024 | 955073 | 955073 | 100% | 0 | 0 | 0 | 115610.7 | -552.97 | 115057.73 | -4.5739e-05 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Ice-Make Refrigeration | Individual | ASP | IND | REF | 35 | INV | 340 | A | I | CFC | 12.4 | 12.4 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2004-07-01 |  | 2003-11-01 | 2005-12-01 | 157305 | -1232 | 156073 | 156073 | 100% | 0 | 0 | 0 | 20449.65 | -160 | 20289.65 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Konark Refrigeration Appliances P., Ltd. | Individual | ASP | IND | REF | 35 | INV | 341 | A | I | CFC | 13.1 | 13.1 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2004-07-01 |  | 2003-11-01 | 2005-09-01 | 182684 | -1327 | 181357 | 181357 | 100% | 0 | 0 | 0 | 23748.92 | -173 | 23575.92 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at nine enterprises | Individual | ASP | IND | REF | 35 | INV | 342 | A | I | CFC | 56.5 | 56.5 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2004-07-01 |  | 2003-11-01 | 2007-03-01 | 726448 | -9086 | 717362 | 717362 | 100% | 0 | 0 | 0 | 89909.28 | -999.18 | 88910.1 | 0 | 0 | Completed in 2003. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Project preparation in the manufacturing refrigeration (terminal phase-out) sector | Individual | ASP | IND | REF | 36 | PRP | 344 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2005-11-01 | 20000 | -2741 | 17259 | 17259 | 100% | 0 | 0 | 0 | 2600 | -356.33 | 2243.67 | 0 | 0 | Completed in 2002. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNIDO | Preparation of an umbrella investment project in the commercial refrigeration sector | Individual | ASP | IND | REF | 36 | PRP | 346 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-08-01 | 2003-04-01 |  | 2003-09-01 | 2004-09-01 | 30000 | -4889 | 25111 | 25111.42 | 100% | -0.42 | 0 |  | 3900 | -641 | 3259 | 0 | 0 | FIN |  |  |  | INV
FIN | UNDP | Plan for phase out of CFCs in the refrigeration manufacturing sector (first tranche) | Multi-Year | ASP | IND | REF | 38 | INV | 356 | N | I | CFC | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-11-01 | 2004-11-01 |  | 2006-07-01 | 2013-02-01 | 2000000 | 0 | 2000000 | 2000000 | 100% | 0 | 0 | 0 | 172971 | 0 | 172971 | 0 | 0 | Financially completed in 2013. |  | 2002 |  | Investment
FIN | IBRD | Complete phase out of CFC-12 to non-ODS technology (HFC-134a) for manufacturing of mobile air-conditioners (MACs) at Subros Limited (phase II) | Individual | ASP | IND | REF | 38 | INV | 357 | N | I | CFC | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-11-01 | 2003-11-01 |  | 2003-11-01 | 2005-01-01 | 1181693 | -83277 | 1098416 | 1098416 | 100% | 0 | 0 |  | 222895 | -15708 | 207187.01 | -0.01 | -0.01 | Project financially completed and balance funds returned. PCR submitted to ExCom. |  |  |  | INV | 0
FIN | UNIDO | Plan for phase-out of CFCs in the refrigeration (manufacturing) sector | Multi-Year | ASP | IND | REF | 38 | INV | 359 | A | I | CFC | 40 | 59 |  |  | 2002-11-01 | 2003-02-01 | 2004-12-01 |  | 2006-11-01 | 2007-12-01 | 500000 | 0 | 500000 | 499999.63 | 100% | 0.37 | 0 |  | 65000 | 0 | 65000 | 0 | 0 | FIN |  |  |  | INV
FIN | UNDP | Plan for phase-out of CFCs in the refrigeration manufacturing sector (second tranche) | Multi-Year | ASP | IND | REF | 41 | INV | 364 | N | I | CFC | 0 | 0 | 0 | 0 | 2003-12-01 | 2006-03-01 | 2004-12-01 |  | 2006-12-01 | 2013-02-01 | 476536 | 0 | 476536 | 476536 | 100% | 0 | 0 | 0 | 43243 | 0 | 43243 | 0 | 0 | Financially completed in 2013. |  | 2003 | 2006-12-01 | Investment
FIN | UNIDO | Plan for phase-out of CFCs in the refrigeration manufacturing sector (second tranche) | Multi-Year | ASP | IND | REF | 41 | INV | 366 | A | I | CFC | 67 | 77 |  |  | 2003-12-01 | 2006-10-01 | 2005-12-01 |  | 2007-03-01 | 2009-12-01 | 173200 | -35 | 173165 | 173164.63 | 100% | 0.37 | 0 |  | 19052 | -4 | 19048 | 0 | 0 | FIN |  |  |  | INV
FIN | Germany | National CFC consumption phase-out plan focussing on the refrigeration service sector: 2004 work programme | Multi-Year | ASP | IND | REF | 42 | INV | 369 | A | I | CTC | 0 |  | 0 |  | 2004-04-01 | 2004-06-01 | 2005-04-01 |  | 2006-04-01 | 2006-04-01 | 414370 | 0 | 414370 | 414370 | 100% | 0 | 0 | 0 | 53868 | 0 | 53868 | 0 | 0 | The project infrastructure has been successfully established and all activites as per the the annual working plan have been accomplished.
FIN | Switzerland | National CFC consumption phase-out plan focussing on the refrigeration service sector: 2004 work programme | Multi-Year | ASP | IND | REF | 42 | INV | 370 | A | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-09-01 | 2005-04-01 |  | 2005-03-01 | 2005-03-01 | 353020 | 0 | 353020 | 353020 | 100% | 0 | 0 | 0 | 45893 | 0 | 45893 | 0 | 0 | * Consumption reporting by Lead Agency (GTZ) | Report on annual work plan 2004: Four new training cells have been established and a Training of Trainers Wokshop was held for 12 particpants. With this, 13 training cells provided in 2004 standard training programs for refrigeration service technicians. | 2004 |  | 2004
FIN | UNDP | National CFC consumption phase-out plan focussing on the refrigeration service sector: 2004 work programme | Multi-Year | ASP | IND | REF | 42 | INV | 371 | N | I | CFC | 0 | 0 | 0 | 0 | 2004-04-01 | 2005-11-01 | 2005-04-01 |  | 2006-06-01 | 2013-02-01 | 277200 | 0 | 277200 | 277200 | 100% | 0 | 0 | 0 | 20790 | 0 | 20790 | 0 | 0 | Financially completed in 2013. |  | 2004 |  | Investment
FIN | UNEP | National CFC consumption phase-out plan focussing on the refrigeration service sector: 2004 work programme | Multi-year | ASP | IND | REF | 42 | TAS | 377 | A | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-12-01 | 2005-04-01 |  | 2005-04-01 | 2007-06-01 | 256300 | 0 | 256300 | 256300 | 100% | 0 | 0 |  | 33319 | 0 | 33319 | 0 | 0
FIN | UNDP | National CFC consumption phase-out plan focussing on the refrigeration service sector: 2005 work programme | Multi-Year | ASP | IND | REF | 44 | INV | 379 | N | I | CFC | 0 | 0 | 0 | 0 | 2004-12-01 | 2006-03-01 | 2005-12-01 |  | 2006-06-01 | 2013-02-01 | 277050 | 0 | 277050 | 277050 | 100% | 0 | 0 | 0 | 20779 | 0 | 20779 | 0 | 0 | Financially completed in 2013. |  | 2004 |  | Investment
FIN | Germany | National CFC consumption phase-out plan focussing on the refrigeration service sector: 2005 work programme | Multi-Year | ASP | IND | REF | 44 | INV | 380 | A | I | CFC | 0 |  | 0 |  | 2004-12-01 | 2006-01-01 | 2005-12-01 |  | 2006-04-01 | 2006-04-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | All activities as per the annual working plan have been accomplished.
FIN | Switzerland | National CFC consumption phase-out plan focussing on the refrigeration service sector: 2005 work programme | Multi-Year | ASP | IND | REF | 44 | INV | 381 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-09-01 | 2005-12-01 |  | 2006-03-01 | 2006-03-01 | 256650 | 0 | 256650 | 256650 | 100% | 0 | 0 | 0 | 33365 | 0 | 33365 | 0 | 0 | * Consumption reporting by Lead Agency (GTZ) | Report on annual work plan 2005: In the operational year 05-06 the following number of technicians are trained: a) in Standard RSE programs: 1685 participants b) Mobile Air-Conditioning programs 130 participants c) Open Type compressor programs: 64 partic | 2005 |  | 2005
FIN | UNDP | Plan for phase-out of CFCs in the refrigeration manufacturing sector (third tranche) | Multi-Year | ASP | IND | REF | 44 | INV | 383 | N | I | CFC | 141 | 141 | 0 | 0 | 2004-12-01 | 2006-01-01 | 2006-12-01 |  | 2006-12-01 | 2012-11-01 | 250000 | 0 | 250000 | 250000 | 100% | 0 | 0 | 0 | 21621 | 0 | 21621 | 0 | 0 | Completed in 2006. |  | 2004 |  | Investment
FIN | UNEP | National CFC consumption phase-out plan focussing on the refrigeration service sector: 2005 work programme | Multi-year | ASP | IND | REF | 44 | TAS | 382 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-09-01 | 2005-12-01 |  | 2006-04-01 | 2009-04-01 | 256300 | 0 | 256300 | 256300 | 100% | 0 | 0 |  | 33319 | 0 | 33319 | 0 | 0
FIN | Germany | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2006 work programme | Multi-Year | ASP | IND | REF | 47 | INV | 393 | A | I | CFC | 0 |  | 0 |  | 2005-11-01 | 2006-01-01 | 2006-12-01 |  | 2007-04-01 | 2007-04-01 | 105090 | 0 | 105090 | 105090 | 100% | 0 | 0 | 0 | 13662 | 0 | 13662 | 0 | 0 | All activities as per the annual working plan have been accomplished.
FIN | Switzerland | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2006 work programme | Multi-Year | ASP | IND | REF | 47 | INV | 394 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-09-01 | 2006-12-01 |  | 2007-03-01 | 2007-03-01 | 256650 | 0 | 256650 | 256650 | 100% | 0 | 0 | 0 | 33365 | 0 | 33365 | 0 | 0 | * Consumption reporting by Lead Agency (GTZ) | Report on annual work plan 2006: In the operational year 06-07 the following number of technicians are trained: a) in Standard RSE programs: 1810 participants b) Mobile Air-Conditioning programs 238 participants c) Open Type compressor programs: 55 partic | 2006 |  | 2006
FIN | UNDP | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2006 work programme | Multi-Year | ASP | IND | REF | 47 | INV | 395 | N | I | CFC | 428 | 428 | 0 | 0 | 2005-11-01 | 2007-01-01 | 2006-12-01 |  | 2009-12-01 | 2012-11-01 | 1332377 | -134566.94 | 1197810.06 | 1197810 | 100% | 0.06 | 0 | 0 | 112417 | -11353.85 | 101063.1426 | 0.0073624 | 0 | Financially completed in 2012. | Financially completed in 2012. | 2005 |  | Investment
FIN | UNEP | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2006 work programme | Multi-year | ASP | IND | REF | 47 | TAS | 396 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-05-01 | 2006-12-01 |  | 2007-04-01 | 2010-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 |  | 11050 | 0 | 11050 | 0 | 0
FIN | UNDP | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2007 work programme | Multi-Year | ASP | IND | REF | 50 | INV | 403 | N | I | CFC | 639 | 639 | 0 | 0 | 2006-11-01 | 2012-02-01 | 2008-06-01 |  | 2013-12-01 | 2014-06-01 | 167860 | -67899 | 99961 | 99961 | 100% | 0 | 0 | 0 | 12590 | -5092.63 | 7497.37 | 0 | 0 | Financially completed in 2014. | Completed in 2013. | 2006 |  | Investment
FIN | Germany | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2007 work programme | Multi-Year | ASP | IND | REF | 50 | INV | 404 | A | I | CFC | 158 | 358 | 0 |  | 2006-11-01 | 2007-01-01 | 2007-11-01 |  | 2008-04-01 | 2009-04-01 | 436200 | 0 | 436200 | 436200 | 100% | 0 | 0 | 0 | 56706 | 0 | 56706 | 0 | 0 | All activities as per the annual working plan have been accomplished.
FIN | Switzerland | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2007 work programme | Multi-Year | ASP | IND | REF | 50 | INV | 406 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-09-01 | 2007-11-01 |  | 2008-03-01 | 2008-03-01 | 367140 | 0 | 367140 | 367140 | 100% | 0 | 0 | 0 | 47728 | 0 | 47728 | 0 | 0 | * Consumption reporting by Lead Agency (GTZ) | Report on annual work plan 2007: In the operational year 07-08 the following number of technicians are trained: a) in Standard RSE programs: 1880 participants b) Mobile Air-Conditioning programs 275 participants c) Open Type compressor programs: 113 partic. | 2007 |  | 2007
FIN | UNEP | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2007 work programme | Multi-year | ASP | IND | REF | 50 | TAS | 405 | A | I | CFC | 101.5 | 0 | 0 | 0 | 2006-11-01 | 2007-03-01 | 2007-11-01 |  | 2008-04-01 | 2010-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 |  | 11050 | 0 | 11050 | 0 | 0
FIN | Switzerland | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2008 work programme | Multi-Year | ASP | IND | REF | 54 | INV | 418 | A | I |  | 211.1 | 0 | 0 |  | 2008-04-01 | 2008-09-01 | 2009-03-01 |  | 2010-03-01 | 2010-03-01 | 81141 | 0 | 81141 | 81141 | 100% | 0 |  |  | 10548 | 0 | 10548 | 0 |  | * Consumption reporting by Lead Agency (GTZ) | Report on annual work plan 2008: In the operational year 08-09 the following number of technicians are trained: a) in Standard RSE programs: 1716 participants | 2008 |  | 2008
FIN | UNDP | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2008 work programme | Multi-Year | ASP | IND | REF | 54 | INV | 419 | N | I | CFC | 219.1 | 219.1 | 0 | 0 | 2008-04-01 |  | 2010-03-01 |  | 2012-11-01 | 2013-02-01 | 47881 | -47881 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 3591 | -3591 | 0 | 0 | 0 | Financially completed in 2013. | Completed in 2012. Remaining invoices to be settled in 2013. | 2008 |  | Investment
FIN | Germany | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2008 work programme | Multi-Year | ASP | IND | REF | 54 | INV | 421 | A | I | CFC | 158 | 158 | 0 |  | 2008-04-01 | 2008-07-01 | 2009-03-01 |  | 2009-12-01 | 2009-12-01 | 101078 | 0 | 101078 | 101078 | 100% | 0 | 0 | 0 | 13140 | 0 | 13140 | 0 | 0 | All activities as per the annual working plan have been accomplished. PCR is under preperation.
FIN | UNEP | National CFC consumption phase-out plan focusing on the refrigeration service sector: 2008 work programme | Multi-year | ASP | IND | REF | 54 | TAS | 420 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-06-01 | 2009-03-01 |  | 2011-01-01 | 2012-01-01 | 19900 | 0 | 19900 | 19900 | 100% | 0 | 0 |  | 2587 | 0 | 2587 | 0 | 0
ONG | UNDP | Preparation for HCFC phase-out investment activities (stage II) (refrigeration sector) | Individual | ASP | IND | REF | 72 | PRP | 453 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 | 2015-03-01 | 2016-05-01 | 2017-06-01 |  |  | 120000 | 0 | 120000 | 69522 | 57.94% | 50478 | 40000 | 20191.2 | 8400 | 0 | 4866.54 | 3533.46 | 2800 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Survery of enterprises in RAC sector was completed. Sectoral data was analysed and HPMP II Plan prepared and approved at the 77th ExCom. Prodoc signed (actual/planned, yes/no and date):LoA signed Nov 2015 Missions undertaken (actual/planned):3 TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: signed earlier First disbursement date (actual/planned): 42339Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | The process for selection of agency for verification of enterpises is initiated. |  |  | Non-Investment
ONG | UNDP | Preparation for HCFC phase-out investment activities (stage II) (air-conditioning sector) | Individual | ASP | IND | REF | 72 | PRP | 459 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 | 2015-03-01 | 2016-05-01 | 2017-06-01 |  |  | 120000 | 0 | 120000 | 48055.86 | 40.05% | 71944.14 | 7383.26 | 28777.656 | 8400 | 0 | 3363.9102 | 5036.0898 | 516.8282 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Survery of enterprises in RAC sector was completed. Sectoral data was analysed. HPMP Stage II Plan submitted and approved at 77th ExCom. Prodoc signed (actual/planned, yes/no and date):Letter of Authorisation sent 6 February 2015 Missions undertaken (actual/planned):3 TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: signed earlier First disbursement date (actual/planned): 42278Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | The process for selection of agency for verification of enterpises is initiated. |  |  | Non-Investment
FIN | UNDP | Institutional strengthening | Individual | ASP | IND | SEV | 08 | INS | 02 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1994-06-01 | 1995-10-01 |  | 1996-12-01 | 1999-12-01 | 430600 | -1671 | 428929 | 428929 | 100% | 0 | 0 | 0 | 55978 | -217.44 | 55760.56 | 0 | 0 | Completed in 1996. Financially completed in 1999. |  | 1992 |  | Non-Investment
FIN | UNDP | Assistance in project preparation in all sectors | Individual | ASP | IND | SEV | 08 | PRP | 01 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1992-11-01 | 1993-10-01 |  | 1994-03-01 | 1997-12-01 | 100000 | -18339 | 81661 | 81661 | 100% | 0 | 0 | 0 | 13000 | -2384.07 | 10615.93 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1992 |  | Investment
FIN | UNDP | Country programme preparation | Individual | ASP | IND | SEV | 09 | CPG | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1993-11-01 | 1997-12-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 26000 | 0 | 26000 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1993 |  | Non-Investment
FIN | IBRD | User-sector pre-investment studies |  | ASP | IND | SEV | 09 | PRP | 04 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 400000 | 11292 | 411292 | 411292 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNIDO | Project formulation for phasing out ODS in the unorganized sector | Individual | ASP | IND | SEV | 10 | PRP | 06 | A | I |  | 0 | 0 |  |  | 1993-06-01 | 1994-05-01 | 1993-10-01 |  | 1999-12-01 | 2000-09-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 |  | 7150 | 0 | 7150 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNDP | Survey of ODS use in the small scale (including tiny) and informal sectors, data base generation and ODS transition management planning | Individual | ASP | IND | SEV | 11 | TAS | 11 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-11-01 | 1994-05-01 |  | 1996-12-01 | 2001-12-01 | 120000 | -11230 | 108770 | 108770 | 100% | 0 | 0 | 0 | 15600 | -1460.13 | 14139.87 | 0 | 0 | Completed in 1996. Financially completed in 2001. |  | 1993 |  | Non-Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | IND | SEV | 12 | PRP | 19 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-03-01 |  | 1995-12-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Investment
FIN | IBRD | Preparation of investment projects (1994) |  | ASP | IND | SEV | 12 | PRP | 20 | N | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-12-31 | 1994-12-01 |  | 1996-12-01 | 1996-12-01 | 430000 | -241165 | 188835 | 188835 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects for India ODS II (1994) |  | ASP | IND | SEV | 12 | PRP | 21 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 70837 | -6037 | 64800 | 64800 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. |  |  |  | Non-INV | 0
FIN | IBRD | Training of the Financial Intermediary on Multilateral Fund and World Bank project processing procedures | Individual | ASP | IND | SEV | 12 | TRA | 22 | N | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-03-01 | 1995-03-01 |  | 1995-03-01 | 1995-03-01 | 345000 | -239292 | 105708 | 105708 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation advance of $345,000 to IDBI has been cleared by the Bank to support the preparation of subprojects to be processed thru the umbrella grant agreement. |  |  |  | Non-INV | 0
FIN | Canada | Initiative to help phase out the release of ODS by Asian SMEs | Individual | ASP | IND | SEV | 15 | TAS | 31 | A | I |  | 0 |  | 0 |  | 1994-12-01 |  | 1995-12-01 |  | 1996-02-01 | 1996-02-01 | 109780 | 0 | 109780 | 109780 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1994 | 2000-01-01 | Non-Inv.
CLO | IBRD | Preparation/supervision of investment projects (1995) |  | ASP | IND | SEV | 16 | PRP | 142 | N | I |  | 0 | 0 | 0 | 0 | 1995-03-01 |  | 1995-12-01 |  |  | 1995-12-01 | 70000 | -70000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Closed. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation/supervision of investment projects ODS I (1995) |  | ASP | IND | SEV | 16 | PRP | 32 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 24065 | 0 | 24065 | 24065 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation/supervision of investment projects ODS II (1995) |  | ASP | IND | SEV | 16 | PRP | 33 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 355246 | 0 | 355246 | 355246 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. |  |  |  | Non-INV | 0
FIN | UNDP | Project preparation assistance | Individual | ASP | IND | SEV | 18 | PRP | 67 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-11-01 | 2002-05-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1996. Financially completed in 2002. |  | 1995 |  | Investment
FIN | IBRD | Project preparation |  | ASP | IND | SEV | 18 | PRP | 68 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1997-12-01 | 1997-12-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 |  | 39000 | 0 | 39000 | 0 | 0 | Complete. |  |  |  | Non-INV | 0
FIN | UNDP | Institutional strengthening project for the phaseout of ODSs under the Montreal Protocol: Phase II | Individual | ASP | IND | SEV | 20 | INS | 107 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-01-01 | 1998-10-01 |  | 1999-03-01 | 1999-12-01 | 287100 | 0 | 287100 | 287100 | 100% | 0 | 0 | 0 | 37323 | 0 | 37323 | 0 | 0 | Completed in 1999. Financially completed in 1999. |  | 1996 |  | Non-Investment
FIN | UNDP | Project preparation in the foam and refrigeration sectors | Individual | ASP | IND | SEV | 21 | PRP | 109 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1997-11-01 | 2000-12-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 | 0 | 0 | 15600 | 0 | 15600 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Project preparation | Individual | ASP | IND | SEV | 22 | PRP | 129 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-03-01 | 1999-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1997 |  | Investment
FIN | IBRD | Project preparation in the refrigeration, solvent and halon production sectors |  | ASP | IND | SEV | 24 | PRP | 178 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1999-06-01 | 1999-06-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0 | Complete. |  |  |  | Non-INV | 0
FIN | UNDP | Renewal of Institutional strengthening project for the phaseout of ozone depleting substance under the Montreal Protocol : Phase 3 | Individual | ASP | IND | SEV | 27 | INS | 199 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2001-04-01 |  | 2001-08-01 | 2002-01-01 | 287100 | 0 | 287100 | 287100 | 100% | 0 | 0 | 0 | 37323 | 0 | 37323 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1999 |  | Non-Investment
FIN | IBRD | Preparation of projects in the refrigeration, solvent and CFC-halon production sectors |  | ASP | IND | SEV | 27 | PRP | 203 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-06-30 | 2000-01-01 |  | 2000-12-01 | 2000-12-01 | 220000 | 0 | 220000 | 220000 | 100% | 0 | 0 |  | 28600 | 0 | 28600 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNEP | Develop policy and customs training strategies | Individual | ASP | IND | SEV | 30 | TAS | 253 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-12-01 | 2001-06-01 |  | 2003-04-01 | 2005-12-01 | 50000 | -22000 | 28000 | 28000 | 100% | 0 | 0 |  | 6500 | -2860 | 3640 | 0 | 0
FIN | UNDP | Renewal of institutional strengthening project (phase IV) | Individual | ASP | IND | SEV | 34 | INS | 310 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-09-01 | 2003-08-01 |  | 2004-03-01 | 2009-01-01 | 287100 | -1304.01 | 285795.99 | 285796 | 100% | -0.01 | 0 | 0 | 37323 | -169.52 | 37153.48 | 0 | 0 | Completed in 2004.Financially completed in 2009. |  | 2001 |  | Non-Investment
FIN | UNDP | Country programme update | Individual | ASP | IND | SEV | 36 | CPG | 349 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2004-09-01 | 2003-10-01 |  | 2006-07-01 | 2007-03-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 | 0 | 19500 | 0 | 19500 | 0 | 0 | Completed in 2006. Financially completed in 2007. |  | 2002 | 2004-12-01 | Non-Investment
FIN | UNDP | Extension of institutional strengthening project: phase 5 | Individual | ASP | IND | SEV | 41 | INS | 367 | N | I | No_ODP | 30.8 | 30.8 | 0 | 0 | 2003-12-01 | 2004-07-01 | 2005-12-01 |  | 2006-07-01 | 2011-12-01 | 373230 | -2920 | 370310 | 370310 | 100% | 0 | 0 | 0 | 27992 | -219 | 27773.002 | -0.002 | 0 | Completed in 2006. Financially completed in 2011. |  | 2003 |  | Non-Investment
FIN | UNDP | Assistance to carry out an HCFC survey | Individual | ASP | IND | SEV | 45 | TAS | 391 | A | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-10-01 | 2006-12-01 |  | 2008-08-01 | 2011-12-01 | 183486 | -16859 | 166627 | 166627 | 100% | 0 | 0 | 0 | 16514 | -1517.33 | 14996.6661 | 0.0039 | 0 | Completed in 2008. Financially completed in 2011. |  | 2005 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase VI) | Individual | ASP | IND | SEV | 47 | INS | 392 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-07-01 | 2007-12-01 |  | 2008-12-01 | 2013-03-01 | 373230 | 0 | 373230 | 373230 | 100% | 0 | 0 | 0 | 27992.25 | 0 | 27992.25 | 0 | 0 | Financially completed in 2013. |  | 2005 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase VII) | Individual | ASP | IND | SEV | 54 | INS | 416 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2008-04-01 | 2009-05-01 | 2010-03-01 |  | 2010-12-01 | 2013-07-01 | 373230 | 0 | 373230 | 373230 | 100% | 0 | 0 | 0 | 27992 | 0 | 27992 | 0 | 0 | Financially completed in 2013. |  | 2008 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase VIII) | Individual | ASP | IND | SEV | 60 | INS | 436 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2010-04-01 | 2011-04-01 | 2012-03-01 |  | 2012-06-01 | 2013-08-01 | 326576 | 0 | 326576 | 326576 | 100% | 0 | 0 | 0 | 24493 | 0 | 24493 | 0 | 0 | Financially completed in 2013. |  | 2010 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (remaining balance for phase VIII) | Individual | ASP | IND | SEV | 65 | INS | 439 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-03-01 | 2012-03-01 |  | 2013-03-01 | 2013-12-01 | 46654 | 0 | 46654 | 46654 | 100% | 0 | 0 | 0 | 3499 | 0 | 3499 | 0 | 0 | Financially completed in 2013. |  | 2011 |  | Non-investment
FIN | UNDP | Extension of institutional strengthening project (phase IX: 4/2012-3/2014) | Individual | ASP | IND | SEV | 66 | INS | 444 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2012-04-01 | 2013-06-01 | 2014-03-01 |  | 2015-12-01 | 2016-12-01 | 373230 | 0 | 373230 | 373230 | 100% | 0 | 0 | 0 | 27992 | 0 | 27992 | 0 | 0 | Financially completed in 2016. | The activities have been implementated as planned. The NOU participated in the joint SEAP/SA network meeting in March in Korea. The 2014 CP report was submitted in a timely manner. | 2012 |  | Non-Investment
ONG | UNDP | Extension of institutional strengthening project (phase X: 4/2014-3/2016) | Individual | ASP | IND | SEV | 72 | INS | 457 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2014-05-01 | 2015-05-01 | 2016-03-01 | 2017-01-01 |  |  | 373230 | 0 | 373230 | 234843.36 | 62.92% | 138386.64 | -0.07 | 55354.656 | 26126 | 0 | 16438.9723 | 9687.0277 | -0.0049 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Monitoring of ongoing ODS phase-out projects continued. Controls on ODSs through licensing system were implemented during the year. NOU participated in MP-related international and regional meetings. Awareness activities including National Ozone Day celebrations were also undertaken. CP progress and Article 7 data for 2014 was reported in a timely manner. Consultations were held with industry and national stakeholders on adoption of low GWP alternatives. Prodoc signed (actual/planned, yes/no and date):42036 Missions undertaken (actual/planned):- TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: signed earlier First disbursement date (actual/planned): 42125Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | The monitoring of ongoing ODS phase-out projects continued. Controls on ODSs through licensing system were implemented during the year. CP progress and Article 7 data was reported in a timely manner. |  |  | Non-Investment
ONG | UNDP | Survey of ODS alternatives at the national level | Individual | ASP | IND | SEV | 74 | TAS | 461 | N | I | HFC | 0 | 0 | 0 | 0 | 2015-05-01 | 2016-12-01 | 2016-11-01 | 2017-06-01 |  |  | 180000 | 0 | 180000 | 275.81 | 0.1532% | 179724.19 | 6399.41 | 71889.676 | 16200 | 0 | 24.8229 | 16175.1771 | 575.9469 | Remarks1 - up to 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Agency was appointed for ODS alternatives survey. The agency would prepare the survey report which would include production and consumption. Industry association and technical consultancy organisation are expected to be involved in preparation activities. Prodoc signed (actual/planned, yes/no and date):42461 Missions undertaken (actual/planned): 3 TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: signed earlier First disbursement date (actual/planned): 42705Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve: The tranistion in the Govt. delayed the survey. The contract is issued and work started. MPU - BKK is following up for early completion. | The agency selected for doing ODS sruvey submitted inception report and initiated work. | 2015 |  | Non-Investment
ONG | UNDP | Extension of institutional strengthening project (phase X: 4/2016-3/2018) | Individual | ASP | IND | SEV | 76 | INS | 467 | N | I | HCFC | 0 | 0 | 0 | 0 | 2016-05-01 |  | 2018-03-01 | 2017-03-01 |  |  | 477734 | 0 | 477734 | 0 | 0% | 477734 | 0 | 191093.6 | 33441 | 0 | 0 | 33441 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Monitoring of ongoing ODS phase-out projects continued. Controls on ODSs through licensing system were implemented during the year. NOU participated in MP-related international and regional meetings. Awareness activities including National Ozone Day celebrations were also undertaken. CP progress and Article 7 data for 2014 was reported in a timely manner. Consultations were held with industry and national stakeholders on adoption of low GWP alternatives. Prodoc signed (actual/planned, yes/no and date):42767 Missions undertaken (actual/planned):- TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: signed earlier First disbursement date (actual/planned): Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:The Govt. has to open budget line for funds transfer as GoI rules. Due to that we can make any disbursement. MP-BKK is following up the matter. | The monitoring of ongoing ODS phase-out projects continued. Controls on ODSs through licensing system were implemented during the year. CP progress and Article 7 data was reported in a timely manner. |  |  | Non-Investment
FIN | UNIDO | Project formulation for the conversion of electronic cleaning processes from CFC-113/alcohol blended and 1,1,1 trichlorethane to non-CFC cleaning | Individual | ASP | IND | SOL | 10 | PRP | 07 | A | I |  | 0 | 0 |  |  | 1993-06-01 | 1994-10-01 | 1993-10-01 |  | 1998-12-01 | 2000-07-01 | 74000 | -332 | 73668 | 73668 | 100% | 0 | 0 |  | 9620 | -58 | 9562 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNIDO | Conversion of electronic cleaning processes from ODS solvents aqueous cleaning at ITI Mankapur | Individual | ASP | IND | SOL | 13 | INV | 25 | A | I | CFC | 34 | 48.8 |  |  | 1994-07-01 | 1996-06-01 | 1996-01-01 |  | 1996-10-01 | 2000-12-01 | 610160 | 0 | 610160 | 610160 | 100% | 0 | 0 |  | 79321 | -2 | 79319 | 0 | 0 | FIN
FIN | IBRD | ODS phase-out in sterilization and siliconisation of disposable syringes and needle at Hindustan Syringes and Medical Devices Private Ltd., Haryana | Individual | ASP | IND | SOL | 13 | INV | 26 | N | I | CFC | 53.2 | 56 | 0 | 0 | 1994-07-01 | 1996-03-01 | 1995-07-01 |  | 1996-12-01 | 1998-09-01 | 481000 | -22298 | 458702 | 458702 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. |  |  | 1996-12-01 | INV | 0
FIN | UNIDO | Conversion of electronic cleaning processes for ODS solvents to non-clean and hydrocarbon cleaning technologies at ERL-Bangalore | Individual | ASP | IND | SOL | 18 | INV | 65 | A | I | CFC TCA | 16.4 | 16.4 |  |  | 1995-11-01 | 1996-12-01 | 1997-05-01 |  | 1998-12-01 | 2000-12-01 | 192421 | -1899 | 190522 | 190522 | 100% | 0 | 0 |  | 25015 | -286 | 24729 | 0 | 0 | FIN
FIN | UNIDO | Conversion of electronic cleaning processes from ODS solvents to no-clean and aqueous photo resist developing and stripping technologies at ITI Palakkad | Individual | ASP | IND | SOL | 18 | INV | 66 | A | I | CFC TCA | 15 | 15 |  |  | 1995-11-01 | 1996-09-01 | 1997-05-01 |  | 1996-12-01 | 1998-08-01 | 235744 | 5652 | 241396 | 241396 | 100% | 0 | 0 |  | 30647 | 734 | 31381 | 0 | 0 | FIN
FIN | UNIDO | Conversion of electronic cleaning processes from ODS solvents to semi-aqueous cleaning and no-clean soldering technologies at ITI, Bangalore | Individual | ASP | IND | SOL | 19 | INV | 95 | A | I | CFC TCA | 7 | 7 |  |  | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1996-12-01 | 1999-08-01 | 107954 | -808 | 107146 | 107146 | 100% | 0 | 0 |  | 14034 | -127 | 13907 | 0 | 0 | FIN
FIN | IBRD | Elimination of 1,1,1 TCA from the precision cleaning processes at Modi Xerox | Individual | ASP | IND | SOL | 22 | INV | 112 | N | I | TCA | 6.07 | 6.07 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1998-06-01 |  | 1998-06-01 | 1998-01-01 | 130819 | -25985 | 104834 | 104834 | 100% | 0 | 0 |  | 17006.47 | -3378.05 | 13628.42 | 0 | 0 | Complete. |  |  |  | INV | 0
FIN | UNIDO | Preparation investment projects in the solvent (CFC 113) sector at Harbans Lal Mahotra & Sons Ltd. Calcutta | Individual | ASP | IND | SOL | 24 | PRP | 162 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-06-01 | 1999-04-01 |  | 2000-06-01 | 2001-07-01 | 25000 | -177 | 24823 | 24822.7 | 100% | 0.3 | 0 |  | 3250 | -28 | 3222 | 0 | 0 | FIN
FIN | UNIDO | Conversion of precision cleaning and coating processes from ODS solvents to heat cleaning technologies and ODS free solvent coating at Malhotra Shaving Products Ltd. | Individual | ASP | IND | SOL | 25 | INV | 181 | A | I | CFC | 13.6 | 13.6 |  |  | 1998-07-01 | 1998-12-01 | 2000-02-01 |  | 2000-09-01 | 2001-01-01 | 255112 | 0 | 255112 | 255111.63 | 100% | 0.37 | 0 |  | 33165 | 0 | 33165 | 0 | 0 | FIN
FIN | UNIDO | Conversion of precision cleaning and coating processes from ODS to heat cleaning technologies and ODS free solvent coating at Lal Malhotra & Sons Ltd. | Individual | ASP | IND | SOL | 26 | INV | 191 | A | I | CFC | 16 | 16 |  |  | 1998-11-01 | 1999-11-01 | 2000-06-01 |  | 2000-12-01 | 2002-09-01 | 308899 | 0 | 308899 | 308899.16 | 100% | -0.16 | 0 |  | 40157 | -8 | 40149 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the solvent sector | Individual | ASP | IND | SOL | 27 | PRP | 195 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-11-01 | 1999-12-01 |  | 2000-07-20 | 2000-11-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | FIN
FIN | UNIDO | Conversion of cleaning and coating processes based on CFC-113 and CTC to processes based on IPA at Vidyut Metallics Ltd. (VML) | Individual | ASP | IND | SOL | 28 | INV | 223 | A | I | CFC CTC | 19.7 | 19.7 |  |  | 1999-07-01 | 1999-11-01 | 2001-02-01 |  | 2003-09-01 | 2004-06-01 | 225452 | -387 | 225065 | 225064.66 | 100% | 0.34 | 0 |  | 29309 | -97 | 29212 | 0 | 0 | FIN |  |  | 2002-03-01
FIN | UNIDO | Conversion of cleaning processes from TCA and CTC to non-ODS solvent cleaning technologies (trichloroethylene and alkozypropanol) at Videocon Group (VDC) | Individual | ASP | IND | SOL | 28 | INV | 225 | A | I | CTC TCA | 7.2 | 7.2 |  |  | 1999-07-01 | 2000-06-01 | 2001-02-01 |  | 2002-01-01 | 2003-03-01 | 234978 | -4 | 234974 | 234973.65 | 100% | 0.35 | 0 |  | 30547 | -49 | 30498 | 0 | 0 | FIN
FIN | UNIDO | Conversion of cleaning and coating processes based on CFC-113 to IPA and xylene at Microraj Electronics PVT Ltd. & RCC (Sales) PVT ltd., Hyderabad (MRJ) | Individual | ASP | IND | SOL | 28 | INV | 230 | A | I | CFC | 4.3 | 4.3 |  |  | 1999-07-01 | 2000-06-01 | 2001-02-01 |  | 2001-11-01 | 2002-12-01 | 85431 | -431 | 85000 | 85000.01 | 100% | -0.01 | 0 |  | 11106 | -74 | 11032 | 0 | 0 | FIN
FIN | IBRD | Preparation of projects in the solvent general sector |  | ASP | IND | SOL | 30 | PRP | 247 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 |  | 4550 | 0 | 4550 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNIDO | Conversion of carbon tetrachloride (CTC) as cleaning solvent to trichloroethylene at Blue Star Ltd., Thane | Individual | ASP | IND | SOL | 31 | INV | 266 | A | I | CTC | 6.6 | 6.6 |  |  | 2000-07-01 | 2001-12-01 | 2002-01-01 |  | 2002-12-01 | 2003-10-01 | 76027 | 0 | 76027 | 76027 | 100% | 0 | 0 |  | 9884 | 0 | 9884 | 0 | 0 | FIN
FIN | UNIDO | Formulation of CTC process cleaning agent project in the solvent sector | Individual | ASP | IND | SOL | 31 | PRP | 264 | A | I |  | 0 | 0 |  |  | 2000-07-01 | 2000-11-01 | 2001-07-01 |  | 2002-03-01 | 2003-05-01 | 20000 | -261 | 19739 | 19739 | 100% | 0 | 0 |  | 2600 | -38 | 2562 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects for SMEs in the solvent sector | Individual | ASP | IND | SOL | 31 | PRP | 265 | A | I |  | 0 | 0 |  |  | 2000-07-01 | 2000-09-01 | 2002-04-01 |  | 2003-06-01 | 2003-06-01 | 30000 | -29 | 29971 | 29971.09 | 100% | -0.09 | 0 |  | 3900 | -10 | 3890 | 0 | 0 | FIN
FIN | UNIDO | Conversion of carbon tetrachloride as cleaning solvent to trichloroethylene at Sapna Engineering, Mazgaon | Individual | ASP | IND | SOL | 34 | INV | 306 | A | I | CTC | 14.5 | 14.5 |  |  | 2001-07-01 | 2002-09-01 | 2003-08-01 |  | 2003-08-01 | 2004-03-01 | 240435 | 0 | 240435 | 240434.89 | 100% | 0.11 | 0 |  | 31257 | -19 | 31238 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of carbon tetrachloride as cleaning solvent to trichloroethylene at Engineer Industries, Mazgaon | Individual | ASP | IND | SOL | 34 | INV | 308 | A | I | CTC | 20.2 | 20.2 |  |  | 2001-07-01 | 2002-09-01 | 2003-08-01 |  | 2003-08-01 | 2004-03-01 | 238776 | 0 | 238776 | 238775.51 | 100% | 0.49 | 0 |  | 31041 | -9 | 31032 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of carbon tetrachloride as cleaning solvent to trichloroethylene at Sapna Coils Ltd., Palghar | Individual | ASP | IND | SOL | 34 | INV | 327 | A | I | CTC | 22.8 | 22.8 |  |  | 2001-07-01 | 2002-04-01 | 2003-08-01 |  | 2003-08-01 | 2004-03-01 | 245024 | 0 | 245024 | 245023.89 | 100% | 0.11 | 0 |  | 31853 | -19 | 31834 | 0 | 0 | FIN |  |  |  | INV
FIN | UNEP | Overall strategy for the solvent sector to support the phase-out of ODS in SMEs | Individual | ASP | IND | SOL | 35 | TAS | 343 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-05-01 | 2003-12-01 |  | 2005-06-01 | 2007-07-01 | 169000 | -10140 | 158860 | 158860 | 100% | 0 | 0 |  | 21970 | -1318 | 20652 | 0 | 0
FIN | UNIDO | Preparation of an investment project in the solvent (CFC-113) sector | Individual | ASP | IND | SOL | 36 | PRP | 347 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-06-01 | 2003-04-01 |  | 2003-04-01 | 2004-04-01 | 30000 | -479 | 29521 | 29521.01 | 100% | -0.01 | 0 |  | 3900 | -68 | 3832 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of carbon tetrachloride (CTC) as cleaning solvent to trichloroethylene at Navdeep Engineering, Palghar | Individual | ASP | IND | SOL | 38 | INV | 354 | A | I | CTC | 53.9 | 53.9 |  |  | 2002-11-01 | 2003-04-01 | 2004-12-01 |  | 2005-12-01 | 2007-01-01 | 661842 | -1087 | 660755 | 660754.55 | 100% | 0.45 | 0 |  | 82803 | -120 | 82683 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of CFC-113 as cleaning solvent to TCE at Bharat Electronics Limited (BEL), Bangalore | Individual | ASP | IND | SOL | 40 | INV | 362 | A | I | CFC | 16 | 16 |  |  | 2003-07-01 | 2004-12-01 | 2005-07-01 |  | 2005-12-01 | 2006-12-01 | 151291 | -684 | 150607 | 150606.61 | 100% | 0.39 | 0 |  | 13616 | -61 | 13555 | 0 | 0 | FIN
FIN | UNIDO | Preparation of an MDI project | Individual | ASP | IRA | ARS | 47 | PRP | 173 | A | I |  |  | 0 |  |  | 2005-11-01 | 2007-01-01 | 2006-12-01 |  | 2008-04-01 | 2008-09-01 | 70000 | 0 | 70000 | 69999.9 | 100% | 0.1 | 0 |  | 5250 | 0 | 5250 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Phase-out of CFC consumption in the manufacture of aerosol MDIs | Individual | ASP | IRA | ARS | 52 | INV | 183 | A | I | CFC | 96.4 | 96.4 |  |  | 2007-07-01 | 2007-12-01 | 2010-09-30 |  | 2010-12-01 | 2012-12-01 | 3529508 | -233499 | 3296009 | 3296009.14 | 100% | -0.14 | 0 |  | 264713 | -17512 | 247201 | 0 | 0 | FIN |  |  |  | INV
FIN | UNEP | National transition strategy for the phase-out of CFC propellants in MDIs | Individual | ASP | IRA | ARS | 52 | TAS | 184 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-03-01 | 2010-09-01 |  | 2011-01-01 | 2011-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0
FIN | UNIDO | DBL project Iran. Phasing out CFC-11 through conversion of rigid PU-foam manufactured with the technique of continuous lamination at Fabis, Iran Steel, Mammoth Tehran, F.M., and Urethane Systems | Individual | ASP | IRA | FOA | 17 | INV | 11 | A | I | CFC | 1200 | 1200 |  |  | 1995-07-01 | 1995-12-01 | 1997-07-01 |  | 1998-12-01 | 2003-05-01 | 2571250 | 0 | 2571250 | 2571249.92 | 100% | 0.08 | 0 |  | 334263 | -361 | 333902 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 from flexible slabstock foam manufacturing at Safoam Co. | Individual | ASP | IRA | FOA | 22 | INV | 20 | A | I | CFC | 120 | 120 |  |  | 1997-05-01 | 1998-06-01 | 1998-06-01 |  | 2002-12-01 | 2003-12-01 | 487125 | 0 | 487125 | 487125.1 | 100% | -0.1 | 0 |  | 63326 | -85 | 63241 | 0 | 0 | FIN |  |  | 2000-11-01
FIN | UNIDO | Phasing out of CFC-11 from flexible slabstock foam manufacturing at Urethane Systems Company (USC) | Individual | ASP | IRA | FOA | 22 | INV | 21 | A | I | CFC | 110 | 110 |  |  | 1997-05-01 | 2001-09-01 | 1998-06-01 |  | 2003-03-01 | 2004-02-01 | 487125 | -4690 | 482435 | 482435.39 | 100% | -0.39 | 0 |  | 63326 | -709 | 62617 | 0 | 0 | FIN |  |  | 2000-11-01
FIN | UNIDO | Phasing out CFC-11 from flexible slabstock foam manufacturing at Shizar Co. | Individual | ASP | IRA | FOA | 22 | INV | 22 | A | I | CFC | 120 | 120 |  |  | 1997-05-01 | 2001-07-01 | 1998-06-01 |  | 2003-12-01 | 2004-12-01 | 487125 | 0 | 487125 | 487124.7 | 100% | 0.3 | 0 |  | 63326 | 0 | 63326 | 0 | 0 | FIN |  |  | 2000-11-01
FIN | UNIDO | Phasing out of CFC-11 from flexible slabstock foam manufacturing at Mashhad Foam | Individual | ASP | IRA | FOA | 23 | INV | 29 | A | I | CFC | 90 | 90 |  |  | 1997-11-01 | 1999-01-01 | 1998-12-01 |  | 2003-12-01 | 2004-12-01 | 503330 | -1856 | 501474 | 501473.82 | 100% | 0.18 | 0 |  | 65433 | -345 | 65088 | 0 | 0 | FIN |  |  | 2000-11-01
FIN | UNIDO | Preparation of an investment project in the foam sector for phasing out ODS at three enterprises including Bahaman Plastic | Individual | ASP | IRA | FOA | 23 | PRP | 27 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-09-01 | 1998-06-01 |  | 2000-09-01 | 2001-07-01 | 10000 | -2561 | 7439 | 7439 | 100% | 0 | 0 |  | 1300 | -334 | 966 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the foam sector (flexible polyurethane) | Individual | ASP | IRA | FOA | 27 | PRP | 39 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-11-01 | 1999-12-01 |  | 2000-12-01 | 2002-05-01 | 18000 | -1160 | 16840 | 16839.62 | 100% | 0.38 | 0 |  | 2340 | -154 | 2186 | 0 | 0 | FIN
FIN | UNDP | Preparation of four projects in the integral skin foam subsector | Individual | ASP | IRA | FOA | 27 | PRP | 40 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-12-01 | 2004-01-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 2000. Financially completed in 2004. |  | 1999 |  | Investment
CLO | UNIDO | Phasing out ODS in manufacturing of flexible PU slabstock foam through the use of liquid CO2 blowing technology at Bahman Plastic Co. | Individual | ASP | IRA | FOA | 28 | INV | 50 | A | I | CFC | 83 | 83 |  |  | 1999-07-01 | 2000-11-01 | 2001-02-01 |  |  | 2009-05-01 | 485929 | -5381 | 480548 | 480548.04 | 100% | -0.04 | 0 |  | 63171 | -700 | 62471 | 0 | 0 | CLO |  |  | 2002-06-01
FIN | UNIDO | Conversion from CFC-11 to n-pentane in the production of rigid foam panels at Rashestan Co. | Individual | ASP | IRA | FOA | 31 | INV | 73 | A | I | CFC | 70 | 70 |  |  | 2000-07-01 | 2001-04-01 | 2003-01-01 |  | 2005-07-01 | 2005-12-01 | 539882 | 0 | 539882 | 539882.07 | 100% | -0.07 | 0 |  | 69387 | -79 | 69308 | 0 | 0 | FIN
CLO | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Nobough Industrial Co. | Individual | ASP | IRA | FOA | 32 | INV | 75 | A | I | CFC | 31.8 | 21 | 0 | 0 | 2000-12-01 | 2002-01-01 | 2004-01-01 |  |  | 2003-07-01 | 248736 | -198081 | 50655 | 50655 | 100% | 0 | 0 | 0 | 32335.68 | -25751 | 6584.68 | 0 | 0 | Canceled in 2003. Financially completed in 2006. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to n-pentane technology in the manufacture of integral skin polyurethane foam products at Iran Polyurethane Manufacturing Co. | Individual | ASP | IRA | FOA | 32 | INV | 76 | A | I | CFC | 51.8 | 51.8 | 0 | 0 | 2000-12-01 | 2002-05-01 | 2004-01-01 |  | 2003-08-01 | 2003-11-01 | 796230 | 0 | 796230 | 796230 | 100% | 0 | 0 | 0 | 97585.3 | 0 | 97585.3 | 0 | 0 | Completed in 2003. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Project preparation in the flexible polyurethane foam sector | Individual | ASP | IRA | FOA | 33 | PRP | 77 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-05-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | ASP | IRA | FOA | 33 | PRP | 79 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-05-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | Germany | Conversion of the use of CFC to LCD in the manufacture of flexible foam at Iranogharb | Individual | ASP | IRA | FOA | 34 | INV | 114 | A | I | CFC | 62 | 62 | 0 |  | 2001-07-01 | 2001-08-01 | 2002-12-01 |  | 2004-12-01 | 2007-12-01 | 386260 | 0 | 386260 | 386260 | 100% | 0 | 0 | 0 | 50214 | 0 | 50214 | 0 | 0 | Project completed except for the certificate of destruction which is still outstanding. PCR was prepared and forwarded to the country for comment..
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded and integral skin polyurethane foams at Abre Sanati Iran | Individual | ASP | IRA | FOA | 34 | INV | 88 | A | I | CFC | 47.5 | 47.5 | 0 | 0 | 2001-07-01 | 2002-05-01 | 2004-08-01 |  | 2003-06-01 | 2005-11-01 | 344407 | -7956 | 336451 | 336451 | 100% | 0 | 0 | 0 | 44772.91 | -1034 | 43738.91 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNIDO | Preparation of one investment project in the rigid foam sector | Individual | ASP | IRA | FOA | 34 | PRP | 106 | A | I |  | 0 | 0 |  |  | 2001-07-01 | 2002-03-01 | 2002-08-01 |  | 2002-12-01 | 2003-02-01 | 20000 | -840 | 19160 | 19160.19 | 100% | -0.19 | 0 |  | 2600 | -113 | 2487 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phasing out ODS in the manufacture of flexible slab stock foam through the use of LCD blowing technology at Abre Shomal Co. | Individual | ASP | IRA | FOA | 35 | INV | 115 | A | I | CFC | 90.4 | 90.4 |  |  | 2001-12-01 | 2002-06-01 | 2003-07-01 |  | 2004-03-01 | 2005-08-01 | 552148 | -50609 | 501539 | 501538.52 | 100% | 0.48 | 0 |  | 70736 | -5654 | 65082 | 0 | 0 | FIN |  |  |  | INV
FIN | Germany | Conversion of the use of CFC to LCD in the manufacture of flexible foam at Esfanj Jajerood foam company | Individual | ASP | IRA | FOA | 35 | INV | 116 | A | I | CFC | 89 | 89 | 0 |  | 2001-12-01 | 2001-01-01 | 2003-05-01 |  | 2004-12-01 | 2007-12-01 | 499299 | 0 | 499299 | 499299 | 100% | 0 | 0 | 0 | 64909 | 0 | 64909 | 0 | 0 | Project completed. PCR has been submitted to the country
FIN | UNDP | Conversion from CFC-11 to water-blown technology in the manufacture of flexible molded polyurethane foam at Sandalisazi Esfanje Ghalebi Iran | Individual | ASP | IRA | FOA | 35 | INV | 117 | A | I | CFC | 22.4 | 22.4 | 0 | 0 | 2001-12-01 | 2003-08-01 | 2004-07-01 |  | 2004-11-01 | 2007-02-01 | 188820 | -7749 | 181071 | 181071 | 100% | 0 | 0 | 0 | 24546.6 | -1007.39 | 23539.2136 | -0.0036 | 0 | Completed in 2004. Financially completed in 2007. |  | 2001 |  | Investment
FIN | Germany | Project preparation for the phase out of ODS use in the flexible foam sub-sector in 5 companies | Individual | ASP | IRA | FOA | 35 | PRP | 118 | A | I |  | 0 |  | 0 |  | 2001-12-01 | 2001-01-01 | 2003-01-01 |  | 2002-09-01 | 2002-12-01 | 23750 | 0 | 23750 | 23750 | 100% | 0 | 0 | 0 | 3088 | 0 | 3088 | 0 | 0 | 5 projects submitted and approved in Jul-02.
FIN | UNDP | Project preparation for 2 projects in the flexible slabstock foam sector | Individual | ASP | IRA | FOA | 36 | PRP | 141 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2003-04-01 | 2005-11-01 | 10000 | -653 | 9347 | 9347 | 100% | 0 | 0 | 0 | 1300 | -84.89 | 1215.11 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Project preparation for 2 projects in the rigid foam sector | Individual | ASP | IRA | FOA | 36 | PRP | 142 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2003-04-01 | 2005-11-01 | 10000 | -653 | 9347 | 9347 | 100% | 0 | 0 | 0 | 1300 | -84.89 | 1215.11 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Project preparation for 4 projects in the flexible slabstock foam sector | Individual | ASP | IRA | FOA | 36 | PRP | 143 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 |  | 2003-04-01 |  | 2003-04-01 | 2005-11-01 | 12500 | -12500 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 1625 | -1625 | 0 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Project preparation for 6 projects in the rigid foam sector | Individual | ASP | IRA | FOA | 36 | PRP | 144 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 |  | 2003-04-01 |  | 2003-04-01 | 2005-11-01 | 12500 | -12500 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 1625 | -1625 | 0 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNIDO | Formulation of two umbrella investment projects in the rigid and flexible foam sector | Individual | ASP | IRA | FOA | 36 | PRP | 148 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-11-01 | 2003-04-01 |  | 2003-10-01 | 2004-07-01 | 35000 | -557 | 34443 | 34442.85 | 100% | 0.15 | 0 |  | 4550 | -80 | 4470 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phasing out of ODS in the manufacture of flexible slabstock foam through the use of LCD blowing technology at Esfanj Shirvan Co. | Individual | ASP | IRA | FOA | 37 | INV | 149 | A | I | CFC | 91.1 | 91.1 |  |  | 2002-07-01 | 2002-11-01 | 2004-03-01 |  | 2008-12-01 | 2009-03-01 | 373515 | 0 | 373515 | 373514.99 | 100% | 0.01 | 0 |  | 48557 | 0 | 48557 | 0 | 0 | FIN |  |  | 2005-06-01 | INV
FIN | Germany | Conversion from CFC-11 to pentane technology in the manufacture of integral skin PU foam at Jahad Tahghihat Group | Individual | ASP | IRA | FOA | 37 | INV | 150 | A | I | CFC | 23 | 23 | 0 |  | 2002-07-01 | 2002-10-01 | 2004-03-01 |  | 2004-09-01 | 2007-12-01 | 335249 | 0 | 335249 | 335249 | 100% | 0 | 0 | 0 | 43582 | 0 | 43582 | 0 | 0 | Project completed. PCR has been submitted to the country
FIN | Germany | Conversion of the use of CFC to LCD in the manufacture of flexible foam at Abre Baspar foam company | Individual | ASP | IRA | FOA | 37 | INV | 151 | A | I | CFC | 77 | 77 | 0 |  | 2002-07-01 | 2002-08-01 | 2004-01-01 |  | 2004-09-01 | 2007-12-01 | 387174 | 0 | 387174 | 387174 | 100% | 0 | 0 | 0 | 50333 | 0 | 50333 | 0 | 0 | Equipment has been delivered and installed, certificate of destruction was signed. Project is completed. PCR has been submitted for comment to the country.
FIN | Germany | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible molded PU foam at Sanayeh Dashboard Iran | Individual | ASP | IRA | FOA | 37 | INV | 152 | A | I | CFC | 22 | 22 | 0 |  | 2002-07-01 | 2002-08-01 | 2004-03-01 |  | 2007-12-01 | 2009-12-01 | 185632 | -42000 | 143632 | 143632 | 100% | 0 | 0 | 0 | 24132 | -5459.96 | 18672 | 0.04 | 0 | NOU acknowledged destruction of old equipment in December 2007. PCR was approved by NOU in Oct-2009. Funds of USD 42.000 have been returned to MFS.
FIN | Germany | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible molded polyurethane foam at Nikou Esfandj | Individual | ASP | IRA | FOA | 37 | INV | 153 | A | I | CFC | 18.6 | 18.6 | 0 |  | 2002-07-01 | 2002-08-01 | 2004-03-01 |  | 2004-09-01 | 2007-12-01 | 228310 | 0 | 228310 | 228310 | 100% | 0 | 0 | 0 | 29680 | 0 | 29680 | 0 | 0 | Project completed. PCR has been submitted to the country
FIN | UNIDO | Conversion from CFC-11 to n-pentane in the production of rigid foam panels at Yakhchavan Co. | Individual | ASP | IRA | FOA | 37 | INV | 155 | A | I | CFC | 73.6 | 73.6 |  |  | 2002-07-01 | 2002-11-01 | 2005-03-01 |  | 2005-12-01 | 2008-12-01 | 531838 | -7193 | 524645 | 524645.32 | 100% | -0.32 | 0 |  | 68502 | -791 | 67711 | 0 | 0 | FIN |  |  |  | INV
FIN | Germany | Conversion from CFC-11 to fully water-based technology in the manufacture of flexible molded polyurethane foam at Phira Khodro | Individual | ASP | IRA | FOA | 37 | INV | 156 | A | I | CFC | 20.2 | 20.2 | 0 |  | 2002-07-01 | 2002-08-01 | 2004-01-01 |  | 2004-09-01 | 2007-12-01 | 158166 | 0 | 158166 | 158166 | 100% | 0 | 0 | 0 | 20562 | 0 | 20562 | 0 | 0 | Project is completed. PCR was signed by NOU in June 2007 and submitted by end 2007.
FIN | Germany | Project preparation for the development of a foam sector strategy | Individual | ASP | IRA | FOA | 37 | PRP | 154 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2002-10-01 | 2003-08-01 |  | 2002-12-01 | 2003-12-01 | 51850 | 0 | 51850 | 51850 | 100% | 0 | 0 | 0 | 6741 | 0 | 6741 | 0 | 0 | Project preparation lead to sector phase out strategy, included in NPOP approved at 41st ExCom.
FIN | UNDP | Preparation for HCFC phase-out investment activities (rigid foam) | Individual | ASP | IRA | FOA | 57 | PRP | 195 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-10-01 | 2010-03-01 |  | 2012-08-01 | 2014-02-01 | 30000 | -79 | 29921 | 29921 | 100% | 0 | 0 | 0 | 2250 | -5.93 | 2244.075 | -0.005 | 0 | Financially completed in 2014. | Completed in 2012. | 2009 |  | Investment
COM | Germany | Preparation for HCFC phase-out investment activities (stage II) (foam sector) | Individual | ASP | IRA | FOA | 72 | PRP | 218 | A | I | HCFC | 0 |  | 0 |  | 2014-05-01 | 2015-03-01 | 2016-05-01 |  | 2016-11-01 |  | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 |  | revision of submitted documents, update of survey and sector data
ONG | UNIDO | Preparation for HCFC phase-out investment activities (stage II) (rigid polyurethane foam sector) | Individual | ASP | IRA | FOA | 74 | PRP | 222 | A | I |  | 0 | 0 |  |  | 2015-05-01 | 2015-07-01 | 2016-05-31 | 2017-06-01 |  |  | 75000 | 0 | 75000 | 50176.25 | 66.9% | 24823.75 | 16321.05 | 20000 | 5250 | 0 | 0 | 5250 | 1142.4735 | Further consultation with stakeholders and NOU, project document finalized for the HPMP stage II. HPMP Stage II first tranche in the foam sector was approved in 2016 by the 77th Meeting of the ExCom. | - Activities planned but not implemented, reasons and strategy: The list of the companies shortlisted in the project document is being reviewed and updated. - Actions towards next goals: A mission is planned at the end of April 2017 to agree on the updated business plans. Was there any delay during the reporting year? Yes The list of the companies shortlisted in the project document has to be reviewed and updated. Any recurring problem? No Any impact on project completion date: Yes Any action required by Executive Committee? No |  |  | NON-INV
FIN | UNIDO | Preparation of a demonstration project in the methyl bromide sector | Individual | ASP | IRA | FUM | 23 | PRP | 33 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-06-01 | 1998-03-01 |  | 1999-01-01 | 2001-07-01 | 10000 | 13050 | 23050 | 23050 | 100% | 0 | 0 |  | 1300 | 1692 | 2992 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of the important non critical, non-essential use of methyl bromide for post-harvest treatment | Individual | ASP | IRA | FUM | 29 | INV | 57 | A | I | MBR | 12.4 | 12.4 |  |  | 1999-11-01 | 2000-04-01 | 2001-12-01 |  | 2006-12-01 | 2009-03-01 | 260698 | -15748 | 244950 | 244950.15 | 100% | -0.15 | 0 |  | 33891 | -2047 | 31844 | 0 | 0 | FIN
CLO | UNIDO | Project preparation in soil fumigation | Individual | ASP | IRA | FUM | 33 | PRP | 78 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-09-01 | 2002-04-01 |  |  | 2003-05-01 | 25000 | -19845 | 5155 | 5155 | 100% | 0 | 0 |  | 3250 | -2581 | 669 | 0 | 0 | CLO |  |  |  | INV
FIN | UNIDO | Preparatory assistance in methyl bromide (soil fumigation in olive tree nurseries) | Individual | ASP | IRA | FUM | 44 | PRP | 168 | A | I |  | 0 | 0 |  |  | 2004-12-01 | 2005-07-01 | 2005-12-01 |  | 2005-12-01 | 2006-12-01 | 9830 | -1250 | 8580 | 8579.53 | 99.99% | 0.47 | 0 |  | 737 | -93 | 643 | 1 | 0 | FIN
FIN | UNIDO | Total phase-out of methyl bromide in soil fumigation in olive seedings, fruit trees, nurseries and others | Individual | ASP | IRA | FUM | 47 | INV | 175 | A | I | MBR | 14.4 | 14.4 |  |  | 2005-11-01 | 2006-08-01 | 2010-12-01 |  | 2008-12-01 | 2009-12-01 | 227950 | -107 | 227843 | 227842.61 | 100% | 0.39 | 0 |  | 20516 | -10 | 20506 | 0 | 0 | FIN |  |  |  | INV
FIN | France | Projects preparation and technical assistance in the halon sector |  | ASP | IRA | HAL | 23 | PRP | 32 | A | I |  | 0 |  | 0 |  | 1997-11-01 | 1998-04-01 | 1998-12-01 |  | 1999-05-01 | 1999-07-01 | 31500 | 0 | 31500 | 31500 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed.
TRF | France | Halon management programme | Halon Banking | ASP | IRA | HAL | 28 | TAS | 49 | A | I |  | 0 |  | 0 |  | 1999-07-01 | 2002-05-01 | 2003-08-01 |  |  | 2011-08-01 | 511175 | -397500 | 113675 | 113675 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | The project transfer to UNIDO was acted by the 63rd ExCom meeting.
COM | UNIDO | Halon phase-out project (Transfer from France) | Individual | ASP | IRA | HAL | 63 | TAS | 198 | A | I |  | 0 | 0 |  |  | 2011-04-01 | 2011-11-01 | 2012-04-01 |  | 2016-12-01 |  | 397500 | 0 | 397500 | 372960.24 | 93.83% | 24539.76 | 0 | 1 | 29813 | 0 | 27972 | 1841 | 0 | - The Mashhad Waste Management Organization allocated the space for the installation of the equipment. - A technician attended a training course for equipment installation and management at the equipment supplier factory. - Installation of the equipment was completed by end of July 2016. - Commissioning and completion of the project by Nov 2016. | Project completed in 2016. |  |  | NON-INV
FIN | Germany | Preparation of a national CFC phase-out plan | Individual | ASP | IRA | PHA | 39 | PRP | 159 | A | I |  | 0 |  | 0 |  | 2003-04-01 | 2003-04-01 | 2004-04-01 |  | 2003-11-01 | 2003-12-01 | 24000 | 0 | 24000 | 24000 | 100% | 0 | 0 | 0 | 3120 | 0 | 3120 | 0 | 0 | National Phase Out Plan has been submitted and appproved at the 41th meeting
FIN | Germany | National CFC phase-out plan: 2004 annual implementation programme | Multi-Year | ASP | IRA | PHA | 41 | INV | 160 | A | I | CFC | 0 |  | 0 |  | 2003-12-01 | 2004-03-01 | 2004-12-01 |  | 2007-12-01 | 2007-12-01 | 694124 | 946405 | 1640529 | 1640529 | 100% | 0 | 0 | 0 | 76354 | 104105 | 180459 | 0 | 0 | Activity progressed according to plan. So far, a total of 1500 ODP tons have been replaced with CFC-free technology. All of the funds have been disbursed and the targeted ODP phase out has been achieved. The tranche is completed, all outstanding certificates of destruction were handed in by december 2007.
FIN | UNIDO | National CFC phase-out plan (first tranche of implementation plan 2004) | Multi-Year | ASP | IRA | PHA | 41 | INV | 162 | A | I | CFC | 274.1 | 274.1 |  |  | 2003-12-01 | 2004-03-01 | 2005-04-01 |  | 2005-12-01 | 2007-12-01 | 361840 | 2104066 | 2465906 | 2465905.96 | 100% | 0.04 | 0 |  | 27138 | 157805 | 184943 | 0 | 0 | FIN |  |  |  | INV
FIN | France | National CFC phase-out plan: 2004 annual implementation programme | Multi-Year | ASP | IRA | PHA | 41 | INV | 163 | A | I | CFC | 0 | 0 | 0 |  | 2003-12-01 | 2004-05-01 | 2005-12-01 |  | 2007-12-01 | 2011-05-01 | 1006620 | 0 | 1006620 | 1006620 | 100% | 0 |  | 0 | 110728 | 0 | 110728 | 0 |  | The French contribution is implemented by GTZ-Proklima. Project completed.
FIN | UNEP | National CFC phase-out plan: 2004 annual implementation programme | Multi-year | ASP | IRA | PHA | 41 | TAS | 161 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-08-01 | 2006-12-01 |  | 2010-12-01 | 2011-12-01 | 140253 | 0 | 140253 | 140253 | 100% | 0 | 0 |  | 18233 | 0 | 18233 | 0 | 0
FIN | UNDP | National CFC phase-out plan: first tranche | Multi-Year | ASP | IRA | PHA | 42 | INV | 165 | N | I | CFC | 56 | 56 | 0 | 0 | 2004-04-01 | 2005-05-01 | 2007-04-01 |  | 2007-12-01 | 2011-12-01 | 770000 | -13453.09 | 756546.91 | 756547 | 100% | -0.09 | 0 | 0 | 57750 | -1008.98 | 56741.025 | -0.00505 | 0 | Completed in 2007. Financially completed in 2011. |  | 2004 |  | Investment
FIN | Germany | National CFC phase-out plan: 2005 annual implementation programme | Multi-Year | ASP | IRA | PHA | 45 | INV | 169 | A | I | CFC | 0 | 0 | 0 |  | 2005-04-01 | 2005-05-01 | 2006-04-01 |  | 2007-12-01 | 2007-12-01 | 479044 | 0 | 479044 | 479044 | 100% | 0 | 0 | 0 | 52695 | 0 | 52695 | 0 | 0 | Funds have been disbursed for the conversion of additional manufacturers in the foam sector. Certificates of destruction were handed in by Dec-2008.
FIN | UNIDO | National CFC phase-out plan: 2005 annual implementation programme | Multi-Year | ASP | IRA | PHA | 45 | INV | 170 | A | I | CFC | 115.5 | 115.5 |  |  | 2005-04-01 | 2005-11-01 | 2006-04-01 |  | 2006-12-01 | 2008-05-01 | 742449 | -52 | 742397 | 742396.93 | 100% | 0.07 | 0 |  | 55684 | -4 | 55680 | 0 | 0 | FIN |  |  |  | INV
FIN | France | National CFC phase-out plan: 2005 annual implementation programme | Multi-Year | ASP | IRA | PHA | 45 | INV | 171 | A | I | CFC | 424.5 | 94.3 | 0 |  | 2005-04-01 | 2007-04-01 | 2007-04-01 |  | 2010-06-01 | 2012-04-01 | 500000 | -147981 | 352019 | 352019 | 100% | 0 |  | 0 | 55000 | -16278 | 38722 | 0 |  | The French contribution was implemented by GIZ-Proklima. Project completed. | Expenses data have been corrected.
FIN | Germany | National CFC phase-out plan: 2006 annual implementation programme | Multi-Year | ASP | IRA | PHA | 48 | INV | 176 | A | I | CFC | 30 | 30 | 0 |  | 2006-04-01 | 2006-10-01 | 2007-04-01 |  | 2008-08-01 | 2011-09-01 | 1007124 | 0 | 1007124 | 1007124 | 100% | 0 | 0 | 0 | 110784 | 0 | 110784 | 0 | 0 | Funds have been disbursed for the conversion of manufacturers in the foam sector. Certificates of destruction will be collected and handed in during 2009.
FIN | UNIDO | National CFC phase-out plan: 2006 annual implementation programme | Multi-Year | ASP | IRA | PHA | 48 | INV | 177 | A | I | CFC | 230 | 230 |  |  | 2006-04-01 | 2006-08-01 | 2007-04-01 |  | 2007-04-01 | 2008-12-01 | 66224 | -549 | 65675 | 65675.33 | 100% | -0.33 | 0 |  | 4967 | -41 | 4926 | 0 | 0 | FIN |  |  |  | INV
FIN | Germany | National CFC phase-out plan: 2007 annual implementation programme | Multi-Year | ASP | IRA | PHA | 51 | INV | 181 | A | I | CFC | 250 | 250.3 | 0 |  | 2007-03-01 | 2007-04-01 | 2008-03-01 |  | 2009-04-01 | 2011-09-01 | 920868 | 0 | 920868 | 920868 | 100% | 0 | 0 | 0 | 101295 | 0 | 101295 | 0 | 0 | 4 tenders were contracted and production started for 2 machines by end of 2008. The other 2 installations were completed by end of 2009/ beginning 2010.
FIN | UNIDO | National CFC phase-out plan: 2007 annual implementation programme | Multi-Year | ASP | IRA | PHA | 51 | TRA | 182 | A | I |  | 0 | 66.6 |  |  | 2007-03-01 | 2007-10-01 | 2008-03-01 |  | 2008-04-01 | 2009-03-01 | 36179 | -1894 | 34285 | 34284.79 | 100% | 0.21 | 0 |  | 2713 | -142 | 2571 | 0 | 0 | FIN |  |  |  | INV
FIN | Germany | National CFC phase-out plan: 2008 annual implementation programme | Multi-Year | ASP | IRA | PHA | 54 | INV | 186 | A | I | CFC | 195.7 | 195.7 | 0 |  | 2008-04-01 | 2008-04-01 | 2009-03-01 |  | 2011-04-01 | 2011-09-01 | 729846 | 0 | 729846 | 729846 | 100% | 0 | 0 | 0 | 80283 | 0 | 80283 | 0 | 0 | project completed
FIN | UNDP | Preparation of a HCFC phase-out management plan (overarching strategy) | Individual | ASP | IRA | PHA | 56 | PRP | 188 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-11-01 | 2010-07-01 | 2009-11-01 |  | 2010-12-01 | 2012-04-01 | 113750 | 0 | 113750 | 113750 | 100% | 0 | 0 | 0 | 8531 | 0 | 8531 | 0 | 0 | Financially completed in 2012. | Financially completed in 2012. | 2008 |  | Investment
FIN | UNEP | Preparation of a HCFC phase-out management plan (overarching strategy) | RMP | ASP | IRA | PHA | 56 | PRP | 189 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-03-01 | 2009-11-01 |  | 2011-01-01 | 2012-10-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | Germany | Preparation of a HCFC phase-out management plan (overarching strategy) | Individual | ASP | IRA | PHA | 56 | PRP | 190 | A | I | HCFC | 0 |  | 0 |  | 2008-11-01 | 2009-04-01 | 2009-11-01 |  | 2011-04-01 | 2012-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 |  | HPMP was approved based on preparatory study
FIN | Germany | National CFC phase-out plan: 2009 annual implementation programme | Multi-Year | ASP | IRA | PHA | 57 | INV | 191 | A | I | CFC | 132.7 | 132.7 | 0 |  | 2009-04-01 | 2009-04-01 | 2010-03-01 |  | 2011-04-01 | 2013-04-01 | 512208 | 0 | 512208 | 512208 | 100% | 0 | 0 | 0 | 56343 | 0 | 56343 | 0 |  | project finally completed, financial completion under way
FIN | Germany | Preparation of a HCFC phase-out management plan (foam sector) | Individual | ASP | IRA | PHA | 57 | PRP | 192 | A | I | HCFC | 0 |  | 0 |  | 2009-04-01 | 2009-09-01 | 2010-03-01 |  | 2011-04-01 | 2011-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 |  | HPMP was approved based on preparatory study
FIN | UNDP | HCFC phase-out management plan (stage I, first tranche) (air conditioning sector plan) | Multi-Year | ASP | IRA | PHA | 63 | INV | 199 | N | I | HCFC | 29.3 | 29.3 | 0 | 0 | 2011-04-01 | 2012-12-01 | 2015-03-01 |  | 2013-12-01 | 2013-12-01 | 1938500 | 0 | 1938500 | 1938500 | 100% | 0 | 0 | 0 | 145387 | 0 | 145387 | 0 | 0 | Financially completed in 2013. |  | 2011 |  | Investment
ONG | Germany | HCFC phase-out management plan (stage I, first tranche) (foam sector plan) | Multi-Year | ASP | IRA | PHA | 63 | INV | 201 | A | I | HCFC | 30.5 | 3 | 0 |  | 2011-04-01 | 2011-05-01 | 2012-03-01 | 2017-06-01 |  |  | 1962400 | 0 | 1962400 | 1772400 | 90.32% | 190000 | 0 | 190000 | 222664 | 0 | 201106 | 21558 |  | Pakran and Arya Baron installation and comissioning took place in September 2016 | installation commissioning completed - final acceptance still pending for Kian and Parlo
COM | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | IRA | PHA | 63 | INV | 202 | A | I | HCFC | 32.1 | 32.1 |  |  | 2011-04-01 | 2011-08-01 | 2015-03-31 |  | 2015-12-01 |  | 1300000 | 0 | 1300000 | 1289445.94 | 99.19% | 10554.06 | 4772.77 | 1 | 97500 | 0 | 96708 | 792 | 358 | The project was operationally completed. |  |  |  | INV
FIN | UNDP | HCFC phase-out management plan (stage I, first tranche) (foam sector plan: one foam systems house) | Multi-Year | ASP | IRA | PHA | 63 | INV | 204 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-04-01 |  | 2015-03-01 |  | 2014-12-01 | 2015-06-01 | 225500 | -225500 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 16913 | -16913 | 0 | 0 | 0 | Financially completed in 2015. | As planned, consultations are currently underway on how we can move forward with the systems house component. | 2011 |  | Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | ASP | IRA | PHA | 63 | TAS | 200 | A | I |  | 3.2 | 0 | 0 | 0 | 2011-04-01 | 2013-08-01 | 2015-03-01 | 2017-12-01 |  |  | 262000 | -60000 | 202000 | 105263.99 | 52.11% | 96736.01 | 65000 | 9673.601 | 34060 | -7800 | 13684.3187 | 12575.6813 | 8450 | Brief progress report (actual/planned): 10 technician trainings, 3 customs trainings, 2 awareness raising meeting on EE, promotional activities carried out. Customs and NOU linked now to a common online system for issuing licenses for importation of HCFC Legal arrangements(actual/planned): Yes First mission (actual/planned): 1 mission in 2016 TOR completed(actual/planned): ___ First disbursement date (actual/planned): Aug 2013 All funds disbursed (yes/no): No Any delay? (yes/no): yes If Yes, reasons for delay & action plan to resolve: NOU attention on investment components If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): 1 mission undertaken for IACM for Stage 2, which also enabled monitoring of Stage 1. 1 technician and 1 customs training undertaken
FIN | UNDP | HCFC phase-out management plan (stage I, first tranche) (project management unit) | Multi-Year | ASP | IRA | PHA | 63 | TAS | 203 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-04-01 | 2013-02-01 | 2012-03-01 |  | 2014-06-01 | 2015-03-01 | 78000 | 0 | 78000 | 78000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Financially completed in 2015. | In Q1 of 2014, activities progressing as planned. HPMP third tranche funding request submitted for the consideration of 72 Excom. | 2011 |  | Investment
FIN | Germany | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | ASP | IRA | PHA | 63 | TAS | 205 | A | I | HCFC | 1.2 | 0 | 0 |  | 2011-04-01 | 2011-05-01 | 2012-03-01 |  | 2013-12-01 | 2015-12-01 | 100600 | 0 | 100600 | 100600 | 100% | 0 | 0 | 0 | 11415 | 0 | 11415 | 0 |  | All planned activities completed
COM | Germany | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | Multi-Year | ASP | IRA | PHA | 68 | INV | 207 | A | I | HCFC | 0 | 0 | 0 |  | 2012-12-01 | 2013-05-01 | 2015-12-01 |  | 2016-11-01 |  | 534233 | 0 | 534233 | 534233 | 100% | 0 | 0 | 0 | 60617 | 0 | 60617 | 0 |  | technical assistance with beneficiaries, bilateral meetings with stakeholders related to good service practices and possible involvement in future activities |  |  |  | INV
FIN | UNDP | HCFC phase-out management plan (stage I, second tranche) (air conditioning sector plan) | Multi-Year | ASP | IRA | PHA | 68 | INV | 208 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-05-01 | 2015-12-01 |  | 2015-04-01 | 2016-04-01 | 1370000 | 0 | 1370000 | 1370000 | 100% | 0 | 0 | 0 | 102750 | 0 | 102750 | 0 | 0 | Financially completed in 2016. | Activities progressing satisfactorily. Last tranche request for HPMP submitted to and approved in 74th Excom. | 2012 |  | Investment
COM | UNIDO | HCFC phase-out management plan (stage I, second tranche) (foam sector plan) | Multi-Year | ASP | IRA | PHA | 68 | INV | 209 | A | I | HCFC | 11.9 | 11.9 |  |  | 2012-12-01 | 2013-07-01 | 2013-12-31 |  | 2016-12-01 |  | 830000 | 0 | 830000 | 660537.14 | 79.58% | 169462.86 | 167176.51 | 150000 | 62250 | 0 | 49540 | 12710 | 12538.2383 | Monitoring of equipment operation and effective HCFC-141b phase-out. Project completed in August 2016. | Project completed. |  |  | INV
FIN | UNDP | HCFC phase-out management plan (stage I, third tranche) (air conditioning sector plan and project management unit) | Multi-Year | ASP | IRA | PHA | 72 | INV | 211 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 | 2015-03-01 | 2016-05-01 |  | 2015-12-01 | 2016-12-01 | 477816 | 0 | 477816 | 477816 | 100% | 0 | 0 | 0 | 35836 | 0 | 35836 | 0 | 0 | Financially completed in 2016. | Activities progressing satisfactorily. Last tranche request for HPMP submitted to and approved in 74th Excom. |  |  | Investment
COM | UNIDO | HCFC phase-out management plan (stage I, third tranche) (foam sector plan) | Multi-Year | ASP | IRA | PHA | 72 | INV | 215 | A | I | HCFC | 1.2 | 1.2 |  |  | 2014-05-01 | 2015-04-01 | 2016-05-31 |  | 2016-12-01 |  | 101450 | 0 | 101450 | 11752.51 | 11.58% | 89697.49 | 85909.86 | 80000 | 7609 | 0 | 881 | 6728 | 6443 | The third and fourth tranches of Stage I HPMP cover the final payment to Emersun. (This is a reimbursable loan.) - The company has received all the equipment in Sept 2016. - Monitoring of equipment operation and effective HCFC-141b phase-out. | Project completed. |  |  | INV
ONG | UNEP | Preparation of a HCFC phase-out management plan (stage II) | Multi-Year | ASP | IRA | PHA | 72 | PRP | 212 | A | I |  | 0 |  | 0 |  | 2014-05-01 | 2015-06-01 | 2016-05-01 | 2017-06-01 |  |  | 25000 | 0 | 25000 | 0 | 0% | 25000 | 0 | 2500 | 3250 | 0 | 0 | 3250 | 0 | Newly approved project | Brief progress report (actual/planned): The whole Project Documents for Stage 2 needs to be redefined and action plan is udner development.
COM | Germany | Preparation of a HCFC phase-out management plan (stage II) | Individual | ASP | IRA | PHA | 72 | PRP | 214 | A | I | HCFC | 0 |  | 0 |  | 2014-05-01 | 2015-05-01 | 2016-05-01 |  | 2016-11-01 |  | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 |  | preparation of project proposal Stage II (stakeholder dialogue, sector survey)
ONG | UNDP | Preparation of a HCFC phase-out management plan (stage II) | Individual | ASP | IRA | PHA | 72 | PRP | 216 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 | 2016-12-01 | 2016-05-01 | 2017-06-01 |  |  | 45000 | 0 | 45000 | 10928.46 | 24.29% | 34071.54 | 0 | 13628.616 | 3150 | 0 | 764.9922 | 2385.0078 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Documents related to HPMP Stage I received and reviewed, Compiling initial draft of Stage II, HPMP with inputs from Agencies and NOU, Several meetings with agencies and NOU held in Tehran during August 6 -11, 2016 to clarify data and request for information/data to help finalise the Stage II HPMP Submission of finalized document to MLF secretariat, The initial project document was submitted by UNDP MPU to the MLF Secretariat on August 23, 2016. A lot more work was needed to put the document into proper shape, and with the assistance of UNDP, MPU, the revised document was submitted on September 01, 2016. Several comments were received from the MLF Secretariat, and they were handled by UNDP MPU in consultation with all the partner agencies and final discussions with the Secretariat. The Secretariat uploaded their summarized version of the original prodoc and the results of the subsequent discussions onto their website for the 77th ExCom by document UNEP/OzL.Pro/ExCom/77/50 dated November 5, 2016 Prodoc signed (actual/planned, yes/no and date):Letter of Authorisation sent 21 January 2016 Missions undertaken (actual/planned):1 TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: Contract signed First disbursement date (actual/planned): 42705Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | The remaining commitment will be delivered by June 17 |  |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, fourth tranche) (air conditioning sector plan and project management unit) | Multi-year | ASP | IRA | PHA | 74 | INV | 219 | N | I | HCFC | 0 | 0 | 0 | 0 | 2015-05-01 | 2015-08-01 | 2016-12-01 | 2017-12-01 |  |  | 250430 | 0 | 250430 | 134937 | 53.88% | 115493 | -0.36 | 46197.2 | 18782 | 0 | 10120.1403 | 8661.8597 | -0.027 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): NOU supervised the implementation of conversion projects in HCFCs consuming sectors including foam, refrigeration and air-conditioning. Mer Als project which was aimed to convert the residential air-conditioners production line to R410A was successfully completed in Dec 2015. Prodoc signed (actual/planned, yes/no and date):42309 Missions undertaken (actual/planned):1 TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: Contract signed First disbursement date (actual/planned): 42309Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | De-commissioning and/or destruction of redundant baseline equipment | 2015 |  | Investment |  | To request the submission of additional status report to the 79th meeting to monitor the activities implemented by the project management unit.
ONG | UNIDO | HCFC phase-out management plan (stage I, fourth tranche) (foam sector plan) | Multi-Year | ASP | IRA | PHA | 74 | INV | 220 | A | I | HCFC | 63.1 | 0 |  |  | 2015-05-01 | 2015-11-01 | 2017-05-31 | 2017-12-01 |  |  | 274827 | 0 | 274827 | 37207.83 | 13.54% | 237619.17 | 219547.42 | 120000 | 20612 | 0 | 0 | 20612 | 16466.0565 | The third and fourth tranches of Stage I HPMP cover the final payment to Emersun. (This is a reimbursable loan.) - The company has received all the equipment in Sept 2016. - Monitoring of equipment operation and effective HCFC-141b phase-out. | Actions towards next goals: - Commissioning is expected in May 2017. - Final payment to Emersun to be processed. - A company in Masshab will be visited for verification in April 2017. - No delay - No recurring problem - No impact on project completion date - No action required by Executive Committee |  |  | INV
COM | Germany | HCFC phase-out management plan (stage I, fourth tranche) (refrigeration servicing sector) | Multi-Year | ASP | IRA | PHA | 74 | INV | 221 | A | I | HCFC | 0 |  | 0 |  | 2015-05-01 | 2015-07-01 | 2015-12-01 |  | Dec-16 |  | 288582 | 0 | 288582 | 288582 | 100% | 0 | 0 | 0 | 32744 | 0 | 32744 | 0 |  | technical assistance with beneficiaries, bilateral meetings with stakeholders related to good service practices and possible involvement in future activities
ONG | Italy | HCFC phase-out management plan (stage II, first tranche) (foam sector) | Multi-Year | ASP | IRA | PHA | 77 | INV | 224 | A | I | HCFC | 7.1 |  | 0 |  | 2016-12-01 |  | 2019-12-01 | 2019-12-01 |  |  | 403203 | 0 | 403203 | 0 | 0% | 403203 | 0 | 100000 | 48797 | 0 | 0 | 48797 |  | The Stage II HPMP was approved at the 77th ExCom Meeting in December 2016. - The Government of Italy and UNIDO have started to initiate the preparation of a trust fund agreement (see latest remarks for details on the state of the art). | - The Trust Fund Agreement between the Government of Italy and UNIDO entrusting UNIDO as executing agency on behalf of the Government of Italy has been signed on 6 March 2017. Funds are expected to be transferred to UNIDO during May 2017. - The budget has been set up. Actions towards next goals: - A mission by UNIDO is planned in May 2017 for verifying the conversion. - Contracts will be processed. - The national consultant will visit other companies and will agree on the conversion modality. - A list of updated company/equipment list plans to be submitted to MLF within this year. - No delay - No recurring problem - No impact on project completion date - No action required by Executive Committee | 2016
ONG | Germany | HCFC phase-out management plan (stage II, first tranche) (foam sector) |  | ASP | IRA | PHA | 77 | INV | 225 | A | I | HCFC | 3.6 |  | 0 |  | 2016-12-01 |  | 2018-12-01 | 2018-12-01 |  |  | 645500 | 0 | 645500 |  | 0% | 645500 | 0 | 380000 | 73420 | 0 |  | 73420 |  |  | Kick-off meeting for foam sector held in February 2017, kick off meeting for commerical refrigration planned for May 2017, preparation of procurement, selection of beneficiaries
ONG | UNDP | HCFC phase-out management plan (stage II, first tranche) (foam sector) | Multi-year | ASP | IRA | PHA | 77 | INV | 226 | N | I | HCFC | 23.8 | 0 | 0 | 0 | 2016-12-01 |  | 2019-12-01 | 2017-12-01 |  |  | 1298170 | 0 | 1298170 | 0 | 0% | 1298170 | 0 | 519268 | 90872 | 0 | 0 | 90872 | 0 | Newly Approved | Awaiting AWP for DoA issuance. | 2016 |  | Investment
ONG | UNIDO | HCFC phase-out management plan (stage II, first tranche) (foam sector) | Multi-Year | ASP | IRA | PHA | 77 | INV | 228 | A | I | HCFC | 8.4 | 0 |  |  | 2016-11-01 |  | 2019-12-31 | 2019-12-01 |  |  | 473567 | 0 | 473567 | 0 | 0% | 473567 | 0 | 40000 | 33150 | 0 | 0 | 33150 | 0 | Approved in accordance with the Agreement between the Government and the Executive Committee for the period 2016 to 2023 to reduce HCFC consumption by 75 per cent of the baseline, noting that the approach taken for the refrigeration and air-conditioning sector was agreed on an exceptional basis owing to the special circumstances in the country. Noted the commitment of the Government to reduce HCFC consumption by 75 per cent by 2023; and to issue a ban on import and use of HCFC-141b pure or contained in pre-blended polyols upon completion of the conversion of all the eligible enterprises and no later than 1 July 2023, a ban on new manufacturing capacity using HCFC-22 by 1 January 2020, and a ban on the use of HCFC-22 in manufacturing of refrigeration and air conditioning equipment upon completion of the conversions of all the eligible enterprises and no later than 1 January 2023. The Government, UNDP, UNEP, UNIDO and Germany were requested to deduct 162.37 ODP tonnes of HCFCs from the remaining HCFC consumption eligible for funding. UNDP was requested to include in the submission of the request for the second funding tranche a report on the results of the conversion of the first 15 enterprises in the refrigeration and air-conditioning manufacturing sector to low-global warming potential alternatives highlighting lessons learned and challenges faced. | - An additional inventory number has been requested from the MLFS by UNIDO in order to differentiate and separate activities under the foam and the refrigeration servicing sectors. - The first tranche in the refrigeration servicing sector is budgeted to US$ 84,000, which will be deducted from the USD 437,567. Refrigeration servicing sector: - Work plan is being negotiated with the cooperating implementing agency, UNEP and the NOU. - The specification/purchase/delivery of training equipment for 6 training centers in different provinces of Iran is being negotiated with the cooperating implementing agency, UNEP and the NOU. Foam sector activities: - All the companies listed in the project document have been revisited. It was found that, among those, 4 companies are closed (Hanzad, Tara Sanat Barfin (SEP and Afrouz), Javad Hasani (Mamut Delijan), and Shiller (Favanvari Novin Shiller), 2 companies retrofitted their equipment for conversion to cyclopentane (Aysan Sanat in October 2016 and Forouzan in April 2016). Javaheran in Tabriz will complete its conversion in April 2017. - A national consultant has been selected and agreed by NOU. Actions towards next goals: - A mission by UNIDO is planned in April 2017 for verifying the conversion. - Retroactive incremental capital/operational cost contracts will be processed. - The national consultant will visit other companies and will agree on the conversion modality. - A list of updated company/equipment list plans to be submitted to MLF this year. - No delay - No recurring problem - No impact on project completion date - No action required by Executive Committee
ONG | UNEP | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | Multi-Year | ASP | IRA | PHA | 77 | TAS | 227 | A | I |  | 2.3 |  | 0 |  | 2016-12-01 |  | 2018-12-01 | 2018-12-01 |  |  | 200000 | 0 | 200000 | 0 | 0% | 200000 | 0 | 20000 | 24857 | 0 | 0 | 24857 | 0 | Newly approved project | Brief progress report (actual/planned): IACM in Feb 2017 organized with UNDP, UNIDO, GIZ and NOU Legal arrangements(actual/planned): SSFA in process First mission (actual/planned): February 2017 TOR completed(actual/planned): drafted for a local consultant to coordinate the UNEP component First disbursement date (actual/planned): Not yet All funds disbursed (yes/no): No Any delay? (yes/no): ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___
FIN | UNIDO | Preparatory assistance for phase out of ODS in domestic refrigeration industry | Individual | ASP | IRA | REF | 09 | PRP | 07 | A | I |  | 0 | 0 |  |  | 1993-03-01 | 1993-07-01 | 1993-06-01 |  | 1996-05-01 | 1998-08-01 | 50000 | 13633 | 63633 | 63633 | 100% | 0 | 0 |  | 6500 | 1772 | 8272 | 0 | 0 | FIN
FIN | UNIDO | Conversion of domestic refrigerator production facilities to phase-out CFC-11 and CFC-12 | Individual | ASP | IRA | REF | 11 | INV | 08 | A | I | CFC | 757 | 757 |  |  | 1993-11-01 | 1994-12-01 | 1995-11-01 |  | 1997-12-01 | 2002-09-01 | 3228395 | 5674963 | 8903358 | 8903358 | 100% | 0 | 0 |  | 419691 | 735911 | 1155602 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project for phase-out of CFC-11 and CFC-12 in the commercial and small domestic refrigeration industry | Individual | ASP | IRA | REF | 15 | PRP | 09 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-02-01 | 1995-06-01 |  | 1997-12-01 | 1998-05-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0 | FIN
FIN | UNIDO | Conversion of domestic refrigerator production facilities to phase out CFC-12 and CFC-11 (2nd group) at Movalled Home Appliances Co. | Individual | ASP | IRA | REF | 18 | INV | 12 | A | I | CFC | 70 | 70 |  |  | 1995-11-01 | 1996-05-01 | 1997-11-01 |  | 1998-12-01 | 2002-09-01 | 607732 | -1500 | 606232 | 606231.7394 | 100% | 0.2606 | 0 |  | 79005 | -320 | 78685 | 0 | 0 | FIN
FIN | UNIDO | Conversion of domestic refrigerator production facilities to phase out CFC-12 and CFC-11 (2nd group) at Pars Machine Manufacturing Co. | Individual | ASP | IRA | REF | 18 | INV | 13 | A | I | CFC | 62 | 62 |  |  | 1995-11-01 | 1996-05-01 | 1997-11-01 |  | 1998-12-01 | 2002-09-01 | 608605 | -1737 | 606868 | 606867.5278 | 100% | 0.4722 | 0 |  | 79119 | -351 | 78768 | 0 | 0 | FIN
FIN | UNIDO | Conversion of domestic refrigerator production facilities to phase out CFC-12 and CFC-11 (2nd group) at Lorestan Refrigerator Manufacturing Industries | Individual | ASP | IRA | REF | 18 | INV | 14 | A | I | CFC | 94 | 94 |  |  | 1995-11-01 | 1996-05-01 | 1997-11-01 |  | 1998-12-01 | 2002-09-01 | 615018 | -1793 | 613225 | 613225.4118 | 100% | -0.4118 | 0 |  | 79952 | -359 | 79593 | 0 | 0 | FIN
FIN | UNIDO | Conversion of domestic refrigerator production facilities to phase out CFC-12 and CFC-11 (2nd group) at Gadook Industries, Co. | Individual | ASP | IRA | REF | 18 | INV | 15 | A | I | CFC | 18.5 | 18.5 |  |  | 1995-11-01 | 1996-05-01 | 1997-11-01 |  | 1998-12-01 | 2002-09-01 | 373838 | -944 | 372894 | 372894.3966 | 100% | -0.3966 | 0 |  | 48599 | -200 | 48399 | 0 | 0 | FIN
FIN | UNIDO | Conversion of domestic refrigerator production facilities to phase out CFC-12 and CFC-11 (2nd group) at Faritz, Iran | Individual | ASP | IRA | REF | 18 | INV | 16 | A | I | CFC | 109 | 109 |  |  | 1995-11-01 | 1996-05-01 | 1997-11-01 |  | 1998-12-01 | 2002-09-01 | 612504 | -1822 | 610682 | 610682.2582 | 100% | -0.2582 | 0 |  | 79626 | -363 | 79263 | 0 | 0 | FIN
FIN | UNIDO | Conversion of domestic refrigerator production facilities to phase out CFC-12 and CFC-11 (2nd group) at Pars Monark Co. | Individual | ASP | IRA | REF | 18 | INV | 17 | A | I | CFC | 18.5 | 18.5 |  |  | 1995-11-01 | 1996-05-01 | 1997-11-01 |  | 1998-12-01 | 2002-09-01 | 369939 | -859 | 369080 | 369079.6662 | 100% | 0.3338 | 0 |  | 48092 | -188 | 47904 | 0 | 0 | FIN
FIN | France | Project preparation/technical assistance for MAC recycling and training in good servicing practices |  | ASP | IRA | REF | 20 | PRP | 18 | A | I |  | 0 |  | 0 |  | 1996-10-01 | 1997-01-01 | 1997-10-01 |  | 1997-08-01 | 1997-09-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed.
FIN | UNIDO | Phasing out ODS at Electro Steel Co. | Individual | ASP | IRA | REF | 23 | INV | 24 | A | I | CFC | 120 | 120 |  |  | 1997-11-01 | 1998-06-01 | 1999-12-01 |  | 1999-12-01 | 2003-05-01 | 898159 | -20754 | 877405 | 877404.93 | 100% | 0.07 | 0 |  | 116761 | -2879 | 113882 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Yakh Chavan Manufacturing Company | Individual | ASP | IRA | REF | 23 | INV | 25 | A | I | CFC | 41.8 | 41.8 |  |  | 1997-11-01 | 1998-06-01 | 1999-12-01 |  | 1999-12-01 | 2003-03-01 | 527802 | 0 | 527802 | 527801.81 | 100% | 0.19 | 0 |  | 68614 | 0 | 68614 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Yakh Saran Co. | Individual | ASP | IRA | REF | 23 | INV | 26 | A | I | CFC | 34 | 34 |  |  | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 2002-06-01 | 2003-10-01 | 458663 | -2976 | 455687 | 455687.08 | 100% | -0.08 | 0 |  | 59626 | -481 | 59145 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Zagross II Co. | Individual | ASP | IRA | REF | 23 | INV | 28 | A | I | CFC | 34 | 34 |  |  | 1997-11-01 | 1998-06-01 | 1999-12-01 |  | 1999-12-01 | 2003-05-01 | 444858 | -3734 | 441124 | 441123.94 | 100% | 0.06 | 0 |  | 57832 | -577 | 57255 | 0 | 0 | FIN
FIN | France | Set up of a national programme of recovery and recycling CFC-12 (pilot project in Tehran) |  | ASP | IRA | REF | 23 | TAS | 31 | A | I |  | 0 |  | 0 |  | 1997-11-01 | 1999-10-01 | 1998-12-01 |  | 2004-12-01 | 2004-12-01 | 345923 | -103154.97 | 242768.03 | 242768 | 100% | 0.03 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed; balance returned at the 57th meeting.
FIN | France | Conversion to non-CFC facilities of 4 companies producing cars and wagons equipped with MAC-umbrella project |  | ASP | IRA | REF | 24 | INV | 34 | A | I |  | 0 |  | 0 |  | 1998-03-01 | 2000-02-01 | 1999-04-01 |  | 2002-06-01 | 2008-09-01 | 138600 | -35471 | 103129 | 103129 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed. |  |  | 2002-06-01
FIN | UNIDO | Replacement of CFC-11 foam blowing agent with HCFC-141b and CFC-12 refrigerant with HCFC-134a in manufacture of commercial refrigeration equipment at Sobouhi Refrigeration | Individual | ASP | IRA | REF | 26 | INV | 35 | A | I | CFC | 30.4 | 30.4 |  |  | 1998-11-01 | 1999-01-01 | 2000-12-01 |  | 1999-12-01 | 2001-07-01 | 237847 | -23768 | 214079 | 214078.79 | 100% | 0.21 | 0 |  | 30920 | -3134 | 27786 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-11 foam blowing agent with HCFC-141b in manufacture of commercial refrigeration equipment at Yazd Arg Metal, Yazd Sardin and Shervin Electric | Individual | ASP | IRA | REF | 26 | INV | 37 | A | I | CFC | 62.2 | 62.2 |  |  | 1998-11-01 | 1999-01-01 | 2000-12-01 |  | 1999-12-01 | 2003-02-01 | 743990 | -95365 | 648625 | 648625.39 | 100% | -0.39 | 0 |  | 91839 | -10603 | 81236 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in the commercial refrigeration sector | Individual | ASP | IRA | REF | 27 | PRP | 38 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-05-01 | 1999-12-01 |  | 2000-12-01 | 2001-09-01 | 20000 | -1807 | 18193 | 18192.87 | 100% | 0.13 | 0 |  | 2600 | -239 | 2361 | 0 | 0 | FIN
FIN | UNDP | Preparation of three projects in the commercial refrigeration subsector | Individual | ASP | IRA | REF | 27 | PRP | 41 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-12-01 | 2004-01-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2000. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and domestic refrigeration at the Sherkate Sanayee Emerson (Emerson Co). | Individual | ASP | IRA | REF | 28 | INV | 42 | A | I | CFC | 45.8 | 45.8 |  |  | 1999-07-01 | 1999-09-01 | 2001-08-01 |  | 2001-12-01 | 2003-05-01 | 343873 | -10039 | 333834 | 333833.93 | 100% | 0.07 | 0 |  | 44703 | -1373 | 43330 | 0 | 0 | FIN
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Foroughmanesh Co. | Individual | ASP | IRA | REF | 28 | INV | 43 | A | I | CFC | 35.8 | 35.8 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2002-02-01 |  | 2000-12-01 | 2003-09-01 | 399803 | -13456 | 386347 | 386347 | 100% | 0 | 0 | 0 | 51974.39 | -1749.18 | 50225.21 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Tahvieh Garm va Sard Co. | Individual | ASP | IRA | REF | 28 | INV | 44 | A | I | CFC | 20.5 | 20.5 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2002-02-01 |  | 2000-12-01 | 2003-02-01 | 278659 | -13367 | 265292 | 265292 | 100% | 0 | 0 | 0 | 36225.67 | -1738 | 34487.67 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b AND cfc-12 TO hfc-134A in commercial refrigeration at the second group of Iranian Commercial Refrigeration Manufacturers | Individual | ASP | IRA | REF | 28 | INV | 45 | A | I | CFC | 42.5 | 42.5 |  |  | 1999-07-01 | 1999-09-01 | 2001-08-01 |  | 2001-12-01 | 2003-09-01 | 309966 | -1621 | 308345 | 308345.18 | 100% | -0.18 | 0 |  | 40296 | -275 | 40021 | 0 | 0 | FIN
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Movaledsarma Co. (Zagross 1) | Individual | ASP | IRA | REF | 28 | INV | 46 | A | I | CFC | 77.6 | 77.6 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2002-02-01 |  | 2000-12-01 | 2004-01-01 | 816698 | -12094.36 | 804603.64 | 804604 | 100% | -0.36 | 0 | 0 | 99836.78 | -1330.41 | 98506.4145 | -0.044474 | 0 | Completed in 2000. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration at the Sherkate Broudati Ghandil Iran (Ghandil Co.) | Individual | ASP | IRA | REF | 28 | INV | 47 | A | I | CFC | 27.5 | 27.5 |  |  | 1999-07-01 | 1999-09-01 | 2001-08-01 |  | 2001-12-01 | 2002-12-01 | 335423 | -3923 | 331500 | 331499.51 | 100% | 0.49 | 0 |  | 43605 | -578 | 43027 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-12 refrigerant by HFC-134a at Iran Compressor Manufacturing Company (ICMC) | Individual | ASP | IRA | REF | 28 | INV | 51 | A | I | CFC | 0 | 0 |  |  | 1999-07-01 | 1999-11-01 | 2001-08-01 |  | 2008-08-01 | 2009-09-01 | 1076148 | 58673 | 1134821 | 1134821.36 | 100% | -0.36 | 0 |  | 128376 | 6454 | 134830 | 0 | 0 | FIN
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HCFC-134a technology in the manufacture of commercial refrigeration equipment at Behsarma Co. | Individual | ASP | IRA | REF | 28 | INV | 65 | A | I | CFC | 34.5 | 34.5 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2002-02-01 |  | 2000-12-01 | 2003-09-01 | 455593 | -13588 | 442005 | 442005 | 100% | 0 | 0 | 0 | 59227.09 | -1766.34 | 57460.75 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration at the Saiwan Sannat Co. | Individual | ASP | IRA | REF | 29 | INV | 52 | A | I | CFC | 14.9 | 14.9 |  |  | 1999-11-01 | 2000-01-01 | 2001-12-01 |  | 2002-12-01 | 2003-03-01 | 200709 | 0 | 200709 | 200709 | 100% | 0 | 0 |  | 26092 | 0 | 26092 | 0 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration at the Sherkate Sanaayee Toulidy Bard Co. | Individual | ASP | IRA | REF | 29 | INV | 53 | A | I | CFC | 16.4 | 16.4 |  |  | 1999-11-01 | 2000-01-01 | 2001-12-01 |  | 2002-12-01 | 2003-12-01 | 205529 | 0 | 205529 | 205528.61 | 100% | 0.39 | 0 |  | 26719 | 0 | 26718 | 1 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration at the Minavand Refrigeration Company | Individual | ASP | IRA | REF | 29 | INV | 54 | A | I | CFC | 13.4 | 13.4 |  |  | 1999-11-01 | 2000-01-01 | 2001-12-01 |  | 2002-12-01 | 2003-12-01 | 176777 | -3308 | 173469 | 173468.82 | 100% | 0.18 | 0 |  | 22981 | -466 | 22515 | 0 | 0 | FIN
FIN | UNDP | Conversion from CFC-11 tgo HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Electro Shargh Mazandaran Co. | Individual | ASP | IRA | REF | 29 | INV | 55 | A | I | CFC | 28.2 | 28.2 | 0 | 0 | 1999-11-01 | 2001-05-01 | 2002-12-01 |  | 2002-07-01 | 2003-11-01 | 301715 | -31900 | 269815 | 269815 | 100% | 0 | 0 | 0 | 39222.95 | -4146.87 | 35076.08 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Sardkaran Industrial Manufacturing Co. | Individual | ASP | IRA | REF | 29 | INV | 56 | A | I | CFC | 25.3 | 25.3 | 0 | 0 | 1999-11-01 | 2001-02-01 | 2002-12-01 |  | 2002-03-01 | 2003-11-01 | 155405 | -6082 | 149323 | 149323 | 100% | 0 | 0 | 0 | 20202.65 | -790.66 | 19411.99 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Khozestan Technique Co. | Individual | ASP | IRA | REF | 29 | INV | 58 | A | I | CFC | 9.6 | 9.6 | 0 | 0 | 1999-11-01 | 2001-06-01 | 2002-12-01 |  | 2002-07-01 | 2003-04-01 | 132041 | -1 | 132040 | 132040 | 100% | 0 | 0 | 0 | 17165.33 | 0 | 17165.33 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration at the Forouzan Yakhchal Company (Forouzan Ref. Co.) | Individual | ASP | IRA | REF | 29 | INV | 59 | A | I | CFC | 16.7 | 16.7 |  |  | 1999-11-01 | 2000-01-01 | 2001-12-01 |  | 2002-12-01 | 2003-12-01 | 192704 | -5358 | 187346 | 187345.54 | 100% | 0.46 | 0 |  | 25052 | -736 | 24316 | 0 | 0 | FIN
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment and rigid polyurethane foam at Electro Sard Azna Co,. | Individual | ASP | IRA | REF | 29 | INV | 60 | A | I | CFC | 18.7 | 18.7 | 0 | 0 | 1999-11-01 | 2001-06-01 | 2002-12-01 |  | 2002-07-01 | 2003-11-01 | 191061 | -33421 | 157640 | 157640 | 100% | 0 | 0 | 0 | 24837.93 | -4344.73 | 20493.2 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNIDO | Preparation of investment projects in the commercial refrigeration sector | Individual | ASP | IRA | REF | 30 | PRP | 61 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-07-01 | 2001-04-01 |  | 2002-05-01 | 2003-02-01 | 30000 | -108 | 29892 | 29891.68 | 100% | 0.32 | 0 |  | 3900 | -20 | 3880 | 0 | 0 | FIN
FIN | UNDP | Preparation of 4 projects in the commercial refrigeration subsector | Individual | ASP | IRA | REF | 30 | PRP | 62 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2000-12-01 | 2006-12-01 | 30000 | -6577 | 23423 | 23423 | 100% | 0 | 0 | 0 | 3900 | -855.01 | 3044.99 | 0 | 0 | Completed in 2000. Financially completed in 2006. |  | 2000 |  | Investment
FIN | UNDP | Preparation of 3 projects in the domestic refrigeration subsector | Individual | ASP | IRA | REF | 30 | PRP | 63 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-07-01 | 2003-01-01 | 20000 | -4385 | 15615 | 15615 | 100% | 0 | 0 | 0 | 2600 | -570.05 | 2029.95 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Prepare 2 projects in the commercial refrigeration subsector | Individual | ASP | IRA | REF | 30 | PRP | 64 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-01-01 | 2001-04-01 |  | 2001-07-01 | 2003-01-01 | 20000 | -4385 | 15615 | 15615 | 100% | 0 | 0 | 0 | 2600 | -570.05 | 2029.95 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Fadak Refrigeration Industries | Individual | ASP | IRA | REF | 31 | INV | 66 | A | I | CFC | 17.3 | 17.3 | 0 | 0 | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2002-11-01 | 2003-11-01 | 258937 | 0 | 258937 | 258937 | 100% | 0 | 0 | 0 | 33661.81 | 0 | 33661.81 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial and domestic refrigeration equipment at Jaleh & Segin Co. | Individual | ASP | IRA | REF | 31 | INV | 67 | A | I | CFC | 23.6 | 23.6 | 0 | 0 | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2002-07-01 | 2003-04-01 | 322309 | 0 | 322309 | 322309 | 100% | 0 | 0 | 0 | 41900.17 | 0 | 41900.17 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at MH Seyed Salaki Co. | Individual | ASP | IRA | REF | 31 | INV | 68 | A | I | CFC | 9.8 | 9.8 | 0 | 0 | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2002-07-01 | 2003-04-01 | 141590 | 0 | 141590 | 141590 | 100% | 0 | 0 | 0 | 18406.7 | 0 | 18406.7 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration at Sanayee Broudati Partou Sard Tawan (Barez-Himalia) and Sanayee Broudati Himalia (Himalia) | Individual | ASP | IRA | REF | 31 | INV | 69 | A | I | CFC | 36.09 | 36.09 |  |  | 2000-07-01 | 2000-11-01 | 2003-08-01 |  | 2002-12-01 | 2004-06-01 | 377544 | -3754 | 373790 | 373789.7 | 100% | 0.3 | 0 |  | 49081 | -565 | 48516 | 0 | 0 | FIN
CLO | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment and rigid polyurethane foam at Baharanfarr Co. | Individual | ASP | IRA | REF | 31 | INV | 70 | A | I | CFC | 0 | 0 | 0 | 0 | 2000-07-01 | 2002-01-01 | 2003-08-01 |  |  | 2002-11-01 | 208070 | -207415 | 655 | 655 | 100% | 0 | 0 | 0 | 27049.1 | -26963.95 | 85.15 | 0 | 0 | Canceled in 2002. Financially completed in 2002. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Fereidooni Refrigerant Industries | Individual | ASP | IRA | REF | 31 | INV | 71 | A | I | CFC | 10.4 | 10.4 | 0 | 0 | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2002-07-01 | 2003-11-01 | 157454 | 0 | 157454 | 157454 | 100% | 0 | 0 | 0 | 20469.02 | 0 | 20469.02 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNIDO | Strategy for the preparation of an RMP | Individual | ASP | IRA | REF | 31 | PRP | 72 | A | I |  | 0 | 0 |  |  | 2000-07-01 | 2001-04-01 | 2002-01-01 |  | 2002-08-01 | 2003-02-01 | 70000 | -1431 | 68569 | 68568.92 | 100% | 0.08 | 0 |  | 9100 | -200 | 8900 | 0 | 0 | FIN
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Hanzad Co. | Individual | ASP | IRA | REF | 34 | INV | 100 | A | I | CFC | 19.8 | 19.8 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2004-08-01 |  | 2003-08-01 | 2007-03-01 | 199627 | -28424 | 171203 | 171203 | 100% | 0 | 0 | 0 | 25951.51 | -3695.19 | 22256.3202 | -0.0002 | 0 | Completed in 2003. Financially completed in 2007. |  | 2000 |  | Investment
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at the Tehran Shirak | Individual | ASP | IRA | REF | 34 | INV | 101 | A | I | CFC | 20.5 | 20.5 |  |  | 2001-07-01 | 2001-11-01 | 2003-12-01 |  | 2004-06-01 | 2005-09-01 | 202836 | -1649 | 201187 | 201186.61 | 100% | 0.39 | 0 |  | 26369 | -256 | 26113 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at the Donyaye Mojdeh | Individual | ASP | IRA | REF | 34 | INV | 103 | A | I | CFC | 15.4 | 15.4 |  |  | 2001-07-01 | 2001-11-01 | 2003-12-01 |  | 2004-06-01 | 2004-09-01 | 191020 | -2225 | 188795 | 188794.71 | 100% | 0.29 | 0 |  | 24833 | -329 | 24504 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at the Zarifan Mashad | Individual | ASP | IRA | REF | 34 | INV | 104 | A | I | CFC | 22 | 22 |  |  | 2001-07-01 | 2002-03-01 | 2003-12-01 |  | 2004-06-01 | 2005-12-01 | 200550 | -1183 | 199367 | 199367.16 | 100% | -0.16 | 0 |  | 26072 | -195 | 25877 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at the Novin Enjemad | Individual | ASP | IRA | REF | 34 | INV | 105 | A | I | CFC | 10.1 | 10.1 |  |  | 2001-07-01 | 2001-11-01 | 2003-12-01 |  | 2003-12-01 | 2004-09-01 | 138702 | -1665 | 137037 | 137037.35 | 100% | -0.35 | 0 |  | 18031 | -244 | 17787 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at the Roshan Ind. Group | Individual | ASP | IRA | REF | 34 | INV | 107 | A | I | CFC | 18.6 | 18.6 |  |  | 2001-07-01 | 2001-11-01 | 2003-12-01 |  | 2004-06-01 | 2006-03-01 | 203960 | -5201 | 198759 | 198759.1 | 100% | -0.1 | 0 |  | 26515 | -717 | 25798 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at the Avaj Sarma Co. | Individual | ASP | IRA | REF | 34 | INV | 108 | A | I | CFC | 15.2 | 15.2 |  |  | 2001-07-01 | 2001-11-01 | 2004-08-01 |  | 2004-06-01 | 2005-08-01 | 176477 | -534 | 175943 | 175943.3 | 100% | -0.3 | 0 |  | 22942 | -106 | 22836 | 0 | 0 | FIN |  |  |  | INV
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Sana Commercial Co. | Individual | ASP | IRA | REF | 34 | INV | 109 | A | I | CFC | 11.4 | 11.4 | 0 | 0 | 2001-07-01 | 2002-05-01 | 2004-08-01 |  | 2004-11-01 | 2005-11-01 | 156286 | -367 | 155919 | 155919 | 100% | 0 | 0 | 0 | 20317.18 | -47.71 | 20269.4704 | -0.000391 | 0 | Completed in 2004. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators and freezers at Golsarma Co. | Individual | ASP | IRA | REF | 34 | INV | 110 | A | I | CFC | 28.3 | 28.3 | 0 | 0 | 2001-07-01 | 2002-05-01 | 2004-08-01 |  | 2003-06-01 | 2003-12-01 | 230066 | -13115 | 216951 | 216951 | 100% | 0 | 0 | 0 | 29908.58 | -1705 | 28203.58 | 0 | 0 | Completed in 2003. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration at the Arjah Boroudat Co. | Individual | ASP | IRA | REF | 34 | INV | 111 | A | I | CFC | 27.4 | 27.4 |  |  | 2001-07-01 | 2001-11-01 | 2003-12-01 |  | 2005-06-01 | 2006-09-01 | 209425 | -304 | 209121 | 209121.07 | 100% | -0.07 | 0 |  | 27225 | -39 | 27186 | 0 | 0 | FIN |  |  |  | INV
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators and freezers at Shagayegh Boroudat Co. | Individual | ASP | IRA | REF | 34 | INV | 112 | A | I | CFC | 10 | 10 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2002-11-01 | 2004-01-01 | 137985 | -514 | 137471 | 137471 | 100% | 0 | 0 | 0 | 17938.05 | -67 | 17871.05 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at the Gasso Co. | Individual | ASP | IRA | REF | 34 | INV | 113 | A | I | CFC | 11.7 | 11.7 |  |  | 2001-07-01 | 2001-11-01 | 2003-12-01 |  | 2004-06-01 | 2006-03-01 | 158232 | -4811 | 153421 | 153421.46 | 100% | -0.46 | 0 |  | 20570 | -657 | 19913 | 0 | 0 | FIN |  |  |  | INV
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators and freezers at Yakhchalsazi Yazd Co. | Individual | ASP | IRA | REF | 34 | INV | 82 | A | I | CFC | 30 | 30 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2003-06-01 | 2003-12-01 | 248646 | -43159 | 205487 | 205487 | 100% | 0 | 0 | 0 | 32323.98 | -5611 | 26712.98 | 0 | 0 | Completed in 2003. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Rezvan Co. | Individual | ASP | IRA | REF | 34 | INV | 84 | A | I | CFC | 13.2 | 13.2 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2003-09-01 | 2005-09-01 | 182182 | -34099 | 148083 | 148083 | 100% | 0 | 0 | 0 | 23683.66 | -4432.93 | 19250.7264 | 0.0036 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Electro Ara Co. | Individual | ASP | IRA | REF | 34 | INV | 85 | A | I | CFC | 13 | 13 | 0 | 0 | 2001-07-01 | 2002-07-01 | 2004-08-01 |  | 2003-06-01 | 2007-02-01 | 178784 | -45309 | 133475 | 133475 | 100% | 0 | 0 | 0 | 23241.92 | -5890.19 | 17351.7297 | 0.0003 | 0 | Completed in 2003. Financially completed in 2007. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators and freezers at Boloorin Yazd Refrigerator Co. | Individual | ASP | IRA | REF | 34 | INV | 86 | A | I | CFC | 20.5 | 20.5 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2004-08-01 |  | 2003-06-01 | 2005-09-01 | 212320 | -37255 | 175065 | 175065 | 100% | 0 | 0 | 0 | 27601.6 | -4843 | 22758.6 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators and freezers at Sarmaye Sepahan Co. | Individual | ASP | IRA | REF | 34 | INV | 87 | A | I | CFC | 10.8 | 10.8 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2002-11-01 | 2004-01-01 | 148525 | 0 | 148525 | 148525 | 100% | 0 | 0 | 0 | 19308.25 | 0 | 19308.25 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Mersun Co. | Individual | ASP | IRA | REF | 34 | INV | 89 | A | I | CFC | 11.8 | 11.8 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2003-08-01 | 2005-10-01 | 162891 | -25194 | 137697 | 137697 | 100% | 0 | 0 | 0 | 21175.83 | -3275 | 17900.83 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Ideal Sardsir Co. | Individual | ASP | IRA | REF | 34 | INV | 90 | A | I | CFC | 16.2 | 16.2 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2004-08-01 |  | 2003-09-01 | 2005-09-01 | 187907 | -13311 | 174596 | 174596 | 100% | 0 | 0 | 0 | 24427.91 | -1730 | 22697.91 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Parsa Sazan Co. | Individual | ASP | IRA | REF | 34 | INV | 91 | A | I | CFC | 20 | 20 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2004-08-01 |  | 2003-08-01 | 2005-09-01 | 212845 | -60001 | 152844 | 152844 | 100% | 0 | 0 | 0 | 27669.85 | -7800 | 19869.85 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Zenoz Sanaat Co. | Individual | ASP | IRA | REF | 34 | INV | 92 | A | I | CFC | 10.2 | 10.2 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2002-11-01 | 2003-12-01 | 140036 | 0 | 140036 | 140036 | 100% | 0 | 0 | 0 | 18204.68 | 0 | 18204.68 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Sanaye Part | Individual | ASP | IRA | REF | 34 | INV | 93 | A | I | CFC | 8.2 | 8.2 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2003-06-01 | 2005-10-01 | 114770 | 0 | 114770 | 114770 | 100% | 0 | 0 | 0 | 14920.1 | 0 | 14920.1 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Sepand Afroz Co. | Individual | ASP | IRA | REF | 34 | INV | 94 | A | I | CFC | 12.6 | 12.6 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2003-08-01 | 2005-09-01 | 172881 | -13071 | 159810 | 159810 | 100% | 0 | 0 | 0 | 22474.53 | -1699 | 20775.53 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Yakhchalsazi Anzabi Co. | Individual | ASP | IRA | REF | 34 | INV | 95 | A | I | CFC | 10.1 | 10.1 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2004-11-01 | 2005-11-01 | 138935 | -17 | 138918 | 138918 | 100% | 0 | 0 | 0 | 18061.55 | -2.21 | 18059.34 | 3.8e-05 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators and freezers at General Industries | Individual | ASP | IRA | REF | 34 | INV | 96 | A | I | CFC | 31.1 | 31.1 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2004-08-01 |  | 2004-11-01 | 2005-11-01 | 428197 | 0 | 428197 | 428197 | 100% | 0 | 0 | 0 | 55665.61 | 0 | 55665.61 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Ghaynar Khazar Co. | Individual | ASP | IRA | REF | 34 | INV | 97 | A | I | CFC | 16.8 | 16.8 | 0 | 0 | 2001-07-01 | 2002-05-01 | 2004-08-01 |  | 2002-11-01 | 2003-11-01 | 191092 | -30740 | 160352 | 160352 | 100% | 0 | 0 | 0 | 24841.96 | -3996.33 | 20845.63 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration at the Takran Mobbarad Co. | Individual | ASP | IRA | REF | 34 | INV | 98 | A | I | CFC | 9.6 | 9.6 |  |  | 2001-07-01 | 2001-11-01 | 2003-12-01 |  | 2003-12-01 | 2004-09-01 | 119864 | -2915 | 116949 | 116948.51 | 100% | 0.49 | 0 |  | 15582 | -403 | 15179 | 0 | 0 | FIN |  |  |  | INV
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Ojan Cooling Industries | Individual | ASP | IRA | REF | 34 | INV | 99 | A | I | CFC | 7.5 | 7.5 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2004-08-01 |  | 2003-06-01 | 2004-01-01 | 110863 | 0 | 110863 | 110863 | 100% | 0 | 0 | 0 | 14412.19 | 0 | 14412.19 | 0 | 0 | Completed in 2003. Financially completed in 2004. |  | 2001 |  | Investment
FIN | UNIDO | Preparation of 12 investment projects in the commercial refrigeration sector | Individual | ASP | IRA | REF | 34 | PRP | 102 | A | I |  | 0 | 0 |  |  | 2001-07-01 | 2001-10-01 | 2002-08-01 |  | 2002-12-01 | 2003-02-01 | 15000 | -403 | 14597 | 14597.4 | 100% | -0.4 | 0 |  | 1950 | -55 | 1895 | 0 | 0 | FIN |  |  |  | INV
FIN | UNDP | Project preparation in the commercial refrigeration sector | Individual | ASP | IRA | REF | 34 | PRP | 81 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-08-01 | 2002-08-01 |  | 2001-12-01 | 2003-07-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Project preparation in the domestic refrigeration sector | Individual | ASP | IRA | REF | 34 | PRP | 83 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-08-01 | 2002-08-01 |  | 2001-12-01 | 2003-07-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Abbaspour Co. | Individual | ASP | IRA | REF | 35 | INV | 119 | A | I | CFC | 9.7 | 9.7 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 | 2004-09-01 | 144206 | -741 | 143465 | 143464.74 | 100% | 0.26 | 0 |  | 18747 | -126 | 18621 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Moradi Company | Individual | ASP | IRA | REF | 35 | INV | 120 | A | I | CFC | 6.4 | 6.4 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-12-01 | 2006-03-01 | 82400 | -2031 | 80369 | 80368.84 | 100% | 0.16 | 0 |  | 10712 | -281 | 10431 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Bouran Saz Karaj (Kohsar Co.) | Individual | ASP | IRA | REF | 35 | INV | 121 | A | I | CFC | 9.6 | 9.6 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 | 2004-09-01 | 120526 | -2024 | 118502 | 118501.73 | 100% | 0.27 | 0 |  | 15668 | -287 | 15381 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at the Sherkate Taavoni 435 (Khorsandi Co.) | Individual | ASP | IRA | REF | 35 | INV | 122 | A | I | CFC | 5.4 | 5.4 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 | 2004-09-01 | 82107 | -1871 | 80236 | 80236.24 | 100% | -0.24 | 0 |  | 10674 | -260 | 10414 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Alborz Neishabour | Individual | ASP | IRA | REF | 35 | INV | 123 | A | I | CFC | 16 | 16 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 | 2005-08-01 | 189669 | -4567 | 185102 | 185102.48 | 100% | -0.48 | 0 |  | 24657 | -632 | 24025 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic refrigeration equipment at the Ariz Pooyaye Sanat (Ariz Co.) | Individual | ASP | IRA | REF | 35 | INV | 124 | A | I | CFC | 7.6 | 7.6 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 | 2006-03-01 | 86365 | -3752 | 82613 | 82612.98 | 100% | 0.02 | 0 |  | 11227 | -504 | 10723 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic refrigeration equipment at Yaghoubali Bazdid Vahdat (Isun Co.) | Individual | ASP | IRA | REF | 35 | INV | 125 | A | I | CFC | 10.5 | 10.5 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 | 2004-09-01 | 131605 | -2900 | 128705 | 128704.73 | 100% | 0.27 | 0 |  | 17109 | -404 | 16705 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Darvish Mohamad Nazari Company (Jahan Nama) | Individual | ASP | IRA | REF | 35 | INV | 126 | A | I | CFC | 9.3 | 9.3 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-12-01 | 2006-05-01 | 139970 | -140 | 139830 | 139830.4 | 100% | -0.4 | 0 |  | 18196 | -47 | 18149 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic refrigeration equipment at Borna Sanat Arak | Individual | ASP | IRA | REF | 35 | INV | 127 | A | I | CFC | 8 | 8 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 | 2007-05-01 | 108238 | -802 | 107436 | 107435.59 | 100% | 0.41 | 0 |  | 14071 | -104 | 13967 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Sard Va Garm | Individual | ASP | IRA | REF | 35 | INV | 128 | A | I | CFC | 8.4 | 8.4 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 | 2006-03-01 | 125350 | -4570 | 120780 | 120779.6 | 100% | 0.4 | 0 |  | 16296 | -619 | 15677 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Sardintous Co. | Individual | ASP | IRA | REF | 35 | INV | 129 | A | I | CFC | 10.3 | 10.3 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 | 2004-09-01 | 145879 | -281 | 145598 | 145597.6 | 100% | 0.4 | 0 |  | 18964 | -66 | 18898 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Sarma Gostar Co. | Individual | ASP | IRA | REF | 35 | INV | 130 | A | I | CFC | 9.3 | 9.3 |  |  | 2001-12-01 | 2002-06-01 | 2004-05-01 |  | 2004-09-01 | 2004-09-01 | 100384 | -3803 | 96581 | 96580.99 | 100% | 0.01 | 0 |  | 13050 | -514 | 12536 | 0 | 0 | FIN |  |  |  | INV
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Alireza Abdolrezazadeh Co. | Individual | ASP | IRA | REF | 35 | INV | 131 | A | I | CFC | 7.7 | 7.7 | 0 | 0 | 2001-12-01 | 2003-08-01 | 2004-07-01 |  | 2004-11-01 | 2005-12-01 | 116646 | -327 | 116319 | 116319 | 100% | 0 | 0 | 0 | 15163.98 | -43 | 15120.98 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Garm Iran Co. | Individual | ASP | IRA | REF | 35 | INV | 132 | A | I | CFC | 11.8 | 11.8 | 0 | 0 | 2001-12-01 | 2003-08-01 | 2004-07-01 |  | 2004-11-01 | 2006-10-01 | 153447 | -30506 | 122941 | 122941 | 100% | 0 | 0 | 0 | 19948.11 | -3966 | 15982.11 | 0 | 0 | Completed in 2004. Financially completed in 2006. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Ghotb Jonoub Industrial Group | Individual | ASP | IRA | REF | 35 | INV | 133 | A | I | CFC | 14.6 | 14.6 | 0 | 0 | 2001-12-01 | 2004-06-01 | 2004-07-01 |  | 2006-04-01 | 2011-07-01 | 170125 | -2574.31 | 167550.69 | 167551 | 100% | -0.31 | 0 | 0 | 22116.25 | -334.66 | 21781.6338 | -0.0438 | 0 | Completed in 2006. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Havasaz Manufacturing and Industrial Co. | Individual | ASP | IRA | REF | 35 | INV | 134 | A | I | CFC | 24.5 | 24.5 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2004-07-01 |  | 2004-11-01 | 2005-11-01 | 252294 | -19021 | 233273 | 233273 | 100% | 0 | 0 | 0 | 32798.22 | -2472.71 | 30325.5065 | 0.003462 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment and rigid foam at Mehran Sard, Co. | Individual | ASP | IRA | REF | 35 | INV | 135 | A | I | CFC | 17.7 | 17.7 | 0 | 0 | 2001-12-01 | 2003-02-01 | 2004-07-01 |  | 2004-11-01 | 2005-11-01 | 144715 | -1097 | 143618 | 143618 | 100% | 0 | 0 | 0 | 18812.95 | -142.61 | 18670.3396 | 0.000386 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Parto Shiva Sanaat | Individual | ASP | IRA | REF | 35 | INV | 136 | A | I | CFC | 23.9 | 23.9 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2004-07-01 |  | 2004-11-01 | 2007-01-01 | 283948 | -36625 | 247323 | 247323 | 100% | 0 | 0 | 0 | 36913.24 | -4761.22 | 32152.021 | -0.001 | 0 | Completed in 2004. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Sain Electric Co. | Individual | ASP | IRA | REF | 35 | INV | 137 | A | I | CFC | 11.2 | 11.2 | 0 | 0 | 2001-12-01 | 2003-08-01 | 2004-07-01 |  | 2004-11-01 | 2005-12-01 | 152024 | -32223 | 119801 | 119801 | 100% | 0 | 0 | 0 | 19763.12 | -4189 | 15574.12 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Sanaye Boroudati Maleki | Individual | ASP | IRA | REF | 35 | INV | 138 | A | I | CFC | 17.9 | 17.9 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2004-07-01 |  | 2004-11-01 | 2006-06-01 | 215052 | -178 | 214874 | 214874 | 100% | 0 | 0 | 0 | 27956.76 | -23 | 27933.76 | 0 | 0 | Completed in 2004. Financially completed in 2006. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Sarma Fan, Co. | Individual | ASP | IRA | REF | 35 | INV | 139 | A | I | CFC | 20.8 | 20.8 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2004-07-01 |  | 2004-11-01 | 2005-10-01 | 267075 | -26729 | 240346 | 240346 | 100% | 0 | 0 | 0 | 34719.75 | -3474.8 | 31244.955 | -0.004995 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment and rigid foam at Tehran Sardsazi Industrial Co. | Individual | ASP | IRA | REF | 35 | INV | 140 | A | I | CFC | 15.5 | 15.5 | 0 | 0 | 2001-12-01 | 2003-08-01 | 2004-07-01 |  | 2004-11-01 | 2005-11-01 | 125244 | 0 | 125244 | 125244 | 100% | 0 | 0 | 0 | 16281.72 | 0 | 16281.72 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNIDO | Preparation of 3 umbrella investment projects in the commercial and domestic refrigeration sector | Individual | ASP | IRA | REF | 36 | PRP | 146 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2003-10-01 | 2004-09-01 | 30000 | -2109 | 27891 | 27890.98 | 100% | 0.02 | 0 |  | 3900 | -280 | 3620 | 0 | 0 | FIN |  |  |  | INV
FIN | UNDP | Project preparation in the manufacturing of refrigeration equipment sector (terminal phase-out) | Individual | ASP | IRA | REF | 36 | PRP | 147 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2003-12-01 | 2005-11-01 | 35000 | -5431 | 29569 | 29569 | 100% | 0 | 0 | 0 | 4550 | -706.03 | 3843.97 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (refrigeration manufacturing sector except air-to-air air-conditioning) | Individual | ASP | IRA | REF | 57 | PRP | 193 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-05-01 | 2010-03-01 |  | 2011-12-01 | 2013-01-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 3375 | 0 | 3375 | 0 | 0 | Financially completed in 2013. | The project is being closed by June 12. | 2009 |  | Investment
FIN | UNIDO | Preparation for HCFC phase-out investment activities (room air-conditioning and compressors) | Individual | ASP | IRA | REF | 58 | PRP | 196 | A | I |  | 0 | 0 |  |  | 2009-07-01 | 2009-10-01 | 2010-07-31 |  | 2011-04-01 | 2012-12-01 | 45000 | -61 | 44939 | 44938.82 | 100% | 0.18 | 0 |  | 3375 | -5 | 3370 | 0 | 0 | FIN |  |  |  | NON-INV
COM | UNIDO | Preparation for HCFC phase-out investment activities (stage II) (refrigeration and air-conditioning sector) | Individual | ASP | IRA | REF | 72 | PRP | 210 | A | I |  | 0 | 0 |  |  | 2014-05-01 | 2015-02-01 | 2016-05-31 |  | 2016-12-01 |  | 20000 | 0 | 20000 | 19413.17 | 97.07% | 586.83 | 0 | 1 | 1400 | 0 | 1359 | 41 | 0 | - Further consultation with stakeholders and NOU took place in 2016 and the HPMP stage II project document was finalized. - HPMP Stage II first tranche in the refrigeration and air-conditioning sector was approved in 2016 by the 77th Meeting of the ExCom. | Project completed. |  |  | NON-INV
ONG | UNDP | Preparation for HCFC phase-out investment activities (stage II) (refrigeration and air-conditioning sector) | Individual | ASP | IRA | REF | 72 | PRP | 217 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 |  | 2016-05-01 | 2017-05-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 12000 | 2100 | 0 | 0 | 2100 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): No activity/contract planned under this budget Prodoc signed (actual/planned, yes/no and date):Letter of Authorisation sent 21 January 2016 Missions undertaken (actual/planned):1 TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: Contract signed First disbursement date (actual/planned): Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | - |  |  | Non-Investment
FIN | UNDP | Study to determine production and consumption of ODS | Individual | ASP | IRA | SEV | 04 | TAS | 01 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-08-01 | 1992-06-01 |  | 1992-02-01 | 1997-12-01 | 30350 | 0 | 30350 | 30350 | 100% | 0 | 0 | 0 | 3945.5 | 0 | 3945.5 | 0 | 0 | Completed in 1992. Financially completed in 1997. |  | 1991 |  | Non-Investment
CLO | IBRD | Country programme preparation | Individual | ASP | IRA | SEV | 06 | CPG | 02 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1992-12-01 |  |  | 1992-12-01 | 150000 | -150000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Country programme preparation | Individual | ASP | IRA | SEV | 06 | CPG | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-02-01 | 1992-12-01 |  | 1993-06-01 | 1997-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
CLO | IBRD | Preparation of investment projects (1992) |  | ASP | IRA | SEV | 06 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1992-12-01 |  |  | 1992-12-01 | 40000 | -39579 | 421 | 421 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Institutional strengthening | Individual | ASP | IRA | SEV | 08 | INS | 05 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1993-10-01 | 1995-10-01 |  | 1997-12-01 | 2000-12-01 | 200200 | 0 | 200200 | 200200 | 100% | 0 | 0 | 0 | 26026 | 0 | 26026 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1992 |  | Non-Investment
FIN | UNDP | Preparation of investment projects | Individual | ASP | IRA | SEV | 08 | PRP | 06 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1993-11-01 | 1993-10-01 |  | 1995-03-01 | 1997-12-01 | 17935 | 0 | 17935 | 17935 | 100% | 0 | 0 | 0 | 2331.55 | 0 | 2331.55 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1992 |  | Investment
FIN | UNIDO | Preparation of investment projects in the foam sector | Individual | ASP | IRA | SEV | 17 | PRP | 10 | A | I |  | 0 | 0 |  |  | 1995-07-01 | 1996-07-01 | 1996-07-01 |  | 1997-12-01 | 1998-08-01 | 32065 | 698 | 32763 | 32763 | 100% | 0 | 0 |  | 4168 | 91 | 4259 | 0 | 0 | FIN
FIN | UNIDO | Project formulation in the commercial refrigeration sector (remaining enterprises), compressors and the foam sector | Individual | ASP | IRA | SEV | 21 | PRP | 19 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-04-01 | 1998-02-01 |  | 1999-12-01 | 2001-03-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | -8 | 6492 | 0 | 0 | FIN
FIN | UNDP | Renewal of institutional strengthening | Individual | ASP | IRA | SEV | 23 | INS | 30 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1997-11-01 | 2000-08-01 | 1999-12-01 |  | 2002-05-01 | 2003-11-01 | 133470 | 0 | 133470 | 133470 | 100% | 0 | 0 | 0 | 17351.1 | 0 | 17351.1 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1997 |  | Non-Investment
FIN | France | Small and medium enterprises study |  | ASP | IRA | SEV | 26 | TAS | 36 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 2002-05-01 | 1999-12-01 |  | 2005-04-01 | 2005-04-01 | 75000 | -55000 | 20000 | 20000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Closed as per decision 45/12, financial closure to be finalised. |  |  | 2002-12-01
FIN | UNDP | Extension of the institutional strengthening project (Phase III) | Individual | ASP | IRA | SEV | 32 | INS | 74 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2003-01-01 |  | 2003-08-01 | 2004-01-01 | 133470 | -25 | 133445 | 133445 | 100% | 0 | 0 | 0 | 17351.1 | -3.25 | 17347.85 | 0 | 0 | Completed in 2003. Financially completed in 2004. |  | 2000 |  | Non-Investment
FIN | UNEP | Preparation of country programme update | Individual | ASP | IRA | SEV | 36 | CPG | 145 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-04-01 | 2003-04-01 |  | 2003-12-01 | 2005-05-01 | 26250 | -3250 | 23000 | 23000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNDP | Extension of institutional strengthening project | Individual | ASP | IRA | SEV | 38 | INS | 157 | N | I | No_ODP | 14.3 | 14.3 | 0 | 0 | 2002-11-01 | 2003-09-01 | 2004-12-01 |  | 2005-12-01 | 2007-06-01 | 173511 | -1407 | 172104 | 172104 | 100% | 0 | 0 | 0 | 22556.43 | -182.91 | 22373.5222 | -0.0022 | 0 | Completed in 2005. Financially completed in 2007. |  | 2002 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase V) | Individual | ASP | IRA | SEV | 44 | INS | 167 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2005-12-01 |  | 2006-03-01 | 2007-06-01 | 86755 | -1313 | 85442 | 85442 | 100% | 0 | 0 | 0 | 6507 | -98.45 | 6408.5508 | -0.0008 | 0 | Completed in 2006. Financially completed in 2007. |  | 2004 |  | Non-Investment
FIN | UNDP | Assistance to carry out an HCFC survey | Individual | ASP | IRA | SEV | 45 | TAS | 172 | A | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-10-01 | 2006-12-01 |  | 2008-08-01 | 2009-12-01 | 68807 | -10271 | 58536 | 58536 | 100% | 0 | 0 | 0 | 6193 | -924.45 | 5268.5548 | -0.0048 | 0 | Completed in 2008. Financially completed in 2009. |  | 2005 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase V, year 2) | Individual | ASP | IRA | SEV | 47 | INS | 174 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-06-01 | 2006-12-01 |  | 2007-03-01 | 2008-09-01 | 86756 | -69 | 86687 | 86687 | 100% | 0 | 0 | 0 | 6507 | -5.18 | 6501.8248 | -0.0048 | 0 | Completed in 2007. Financially Completed in 2008. |  | 2005 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VI) | Individual | ASP | IRA | SEV | 50 | INS | 179 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-01-01 | 2008-11-01 |  | 2008-07-01 | 2009-06-01 | 86755 | -65 | 86690 | 86690 | 100% | 0 | 0 | 0 | 6507 | -4.88 | 6502.1247 | -0.0047 | 0 | Completed in 2008.Financially completed in 2009. |  | 2006 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VI, second year) | Individual | ASP | IRA | SEV | 53 | INS | 185 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-01-01 | 2008-11-01 |  | 2008-12-01 | 2011-11-01 | 86756 | -87.31 | 86668.69 | 86669 | 100% | -0.31 | 0 | 0 | 6507 | -6.55 | 6500.4747 | -0.024651 | 0 | Completed in 2008. |  | 2007 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VII) | Individual | ASP | IRA | SEV | 56 | INS | 187 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-05-01 | 2010-12-01 |  | 2010-12-01 | 2011-12-01 | 173511 | -403.06 | 173107.94 | 173108 | 100% | -0.06 | 0 | 0 | 13013 | -30.23 | 12982.7758 | -0.0057999 | 0 | Completed in 2010. Financially completed in 2011. |  | 2008 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VIII) | Individual | ASP | IRA | SEV | 61 | INS | 197 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-02-01 | 2012-12-01 |  | 2013-03-01 | 2014-06-01 | 173511 | 0 | 173511 | 173511 | 100% | 0 | 0 | 0 | 13013 | 0 | 13013 | 0 | 0 | Financially completed in 2014. | Completed in 2013. | 2010 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase IX: 1/2013-12/2014) | Individual | ASP | IRA | SEV | 67 | INS | 206 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2012-07-01 | 2013-06-01 | 2014-12-01 |  | 2015-06-01 | 2016-06-01 | 173511 | 0 | 173511 | 173511 | 100% | 0 | 0 | 0 | 12146 | 0 | 12146 | 0 | 0 | Financially completed in 2016. | The IS Phase-IX has been operationallly completed in month 2015. The IS activities continue under the IS Phase-X. | 2012 |  | Non-Investment
ONG | UNDP | Extension of the institutional strengthening project (phase X: 1/2015-12/2016) | Individual | ASP | IRA | SEV | 72 | INS | 213 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2014-05-01 | 2015-05-01 | 2016-12-01 | 2017-07-01 |  |  | 173511 | 0 | 173511 | 150691.97 | 86.85% | 22819.03 | 0 | 9127.612 | 12146 | 0 | 10548.6377 | 1597.3623 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): The Project provided infrastructure for the country to sustain Ozone Depleting Substances phase out targets which were already achieved in previous years. The continuous inter-organizational collaboration including coordination and cooperation with Custom Administration , Standardization and Industrial Research Institute , Ministry of Industry, Mine and Trade, the Trade Promotion Organization and the National Ozone Network have created a national working mechanism that enabled the country to remain in full compliance toward its commitments to protect the ozone layer. Prodoc signed (actual/planned, yes/no and date):42125 Missions undertaken (actual/planned): TOR for consultants/subcontracts completed (actual/planned): ToR Completed earlier Contract/PO/MOA agreements signed: Contract signed First disbursement date (actual/planned): 42125Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | IA meeting held and finalized the AWP. |  |  | Non-Investment
ONG | UNDP | Survey of ODS alternatives at the national level | Individual | ASP | IRA | SEV | 74 | TAS | 223 | N | I | HFC | 0 | 0 | 0 | 0 | 2015-05-01 | 2016-12-01 | 2016-11-01 | 2017-05-01 |  |  | 130000 | 0 | 130000 | 13882.66 | 10.68% | 116117.34 | 51698.83 | 46446.936 | 11700 | 0 | 1249.4394 | 10450.5606 | 4652.8947 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): One mission to Tehran in August 2016 with two objectives: 1. Meet with the local consultant appointed to carry out the ODS alternative survey. 2. Meet with the NOU and all Agencies involved in the preparation of Iran’s Stage II HPMP and try to resolve all issues. Prodoc signed (actual/planned, yes/no and date):Letter of Authorisation sent 26 May 2016 Missions undertaken (actual/planned):1 TOR for consultants/subcontracts completed (actual/planned): ToR Completed earlier Contract/PO/MOA agreements signed: Contract signed First disbursement date (actual/planned): 42705Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:Given that the contracts required extensive field surveys and engagement with several national partners, the timing provisioned in the table of deliverables in both ToRs were unlikely to be met accurately. At the same time, developing the ODS alternative strategies requires consultation with several stakeholders including Customs Offices in different provinces across the country, which needed much more time than expected. As the national studies, surveys and analysis would take more time than expected, and the nature of deliverables of national and international consultants are intertwined, hence this affects both contracts. On the other hand, to ensure that the process is going technically well, the National Ozone Unit needs more involvement in the process at different check-points and in some cases, needs to accompany the team in the field surveys as well as consultation meetings. | To complete the ODS alternatives survey | 2015 |  | Non-Investment
ONG | UNDP | Extension of the institutional strengthening project (phase XI: 4/2017-3/2019) | Individual | ASP | IRA | SEV | 77 | INS | 229 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2016-12-01 |  | 2019-03-01 | 2017-03-01 |  |  | 222094 | 0 | 222094 | 0 | 0% | 222094 | 0 | 88837.6 | 15547 | 0 | 0 | 15547 | 0 | Newly Approved | DoA sent Feb 2017. Awaiting prodoc & AWP from CO for ASL request. | 2016 |  | Non-Investment
FIN | France | Project preparation and technical assistance in the solvent sector |  | ASP | IRA | SOL | 23 | PRP | 23 | A | I |  | 0 |  | 0 |  | 1997-11-01 | 1998-04-01 | 1998-12-01 |  | 1999-12-01 | 1999-12-01 | 31500 | 0 | 31500 | 31500 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed.
FIN | France | Conversion to ODS-free technology at Dorcharkh Company |  | ASP | IRA | SOL | 28 | INV | 48 | A | I | CTC | 11 | 11 | 0 |  | 1999-07-01 | 2001-08-01 | 2001-08-01 |  | 2002-12-01 | 2008-10-01 | 165140 | 0 | 165140 | 165140 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Project completed. 5% support costs mentioned by the financing agreement were included in the allocated amount.
FIN | UNIDO | Project preparation in the solvent (CTC) sector | Individual | ASP | IRA | SOL | 33 | PRP | 80 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-08-01 | 2002-04-01 |  | 2005-12-01 | 2006-02-01 | 20000 | 0 | 20000 | 20000.02 | 100% | -0.02 | 0 |  | 2600 | -2 | 2598 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of investment projects in the solvent sector (CTC/TCA) | Individual | ASP | IRA | SOL | 39 | PRP | 158 | A | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-08-01 | 2004-04-01 |  | 2004-04-01 | 2004-07-01 | 10000 | 0 | 10000 | 10000.47 | 100% | -0.47 | 0 |  | 750 | 0 | 750 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in the solvent sector CTC/TCA | Individual | ASP | IRA | SOL | 42 | PRP | 164 | A | I |  | 0 | 0 |  |  | 2004-04-01 | 2004-09-01 | 2005-04-01 |  | 2005-12-01 | 2006-12-01 | 15000 | -110 | 14890 | 14889.61 | 100% | 0.39 | 0 |  | 1125 | -8 | 1117 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of a phase-out plan in the solvent sector | Individual | ASP | IRA | SOL | 48 | PRP | 178 | A | I |  | 0 | 0 |  |  | 2006-04-01 | 2006-07-01 | 2007-04-01 |  | 2006-12-01 | 2007-05-01 | 15000 | -512 | 14488 | 14487.67 | 100% | 0.33 | 0 |  | 1125 | -38 | 1087 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Terminal solvent sector umbrella project | Individual | ASP | IRA | SOL | 50 | INV | 180 | A | I | CTC TCA | 52.7 | 52.7 |  |  | 2006-11-01 | 2007-11-01 | 2008-02-01 |  | 2009-12-01 | 2012-09-01 | 856478 | -1457 | 855021 | 855021.12 | 100% | -0.12 | 0 |  | 64236 | -109 | 64127 | 0 | 0 | FIN |  |  | 2009-12-01 | INV
FIN | UNDP | Preparation for HCFC phase-out investment activities (fire-fighting and solvent sectors) | Individual | ASP | IRA | SOL | 57 | PRP | 194 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-10-01 | 2010-03-01 |  | 2011-12-01 | 2013-01-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 750 | 0 | 750 | 0 | 0 | Financially completed in 2013. | Project targeted for financial closure in 2012 | 2009 |  | Investment
FIN | UNIDO | Conversion from CFC-11 to methylene chloride in the production of flexible slabstock foam at Al Hadi Co. | Individual | ASP | IRQ | FOA | 57 | INV | 06 | A | I | CFC | 20 | 20 |  |  | 2009-04-01 | 2010-12-01 | 2011-03-31 |  | 2014-09-01 | 2014-09-01 | 126457 | -1352 | 125105 | 125104.58 | 100% | 0.42 | 0 |  | 11381 | -122 | 11259 | 0 | 0 | FIN |  |  | 2011-12-01 | INV
FIN | UNIDO | Project preparation for the elimination of controlled uses of methyl bromide in pre and post-harvest sectors | Individual | ASP | IRQ | FUM | 58 | PRP | 08 | A | I |  | 0 | 0 |  |  | 2009-07-01 | 2010-07-01 | 2010-07-31 |  | 2010-12-01 | 2011-06-01 | 40000 | -239 | 39761 | 39761.16 | 100% | -0.16 | 0 |  | 3000 | -18 | 2982 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | Technical assistance for alternatives to methyl bromide | Individual | ASP | IRQ | FUM | 62 | INV | 13 | A | I | MBR | 3.5 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2013-06-30 | 2018-04-01 |  |  | 211970 | 0 | 211970 | 163431.07 | 77.1% | 48538.93 | 26990.36 | 1 | 19077 | 0 | 14709 | 4368 | 2429 | - No progress occurred in 2016, considering the same logistic difficulties in the country and the difficulty to identify an alternative training scheme to overcome those barriers. - All contractual arrangements are in place to ensure a timely implementation as soon as logistic and safe conditions allow. - One main impediment was the difficulty to mobilize funds from the Government to implement the activities agreed with UNIDO. UNIDO and the NOU are monitoring the status of payment release. Milestones achieved: Milestone 1: Grant agreement submitted to beneficiary - Yes Milestone 2: Grant agreement signature - Yes Milestone 3: Bids prepared and requested - Yes Milestone 4: Contracts awarded - Yes Milestone 5: Equipment delivered - Yes Milestone 6: Commissioning and trial runs - Yes (partially: some training activities still needed) Milestone 7: De-commissioning and/or destruction of redundant baseline equipment - No Activities planned but not implemented, reasons and strategy: All contracts have been signed and everything is in place for a full project implementation. However, some training activities could not be implemented because of logistic impediments in the country. Actions towards next goals: Organize training activities Was there any delay during the reporting year? Yes If yes, reasons and action plan: Internal political instability. Develop an alternative training scheme to overcome the logistic impediments in a safe manner. Any recurring problem? Yes If yes, description of the problem/s: Internal political instability. Any impact on project completion date: Yes If yes, implications: Training activates need to be re-organized taking into consideration the safe implementation of project activities according to local instability Any action required by Executive Committee? Yes; To extend the grant validity | - No progress occurred in 2017, considering the same logistic difficulties in the country and the difficulty to identify an alternative training scheme to overcome those barriers. Actions towards next goals: Organize training activities Was there any delay during the reporting year? Yes If yes, reasons and action plan: Internal political instability. Any recurring problem? Yes If yes, description of the problem/s: Internal political instability. Any impact on project completion date: Yes If yes, implications: Training activates need to be re-organized taking into consideration the safe implementation of project activities according to local instability Any action required by Executive Committee? No |  |  | INV |  | Continued Monitoring
FIN | UNEP | Preparation of country programme and national phase-out plan | RMP | ASP | IRQ | PHA | 55 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-07-01 | 2009-07-01 |  | 2009-06-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0
FIN | UNIDO | Preparation of country programme and national phase-out plan. | Individual | ASP | IRQ | PHA | 55 | PRP | 03 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-10-01 | 2009-07-31 |  | 2009-07-01 | 2010-12-01 | 40000 | 0 | 40000 | 40000.01 | 100% | -0.01 | 0 |  | 3600 | 0 | 3600 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | ASP | IRQ | PHA | 55 | PRP | 04 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 |  | 2011-12-01 | 2012-12-01 | 30000 | -2909 | 27091 | 27090.88 | 100% | 0.12 | 0 |  | 2250 | -218 | 2032 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | National phase-out plan (first tranche) | Multi-Year | ASP | IRQ | PHA | 58 | INV | 09 | A | I | CFC CTC | 1257.9 | 1257.9 |  |  | 2009-07-01 | 2009-11-01 | 2012-07-31 | 2017-12-17 |  |  | 4353530 | 0 | 4353530 | 3625879.48 | 83.29% | 727650.52 | 611608.29 | 500000 | 326515 | 0 | 271941 | 54574 | 45870.6217 | UNIDO has identified a suitable company to do inspection of the supplied equipment; assessment of beneficiaries; definition of civil works needed prior to installation as well as do installation, commissioning and trial runs. First mission to project sites was conducted in September 2016. Findings of the mission were positive; and it was subsequently agreed to proceed with installation and commissioning. Draft ToR for these services were discussed and agreed with Iraqi counterparts. | UNIDO did request offer for installation/commissioning in Q1/2017. Additional clarification was needed; and UNIDO is in process of finalizing the contract; expected to be issued early Q2/2017. Installation/commissioning is scheduled for 30-40 days per company (3 in total - combined with Light Industries); however, with a reservation that work may not be possible during periods in summer due to very high ambient temperatures. '- Delay in implementation due to the above - No recurring problem - Impact on project completion date: Yes - No action required by Executive Committee |  |  | INV |  | To request the submission of additional status report to the 79th meeting to monitor the installation of the equipment.
ONG | UNEP | National phase-out plan (first tranche) | Multi-Year | ASP | IRQ | PHA | 58 | TAS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2009-10-01 | 2012-07-01 | 2017-07-01 |  |  | 1136000 | 0 | 1136000 | 893129.89 | 78.62% | 242870.11 | 27862.47 | 24287.011 | 147680 | 0 | 116106.8857 | 31573.1143 | 3622.1211 | Brief progress report (actual/planned): All financial reports submitted by Iraq, payments under country contract is transferred to country, one last payment is due during 1st half of 2017 after receipt of final technical, financial and auditing reports. ExCom-77 extended duration of NPP of Iraq till June 2017. Final training program under NPP is organized by UNEP in cooperation with Italian Technicians Association (ATF) where 15 Master Trainers from Iraq were trained and certified on Sound Management of Refrigerants in commercial refrigeration applications. • Legal arrangements(actual/planned): Country contract with the country is signed with the country for both NPP-1 NPP-2 and amended several times to allow completion of all activities • First mission (actual/planned): Two coordination and technical meetings organized with NOU/PMU outside Iraq due to security considerations • TOR completed(actual/planned): TORs for the project implementation are already in the country contract since signature in 2010. It’s being updated from time to time to accommodate progress on ground • All funds disbursed (yes/no): No, only US$ 25,000 is pending to be transferred. Both NPP-1 & NPP-2 are merged in one country contract • Any delay? (yes/no): Yes • If Yes, reasons for delay & action plan to resolve: Delay in the utilizing the funds locally and financial reporting due to local administrative difficulties after merging the Ministry of Environment with the Ministry of Health in 2015. • If Yes, will delay have impact on project completion date (yes/no): Yes, request to MFS sent to extend project duration which is granted by ExCom-77 • If Yes, is any action required by ExCom: NO | Brief progress report (actual/planned): - PMU set quick work plan to complete remaining activities (which are collecting information about all NPP training activities and develop one final technical report + submitting final financial and auditing report) - Project planned to be completed by mid 2017
FIN | UNIDO | Preparation of a HCFC phase-out management plan (additional funding) | Individual | ASP | IRQ | PHA | 59 | PRP | 11 | A | I |  | 0 | 0 |  |  | 2009-11-01 | 2010-11-01 | 2010-11-30 |  | 2011-12-01 | 2015-03-01 | 65000 | -3288 | 61712 | 61712.39 | 100% | -0.39 | 0 |  | 4875 | -247 | 4628 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | IRQ | PHA | 60 | PRP | 12 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2011-01-01 | 2011-04-01 |  | 2011-12-01 | 2014-05-01 | 100000 | -25671 | 74329 | 74329 | 100% | 0 | 0 |  | 13000 | -3337.23 | 9662.77 | 0 | 0
COM | UNIDO | National phase-out plan (second tranche) | Multi-Year | ASP | IRQ | PHA | 63 | INV | 15 | A | I |  | 0 | 0 |  |  | 2011-04-01 | 2015-10-01 | 2012-03-31 |  | 2015-12-01 |  | 303000 | 0 | 303000 | 303000 | 100% | 0 | 0 |  | 22725 | 0 | 22725 | 0 | 0 | The project was operationally completed. |  |  |  | INV
ONG | UNEP | National phase-out plan (second tranche) | Multi-Year | ASP | IRQ | PHA | 63 | TAS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2012-05-01 | 2012-03-01 | 2017-07-01 |  |  | 505000 | 0 | 505000 | 14480 | 2.867% | 490520 | 0 | 49052 | 65650 | 0 | 1882.4 | 63767.6 | 0 | Brief progress report (actual/planned): All financial reports submitted by Iraq, payments under country contract is transferred to country, one last payment is due during 1st half of 2017 after receipt of final technical, financial and auditing reports. ExCom-77 extended duration of NPP of Iraq till June 2017. Final training program under NPP is organized by UNEP in cooperation with Italian Technicians Association (ATF) where 15 Master Trainers from Iraq were trained and certified on Sound Management of Refrigerants in commercial refrigeration applications. • Legal arrangements(actual/planned): Country contract with the country is signed with the country for both NPP-1 NPP-2 and amended several times to allow completion of all activities • First mission (actual/planned): Two coordination and technical meetings organized with NOU/PMU outside Iraq due to security considerations • TOR completed(actual/planned): TORs for the project implementation are already in the country contract since signature in 2010. It’s being updated from time to time to accommodate progress on ground • All funds disbursed (yes/no): No, only US$ 25,000 is pending to be transferred. Both NPP-1 & NPP-2 are merged in one country contract • Any delay? (yes/no): Yes • If Yes, reasons for delay & action plan to resolve: Delay in the utilizing the funds locally and financial reporting due to local administrative difficulties after merging the Ministry of Environment with the Ministry of Health in 2015. • If Yes, will delay have impact on project completion date (yes/no): Yes, request to MFS sent to extend project duration which is granted by ExCom-77 • If Yes, is any action required by ExCom: NO | Brief progress report (actual/planned): - PMU set quick work plan to complete remaining activities (which are collecting information about all NPP training activities and develop one final technical report + submitting final financial and auditing report) - Project planned to be completed by mid 2017
COM | UNIDO | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | ASP | IRQ | PHA | 65 | INV | 16 | A | I |  | 0 | 0 |  |  | 2011-11-01 | 2015-10-01 | 2013-11-30 |  | 2015-12-01 |  | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 6000 | 0 | 6000 | 0 | 0 | The project was operationally completed. |  |  |  | INV
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | ASP | IRQ | PHA | 65 | TAS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2016-11-01 | 2013-11-01 | 2017-12-01 |  |  | 115000 | 0 | 115000 | 0 | 0% | 115000 | 85000 | 11500 | 14144 | 0 | 0 | 14144 | 10454.2609 | Brief progress report (actual/planned): Initial delays overcome after start utilizing the transferred funds by the Ministry. - Legal arrangements (actual/planned): Legal instrument signed since 2015 and first payment made - Initial stages of project implementation (actual/planned): all initial stages completed including the contracting arrangements, planning of activities and kick-off of all programs - Intermediate goals achieved (actual/planned): Two regulatory enforcement workshops organized, outreach materials developed in different format and circulated to all ministries and stakeholders, local technical taskforce formed and drafted educational booklets to support the updated curricula of three different technical education and vocational training disciplines & national committee established to prepare the certification scheme and first draft is developed and under consultation. - Project completion and follow up: Tranche related activities are expected to be completed by end of 2017 - All funds disbursed (yes/no): No, 2nd payment will be made in beginning of 2017 and final payment before end of 2017 - Project ongoing & delayed Any delay? (yes/no): Ongoing with some delays due to delays in receiving the funds by the Ministry as it goes through Ministry of Finance and takes time - If Yes, will delay have impact on project completion date (yes/no): Stage-I of the HPMP of Iraq is already rescheduled, when 2nd tranche approved, to cover till end of 2017 - Any ongoing problems (yes/no): No | Brief progress report (actual/planned): - Second technical and financial report submitted by the country and subsequent payment made - Draft educational and training booklets reviewed and under printing for distribution and start orientation sessions |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor the submission of required expenditure and progress reports from the Government to UNEP.
ONG | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | Individual | ASP | IRQ | PHA | 73 | PRP | 19 | A | I |  | 0 | 0 |  |  | 2014-11-01 |  | 2016-11-30 | 2018-07-18 |  |  | 25000 | 0 | 25000 | 0 | 0% | 25000 | 0 | 10000 | 1750 | 0 | 0 | 1750 | 0 | Due to slow progress of NPP and HPMP stage I, stage II couldn't be submitted. - Delay in implementation due to the above - No recurring problem - Impact on project completion date: Yes - No action required by Executive Committee | Due to slow progress of NPP and HPMP stage I, stage II can't be submitted yet. |  |  | NON-INV |  | To request the submission of additional status report to the 79th meeting to monitor the resumption of activities.
ONG | UNEP | Preparation of a HCFC phase-out management plan (stage II) | Multi-Year | ASP | IRQ | PHA | 73 | PRP | 21 | A | I |  | 0 |  | 0 |  | 2014-11-01 |  | 2016-11-01 | 2017-12-01 |  |  | 45000 | 0 | 45000 | 0 | 0% | 45000 | 0 | 4500 | 5850 | 0 | 0 | 5850 | 0 | Brief progress report (actual/planned): - Work Plan for the preparation of Stage-II is developed. - Agreement is made with country to start the country contract and survey by mid of 2017 since Stage-I is extended till end of 2017 and stage-II will not be submitted before end of 2017 or beginning of 2018. therefore, earlier preparation and survey would have resulted in to a gap between preparation and implementation - UNEP organized training session for the local survey teams (6 local experts heading 6 different teams) about type of data to be collected, validation of data and consolidating the final results | Brief progress report (actual/planned): - Country contract drafted and under signature - NOU formed the survey teams and started the data collection process which should be completed by mid of 2017 - Consultation meetings conducted by NOU for different group of Stakeholders |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor the signing of the agreements by the Government and UNEP.
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | Multi-Year | ASP | IRQ | PHA | 74 | INV | 23 | A | I | HCFC | 3.9 | 0 |  |  | 2015-05-01 |  | 2018-05-31 | 2019-03-01 |  |  | 230000 | 0 | 230000 | 0 | 0% | 230000 | 0 | 30000 | 17250 | 0 | 0 | 17250 | 0 | Due to slow progress of NPP and HPMP stage I, implementation of second tranche could not start. '- Delay in implementation due to the above - No recurring problem - Impact on project completion date: Yes - No action required by Executive Committee | Due to slow progress of NPP and HPMP stage I, implementation of second tranche did not yet start. |  |  | INV
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | Multi-year | ASP | IRQ | PHA | 74 | TAS | 22 | A | I |  | 5.6 |  | 0 |  | 2015-05-01 |  | 2017-05-01 | 2017-05-01 |  |  | 325000 | 0 | 325000 | 0 | 0% | 325000 | 0 | 32500 | 40822 | 0 | 0 | 40822 | 0 | Brief progress report (actual/planned): Newly approved. TORs for 2nd tranche is developed and reviewed with the country. Coordination meeting organized by UNEP for NOU/PMU. Draft country contract drafted. Formation of the technical teams is established by NOU. | Brief progress report (actual/planned): - Work plan and country contract drafted and under signature. Delay in start utilizing 2nd tranche fund is due to delay in disbursing the funds from the first tranche, by the country, while all activities of 2nd tranche are linked to 1st tranche progress - country contract and 2nd tranche activities will start by mid of 2017 and will be expedited as the Ministry is reaching agreement with the Ministry of Finance for speeding the utilization of funds |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor the signing of the agreement by the Government and UNEP.
ONG | UNIDO | Replacement of refrigerant CFC-12 with isobutane and foam blowing agent CFC-11 with cyclopentane in the manufacture of domestic refrigerators and chest freezers at Light Industries Company | Individual | ASP | IRQ | REF | 57 | INV | 07 | A | I | CFC | 193.6 | 193.6 |  |  | 2009-04-01 | 2009-11-01 | 2011-03-31 | 2017-12-17 |  |  | 2161581 | 0 | 2161581 | 1899333.08 | 87.87% | 262247.92 | 262247.92 | 260000 | 162119 | 0 | 142450 | 19669 | 19668.594 | UNIDO has identified a suitable company to do inspection of the supplied equipment; assessment of beneficiaries; definition of civil works needed prior to installation as well as do installation, commissioning and trial runs. First mission to project sites was conducted in September 2016. Findings of the mission were positive; and it was subsequently agreed to proceed with installation and commissioning. Draft ToR for these services were discussed and agreed with Iraqi counterparts. | UNIDO did request offer for installation/commissioning in Q1/2017. Additional clarification was needed; and UNIDO is in process of finalizing the contract; expected to be issued early Q2/2017. Installation/commissioning is scheduled for 30-40 days per company (3 in total - combined with Nassr and Iraqi Steel); however, with a reservation that work may not be possible during periods in summer due to very high ambient temperatures. '- Delay in implementation due to the above - No recurring problem - Impact on project completion date: Yes - No action required by Executive Committee |  |  | INV |  | Continued Monitoring
ONG | UNIDO | Preparation for HCFC phase-out investment activities (stage II) (air-conditioning sector) | Individual | ASP | IRQ | REF | 73 | PRP | 20 | A | I |  | 0 | 0 |  |  | 2014-11-01 |  | 2016-11-30 | 2018-07-18 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 10000 | 2100 | 0 | 0 | 2100 | 0 | Due to slow progress of NPP and HPMP stage I, stage II couldn't be submitted. - Delay in implementation due to the above - No recurring problem - Impact on project completion date: Yes - No action required by Executive Committee | Due to slow progress of NPP and HPMP stage I, stage II can't be submitted yet. |  |  | NON-INV |  | To request the submission of additional status report to the 79th meeting to monitor the resumption of activities.
FIN | UNEP | Institutional strengthening project (start-up cost) | Individual | ASP | IRQ | SEV | 54 | INS | 01 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-10-01 | 2010-03-01 |  | 2009-06-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Institutional strengthening (phase I) | Individual | ASP | IRQ | SEV | 57 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-11-01 | 2011-03-01 |  | 2012-12-01 | 2013-12-01 | 240000 | -1359 | 238641 | 238641 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed | Project financially completed
COM | UNEP | Extension of institutional strengthening project (phase II: 6/2013-5/2015) | Individual | ASP | IRQ | SEV | 69 | INS | 18 | A | I |  | 0 |  | 0 |  | 2013-04-01 | 2015-01-01 | 2015-03-01 |  | 2016-12-01 |  | 240000 | 0 | 240000 | 78659.19 | 32.77% | 161340.81 | 161340.81 | 161341 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Project is completed. NOU faced delays in accessing & disbursing full funding of Phase II and requested officially to extend implementation to Dec-16 Legal arrangements (actual/planned): complete Initial stages of project implementation (actual/planned): Although delay was faced with release of funding by parliament, the NOU continued to operate as best possible. Intermediate goals achieved (actual/planned): Article 7 and CP data collected and reports submitted to OS and MLFS for the year of 2014 & 2015; NOU supervised implementation of other MP projects Project completion and follow up: Project is implemented with delay. First disbursement date (actual/planned): Feb-2014 All funds disbursed (yes/no): Yes. Project ongoing & faced Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: Country did not receive cash in hand from MOFinance and therefore requested additional time to complete final implementation up to end of Dec-16. If Yes, will delay have impact on project completion date (yes/no): Yes. Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: No. | Project is completed. All payments disbursed, but the final expenditure is under process to be recorded.
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | ASP | IRQ | SEV | 75 | TAS | 24 | A | I |  | 0 |  | 0 |  | 2015-11-01 |  | 2016-12-01 | 2017-07-01 |  |  | 110000 | 0 | 110000 | 0 | 0% | 110000 | 0 | 11000 | 14300 | 0 | 0 | 14300 | 0 | Brief progress report (actual/planned): TORs developed for the work under the survey, consultation meeting with NOU is arranged in margins of network meeting, detailed work-plan and sample documentation and forms sent to country for review and clearance, training for national expert arranged through regional workshop organized in back-to-back with the network meeting. Consultation meetings are organized with country and local experts to orient about the survey requirements. Special training workshop organized by UNEP for the heads of the survey teams to orient them with the data need to be collected, means of verification and format need to be used as per guidelines of ExCom. • Legal arrangements(actual/planned): Legal instrument drafted • Initial stages of project implementation(actual/planned): Started and all preparatory work arranged by UNEP • Intermediate goals achieved (actual/planned): Start of data collection delayed due to delay due to delay in forming the survey teams • Project completion and follow up: Planned by mid of 2017 • First disbursement date (actual/planned): Planned early 2017 • All funds disbursed (yes/no): No • Any delay?(yes/no): Yes • If Yes, reasons for delay & action plan to resolve: Due to delay in forming the survey teams • If Yes, will delay have impact on project completion date (yes/no): Yes, completion planned by mid of 2017 instead of end of 2016 | Brief progress report (actual/planned): - National survey teams formed at end of 2016 and started collecting data - UNEP signed contract with the country and disburse first payment by March 2017 - Data collection is ongoing and expected to be completed by April 2017 - Final report under preparation and will be submitted to ExCom-79
ONG | UNEP | Extension of institutional strengthening project (phase III: 5/2016-4/2018) | Individual | ASP | IRQ | SEV | 76 | INS | 25 | A | I |  | 0 |  | 0 |  | 2016-05-01 |  | 2018-04-01 | 2018-12-01 |  |  | 307200 | 0 | 307200 | 0 | 0% | 307200 | 85000 | 30720 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Newly approved. Implementation delay requested by Country to start Jan-17 Legal arrangements (actual/planned): not signed yet Initial stages of project implementation (actual/planned): n/a Intermediate goals achieved (actual/planned): n/a Project completion and follow up: not started as country requested to delay First disbursement date (actual/planned): none All funds disbursed (yes/no): No Project ongoing & delayed Any delay? (yes/no): Not started and delayed If Yes, will delay have impact on project completion date (yes/no): Yes Any ongoing problems (yes/no): No | Brief progress report (actual/planned): Implementation started Legal arrangements (actual/planned): signed Initial stages of project implementation (actual/planned): NOU providing support to MP projects as required Intermediate goals achieved (actual/planned): on going Project completion and follow up: on going First disbursement date (actual/planned): Mar-17 All funds disbursed (yes/no): No Project ongoing & delayed Any delay? (yes/no): ONG with delay If Yes, will delay have impact on project completion date (yes/no): Yes Any ongoing problems (yes/no): No
FIN | UNIDO | Phasing out CFCs at Parfumerie Gandour D.A.F. | Individual | AFR | IVC | ARS | 20 | INV | 07 | A | I | CFC | 66 | 66 |  |  | 1996-10-01 | 1997-06-01 | 1997-10-01 |  | 1999-12-01 | 2002-10-01 | 106061 | 0 | 106061 | 106060.67 | 100% | 0.33 | 0 |  | 13788 | 0 | 13788 | 0 | 0 | FIN |  |  | 1999-12-01
FIN | UNIDO | Phasing out CFCs at Sicobel | Individual | AFR | IVC | ARS | 20 | INV | 08 | A | I | CFC | 20.8 | 20.8 |  |  | 1996-10-01 | 1997-06-01 | 1997-10-01 |  | 1999-12-01 | 2002-09-01 | 59171 | -453 | 58718 | 58717.83 | 100% | 0.17 | 0 |  | 7692 | -71 | 7621 | 0 | 0 | FIN |  |  | 1999-12-01
FIN | UNIDO | Preparation of an investment project in the aerosol sector | Individual | AFR | IVC | ARS | 44 | PRP | 22 | A | I |  | 0 | 0 |  |  | 2004-12-01 | 2005-03-01 | 2005-12-01 |  | 2005-12-01 | 2006-12-01 | 15000 | -1832 | 13168 | 13167.99 | 100% | 0.01 | 0 |  | 1125 | -137 | 988 | 0 | 0 | FIN
CLO | UNIDO | Phase-out of CFC-12 in the manufacture of cosmetics aerosols (deodorants) by conversion to hydrocarbon aerosol propellant (HAP) at COPACI, Abidjan (terminal aerosol sector project) | Individual | AFR | IVC | ARS | 46 | INV | 23 | A | I | CFC | 43.4 | 0 |  |  | 2005-07-01 | 2005-10-01 | 2007-09-01 |  |  | 2009-06-01 | 110428 | -109351 | 1077 | 1077 | 100% | 0 | 0 |  | 9939 | -9842 | 97 | 0 | 0 | CLO |  |  |  | INV
FIN | UNIDO | Phasing out CFC-11 at F.I.M.A. flexible polyurethane foam plant | Individual | AFR | IVC | FOA | 19 | INV | 06 | A | I | CFC | 53.1 | 53.1 |  |  | 1996-05-01 | 1997-09-01 | 1997-07-01 |  | 1997-12-01 | 2001-03-01 | 85087 | -246 | 84841 | 84841 | 100% | 0 | 0 |  | 11061 | -49 | 11012 | 0 | 0 | FIN
CLO | UNIDO | Preparation of a project for stored commodities (cocoa beans) | Individual | AFR | IVC | FUM | 27 | PRP | 13 | A | I |  | 0 | 0 |  |  | 1999-03-01 |  | 1999-12-01 |  |  | 2001-03-01 | 25000 | -25000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 3250 | -3250 | 0 | 0 | 0 | CLO
FIN | UNIDO | Preparation of a phase-out plan in the fumigant sector | Individual | AFR | IVC | FUM | 39 | PRP | 18 | A | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-11-01 | 2004-04-01 |  | 2004-04-01 | 2004-07-01 | 10000 | -198 | 9802 | 9801.98 | 100% | 0.02 | 0 |  | 750 | -16 | 734 | 0 | 0 | FIN
FIN | UNIDO | Phase-out the use of methyl bromide commodities and storage fumigation | Individual | AFR | IVC | FUM | 42 | INV | 19 | A | I | MBR | 8.5 | 8.5 |  |  | 2004-04-01 | 2004-04-01 | 2006-10-01 |  | 2008-12-01 | 2010-12-01 | 222210 | -19676 | 202534 | 202534.15 | 100% | -0.15 | 0 |  | 19999 | -1771 | 18228 | 0 | 0 | FIN |  |  |  | INV
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | IVC | PHA | 48 | PRP | 25 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-04-01 | 2007-04-01 |  | 2007-12-01 | 2008-12-01 | 15000 | -9 | 14991 | 14991 | 100% | 0 | 0 |  | 1950 | -1.17 | 1948.83 | 0 | 0
FIN | UNIDO | Preparation of a terminal phase-out management plan | Individual | AFR | IVC | PHA | 48 | PRP | 26 | A | I |  | 0 | 0 |  |  | 2006-04-01 | 2006-09-01 | 2007-04-01 |  | 2008-04-01 | 2008-12-01 | 15000 | -15 | 14985 | 14984.65 | 100% | 0.35 | 0 |  | 1125 | -1 | 1124 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | IVC | PHA | 54 | INV | 29 | A | I |  | 0 | 0 |  |  | 2008-04-01 | 2008-11-01 | 2010-03-31 |  | 2009-12-01 | 2010-12-01 | 162000 | 0 | 162000 | 162000.02 | 100% | -0.02 | 0 |  | 12150 | 0 | 12150 | 0 | 0 | FIN |  |  |  | INV
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | IVC | PHA | 54 | TAS | 28 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-08-01 | 2010-03-01 |  | 2010-03-01 | 2011-03-01 | 173000 | 0 | 173000 | 173000 | 100% | 0 | 0 |  | 22490 | 0 | 22490 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | IVC | PHA | 57 | PRP | 30 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-08-01 | 2010-03-01 |  | 2012-02-01 | 2013-02-01 | 85000 | -18026 | 66974 | 66974 | 100% | 0 | 0 |  | 11050 | -2343.38 | 8706.62 | 0 | 0
FIN | UNEP | TPMP verification | Individual | AFR | IVC | PHA | 57 | TAS | 31 | A | I |  | 0 | 0 | 0 |  | 2009-04-01 | 2009-08-01 | 2010-03-01 |  | 2009-12-01 | 2010-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0
FIN | UNIDO | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | IVC | PHA | 58 | INV | 34 | A | I | CFC | 44.1 | 44.1 |  |  | 2009-07-01 | 2009-12-01 | 2010-07-31 |  | 2014-03-01 | 2014-09-01 | 121000 | -11401 | 109599 | 109599.34 | 100% | -0.34 | 0 |  | 9075 | -855 | 8220 | 0 | 0 | FIN |  |  |  | INV
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | IVC | PHA | 58 | TAS | 33 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2009-12-01 | 2010-07-01 |  | 2012-02-01 | 2013-12-01 | 109000 | 0 | 109000 | 109000 | 100% | 0 | 0 |  | 14170 | 0 | 14170 | 0 | 0
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | IVC | PHA | 66 | INV | 36 | A | I | HCFC | 3.3 | 0 |  |  | 2012-04-01 | 2013-11-01 | 2016-04-30 | 2019-03-01 |  |  | 460000 | 0 | 460000 | 7995.88 | 1.738% | 452004.12 | 178792.17 | 100000 | 34500 | 0 | 600 | 33900 | 13409.4127 | Equipment prepared by supplier, shipped and is now in the country. Procedure for removal from port is completed. Equipment could not be delivered to beneficiary due to lack of adequate rooms. Was there any delay during the reporting year? Yes, as above. Any recurring problem? No Any impact on project completion date: Yes Any action required by Executive Committee? No | Equipment not yet handed over to beneficiary training center, pending upgrade of dedicated rooms. |  |  | INV
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | IVC | PHA | 66 | TAS | 37 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 | 2012-10-01 | 2014-04-01 | 2017-12-01 |  |  | 250000 | 0 | 250000 | 143417.74 | 57.37% | 106582.26 | 104943.97 | 10658.226 | 30260 | 0 | 17359.2832 | 12900.7168 | 12702.4181 | UNEP was to quick in putting COM as the new SSFA is needed to be signed to complete the work. The project is now ONG. | UNEP was to quick in putting COM as the new SSFA is needed to be signed to complete the work. The project is now ONG.
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | AFR | IVC | PHA | 75 | TAS | 41 | A | I |  | 3.1 |  | 0 |  | 2015-11-01 | 2016-07-01 | 2017-09-01 | 2017-12-01 |  |  | 190000 | 0 | 190000 | -0.41 | -0.0002158% | 190000.41 | 190000 | 19000.041 | 22998 | 0 | -0.049627 | 22998.0496 | 22998 | Brief progress report (actual/planned): SSFA was signed in March 2016 and first payment sent in July 2016. Legal arrangements (actual/planned): signed in March 2016 (Yes/No):_ First mission (actual/planned): _n/a TOR completed (actual/planned): _N/A__ First disbursement date (actual/planned): July 2016__ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _No_ If Yes, reasons for delay & action plan to resolve: __ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): SSFA was signed in March 2016 and first payment sent in July 2016. Country reported 2015 Art5 data and 2015 CP data in May 2016. Legal arrangements (actual/planned): signed in March 2016. NOU trained 50 RAC technicians and 30 enforcement officers in 2016. (Yes/No):_ First mission (actual/planned): _n/a TOR completed (actual/planned): _N/A__ First disbursement date (actual/planned): July 2016__ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _No_ If Yes, reasons for delay & action plan to resolve: __ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__
FIN | UNEP | Training for refrigeration and air conditioning technicians | Individual | AFR | IVC | REF | 13 | TRA | 03 | A | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1995-10-01 | 1995-07-01 |  | 1997-03-01 | 1999-04-01 | 76000 | 0 | 76000 | 76000 | 100% | 0 | 0 |  | 9880 | 0 | 9880 | 0 | 0
CLO | UNIDO | Project formulation for the ODS phase-out in the refrigeration sector | Individual | AFR | IVC | REF | 16 | PRP | 04 | A | I |  | 0 | 0 |  |  | 1995-03-01 | 1995-05-01 | 1995-06-01 |  |  | 1999-11-01 | 15000 | -84 | 14916 | 14916 | 100% | 0 | 0 |  | 1950 | -14 | 1936 | 0 | 0 | CLO
FIN | France | Refrigeration management plan preparation |  | AFR | IVC | REF | 21 | PRP | 09 | A | I |  | 0 |  | 0 |  | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1998-03-01 | 1998-03-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed
FIN | UNIDO | Preparation of an investment project in the domestic refrigeration (hydrocarbon) sector for Serti | Individual | AFR | IVC | REF | 24 | PRP | 11 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-09-01 | 1999-04-01 |  | 1999-10-01 | 2000-12-01 | 20000 | -10918 | 9082 | 9082 | 100% | 0 | 0 |  | 2600 | -1421 | 1179 | 0 | 0 | FIN |  |  | 1999-06-01
CLO | France | Implementation of the RMP | RMP | AFR | IVC | REF | 24 | TAS | 10 | A | I | CFC | 24.8 |  | 0 |  | 1998-03-01 | 1999-10-01 | 2000-04-01 |  |  | 2009-04-01 | 227650 | -196214 | 31436 | 31436 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project cancelled in favor of TPMP as per decision 57/xx(e).
FIN | France | Documentary on traffic in second-hand refrigerators |  | AFR | IVC | REF | 27 | TAS | 14 | A | I |  | 0 |  | 0 |  | 1999-03-01 | 1999-04-01 | 2000-06-01 |  | 1999-07-01 | 1999-07-01 | 12000 | -2381 | 9619 | 9619 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed
TRF | France | ODS phase out in 50 existing centrifugal chillers units | Individual | AFR | IVC | REF | 37 | INV | 17 | A | I | CFC | 0 |  | 0 |  | 2002-07-01 |  | 2006-08-01 |  |  | 2009-04-01 | 1000000 | -1000000 | 0 | 0 |  | 0 |  | 0 | 100000 | -100000 | 0 | 0 |  | Project transferred to UNIDO per decision 57/xx(f).
FIN | France | Project preparation for projects in commercial refrigeration production facilities |  | AFR | IVC | REF | 37 | PRP | 15 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 1999-12-01 | 2003-08-01 |  | 2004-12-01 | 2004-12-01 | 15000 | -1636 | 13364 | 13364 | 100% | 0 |  | 0 | 750 | 0 | 750 | 0 |  | Project completed. A study on a replacement programme for centrifugal chillers was completed in 2002. It was followed by a proposal on the phase out of CFC emissions in centrifugal chillers through energy related activities. Balance returned at the 57th ExCom.
CLO | France | Implementation of the refrigerant management plan: monitoring the activities of the RMP and set up of an import/export licensing system | RMP | AFR | IVC | REF | 37 | TAS | 16 | A | I | CFC | 188.7 |  | 0 |  | 2002-07-01 |  | 2004-08-01 |  |  | 2009-04-01 | 49500 | -49500 | 0 | 0 |  | 0 |  | 0 | 4950 | -4950 | 0 | 0 |  | Project cancelled in favor of TPMP as per decision 57/xx(e).
FIN | UNIDO | ODS phase out in 50 existing centrifugal chillers units | Individual | AFR | IVC | REF | 57 | INV | 32 | A | I | CFC | 18 | 17.5 |  |  | 2009-04-01 | 2009-06-01 | 2011-04-01 |  | 2013-12-01 | 2014-04-01 | 1000000 | -968426 | 31574 | 31573.91 | 100% | 0.09 | 0 |  | 75000 | -72632 | 2368 | 0 | 0 | FIN |  |  |  | INV
FIN | UNEP | Country programme preparation | Individual | AFR | IVC | SEV | 11 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-01 | 1994-11-01 |  | 1994-03-01 | 1994-12-01 | 13000 | 0 | 13000 | 13000 | 100% | 0 | 0 |  | 1690 | 0 | 1690 | 0 | 0
FIN | UNEP | Institutional strengthening (establishment of the Ozone Secretariat) | Individual | AFR | IVC | SEV | 13 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1996-01-01 | 1997-07-01 |  | 1998-10-01 | 1999-07-01 | 122810 | -300 | 122510 | 122510 | 100% | 0 | 0 |  | 15965 | -39 | 15926 | 0 | 0
FIN | UNIDO | ODS phase-out of a foam producing plant (Fabrique Ivoirienne de mousse et amemblement) and 2 aerosol fillers (Sicobel and Gandoor) | Individual | AFR | IVC | SEV | 17 | PRP | 05 | A | I |  | 0 | 0 |  |  | 1995-07-01 | 1996-02-01 | 1995-09-01 |  | 1996-10-01 | 1998-08-01 | 10000 | -388 | 9612 | 9612 | 100% | 0 | 0 |  | 1300 | -52 | 1248 | 0 | 0 | FIN
FIN | UNEP | Renewal of the institutional strengthening project | Individual | AFR | IVC | SEV | 26 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-08-01 | 2000-12-01 |  | 2004-04-01 | 2004-12-01 | 81800 | 0 | 81800 | 81800 | 100% | 0 | 0 |  | 10634 | 0 | 10634 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (phase III) | Individual | AFR | IVC | SEV | 43 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-09-01 | 2005-07-01 |  | 2005-11-01 | 2007-08-01 | 53170 | 0 | 53170 | 53170 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase III, year 2) | Individual | AFR | IVC | SEV | 48 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-05-01 | 2007-04-01 |  | 2007-12-01 | 2008-12-01 | 53170 | 0 | 53170 | 53170 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | IVC | SEV | 53 | INS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-02-01 | 2009-11-01 |  | 2010-06-01 | 2011-06-01 | 106340 | 0 | 106340 | 106340 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | AFR | IVC | SEV | 62 | INS | 35 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-02-01 | 2012-12-01 |  | 2012-12-01 | 2013-12-01 | 106340 | 0 | 106340 | 106340 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of the institutional strengthening project (phase VI: 1/2013-12/2014) | Individual | AFR | IVC | SEV | 68 | INS | 38 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-03-01 | 2014-12-01 |  | 2015-12-01 |  | 106340 | 0 | 106340 | 81085.93 | 76.25% | 25254.07 | 25235.28 | 25254 | 0 | 0 | 0 | 0 | 0 | Project completed | Project completed
ONG | UNEP | Extension of the institutional strengthening project (phase VII: 1/2015-12/2016) | Individual | AFR | IVC | SEV | 73 | INS | 39 | A | I |  | 0 |  | 0 |  | 2014-11-01 | 2016-01-01 | 2016-12-01 | 2017-12-01 |  |  | 106340 | 0 | 106340 | 0 | 0% | 106340 | 106340 | 10634 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Country reported 2015 Art5 data and 2015 CP data in May 2016. Legal arrangements (actual/planned): Agreement signed in April 2015. First payment sent in January 2016. All activities under the SSFA are completed (as planned) __No_ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in January 2016 __ All funds disbursed (yes/no): Yes_ _ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Brief progress report (actual/planned): Legal arrangements (actual/planned): Agreement signed in April 2015. First payment sent in January 2016. Country reported 2015 Art5 data and 2015 CP data in May 2016. NOU trained 50 RAC technicians and 30 enforcement officers in 2016. All activities under the SSFA are completed (as planned) __No_ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in January 2016 __ All funds disbursed (yes/no): Yes_ _ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | AFR | IVC | SEV | 74 | TAS | 40 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-06-01 | 2016-05-01 | 2017-10-01 |  |  | 110000 | 0 | 110000 | -0.08 | -7.273e-05% | 110000.08 | 110000 | 11000.008 | 14300 | 0 | -0.0104 | 14300.0104 | 14300 | Brief progress report (actual/planned): Legal arrangements (actual/planned): signed in March 2016_Consultant hired in April 2016, and ODS alternatives survey report draft is planned to be sent in Jan. 2017. First mission (actual/planned): __n/a_ TOR completed (actual/planned): _N/A__ First disbursement date (actual/planned): June 2016__ all funds disbursed (yes/no): _NO__ Any delay? (yes/no): _No_ If Yes, reasons for delay & action plan to resolve: NO__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): _Consultant hired in April 2016, and ODS alternatives survey report draft sent in Jan. 2017. Legal arrangements (actual/planned): signed in March 2016 (Yes/No): No_ First mission (actual/planned): __n/a_ TOR completed (actual/planned): _N/A__ First disbursement date (actual/planned): June 2016__ all funds disbursed (yes/no): _NO__ Any delay? (yes/no): _YES_ If Yes, reasons for delay & action plan to resolve: NO__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__
ONG | UNEP | Extension of the institutional strengthening project (phase VIII: 1/2017-12/2018) | Individual | AFR | IVC | SEV | 77 | INS | 42 | A | I |  | 0 |  | 0 |  | 2016-12-01 |  | 2018-12-01 | 2018-12-01 |  |  | 136115 | 0 | 136115 | 0 | 0% | 136115 | 0 | 13611.5 | 0 | 0 | 0 | 0 | 0 | Newly approved project | Brief progress report (actual/planned): Project newly approved. Agreement not signed yet. Legal arrangements (actual/planned): Agreement not signed yet. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement _no __ All funds disbursed (yes/no): _ Final payment _no___ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
FIN | UNDP | Elimination of CFCs in the manufacture of extruded polystyrene foam sheet at West Indies Synthetics Company, Ltd (Wisynco) | Individual | LAC | JAM | FOA | 22 | INV | 06 | A | I | CFC | 81.6 | 81.6 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-05-01 |  | 1998-12-01 | 2000-12-01 | 596000 | -3008.19 | 592991.81 | 592992 | 100% | -0.19 | 0 | 0 | 77480 | -391.06 | 77088.96 | -0.02 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | LAC | JAM | FOA | 61 | PRP | 26 | N | I | HCFC | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-04-01 | 2011-07-01 |  | 2012-05-01 | 2013-06-01 | 30000 | -987.3 | 29012.7 | 29013 | 100% | -0.3 | 0 | 0 | 2250 | -74.05 | 2175.975 | -0.025 | 0 | Financially completed in 2013. | Completed in 2012. No activities in 2013. | 2010 |  | Investment
FIN | UNIDO | Preparation of a phase out project (tobacco fumigation) | Individual | LAC | JAM | FUM | 24 | PRP | 08 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-04-01 | 1999-04-01 |  | 1998-09-01 | 2001-07-01 | 25000 | -1950 | 23050 | 23050 | 100% | 0 | 0 |  | 3250 | -258 | 2992 | 0 | 0 | FIN
CLO | UNIDO | Demonstration project - alternatives to the use of methyl bromide in structural and commodity fumigation | Individual | LAC | JAM | FUM | 26 | DEM | 10 | A | I |  | 0 | 0 |  |  | 1998-11-01 |  | 1999-12-01 |  |  | 2001-07-01 | 102850 | -102850 | 0 | 0 | #DIV/0! | 0 | 0 |  | 13371 | -13371 | 0 | 0 | 0 | CLO
FIN | Canada | Project preparation for the phase-out of methyl bromide |  | LAC | JAM | FUM | 43 | PRP | 21 | A | I |  | 0 |  | 0 |  | 2004-07-01 | 2005-01-01 | 2005-07-01 |  | 2005-09-01 | 2005-09-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 |  | 0 | 1125 | 0 | 1125 | 0 |  | Project proposal completed in September 2005, submitted and approved at ExCom 47. |  | 2004 |  | Non-Inv.
FIN | Canada | Technical assistance to phase-out the use of methyl bromide | Individual | LAC | JAM | FUM | 47 | TAS | 22 | A | I | MBR | 1.2 | 1.2 | 0 |  | 2005-11-01 | 2006-09-01 | 2007-12-01 |  | 2011-11-01 | 2013-08-01 | 55530 | -7162 | 48368 | 48368 | 100% | 0 |  | 0 | 7219 | 0 | 7219 | 0 |  | Project completed in November 2011 as reported to ExCom 65. Initally, $2,733 in project costs were identified as remaining upon closure and were returned to ExCom 67 in July 2012. However, in developing PCR, Canada identified another unspent of balance $4,429 for the project and returned this amount to ExCom 70, which was when the project was considered financially closed. |  | 2005 | 2009-04-01 | Investment
FIN | Canada | Terminal phase-out management plan for CFCs: training and recovery and recycling | One-off Phase-out | LAC | JAM | PHA | 37 | TAS | 16 | A | I | CFC | 57.5 | 57.5 | 0 |  | 2002-07-01 | 2002-09-01 | 2006-01-01 |  | 2006-03-01 | 2006-03-01 | 240000 | 0 | 240000 | 240000 | 100% | 0 |  | 0 | 31200 | 0 | 31200 | 0 |  | All activities completed by end of 2005. Final monitoring reports received in March 2006. Jamaica provided comprehensive report on R&R activities. |  | 2002 |  | Non-Inv.
FIN | UNDP | Terminal phase-out management plan for CFCs: retrofitting/replacement programme | Individual | LAC | JAM | PHA | 37 | TAS | 17 | N | I | CFC | 2 | 2 | 0 | 0 | 2002-07-01 | 2003-02-01 | 2006-01-01 |  | 2007-12-01 | 2011-09-01 | 140000 | -7662.97 | 132337.03 | 132337 | 100% | 0.03 | 0 | 0 | 18200 | -996.19 | 17203.81 | 0 | 0 | Financially completed in 2011. |  | 2002 |  | Non-Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | JAM | PHA | 55 | PRP | 24 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2011-07-01 | 2012-08-01 | 85000 | -28034.97 | 56965.03 | 56965 | 100% | 0.03 | 0 | 0 | 6375 | -2102.62 | 4272.375 | 0.00505 | 0 | Financially completed in 2012. | Completed in 2011. HPMP approved by the 64th Executive Committee Meeting. Some final invoices pending. | 2008 |  | Investment
COM | UNDP | HCFC phase-out management plan (foam sector) (stage I, first tranche) | Multi-Year | LAC | JAM | PHA | 64 | INV | 28 | N | I | HCFC | 3.6 | 3.6 | 0 | 0 | 2011-07-01 | 2012-07-01 | 2013-07-01 |  | 2014-12-01 |  | 95450 | 0 | 95450 | 89537.4 | 93.81% | 5912.6 | 0 | 5025.71 | 7159 | 0 | 6715.5395 | 443.4605 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2014. |  | 2011 |  | Investment
FIN | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | JAM | PHA | 64 | INV | 29 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-02-01 | 2013-07-01 |  | 2015-05-01 | 2016-05-01 | 142000 | 0 | 142000 | 142000 | 100% | 0 | 0 | 0 | 10650 | 0 | 10650 | 0 | 0 | Financially completed in 2016. | Since 2014, third "train the trainers" took place in Ocho Rios. Tools were delivered to the training local in Ocho Rios and awareness activities took place in the country | 2011 |  | Investment
COM | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | JAM | PHA | 64 | TAS | 30 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-06-01 | 2013-07-01 |  | 2015-12-01 |  | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Project completed. All funds have been disbursed and the final expenditure report needs to be processed. | Project completed. All funds have been disbursed and the final expenditure report needs to be processed.
COM | UNDP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | LAC | JAM | PHA | 70 | INV | 32 | N | I | HCFC | 4.7 | 0.9 | 0 | 0 | 2013-07-01 | 2014-01-01 | 2016-07-01 |  | 2016-07-01 |  | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 7500 | 0 | 7500 | 0 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Equipment procured in 2016 and delivered to beneficiary technicians that completed the training. Training by international expert conducted. Working with vocational schools to improve training. Prodoc signed (actual/planned, yes/no and date):Signed earlier Missions undertaken (actual/planned):1 of 1 TOR for consultants/subcontracts completed (actual/planned): 1 of 1 Contract/PO/MOA agreements signed: NA First disbursement date (actual/planned): 41640Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | Completed in 2016 | 2013 |  | Investment
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | LAC | JAM | PHA | 70 | TAS | 33 | A | I |  | 0.2 |  | 0 |  | 2013-07-01 | 2016-04-01 | 2016-07-01 | 2017-06-01 |  |  | 18000 | 0 | 18000 | 9326.56 | 51.81% | 8673.44 | 8673.44 | 867.344 | 2340 | 0 | 1212.4528 | 1127.5472 | 1127.5472 | Brief progress report (actual/planned): SSFA signed in Mar-16. First disbursement processed in Apr-16. Training of 10 enforcement officers in two workshops. Procurement of 2 identifiers. Code of practice for RAC industry was revised; printing and distribution will follow. Third tranche request submitted to ExCom 76 and approved___ Legal arrangements (actual/planned): Mar-16 /Dec-2015 ___ First mission (actual/planned): ___ TOR completed (actual/planned): ___ First disbursement date (actual/planned): Apr-16/Dec-15___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): yes___ If Yes, reasons for delay & action plan to resolve: outstanding reports from first tranche delayed signature of SSFA corresponding to second tranche. UN Environment guided and follow-up with NOU on progress. ___ If Yes, will delay have impact on project completion date (yes/no): yes___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): Final progress and financial report sent by NOU in Jan-17. UN Environment processing last disbursement to complete this project___ Legal arrangements (actual/planned): Mar-16 /Dec-2015 ___ First mission (actual/planned): ___ TOR completed (actual/planned): ___ First disbursement date (actual/planned): Apr-16/Dec-15___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): yes___ If Yes, reasons for delay & action plan to resolve: financial report required disaggregation of expenditures by tranche. This has delayed release of last disbursement. UN Environment is guiding NOU on how to report and will process payment once report is re-submitted. ___ If Yes, will delay have impact on project completion date (yes/no): yes___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___
ONG | UNDP | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | LAC | JAM | PHA | 76 | INV | 36 | N | I | HCFC | 0 | 0 | 0 | 0 | 2016-05-01 | 2016-11-01 | 2019-12-01 | 2017-12-01 |  |  | 183000 | 0 | 183000 | 34247.08 | 18.71% | 148752.92 | 0 | 59501.168 | 13725 | 0 | 2568.531 | 11156.469 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Equipment procured in 2016 and delivered to beneficiary technicians that completed the training. Training by international expert conducted. Working with vocational schools to improve training. Prodoc signed (actual/planned, yes/no and date):Signed earlier Missions undertaken (actual/planned):1 of 1 TOR for consultants/subcontracts completed (actual/planned): 1 of 1 Contract/PO/MOA agreements signed: NA First disbursement date (actual/planned): Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | identification of additional technicians that need could be included in the training programme. |  |  | Investment
ONG | UNEP | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | LAC | JAM | PHA | 76 | TAS | 37 | A | I |  | 0.4 |  | 0 |  | 2016-05-01 |  | 2019-12-01 | 2019-12-01 |  |  | 31000 | 0 | 31000 | 0 | 0% | 31000 | 0 | 3100 | 4030 | 0 | 0 | 4030 | 0 | Brief progress report (actual/planned): Project approved in ExCom 76. It was agreed with country to discuss a new SSFA in 2017 once activities of second tranche are about to be completed___ Legal arrangements (actual/planned): ---/Mar-17 ___ First mission (actual/planned): ___ TOR completed (actual/planned): ___ First disbursement date (actual/planned): ---/Mar-17___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): no___ If Yes, reasons for delay & action plan to resolve. ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): Draft SSFA to be prepared in Mar-17, discusssed and signed___ Legal arrangements (actual/planned): ---/Apr-17 ___ First mission (actual/planned): ___ TOR completed (actual/planned): ___ First disbursement date (actual/planned): ---/May-17___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): no___ If Yes, reasons for delay & action plan to resolve. ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | JAM | REF | 18 | TAS | 03 | A | I | CFC | 17 | 17 | 0 | 0 | 1995-11-01 | 1996-02-01 | 1997-05-01 |  | 1997-05-01 | 2000-12-01 | 172465 | -13366.44 | 159098.56 | 159099 | 100% | -0.44 | 0 | 0 | 22420.45 | -1737.64 | 20682.87 | -0.06 | 0 | Completed in 1997. Financially completed in 2000. |  | 1995 |  | Investment
FIN | USA | MAC demonstration project |  | LAC | JAM | REF | 23 | DEM | 07 | A | I | CFC | 9.6 |  | 0 |  | 1997-11-01 | 1998-02-01 | 1998-12-01 |  | 1999-06-01 | 2000-07-01 | 130000 | 0 | 130000 | 130000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Equipment delivered and training conducted in March 99, with follow-up mission in June 1999. Final report will be submitted June 2000. |  | 1997
FIN | UNEP | Development of refrigerant management plan | RMP | LAC | JAM | REF | 24 | PRP | 09 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1999-02-01 |  | 1999-02-01 | 1999-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | Canada | Implementation of the RMP: training of trainers in refrigeration and certification of technicians | RMP | LAC | JAM | REF | 27 | TRA | 11 | A | I |  | 0 |  | 0 |  | 1999-03-01 | 1999-05-01 | 2000-10-01 |  | 2000-08-01 | 2001-03-01 | 50850 | 0 | 50850 | 50850 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Phase 1 (train-the trainer) completed 7-11 June 1999. Phase 2 completed in June 2000. Monitoring and evaluation completed August 2000. |  | 1999 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: customs officers training programme | RMP | LAC | JAM | REF | 27 | TRA | 12 | A | I |  | 0 |  | 0 |  | 1999-03-01 | 2000-03-01 | 2000-10-01 |  | 2001-11-01 | 2001-12-01 | 54240 | 0 | 54240 | 54240 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Legislation finalized in July 99. Phase 1 -train-the-trainer- completed June 2000, Phase 2 completed in Nov. 2000, Monitoring and evaluation completed in Nov. 2001. |  | 1999 | 2001-12-01 | Non-Inv.
FIN | UNDP | Preparation of a project in the commercial refrigeration subsector | Individual | LAC | JAM | REF | 30 | PRP | 14 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2002-05-01 | 2004-02-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNEP | Country programme preparation | Individual | LAC | JAM | SEV | 12 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-06-01 | 1995-06-01 |  | 1996-06-01 | 1997-05-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNDP | Project preparation assistance | Individual | LAC | JAM | SEV | 14 | PRP | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-09-01 | 1994-10-01 | 1995-05-01 |  | 1996-12-01 | 1998-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNEP | Institutional strengthening through creation of a National Ozone Unit | Individual | LAC | JAM | SEV | 20 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-05-01 | 1999-10-01 |  | 2000-05-01 | 2001-12-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 |  | 8580 | 0 | 8580 | 0 | 0 |  |  |  | 2000-03-01
FIN | UNDP | Project preparation in the aerosol, foam and refrigeration sectors | Individual | LAC | JAM | SEV | 21 | PRP | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2000-12-01 | 30000 | -16175 | 13825 | 13825 | 100% | 0 | 0 | 0 | 3900 | -2102.75 | 1797.25 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | LAC | JAM | SEV | 29 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-05-01 | 2001-12-01 |  | 2001-12-01 | 2003-01-01 | 44000 | 0 | 44000 | 44000 | 100% | 0 | 0 |  | 5720 | 0 | 5720 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project | Individual | LAC | JAM | SEV | 35 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-03-01 | 2004-01-01 |  | 2003-08-01 | 2004-10-01 | 44000 | 0 | 44000 | 44000 | 100% | 0 | 0 |  | 5720 | 0 | 5720 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project | Individual | LAC | JAM | SEV | 40 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2004-01-01 | 2005-07-01 |  | 2006-01-01 | 2007-01-01 | 57200 | 0 | 57200 | 57200 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase V) | Individual | LAC | JAM | SEV | 47 | INS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-06-01 | 2008-02-01 |  | 2008-06-01 | 2009-06-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase VI) | Individual | LAC | JAM | SEV | 55 | INS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-12-01 | 2010-11-01 |  | 2010-11-01 | 2011-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase VII) | Individual | LAC | JAM | SEV | 62 | INS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-08-01 | 2012-11-01 |  | 2013-10-01 | 2015-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of institutional strengthening project (phase VIII: 1/2013-12/2014) | Individual | LAC | JAM | SEV | 68 | INS | 31 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2014-04-01 | 2014-12-01 |  | 2015-12-01 |  | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. All funds are disbursed. The final expenditure report is received and processed | Project completed. All funds are disbursed. The final expenditure report is received and processed
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | LAC | JAM | SEV | 74 | TAS | 34 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-03-01 | 2016-05-01 | 2017-07-01 |  |  | 70000 | 0 | 70000 | 0.38 | 0.0005429% | 69999.62 | 63030 | 6999.962 | 9100 | 0 | 0.0494 | 9099.9506 | 8193.9 | Brief progress report (actual/planned): SSFA signed by UN Environment in Feb-16 and by Government in Jun-16. Regional Consultant selected and contract signed in Jul-16. National consultant hired in Oct-16. Stakeholders meeting held in Nov-16. Collection of information completed in Dec-16. Report sent in Dec-16 ___. Legal arrangements (actual/planned): Jun-16/Feb-16 ___ First mission (actual/planned):Dec-16/Mar-16 ___ TOR completed (actual/planned): May-16/Feb-16___ First disbursement date (actual/planned): March-16/Feb-16 ___ All funds disbursed (yes/no): No___ Any delay? (yes/no): no___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no):___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): Report review ongoing. Completion date revised to Jul-17 to reflect submission of the report to the second ExCom in 2017 ___. Legal arrangements (actual/planned): Jun-16/Feb-16 ___ First mission (actual/planned):Dec-16/Mar-16 ___ TOR completed (actual/planned): May-16/Feb-16___ First disbursement date (actual/planned): March 16/Feb-16 ___ All funds disbursed (yes/no): No___ Any delay? (yes/no): no___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no):___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___
ONG | UNEP | Extension of institutional strengthening project (phase IX: 12/2015-11/2017) | Individual | LAC | JAM | SEV | 75 | INS | 35 | A | I |  | 0 |  | 0 |  | 2015-11-01 |  | 2017-11-01 | 2017-11-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Licensing and quotas have been implemented. 2015 CP Data and Art.7 Data reported on time. Management of HPMP implementation, tranche request and ODS Alternatives Survey. Celebration of Ozone day activities and other realted awareness raising activities during 2016. NOU participated in the Joint Network Meeting in Chile, May-16 and in the Caribbean Thematic Meeting on ODS Alternatives Surveys in Barbados, Dec-16. Discussion of text of new SSFA required review and clearance from UN Environment Legal Department. The text of the SSFA was agreed in Dec-16 ___Legal arrangements (actual/planned): ---/Jul-16.___Initial stages of project implementation (actual/planned):___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): ---/Dec-16.___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): yes___ If Yes, reasons for delay & action plan to resolve: Signature of SSFA delayed since proposed changes on standard clauses of SSFA required clearance by UN Environment Legal department. UN Environment consulted promptly Legal Department until an agreement on the final text was reached. ___ If Yes, will delay have impact on project completion date (yes/no): no. ___ Any ongoing problems (yes/no): no. ___ If Yes, is any action required by ExCom: ___. | Brief progress report (actual/planned): NOU collecting 2016 data in order to report timely CP Data and Art.7 Data to corresponding Secretariats. Reprogramming of funds into 2017 completed. SSFA signed by UN Environment in Feb-17. Awaiting country's signature ___Legal arrangements (actual/planned): ---/ Jul-16.___Initial stages of project implementation (actual/planned):___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): ---/Dec-16.___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): yes___ If Yes, reasons for delay & action plan to resolve: Signature of SSFA delayed since proposed changes on standard clauses of SSFA required clearance by UN Environment Legal department. UN Environment consulted promptly Legal Department until an agreement on the final text was reached. ___ If Yes, will delay have impact on project completion date (yes/no): no. ___ Any ongoing problems (yes/no): no. ___ If Yes, is any action required by ExCom: ___.
FIN | UNDP | Formulation of the solvent sectoral phase out plan | Individual | LAC | JAM | SOL | 39 | PRP | 18 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2005-07-01 | 2006-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1125 | 0 | 1125 | 0 | 0 | Completed in 2005. Financially completed in 2006. |  | 2003 |  | Investment
FIN | UNDP | Technical assistance umbrella project to phase out ODS solvent use | Individual | LAC | JAM | SOL | 42 | TAS | 20 | N | I | TCA | 0.8 | 0.8 | 0 | 0 | 2004-04-01 | 2005-02-01 | 2006-04-01 |  | 2006-12-01 | 2011-08-01 | 25000 | -3609.49 | 21390.51 | 21391 | 100% | -0.49 | 0 | 0 | 2250 | -324.85 | 1925.19 | -0.04 | 0 | Completed in 2006. Financially completed in 2011. |  | 2004 |  | Non-Investment
FIN | UNDP | Technical assistance and pre-feasibility study in aerosol sector | Individual | ASP | JOR | ARS | 04 | TAS | 01 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-08-01 | 1992-06-01 |  | 1992-02-01 | 1997-12-01 | 29000 | 0 | 29000 | 29000 | 100% | 0 | 0 | 0 | 3770 | 0 | 3770 | 0 | 0 | Completed in 1992. Financially completed in 1997. |  | 1991 |  | Non-Investment
FIN | UNDP | Feasibility study on deodorization of local gas as a CFC substitute in cosmetics | Individual | ASP | JOR | ARS | 06 | TAS | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-02-01 | 1993-06-01 |  | 1993-06-01 | 1997-12-01 | 12000 | 0 | 12000 | 12000 | 100% | 0 | 0 | 0 | 1560 | 0 | 1560 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | IBRD | LPG purification at Jordan Refinery Company | Individual | ASP | JOR | ARS | 07 | INV | 12 | N | I | CFC | 0 | 0 | 0 | 0 | 1992-06-01 | 1997-01-01 | 1995-06-01 |  | 1998-01-01 | 1998-05-01 | 805000 | 0 | 805000 | 805000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. This project is part of the line-of-grant project and was covered by part of the $1.5 million total approved. $1,496,095 disbursed for the line-of-grant - balance returned to the 36th ExCom. |  |  | 1997-07-01 | INV | 0
FIN | IBRD | Phase out of CFC use in aerosol at Household and Toiletries | Individual | ASP | JOR | ARS | 07 | INV | 13 | N | I | CFC | 30 | 30 | 0 | 0 | 1992-06-01 | 1996-07-01 | 1995-06-01 |  | 1998-04-01 | 1998-05-01 | 135000 | 0 | 135000 | 135000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. This project is part of the line-of-grant project and was covered by part of the $1.5 million total approved. $1,496,095 disbursed for the line-of-grant - balance returned to the 36th ExCom. |  |  | 1997-06-01 | INV | 0
FIN | IBRD | Phase out of CFC use in aerosol at Haddad and Sons Inc. | Individual | ASP | JOR | ARS | 07 | INV | 14 | N | I | CFC | 85 | 85 | 0 | 0 | 1992-06-01 | 1995-08-01 | 1995-06-01 |  | 1997-12-01 | 1998-05-01 | 214200 | 0 | 214200 | 214200 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. This project is part of the line-of-grant project and was covered by part of the $1.5 million total approved. $1,496,095 disbursed for the line-of-grant - balance returned to the 36th ExCom. |  |  | 1997-07-01 | INV | 0
FIN | IBRD | Aerosol conversion at Jordan Industrial Petrochemical Co. Ltd. (JIPCO) | Individual | ASP | JOR | ARS | 20 | INV | 26 | N | I | CFC | 98 | 98 | 0 | 0 | 1996-10-01 | 2002-12-01 | 1997-10-01 |  | 2003-10-01 | 2003-12-01 | 102855 | 0 | 102855 | 102855 | 100% | 0 | 0 |  | 13371.15 | 0 | 13371.15 | 0 | 0 | Project completed. |  |  | 2002-03-01 | INV | 0
FIN | IBRD | Aerosol conversion at Jordan Antiseptics and Detergents Ind. Co. Ltd. (JADICO) | Individual | ASP | JOR | ARS | 20 | INV | 27 | N | I | CFC | 20 | 20 | 0 | 0 | 1996-10-01 | 1999-03-01 | 1997-10-01 |  | 1998-12-01 | 1999-05-01 | 65720 | 0 | 65720 | 65720 | 100% | 0 | 0 |  | 8543.6 | 0 | 8543.6 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Aerosol conversion at Jordan Chemical Products Co. Ltd. (JCPCO) | Individual | ASP | JOR | ARS | 20 | INV | 28 | N | I | CFC | 61 | 61 | 0 | 0 | 1996-10-01 | 1998-01-01 | 1997-10-01 |  | 1998-12-01 | 1999-05-01 | 203328 | 0 | 203328 | 203328 | 100% | 0 | 0 |  | 26432.64 | 0 | 26432.64 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | UNIDO | Project preparation in the aerosol sector | Individual | ASP | JOR | ARS | 30 | PRP | 56 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-08-01 | 2001-04-01 |  | 2001-01-01 | 2002-05-01 | 20000 | -7413 | 12587 | 12587.48 | 100% | -0.48 | 0 |  | 2600 | -966 | 1634 | 0 | 0 | FIN
FIN | IBRD | Project preparation of projects in the aerosol sector |  | ASP | JOR | ARS | 30 | PRP | 59 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Substitution of CFC-12 for HAPs for perfumes and cosmetics at the aerosol plant Abu Shakra Factory | Individual | ASP | JOR | ARS | 31 | INV | 63 | N | I | CFC | 18 | 18 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2003-01-01 |  | 2003-08-01 | 2003-11-01 | 76676 | 0 | 76676 | 76676 | 100% | 0 | 0 |  | 9967.88 | 0 | 9967.88 | 0 | 0 | Enterprise has ceased using CFCs. Project conversion is completed. Remaining amount of the grant has been requested and payment process initiated. |  |  |  | INV | 0
FIN | IBRD | Substitution of CFC-12 for HAPs at the aerosol plant of Arab Chemical Industries | Individual | ASP | JOR | ARS | 31 | INV | 64 | N | I | CFC | 13 | 13 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2003-01-01 |  | 2005-02-01 | 2005-02-01 | 49539 | 0 | 49539 | 49539 | 100% | 0 | 0 |  | 6440.07 | 0 | 6440.07 | 0 | 0 | Project completed. |  |  | 2003-06-01 | INV | 0
FIN | UNIDO | Phase-out of CFC-12 in the manufacture of hair lacquers by conversion to hydrocarbon propellant at Jordan Tunisian Chemical Company | Individual | ASP | JOR | ARS | 32 | INV | 68 | A | I | CFC | 12 | 12 |  |  | 2000-12-01 | 2001-10-01 | 2003-03-01 |  | 2002-12-01 | 2003-10-01 | 52800 | -23 | 52777 | 52776.74 | 100% | 0.26 | 0 |  | 6864 | -14 | 6850 | 0 | 0 | FIN
TRF | IBRD | Reduction of CFC-11 in rigid insulation foams in domestic and commercial refrigerators | Individual | ASP | JOR | FOA | 07 | INV | 05 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1994-06-01 |  |  | 1994-01-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Transferred project to UNIDO. As it was part of a line-of-grant approval, funding for this item was reallocated to finance other line-of-grant activities in accordance with the ExCom approval. |  |  | 1994-06-01 | INV | 0
CLO | IBRD | Phase out of CFC use in flexible foam at International Foam Industries Co. Ltd. | Individual | ASP | JOR | FOA | 07 | INV | 06 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1994-06-01 |  |  | 1994-01-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Closed. Company moved to the Sudan. |  |  | 1994-06-01 | INV | 0
FIN | IBRD | Phase out of CFC use in flexible foam at Kolaghassi Foam and Mattress Factory Co. | Individual | ASP | JOR | FOA | 07 | INV | 08 | N | I | CFC | 40 | 40 | 0 | 0 | 1992-06-01 | 1996-07-01 | 1994-06-01 |  | 1997-12-01 | 1998-05-01 | 172800 | -3904.84 | 168895.16 | 168895.16 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. This project is part of the line-of-grant project and was covered by part of the $1.5 million total approved. $1,496,095 disbursed for the line-of-grant - balance returned to the 36th ExCom. |  |  | 1997-06-01 | INV | 0
FIN | IBRD | Technology transfer and engineering support | Individual | ASP | JOR | FOA | 07 | TAS | 07 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1995-01-01 | 1994-06-01 |  | 1996-06-01 | 1998-05-01 | 73000 | 0 | 73000 | 73000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed for Phase-1 ODS projects. It is part of a line-of-grant approval. The project was carried out as part of IS project. To avoid double counting, disbursement was claimed under the IS project approved at the 7th Meeting. |  |  | 1994-06-01 | Non-INV | 0
FIN | IBRD | Umbrella project for conversion to CFC-free technology at three flexible polyurethane foam factories at Arab Foam, Jordan Plastics, National Foam | Individual | ASP | JOR | FOA | 15 | INV | 22 | N | I | CFC | 114 | 114 | 0 | 0 | 1994-12-01 | 1998-08-01 | 1995-09-01 |  | 2002-12-01 | 2003-12-01 | 368500 | 0 | 368500 | 368500 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1999-04-01 | INV | 0
FIN | IBRD | Umbrella project for conversion to CFC-free technology at Five Star Polyurethane Foam Factory | Individual | ASP | JOR | FOA | 17 | INV | 24 | N | I | CFC | 20 | 20 | 0 | 0 | 1995-07-01 | 1997-02-01 | 1996-04-01 |  | 1998-03-01 | 1998-05-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1997-12-01 | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of extruded polysterene at Al Hussam | Individual | ASP | JOR | FOA | 22 | INV | 31 | N | I | CFC | 50 | 50 | 0 | 0 | 1997-05-01 | 1999-12-01 | 1999-06-01 |  | 2001-02-01 | 2002-01-01 | 347855 | 0 | 347855 | 347855 | 100% | 0 | 0 |  | 45221.15 | 0 | 45221.15 | 0 | 0 | Project completed. |  |  | 1999-12-01 | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible slabstock PUF (box foam) at Baybars | Individual | ASP | JOR | FOA | 22 | INV | 32 | N | I | CFC | 30 | 30 | 0 | 0 | 1997-05-01 | 2001-12-01 | 1998-11-01 |  | 2002-12-01 | 2003-12-01 | 112500 | 0 | 112500 | 112500 | 100% | 0 | 0 |  | 14625 | 0 | 14625 | 0 | 0 | Project completed. |  |  | 1999-12-01 | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (miscellaneous applications) at Fathei Abu Arja | Individual | ASP | JOR | FOA | 23 | INV | 37 | N | I | CFC | 105.4 | 105.4 | 0 | 0 | 1997-11-01 | 1999-12-01 | 2000-12-01 |  | 1999-12-01 | 2004-08-01 | 824869 | -7968 | 816901 | 816901 | 100% | 0 | 0 |  | 107233 | -1035.84 | 106197.13 | 0.03 | 0.03 | FAA project is technically and financially completed. There is no more ODS used in production. Baseline equipment modified so as to fit the new alternative of 141-b. |  |  |  | INV | 0
FIN | IBRD | Project preparation in the foam general sector |  | ASP | JOR | FOA | 30 | PRP | 60 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 |  |  |  |  | Non-INV | 0
ONG | UNIDO | Preparation for HCFC phase-out investment activities (stage II) (rigid polyurethane foam sector) | Individual | ASP | JOR | FOA | 75 | PRP | 94 | A | I |  | 0 | 0 |  |  | 2015-11-01 | 2016-03-01 | 2017-12-01 | 2017-06-01 |  |  | 55000 | 0 | 55000 | 29194.43 | 53.08% | 25805.57 | 6103.64 | 25800 | 3850 | 0 | 0 | 3850 | 427.2548 | - Project is completed. - HPMP Stage II first tranche approved at 77th ExCom. | - Activities to ensure a fast implementation of the project were completed in early 2017, including the launching ceremony and the signature of the project document. |  |  | NON-INV
FIN | IBRD | Preparation for HCFC phase-out investment activities (stage II) (foam sector) |  | ASP | JOR | FOA | 75 | PRP | 96 | A | I |  | 0 | 0 | 0 | 0 | 2015-11-01 | 2016-12-01 | 2017-12-31 |  | 2016-12-01 | 2016-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 3150 | 0 | 3150 | 0 | 0 | Consultant TOR prepared in early 2016. WB mission conducted in Feb 16 where site visits to larger foam companies conducted (except spray foam). Consultant selected and began data collection and site visits in Apr 15. Data collection workshops held in May 16, followed by another WB preparation mission. Foam sector plan prepared and submitted within the Stage II HPMP and approved in Dec. 16. | Preparation funding fully disbursed. |  |  | Non-INV | 0
FIN | UNIDO | Preparation of a demonstration project in the methyl bromide sector | Individual | ASP | JOR | FUM | 23 | PRP | 36 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-01-01 | 1998-03-01 |  | 1998-03-01 | 2001-07-01 | 10000 | 13050 | 23050 | 23050 | 100% | 0 | 0 |  | 1300 | 1692 | 2992 | 0 | 0 | FIN
FIN | UNIDO | Three alternatives to the use of methyl bromide: steam pasteurization, non-soil cultivation and optimal use of soil fumigants in combination with an integrated pest management | Individual | ASP | JOR | FUM | 25 | DEM | 40 | A | I |  | 0 | 0 |  |  | 1998-07-01 | 1998-10-01 | 2000-08-01 |  | 2001-12-01 | 2003-08-01 | 385000 | -64217 | 320783 | 320783.16 | 100% | -0.16 | 0 |  | 50050 | -8414 | 41636 | 0 | 0 | FIN
FIN | Germany | Comprehensive approach to disseminate soil solarization technology for methyl bromide substitution | Individual | ASP | JOR | FUM | 26 | DEM | 41 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-06-01 | 1999-12-01 |  | 2000-08-01 | 2002-01-01 | 232789 | 0 | 232789 | 232789 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completion report submitted
ONG | Germany | Complete phase-out of the use of methyl bromide in Jordan | Individual | ASP | JOR | FUM | 29 | INV | 54 | A | I | MBR | 180 | 164 | 0 |  | 1999-11-01 | 2000-03-01 | 2014-12-01 | 2017-06-01 |  |  | 3063000 | 0 | 3063000 | 3062366 | 99.98% | 634 | 0 | 634 | 398190 | 0 | 398108 | 82 |  | all project activities implemented but financing agreement still not completed | Monitoring to sustain phase-out, completion of financing agreement ongoing |  |  |  |  | 12 months delays
FIN | IBRD | Halon management programme, halon recovery, recycling and banking | Halon Banking | ASP | JOR | HAL | 29 | TAS | 53 | N | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2002-12-01 | 2003-12-01 |  | 2007-12-01 | 2008-01-01 | 382250 | 0 | 382250 | 382250 | 100% | 0 | 0 |  | 49693 | 0 | 49693 | 0 | 0 | The halon recycling center has been completed and is operational. Consistent with ExCom policies, no newly produced halons will be allowed to be imported. The ban will be enforced thru the existing import lincensing system. |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation in the halon non-recycling |  | ASP | JOR | HAL | 30 | PRP | 61 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Terminal halon-1211 and halon-1301 phaseout umbrella project for fire equipment manufacturers and suppliers in Jordan converting to ABC powder, CO2, HFC-227ea and inert gases as substitutes | Individual | ASP | JOR | HAL | 32 | INV | 69 | N | I | HAL | 421.8 | 421.8 | 0 | 0 | 2000-12-01 | 2002-12-01 | 2004-03-01 |  | 2008-01-01 | 2008-12-01 | 563000 | 0 | 563000 | 563000 | 100% | 0 | 0 |  | 71930 | 0 | 71930 | 0 | 0 | Project completed. PCR under preparation. |  |  | 2003-06-01 | INV | 0
FIN | IBRD | National ODS phase out plan: aerosol, foam, MAC service and solvent sectors | One off phaseout | ASP | JOR | PHA | 38 | INV | 77 | N | I |  | 157.4 | 157.4 | 0 | 0 | 2002-11-01 | 2005-11-01 | 2009-11-01 |  | 2009-11-01 | 2009-12-01 | 590000 | 0 | 590000 | 590000 | 100% | 0 | 0 |  | 74900 | 0 | 74900 | 0 | 0 | All investment work has been undertaken. Last public awareness event held in 2009 on the achievements of the NOPP and future challenges. Training was also conducted for the solvents sector. PCR is under preparation. |  |  |  | INV | 0
FIN | UNIDO | National ODS phase out plan: commercial manufacturing and servicing and transport refrigeration | One-off Phase Out | ASP | JOR | PHA | 38 | INV | 78 | A | I | CFC | 41 | 41 |  |  | 2002-11-01 | 2003-06-01 | 2009-12-01 |  | 2006-12-01 | 2007-12-01 | 410000 | -2466 | 407534 | 407534.13 | 100% | -0.13 | 0 |  | 53300 | -321 | 52979 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | ASP | JOR | PHA | 55 | PRP | 82 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-09-01 | 2009-07-31 |  | 2011-12-01 | 2012-05-01 | 150000 | -975 | 149025 | 149025.08 | 100% | -0.08 | 0 |  | 11250 | -73 | 11177 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | IBRD | HCFC phase-out management plan (stage I, first tranche) (air-conditioning sector plan) | Multiyear | ASP | JOR | PHA | 65 | INV | 91 | N | I | HCFC | 7.8 | 7.8 | 0 | 0 | 2011-11-01 | 2014-04-01 | 2013-11-30 | 2017-11-01 |  |  | 1070100 | -89800 | 980300 | 631319 | 64.4% | 348981 | 348981 | 348981 | 80258 | -6735 | 10320.06 | 63202.94 | 63202.94 | 60% of subproject grants disbursed to two AC sector beneficiaries, National Refrigeration Company (NRC) and Abu Haltam. Both completed new equipment installation and testing, and trials by mid 2016. Prototype development completed and subprojects physically completed by end 2016. Companies have ceased R-22 use. Minister of MoE approved the ban of R-22 use in AC manufacturing and imports in mid-2016 and it became effective by end 2016. Drafting workshops and new vocational training guide completed for the servicing demo. TORs for trainers done and bid documentation for servicing equipment and tools prepared. | Subproject beneficiaries are operating normally with HCFC alternative and collecting receipts and invoices for IOC payment, expected before end-Jun 2017 and after PCRs are completed. AC sector study tour to Thailand completed in Mar. 17. Manual for AC technicians on maintenance completed. 12 trainers hired to work with Ministry of Education and NOU on vocational training materials under the servicing demo. Equipment and tools procurement underway. |  |  | INV | 0
COM | UNIDO | HCFC phase-out management plan (stage I, first tranche) (policy support, awareness promotion, monitoring) | Multi-Year | ASP | JOR | PHA | 65 | TAS | 90 | A | I |  | 0 | 0 |  |  | 2011-11-01 | 2012-04-01 | 2013-11-30 |  | 2015-12-01 |  | 70000 | 0 | 70000 | 70169.52 | 100.2% | -169.52 | 0 |  | 6300 | 0 | 6315 | -15 | 0 | The project was operationally completed. |  |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) (policy and monitoring) | Multi-Year | ASP | JOR | PHA | 75 | INV | 97 | A | I |  | 0 | 0 |  |  | 2015-11-01 | 2016-04-01 | 2017-12-01 | 2017-12-01 |  |  | 22184 | 0 | 22184 | 11419.85 | 51.48% | 10764.15 | 0 | 10764 | 1997 | 0 | 0 | 1997 | 0 | We continue to assist the government in policy support and monitoring. Ongoing/planned activities: Final workshop in Petra Co, verification report and coordination with the cooperating agency. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Meeting in Vienna took place to discuss on last monitoring activities, to be completed before the end of the year. Ongoing/planned activities: Final workshop in Petra Co, verification report and coordination with the cooperating agency. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
ONG | IBRD | Preparation of a HCFC phase-out management plan (stage II) |  | ASP | JOR | PHA | 75 | PRP | 95 | A | I |  | 0 | 0 | 0 | 0 | 2015-11-01 | 2016-12-01 | 2017-12-31 | 2017-12-31 |  |  | 70000 | 0 | 70000 | 30927.79 | 44.18% | 39072.21 | 39072.21 | 39072.21 | 4900 | 0 | 2164.94 | 2735.06 | 2735.06 | Stage II HPMP TOR prepared in early 2016. WB mission conducted in Feb 16 to discuss initial preparation arrangements and lessons learned from Stage I HPMP implementation. Consultations undertaken with industry in workshops through Stage II HPMP launch workshops in May 16, followed by another WB preparation mission. Stage II HPMP with sector plans in foam and refrigeration submitted to and approved at the 77th ExCom in Dec 16. | WB preparation activities underway to incorporate the additional financing into the existing Grant Agreement between Jordan and the WB, with a mission held in Feb 17. This includes finalizing implementation and disbursement modalities for SMEs. Commitments from 2016 to be paid by early 2017. |  |  | Non-INV | 0
ONG | UNIDO | HCFC phase-out management plan (stage II, first tranche) (polyurethane spray foam sector) | Multi-Year | ASP | JOR | PHA | 77 | INV | 100 | A | I | HCFC | 3.5 | 0 |  |  | 2016-11-01 |  | 2019-12-31 | 2019-12-31 |  |  | 164485 | 0 | 164485 | 0 | 0% | 164485 | 0 | 30000 | 11514 | 0 | 0 | 11514 | 0 | Approved in accordance with the Agreement between the Government and the Executive Committee for the period 2017 to 2022, to reduce HCFC consumption by 50 per cent of its baseline. Noted the commitment of the Government to reduce its HCFC consumption by 35 per cent of its baseline by 2020 and by 50 per cent of its baseline by 2022; that the Government would phase out HCFC-141b in bulk and contained in imported pre-blended polyols by 1 January 2022; that the Government would have flexibility in using the funds approved for the polyurethane foam sector to achieve a smooth and efficient HCFC 141b phase-out in line with the Agreement between it and the Executive Committee. The Government, the World Bank and UNIDO were requested to deduct 44.79 ODP tonnes of HCFCs from the remaining HCFC consumption eligible for funding. | - UNIDO and NOU discussed the plan of action for the implementation of the sector plan. - UNIDO and NOU are undergoing a detailed assessment of the sector to identify the baseline technology and needs for support to beneficiaries. - It was agreed to prepare a seminar for local beneficiaries on alternative technologies in September-October 2017. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No
ONG | UNIDO | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | Multi-Year | ASP | JOR | PHA | 77 | INV | 101 | A | I | HCFC | 2.8 | 0 |  |  | 2016-11-01 |  | 2019-12-31 | 2019-12-31 |  |  | 227686 | 0 | 227686 | 0 | 0% | 227686 | 0 | 15000 | 15938 | 0 | 0 | 15938 | 0 | Approved in accordance with the Agreement between the Government and the Executive Committee for the period 2017 to 2022, to reduce HCFC consumption by 50 per cent of its baseline. Noted the commitment of the Government to reduce its HCFC consumption by 35 per cent of its baseline by 2020 and by 50 per cent of its baseline by 2022; that the Government would phase out HCFC-141b in bulk and contained in imported pre-blended polyols by 1 January 2022; that the Government would have flexibility in using the funds approved for the polyurethane foam sector to achieve a smooth and efficient HCFC 141b phase-out in line with the Agreement between it and the Executive Committee. The Government, the World Bank and UNIDO were requested to deduct 44.79 ODP tonnes of HCFCs from the remaining HCFC consumption eligible for funding. | - UNIDO and NOU met and discussed on business plan for the component, which includes overall project monitoring activities. Actions towards next goal: hire the Project coordinator and establish the overall coordination unit, in consultation with lead agency. Provide assessment on the servicing needs and identify the list of tentative tools/equipment to purchase. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No
ONG | IBRD | HCFC phase-out management plan (stage II, first tranche) (polyurethane foam sector) | Multiyear | ASP | JOR | PHA | 77 | INV | 99 | N | I | HCFC | 10 | 0 | 0 | 0 | 2016-12-01 |  | 2018-12-31 | 2018-12-31 |  |  | 526956 | 0 | 526956 | 0 | 0% | 526956 | 526956 | 20000 | 36887 | 0 | 0 | 36887 | 36887 | Stage II project newly approved in Dec. 16. | A WB mission traveled to Jordan Feb. 17 to initiate amendment/additional financing procedures for the Grant Agreement between Jordan and the WB. Implementation and disbursement modalities discussed for SMEs and procedures will be captured in a revised project implementation manual. Expected date of effectiveness of additional funds is mid-2017. |  |  | INV | 0
CLO | IBRD | Recovery and recycling of CFC-12 in refrigeration equipment and maintenance procedures and recycling in halon systems | Individual | ASP | JOR | REF | 07 | DEM | 10 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1996-06-01 |  |  | 1994-01-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Cancelled. UNIDO took over. As it was part of a line-of-grant approval, funding for this item was reallocated to finance other line-of-grant activities in accordance with the ExCom approval. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects in air conditioning, commercial and domestic refrigeration (1992) |  | ASP | JOR | REF | 07 | PRP | 09 | A | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1992-06-30 | 1996-06-01 |  | 1992-12-01 | 1992-12-01 | 500000 | -445139 | 54861 | 54861 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNIDO | Preparation of investment project for phase out of ODS in selected industries in the refrigeration and air-conditioning sector | Individual | ASP | JOR | REF | 10 | PRP | 16 | A | I |  | 0 | 0 |  |  | 1993-06-01 | 1993-10-01 | 1993-10-01 |  | 1994-12-01 | 1998-08-01 | 90000 | -14930 | 75070 | 75070 | 100% | 0 | 0 |  | 11700 | -1956 | 9744 | 0 | 0 | FIN
FIN | UNIDO | ODS phase out at National Refrigeration Co. (NRC) | Individual | ASP | JOR | REF | 13 | INV | 18 | A | I | CFC | 14.3 | 19.3 |  |  | 1994-07-01 | 1997-04-01 | 1996-01-01 |  | 1998-12-01 | 2001-07-01 | 813887 | -29 | 813858 | 813857.62 | 100% | 0.38 | 0 |  | 105805 | -171 | 105634 | 0 | 0 | FIN
FIN | UNIDO | ODS phase out at Household Appliance Manufacturing Co. (HAMCO) | Individual | ASP | JOR | REF | 13 | INV | 19 | A | I | CFC | 21.2 | 21.2 |  |  | 1994-07-01 | 1997-04-01 | 1996-01-01 |  | 1998-12-01 | 2001-12-01 | 775602 | 0 | 775602 | 775602.11 | 100% | -0.11 | 0 |  | 100828 | -19 | 100809 | 0 | 0 | FIN
FIN | UNIDO | ODS phase out at Middle East Electrical Industries Co. Ltd. | Individual | ASP | JOR | REF | 13 | INV | 20 | A | I | CFC | 16.6 | 23 |  |  | 1994-07-01 | 1994-12-01 | 1996-01-01 |  | 1998-12-01 | 2001-12-01 | 883153 | -51 | 883102 | 883102.34 | 100% | -0.34 | 0 |  | 114810 | -189 | 114621 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC at Abdin Industrial Est.Co. | Individual | ASP | JOR | REF | 20 | INV | 29 | A | I | CFC | 10.4 | 21.5 |  |  | 1996-10-01 | 1997-09-01 | 1998-04-01 |  | 1997-12-01 | 2000-07-01 | 116928 | -636 | 116292 | 116292 | 100% | 0 | 0 |  | 15201 | -107 | 15094 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at the Ihsan & Tahseen Baalbaki Co. | Individual | ASP | JOR | REF | 23 | INV | 35 | A | I | CFC | 66.5 | 66.5 |  |  | 1997-11-01 | 1998-06-01 | 1999-12-01 |  | 1999-06-01 | 2001-12-01 | 545103 | -5327 | 539776 | 539776.26 | 100% | -0.26 | 0 |  | 70863 | -803 | 70060 | 0 | 0 | FIN
FIN | UNIDO | Preparation of refrigerant management plan | Individual | ASP | JOR | REF | 24 | PRP | 39 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-07-01 | 1999-04-01 |  | 1999-05-01 | 2000-12-01 | 30000 | -3410 | 26590 | 26590 | 100% | 0 | 0 |  | 3900 | -449 | 3451 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-11 foam blowing agent with HCFC-141b and CFC-12 refrigerant with HCFC-134a in manufacture of commercial refrigeration equipment at six Jordanian companies | Individual | ASP | JOR | REF | 26 | INV | 42 | A | I | CFC | 25.1 | 25.1 |  |  | 1998-11-01 | 1999-04-01 | 2000-12-01 |  | 1999-12-01 | 2002-09-01 | 305764 | -4822 | 300942 | 300941.61 | 100% | 0.39 | 0 |  | 39749 | -689 | 39060 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-11 foam blowing agent with HCFC-141b and CFC-12 refrigerant with HFC-134a in manufacture of commercial refrigeration equipment at Maurice al-Deek Co. | Individual | ASP | JOR | REF | 26 | INV | 43 | A | I | CFC | 25.7 | 25.7 |  |  | 1998-11-01 | 1999-03-01 | 2000-12-01 |  | 1999-12-01 | 2001-07-01 | 336233 | -7042 | 329191 | 329191.08 | 100% | -0.08 | 0 |  | 43710 | -983 | 42727 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in the commercial refrigeration sector | Individual | ASP | JOR | REF | 27 | PRP | 45 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-05-01 | 1999-12-01 |  | 1999-12-01 | 2001-03-01 | 5000 | -693 | 4307 | 4307 | 100% | 0 | 0 |  | 650 | -91 | 559 | 0 | 0 | FIN
FIN | France | Technical assistance in air-conditioning |  | ASP | JOR | REF | 27 | TAS | 46 | A | I |  | 0 |  | 0 |  | 1999-03-01 | 2000-03-01 | 2000-04-01 |  | 2002-06-01 | 2002-06-01 | 42000 | -31575 | 10425 | 10425 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed. Le rapport d'enquête a été achevé. D'un commun accord avec le Gouvernement jordanien, le projet sera transféré à la Banque Mondiale. |  |  | 2001-11-01
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b and CFC-12 to HFC-134a in manufacture of commercial refrigeration equipment at the Third Group of Jordanian Commercial Refrigerator Manufacturers | Individual | ASP | JOR | REF | 28 | INV | 52 | A | I | CFC | 16.8 | 17.74 |  |  | 1999-07-01 | 2000-01-01 | 2001-08-01 |  | 2001-12-01 | 2002-12-01 | 243764 | -79664 | 164100 | 164100.37 | 100% | -0.37 | 0 |  | 31689 | -10390 | 21299 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b and CFC-12 to HFC-134a in manufacture of commercial refrigeration equipment at the Second Group of Jordanian Commercial Refrigerator Manufacturers | Individual | ASP | JOR | REF | 28 | INV | 62 | A | I | CFC | 25.8 | 25.8 |  |  | 1999-07-01 | 1999-10-01 | 2001-08-01 |  | 2000-08-01 | 2002-09-01 | 278950 | -2424 | 276526 | 276526.2 | 100% | -0.2 | 0 |  | 36264 | -373 | 35891 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: technical assistance and support to develop regulations for ODS to implement the Environment law of 1999 | RMP | ASP | JOR | REF | 28 | TAS | 49 | A | I |  | 0 | 0 |  |  | 1999-07-01 | 2000-05-01 | 2001-08-01 |  | 2001-03-01 | 2002-07-01 | 20000 | -2979 | 17021 | 17020.85 | 100% | 0.15 | 0 |  | 2600 | -391 | 2209 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Refrigerant management plan: national recovery and recycling project | RMP | ASP | JOR | REF | 28 | TAS | 50 | A | I | CFC | 19.1 | 19.1 |  |  | 1999-07-01 | 2001-09-01 | 2001-08-01 |  | 2004-06-01 | 2005-09-01 | 311950 | -2650 | 309300 | 309299.95 | 100% | 0.05 | 0 |  | 40554 | -409 | 40145 | 0 | 0 | FIN |  |  | 2002-12-01
FIN | UNIDO | Refrigerant management plan: phase I: training of trainers in good refrigerant management practices; phase II: national technicians training | RMP | ASP | JOR | REF | 28 | TRA | 47 | A | I | CFC | 0 | 0 |  |  | 1999-07-01 | 2000-07-01 | 2001-08-01 |  | 2002-10-01 | 2004-03-01 | 70000 | -654 | 69346 | 69345.66 | 100% | 0.34 | 0 |  | 9100 | -99 | 9001 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: customs training | RMP | ASP | JOR | REF | 28 | TRA | 48 | A | I | CFC | 0 | 0 |  |  | 1999-07-01 | 2000-12-01 | 2001-08-01 |  | 2002-07-01 | 2003-06-01 | 38250 | -187 | 38063 | 38062.56 | 100% | 0.44 | 0 |  | 4973 | -33 | 4940 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b and CFC-12 to HFC-134a in manufacture of commercial refrigertion equipment at Al-Arghawin & Marka commercial refrigerator manufacturers | Individual | ASP | JOR | REF | 29 | INV | 55 | A | I | CFC | 27.4 | 27.4 |  |  | 1999-11-01 | 2000-05-01 | 2001-12-01 |  | 2001-12-01 | 2003-02-01 | 255203 | -9070 | 246133 | 246133.04 | 100% | -0.04 | 0 |  | 33176 | -1229 | 31947 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in the commercial refrigeration sector | Individual | ASP | JOR | REF | 30 | PRP | 57 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2001-04-01 | 2001-04-01 |  | 2002-12-01 | 2003-08-01 | 20000 | -1759 | 18241 | 18241.11 | 100% | -0.11 | 0 |  | 2600 | -232 | 2368 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-11 and CFC-12 with HCFC-141b and HFC-134a in production commercial refrigeration equipment at the medium size commercial refrigerator manufacturers (Jordan Catering Supplies, El-Shami, and Nedal Raja Al-Dwaik companies) in Jordan | Individual | ASP | JOR | REF | 31 | INV | 65 | A | I | CFC | 34.72 | 34.72 |  |  | 2000-07-01 | 2000-10-01 | 2003-08-01 |  | 2002-12-01 | 2004-09-01 | 469525 | -33258 | 436267 | 436266.87 | 100% | 0.13 | 0 |  | 61038 | -4413 | 56625 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b and CFC-12 to HFC-134a in manufacture of commercial refrigeration equipment at Fourth Group of small size Jordanian Commercial refrigerator manufacturers | Individual | ASP | JOR | REF | 31 | INV | 66 | A | I | CFC | 23.1 | 23.07 |  |  | 2000-07-01 | 2001-01-01 | 2003-01-01 |  | 2002-12-01 | 2004-09-01 | 270034 | -18831 | 251203 | 251203.16 | 100% | -0.16 | 0 |  | 35104 | -2499 | 32605 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the commercial refrigeration (umbrella project) sector | Individual | ASP | JOR | REF | 33 | PRP | 70 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-07-01 | 2002-04-01 |  | 2002-07-01 | 2003-09-01 | 20000 | -477 | 19523 | 19523.09 | 100% | -0.09 | 0 |  | 2600 | -66 | 2534 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phasing out of CFC-11 and CFC-12 with HCFC-141b and HFC-134a in the production of commercial refrigeration equipment at the second medium-size commercial refrigerator manufacturers group (Abu Azmi, Hasouni Refrigeration and Majdi) | Individual | ASP | JOR | REF | 34 | INV | 71 | A | I | CFC | 26.4 | 26.4 |  |  | 2001-07-01 | 2001-12-01 | 2004-08-01 |  | 2004-07-01 | 2005-09-01 | 342652 | -5429 | 337223 | 337222.65 | 100% | 0.35 | 0 |  | 44545 | -776 | 43769 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b and CFC-12 to HFC-134a in manufacture of commercial refrigeration equipment at 6th group of SMEs (Abu-Khalaf, Al-Taghwa, Farough Refrigeration, Dawudiah Workshop, Makka Refrigeration and Teck-Tack workshop) | Individual | ASP | JOR | REF | 34 | INV | 72 | A | I | CFC | 24.4 | 24.4 |  |  | 2001-07-01 | 2001-12-01 | 2003-08-01 |  | 2004-07-01 | 2005-09-01 | 286523 | -5667 | 280856 | 280856.08 | 100% | -0.08 | 0 |  | 37248 | -795 | 36453 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b and CFC-12 to HFC-134a in manufacturing commercial refrigeration equipment at 5th group of SMEs (Abdoulah Factory, Emad Addin Al- Sareegy, Ma-nna, Al-Mansour, Al-Ostath, Raed) | Individual | ASP | JOR | REF | 34 | INV | 74 | A | I | CFC | 26 | 26 |  |  | 2001-07-01 | 2001-12-01 | 2003-08-01 |  | 2004-07-01 | 2005-09-01 | 244954 | -5781 | 239173 | 239173.25 | 100% | -0.25 | 0 |  | 31844 | -801 | 31043 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a demonstration project for the conversion of HCFC to non-HCFC technology in the manufacturing of mini-split units at Petra Engineering | Individual | ASP | JOR | REF | 56 | PRP | 83 | A | I |  | 0 | 0 |  |  | 2008-11-01 | 2009-04-01 | 2009-11-30 |  | 2010-12-01 | 2011-07-01 | 40000 | -327 | 39673 | 39672.83 | 100% | 0.17 | 0 |  | 3000 | -25 | 2975 | 0 | 0 | FIN |  |  |  | NON-INV
COM | UNIDO | Phase-out of HCFC-22 and HCFC-141b from the manufacture of unitary air-conditioning equipment at Petra Engineering Industries Co. | Multi-Year | ASP | JOR | REF | 60 | INV | 86 | A | I | HCFC | 8.1 | 8.1 |  |  | 2010-04-01 | 2010-12-01 | 2011-10-31 |  | 2015-12-01 | 2016-05-01 | 2167033 | 126500 | 2293533 | 2291670.35 | 99.92% | 1862.65 | 0 | 1 | 162527 | 9488 | 171875 | 140 | 0 | The project was operationally completed.
FIN | IBRD | Preparation of a HCFC refrigeration sector plan (commercial refrigeration sector) |  | ASP | JOR | REF | 60 | PRP | 85 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2011-09-01 | 2011-04-30 |  | 2011-07-01 | 2011-09-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 2250 | 0 | 2250 | 0 | 0 | Project preparation of the commercial ref. sector plan continued into Jul 11, including survey, site visits and a stakeholders workshop (in Jun 11) but was suspended after the Jordan HPMP was considered by ExCom at its 64th Meeting and Jordan was discouraged to include phaseout exceeding 25% of its baseline for the Stage I HPMP. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of a HCFC refrigeration sector plan (additional funding for the commercial refrigeration subsector) |  | ASP | JOR | REF | 61 | PRP | 87 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-08-01 | 2011-07-31 |  | 2011-07-01 | 2011-08-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 2250 | 0 | 2250 | 0 | 0 | Project preparation of the commercial ref. sector plan continued into Jul 11, including survey, site visits and a stakeholders workshop (in Jun 11) but was suspended after the Jordan HPMP was considered by ExCom at its 64th Meeting and Jordan was discouraged to include phaseout exceeding 25% of its baseline for the Stage I HPMP. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation for HCFC phase-out investment activities (refrigeration air-conditioning sector) |  | ASP | JOR | REF | 63 | PRP | 89 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-11-01 | 2012-03-31 |  | 2011-08-01 | 2011-11-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 2250 | 0 | 2250 | 0 | 0 | HCFC air-conditioning sector plan prepared and submitted to the 64th and 65th ExCom Meetings. Sector plan approved in Nov 11. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1991) |  | ASP | JOR | SEV | 04 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 24464 | -21052 | 3412 | 3412 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Country programme preparation |  | ASP | JOR | SEV | 04 | PRP | 34 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 25079 | 47196 | 72275 | 72275 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Country programme preparation | Individual | ASP | JOR | SEV | 06 | CPG | 03 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 70000 | -17005 | 52995 | 52995 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Policy and monitoring measures | Individual | ASP | JOR | SEV | 07 | INS | 11 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1994-06-01 | 1995-12-01 |  | 1997-06-01 | 1997-06-01 | 100000 | 70000 | 170000 | 170000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | PIU fully operational. Total funding of $170,000 was disbursed. |  |  | 1997-06-01 | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1993) |  | ASP | JOR | SEV | 09 | PRP | 15 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 123200 | -38647 | 84553 | 84553 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Supervision of project implementation (1994) |  | ASP | JOR | SEV | 12 | PRP | 17 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 72900 | 6579 | 79479 | 79479 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNIDO | Preparatory assistance for investment projects in commercial refrigeration, air-conditioning, foam and halon sectors | Individual | ASP | JOR | SEV | 15 | PRP | 21 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-02-01 | 1995-06-01 |  | 2000-06-01 | 2001-07-01 | 50000 | -827 | 49173 | 49173 | 100% | 0 | 0 |  | 6500 | -118 | 6382 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | ASP | JOR | SEV | 16 | PRP | 23 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 64680 | 0 | 64680 | 64680 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation |  | ASP | JOR | SEV | 18 | PRP | 25 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 | Project preparation is completed. |  |  |  | Non-INV | 0
FIN | IBRD | Renewal of institutional strengthening | Individual | ASP | JOR | SEV | 22 | INS | 30 | N | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-06-01 | 1999-05-01 |  | 1999-05-01 | 1999-06-01 | 113333 | 0 | 113333 | 113333 | 100% | 0 | 0 |  | 14733 | 0 | 14733 | 0 | 0 | PIU fully operational. Funds were fully disbursed. |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation to phase out CFC consumption that is not accounted for in the original country programme |  | ASP | JOR | SEV | 22 | PRP | 33 | A | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-12-31 | 1997-12-01 |  | 1999-06-01 | 1999-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | Completed |  |  | 1999-06-01 | Non-INV | 0
FIN | IBRD | Project preparation in the foam and halon recycling sectors |  | ASP | JOR | SEV | 24 | PRP | 38 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1999-03-31 | 1998-12-01 |  | 1999-12-01 | 1999-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | Completed |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of project in the aerosol and halon recycling sectors |  | ASP | JOR | SEV | 27 | PRP | 44 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-31 | 2000-01-01 |  | 1999-12-01 | 1999-12-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 |  | 650 | 0 | 650 | 0 | 0 | Completed |  |  |  | Non-INV | 0
FIN | IBRD | Renewal of institutional strengthening (phase II) |  | ASP | JOR | SEV | 28 | INS | 51 | N | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 1999-08-01 | 1999-08-01 |  | 2001-07-01 | 2001-07-01 | 113333 | 0 | 113333 | 113333 | 100% | 0 | 0 |  | 14733 | 0 | 14733 | 0 | 0 | IS tranche completed and full funding dibursed. |  |  | 2000-12-01 | Non-INV | 0
FIN | IBRD | Country programme update | Individual | ASP | JOR | SEV | 31 | CPG | 67 | A | I |  | 0 | 0 | 0 | 0 | 2000-07-01 | 2002-09-01 | 2001-04-01 |  | 2002-09-01 | 2002-09-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0 | CP update submitted to the 38th ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | Renewal of the institutional strengthening project |  | ASP | JOR | SEV | 34 | INS | 73 | N | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-12-01 | 2003-08-01 |  | 2004-12-01 | 2004-12-01 | 133333 | -20000 | 113333 | 113333 | 100% | 0 | 0 |  | 17333.29 | -2600 | 14733.29 | 0 | 0 | Final activities of this IS tranche completed. NOU supervised ongoing projects, organized Ozone Day and conducted public awareness. |  |  |  | Non-INV | 0
FIN | IBRD | Extension of institutional strengthening project | Individual | ASP | JOR | SEV | 40 | INS | 79 | N | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2005-06-01 | 2005-07-01 |  | 2005-06-01 | 2005-06-01 | 147333 | 0 | 147333 | 147333 | 100% | 0 | 0 |  | 11050 | 0 | 11050 | 0 | 0 | Phase 6 of the IS project completed. |  |  |  | Non-INV | 0
FIN | IBRD | Renewal of institutional strengthening project (phase VI) | Individual | ASP | JOR | SEV | 46 | INS | 80 | N | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-12-01 | 2007-07-01 |  | 2007-07-01 | 2007-12-31 | 147320 | 0 | 147320 | 147320 | 100% | 0 | 0 |  | 11049 | 0 | 11049 | 0 | 0 | IS Phase VI is completed. |  |  |  | Non-INV | 0
FIN | IBRD | Extension of institutional strengthening project (phase VII) | Individual | ASP | JOR | SEV | 52 | INS | 81 | N | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-12-01 | 2009-07-01 |  | 2009-09-01 | 2010-01-01 | 147333 | 0 | 147333 | 147333 | 100% | 0 | 0 |  | 11050 | 0 | 11050 | 0 | 0 | IS Phase VII is completed. |  |  |  | Non-INV | 0
FIN | IBRD | Extension of institutional strengthening project (phase VIII) | Individual | ASP | JOR | SEV | 58 | INS | 84 | N | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2010-12-01 | 2010-12-01 |  | 2011-03-01 | 2011-03-01 | 110500 | 0 | 110500 | 110500 | 100% | 0 | 0 |  | 8288 | 0 | 8288 | 0 | 0 | IS Phase VIII completed. |  |  |  | Non-INV | 0
FIN | IBRD | Extension of institutional strengthening project (phase IX) | Individual | ASP | JOR | SEV | 62 | INS | 88 | N | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-12-01 | 2012-12-31 |  | 2012-12-01 | 2012-12-01 | 147333 | 0 | 147333 | 147333 | 100% | 0 | 0 |  | 11050 | 0 | 11050 | 0 | 0 | IS Phase IX completed. |  |  |  | Non-INV | 0
FIN | IBRD | Extension of institutional strengthening project (phase X: 1/2013-12/2014) | Individual | ASP | JOR | SEV | 68 | INS | 92 | N | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-12-01 | 2014-12-31 |  | 2014-12-01 | 2015-04-01 | 147333 | 0 | 147333 | 147333 | 100% | 0 | 0 |  | 10313 | 0 | 10313 | 0 | 0 | ISP Phase X completed. Final $19,621 disbursed in 2015. |  |  |  | Non-INV | 0
COM | IBRD | Extension of institutional strengthening project (phase XI: 1/2015-12/2016) | Individual | ASP | JOR | SEV | 73 | INS | 93 | N | I |  | 0 | 0 | 0 | 0 | 2014-11-01 | 2015-12-01 | 2016-12-31 | 25.3667 | 2016-12-01 |  | 147333 | 0 | 147333 | 139333 | 94.57% | 8000 | 8000 | 8000 | 10313 | 0 | 9753.01 | 559.99 | 559.99 | In 2016, the NOU facilitated issuance of 200 import licenses and management of HCFC quotas; provided overall oversight of the Stage I HPMP; supported preparation of the Stage II HPMP by coordinating survey consultant and organizing stakeholder/enterprise consultations; organized experts and steering committee meetings on new ODS regulation (including the ban in R-22 based imports and manufacturing of AC) and published 500 copies of new regulation; hosted UNEP workshop on insulation and building codes in Dec 16 and organized another workshop on commercial refrigeration (CO2) technology; attended the 76th-77th ExCom meetings as well as MP meetings in Geneva, Vienna and Kigali. | ISP XI completed. Financial completion expected before the first half of 2017. |  |  | Non-INV | 0
ONG | IBRD | Survey of ODS alternatives at the national level | Individual | ASP | JOR | SEV | 76 | TAS | 98 | A | I |  | 0 | 0 | 0 | 0 | 2016-05-01 |  | 2017-12-31 | 2017-12-31 |  |  | 55000 | 0 | 55000 | 0 | 0% | 55000 | 55000 | 55000 | 4950 | 0 | 0 | 4950 | 4950 | Terms of reference for overall non-ODS alternative survey prepared, as well as individual consultant TORs for the data survey. Coordination meetings held in regards to the HFC inventory funding provided to UNIDO by the CCAC. | Team Lead and two National Technical Consultants contracted in Jan. 17 to deliver the ODS alternative survey report. Inception report prepared and accepted, including survey tables that will be used. Survey period expected to be completed by end Mar 17; submission of compiled data (database) of HFCs and ODS alternatives consumed by end Apr 17 and analysis by consultants to be done and survey report submitted by end Jun 17 to WB and Jordan for completion of ODS alternative report for the ExCom. |  |  | Non-INV | 0
ONG | IBRD | Extension of institutional strengthening project (phase XII: 1/2017-12/2018) | Individual | ASP | JOR | SEV | 77 | INS | 102 | N | I |  | 0 | 0 | 0 | 0 | 2016-12-01 |  | 2018-12-31 | 2018-12-31 |  |  | 188586 | 0 | 188586 | 0 | 0% | 188586 | 188586 | 85000 | 13201 | 0 | 0 | 13201 | 13201 | Phase XII newly approved at the 77th ExCom. | In 2017, NOU facilitated issuance of instructions for controlling ODS import and export of ODS and alternatives; issued approvals for HCFC imports, compressors etc.; and, conducted field visits to HCFC-using industry. It has facilitated HFC data collection from enterprises for the HFC and ODS alternatives surveys. It will attend upcoming MP meetings and host the UNEP W.Asia Ozone Officers meeting in April 2017. |  |  | Non-INV | 0
FIN | UNIDO | Project preparation in the solvent sector (CFC-113) sector | Individual | ASP | JOR | SOL | 30 | PRP | 58 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-06-01 | 2001-04-01 |  | 2002-12-01 | 2003-06-01 | 25000 | -2455 | 22545 | 22544.58 | 100% | 0.42 | 0 |  | 3250 | -324 | 2926 | 0 | 0 | FIN
FIN | UNIDO | Conversion of metal cleaning processes from TCA solvent to TCE degreasing at the King Hussein Workshop, Zarqa | Individual | ASP | JOR | SOL | 34 | INV | 75 | A | I | TCA | 6.4 | 6.4 |  |  | 2001-07-01 | 2002-12-01 | 2003-02-01 |  | 2003-12-01 | 2004-10-01 | 191316 | 0 | 191316 | 191316.01 | 100% | -0.01 | 0 |  | 24871 | 0 | 24871 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of metal cleaning processes from TCA solvent to TCE degreasing at the Royal Jordanian Air Force | Individual | ASP | JOR | SOL | 37 | INV | 76 | A | I | TCA | 10.4 | 10.4 |  |  | 2002-07-01 | 2003-11-01 | 2004-08-01 |  | 2005-12-01 | 2007-01-01 | 342757 | -17 | 342740 | 342740.39 | 100% | -0.39 | 0 |  | 44558 | -2 | 44556 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Training and awareness workshop in the fumigants sector (methyl bromide) | Individual | ASP | KAM | FUM | 46 | TAS | 10 | A | I |  | 0 | 0 |  |  | 2005-07-01 | 2006-02-01 | 2006-07-01 |  | 2006-07-01 | 2008-09-01 | 30000 | -2430 | 27570 | 27569.64 | 100% | 0.36 | 0 |  | 2700 | -219 | 2481 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNDP | Project preparation for a terminal phase-out management plan | Individual | ASP | KAM | PHA | 50 | PRP | 12 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-04-01 | 2007-11-01 |  | 2007-09-01 | 2009-12-01 | 15000 | -9560 | 5440 | 5440 | 100% | 0 | 0 | 0 | 1125 | -717 | 408 | 0 | 0 | Completed in 2007. Financially completed in 2009. |  | 2006 |  | Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | ASP | KAM | PHA | 50 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2007-11-01 |  | 2007-09-01 | 2008-01-01 | 15000 | -11 | 14989 | 14989 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0
FIN | UNDP | Terminal phase-out management plan for the phase-out of CFCs (first tranche) | Multi-Year | ASP | KAM | PHA | 53 | INV | 16 | N | I | CFC | 3.5 | 3.5 | 0 | 0 | 2007-11-01 | 2008-02-01 | 2009-11-01 |  | 2009-12-01 | 2013-01-01 | 195000 | 0 | 195000 | 195000 | 100% | 0 | 0 | 0 | 14625 | 0 | 14625 | 0 | 0 | Financially completed in 2013. |  | 2007 |  | Investment
FIN | UNEP | Terminal phase-out management plan for the phase-out of CFCs (first tranche) | Multi-year | ASP | KAM | PHA | 53 | TAS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-03-01 |  | 2009-03-01 | 2009-12-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 | 0 |  | 15600 | 0 | 15600 | 0 | 0
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | ASP | KAM | PHA | 55 | PRP | 17 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2010-03-01 | 2009-07-01 |  | 2010-12-01 | 2012-06-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 1875 | 0 | 1875 | 0 | 0 | Financially completed in 2012. |  | 2008 |  | Investment
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | KAM | PHA | 55 | PRP | 18 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-09-01 | 2009-07-01 |  | 2010-07-01 | 2011-07-01 | 125000 | -3750 | 121250 | 121250 | 100% | 0 | 0 |  | 16250 | -487.5 | 15762.5 | 0 | 0
FIN | UNDP | Terminal phase-out management plan for the phase-out of CFCs (second tranche) | Multi-Year | ASP | KAM | PHA | 57 | INV | 20 | N | I | CFC | 10 | 10 | 0 | 0 | 2009-04-01 | 2009-05-01 | 2011-03-01 |  | 2010-12-01 | 2013-01-01 | 85000 | -1774.06 | 83225.94 | 83226 | 100% | -0.06 | 0 | 0 | 6375 | -133.05 | 6241.95 | 0 | 0 | Financially completed in 2013. |  | 2009 |  | Investment
FIN | UNEP | Terminal phase-out management plan for the phase-out of CFCs (second tranche) | Multi-Year | ASP | KAM | PHA | 57 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-07-01 | 2010-03-01 |  | 2010-03-01 | 2011-03-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNDP | HCFC phase-out management plan (phase I, first tranche) | Multi-year | ASP | KAM | PHA | 61 | INV | 24 | N | I | HCFC | 0 | 0 | 0 | 0 | 2010-07-01 | 2012-05-01 | 2019-12-01 |  | 2015-12-01 | 2016-12-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 15000 | 0 | 15000 | 0 | 0 | Financially completed in 2016. | A few awareness outreach activities have been conducted in Q1/Q2 in 2015. The project is expected to be operationally completed by late 2015. | 2010 |  | Investment
COM | UNEP | HCFC phase-out management plan (phase I, first tranche) | Multi-Year | ASP | KAM | PHA | 61 | TAS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2010-12-01 | 2019-12-01 |  | 2013-12-01 |  | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 | 0 | 19500 | 0 | 19500 | 0 | 0 | Project completed. | Project completed. There are ongoing discussions with the Government on the financial closure of the tranche. There are certain internal procedures to be followed.
ONG | UNDP | HCFC phase-out management plan (second tranche) | Multi-year | ASP | KAM | PHA | 70 | INV | 28 | N | I | HCFC | 0.6 | 0 | 0 | 0 | 2013-07-01 | 2014-05-01 | 2016-07-01 | 2017-07-01 |  |  | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 15000 | 0 | 15000 | 0 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): provision of recovery equipment to RAC workshops, reclamation machines to 2 enterprises. Workshops with stake holders for retrofitting. Prodoc signed (actual/planned, yes/no and date):LoA signed 21 March 2014 and Feb 2016 Missions undertaken (actual/planned):- TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: Contract signed First disbursement date (actual/planned): 41760Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve: Incentive Program was delay due to no alternative in place yet | Ongoing | 2013 |  | Investment
COM | UNEP | HCFC phase-out management plan (second tranche) | Multi-year | ASP | KAM | PHA | 70 | TAS | 26 | A | I |  | 0.9 |  | 0 |  | 2013-07-01 | 2014-03-01 | 2016-07-01 |  | 2016-12-01 |  | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Brief progress report (actual/planned): The licensing and quota system as well as mandatory labeling requirement was strictly implemented in 2016. In 2016, the Government organized one RAC techncian workshop in August 2016 with 32 participants. One more specific training on HC technoogy was organized in October 2016 with 24 participants. The Customs Handbook has been translated in Khmer, printed with 600 copies and distributed to the Customs and Excise General Department and other concerned institutions. The Guideline for Skill Standard and Certificate Testing for the technician has been finalized and waiting for approval. The certification requirement will be included in the draft Natural Resources and Environment Code; which was being developed by the Government. Project was completed as of December 2016. 2015 CP data was submitted online. Legal arrangements (actual/planned): The SSFA was signed in March 2014. First Mission: Feb 2014. TOR completed: Not applicable. First disbursement date: March 2014. All funds disbursed (yes/no): No, but the last payment has been processed to transfer to country. Any delay? (yes/no): No. Any ongoing problems (yes/no): No. | Project completed. The last payments as per the SSFA is being processed to transfer to the country.
COM | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Multi-Year | ASP | KAM | PHA | 73 | TAS | 29 | A | I |  | 0 |  | 0 |  | 2014-11-01 | 2016-03-01 | 2016-05-01 |  | 2016-12-01 |  | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Brief progress report (actual/planned): A local consultant was hired by UNEP in February 2016 to conduct verification from March-May 2016. The consultant reviewed the national legislation, policies and procedures on ODS import and export in Cambodia and conducted an assessment of the existing licensing and quota system to control HCFC import and export. The consultant also reviewed official statistics on import and export maintained by different sources and analyzed and compare those statistics. In addition, the consultant conducted the necessary on-site visits and interviews, and analyzed and cross-check various data collected from different sources. The consultant drafted verification report for the years of 2013-2015. The reports was produced in English and provides detailed data demonstrating and confirming whether the consumption targets in the Agreement were achieved, whether there is existence of an operational licensing and quota system for HCFC imports and exports and whether the system is capable to ensure the country's compliance with the targets as set out in the Agreement between Mongolia and the ExCom. UNEP worked closely with the consultant and NOU to finalize the verification report taking into account the observations from the National Ozone Authority. A mission was conducted in March 2016 to review the draft report. The verification report was submitted to the Multilateral Fund Secretariat in July 2016. The MLFS has accepted the verification report and the project was completed. Ministry of Environment provided full support in the verification. SSFA with the Ministry of Environment to facilitate the verification conducted by the local consultant was closed in 2016. Legal arrangements(actual/planned): The SSFA was signed in November 2015_ Initial stages of project implementation(actual/planned): Nov/Nov 2015. Intermediate goals achieved (actual/planned): Not applicable. Project completion and follow up: Not applicable. First disbursement date (actual/planned): March 2016. All funds disbursed (yes/no): No Any delay?(yes/no): No. _Yes__ If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: N/A | Project completed.
ONG | UNDP | HCFC phase-out management plan (third tranche) | Multi-Year | ASP | KAM | PHA | 76 | INV | 33 | N | I | HCFC | 0 | 0 | 0 | 0 | 2016-05-01 |  | 2019-12-01 | 2017-12-01 |  |  | 100000 | 0 | 100000 | 0 | 0% | 100000 | 0 | 40000 | 7500 | 0 | 0 | 7500 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): The verification report of HCFC has been submitted and the country is in compliance. 3rd tranche approved. Prodoc signed (actual/planned, yes/no and date): Missions undertaken (actual/planned):- TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: Contract signed First disbursement date (actual/planned): Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | Procurement will be completed by December 2017. |  |  | Investment
ONG | UNEP | HCFC phase-out management plan (third tranche) | Multi-year | ASP | KAM | PHA | 76 | TAS | 32 | A | I |  | 0 |  | 0 |  | 2016-05-01 |  | 2018-12-01 | 2019-12-01 |  |  | 150000 | 0 | 150000 | 0 | 0% | 150000 | 3921.93 | 15000 | 19500 | 0 | 0 | 19500 | 509.8509 | Brief progress report (actual/planned): The project was approved at the 76th ExCom in May 2016. UNEP worked closely with the government to draft the SSFA. The first mission was conducted in October 2016 to finalize the SSFA and implementation plan. The SSFA for the third tranche was signed by the Government and become effective on 29 December 2016. The first payment has been requested, but not yet been transferred to the government. Legal arrangements (actual/planned): The SSFA was signed in December 2016. First Mission: October 2016 TOR completed: Not applicable. First disbursement date: Not yet. All funds disbursed (yes/no): No. Any delay? (yes/no): No. Any ongoing problems (yes/no): No. | Brief progress report (actual/planned): The implementation of the third tranche will be implemented immediately after the first payment is released to the country. Through the south-south cooperation with China, Cambodia will have an extensive training on good practices for flammable refrigerant which would sustain the phase-out of HCFC-22.
FIN | UNDP | Formulation of investment components of the RMP | Individual | ASP | KAM | REF | 36 | PRP | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2003-12-01 | 2005-11-01 | 15000 | -1844 | 13156 | 13156 | 100% | 0 | 0 | 0 | 1950 | -239.72 | 1710.28 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Formulation of the investment components of the RMP | Individual | ASP | KAM | REF | 39 | PRP | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-04-01 | 2005-12-01 | 7500 | 0 | 7500 | 7500 | 100% | 0 | 0 | 0 | 562 | 0 | 562 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2003 |  | Investment
FIN | UNDP | Implementation of the RMP: recovery and recycling of CFC-12 refrigerant and awareness and incentive programme for the MAC sub-sector | RMP-Component | ASP | KAM | REF | 41 | TAS | 05 | N | I | CFC | 56.2 | 56.2 | 0 | 0 | 2003-12-01 | 2005-07-01 | 2007-12-01 |  | 2007-12-01 | 2010-06-01 | 625000 | -267.41 | 624732.59 | 624733 | 100% | -0.41 | 0 | 0 | 46875 | -20.06 | 46854.975 | -0.03495 | 0 | Financially completed in 2010. |  | 2003 |  | Investment
FIN | UNEP | Implementation of the RMP: implementation support and monitoring | Individual | ASP | KAM | REF | 41 | TAS | 08 | A | I | CFC | 4.5 | 4.5 | 0 | 0 | 2003-12-01 | 2004-03-01 | 2006-12-01 |  | 2006-12-01 | 2007-03-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Implementation of the RMP: refrigeration and air-conditioning technicians training programme | Individual | ASP | KAM | REF | 41 | TRA | 06 | A | I | CFC | 11.7 | 11.7 | 0 | 0 | 2003-12-01 | 2004-03-01 | 2005-12-01 |  | 2006-12-01 | 2007-03-01 | 130000 | -54 | 129946 | 129946 | 100% | 0 | 0 |  | 16900 | -7 | 16893 | 0 | 0
FIN | UNEP | Implementation of the RMP: customs training programme | Individual | ASP | KAM | REF | 41 | TRA | 07 | A | I | CFC | 7.6 | 7.6 | 0 | 0 | 2003-12-01 | 2004-04-01 | 2005-12-01 |  | 2005-12-01 | 2006-03-01 | 85000 | -199 | 84801 | 84801 | 100% | 0 | 0 |  | 11050 | -26 | 11024 | 0 | 0
FIN | UNEP | Formulation of national phase out strategy | Individual | ASP | KAM | SEV | 35 | TAS | 01 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2003-03-01 | 2003-08-01 |  | 2004-12-01 | 2005-01-01 | 60000 | -433 | 59567 | 59567 | 100% | 0 | 0 |  | 7800 | -56 | 7744 | 0 | 0
FIN | UNEP | Establishment of the Ozone Unit | Individual | ASP | KAM | SEV | 36 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-12-01 | 2004-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project: phase 2 | Individual | ASP | KAM | SEV | 41 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-03-01 | 2005-12-01 |  | 2006-01-01 | 2006-02-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project: phase III | Individual | ASP | KAM | SEV | 47 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-03-01 | 2007-12-01 |  | 2007-11-01 | 2007-12-01 | 112667 | 0 | 112667 | 112667 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | ASP | KAM | SEV | 53 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-02-01 | 2009-11-01 |  | 2009-10-01 | 2010-12-01 | 112667 | 0 | 112667 | 112667 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase V) | Individual | ASP | KAM | SEV | 58 | INS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2009-12-01 | 2011-11-01 |  | 2011-12-01 | 2012-12-01 | 61028 | 51639 | 112667 | 112666.58 | 100% | 0.42 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase VI:12/2011-11/2013) | Individual | ASP | KAM | SEV | 64 | INS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2011-11-01 | 2013-11-01 |  | 2013-12-01 | 2014-12-01 | 112667 | 0 | 112667 | 112667 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of institutional strengthening project (phase VII:1/2014-12/2015) | Individual | ASP | KAM | SEV | 70 | INS | 27 | A | I |  | 0 |  | 0 |  | 2013-07-01 | 2014-05-01 | 2015-12-01 |  | 2015-12-01 |  | 112667 | 0 | 112667 | 112667 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Activities completed since 2015. However, the last two payment could not be transferred to the country due to errors in the system. The problems has been fixed and the payments have been requested in the system. | Brief progress report (actual/planned): The pending last two payments are being reimbursed to the country.
ONG | UNEP | Extension of institutional strengthening project (phase VIII:1/2016-12/2017) | Individual | ASP | KAM | SEV | 74 | INS | 30 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-05-01 | 2017-12-01 | 2017-12-01 |  |  | 112667 | 0 | 112667 | 77242.96 | 68.56% | 35424.04 | 35424.04 | 3542.404 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The operation of the NOU was going on well. The license/quota system was strictly enforced, and total quota of 220 MT of HCFC-22 and 10 MT for HCFC-123 was issued to 5 companies. Of which, about 82.13 MT of HCFC-22 was imported. NOU in coordination with the Customs and Excise General Department and the Anti-economic Crime Police Department also conducted market inspection on the quarterly basis as well as random checking to enforce the labeling requirement. NOU also coordinated and facilitated the implementation of HPMP, ODS Alternative Survey and verification of HCFC consumption as well as the submission of the third tranche request to the 76th meeting of Excom. The NOU also organized the 2016 ozone day celebration, and actively joined the regional and global ozone related meetings e.g. the network meeting, OEWG and the MOP meetings. 2015 Article 7 and CP data were submitted to the Ozone Secretariat and MLFS respectively. Legal arrangements(actual/planned): The SSFA was signed in October 2015 _Initial stages of project implementation(actual/planned): Jan/Jan 2016. Intermediate goals achieved (actual/planned): Yes Project completion and follow up: Not applicable. First disbursement date (actual/planned): May 2016 All funds disbursed (yes/no): No. Any delay?(yes/no): _NO If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned):NOU continues enforcing the licensing and quota system as well as mandatoty labeling requirement for HCFC containers. In 2017, the quota of 220 MT of HCFC-22 was allocated to 6 importers. The third payment has been requested by the NOU. Project will be completed in December 2017.
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | ASP | KAM | SEV | 74 | TAS | 31 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-05-01 | 2016-05-01 | 2017-06-01 |  |  | 35000 | 0 | 35000 | 11809.63 | 33.74% | 23190.37 | 20740.14 | 2319.037 | 4550 | 0 | 1535.2519 | 3014.7481 | 2696.2182 | Brief progress report (actual/planned): The project was on track. The SSFA was signed by UNEP and the Government of Cambodia on in April 2016. A national consultant and survey teams were hired by the NOU to support the data collection. Consultants assisted the NOU in the identification of the current use of ODS alternatives by substance/sector and collection of import/export data for the substances for the past a couple of years. Consultants also provided support in establishing growth patterns in use by substance/sector and in compiling data on available ODS alternatives for various applications. The NOU and national consultants drafted and cross checked the information to ensure the completion of end-user surveys, collection, analysis, and aggregation of consumption data. The various sections of the report were drafted. 7 consultation workshops were organzied in 2016 in different locations in the country. Legal arrangements(actual/planned): April 2016 Initial stages of project implementation(actual/planned): April 2016 . Intermediate goals achieved (actual/planned): Not applicable. Project completion and follow up: Not applicable. First disbursement date (actual/planned): May 2016. All funds disbursed (yes/no): _No__ Any delay?(yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): The final consultation workshop was organized in January 2017. The draft report prepared by the NOU and national consultants incorporating comments from the stakeholders was submitted to UNEP for review and comment. The NOU and consultants have revised the draft report based on UNEP's observation to ensure that it is based on the format approved by ExCom decision 75/67 as contained in document UNEP/OzL.Pro/ExCom/75/77/Rev.1. The report is under final reviewed by UNEP and will be submitted to MLFS by March 2017.
FIN | UNIDO | Technical assistance for the total phase-out of CTC and TCA in the solvent sector | Individual | ASP | KAM | SOL | 57 | TAS | 21 | A | I | TCA | 0.3 | 0.3 |  |  | 2009-04-01 | 2010-02-01 | 2010-03-31 |  | 2010-08-01 | 2010-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 3600 | 0 | 3600 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase out CFCs at Aesthetics Ltd. | Individual | AFR | KEN | ARS | 19 | INV | 10 | A | I | CFC | 107 | 107 |  |  | 1996-05-01 | 1997-12-01 | 1997-11-01 |  | 1997-12-01 | 2002-08-01 | 55000 | 0 | 55000 | 54999.76 | 100% | 0.24 | 0 |  | 7150 | -1 | 7149 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Mirage Industries Ltd. | Individual | AFR | KEN | ARS | 19 | INV | 11 | A | I | CFC | 51 | 51 |  |  | 1996-05-01 | 1997-08-01 | 1997-11-01 |  | 1997-12-01 | 2002-08-01 | 47250 | -371 | 46879 | 46879.18 | 100% | -0.18 | 0 |  | 6143 | -58 | 6085 | 0 | 0 | FIN
CLO | Australia | Replacement of methyl bromide with non ozone depleting substances in grain storage | Individual | AFR | KEN | FUM | 21 | DEM | 12 | A | D |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-06-01 | 1997-07-01 |  |  | 2000-06-01 | 232834 | -91869 | 140965 | 140965 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Cancelled |  | 1996
FIN | UNIDO | Preparation of a demonstration project in the methyl bromide sector | Individual | AFR | KEN | FUM | 23 | PRP | 15 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1997-12-01 | 1998-03-01 |  | 1999-01-01 | 2001-07-01 | 10000 | 13050 | 23050 | 23050 | 100% | 0 | 0 |  | 1300 | 1692 | 2992 | 0 | 0 | FIN
FIN | UNIDO | Alternatives to the use of methyl bromide for soil fumigation in cut-flowers at Kenya Agricultural Research Institute - KARI | Individual | AFR | KEN | FUM | 24 | DEM | 17 | A | I | MBR | 0 | 0 |  |  | 1998-03-01 | 1998-10-01 | 2000-04-01 |  | 2003-03-01 | 2004-03-01 | 328900 | -2958 | 325942 | 325942.31 | 100% | -0.31 | 0 |  | 42757 | -452 | 42305 | 0 | 0 | FIN
FIN | Canada | Methyl bromide replacement demonstration programme | Individual | AFR | KEN | FUM | 26 | DEM | 20 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-05-01 | 1999-12-01 |  | 2007-06-01 | 2007-06-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1998 |  | Non-Inv.
CLO | UNIDO | Preparation of a phase-out project in the methyl bromide sector | Individual | AFR | KEN | FUM | 30 | PRP | 21 | A | I |  | 0 | 0 |  |  | 2000-03-01 |  | 2001-04-01 |  |  | 2002-05-01 | 30000 | -30000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 3900 | -3900 | 0 | 0 | 0 | CLO
FIN | Germany | Development of an investment project for the phase out of methyl bromide in vegetable production | Individual | AFR | KEN | FUM | 30 | PRP | 23 | A | I |  | 0 |  | 0 |  | 2000-03-01 | 2001-08-01 | 2000-12-01 |  | 2002-11-01 | 2003-09-01 | 13360 | 0 | 13360 | 13360 | 100% | 0 | 0 | 0 | 1737 | 0 | 1737 | 0 | 0 | Project initially blocked by 30th ExCom Decision on Kenya. Work completed November 2002. Investtment project approved at 39th ExCom.
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organizations in methyl bromide communication | Individual | AFR | KEN | FUM | 30 | TAS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9392 | 15608 | 15608 | 100% | 0 | 0 |  | 3250 | -1221 | 2029 | 0 | 0
FIN | UNDP | Project preparation in the soil fumigant sector (cut flowers) | Individual | AFR | KEN | FUM | 36 | PRP | 28 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2003-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2002 |  | Investment
CLO | UNDP | Technology transfer leading to methyl bromide phase-out in soil fumigation in cut flower component (first tranche) | Multi-Year | AFR | KEN | FUM | 38 | INV | 31 | A | I | MeBr | 10 | 10 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2004-11-01 |  |  | 2010-10-01 | 510660 | -6535.52 | 504124.48 | 504124 | 100% | 0.48 | 0 | 0 | 66173 | -846.89 | 65326.0437 | 0.0663 | 0 | Financially completed in 2010 and cancelled in 2007. |  | 2002 | 2005-07-01 | Investment
FIN | Germany | Technology transfer leading to methyl bromide phase-out in soil fumigation in all other horticulture (first tranche) | Multi-Year | AFR | KEN | FUM | 39 | INV | 33 | A | I | MBR | 5 | 8 | 0 |  | 2003-04-01 | 2003-07-01 | 2004-04-01 |  | 2005-04-01 | 2006-04-01 | 287247 | 0 | 287247 | 287247 | 100% | 0 | 0 | 0 | 37342 | 0 | 37342 | 0 | 0 | During 2004 the project staff was completed, a demonstration facility was set up in cooperation with the University of Nairobi, a very successful demonstration of substrates as alternative to MB was held at this facility. In sectors and areas where viable
FIN | Germany | Technology transfer leading to methyl bromide phase-out in soil fumigation in all other horticulture (second tranche) | Multi-Year | AFR | KEN | FUM | 42 | INV | 35 | A | I | MBR | 12 | 14.7 | 0 |  | 2004-04-01 | 2005-05-01 | 2006-04-01 |  | 2006-12-01 | 2011-05-01 | 172347 | 0 | 172347 | 172347 | 100% | 0 | 0 | 0 | 22405 | 0 | 22405 | 0 | 0 | Second tranche approved at 42nd ExCom. During 2005 technology transfer activities continued through agreements with farms for the adoption of alternatives such as substrates, IPM and chemicals such as metham sodium.
TRF | UNDP | Technology transfer leading to methyl bromide phase-out in soil fumigation (second tranche) | Multi-Year | AFR | KEN | FUM | 44 | INV | 38 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2006-12-01 |  |  | 2007-11-01 | 306396 | -306396 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 22980 | -22980 | 0 | 0 | 0 | Transferred in 2007. Financially Completed in 2007. |  | 2004 |  | Investment
TRF | UNDP | Technology transfer leading to methyl bromide phase-out in soil fumigation in cut flowers (third tranche) | Multi-Year | AFR | KEN | FUM | 50 | INV | 40 | A | I | MeBr | 0 | 0 | 0 | 0 | 2006-11-01 |  | 2009-12-01 |  |  | 2007-11-01 | 204263 | -204263 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 15320 | -15320 | 0 | 0 | 0 | Transferred in 2007. Financially Completed in 2007. |  | 2006 |  | Investment
FIN | Germany | Technology transfer leading to methyl bromide phase-out in soil fumigation in all other horticulture (third tranche) | Multi-Year | AFR | KEN | FUM | 50 | INV | 41 | A | I | MBR | 17 | 9.7 | 0 |  | 2006-11-01 | 2007-01-01 | 2009-12-01 |  | 2010-01-01 | 2011-05-01 | 114898 | 0 | 114898 | 114898 | 100% | 0 | 0 | 0 | 14937 | 0 | 14937 | 0 | 0 | The Project has been completed. PCR submitted in September 2010
FIN | UNIDO | Technology transfer leading to methyl bromide phase-out in soil fumigation | Multi-Year | AFR | KEN | FUM | 53 | INV | 43 | A | I | MBR | 53 | 53 |  |  | 2007-11-01 | 2008-02-01 | 2010-11-01 |  | 2009-12-01 | 2012-07-01 | 510659 | -1888 | 508771 | 508770.66 | 100% | 0.34 | 0 |  | 38300 | -142 | 38158 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project preparation for the elimination of controlled uses of methyl bromide in post-harvest sector | Individual | AFR | KEN | FUM | 60 | PRP | 50 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-12-01 | 2011-04-30 |  | 2011-12-01 | 2013-12-01 | 40000 | -184 | 39816 | 39815.8 | 100% | 0.2 | 0 |  | 3000 | -14 | 2986 | 0 | 0 | FIN
FIN | UNIDO | Technical assistance for the final elimination of methyl bromide in post harvest sector | Individual | AFR | KEN | FUM | 65 | INV | 52 | A | I | MBR | 6.6 | 6.6 |  |  | 2011-11-01 | 2012-09-01 | 2012-11-30 |  | 2014-12-01 | 2016-10-01 | 287700 | -3455 | 284245 | 284244.9 | 100% | 0.1 | 0 |  | 21578 | -259 | 21318 | 1 | 0 | The project was financially completed and the balance was returned at the 77th ExCom. |  |  | 2014-01-01 | INV
FIN | France | Terminal CFCs phase-out management plan (first tranche) | Multi-Year | AFR | KEN | PHA | 44 | INV | 37 | A | I | CFC | 53 | 53 | 0 |  | 2004-12-01 | 2007-08-01 | 2005-12-01 |  | 2008-05-01 | 2008-07-01 | 215914 | 0 | 215914 | 215914 | 100% | 0 |  | 0 | 28069 | 0 | 28069 | 0 |  | The French contribution was implemented by GTZ-Proklima. Project completed. |  |  | 2007-06-01
FIN | France | Terminal CFCs phase-out management plan (second tranche) | Multi-Year | AFR | KEN | PHA | 54 | INV | 44 | A | I | CFC | 20 |  | 0 |  | 2008-04-01 | 2008-10-01 | 2009-03-01 |  | 2010-03-01 | 2012-09-01 | 297000 | 0 | 297000 | 297000 | 100% | 0 |  | 0 | 38610 | 0 | 38610 | 0 |  | The French contribution was implemented by GTZ-Proklima. 2 trainers from local colleges were trained in a regional hydrocarbon training course in Namibia. Commercial refrigeration installations are being converted under the verification scheme. The project is completed.
FIN | France | Terminal CFCs phase-out management plan (third tranche) | Multi-Year | AFR | KEN | PHA | 57 | INV | 46 | A | I | CFC | 65.8 | 65.2 | 0 |  | 2009-04-01 | 2009-06-01 | 2010-03-01 |  | 2012-03-01 | 2012-12-01 | 179086 | -138033 | 41053 | 41053 | 100% | 0 |  | 0 | 23281 | -17944 | 5337 | 0 |  | The French contribution was implemented by GTZ-Proklima. The project is completed.
FIN | Germany | Preparation of a HCFC phase-out management plan | Individual | AFR | KEN | PHA | 58 | PRP | 49 | A | I | HCFC | 0 |  | 0 |  | 2009-07-01 | 2009-10-01 | 2010-07-01 |  | 2012-04-01 | 2013-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | The HPMP document was finalised and was approved at the 66th Excom as bilateral contribution of France. | The HPMP is being successfully implemented.
FIN | France | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | KEN | PHA | 66 | INV | 53 | A | I | HCFC | 3.1 | 19.2 | 0 |  | 2012-04-01 | 2012-05-01 | 2014-04-01 |  | 2014-07-01 | 2014-09-01 | 257500 | 0 | 257500 | 257500 | 100% | 0 |  | 0 | 31186 | 0 | 31186 | 0 |  | The French contribution is implemented by GIZ. Project completed.
COM | France | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | AFR | KEN | PHA | 72 | INV | 55 | A | I | HCFC | 5.2 | 27.5 | 0 |  | 2014-05-01 | 2014-07-01 | 2015-05-01 |  | 2015-10-01 |  | 200000 | 0 | 200000 | 200000 | 100% | 0 |  | 0 | 24222 | 0 | 24222 | 0 |  | 4 safe handling of HC refrigerant trainings were completed with the remaining funds left under the tranche
ONG | France | HCFC phase-out management plan (stage I, third tranche) |  | AFR | KEN | PHA | 75 | INV | 59 | A | I | HCFC | 0 |  | 0 |  | 2015-11-01 | 2016-01-01 | 2016-12-01 | 2017-05-01 |  |  | 176250 | 0 | 176250 | 154550 | 87.69% | 21700 |  | 21700 | 21346 | 0 | 18784 | 2562 |  | The achievement under tranche 2 has been the active involvement of the training institutes in encouraging best practice trainings as safe handling of HCs. A total of 467 technicians have been trained with a huge interest in the industry being created through the project partnering and supporting the Refrigeration association HEVAC. The issue that has held Kenya back remains enforcement, re-structuring of the Customs department, now the new single window system adoption by the government has created considerable problems on proper enforcement. It is hoped that 2017 this will be resolved and government will be able to improve the current situation with respect to controls on trade. | Customs trainings are currently ongoing in the country. 2 have been completed and the 3rd is planned for later in March 2017. NEMA has been contracted to do monitoring and reconcilation of the import permits and liaise with importers to have a better control on the imports into the country.
ONG | France | Preparation of a HCFC phase-out management plan (stage II) |  | AFR | KEN | PHA | 75 | PRP | 58 | A | I | HCFC | 0 |  | 0 |  | 2015-11-01 | 2016-04-01 | 2016-12-01 | 2017-04-01 |  |  | 60000 | 0 | 60000 | 56200 | 93.67% | 3800 |  | 3800 | 7800 | 0 | 7332 | 468 |  | The Stage 2 proposal was drafted for submisison at the 78th Excom however due to issues related to enforcement it was agreed that the submisison would be withdrawn and then re-submitted at the 1st meeting in 2017 following confirmation on progress made on enforcement. | GIZ has visited Kenya in 2017 and met with PS and enforcement agencies NEMA and KRA to impress on them the importance of stringent enforcement of the licensing system in the country.
ONG | France | HCFC phase-out management plan (stage I, fourth tranche) |  | AFR | KEN | PHA | 77 | INV | 60 | A | I | HCFC | 5.8 |  | 0 |  | 2016-12-01 | 2017-03-01 | 2017-12-01 | 2018-03-01 |  |  | 176250 | 0 | 176250 | 0 | 0% | 176250 |  | 120000 | 21346 | 0 |  | 21346 |  | The tranche was approved in late Nov 2016. Ccurrently efforts are ongoing to finalise the activities under the previous tranche and once funds are spent from the previous tranche activities will be initiaited from this tranche. Expected April/May 2017
TRF | UNDP | Demonstration and training unit for maintenance and recharge of refrigeration and air conditioning equipment | RMP-Component | AFR | KEN | REF | 04 | TRA | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1992-06-01 | 1993-06-01 |  |  | 1993-06-01 | 115100 | -105248 | 9852 | 9852 | 100% | 0 | 0 | 0 | 14963 | -13682 | 1281 | 0 | 0 | Transferred in 1993. Financially completed in 1993. |  | 1991 |  | Non-Investment
FIN | UNEP | Support to a national workshop on refrigeration | Individual | AFR | KEN | REF | 10 | TRA | 05 | A | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-07-01 | 1995-06-01 |  | 2001-07-01 | 2001-07-01 | 115000 | 0 | 115000 | 115000 | 100% | 0 | 0 |  | 14950 | 0 | 14950 | 0 | 0 |  |  |  | 1999-12-01
FIN | UNIDO | CFC-phase out project at Kenya Cold Storages Ltd. and subsidiary companies: Hall Equatorial, Premier Refrigeration and Engineering, Refrigeration Services | Individual | AFR | KEN | REF | 11 | INV | 06 | A | I | CFC | 40.8 | 40.8 |  |  | 1993-11-01 | 1996-12-01 | 1997-03-01 |  | 1998-12-01 | 2001-07-01 | 380875 | 123140 | 504015 | 504015 | 100% | 0 | 0 |  | 49514 | 15904 | 65418 | 0 | 0 | FIN
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | KEN | REF | 23 | PRP | 16 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1998-03-01 |  | 1998-07-01 | 2000-07-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | KEN | REF | 26 | TAS | 19 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2003-08-01 | 2004-05-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Completed. PCR submitted. TPMP approved in Dec 2004
FIN | Germany | Recovery and recycling project | Individual | AFR | KEN | REF | 28 | TAS | 24 | A | I | CFC | 8.5 | 5 | 0 | 0 | 1999-07-01 | 2000-03-01 | 2001-08-01 |  | 2004-05-01 | 2004-10-01 | 98725 | 0 | 98725 | 98725 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PCR submitted to the 44th Excom.
FIN | Germany | Project preparation for the RMP update | RMP Update | AFR | KEN | REF | 36 | TAS | 27 | A | I |  | 203.6 |  | 0 |  | 2002-03-01 | 2003-06-01 | 2003-03-01 |  | 2004-11-01 | 2004-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | A TPMP developed through the preparation process was approved at the 44th ExCom
FIN | IBRD | Country programme preparation |  | AFR | KEN | SEV | 04 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 31498 | -22816 | 8682 | 8682 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Country programme preparation | Individual | AFR | KEN | SEV | 06 | CPG | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-03-01 | 1993-07-01 |  | 1994-06-01 | 1997-12-01 | 25000 | -2270 | 22730 | 22730 | 100% | 0 | 0 | 0 | 3250 | -295.1 | 2954.9 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Institutional strengthening | Individual | AFR | KEN | SEV | 09 | INS | 03 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1995-12-01 | 1996-03-01 |  | 1998-06-01 | 2005-09-01 | 175000 | -34 | 174966 | 174966 | 100% | 0 | 0 | 0 | 22750 | -4.42 | 22745.58 | 0 | 0 | Completed in 1998. Financially completed in 2005. |  | 1993 |  | Non-Investment
FIN | UNIDO | Identification and preparation of projects in the solvents and aerosols sectors | Individual | AFR | KEN | SEV | 17 | PRP | 07 | A | I |  | 0 | 0 |  |  | 1995-07-01 | 1996-04-01 | 1995-11-01 |  | 1998-03-02 | 1999-08-01 | 15000 | -938 | 14062 | 14062 | 100% | 0 | 0 |  | 1950 | -125 | 1825 | 0 | 0 | FIN
FIN | UNDP | Renewal of institutional strengthening | Individual | AFR | KEN | SEV | 25 | INS | 18 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-08-01 | 2000-07-01 |  | 2000-12-01 | 2003-10-01 | 116667 | 0 | 116667 | 116667 | 100% | 0 | 0 | 0 | 15166.71 | 0 | 15166.71 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1998 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening (Phase III) | Individual | AFR | KEN | SEV | 32 | INS | 25 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2003-01-01 |  | 2003-01-01 | 2005-09-01 | 116667 | -234 | 116433 | 116433 | 100% | 0 | 0 | 0 | 15166.71 | -30.42 | 15136.2894 | 0.0006 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Non-Investment
FIN | UNEP | Policy and technical assistance | Individual | AFR | KEN | SEV | 37 | TAS | 29 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-07-01 | 2003-08-01 |  | 2005-12-01 | 2007-03-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNDP | Extension of institutional strengthening project | Individual | AFR | KEN | SEV | 38 | INS | 30 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-02-01 | 2004-12-01 |  | 2004-12-01 | 2006-12-01 | 151667 | -204 | 151463 | 151463 | 100% | 0 | 0 | 0 | 19716.71 | -27 | 19689.71 | 0 | 0 | Completed in 2004. Financially completed in 2006. |  | 2002 |  | Non-Investment
TRF | UNDP | Extension of institutional strengthening project (phase V) | Individual | AFR | KEN | SEV | 44 | INS | 39 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2006-12-01 |  |  | 2010-10-01 | 151667 | -785.64 | 150881.36 | 150881 | 100% | 0.36 | 0 | 0 | 11375 | -58.92 | 11316.0501 | 0.0299 | 0 | Transferred in 2007. Financially completed in 2010. |  | 2004 |  | Non-Investment
TRF | UNDP | Extension of the institutional strengthening project (1st year of phase VI) | Individual | AFR | KEN | SEV | 50 | INS | 39 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 |  | 2007-11-01 |  |  | 2007-12-01 | 75833 | -75833 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 5688 | -5688 | 0 | 0 | 0 | Transferred in 2007. Financially Completed in 2007. |  | 2006 |  | Non-Investment
FIN | UNEP | Extension of the institutional strengthening project (1st year of phase VI) | Individual | AFR | KEN | SEV | 52 | INS | 42 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-11-01 | 2007-11-01 |  | 2008-11-01 | 2009-11-01 | 75833 | 0 | 75833 | 75833 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (2nd year of phase VI) | Individual | AFR | KEN | SEV | 55 | INS | 45 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-10-01 | 2009-06-01 |  | 2010-12-01 | 2011-12-01 | 75833 | 0 | 75833 | 75833 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VII) | Individual | AFR | KEN | SEV | 58 | INS | 48 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2010-07-01 | 2010-12-01 |  | 2010-12-01 | 2011-12-01 | 107431 | 0 | 107431 | 107431 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase VIII) | Individual | AFR | KEN | SEV | 62 | INS | 51 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-09-01 | 2012-12-01 |  | 2013-08-01 | 2014-12-01 | 151667 | 0 | 151667 | 151667 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of institutional strengthening project (phase IX: 4/2013-3/2015) | Individual | AFR | KEN | SEV | 69 | INS | 54 | A | I |  | 0 |  | 0 |  | 2013-04-01 | 2014-02-01 | 2015-03-01 |  | 2015-12-01 |  | 151667 | 0 | 151667 | 113867 | 75.08% | 37800 | 37800 | 37800 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): __ The licensing and quota systems are in place and operational. The NOU registered all importers of HCFCs and other ODS and organized stakeholders’ workshop to allocate HCFC licenses and quotas to importers. The NOU conducted two inspection visits to monitor distribution of HCFCs to check compliance with the quotas allocated. The NOU conducted two RAC training workshops and two custom training workshops, and trained 60 technicians and 40 custom officers respectively. The NOU celebrated the 2016 international ozone day with several activities including school essay composition. The NOU collected, processed and submitted 2015 Country Programme and Article 7 Data reports. The NOU participated in all Montreal Protocol meetings organized in 2016. project activities completed__ Legal arrangements(actual/planned): The SSFA was signed between the country and UNEP in December 2013 __Initial stages of project implementation(actual/planned): Yes___ Intermediate goals achieved (actual/planned): Yes___ Project completion and follow up: _Yes__ First disbursement date (actual/planned): The 1st disbursement ($37,800) was made in Feb 2014, the 2nd payment ($38,100) was made in September 2014, the 3rd disbursement ($37967) was made in March 2015, and the final disbursement ($37,800) was made in December 2015.___ All funds disbursed (yes/no): _Yes__ Any delay?(yes/no): __No_ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: _N/A__ | Project completed
ONG | UNEP | Extension of institutional strengthening project (phase X: 4/2015-3/2017) | Individual | AFR | KEN | SEV | 74 | INS | 56 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-07-01 | 2017-03-01 | 2018-03-01 |  |  | 151667 | 0 | 151667 | 0 | 0% | 151667 | 151667 | 15166.7 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): __ The licensing and quota systems are in place and operational. The NOU registered all importers of HCFCs and other ODS and organized stakeholders’ workshop to allocate HCFC licenses and quotas to importers. The NOU conducted two inspection visits to monitor distribution of HCFCs to check compliance with the quotas allocated. The NOU conducted two RAC training workshops and two custom training workshops, and trained 60 technicians and 40 custom officers respectively. The NOU celebrated the 2016 international ozone day with several activities including school essay composition. The NOU collected, processed and submitted 2015 Country Programme and Article 7 Data reports. The NOU participated in all Montreal Protocol meetings organized in 2016.__ Legal arrangements(actual/planned): The SSFA was drafted and signed by UNEP and the Government of Kenya in March 2106 __Initial stages of project implementation(actual/planned): Yes___ Intermediate goals achieved (actual/planned): Yes___ Project completion and follow up: _Yes__ First disbursement date (actual/planned): July 2016 ___ All funds disbursed (yes/no): No__ Any delay?(yes/no): __No_ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): The NOU continues to monitor imports and trade of ODS and ODS related equipment. Collection of the 2016 data on ODS imports and consumption has been completed and is being analyzed for submission. NOU commenced preparation of national legislative requirement processes in planning for ratification of Kigali amendment.
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | AFR | KEN | SEV | 74 | TAS | 57 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-04-01 | 2016-05-01 | 2017-05-01 |  |  | 110000 | 0 | 110000 | 10100 | 9.182% | 99900 | 0 | 9990 | 14300 | 0 | 1313 | 12987 | 0 | Brief progress report (actual/planned): The first stakeholders meeting was organized by the NOU in June 2016 with the main goal to agree on the plan for the Survey of ODS alternatives at the national level and obtain support of main national stakeholders. The meeting was attended by 35 participants. One National Consultant was hired in June 2016 by the NOU to support the data collection. The National Consultant assisted the NOU in the identification of the current use of ODS alternatives by substance/sector and collection of import/export data for the substances for the past a couple of years. The National Consultant also provided support in establishing growth patterns in use by substance/sector and in compiling data on available ODS alternatives for various applications.The NOU and the National Consultant drafted and cross checked the information to ensure the completion of end-user surveys, collection, analysis, and aggregation of consumption data. The various sections of the report were drafted. The second stakeholders meeting was organized by the NOU in September 2016 with the main goal to organise consultations with representatives of the government and private sector to finalize the outcomes of the Survey of ODS alternatives and discuss potential opportunities for introduction of those alternatives in the country. The draft report was prepared by the NOU and the National Consultant. It was reviewed and finalized based on the format approved by ExCom decision 75/67 as contained in document UNEP/OzL.Pro/ExCom/75/77/Rev.1 after incorporating inputs/ comments raised during National Stakeholders’ workshop. The final report has been submitted to UNEP for final review and submission to MLFS. Legal arrangements(actual/planned): N/A___Initial stages of project implementation(actual/planned): _Yes__ Intermediate goals achieved (actual/planned): Yes___ Project completion and follow up: _No__ First disbursement date (actual/planned): _N/A__ All funds disbursed (yes/no): No___ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): __N/A_ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): The NOU incorporated comments from UNEP ROA and Paris and re-submitted final ODS survey report in January 2017.
FIN | UNIDO | Conversion of ODS cleaning processes from TCA to aqueous cleaning and cleaning in TCE at Kenyan Railways Central Workshop | Individual | AFR | KEN | SOL | 23 | INV | 14 | A | I | TCA | 6 | 6 |  |  | 1997-11-01 | 1998-08-01 | 1998-12-01 |  | 1999-12-01 | 2002-09-01 | 205524 | 0 | 205524 | 205524.21 | 100% | -0.21 | 0 |  | 26718 | 0 | 26718 | 0 | 0 | FIN
FIN | Germany | Project preparation for the solvent sector | Individual | AFR | KEN | SOL | 35 | PRP | 26 | A | I |  | 0 |  | 0 |  | 2001-12-01 | 2002-05-01 | 2003-07-01 |  | 2002-11-01 | 2004-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project completed , investment project being implemented
FIN | Germany | Conversion of TCA based cleaning process to non-ODS alternatives at the Kenya Power and Lighting Company | Individual | AFR | KEN | SOL | 39 | INV | 32 | A | I | TCA | 1.9 | 1 | 0 | 0 | 2003-04-01 | 2003-07-01 | 2004-10-01 |  | 2007-12-01 | 2009-09-01 | 85800 | -3112 | 82688 | 82688 | 100% | 0 | 0 | 0 | 11154 | -405 | 10749 | 0 | 0 | PCR was submitted sept 2009
FIN | UNDP | Project preparation for the formulation of solvent sectoral phase-out plan | Individual | AFR | KEN | SOL | 42 | PRP | 34 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2005-04-01 |  | 2007-09-01 | 2010-10-01 | 20000 | -1850.32 | 18149.68 | 18150 | 100% | -0.32 | 0 | 0 | 1500 | -138.77 | 1361.25 | -0.02 | 0 | Financially completed in 2010. |  | 2004 |  | Investment
FIN | UNIDO | Technical assistance for the total phase-out of CTC and TCA in the solvent sector | Individual | AFR | KEN | SOL | 57 | TAS | 47 | A | I | CTC TCA | 0.2 | 0.2 |  |  | 2009-04-01 | 2010-12-01 | 2010-03-31 |  | 2012-07-01 | 2012-12-01 | 40000 | -988 | 39012 | 39012.44 | 100% | -0.44 | 0 |  | 3600 | -89 | 3511 | 0 | 0 | FIN |  |  |  | INV
FIN | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, first tranche, Kiribati) | Multi-Year | ASP | KIR | PHA | 63 | TAS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-10-01 | 2015-03-01 |  | 2015-04-01 | 2016-12-01 | 53250 | 0 | 53250 | 53250 | 100% | 0 | 0 |  | 6923 | 0 | 6923 | 0 | 0 | Project financially completed. | Project financially completed.
ONG | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, second tranche, Kiribati) | Multi-year | ASP | KIR | PHA | 74 | TAS | 11 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-08-01 | 2020-05-01 | 2020-12-01 |  |  | 44850 | 0 | 44850 | 7264.65 | 16.2% | 37585.35 | 21314.25 | 3758.535 | 5831 | 0 | 944.4855 | 4886.5145 | 2771.0901 | Brief progress report (actual/planned): The SSFA was signed by UNEP and the Government of Kiribati in March 2016. The first payment under the second tranche was made to the country in August 2016. The licensing and quota system was implemented in 2016. A RAC expert was recruited to deliver update RAC training workshop. Despite the absence of the NOO, the government assigned interim NOO and organized 2 update RAC training workshops in Tawara from 21-25 November and in Kiritimati Islands from 1-3 December 2016 (with total 48 participants). UNEP worked closely with the NOU to engage multi-stakeholders in the implementation of HPMP, second tranche to synergize HPMP with other on-going environmental policies/projects e.g. PALS, Samoa Pathway. 2015 CP data was submitted to MLFS online. Legal arrangements (actual/planned): The SSFA was signed in March 2016 First Mission: Not yet. TOR completed: Not applicable First disbursement date: August 2016. All funds disbursed (yes/no): No. Any delay? (yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): A new NOO has been assigned. UNEP keeps regular communications with the country to expedite HPMP implementation as per the agreed work plan. The capacity building activities for new NOO will be conducted as part of the PIC network meeting in 2017. UNEP mission is planned in 2017.
FIN | Australia | Implementation of the PIC Strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | KIR | REF | 36 | TAS | 02 | A | I |  | 0.2 | 0 | 0 | 0 | 2002-03-01 | 2003-05-01 | 2005-04-01 |  | 2008-06-01 | 2012-05-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | completed |  | 2002
FIN | Australia | Implementation of the PIC Strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | KIR | REF | 36 | TAS | 03 | A | I |  | 0.4 | 0 | 0 | 0 | 2002-03-01 | 2003-05-01 | 2005-04-01 |  | 2008-06-01 | 2012-05-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 | 0 | 2340 | 0 | 2340 | 0 | 0 | completed |  | 2002
FIN | UNEP | Country programme preparation | Individual | ASP | KIR | SEV | 17 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1997-01-01 | 1996-10-01 |  | 2002-03-01 | 2003-07-01 | 20000 | -7000 | 13000 | 13000 | 100% | 0 | 0 |  | 2600 | -910 | 1690 | 0 | 0 |  |  |  | 1999-10-01
FIN | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | KIR | SEV | 36 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2004-01-01 | 2005-04-01 |  | 2006-06-01 | 2007-06-01 | 23000 | 0 | 23000 | 23000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase II) | Individual | ASP | KIR | SEV | 49 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2009-01-01 | 2007-03-01 |  | 2008-12-01 | 2009-12-01 | 7666 | 0 | 7666 | 7666 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase II, second year) | Individual | ASP | KIR | SEV | 53 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2009-02-01 | 2008-11-01 |  | 2010-03-01 | 2010-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase III) | Individual | ASP | KIR | SEV | 59 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-09-01 | 2011-11-01 |  | 2011-12-01 | 2012-12-01 | 32500 | 27500 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase IV: 12/2011-11/2013) | Individual | ASP | KIR | SEV | 64 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-05-01 | 2013-11-01 |  | 2013-11-01 | 2014-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Renewal of institutional strengthening project (phase V: 12/2013-11/2015) | Individual | ASP | KIR | SEV | 70 | INS | 10 | A | I |  | 0 |  | 0 |  | 2013-07-01 | 2014-11-01 | 2015-11-01 | 2017-07-01 |  |  | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The NOU has been responsible for the management of all Montreal Protocol activities. The operation of the NOU was going on well. The license/quota system has been enforced in 2016. NOU also coordinated and facilitated the implementation of HPMPand ODS Alternative Survey. The NOU also organized the 2016 ozone day celebration, and the Government actively joined the regional and global ozone related meetings e.g. the network meeting, OEWG and the MOP meetings. 2015 Article 7 and CP data were submitted to the Ozone Secretariat and MLFS respectively. The SSFA was amended to extend the closing date to 31 July 2017 to accommodate the disbursement of the remaining payments. However, the NOO who was appointed in 2015 left the government in 2016. Legal arrangements(actual/planned): The SSFA was signed April 2014. Initial stages of project implementation(actual/planned): Dec 2013/Apr 2014. Intermediate goals achieved (actual/planned): New NOO appointed in 2015 was still in charge of the Montreal Protocol activities. Compliance (2015) sustained : Project completion and follow up: Not applicable. First disbursement date (actual/planned): December 2014. All funds disbursed (yes/no): No. Any delay?(yes/no): Yes If Yes, reasons for delay & action plan to resolve: The delay was caused by the lost of NOU until new NOO is appointed. If Yes, will delay have impact on project completion date (yes/no): Yes, the SSFA was extended to 31 July 2017. Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): Country continues to enforce the licensing and quota system. A new NOO has been assigned. UNEP kept regular communication with the new NOO to strengthen their Montreal Protocol knowledge and implementation capacity (from Bangkok through phone calls, emails, skype conference calls etc.). The capacity building activities for new NOO will be conducted as part of the PIC network meeting in 2017. There are 2 remaining payments to be disbursed to the country. Projecct will be completed in June 2017.
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | ASP | KIR | SEV | 75 | TAS | 12 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-09-01 | 2016-12-01 | 2017-06-01 |  |  | 40000 | 0 | 40000 | 19526.78 | 48.82% | 20473.22 | 13103.98 | 2047.322 | 5200 | 0 | 2538.4814 | 2661.5186 | 1703.5174 | Brief progress report (actual/planned): The SSFA was signed by UNEP and the Government of Kiribati in June 2016. The first payment was made to the country in September 2016. NOO (already left the NOU in 2017) attended the training for conducting natiional surveys as part of Thematic workshop for Asia and the Pacific in June 2016. A regional expert was appointed by UNEP to provide support to the NOO in the planned, data collection and preparation of report. The regioanl consultant conducted a mission in November 2016 to support the NOO to lead the data collection. The regional consultant assisted the NOU and the local consultant in the identification of the current use of ODS alternatives by substance/sector and collection of import/export data for the substances for the past a couple of years. The regional consultant also provided support in establishing growth patterns in use by substance/sector and in compiling data on available ODS alternatives for various applications. The NOU and consulting firm drafted and cross checked the information to ensure the completion of end-user surveys, collection, analysis, and aggregation of consumption data. Legal arrangements(actual/planned): The SSFA was signed in June 2016 Initial stages of project implementation(actual/planned): June 2016 . Intermediate goals achieved (actual/planned): Not applicable. Project completion and follow up: Not applicable. First disbursement date (actual/planned): September 2016. All funds disbursed (yes/no): No. Any delay?(yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): The draft report was prepared by the NOU and the regional consultant based on the format approved by ExCom decision 75/67 as contained in document UNEP/OzL.Pro/ExCom/75/77/Rev.1. UNEP reviewed the draft and provide comments/observations for the NOU and the regional consultant to finalize the report.
ONG | UNEP | Renewal of institutional strengthening project (phase VI: 12/2016-11/2018) | Individual | ASP | KIR | SEV | 76 | INS | 13 | A | I |  | 0 |  | 0 |  | 2016-05-01 | 2016-09-01 | 2018-11-01 | 2018-11-01 |  |  | 85000 | 0 | 85000 | 13060.67 | 15.37% | 71939.33 | 31939.33 | 7193.933 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The project was approved at the 76th ExCom Meeting in May 2016. The SSFA was drafted in consultation with the country. Legal arrangements(actual/planned): Not yet Initial stages of project implementation(actual/planned): Not yet Intermediate goals achieved (actual/planned): Not yet Project completion and follow up: Not applicable. First disbursement date (actual/planned): Not yet. All funds disbursed (yes/no): _No__ Any delay?(yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): UNEP is working with the NOU to finalize the SSFA for IS project phase VI.
FIN | UNIDO | Preparation for HCFC phase-out investment activities (polyurethane foam component) | Individual | ASP | KUW | FOA | 63 | PRP | 17 | A | I |  | 0 | 0 |  |  | 2011-04-01 | 2011-07-01 | 2012-03-31 |  | 2012-12-01 | 2013-12-01 | 60000 | -700 | 59300 | 59300.05 | 100% | -0.05 | 0 |  | 4500 | -52 | 4448 | 0 | 0 | FIN |  |  |  | NON-INV
CLO | UNIDO | Preparation of a halon phase-out plan | Individual | ASP | KUW | HAL | 45 | PRP | 07 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2007-01-01 | 2006-04-01 |  |  | 2010-09-01 | 25000 | -3210 | 21790 | 21790 | 100% | 0 | 0 |  | 1875 | -241 | 1634 | 0 | 0 | CLO |  |  |  | NON-INV
FIN | UNIDO | Preparation of a terminal phase-out management project | Individual | ASP | KUW | PHA | 48 | PRP | 09 | A | I |  | 0 | 0 |  |  | 2006-04-01 | 2007-01-01 | 2007-04-01 |  | 2007-07-01 | 2008-08-01 | 25000 | -2 | 24998 | 24998.08 | 100% | -0.08 | 0 |  | 1875 | 0 | 1875 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | ASP | KUW | PHA | 52 | INV | 11 | A | I | CFC | 15 | 15 |  |  | 2007-07-01 | 2007-12-01 | 2008-11-01 |  | 2010-11-01 | 2013-04-01 | 220000 | -527 | 219473 | 219472.94 | 100% | 0.06 | 0 |  | 19800 | -47 | 19753 | 0 | 0 | FIN |  |  |  | INV
COM | UNEP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-year | ASP | KUW | PHA | 52 | TAS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2009-06-01 | 2008-11-01 |  | 2016-01-01 |  | 240000 | 0 | 240000 | 12912.27 | 5.38% | 227087.73 | 227087.73 | 227088 | 31200 | 0 | 1678.5951 | 29521.4049 | 29521.4049 | Project Completed, remaining funds transferred to HPMP as per Decision 66/47, respective progress is under the HPMP project | Project Completed, remaining funds transferred to HPMP as per Decision 66/47, respective progress is under the HPMP project
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | ASP | KUW | PHA | 55 | PRP | 13 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2009-04-01 | 2009-07-31 |  | 2012-12-01 | 2012-12-01 | 70000 | -757 | 69243 | 69242.53 | 100% | 0.47 | 0 |  | 5250 | -57 | 5193 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | KUW | PHA | 55 | PRP | 14 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-10-01 | 2009-07-01 |  | 2011-12-01 | 2014-05-01 | 125000 | -16223 | 108777 | 108777 | 100% | 0 | 0 |  | 16250 | -2108.99 | 14141.01 | 0 | 0
FIN | UNEP | TPMP verification | Individual | ASP | KUW | PHA | 57 | TAS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 |  | 2010-03-01 |  | 2014-11-01 | 2014-11-01 | 20000 | -20000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 2600 | -2600 |  | 0 |  |  |  |  | 2012-07-01
COM | UNIDO | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | ASP | KUW | PHA | 66 | INV | 18 | A | I |  | 0 | 0 |  |  | 2012-04-01 | 2014-10-01 | 2014-04-30 |  | 2016-12-01 |  | 12000 | 0 | 12000 | 9899.57 | 82.5% | 2100.43 | 1040 | 1000 | 900 | 0 | 742 | 158 | 78 | Installation and commissioning took place during 2nd half of 2016. Actions towards next goals: Get approval of the NOU for another technical expert. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | Project completed, Financial closure is ongoing. |  |  | INV |  | To request the submission of additional status report to the 79th meeting to monitor the procurement and/or delivery of the equipment.
COM | UNIDO | HCFC phase-out management plan (stage I, first tranche) (polyurethane foam sector phase-out: Kuwait polyurethane Industry Co.; Kirby Building Systems, technical assistance to spray foam users and other small users) | Multi-Year | ASP | KUW | PHA | 66 | INV | 20 | A | I | HCFC | 10.9 | 10.9 |  |  | 2012-04-01 | 2013-01-01 | 2014-04-30 |  | 2016-12-01 |  | 15000 | 0 | 15000 | 14459.94 | 96.4% | 540.06 | 540.06 | 1 | 1125 | 0 | 1084 | 41 | 40.5045 | Project completed, activities are continuing within the second tranche. |  |  |  | INV |  | To request the submission of additional status report to the 79th meeting to monitor the procurement and/or delivery of the equipment.
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (extruded polystyrene foam sector phase-out: Gulf Insulating Materials Manufacturing and Trading; Isofoam Insulating Materials Plants; and Al Masaha Comapny) | Multi-Year | ASP | KUW | PHA | 66 | INV | 21 | A | I | HCFC | 49.8 | 0 |  |  | 2012-04-01 | 2013-01-01 | 2014-04-30 | 2017-12-01 |  |  | 3510450 | 0 | 3510450 | 310942.43 | 8.858% | 3199507.57 | 2994893.43 | 204614 | 263284 | 0 | 23321 | 239963 | 224617.0072 | Pre-shipment inspection of the equipment for the for the 1st XPS production lines was done in January 2016. Shipment of the equipment had to be postponed since the beneficiaries had to request approval of additional electrical load for their factories from the authorities and procure a new electrical transformer. The approval was obtained in September 2016 and the shipment was delivered in December 2016. Installation and commissioning is scheduled for early 2017. Milestones achieved: Milestone 1: Pre-shipment inspection - Yes Milestone 2: Shipment initiated - Yes Milestone 3: Customs clearance obtained - Yes Milestone 4: Installation/Commissioning - No Actions towards next goals: Requested the supplier to schedule installation/commissioning. Was there any delay during the reporting year? Yes, due to internal administrative delays. Any recurring problem? No Any impact on project completion date: Yes Any action required by Executive Committee? No | Installation and commissioning is ongoing and is expected to be completed in the second half of 2017. Milestones achieved: Milestone 1: Installation/Commissioning - No Actions towards next goals: Monitor the installation and commissioning. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: Yes Any action required by Executive Committee? No |  |  | INV |  | To request the submission of additional status report to the 79th meeting to monitor the procurement and/or delivery of the equipment.
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector and monitoring and verification) | Multi-Year | ASP | KUW | PHA | 66 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 | 2015-05-01 | 2014-04-01 | 2017-12-01 |  |  | 277000 | 0 | 277000 | 16454.16 | 5.94% | 260545.84 | 149644.05 | 26054.584 | 33126 | 0 | 1967.7275 | 31158.2725 | 17895.6996 | Brief progress report (actual/planned): Technical Committees for the standards and certification programs continued their work. Draft code of practice for 4 RAC professions is developed and currently under review. E-Likening S/W is developed and started to be tested by NOU for official launch and use by end of 2016. MOUs with customs and Standards authorities are ready for signature. UNEP conducted mission to country to review the work plan of different technical teams and provide technical advice to the process of standards update and certification scheme. - Legal arrangements (actual/planned): Legal instrument signed since 2014 and first payment made - Initial stages of project implementation (actual/planned): all initial stages completed including the contracting arrangements, planning of activities and kick-off of all programs - Project completion and follow up: Tranche related activities are expected to be completed by end of 2017 - All funds disbursed (yes/no): No, remaining payments under country contract to be disbursed during 2017 - Project ongoing & delayed Any delay? (yes/no): Ongoing with some delays due to delays in utilizing the funds by EPA as well as delay in concluding internal agreements with Customs and standards authorities. Delay as well in the certification program since the national certification body is dissolved and merged with another ministry - If Yes, will delay have impact on project completion date (yes/no): Yes, it will affect the tranche completion date but will not affect targets of stage-I - Any ongoing problems (yes/no): No | Brief progress report (actual/planned): - Internal contracts with customs & Standards authorities are signed - Training program for the customs is developed including materials and training to start after summer holidays - E-Licensing system is tested and fully operational as of 1st quarter of 2017
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) (polyurethane foam sector phase-out: Kuwait polyurethane Industry Co.; Kirby Building Systems, technical assistance to spray foam users and other small users) | Multi-Year | ASP | KUW | PHA | 74 | INV | 24 | A | I | HCFC | 96.7 | 0 |  |  | 2015-05-01 |  | 2018-05-31 | 2018-06-30 |  |  | 643382 | 0 | 643382 | 0 | 0% | 643382 | 233346 | 200000 | 45037 | 0 | 0 | 45037 | 16334.22 | Technical Expert recommended by NOU/EPA was scheduled to visit the two PU foam factories in September 2016 to elaborate Terms of Reference for conversion to pentane. The visit had to be postponed several times because of the unavailability of the expert. Milestones achieved: Milestone 1: Technical Expert's mission - No Milestone 2: Terms of Reference elaborated - No Milestone 3: Bidding for Equipment - No Milestone 4: Shipment of equipment - No Activities planned but not implemented, reasons and strategy: Technical Expert's mission, due to unavailability of the recommended consultant. Actions towards next goals: Another Technical Expert identified; approval of NOU/EPA obtained. Was there any delay during the reporting year? Yes, due to internal administrative delays. Any recurring problem? No Any impact on project completion date: Yes Any action required by Executive Committee? No | After obtaining approval from the NOU/EPA, the Technical Expert selected by UNIDO visited the two PU foam factories in March 2016 and elaborated the Terms of Reference for conversion to pentane. The expert also visited two local systems houses and discussed a plan for technical assistance to spray foam users. The bidding process for PU foam equipment started in April 2017 and contract award is expected in May/June 2017. Milestones achieved: Milestone 1: Technical Expert's mission - Yes Milestone 2: Terms of Reference elaborated - Yes Milestone 3: Bidding for Equipment - Yes Milestone 4: Contract award - No Milestone 5: Equipment shipped - No Milestone 6: Technical assistance to SHs/spray foamers - No Actions towards next goals: Publish RFx, technical evaluation, shipment. Was there any delay during the reporting year? Yes, due to internal administrative delays. Any recurring problem? No Any impact on project completion date: Yes Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) (extruded polystyrene foam sector phase-out: Gulf Insulating Materials Manufacturing and Trading; Isofoam Insulating Materials Plants; and Al Masaha Company) | Multi-Year | ASP | KUW | PHA | 74 | INV | 25 | A | I | HCFC | 47.3 | 0 |  |  | 2015-05-01 |  | 2018-05-31 | 2018-06-30 |  |  | 2706000 | 0 | 2706000 | 0 | 0% | 2706000 | 2569298.95 | 100000 | 189420 | 0 | 0 | 189420 | 179850.9265 | Terms of Reference for conversion of the 2nd production lines was prepared in September, bidding process was completed in November and contract to the selected supplier was awarded in December 2016. Milestones achieved: Milestone 1: Terms of Reference - Yes Milestone 2: Bidding completed - Yes Milestone 3: Contract warded - Yes Milestone 4: First disbursement made - No Activities planned but not implemented, reasons and strategy: Request first disbursement by the beneficiary. Actions towards next goals: Arrange pre-shipment inspection. Was there any delay during the reporting year? Yes, due to internal administrative delays. Any recurring problem? No Any impact on project completion date: Yes Any action required by Executive Committee? No | First disbursement was made upon provision of a bank guarantee by the supplier in April 2017. Pre-shipment inspection is expected in September 2017 and shipment by the end of 2017. Milestones achieved: Milestone 1: First disbursement by the beneficiary made - Yes Milestone 2: Work plan withe the supplier - Yes Milestone 3: Pre-shipment inspection - No Milestone 4: Equipment shipped - No Activities planned but not implemented, reasons and strategy: Slight delay because of delay in performance bank guarantee by the supplier - received in April 2017. Actions towards next goals: According to work plan schedule pre-shipment inspection. Was there any delay during the reporting year? Yes, due to internal administrative delays. Any recurring problem? No Any impact on project completion date: Yes Any action required by Executive Committee? No |  |  | INV
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector and monitoring and verification) | Multi-year | ASP | KUW | PHA | 74 | TAS | 23 | A | I |  | 5.2 |  | 0 |  | 2015-05-01 |  | 2017-05-01 | 2017-05-01 |  |  | 337000 | 0 | 337000 | 0 | 0% | 337000 | 0 | 33700 | 40301 | 0 | 0 | 40301 | 0 | Brief progress report (actual/planned): 2nd tranche activities are linked to 1st tranche. Detailed work plan is developed jointly with the country - Legal arrangements (actual/planned): Due to delay in utilizing the funds from the 1st tranche, 2nd tranche contract was deferred till beginning of 2017 - Initial stages of project implementation (actual/planned): implementation to start in 2017 - Project completion and follow up: Tranche related activities are expected to be completed by end of 2018 - All funds disbursed (yes/no): No - Project ongoing & delayed Any delay? (yes/no): Ongoing. Due to delay in utilizing the funds from the 1st tranche, 2nd tranche contract was deferred till beginning of 2017 - If Yes, will delay have impact on project completion date (yes/no): Yes, it will affect the tranche completion date but will not affect targets of stage-I of the HPMP - Any ongoing problems (yes/no): No | Brief progress report (actual/planned): - Country contract drafted and under signature - Funds disbursement planned to start mid of 2017
FIN | UNIDO | Implementation of the RMP: national recovery and recycling | RMP Update | ASP | KUW | REF | 37 | TAS | 05 | A | I | CFC | 64 | 64 |  |  | 2002-07-01 | 2003-07-01 | 2005-08-01 |  | 2006-12-01 | 2008-12-01 | 448816 | -2441 | 446375 | 446375.13 | 100% | -0.13 | 0 |  | 22441 | 35588 | 58029 | 0 | 0 | FIN |  |  |  | INV
FIN | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | ASP | KUW | REF | 37 | TAS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2005-12-01 | 2005-08-01 |  | 2009-12-01 | 2010-12-01 | 27000 | 0 | 27000 | 27000 | 100% | 0 | 0 |  | 3510 | 0 | 3510 | 0 | 0
FIN | UNEP | Implementation of the RMP: training of customs officers in monitoring of ODS | Individual | ASP | KUW | REF | 37 | TRA | 03 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-11-01 | 2004-01-01 |  | 2004-12-01 | 2006-12-01 | 53445 | 0 | 53445 | 53445 | 100% | 0 | 0 |  | 6948 | 0 | 6948 | 0 | 0
FIN | UNEP | Implementation of the RMP: training programme on good refrigerant management practices and hydrocarbon (HC) refrigerants safe handling | Individual | ASP | KUW | REF | 37 | TRA | 04 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2004-09-01 | 2004-08-01 |  | 2011-12-01 | 2014-11-01 | 95325 | -8962 | 86363 | 86363 | 100% | 0 | 0 |  | 12392 | -1165.04 | 11226.96 | 0 | 0
ONG | UNDP | Preparation of a demonstration project for low-global warming potential alternatives in high ambient temperature conditions in air-conditioning applications | Individual | ASP | KUW | REF | 74 | PRP | 26 | N | I | HCFC | 0 | 0 | 0 | 0 | 2015-05-01 |  | 2016-05-01 | 2017-05-01 |  |  | 20000 | 0 | 20000 | 0 | 0% | 20000 | 0 | 8000 | 1400 | 0 | 0 | 1400 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Project document was developed and approved by ExCom in 2016 for implementation. National Refrigeration Institute (KISR) provided technical assistance with the formulation of the project. Prodoc signed (actual/planned, yes/no and date):No. Special national procedure on KISR involvement initiated with follow-up compensatory mechanism to be engaged. Missions undertaken (actual/planned):1/1: One mission fielded TOR for consultants/subcontracts completed (actual/planned): 1/1: One international expert was recruited and involved in the project formulation process. Contract/PO/MOA agreements signed: 0/0: No procurement required in the PRP First disbursement date (actual/planned): Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | Financial disbursements expected in March 2017 to allow cost recovery to KISR | 2015 |  | Non-Investment
ONG | UNIDO | Comparative analysis of three not-in-kind technologies for use in central air-conditioning | Individual | ASP | KUW | REF | 75 | TAS | 28 | A | I |  | 0 | 0 |  |  | 2015-11-01 | 2016-12-01 | 2017-12-01 | 2017-12-18 |  |  | 63521 | 0 | 63521 | 5262.19 | 8.284% | 58258.81 | 3987.94 | 40000 | 5717 | 0 | 0 | 5717 | 358.9146 | Participation of two national experts at the conference in Stockholm September 2016. Coordination meeting with cooperating agency UNEP held in November 2016. Work plan for the project prepared. Milestones achieved: Milestone 1: Participation at Stockholm conference - Yes Milestone 2: Coordination meeting - Yes Milestone 3: Work plan for 2017 - Yes Actions towards next goals: Recruitment of technical and financial experts. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | Appointment of technical and financial experts is pending on approval of the NOU. The work plan was discussed with the NOU and UNEP at the regional network meeting in Jordan. Milestones achieved: Milestone 1: Approval of technical/financial expert - Yes Milestone 2: Recruitment of tech/fin experts - No Milestone 3: Experts reports - No Actions towards next goals: Recruitment of technical and financial experts with approval of the NOU. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | NON-INV
ONG | UNEP | Comparative analysis of three not-in-kind technologies for use in central air-conditioning (feasibility study for district cooling) | Individual | ASP | KUW | REF | 75 | TAS | 29 | A | I |  | 0 |  | 0 |  | 2015-11-01 |  | 2016-12-01 | 2017-12-01 |  |  | 27223 | 0 | 27223 | 0 | 0% | 27223 | 0 | 2722.3 | 3539 | 0 | 0 | 3539 | 0 | Brief progress report (actual/planned): - Coordination meeting is arranged with NOU and UNIDO. - Field visit is arranged to attend the Sweden District cooling Workshop (Sept 2016) by the local experts that will develop the national DC operational guidelines that will be institutionally adopted by Kuwait. - Country visit made and meeting with the project team is organized including Ministry of electricity, Kuwait foundation for Advancement of Science (KFAS) and Kuwait Institute for Scientific Research (KISR) - International Expert identified and contracted for conducting the technical and financial feasibility - Detailed TORs for the technical and financial feasibility are developed as well as TORs for the institutional and regulatory framework - Country formed local Taskforce for the project represented by different relevant authorities and local experts | Brief progress report (actual/planned): - Country contract drafted for the development of the institutional and regulatory framework - Plans to complete the project by 4th quarter of 2017
ONG | UNDP | Demonstration project for HCFC-free low-global warming potential technology performance in air-conditioning applications (capacity above 8TR) | Individual | ASP | KUW | REF | 76 | DEM | 32 | N | I | HCFC | 0 | 0 | 0 | 0 | 2016-05-01 |  | 2019-05-01 | 2019-05-01 |  |  | 293000 | 0 | 293000 | 0 | 0% | 293000 | 0 | 117200 | 20510 | 0 | 0 | 20510 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): DOA documentation prepared and dispatched to UNDP-Kuwait. Project signature's preparatory activities were initiated with official meetings. Project workplans were discussed and drafted. Prodoc signed (actual/planned, yes/no and date):No. New approval. Missions undertaken (actual/planned):0/0. Project document not signed. TOR for consultants/subcontracts completed (actual/planned): 0/0: Project document not signed Contract/PO/MOA agreements signed: 0/0: Project document not signed First disbursement date (actual/planned): No. Project document not signed.Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | Project document signed in February 2017. Meetings held with NOU on the workplan and technology procurement processes. NOU requested UNDP to support the Government with the procurement of the new technologies. Discussion on specifications is ongoing. Project is set up financially in the system. |  |  | Investment
FIN | UNEP | Preparation of country programme | Individual | ASP | KUW | SEV | 30 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-01-01 | 2001-06-01 |  | 2002-07-01 | 2003-07-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Institutional strengthening and capacity building | Individual | ASP | KUW | SEV | 37 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-03-01 | 2005-08-01 |  | 2006-01-01 | 2008-12-01 | 121520 | 0 | 121520 | 121520 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase II) | Individual | ASP | KUW | SEV | 47 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2007-05-01 | 2007-12-01 |  | 2007-12-01 | 2008-12-01 | 105320 | 0 | 105320 | 105320 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | ASP | KUW | SEV | 53 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-08-01 | 2009-11-01 |  | 2009-11-01 | 2010-12-01 | 105320 | 0 | 105320 | 105320 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | ASP | KUW | SEV | 59 | INS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-09-01 | 2011-11-01 |  | 2012-12-01 | 2013-12-01 | 57048 | 48272 | 105320 | 105320 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of institutional strengthening project (phase V: 1/2013-12/2014) | Individual | ASP | KUW | SEV | 68 | INS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2014-11-01 | 2014-11-01 | 2017-12-01 |  |  | 105320 | 0 | 105320 | 48663.02 | 46.2% | 56656.98 | 56656.98 | 5665.698 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Implementation of phase complete and new cycle approved in Apr-16. Legal arrangements (actual/planned): closed Initial stages of project implementation (actual/planned): Waiting NOU to submit final TR & ER reports Intermediate goals achieved (actual/planned): project complete and data reporting submitted on time Project completion and follow up: ISP completed, updated financial & terminal report missing First disbursement date (actual/planned): Nov-14 All funds disbursed (yes/no): Yes. Project ongoing & delayed Any delay? (yes/no): COM, overall delay faced as justified by country in terminal report & awaiting financial report to close project financially If Yes, will delay have impact on project completion date (yes/no): NO Any ongoing problems (yes/no): No | Project is completed
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | ASP | KUW | SEV | 75 | TAS | 27 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-07-01 | 2016-12-01 | 2017-07-01 |  |  | 70000 | 0 | 70000 | 2218.27 | 3.169% | 67781.73 | 50000 | 6778.173 | 9100 | 0 | 288.3751 | 8811.6249 | 6500 | Brief progress report (actual/planned): TORs developed for the work under the survey, consultation meeting with NOU is arranged in margins of network meeting, detailed work-plan and sample documentation and forms sent to country for review and clearance, training for national expert arranged through regional workshop organized in back-to-back with the network meeting. Consultation meetings are organized with country and local experts to orient about the survey requirements. Another consultation meeting orgnized (for both surveys of Bahrain and Kuwait) • Legal arrangements(actual/planned): Legal instrument signed • Initial stages of project implementation(actual/planned): Started and all preparatory work arranged by UNEP • Intermediate goals achieved (actual/planned): Start of data collection delayed • Project completion and follow up: Planned by mid of 2017 • First disbursement date (actual/planned): Paid during 4th quarter of 2016 • All funds disbursed (yes/no): No • Any delay?(yes/no): Yes • If Yes, reasons for delay & action plan to resolve: Due to delay in forming the local survey team • If Yes, will delay have impact on project completion date (yes/no): Yes, completion planned by mid of 2017 instead of end of 2016 | Brief progress report (actual/planned): - National survey teams formed at end of 2016 and started collecting data - Data collectionand validation to be completed by end of April 2017 - Final report under preparation and will be submitted to ExCom-79
ONG | UNIDO | Survey of ODS alternatives at the national level | Individual | ASP | KUW | SEV | 75 | TAS | 30 | A | I |  | 0 | 0 |  |  | 2015-11-01 |  | 2017-12-01 | 2017-12-18 |  |  | 50000 | 0 | 50000 | 0 | 0% | 50000 | 0 | 40000 | 4500 | 0 | 0 | 4500 | 0 | Coordination meeting with UNEP held in November 2016. Waiting for the approval of the NOU (EPA). Milestones achieved: Milestone 1: Coordination meeting - Yes Milestone 2: Recruitment of consultants-No Milestone 3: Survey conducted - No Milestone 4: Survey report submitted - No Actions towards next goals: Waiting for the approval of the NOU(EPA). Was there any delay during the reporting year? Yes, delay in approval by the NOU. Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | Contract to EPA for recruitment of consultants issued in March 2017. Milestones achieved: Milestone 1: Recruitment of consultants-Yes Milestone 2: Survey conducted - No Milestone 3: Survey report submitted - No Actions towards next goals: Waiting for the survey report. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | NON-INV
ONG | UNEP | Extension of institutional strengthening project (phase VI: 5/2016-4/2018) | Individual | ASP | KUW | SEV | 76 | INS | 31 | A | I |  | 0 |  | 0 |  | 2016-05-01 |  | 2018-04-01 | 2018-04-01 |  |  | 134810 | 0 | 134810 | 0 | 0% | 134810 | 0 | 13481 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Newly approved. Legal arrangements (actual/planned): still under process due to awaiting country input Initial stages of project implementation (actual/planned): implementation on going; Intermediate goals achieved (actual/planned): project on going; data reporting submitted on time; ozone day celebration done; NOU continues supervising other MP projects Project completion and follow up: on going First disbursement date (actual/planned): still awaiting legal instrument All funds disbursed (yes/no): NO Project ongoing & delayed Any delay? (yes/no): ONG If Yes, will delay have impact on project completion date (yes/no): NO Any ongoing problems (yes/no): No | Brief progress report (actual/planned): Implementation on going Legal arrangements (actual/planned): SSFA signed Initial stages of project implementation (actual/planned): implementation on going; Intermediate goals achieved (actual/planned): project on going; NOU continues supervising other MP projects Project completion and follow up: on going First disbursement date (actual/planned): Mar-17 All funds disbursed (yes/no): NO Project ongoing & delayed Any delay? (yes/no): ONG If Yes, will delay have impact on project completion date (yes/no): NO Any ongoing problems (yes/no): No
CLO | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | ASP | KYR | FOA | 58 | PRP | 22 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-07-01 | 2010-01-01 | 2010-07-01 |  |  | 2010-12-01 | 30000 | -24996 | 5004 | 5004 | 100% | 0 | 0 | 0 | 2250 | -1874.7 | 375.3 | 0 | 0 | After technical visit in early 2010, and discussions with foam company Winterlux, the company decided to switch to non-HCFC technology itself. The further work on the formulation of investment project proposal was discontinued. MLF Secretariat was informe |  | 2009 |  | Investment
FIN | UNDP | Technical assistance project to install alternatives and phase-out methyl bromide | One-off-Phaseout | ASP | KYR | FUM | 41 | TAS | 08 | N | I | MeBr | 14.2 | 14.2 | 0 | 0 | 2003-12-01 | 2004-07-01 | 2008-12-01 |  | 2007-12-01 | 2009-08-01 | 300000 | -407 | 299593 | 299593 | 100% | 0 | 0 | 0 | 22500 | -30.53 | 22469.475 | -0.005 | 0 | Completed in 2007.Financially completed in 2009. |  | 2003 |  | Non-Investment
FIN | UNIDO | Halon phase-out programme | Individual | EUR | KYR | HAL | 48 | TAS | 12 | A | I | HAL | 2.4 | 2.4 |  |  | 2006-04-01 | 2006-12-01 | 2009-04-01 |  | 2008-12-01 | 2012-05-01 | 50000 | -3838 | 46162 | 46161.89 | 100% | 0.11 | 0 |  | 4500 | -345 | 4155 | 0 | 0 | FIN |  |  |  | INV
FIN | UNDP | Project preparation of a terminal phase-out management plan | Individual | ASP | KYR | PHA | 47 | PRP | 11 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-03-01 | 2006-12-01 |  | 2007-04-01 | 2011-11-01 | 30000 | -908.45 | 29091.55 | 29092 | 100% | -0.45 | 0 | 0 | 2250 | -68.13 | 2181.9001 | -0.03005 | 0 | Completed in 2007. |  | 2005 |  | Investment
FIN | UNDP | Terminal CFC phase-out management plan (first tranche) | Multi-Year | ASP | KYR | PHA | 50 | INV | 14 | N | I | CFC | 1 | 1 | 0 | 0 | 2006-11-01 | 2007-10-01 | 2009-11-01 |  | 2008-12-01 | 2011-01-01 | 194000 | 0 | 194000 | 194000 | 100% | 0 | 0 | 0 | 14550 | 0 | 14550 | 0 | 0 | Completed in 2008. Financially completed in 2011. |  | 2006 |  | Investment
FIN | UNEP | Terminal CFC phase-out management plan (first tranche) | Multi-Year | EUR | KYR | PHA | 50 | TAS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-08-01 | 2007-11-01 |  | 2008-07-01 | 2009-07-01 | 142600 | 0 | 142600 | 142600 | 100% | 0 | 0 |  | 18538 | 0 | 18538 | 0 | 0
FIN | UNDP | Terminal CFC phase-out management plan (second tranche) | Multi-year | ASP | KYR | PHA | 55 | INV | 18 | N | I | CFC | 1 | 1 | 0 | 0 | 2008-07-01 | 2009-05-01 | 2010-07-01 |  | 2010-12-01 | 2011-01-01 | 63000 | 0 | 63000 | 63000 | 100% | 0 | 0 | 0 | 4725 | 0 | 4725 | 0 | 0 | Completed in 2010. Financially completed in 2011. |  | 2008 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | ASP | KYR | PHA | 55 | PRP | 20 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2010-12-01 | 2011-09-01 | 85000 | -739.48 | 84260.52 | 84261 | 100% | -0.48 | 0 | 0 | 6375 | -55.46 | 6319.575 | -0.035 | 0 | Completed in 2010. Financially completed in 2011. |  | 2008 |  | Investment
FIN | UNEP | Terminal CFC phase-out management plan (second tranche) | Multi-Year | EUR | KYR | PHA | 55 | TAS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-11-01 | 2009-07-01 |  | 2011-02-01 | 2011-12-01 | 65100 | 0 | 65100 | 65100 | 100% | 0 | 0 |  | 8463 | 0 | 8463 | 0 | 0
FIN | UNEP | TPMP verification report | Individual | EUR | KYR | PHA | 55 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-12-01 | 2009-07-01 |  | 2010-12-01 | 2011-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0
FIN | UNDP | Terminal CFC phase-out management plan (third tranche) | Multi-year | ASP | KYR | PHA | 60 | INV | 23 | N | I | CFC | 5 | 5 | 0 | 0 | 2010-04-01 | 2010-07-01 | 2011-04-01 |  | 2010-12-01 | 2011-01-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 4500 | 0 | 4500 | 0 | 0 | Completed in 2010. Financially completed in 2011. |  | 2010 |  | Investment
FIN | UNEP | Terminal CFC phase-out management plan (third tranche) | Multi-Year | EUR | KYR | PHA | 60 | TAS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-04-01 | 2011-04-01 |  | 2011-04-01 | 2011-07-01 | 25300 | 0 | 25300 | 25300 | 100% | 0 | 0 |  | 3289 | 0 | 3289 | 0 | 0
FIN | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | KYR | PHA | 63 | INV | 26 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-08-01 | 2014-12-01 |  | 2013-12-01 | 2015-02-01 | 47520 | 0 | 47520 | 47520 | 100% | 0 | 0 | 0 | 4277 | 0 | 4277 | 0 | 0 | Financially completed in 2015. | Workplan for 2014 formulated and endorsed by NOU. Funds for 2014 plan allocated. Request for HPMP Stage I Tranche II submitted jointly with UNEP to the 72nd ExCom. HPMP Stage II PRP request was submitted to the 72nd ExCom and received recommendations from | 2011 |  | Investment
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | EUR | KYR | PHA | 63 | TAS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-11-01 | 2014-12-01 |  | 2014-05-01 | 2016-03-01 | 31680 | 0 | 31680 | 31680 | 100% | 0 | 0 |  | 4118 | 0 | 4118 | 0 | 0 | Project financially completed. | Project financially completed.
COM | UNDP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | ASP | KYR | PHA | 72 | INV | 29 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 | 2015-02-01 | 2016-05-01 |  | 2015-10-01 |  | 5280 | 0 | 5280 | 5272 | 99.85% | 8 | 0 | 6.8 | 475 | 0 | 474.2803 | 0.7197 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2015. |  |  |  | Investment
COM | UNDP | Preparation of a HCFC phase-out management plan (stage II) | Individual | ASP | KYR | PHA | 72 | PRP | 30 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 | 2014-11-01 | 2016-05-01 |  | 2015-12-01 |  | 20000 | 0 | 20000 | 19929 | 99.64% | 71 | 0 | 60.35 | 1400 | 0 | 1395.03 | 4.97 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2015. |  |  |  | Investment
FIN | UNEP | Preparation of a HCFC phase-out management plan (stage II) | Individual | EUR | KYR | PHA | 72 | PRP | 31 | A | I |  | 0 |  | 0 |  | 2014-05-01 | 2014-11-01 | 2015-05-01 |  | 2015-05-01 | 2016-03-01 | 10000 | -447 | 9553 | 9552.68 | 100% | 0.32 | 0 |  | 1300 | -58.11 | 1241.8484 | 0.0416 | 0 | Project financially completed. | Project financially completed.
FIN | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | EUR | KYR | PHA | 72 | TAS | 32 | A | I | HCFC-22 | 0.2 |  | 0 |  | 2014-05-01 | 2014-07-01 | 2015-05-01 |  | 2014-12-01 | 2016-03-01 | 3520 | 0 | 3520 | 3520 | 100% | 0 | 0 |  | 458 | 0 | 458 | 0 | 0 | Project financially completed. | Project financially completed.
ONG | UNDP | HCFC phase-out management plan (stage II, first tranche) | Multi-year | ASP | KYR | PHA | 74 | INV | 34 | N | I | HCFC | 1.3 | 0 | 0 | 0 | 2015-05-01 | 2016-01-01 | 2018-05-01 | 2017-05-01 |  |  | 170000 | 0 | 170000 | 35209.26 | 20.71% | 134790.74 | 50370 | 53916.296 | 11900 | 0 | 2464.6482 | 9435.3518 | 3525.9 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): One (1) mission fielded in 2016 to discuss acceleration of the workplans in light of the Customs Union's pressure on timely implemenattion of the HCFC programme. National expert recruited, and R&R equipment specifications developed for tender. Two (2) rounds of ITBs were announced in 2016 for R&R equipment and tools, and one was successful. Sub-contract with selected supplier was arranged, and equipment/tools expected to arrive early 2017. Prodoc signed (actual/planned, yes/no and date):1/1. Yes. Agreement has been signed earlier Missions undertaken (actual/planned):1/1: Mission was fielded in 2016. TOR for consultants/subcontracts completed (actual/planned): 1/1: National expert was recruited Contract/PO/MOA agreements signed: 1/1: R&R equipment supply sub-contract was signed after succesful tendering First disbursement date (actual/planned): 42370Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:Initial R&R equipment tender was not successful. A new round of tender was announced in October 2016 and was successful. | R&R equipment and tools have arrived to Kyrgyzstan, and are awaiting Customs clearance | 2015 |  | Investment
ONG | UNEP | HCFC phase-out management plan (stage II, first tranche) | Multi-Year | EUR | KYR | PHA | 74 | TAS | 35 | A | I |  | 1.1 |  | 0 |  | 2015-05-01 | 2016-02-01 | 2018-05-01 | 2018-05-01 |  |  | 150000 | 0 | 150000 | 35218 | 23.48% | 114782 | 114782 | 11478.2 | 19500 | 0 | 4578.34 | 14921.66 | 14921.66 | Brief progress report (actual/planned): A series of ten laws, resolutions and instructions as well as the inter-state standard for refrigeration systems and heat pumps - safety requirements and environment protection were developed and partly adopted. Workshops on the final HCFC phase-out for RAC technicians took place in Bishkek / 10-11 March 2013, in Cholpon-Ata / 20-21 May 2016, in Osh / 20-21 December 2016 and in Bishkek / 26-27 December 2016. In total, 165 RAC technicians participated. Coordination Committee meeting and HPMP stage II workshop took place in Bishkek on 25 March 2016. Workshop on HCFC alternatives in the RAC sector took place in Osh / 23-24 November 2016 with 45 participants. The 10th National Congress of the RAC association Ecoholod took place in Cholpon-Ata / 14-15 May 2016 with 42 participants. A series of five training workshops for RAC technicians was conducted in Bishkek / 10-11 March 2016, in Cholpon-Ata / 20-21 May 2016, in Osh / 23-24 November 2016, in Bishkek / 20-21 December 2016 and in Osh / 26-27 December 2016. In total, 210 technicians were trained. In 2016, 123 kg R12 1420 kg R22 was recovered - 22 kg R12 and 69 kg R22 was reused. In addition, 319 students of higher educational institutions were trained by the Kyrgyz State Technical University and Ecoholod. A manual on the safe use of propane, several posters and an information disk for RAC technicians was produced. A series of eight training workshops for customs officers, police and inspectors took place in Leninskoe on 28 September 2016, in Osh on 25 October, 8 December, 9 December and 12 December 2016, in Bishkek on 29 November and 6 December 2016, and in Novo-Pokrovka on 23 December 2016. In total, 285 participants were trained. NOU Kyrgyzstan also up-dated four thematic websites, published 12 information materials including leaflets and posters, ensured public outreach through printed media, radio and TV, arranged the bidding for refrigerant identifiers. The Coordination Committee met on 28 December 2016 and reviewed action plan for HCFC phase-out by 2020. Legal arrangements(actual/planned): SSFA was signed by both parties in November 2015. First mission (actual/planned): N.a. TOR completed(actual/planned): N.a. First disbursement date (actual/planned): February 2016 All funds disbursed (yes/no): No Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: N.a. If Yes, will delay have impact on project completion date (yes/no): N.a. Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N.a. | Brief progress report (actual/planned): NOU Kyrgyzstan has been working on the guide on the use of propane technologies for technicians and the guide for customs officers. The Kyrgyz RAC association has been completing the certification of 23 technicians. Legal arrangements(actual/planned): SSFA was signed by both parties in November 2015. First mission (actual/planned): N.a. TOR completed(actual/planned): N.a. First disbursement date (actual/planned): February 2016 All funds disbursed (yes/no): No Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: N.a. If Yes, will delay have impact on project completion date (yes/no): N.a. Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N.a.
ONG | UNDP | Verification report for stage I of HCFC phase-out management plan | Individual | ASP | KYR | PHA | 77 | TAS | 38 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2016-12-01 |  | 2018-03-01 | 2017-03-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 12000 | 2700 | 0 | 0 | 2700 | 0 | Newly Approved | DOA was prepared and sent to UNDP and NOU-Kyrgzystan in February 2017. Once the project document is signed with the Government, the verificaiton process will start. UNDP shared similar TORs with NOU-Kyrgyzstan to facilitate local works. | 2016 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: monitoring the activities in the RMP | RMP-Component | ASP | KYR | REF | 37 | TAS | 01 | A | I | CFC | 1.8 | 1.8 | 0 | 0 | 2002-07-01 | 2003-02-01 | 2007-08-01 |  | 2006-12-01 | 2008-03-01 | 16500 | -1 | 16499 | 16499 | 100% | 0 | 0 | 0 | 2145 | -0.13 | 2144.87 | 0 | 0 | Completed in 2006. Financially completed in 2008. |  | 2002 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: awareness and incentive programme | RMP-Component | ASP | KYR | REF | 37 | TAS | 02 | A | I | CFC | 20.6 | 20.6 | 0 | 0 | 2002-07-01 | 2003-02-01 | 2007-07-01 |  | 2007-12-01 | 2011-12-01 | 187242 | -3510.54 | 183731.46 | 183731 | 100% | 0.46 | 0 | 0 | 24341.46 | -456.37 | 23885.03 | 0.06 | 0 | Completed in 2007. |  | 2002 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: national programme for refrigerant recovery and recycling | RMP-Component | ASP | KYR | REF | 37 | TAS | 04 | A | I | CFC | 20.4 | 20.4 | 0 | 0 | 2002-07-01 | 2002-12-01 | 2005-08-01 |  | 2003-10-01 | 2007-03-01 | 185175 | -1007 | 184168 | 184168 | 100% | 0 | 0 | 0 | 24072.75 | -130.91 | 23941.8386 | 0.0014 | 0 | Completed in 2003. Financially completed in 2007. |  | 2002 |  | Investment
FIN | UNEP | Implementation of the RMP: training for customs excise and personnel involved in the monitoring of ODS/equipment | Individual | EUR | KYR | REF | 37 | TRA | 03 | A | I | CFC | 8.3 | 8.3 | 0 | 0 | 2002-07-01 | 2004-01-01 | 2004-08-01 |  | 2005-06-01 | 2009-06-01 | 74910 | 0 | 74910 | 74910 | 100% | 0 | 0 |  | 9738 | 0 | 9738 | 0 | 0
FIN | UNEP | Implementation of the RMP: training of refrigeration technicians | Individual | EUR | KYR | REF | 37 | TRA | 06 | A | I | CFC | 10.8 | 10.8 | 0 | 0 | 2002-07-01 | 2004-01-01 | 2003-08-01 |  | 2005-08-01 | 2009-08-01 | 97900 | 0 | 97900 | 97900 | 100% | 0 | 0 |  | 12727 | 0 | 12727 | 0 | 0
CLO | UNDP | Preparation for HCFC phase-out investment activities (refrigeration sector) | Individual | ASP | KYR | REF | 57 | PRP | 21 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-01-01 | 2010-03-01 |  |  | 2010-12-01 | 30000 | -23994 | 6006 | 6006 | 100% | 0 | 0 | 0 | 2250 | -1799.55 | 450.45 | 0 | 0 | After technical visit in early 2010, it was recommended to prepare a stand-alone component on technical assistance to HCFC equipment assemblers as a part of HPMP servicing sector. The further work on the formulation of investment project proposal was disc |  | 2009 |  | Investment
FIN | UNEP | Country programme | Individual | EUR | KYR | SEV | 37 | CPG | 07 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 |  | 2002-07-01 |  | 2002-07-01 | 2002-07-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 |  | 0
FIN | UNEP | Establishment of the Ozone Unit | Individual | EUR | KYR | SEV | 37 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2002-10-01 | 2005-08-01 |  | 2004-12-01 | 2011-03-01 | 133650 | 0 | 133650 | 133650 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase II) | Individual | EUR | KYR | SEV | 44 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-04-01 | 2006-12-01 |  | 2006-12-01 | 2007-01-01 | 115830 | 0 | 115830 | 115830 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | EUR | KYR | SEV | 50 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-01-01 | 2008-11-01 |  | 2008-11-01 | 2009-11-01 | 115830 | 0 | 115830 | 115830 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | EUR | KYR | SEV | 55 | INS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-11-01 | 2009-01-01 |  | 2010-07-01 | 2011-07-01 | 115830 | 0 | 115830 | 115830 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | EUR | KYR | SEV | 61 | INS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-02-01 | 2012-12-01 |  | 2013-12-01 | 2014-12-01 | 115830 | 0 | 115830 | 115830 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VI: 1/2013-12/2014) | Individual | EUR | KYR | SEV | 68 | INS | 28 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-02-01 | 2014-12-01 |  | 2014-12-01 | 2016-03-01 | 115830 | 0 | 115830 | 115830 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
ONG | UNEP | Extension of the institutional strengthening project (phase VII: 1/2015-12/2016) | Individual | EUR | KYR | SEV | 73 | INS | 33 | A | I |  | 0 |  | 0 |  | 2014-11-01 | 2015-03-01 | 2016-12-01 | 2017-03-01 |  |  | 115830 | 0 | 115830 | 115830 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Approval of the order on HCFC quotas and procedures for quota distribution in February 2016, monitoring ODS trade through the licensing system, quota allocation and iPIC, analysis of discrepancies of reported trade data for 2014 jointly with the Ozone Secretariat, Coordination Committee meetings in March and December 2016, National Congress of the RAC association «Ecoholod», publication of guidelines for RAC specialists, leaflets, calendars and CDs, innovative awareness and information activities ( leaflets, posters, a calendar, information CD for RAC technicians, outreach through radio, TV and newpapers, up-dating websites, educational festival, media for improved reporting on environment and natural resources etc.), implementation of HPMP, ODS alternatives survey (MLF) and the HFC inventory (CCAC), participation in the ECA customs cooperation and network meeting in Ashgabat, 24-27 May 2016 as well as Montreal Protocol meetings, puchase of equipment for the training centers and vocational schools and refrigerant identifiers. Legal arrangements(actual/planned): SSFA signed in January of 2015. Initial stages of project implementation(actual/planned): N.a. Intermediate goals achieved (actual/planned): N.a. Project completion and follow up: N.a. First disbursement date (actual/planned): March 2015 All funds disbursed (yes/no): No Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: N.a. If Yes, will delay have impact on project completion date (yes/no): N.a. Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N.a. | Brief progress report (actual/planned): NOU Kyrgyzstan has been preparing several project related reports required by different government authorities and the implementing agencies UNDP and UN Environment, working on the production of awareness materials (posters, stickers etc.) and finalized the ODS alternatives survey report (MLF) and HFC inventory report (CCAC). Legal arrangements(actual/planned): SSFA signed in January of 2015. Initial stages of project implementation(actual/planned): N.a. Intermediate goals achieved (actual/planned): N.a. Project completion and follow up: N.a. First disbursement date (actual/planned): March 2015 All funds disbursed (yes/no): No Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: N.a. If Yes, will delay have impact on project completion date (yes/no): N.a. Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N.a.
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | EUR | KYR | SEV | 74 | TAS | 36 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-05-01 | 2016-05-01 | 2017-03-01 |  |  | 20000 | 0 | 20000 | 8500 | 42.5% | 11500 | 11500 | 1150 | 2600 | 0 | 1105 | 1495 | 1495 | Brief progress report (actual/planned): In preparation of the ODS alternatives survey, official letters were sent to importers of refrigeration equipment and refrigerants (ODS, HFC, blends, natural) in January and February 2016, requesting them to report relevant imports and use of any type of refrigerant. In March 2016, data on import and export of ODS alternatives and products containing them were collected from the State Customs Service as well as the register of importers of ODS alternatives from the Ministry of Economy and Industry. The actual project activities started only in March 2016, due to the delay in establishing the SSFA and releasing the first disbursement. The first stakeholder consultation took place in Bishkek on 25 March 2016 with the participation of leading technicians from the refrigeration and foam sectors, and representatives of the Ministry of Economy and Industry, State Customs Service, State Agency on Environment Protection and Forestry, State Inspectorate for Ecological and Technical Safety. The following was elaborated during the consultation: 1) work plan on carrying out the survey of the ODS alternatives consumption during the period 2012-2015, 2) list of main and auxiliary working groups, 3) regional action plans including the compilation of tables and survey questionnaires, 4) list of enterprises and individual entrepreneurs which use ODS alternatives. The Coordinating Committee on the implementation of the Country Program and the workshop on the terminal HCFC phase-out and review of ODS alternatives consumption took place in Bishkek in March 2016. Another workshop on terminal HCFC phase-out and review of ODS alternatives took place in Cholpon-Ata in May 2016. Sector-specific data on ODS alternatives have been collected in all regions. The collected data analysed in the second half of 2016. Legal arrangements (actual/planned): SSFA was signed by both parties in March 2016. Initial stages of project implementation (actual/planned): N.a. Intermediate goals achieved (actual/planned): N.a. Project completion and follow up: N.a. First disbursement date (actual/planned): May 2016 All funds disbursed (yes/no): No Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: Delays due to slow disbursement. If Yes, will delay have impact on project completion date (yes/no): Yes Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N.a. | Brief progress report (actual/planned): Data analysis was continued, a stakeholder consultation conducted, additional data collected to close data gaps and the draft report prepared in February 2017. Legal arrangements (actual/planned): SSFA was signed by both parties in March 2016. Initial stages of project implementation (actual/planned): N.a. Intermediate goals achieved (actual/planned): N.a. Project completion and follow up: N.a. First disbursement date (actual/planned): May 2016 All funds disbursed (yes/no): No Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: Delays due to slow disbursement. If Yes, will delay have impact on project completion date (yes/no): Yes Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N.a.
ONG | UNEP | Extension of the institutional strengthening project (phase VIII: 1/2017-12/2018) | Individual | EUR | KYR | SEV | 77 | INS | 37 | A | I |  | 0 |  | 0 |  | 2016-12-01 |  | 2018-12-01 | 2018-12-01 |  |  | 148262 | 0 | 148262 | 0 | 0% | 148262 | 0 | 14826.2 | 0 | 0 | 0 | 0 | 0 | Project newly approved by ExCom 77. | Brief progress report (actual/planned): Project newly approved by ExCom 77. Legal arrangements(actual/planned): SSFA with the Ministry of Environment submitted for internal clearance and signature in December 2016. Initial stages of project implementation(actual/planned): N.a. Intermediate goals achieved (actual/planned): N.a. Project completion and follow up: N.a. First disbursement date (actual/planned): Pending All funds disbursed (yes/no): No Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: The time required for programming of project funds and the release of payments. If Yes, will delay have impact on project completion date (yes/no): No Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N.a.
FIN | UNDP | Low-CFC foam training and demonstration programme in Latin America | Individual | LAC | LAC | FOA | 06 | TRA | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-11-01 | 1994-02-01 |  | 1993-12-01 | 1997-12-01 | 52500 | 1312 | 53812 | 53812 | 100% | 0 | 0 | 0 | 6825 | 170.56 | 6995.56 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Methyl bromide data collection for Latin America and the Caribbean | Individual | LAC | LAC | FUM | 17 | TAS | 14 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-08-01 | 1996-01-01 |  | 1996-03-01 | 1998-12-01 | 57700 | 0 | 57700 | 57700 | 100% | 0 | 0 | 0 | 7501 | 0 | 7501 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Non-Investment
FIN | UNEP | Regional workshop on methyl bromide for Latin America and the Caribbean | Individual | LAC | LAC | FUM | 17 | TRA | 13 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-10-01 | 1996-01-01 |  | 1995-11-01 | 1999-04-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 | 0 |  | 15600 | 0 | 15600 | 0 | 0
CLO | UNIDO | Preparation of a demonstration project for broccoli, cucurbits, tobacco, seed beds, grain fumigation in El Salvador, Honduras and Nicaragua | Individual | LAC | LAC | FUM | 27 | PRP | 31 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-06-01 | 1999-12-01 |  |  | 2001-12-01 | 40000 | -29186 | 10814 | 10814 | 100% | 0 | 0 |  | 5200 | -3796 | 1404 | 0 | 0 | CLO
FIN | UNEP | Regional training workshop on policy development | Individual | LAC | LAC | FUM | 27 | TRA | 30 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 2000-03-01 |  | 2000-04-01 | 2001-12-01 | 130000 | 0 | 130000 | 130000 | 100% | 0 | 0 |  | 16900 | 0 | 16900 | 0 | 0
FIN | UNEP | Regional training of trainer courses for extension workers | Individual | LAC | LAC | FUM | 27 | TRA | 32 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 2001-10-01 |  | 2001-12-01 | 2003-12-01 | 80000 | -4000 | 76000 | 76000 | 100% | 0 | 0 |  | 10400 | -520 | 9880 | 0 | 0
FIN | Spain | Policy assistance to support the methyl bromide phase-out with special focus in Guatemala and Honduras | Individual | LAC | LAC | FUM | 47 | TAS | 37 | A | I | MBR | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-02-01 | 2007-12-01 |  | 2007-07-01 | 2008-06-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 | 0 | 10400 | 0 |  | 10400
FIN | Spain | Technical assistance to introduce chemical alternatives in countries which have rescheduled methyl bromide phase out plan (Argentina and Uruguay) | Individual | LAC | LAC | FUM | 54 | TAS | 40 | A | I | MBR | 0 |  | 0 |  | 2008-04-01 | 2008-07-01 | 2010-03-01 |  | 2015-03-01 | 2015-09-01 | 147400 | -221 | 147179 | 147179 | 100% | 0 | 0 | 0 | 19162 | -29 | 19133.27 | -0.27 | 0 | Project completed in March 2015 |  |  |  | Investment
FIN | UNDP | Training and demonstration programmes in halon reduction in Latin America | Individual | LAC | LAC | HAL | 06 | TRA | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-11-01 | 1994-02-01 |  | 1994-06-01 | 1997-12-01 | 60000 | -15158 | 44842 | 44842 | 100% | 0 | 0 | 0 | 7800 | -1970.54 | 5829.46 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | USA | Follow-up to regional halon-1211 workshop |  | LAC | LAC | HAL | 08 | TRA | 06 | A | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1993-10-01 |  | 1993-10-01 | 1993-10-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1992
FIN | Canada | Development of a regional halon bank management plan for the English-speaking Caribbean (Bahamas, Barbados, Grenada, Guyana, Jamaica, and Trinidad and Tobago) | Halon Banking | LAC | LAC | HAL | 26 | TAS | 28 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-10-01 | 2000-06-01 |  | 2005-12-01 | 2006-03-01 | 177410 | 0 | 177410 | 177410 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Establishment of halon clearing house in Trinidad and promotional brochure completed in 2005. All 6 countries finished their halon surveys. All project activities completed. Last payment to UNEP to reimburse University of West Indies for halon clearing |  | 1998 |  | Non-Inv.
CLO | UNEP | Development of regional halon banking management plan for the Latin American region (Dominican Republic, El Salvador, Chile, Colombia and Peru) | Individual | LAC | LAC | HAL | 29 | PRP | 34 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 |  | 2001-06-01 |  |  | 2002-07-01 | 174000 | -174000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 22620 | -22620 |  | 0
FIN | UNDP | Training and demonstration programme in CFC recycling in MAC in Latin America | RMP-Component | LAC | LAC | REF | 06 | TRA | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1995-11-01 | 1994-02-01 |  | 1995-11-01 | 1997-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Training and demonstration programme in commercial/industrial refrigeration in Latin America | Individual | LAC | LAC | REF | 06 | TRA | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-07-01 | 1993-02-01 |  | 1992-09-01 | 1997-12-01 | 40000 | -16953 | 23047 | 23047 | 100% | 0 | 0 | 0 | 5200 | -2204 | 2996 | 0 | 0 | Completed in 1992. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | USA | Project preparation for low consuming countries |  | LAC | LAC | REF | 13 | PRP | 09 | A | I |  | 0 |  | 0 |  | 1994-07-01 |  | 1995-07-01 |  | 1995-07-01 | 1995-07-01 | 65000 | 0 | 65000 | 65000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | UNEP | Regional workshop on non-CFC technologies for domestic refrigerator manufacturing industries | Individual | LAC | LAC | REF | 15 | TRA | 10 | A | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-02-01 | 1995-05-01 |  | 1995-05-01 | 1995-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0
FIN | UNEP | Regional workshop on technology assessment (in refrigeration) | Individual | LAC | LAC | REF | 16 | TAS | 12 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1998-01-01 | 1996-03-01 |  | 1999-05-01 | 2000-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 |  |  |  | 1999-05-01
FIN | UNDP | Regional Latin America demonstration project in recovery of ODS in MACs: Phase I (Argentina, Colombia) | RMP-Component | LAC | LAC | REF | 18 | TAS | 15 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-12-01 | 1999-05-01 | 207000 | 0 | 207000 | 207000 | 100% | 0 | 0 | 0 | 26910 | 0 | 26910 | 0 | 0 | Completed in 1996. Financially completed in 1999. |  | 1995 |  | Non-Investment
FIN | USA | Project preparation in MAC and refrigerated transport in Central American and the Caribbean |  | LAC | LAC | REF | 19 | PRP | 16 | A | I |  | 0 |  | 0 |  | 1996-05-01 | 1997-01-01 | 1997-05-01 |  | 1998-02-01 | 1999-06-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Final report submitted in June 1998. |  | 1995 | 1997-05-01
FIN | USA | Mobile air conditioning (MAC) and refrigerated transport (RT) in Central America: El Salvador, Honduras, Nicaragua and Panama |  | LAC | LAC | REF | 24 | DEM | 27 | A | I |  | 0 |  | 0 |  | 1998-03-01 | 1998-05-01 | 1999-04-01 |  | 1999-06-01 | 2000-07-01 | 569000 | 0 | 569000 | 569000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Training and equipment were provided in El Salvador, Honduras, Nicaragua and Panama in April - May 1999. Final report will be submitted in June 2000.
FIN | UNDP | Demonstration project for integrated management of the centrifugal chiller sub-sector in the Caribbean, focusing on application of energy-efficient CFC-free technologies for replacement of CFC-based chillers | Individual | LAC | LAC | REF | 47 | DEM | 36 | N | I | CFC | 0 | 0 | 0 | 0 | 2005-11-01 |  | 2008-12-01 |  | 2010-12-01 | 2013-02-01 | 1000000 | -1000000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 75000 | -75000 | 0 | 0 | 0 | Financially completed in 2013. |  | 2005 |  | Investment
FIN | UNEP | Regional workshop for Latin America and the Caribbean | Individual | LAC | LAC | SEV | 04 | TRA | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-08-01 | 1992-06-01 |  | 1992-05-01 | 1992-12-01 | 246000 | 0 | 246000 | 246000 | 100% | 0 | 0 |  | 31980 | 0 | 31980 | 0 | 0
FIN | UNEP | Support to regional network for OzonAction/ODS focal points | Individual | LAC | LAC | SEV | 09 | TAS | 07 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-06-01 | 1994-03-01 |  | 1994-03-01 | 2000-12-01 | 130000 | -9000 | 121000 | 121000 | 100% | 0 | 0 |  | 16900 | -1170 | 15730 | 0 | 0
FIN | UNEP | ODS officers network for Latin America and the Caribbean (1994) | Individual | LAC | LAC | SEV | 12 | TAS | 08 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-11-01 | 1995-03-01 |  | 1995-03-01 | 2000-12-01 | 224000 | -14500 | 209500 | 209500 | 100% | 0 | 0 |  | 29120 | -1885 | 27235 | 0 | 0
FIN | UNEP | ODS officers network for Latin America and the Caribbean (1995) | Individual | LAC | LAC | SEV | 16 | TAS | 11 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-05-01 | 1996-03-01 |  | 1995-08-01 | 2000-12-01 | 299000 | 0 | 299000 | 299000 | 100% | 0 | 0 |  | 38870 | 0 | 38870 | 0 | 0
FIN | UNEP | Networking and Training in Latin American Region Network (including English-speaking Caribbean) | Individual | LAC | LAC | SEV | 19 | TAS | 23 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-06-01 | 1997-05-01 |  | 1996-12-01 | 1999-12-01 | 299000 | -57167 | 241833 | 241833 | 100% | 0 | 0 |  | 38870 | -7431.71 | 31438.29 | 0 | 0
FIN | UNEP | Regional workshop on monitoring and control of ODS consumption for Latin America and Caribbean | Individual | LAC | LAC | SEV | 19 | TRA | 17 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-07-01 | 1997-05-01 |  | 1998-04-01 | 1999-04-01 | 105000 | 0 | 105000 | 105000 | 100% | 0 | 0 |  | 13650 | 0 | 13650 | 0 | 0
FIN | UNEP | Latin American Region Network (1997) | Individual | LAC | LAC | SEV | 21 | TAS | 24 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1999-12-01 | 380000 | -38093 | 341907 | 341907 | 100% | 0 | 0 |  | 49400 | -4952.09 | 44447.91 | 0 | 0
FIN | UNEP | Latin America Region Networks for LAC South, LAC Central, and Caribbean (1998) | Individual | LAC | LAC | SEV | 23 | TAS | 25 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-12-01 |  | 1998-12-01 | 1999-12-01 | 399000 | -53324 | 345676 | 345676 | 100% | 0 | 0 |  | 51870 | -6932.12 | 44937.88 | 0 | 0
FIN | UNEP | Regional workshop on monitoring and control of ODS consumption for the Caribbean region | Individual | LAC | LAC | SEV | 23 | TRA | 26 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-02-01 | 1998-11-01 |  | 1998-06-01 | 1999-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 |  | 11050 | 0 | 11050 | 0 | 0
FIN | UNEP | Latin America Region Network (South America, Central America and the Caribbean) | Individual | LAC | LAC | SEV | 26 | TAS | 29 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 2000-12-01 | 2000-12-01 | 399000 | -55099 | 343901 | 343901 | 100% | 0 | 0 |  | 51870 | -7162.87 | 44707.13 | 0 | 0
FIN | UNEP | Latin America and the Caribbean regional networks (South America, Central America, Caribbean) (2000) | Individual | LAC | LAC | SEV | 29 | TAS | 33 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-12-01 | 2005-12-01 | 418950 | -30000 | 388950 | 388950 | 100% | 0 | 0 |  | 54464 | -3900 | 50564 | 0 | 0
FIN | UNEP | South American, Central American and the Caribbean regional networks (2001) | Individual | LAC | LAC | SEV | 32 | TAS | 35 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2001-12-01 |  | 2001-12-01 | 2003-07-01 | 429000 | -17257 | 411743 | 411743 | 100% | 0 | 0 |  | 55770 | -2243.41 | 53526.59 | 0 | 0
FIN | Canada | Latin American Customs Enforcement Network: Preventing illegal trade of ODS | Individual | LAC | LAC | SEV | 51 | TAS | 38 | A | I |  | 0 | 0 | 0 |  | 2007-03-01 | 2008-09-01 | 2008-03-01 |  | 2010-12-01 | 2010-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 |  | 0 | 6500 | 0 | 6500 | 0 |  | This project is implemented by UNEP on behalf of Canada. A study on illegal tradeof ODS in the region was completed in June 2009 and presented to participants to UNEP LAC Network meeting in october 2009. Countries opted to test the informal Prior Informed Consent (iPIC) form as a tool to control illegal trade of ODS. Work initiated at the end of the year to complete iPIC forms for all participating countries. This last activity of the project was completed by the end of 2010. |  | 2007 | 2009-12-01 | Non-Inv.
FIN | UNEP | Latin American Customs Enforcement Network: Preventing illegal trade of ODS | Individual | LAC | LAC | SEV | 51 | TAS | 39 | A | I |  | 0 | 0 | 0 | 0 | 2007-03-01 | 2008-02-01 | 2008-03-01 |  | 2011-02-01 | 2015-12-01 | 80000 | -4109 | 75891 | 75891 | 100% | 0 | 0 |  | 10400 | -534.17 | 9865.83 | 0 | 0 |  |  |  | 2009-10-01
FIN | UNDP | Project preparation for 2 projects in the flexible slabstock foam sector | Individual | ASP | LAO | FOA | 36 | PRP | 08 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2003-04-01 | 2005-11-01 | 20000 | -2741 | 17259 | 17259 | 100% | 0 | 0 | 0 | 2600 | -356.33 | 2243.67 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Conversion from CFC-11 to methylene chloride (MC) in the manufacture of flexible polyurethane foam (box) at Prasert Foam Co., Ltd. | Individual | ASP | LAO | FOA | 38 | INV | 10 | A | I | CFC | 16.3 | 16.3 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2004-12-01 |  | 2004-08-01 | 2005-11-01 | 139343 | 0 | 139343 | 139343 | 100% | 0 | 0 | 0 | 18114.59 | 0 | 18114.59 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Formulation of a terminal phase out project in the foam sector | Individual | ASP | LAO | FOA | 39 | PRP | 11 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-12-01 | 2005-12-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 375 | 0 | 375 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2003 |  | Investment
CLO | UNDP | Conversion from CFC-11 in the manufacture of boxfoam (FPF) and insulated containers (RPF) in Prasert Sofa Shop Co., Ltd. | Individual | ASP | LAO | FOA | 44 | INV | 14 | N | I | CFC | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2006-12-01 |  |  | 2007-12-01 | 184660 | -184660 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 16619 | -16619 | 0 | 0 | 0 | Canceled in 2006. Financially completed in 2007. |  | 2004 |  | Investment
CLO | UNDP | Project preparation for foam multiple sub-sectors | Individual | ASP | LAO | FOA | 45 | PRP | 15 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-06-01 | 2006-04-01 |  |  | 2006-12-01 | 22493 | 0 | 22493 | 22493 | 100% | 0 | 0 | 0 | 1687 | 0 | 1687 | 0 | 0 | Canceled in 2006. Financially completed in 2006. |  | 2005 |  | Investment
FIN | France | Project preparation for a terminal phase-out management plan for CFCs |  | ASP | LAO | PHA | 49 | PRP | 16 | A | I | CFC | 0 |  | 0 |  | 2006-07-01 | 2007-05-01 | 2007-07-01 |  | 2008-02-01 | 2009-02-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  | 0 | 3900 | 0 | 3900 | 0 |  | Project completed. TPMP approved by 54th ExCom.
COM | France | Terminal phase-out management plan (first tranche) | Multi-Year | ASP | LAO | PHA | 54 | INV | 18 | A | I | CFC | 0 |  | 0 |  | 2008-04-01 | 2010-05-01 | 2010-03-01 |  | 2013-05-01 |  | 181500 | 0 | 181500 | 181500 | 100% | 0 |  |  | 23595 | 0 | 23595 | 0 |  | The project is competed. Implementation of tranches 1 and 2 were binded in order to accelerate the pace of implementation. It is to be noted that following an incident in the management of the funds, the agency support costs were in fact used for the project activities.
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | LAO | PHA | 55 | PRP | 19 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-11-01 | 2009-07-01 |  | 2011-01-01 | 2012-01-01 | 150000 | -23373 | 126627 | 120911 | 95.49% | 5716 | 0 |  | 19500 | -3038.49 | 15718.43 | 743.08 | 0
COM | France | Terminal phase-out management plan (second tranche) | Multi-Year | ASP | LAO | PHA | 61 | INV | 21 | A | I | CFC | 6.5 |  | 0 |  | 2010-07-01 |  | 2011-07-01 |  | 2013-05-01 |  | 138500 | 0 | 138500 | 138500 | 100% | 0 |  | 0 | 18005 | 0 | 18005 | 0 |  | The project is competed. Implementation of tranches 1 and 2 were binded in order to accelerate the pace of implementation. It is to be noted that following an incident in the management of the funds, the agency support costs were in fact used for the project activities.
COM | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | ASP | LAO | PHA | 63 | TAS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-10-01 | 2015-03-01 |  | 2016-12-01 |  | 113625 | 0 | 113625 | 90565.81 | 79.71% | 23059.19 | 1291 | 23059 | 14771 | 0 | 11773.356 | 2997.644 | 167.8272 | Brief progress report (actual/planned): Following recommendation of the verification of HCFC consumption, the Government requested to use the remaining balance of the HPMP first tranche to support the establishment and operation of the working group for on-site inspection of non-label HCFC cylinders and set up mechanism to prosecute offenders of the regulations. On-site inspections were jointly conducted by the NOU, Environmental Police, the Department of Domestic Trade and Vientiane Capital provincial office to understand the current situation to allow the country to proper actions. The memo has been submitted to the Minister of the Ministry of Natural Resources and Environment for approval. Legal arrangements (actual/planned): The SSFA has been signed in May 2012. First Mission: June 2012. TOR completed: N/A First disbursement date: Oct 2011 All funds disbursed (yes/no): No. Any delay? (yes/no): No. Any ongoing problems (yes/no): No. | Brief progress report (actual/planned): The Minister of the Ministry of Natural Resources and Environment has approved the proposal to establish the working group comprising of NOU, Environmental Police, the Department of Domestic Trade and Vientiane Capital provincial office. NOU is working with these agencies to officially establish the working group, which will be followed by the on-site inspection. The project will be completed by December 2017.
COM | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Individual | ASP | LAO | PHA | 71 | TAS | 25 | A | I |  | 0 |  | 0 |  | 2013-12-01 | 2015-12-01 | 2015-05-01 |  | 2016-03-01 |  | 30000 | 0 | 30000 | 15027.58 | 50.09% | 14972.42 | 0 | 14972 | 3900 | 0 | 1953.5854 | 1946.4146 | 0 | Project completed. | Project completed.
ONG | France | HCFC phase-out management plan (stage I, second tranche) |  | ASP | LAO | PHA | 74 | INV | 28 | A | I |  | 0.1 |  | 0 |  | 2015-05-01 |  | 2020-05-01 |  |  |  | 40500 | 0 | 40500 |  | 0% | 40500 |  |  | 5265 | 0 |  | 5265 |  | According to Lao National Ozone Unit, this scheme may not be ready to be implemented at the moment because of the low price of virgin HCFC, which does not provide incentive for the technicians to collect and reclaim. Further discussions on the matter will be necessary
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | ASP | LAO | PHA | 74 | TAS | 27 | A | I |  | 0.7 |  | 0 |  | 2015-05-01 | 2016-05-01 | 2020-05-01 | 2020-12-01 |  |  | 97875 | 0 | 97875 | 0 | 0% | 97875 | 86875 | 9787.5 | 12724 | 0 | 0 | 12724 | 11293.9719 | Brief progress report (actual/planned): The licensing and quota system as well as mandatory labeling requirement was strictly implemented in 2016. Despite some delay in receiving the first payment, the Pollution Control Department (PCD) coordinated with the Ministry of Industry and Commerce to establish the regulation to ban the use of HCFC-141b and HCFC-141b in pre-blended polyol. This also included working with the ministries concerned to explore option to prohibit the installation of large HCFC-based equipment in the country. The quota system and mandatory labeling requirement was implemented. The Pollution Control Department organized one update RAC training workshop for the safe handling of low GWP alternatives in December 2016 with 29 participants. UNEP mission was conducted in December 2016 to follow-up implementation progress. Lao PDR also attended the regional workshop on Environmentally Friendly Refrigerants in the Room Air Conditioners (RAC). 2015 CP data was submitted online. Legal arrangements (actual/planned): The SSFA was signed in December 2015. First Mission: October 2015. TOR completed: Not applicable. First disbursement date: May 2016 All funds disbursed (yes/no): No. Any delay? (yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No. | Brief progress report (actual/planned): The training plan for customs and RAC technicians for 2017 has been prepared. PCD will organize the training of customs and RAC technician to catch up the planned implementation schedule. This also includes working with the ministries concerned to establish the regulations to support HPMP, second tranche.
FIN | Sweden | Implementation of the RMP: development of import/export licensing system | Individual | ASP | LAO | REF | 34 | TAS | 05 | A | I |  | 1.6 |  | 0 |  | 2001-07-01 | 2002-11-01 | 2002-09-01 |  | 2005-12-01 | 2005-12-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The Swedish contribution in Lao PDR consists of technical assistance to prepare an import/export licensing system. International and national consultants were contracted in April 2002. After an initial delay in the signing of agreement and data collection the project is completed, we are only awaiting Lao PDR’s approval of the final report. The Decree for the "Control of the Import-Export and Consumption of ODS" was signed late 2003. A regulation for how the new Decree shall be implemented has been developed and the regulation was signed by the Minister in November 2004. SEI and the IC gave a number of suggestions on drafts on the regulation during 2004. An information brochure to all importers informing them about the licensing system was finalized during 2005. |  | 2001
FIN | France | Implementation of the RMP: recovery and recycling, training and demonstration project (complement) | RMP | ASP | LAO | REF | 34 | TAS | 06 | N | I | CFC | 1.2 |  | 0 |  | 2001-07-01 | 2006-03-01 | 2004-08-01 |  | 2009-04-01 | 2012-12-01 | 40800 | 0 | 40800 | 40800 | 100% | 0 |  | 0 | 2040 | 0 | 2040 | 0 |  | Lao has reported an error concerning this activity in PR for 2006. The financial agreement signed in between Lao PDR and France combined both LAO/REF/34/TAS/06 recovery and recycling, training and demonstration project (complement) and LAO/REF/34/TRA/03: training of trainers in good refrigerant management practices (phase I); national technicians training project (phase II). With the 2 budgets combined, 3 sets of R&R equipment have been bought and handed over to three institutions, 21 sets of basic servicing equipment were bought, and the training of trainers included sessions on best practices, MAC and R&R. Furthermore, a recovery and recycling machine was built locally as part of a university training course. The project is completed.
FIN | UNEP | Implementation of the RMP: monitoring the activities contained in the RMP | Individual | ASP | LAO | REF | 34 | TAS | 07 | A | I | CFC | 0.5 | 0 | 0 | 0 | 2001-07-01 | 2003-06-01 | 2003-08-01 |  | 2006-12-01 | 2009-12-01 | 17500 | -12500 | 5000 | 5000 | 100% | 0 | 0 |  | 2275 | -1624.54 | 650.46 | 0 | 0
FIN | France | Implementation of the RMP: training of trainers in good refrigerant management practices (phase I); national technicians training project (phase II) | RMP | ASP | LAO | REF | 34 | TRA | 03 | N | I |  | 2.4 |  | 0 |  | 2001-07-01 | 2005-01-01 | 2004-08-01 |  | 2009-04-01 | 2012-12-01 | 78750 | 0 | 78750 | 78750 | 100% | 0 |  | 0 | 10237 | 0 | 10237 | 0 |  | Lao had reported an error concerning the training of technicians in PR for 2006. The financial agreement signed in between Lao PDR and France combined both LAO/REF/34/TAS/06 recovery and recycling, training and demonstration project (complement) and LAO/REF/34/TRA/03: training of trainers in good refrigerant management practices (phase I); national technicians training project (phase II). The amount of expenses made for these 2 lines were inserted under LAO/REF/34/TRA/03. The final training was carried out in April 2009. The project is completed.
FIN | France | Implementation of the RMP: customs training programme | RMP | ASP | LAO | REF | 34 | TRA | 04 | N | I | CFC | 2.4 |  | 0 |  | 2001-07-01 | 2005-01-01 | 2003-08-01 |  | 2010-06-01 | 2012-12-01 | 81542 | -11242 | 70300 | 70761 | 100.7% | -461 |  | 0 | 10600 | -1461 | 9208 | -69 |  | Project completed. | Balance return in March 2013
FIN | UNEP | Country programme preparation | Individual | ASP | LAO | SEV | 27 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-10-01 | 2000-07-01 |  | 2001-07-01 | 2001-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | France | Technical assistance for country programme and refrigerant management plan preparation |  | ASP | LAO | SEV | 27 | CPG | 09 | A | I |  | 0 |  | 0 |  | 1999-03-01 | 1999-05-01 | 2000-12-01 |  | 2001-02-01 | 2001-02-01 | 31500 | 0 | 31500 | 31500 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Le Plan de gestion des réfriférants a été approuvé en même temps que le Programme de pays à la 34ème réunion du Comité Exécutif. Project completed.
FIN | UNEP | Establishment of the Ozone Unit for implementing the phase-out of ODS under the Montreal Protocol | Individual | ASP | LAO | SEV | 34 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-08-01 | 2004-08-01 |  | 2004-08-01 | 2006-02-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 |  | 8580 | 0 | 8580 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (phase II) | Individual | ASP | LAO | SEV | 43 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2006-02-01 | 2006-07-01 |  | 2006-12-01 | 2007-12-01 | 57200 | 0 | 57200 | 57200 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (phase III) | Individual | ASP | LAO | SEV | 50 | INS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-05-01 | 2008-11-01 |  | 2008-11-01 | 2009-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (phase IV) | Individual | ASP | LAO | SEV | 56 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-06-01 | 2010-11-01 |  | 2010-11-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (phase V) | Individual | ASP | LAO | SEV | 61 | INS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2010-12-01 | 2012-11-01 |  | 2012-11-01 | 2013-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (phase VI: 12/2012-11/2014) | Individual | ASP | LAO | SEV | 67 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2013-03-01 | 2014-11-01 |  | 2014-11-01 | 2015-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Renewal of the institutional strengthening project (phase VII: 12/2014-11/2016) | Individual | ASP | LAO | SEV | 72 | INS | 26 | A | I |  | 0 |  | 0 |  | 2014-05-01 | 2015-05-01 | 2016-11-01 | 2017-06-01 |  |  | 60000 | 0 | 60000 | 47679.82 | 79.47% | 12320.18 | 12320.18 | 1232.018 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The NOU was operating normally, but one of two staff, who were recruited in 2015, resigned in mid of 2016. The license/quota system was strictly enforced. In 2016, the total quota of 37 MT of HCFC-22 were allocated to two importers and the actual import was 36.9 MT. NOU took intitative to establish the working for on-site inspection comprising NOU, Environmental Police, the Department of Domestic Trade and Vientiane Capital provincial office. Following the Minister approval, several meetings were conducted to explore the legal framework for the working group to inspect and seizerefrigerants that does not contain the government sticker in the domestic market. NOU also coordinated and facilitated the implementation of HPMP, ODS Alternative Survey and verification of HCFC consumption. The NOU also organized the 2016 ozone day celebration, and actively joined the regional and global ozone related meetings e.g. the network meeting, OEWG and the MOP meetings. 2015 Article 7 and CP data were submitted to the Ozone Secretariat and MLFS respectively. NOU coordinated with importers for submitting their request for 2017 quota in November 2016. The project was completed in December 2016. Legal arrangements(actual/planned): The SSFA was signed in December 2014. Initial stages of project implementation(actual/planned): Dec/Dec 2014 Intermediate goals achieved (actual/planned): Yes_First disbursement date (actual/planned): May 2015 All funds disbursed (yes/no): No. Any delay?(yes/no): No.. If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): N/A. Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): The last payment under IS Phase VII is being proceed, it is expected to be released to the country by March 2017.
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | ASP | LAO | SEV | 74 | TAS | 29 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-03-01 | 2016-05-01 | 2017-06-01 |  |  | 40000 | 0 | 40000 | 15267.25 | 38.17% | 24732.75 | 14732.75 | 2473.275 | 5200 | 0 | 1984.7425 | 3215.2575 | 1915.2575 | Brief progress report (actual/planned): The project was on track. Two consultation workshops were organized. A consulting firm was hired by the NOU to support the data collection. UNEP mission was conducted in April 2016 to guide the consultant and finalize the methodology. The consulting firm assisted the NOU in the identification of the current use of ODS alternatives by substance/sector and collection of import/export data for the substances for the past a couple of years. Consulting firm also provided support in establishing growth patterns in use by substance/sector and in compiling data on available ODS alternatives for various applications. The NOU and consulting firm drafted and cross checked the information to ensure the completion of end-user surveys, collection, analysis, and aggregation of consumption data. The various sections of the report were drafted based on the format approved by ExCom decision 75/67 as contained in document UNEP/OzL.Pro/ExCom/75/77/Rev.1. , but not yet completed. Legal arrangements (actual/planned): The SSFA was signed in November 2015. Initial stages of project implementation(actual/planned): November 2015. Intermediate goals achieved (actual/planned): Not applicable. Project completion and follow up: Not applicable. First disbursement date (actual/planned): March 2016 All funds disbursed (yes/no): _No__ Any delay?(yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): The draft report is being finalized by the NOU and consulting firm and will be submitted to UNEP for review by end of March 2017. The report is expected for submission to the MLFS by April 2017.
ONG | UNEP | Renewal of the institutional strengthening project (phase VIII: 12/2016-11/2018) | Individual | ASP | LAO | SEV | 76 | INS | 30 | A | I |  | 0 |  | 0 |  | 2016-05-01 |  | 2018-11-01 | 2018-11-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The project was approved at the 76th ExCom Meeting in May 2016. The SSFA was drafted in consultation with the country and was signed by UNEP and the Govrnment of Lao PDR in November 2016. Legal arrangements(actual/planned): The SSFA was signed in Novemer 2016 Initial stages of project implementation(actual/planned): Not yet Intermediate goals achieved (actual/planned): Not yet Project completion and follow up: Not applicable. First disbursement date (actual/planned): Not yet. All funds disbursed (yes/no): _No__ Any delay?(yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): Following closure of the IS project phase VII, the first payment of IS project phase VIII has been requested. NOU continues enforcing the licensing and quota system as well as mandatoty labeling requirement for HCFC containers. NOU advertised the expression of interest in February 2017 to recruit a technical consultant, who will provide dialy support to the NOU.
FIN | UNIDO | Project formulation for phase out of ODS in aerosol sector (Cosmaline Industries S.A.) | Individual | ASP | LEB | ARS | 16 | PRP | 02 | A | I |  | 0 | 0 |  |  | 1995-03-01 | 1995-05-01 | 1995-06-01 |  | 1996-06-01 | 1998-08-01 | 15000 | -8784 | 6216 | 6216 | 100% | 0 | 0 |  | 1950 | -1143 | 807 | 0 | 0 | FIN
FIN | UNIDO | Investment project for phasing out of CFCs at Cosmaline Industries s.a.al. | Individual | ASP | LEB | ARS | 19 | INV | 05 | A | I | CFC | 87.7 | 87.7 |  |  | 1996-05-01 | 1996-11-01 | 1997-05-01 |  | 1997-12-01 | 1999-07-01 | 212500 | 0 | 212500 | 212500 | 100% | 0 | 0 |  | 27625 | 0 | 27625 | 0 | 0 | FIN
FIN | UNIDO | Investment project for phasing out CFCs at Zeeni's Trading Agency | Individual | ASP | LEB | ARS | 19 | INV | 06 | A | I | CFC | 212 | 212 |  |  | 1996-05-01 | 1996-11-01 | 1997-05-01 |  | 1997-12-01 | 2000-07-01 | 361900 | -9467 | 352433 | 352433 | 100% | 0 | 0 |  | 47047 | -1303 | 45744 | 0 | 0 | FIN
CLO | Germany | Project preparation and technical assistance at Arnatoury S.A.R.L., Sin-El-Fil | Individual | ASP | LEB | ARS | 26 | PRP | 26 | N | I |  | 0 | 0 | 0 | 0 | 1998-11-01 |  | 1999-12-01 |  |  | 1999-03-01 | 15000 | -15000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project will not be implemented
FIN | UNDP | Preparation of four projects in the aerosol sector | Individual | ASP | LEB | ARS | 27 | PRP | 28 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-11-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1999 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of aerosol at International Cosmetic Manufacturing Co. (Incoma), SAL | Individual | ASP | LEB | ARS | 28 | INV | 30 | A | I | CFC | 53.5 | 53.5 | 0 | 0 | 1999-07-01 | 2001-02-01 | 2002-02-01 |  | 2004-09-01 | 2005-10-01 | 158582 | -5069 | 153513 | 153513 | 100% | 0 | 0 | 0 | 20615.66 | -658.98 | 19956.6791 | 0.000909 | 0 | Completed in 2004. Financially completed in 2005. |  | 1999 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of aerosols at Societe Nougeaim PMOSAL | Individual | ASP | LEB | ARS | 28 | INV | 35 | A | I | CFC | 54 | 54 | 0 | 0 | 1999-07-01 | 2001-02-01 | 2002-02-01 |  | 2004-09-01 | 2005-10-01 | 147333 | -2643 | 144690 | 144690 | 100% | 0 | 0 | 0 | 19153.29 | -343.59 | 18809.7052 | -0.005181 | 0 | Completed in 2004. Financially completed in 2005. |  | 1999 |  | Investment
FIN | UNDP | Group SME's project for the conversion to CFC-free technology in manufacturer of aerosol at Zahdreddine Trade and Manufacturing Sarl (ZTME), at Societe Nouvelle pour le Commerce et l'Industrie (SNCI) | Individual | ASP | LEB | ARS | 29 | INV | 32 | A | I | CFC | 50.7 | 50.7 | 0 | 0 | 1999-11-01 | 2001-02-01 | 2002-12-01 |  | 2004-09-01 | 2005-10-01 | 314092 | -1547 | 312545 | 312545 | 100% | 0 | 0 | 0 | 40831.96 | -201.11 | 40630.8498 | 0.000247 | 0 | Completed in 2004. Financially completed in 2005. |  | 1999 |  | Investment
FIN | UNIDO | Preparation for pilot demonstration project on ODS waste management and disposal | Individual | ASP | LEB | DES | 61 | PRP | 72 | A | I |  | 0 | 0 |  |  | 2010-07-01 | 2010-12-01 | 2011-07-31 |  | 2014-11-01 | 2016-03-01 | 85000 | -397 | 84603 | 84602.66 | 100% | 0.34 | 0 |  | 6375 | -30 | 6345 | 0 | 0 | The project was financially completed and the balance was returned at the 76th ExCom. |  |  |  | NON-INV
ONG | UNIDO | Pilot demonstration project on ODS waste management and disposal | Individual | ASP | LEB | DES | 73 | DEM | 83 | A | I |  | 0 | 0 |  |  | 2014-11-01 | 2016-01-01 | 2016-11-30 | 2018-03-18 |  |  | 123475 | 0 | 123475 | 38628.56 | 31.28% | 84846.44 | 6845.92 | 30000 | 11113 | 0 | 3477 | 7636 | 616 | ODS stocks in process of being collected. Logistical arrangements for transportation and storage in place. The recruitment of legal expert to facilitate export of collected ODS is in process. '- No delay in implementation - No recurring problem - Impact on project completion date: No - No action required by Executive Committee | ODS stocks in process of being collected. Logistical arrangements for transportation and storage in place. The recruitment of legal expert to facilitate export of collected ODS in process. '- No delay in implementation - No recurring problem - Impact on project completion date: No - No action required by Executive Committee |  |  | INV
FIN | UNIDO | Project formulation for the phase out of ODS in the foam sector in 2 plants (Ets. Henri Abdallah and Nasri Karam) | Individual | ASP | LEB | FOA | 16 | PRP | 04 | A | I |  | 0 | 0 |  |  | 1995-03-01 | 1995-05-01 | 1995-07-01 |  | 1997-03-01 | 1998-08-01 | 20000 | -7358 | 12642 | 12642 | 100% | 0 | 0 |  | 2600 | -959 | 1641 | 0 | 0 | FIN
FIN | France | Projects preparation and technical assistance in the foam sector |  | ASP | LEB | FOA | 19 | TAS | 07 | A | D |  | 0 |  | 0 |  | 1996-05-01 | 1996-07-01 | 1997-05-01 |  | 1996-08-01 | 1996-09-01 | 20000 | -495 | 19505 | 19505 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed
FIN | UNIDO | Phasing out of CFC-11 at Nasri Karam and Sons | Individual | ASP | LEB | FOA | 20 | INV | 09 | A | I | CFC | 22 | 22 |  |  | 1996-10-01 | 1997-07-01 | 1997-10-01 |  | 1998-12-01 | 2000-07-01 | 100109 | -106 | 100003 | 100003 | 100% | 0 | 0 |  | 13014 | -34 | 12980 | 0 | 0 | FIN
FIN | France | Conversion to non-CFC technology in the manufacture of polyurethane flexible molded foam at Meuble Mode Sarl |  | ASP | LEB | FOA | 20 | INV | 10 | A | I | CFC | 9 | 9 | 0 |  | 1996-10-01 | 1997-01-01 | 1997-10-01 |  | 2000-03-01 | 2000-03-01 | 55700 | -235 | 55465 | 55465 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed.
FIN | France | Conversion to non-CFC technology in the manufacture of flexible foam (slabstock) at Furniture and Plastic Sarl (FAP) |  | ASP | LEB | FOA | 20 | INV | 11 | A | I | CFC | 28 | 28 | 0 |  | 1996-10-01 | 1998-06-01 | 1997-10-01 |  | 2000-09-01 | 2000-12-01 | 128700 | 0 | 128700 | 128700 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed. |  |  | 2000-01-01
FIN | France | Conversion to non-CFC technology in the manufacture of flexible foam (slabstock) at Plastiflex Sarl |  | ASP | LEB | FOA | 20 | INV | 12 | A | I | CFC | 42 | 42 | 0 |  | 1996-10-01 | 1997-01-01 | 1997-10-01 |  | 1999-03-01 | 1999-08-01 | 154000 | -7224 | 146776 | 146776 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Projet achevé. PCR soumis |  |  | 2000-01-01
FIN | France | Conversion to non-CFC technology in the manufacture of flexible foam (slabstock) at Merza Foam Sarl |  | ASP | LEB | FOA | 20 | INV | 13 | A | I | CFC | 45 | 45 | 0 |  | 1996-10-01 | 1997-01-01 | 1997-10-01 |  | 2000-03-01 | 2000-04-01 | 108172 | -950 | 107222 | 107222 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed.
FIN | France | Conversion to non-CFC technology in the manufacture of rigid foam (sandwich panels) at Kilzi and Co. Sarl |  | ASP | LEB | FOA | 20 | INV | 14 | A | I | CFC | 22.5 | 22.5 | 0 |  | 1996-10-01 | 1997-01-01 | 1997-10-01 |  | 1999-11-01 | 1999-12-01 | 141000 | 0 | 141000 | 141000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Projet achevé. PCR soumis. |  |  | 2000-01-01
FIN | France | Conversion to non-CFC technology in the manufacture of flexible foam (slabstock) at Fomaco Sarl |  | ASP | LEB | FOA | 20 | INV | 15 | A | I | CFC | 26 | 26 | 0 |  | 1996-10-01 | 1997-01-01 | 1997-10-01 |  | 1999-09-01 | 1999-12-01 | 154000 | -2258 | 151742 | 151742 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Projet achevé. PCR soumis
FIN | UNIDO | Phasing out CFC-11 at Ets. Henri Abdallah P.F.M. | Individual | ASP | LEB | FOA | 21 | INV | 18 | A | I | CFC | 16.6 | 16.6 |  |  | 1997-02-01 | 1997-06-01 | 1998-02-01 |  | 1998-12-01 | 2000-07-01 | 81291 | -583 | 80708 | 80708 | 100% | 0 | 0 |  | 10568 | -93 | 10475 | 0 | 0 | FIN
FIN | UNDP | Preparation of project in the foam subsector | Individual | ASP | LEB | FOA | 27 | PRP | 27 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2000-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1999 |  | Investment
FIN | UNDP | Project preparation in the flexible polyurethane foam sector | Individual | ASP | LEB | FOA | 33 | PRP | 41 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 12000 | -1934 | 10066 | 10066 | 100% | 0 | 0 | 0 | 1560 | -251.42 | 1308.58 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | ASP | LEB | FOA | 57 | PRP | 71 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-03-01 | 2010-03-01 |  | 2012-09-01 | 2013-11-01 | 25000 | -643.21 | 24356.79 | 24357 | 100% | -0.21 | 0 | 0 | 1875 | -48.24 | 1826.775 | -0.015 | 0 | Financially completed in 2013. | Completed in 2012. | 2009 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (stage II) (foam sector) | Individual | ASP | LEB | FOA | 72 | PRP | 81 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 | 2015-05-01 | 2016-05-01 |  | 2015-06-01 | 2016-06-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 1400 | 0 | 1400 | 0 | 0 | Financially completed in 2016. | HPMP Stage-II preparation is ongoing and the strategy is expected to be submitted to the 75th Excom. |  |  | Non-Investment
FIN | UNDP | Project preparation for one methyl bromide alternative demonstration project | Individual | ASP | LEB | FUM | 25 | PRP | 23 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-08-01 | 1999-08-01 |  | 1998-08-01 | 2000-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1998 |  | Investment
FIN | UNDP | Demonstration project of alternative to methyl bromide for soil fumigation (greenhouse) | Individual | ASP | LEB | FUM | 26 | DEM | 24 | N | I | MeBr | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-03-01 | 2000-12-01 |  | 2001-07-01 | 2003-04-01 | 328200 | -2958 | 325242 | 325242 | 100% | 0 | 0 | 0 | 42666 | -384.54 | 42281.46 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Project preparation in soil fumigation | Individual | ASP | LEB | FUM | 33 | PRP | 42 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-07-01 | 2002-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 2001 |  | Investment
FIN | UNIDO | Project preparation in the fumigants (strawberries) sector | Individual | ASP | LEB | FUM | 33 | PRP | 43 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2002-12-01 | 30000 | -904 | 29096 | 29096.46 | 100% | -0.46 | 0 |  | 3900 | -123 | 3777 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of methyl bromide for soil fumigation in strawberry production (first tranche) | Multi-Year | ASP | LEB | FUM | 34 | INV | 44 | A | I | MBR | 26.1 | 26.1 |  |  | 2001-07-01 | 2002-04-01 | 2002-12-01 |  | 2002-12-01 | 2003-12-01 | 350000 | 0 | 350000 | 350000 | 100% | 0 | 0 |  | 45500 | 0 | 45500 | 0 | 0 | FIN |  |  |  | INV
FIN | UNDP | Sectors phase-out of methyl bromide in vegetable, cut flower and tobacco production (first tranche) | Multi-Year | ASP | LEB | FUM | 34 | INV | 46 | N | I | MeBr | 25.8 | 25.8 | 0 | 0 | 2001-07-01 | 2002-01-01 | 2002-12-01 |  | 2004-12-01 | 2012-01-01 | 800000 | 0 | 800000 | 800000 | 100% | 0 | 0 | 0 | 98000 | 0 | 98000 | 0 | 0 | Financially completed in 2012. |  | 2001 |  | Investment
FIN | UNDP | Sectors phase-out of methyl bromide in vegetable, cut flower and tobacco production (second tranche) | Multi-Year | ASP | LEB | FUM | 38 | INV | 51 | N | I | MeBr | 31.8 | 31.8 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2003-12-01 |  | 2004-12-01 | 2012-01-01 | 600000 | 0 | 600000 | 600000 | 100% | 0 | 0 | 0 | 76000 | 0 | 76000 | 0 | 0 | Financially completed in 2012. |  | 2002 |  | Investment
FIN | UNIDO | Phase-out of methyl bromide (strawberries): release of second tranche | Multi-Year | ASP | LEB | FUM | 38 | INV | 52 | A | I | MBR | 10.1 | 10.1 |  |  | 2002-11-01 | 2003-11-01 | 2003-12-01 |  | 2003-12-01 | 2007-12-01 | 421946 | 0 | 421946 | 421945.97 | 100% | 0.03 | 0 |  | 54853 | 0 | 54853 | 0 | 0 | FIN |  |  |  | INV
FIN | UNDP | Sector phase-out of methyl bromide in vegetable, cut flower and tobacco production (third tranche) | Multi-Year | ASP | LEB | FUM | 41 | INV | 53 | N | I | MeBr | 54 | 54 | 0 | 0 | 2003-12-01 | 2005-02-01 | 2005-12-01 |  | 2006-06-01 | 2012-01-01 | 500000 | 0 | 500000 | 500000 | 100% | 0 | 0 | 0 | 37500 | 0 | 37500 | 0 | 0 | Financially completed in 2012. |  | 2003 |  | Investment
FIN | UNIDO | Phase-out of methyl bromide for soil fumigation in strawberry production (third tranche) | Multi-Year | ASP | LEB | FUM | 41 | INV | 54 | A | I | MBR | 14.2 | 25.3 |  |  | 2003-12-01 | 2005-07-01 | 2004-12-01 |  | 2008-12-01 | 2011-05-01 | 450000 | -18846 | 431154 | 431153.54 | 100% | 0.46 | 0 |  | 33750 | -1413 | 32337 | 0 | 0 | FIN |  |  |  | INV
FIN | UNDP | Sector phase-out of methyl bromide in vegetables, cut flowers, and tobacco production (fourth tranche) | Multi-Year | ASP | LEB | FUM | 44 | INV | 58 | N | I | MeBr | 36 | 36 | 0 | 0 | 2004-12-01 | 2006-02-01 | 2005-12-01 |  | 2008-12-01 | 2012-01-01 | 400000 | 0 | 400000 | 400000 | 100% | 0 | 0 | 0 | 30000 | 0 | 30000 | 0 | 0 | Financially completed in 2012. |  | 2004 |  | Investment
FIN | UNDP | Sector phase-out of methyl bromide in vegetables, cut flowers, and tobacco production (fifth tranche) | Multi-Year | ASP | LEB | FUM | 47 | INV | 61 | N | I | MeBr | 66.4 | 66.4 | 0 | 0 | 2005-11-01 | 2008-01-01 | 2009-03-01 |  | 2009-12-01 | 2012-01-01 | 210000 | 56716.59 | 266716.59 | 266717 | 100% | -0.41 | 0 | 0 | 15750 | 4254.24 | 20004.274 | -0.033951 | 0 | Financially completed in 2012. |  | 2005 |  | Investment
FIN | UNIDO | Phase-out of methyl bromide for soil fumigation in strawberry production (fifth tranche) | Multi-Year | ASP | LEB | FUM | 47 | INV | 62 | A | I | MBR | 9 | 9 |  |  | 2005-11-01 | 2008-02-01 | 2006-12-01 |  | 2009-12-01 | 2010-12-01 | 42504 | -692 | 41812 | 41811.71 | 100% | 0.29 | 0 |  | 3188 | -52 | 3136 | 0 | 0 | FIN |  |  |  | INV
FIN | UNDP | Preparation of a CFC terminal programme | Individual | ASP | LEB | PHA | 36 | PRP | 48 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2004-12-01 | 2007-03-01 | 15000 | -3601 | 11399 | 11399 | 100% | 0 | 0 | 0 | 1950 | -468.13 | 1481.87 | 0 | 0 | Completed in 2004. Financially completed in 2007. |  | 2002 |  | Investment
FIN | UNDP | Project preparation for the formulation of a CFC phase-out plan | Individual | ASP | LEB | PHA | 42 | PRP | 55 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2005-04-01 |  | 2004-12-01 | 2005-12-01 | 16000 | 0 | 16000 | 16000 | 100% | 0 | 0 | 0 | 1200 | 0 | 1200 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2004 |  | Investment
FIN | UNDP | National phase-out management plan for Annex-A Group-I substances (CFCs) (first tranche) | Multi-Year | ASP | LEB | PHA | 44 | INV | 57 | N | I | CFC | 55 | 55 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2005-12-01 |  | 2007-12-01 | 2012-01-01 | 1061420 | 0 | 1061420 | 1061420 | 100% | 0 | 0 | 0 | 79607 | 0 | 79607 | 0 | 0 | Financially completed in 2012. |  | 2004 |  | Investment
FIN | UNDP | National phase-out management plan for Annex-A Group-I substances (CFCs) (second and third tranches) | Multi-Year | ASP | LEB | PHA | 48 | INV | 63 | N | I | CFC | 287 | 287 | 0 | 0 | 2006-04-01 | 2008-01-01 | 2007-04-01 |  | 2008-12-01 | 2012-01-01 | 865000 | 0 | 865000 | 865000 | 100% | 0 | 0 | 0 | 64875 | 0 | 64875 | 0 | 0 | Financially completed in 2012. |  | 2006 |  | Investment
FIN | UNDP | National phase-out management plan for Annex-A Group-I substances (CFCs) (fourth tranche) | Multi-Year | ASP | LEB | PHA | 53 | INV | 65 | N | I | CFC | 40 | 40 | 0 | 0 | 2007-11-01 | 2009-10-01 | 2009-11-01 |  | 2009-12-01 | 2012-01-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 7500 | 0 | 7500 | 0 | 0 | Financially completed in 2012. |  | 2007 |  | Investment
FIN | UNDP | National phase-out management plan for Annex-A Group-I substances (CFCs) (fifth tranche) | Multi-year | ASP | LEB | PHA | 55 | INV | 66 | N | I | CFC | 35 | 35 | 0 | 0 | 2008-07-01 | 2009-05-01 | 2010-07-01 |  | 2010-12-01 | 2012-01-01 | 65000 | -400.46 | 64599.54 | 64600 | 100% | -0.46 | 0 | 0 | 4875 | -30.03 | 4845 | -0.03 | 0 | Financially completed in 2012. |  | 2008 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | ASP | LEB | PHA | 55 | PRP | 67 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2010-03-01 | 2009-07-01 |  | 2011-12-01 | 2013-11-01 | 137250 | 0 | 137250 | 137250 | 100% | 0 | 0 | 0 | 10293.75 | 0 | 10293.75 | 0 | 0 | Financially completed in 2013. | Project targeted for financial closure in 2012 | 2008 |  | Investment
FIN | UNDP | HCFC phase-out management plan (air conditioning sector plan) (stage I, first tranche) | Multi-Year | ASP | LEB | PHA | 64 | INV | 74 | N | I | HCFC | 3 | 3 | 0 | 0 | 2011-07-01 | 2012-04-01 | 2013-07-01 |  | 2013-07-01 | 2013-12-01 | 555000 | 0 | 555000 | 555000 | 100% | 0 | 0 | 0 | 41625 | 0 | 41625 | 0 | 0 | Financially completed in 2013. |  | 2011 |  | Investment
FIN | UNDP | HCFC phase-out management plan (foam sector plan) (stage I, first tranche) | Multi-Year | ASP | LEB | PHA | 64 | INV | 76 | N | I | HCFC | 9.1 | 9.1 | 0 | 0 | 2011-07-01 | 2012-04-01 | 2013-07-01 |  | 2013-07-01 | 2013-12-01 | 810000 | 0 | 810000 | 810000 | 100% | 0 | 0 | 0 | 60750 | 0 | 60750 | 0 | 0 | Financially completed in 2013. |  | 2011 |  | Investment
FIN | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | LEB | PHA | 64 | TAS | 75 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-07-01 | 2013-02-01 | 2013-07-01 |  | 2013-07-01 | 2013-12-01 | 135000 | 0 | 135000 | 135000 | 100% | 0 | 0 | 0 | 10125 | 0 | 10125 | 0 | 0 | Financially completed in 2013. |  | 2011 |  | Non-Investment
FIN | UNDP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | ASP | LEB | PHA | 70 | INV | 78 | N | I | HCFC | 0 | 0 | 0 | 0 | 2013-07-01 | 2013-09-01 | 2015-07-01 |  | 2015-12-01 | 2016-12-01 | 745589 | 0 | 745589 | 745589 | 100% | 0 | 0 | 0 | 55919 | 0 | 55919 | 0 | 0 | Financially completed in 2016. | Activities progressing satisfactorily. Third tranche request for Lebanon approved in 74th Excom. Enterprise level conversion in RAC and foam sector completed. Other technical support and information outreach activities are in progress. | 2013 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan (stage II) | Individual | ASP | LEB | PHA | 72 | PRP | 80 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 | 2015-02-01 | 2016-05-01 |  | 2015-06-01 | 2016-06-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 4900 | 0 | 4900 | 0 | 0 | Financially completed in 2016. | HPMP Stage-II preparation is ongoing and the strategy is expected to be submitted to the 75th Excom. |  |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, third tranche) | Multi-year | ASP | LEB | PHA | 74 | INV | 84 | N | I | HCFC | 0 | 0 | 0 | 0 | 2015-05-01 | 2016-11-01 | 2017-05-01 | 2017-12-01 |  |  | 124760 | 0 | 124760 | 60935.21 | 48.84% | 63824.79 | 0 | 25529.916 | 9357 | 0 | 4570.1407 | 4786.8593 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Under NOU's guidance, the project provided technical assistance and work schedule compliance of investment components, with specific respect to technology conversion projects, in foam and air-conditioning sectors, which were completed. On enforcement of a ministerial decision related to the amended ODS licensing system, required legal works were finished by a special legal consultant. Three technical workshops targeting enterprises in foam and air-conditioning sectors organized in April, June, and December 2016. Two trainings/ capacity building workshops for institutional and government stakeholders on HCFC controls were held in July and December 2016. In addition, two public awareness workshops were organized, and design and initial implementation of an awareness outreach programme were carried out. Two workshops to Customs officers on the control of the illegal and forged imports of refrigerants were held and the project provided the Customs authority with required equipment (identifiers (qty. 5). Prodoc signed (actual/planned, yes/no and date):1/1. Yes. Agreement signed earlier. Missions undertaken (actual/planned):0/0: No mission fielded in the reporting period TOR for consultants/subcontracts completed (actual/planned): 0/0. The TORs for trainers were completed earlier. New TORs prepared in 2017 for the PVR of the years 2015&2016. Contract/PO/MOA agreements signed: 1/1: One tender on refrigerant analyzers was completed and equipment supplied to Customs First disbursement date (actual/planned): Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | The project focussed on preparation of the Annual implementation plan for the year 2017 and relevant reports for the previous year, including for workshops, training programmes and awareness activities addressed to servicing technicians in the air conditioning sectors. | 2015 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage II, first tranche) (foam sector) | Multi-year | ASP | LEB | PHA | 75 | INV | 85 | N | I | HCFC | 19.1 | 0 | 0 | 0 | 2015-11-01 | 2016-10-01 | 2019-12-01 | 2017-12-01 |  |  | 1147649 | 0 | 1147649 | 441666.62 | 38.48% | 705982.38 | 0 | 282392.952 | 80336 | 0 | 30916.8828 | 49419.1172 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Project document signed in August 2016 with MOAs with companies established in September 2016. Implementation of the projects is ongoing. The project provides technical advice on the implementation of the projects based on our previous experience in this sector. Prodoc signed (actual/planned, yes/no and date):1/1. Yes. In August 2016. Missions undertaken (actual/planned):0/0: No missions fielded in this period. TOR for consultants/subcontracts completed (actual/planned): 1/1: One technical national expert is on board Contract/PO/MOA agreements signed: 4/4: MoAs for the foam industries were prepared in September 2016 (4 foam industries to phase out HCFCs) First disbursement date (actual/planned): 42644Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:Delay in the grant approval's Decree by the Council of Ministers. Regular contacts with Governmental focal points maintained, and follow-up with foam industry assisted to keep workplans ready to start implementation once approval is granted. | Activities focussed on MOA implementation and workplan for 2017. | 2015 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage II, first tranche) (air conditioning sector) | Multi-year | ASP | LEB | PHA | 75 | INV | 86 | N | I | HCFC | 5 | 0 | 0 | 0 | 2015-11-01 |  | 2019-12-01 | 2017-12-01 |  |  | 547504 | 0 | 547504 | 0 | 0% | 547504 | 0 | 219001.6 | 38325 | 0 | 0 | 38325 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Project document was signed in August 2016 with subsequent siganture of MOAs with the industry in September 2016. Implementation of the projects is ongoing. The project provides technical advice on the implementation of the projects based on our previous experience in this sector. Prodoc signed (actual/planned, yes/no and date):1/1. Yes. In August 2016. Missions undertaken (actual/planned):0/0: No missions fielded in this period. TOR for consultants/subcontracts completed (actual/planned): 1/1: One technical national expert is on board Contract/PO/MOA agreements signed: 2/2: MOAs with two AC industries were concluded in September 2016 First disbursement date (actual/planned): 42644Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:Delay in the grant approval's Decree by the Council of Ministers. Regular contacts with Governmental focal points maintained, and follow-up with AC industry assisted to keep workplans ready to start implementation once approval is granted. | Activities focussed on MOA implementation and workplan for 2017. | 2015 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | Multi-year | ASP | LEB | PHA | 75 | INV | 87 | N | I | HCFC | 5.7 | 0 | 0 | 0 | 2015-11-01 |  | 2019-12-01 | 2017-12-01 |  |  | 495756 | 0 | 495756 | 0 | 0% | 495756 | 0 | 198302.4 | 34703 | 0 | 0 | 34703 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Project documentation was signed in August 2016. According to workplan, activities in this sector will start in the 3rd quarter of 2017, with subsequent reporting in the next 2017 cycle. Prodoc signed (actual/planned, yes/no and date):1/1. Yes. In August 2016. Missions undertaken (actual/planned):0/0: No missions fielded in this period. TOR for consultants/subcontracts completed (actual/planned): 0/0: Activities will start in the 3rd quarter of 2017. Contract/PO/MOA agreements signed: 0/0: Activities will start in the 3rd quarter of 2017.Yes First disbursement date (actual/planned): October 2017 as planned dateAny delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:Delay in the grant approval's Decree by the Council of Ministers. | Activities under this component will start in the 3rd quarter of 2017. | 2015 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage II, first tranche) (project management and coordination) | Multi-year | ASP | LEB | PHA | 75 | TAS | 88 | N | I | HCFC | 0 | 0 | 0 | 0 | 2015-11-01 |  | 2019-12-01 | 2017-12-01 |  |  | 219091 | 0 | 219091 | 0 | 0% | 219091 | 0 | 87636.4 | 15336 | 0 | 0 | 15336 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Project document was signed in August 2016. Project management, coordination and implementation is maintained to support the ongoing activities, mainly the supervision of the HCFC phase-out investment and capacity building projects. Preparation of the annual work-plan for the years 2016-2017 has ben completed. Prodoc signed (actual/planned, yes/no and date):1/1. Yes. In August 2016. Missions undertaken (actual/planned):0/0: No missions fielded in this period. TOR for consultants/subcontracts completed (actual/planned): 1/1: Support expert is in place Contract/PO/MOA agreements signed: 0/0: No procurement planned under this component First disbursement date (actual/planned): 42644Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:Delay in the grant approval's Decree by the Council of Ministers. Regular contacts with Governmental focal points maintained. | Preparation of the workplan and activities planned for the year 2017 | 2015 |  | Non-Investment
FIN | UNIDO | Project formulation for phase out of ODS in the refrigeration sector (Weather-mate and OPACO Ltd.) | Individual | ASP | LEB | REF | 16 | PRP | 03 | A | I |  | 0 | 0 |  |  | 1995-03-01 | 1997-08-01 | 1995-07-01 |  | 1997-12-01 | 2000-12-01 | 15000 | -1497 | 13503 | 13503 | 100% | 0 | 0 |  | 1950 | -197 | 1753 | 0 | 0 | FIN
FIN | France | Project preparation for the commercial refrigeration sector |  | ASP | LEB | REF | 20 | PRP | 16 | A | I |  | 0 |  | 0 |  | 1996-10-01 | 1996-11-01 | 1997-10-01 |  | 1998-08-01 | 1998-09-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed.
FIN | France | Project preparation to establish a CFC and HCFC recovery and recycling centre |  | ASP | LEB | REF | 20 | PRP | 17 | A | I |  | 0 |  | 0 |  | 1996-10-01 | 1996-11-01 | 1997-10-01 |  | 1998-08-01 | 1998-09-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed.
FIN | UNIDO | Phasing out of CFCs at Lebanese Modern Industrial and Trading Co. | Individual | ASP | LEB | REF | 22 | INV | 19 | A | I | CFC | 135 | 135 |  |  | 1997-05-01 | 1997-08-01 | 1998-11-01 |  | 1999-12-01 | 2002-10-01 | 1313121 | -65527 | 1247594 | 1247593.65 | 100% | 0.35 | 0 |  | 170706 | -8776 | 161930 | 0 | 0 | FIN |  |  | 1999-12-01
FIN | France | Conversion of refrigeration industrial facilities |  | ASP | LEB | REF | 23 | INV | 22 | A | I | CFC | 10.4 | 10.4 | 0 |  | 1997-11-01 | 1999-01-01 | 1999-06-01 |  | 1999-12-01 | 2000-12-01 | 166605 | -13443 | 153162 | 153162 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Projet achevé
FIN | France | Implementation of an ODS recovery and recycling network | Recovery and recycling | ASP | LEB | REF | 23 | TAS | 21 | A | I | CFC | 62 |  | 0 |  | 1997-11-01 | 2010-04-01 | 1998-12-01 |  | 2011-03-01 | 2012-10-01 | 425289 | 0 | 425289 | 425289 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed. |  |  | 2002-11-01
FIN | France | Training of refrigeration technicians on recovery and recycling methodologies |  | ASP | LEB | REF | 23 | TRA | 20 | A | I |  | 0 |  | 0 |  | 1997-11-01 | 1998-03-01 | 1999-06-01 |  | 2000-10-01 | 2000-12-01 | 52668 | 0 | 52668 | 52668 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Projet achevé en octobre 2000
FIN | Germany | Training in improved operations, service and maintenance for refrigeration technicians in using hydrocarbons | Individual | ASP | LEB | REF | 26 | TRA | 25 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 1999-12-01 |  | 1999-09-01 | 2002-01-01 | 49500 | -8197 | 41303 | 41303 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed, final report submitted
FIN | France | Remaining issues for a RMP and preparation of strategy and projects for reduction of CFC emissions in centrifugal chillers |  | ASP | LEB | REF | 28 | TAS | 29 | A | I |  | 0 |  | 0 |  | 1999-07-01 | 2000-03-01 | 2002-02-01 |  | 2001-08-01 | 2002-01-01 | 45750 | -20966 | 24784 | 24784 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | The study was completed and a draft report was handed over to the NOU (08/2001). Remaining activities could be carried out at the same time than the R&R project.Project completed.
FIN | Germany | Remaining issues for a RMP and preparation of strategy and projects for reduction of CFC emissions in centrifugal chillers | RMP | ASP | LEB | REF | 28 | TAS | 31 | A | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-05-01 | 2002-02-01 |  | 2001-11-01 | 2003-10-01 | 37550 | -3 | 37547 | 37547 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed, final report submitted
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141B and CFC-12 to HFC-134a in the manufacture of commercial refrigeration at the first group of Lebanese Commercial Refrigerator Manufacturers | Individual | ASP | LEB | REF | 29 | INV | 33 | A | I | CFC | 18.5 | 18.5 |  |  | 1999-11-01 | 2000-01-01 | 2001-12-01 |  | 2000-07-01 | 2002-09-01 | 258006 | -8773 | 249233 | 249233.23 | 100% | -0.23 | 0 |  | 33541 | -1192 | 32349 | 0 | 0 | FIN
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Farjallah Co. | Individual | ASP | LEB | REF | 29 | INV | 34 | A | I | CFC | 20.1 | 20.1 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2002-05-01 | 2003-07-01 | 200046 | 0 | 200046 | 200046 | 100% | 0 | 0 | 0 | 26005.98 | 0 | 26005.98 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b and CFC-12 to HFC-134a in manufacture of commercial refrigeration at the second group of Lebanese commercial refrigeration manufacturers | Individual | ASP | LEB | REF | 31 | INV | 36 | A | I | CFC | 15.66 | 15.66 |  |  | 2000-07-01 | 2000-09-01 | 2003-01-01 |  | 2002-12-01 | 2003-12-01 | 203191 | -1043 | 202148 | 202147.72 | 100% | 0.28 | 0 |  | 26415 | -177 | 26238 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b and CFC-12 to HFC-134a in manufacture of commercial refrigeration at the third group of Lebanese commercial refrigerator manufacturers | Individual | ASP | LEB | REF | 31 | INV | 39 | A | I | CFC | 15.8 | 15.8 |  |  | 2000-07-01 | 2001-01-01 | 2003-01-01 |  | 2002-12-01 | 2004-09-01 | 208498 | -8133 | 200365 | 200364.97 | 100% | 0.03 | 0 |  | 27105 | -1099 | 26006 | 0 | 0 | FIN
FIN | UNIDO | Project preparation of two umbrella investment projects in the commercial refrigeration sector, covering six SME factories each | Individual | ASP | LEB | REF | 31 | PRP | 38 | A | I |  | 0 | 0 |  |  | 2000-07-01 | 2000-11-01 | 2001-07-01 |  | 2001-11-01 | 2002-12-01 | 20000 | -1076 | 18924 | 18923.55 | 100% | 0.45 | 0 |  | 2600 | -144 | 2456 | 0 | 0 | FIN
FIN | UNIDO | Preparation of two umbrella projects in the commercial refrigeration sector | Individual | ASP | LEB | REF | 33 | PRP | 40 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2002-01-01 | 2002-04-01 |  | 2002-07-01 | 2003-06-01 | 15000 | -229 | 14771 | 14770.5 | 100% | 0.5 | 0 |  | 1950 | -33 | 1917 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phasing out CFC-11 by conversion to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at 4th group of enterprises | Individual | ASP | LEB | REF | 34 | INV | 45 | A | I | CFC | 18.8 | 18.8 |  |  | 2001-07-01 | 2002-04-01 | 2003-08-01 |  | 2004-06-01 | 2005-12-01 | 279672 | -9510 | 270162 | 270161.81 | 100% | 0.19 | 0 |  | 36357 | -1292 | 35065 | 0 | 0 | FIN |  |  |  | INV
CLO | UNIDO | Preparation of 2 umbrella investment projects in the commercial refrigeration sector | Individual | ASP | LEB | REF | 36 | PRP | 47 | A | I |  | 0 | 0 |  |  | 2002-03-01 |  | 2003-04-01 |  |  | 2003-05-01 | 15000 | -15000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 1950 | -1950 | 0 | 0 | 0 | CLO |  |  |  | INV
FIN | UNDP | Preparation for HCFC phase-out investment activities (refrigeration manufacturing sector except air-to-air air-conditioning) | Individual | ASP | LEB | REF | 57 | PRP | 69 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-03-01 | 2010-03-01 |  | 2011-12-01 | 2013-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 4500 | 0 | 4500 | 0 | 0 | Financially completed in 2013. | Project targeted for financial closure in 2012 | 2009 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (air-to-air air-conditioning sector) | Individual | ASP | LEB | REF | 57 | PRP | 70 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-03-01 | 2010-03-01 |  | 2011-12-01 | 2013-11-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1125 | 0 | 1125 | 0 | 0 | Financially completed in 2013. | Project targeted for financial closure in 2012 | 2009 |  | Investment
ONG | UNDP | Preparation for HCFC phase-out investment activities (stage II) (refrigeration and air-conditioning sectors) | Individual | ASP | LEB | REF | 72 | PRP | 79 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 | 2015-08-01 | 2016-05-01 | 2017-12-01 |  |  | 60000 | 0 | 60000 | 59965.44 | 99.94% | 34.56 | 0 | 13.824 | 4200 | 0 | 4197.5808 | 2.4192 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Project was completed and closed in December 2016. HPMP-II was prepared, submitted and approved at the 75th ExCom. Prodoc signed (actual/planned, yes/no and date):1/1: Yes. Agreement signed earlier. Missions undertaken (actual/planned):0/0: No missions fielded in this period. TOR for consultants/subcontracts completed (actual/planned): 0/0: TORs prepared earlier and already closed Contract/PO/MOA agreements signed: 0/0: POs closed earlier First disbursement date (actual/planned): 42217Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | No activities due to this PRP having been closed earlier in 2016. |  |  | Non-Investment
FIN | UNEP | Country programme preparation | Individual | ASP | LEB | SEV | 12 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-07-01 | 1995-07-01 |  | 1996-05-01 | 1995-09-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNDP | Creation of an Ozone Unit | Individual | ASP | LEB | SEV | 19 | INS | 08 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1996-05-01 | 1997-05-01 | 2000-05-01 |  | 2000-12-01 | 2002-03-01 | 179000 | -63 | 178937 | 178937 | 100% | 0 | 0 | 0 | 23270 | -8.19 | 23261.81 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1996 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening (Phase II) | Individual | ASP | LEB | SEV | 31 | INS | 37 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2000-07-01 | 2000-08-01 | 2002-08-01 |  | 2003-07-01 | 2004-12-01 | 119300 | 0 | 119300 | 119300 | 100% | 0 | 0 | 0 | 15509 | 0 | 15509 | 0 | 0 | Completed in 2003. Financially completed in 2004. |  | 2000 |  | Non-Investment
FIN | UNDP | Country programme update | Individual | ASP | LEB | SEV | 36 | CPG | 49 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-01-01 | 2003-10-01 |  | 2003-12-01 | 2004-12-01 | 37500 | 0 | 37500 | 37500 | 100% | 0 | 0 | 0 | 4875 | 0 | 4875 | 0 | 0 | Completed in 2003. Financially completed in 2004. |  | 2002 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening project (Phase 3) | Individual | ASP | LEB | SEV | 37 | INS | 50 | N | I | No_ODP | 12.8 | 12.8 | 0 | 0 | 2002-07-01 | 2003-02-01 | 2004-08-01 |  | 2004-12-01 | 2009-07-01 | 155090 | -979 | 154111 | 154111 | 100% | 0 | 0 | 0 | 20161.7 | -127.27 | 20034.4281 | 0.0019 | 0 | Completed in 2004.Financially completed in 2009. |  | 2002 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase IV) | Individual | ASP | LEB | SEV | 44 | INS | 59 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2006-12-01 |  | 2007-06-01 | 2010-10-01 | 155090 | -2834.99 | 152255.01 | 152255 | 100% | 0.01 | 0 | 0 | 11632 | -212.63 | 11419.3704 | -0.00044998 | 0 | Financially completed in 2010. |  | 2004 |  | Non-Investment
FIN | UNDP | Assistance to carry out an HCFC survey | Individual | ASP | LEB | SEV | 45 | TAS | 60 | A | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-09-01 | 2006-12-01 |  | 2008-08-01 | 2009-12-01 | 45872 | -6848 | 39024 | 39024 | 100% | 0 | 0 | 0 | 4128 | -616.25 | 3511.7517 | -0.0017 | 0 | Completed in 2008. Financially completed in 2009. |  | 2005 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase V) | Individual | ASP | LEB | SEV | 50 | INS | 64 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-01-01 | 2008-11-01 |  | 2008-12-01 | 2011-08-01 | 155090 | -372.8 | 154717.2 | 154717 | 100% | 0.2 | 0 | 0 | 11632 | -27.96 | 11604.0244 | 0.0156 | 0 | Completed in 2008. |  | 2006 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VI) | Individual | ASP | LEB | SEV | 56 | INS | 68 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-01-01 | 2009-03-01 |  | 2011-06-01 | 2013-02-01 | 155090 | 0 | 155090 | 155090 | 100% | 0 | 0 | 0 | 11632 | 0 | 11632 | 0 | 0 | Financially completed in 2013. | Completed in 2011. The project is being financially closed in 2012. | 2008 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VII) | Individual | ASP | LEB | SEV | 62 | INS | 73 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-09-01 | 2013-03-01 |  | 2013-03-01 | 2013-12-01 | 155090 | 0 | 155090 | 155090 | 100% | 0 | 0 | 0 | 11632 | 0 | 11632 | 0 | 0 | Financially completed in 2013. |  | 2010 |  | Non-Investment
COM | UNDP | Extension of the institutional strengthening project (phase VIII: 4/2013-3/2015) | Individual | ASP | LEB | SEV | 68 | INS | 77 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-09-01 | 2015-03-01 |  | 2015-09-01 |  | 155090 | 0 | 155090 | 152600 | 98.39% | 2490 | 0 | 2116.5 | 10856 | 0 | 10681.7048 | 174.2952 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2015. |  | 2012 |  | Non-investment
ONG | UNDP | Extension of the institutional strengthening project (phase IX: 4/2015-3/2017) | Individual | ASP | LEB | SEV | 73 | INS | 82 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-11-01 | 2016-02-01 | 2017-03-01 | 2017-12-01 |  |  | 155090 | 0 | 155090 | 90468.77 | 58.33% | 64621.23 | 0 | 25848.492 | 10856 | 0 | 6332.6389 | 4523.3611 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): NOU's work focussed on enforcement of the amended ODS licensing system to accommodate HCFCs. The following key activities were carried out in the reporting period: (1) close coordination with the legal department at MoEe and the customs authority on legislation issues. (i.e. preparation of several Ministerial decisions for proper implementation of the amended ODS Licensing system); (2) strengthening the cooperation with the various stakeholders (Liason with the governmental and semi-governmental institutions, industrial sector and NGOs); (3) close coordination with the importers and suppliers of the ODSs as well as equipment; (4) organization of technical workshops addressing HCFCs and their alternatives to importers (February 2016, July 2016, October 2016); (5) provision of technical advice and information to end-users (Industries and servicing sectors); (6) active participation in all international MP meetings (ODS Network Meeting for West Asia; ExCom, OEWG and MOP Meetings); (6) overall monitoring and supervision of all projects that are under implementation (HPMPs, ODS survey and ODS destruction); (7) preparation, on the occasion of the Ozone day, of several press released to the media, TV interviews, promotion material and initiation of a university course related to the Ozone material; and (8) preparation of the annual reports for the year 2016 (CP data report and A7 data report) Prodoc signed (actual/planned, yes/no and date):1/1. Yes. Agreement signed in January 2016. Missions undertaken (actual/planned):0/0: No missions fielded in this period. TOR for consultants/subcontracts completed (actual/planned): 3/3: IS project's personnel received contract extensions Contract/PO/MOA agreements signed: 4/4: Relevant supporting POs were placed to support operations of the project and awareness raising campaigns First disbursement date (actual/planned): 42401Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | Workplan preparations for 2017 on IS-X phase. DOA sent. Regular discussions to faciliate prodoc signature. | 2014 |  | Non-Investment
ONG | UNDP | Survey of ODS alternatives at the national level | Individual | ASP | LEB | SEV | 74 | TAS | 35 | N | I | HFC | 0 | 0 | 0 | 0 | 2015-05-01 | 2016-05-01 | 2016-11-01 | 2017-08-01 |  |  | 110000 | 0 | 110000 | 71411.25 | 64.92% | 38588.75 | 6000 | 15435.5 | 9900 | 0 | 6427.0125 | 3472.9875 | 540 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Project document was signed in May 2016, with required ToRs for consultants and sub-contracts put in place for data collection. Work was continued with preparation of survey forms for ODS alterantive data collection by sectors. Recruited experts assisted with the data and its analysis. A final ODS alternatives survey report was prepared, reviewed. Prodoc signed (actual/planned, yes/no and date):1/1. Yes. Agreement signed in May 2016. Missions undertaken (actual/planned):0/0: No missions fielded in this period. TOR for consultants/subcontracts completed (actual/planned): 4/4: TORs for project coordinator and support experts were prepared in April 2016 Contract/PO/MOA agreements signed: 0/0: No procurement planned in this project's cycle except other personnel sub-contracts. First disbursement date (actual/planned): 42491Any delays/problems (yes/no):No. ODS alternatives survey was on time. If Yes, reasons for delay & action plan to resolve: | Final report submitted to the MLF Secretariat in January 2017. No comments received. | 2015 |  | Non-Investment
ONG | UNDP | Extension of the institutional strengthening project (phase X: 4/2017-3/2019) | Individual | ASP | LEB | SEV | 77 | INS | 89 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2016-12-01 |  | 2019-03-01 | 2017-03-01 |  |  | 198515 | 0 | 198515 | 0 | 0% | 198515 | 0 | 79406 | 13896 | 0 | 0 | 13896 | 0 | Newly Approved | DOA was prepared and sent to UNDP and NOU-Lebanon in February 2017. UNDP Project document drafted, along with 2017 workplan, and submitted for signature with the Government. Signature expected in April/May 2017 to allow to start with implementation of workplans, TORs etc. | 2016 |  | Non-Investment
FIN | Germany | Terminal CFC phase-out management plan (first tranche) | Multi-Year | AFR | LES | PHA | 41 | INV | 08 | A | I | CFC | 0.6 | 0.8 | 0 |  | 2003-12-01 | 2003-12-01 | 2004-12-01 |  | 2005-03-01 | 2005-06-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | Second tranche was requested for the TPMP.
FIN | Germany | Terminal CFC phase-out management plan (second tranche) | Multi-Year | AFR | LES | PHA | 45 | INV | 09 | A | I | CFC | 0.6 | 0.6 | 0 |  | 2005-04-01 | 2005-04-01 | 2006-04-01 |  | 2007-12-01 | 2008-03-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | 3rd tranche was requested and approved.
FIN | Germany | Terminal CFC phase-out management plan (third tranche) | Multi-Year | AFR | LES | PHA | 50 | INV | 10 | A | I | CFC | 1.4 | 1.4 | 0 |  | 2006-11-01 | 2007-05-01 | 2007-11-01 |  | 2009-11-01 | 2011-12-01 | 17300 | 0 | 17300 | 17300 | 100% | 0 | 0 | 0 | 2249 | 0 | 2249 | 0 | 0 | Project has been completed, Lesotho has achieved complete phase out as per the Agreement with the Excom on the TPMP.
FIN | Germany | Preparation of a HCFC phase-out management plan | Individual | AFR | LES | PHA | 57 | PRP | 12 | A | I | HCFC | 0 |  | 0 |  | 2009-04-01 | 2009-10-01 | 2010-03-01 |  | 2011-06-01 | 2012-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | The HPMP was prepared and submitted and approved at the 64th Excom. The document was developed following the completion of a detailed survey and stakeholder workshop.
FIN | Germany | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | LES | PHA | 64 | INV | 14 | A | I | HCFC | 0 | 0.6 | 0 |  | 2011-07-01 | 2011-08-01 | 2014-07-01 |  | 2014-12-01 | 2015-06-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 |  | 58 technicians were trained in 2014 on best practices and safe handling of refrigerants. 6 recovery units have been provided. | Project completed.
ONG | Germany | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | AFR | LES | PHA | 74 | INV | 17 | A | I | HCFC | 0 |  | 0 |  | 2015-05-01 | 2015-11-01 | 2017-11-01 | 2017-11-01 |  |  | 68000 | 0 | 68000 | 13423 | 19.74% | 54577 | 0 | 54577 | 8840 | 0 | 1745 | 7095 |  | 3 customs trainings were completed in 2016. The NOU requested funds to attend the OEWG in 2016 as Lesotho was not supported due to lack of funds. Support was also given to the NOU for the Ozone day celebrations as ISP funds were not sufficient. However NOU was focusing on the ODS alternative survey and therefore little effort was made for implmentation of the project activities which is to change in 2017. | Currently NOU is working towards holding CO2 train the trainers on Coke units conducted by the local coke trainer. CO2 beverage coolers are being procured to be provided to the local VTCs to help with hands on training. Additional upgrade training for trainers is also being discussed which will be done by trainers attending courses probably in South Africa.
ONG | Germany | Verification report for stage I of HCFC phase-out management plan | Individual | AFR | LES | PHA | 74 | TAS | 18 | A | I | HCFC | 0 |  | 0 |  | 2015-05-01 | 2015-12-01 | 2017-05-01 | 2017-05-01 |  |  | 30000 | 0 | 30000 | 7329 | 24.43% | 22671 | 0 | 22671 | 3900 | 0 | 953 | 2947 |  | No further funds were spent in 2016 as the contract for the consultant was made in 2017 | The verification is currently ongoing to be completed by end of April, prior to submisison of the next tranche request in July 2017.
FIN | UNDP | Project preparation in refrigeration recycling | Individual | AFR | LES | REF | 21 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1997-06-01 | 2002-03-01 | 20000 | -2704 | 17296 | 17296 | 100% | 0 | 0 | 0 | 2600 | -351.52 | 2248.48 | 0 | 0 | Completed in 1997. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | AFR | LES | REF | 22 | TAS | 04 | A | I | CFC | 3.6 | 3.6 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1999-06-01 | 2000-12-01 | 56095 | 0 | 56095 | 56095 | 100% | 0 | 0 | 0 | 7292.35 | 0 | 7292.35 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1997 |  | Investment
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | LES | REF | 26 | TAS | 05 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2001-11-01 | 2004-05-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Completed. PCR submitted TPMP submitted and approved at 41st Excom
FIN | Germany | Project preparation for an RMP update | RMP Update | AFR | LES | REF | 37 | PRP | 07 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-02-01 | 2003-08-01 |  | 2003-08-01 | 2004-06-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project completed, TPMP approved at 41st Excom
FIN | UNEP | Country programme preparation | Individual | AFR | LES | SEV | 15 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-05-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNEP | Institutional strengthening for the phase out of ODS and the establishment of a National Ozone Office | Individual | AFR | LES | SEV | 20 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-09-01 | 1999-10-01 |  | 1999-12-01 | 2004-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 |  |  |  | 2000-03-01
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | AFR | LES | SEV | 29 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2004-01-01 | 2001-12-01 |  | 2005-04-01 | 2007-05-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | AFR | LES | SEV | 45 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2007-03-01 | 2007-04-01 |  | 2008-02-01 | 2009-02-01 | 26000 | 0 | 26000 | 26000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | LES | SEV | 53 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2010-05-01 | 2009-11-01 |  | 2012-12-01 | 2013-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | AFR | LES | SEV | 62 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-06-01 | 2012-12-01 |  | 2012-12-01 | 2013-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of the institutional strengthening project (phase VI: 1/2013-12/2014) | Individual | AFR | LES | SEV | 68 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-07-01 | 2014-11-01 |  | 2016-12-01 |  | 60000 | 0 | 60000 | 19500 | 32.5% | 40500 | 40500 | 40500 | 0 | 0 | 0 | 0 | 0 | Project completed | Project completed
ONG | UNEP | Extension of the institutional strengthening project (phase VII: 1/2015-12/2016) | Individual | AFR | LES | SEV | 73 | INS | 16 | A | I |  | 0 |  | 0 |  | 2014-11-01 | 2016-04-01 | 2016-12-01 | 2017-09-01 |  |  | 60000 | 0 | 60000 | 14925.78 | 24.88% | 45074.22 | 45074.22 | 4507.422 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The licensing and quota systems are in place and operational. The NOU registered all importers of HCFCs and organized stakeholders’ workshop to allocate HCFC licenses and quotas to importers. The NOU conducted two inspection visits to monitor distribution of HCFCs to check compliance with the quotas allocated. The NOU conducted two RAC training workshops and two custom training workshops, and trained 60 technicians and 40 custom officers respectively. The NOU celebrated the 2016 international ozone day with several activities including printing 300 T-shirts. The NOU collected, processed and submitted 2015 Country Programme and Article 7 Data reports. The NOU participated in all Montreal Protocol meetings organized in 2016.__ Legal arrangements (actual/planned): The SSFA was drafted and signed by UNEP and the Government of Lesotho in September 2016. Initial stages of project implementation(actual/planned): Yes___ Intermediate goals achieved (actual/planned): __yes_ Project completion and follow up: No___ First disbursement date (actual/planned): _April 2016__ All funds disbursed (yes/no): _No__ Any delay?(yes/no): ___ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): No___ If Yes, is any action required by ExCom: __N/A_ | Brief progress report (actual/planned): The NOU continues to monitor imports and trade of ODS and ODS related equipment. Collection of the 2016 data on ODS imports and consumption has been completed and is being analyzed for submission. NOU commenced preparation of national legislative requirement processes in planning for ratification of Kigali amendment.
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | AFR | LES | SEV | 74 | TAS | 19 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-03-01 | 2016-05-01 | 2017-05-01 |  |  | 40000 | 0 | 40000 | 5050 | 12.62% | 34950 | 34950 | 3495 | 5200 | 0 | 656.5 | 4543.5 | 4543.5 | Brief progress report (actual/planned): The first stakeholders meeting was organized by the NOU in April 2016 in Maseru with the main goal to agree on the plan for the Survey of ODS alternatives at the national level and obtain support of main national stakeholders. The meeting was attended by 30 participants. One National Consultant as hired by the NOU to support the data collection. The National Consultant assisted the NOU in the identification of the current use of ODS alternatives by substance/sector and collection of import/export data for the substances for the past a couple of years. The National Consultant also provided support in establishing growth patterns in use by substance/sector and in compiling data on available ODS alternatives for various applications. The NOU and the National Consultant drafted and cross checked the information to ensure the completion of end-user surveys, collection, analysis, and aggregation of consumption data. The various sections of the report were drafted. The second stakeholders meeting was organized by the NOU in September 2016 in Maseru with the main goal to organise consultations with representatives of the government and private sector to finalize the outcomes of the Survey of ODS alternatives and discuss potential opportunities for introduction of those alternatives in the country. The draft report was prepared by the NOU and the National Consultant. It was reviewed and finalized based on the format approved by ExCom decision 75/67 as contained in document UNEP/OzL.Pro/ExCom/75/77/Rev.1 after incorporating inputs/ comments raised during National Stakeholders’ workshop. The NOU participated in the ODS Alternative Thematic workshop held in December 2016 to refine the draft report according to the revised template for the report. The final report has been submitted to UNEP for final review and submission to MLFS. ___ Legal arrangements(actual/planned):The SSFA was drafted and signed by UNEP and the Government of Lesotho in February 2016. ____Initial stages of project implementation(actual/planned): _Yes__ Intermediate goals achieved (actual/planned): Yes___ Project completion and follow up: _No__ First disbursement date (actual/planned): _March 2016__ All funds disbursed (yes/no): No___ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): __N/A_ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): The NOU incorporated comments from UNEP ROA and Paris and re-submitted final ODS survey report.
ONG | UNEP | Extension of the institutional strengthening project (phase VIII: 1/2017-12/2018) | Individual | AFR | LES | SEV | 77 | INS | 20 | A | I |  | 0 |  | 0 |  | 2016-12-01 |  | 2018-12-01 | 2018-12-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | Newly approved project. | Brief progress report (actual/planned): The project was approved in Dec 2016. The licensing and quota system are in place and operational. The NOU continues to monitor imports and trade of ODS and ODS related equipment. Collection of the 2016 data on ODS imports and consumption has been completed and is being analyzed for submission. NOU commenced preparation of national legislative requirement processes in planning for ratification of Kigali amendment. ___ Legal arrangements (actual/planned): The SSFA was drafted and sent to the Government of Lesotho for signature. ___Initial stages of project implementation (actual/planned): __Yes_ Intermediate goals achieved (actual/planned): _No__ Project completion and follow up: _Yes__ First disbursement date (actual/planned): __No ____. All funds disbursed (yes/no): No__ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: __N/A_
CLO | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Sebha Unit | Individual | AFR | LIB | FOA | 32 | INV | 05 | A | I | CFC | 26 | 19 | 0 | 0 | 2000-12-01 | 2002-12-01 | 2004-01-01 |  |  | 2008-04-01 | 128097 | -106916 | 21181 | 21181 | 100% | 0 | 0 | 0 | 16652.61 | -13899.41 | 2753.2045 | -0.0045 | 0 | Canceled in 2005. Financially completed in 2008. Balance returned in 2009. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Garabouli Unit | Individual | AFR | LIB | FOA | 32 | INV | 06 | A | I | CFC | 40.3 | 40.3 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2005-12-01 | 2011-12-01 | 109810 | 0 | 109810 | 109810 | 100% | 0 | 0 | 0 | 14275.3 | 0 | 14275.3 | 0 | 0 | Completed in 2005. Financially completed in 2011. |  | 2000 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam at Electrical Household Appliance-Tajura by conversion to a combination of water and HCFC-141b based systems | Individual | AFR | LIB | FOA | 32 | INV | 07 | A | I | CFC | 15.3 | 15.3 | 0 | 0 | 2000-12-01 | 2002-05-01 | 2004-01-01 |  | 2005-12-01 | 2008-04-01 | 119802 | -7675 | 112127 | 112127 | 100% | 0 | 0 | 0 | 15574.26 | -997.73 | 14576.5267 | 0.0033 | 0 | Completed in 2005. Financially completed in 2008. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Ben Ghazi Unit | Individual | AFR | LIB | FOA | 32 | INV | 08 | A | I | CFC | 31.4 | 31.4 | 0 | 0 | 2000-12-01 | 2002-07-01 | 2004-01-01 |  | 2007-04-01 | 2008-03-01 | 124860 | -97 | 124763 | 124763 | 100% | 0 | 0 | 0 | 16231.8 | -12.61 | 16219.1898 | 0.0002 | 0 | Completed in 2007. Financially completed in 2008. |  | 2000 |  | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | AFR | LIB | FOA | 32 | PRP | 09 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2000-12-01 | 2001-12-01 |  | 2001-03-01 | 2002-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 2000 |  | Investment
FIN | UNDP | Project preparation in the flexible polyurethane foam sector | Individual | AFR | LIB | FOA | 33 | PRP | 10 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 25000 | -1934 | 23066 | 23066 | 100% | 0 | 0 | 0 | 3250 | -251.42 | 2998.58 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Phase out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Tasharoukiate Essadek | Individual | AFR | LIB | FOA | 34 | INV | 12 | A | I | CFC | 32 | 32 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2005-12-01 | 2007-03-01 | 129109 | 0 | 129109 | 129109 | 100% | 0 | 0 | 0 | 16784.17 | 0 | 16784.17 | 0 | 0 | Completed in 2005. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Phase out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Hilal Africa | Individual | AFR | LIB | FOA | 34 | INV | 13 | A | I | CFC | 22 | 22 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2005-12-01 | 2008-04-01 | 113727 | 0 | 113727 | 113727 | 100% | 0 | 0 | 0 | 14784.51 | 0 | 14784.51 | 0 | 0 | Completed in 2005. Financially completed in 2008. |  | 2001 |  | Investment
FIN | UNDP | Phase out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Tasharoukiate El Hani | Individual | AFR | LIB | FOA | 35 | INV | 14 | A | I | CFC | 28 | 28 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-01-01 |  | 2005-12-01 | 2008-10-01 | 112440 | 0 | 112440 | 112440 | 100% | 0 | 0 | 0 | 14617.2 | 0 | 14617.2 | 0 | 0 | Completed in 2005. Financially completed in 2008. |  | 2001 |  | Investment
FIN | UNDP | Phase out of CFC-11 by conversion to liquid carbon dioxide (LCD) in the manufacture of flexible polyurethane foam at El Houria Unit Plant | Individual | AFR | LIB | FOA | 35 | INV | 15 | A | I | CFC | 96 | 96 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-01-01 |  | 2006-08-01 | 2011-11-01 | 520405 | -49886.77 | 470518.23 | 470518 | 100% | 0.23 | 0 | 0 | 67244.55 | -6446.2 | 60798.3181 | 0.03192 | 0 | Completed in 2006. |  | 2001 |  | Investment
FIN | UNDP | Phase out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Tasharoukiate Ali Sannoga | Individual | AFR | LIB | FOA | 35 | INV | 16 | A | I | CFC | 23 | 23 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-01-01 |  | 2005-12-01 | 2007-03-01 | 125640 | 0 | 125640 | 125640 | 100% | 0 | 0 | 0 | 16333.2 | 0 | 16333.2 | 0 | 0 | Completed in 2005. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Project preparation for 4 projects in the rigid foam sector | Individual | AFR | LIB | FOA | 36 | PRP | 17 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 |  | 2003-04-01 |  | 2002-12-01 | 2007-03-01 | 12500 | -12500 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 1625 | -1625 | 0 | 0 | 0 | Completed in 2002. Financially completed in 2007. |  | 2002 |  | Investment
FIN | UNDP | Project preparation for 6 projects in the flexible slabstock foam sector | Individual | AFR | LIB | FOA | 36 | PRP | 18 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 |  | 2003-04-01 |  | 2002-12-01 | 2007-03-01 | 12500 | -12500 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 1625 | -1625 | 0 | 0 | 0 | Completed in 2002. Financially completed in 2007. |  | 2002 |  | Investment
FIN | UNDP | Project preparation for 3 projects in the flexible slabstock foam sector | Individual | AFR | LIB | FOA | 36 | PRP | 19 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2003-12-01 | 2007-03-01 | 20000 | -9146 | 10854 | 10854 | 100% | 0 | 0 | 0 | 2600 | -1188.98 | 1411.02 | 0 | 0 | Completed in 2003. Financially completed in 2007. |  | 2002 |  | Investment
COM | UNIDO | Preparation for HCFC phase-out investment activities (polyurethane foam component) | Individual | AFR | LIB | FOA | 63 | PRP | 33 | A | I |  | 0 | 0 |  |  | 2011-04-01 | 2013-02-01 | 2012-03-31 |  | 2016-07-01 |  | 60000 | 0 | 60000 | 59977.18 | 99.96% | 22.82 | 0 | 1 | 4500 | 0 | 4498 | 2 | 0 | - HPMP Stage I first tranche in the foam sector was approved. - Project completed in Jul 2016. - Financially completed | Balance will be returned to the 79th Meeting of the ExCom. |  |  | NON-INV
FIN | UNIDO | Preparation of a phase-out plan in the fumigants sector (methyl bromide) | Individual | AFR | LIB | FUM | 45 | PRP | 24 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-09-01 | 2006-04-01 |  | 2005-12-01 | 2006-11-01 | 15000 | -1137 | 13863 | 13863.13 | 100% | -0.13 | 0 |  | 1125 | -85 | 1040 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Phase-out of methyl bromide in horticulture: tomatoes, cucumbers, peppers and others | Multi-Year | AFR | LIB | FUM | 47 | INV | 27 | A | I | MBR | 56 | 56 |  |  | 2005-11-01 | 2006-04-01 | 2009-12-01 |  | 2010-12-01 | 2012-10-01 | 743000 | 0 | 743000 | 743000.05 | 100% | -0.05 | 0 |  | 55725 | 0 | 55725 | 0 | 0 | FIN |  |  |  | INV
ONG | Spain | Phase-out of methyl bromide in horticulture: tomatoes, cucumbers, peppers and others (second tranche) | Multi-Year | AFR | LIB | FUM | 56 | INV | 30 | A | I | MBR | 40 |  | 0 |  | 2008-11-01 | 2010-05-01 | 2010-11-01 | 2017-12-01 |  |  | 500000 | 0 | 500000 | 427471.92 | 85.49% | 72528.08 | 37178.54 | 40000 | 65000 | 0 | 55571.3496 | 9428.6504 | 4833.2102 | - Project is almost completed. The remaining activity is the finalization of the installation and commissioning of the purchased equipment (already delivered on site). Indeed, the installation of the last equipment could not be finalized in 2016 due to the instability in the country. - However, UNIDO and NOU identified an option to have the last training abroad to allow local completion of installation by local experts. Was there any delay during the reporting year? Yes Any impact on project completion date? Yes Any recurring problem? Yes Any action required by Executive Committee? No | - The prevailing political and security situation and the instability in Libya do not allow the implementing agency in charge (UNIDO) to advance with the completion of the project. - UNIDO has been identifying logistical arrangements for the training of local experts in Spain hosted by the equipment supplier to complete installation and proceed with commissioning of equipment. Was there any delay during the reporting year? Yes Any impact on project completion date? Yes Any recurring problem? Yes Any action required by Executive Committee? No |  |  | Investment
FIN | UNIDO | Preparation of a halon phase-out plan | Individual | AFR | LIB | HAL | 45 | PRP | 23 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-08-01 | 2006-04-01 |  | 2006-12-01 | 2007-09-01 | 25000 | -264 | 24736 | 24736 | 100% | 0 | 0 |  | 1875 | -20 | 1855 | 0 | 0 | FIN |  |  |  | NON-INV
CLO | UNIDO | Plan for the phase-out of import and net consumption of halons in the fire fighting sector | Individual | AFR | LIB | HAL | 47 | TAS | 26 | A | I | HAL | 653.9 | 0 |  |  | 2005-11-01 | 2006-09-01 | 2008-12-01 |  |  | 2010-09-01 | 343500 | -335125 | 8375 | 8375.18 | 100% | -0.18 | 0 |  | 25763 | -25135 | 628 | 0 | 0 | CLO |  |  |  | INV
FIN | UNIDO | National phase-out plan (first tranche) | Multi-Year | AFR | LIB | PHA | 41 | INV | 22 | A | I | CFC | 150 | 150.4 |  |  | 2003-12-01 | 2004-03-01 | 2005-12-01 |  | 2005-08-01 | 2008-12-01 | 1500000 | -21 | 1499979 | 1499978.61 | 100% | 0.39 | 0 |  | 112500 | -2 | 112498 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National CFC phase-out plan: 2nd tranche | Multi-Year | AFR | LIB | PHA | 45 | INV | 25 | A | I | CFC | 124 | 124 |  |  | 2005-04-01 | 2005-11-01 | 2006-04-01 |  | 2013-12-01 | 2014-04-01 | 720000 | -3679 | 716321 | 716321.13 | 100% | -0.13 | 0 |  | 54000 | -276 | 53724 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National ODS phase-out plan: 3rd tranche | Multi-Year | AFR | LIB | PHA | 54 | INV | 28 | A | I | CFC | 176 | 176 |  |  | 2008-04-01 | 2010-03-01 | 2009-03-31 |  | 2013-12-01 | 2015-03-01 | 277947 | -9220 | 268727 | 268727.12 | 100% | -0.12 | 0 |  | 20846 | -692 | 20155 | -1 | 0 | FIN |  |  |  | INV
COM | UNIDO | Preparation of a HCFC phase-out management plan | Individual | AFR | LIB | PHA | 55 | PRP | 29 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-09-01 | 2009-07-31 |  | 2016-07-01 |  | 85000 | 0 | 85000 | 84362.78 | 99.25% | 637.22 | 0 | 1 | 6375 | 0 | 6327 | 48 | 0 | - HPMP Stage I first tranche was approved. - Project completed in Jul 2016. - Financially completed | Balance will be returned to the 79th Meeting of the ExCom. |  |  | NON-INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan (additional funding) | Individual | AFR | LIB | PHA | 63 | PRP | 32 | A | I |  | 0 | 0 |  |  | 2011-04-01 | 2012-08-01 | 2012-03-31 |  | 2016-04-01 | 2016-04-01 | 65000 | -13395 | 51605 | 51604.83 | 100% | 0.17 | 0.01 |  | 4875 | -1005 | 3870 | 0 | 0 | Project completed in Apr 2016. |  |  |  | NON-INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (foam sector) | Multi-Year | AFR | LIB | PHA | 75 | INV | 36 | A | I | HCFC | 23.8 | 0 |  |  | 2015-11-01 |  | 2018-12-01 | 2019-06-01 |  |  | 1690627 | 0 | 1690627 | 0 | 0% | 1690627 | 608200 | 500000 | 118344 | 0 | 0 | 118344 | 42574 | - TORs for three beneficiaries prepared. - Mission could not take place due to security reasons. - One beneficiary (Alyem) has not responded yet to draft TOR and grant agreement; the procurement of equipment is on hold. The procurement for Al Najah is in a stage that the supplier is exploring the ways for safe delivery at site. - The procurement of equipment for Al Amal Al Akhdar is delayed since the ownership of the company was changed; UNIDO purchase order will be issued only after the new owner is fully confirmed by NOU. Milestones achieved: 1. Grant agreement submitted to beneficiary: Yes 2. Grant agreement signature: two beneficiaries signed; one counterpart, pending. One change in ownership to be confirmed. 3. Bids prepared and requested: Yes 4. Contracts awarded: yes 5. Equipment delivered: Not yet 6. Commissioning and trial runs: No 7. De-commissioning and/or destruction of redundant baseline equipment: No Activities planned but not implemented, reasons and strategy: TOR and Implementation Agreement for one beneficiary on hold. Actions towards next goals: equipment to be delivered. Beneficiaries to receive training abroad. Was there any delay during the reporting year? No If yes, reasons and action plan. Action plan: is based on the Agreement on Implementation procedures. Any recurring problem? No Any impact on project completion date: if unstable situation in Libya persists delays are likely. If yes, implications: likely delays in project implementation/completion if unstable situation in Libya continues Any action required by Executive Committee? No | - Study tour for beneficiaries and NOU to Turkey is initiated. Actions towards next goals: equipment to be delivered. Was there any delay during the reporting year? No Any recurring problem? Security situation in the country Any impact on project completion date: if unstable situation in Libya persists delays are likely. If yes, implications: likely delays in project implementation/completion if unstable situation in Libya continues. Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | AFR | LIB | PHA | 75 | INV | 37 | A | I | HCFC | 0.3 | 0 |  |  | 2015-11-01 | 2016-07-01 | 2018-12-01 | 2019-06-01 |  |  | 27323 | 0 | 27323 | 4451.53 | 16.29% | 22871.47 | 6994.54 | 5000 | 1913 | 0 | 0 | 1913 | 489.6178 | -International consultant recruited. - Workshop for government offices concerned (Ministry of Trade, Customs Department, Environment General Authority (EGA) etc.)and importers could not take place due to security reasons. - Project and programme planning and training on quota and licensing procedures for NOU and EGA technical consultant took place at UNIDO HQ in Vienna. Milestones achieved: 1: - Legal arrangements - Yes 2: - Initial stages of project implementation began - Yes 3: - Intermediate goals achieved - Yes 4:- Project completion and follow-up - No Activities planned but not implemented, reasons and strategy: See above. Actions towards next goals: Provide assistance to NOU on monitoring, licensing and quota set-up based on information from importers, foam and refrigeration/AC manufacturing sectors. Country is in compliance with the Action Plan. Was there any delay during the reporting year? No Any recurring problem? Security situation in the country Any impact on project completion date: if unstable situation in Libya persists delays are likely. If yes, implications: likely delays in project implementation/completion if unstable situation in Libya continues Any action required by Executive Committee? No | - NOU collaboration and monitoring with relevant government offices is going on. Actions towards next goals: Provide assistance to NOU on monitoring, licensing and quota set-up based on information from importers, foam and refrigeration/AC manufacturing sectors. Was there any delay during the reporting year? No Any recurring problem? Security situation in the country Any impact on project completion date: if unstable situation in Libya persists delays are likely. If yes, implications: likely delays in project implementation/completion if unstable situation in Libya continues Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Preparation of investment project in the Refrigeration sector | Individual | AFR | LIB | REF | 30 | PRP | 02 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-10-01 | 2001-04-01 |  | 2003-07-01 | 2004-04-01 | 20000 | -550 | 19450 | 19449.96 | 100% | 0.04 | 0 |  | 2600 | -76 | 2524 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS in the production of refrigerators and freezers at Electrical Household Appliance Manufacturing | Individual | AFR | LIB | REF | 32 | INV | 03 | A | I | CFC | 53.4 | 53.4 |  |  | 2000-12-01 | 2001-09-01 | 2003-06-01 |  | 2004-03-01 | 2009-12-01 | 558113 | -1527 | 556586 | 556585.87 | 100% | 0.13 | 0 |  | 71392 | -168 | 71224 | 0 | 0 | FIN
CLO | UNIDO | Project preparation in the commercial refrigeration sector | Individual | AFR | LIB | REF | 33 | PRP | 11 | A | I |  | 0 | 0 |  |  | 2001-03-01 |  | 2002-04-01 |  |  | 2003-06-01 | 15000 | -15000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 1950 | -1950 | 0 | 0 | 0 | CLO |  |  |  | INV
FIN | UNIDO | Preparation of an investment project in the commercial refrigeration sector | Individual | AFR | LIB | REF | 36 | PRP | 20 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2003-06-01 | 2003-04-01 |  | 2003-10-01 | 2004-09-01 | 20000 | -722 | 19278 | 19277.77 | 100% | 0.23 | 0 |  | 2600 | -98 | 2502 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of country programme | Individual | AFR | LIB | SEV | 27 | CPG | 01 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-10-01 | 1999-12-01 |  | 2000-12-01 | 2002-09-01 | 80000 | -3440 | 76560 | 76560.15 | 100% | -0.15 | 0 |  | 10400 | -463 | 9937 | 0 | 0 | FIN
FIN | UNIDO | Creation of the National Ozone Unit | Individual | AFR | LIB | SEV | 32 | INS | 04 | N | I |  | 0 | 0 |  |  | 2000-12-01 | 2002-12-01 | 2004-01-01 |  | 2009-06-01 | 2011-12-01 | 157000 | -48043 | 108957 | 108956.98 | 100% | 0.02 | 0 |  | 20410 | -6246 | 14164 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | National phase-out plan | Individual | AFR | LIB | SEV | 38 | PRP | 21 | A | I | CFC | 0 | 0 |  |  | 2002-11-01 | 2003-09-01 | 2003-12-01 |  | 2005-06-01 | 2006-08-01 | 40000 | -468 | 39532 | 39531.5 | 100% | 0.5 | 0 |  | 5200 | -61 | 5139 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Renewal of institutional strengthening project (phase II) | Individual | AFR | LIB | SEV | 59 | INS | 31 | N | I |  | 0 | 0 |  |  | 2009-11-01 | 2009-12-01 | 2011-11-01 |  | 2014-03-01 | 2015-09-01 | 73702 | 62363 | 136065 | 136064.54 | 100% | 0.46 | 0 |  | 5528 | 4677 | 10205 | 0 | 0 | FIN |  |  |  | NON-INV
COM | UNIDO | Renewal of institutional strengthening project (phase III: 12/2013-11/2015) | Individual | AFR | LIB | SEV | 71 | INS | 34 | N | I |  | 0 | 0 |  |  | 2013-12-01 | 2014-07-01 | 2015-11-30 |  | 2016-12-01 |  | 136065 | 0 | 136065 | 132021.04 | 97.03% | 4043.96 | 2361.23 | 2361 | 9525 | 0 | 9241 | 284 | 165.2861 | The project is completed as of December 2016. | Financial closure is ongoing. |  |  | NON-INV
COM | UNIDO | Renewal of institutional strengthening project (phase IV: 12/2015-11/2017) | Individual | AFR | LIB | SEV | 74 | INS | 35 | N | I |  | 0 | 0 |  |  | 2015-05-01 | 2015-10-01 | 2017-11-30 |  | 2016-12-01 |  | 68033 | 0 | 68033 | 43876.93 | 64.49% | 24156.07 | 26447.65 | 22000 | 4762 | 0 | 0 | 4762 | 1851.3355 | Project was approved for one year duration due to risk of non-compliance. NOU was fully staffed and substantive progress was achieved in legislation enforcement. Quotas for 2016 were established and are monitored on regular basis. Disbursement difficulties due to security situation were addressed successfully by NOU first half of 2016, however, disbursement delays remain a risk due to the security issues and political changes. The project was operationally completed in 2016, however financial completion is pending due to expenditures verification Milestone 1: NOU staff contracts released - Yes Milestone 2: Public awareness activities organized for interested stakeholders - yes Actions towards next goals: NA Was there any delay during the reporting year? No Any recurring problem? yes. Disbursements difficulties due to security situation Any impact on project completion date: Yes If yes, implications: delayed disbursements in field were addressed by UNIDO, counterpart and UNDP field Office, however, it produced delays in financial completion of the project Any action required by Executive Committee? No | Project completed. Financial closure is ongoing. |  |  | NON-INV
ONG | UNIDO | Survey of ODS alternatives at the national level | Individual | AFR | LIB | SEV | 75 | TAS | 38 | A | I |  | 0 | 0 |  |  | 2015-11-01 | 2016-01-01 | 2017-12-01 | 2017-12-01 |  |  | 110000 | 0 | 110000 | 44218.26 | 40.2% | 65781.74 | 21523.47 | 10000 | 9900 | 0 | 0 | 9900 | 1937.1123 | - TORs for international and national consultants prepared; - International consultant recruited. Recruitment of national consultants did not take place; travel within the country considered in-secure. Abroad travel of NOU and its technical assistant to attend workshops and other meetings, have been facilitated to build capacity. Milestones: 1. First mission/Working arrangements agreed: Yes 2. ToR for HCFC survey completed: Yes 3. Local institutions identified: Yes 4. Experts recruited: No (not completed for national experts) 5. Stakeholders workshop held: No 6. HFC survey completed: No 7. All technical input completed: No 8. Draft document completed: No | - Draft report, based on a desk study to be prepared. Decision to be consulted with NOU according to situation in the country and importance and weight of relevant assumptions if the situation not improved. |  |  | NON-INV
ONG | UNIDO | Renewal of institutional strengthening project (second year of phase IV: 12/2016-11/2017) | Individual | AFR | LIB | SEV | 77 | INS | 39 | N | I |  | 0 | 0 |  |  | 2016-11-01 |  | 2017-11-30 | 2017-11-17 |  |  | 87082 | 0 | 87082 | 0 | 0% | 87082 | 0 | 40000 | 6096 | 0 | 0 | 6096 | 0 | Approved without prejudice to the operation of the Montreal Protocol’s mechanism on-non compliance | NOU work plan for the year 2017 has been agreed. NOU is fully staffed and activities has been initiated in line with the project document.
FIN | UNDP | Project preparation for a terminal phase-out management plan | Individual | AFR | LIR | PHA | 49 | PRP | 09 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-04-01 | 2006-07-01 |  | 2007-12-01 | 2009-12-01 | 12000 | -617 | 11383 | 11383 | 100% | 0 | 0 | 0 | 900 | -46.28 | 853.725 | -0.005 | 0 | Completed in 2007. Financially completed in 2009. |  | 2006 |  | Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | LIR | PHA | 49 | PRP | 10 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2006-12-01 | 2007-07-01 |  | 2007-12-01 | 2008-12-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 |  | 2340 | 0 | 2340 | 0 | 0
FIN | UNDP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | LIR | PHA | 53 | INV | 13 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-08-01 | 2009-11-01 |  | 2009-12-01 | 2011-12-01 | 104000 | 0 | 104000 | 104000 | 100% | 0 | 0 | 0 | 9360 | 0 | 9360 | 0 | 0 | Completed in 2009. Financially completed in 2011. |  | 2007 |  | Investment
FIN | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-year | AFR | LIR | PHA | 53 | TAS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-03-01 |  | 2009-03-01 | 2010-12-01 | 131500 | 0 | 131500 | 131500 | 100% | 0 | 0 |  | 17095 | 0 | 17095 | 0 | 0
FIN | UNDP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | LIR | PHA | 57 | INV | 16 | N | I | CFC | 8.4 | 8.4 | 0 | 0 | 2009-04-01 | 2009-05-01 | 2011-03-01 |  | 2009-12-01 | 2011-12-01 | 28000 | -1436.95 | 26563.05 | 26563 | 100% | 0.05 | 0 | 0 | 2520 | -129.33 | 2390.67 | 0 | 0 | Completed in 2009. Financially completed in 2011. |  | 2009 |  | Investment
FIN | Germany | Preparation of a HCFC phase-out management plan |  | AFR | LIR | PHA | 57 | PRP | 14 | A | I | HCFC | 0 |  | 0 |  | 2009-04-01 | 2009-09-01 | 2010-03-01 |  | 2010-12-01 | 2011-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | HPMP was submitted as planned in Dec 2010.
FIN | UNEP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | LIR | PHA | 57 | TAS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-07-01 | 2010-03-01 |  | 2011-12-01 | 2012-12-01 | 81500 | -5000 | 76500 | 76500 | 100% | 0 | 0 |  | 10595 | -650 | 9945 | 0 | 0
COM | Germany | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | LIR | PHA | 63 | INV | 18 | A | I | HCFC | 0.6 | 0.6 | 0 |  | 2011-04-01 | 2011-06-01 | 2015-03-01 |  | 2015-09-01 |  | 157500 | 0 | 157500 | 157500 | 100% | 0 | 0 | 0 | 20475 | 0 | 20475 | 0 |  | Demo conversion of 15 R22 AC units was completed. Ref Association developed Code of practice for technicians and distributed to the industry. |  |  |  | INV
ONG | Germany | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | AFR | LIR | PHA | 74 | INV | 21 | A | I | HCFC | 1.4 |  | 0 |  | 2015-05-01 | 2015-11-01 | 2020-05-01 | 2020-05-01 |  |  | 126000 | 0 | 126000 | 16192 | 12.85% | 109808 | 0 | 30000 | 16380 | 0 | 2105 | 14275 |  | Curriculum upgrade has been completd with the inclusion of Safe handling of HCs into the MVTC training course ensuring that all graduates have the necessary skills to handle HCs. 3 customs trainings were completed. | A detailed equipment list was developed by the MVTC for conducting hands on trainings based on upgraded curriculum. A purchase order has bene placed and equipment will be supplied in the coming weeks.
FIN | Germany | Implementation of the RMP: improved servicing and maintenance within the refrigeration sector and recovery and recycling | RMP Update | AFR | LIR | REF | 41 | TAS | 04 | A | I | CFC | 10.1 | 10.1 | 0 |  | 2003-12-01 | 2005-06-01 | 2006-12-01 |  | 2009-11-01 | 2011-12-01 | 92400 | 0 | 92400 | 92400 | 100% | 0 | 0 | 0 | 12012 | 0 | 12012 | 0 | 0 | PCR submitted in September 2010
FIN | Germany | Implementation of the RMP: incentive programme for the commercial and industrial refrigeration end-user sector | RMP Update | AFR | LIR | REF | 41 | TAS | 05 | A | I | CFC | 11.7 | 1.5 | 0 |  | 2003-12-01 | 2005-04-01 | 2008-12-01 |  | 2009-12-01 | 2011-12-01 | 107350 | 0 | 107350 | 107350 | 100% | 0 | 0 | 0 | 13996 | 0 | 13996 | 0 | 0 | PCR submitted in September 2010
FIN | Germany | Implementation of the RMP: MAC recovery/recycling of CFC-12 | Individual | AFR | LIR | REF | 41 | TAS | 06 | A | I | CFC | 6.8 | 3 | 0 |  | 2003-12-01 | 2005-04-01 | 2006-12-01 |  | 2008-12-01 | 2011-12-01 | 61858 | 0 | 61858 | 61858 | 100% | 0 | 0 | 0 | 8042 | 0 | 8042 | 0 | 0 | PCR submitted in September 2010
FIN | Germany | Implementation of the RMP: monitoring the activities in the RMP | RMP Update | AFR | LIR | REF | 41 | TAS | 08 | A | I | CFC | 1.7 | 0 | 0 |  | 2003-12-01 | 2003-12-01 | 2006-12-01 |  | 2009-12-01 | 2011-12-01 | 15455 | 0 | 15455 | 15455 | 100% | 0 | 0 | 0 | 2009 | 0 | 2009 | 0 | 0 | PCR submitted in July 2010
FIN | Germany | Implementation of the RMP: training of trainers in code of good refrigeration practices and establishment of national refrigeration demonstration centre | Individual | AFR | LIR | REF | 41 | TRA | 03 | A | I |  | 13 | 13 | 0 |  | 2003-12-01 | 2004-03-01 | 2006-12-01 |  | 2008-12-01 | 2011-12-01 | 119460 | 0 | 119460 | 119460 | 100% | 0 | 0 | 0 | 15530 | 0 | 15530 | 0 | 0 | Project completed. PCR submitted in July 2010
FIN | UNEP | Implementation of the RMP: customs training programme | Individual | AFR | LIR | REF | 41 | TRA | 07 | A | I | CFC | 4.4 | 4.4 | 0 | 0 | 2003-12-01 | 2004-08-01 | 2004-12-01 |  | 2006-06-01 | 2008-12-01 | 40040 | -2389 | 37651 | 37651 | 100% | 0 | 0 |  | 5205 | -311 | 4894 | 0 | 0
FIN | UNEP | Country programme preparation | Individual | AFR | LIR | SEV | 27 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-03-01 | 2000-07-01 |  | 2003-09-01 | 2008-12-01 | 50000 | -17000 | 33000 | 33000 | 100% | 0 | 0 |  | 6500 | -2210 | 4290 | 0 | 0 |  |  |  | 2003-12-01
FIN | UNEP | Establishment of the ozone unit | Individual | AFR | LIR | SEV | 41 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-06-01 | 2006-12-01 |  | 2007-12-01 | 2007-12-01 | 127820 | 0 | 127820 | 127820 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase II) | Individual | AFR | LIR | SEV | 51 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2007-03-01 | 2007-06-01 | 2009-03-01 |  | 2009-03-01 | 2010-12-01 | 85213 | 0 | 85213 | 85213 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | AFR | LIR | SEV | 57 | INS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-07-01 | 2011-03-01 |  | 2010-11-01 | 2011-11-01 | 85213 | 0 | 85213 | 85213 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | LIR | SEV | 63 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-11-01 | 2013-03-01 |  | 2013-10-01 | 2014-12-01 | 85213 | 0 | 85213 | 85213 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of the institutional strengthening project (phase V: 4/2013-3/2015)) | Individual | AFR | LIR | SEV | 69 | INS | 20 | A | I |  | 0 |  | 0 |  | 2013-04-01 | 2013-12-01 | 2015-03-01 |  | 2016-05-01 |  | 85213 | 0 | 85213 | 39000 | 45.77% | 46213 | 19500 | 46213 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): _ The licensing and quota systems are in place and operational. The NOU registered all importers of HCFCs and organized stakeholders’ workshop to allocate HCFC licenses and quotas to importers. The NOU conducted three inspection visits to monitor distribution of HCFCs to check compliance with the quotas allocated. The NOU conducted two RAC training workshops and two custom training workshops, and trained 80 technicians and 40 custom officers respectively. The NOU celebrated the 2016 international ozone day with several activities. The NOU collected, processed and submitted 2015 Country Programme and Article 7 Data reports. The NOU participated in all Montreal Protocol meetings organized in 2016. Project activities are completed__ Legal arrangements (actual/planned): The SSFA was drafted and signed by UNEP and the Government of Liberia in November 2013. Initial stages of project implementation(actual/planned): Yes___ Intermediate goals achieved (actual/planned): __yes_ Project completion and follow up: No___ First disbursement date (actual/planned): _Dec 2013__ All funds disbursed (yes/no): _Yes__ Any delay?(yes/no): ___ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): No___ If Yes, is any action required by ExCom: __N/A_ | Project completed
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | AFR | LIR | SEV | 74 | TAS | 22 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-03-01 | 2016-05-01 | 2017-05-01 |  |  | 40000 | 0 | 40000 | 5050 | 12.62% | 34950 | 34950 | 3495 | 5200 | 0 | 656.5 | 4543.5 | 4543.5 | Brief progress report (actual/planned): The first stakeholders meeting was organized by the NOU on 1st June, 2016 at Corina Hotel in Monrovia and 40 participants from the ODS Alternative user sectors and importers attended. The main goal of the meeting was to sensitize the government and industry on the survey and agree on the plan for the Survey of ODS alternatives at the national level and obtain support of main national stakeholders. In addition to the ODS alternatives initiation stakeholders workshop, the Ozone Unit carried out two weeks awareness between 13 and 24 June 2016, respectively, informing stakeholders and the general public about the conduct of the ODS alternative survey as well as the objectives of the survey and what benefits the country stands to reap. The awareness was carried out in three dailies and four radio stations, including the Nations Station (ELBC), Radio ELWA, Radio Gbehzon (Grand Bassa County), and Nimba Community Radio. One National Consultant was hired in March 2016 by the NOU to support the data collection. The National Consultant assisted the NOU in the identification of the current use of ODS alternatives by substance/sector and collection of import/export data for the substances for the past a couple of years. The NOU, on 15 July, 2016, conducted a one day refresher workshop for ODS alternatives data collectors from the Liberian Refrigeration Union. A total of 21 data collectors were in attendance. Samples of the data collection forms for the different sectors were demonstrated. The data collectors praised and appreciated the refresher workshop for enhancing their knowledge. The National Consultant also provided support in establishing growth patterns in use by substance/sector and in compiling data on available ODS alternatives for various applications. The NOU and the National Consultant drafted and cross checked the information to ensure the completion of end-user surveys, collection, analysis, and aggregation of consumption data. The various sections of the report were drafted. The second stakeholders meeting was organized by the NOU in November 2016in Monrovia with the main goal to organise consultations with representatives of the government and private sector to finalize the outcomes of the Survey of ODS alternatives and discuss potential opportunities for introduction of those alternatives in the country. A total of 45 participants from the sectors using ODS Alternatives were in attendance. The draft report was prepared by the NOU and the National Consultant. It was reviewed and finalized based on the format approved by ExCom decision 75/67 as contained in document UNEP/OzL.Pro/ExCom/75/77/Rev.1 after incorporating inputs/ comments raised during National Stakeholders’ workshop. The final report was submitted to UNEP in November 2016 for final review and submission to MLFS. The NOU participated in the ODS Alternative Thematic workshop held in December 2016 to refine the draft report according to the revised template for the report. The report has been finally submitted to UNEP Legal arrangements (actual/planned): The SSFA was drafted and signed by UNEP and the Government of Liberia in February 2016. ____Initial stages of project implementation(actual/planned): _Yes__ Intermediate goals achieved (actual/planned): Yes___ Project completion and follow up: _No__ First disbursement date (actual/planned): _Feb 2016__ All funds disbursed (yes/no): No___ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): __N/A_ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned):The NOU incorporated comments from UNEP ROA and Paris and re-submitted final ODS survey report.
ONG | UNEP | Extension of the institutional strengthening project (phase VI: 11/2015-10/2017) | Individual | AFR | LIR | SEV | 75 | INS | 23 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-08-01 | 2017-11-01 | 2018-05-01 |  |  | 109073 | 0 | 109073 | 39.2 | 0.03594% | 109033.8 | 109033.8 | 10903.38 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): _ The licensing and quota systems are in place and operational. The NOU registered all importers of HCFCs and organized stakeholders’ workshop to allocate HCFC licenses and quotas to importers. The NOU conducted three inspection visits to monitor distribution of HCFCs to check compliance with the quotas allocated. The NOU conducted two RAC training workshops and two custom training workshops, and trained 80 technicians and 40 custom officers respectively. The NOU celebrated the 2016 international ozone day with several activities. The NOU collected, processed and submitted 2015 Country Programme and Article 7 Data reports. The NOU participated in all Montreal Protocol meetings organized in 2016. Project activities are completed__ Legal arrangements (actual/planned): The SSFA was drafted and signed by UNEP and the Government of Liberia in November 2013. Initial stages of project implementation(actual/planned): Yes___ Intermediate goals achieved (actual/planned): __yes_ Project completion and follow up: No___ First disbursement date (actual/planned): _Dec 2013__ All funds disbursed (yes/no): _No__ Any delay?(yes/no): ___ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): No___ If Yes, is any action required by ExCom: __N/A_ | Brief progress report (actual/planned): The NOU continues to monitor imports and trade of ODS and ODS related equipment. Collection of the 2016 data on ODS imports and consumption has been completed and is being analyzed for submission. NOU commenced preparation of national legislative requirement processes in planning for ratification of Kigali amendment.
FIN | UNIDO | Training and awareness workshop in the fumigants sector (methyl bromide) | Individual | AFR | MAG | FUM | 45 | TAS | 09 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-11-01 | 2006-04-01 |  | 2006-12-01 | 2009-04-01 | 40000 | -724 | 39276 | 39275.61 | 100% | 0.39 | 0 |  | 3600 | -65 | 3535 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | MAG | PHA | 49 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2006-11-01 | 2007-07-01 |  | 2007-07-01 | 2008-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNIDO | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | MAG | PHA | 52 | INV | 16 | A | I |  | 0 | 0 |  |  | 2007-07-01 | 2007-12-01 | 2008-07-01 |  | 2008-11-01 | 2009-05-01 | 78000 | -13 | 77987 | 77986.83 | 100% | 0.17 | 0 |  | 7020 | -1 | 7019 | 0 | 0 | FIN |  |  |  | INV
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | MAG | PHA | 52 | TAS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-10-01 | 2008-07-01 |  | 2009-07-01 | 2010-12-01 | 133000 | 0 | 133000 | 133000 | 100% | 0 | 0 |  | 17290 | 0 | 17290 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | MAG | PHA | 55 | PRP | 17 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2011-01-01 | 2011-07-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 |  | 11050 | 0 | 11050 | 0 | 0
FIN | UNIDO | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | MAG | PHA | 56 | INV | 19 | A | I | CFC CTC | 2.4 | 2.4 |  |  | 2008-11-01 | 2009-02-01 | 2009-11-30 |  | 2009-11-01 | 2010-12-01 | 47000 | -2474 | 44526 | 44526 | 100% | 0 | 0 |  | 4230 | -223 | 4007 | 0 | 0 | FIN |  |  |  | INV
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | MAG | PHA | 56 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-07-01 | 2009-11-01 |  | 2011-03-01 | 2011-07-01 | 87000 | 0 | 87000 | 87000 | 100% | 0 | 0 |  | 11310 | 0 | 11310 | 0 | 0
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | MAG | PHA | 62 | INV | 22 | A | I |  | 0 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2013-12-31 | 2017-12-01 |  |  | 140000 | 0 | 140000 | 126101.79 | 90.07% | 13898.21 | 1824.17 | 12000 | 10500 | 0 | 9458 | 1042 | 137 | - Remaining balance will be used towards training on reclamation and incentives for reclamation and for conversion of air-conditioners. - 3nd tranche for UNIDO was approved at the 76th ExCom. - Funds from 1st tranche should be combined with 2nd tranche to continue activities. Milestone 1: Recruitment of national expert Was there any delay during the reporting year? Yes -National expert required more time to select potential beneficiaries Was there any delay during the reporting year? Yes, the National expert required more time to select potential beneficiaries. Any recurring problem? No Any impact on project completion date: Yes Any action required by Executive Committee? No | '- Remaining balance will be used towards training on reclamation and incentives for reclamation and for conversion of air-conditioners. - 3nd tranche for UNIDO was approved at the 76th ExCom. - Funds from 1st tranche should be combined with 2nd tranche to continue activities. Milestone 1: Recruitment of national expert - Selection of beneficiaries ongoing Was there any delay during the reporting year? Yes, the National expert required more time to select potential beneficiaries. Any recurring problem? No Any impact on project completion date: Yes. Any action required by Executive Committee? No |  |  | INV
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | MAG | PHA | 62 | TAS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-05-01 | 2013-12-01 |  | 2013-12-01 | 2014-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0
COM | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | AFR | MAG | PHA | 70 | TAS | 24 | A | I |  | 0.9 |  | 0 |  | 2013-07-01 | 2014-08-01 | 2016-07-01 |  | 2016-12-01 |  | 70000 | 0 | 70000 | 36380 | 51.97% | 33620 | 33620 | 33620 | 9100 | 0 | 4729.4 | 4370.6 | 4370.6 | Brief progress report (actual/planned): Country signed the SSFA in May 2014. In 2016, 66 RAC technicians and 53 customs officers were trained. Final payment disbursed in August 2016. Legal arrangements (actual/planned): Agreement signed in August 2014. All activities under the SSFA are completed (as planned) _YES___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ YES __ First disbursement date (actual/planned): _1st disbursement done in May 2014 __ All funds disbursed (yes/no): _ YES, Final payment disbursed in August 2016.__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a __ | Brief progress report (actual/planned): Country signed the SSFA in May 2014. In 2016, 66 RAC technicians and 53 customs officers were trained. Final payment disbursed in August 2016. Legal arrangements (actual/planned): Agreement signed in August 2014. All activities under the SSFA are completed (as planned) _YES_. SSFA expired in May 2016 with balance US $ 0. First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ YES __ First disbursement date (actual/planned): _1st disbursement done in May 2014 __ All funds disbursed (yes/no): _ YES, Final payment disbursed in August 2016.__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
ONG | UNIDO | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | AFR | MAG | PHA | 76 | INV | 28 | A | I | HCFC | 2.8 | 0 |  |  | 2016-05-01 |  | 2020-05-31 | 2020-05-31 |  |  | 120000 | 0 | 120000 | 0 | 0% | 120000 | 0 | 15000 | 9000 | 0 | 0 | 9000 | 0 | 3nd tranche for UNIDO was approved at the 76th ExCom. | Milestone 1: Selection of beneficiaries is ongoing. |  |  | INV
ONG | UNEP | HCFC phase-out management plan (stage I, third tranche) | Multi-year | AFR | MAG | PHA | 76 | TAS | 27 | A | I |  | 0 |  | 0 |  | 2016-05-01 | 2016-12-01 | 2018-12-01 | 2018-12-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 60000 | 6000 | 7800 | 0 | 0 | 7800 | 7800 | Newly approved project | Brief progress report (actual/planned): Country reported 2015 Art5 data and 2015 CP data. Legal arrangements (actual/planned): Agreement signed in Nov. 2016. First payment sent in Dec. 2016. All activities under the SSFA are completed (as planned) __No_ First mission (actual/planned): _ April 2017 __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in Dec. 2016 __ All funds disbursed (yes/no): Yes_ _ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
FIN | France | Implementation of the RMP: set up a national recovery and recycling network |  | AFR | MAG | REF | 29 | TAS | 05 | A | I | CFC | 13.9 | 10.2 | 0 |  | 1999-11-01 | 2002-05-01 | 2002-12-01 |  | 2004-08-01 | 2005-01-01 | 82700 | -11895 | 70805 | 70805 | 100% | 0 |  | 0 | 4135 | -595 | 3540 | 0 |  | Project completed.
FIN | France | Implementation of the RMP: training of personnel in charge of control and monitoring of imports of ODS |  | AFR | MAG | REF | 29 | TRA | 02 | A | I | CFC | 4.4 | 3.2 | 0 |  | 1999-11-01 | 2002-05-01 | 2000-12-01 |  | 2003-06-01 | 2005-01-01 | 26000 | -851 | 25149 | 25149 | 100% | 0 |  | 0 | 1300 | -43 | 1257 | 0 |  | Project completed.
FIN | France | Implementation of the RMP: training of trainers and refrigeration technicians in good service practices |  | AFR | MAG | REF | 29 | TRA | 03 | A | I | CFC | 7.8 | 5.7 | 0 |  | 1999-11-01 | 2002-05-01 | 2000-12-01 |  | 2004-08-01 | 2005-01-01 | 46200 | -1519 | 44681 | 44681 | 100% | 0 |  | 0 | 2310 | -76 | 2234 | 0 |  | Project completed.
FIN | UNEP | Preparation of refrigerant management plan update | RMP update | AFR | MAG | REF | 44 | PRP | 08 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-05-01 | 2005-12-01 |  | 2005-06-01 | 2007-06-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0
FIN | France | Implementation of the RMP: recovery and recycling component | RMP | AFR | MAG | REF | 47 | TAS | 12 | A | I | CFC | 6.8 | 6 | 0 |  | 2005-11-01 | 2008-03-01 | 2007-06-01 |  | 2010-12-01 | 2005-03-01 | 40500 | 0 | 40500 | 40500 | 100% | 0 |  |  | 5265 | 0 | 5265 | 0 |  | Project completed.
FIN | UNEP | Implementation of the RMP: training of customs officers and other officers to control and follow-up of ODS and its containers | Individual | AFR | MAG | REF | 47 | TRA | 10 | A | I | CFC | 3.7 | 3.7 | 0 | 0 | 2005-11-01 | 2006-02-01 | 2006-12-01 |  | 2006-12-01 | 2007-12-01 | 22000 | 0 | 22000 | 22000 | 100% | 0 | 0 |  | 2860 | 0 | 2860 | 0 | 0
FIN | UNEP | Implementation of the RMP: training of maintenance technicians including small craftsmen of informal sector | Individual | AFR | MAG | REF | 47 | TRA | 11 | A | I | CFC | 4.2 | 4.2 | 0 | 0 | 2005-11-01 | 2006-02-01 | 2006-12-01 |  | 2006-12-01 | 2007-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0
FIN | France | Country programme preparation |  | AFR | MAG | SEV | 21 | CPG | 01 | A | D |  | 0 |  | 0 |  | 1997-02-01 | 1997-08-01 | 1998-02-01 |  | 1999-09-01 | 1999-12-01 | 40000 | -3019 | 36981 | 36981 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Projet achevé. PCR soumis
FIN | UNEP | Creation of a Ozone Unit | Individual | AFR | MAG | SEV | 29 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-11-01 | 2002-12-01 |  | 2004-07-01 | 2007-06-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (phase II) | Individual | AFR | MAG | SEV | 43 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-11-01 | 2006-07-01 |  | 2006-12-01 | 2008-12-01 | 60700 | 0 | 60700 | 60700 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase III) | Individual | AFR | MAG | SEV | 49 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-07-01 | 2008-06-01 |  | 2009-06-01 | 2010-12-01 | 60700 | 0 | 60700 | 60700 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase IV) | Individual | AFR | MAG | SEV | 59 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-09-01 | 2011-11-01 |  | 2012-07-01 | 2013-12-01 | 32879 | 27821 | 60700 | 60700 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Renewal of institutional strengthening project (phase V: 7/2012-6/2014) | Individual | AFR | MAG | SEV | 67 | INS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2012-12-01 | 2014-06-01 |  | 2015-12-01 |  | 60700 | 0 | 60700 | 60700 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed | Project completed
ONG | UNEP | Renewal of institutional strengthening project (phase VI: 12/2014-11/2016) | Individual | AFR | MAG | SEV | 73 | INS | 25 | A | I |  | 0 |  | 0 |  | 2014-11-01 | 2016-02-01 | 2016-11-01 | 2017-12-01 |  |  | 60700 | 0 | 60700 | 19171 | 31.58% | 41529 | 41529 | 4152.9 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Country signed the SSFA in April 2015. Country reported 2015 CP data and 2015 Art7 data. Ozone day celebrated in September 2016. Legal arrangements (actual/planned): Agreement signed in April 2015.First payment: February 2016. All activities under the SSFA are completed (as planned) No__ First mission (actual/planned): _ N/A -TOR completed (actual/planned): _ Yes __ First disbursement date (actual/planned): _1st disbursement done in February 2016__ All funds disbursed (yes/no): _ No__ Any delay? (yes/no): No ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): _ No __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Brief progress report (actual/planned): Country signed the SSFA in April 2015. Country reported 2015 CP data and 2015 Art7 data. Ozone day celebrated in September 2016. Legal arrangements (actual/planned): Agreement signed in April 2015.First payment: February 2016. All activities under the SSFA are completed (as planned) No. NOU trained 66 RAC technicians and 53 customs officers__ First mission (actual/planned): _ N/A -TOR completed (actual/planned): _ Yes __ First disbursement date (actual/planned): _1st disbursement done in February 2016__ All funds disbursed (yes/no): _ No__ Any delay? (yes/no): No ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): _ No __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a __
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | AFR | MAG | SEV | 74 | TAS | 26 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-04-01 | 2016-05-01 | 2017-10-01 |  |  | 110000 | 0 | 110000 | 110000 | 100% | 0 | 0 | 0 | 14300 | 0 | 14300 | 0 | 0 | Brief progress report (actual/planned): Country signed the SSFA in February 2016. First payment sent in April 2016. Local consultants hired in May 2016 and survey activities started in June 2016.. Legal arrangements (actual/planned): Agreement signed in February 2016. All activities under the SSFA are completed (as planned) No__First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ Yes __ First disbursement date (actual/planned): _1st disbursement done in April 2016 __ All funds disbursed (yes/no): _ No__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Brief progress report (actual/planned): Country signed the SSFA in February 2016. First payment sent in April 2016. Local consultants hired in May 2016 and survey activities started in June 2016. Country submitted the Non ODS survey report in January 2017. Legal arrangements (actual/planned): Agreement signed in February 2016. All activities under the SSFA are completed (as planned) No__First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ Yes __ First disbursement date (actual/planned): _1st disbursement done in April 2016 __ All funds disbursed (yes/no): _ No__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
ONG | UNEP | Renewal of institutional strengthening project (phase VII: 1/2017-12/2018) | Individual | AFR | MAG | SEV | 77 | INS | 29 | A | I |  | 0 |  | 0 |  | 2016-12-01 |  | 2018-12-01 | 2018-12-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | Newly approved project | Brief progress report (actual/planned): Project newly approved. Agreement not signed yet. Legal arrangements (actual/planned): Agreement not signed yet. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement _no __ All funds disbursed (yes/no): _ Final payment _no___ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
FIN | UNDP | Safety and technical programme to aid manufacturers of aerosol products | Individual | ASP | MAL | ARS | 12 | TAS | 30 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-10-01 | 1996-03-01 |  | 1995-12-01 | 2001-12-01 | 145700 | -40377 | 105323 | 105323 | 100% | 0 | 0 | 0 | 18941 | -5249.01 | 13691.99 | 0 | 0 | Completed in 1995. Financially completed in 2001. |  | 1994 |  | Non-Investment
FIN | IBRD | Conversion project at Argon Malaysia, Sdn. Bhd | Individual | ASP | MAL | ARS | 15 | INV | 53 | N | I | CFC | 38 | 38 | 0 | 0 | 1994-12-01 | 1997-04-01 | 1995-12-01 |  | 1997-08-01 | 1997-08-01 | 131200 | 0 | 131200 | 131200 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1997-04-01 | INV | 0
FIN | IBRD | Conversion of the aerosol filling plant Kontrak Manufacturing Services Sdn. Bhd. | Individual | ASP | MAL | ARS | 15 | INV | 55 | N | I | CFC | 200 | 200 | 0 | 0 | 1994-12-01 | 1997-06-01 | 1995-12-01 |  | 1998-10-01 | 1998-11-01 | 618000 | 0 | 618000 | 618000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1997-07-01 | INV | 0
FIN | UNDP | Conversion to hydrocarbon technology in the manufacture of aerosol products at Maya Chemical Industries Sdn., Bhd. | Individual | ASP | MAL | ARS | 17 | INV | 60 | A | R | CFC | 13 | 13 | 0 | 0 | 1995-07-01 | 1995-11-01 | 1996-01-01 |  | 1995-11-01 | 1998-12-01 | 37808 | 0 | 37808 | 37808 | 100% | 0 | 0 | 0 | 4915.04 | 0 | 4915.04 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1995 |  | Investment
FIN | IBRD | Tenco Industries Sdn., Bhd., aerosol conversion project | Individual | ASP | MAL | ARS | 18 | INV | 63 | N | D | CFC | 18 | 18 | 0 | 0 | 1995-11-01 | 1997-02-01 | 1996-11-01 |  | 1996-03-01 | 1997-03-01 | 79200 | 0 | 79200 | 79200 | 100% | 0 | 0 |  | 10296 | 0 | 10296 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | UNDP | Alloychem Malaysia Sdn., Bhd., aerosol conversion project | Individual | ASP | MAL | ARS | 18 | INV | 64 | A | I | CFC | 29 | 29 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 2001-12-01 | 2003-11-01 | 99500 | -13228 | 86272 | 86272 | 100% | 0 | 0 | 0 | 12935 | -1719.51 | 11215.49 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1995 | 1999-12-01 | Investment
FIN | UNDP | Umbrella project to phase out ODS at SMEs in the aerosol sector | Individual | ASP | MAL | ARS | 19 | INV | 85 | A | I | CFC | 250 | 250 | 0 | 0 | 1996-05-01 | 1997-06-01 | 1998-04-01 |  | 2005-12-01 | 2011-05-01 | 1486660 | -149073.72 | 1337586.28 | 1337586 | 100% | 0.28 | 0 | 0 | 193265.8 | -19379.58 | 173886.18 | 0.04 | 0 | Completed in 2005. |  | 1996 | 2001-12-01 | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of extruded polystyrene foam sheet at Jumaya Industries Sdn. Bhd. | Individual | ASP | MAL | FOA | 10 | INV | 11 | A | R | CFC | 150 | 150 | 0 | 0 | 1993-06-01 | 1993-12-01 | 1994-12-01 |  | 1993-12-01 | 1997-12-01 | 235811 | 62 | 235873 | 235873 | 100% | 0 | 0 | 0 | 30655.43 | 8.06 | 30663.49 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1993 |  | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of integral skin polyurethene foam at Key Asset Sdn. Bhd. | Individual | ASP | MAL | FOA | 11 | INV | 15 | A | I | CFC | 50 | 50 | 0 | 0 | 1993-11-01 | 1994-05-01 | 1994-11-01 |  | 1995-02-01 | 1998-12-01 | 690000 | -15755 | 674245 | 674245 | 100% | 0 | 0 | 0 | 89700 | -2048 | 87652 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1993 |  | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of rigid polyurethane insulation foam at Insafoam Insulation Sdn. Bhd. | Individual | ASP | MAL | FOA | 11 | INV | 16 | A | I | CFC | 30 | 30 | 0 | 0 | 1993-11-01 | 1995-06-01 | 1994-11-01 |  | 1995-11-01 | 1998-12-01 | 310000 | -3393 | 306607 | 306607 | 100% | 0 | 0 | 0 | 40300 | -441 | 39859 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1993 |  | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of integral skin polyurethene foam at Island Resources Sdn. Bhd. | Individual | ASP | MAL | FOA | 11 | INV | 17 | A | I | TCA/CFC | 16.5 | 16.5 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1994-11-01 |  | 1994-04-01 | 1998-12-01 | 230000 | -14204 | 215796 | 215796 | 100% | 0 | 0 | 0 | 29900 | -1846 | 28054 | 0 | 0 | Completed in 1994. Financially completed in 1998. |  | 1993 |  | Investment
FIN | UNDP | Elimination of CFC-12 in the manufacture of extruded polysterene and polyethylene foam sheet at Associated Air-Pack Industries, Sdb. Bhd. | Individual | ASP | MAL | FOA | 11 | INV | 21 | A | I | CFC | 50 | 50 | 0 | 0 | 1993-11-01 | 1994-06-01 | 1994-11-01 |  | 1995-11-01 | 1998-12-01 | 234000 | 17126 | 251126 | 251126 | 100% | 0 | 0 | 0 | 30420 | 2226 | 32646 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1993 |  | Investment
FIN | UNDP | Phase-out of the use of CFC in the manufacture of polyurethane insulated panel at Cycle World Sdn. Bhd. | Individual | ASP | MAL | FOA | 12 | INV | 22 | A | I | CFC | 45 | 45 | 0 | 0 | 1994-03-01 | 1995-06-01 | 1995-03-01 |  | 1997-06-01 | 2000-12-01 | 353000 | -1 | 352999 | 352999 | 100% | 0 | 0 | 0 | 45890 | -0.13 | 45889.87 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Phase-out of the use of CFC-12 in the manufacture of EPS/EPE foam sheet at Pulai Lamipak Industries Sdn. Bhd. | Individual | ASP | MAL | FOA | 12 | INV | 23 | A | I | CFC | 50 | 50 | 0 | 0 | 1994-03-01 | 1994-08-01 | 1994-12-01 |  | 1996-08-01 | 2002-03-01 | 355000 | -17066 | 337934 | 337934 | 100% | 0 | 0 | 0 | 46150 | -2219 | 43931 | 0 | 0 | Completed in 1996. Financially completed in 2002. |  | 1994 |  | Investment
FIN | UNDP | Phase-out of the use of CFC-11 in the manufacture of integral skin, spoiler and moulded flexible foam at P.U. Tech Sdn. Bhd. | Individual | ASP | MAL | FOA | 12 | INV | 24 | A | I | CFC | 24 | 24 | 0 | 0 | 1994-03-01 | 1994-08-01 | 1995-03-01 |  | 1995-02-01 | 1998-12-01 | 198000 | -0.35 | 197999.65 | 198000 | 100% | -0.35 | 0 | 0 | 25740 | -0.31 | 25739.74 | -0.05 | 0 | Completed in 1995. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Phase-out of the use of CFC-11 in the manufacture of integral skin polyurethane foam at P.U. Mate Sdn. Bhd. | Individual | ASP | MAL | FOA | 12 | INV | 25 | A | I | CFC | 10 | 10 | 0 | 0 | 1994-03-01 | 1994-08-01 | 1995-03-01 |  | 1996-06-01 | 1998-12-01 | 113000 | -9294 | 103706 | 103706 | 100% | 0 | 0 | 0 | 14690 | -1208 | 13482 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Phase-out of the use of CFC-11 in the manufacture of flexible polyurethane foam at Pexafoam Sdn. Bhd. | Individual | ASP | MAL | FOA | 12 | INV | 26 | A | I | CFC | 120 | 120 | 0 | 0 | 1994-03-01 | 1994-08-01 | 1995-03-01 |  | 1995-02-01 | 2003-09-01 | 195000 | -5077.19 | 189922.81 | 189923 | 100% | -0.19 | 0 | 0 | 25350 | -660.01 | 24690.0147 | -0.0247 | 0 | Completed in 1995. Financially completed in 2003. |  | 1994 |  | Investment
FIN | UNDP | Phase-out of the use of CFC-11 in the manufacture of flexible polyurethane foam (slabstock) at N.L.Y. Sdn. Bhd. | Individual | ASP | MAL | FOA | 12 | INV | 27 | A | I | CFC | 55 | 55 | 0 | 0 | 1994-03-01 | 1994-08-01 | 1995-03-01 |  | 1995-02-01 | 1998-12-01 | 130000 | -14651 | 115349 | 115349 | 100% | 0 | 0 | 0 | 16900 | -1905 | 14995 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Phase-out of the use of CFC in the manufacture of flexible polyurethane foam (slabstock) at small scale producers | Individual | ASP | MAL | FOA | 12 | INV | 33 | A | I | CFC | 80 | 80 | 0 | 0 | 1994-03-01 | 1994-09-01 | 1995-03-01 |  | 1998-08-01 | 2000-12-01 | 1045000 | -55551.66 | 989448.34 | 989448 | 100% | 0.34 | 0 | 0 | 135850 | -7221.72 | 128628.24 | 0.04 | 0 | Completed in 1998. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of rigid polyurethane foam panels for cold storage at Wong Brothers Electrical and Refrigeration Sdn. Bhd. | Individual | ASP | MAL | FOA | 13 | INV | 38 | A | I | CFC | 35 | 35 | 0 | 0 | 1994-07-01 | 1995-10-01 | 1995-07-01 |  | 1999-03-01 | 2001-12-01 | 299000 | -1 | 298999 | 298999 | 100% | 0 | 0 | 0 | 38870 | -0.13 | 38869.87 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1994 | 1999-05-01 | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of cold cure molded flexible polyurethane foam at Eversoft Foam Industries Sdn. Bhd. | Individual | ASP | MAL | FOA | 13 | INV | 39 | A | I | CFC | 30 | 30 | 0 | 0 | 1994-07-01 | 1995-10-01 | 1995-07-01 |  | 1996-12-01 | 1998-12-01 | 185000 | -1 | 184999 | 184999 | 100% | 0 | 0 | 0 | 24050 | -0.13 | 24049.87 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of cold cure molded flexible polyurethane foam at Nian Aik Foam Sdn. Bhd. | Individual | ASP | MAL | FOA | 13 | INV | 40 | A | I | CFC | 30 | 30 | 0 | 0 | 1994-07-01 | 1995-01-01 | 1995-07-01 |  | 1996-09-01 | 2000-12-01 | 245000 | -53100 | 191900 | 191900 | 100% | 0 | 0 | 0 | 31850 | -6903 | 24947 | 0 | 0 | Completed in 1996. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of rigid panels for commercial refrigerators at Pangkat Refrigeration Industries Sdn. Bhd. | Individual | ASP | MAL | FOA | 13 | INV | 41 | A | I | CFC | 20 | 20 | 0 | 0 | 1994-07-01 | 1995-12-01 | 1995-07-01 |  | 1996-12-01 | 2000-12-01 | 210000 | -6736 | 203264 | 203264 | 100% | 0 | 0 | 0 | 27300 | -875.68 | 26424.32 | 0 | 0 | Completed in 1996. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of polyurethane foam for pipe insulation at Allied Foam Insulation | Individual | ASP | MAL | FOA | 13 | INV | 43 | A | I | CFC | 25 | 25 | 0 | 0 | 1994-07-01 | 1995-12-01 | 1995-07-01 |  | 1996-12-01 | 2000-12-01 | 276000 | -2955 | 273045 | 273045 | 100% | 0 | 0 | 0 | 35880 | -384.15 | 35495.85 | 0 | 0 | Completed in 1996. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-11 in the manufacture of flexible polyurethane foam at Phoenix Base Sdn. Bhd. | Individual | ASP | MAL | FOA | 13 | INV | 44 | A | I | CFC | 61 | 61 | 0 | 0 | 1994-07-01 | 1994-10-01 | 1995-06-01 |  | 1995-02-01 | 1998-12-01 | 165000 | 12784 | 177784 | 177784 | 100% | 0 | 0 | 0 | 21450 | 1662 | 23112 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Phase out of CFC in the manufacture of rigid foam for use as imitation wood at Saferay (M) SDN BHD | Individual | ASP | MAL | FOA | 15 | INV | 46 | A | I | CFC | 11 | 11 | 0 | 0 | 1994-12-01 | 1995-12-01 | 1995-11-01 |  | 1997-06-01 | 1998-12-01 | 246000 | 0 | 246000 | 246000 | 100% | 0 | 0 | 0 | 31980 | 0 | 31980 | 0 | 0 | Completed in 1997. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Phase out of CFC-11 in the manufacture of pipe insulation at Ricwil Sdn Bhd | Individual | ASP | MAL | FOA | 15 | INV | 47 | A | I | CFC | 25 | 25 | 0 | 0 | 1994-12-01 | 1995-10-01 | 1995-11-01 |  | 1995-11-01 | 1998-12-01 | 118000 | -13464 | 104536 | 104536 | 100% | 0 | 0 | 0 | 15340 | -1750 | 13590 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of moulded and flexible PU foams at Dream Products Snd. Bhd. | Individual | ASP | MAL | FOA | 15 | INV | 48 | A | D | CFC | 15 | 15 | 0 | 0 | 1994-12-01 | 1997-06-01 | 1995-11-01 |  | 1998-09-01 | 2000-07-01 | 66500 | -154 | 66346 | 66346 | 100% | 0 | 0 | 0 | 8645 | -20.02 | 8624.98 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC in the manufacture of rigid foam panels at Rigid Foam Industries, Sdn. Bhd. | Individual | ASP | MAL | FOA | 15 | INV | 49 | A | I | CFC | 19 | 19 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1995-11-01 |  | 1997-12-01 | 2000-07-01 | 335000 | -3198 | 331802 | 331802 | 100% | 0 | 0 | 0 | 43550 | -415.74 | 43134.26 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC in the manufacture of rigid foam panels and shipyard insulation works at Leading Refrigeration and Engineering, Sdn. Bhd. | Individual | ASP | MAL | FOA | 15 | INV | 50 | A | I | CFC | 10 | 10 | 0 | 0 | 1994-12-01 | 1995-03-01 | 1995-11-01 |  | 1995-11-01 | 1998-12-01 | 214000 | -13246 | 200754 | 200754 | 100% | 0 | 0 | 0 | 27820 | -1722 | 26098 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Phase out of the use of CFC in the manufacture of rigid PU panels at Shaga Cooling Technology | Individual | ASP | MAL | FOA | 15 | INV | 56 | A | I | CFC | 24 | 24 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1995-11-01 |  | 1996-10-01 | 2000-12-01 | 190000 | -12498 | 177502 | 177502 | 100% | 0 | 0 | 0 | 24700 | -1624.74 | 23075.26 | 0 | 0 | Completed in 1996. Financially completed in 2000. |  | 1994 |  | Investment
FIN | IBRD | Elimination of ODS in the process of EPE/EPS foam sheet at Star Foam Paper Products Sdn. Bhd. | Individual | ASP | MAL | FOA | 17 | INV | 59 | N | I | CFC | 66 | 66 | 0 | 0 | 1995-07-01 | 1997-07-01 | 1996-07-01 |  | 2000-10-01 | 2002-03-01 | 295000 | -43111 | 251889 | 251889 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Safety audit cannot be performed as enterprise out of business due to economic slowdown. Given this subproject was physically completed many years ago and the enterprise cannot recover its business, DOE and the Bank decided safety audit cannot be done and PCR should be sent to ExCom after receiving endorsement letter from the Government. |  |  | 1997-03-01 | INV | 0
FIN | UNDP | Elimination of CFCs in the manufacture of cold cured PUF molded products at Urethane Technologies Sdn., Bhd. | Individual | ASP | MAL | FOA | 17 | INV | 61 | A | D | CFC | 35 | 35 | 0 | 0 | 1995-07-01 | 1997-06-01 | 1996-07-01 |  | 1997-12-01 | 2000-12-01 | 199000 | -7010 | 191990 | 191990 | 100% | 0 | 0 | 0 | 25870 | -911.3 | 24958.7 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of integral skin PUF at Artwright Technology Sdn. Bhd. | Individual | ASP | MAL | FOA | 18 | INV | 65 | A | I | CFC | 6 | 6 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 1997-12-01 | 2002-03-01 | 90320 | 0 | 90320 | 90320 | 100% | 0 | 0 | 0 | 11741.6 | 0 | 11741.6 | 0 | 0 | Completed in 1997. Financially completed in 2002. |  | 1995 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of cold cured/integral skin PUF molded at Muda Murni Sdn. Bhd. | Individual | ASP | MAL | FOA | 18 | INV | 66 | A | I | CFC | 21 | 21 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 1997-12-01 | 2000-12-01 | 236500 | -52362 | 184138 | 184138 | 100% | 0 | 0 | 0 | 30745 | -6807.06 | 23937.94 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of molded/integral skin PUF at Bristol Sdn. Bhd. | Individual | ASP | MAL | FOA | 18 | INV | 67 | A | I | CFC | 8 | 8 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 1998-02-01 | 2000-07-01 | 123400 | -475 | 122925 | 122925 | 100% | 0 | 0 | 0 | 16042 | -61.49 | 15980.51 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of integral skin PUF at Sze Chuan Sdn. Bhd. | Individual | ASP | MAL | FOA | 18 | INV | 68 | A | I | CFC | 6 | 6 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 1998-06-01 | 2000-12-01 | 96000 | 0 | 96000 | 96000 | 100% | 0 | 0 | 0 | 12480 | 0 | 12480 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid polyurethane foam at TM Cooling Technology Sdn. Bhd. | Individual | ASP | MAL | FOA | 18 | INV | 70 | A | I | CFC | 10 | 10 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 1998-06-01 | 1999-05-01 | 78000 | 0 | 78000 | 78000 | 100% | 0 | 0 | 0 | 10140 | 0 | 10140 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1995 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid polyurethane foam decorative products at Florafoam Marketing Sdn. Bhd. | Individual | ASP | MAL | FOA | 18 | INV | 71 | A | D | CFC | 23 | 23 | 0 | 0 | 1995-11-01 | 1997-05-01 | 1996-11-01 |  | 1997-06-01 | 2000-12-01 | 152000 | -1 | 151999 | 151999 | 100% | 0 | 0 | 0 | 19760 | -0.13 | 19759.87 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNIDO | Preparation of an investment project in the foam sector | Individual | ASP | MAL | FOA | 18 | PRP | 69 | A | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-06-01 | 1996-02-01 |  | 1999-02-01 | 2000-07-01 | 40000 | -35 | 39965 | 39965 | 100% | 0 | 0 |  | 5200 | -13 | 5187 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | IBRD | Elimination of CFC-11 in the manufacture of polyurethane refrigerator panels at Penang Trading Co. | Individual | ASP | MAL | FOA | 19 | INV | 86 | N | I | CFC | 10.5 | 10.5 | 0 | 0 | 1996-05-01 | 2000-02-01 | 2000-05-01 |  | 2001-12-01 | 2000-05-01 | 71500 | -6500 | 65000 | 65000 | 100% | 0 | 0 |  | 9295 | -845 | 8450 | 0 | 0 | Project is physically and financially completed. Equipment and accessories have been installed and operated with 3-phase electrical supply in its new location. Enterprise has stopped using CFC and converted to alternative blowing agents since Nov. 2001. As no contingency was claimed, financial completion occurred when funding was, in this case, provided directly to supplier for capital costs. PCR to be submitted to the Bank in 02. The Bank is waiting for certificate of destruction from DOE before issuing an approval letter |  |  | 1999-06-01 | INV | 0
FIN | IBRD | Elimination of CFC-11 in the manufactue of polyurethane cold-room insulation panels/truck container panels at Kejuruteraan Transfreeze Sdn Bhd | Individual | ASP | MAL | FOA | 19 | INV | 87 | N | I | CFC | 11.4 | 11.4 | 0 | 0 | 1996-05-01 | 2000-02-01 | 1997-05-01 |  | 2001-11-01 | 2000-05-01 | 71500 | -6500 | 65000 | 65000 | 100% | 0 | 0 |  | 9295 | -845 | 8450 | 0 | 0 | Project is physically and financially completed. Equipment and accessories have been installed and operated with 3-phrase electrical supply in its new location. Enterprise has stopped using CFC and converted to alternative blowing agents as of Dec. 2001. As no contingency was claimed, financial completion occurred when funding was, in this case, provided directly to supplier for capital costs. PCR to be submitted to the Bank Mar. 02. These both projects has two funding parts that are ICC and contingency. |  |  | 1999-06-01 | INV | 0
FIN | UNDP | Conversion to CFC-free technology for the manufacture of flexible polyurethane foam at Nite Beauty Industries | Individual | ASP | MAL | FOA | 19 | INV | 88 | A | I | CFC | 10 | 10 | 0 | 0 | 1996-05-01 | 1997-07-01 | 1997-05-01 |  | 1998-06-01 | 1999-12-01 | 36875 | 0 | 36875 | 36875 | 100% | 0 | 0 | 0 | 4793.75 | 0 | 4793.75 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1996 |  | Investment
FIN | UNDP | Conversion to CFC -free technology for the manufacture of flexible polyurethane foam at Far East Foam Industries | Individual | ASP | MAL | FOA | 19 | INV | 89 | A | I | CFC | 41.2 | 41.2 | 0 | 0 | 1996-05-01 | 1997-07-01 | 1997-05-01 |  | 1998-09-01 | 2001-12-01 | 209000 | -2275 | 206725 | 206725 | 100% | 0 | 0 | 0 | 27170 | -295.75 | 26874.25 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1996 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Amstrad | Individual | ASP | MAL | FOA | 22 | INV | 94 | A | I | CFC | 13.9 | 13.9 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1999-06-01 |  | 1999-12-01 | 2001-12-01 | 108800 | -86 | 108714 | 108714 | 100% | 0 | 0 | 0 | 14144 | -11.18 | 14132.82 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 | 1999-06-01 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Anchor Profit Sdn Bhd | Individual | ASP | MAL | FOA | 22 | INV | 95 | A | I | CFC | 18.5 | 18.5 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1997-12-01 | 2000-12-01 | 131000 | 0 | 131000 | 131000 | 100% | 0 | 0 | 0 | 17030 | 0 | 17030 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Rollbond | Individual | ASP | MAL | FOA | 22 | INV | 96 | A | I | CFC | 22.2 | 22.2 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1997-12-01 | 2000-12-01 | 155500 | 0 | 155500 | 155500 | 100% | 0 | 0 | 0 | 20215 | 0 | 20215 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at RCA Group | Individual | ASP | MAL | FOA | 22 | INV | 98 | A | I | CFC | 41.9 | 41.9 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1999-11-01 | 2000-12-01 | 284500 | -12922 | 271578 | 271578 | 100% | 0 | 0 | 0 | 36985 | -1679.86 | 35305.14 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNIDO | Phasing out ODS at Summer Technologies Sdn. Bhd. | Individual | ASP | MAL | FOA | 23 | INV | 100 | A | I | CFC | 12.1 | 12.1 |  |  | 1997-11-01 | 1998-12-01 | 1999-06-01 |  | 1998-12-01 | 2001-05-01 | 89407 | 0 | 89407 | 89407.11 | 100% | -0.11 | 0 |  | 11623 | 0 | 11623 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Kean Chong Industries Sdn. Bhd | Individual | ASP | MAL | FOA | 23 | INV | 101 | A | I | CFC | 16.3 | 16.3 |  |  | 1997-11-01 | 1998-12-01 | 1999-06-01 |  | 1998-12-01 | 2000-11-23 | 107819 | 0 | 107819 | 107819 | 100% | 0 | 0 |  | 14016 | 0 | 14016 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Visdamax Sdn. Bhd | Individual | ASP | MAL | FOA | 23 | INV | 102 | A | I | CFC | 18.5 | 18.5 |  |  | 1997-11-01 | 1998-06-01 | 1999-06-01 |  | 1998-12-01 | 2001-05-01 | 139959 | 0 | 139959 | 139958.67 | 100% | 0.33 | 0 |  | 18195 | 0 | 18195 | 0 | 0 | FIN
FIN | UNDP | Conversion to CFC-free techology in the manufacture of polyurethane foam at Hi Tech Insulation | Individual | ASP | MAL | FOA | 23 | INV | 104 | A | I | CFC | 18.5 | 18.5 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1998-09-01 | 2002-03-01 | 96815 | -3942 | 92873 | 92873 | 100% | 0 | 0 | 0 | 12585.95 | -512.46 | 12073.49 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Heng Huat Furniture | Individual | ASP | MAL | FOA | 23 | INV | 105 | A | I | CFC | 50 | 50 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-11-01 | 2001-12-01 | 269500 | 0 | 269500 | 269500 | 100% | 0 | 0 | 0 | 35035 | 0 | 35035 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Frank Chee | Individual | ASP | MAL | FOA | 23 | INV | 106 | A | I | CFC | 28 | 28 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2000-08-01 | 2001-12-01 | 174350 | 0 | 174350 | 174350 | 100% | 0 | 0 | 0 | 22665.5 | 0 | 22665.5 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at OAL Enterprise | Individual | ASP | MAL | FOA | 23 | INV | 107 | A | I | CFC | 7.4 | 7.4 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 1999-11-01 | 2003-05-01 | 58300 | -19611 | 38689 | 38689 | 100% | 0 | 0 | 0 | 7579 | -2549.43 | 5029.57 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at CT Foam | Individual | ASP | MAL | FOA | 23 | INV | 99 | A | I | CFC | 14 | 14 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-11-01 | 2001-12-01 | 236000 | 0 | 236000 | 236000 | 100% | 0 | 0 | 0 | 30680 | 0 | 30680 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Project preparation for 4 projects in the rigid foam subsector | Individual | ASP | MAL | FOA | 24 | PRP | 108 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-09-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNIDO | Preparation of investment projects in the foam sector (rigid polyurethane) for Chon Son, Ngui Soon, Ming Soon, Yon Tuck | Individual | ASP | MAL | FOA | 24 | PRP | 110 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-06-01 | 1999-04-01 |  | 1998-09-01 | 2000-12-01 | 20000 | -205 | 19795 | 19795 | 100% | 0 | 0 |  | 2600 | -31 | 2569 | 0 | 0 | FIN
FIN | UNDP | Conversion to LCD technology in the manufacture of polyurethane foam at Tenaga | Individual | ASP | MAL | FOA | 25 | INV | 111 | A | I | CFC | 23 | 23 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 2000-08-01 | 2001-12-01 | 308800 | 0 | 308800 | 308800 | 100% | 0 | 0 | 0 | 40144 | 0 | 40144 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNIDO | Replacement of CFC-11 foam blowing agent by HCFC-141b in the insulation of GRP fish boxes and flotation buoys at C.C. Chong Co. | Individual | ASP | MAL | FOA | 26 | INV | 112 | A | I | CFC | 4.5 | 4.5 |  |  | 1998-11-01 | 1999-03-01 | 2000-06-01 |  | 2000-05-01 | 2001-09-01 | 34583 | 0 | 34583 | 34583.03 | 100% | -0.03 | 0 |  | 4496 | -1 | 4495 | 0 | 0 | FIN
FIN | UNIDO | The replacement of CFC-11 foam blowing agent by HCFC-141b in the manufacture of insulation panels at Ming Soon Enterprise Sdn. Bhd. | Individual | ASP | MAL | FOA | 26 | INV | 113 | A | I | CFC | 6.2 | 6.23 |  |  | 1998-11-01 | 1999-06-01 | 2000-06-01 |  | 2000-02-01 | 2002-09-01 | 48799 | 0 | 48799 | 48798.94 | 100% | 0.06 | 0 |  | 6344 | -8 | 6336 | 0 | 0 | FIN
FIN | UNDP | Phaseout of CFC-11 by conversion to water and HCFC-141b technology in the manufacture of integral skin and rigid molded polyurethane foam at Minply | Individual | ASP | MAL | FOA | 26 | INV | 115 | A | I | CFC | 16.5 | 16.5 | 0 | 0 | 1998-11-01 | 1999-07-01 | 2000-12-01 |  | 2000-10-01 | 2002-03-01 | 158050 | -3297 | 154753 | 154753 | 100% | 0 | 0 | 0 | 20546.5 | -428.61 | 20117.89 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to water and HCFC-141b technology in the manufacture of integral skin and rigid molded polyurethane foam at Grorich | Individual | ASP | MAL | FOA | 26 | INV | 116 | A | I | CFC | 32.9 | 32.9 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2000-10-01 | 2001-12-01 | 174150 | 0 | 174150 | 174150 | 100% | 0 | 0 | 0 | 22639.5 | 0 | 22639.5 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNIDO | Replacement of CFC-11 foam blowing agent by HCFC-141b in the manufacture of insulation panels at Yong Tuck Refrigerators Trading Co. | Individual | ASP | MAL | FOA | 27 | INV | 120 | A | I | CFC | 8 | 8 |  |  | 1999-03-01 | 1999-08-01 | 2000-10-01 |  | 2000-06-01 | 2001-09-01 | 61735 | -643 | 61092 | 61091.82 | 100% | 0.18 | 0 |  | 8026 | -97 | 7929 | 0 | 0 | FIN
FIN | UNIDO | Preparation of three investment projects in the foam sector (rigid polyrethane) | Individual | ASP | MAL | FOA | 27 | PRP | 118 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-06-01 | 1999-12-01 |  | 2000-07-01 | 2002-05-01 | 25000 | -47 | 24953 | 24953.14 | 100% | -0.14 | 0 |  | 3250 | -11 | 3239 | 0 | 0 | FIN
FIN | UNDP | Preparation of three projects in rigid foam subsector | Individual | ASP | MAL | FOA | 27 | PRP | 119 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-04-01 | 2004-01-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2000. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 in the manufacture of cold room panels and insulation slabs by conversion to HCFC-141b at PKL Insulation | Individual | ASP | MAL | FOA | 28 | INV | 121 | A | I | CFC | 8.1 | 8.1 | 0 | 0 | 1999-07-01 | 2000-05-01 | 2002-02-01 |  | 2000-12-01 | 2003-07-01 | 57019 | -1434 | 55585 | 55585 | 100% | 0 | 0 | 0 | 7412.47 | -186.42 | 7226.05 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam (spray and blocks) at Polyedge Trading | Individual | ASP | MAL | FOA | 28 | INV | 122 | A | I | CFC | 10.3 | 10.3 | 0 | 0 | 1999-07-01 | 2000-06-01 | 2002-02-01 |  | 2000-12-01 | 2001-12-01 | 80650 | 0 | 80650 | 80650 | 100% | 0 | 0 | 0 | 10484.5 | 0 | 10484.5 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1999 |  | Investment
FIN | UNDP | Retroactive project for phasing-out ODS consumption in the manufacture of cold room panels by conversion to HCFC-141b at FMCP Sdn. Bhd. | Individual | ASP | MAL | FOA | 28 | INV | 123 | A | R | CFC | 12.2 | 12.2 | 0 | 0 | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2000-07-01 | 2001-12-01 | 45557 | 0 | 45557 | 45557 | 100% | 0 | 0 | 0 | 5922.41 | 0 | 5922.41 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1999 |  | Investment
FIN | UNIDO | Phase out CFC-11 consumption by conversion to HCFC-141b AT Perniagaan Hower in the manufacture of sandwich panels | Individual | ASP | MAL | FOA | 28 | INV | 124 | A | I | CFC | 5.3 | 5.3 |  |  | 1999-07-01 | 1999-12-01 | 2001-08-01 |  | 2001-02-01 | 2002-09-01 | 41499 | -87 | 41412 | 41412.44 | 100% | -0.44 | 0 |  | 5395 | -20 | 5375 | 0 | 0 | FIN
FIN | UNIDO | Phase out of CFC-11 by conversion to HCFC-141b technology at Automated Plastic System Sdn. Bhd. in the manufacture of insulated fishing boxes | Individual | ASP | MAL | FOA | 28 | INV | 125 | A | I | CFC | 5.2 | 5.2 |  |  | 1999-07-01 | 1999-12-01 | 2001-08-01 |  | 2001-01-01 | 2001-12-01 | 40716 | 0 | 40716 | 40716.48 | 100% | -0.48 | 0 |  | 5293 | 0 | 5293 | 0 | 0 | FIN
FIN | UNIDO | Phase out CFC-11 consumption at Chong Brother Group of Companies | Individual | ASP | MAL | FOA | 28 | INV | 127 | A | I | CFC | 27.6 | 27.6 |  |  | 1999-07-01 | 1999-09-01 | 2001-08-01 |  | 2001-02-01 | 2002-09-01 | 216108 | 0 | 216108 | 216107.83 | 100% | 0.17 | 0 |  | 28094 | -21 | 28073 | 0 | 0 | FIN
FIN | UNDP | Conversion from CFC-11 to liquid carbon dioxide technology in the manufacture of flexible polyurethane foam at Masterfoam Products | Individual | ASP | MAL | FOA | 29 | INV | 130 | A | I | CFC | 25 | 25 | 0 | 0 | 1999-11-01 | 2001-06-01 | 2002-12-01 |  | 2001-11-01 | 2003-04-01 | 208900 | 0 | 208900 | 208900 | 100% | 0 | 0 | 0 | 27157 | 0 | 27157 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to LCD technology in the manufacture of flexible polyurethane foam at Kemas Mekar Sdn Bhd | Individual | ASP | MAL | FOA | 29 | INV | 131 | A | I | CFC | 23.3 | 23.3 | 0 | 0 | 1999-11-01 | 2001-10-01 | 2002-12-01 |  | 2002-06-01 | 2003-11-01 | 385900 | -11270 | 374630 | 374630 | 100% | 0 | 0 | 0 | 50167 | -1465.1 | 48701.9 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Preparation of 4 projects in the rigid foam subsector | Individual | ASP | MAL | FOA | 30 | PRP | 133 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-04-01 | 2003-01-01 | 30000 | -9677.8 | 20322.2 | 20322 | 100% | 0.2 | 0 | 0 | 3900 | -1257.87 | 2642.1052 | 0.024837 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to LIA technology in the manufacture of flexible polyurethane boxfoam and to LCD technology in the manufacture of flexible molded foam at Sy Heng Huat | Individual | ASP | MAL | FOA | 31 | INV | 136 | A | I | CFC | 46.2 | 46.2 | 0 | 0 | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2002-01-01 | 2003-11-01 | 272235 | 0 | 272235 | 272235 | 100% | 0 | 0 | 0 | 35390.55 | 0 | 35390.55 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to LCD and water-based technology in the manufacture of flexible molded foam at Unique Field | Individual | ASP | MAL | FOA | 31 | INV | 137 | A | I | CFC | 18.5 | 18.5 | 0 | 0 | 2000-07-01 | 2001-06-01 | 2003-08-01 |  | 2001-12-01 | 2003-04-01 | 109990 | 0 | 109990 | 109990 | 100% | 0 | 0 | 0 | 14298.7 | 0 | 14298.7 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to LCD technology in the manufacture of flexible molded foam at Pointray | Individual | ASP | MAL | FOA | 31 | INV | 138 | A | I | CFC | 24.3 | 24.3 | 0 | 0 | 2000-07-01 | 2001-08-01 | 2003-08-01 |  | 2001-12-01 | 2003-11-01 | 130896 | -27 | 130869 | 130869 | 100% | 0 | 0 | 0 | 17016.48 | -3.51 | 17012.97 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNIDO | Preparation of three investment projects in the rigid foam sector | Individual | ASP | MAL | FOA | 31 | PRP | 139 | A | I |  | 0 | 0 |  |  | 2000-07-01 | 2000-10-01 | 2001-07-01 |  | 2002-01-01 | 2003-05-01 | 20000 | -740 | 19260 | 19259.64 | 100% | 0.36 | 0 |  | 2600 | -100 | 2500 | 0 | 0 | FIN
FIN | UNIDO | Phase out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam for insulating purposes at Composites Truck Body Sdn., Bhd. | Individual | ASP | MAL | FOA | 34 | INV | 143 | A | I | CFC | 8.1 | 8.1 |  |  | 2001-07-01 | 2002-12-01 | 2004-02-01 |  | 2003-12-01 | 2003-12-01 | 63280 | -129 | 63151 | 63150.56 | 100% | 0.44 | 0 |  | 8226 | -29 | 8197 | 0 | 0 | FIN |  |  |  | INV
FIN | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | ASP | MAL | FOA | 57 | PRP | 164 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2011-08-01 | 2010-03-01 |  | 2012-07-01 | 2013-12-01 | 100000 | -66756 | 33244 | 33244 | 100% | 0 | 0 | 0 | 7500 | -5006.7 | 2493.3 | 0 | 0 | Financially completed in 2013. | Completed in 2012. | 2009 |  | Investment
ONG | UNDP | Preparation for HCFC phase-out investment activities (stage II) (foam sector) | Individual | ASP | MAL | FOA | 72 | PRP | 175 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 | 2015-07-01 | 2016-05-01 | 2017-05-01 |  |  | 150000 | 0 | 150000 | 65397.75 | 43.6% | 84602.25 | 0 | 33840.9 | 10500 | 0 | 4577.8425 | 5922.1575 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): HCFC survey completed, Stakeholders workshop held, Local institutions identified, Experts recruited, All technical input completed, Draft document completed Prodoc signed (actual/planned, yes/no and date):Letter of Authorisation sent 29 September 2014 Missions undertaken (actual/planned):1 TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: Contract signed First disbursement date (actual/planned): 42186Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | - |  |  | Non-Investment
FIN | UNDP | Project preparation for a methyl bromide alternative demonstration project (timber) | Individual | ASP | MAL | FUM | 24 | PRP | 109 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1999-11-01 | 2004-12-01 | 30000 | -983 | 29017 | 29017 | 100% | 0 | 0 | 0 | 3900 | -127.79 | 3772.21 | 0 | 0 | Completed in 1999. Financially completed in 2004. |  | 1998 |  | Investment
FIN | UNDP | Alternatives to the use of methyl bromide on Malaysian timbers | Individual | ASP | MAL | FUM | 29 | DEM | 129 | N | I | MeBr | 0 | 0 | 0 | 0 | 1999-11-01 | 2003-02-01 | 2002-12-01 |  | 2006-07-01 | 2010-10-01 | 230000 | -8078.19 | 221921.81 | 221922 | 100% | -0.19 | 0 | 0 | 29900 | -1050.16 | 28849.86 | -0.02 | 0 | Financially completed in 2010. |  | 1999 |  | Investment
FIN | UNDP | Project preparation in the soil fumigant sector | Individual | ASP | MAL | FUM | 36 | PRP | 146 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2003-09-01 | 2005-11-01 | 10000 | -947 | 9053 | 9053 | 100% | 0 | 0 | 0 | 1300 | -123.11 | 1176.89 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Project preparation for the formulation of fumigant methyl bromide | Individual | ASP | MAL | FUM | 42 | PRP | 150 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2005-04-01 |  | 2005-01-01 | 2006-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 750 | 0 | 750 | 0 | 0 | Completed in 2005. Financially completed in 2006. |  | 2004 |  | Investment
FIN | UNDP | Technical assistance programme to install alternatives and phase-out all remaining non-QPS uses of methyl bromide | Individual | ASP | MAL | FUM | 43 | TAS | 151 | N | I | MeBr | 8.7 | 8.7 | 0 | 0 | 2004-07-01 | 2006-01-01 | 2007-12-01 |  | 2011-07-01 | 2012-05-01 | 200000 | -10970.51 | 189029.49 | 189029 | 100% | 0.49 | 0 | 0 | 18000 | -987.35 | 17012.61 | 0.04 | 0 | Financially completed in 2012. | The project is expected to be financially closed by June 12. | 2004 |  | Non-Investment
FIN | IBRD | Servicing, maintenance and recovery of portable extinguishers (halon-1211) and training programme | Individual | ASP | MAL | HAL | 06 | INV | 04 | N | I | HAL | 900 | 900 | 0 | 0 | 1992-02-01 | 1996-03-01 | 1993-02-01 |  | 1998-09-01 | 2002-04-01 | 720000 | -1150 | 718850 | 718850 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project physically and financially completed. |  |  | 1997-06-01 | INV | 0
FIN | UNEP | Support to a sub-regional workshop on halon and halon bank management | Individual | ASP | MAL | HAL | 09 | TRA | 07 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1994-01-01 | 1994-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0
FIN | USA | Project preparation in the halon sector |  | ASP | MAL | HAL | 15 | PRP | 54 | A | I |  | 0 |  | 0 |  | 1994-12-01 |  | 1995-06-01 |  | 1995-06-01 | 1996-06-01 | 45000 | -28116 | 16884 | 16884 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | UNDP | Converson of production of portable fire extinguishers at Eversafe | Individual | ASP | MAL | HAL | 18 | INV | 72 | A | D | Halon | 574 | 574 | 0 | 0 | 1995-11-01 | 1996-10-01 | 1996-11-01 |  | 1996-10-01 | 2002-03-01 | 179586 | -4214 | 175372 | 175372 | 100% | 0 | 0 | 0 | 23346.18 | -547.82 | 22798.36 | 0 | 0 | Completed in 1996. Financially completed in 2002. |  | 1995 |  | Investment
FIN | IBRD | National CFC phaseout plan: 2002 Annual Programme | Multiyear | ASP | MAL | PHA | 35 | INV | 145 | N | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2002-12-01 |  | 2002-12-01 | 2012-04-01 | 1799940 | 0 | 1799940 | 1799940 | 100% | 0 | 0 |  | 140395 | 0 | 140395 | 0 | 0 | NCPP completed. |  |  |  | INV | 0
FIN | IBRD | National CFC phase-out plan: release of second tranche for implementation of the 2002 annual plan | Multiyear | ASP | MAL | PHA | 37 | INV | 147 | N | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2004-12-01 | 2003-08-01 |  | 2003-08-01 | 2012-04-01 | 2969065 | 0 | 2969065 | 2969065 | 100% | 0 | 0 |  | 259216 | 0 | 259216 | 0 | 0 | NCPP completed. |  |  |  | INV | 0
FIN | IBRD | National CFC phase-out plan: 2003 annual work programme | Multiyear | ASP | MAL | PHA | 40 | INV | 149 | N | I | CFC | 292 | 292 | 0 | 0 | 2003-07-01 | 2005-12-01 | 2004-07-01 |  | 2004-12-01 | 2012-04-01 | 2013100 | 0 | 2013100 | 2013100 | 100% | 0 | 0 |  | 169179 | 0 | 169179 | 0 | 0 | NCPP completed. |  |  |  | INV | 0
FIN | IBRD | National CFC phase-out plan: 2004 annual programme | Multiyear | ASP | MAL | PHA | 44 | INV | 154 | N | I | CFC | 430 | 430 | 0 | 0 | 2004-12-01 | 2005-12-01 | 2005-12-01 |  | 2005-12-01 | 2012-04-01 | 1688300 | 0 | 1688300 | 1688300 | 100% | 0 | 0 |  | 143947 | 0 | 143947 | 0 | 0 | NCPP completed. |  |  |  | INV | 0
FIN | IBRD | National CFC phase-out plan: 2005 annual programme | Multiyear | ASP | MAL | PHA | 47 | INV | 156 | N | I | CFC | 470.8 | 470.8 | 0 | 0 | 2005-11-01 | 2006-12-01 | 2006-12-01 |  | 2008-12-01 | 2012-04-01 | 1208300 | 0 | 1208300 | 1208300 | 100% | 0 | 0 |  | 100747 | 0 | 100747 | 0 | 0 | NCPP completed. |  |  |  | INV | 0
FIN | IBRD | National CFC phase-out plan: 2006 annual programme | Multiyear | ASP | MAL | PHA | 49 | INV | 157 | N | I | CFC | 120 | 120 | 0 | 0 | 2006-07-01 | 2008-12-01 | 2007-07-01 |  | 2009-12-01 | 2012-04-01 | 1013300 | 0 | 1013300 | 1013300 | 100% | 0 | 0 |  | 83197 | 0 | 83197 | 0 | 0 | NCPP completed. |  |  |  | INV | 0
FIN | IBRD | National CFC phase-out plan: 2007 annual programme | Multiyear | ASP | MAL | PHA | 52 | INV | 158 | N | I | CFC | 88.3 | 88.3 | 0 | 0 | 2007-07-01 | 2009-12-01 | 2008-07-31 |  | 2010-09-01 | 2012-04-01 | 275000 | 0 | 275000 | 275000 | 100% | 0 | 0 |  | 24750 | 0 | 24750 | 0 | 0 | NCPP completed. |  |  |  | INV | 0
FIN | IBRD | National CFC phase-out plan: 2008 annual programme | Multiyear | ASP | MAL | PHA | 55 | INV | 160 | N | I | CFC | 89 | 89 | 0 | 0 | 2008-07-01 | 2010-12-01 | 2009-07-31 |  | 2010-12-01 | 2012-04-01 | 275000 | 0 | 275000 | 275000 | 100% | 0 | 0 |  | 24750 | 0 | 24750 | 0 | 0 | NCPP completed. |  |  |  | INV | 0
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | ASP | MAL | PHA | 55 | PRP | 161 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2010-11-01 | 2009-07-01 |  | 2011-12-01 | 2013-12-01 | 173750 | 0 | 173750 | 173750 | 100% | 0 | 0 | 0 | 13031 | 0 | 13031 | 0 | 0 | Financially completed in 2013. | Project targeted for financial closure in 2012 | 2008 |  | Investment
FIN | IBRD | National CFC phase-out plan: 2009 annual programme | Multiyear | ASP | MAL | PHA | 59 | INV | 166 | N | I | CFC | 350.7 | 350.7 | 0 | 0 | 2009-11-01 | 2010-12-01 | 2010-11-30 |  | 2010-12-01 | 2012-04-01 | 275000 | -75992 | 199008 | 199008 | 100% | 0 | 0 |  | 24750 | -6839.28 | 17910.72 | 0 | 0 | NCPP completed. |  |  |  | INV | 0
FIN | UNDP | HCFC phase-out management plan (stage I, first tranche) (polyurethane foam sector plan) | Multi-year | ASP | MAL | PHA | 65 | INV | 169 | N | I | HCFC | 49.3 | 49.3 | 0 | 0 | 2011-11-01 | 2012-06-01 | 2016-10-01 |  | 2013-12-01 | 2013-12-01 | 4327247 | 0 | 4327247 | 4327247 | 100% | 0 | 0 | 0 | 324544 | 0 | 324544 | 0 | 0 | Financially completed in 2013. |  | 2011 |  | Investment
FIN | UNDP | HCFC phase-out management plan (stage I, first tranche) (technical assistance for the servicing sector) | Multi-year | ASP | MAL | PHA | 65 | TAS | 168 | N | I | HCFC | 4.4 | 4.4 | 0 | 0 | 2011-11-01 | 2013-02-01 | 2016-10-01 |  | 2013-12-01 | 2013-12-01 | 359845 | 0 | 359845 | 359845 | 100% | 0 | 0 | 0 | 26988 | 0 | 26988 | 0 | 0 | Financially completed in 2013. |  | 2011 |  | Investment
FIN | UNDP | HCFC phase-out management plan (stage I, first tranche) (management and coordination) | Multi-year | ASP | MAL | PHA | 65 | TAS | 170 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-11-01 | 2013-04-01 | 2016-10-01 |  | 2015-04-01 | 2016-04-01 | 312908 | 0 | 312908 | 312908 | 100% | 0 | 0 | 0 | 23468 | 0 | 23468 | 0 | 0 | Financially completed in 2016. | Project management and coordination activities are progressing satisfactorily. Verification of 2013 and 2014 is expected to be completed by July 2015. | 2011 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) (polyurethane foam sector plan) | Multi-Year | ASP | MAL | PHA | 71 | INV | 172 | N | I | HCFC | 35.8 | 26.8 | 0 | 0 | 2013-12-01 | 2014-04-01 | 2015-12-01 | 2017-06-01 |  |  | 3140476 | 0 | 3140476 | 3140476 | 100% | 0 | 0 | 0 | 235536 | 0 | 235536 | 0 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): 17 investments completed; on going consultancy for verification & demo project Prodoc signed (actual/planned, yes/no and date):41699 Missions undertaken (actual/planned):1 TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: Contract signed First disbursement date (actual/planned): 41730Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | on going | 2013 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) (technical assistance for the servicing sector) | Multi-Year | ASP | MAL | PHA | 71 | TAS | 173 | N | I | HCFC | 3.2 | 2 | 0 | 0 | 2013-12-01 | 2014-03-01 | 2015-12-01 | 2017-06-01 |  |  | 261156 | 0 | 261156 | 32824.96 | 12.57% | 228331.04 | 228331.04 | 91332.416 | 19587 | 0 | 2461.9097 | 17125.0903 | 17125.0903 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): 2 training workshops completed; retrofitting of aircon units completed Prodoc signed (actual/planned, yes/no and date):41671 Missions undertaken (actual/planned):1 TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: Contract signed First disbursement date (actual/planned): 41699Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | on going | 2013 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) (management and coordination) | Multi-Year | ASP | MAL | PHA | 71 | TAS | 174 | N | I | HCFC | 0 | 0 | 0 | 0 | 2013-12-01 | 2014-03-01 | 2015-12-01 | 2017-06-01 |  |  | 227091 | 0 | 227091 | 100644.23 | 44.32% | 126446.77 | 0 | 50578.708 | 17031 | 0 | 7547.9516 | 9483.0484 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): procurement of R&R & reclaim machine completed; Prodoc signed (actual/planned, yes/no and date):41699 Missions undertaken (actual/planned):1 TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: Contract signed First disbursement date (actual/planned): 41699Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | consultancy signed 2016 for prodoc formulation | 2013 |  | Investment
ONG | UNDP | Preparation of a HCFC phase-out management plan (stage II) | Individual | ASP | MAL | PHA | 72 | PRP | 176 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 | 2015-07-01 | 2016-05-01 | 2017-06-01 |  |  | 65000 | 0 | 65000 | 22725.94 | 34.96% | 42274.06 | 7800 | 16909.624 | 4550 | 0 | 1590.8158 | 2959.1842 | 546 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): TOR in 2016. Work in progress Prodoc signed (actual/planned, yes/no and date):Letter of Authorisation sent 29 September 2014 Missions undertaken (actual/planned):1 TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: Contract signed First disbursement date (actual/planned): 42186Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:Dificulty in engaging consultant | on going |  |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing, management and coordination) | Multi-year | ASP | MAL | PHA | 75 | TAS | 179 | N | I | HCFC | 9.5 | 0 | 0 | 0 | 2015-11-01 |  | 2017-11-01 | 2017-11-01 |  |  | 817452 | 0 | 817452 | 0 | 0% | 817452 | 0 | 326980.8 | 61309 | 0 | 0 | 61309 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Delay in budget revision due to unders staff of CO. BKK team isfollowing up for progress. Prodoc signed (actual/planned, yes/no and date):42736 Missions undertaken (actual/planned):1 TOR for consultants/subcontracts completed (actual/planned): Contract/PO/MOA agreements signed: First disbursement date (actual/planned): 42736Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:under staffing at CO office | Disbursement only in 2017 | 2015 |  | Non-Investment
ONG | UNDP | HCFC phase-out management plan (stage II, first tranche) (polyurethane foam sector) | Multi-year | ASP | MAL | PHA | 77 | INV | 181 | N | I | HCFC | 38.3 | 0 | 0 | 0 | 2016-12-01 |  | 2020-12-01 | 2017-12-01 |  |  | 2272640 | 0 | 2272640 | 0 | 0% | 2272640 | 0 | 909056 | 159085 | 0 | 0 | 159085 | 0 | Newly Approved | Awaiting AWP from CO for DoA issuance. | 2016 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, fourth tranche) (refrigeration servicing, management and coordination) | Multi-year | ASP | MAL | PHA | 77 | INV | 184 | N | I | HCFC | 0.8 | 0 | 0 | 0 | 2016-12-01 |  | 2017-12-01 | 2017-12-01 |  |  | 141295 | 0 | 141295 | 0 | 0% | 141295 | 0 | 56518 | 10597 | 0 | 0 | 10597 | 0 | Newly Approved | DoA sent Feb 2017, waiting for AWP from CO for ASL request. | 2016 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | Multi-year | ASP | MAL | PHA | 77 | TAS | 182 | N | I | HCFC | 45.3 | 0 | 0 | 0 | 2016-12-01 |  | 2020-12-01 | 2017-12-01 |  |  | 949548 | 0 | 949548 | 0 | 0% | 949548 | 0 | 379819.2 | 66468 | 0 | 0 | 66468 | 0 | Newly Approved | Awaiting AWP from CO for DoA issuance. | 2016 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage II, first tranche) (management and coordination) | Multi-year | ASP | MAL | PHA | 77 | TAS | 183 | N | I | HCFC | 0 | 0 | 0 | 0 | 2016-12-01 |  | 2020-12-01 | 2017-12-01 |  |  | 285750 | 0 | 285750 | 0 | 0% | 285750 | 0 | 114300 | 20003 | 0 | 0 | 20003 | 0 | Newly Approved | Awaiting AWP from CO for DoA issuance. | 2016 |  | Investment
FIN | UNDP | Training in MAC sector | RMP-Component | ASP | MAL | REF | 04 | TRA | 01 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1994-10-01 | 1993-12-01 |  | 1995-12-01 | 1997-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1991 |  | Non-Investment
FIN | IBRD | Conservation, leakage control and recycling of CFC-12 and demonstration project in MAC sector | Individual | ASP | MAL | REF | 06 | TAS | 05 | N | D | CFC | 370 | 370 | 0 | 0 | 1992-02-01 | 1994-03-01 | 1992-12-01 |  | 1997-06-01 | 1997-07-01 | 910000 | -1845 | 908155 | 908155 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1995-08-01 | INV | 0
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of home refrigerators at Sharp Roxy Appliance Corp. | Individual | ASP | MAL | REF | 12 | INV | 29 | A | D | CFC | 65 | 65 | 0 | 0 | 1994-03-01 | 1995-05-01 | 1995-06-01 |  | 1997-12-01 | 2000-12-01 | 962000 | -103353 | 858647 | 858647 | 100% | 0 | 0 | 0 | 125060 | -13435.89 | 111624.11 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC in the manufacture of commercial refrigeration products at United Refrigerator Sdn. Bhd. | Individual | ASP | MAL | REF | 13 | INV | 37 | A | I | CFC | 71 | 71 | 0 | 0 | 1994-07-01 | 1997-06-01 | 1995-07-01 |  | 1997-12-01 | 2003-07-01 | 351200 | -11852 | 339348 | 339348 | 100% | 0 | 0 | 0 | 45656 | -1540.76 | 44115.24 | 0 | 0 | Completed in 1997. Financially completed in 2003. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC in the manufacture of refrigeration products at Oyl Appliances | Individual | ASP | MAL | REF | 13 | INV | 42 | A | I | CFC | 22 | 22 | 0 | 0 | 1994-07-01 | 1995-11-01 | 1995-12-01 |  | 1997-12-01 | 2002-03-01 | 625100 | -38549 | 586551 | 586551 | 100% | 0 | 0 | 0 | 81263 | -5011.37 | 76251.63 | 0 | 0 | Completed in 1997. Financially completed in 2002. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC in the manufacture of commercial refrigeration products at Lian Pang Refrigerator and Electrical Sdn. Bhd. | Individual | ASP | MAL | REF | 13 | INV | 45 | A | I | CFC | 12.5 | 12.5 | 0 | 0 | 1994-07-01 | 1995-11-01 | 1995-07-01 |  | 1998-10-01 | 2003-09-01 | 201100 | -1 | 201099 | 201099 | 100% | 0 | 0 | 0 | 26143 | -0.13 | 26142.87 | 0 | 0 | Completed in 1998. Financially completed in 2003. |  | 1994 |  | Investment
FIN | IBRD | Substitution of CFC-12 and CFC-11 with HFC-134a and HCFC-141b respectively and elimination of the use of 1.1.1. TCA in household refrigerator manufacturing at Matsuchita Electric Co. (Melcom) | Individual | ASP | MAL | REF | 15 | INV | 51 | N | D |  | 99.73 | 99.73 | 0 | 0 | 1994-12-01 | 1996-04-01 | 1997-12-01 |  | 1996-01-01 | 1997-08-01 | 1276500 | -4307 | 1272193 | 1272193 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. $5,096.82 will be returned. |  |  | 1996-01-01 | INV | 0
FIN | UNDP | Umbrella project for elimination of CFCs 11 and 12 in the manufacture of commercial refrigeration at 4 small enterprises: Lim Yew, Exquisite, FMC, Noblelane | Individual | ASP | MAL | REF | 18 | INV | 73 | A | I | CFC | 44.8 | 44.8 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1997-05-01 |  | 2001-12-01 | 2003-04-01 | 680000 | -49438 | 630562 | 630562 | 100% | 0 | 0 | 0 | 88400 | -6426.82 | 81973.18 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1995 | 1997-10-01 | Investment
FIN | UNDP | Elimination of CFCs 11 and 12 in the manufacture of domestic refrigerators at Sanyo Industries (Malaysia) Berhad | Individual | ASP | MAL | REF | 18 | INV | 74 | A | I | CFC | 13.4 | 13.4 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1996-11-01 |  | 1998-12-01 | 2000-12-01 | 183260 | -1 | 183259 | 183259 | 100% | 0 | 0 | 0 | 23823.8 | -0.13 | 23823.67 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1995 |  | Investment
FIN | IBRD | Phase out of CFC-12 MAC system production equipment and conversion to HFC-134a MAC system manufacturing in Nippondenso Capital Sdn. Bhd. | Individual | ASP | MAL | REF | 18 | INV | 75 | N | I | CFC | 0 | 0 | 0 | 0 | 1995-11-01 | 1997-03-01 | 1999-11-01 |  | 1998-11-01 | 1998-12-01 | 2232718 | -420628.19 | 1812089.81 | 1812089.81 | 100% | 0 | 0 |  | 290253.34 | -30624.23 | 259629.11 | 0 | 0 | Project completed. Disbursement figure in 1999 and 2000 progress reports is incorrect. Additional balance to be returned to 37th ExCom. |  |  | 1997-07-01 | INV | 0
FIN | IBRD | Phase out of CFC-12 MAC manufacturing equipment and conversion to HFC-134a MAC system manufacturing at APM Air Conditioners Sdn., Bhd. | Individual | ASP | MAL | REF | 18 | INV | 76 | N | I |  | 5 | 5 | 0 | 0 | 1995-11-01 | 1998-01-01 | 1999-11-01 |  | 2001-12-01 | 2002-10-01 | 1181553 | -150254.79 | 1031298.21 | 1031298.21 | 100% | 0 | 0 |  | 153601.89 | -19533.15 | 134068.74 | 0 | 0 | Project was physically and financially completed. DOE has endorsed destruction of equipment and disposal plan. PCR submitted. Balance to be returned at the 39th ExCom. |  |  | 1999-06-01 | INV | 0
FIN | IBRD | Reduction of the consumption of ODSs in the commercial air-conditioning sector via training, recovery and recycling of CFC-11 and CFC-12 in chillers at Mashrae | Individual | ASP | MAL | REF | 18 | TAS | 77 | N | I | CFC | 105 | 4.45 | 0 | 0 | 1995-11-01 | 1998-03-01 | 1996-11-01 |  | 2000-11-01 | 2002-10-01 | 824078 | -118061 | 706017 | 706017 | 100% | 0 | 0 |  | 107130.14 | -15347.93 | 91782.21 | 0 | 0 | Final PCR not submitted to ExCom as DOE and the Bank requested MASHRAE and CETEC to revise PCR to ensure that information accurately reflects the actual nature of this project including lessons learned. Actual ODP phaseout low because many chiller owners decided to replace the CFC unit with the new non-CFC unit instead of using the facility. |  |  | 1999-12-01 | INV | 0
FIN | IBRD | Phase-out of CFC-12 MAC manufacturing equipment and conversion of HFC-134a MAC manufacturing equipment at UCM Industrial Corporation Berhad | Individual | ASP | MAL | REF | 19 | INV | 90 | N | I | CFC | 0 | 0 | 0 | 0 | 1996-05-01 | 1998-05-01 | 2000-05-01 |  | 2000-08-01 | 2002-10-01 | 1468797 | -263251 | 1205546 | 1205546 | 100% | 0 | 0 |  | 190943.61 | -34222.63 | 156720.98 | 0 | 0 | Project was physically and financially completed. DOE has endorsed destruction of equipment and disposal plan. PCR submitted. Savings to be returned at the 39th ExCom. |  |  | 2000-03-01 | INV | 0
FIN | UNDP | Conversion to CFC-free technology in the manufature of polyurethane foam at Kwang Tai Refrigeration | Individual | ASP | MAL | REF | 23 | INV | 103 | A | I | CFC | 28.5 | 28.5 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2001-08-01 | 2003-04-01 | 316000 | -9988 | 306012 | 306012 | 100% | 0 | 0 | 0 | 41080 | -1298.44 | 39781.56 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Preparation of two projects in commercial refrigeration subsector | Individual | ASP | MAL | REF | 27 | PRP | 117 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-04-01 | 2000-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2000. Financially completed in 2000. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 and R502 consumption at Thermo Cooling Engineering, Sdn. Bhd. | Individual | ASP | MAL | REF | 28 | INV | 126 | A | I | CFC | 5.9 | 5.9 | 0 | 0 | 1999-07-01 | 1999-12-01 | 2002-02-01 |  | 2000-12-01 | 2002-03-01 | 46502 | -1900 | 44602 | 44602 | 100% | 0 | 0 | 0 | 6045.26 | -247 | 5798.26 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 and CFC-12 and R-502 in the manufacture of commercial refrigerators by conversion HCFC-141b, HCFC-22 and HFC-404a at Gai Hin Refrigeration Sdn. Bhd. | Individual | ASP | MAL | REF | 29 | INV | 128 | A | I | CFC | 41 | 41 | 0 | 0 | 1999-11-01 | 2001-06-01 | 2002-12-01 |  | 2002-06-01 | 2003-11-01 | 354147 | -16712 | 337435 | 337435 | 100% | 0 | 0 | 0 | 46039.11 | -2172.56 | 43866.55 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1999 |  | Investment
FIN | IBRD | Project preparation for MACs and compressors project category |  | ASP | MAL | REF | 30 | PRP | 132 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2000-12-01 |  | 2001-12-01 | 2001-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Preparation of 2 projects in the commercial refrigeration subsector | Individual | ASP | MAL | REF | 30 | PRP | 134 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-06-01 | 2001-04-01 |  | 2001-04-01 | 2003-01-01 | 20000 | -4121.12 | 15878.88 | 15879 | 100% | -0.12 | 0 | 0 | 2600 | -536.08 | 2063.9386 | -0.018623 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at eleven small and sedium-sized enterprises | Individual | ASP | MAL | REF | 32 | INV | 140 | A | I | CFC | 64.8 | 64.8 | 0 | 0 | 2000-12-01 | 2002-06-01 | 2004-01-01 |  | 2003-11-01 | 2005-10-01 | 960658 | -29788 | 930870 | 930870 | 100% | 0 | 0 | 0 | 115672.4 | -3276 | 112396.4 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at three enterprises (SKE Fookmei, Master Shanghai Turnparts and Maltar Industries) | Individual | ASP | MAL | REF | 32 | INV | 141 | A | I | CFC | 34.9 | 34.9 | 0 | 0 | 2000-12-01 | 2002-12-01 | 2004-01-01 |  | 2003-11-01 | 2005-09-01 | 505184 | -12891 | 492293 | 492293 | 100% | 0 | 0 | 0 | 65570.24 | -1418 | 64152.24 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNIDO | Replacement of CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigerating equipment at Tung Kiong Factories Sdn. Bhd. | Individual | ASP | MAL | REF | 32 | INV | 143 | A | I | CFC | 18.9 | 18.9 |  |  | 2000-12-01 | 2001-10-01 | 2003-07-01 |  | 2003-03-01 | 2004-05-01 | 202075 | -503 | 201572 | 201571.65 | 100% | 0.35 | 0 |  | 26270 | -107 | 26163 | 0 | 0 | FIN
FIN | IBRD | Replacement of CFC-12 refrigerant with HFC 134a in the manufacturing of MAC system at Sanden International (M) Sdn., Bhd. | Individual | ASP | MAL | REF | 34 | INV | 144 | N | R | CFC | 0 | 0 | 0 | 0 | 2001-07-01 | 2003-02-01 | 2003-01-01 |  | 2002-08-01 | 2003-02-01 | 807280 | -15079 | 792201 | 792201 | 100% | 0 | 0 |  | 48440 | -904.74 | 47535.26 | 0 | 0 | Project fully completed. |  |  |  | INV | 0
FIN | UNDP | Preparation for HCFC phase-out investment activities (refrigeration manufacturing sector except air-to-air air-conditioning) | Individual | ASP | MAL | REF | 57 | PRP | 162 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-06-01 | 2010-03-01 |  | 2012-07-01 | 2013-12-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 | 0 | 0 | 9000 | 0 | 9000 | 0 | 0 | Financially completed in 2013. | Completed in 2012. | 2009 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (air-to-air air-conditioning sector) | Individual | ASP | MAL | REF | 57 | PRP | 163 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2011-08-01 | 2010-03-01 |  | 2012-07-01 | 2013-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 2250 | 0 | 2250 | 0 | 0 | Financially completed in 2013. | Completed in 2012. | 2009 |  | Investment
ONG | UNDP | Preparation for HCFC phase-out investment activities (stage II) (refrigeration sector) | Individual | ASP | MAL | REF | 72 | PRP | 177 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 | 2015-07-01 | 2016-05-01 | 2017-06-01 |  |  | 50000 | 0 | 50000 | 21366.82 | 42.73% | 28633.18 | 0 | 11453.272 | 3500 | 0 | 1495.6774 | 2004.3226 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Prepration of HPMP Stage II refrigeration completed and submitted in 77th ExCom Prodoc signed (actual/planned, yes/no and date):Letter of Authorisation sent 29 September 2014 Missions undertaken (actual/planned):1 TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: Contract signed First disbursement date (actual/planned): 42186Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | on going |  |  | Non-Investment
ONG | UNDP | Preparation for HCFC phase-out investment activities (stage II) (air-conditioning sector) | Individual | ASP | MAL | REF | 72 | PRP | 178 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 | 2015-07-01 | 2016-05-01 | 2017-06-01 |  |  | 50000 | 0 | 50000 | 6914.11 | 13.83% | 43085.89 | 0 | 17234.356 | 3500 | 0 | 483.9877 | 3016.0123 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Prepration of HPMP Stage II compled for AC sector and submitted in 77th ExCom. Prodoc signed (actual/planned, yes/no and date):Letter of Authorisation sent 29 September 2014 Missions undertaken (actual/planned):1 TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: Contract signed First disbursement date (actual/planned): 42186Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:Prodoc signed at HQ in 2015/2016. Due to long process of getting EPU's signature, it was agreed that the approval is at HQ level | on going |  |  | Non-Investment
FIN | IBRD | Country programme preparation | Individual | ASP | MAL | SEV | 04 | CPG | 02 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 16294 | -8287 | 8007 | 8007 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1991) |  | ASP | MAL | SEV | 04 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 38289 | 5307 | 43596 | 43596 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1992) |  | ASP | MAL | SEV | 06 | PRP | 06 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 120000 | -65592 | 54408 | 54408 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Initially we reported expenditure of $54,408 and expenditure of $35,201 for country program. However, that was due to a coding mistake and the expenditure has been adjusted to $89,609 and entry for country program removed. |  |  |  | Non-INV | 0
FIN | UNDP | Institutional strengthening in relation to projects on reduction of ozone depleting substances | Individual | ASP | MAL | SEV | 09 | INS | 08 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-10-01 | 1996-03-01 |  | 1996-12-01 | 2003-04-01 | 322520 | -15703 | 306817 | 306817 | 100% | 0 | 0 | 0 | 41927.6 | -2041.39 | 39886.21 | 0 | 0 | Completed in 1996. Financially completed in 2003. |  | 1993 |  | Non-Investment
FIN | IBRD | Preparation of investment projects (1993) |  | ASP | MAL | SEV | 09 | PRP | 09 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 28200 | 916 | 29116 | 29116 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | User-sector pre-investment studies (1993) |  | ASP | MAL | SEV | 10 | PRP | 10 | A | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-06-30 | 1994-06-01 |  | 1993-12-01 | 1993-12-01 | 75000 | -58343 | 16657 | 16657 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Project preparation assistance | Individual | ASP | MAL | SEV | 10 | PRP | 12 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-07-01 | 1993-12-01 |  | 1994-03-01 | 1997-12-01 | 50000 | 4438 | 54438 | 54438 | 100% | 0 | 0 | 0 | 6500 | 576.94 | 7076.94 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1993 |  | Investment
FIN | UNDP | National ODS conference | Individual | ASP | MAL | SEV | 10 | TRA | 13 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-07-01 | 1993-07-01 |  | 1993-07-01 | 1997-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1993 |  | Non-Investment
FIN | IBRD | Up-date country programme | Individual | ASP | MAL | SEV | 12 | CPG | 34 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The Country Program up-date is complete. Final document submitted to the Bank and the Government on 4/30/95. |  |  |  | Non-INV | 0
FIN | UNDP | Project preparation assistance | Individual | ASP | MAL | SEV | 12 | PRP | 31 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-03-01 |  | 1994-07-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1994 |  | Investment
FIN | IBRD | Supervision of project implementation (1994) |  | ASP | MAL | SEV | 12 | PRP | 32 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 35815 | 12744 | 48559 | 48559 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1994) |  | ASP | MAL | SEV | 12 | PRP | 36 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 66610 | 2803 | 69413 | 69413 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Project preparation assistance | Individual | ASP | MAL | SEV | 15 | PRP | 52 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-01-01 | 1995-06-01 |  | 1995-12-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Investment
FIN | IBRD | Preparation/supervision of investment projects ODS I (1995) |  | ASP | MAL | SEV | 16 | PRP | 57 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 206488 | 0 | 206488 | 206488 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Preparation of subprojects which was initiated in 1994 is complete resulting in 11 proposals. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation/supervision of investment projects ODS II (1995) |  | ASP | MAL | SEV | 16 | PRP | 58 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 12258 | 0 | 12258 | 12258 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | This budget is being utilized to supervise the MACs and halon Recover and Recycling projects approved for Malaysia in 1993. |  |  |  | Non-INV | 0
FIN | UNDP | Project preparation assistance | Individual | ASP | MAL | SEV | 18 | PRP | 83 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-11-01 | 2002-05-01 | 18000 | -4 | 17996 | 17996 | 100% | 0 | 0 | 0 | 2340 | -1 | 2339 | 0 | 0 | Completed in 1996. Financially completed in 2002. |  | 1995 |  | Investment
FIN | IBRD | Project preparation |  | ASP | MAL | SEV | 18 | PRP | 84 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | Project completed. |  |  |  | Non-INV | 0
FIN | UNDP | Extension of institutional strengthening project | Individual | ASP | MAL | SEV | 20 | INS | 91 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1996-10-01 | 1998-03-01 | 1998-10-01 |  | 1998-10-01 | 2003-04-01 | 215000 | -5523 | 209477 | 209477 | 100% | 0 | 0 | 0 | 27950 | -717.99 | 27232.01 | 0 | 0 | Completed in 1998. Financially completed in 2003. |  | 1996 |  | Non-Investment
FIN | IBRD | Project preparation |  | ASP | MAL | SEV | 21 | PRP | 92 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1998-03-01 | 1997-12-01 |  | 1999-06-01 | 1999-06-01 | 27000 | 0 | 27000 | 27000 | 100% | 0 | 0 |  | 3510 | 0 | 3510 | 0 | 0 | Completed. |  |  | 1999-06-01 | Non-INV | 0
FIN | UNDP | Project preparation in the foam and refrigeration sectors | Individual | ASP | MAL | SEV | 21 | PRP | 93 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-12-01 | 2004-12-01 | 100000 | -34365 | 65635 | 65635 | 100% | 0 | 0 | 0 | 13000 | -4467 | 8533 | 0 | 0 | Completed in 1998. Financially Completed in 2004. |  | 1997 |  | Investment
FIN | UNDP | Extension of the institutional strengthening project (Phase III) | Individual | ASP | MAL | SEV | 26 | INS | 114 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-01-01 | 2000-12-01 |  | 2000-12-01 | 2005-05-01 | 215000 | -36884 | 178116 | 178116 | 100% | 0 | 0 | 0 | 27950 | -4795 | 23155 | 0 | 0 | Completed in 2000. Financially completed in 2005. |  | 1998 |  | Non-Investment
FIN | IBRD | Preparation of projects in the solvent sector and a national CFC phase out programme |  | ASP | MAL | SEV | 27 | PRP | 135 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-31 | 2001-01-01 |  | 2000-12-01 | 2000-12-01 | 95000 | 0 | 95000 | 95000 | 100% | 0 | 0 |  | 12350 | 0 | 12350 | 0 | 0 | Ongoing |  |  |  | Non-INV | 0
FIN | UNDP | Extension of the institutional strengthening project (Phase IV) | Individual | ASP | MAL | SEV | 32 | INS | 142 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2003-02-01 | 2003-01-01 |  | 2005-03-01 | 2009-07-01 | 215000 | -10994 | 204006 | 204006 | 100% | 0 | 0 | 0 | 27950 | -1429.22 | 26520.78 | 0 | 0 | Completed in 2005.Financially completed in 2009. |  | 2000 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project | Individual | ASP | MAL | SEV | 38 | INS | 148 | N | I | No_ODP | 23.1 | 23.1 | 0 | 0 | 2002-11-01 | 2004-01-01 | 2004-12-01 |  | 2005-12-01 | 2010-10-01 | 279500 | -17132.83 | 262367.17 | 262367 | 100% | 0.17 | 0 | 0 | 36335 | -2227.27 | 34107.71 | 0.02 | 0 | Financially completed in 2010. |  | 2002 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase VI) | Individual | ASP | MAL | SEV | 44 | INS | 153 | N | I | No_ODP | 23.1 | 23.1 | 0 | 0 | 2004-12-01 | 2006-02-01 | 2006-12-01 |  | 2008-07-01 | 2011-12-01 | 279500 | 0 | 279500 | 279500 | 100% | 0 | 0 | 0 | 20963 | 0 | 20963 | 0 | 0 | Completed in 2008. Financially completed in 2011. |  | 2004 |  | Non-Investment
FIN | UNDP | Assistance to carry out an HCFC survey | Individual | ASP | MAL | SEV | 45 | TAS | 155 | A | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-04-01 | 2006-12-01 |  | 2008-08-01 | 2009-12-01 | 91743 | -13695 | 78048 | 78048 | 100% | 0 | 0 | 0 | 8257 | -1232.57 | 7024.4306 | -0.0006 | 0 | Completed in 2008. Financially completed in 2009. |  | 2005 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase VII) | Individual | ASP | MAL | SEV | 53 | INS | 159 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-01-01 | 2009-11-01 |  | 2010-12-01 | 2011-12-01 | 279500 | -2000.74 | 277499.26 | 277499 | 100% | 0.26 | 0 | 0 | 20963 | -150.06 | 20812.9214 | 0.0186 | 0 | Completed in 2010. Financially completed in 2011. |  | 2007 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase VIII) | Individual | ASP | MAL | SEV | 58 | INS | 165 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2009-07-01 | 2010-03-01 | 2011-11-01 |  | 2011-12-01 | 2014-03-01 | 139750 | 139518 | 279268 | 279268 | 100% | 0 | 0 | 0 | 10481 | 10463.6 | 20944.6 | 0 | 0 | Financially completed in 2014. | The project is being financially closed in 2012. | 2009 |  | Non-Investment
COM | UNDP | Extension of institutional strengthening project (phase IX: 1/2012-12/2013) | Individual | ASP | MAL | SEV | 64 | INS | 167 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2011-07-01 | 2011-12-01 | 2013-12-01 |  | 2015-06-01 |  | 279500 | 0 | 279500 | 279500 | 100% | 0 | 0 | 0 | 20963 | 0 | 20963 | 0 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2015. |  | 2011 |  | Non-Investment
COM | UNDP | Extension of institutional strengthening project (phase X: 1/2014-12/2015) | Individual | ASP | MAL | SEV | 70 | INS | 171 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2013-07-01 | 2014-11-01 | 2015-12-01 |  | 2015-12-01 |  | 279500 | 0 | 279500 | 231416.16 | 82.8% | 48083.84 | 0 | 40871.264 | 19565 | 0 | 16199.1312 | 3365.8688 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2015. |  | 2013 |  | Non-Investment
ONG | UNDP | Extension of institutional strengthening project (phase XI: 1/2016-12/2017) | Individual | ASP | MAL | SEV | 75 | INS | 180 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2015-11-01 | 2016-11-01 | 2017-12-01 | 2017-12-01 |  |  | 357760 | 0 | 357760 | 42860.55 | 11.98% | 314899.45 | 0 | 125959.78 | 25043 | 0 | 3000.2145 | 22042.7855 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Ozone Day celebration, A7 data and CP data reporting, awareness workshops Prodoc signed (actual/planned, yes/no and date):42583 Missions undertaken (actual/planned):- TOR for consultants/subcontracts completed (actual/planned): Contract/PO/MOA agreements signed: First disbursement date (actual/planned): 42675Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | ongoing | 2015 |  | Non-Investment
FIN | UNDP | Conversion of metal cleaning processes from trichloroethane solvents to non-ODS organic solvents at Ngai Cheong Metal Industries | Individual | ASP | MAL | SOL | 11 | INV | 18 | A | I | TCA | 2 | 2 | 0 | 0 | 1993-11-01 | 1995-04-01 | 1994-11-01 |  | 1995-04-01 | 1998-12-01 | 63480 | 0 | 63480 | 63480 | 100% | 0 | 0 | 0 | 8252.4 | 0 | 8252.4 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1993 |  | Investment
FIN | UNDP | Elimination of trichloroethane in home appliances parts manufacturing at Matsushita Electric Co. Main Plant | Individual | ASP | MAL | SOL | 11 | INV | 19 | A | I | TCA | 1 | 1 | 0 | 0 | 1993-11-01 | 1994-05-01 | 1994-10-01 |  | 1994-05-01 | 1998-12-01 | 113570 | -2661 | 110909 | 110909 | 100% | 0 | 0 | 0 | 14764.1 | -346 | 14418.1 | 0 | 0 | Completed in 1994. Financially completed in 1998. |  | 1993 |  | Investment
FIN | UNDP | Elimination of trichloroethane in home appliances parts manufacturing at Matsushita Electric Co. Port Klang Plant | Individual | ASP | MAL | SOL | 11 | INV | 20 | A | I | TCA | 1 | 1 | 0 | 0 | 1993-11-01 | 1995-04-01 | 1994-10-01 |  | 1995-04-01 | 1998-12-01 | 173280 | 25992 | 199272 | 199272 | 100% | 0 | 0 | 0 | 22526.4 | 3378.96 | 25905.36 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1993 |  | Investment
FIN | USA | Conference on the elimination of ozone depleting solvents |  | ASP | MAL | SOL | 11 | TRA | 14 | A | I |  | 0 |  | 0 |  | 1993-11-01 |  | 1994-11-01 |  | 1994-11-01 | 1994-11-01 | 24000 | 0 | 24000 | 24000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1993
CLO | UNDP | Elimination of the use of CFC-113 in the integral circuit lead frame cleaning processes at San Matech Sdn. Bhd. | Individual | ASP | MAL | SOL | 12 | INV | 28 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1995-07-01 |  |  | 1995-07-01 | 141000 | -141000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 18330 | -18330 | 0 | 0 | 0 | Canceled in 1995. Financially Completed in 1995. |  | 1994 |  | Investment
FIN | UNDP | Elimination of the use of 111 TCA in the automobile bumper cleaning processes at Perusahaan Otomobil National Bhd. (Proton) | Individual | ASP | MAL | SOL | 12 | INV | 35 | A | I | TCA | 20 | 20 | 0 | 0 | 1994-03-01 | 1995-04-01 | 1995-12-01 |  | 1995-04-01 | 1998-12-01 | 700439 | -59344 | 641095 | 641095 | 100% | 0 | 0 | 0 | 91057.07 | -7715 | 83342.07 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1994 |  | Investment
FIN | IBRD | Conversion of metal cleaning process from 1,1,1 TCA to non-ozone depleting organic solvents in Ban Seng Lee Industries Sdn. Bhd. | Individual | ASP | MAL | SOL | 17 | INV | 62 | N | D | TCA | 3.36 | 3.36 | 0 | 0 | 1995-07-01 | 1996-09-01 | 1996-07-01 |  | 1996-07-01 | 1996-09-01 | 108400 | 0 | 108400 | 108400 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1996-07-01 | INV | 0
CLO | France | Phasing out the use of CFC-113 in the electronics industry through the technical promotion of no clean processes |  | ASP | MAL | SOL | 18 | INV | 78 | A | D |  | 0 |  | 0 |  | 1995-11-01 |  | 1996-11-01 |  |  | 1997-11-01 | 226600 | -226600 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Projet annulé
FIN | IBRD | Conversion of metal cleaning process from 1,1,1 TCA to hydrocarbons at AE Technology Sdn. Bhd. | Individual | ASP | MAL | SOL | 18 | INV | 79 | N | R | TCA | 17 | 16.8 | 0 | 0 | 1995-11-01 | 1996-11-01 | 1997-05-01 |  | 1995-08-01 | 1996-09-01 | 56893 | 0 | 56893 | 56893.2 | 100% | -0.2 | -0.4 |  | 7396.09 | 0 | 7396.11 | -0.02 | -0.02 | Project completed. |  |  |  | INV | 0
CLO | IBRD | Conversion of correction fluid manufacturing process from 1,1,1 TCA to non-ODS solvent at Mondial Sdn. Bhd. | Individual | ASP | MAL | SOL | 18 | INV | 80 | N | R |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1996-11-01 |  |  | 2001-03-01 | 144447 | -144447 | 0 | 0 | #DIV/0! | 0 | 0 |  | 18778.11 | -18778.11 | 0 | 0 | 0 | Project cancelled. |  |  | 1999-06-01 | INV | 0
FIN | IBRD | Conversion of correction fluid manufacturing process from 1,1,1 TCA to non-ODS solvent at Widetech | Individual | ASP | MAL | SOL | 18 | INV | 81 | N | I | TCA | 29 | 29 | 0 | 0 | 1995-11-01 | 1997-09-01 | 1996-11-01 |  | 1997-12-01 | 1997-12-01 | 398418 | 0 | 398418 | 398418 | 100% | 0 | 0 |  | 51794.34 | 0 | 51794.34 | 0 | 0 | Project completed. |  |  | 1997-07-01 | INV | 0
FIN | IBRD | Conversion of metal cleaning process from 1,1,1 TCA to hydrocarbons at Eng Teknologi Sdn. Bhd. | Individual | ASP | MAL | SOL | 18 | INV | 82 | N | I | TCA | 3.4 | 3.36 | 0 | 0 | 1995-11-01 | 1998-07-01 | 1996-11-01 |  | 1998-09-01 | 1999-02-01 | 117379 | 0 | 117379 | 117378.6 | 100% | 0.4 | 0.4 |  | 15259.27 | 0 | 15259.21 | 0.06 | 0.06 | Project completed. |  |  | 1997-04-01 | INV | 0
FIN | France | No clean process improvement training for electronic assemblers who phased out the use of CFC-113 |  | ASP | MAL | SOL | 22 | TRA | 97 | A | D |  | 0 |  | 0 |  | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1999-04-01 | 1999-04-01 | 192423 | 25462 | 217885 | 217885 | 100% | 0 |  |  | 0 | 1500 | 1500 | 0 |  | Projet achevé.
FIN | UNDP | Aerosol conversion at Compagnie Manufacturiere de Produits Cosmetiques Ltee. | Individual | AFR | MAR | ARS | 12 | INV | 03 | A | D | CFC | 25 | 25 | 0 | 0 | 1994-03-01 | 1996-06-01 | 1995-03-01 |  | 1996-06-01 | 1998-12-01 | 62150 | 0 | 62150 | 62150 | 100% | 0 | 0 | 0 | 8079.5 | 0 | 8079.5 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1994 |  | Investment
FIN | Germany | Project preparation and technical assistance at Chem Tech | Individual | AFR | MAR | ARS | 26 | PRP | 09 | N | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1998-06-01 | 1999-12-01 |  | 1999-12-01 | 2001-01-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation
FIN | Germany | Investment project for phasing out CFCs at Chem Tech-Stella Industries, Port Louis | Individual | AFR | MAR | ARS | 27 | INV | 11 | A | I | CFC | 16 | 16 | 0 | 0 | 1999-03-01 | 1999-03-01 | 1999-11-01 |  | 2001-06-01 | 2002-01-01 | 90400 | 0 | 90400 | 90400 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed, final report submitted |  |  | 2000-12-01
FIN | Germany | Project preparation for the phase out of methyl bromide use | Individual | AFR | MAR | FUM | 37 | PRP | 13 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2002-12-01 | 2003-08-01 |  | 2002-10-01 | 2003-12-01 | 11000 | 0 | 11000 | 11000 | 100% | 0 | 0 | 0 | 1430 | 0 | 1430 | 0 | 0 | A project proposal was prepared but not accepted by the beneficiary. Assistance of beneficiary will now be unter the TPMP approved at 41st ExCom.
FIN | Germany | Implementation of an ODS terminal phase out management plan (first tranche) | Multi-Year | AFR | MAR | PHA | 41 | INV | 15 | A | I | CFC | 0 | 2.6 | 0 |  | 2003-12-01 | 2004-05-01 | 2004-12-01 |  | 2005-10-01 | 2006-04-01 | 110000 | 0 | 110000 | 110000 | 100% | 0 | 0 | 0 | 14300 | 0 | 14300 | 0 | 0 | 2 Hydrocarbon trainings have been conducted. NOU started the process of converting the New Court House through a subsidy scheme provided under the project. Next tranche has been approved.
FIN | Germany | Implementation of an ODS terminal phase-out management plan (second tranche) | Multi-Year | AFR | MAR | PHA | 45 | INV | 16 | A | I | CFC | 2 | 2 | 0 |  | 2005-04-01 | 2005-11-01 | 2006-04-01 |  | 2007-12-01 | 2008-04-01 | 62030 | 0 | 62030 | 62030 | 100% | 0 | 0 | 0 | 8064 | 0 | 8064 | 0 | 0 | 2nd tranche was approved.
FIN | Germany | Implementation of an ODS terminal phase-out management plan (third tranche) | Multi-Year | AFR | MAR | PHA | 50 | INV | 18 | A | I | CFC | 2 | 2 | 0 |  | 2006-11-01 | 2007-03-01 | 2007-12-01 |  | 2010-08-01 | 2012-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | All activities under the TPMP have been completed.
FIN | Germany | Preparation of a HCFC phase-out management plan | Individual | AFR | MAR | PHA | 55 | PRP | 20 | A | I | HCFC | 0 |  | 0 |  | 2008-07-01 | 2008-11-01 | 2009-07-01 |  | 2010-12-01 | 2012-12-01 | 75000 | 0 | 75000 | 75000 | 100% | 0 | 0 | 0 | 9750 | 0 | 9750 | 0 | 0 | HPMP submitted as planned in Dec 2010
COM | Germany | HCFC phase-out management plan (first tranche) | Multi-Year | AFR | MAR | PHA | 63 | INV | 21 | A | I | HCFC | 0 | 2.5 | 0 |  | 2011-04-01 | 2011-10-01 | 2014-03-01 |  | 2014-06-01 |  | 157050 | 0 | 157050 | 157050 | 100% | 0 | 0 | 0 | 18846 | 0 | 18846 | 0 |  | Specifications were developed and tender advertised for the CO2 demonstration unit for supermarkets to be installed at the local University. | Funds disbursed
ONG | Germany | HCFC phase-out management plan (second tranche) | Multi-Year | AFR | MAR | PHA | 72 | INV | 22 | A | I | HCFC | 0 |  | 0 |  | 2014-05-01 | 2014-06-01 | 2017-05-01 | 2017-01-01 |  |  | 131400 | 0 | 131400 | 131400 | 100% | 0 | 0 | 0 | 15851 | 0 | 15851 | 0 |  | 2 technician trainings were conducted, 1 each on HC and CO2. NOU also attended the Cool training in Germany to gain better understanding of natural refrigerants. | Currently the next tranche is being prepared for submission |  |  | INV
ONG | Germany | Verification report for stage I of HCFC phase-out management plan | Individual | AFR | MAR | PHA | 75 | TAS | 25 | A | I | HCFC | 0 |  | 0 |  | 2015-11-01 | 2016-11-01 | 2016-12-01 | 2017-05-01 |  |  | 30000 | 0 | 30000 | 5200 | 17.33% | 24800 | 0 | 24800 | 3900 | 0 | 3900 | 0 |  | No work was done in 2016 as tranche submisison is planned for 2017. | The verification consultant was hired in Feb and currently the verification is ongoing to be completed by end of April 2017
FIN | UNDP | Preparation of projects in the refrigeration and foam sectors | Individual | AFR | MAR | REF | 12 | PRP | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-05-01 | 1994-09-01 |  | 1995-06-01 | 1997-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Blyfridge Ltd. | Individual | AFR | MAR | REF | 15 | INV | 05 | A | I | CFC | 2 | 2 | 0 | 0 | 1994-12-01 | 1996-06-01 | 1996-06-01 |  | 1997-11-01 | 2000-12-01 | 197208 | -20441.78 | 176766.22 | 176766 | 100% | 0.22 | 0 | 0 | 25637.04 | -2657.43 | 22979.58 | 0.03 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at A.H. Bahemia | Individual | AFR | MAR | REF | 15 | INV | 06 | A | I | CFC | 2.7 | 2.7 | 0 | 0 | 1994-12-01 | 1996-06-01 | 1996-06-01 |  | 1997-11-01 | 2000-12-01 | 213500 | -25495 | 188005 | 188005 | 100% | 0 | 0 | 0 | 27755 | -3314.35 | 24440.65 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
TRF | UNDP | National CFC-12 recovery and recycling programme and demonstration of retrofit technology in commercial refrigeration | RMP-Component | AFR | MAR | REF | 17 | TAS | 07 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1997-05-01 | 1996-07-01 |  |  | 1999-07-01 | 176350 | -162281 | 14069 | 14069 | 100% | 0 | 0 | 0 | 22925.5 | -21096 | 1829.5 | 0 | 0 | Transferred in 1999. Financially completed in 1999. |  | 1995 | 1999-07-01 | Investment
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | MAR | REF | 23 | PRP | 08 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1997-12-01 | 1998-03-01 |  | 1998-03-01 | 2000-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | MAR | REF | 26 | TAS | 10 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2002-08-01 | 2004-05-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted TPMP approved at 41st Excom
FIN | Germany | National CFC-12 recovery and recycling programme and demonstration of retrofit technology in commercial refrigeration | Individual | AFR | MAR | REF | 28 | TAS | 12 | A | I | CFC | 8 | 5 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2001-06-01 |  | 2005-12-01 | 2006-09-01 | 183377 | -3647 | 179730 | 179730 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Certification of R&R center. Follow-up evaluation of the performance of recycling center. Recommendation that the training institue should cooperate with the local gas dealer in utilizing the facility. PCR was submitted in 2006.
FIN | Germany | Project preparation for a CFC terminal phase out management plan | Individual | AFR | MAR | REF | 37 | PRP | 14 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-02-01 | 2003-08-01 |  | 2003-08-01 | 2004-06-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project completed. TPMP approved at 41st Excom
FIN | UNEP | Complement for country programme preparation | Individual | AFR | MAR | SEV | 09 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-06-01 |  | 1993-06-01 | 1993-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0
FIN | UNEP | Institutional strengthening for the phase-out of ozone depleting substances | Individual | AFR | MAR | SEV | 10 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1995-08-01 | 1996-06-01 |  | 2004-12-01 | 2007-07-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0 |  |  |  | 1999-12-01
FIN | UNEP | Extension of the institutional strengthening project (phase II) | Individual | AFR | MAR | SEV | 45 | INS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-10-01 | 2007-04-01 |  | 2007-11-01 | 2009-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of the institutional strengthening project (phase III) | Individual | AFR | MAR | SEV | 53 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2012-03-01 | 2009-11-01 |  | 2014-12-01 |  | 60000 | 0 | 60000 | 46504.05 | 77.51% | 13495.95 | 0 | 13496 | 0 | 0 | 0 | 0 | 0 | Project completed | Project completed
ONG | UNEP | Extension of the institutional strengthening project (phase IV: 1/2015-12/2016) | Individual | AFR | MAR | SEV | 73 | INS | 23 | A | I |  | 0 |  | 0 |  | 2014-11-01 | 2015-12-01 | 2016-12-01 | 2017-09-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 60000 | 6000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): _ The licensing and quota system are in place and functioning. The NOU registered all importers of HCFCs and organized stakeholders’ workshop to allocate HCFC licenses and quotas to importers. The NOU conducted three inspection visits to monitor distribution of HCFCs to check compliance with the quotas allocated. On 22 February, 2016, the NOU conducted Capacity Building workshop for Customs Officers on Tracking of Illegal Trade, attended by 30 custom officers. The NOU conducted two training workshops for technicians, namely, on hydrocarbons at MITD from 13-15 Sept, 2016 on carbon dioxide cascade system at UDM from 20-22 Sept, 2016. The NOU collected, analyzed, compiled and submitted 2015 Country Programme and Article 7 Data reports in May 2016. The NOU celebrated the 2016 international ozone day with several activities. The NOU participated in all Montreal Protocol meetings organized in 2016. __ Legal arrangements(actual/planned): The SSFA was drafted and signed by UNEP and the Government of Mauritius in Sept 2015.___Initial stages of project implementation(actual/planned): _Yes__ Intermediate goals achieved (actual/planned): Yes___ Project completion and follow up: __No_ First disbursement date (actual/planned): First payment ($15,000) was disbursed in February 2016.___ All funds disbursed (yes/no): _No__ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): __N/A_ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: __N/A_ | Brief progress report (actual/planned): The NOU continues to monitor imports and trade of ODS and ODS related equipment. Collection of the 2016 data on ODS imports and consumption has been completed and is being analyzed for submission. NOU commenced preparation of national legislative requirement processes in planning for ratification of Kigali amendment.
ONG | Germany | Survey of ODS alternatives at the national level | Individual | AFR | MAR | SEV | 75 | TAS | 24 | A | I | HCFC | 0 |  | 0 |  | 2015-11-01 | 2016-05-01 | 2016-11-01 | 2017-05-01 |  |  | 70000 | 0 | 70000 | 26073 | 37.25% | 43927 | 0 | 43927 | 9100 | 0 | 3389 | 5711 |  | The alternative survey was conducted over a period of 6 months between 2016 and 2017 | The final report has been submitted to MLF in April 2017.
ONG | UNEP | Extension of the institutional strengthening project (phase V: 1/2017-12/2018) | Individual | AFR | MAR | SEV | 77 | INS | 26 | A | I |  | 0 |  | 0 |  | 2016-12-01 |  | 2018-12-01 | 2018-12-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | Newly approved project. | Brief progress report (actual/planned): The project was approved in Dec 2016. The licensing and quota system are in place and operational.The NOU continues to monitor imports and trade of ODS and ODS related equipment. Collection of the 2016 data on ODS imports and consumption has been completed and is being analyzed for submission. NOU commenced preparation of national legislative requirement processes in planning for ratification of Kigali amendment. ___ Legal arrangements (actual/planned): The SSFA was drafted and sent to the Government of Mauritius for signature. ___Initial stages of project implementation (actual/planned): __Yes_ Intermediate goals achieved (actual/planned): _No__ Project completion and follow up: _Yes__ First disbursement date (actual/planned): __No ____. All funds disbursed (yes/no): No__ Any delay? (yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: __N/A_
COM | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, first tranche, Marshall Islands) | Multi-year | ASP | MAS | PHA | 63 | TAS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2012-04-01 | 2015-03-01 |  | 2016-12-01 |  | 54000 | 0 | 54000 | 36375 | 67.36% | 17625 | 1300 | 1300 | 7020 | 0 | 4728.75 | 2291.25 | 169 | Brief progress report (actual/planned): The activities that were implemented in 2016 comprised of (i) implementation of licensing and quota system, (ii) permit system for sales of HCFCs, (iii) monitoring of refrigerant identifiers and RAC servicing tools and (iv) outreaching and awareness raising. Remaining activities regarding training of customs and enforcement officers was organized from 29-30 August 2016 in Majuro with 10 participants. RMI also continued enforcing the import control of HCFC-based RAC equipment for which license is valid on a calender year basis. However, Marshall Islands has not yet adopted 2012 HS Code in the national customs tariff and there was challenges in the establishment of RAC Association. This will be continued under the second tranche of HPMP. 2015 CP data was submitted to the MLFS online. Project was completed as of Decembner 2016. The last payment to country was approved and the payment was requested in the UMOJA system. Legal arrangement: The SSFA was signed in April 2012. First Mission: September 2012 TOR completed: Not applicable First disbursement date: April 2012 All funds disbursed (yes/no): No, waiting for the last payment to be transferred to country. Any delay? (yes/no): No, project was completed in 2016. If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): Yes Any ongoing problems (yes/no): No, project was completed in 2016. If Yes, is any action required by ExCom: N/A | Project is completed. The request for the final payment has been approved and waiting to be transfered to the country.
ONG | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, second tranche, Marshall Islands) | Multi-year | ASP | MAS | PHA | 74 | TAS | 11 | A | I |  | 0.1 |  | 0 |  | 2015-05-01 | 2016-12-01 | 2020-05-01 | 2020-12-01 |  |  | 47700 | 0 | 47700 | 9227.51 | 19.34% | 38472.49 | 33000 | 3847.249 | 6201 | 0 | 1199.5763 | 5001.4237 | 4290 | Brief progress report (actual/planned): The SSFA was signed by UNEP and the Government of RMI in February 2016. As the SSFA of the first tranche has not yet been closed until December 2016, the priority was given to the closure of the first tranche SSFA. The first payment under the second tranche was processed in December 2016 when the SSFA of the first tranche was closed. However, a RAC expert was recruited to deliver update RAC training workshop, which was expected in the first quarter of 2017. 2015 CP data was submitted to MLFS online. Legal arrangements (actual/planned): The SSFA was signed in February 2016. First Mission: Not yet. TOR completed: Not applicable. First disbursement date: Not yet. All funds disbursed (yes/no): No. Any delay? (yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): Yes, limited capacity of the new NOO who was newly assigned by the government in 2016 If Yes, is any action required by ExCom: No. | Brief progress report (actual/planned): The first payment of the second tranche was transferred to the country in Januray 2017. The update RAC training workshop was organized from 24-26 January 2017 to strengthen RAC technician capacity in the safe handling of flammable refrigerants, which has been available in the PIC region. There were 15 participants in the workshops. UNEP keeps regular communications with the country to expedite HPMP implementation as per the agreed work plan. The capacity building activities for new NOO will be conducted as part of the PIC network meeting in 2017. UNEP mission is planned in 2017.
FIN | Australia | Implementation of the PIC Strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | MAS | REF | 36 | TAS | 02 | A | I |  | 0.8 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2005-04-01 |  | 2008-06-01 | 2012-05-01 | 26000 | 0 | 26000 | 26000 | 100% | 0 | 0 | 0 | 3380 | 0 | 3380 | 0 | 0 | completed |  | 2002
FIN | Australia | Implementation of the PIC Strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | MAS | REF | 36 | TAS | 04 | A | I |  | 0.2 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2005-04-01 |  | 2008-06-01 | 2012-05-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 | 0 | 0 | 1040 | 0 | 1040 | 0 | 0 | completed |  | 2002
FIN | UNEP | Country programme preparation | Individual | ASP | MAS | SEV | 21 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1999-01-01 | 1998-08-01 |  | 2002-03-01 | 2005-12-01 | 40000 | -25000 | 15000 | 15000 | 100% | 0 | 0 |  | 5200 | -3250 | 1950 | 0 | 0 |  |  |  | 1999-12-01
FIN | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | MAS | SEV | 36 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-03-01 | 2005-04-01 |  | 2006-08-01 | 2009-12-01 | 34000 | -822 | 33178 | 33178 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase II) | Individual | ASP | MAS | SEV | 50 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2010-02-01 | 2007-11-01 |  | 2008-11-01 | 2010-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase II, second year) | Individual | ASP | MAS | SEV | 53 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-07-01 | 2009-11-01 |  | 2010-03-01 | 2010-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | ASP | MAS | SEV | 59 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-06-01 | 2011-11-01 |  | 2011-12-01 | 2012-12-01 | 32500 | 27500 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV: 12/2011-11/2013) | Individual | ASP | MAS | SEV | 64 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2011-11-01 | 2013-11-01 |  | 2013-11-01 | 2014-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of the institutional strengthening project (phase V: 12/2013-11/2015) | Individual | ASP | MAS | SEV | 70 | INS | 10 | A | I |  | 0 |  | 0 |  | 2013-07-01 | 2014-07-01 | 2015-11-01 | 2017-09-01 |  |  | 60000 | 0 | 60000 | 41029 | 68.38% | 18971 | 18971 | 1897.1 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned: The NOU has been responsible for the management of all Montreal Protocol activities. The operation of the NOU was going on well. The license/quota system has been enforced in 2016. NOU also coordinated and facilitated the implementation of HPMP and ODS Alternative Survey. The NOU also organized the 2016 ozone day celebration, and the Government actively joined the regional and global ozone related meetings e.g. the network meeting, OEWG and the MOP meetings. In April of 2016, there was a change in the NOU. However the last NOO retained supervisory role of the new officer. UNEP kept regular communication with the new NOO to strengthen their Montreal Protocol knowledge and implementation capacity (from Bangkok through phone calls, emails, skype conference calls etc.). 2015 Article 7 and CP data were submitted to the Ozone Secretariat and MLFS respectively. The SSFA was amended to extend the closing date to 30 September 2017 to accommodate the disbursement of the remaining payments. Legal arrangements(actual/planned): The SSFA was signed April 2014. Initial stages of project implementation(actual/planned): Dec 2013/Apr 2014 Intermediate goals achieved (actual/planned): Compliance (2015) sustained : First disbursement date (actual/planned): July 2014. All funds disbursed (yes/no): No. Any delay?(yes/no): Yes. If Yes, reasons for delay & action plan to resolve: The change of the NOO in April 2016. The new NOO was new to the Montreal Protocol. NEP kept regular communication with the new NOO to strengthen their Montreal Protocol knowledge and implementation capacity (from Bangkok through phone calls, emails, skype conference calls etc.). If Yes, will delay have impact on project completion date (yes/no): Yes. The SSFA was extended to September 2017. Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): Country continues to enforce the licensing and quota system. Although the new NOO has been appointed since 2016, the capacity building activities for RMI NOO is necessary and will be conducted as part of the PIC network meeting in 2017. There are 2 remaining payments to be disbursed to the country. Projecct will be completed in September 2017.
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | ASP | MAS | SEV | 75 | TAS | 12 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-06-01 | 2016-12-01 | 2017-06-01 |  |  | 40000 | 0 | 40000 | 2549.85 | 6.375% | 37450.15 | 22450.15 | 3745.015 | 5200 | 0 | 331.4805 | 4868.5195 | 2918.5195 | Brief progress report (actual/planned): The SSFA was signed by UNEP and the Government of RMI in January 2016. The first payment was made to the country in June 2016. A regional expert was appointed by UNEP to provide support to the NOO in the planned, data collection and preparation of report. NOU contracted local consultants to assist in the data collection. The data collection started in 2016. In November 2016, the regional consultant visited RMI to assist the NOU and the local consultant in the identification of the current use of ODS alternatives by substance/sector and collection of import/export data for the substances for the past a couple of years. The regional consultant also provided support in establishing growth patterns in use by substance/sector and in compiling data on available ODS alternatives for various applications. The data collection was on-going. Legal arrangements(actual/planned): The SSFA was signed in Januray 2016 Initial stages of project implementation(actual/planned): January 2016 . Intermediate goals achieved (actual/planned): Not applicable. Project completion and follow up: Not applicable. First disbursement date (actual/planned): June 2016. All funds disbursed (yes/no): No. Any delay?(yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): Yes, limited capacity of the new NOO who was newly assigned by the government in 2016. If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): NOU with assistance of UNEP and regional consultant is still conducting the data survey (advance stage) to identify the current use of ODS alternatives by substance/sector and collection of import/export data for the substances for the past a couple of years. The draft report will be prepared by the NOU and the regional consultant based on the format approved by ExCom decision 75/67 as contained in document UNEP/OzL.Pro/ExCom/75/77/Rev.1.
FIN | UNEP | Country programme preparation | Individual | EUR | MAT | SEV | 12 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-07-01 | 1995-06-01 |  | 1995-07-01 | 1995-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | AFR | MAU | PHA | 48 | PRP | 15 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-02-01 | 2007-04-01 |  | 2007-11-01 | 2008-12-01 | 12000 | 0 | 12000 | 12000 | 100% | 0 | 0 | 0 | 900 | 0 | 900 | 0 | 0 | Completed in 2007. Financially completed in 2008. |  | 2006 |  | Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | MAU | PHA | 48 | PRP | 16 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-01-01 | 2007-04-01 |  | 2007-04-01 | 2007-12-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 |  | 2340 | 0 | 2340 | 0 | 0
FIN | UNDP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | MAU | PHA | 53 | INV | 19 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 | 2009-10-01 | 2009-11-01 |  | 2009-12-01 | 2013-03-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 7650 | 0 | 7650 | 0 | 0 | Financially completed in 2013. |  | 2007 |  | Investment
FIN | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-year | AFR | MAU | PHA | 53 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-03-01 |  | 2011-03-01 | 2011-07-01 | 96000 | 0 | 96000 | 96000 | 100% | 0 | 0 |  | 12480 | 0 | 12480 | 0 | 0
ONG | UNEP | Preparation of a HCFC phase-out management plan | Individual | AFR | MAU | PHA | 55 | PRP | 20 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-12-01 | 2009-07-01 | 2017-12-01 |  |  | 85000 | 0 | 85000 | 25000 | 29.41% | 60000 | 60000 | 6000 | 11050 | 0 | 3250 | 7800 | 7800 | Brief progress report (actual/planned): Country signed the SSFA in February 2016. First payment sent in April 2016. Legal arrangements (actual/planned): Agreement signed in February 2016. All activities under the SSFA are completed (as planned) No__First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ Yes __ First disbursement date (actual/planned): _1st disbursement done in April 2016 __ All funds disbursed (yes/no): _ No__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Brief progress report (actual/planned): Country signed the SSFA in February 2016. First payment sent in April 2016. Legal arrangements (actual/planned): Agreement signed in February 2016. All activities under the SSFA are completed (as planned) No. __First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ Yes __ First disbursement date (actual/planned): _1st disbursement done in April 2016 __ All funds disbursed (yes/no): _ No__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor the submission of the HCFC phase-out management plan.
FIN | UNDP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | MAU | PHA | 57 | INV | 22 | N | I | CFC | 3 | 3 | 0 | 0 | 2009-04-01 | 2010-01-01 | 2011-03-01 |  | 2010-12-01 | 2013-03-01 | 55000 | -4966.47 | 50033.53 | 50034 | 100% | -0.47 | 0 | 0 | 4950 | -446.98 | 4503.06 | -0.04 | 0 | Financially completed in 2013. |  | 2009 |  | Investment
FIN | UNEP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | MAU | PHA | 57 | TAS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 |  | 2010-03-01 |  | 2013-12-01 | 2014-12-01 | 59000 | -59000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 7670 | -7670 |  | 0
FIN | France | Conversion of CFC-based commercial refrigeration installations in the fishing industry |  | AFR | MAU | REF | 14 | TAS | 05 | A | D | CFC | 2 |  | 0 |  | 1994-09-01 | 1999-07-01 | 1996-09-01 |  | 2000-11-01 | 2000-12-01 | 106900 | -7378 | 99522 | 99522 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Projet achevé. PCR soumis |  |  | 2000-06-01
FIN | France | Training of refrigeration technicians |  | AFR | MAU | REF | 14 | TRA | 04 | A | D |  | 0 |  | 0 |  | 1994-09-01 | 1997-07-01 | 1995-09-01 |  | 1999-06-01 | 1999-08-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Projet achevé. PCR soumis |  |  | 1997-05-01
FIN | UNEP | Development of an RMP | Individual | AFR | MAU | REF | 33 | PRP | 06 | A | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-12-01 | 2003-12-01 |  | 2003-12-01 | 2011-03-01 | 60000 | -25000 | 35000 | 35000 | 100% | 0 | 0 |  | 7800 | -3250 | 4550 | 0 | 0
FIN | UNDP | Formulation of the investment components of the RMP | Individual | AFR | MAU | REF | 39 | PRP | 08 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-12-01 | 2005-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1125 | 0 | 1125 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2003 |  | Investment
FIN | UNDP | Implementation of the RMP: centralized recovery and recycling of CFC-12 programme | RMP-Component | AFR | MAU | REF | 41 | TAS | 11 | N | I | CFC | 4 | 4 | 0 | 0 | 2003-12-01 | 2005-02-01 | 2006-12-01 |  | 2007-12-01 | 2013-09-01 | 100995 | -695.89 | 100299.11 | 100299 | 100% | 0.11 | 0 | 0 | 9089.55 | -62.63 | 9026.91 | 0.01 | 0 | Financially completed in 2013. |  | 2003 |  | Investment
FIN | UNDP | Implementation of the RMP: awareness and incentive programme for MAC, commercial and industrial end-users | RMP-Component | AFR | MAU | REF | 41 | TAS | 12 | N | I | CFC | 4 | 4 | 0 | 0 | 2003-12-01 | 2005-02-01 | 2006-12-01 |  | 2007-12-01 | 2011-08-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 9000 | 0 | 9000 | 0 | 0 | Completed in 2007. Financially completed in 2011. |  | 2003 |  | Non-Investment
FIN | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | AFR | MAU | REF | 41 | TAS | 13 | A | I | CFC | 1.2 | 1.2 | 0 | 0 | 2003-12-01 | 2004-06-01 | 2006-12-01 |  | 2007-12-01 | 2008-12-01 | 30000 | -834 | 29166 | 29166 | 100% | 0 | 0 |  | 3900 | -108 | 3792 | 0 | 0
FIN | UNEP | Implementation of the RMP: training programme for customs excise | Individual | AFR | MAU | REF | 41 | TRA | 09 | A | I | CFC | 1.6 | 1.6 | 0 | 0 | 2003-12-01 | 2004-06-01 | 2004-12-01 |  | 2007-12-01 | 2008-12-01 | 39800 | -1069 | 38731 | 38731 | 100% | 0 | 0 |  | 5174 | -139 | 5035 | 0 | 0
FIN | UNEP | Implementation of the RMP: training the trainers of refrigeration technicians | Individual | AFR | MAU | REF | 41 | TRA | 10 | A | I | CFC | 2.6 | 2.6 | 0 | 0 | 2003-12-01 | 2004-06-01 | 2005-07-01 |  | 2007-12-01 | 2011-03-01 | 65000 | -21716 | 43284 | 43284 | 100% | 0 | 0 |  | 8450 | -2823.08 | 5626.92 | 0 | 0
FIN | France | Country programme preparation |  | AFR | MAU | SEV | 13 | CPG | 01 | A | D |  | 0 |  | 0 |  | 1994-07-01 | 1994-07-01 | 1995-07-01 |  | 1995-07-01 | 1995-09-01 | 44000 | -4229 | 39771 | 39771 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed. Balance returned at 57th ExCom.
FIN | France | Institutional strengthening project proposal |  | AFR | MAU | SEV | 14 | INS | 02 | A | D |  | 0 |  | 0 |  | 1994-09-01 | 1996-01-01 | 1997-09-01 |  | 1999-12-01 | 1999-12-01 | 38874 | -12891 | 25983 | 25983 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Projet achevé. PCR soumis
FIN | France | Training and awareness of personnel involved in the task of codifying and identifying ODS and ODS-containing material |  | AFR | MAU | SEV | 14 | TRA | 03 | A | D |  | 0 |  | 0 |  | 1994-09-01 | 1996-10-01 | 1995-09-01 |  | 1996-11-01 | 1996-12-01 | 10000 | -544 | 9456 | 9456 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | La formation a eu lieu du 02 au 04 novembre 1996. Project completed.
FIN | UNEP | Renewal of the institutional strengthening project (Phase II) | Individual | AFR | MAU | SEV | 33 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2004-01-01 | 2003-04-01 |  | 2004-01-01 | 2007-01-01 | 25900 | 0 | 25900 | 25900 | 100% | 0 | 0 |  | 3367 | 0 | 3367 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (phase III) | Individual | AFR | MAU | SEV | 43 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2005-01-01 | 2006-07-01 |  | 2007-12-01 | 2008-12-01 | 33670 | 0 | 33670 | 33670 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase IV) | Individual | AFR | MAU | SEV | 49 | INS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-01-01 | 2008-06-01 |  | 2015-12-01 | 2016-12-01 | 60000 | 0 | 60000 | 59113 | 98.52% | 887 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. All balances to be returned. | Project financially completed. All balances to be returned.
ONG | UNEP | Renewal of the institutional strengthening project (phase V) | Individual | AFR | MAU | SEV | 57 | INS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2016-03-01 | 2011-03-01 | 2017-12-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 60000 | 6000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Legal arrangements (actual/planned): SSFA signed in March 2016. First payment sent in April 2016. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): April 2016__ All funds disbursed (yes/no): _No.__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a __ | Brief progress report (actual/planned): Legal arrangements (actual/planned): SSFA signed in March 2016. First payment sent in April 2016. Country reported 2015 CP data and 2015 Art7 data. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): April 2016__ All funds disbursed (yes/no): _No.__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a __
FIN | UNIDO | Project preparation in the aerosol sector | Individual | EUR | MDN | ARS | 30 | PRP | 13 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-06-01 | 2001-04-01 |  | 2000-12-01 | 2001-07-01 | 15000 | -2425 | 12575 | 12575.43 | 100% | -0.43 | 0 |  | 1950 | -318 | 1632 | 0 | 0 | FIN
CLO | UNIDO | Phase-out of CFC 11/12 in the manufacture of aerosols by conversion to HFC and hydrocarbon propellants at Alkaloid A.D. | Individual | EUR | MDN | ARS | 32 | INV | 17 | A | I | CFC | 25 | 25 |  |  | 2000-12-01 | 2001-12-01 | 2003-03-01 |  |  | 2008-12-01 | 110000 | -10533 | 99467 | 99467 | 100% | 0 | 0 |  | 14300 | -1369 | 12931 | 0 | 0 | CLO
FIN | UNIDO | Phasing out of CFC-11 from flexible slabstock foam manufacturing at Sileks Ad Co. | Individual | EUR | MDN | FOA | 22 | INV | 05 | A | I | CFC | 280 | 280 |  |  | 1997-05-01 | 1997-12-01 | 1998-11-01 |  | 1998-12-01 | 2002-09-01 | 520125 | -4895 | 515230 | 515230.18 | 100% | -0.18 | 0 |  | 67616 | -742 | 66874 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 from manufacturing of rigid PU sandwich panels at Sileks Ad Co. | Individual | EUR | MDN | FOA | 22 | INV | 06 | A | I | CFC | 67.6 | 67.6 |  |  | 1997-05-01 | 1997-12-01 | 1998-06-01 |  | 1997-12-01 | 2002-05-01 | 284236 | -6661 | 277575 | 277574.83 | 100% | 0.17 | 0 |  | 36951 | -923 | 36028 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a demonstration project in methyl bromide (tobacco, pepper, tomatoes) | Individual | EUR | MDN | FUM | 25 | PRP | 08 | A | I |  | 0 | 0 |  |  | 1998-07-01 | 1998-08-01 | 1999-08-01 |  | 1998-09-01 | 2001-07-01 | 20000 | -1561 | 18439 | 18439 | 100% | 0 | 0 |  | 2600 | -207 | 2393 | 0 | 0 | FIN
FIN | UNIDO | Demonstration project - three alternatives to the use of methyl bromide: non-soil cultivation, biofumigation and low dose chemicals in tobacco and horticultural production | Individual | EUR | MDN | FUM | 26 | DEM | 09 | A | I | MBR | 0 | 0 |  |  | 1998-11-01 | 1999-02-01 | 2000-12-01 |  | 2002-04-01 | 2003-05-01 | 259600 | -558 | 259042 | 259042.44 | 100% | -0.44 | 0 |  | 33748 | -126 | 33622 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a phase-out project in the methyl bromide sector | Individual | EUR | MDN | FUM | 30 | PRP | 14 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-07-01 | 2001-04-01 |  | 2001-10-01 | 2002-12-01 | 20000 | -499 | 19501 | 19500.93 | 100% | 0.07 | 0 |  | 2600 | -69 | 2531 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of methyl bromide in tobacco seedling and horticulture production sector | Individual | EUR | MDN | FUM | 32 | INV | 16 | A | I | MBR | 27.2 | 27.2 |  |  | 2000-12-01 | 2001-10-01 | 2006-01-01 |  | 2004-12-01 | 2006-05-01 | 1075207 | -3327 | 1071880 | 1071880.3 | 100% | -0.3 | 0 |  | 128273 | -553 | 127720 | 0 | 0 | FIN
FIN | UNIDO | Technical assistance in preparation of the national halon management plan | Individual | EUR | MDN | HAL | 37 | TAS | 19 | A | I | HAL | 32.1 | 32.1 |  |  | 2002-07-01 | 2002-12-01 | 2003-01-01 |  | 2003-05-01 | 2004-02-01 | 25000 | -8 | 24992 | 24992.06 | 100% | -0.06 | 0 |  | 3250 | -6 | 3244 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | EUR | MDN | PHA | 45 | INV | 21 | A | I | CFC | 10 | 10 |  |  | 2005-04-01 | 2005-12-01 | 2006-04-01 |  | 2006-11-01 | 2007-12-01 | 154210 | -134 | 154076 | 154075.51 | 100% | 0.49 | 0 |  | 11566 | -10 | 11556 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | EUR | MDN | PHA | 50 | INV | 23 | A | I | CFC | 5 | 5 |  |  | 2006-11-01 | 2007-05-01 | 2007-11-01 |  | 2007-11-01 | 2008-07-01 | 79871 | -123 | 79748 | 79748.05 | 100% | -0.05 | 0 |  | 5990 | -9 | 5981 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal phase-out management plan for CFCs (third tranche) | Multi-Year | EUR | MDN | PHA | 53 | INV | 24 | A | I | CFC | 5 | 5 |  |  | 2007-11-01 | 2008-06-01 | 2008-11-30 |  | 2008-11-01 | 2010-05-01 | 15000 | -15 | 14985 | 14985.03 | 100% | -0.03 | 0 |  | 1125 | -1 | 1124 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | EUR | MDN | PHA | 55 | PRP | 25 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-09-01 | 2009-07-31 |  | 2010-04-01 | 2010-12-01 | 85000 | -634 | 84366 | 84366.02 | 100% | -0.02 | 0 |  | 6375 | -48 | 6327 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Terminal phase-out management plan for CFCs (fourth tranche) | Multi-Year | EUR | MDN | PHA | 56 | INV | 26 | A | I | CFC | 5 | 5 |  |  | 2008-11-01 | 2009-08-01 | 2009-11-30 |  | 2010-12-01 | 2010-12-01 | 15000 | 0 | 15000 | 14999.99 | 100% | 0.01 | 0 |  | 1125 | 0 | 1125 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal phase-out management plan for CFCs (fifth tranche) | Multi-Year | EUR | MDN | PHA | 59 | INV | 28 | A | I |  | 0 | 0 |  |  | 2009-11-01 | 2010-11-01 | 2010-11-30 |  | 2013-12-01 | 2014-04-01 | 15000 | -959 | 14041 | 14040.68 | 100% | 0.32 | 0 |  | 1125 | -72 | 1053 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | HCFC phase-out management plan (phase I, first tranche) | Multi-Year | EUR | MDN | PHA | 60 | INV | 29 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-12-01 | 2015-12-31 |  | 2011-03-01 | 2012-05-01 | 15000 | 0 | 15000 | 14999.98 | 100% | 0.02 | 0 |  | 1125 | 0 | 1125 | 0 | 0 | FIN
FIN | UNIDO | HCFC phase-out management plan (advance funding for the institutional strengthening) | Multi-Year | EUR | MDN | PHA | 63 | INV | 30 | A | I |  | 0 | 0 |  |  | 2011-04-01 | 2011-06-01 | 2012-03-31 |  | 2011-12-01 | 2012-05-01 | 26000 | 0 | 26000 | 26000.01 | 100% | -0.01 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | HCFC phase-out management plan (phase I, remainder of second tranche) | Multi-Year | EUR | MDN | PHA | 64 | INV | 31 | A | I |  | 0 | 0 |  |  | 2011-07-01 | 2011-10-01 | 2012-07-31 |  | 2013-12-01 | 2015-09-01 | 81000 | -1 | 80999 | 80998.72 | 100% | 0.28 | 0 |  | 6075 | 0 | 6075 | 0 | 0 | FIN |  |  |  | INV
COM | UNIDO | HCFC phase-out management plan (phase I, third tranche) (conversion from HCFC-141b to HFCs in the manufacture of polyurethane foam for the commercial refrigeration units, sandwich panels and insulated doors) | Multi-Year | EUR | MDN | PHA | 67 | INV | 32 | A | I | HCFC | 1.6 | 1.6 |  |  | 2012-07-01 | 2012-11-01 | 2014-07-31 |  | 2014-12-01 |  | 136955 | 0 | 136955 | 127957.09 | 93.43% | 8997.91 | 993.65 | 1 | 10272 | 0 | 9597 | 675 | 74.5238 | The project was operationally completed. |  |  |  | INV
FIN | UNIDO | HCFC phase-out management plan (phase I, third tranche) | Multi-Year | EUR | MDN | PHA | 67 | INV | 33 | A | I |  | 0 | 0 |  |  | 2012-07-01 | 2012-11-01 | 2013-07-31 |  | 2014-12-01 | 2016-12-01 | 158000 | -7105 | 150895 | 151387.62 | 100.3% | -492.62 | 0 |  | 11850 | -533 | 11354 | -37 | 0 | The project was financially completed and the balance was returned at the 76th ExCom. |  |  |  | INV
COM | UNIDO | HCFC phase-out management plan (phase I, fourth tranche) | Multi-Year | EUR | MDN | PHA | 70 | INV | 34 | A | I |  | 0 | 0 |  |  | 2013-07-01 | 2013-12-01 | 2014-07-31 |  | 2016-12-01 |  | 148000 | 0 | 148000 | 117317.21 | 79.27% | 30682.79 | 30798.67 | 25000 | 11100 | 0 | 8799 | 2301 | 2309.9003 | 'This specific grant included funding for conversion of 4 foam enterprises. One foam company restructured management and therefore the conversion could not take place as planned. The other tranches referring to servicing sector and IS activities are on track. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | Project completed. Financial closure is ongoing. |  |  | INV
COM | UNIDO | HCFC phase-out management plan (phase I, fifth tranche) | Multi-Year | EUR | MDN | PHA | 72 | INV | 35 | A | I | HCFC | 0.2 | 0.2 |  |  | 2014-05-01 | 2014-12-01 | 2016-05-31 |  | 2015-12-01 |  | 82000 | 0 | 82000 | 81793.74 | 99.75% | 206.26 | 0 | 1 | 6150 | 0 | 6135 | 15 | 0 | The project was operationally completed. |  |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (phase I, sixth tranche) | Multi-Year | EUR | MDN | PHA | 75 | INV | 37 | A | I | HCFC | 0.1 | 0 |  |  | 2015-11-01 | 2016-09-01 | 2017-12-01 | 2017-12-01 |  |  | 82000 | 0 | 82000 | 1081.75 | 1.319% | 80918.25 | 8942.62 | 40000 | 6150 | 0 | 0 | 6150 | 670.6965 | Implementation work plan was agreed with counterpart as of April 2016. The tranche includes IS component that will support HPMP coordination and NOU management. Further implementation of logbooks and support for the enforcement of the inventory of HCFC containing equipment was initiated. Technical specifications were developed for purchase of identifiers for training purpose. Equipment contract was issued last quarter 2016 and delivery will take place first quarter 2017. Was there any delay during the reporting year? Activities are inter-connected with the previous tranches; there are no delays in regard of achieving the HPMP targets and activities execution. Due to use of funding from previous phase, disbursements of current tranche were re-scheduled, without impact on activities progress. Any impact on project completion date: Yes. Any action required by Executive Committee? No | Equipment delivery took place in March 2017. |  |  | INV
ONG | UNIDO | Verification report for stage I of HCFC phase-out management plan | Individual | EUR | MDN | PHA | 75 | TAS | 38 | A | I |  | 0 | 0 |  |  | 2015-11-01 |  | 2017-12-01 | 2017-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 30000 | 2700 | 0 | 0 | 2700 | 0 | Implementation was initiated, national consultants were identified in view of conducting consumption data verification report covering the years 2015 and 2016. Was there any delay during the reporting year? No. The verification report approved budget will be used for covering several years HCFCs consumption data, Any impact on project completion date: Yes, operational completion is planned for Dec 17. Any action required by Executive Committee? No | NC for conducting the verification report has been identified by counterpart and contractual arrangements are pending. Operational completion is planned in the current year. |  |  | NON-INV
FIN | UNIDO | Phasing out of CFCs at the refrigerator plant of Frinko | Individual | EUR | MDN | REF | 20 | INV | 03 | A | I | CFC | 104 | 104 |  |  | 1996-10-01 | 1997-09-01 | 1998-04-01 |  | 1998-12-01 | 2001-12-01 | 1081724 | -556 | 1081168 | 1081168.35 | 100% | -0.35 | 0 |  | 140624 | -295 | 140329 | 0 | 0 | FIN
FIN | UNIDO | Preparation of refrigerant management plan | Individual | EUR | MDN | REF | 24 | PRP | 07 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-06-01 | 1999-04-01 |  | 1998-09-01 | 2000-04-01 | 30000 | -4462 | 25538 | 25538 | 100% | 0 | 0 |  | 3900 | -585 | 3315 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: recovery and recycling | RMP | EUR | MDN | REF | 28 | TAS | 10 | A | I | CFC | 13.5 | 13.5 |  |  | 1999-07-01 | 1999-12-01 | 2001-06-01 |  | 2002-02-01 | 2003-12-01 | 220044 | -43661 | 176383 | 176382.7 | 100% | 0.3 | 0 |  | 28606 | -5713 | 22893 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Refrigerant management plan: training for good practices in refrigeration | RMP | EUR | MDN | REF | 28 | TRA | 11 | A | I |  | 0 | 0 |  |  | 1999-07-01 | 1999-10-01 | 2001-06-01 |  | 2002-03-01 | 2003-05-01 | 70000 | -6146 | 63854 | 63853.74 | 100% | 0.26 | 0 |  | 9100 | -812 | 8288 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: training of customs officers | RMP | EUR | MDN | REF | 28 | TRA | 15 | A | I |  | 0 | 0 |  |  | 1999-07-01 | 1999-12-01 | 2001-03-01 |  | 2002-03-01 | 2003-05-01 | 37180 | -6973 | 30207 | 30207.28 | 100% | -0.28 | 0 |  | 4833 | -912 | 3921 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a Country Programme | Individual | EUR | MDN | SEV | 15 | CPG | 01 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-08-01 | 1995-12-01 |  | 1996-12-01 | 1998-08-01 | 80000 | -7780 | 72220 | 72220 | 100% | 0 | 0 |  | 10400 | -1026 | 9374 | 0 | 0 | FIN
FIN | UNIDO | Preparation of projects in the refrigeration, aerosol and foam sector | Individual | EUR | MDN | SEV | 18 | PRP | 02 | A | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-01-01 | 1996-03-01 |  | 2000-12-01 | 2002-05-01 | 30000 | -3675 | 26325 | 26325.22 | 100% | -0.22 | 0 |  | 3900 | -483 | 3417 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNIDO | Creation of an Ozone Secretariat | Individual | EUR | MDN | SEV | 20 | INS | 04 | N | I |  | 0 | 0 |  |  | 1996-10-01 | 1997-04-01 | 1999-10-01 |  | 2000-08-01 | 2001-07-01 | 152900 | 0 | 152900 | 152900 | 100% | 0 | 0 |  | 19877 | -25 | 19852 | 0 | 0 | FIN |  |  | 1999-10-01 | NON-INV
FIN | UNIDO | Institutional strengthening for Montreal Protocol related activities, Phase II | Individual | EUR | MDN | SEV | 30 | INS | 12 | N | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-06-01 | 2002-04-01 |  | 2002-12-01 | 2003-09-01 | 101950 | 0 | 101950 | 101949.6 | 100% | 0.4 | 0 |  | 13254 | -1 | 13253 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Renewal of the institutional strengthening project (phase III) | Individual | EUR | MDN | SEV | 35 | INS | 18 | N | I |  | 0 | 0 |  |  | 2001-12-01 | 2002-08-01 | 2004-01-01 |  | 2004-07-01 | 2005-09-01 | 101950 | 0 | 101950 | 101949.96 | 100% | 0.04 | 0 |  | 13254 | -1 | 13253 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Renewal of institutional strengthening project: phase IV | Individual | EUR | MDN | SEV | 42 | INS | 20 | N | I |  | 0 | 0 |  |  | 2004-04-01 | 2004-09-01 | 2006-04-01 |  | 2006-12-01 | 2007-05-01 | 132347 | 0 | 132347 | 132347 | 100% | 0 | 0 |  | 9926 | 0 | 9926 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Extension of the institutional strengthening project (phase V) | Individual | EUR | MDN | SEV | 48 | INS | 22 | N | I |  | 0 | 0 |  |  | 2006-04-01 | 2006-09-01 | 2008-04-01 |  | 2008-12-01 | 2011-05-01 | 132347 | -1127 | 131220 | 131220.16 | 100% | -0.16 | 0 |  | 9926 | -84 | 9842 | 0 | -1 | FIN |  |  |  | NON-INV
FIN | UNIDO | Extension of the institutional strengthening project (phase VI) | Individual | EUR | MDN | SEV | 57 | INS | 27 | N | I |  | 0 | 0 |  |  | 2009-04-01 | 2009-08-01 | 2011-03-31 |  | 2010-12-01 | 2012-02-01 | 132347 | -43 | 132304 | 132304.06 | 100% | -0.06 | 0 |  | 9926 | -3 | 9923 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | Survey of ODS alternatives at the national level | Individual | EUR | MDN | SEV | 74 | TAS | 36 | A | I |  | 0 | 0 |  |  | 2015-05-01 | 2016-05-01 | 2016-05-31 | 2017-05-01 |  |  | 40000 | 0 | 40000 | 28681.02 | 71.7% | 11318.98 | 7945.17 | 10000 | 3600 | 0 | 0 | 3600 | 715.0653 | Mission to Skopje took place and a work plan was agreed upon. Consultants were selected to conduct the survey and contracts have been issued. Data collection completed. Report drafting commenced. | Survey report submitted to the 78th ExCom. |  |  | NON-INV
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | ASP | MDV | PHA | 50 | PRP | 12 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2007-11-01 |  | 2007-11-01 | 2007-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | ASP | MDV | PHA | 50 | PRP | 13 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-04-01 | 2007-11-01 |  | 2007-09-01 | 2009-12-01 | 15000 | -8440 | 6560 | 6560 | 100% | 0 | 0 | 0 | 1125 | -633 | 492 | 0 | 0 | Completed in 2007. Financially completed in 2009. |  | 2006 |  | Investment
FIN | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | ASP | MDV | PHA | 53 | INV | 15 | N | I | CFC | 0.7 | 0.7 | 0 | 0 | 2007-11-01 | 2011-04-01 | 2009-11-01 |  | 2015-05-01 | 2016-05-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 7650 | 0 | 7650 | 0 | 0 | Financially completed in 2016. | Reclamation centre operationalisation is underway. Technical support has been requested from India where reclamation centers are in operations - study tour is expected to be undertaken for this in Q3-2015. | 2007 |  | Investment
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-year | ASP | MDV | PHA | 53 | TAS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-04-01 | 2009-03-01 |  | 2009-07-01 | 2010-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | MDV | PHA | 55 | PRP | 16 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-11-01 | 2009-07-01 |  | 2010-12-01 | 2012-12-01 | 85000 | -12971 | 72029 | 72029 | 100% | 0 | 0 |  | 11050 | -1686.23 | 9363.77 | 0 | 0
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | ASP | MDV | PHA | 58 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2009-12-01 | 2010-07-01 |  | 2010-07-01 | 2011-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0
ONG | UNDP | HCFC phase-out management plan (first tranche) | Multi-year | ASP | MDV | PHA | 60 | INV | 20 | N | I | HCFC | 0 | 0 | 0 | 0 | 2010-04-01 | 2013-06-01 | 2019-12-01 | 2017-12-01 |  |  | 400000 | 0 | 400000 | 240637 | 60.16% | 159363 | 0 | 63745.2 | 30000 | 0 | 18047.775 | 11952.225 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Activities remaining under this component are reclamation study tour and pilot retrofit incentive program for HCFC using equipment. All other activities under UNDP component were completed at the end of 2015 Prodoc signed (actual/planned, yes/no and date):40787 Missions undertaken (actual/planned):1 TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: Contract signed First disbursement date (actual/planned): 40848Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:Delayed due to unavailability of Low GWP alternatives | AWP has been finalized and work will start. ToR prepared and under review. | 2010 |  | Investment
COM | UNEP | HCFC phase-out management plan (first tranche) | Multi-Year | ASP | MDV | PHA | 60 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-09-01 | 2019-12-01 |  | 2013-12-01 |  | 355940 | 0 | 355940 | 355940 | 100% | 0 | 0 |  | 46272 | 0 | 46272 | 0 | 0
ONG | UNDP | HCFC phase-out management plan (second tranche) | Multi-year | ASP | MDV | PHA | 69 | INV | 24 | N | I | HCFC | 0 | 0 | 0 | 0 | 2013-04-01 | 2013-08-01 | 2015-04-01 | 2017-12-01 |  |  | 20000 | 0 | 20000 | 4100 | 20.5% | 15900 | 0 | 6360 | 1500 | 0 | 307.5 | 1192.5 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): No activities undertaken during 2016. Prodoc signed (actual/planned, yes/no and date):41426 Missions undertaken (actual/planned):1 TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: Contract signed First disbursement date (actual/planned): 41426Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | AWP has already been approved. The activities will be completed by 2017 December. | 2013 |  | Investment
ONG | UNEP | HCFC phase-out management plan (second tranche) | Multi-Year | ASP | MDV | PHA | 69 | TAS | 23 | A | I |  | 0 |  | 0 |  | 2013-04-01 | 2014-11-01 | 2015-04-01 | 2017-12-01 |  |  | 173400 | 0 | 173400 | 162953.61 | 93.98% | 10446.39 | 10446.39 | 10446 | 22542 | 0 | 21183.9693 | 1358.0307 | 1358.0307 | Brief progress report (actual/planned): 15 stakeholder’s consultation workshop was held with 30 participants. 3 law and enforcement trainings completed in 2015 and two more are planned to be conducted by December 2016. 2 stake holders workshops organized to raise awareness on HCFC phase-out and energy efficiency was held in February 2016 with 25 participants. Issued letters to all government ministries, agencies, resorts regarding the ban on import of HCFC based equipment starting from 31st May 2016. Import ban flyers were distributed among all regional networks on network meeting held in Fiji. 2 workshops (2-days each) on “Good services practices in refrigeration and air-conditioning” for laamu atoll technicians was held on 9-10 December 2015. The workshop brought over 30 distinguished participants from various stakeholder sectors. Legal arrangements(actual/planned): SSFA in place First mission (actual/planned): ____ TOR completed(actual/planned): ___ First disbursement date (actual/planned): Yes, Nov 2014 All funds disbursed (yes/no): NO Any delay? (yes/no): ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): National consultation workshop took place in February to consider the introduction of flammable refrigerants and necessary measures for their introduction such as standards and certification system of technicians. One training of technicians on good practices as well as on R290 took place in February in Male. Legal arrangements(actual/planned): SSFA in place First mission (actual/planned):Feb 2017 TOR completed(actual/planned): ___ First disbursement date (actual/planned): Yes, Nov 2014 All funds disbursed (yes/no): NO Any delay? (yes/no): ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___
COM | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Multi-Year | ASP | MDV | PHA | 73 | TAS | 26 | A | I |  | 0 |  | 0 |  | 2014-11-01 | 2015-04-01 | 2015-05-01 |  | 2016-12-01 |  | 30000 | 0 | 30000 | 29773 | 99.24% | 227 | 227 | 227 | 3900 | 0 | 3870.49 | 29.51 | 29.51 | Project completed | Project completed
ONG | UNEP | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | ASP | MDV | PHA | 75 | TAS | 29 | A | I |  | 0.6 |  | 0 |  | 2015-11-01 | 2016-06-01 | 2017-12-01 | 2018-12-01 |  |  | 100660 | 0 | 100660 | 5000 | 4.967% | 95660 | 95660 | 9566 | 13086 | 0 | 650.0099 | 12435.9901 | 12435.9901 | Brief progress report (actual/planned): Detailed work plan discussed and agreed. Legal arrangements(actual/planned): SSFA signed First mission (actual/planned): Aug 2016 TOR completed(actual/planned): ___ First disbursement date (actual/planned): actual June 2016 All funds disbursed (yes/no): No Any delay? (yes/no): still finalizing the tranch 2 activities If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): In plans to start the work on certification system and developing national standards for flammable refrigerant and equipment. Kigali amendement ratification in process. Legal arrangements(actual/planned): SSFA signed First mission (actual/planned): Aug 2016 TOR completed(actual/planned): ___ First disbursement date (actual/planned): actual June 2016 All funds disbursed (yes/no): No Any delay? (yes/no): still finalizing the tranch 2 activities If Yes, reasons for delay & action plan to resolve: ___
FIN | UNEP | Development of RMP | RMP | ASP | MDV | REF | 30 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2000-04-01 |  | 2002-09-01 | 2003-09-01 | 30000 | -1849 | 28151 | 28151 | 100% | 0 | 0 |  | 3900 | -240.37 | 3659.63 | 0 | 0
ONG | UNDP | Implementation of the RMP: awareness and incentive programme | RMP-Component | ASP | MDV | REF | 38 | TAS | 05 | A | I | CFC | 2.2 | 2.2 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2005-05-01 | 2017-12-01 |  |  | 115000 | 0 | 115000 | 115000 | 100% | 0 | 0 | 0 | 14950 | 0 | 14950 | 0 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): No activities undertaken during 2016, due to no available alternate technology available for retrofitting. Prodoc signed (actual/planned, yes/no and date):42401 Missions undertaken (actual/planned):1 TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: Contract signed First disbursement date (actual/planned): 42401Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:100% safe low GWP technology was not available | AWP has already been approved. The activities will be completed by 2017 December. | 2002 |  | Non-Investment
FIN | UNEP | Implementation of the RMP: monitoring and review | Individual | ASP | MDV | REF | 38 | TAS | 06 | A | I | CFC | 0.3 | 0 | 0 | 0 | 2002-11-01 | 2003-08-01 | 2005-05-01 |  | 2005-08-01 | 2010-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0
FIN | UNEP | Implementation of the RMP: train the trainer programme for refrigeration service technicians | Individual | ASP | MDV | REF | 38 | TRA | 07 | A | I | CFC | 0.7 | 0 | 0 | 0 | 2002-11-01 | 2003-08-01 | 2005-05-01 |  | 2005-07-01 | 2008-12-01 | 35000 | -2000 | 33000 | 33000 | 100% | 0 | 0 |  | 4550 | -260 | 4290 | 0 | 0
FIN | UNEP | Implementation of the RMP: training of customs officials and the Ozone Unit staff | Individual | ASP | MDV | REF | 38 | TRA | 08 | A | I | CFC | 0.7 | 0 | 0 | 0 | 2002-11-01 | 2003-06-01 | 2005-05-01 |  | 2005-11-01 | 2011-03-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 |  | 4550 | 0 | 4550 | 0 | 0
ONG | UNDP | Preparation of a demonstration project for low-global warming potential alternatives for HCFC phase-out in refrigeration applications in fishing industry | Individual | ASP | MDV | REF | 74 | PRP | 27 | N | I | HCFC | 0 | 0 | 0 | 0 | 2015-05-01 | 2016-01-01 | 2016-05-01 | 2017-12-01 |  |  | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1050 | 0 | 1050 | 0 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): PRP for demonstration project was completed and was submitted to 76 Excom. The project for demo project was approved by MLF on May 2016 Prodoc signed (actual/planned, yes/no and date):42370 Missions undertaken (actual/planned):1 TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: Contract signed First disbursement date (actual/planned): 42370Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | Technically completed | 2015 |  | Non-Investment
ONG | UNDP | Demonstration project for HCFC-free low-global warming potential alternatives in refrigeration in fisheries sector | Individual | ASP | MDV | REF | 76 | DEM | 30 | N | I | HCFC | 0 | 0 | 0 | 0 | 2016-05-01 |  | 2018-05-01 | 2018-05-01 |  |  | 141000 | 0 | 141000 | 0 | 0% | 141000 | 0 | 56400 | 12690 | 0 | 0 | 12690 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): AWP approved. ProDoc sent to CO for approval. Work will start by May. Prodoc signed (actual/planned, yes/no and date): Missions undertaken (actual/planned):1 TOR for consultants/subcontracts completed (actual/planned): Contract/PO/MOA agreements signed: First disbursement date (actual/planned): Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | On going |  |  | Investment
FIN | UNEP | Country programme preparation | Individual | ASP | MDV | SEV | 04 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-10-01 | 1992-09-01 |  | 1993-06-01 | 1993-12-01 | 25000 | -5500 | 19500 | 19500 | 100% | 0 | 0 |  | 3250 | -715 | 2535 | 0 | 0
FIN | UNEP | Institutional strengthening for the phase-out of ODS controlled under the Montreal Protocol | Individual | ASP | MDV | SEV | 12 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-02-01 | 1997-03-01 |  | 2002-05-01 | 2005-12-01 | 41250 | 0 | 41250 | 41250 | 100% | 0 | 0 |  | 5363 | 0 | 5363 | 0 | 0 |  |  |  | 1999-12-01
FIN | UNEP | Renewal of institutional strengthening project (Phase 2) | Individual | ASP | MDV | SEV | 37 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-08-01 | 2004-08-01 |  | 2004-10-01 | 2005-12-01 | 35753 | 0 | 35753 | 35753 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | ASP | MDV | SEV | 44 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-03-01 | 2006-12-01 |  | 2005-11-01 | 2007-02-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | ASP | MDV | SEV | 50 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2008-11-01 |  | 2008-11-01 | 2009-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | ASP | MDV | SEV | 56 | INS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-02-01 | 2010-11-01 |  | 2010-11-01 | 2011-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VI) | Individual | ASP | MDV | SEV | 61 | INS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-01-01 | 2012-11-01 |  | 2012-11-01 | 2013-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VII: 12/2012-11/2014) | Individual | ASP | MDV | SEV | 67 | INS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2013-04-01 | 2014-11-01 |  | 2014-12-01 | 2015-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of the institutional strengthening project (phase VIII: 12/2014-11/2016) | Individual | ASP | MDV | SEV | 72 | INS | 25 | A | I |  | 0 |  | 0 |  | 2014-05-01 | 2015-12-01 | 2016-11-01 |  | 2016-12-01 |  | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Ban on HCFC based equipment introduced in May 2016. Import tax incentive approved. Legal arrangements(actual/planned):SSFA completed Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: completed and extension Phase IX approved by 77 Excom First disbursement date(actual/planned): ___ All funds disbursed (yes/no): ___ Any delay?(yes/no): ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___ | Project completed
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | ASP | MDV | SEV | 74 | TAS | 28 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-09-01 | 2016-05-01 | 2017-06-01 |  |  | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Brief progress report(actual/planned): ToR developed and consultant recruited. Survey conducted. Stakeholder consultations meetings held, one during the mission by UNEP in Oct 2016. Full draft of the survey report submitted for review by UNEP. Legal arrangements(actual/planned): Yes Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date(actual/planned): actual Sep 2016 All funds disbursed (yes/no): Yes Any delay?(yes/no): ___ If Yes, reasons for delay & action plan to resolve:___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___ | Brief progress report(actual/planned): Comments on the first draft sent by UNEP Feb 2017. Comments are currently being incorporated into the final draft of the survey report. Legal arrangements(actual/planned): Yes Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date(actual/planned): actual Sep 2016 All funds disbursed (yes/no): Yes Any delay?(yes/no): ___ If Yes, reasons for delay & action plan to resolve:___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___
ONG | UNEP | Extension of the institutional strengthening project (phase IX: 12/2016-11/2018) | Individual | ASP | MDV | SEV | 77 | INS | 31 | A | I |  | 0 |  | 0 |  | 2016-12-01 |  | 2018-11-01 | 2018-11-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | Newly approved project | Brief progress report (actual/planned): SSFA workplan being finalized and SSFA will be soon signed First mission for the finalization of the workplan undertaken in Feb 2017 (within the scope of NON MLF project)
FIN | IBRD | Umbrella project for the conversion of CFC-11, CFC-12 and CFC-113 into HFC, HCFC, HFE for technical aerosols at Tecnosol, Envatec and Dimmex | Individual | LAC | MEX | ARS | 41 | INV | 116 | N | I | CFC | 57.3 | 63.98 | 0 | 0 | 2003-12-01 | 2005-10-01 | 2006-12-01 |  | 2006-03-01 | 2006-03-01 | 252340 | 0 | 252340 | 252340 | 100% | 0 | 0 |  | 18925.5 | 0 | 18925.5 | 0 | 0 | Umbrella project is now completed. |  |  |  | INV | 0
FIN | UNIDO | Project preparation for a MDI project, including the development of a national transitional strategy for the sector | Individual | LAC | MEX | ARS | 52 | PRP | 134 | A | I |  | 0 | 0 |  |  | 2007-07-01 | 2007-09-01 | 2008-07-31 |  | 2008-04-01 | 2008-07-01 | 50000 | -275 | 49725 | 49724.98 | 100% | 0.02 | 0 |  | 3750 | -21 | 3729 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Phase-out of CFC consumption in the manufacture of aerosol MDIs | Individual | LAC | MEX | ARS | 53 | INV | 135 | A | I | CFC | 97 | 97 |  |  | 2007-11-01 | 2008-04-01 | 2010-01-31 |  | 2011-09-01 | 2013-10-01 | 2630503 | -6079 | 2624424 | 2624423.87 | 100% | 0.13 | 0 |  | 197288 | -456 | 196832 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of HCFC-22 and HCFC-141b in aerosol manufacturing at Silimex | Multi-Year | LAC | MEX | ARS | 63 | INV | 156 | A | I | HCFC | 11.1 | 11.1 |  |  | 2011-04-01 | 2011-07-01 | 2013-09-30 |  | 2014-12-01 | 2016-03-01 | 520916 | -22 | 520894 | 520893.65 | 100% | 0.35 | 0 |  | 39069 | -2 | 39067 | 0 | 0 | The project was financially completed and the balance was returned at the 76th ExCom. |  |  |  | INV
FIN | UNIDO | Preparation for HCFC phase-out investment activities (aerosol sector) | Individual | LAC | MEX | ARS | 72 | PRP | 169 | A | I |  | 0 | 0 |  |  | 2014-05-01 | 2014-06-01 | 2015-05-31 |  | 2014-12-01 | 2015-09-01 | 40000 | -533 | 39467 | 39466.93 | 100% | 0.07 | 0 |  | 2800 | -37 | 2763 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of ODS disposal pilot project | Individual | LAC | MEX | DES | 57 | PRP | 142 | A | I |  | 0 | 0 |  |  | 2009-04-01 | 2009-10-01 | 2010-12-31 |  | 2011-12-01 | 2012-04-01 | 50000 | -872 | 49128 | 49127.52 | 100% | 0.48 | 0 |  | 3750 | -65 | 3685 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | IBRD | Preparation for the second component of the pilot demonstration project on ODS waste management and disposal |  | LAC | MEX | DES | 58 | PRP | 143 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2010-12-01 | 2010-12-31 |  | 2012-03-01 | 2012-04-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 3750 | 0 | 3750 | 0 | 0 | Report completed and submitted as an information document to the 66th ExCom. |  |  |  | Non-INV | 0
ONG | UNIDO | Demonstration project for disposal of unwanted ODS | Individual | LAC | MEX | DES | 63 | DEM | 154 | A | I |  | 0 | 0 |  |  | 2011-04-01 | 2011-07-01 | 2013-03-31 | 2017-06-01 |  |  | 927915 | 0 | 927915 | 849468.12 | 91.55% | 78446.88 | 58789.98 | 78400 | 69594 | 0 | 63710 | 5884 | 4409 | - UNIDO finalizes selection of Contractor for the disposal of the final batch of ODS waste. Milestones achieved: Milestone 1: Yes - contract signed for the disposal of the last batch of ODS waste Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Disposal of the remaining amount for destruction took place. - Two videos were produced on project results. - UNIDO and NOU are preparing the final report, to be submitted to MLFS in the coming few months. Was there any delay during the reporting year? Yes Due to administrative and technical reasons, the destruction of the remaining batches took longer than expected. Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
ONG | France | Demonstration project for disposal of unwanted ODS | Individual | LAC | MEX | DES | 63 | DEM | 155 | A | I | CFC | 0 |  | 0 |  | 2011-04-01 | 2012-08-01 | 2013-03-01 | 2017-03-13 |  |  | 500000 | 0 | 500000 | 169972.78 | 33.99% | 330027.22 | 200898 | 329000 | 65000 | 0 | 22096.4614 | 42903.5386 | 26117 |  | - Disposal of the remaining amount for destruction took place. - Two videos were produced on project results. - UNIDO and NOU are preparing the final report, to be submitted to MLFS in the coming few months. Was there any delay during the reporting year? Yes Due to administrative and technical reasons, the destruction of the remaining batches took longer than expected. Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No
FIN | IBRD | Replacement of CFC-11 with HCFC-141b foam blowing in the manufacturing of commercial refrigeration in Refrigeración Ojeda | Individual | LAC | MEX | FOA | 05 | INV | 10 | N | I | CFC | 25 | 25 | 0 | 0 | 1991-11-01 | 1995-01-01 | 1992-11-01 |  | 1995-06-01 | 1995-09-01 | 494500 | 0 | 494500 | 494500 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | CFC-11 phase out at Refrigeración Ojeda | Individual | LAC | MEX | FOA | 05 | INV | 60 | N | I | CFC | 15.6 | 13 | 0 | 0 | 1991-11-01 | 1996-09-01 | 1996-06-01 |  | 1996-12-01 | 1996-12-01 | 390000 | 0 | 390000 | 390000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1996-12-01 | INV | 0
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Paneles | Individual | LAC | MEX | FOA | 18 | INV | 41 | A | I | CFC | 81 | 81 | 0 | 0 | 1995-11-01 | 1996-08-01 | 1996-11-01 |  | 1997-08-01 | 2000-12-01 | 100000 | -5098.2 | 94901.8 | 94902 | 100% | -0.2 | 0 | 0 | 13000 | -662.77 | 12337.26 | -0.03 | 0 | Completed in 1997. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of insulated construction panels at Galvamet, S.A. de C.V. | Individual | LAC | MEX | FOA | 18 | INV | 42 | A | D | CFC | 88.7 | 88.7 | 0 | 0 | 1995-11-01 | 1996-04-01 | 1996-11-01 |  | 1996-04-01 | 1998-12-01 | 195500 | -6004.42 | 189495.58 | 189496 | 100% | -0.42 | 0 | 0 | 25415 | -780.79 | 24634.26 | -0.05 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of insulated construction panels and doors at Multypanel | Individual | LAC | MEX | FOA | 19 | INV | 46 | A | I | CFC | 306 | 306 | 0 | 0 | 1996-05-01 | 1997-08-01 | 1997-11-01 |  | 1997-08-01 | 2001-12-01 | 428000 | -85788.58 | 342211.42 | 342211 | 100% | 0.42 | 0 | 0 | 55640 | -11152.82 | 44487.13 | 0.05 | 0 | Completed in 1997. Financially completed in 2001. |  | 1996 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (spray) - Group project (10 enterprises) | Individual | LAC | MEX | FOA | 19 | INV | 47 | A | I | CFC | 100 | 100 | 0 | 0 | 1996-05-01 | 1997-02-01 | 1997-11-01 |  | 1998-11-01 | 2001-08-01 | 507500 | -43764 | 463736 | 463736 | 100% | 0 | 0 | 0 | 65975 | -5689.32 | 60285.68 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1996 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Carmovil | Individual | LAC | MEX | FOA | 20 | INV | 48 | A | I | CFC | 14.6 | 14.6 | 0 | 0 | 1996-10-01 | 1997-09-01 | 1998-09-01 |  | 1998-11-01 | 2000-12-01 | 80500 | -1092 | 79408 | 79408 | 100% | 0 | 0 | 0 | 10465 | -141.96 | 10323.04 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Umbrella project for conversion to CFC-free technology in the manufacture of polyurethane shoe soles (seven enterprises) | Individual | LAC | MEX | FOA | 20 | INV | 49 | A | I | CFC | 95 | 95 | 0 | 0 | 1996-10-01 | 1997-11-01 | 1998-09-01 |  | 2001-08-01 | 2003-04-01 | 1201590 | -3434 | 1198156 | 1198156 | 100% | 0 | 0 | 0 | 156206.7 | -446.42 | 155760.28 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1996 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (spray) at Acsa | Individual | LAC | MEX | FOA | 22 | INV | 54 | A | I | CFC | 94.4 | 94.4 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1999-12-01 | 2001-12-01 | 597000 | -1890 | 595110 | 595110 | 100% | 0 | 0 | 0 | 77610 | -245.26 | 77364.74 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane shoe soles at Industrias Pol-Rym S.A. de C.V., (IPR) | Individual | LAC | MEX | FOA | 22 | INV | 55 | A | I | CFC | 25 | 25 | 0 | 0 | 1997-05-01 | 1998-09-01 | 1998-11-01 |  | 1998-11-01 | 2001-12-01 | 421500 | -4909 | 416591 | 416591 | 100% | 0 | 0 | 0 | 54795 | -638.13 | 54156.87 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (spray) at Tecnopolimeros | Individual | LAC | MEX | FOA | 22 | INV | 56 | A | I | CFC | 54.4 | 54.4 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1999-06-01 |  | 1999-12-01 | 2002-11-01 | 359000 | -1642 | 357358 | 357358 | 100% | 0 | 0 | 0 | 46670 | -213.41 | 46456.59 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1997 | 1999-06-01 | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at Termopuertos | Individual | LAC | MEX | FOA | 22 | INV | 57 | A | D | CFC | 10 | 10 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1998-07-01 | 2000-12-01 | 78300 | -2557 | 75743 | 75743 | 100% | 0 | 0 | 0 | 10179 | -332.41 | 9846.59 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technolog in the manufacture of rigid foam at Valsa Panel | Individual | LAC | MEX | FOA | 23 | INV | 66 | A | D | CFC | 24 | 24 | 0 | 0 | 1997-11-01 | 1998-07-01 | 1999-12-01 |  | 1998-07-01 | 2000-12-01 | 92000 | -312 | 91688 | 91688 | 100% | 0 | 0 | 0 | 11960 | -40.56 | 11919.44 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (spray) at group project Pumex | Individual | LAC | MEX | FOA | 23 | INV | 69 | A | I | CFC | 167.7 | 167.7 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 2000-08-01 | 2001-12-01 | 1133881 | -20532 | 1113349 | 1113349 | 100% | 0 | 0 | 0 | 147404.5 | -2669 | 144735.5 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of integral skin foam at Air Design | Individual | LAC | MEX | FOA | 23 | INV | 71 | A | I | CFC | 5 | 5 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 1999-12-01 | 2001-12-01 | 80500 | -1178 | 79322 | 79322 | 100% | 0 | 0 | 0 | 10465 | -153.4 | 10311.5984 | 0.0016 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid foam (spray) and integral skin foam at Con Espuma | Individual | LAC | MEX | FOA | 23 | INV | 72 | A | I | CFC | 11.4 | 11.4 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 1999-12-01 | 2001-08-01 | 96100 | -2230 | 93870 | 93870 | 100% | 0 | 0 | 0 | 12493 | -289.9 | 12203.1 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane shoe soles at Group Project (Orca) | Individual | LAC | MEX | FOA | 23 | INV | 73 | A | I | CFC | 190 | 190 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 2001-12-01 | 2003-11-01 | 1471500 | -154071 | 1317429 | 1317429 | 100% | 0 | 0 | 0 | 191295 | -20029.23 | 171265.77 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Project preparation for 5 projects in the foam sector | Individual | LAC | MEX | FOA | 24 | PRP | 79 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1998 |  | Investment
FIN | UNDP | Conversion to HCFC-141b technology in the manufacture of rigid foam for refrigeration systems at Refrigeración Rodríguez | Individual | LAC | MEX | FOA | 25 | INV | 82 | A | I | CFC | 34.9 | 34.9 | 0 | 0 | 1998-07-01 | 1999-11-01 | 2000-08-01 |  | 2000-08-01 | 2001-12-01 | 132650 | -31006 | 101644 | 101644 | 100% | 0 | 0 | 0 | 17244.5 | -4031 | 13213.5 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Conversion to water-based technology in the manufacture of integral skin foam at Moldecor, S.A. de C.V. | Individual | LAC | MEX | FOA | 25 | INV | 84 | A | I | CFC | 9 | 9 | 0 | 0 | 1998-07-01 | 1999-09-01 | 2000-08-01 |  | 2000-04-01 | 2001-12-01 | 86500 | -845 | 85655 | 85655 | 100% | 0 | 0 | 0 | 11245 | -109.97 | 11135.0253 | 0.0047 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam (spray) at Group Project Valcom (Uriel, Limas, Tecknipol, Anzaldua, and Negrete) | Individual | LAC | MEX | FOA | 26 | INV | 87 | A | I | CFC | 44.3 | 44.3 | 0 | 0 | 1998-11-01 | 1999-12-01 | 2000-12-01 |  | 2000-08-01 | 2002-11-01 | 314961 | -3630 | 311331 | 311331 | 100% | 0 | 0 | 0 | 40944.93 | -472 | 40472.93 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Preparation of three projects in the foam sector | Individual | LAC | MEX | FOA | 27 | PRP | 89 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-07-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNIDO | Preparation of investment projects in the rigid foam sector | Individual | LAC | MEX | FOA | 30 | PRP | 92 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-11-01 | 2001-04-01 |  | 2001-10-01 | 2003-03-01 | 30000 | -838 | 29162 | 29162.18 | 100% | -0.18 | 0 |  | 3900 | -115 | 3785 | 0 | 0 | FIN
FIN | UNDP | Preparation of a project in the rigid foam subsector | Individual | LAC | MEX | FOA | 30 | PRP | 94 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2004-02-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b or water-blown technology in rigid polyurethane foam (spray) and to water based formulations in integral skin foam at Comsisa | Individual | LAC | MEX | FOA | 31 | INV | 98 | A | I | CFC | 68.7 | 68.7 | 0 | 0 | 2000-07-01 | 2001-01-01 | 2003-08-01 |  | 2003-10-01 | 2004-01-01 | 424050 | 0 | 424050 | 424050 | 100% | 0 | 0 | 0 | 55126.5 | 0 | 55126.5 | 0 | 0 | Completed in 2003. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Foam phaseout sector strategy | Individual | LAC | MEX | FOA | 31 | TAS | 96 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-07-01 | 2000-08-01 | 2002-01-01 |  | 2001-12-01 | 2004-02-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 2000 |  | Non-Investment
FIN | UNDP | Foam sector ODS phaseout plan (first trnache) | Individual | LAC | MEX | FOA | 35 | INV | 103 | N | I | CFC | 145 | 145 | 0 | 0 | 2001-12-01 | 2003-02-01 | 2003-07-01 |  | 2004-11-01 | 2009-08-01 | 833150 | 0 | 833150 | 833150 | 100% | 0 | 0 | 0 | 101646.5 | 0 | 101646.5 | 0 | 0 | Completed in 2004.Financially completed in 2009. |  | 2000 |  | Investment
FIN | UNDP | Foam sector ODS phase-out plan (second tranche) | Individual | LAC | MEX | FOA | 42 | INV | 117 | N | D | CFC | 192 | 192 | 0 | 0 | 2004-04-01 | 2005-02-01 | 2006-04-01 |  | 2007-12-01 | 2009-08-01 | 1109120 | -78998 | 1030122 | 1030122 | 100% | 0 | 0 | 0 | 83184 | -5924.85 | 77259.15 | 0 | 0 | Completed in 2007.Financially completed in 2009. |  | 2004 |  | Investment
FIN | UNDP | Pilot project for validation of methyl formate in microcellular polyurethane applications (phase I) | Individual | LAC | MEX | FOA | 56 | DEM | 141 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-05-01 | 2009-06-01 |  | 2010-11-01 | 2012-12-01 | 291500 | -1418.38 | 290081.62 | 290082 | 100% | -0.38 | 0 | 0 | 21862 | -106.38 | 21755.6524 | -0.032399 | 0 | Financially completed in 2012. |  | 2008 | 2011-01-01 | Non-Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (foam sector plan) | Individual | LAC | MEX | FOA | 58 | PRP | 144 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-07-01 | 2009-12-01 | 2010-07-01 |  | 2012-04-01 | 2013-06-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 | 0 | 11250 | 0 | 11250 | 0 | 0 | Financially completed in 2013. | Completed in 2012. No activities in 2013. | 2009 |  | Investment
COM | UNDP | Conversion from HCFC-141b in the manufacture of polyurethane rigid insulation foam for domestic refrigerators at Mabe Mexico | Multi-year | LAC | MEX | FOA | 59 | INV | 148 | N | I | HCFC | 55.8 | 55.8 | 0 | 0 | 2009-11-01 | 2010-03-01 | 2013-08-01 |  | 2014-12-01 |  | 2428987 | 0 | 2428987 | 2382002.27 | 98.07% | 46984.73 | 0 | 39937.0205 | 182174 | 0 | 178650.1457 | 3523.8543 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2014. |  | 2009 |  | Investment
FIN | UNIDO | Preparation of a demonstration project in the methyl bromide sector | Individual | LAC | MEX | FUM | 22 | PRP | 58 | A | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-07-01 | 1997-07-01 |  | 1998-05-01 | 2001-07-01 | 20000 | -1561 | 18439 | 18439 | 100% | 0 | 0 |  | 2600 | -207 | 2393 | 0 | 0 | FIN
FIN | UNDP | Project preparation for 2 methyl bromide (flowers and crop storage) alternative demonstration projects | Individual | LAC | MEX | FUM | 24 | PRP | 80 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-11-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1998 |  | Investment
FIN | UNIDO | Demonstration project - Alternatives to the use of methyl bromide in the cultivation of tomatoes, strawberries, tobacco, melons and cut flowers | Individual | LAC | MEX | FUM | 25 | DEM | 81 | A | I | MBR | 0 | 0 |  |  | 1998-07-01 | 1998-12-01 | 2001-08-01 |  | 2004-12-01 | 2006-05-01 | 790350 | -13975 | 776375 | 776375.15 | 100% | -0.15 | 0 |  | 102746 | -1977 | 100769 | 0 | 0 | FIN
FIN | UNDP | Alternatives to methyl bromide for structural fumigation in Mexico | Individual | LAC | MEX | FUM | 26 | DEM | 86 | A | I | MeBr | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-12-01 | 2000-12-01 |  | 2010-10-01 | 2013-04-01 | 498300 | -87984.02 | 410315.98 | 410316 | 100% | -0.02 | 0 | 0 | 64779 | -11437.92 | 53341.08 | 0 | 0 | Financially completed in 2013. |  | 1998 |  | Investment
FIN | UNDP | Project preparation in the storage fumigant sector | Individual | LAC | MEX | FUM | 36 | PRP | 105 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2003-09-01 | 2005-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNIDO | Preparation of a phase-out plan in the fumigant sector (methyl bromide) | Individual | LAC | MEX | FUM | 39 | PRP | 113 | A | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-07-01 | 2004-04-01 |  | 2005-01-01 | 2005-05-01 | 50000 | 0 | 50000 | 49999.86 | 100% | 0.14 | 0 |  | 3750 | -3 | 3747 | 0 | 0 | FIN
FIN | Spain | Technical assistance to comply with 2005 phase-out of 20% of methyl bromide | Individual | LAC | MEX | FUM | 42 | TAS | 118 | A | I | MBR | 107.2 | 107.2 | 0 |  | 2004-04-01 | 2005-10-01 | 2006-10-01 |  | 2008-12-01 | 2010-03-01 | 707965 | -24181 | 683784 | 683784 | 100% | 0 | 0 | 0 | 87876 | -2659.76 | 85216.24 | 0 | 0 | Financial completion in Mar 2010. Refund was reported to 61st ExCom, Jul 2010. FIN. |  |  |  | Investment
FIN | UNIDO | Technical assistance to comply with 2005 phase-out of 20% of methyl bromide | Individual | LAC | MEX | FUM | 42 | TAS | 121 | A | I | MBR | 36.9 | 132.9 |  |  | 2004-04-01 | 2004-11-01 | 2006-10-01 |  | 2006-12-01 | 2008-06-01 | 207035 | -1912 | 205123 | 205122.67 | 100% | 0.33 | 0 |  | 18633 | -172 | 18461 | 0 | 0 | FIN |  |  |  | INV
FIN | Canada | Technical assistance to comply with 2005 phase-out of 20% of methyl bromide | Individual | LAC | MEX | FUM | 42 | TAS | 122 | A | I | MBR | 18.2 | 18.2 | 0 |  | 2004-04-01 | 2006-09-01 | 2006-10-01 |  | 2009-03-01 | 2009-04-01 | 190000 | 0 | 190000 | 190000 | 100% | 0 |  | 0 | 24700 | 0 | 24700 | 0 |  | This project was implemented by UNDP on behalf of Canada. Project was nearly completed by end of 2008, with 10 companies successfully completing alternative fumigations techniques. Remaining activities for 2009 included preparing a report focused on lessons learned from the project and finalizing financial reporting. These were completed by April 2009. |  | 2004 | 2008-06-01 | Investment
FIN | UNIDO | Project preparation in the fumigant sector | Individual | LAC | MEX | FUM | 51 | PRP | 131 | A | I |  | 0 | 0 |  |  | 2007-03-01 | 2007-09-01 | 2008-03-01 |  | 2008-08-01 | 2009-05-01 | 60000 | -509 | 59491 | 59490.51 | 100% | 0.49 | 0 |  | 4500 | -38 | 4462 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | National methyl bromide phase-out plan (first tranche) | Multi-Year | LAC | MEX | FUM | 54 | INV | 136 | A | I | MBR | 130 | 130 |  |  | 2008-04-01 | 2008-06-01 | 2014-03-31 |  | 2012-07-01 | 2012-12-01 | 2000000 | -39 | 1999961 | 1999961.17 | 100% | -0.17 | 0 |  | 150000 | -3 | 149997 | 0 | 0 | FIN |  |  |  | INV
FIN | Italy | National methyl bromide phase-out plan (first tranche) | Multi-Year | LAC | MEX | FUM | 54 | INV | 137 | A | I | MBR | 70 | 70 | 0 |  | 2008-04-01 | 2009-07-01 | 2014-03-01 |  | 2012-11-01 | 2012-11-01 | 1000000 | -6004.48 | 993995.52 | 993996 | 100% | -0.48 | 0 | 0 | 120000 | -720.54 | 119279 | 0.46 | 0 | Project completed in Nov 2012. Financial completion in Nov 2012. |  | 2008 |  | Investment
FIN | Canada | National methyl bromide phase-out plan (first tranche) | Multi-Year | LAC | MEX | FUM | 54 | INV | 138 | A | I | MBR | 20 | 20 | 0 |  | 2008-04-01 | 2009-09-01 | 2014-03-01 |  | 2012-03-01 | 2012-04-01 | 500000 | 0 | 500000 | 500000 | 100% | 0 |  | 0 | 58527 | 0 | 58527 | 0 |  | Project was completed in March 2012 and financially closed in April 2012. |  | 2008 |  | Investment
TRF | Canada | National methyl bromide phase-out plan (second tranche) | Multi-Year | LAC | MEX | FUM | 60 | INV | 149 | A | I | MBR | 0 |  | 0 |  | 2010-04-01 |  | 2011-04-01 |  |  | 2012-04-01 | 500000 | -500000 | 0 | 0 |  | 0 |  | 0 | 58527 | -58527 | 0 | 0 |  | Project was transferred to UNIDO at 63rd ExCom meeting. No expenditures will thus be made by Canada. |  | 2010 |  | Investment
FIN | UNIDO | National methyl bromide phase-out plan (second tranche) | Multi-Year | LAC | MEX | FUM | 60 | INV | 150 | A | I | MBR | 250 | 250 |  |  | 2010-04-01 | 2010-05-01 | 2012-04-30 |  | 2012-12-01 | 2014-07-01 | 2000000 | -712 | 1999288 | 1999287.57 | 100% | 0.43 | 0 |  | 150000 | -53 | 149947 | 0 | 0 | FIN
FIN | Spain | National methyl bromide phase-out plan (second tranche) | Multi-Year | LAC | MEX | FUM | 60 | INV | 151 | A | I | MBR | 50 | 50 | 0 |  | 2010-04-01 | 2012-09-01 | 2012-04-01 |  | 2012-11-01 | 2012-11-01 | 800000 | -32 | 799968 | 799968 | 100% | 0 | 0 | 0 | 93000 | -4 | 92996.28 | -0.28 | 0 | Project completed in Nov 2012. Financial completion in Nov 2012. |  |  |  | Investment
COM | UNIDO | Methyl bromide phase-out plan (Transfer from Canada) | Multi-Year | LAC | MEX | FUM | 63 | INV | 153 | A | I | MBR | 50 | 50 |  |  | 2011-04-01 | 2011-07-01 | 2012-04-30 |  | 2015-12-01 |  | 500000 | 0 | 500000 | 499066.65 | 99.81% | 933.35 | 0 | 1 | 37500 | 0 | 37430 | 70 | 0 | The project was operationally completed. |  |  |  | INV
COM | Spain | National methyl bromide phase-out plan (third tranche) | Multi-Year | LAC | MEX | FUM | 66 | INV | 161 | A | I | MBR | 80 |  | 0 |  | 2012-04-01 | 2014-07-01 | 2013-04-01 |  | 2016-07-01 |  | 800000 | 0 | 800000 | 796035.1 | 99.5% | 3964.9 | 0 | 0 | 93000 | 0 | 92539.0804 | 460.9196 | 0 | - The final official event with authorities and farmers that took place in Colima and the project was completyed in July 2016. | Financial completion is in the process. |  |  | Investment
COM | UNIDO | National methyl bromide phase-out plan (third tranche) | Multi-Year | LAC | MEX | FUM | 66 | INV | 162 | A | I | MBR | 120 | 120 |  |  | 2012-04-01 | 2012-07-01 | 2013-04-30 |  | 2015-12-01 |  | 1200000 | 0 | 1200000 | 1198880.58 | 99.91% | 1119.42 | 0 | 1 | 90000 | 0 | 89916 | 84 | 0 | The project was operationally completed. |  |  |  | INV
COM | UNIDO | National methyl bromide phase-out plan (fourth tranche) | Multi-Year | LAC | MEX | FUM | 69 | INV | 166 | A | I | MBR | 0 | 0 |  |  | 2013-04-01 | 2013-08-01 | 2014-04-30 |  | 2015-12-01 |  | 422379 | 0 | 422379 | 422264.07 | 99.97% | 114.93 | 0 | 1 | 31678 | 0 | 31670 | 8 | 0 | The project was operationally completed. |  |  |  | INV
FIN | UNDP | Preparatory study on halons, inventory, and proposals for revisions of existing standards | Individual | LAC | MEX | HAL | 06 | TAS | 14 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-01 | 1994-04-01 |  | 1995-09-01 | 1998-12-01 | 25000 | 2223 | 27223 | 27223 | 100% | 0 | 0 | 0 | 3250 | 288.99 | 3538.99 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1992 |  | Non-Investment
FIN | UNDP | Project preparation for a halon sector phase out programme | Individual | LAC | MEX | HAL | 24 | PRP | 76 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1999-12-01 | 1998-12-01 |  | 2001-11-01 | 2001-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Project preparation in the recycling halon sector | Individual | LAC | MEX | HAL | 33 | PRP | 101 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | National halon management and banking programme | Individual | LAC | MEX | HAL | 35 | TAS | 104 | A | I | Halon | 230 | 230 | 0 | 0 | 2001-12-01 | 2002-08-01 | 2005-01-01 |  | 2007-12-01 | 2011-07-01 | 500000 | -55841.6 | 444158.4 | 444158 | 100% | 0.4 | 0 | 0 | 65000 | -7259.41 | 57740.54 | 0.05 | 0 | Completed in 2007. |  | 2001 |  | Investment
FIN | IBRD | Safety programme in aerosol plant and recycling training and demonstration project in MAC | Individual | LAC | MEX | MUS | 04 | TRA | 04 | N | I | CFC | 0 | 36 | 0 | 0 | 1991-06-01 | 1996-02-01 | 1992-11-01 |  | 1996-04-01 | 1996-04-01 | 180000 | -126208 | 53792 | 53792 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1995-05-01 | Non-INV | 0
FIN | IBRD | Implementation of projects identified in the country programme | Individual | LAC | MEX | MUS | 05 | INV | 05 | N | I |  | 0 | 0 | 0 | 0 | 1991-11-01 |  | 1996-11-01 |  | 1996-12-01 | 1997-12-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1996-12-01 | INV | 0
FIN | UNIDO | Preparation for HCFC phase-out investment activities (aerosol and solvent sectors) | Individual | LAC | MEX | MUS | 58 | PRP | 146 | A | I |  | 0 | 0 |  |  | 2009-07-01 | 2009-11-01 | 2010-07-31 |  | 2013-12-01 | 2013-12-01 | 100000 | -538 | 99462 | 99462.43 | 100% | -0.43 | 0 |  | 7500 | -40 | 7460 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of a process agent project | Individual | LAC | MEX | PAG | 48 | PRP | 129 | A | I |  | 0 | 0 |  |  | 2006-04-01 | 2006-10-01 | 2007-04-01 |  | 2007-12-01 | 2008-06-01 | 30000 | -94 | 29906 | 29906.35 | 100% | -0.35 | 0 |  | 2250 | -7 | 2243 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Umbrella project for terminal phase-out of CTC | Individual | LAC | MEX | PAG | 52 | INV | 133 | A | I | CTC | 87.3 | 87.3 |  |  | 2007-07-01 | 2007-12-01 | 2008-07-31 |  | 2009-12-01 | 2012-08-01 | 1518094 | -9212 | 1508882 | 1508881.83 | 100% | 0.17 | 0 |  | 113857 | -691 | 113166 | 0 | 0 | FIN |  |  | 2010-01-01 | INV
FIN | UNIDO | National CFC phase-out plan (first tranche) | Multi-Year | LAC | MEX | PHA | 42 | INV | 120 | A | I | CFC | 0 | 0 |  |  | 2004-04-01 | 2004-06-01 | 2005-04-01 |  | 2007-12-01 | 2009-12-01 | 3517000 | 0 | 3517000 | 3517000.03 | 100% | -0.03 | 0 |  | 263775 | 0 | 263775 | 0 | 0 | FIN |  |  | 2006-12-01 | INV
FIN | UNIDO | National CFC phase-out plan: 2nd tranche | Multi-Year | LAC | MEX | PHA | 45 | INV | 123 | A | I | CFC | 100 | 100 |  |  | 2005-04-01 | 2006-05-01 | 2007-04-01 |  | 2011-12-01 | 2014-07-01 | 4478000 | -200076 | 4277924 | 4277923.93 | 100% | 0.07 | 0 |  | 335850 | -15006 | 320844 | 0 | 0 | FIN |  |  |  | INV
FIN | IBRD | National CFC phase-out plan: 2005 work programme | Multiyear | LAC | MEX | PHA | 45 | INV | 124 | N | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-02-01 | 2007-04-01 |  | 2006-02-01 | 2006-02-01 | 500000 | 0 | 500000 | 500000 | 100% | 0 | 0 |  | 37500 | 0 | 37500 | 0 | 0 | Funds were disbursed to FIDE. These funds were added to the rotating fund created with the first tranche. By the end of 2006, 19 chillers had been replaced (the target was 10), and as of Dec 06, collection rates on loans were 100%. |  |  |  | INV | 0
FIN | UNIDO | National CFC phase-out plan: 2006 work programme | Multi-Year | LAC | MEX | PHA | 50 | INV | 130 | A | I | CFC | 1435 | 1435 |  |  | 2006-11-01 | 2007-05-01 | 2007-11-01 |  | 2008-07-01 | 2010-12-01 | 299500 | -7411 | 292089 | 292088.84 | 100% | 0.16 | 0 |  | 22463 | -556 | 21907 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | LAC | MEX | PHA | 55 | PRP | 139 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 |  | 2011-12-01 | 2012-10-01 | 104250 | -291 | 103959 | 103959 | 100% | 0 | 0 |  | 7819 | -22 | 7797 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | MEX | PHA | 55 | PRP | 140 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2009-11-01 | 2012-06-01 | 69500 | -6719.29 | 62780.71 | 62781 | 100% | -0.29 | 0 | 0 | 5212.5 | -503.95 | 4708.5749 | -0.02495 | 0 | Financially completed in 2012. |  | 2008 |  | Investment
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (umbrella project for conversion from HCFC-141b to cyclopentane insulation foam blowing technology at three refrigeration appliances manufacturing enterprises: FERSA, Frigopanel and Metalfrio) | Multi-Year | LAC | MEX | PHA | 64 | INV | 157 | A | I | HCFC | 23 | 9.2 |  |  | 2011-07-01 | 2011-12-01 | 2014-01-31 | 2017-10-01 |  |  | 2046110 | 0 | 2046110 | 1134035.38 | 55.42% | 912074.62 | 840068.97 | 500000 | 153458 | 0 | 85053 | 68405 | 63005 | - Metalfrío: the person responsible for the conversion project was replaced, which delayed the actions required for TUV certification. During UNIDO's expert mission in July, the company was not available to meet and thus, NOU visited the company 2 weeks later and tried to push the enterprise to finalize pending tasks in order to get TUV certification ASAP. Metalfrío promised to send an action plan in due course, but it was never submitted. - Ojeda: Equipment was shipped mid February, arrived at Mexican port mid March and reached the beneficiary in May. Installation was planned for the last quarter 2016, but it did not take place. Company personnel participated in a hands-on training at suppliers premises end July. - Fersa: There have been frequent exchanges between the beneficiary and the supplier on all technical details and the final layout was agreed in July. Fersa management is taking the project very seriously and these technical discussions were extremely useful for the success of the conversion. In addition, a hands-on training was organized at suppliers' premises mid July. Equipment was shipped end July, which reached Mexican port end August. Supplier's team leader visited both enterprises in the 2nd week of September. Installation started in November and was almost completed in December. Milestones achieved: Conversion completed at Metalfrio: Yes, December 2014; TUV certificate issued for Metalfrio: No; Bidding completed for Fersa: Yes, December 2013; Contract signed for Fersa: Yes, July 2015; Bidding completed for Ojeda: Yes, December 2013; Contract signed for Ojeda: Yes, February 2015; Equipment delivered and installed for Ojeda: Delivered May 2016; Equipment delivered and installed for Fersa: Equipment delivered in September, installed in December; Commissioning and trial runs completed at Fersa: No; Commissioning and trial runs completed at Ojeda: No; TUV certificate issued for Fersa: No; TUV certificate issued for Ojeda: No; Activities planned but not implemented, reasons and strategy: TUV certification at Metalfrío (lack of actions from the beneficiary) and installation/commissioning at Ojeda. Actions towards next goals: Continuous follow-up by UNIDO and the NOU with Metalfrio and Ojeda. Was there any delay during the reporting year? Yes If yes, reasons and action plan: For Metalfrio and Ojeda the delay was caused by the supplier as well by the beneficiary. Any recurring problem? Yes, Ojeda and Metalfrío do not fulfill their commitments. Any impact on project completion date: Yes, above mentioned problems have seriously delayed. If yes, implications: If further delay occur, companies may face shortage of HCFC-141b supply. Any action required by Executive Committee? No | Metalfrío and Ojeda: Fersa: installation was finalized in January 2017 and training of technicians and maintenance people was also organized in January. TUV visit together with the supplier and UNIDO took place early February. Fersa has finalized in March all corrective measures identified by TUV and thus, TUV certificate is expected to be issued during April. Milestones achieved: TUV certificate issued for Metalfrio: No; Equipment delivered and installed for Ojeda: Delivered May 2016; Equipment delivered and installed for Fersa: Equipment delivered in September, installed in December; Commissioning and trial runs completed at Fersa: Yes; Commissioning and trial runs completed at Ojeda: No; TUV certificate issued for Fersa: expected in April; TUV certificate issued for Ojeda: No; Activities planned but not implemented, reasons and strategy: TUV certification at Metalfrío (lack of actions from the beneficiary) and installation/commissioning at Ojeda (lack of actions from beneficiary). Actions towards next goals: Continuous follow-up by UNIDO and the NOU with Metalfrio and Ojeda. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Metalfrio and Ojeda had delays due to changes in the company and lack of progress by them. Deadline of mid 2017 was given to the companies to finish the corrective measures for TUV certification at Metalfrío and to do the installation at Ojeda ASAP. Any recurring problem? Yes, Ojeda and Metalfrío do not fulfill their commitments. Any impact on project completion date: Yes, above mentioned problems have seriously delayed the project completion., If yes, implications: If further delay occur, companies may face shortage of HCFC-141b supply. Any action required by Executive Committee? No |  |  | INV
FIN | UNDP | HCFC phase-out management plan (foam sector plan for systems houses and local customers) (stage I, first tranche) | Multi-Year | LAC | MEX | PHA | 64 | INV | 159 | N | I | HCFC | 66.8 | 66.8 | 0 | 0 | 2011-07-01 | 2011-08-01 | 2013-07-01 |  | 2013-07-01 | 2013-12-01 | 2502526 | 0 | 2502526 | 2502526 | 100% | 0 | 0 | 0 | 187689 | 0 | 187689 | 0 | 0 | Financially completed in 2013. |  | 2011 |  | Investment
FIN | UNIDO | HCFC phase-out management plan (stage I, first tranche) (phase-out of HCFC-141b as a cleaning agent in refrigeration servicing) | Multi-Year | LAC | MEX | PHA | 64 | INV | 160 | A | I | HCFC | 4.3 | 4.3 |  |  | 2011-07-01 | 2012-06-01 | 2012-07-31 |  | 2013-03-01 | 2014-07-01 | 100000 | -823 | 99177 | 99177.38 | 100% | -0.38 | 0 |  | 7500 | -62 | 7438 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | HCFC phase-out management plan (stage I, first tranche) (legislation customs training and monitoring) | Multi-Year | LAC | MEX | PHA | 64 | TAS | 158 | A | I | HCFC | 1.1 | 1.1 |  |  | 2011-07-01 | 2011-12-01 | 2012-07-31 |  | 2013-03-01 | 2015-09-01 | 125500 | -267 | 125233 | 125232.58 | 100% | 0.42 | 0 |  | 9413 | -20 | 9392 | 1 | 0 | FIN |  |  |  | INV
COM | UNIDO | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing, technical assistance and monitoring) | Multi-Year | LAC | MEX | PHA | 68 | INV | 164 | A | I | HCFC | 11.4 | 11.4 |  |  | 2012-12-01 | 2013-06-01 | 2013-12-31 |  | 2016-12-01 |  | 695011 | 0 | 695011 | 682124.94 | 98.15% | 12886.06 | 4852.81 | 4000 | 52126 | 0 | 51159 | 967 | 363.9608 | - The final number of centers participating in the training are 11 and each of them are committed to undertake 6 trainings. 9 centers have successfully completed the training, one has finished 3 courses and the status at 1 center is not clear. New motors for the flushing units were distributed to all centers in February and a video tutorial was prepared by an expert on the proper mounting and operation of the flushing unit. Bidding was organized for the purchase of large number of equipment and service tools, evaluation was completed in April, contract signed in June and equipment was delivered September. Project was operationally completed in December 2016. Milestones achieved: PAD issued: Yes Work Plan Agreed with NOU: Yes Training equipment purchased and delivered: Yes, in January 2014 Flushing units replaced: Yes. Equipment delivered: Yes. Training of trainers completed: Yes. Activities planned but not implemented, reasons and strategy: No Actions towards next goals: N/A Was there any delay during the reporting year? No. Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | The tranche was successfully completed, financial completion is being initiated. |  |  | INV
FIN | UNDP | HCFC phase-out management plan (stage I, second tranche) (foam sector plan for systems houses and local customers) | Multi-Year | LAC | MEX | PHA | 68 | INV | 165 | N | I | HCFC | 101.5 | 101.5 | 0 | 0 | 2012-12-01 | 2013-02-01 | 2014-12-01 |  | 2015-12-01 | 2016-12-01 | 3800000 | 0 | 3800000 | 3800000 | 100% | 0 | 0 | 0 | 285000 | 0 | 285000 | 0 | 0 | Financially completed in 2016. | Since 2014, reconversion work at downstream user (DSU) level has been progressing with the National SHs. For the international SHs, Polioles/BASF had signed MOA with the project and have started trials with end-users; DOW has also agreed with the terms of MOA and document is in process of signature (in the meanwhile, their clients alread started to receive technical assistance preparation for trials) and Bayer is reviewing the terms of the MOA to engage in the reconversion process. | 2012 |  | Investment
ONG | UNIDO | HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing, technical assistance and monitoring) | Multi-Year | LAC | MEX | PHA | 71 | INV | 167 | A | I | HCFC | 10.5 | 0 |  |  | 2013-12-01 | 2014-04-01 | 2014-12-31 | 2017-05-01 |  |  | 578341 | 0 | 578341 | 540966.64 | 93.54% | 37374.36 | 0 | 30000 | 43376 | 0 | 40572 | 2804 | 0 | - The final number of centers participating in the training are 11 and each of them are committed to undertake 6 trainings. 10 centers have successfully completed the training and one center has done 3. New motors for the flushing units were distributed to all centers in February and a video tutorial was prepared by an expert on the proper mounting and operation of the flushing unit. Bidding was organized for the purchase of large number of equipment and service tools, evaluation was completed in April, contract signed in June and delivery of equipment is expected September. Milestones achieved: PAD issued: Yes Work Plan Agreed with NOU: Yes TOR for equipment purchase agreed, Yes, July 2015 Equipment contract signed: July 2016 Equipment and tools delivered: Yes, in September. Activities planned but not implemented, reasons and strategy: Activities were implemented as planned. Actions towards next goals: Complete training at all centers and monitoring; Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | The last center has completed 2 more courses and the last course will be completed before May. The remaining activities under this tranche are related to monitoring of all HPMP activities. The tranche will be completed in May 2017. |  |  | INV
ONG | UNDP | HCFC phase-out management plan (stage I, third tranche) (foam sector plan for systems houses and local customers) | Multi-Year | LAC | MEX | PHA | 71 | INV | 168 | N | I | HCFC | 101.5 | 60.2 | 0 | 0 | 2013-12-01 | 2014-06-01 | 2016-06-01 | 2017-06-01 |  |  | 3800000 | 0 | 3800000 | 2291798.63 | 60.31% | 1508201.37 | 9587 | 603280.548 | 285000 | 0 | 171884.8973 | 113115.1028 | 719.025 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Through trials, training, grant agreements and signature of contracts, 11 of the 12 system houses have been successfully converted and are currently HCFC 141b free. One international System House did not accept to participate, however, UNDP reached its customers, offered direct support. Customer is currently HCFC free. All equipment has been distributed. Prodoc signed (actual/planned, yes/no and date):PRODOC signed prior to 2015. Missions undertaken (actual/planned):3 of 3 TOR for consultants/subcontracts completed (actual/planned): 2 of 2 Contract/PO/MOA agreements signed: 1 of 1 First disbursement date (actual/planned): Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | Even though last customer to receive support has fully converted, corresponding support has not yet been completed. Full payment will be finalized by June 2017. Moreover, one Project still has one payment pending. | 2013 |  | Investment
COM | UNIDO | HCFC phase-out management plan (stage I, fourth tranche) (refrigeration servicing, technical assistance and monitoring) | Multi-Year | LAC | MEX | PHA | 73 | INV | 170 | A | I | HCFC | 1.8 | 1.8 |  |  | 2014-11-01 | 2015-02-01 | 2016-12-31 |  | 2016-12-01 |  | 120000 | 0 | 120000 | 115295.51 | 96.08% | 4704.49 | 2035.43 | 2000 | 9000 | 0 | 8647 | 353 | 153 | Tranche completed. - Consultants for the HPMP monitoring unit have continued to monitor all HPMP activities. Milestones achieved: PAD issued: Yes Work Plan agreed with the NOU: Yes Consultants recruited: Yes Verification audit of the 2015 consumption undertaken: Yes Was there any delay during the reporting year? No Any recurring problem? No Any action required by Executive Committee? No | Financial completion is being initiated. |  |  | INV
ONG | Italy | HCFC phase-out management plan (stage II, first tranche) (reclamation of HCFC refrigerants) |  | LAC | MEX | PHA | 73 | INV | 171 | A | I | HCFC | 0 |  | 0 |  | 2014-11-01 |  | 2016-11-01 | 2018-06-01 |  |  | 458191 | 0 | 458191 | 28171 | 6.148% | 430020 | 0 | 200000 | 59565 | 0 | 3662 | 55903 | 0 | - During 2016 there has been regular follow-up by the bilateral implementing agency with the executing agency to monitor the progress of this activity and to coordinate these actions with other ongoing initiatives of the HPMP. - Based on the approved project document and based on local consultations with the NOU and the industry, draft technical specifications were prepared during August, however, bidding was not initiated in 2016 due to administrative reasons. That's why, the level of disbursement is low. Was there any delay during the reporting year? Yes Any impact on project completion date? Yes Any recurring problem? No Any action required by Executive Committee? No | - The specifications and the final TOR have been agreed upon in January 2017 and bidding started in February. - Bidding was finished end of March and the evaluation of the offers was finished mid-April. The contract for some items is expected to be issued by end May. Additional bidding will be organized in the second quarter of the year. - Substantial disbursement is expected during 2017, once the equipment is delivered to the project sites. Was there any delay during the reporting year? No Any impact on project completion date? No Any recurring problem? No Any action required by Executive Committee? No | 2014 |  | Investment
ONG | UNIDO | HCFC phase-out management plan (stage II, first tranche) (phase-out of HCFC-22 and HCFC-141b in solvent) | Multi-Year | LAC | MEX | PHA | 73 | INV | 173 | A | I | HCFC | 39.6 | 0 |  |  | 2014-11-01 | 2015-04-01 | 2018-11-30 | 2018-11-01 |  |  | 1731403 | 0 | 1731403 | 744769.02 | 43.02% | 986633.98 | 953231.3 | 600000 | 121198 | 0 | 52134 | 69064 | 66726 | - Bidding for Marcat was completed and contract was issued in April 2016. Equipment was received at Marcat on 15 August and installation was completed end 2016. TOR for lab test was agreed upon end April 2016, but the bidding was not successful. Milestones achieved: PAD issued: Yes Work Plan agreed with NOU: Yes , in February 2015 Technical expert recruited: Yes, in March 2015 TOR for the conversion at Marcat agreed: Yes, in October 2015 Bidding started: Yes, in November 2015 Contract issued: Yes, in April 2016 Conversion completed: Yes, in December 2016 Sub-contracts for IOC payment signed: Yes, with all enterprises Phase-out of HCFCs verified: Partially Contract for lab-test signed: No Actions towards next goals: Continue verifying the enterprises and releasing payments based on verified progress and the approved alternatives. Undertake lab tests for the alternatives. Was there any delay during the reporting year? No Any recurring problem? No Any action required by Executive Committee? No | - Verification of the successful conversion and Marcat was done in March 2017. A new attempt for the lab test will be made in April 2017. Milestones achieved: TOR for the conversion at Marcat agreed: Yes, in October 2015 Bidding started: Yes, in November 2015 Contract issued: Yes, in April 2016 Conversion completed: Yes, in December 2016 Sub-contracts for IOC payment signed: Yes, with all enterprises Phase-out of HCFCs verified: Partially Contract for lab-test signed: No Actions towards next goals: Continue verifying the enterprises and releasing payments based on verified progress and the approved alternatives. Undertake lab tests for the alternatives. Was there any delay during the reporting year? No Any recurring problem? No Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage II, first tranche) (phase-out in refrigeration servicing sector) | Multi-Year | LAC | MEX | PHA | 73 | INV | 174 | A | I | HCFC | 19.8 | 0 |  |  | 2014-11-01 | 2016-04-01 | 2016-11-30 | 2018-04-01 |  |  | 673009 | 0 | 673009 | 522238.45 | 77.6% | 150770.55 | 0 | 40000 | 47111 | 0 | 36557 | 10554 | 0 | Bidding was organized for the purchase of large number of equipment and service tools, evaluation was completed in April, contract signed in June and equipment was delivered in September. Milestones achieved: PAD issued: Yes Work Plan agreed with the NOU: Yes Stakeholder consultation organized: Yes TOR for equipment purchased agreed upon: Yes, July 2015 Bidding completed and contract issued: Yes Equipment delivered: Yes, September 2016 Activities planned but not implemented, reasons and strategy: N/A Actions towards next goals: Selection of 4 more training centers Was there any delay during the reporting year? No. Any recurring problem? No Any action required by Executive Committee? No | In the second quarter of 2017, agreement will be made with the NOU on the selection of the additional training centers and related activities (purchase of tools and initiation of training activities). Milestones achieved: PAD issued: Yes Work Plan agreed with the NOU: Yes Stakeholder consultation organized: Yes TOR for equipment purchased agreed upon: Yes, July 2015 Bidding completed and contract issued: Yes Equipment delivered: Yes, September 2016 Additional 4 training centers selected: No Activities planned but not implemented, reasons and strategy: N/A Actions towards next goals: Selection of 4 more training centers Was there any delay during the reporting year? No. Any recurring problem? No Any action required by Executive Committee? No |  |  | INV
ONG | Germany | HCFC phase-out management plan (stage II, first tranche) (HC demonstration and training) | Multi-Year | LAC | MEX | PHA | 74 | INV | 172 | A | I | HCFC | 4 |  | 0 |  | 2015-05-01 | 2016-01-01 | 2016-12-01 | 2017-12-01 |  |  | 325000 | 0 | 325000 | 177217 | 54.53% | 147783 | 59321 | 147783 | 40750 | 0 | 15800 | 24950 | 24950 | Project activities delayed: Contracts with international consultancy established, local contracts with individual consultants established, review of national standards and certification scheme, planning and development of a training concept in close cooperation with national experts, work on training material and adaptation to local conditions (ongoing), selection process of local site for training completed, selection of suitable sites for the AC incentive programme ongoing, procurement process for training equipment carried out, preparation of ToT | procurement process for ACs started, ToT planned for first semester of 2017
ONG | UNIDO | HCFC phase-out management plan (stage I, fifth tranche) (refrigeration servicing, technical assistance and monitoring) | Multi-Year | LAC | MEX | PHA | 75 | INV | 177 | A | I | HCFC | 1.4 | 0 |  |  | 2015-11-01 | 2016-01-01 | 2018-12-01 | 2018-12-01 |  |  | 226317 | 0 | 226317 | 105186.3 | 46.48% | 121130.7 | 38658.57 | 30000 | 16974 | 0 | 0 | 16974 | 2899.3927 | - After the successful completion of the training activities at the training centers in previous tranches, 10 centers have already applied for the continuation of the training activities for additional 10 courses each. Contracts for these centers were issued. The PMU is continuing the monitoring activities and the 2016 consumption and production will be verified in 2017. Milestones achieved: PAD issued: Yes Work Plan Agreed with NOU: Yes Contracts signed with training centers: Yes Training courses completed: No. 2016 consumption/production verified: No. Activities planned but not implemented, reasons and strategy: N/A. Actions towards next goals: Follow-up with the other centers Was there any delay during the reporting year? No. Any recurring problem? No Any action required by Executive Committee? No | - The centers are continuing with the training during 2017. The PMU is continuing the monitoring activities and the 2016 consumption and production will be verified in 2017. Milestones achieved: PAD issued: Yes Work Plan Agreed with NOU: Yes Contracts signed with training centers: Yes Training courses completed: Partially yes (33 courses in 6 centers). 2016 consumption/production verified: No. Activities planned but not implemented, reasons and strategy: N/A. Actions towards next goals: Follow-up with the training centers and continue monitoring HPMP activities Was there any delay during the reporting year? No. Any recurring problem? No Any action required by Executive Committee? No |  |  | INV
ONG | UNDP | HCFC phase-out management plan (stage I, fifth tranche) (foam sector plan for systems houses and local customers) | Multi-year | LAC | MEX | PHA | 75 | INV | 178 | N | I | HCFC | 30 | 0 | 0 | 0 | 2015-11-01 |  | 2017-12-01 | 2017-12-01 |  |  | 1122503 | 0 | 1122503 | 0 | 0% | 1122503 | 0 | 449001.2 | 84188 | 0 | 0 | 84188 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Through trials, training, grant agreements and signature of contracts, 11 of the 12 system houses have been successfully converted and are currently HCFC 141b free. One international System House did not accept to participate, however, UNDP reached its customers, offered direct support. Customer is currently HCFC free. All equipment has been distributed. Prodoc signed (actual/planned, yes/no and date):PRODOC signed prior to 2015. Missions undertaken (actual/planned):3 of 3 TOR for consultants/subcontracts completed (actual/planned): 2 of 2 Contract/PO/MOA agreements signed: 1 of 1 First disbursement date (actual/planned): Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | Even though last customer to receive support has fully converted, corresponding support has not yet been completed. Full payment will be finalized by June 2017. Moreover, one Project still has one payment pending. | 2015 |  | Investment
ONG | Germany | HCFC phase-out management plan (stage II, second tranche) (HC demonstration and training) |  | LAC | MEX | PHA | 77 | INV | 179 | A | I | HCFC | 4 |  | 0 |  | 2016-12-01 |  | 2018-12-01 | Dec-18 |  |  | 325000 | 0 | 325000 | 0 | 0% | 325000 | 0 | 78000 | 40750 | 0 | 0 | 40750 |  | Approval in 12/2016
ONG | Spain | HCFC phase-out management plan (stage II, second tranche) (cleaning agent phase-out in refrigeration servicing sector) |  | LAC | MEX | PHA | 77 | INV | 180 | N | I |  | 2.3 |  | 0 |  | 2016-12-01 |  | 2019-12-01 | 2019-12-01 |  |  | 76991 | 0 | 76991 | 0 | 0% | 76991 | 0 | 20000 | 8831 | 0 | 0 | 8831 | 0 | - The tranche was approved at the 77th ExCom Meeting in December 2017 after which the Government of Spain and UNIDO started to work on a Trust Fund Agreement. Milestones achieved: - Trust Fund Agreement signed/funds received/PAD issued: No - Work Plan Agreed with NOU: No Activities planned but not implemented, reasons and strategy: N/A. Actions towards next goals: Sign TFA and agree on work plan. Was there any delay during the reporting year? No. Any recurring problem? No Any action required by Executive Committee? No | - The details of the Trust Fund Agreement were worked out and the TFA was signed with UNIDO and funds were transferred to UNIDO. Milestones achieved: - Trust Fund Agreement signed/funds received/PAD issued: Yes - Work Plan Agreed with NOU: No - Additional milestones to be defined after agreement on the work plan. Activities planned but not implemented, reasons and strategy: N/A. Actions towards next goals: Agree with the NOU on work plan. Was there any delay during the reporting year? No. Any recurring problem? No Any action required by Executive Committee? No
ONG | UNIDO | HCFC phase-out management plan (stage II, second tranche) (phase-out of HCFC-22 and HCFC-141b in solvent) | Multi-Year | LAC | MEX | PHA | 77 | INV | 181 | A | I | HCFC | 19.5 | 0 |  |  | 2016-11-01 |  | 2018-12-31 | 2017-12-01 |  |  | 851229 | 0 | 851229 | 0 | 0% | 851229 | 0 | 500000 | 59586 | 0 | 0 | 59586 | 0 | The tranche was approved at the 77th ExCom Meeting in December 2017 after which the PAD was issued and the Government and the beneficiary company was informed about the approval. This project component is co-financed by the Spanish bilateral contribution. Milestones achieved: PAD issued: Yes, December 2016 Work Plan Agreed with NOU: No Tests with the new alternatives started: No. IOC contract signed with the beneficiary: No. Tests with the new alternatives completed: No. Large-scale production with the new alternative started: No HCFC-phase-out and production with the approved alternative verified: No IOC paid: No Activities planned but not implemented, reasons and strategy: N/A. Actions towards next goals: Agree on work plan and prepare IOC contract. Was there any delay during the reporting year? No. Any recurring problem? No Any action required by Executive Committee? No | The beneficiary has submitted the work plan indicating that tests with the HFO alternative are planned to be undertaken between January and April and large scale production would start in April. The subject work plan has been agreed with the NOU and the beneficiary. Milestones achieved: PAD issued: Yes Work Plan Agreed with NOU: Yes Tests with the new alternatives started: Yes, January 2017 IOC contract signed with the beneficiary: Yes, March 2017 Tests with the new alternatives completed: No. Large-scale production with the new alternative started: No HCFC-phase-out and production with the approved alternative verified: No IOC paid: No Activities planned but not implemented, reasons and strategy: N/A. Actions towards next goals: Finalize tests and start large-scale production with HFOs. Was there any delay during the reporting year? No. Any recurring problem? No Any action required by Executive Committee? No
ONG | Spain | HCFC phase-out management plan (stage II, second tranche) (phase-out of HCFC-22 and HCFC-141b in solvent) |  | LAC | MEX | PHA | 77 | INV | 182 | N | I |  | 0 |  | 0 |  | 2016-12-01 |  | 2018-12-01 | 2018-12-01 |  |  | 700000 | 0 | 700000 | 0 | 0% | 700000 | 0 | 500000 | 80291 | 0 | 0 | 80291 | 0 | - The tranche was approved at the 77th ExCom Meeting in December 2017 after which the Government of Spain and UNIDO started to work on a Trust Fund Agreement. Milestones achieved: - Trust Fund Agreement signed/funds received/PAD issued: No - Work Plan Agreed with NOU: No - Tests with the new alternatives started: No. - IOC contract signed with the beneficiary: No. - Tests with the new alternatives completed: No. - Large-scale production with the new alternative started: No - HCFC-phase-out and production with the approved alternative verified: No - IOC paid: No Activities planned but not implemented, reasons and strategy: N/A. Actions towards next goals: Sign TFA and agree on work plan and prepare IOC contract. Was there any delay during the reporting year? No. Any recurring problem? No Any action required by Executive Committee? No | - The beneficiary has submitted the work plan indicating that tests with the HFO alternative are planned to be undertaken between January and April and large scale production would start in April. The subject work plan has been agreed with the NOU and the beneficiary. Milestones achieved: - Trust Fund Agreement signed/funds received/PAD issued: Yes, February 2017 - Work Plan Agreed with NOU: Yes Tests with the new alternatives started: Yes, January 2017 - IOC contract signed with the beneficiary: Yes, March 2017 - Tests with the new alternatives completed: No. - Large-scale production with the new alternative started: No - HCFC-phase-out and production with the approved alternative verified: No - IOC paid: No Activities planned but not implemented, reasons and strategy: N/A. Actions towards next goals: Finalize tests and start large-scale production with HFOs. Was there any delay during the reporting year? No. Any recurring problem? No Any action required by Executive Committee? No
ONG | UNIDO | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | Multi-Year | LAC | MEX | PHA | 77 | INV | 183 | A | I |  | 0 | 0 |  |  | 2016-11-01 |  | 2019-12-31 | 2019-12-01 |  |  | 314280 | 0 | 314280 | 0 | 0% | 314280 | 0 | 40000 | 22000 | 0 | 0 | 22000 | 0 | The tranche was approved at the 77th ExCom Meeting in December 2017 after which the PAD was issued and the Government was informed about the approval. This project component is co-financed by the Spanish bilateral contribution. Milestones achieved: PAD issued: Yes, December 2016 Work Plan Agreed with NOU: No TOR for equipment purchase agreed upon: No Train the trainers course organized: No Manuals developed and printed: No Activities planned but not implemented, reasons and strategy: N/A. Actions towards next goals: Agree on work plan. Was there any delay during the reporting year? No. Any recurring problem? No Any action required by Executive Committee? No | In the second quarter of 2017, agreement will be made with the NOU on the work plan and the activities will be planned accordingly. Milestones achieved: PAD issued: Yes, December 2016 Work Plan Agreed with NOU: No TOR for equipment purchase agreed upon: No Train the trainers course organized: No Manuals developed and printed: No Activities planned but not implemented, reasons and strategy: N/A. Actions towards next goals: Agree on work plan. Was there any delay during the reporting year? No. Any recurring problem? No Any action required by Executive Committee? No
ONG | Spain | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) |  | LAC | MEX | PHA | 77 | INV | 185 | N | I |  | 0 |  | 0 |  | 2016-12-01 |  | 2019-12-01 | 2019-12-01 |  |  | 280000 | 0 | 280000 | 0 | 0% | 280000 | 0 | 40000 | 32116 | 0 | 0 | 32116 | 0 | - The tranche was approved at the 77th ExCom Meeting in December 2017 after which the Government of Spain and UNIDO started to work on a Trust Fund Agreement. Milestones achieved: - Trust Fund Agreement signed/funds received/PAD issued: No - Work Plan Agreed with NOU: No - TOR for equipment purchase agreed upon: No - Train the trainers course organized: No - Manuals developed and printed: No Activities planned but not implemented, reasons and strategy: N/A. Actions towards next goals: Sign TFA and agree on work plan. Was there any delay during the reporting year? No. Any recurring problem? No Any action required by Executive Committee? No | -The details of the Trust Fund Agreement were worked out and the TFA was signed with UNIDO and funds were transferred to UNIDO. Milestones achieved: - Trust Fund Agreement signed/funds received/PAD issued: Yes - Work Plan Agreed with NOU: No - TOR for equipment purchase agreed upon: No - Train the trainers course organized: No - Manuals developed and printed: No Activities planned but not implemented, reasons and strategy: N/A. Actions towards next goals: Agree with the NOU on work plan. Was there any delay during the reporting year? No. Any recurring problem? No Any action required by Executive Committee? No
ONG | UNEP | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) | Multi-year | LAC | MEX | PHA | 77 | TAS | 184 | A | I |  | 0 |  | 0 |  | 2016-12-01 |  | 2018-12-01 | 2018-12-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 0 | 4000 | 5200 | 0 | 0 | 5200 | 0 | Newly approved project | Brief progress report: Government has asked for UNEP direct administration of these funds. Legal arrangements (actual/planned): N/A. First mission (actual/planned): Expected to April 2017/No specific date established in the project document. TOR completed (actual/planned): Expected to May 2017/No specific date established in the project document. First disbursement date (actual/planned): Expected to June 2017/May 2017 All funds disbursed? (yes/no): No. Any delay? (yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date? N/A. Any ongoing problems? (yes/no): N/A. If Yes, is any action required by ExCom? N/A
FIN | UNIDO | Closure of CFC production facilities of the company Quimobasicos | Individual | LAC | MEX | PRO | 38 | PRP | 112 | A | I |  | 0 | 0 |  |  | 2002-11-01 | 2003-03-01 | 2003-12-01 |  | 2003-06-01 | 2004-04-01 | 38000 | -286 | 37714 | 37713.62 | 100% | 0.38 | 0 |  | 4940 | -45 | 4895 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Sector plan for phasing out CFC-11 and CFC-12 production sector (first tranche) | Multi-Year | LAC | MEX | PRO | 40 | INV | 115 | A | I | CFC | 0 | 0 |  |  | 2003-07-01 | 2003-11-01 | 2004-03-01 |  | 2005-06-01 | 2006-12-01 | 5300000 | 0 | 5300000 | 5300000 | 100% | 0 | 0 |  | 397500 | 0 | 397500 | 0 | 0 | FIN
FIN | UNIDO | Sector plan for phasing out CFC-11 and CFC-12 production sector (second tranche) | Multi-Year | LAC | MEX | PRO | 42 | INV | 119 | A | I | CFC | 0 | 0 |  |  | 2004-04-01 | 2004-05-01 | 2005-04-01 |  | 2005-06-01 | 2006-12-01 | 10700000 | 0 | 10700000 | 10700000.01 | 100% | -0.01 | 0 |  | 802500 | 0 | 802500 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Sector plan for phasing out CFC -11 and CFC -12 production sector: third tranche | Multi-Year | LAC | MEX | PRO | 45 | INV | 126 | A | I | CFC | 0 | 0 | 5616 | 5616 | 2005-04-01 | 2005-06-01 | 2006-12-01 |  | 2006-12-01 | 2009-05-01 | 4000000 | -563 | 3999437 | 3999437.41 | 100% | -0.41 | 0 |  | 300000 | -42 | 299958 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Sector plan for phasing out CFC -11 and CFC -12 production sector: fourth tranche | Multi-Year | LAC | MEX | PRO | 47 | INV | 128 | A | I | CFC | 0 | 0 | 6739 | 6739 | 2005-11-01 | 2006-01-01 | 2009-12-01 |  | 2009-12-01 | 2011-12-01 | 11850000 | -139 | 11849861 | 11849861.21 | 100% | -0.21 | 0 |  | 888750 | -10 | 888740 | 0 | 0 | FIN |  |  |  | INV
FIN | IBRD | Demonstration programme in CFC recovery and recycling of the Instituto Mexicano del Seguro Social (IMSS) refrigeration equipment | Individual | LAC | MEX | REF | 05 | DEM | 06 | N | I | CFC | 15 | 15 | 0 | 0 | 1991-11-01 | 1996-12-01 | 1992-11-01 |  | 1996-12-01 | 1996-12-01 | 499918 | 0 | 499918 | 499918 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1996-12-01 | INV | 0
FIN | IBRD | Replacement of CFC-12 with HFC-134a refrigerant in the manufacturing of commercial refrigeration in Refrigeración Ojeda | Individual | LAC | MEX | REF | 05 | INV | 09 | N | I | CFC | 13 | 13 | 0 | 0 | 1991-11-01 | 1995-08-01 | 1992-11-01 |  | 1995-12-01 | 1995-12-01 | 211543 | 0 | 211543 | 211543 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  |  | INV | 0
FIN | IBRD | ODS phase out at Gigante 1 | Individual | LAC | MEX | REF | 05 | INV | 61 | N | I | CFC | 38 | 5 | 0 | 0 | 1991-11-01 | 1996-08-01 | 1996-06-01 |  | 1997-09-01 | 1997-09-01 | 496380 | 0 | 496380 | 496380 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1997-06-01 | INV | 0
FIN | IBRD | ODS phase out at Aurrera 1 | Individual | LAC | MEX | REF | 05 | INV | 62 | N | I | CFC | 44 | 22.2 | 0 | 0 | 1991-11-01 | 1995-04-01 | 1997-01-01 |  | 1998-10-01 | 1998-10-01 | 500000 | 0 | 500000 | 500000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1997-01-01 | INV | 0
FIN | IBRD | ODS phase out at Gigante 2 | Individual | LAC | MEX | REF | 05 | INV | 63 | N | I | CFC | 18 | 0 | 0 | 0 | 1991-11-01 | 1996-09-01 | 1997-06-01 |  | 1998-10-01 | 1998-10-01 | 278070 | 0 | 278070 | 278070 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1997-06-01 | INV | 0
FIN | IBRD | ODS phase out at Chedraui stores | Individual | LAC | MEX | REF | 05 | INV | 64 | N | I | CFC | 15 | 15 | 0 | 0 | 1991-11-01 | 1996-08-01 | 1996-06-01 |  | 1996-08-01 | 1996-08-01 | 228120 | 0 | 228120 | 228120 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1997-03-01 | INV | 0
FIN | IBRD | ODS phase out at Aurrera 2 | Individual | LAC | MEX | REF | 05 | INV | 65 | N | I | CFC | 22 | 11.8 | 0 | 0 | 1991-11-01 | 1995-04-01 | 1997-01-01 |  | 1998-10-01 | 1998-10-01 | 275000 | 0 | 275000 | 275000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1997-01-01 | INV | 0
FIN | IBRD | CFC recovery and recycling of refrigeration equipment in Monterrey City (Climas Jiménez) | Individual | LAC | MEX | REF | 05 | TAS | 08 | N | I | CFC | 4 | 0.3 | 0 | 0 | 1991-11-01 | 1995-10-01 | 1992-11-01 |  | 1994-06-01 | 1995-12-01 | 29328 | 0 | 29328 | 29328 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  |  | INV | 0
FIN | IBRD | CFC recovery and recycling programme through Quimobasicos, S.A. | Individual | LAC | MEX | REF | 05 | TAS | 13 | N | I | CFC | 140 | 260 | 0 | 0 | 1991-11-01 | 1994-10-01 | 1992-11-01 |  | 1994-07-01 | 1994-12-01 | 222540 | 0 | 222540 | 222540 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The annual rate of ODS phaseout has been determined and has exceeded phaseout expectations, resulting in a phase out of 260 tons of CFC phaseout. Project completed. |  |  |  | INV | 0
CLO | IBRD | Training of Quimobasicos personnel in the use of CFC recovery and recycling equipment | Individual | LAC | MEX | REF | 05 | TRA | 07 | N | I |  | 0 | 0 | 0 | 0 | 1991-11-01 |  | 1992-11-01 |  |  | 1996-12-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project cancelled. |  |  | 1996-12-01 | Non-INV | 0
FIN | USA | Chiller hands-on training |  | LAC | MEX | REF | 08 | TRA | 19 | A | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1993-10-01 |  | 1993-10-01 | 1993-10-01 | 81000 | 259000 | 340000 | 340000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Adjustment of US $259,000 credited against 1993 contributions (11th Meeting).
FIN | USA | Demonstration project in MAC |  | LAC | MEX | REF | 13 | DEM | 27 | A | I | CFC | 25 |  | 0 |  | 1994-07-01 |  | 1995-07-01 |  | 1995-07-01 | 1995-07-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | USA | Pilot sectoral study and action plan in commercial refrigeration |  | LAC | MEX | REF | 13 | TAS | 26 | A | I |  | 0 |  | 0 |  | 1994-07-01 |  | 1995-07-01 |  | 1995-07-01 | 1996-06-01 | 410000 | -139742 | 270258 | 270258 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | USA | Cancun chiller workshop |  | LAC | MEX | REF | 13 | TRA | 25 | A | I |  | 0 |  | 0 |  | 1994-07-01 |  | 1995-07-01 |  | 1995-07-01 | 1995-07-01 | 9000 | 0 | 9000 | 9000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | UNDP | Elimination of CFC in the manufacture of domestic refrigerators at Ensambladora de Refrigeradores (Enresa, Mabe Group) | Individual | LAC | MEX | REF | 15 | INV | 30 | A | I | CFC | 47 | 47 | 0 | 0 | 1994-12-01 | 1995-12-01 | 1995-12-01 |  | 1997-09-01 | 2000-12-01 | 867033 | -51480.82 | 815552.18 | 815552 | 100% | 0.18 | 0 | 0 | 112714.3 | -6692.51 | 106021.77 | 0.02 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC in the manufacture of domestic refrigerators at Industrias Astral (Mabe Group) | Individual | LAC | MEX | REF | 15 | INV | 31 | A | I | CFC | 344 | 344 | 0 | 0 | 1994-12-01 | 1995-12-01 | 1995-12-01 |  | 1997-09-01 | 2000-12-01 | 2439932 | -80899.32 | 2359032.68 | 2359033 | 100% | -0.32 | 0 | 0 | 317191.2 | -10516.91 | 306674.33 | -0.04 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Conversion of CFC-12 domestic refrigerator compressors to HFC-134a at (Comasa, Mabe Group) | Individual | LAC | MEX | REF | 15 | INV | 32 | A | D | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1995-12-01 |  | 1995-11-01 | 1998-12-01 | 1188724 | -152860 | 1035864 | 1035864 | 100% | 0 | 0 | 0 | 154534.1 | -19872 | 134662.1 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1994 |  | Investment
CLO | UNDP | Conversion of CFC-12 domestic refrigerator compressors to HFC-134a at Fabricacion de Compresores S.A. (Facosa, Vitro Group) | Individual | LAC | MEX | REF | 15 | INV | 33 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1996-01-01 | 1996-06-01 |  |  | 1996-05-01 | 584000 | -581001 | 2999 | 2999 | 100% | 0 | 0 | 0 | 75920 | -75530.13 | 389.87 | 0 | 0 | Canceled in 1996. Financially completed in 1996. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC in the manufacture of domestic refrigerators at Supermatic, S.A. (Vitro Group) | Individual | LAC | MEX | REF | 15 | INV | 34 | A | I | CFC | 366 | 366 | 0 | 0 | 1994-12-01 | 1996-03-01 | 1996-06-01 |  | 1997-04-01 | 2000-12-01 | 2017517 | -5120 | 2012397 | 2012397 | 100% | 0 | 0 | 0 | 262277.2 | -665.6 | 261611.6 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC in the manufacture of domestic refrigerators at Estufas y Refrigeradores Nacionales S.A. (Erna, Vitro Group) | Individual | LAC | MEX | REF | 15 | INV | 35 | A | I | CFC | 49 | 49 | 0 | 0 | 1994-12-01 | 1996-02-01 | 1996-06-01 |  | 1997-09-01 | 2000-12-01 | 1038309 | -49630 | 988679 | 988679 | 100% | 0 | 0 | 0 | 134980.2 | -6451.9 | 128528.3 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Recovery of CFC-12 servicing of domestic refrigeration at Vitromatic Comercial y Servicios Integrados | RMP-Component | LAC | MEX | REF | 18 | TAS | 43 | N | I | CFC | 76 | 76 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1997-10-01 | 2002-12-01 | 352610 | -47579 | 305031 | 305031 | 100% | 0 | 0 | 0 | 45839.3 | -6185.27 | 39654.03 | 0 | 0 | Completed in 1997. Financially completed in 2002. |  | 1995 |  | Investment
FIN | UNIDO | Phasing out of CFCs at Criotec S.A. | Individual | LAC | MEX | REF | 23 | INV | 67 | A | R | CFC | 16 | 16 |  |  | 1997-11-01 | 1998-09-01 | 1998-10-01 |  | 1998-12-01 | 1999-05-01 | 240794 | 0 | 240794 | 240794 | 100% | 0 | 0 |  | 31303 | 0 | 31303 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs at Torrey S.A. | Individual | LAC | MEX | REF | 23 | INV | 68 | A | I | CFC | 15.1 | 15.1 |  |  | 1997-11-01 | 1998-06-01 | 1999-06-01 |  | 1999-12-01 | 2002-09-01 | 228165 | -4430 | 223735 | 223734.8 | 100% | 0.2 | 0 |  | 29661 | -622 | 29039 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs at Nieto S.A. | Individual | LAC | MEX | REF | 23 | INV | 70 | A | R | CFC | 24.6 | 24.6 |  |  | 1997-11-01 | 1998-06-01 | 1998-10-01 |  | 1998-12-01 | 1999-05-01 | 353976 | 0 | 353976 | 353976 | 100% | 0 | 0 |  | 46017 | 0 | 46017 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs at Vendo S.A. | Individual | LAC | MEX | REF | 23 | INV | 74 | A | R | CFC | 16.5 | 16.5 |  |  | 1997-11-01 | 1999-03-01 | 1998-10-01 |  | 1998-12-01 | 1999-07-01 | 248524 | 0 | 248524 | 248524 | 100% | 0 | 0 |  | 32308 | 0 | 32308 | 0 | 0 | FIN
FIN | UNIDO | Preparation of an investment project for phasing out ODS at several small enterprises in the commercial refrigeration | Individual | LAC | MEX | REF | 23 | PRP | 75 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-06-01 | 1998-06-01 |  | 1999-11-01 | 2001-03-01 | 20000 | -49 | 19951 | 19951 | 100% | 0 | 0 |  | 2600 | -11 | 2589 | 0 | 0 | FIN
FIN | IBRD | Manufacture of complete heat exchanger systems for air conditioning equipment that use HFC-134a at Climas de Mexico | Individual | LAC | MEX | REF | 24 | INV | 78 | N | I | CFC | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-09-01 | 1999-10-01 |  | 2000-05-01 | 2000-05-01 | 2359812 | 0 | 2359812 | 2359812 | 100% | 0 | 0 |  | 306775.56 | 0 | 306775.56 | 0 | 0 | Project completed. Indirect phaseout of 110.5 MT. |  |  |  | INV | 0
FIN | IBRD | Project preparation in the commercial refrigeration (end users) conversion projects |  | LAC | MEX | REF | 24 | PRP | 77 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1999-03-31 | 1998-12-01 |  | 1999-12-01 | 1999-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNIDO | Phasing out of CFC-11 and CFC-12 with HCFC-141b and HFC 134a at Plasticos Tecnicos Mexicanos (PTM) in the manufacture of commercial refrigeration equipment | Individual | LAC | MEX | REF | 25 | INV | 85 | A | I | CFC | 50.6 | 50.6 |  |  | 1998-07-01 | 1998-11-01 | 2000-01-01 |  | 1999-12-01 | 2002-09-01 | 398439 | 0 | 398439 | 398438.59 | 100% | 0.41 | 0 |  | 51797 | -1 | 51796 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the commercial refrigeration sector | Individual | LAC | MEX | REF | 27 | PRP | 88 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 2000-06-01 | 1999-12-01 |  | 2001-10-01 | 2002-12-01 | 15000 | -2159 | 12841 | 12840.95 | 100% | 0.05 | 0 |  | 1950 | -283 | 1667 | 0 | 0 | FIN
FIN | UK | Chiller concessional lending pilot project | Individual | LAC | MEX | REF | 28 | INV | 95 | N | I | CFC | 5 | 7.8 | 0 |  | 1999-07-01 | 2001-02-22 | 2004-02-01 |  | 2004-03-01 |  | 565000 | 0 | 565000 | 565000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | Phase I is completed and accomplished its objectives improving expected results: Twelve chillers were financed instead of the ten expected, with an additional two chillers financed from accumulated funds. 7.8 ODP tons were eliminated instead of 5 tons as expected. Disbursements have been made on schedule with 100% disbursement achieved in August 2002. 100% of building owners that participated in the program have made their monthly repayment on time. Energy savings were 36% higher than proposed. The project will be completed in March 2004.
FIN | UNIDO | Phasing out CFC-11 with cyclopentane and CFC-12 with HFC-134a in the manufacturing plant of commercial refrigerators of Metaplus S.A. de C.V. | Individual | LAC | MEX | REF | 30 | INV | 90 | A | I | CFC | 20.1 | 20.1 |  |  | 2000-03-01 | 2000-09-01 | 2002-04-01 |  | 2002-12-01 | 2004-04-01 | 303094 | -1405 | 301689 | 301689.18 | 100% | -0.18 | 0 |  | 39402 | -245 | 39157 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 with HCFC-141b and CFC-12 with HFC-134a in the manufacturing plant of commercial refrigerators at Refrigeracion Duran S.A. de C.V. | Individual | LAC | MEX | REF | 30 | INV | 91 | A | I | CFC | 15.1 | 15.1 |  |  | 2000-03-01 | 2000-09-01 | 2001-10-01 |  | 2002-07-01 | 2003-10-01 | 112985 | 0 | 112985 | 112984.94 | 100% | 0.06 | 0 |  | 14688 | -3 | 14685 | 0 | 0 | FIN
FIN | IBRD | Preparation of projects in the commercial refrigeration sector |  | LAC | MEX | REF | 30 | PRP | 93 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2001-12-01 | 2001-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNIDO | Strategy for the preparation of an RMP | RMP | LAC | MEX | REF | 31 | TAS | 99 | A | I | CFC | 0 | 0 |  |  | 2000-07-01 | 2000-10-01 | 2002-05-01 |  | 2004-06-01 | 2004-12-01 | 100000 | -294 | 99706 | 99705.68 | 100% | 0.32 | 0 |  | 13000 | -59 | 12941 | 0 | 0 | FIN |  |  | 2003-12-01 | NON-INV
FIN | UNIDO | Preparation of two projects in the commercial refrigeration sector | Individual | LAC | MEX | REF | 33 | PRP | 100 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-06-01 | 2002-04-01 |  | 2004-04-01 | 2004-12-01 | 50000 | 0 | 50000 | 49999.71 | 100% | 0.29 | 0 |  | 6500 | -3 | 6497 | 0 | 0 | FIN |  |  |  | INV
FIN | IBRD | Conversion of CFC-12 to HFC-134a technology in the production of MAC systems at Airtemp | Individual | LAC | MEX | REF | 34 | INV | 102 | N | I | CFC | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2003-01-01 |  | 2001-11-30 | 2002-03-01 | 1651430 | 0 | 1651430 | 1651430 | 100% | 0 | 0 |  | 191657.3 | 0 | 191657.3 | 0 | 0 | Project successfully completed both physically and financially and all funding disbursed. PCR is under preparation and expected to be submitted in early 2003. Planned and indirect phaseout should be 60 tons on the basis of 1.1 kg installed per unit plus 2 kg of additional service charges (adding up to 3.1 kg per unit). |  |  |  | INV | 0
FIN | IBRD | Project preparation in the MAC sector |  | LAC | MEX | REF | 36 | PRP | 106 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-04-01 | 2003-07-01 | 25000 | -20000 | 5000 | 5000 | 100% | 0 | 0 |  | 3250 | -2600 | 650 | 0 | 0 | Project preparation commenced, however, upon further inspection at the enterprise, enterprise was determined ineligible. |  |  |  | Non-INV | 0
FIN | UNIDO | Preparation of a sectoral phase-out plan in refrigeration | Individual | LAC | MEX | REF | 36 | PRP | 107 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-11-01 | 2003-07-01 |  | 2004-04-01 | 2005-05-01 | 30000 | 0 | 30000 | 30000.19 | 100% | -0.19 | 0 |  | 3900 | -1 | 3899 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation for HCFC phase-out investment activities (refrigeration manufacturing sector) | Individual | LAC | MEX | REF | 58 | PRP | 145 | A | I |  | 0 | 0 |  |  | 2009-07-01 | 2010-06-01 | 2010-07-31 |  | 2013-12-01 | 2014-04-01 | 150000 | -490 | 149510 | 149509.63 | 100% | 0.37 | 0 |  | 11250 | -37 | 11213 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | IBRD | Country programme preparation | Individual | LAC | MEX | SEV | 04 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 36061 | 26194 | 62255 | 62255 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1991) |  | LAC | MEX | SEV | 04 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 68164 | 35178 | 103342 | 103342 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Preparation of terms of reference for investment projects identified in the country programme | Individual | LAC | MEX | SEV | 04 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-07-01 | 1993-12-01 |  | 1995-06-01 | 1997-12-01 | 50000 | 2277 | 52277 | 52277 | 100% | 0 | 0 | 0 | 6500 | 296.01 | 6796.01 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1991 |  | Investment
FIN | IBRD | Preparation of investment projects (1992) |  | LAC | MEX | SEV | 06 | PRP | 15 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 292076 | -223980 | 68096 | 68096 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Initially we reported expenditure of $60,082 and expenditure of $8,014 for country program. However, that was due to a coding mistake and the expenditure has been adjusted to $68,096 and entry for country program removed. |  |  |  | Non-INV | 0
FIN | USA | Institutional strengthening |  | LAC | MEX | SEV | 07 | INS | 16 | A | I |  | 0 |  | 0 |  | 1992-06-01 |  | 1995-06-01 |  | 1995-06-01 | 1995-06-01 | 285000 | 65000 | 350000 | 350000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. US $65,000 against 1994 contributions (15th meeting)
FIN | USA | Support for country programme preparation and development of project proposals |  | LAC | MEX | SEV | 07 | PRP | 17 | A | I |  | 0 |  | 0 |  | 1992-06-01 |  | 1993-06-01 |  | 1993-06-01 | 1993-06-01 | 145000 | 136000 | 281000 | 281000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Adjustment of US $136,000 credited against 1993 contributions (11th Meeting).
FIN | USA | Assistance to country programme and investment projects preparation |  | LAC | MEX | SEV | 08 | CPG | 18 | A | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1993-10-01 |  | 1993-10-01 | 1993-10-01 | 28000 | 0 | 28000 | 28000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1992
FIN | IBRD | Preparation of investment projects (1993) |  | LAC | MEX | SEV | 09 | PRP | 21 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 123400 | -65386 | 58014 | 58014 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Project preparation assistance | Individual | LAC | MEX | SEV | 11 | PRP | 22 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-01 | 1994-11-01 |  | 1994-12-01 | 1997-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1993 |  | Investment
FIN | IBRD | Supervision of project implementation (1994) |  | LAC | MEX | SEV | 12 | PRP | 23 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 100000 | -35085 | 64915 | 64915 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Activities completed |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1994) |  | LAC | MEX | SEV | 12 | PRP | 24 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 52286 | -44858 | 7428 | 7428 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Bank is evaluating its activities in the country. |  |  |  | Non-INV | 0
FIN | UNDP | Project preparation assistance | Individual | LAC | MEX | SEV | 14 | PRP | 29 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-09-01 | 1994-10-01 | 1995-12-01 |  | 1995-12-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Investment
FIN | IBRD | Preparation/supervision of investment projects for ODS I and ODS II (1995) |  | LAC | MEX | SEV | 16 | PRP | 38 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-31 | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 71744 | 0 | 71744 | 71744 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | UNDP | Extension of institutional strengthening | Individual | LAC | MEX | SEV | 17 | INS | 40 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-11-01 | 1996-12-01 |  | 1996-10-01 | 2003-11-01 | 47500 | 47500 | 95000 | 95000 | 100% | 0 | 0 | 0 | 6175 | 6175 | 12350 | 0 | 0 | Completed in 1996. Financially completed in 2003. |  | 1995 |  | Non-Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | MEX | SEV | 17 | PRP | 39 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-08-01 | 1996-07-01 |  | 1996-11-01 | 1998-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNIDO | Preparation of investment projects | Individual | LAC | MEX | SEV | 18 | PRP | 44 | A | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-03-01 | 1996-08-01 |  | 1997-09-01 | 2000-07-01 | 50000 | -477 | 49523 | 49523 | 100% | 0 | 0 |  | 6500 | -72 | 6428 | 0 | 0 | FIN
FIN | UNDP | Project preparation assistance | Individual | LAC | MEX | SEV | 18 | PRP | 45 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-12-01 | 1998-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Renewal of the institutional strengthening project for the phaseout of ODSs under the Montreal Protocol | Individual | LAC | MEX | SEV | 20 | INS | 50 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1996-10-01 | 1996-11-01 | 1998-10-01 |  | 1998-10-01 | 2003-11-01 | 190000 | 0 | 190000 | 190000 | 100% | 0 | 0 | 0 | 24700 | 0 | 24700 | 0 | 0 | Completed in 1998. Financially completed in 2003. |  | 1996 |  | Non-Investment
FIN | IBRD | Project preparation |  | LAC | MEX | SEV | 21 | PRP | 51 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | UNDP | Project preparation in the foam and solvent sectors | Individual | LAC | MEX | SEV | 21 | PRP | 52 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2000-12-01 | 52000 | -2539 | 49461 | 49461 | 100% | 0 | 0 | 0 | 6760 | -330.07 | 6429.93 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Project preparation | Individual | LAC | MEX | SEV | 22 | PRP | 53 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-04-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Survey of ODS use in SMEs and approaches to ODS elimination | Individual | LAC | MEX | SEV | 22 | TAS | 59 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1998-05-01 |  | 1998-05-01 | 2001-12-01 | 60000 | -1400 | 58600 | 58600 | 100% | 0 | 0 | 0 | 7800 | -182 | 7618 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1997 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening project | Individual | LAC | MEX | SEV | 25 | INS | 83 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-09-01 | 2000-07-01 |  | 2000-07-01 | 2003-11-01 | 190000 | 0 | 190000 | 190000 | 100% | 0 | 0 | 0 | 24700 | 0 | 24700 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1998 |  | Non-Investment
FIN | UNDP | Renewal of the institutional strengthening project for the phaseout of ODS under the Montreal Protocol (Phase V) | Individual | LAC | MEX | SEV | 31 | INS | 97 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2000-07-01 | 2000-08-01 | 2002-08-01 |  | 2002-08-01 | 2003-11-01 | 190000 | -45584 | 144416 | 144416 | 100% | 0 | 0 | 0 | 24700 | -5926 | 18774 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Non-Investment
FIN | UNIDO | Renewal of the institutional strengthening project for the phase out of ODS under the Montreal Protocol (Phase V) | Individual | LAC | MEX | SEV | 37 | INS | 109 | N | I |  | 0 | 0 |  |  | 2002-07-01 | 2002-10-01 | 2002-08-01 |  | 2003-12-01 | 2005-03-01 | 0 | 50040 | 50040 | 50039.54 | 100% | 0.46 | 0 |  | 0 | 6495 | 6495 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Renewal of institutional strengthening project (Phase 6) | Individual | LAC | MEX | SEV | 37 | INS | 110 | N | I | CFC | 20.4 | 20.4 |  |  | 2002-07-01 | 2003-02-01 | 2004-08-01 |  | 2005-03-01 | 2006-05-01 | 247000 | -4309 | 242691 | 242690.6 | 100% | 0.4 | 0 |  | 32110 | -610 | 31500 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNDP | Preparation of the country programme update | Individual | LAC | MEX | SEV | 38 | CPG | 111 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-01-01 | 2003-12-01 |  | 2003-12-01 | 2005-10-01 | 48046 | -17955 | 30091 | 30091 | 100% | 0 | 0 | 0 | 6245.98 | -2334.16 | 3911.8225 | -0.002509 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Non-Investment
FIN | UNIDO | Extension of institutional strengthening project: phase VII | Individual | LAC | MEX | SEV | 45 | INS | 125 | N | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-07-01 | 2007-04-01 |  | 2007-08-01 | 2008-08-01 | 247000 | 0 | 247000 | 247000 | 100% | 0 | 0 |  | 18525 | 0 | 18525 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNDP | Assistance to carry out an HCFC survey | Individual | LAC | MEX | SEV | 45 | TAS | 127 | A | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-07-01 | 2006-12-01 |  | 2008-08-01 | 2009-12-01 | 114679 | -17119 | 97560 | 97560 | 100% | 0 | 0 | 0 | 10321 | -1540.69 | 8780.3064 | 0.0036 | 0 | Completed in 2008. Financially completed in 2009. |  | 2005 |  | Non-Investment
FIN | UNIDO | Extension of institutional strengthening project (phase VIII) | Individual | LAC | MEX | SEV | 52 | INS | 132 | N | I |  | 0 | 0 |  |  | 2007-07-01 | 2007-09-01 | 2009-07-31 |  | 2009-06-01 | 2011-12-01 | 247000 | -1203 | 245797 | 245797.09 | 100% | -0.09 | 0 |  | 18525 | -90 | 18435 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Extension of institutional strengthening project (phase IX) | Individual | LAC | MEX | SEV | 58 | INS | 147 | N | I |  | 0 | 0 |  |  | 2009-07-01 | 2009-12-01 | 2010-12-31 |  | 2010-12-01 | 2012-12-01 | 185250 | -281 | 184969 | 184969.2 | 100% | -0.2 | 0 |  | 13894 | -21 | 13873 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Extension of institutional strengthening project (phase X) | Individual | LAC | MEX | SEV | 62 | INS | 152 | N | I |  | 0 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2012-12-31 |  | 2012-06-01 | 2015-03-01 | 247000 | -2606 | 244394 | 244394.38 | 100% | -0.38 | 0 |  | 18525 | -195 | 18330 | 0 | 0 | FIN |  |  |  | NON-INV
COM | UNIDO | Extension of institutional strengthening project (phase XI: 1/2013-12/2014) | Individual | LAC | MEX | SEV | 68 | INS | 163 | N | I |  | 0 | 0 |  |  | 2012-12-01 | 2013-07-01 | 2014-12-31 |  | 2015-12-01 |  | 247000 | 0 | 247000 | 246995.63 | 100% | 4.37 | 0 | 1 | 17290 | 0 | 17290 | 0 | 0 | The project was operationally completed. |  |  |  | NON-INV
ONG | UNIDO | Extension of institutional strengthening project (phase XII: 1/2015-12/2016) | Individual | LAC | MEX | SEV | 73 | INS | 175 | N | I |  | 0 | 0 |  |  | 2014-11-01 | 2015-04-01 | 2016-12-31 | 2017-06-01 |  |  | 247000 | 0 | 247000 | 180473.9 | 73.07% | 66526.1 | 12848.37 | 60000 | 17290 | 0 | 12633 | 4657 | 899 | - NOU staff and NC contract for the year 2016 released. - Work plan for the year 2016 concluded and activities are executed as per the project document. Awareness activities during 2016 were undertaken, regular data collection was done and SISSAO database up-dated. Milestones achieved: Milestone 1: NOU staff contracts released - Yes Milestone 2: Awareness activities planned - Yes Milestone 3: Data collection process for SSISAO database up-date done - Yes Actions towards next goals: Submit 2016 A7 and CP data and Submit next IS phase. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - NOU staff and NC contract are ongoing until July only due to lack of funds for further extension. - Regular data collection was done and SISSAO database was up-dated. 2016 A7 data report submitted to the Ozone Secretariat. Next IS phase will be submitted to the 79th ExCom Meeting. |  |  | NON-INV
ONG | UNIDO | Survey of ODS alternatives at the national level | Individual | LAC | MEX | SEV | 74 | TAS | 176 | A | I |  | 0 | 0 |  |  | 2015-05-01 | 2016-04-01 | 2016-05-31 | 2017-04-01 |  |  | 90000 | 0 | 90000 | 51574.45 | 57.3% | 38425.55 | 32.85 | 35000 | 8100 | 0 | 0 | 8100 | 2.9565 | TOR was prepared for the initiation of the survey and an expert team was recruited for the data collection and analysis. The first interim report was received mid-August, which was reviewed by UNIDO and comments were sent to Mexico in the last quarter of 2016. | The final draft survey was submitted to UNIDO in January 2017, which was submitted to the Secretariat. Additional work is being undertaken to estimate emissions and the survey is also being updated to reflect the comments made by the Fund Secretariat. |  |  | NON-INV
FIN | IBRD | Phase out of CFC-113 used as a cleaning agent in the manufacturing of optical frames at Styloptic, S.A. | Individual | LAC | MEX | SOL | 05 | INV | 11 | N | I | CFC | 3.2 | 0.72 | 0 | 0 | 1991-11-01 | 1995-01-01 | 1992-11-01 |  | 1995-06-01 | 1995-06-01 | 79299 | 0 | 79299 | 79299 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1995-06-01 | INV | 0
FIN | IBRD | Recovery, reclaim and recycling of CFC-113 and methylchloroform through Química Omega S.A. plant | Individual | LAC | MEX | SOL | 05 | INV | 12 | N | I |  | 183.3 | 183.3 | 0 | 0 | 1991-11-01 | 1995-02-01 | 1992-11-01 |  | 1995-11-01 | 1995-11-01 | 295302 | 0 | 295302 | 295302 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1995-11-01 | INV | 0
FIN | USA | Mexican solvents programme to reduce CFC-113 and methyl chloroform |  | LAC | MEX | SOL | 08 | TRA | 20 | A | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1993-03-01 |  | 1993-03-01 | 1993-03-01 | 360000 | 138000 | 498000 | 498000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Adjustment of US $138,000 credited against 1993 contributions (11th Meeting).
FIN | USA | Project preparation |  | LAC | MEX | SOL | 13 | PRP | 28 | A | I |  | 0 |  | 0 |  | 1994-07-01 |  | 1995-07-01 |  | 1995-07-01 | 1996-06-01 | 450000 | -119143 | 330857 | 330857 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | UNDP | Elimination of 1,1,1 TCA from the precision cleaning processes at Lucas Diesel | Individual | LAC | MEX | SOL | 15 | INV | 36 | A | D | TCA | 3 | 3 | 0 | 0 | 1994-12-01 | 1995-12-01 | 1995-06-01 |  | 1997-07-01 | 1999-12-01 | 168000 | 0 | 168000 | 168000 | 100% | 0 | 0 | 0 | 21840 | 0 | 21840 | 0 | 0 | Completed in 1997. Financially completed in 1999. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-113 from the textile cleaning processes at Procesadora y Revitalizadora | Individual | LAC | MEX | SOL | 15 | INV | 37 | A | I | CFC | 3 | 3 | 0 | 0 | 1994-12-01 | 1995-10-01 | 1995-09-01 |  | 1996-08-01 | 2000-12-01 | 71337 | -1889 | 69448 | 69448 | 100% | 0 | 0 | 0 | 9273.81 | -245.57 | 9028.24 | 0 | 0 | Completed in 1996. Financially completed in 2000. |  | 1994 |  | Investment
CLO | UNIDO | Preparation of a sectoral phase-out plan in the solvents sector | Individual | LAC | MEX | SOL | 36 | PRP | 108 | A | I |  | 0 | 0 |  |  | 2002-03-01 |  | 2003-07-01 |  |  | 2003-05-01 | 70000 | -70000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 9100 | -9100 | 0 | 0 | 0 | CLO |  |  |  | INV
CLO | UNIDO | Preparation of investment projects in the solvent sector (TCA) | Individual | LAC | MEX | SOL | 39 | PRP | 114 | A | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-12-01 | 2004-04-01 |  |  | 2004-06-01 | 30000 | -18965 | 11035 | 11035.41 | 100% | -0.41 | 0 |  | 2250 | -1424 | 826 | 0 | 0 | CLO
FIN | IBRD | Sterilization group project to replace CFC-12 technology-based sterilization equipment by alternative technologies in the hospital medical sterilization sector | Individual | LAC | MEX | STE | 40 | INV | 115 | N | I | CFC | 14.5 | 19.94 | 0 | 0 | 2003-07-01 | 2005-12-01 | 2005-07-01 |  | 2006-06-01 | 2006-06-01 | 288700 | -22568 | 266132 | 266132 | 100% | 0 | 0 |  | 21653 | -1692.64 | 19960.36 | 0 | 0 | Umbrella project is now completed. |  |  |  | INV | 0
FIN | France | Project preparation in the foam sector (Fofy) |  | AFR | MLI | FOA | 25 | PRP | 04 | A | I |  | 0 |  | 0 |  | 1998-07-01 | 1998-08-01 | 1999-01-01 |  | 1998-09-01 | 1998-11-01 | 15000 | -1000 | 14000 | 14000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed
FIN | France | Phase-out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Fofy Industrie |  | AFR | MLI | FOA | 26 | INV | 05 | A | I | CFC | 19.5 | 19.5 | 0 |  | 1998-11-01 | 2000-01-01 | 2000-12-01 |  | 2001-12-01 | 2001-12-01 | 151000 | 0 | 151000 | 151000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Projet achevé. PCR soumis
FIN | UNIDO | Preparation of an awareness workshop in the methyl bromide sector | Individual | AFR | MLI | FUM | 36 | TRA | 12 | A | I | MBR | 0 | 0 |  |  | 2002-03-01 | 2002-10-01 | 2003-04-03 |  | 2003-07-01 | 2004-04-01 | 30000 | -596 | 29404 | 29403.72 | 100% | 0.28 | 0 |  | 3900 | -84 | 3816 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | MLI | PHA | 48 | PRP | 20 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-05-01 | 2007-04-01 |  | 2008-02-01 | 2009-02-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 |  | 2340 | 0 | 2340 | 0 | 0
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | AFR | MLI | PHA | 48 | PRP | 21 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-02-01 | 2007-04-01 |  | 2007-11-01 | 2010-01-01 | 12000 | -1262 | 10738 | 10738 | 100% | 0 | 0 | 0 | 900 | -94.65 | 805.35 | 0 | 0 | Financially completed in 2010. |  | 2006 |  | Investment
FIN | UNDP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | MLI | PHA | 53 | INV | 24 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-11-01 |  | 2009-12-01 | 2013-07-01 | 172000 | 0 | 172000 | 172000 | 100% | 0 | 0 | 0 | 12900 | 0 | 12900 | 0 | 0 | Financially completed in 2013. |  | 2007 |  | Investment
FIN | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | MLI | PHA | 53 | TAS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-03-01 |  | 2009-03-01 | 2011-03-01 | 120000 | -5587.86 | 114412.14 | 114412.14 | 100% | 0 | 0 |  | 15600 | -726.42 | 14873.58 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | MLI | PHA | 55 | PRP | 25 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-01-01 | 2009-07-01 |  | 2013-06-01 | 2014-07-01 | 85000 | -11106 | 73894 | 73894 | 100% | 0 | 0 |  | 11050 | -1443.78 | 9606.22 | 0 | 0
FIN | UNDP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | MLI | PHA | 57 | INV | 28 | N | I | CFC | 16.2 | 16.2 | 0 | 0 | 2009-04-01 | 2010-09-01 | 2011-03-01 |  | 2010-12-01 | 2013-07-01 | 150000 | -2802.02 | 147197.98 | 147198 | 100% | -0.02 | 0 | 0 | 11250 | -210.15 | 11039.85 | 0 | 0 | Financially completed in 2013. |  | 2009 |  | Investment
FIN | UNEP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | MLI | PHA | 57 | TAS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-08-01 | 2009-03-01 |  | 2010-12-01 | 2011-03-01 | 78000 | 0 | 78000 | 78000 | 100% | 0 | 0 |  | 10140 | 0 | 10140 | 0 | 0
COM | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | MLI | PHA | 63 | INV | 30 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-11-01 | 2013-03-01 |  | 2013-12-01 |  | 160000 | 0 | 160000 | 153597 | 96% | 6403 | 0 | 5442.55 | 12000 | -0.18 | 11519.607 | 480.213 | 0 | Completed in 2013. |  | 2011 |  | Investment
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | AFR | MLI | PHA | 63 | TAS | 29 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-08-01 | 2013-03-01 |  | 2013-03-01 | 2014-03-01 | 65000 | -3170 | 61830 | 61830 | 100% | 0 | 0 |  | 8450 | -412.1 | 8037.9 | 0 | 0
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | AFR | MLI | PHA | 71 | TAS | 33 | A | I |  | 0.8 |  | 0 |  | 2013-12-01 | 2014-05-01 | 2016-12-01 | 2018-07-01 |  |  | 55000 | 0 | 55000 | 45000 | 81.82% | 10000 | 10000 | 1000 | 7150 | 0 | 5850 | 1300 | 1300 | Brief progress report (actual/planned): 50 Refrigeration technicians trained on good practices and safe handling of hydrocarbon in 2016; and 20 customs officers trained on identification of HCFCs and HCFC based equipment in 2016. Legal arrangements (actual/planned): Agreement signed in May 2014. All activities under the SSFA are completed (as planned) __No_ First mission (actual/planned): _ N/A - Project Completed _No_ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in May 2014 __ All funds disbursed (yes/no): _.__ Any delay? (yes/no): YES ___ If Yes, reasons for delay & action plan to resolve: n/a _Low responsiveness of the NOO__ If Yes, will delay have impact on project completion date (yes/no): _ Yes, the SSFA has already expired with only one payment __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a __ | Brief progress report (actual/planned): Legal arrangements (actual/planned): Agreement signed in May 2014. 50 Refrigeration technicians trained on good practices and safe handling of hydrocarbon in 2016; and 20 customs officers trained on identification of HCFCs and HCFC based equipment in 2016. All activities under the SSFA are completed (as planned) __No_ First mission (actual/planned): _ N/A - Project Completed _No_ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in May 2014 __ All funds disbursed (yes/no): _No__ Any delay? (yes/no): YES ___ If Yes, reasons for delay & action plan to resolve: n/a _Low responsiveness of the NOO__ If Yes, will delay have impact on project completion date (yes/no): _ Yes, the SSFA has already expired with only one payment. Balance of US $ 40,000 __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: Balance of US $ 40,000 to be returned as the 3rd Tranche has been approved. |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor the low disbursement rate of approved funds.
ONG | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Individual | AFR | MLI | PHA | 75 | TAS | 36 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-01-01 | 2017-03-01 | 2017-07-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 30000 | 3000 | 3900 | 0 | 0 | 3900 | 3900 | Brief progress report (actual/planned): Consultant was recruited in March 2016. Draft Verification report sent to UNEP in June 2016 for comments . Verification report approved by MLFS in August 2016. Legal arrangements (actual/planned): n/a (Yes/No): No_ First mission (actual/planned): __n/a_ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): n/a__ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _YES_ If Yes, reasons for delay & action plan to resolve: NO__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): Project completed in December 2016. Legal arrangements (actual/planned): n/a (Yes/No): No_ First mission (actual/planned): __n/a_ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): n/a__ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _YES_ If Yes, reasons for delay & action plan to resolve: NO__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__
ONG | UNDP | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | AFR | MLI | PHA | 76 | INV | 38 | N | I | HCFC | 2.6 | 0 | 0 | 0 | 2016-05-01 |  | 2020-05-01 | 2017-05-01 |  |  | 92000 | 0 | 92000 | 0 | 0% | 92000 | 0 | 36800 | 6900 | 0 | 0 | 6900 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): The project was conditionally approved (Verification Report). With the communication of the report and its approval, the launch of the activities could be planned - though no new activity /disbursement could occurr yet. Prodoc signed (actual/planned, yes/no and date):0/1 No. Missions undertaken (actual/planned):0/0 No TOR for consultants/subcontracts completed (actual/planned): ToR completed earlier Contract/PO/MOA agreements signed: 0/0 No First disbursement date (actual/planned): Any delays/problems (yes/no):Delays were due to the conditional approval and to the time needed for preparation f project-related required documents. If Yes, reasons for delay & action plan to resolve:Expediting the administrative set-p of the new tranche. | Project document drafted. |  |  | Investment
ONG | UNEP | HCFC phase-out management plan (stage I, third tranche) | Multi-year | AFR | MLI | PHA | 76 | TAS | 37 | A | I |  | 0 |  | 0 |  | 2016-05-01 |  | 2018-12-01 | 2018-12-01 |  |  | 80000 | 0 | 80000 | 30276.17 | 37.85% | 49723.83 | 15000 | 4972.383 | 10400 | 0 | 3935.9021 | 6464.0979 | 1950 | Newly approved project | Brief progress report (actual/planned): Project newly approved. Agreement signed in Feb. 2017. Legal arrangements (actual/planned): Agreement signed in Feb. 2017. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st payment not sent yet__ All funds disbursed (yes/no): _ Final payment _no___ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
FIN | UNEP | Development of refrigerant management plan | RMP | AFR | MLI | REF | 24 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-05-01 | 1999-02-01 |  | 1999-10-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0
FIN | UNEP | Implementation of the RMP: assistance in drafting ODS-related legislation | Individual | AFR | MLI | REF | 29 | TAS | 06 | A | I | CFC | 2.7 | 2.7 | 0 | 0 | 1999-11-01 | 2001-02-01 | 2001-06-01 |  | 2002-07-01 | 2003-08-01 | 10980 | 0 | 10980 | 10980 | 100% | 0 | 0 |  | 1427 | 0 | 1427 | 0 | 0
FIN | UNEP | Implementation of the RMP: training programme for customs officers | Individual | AFR | MLI | REF | 29 | TRA | 07 | A | I | CFC | 14.8 | 14.8 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2001-06-01 |  | 2003-12-01 | 2003-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0 |  |  |  | 2003-03-01
FIN | UNEP | Implementation of the RMP: train the trainers programme in the refrigeration servicing sector | Individual | AFR | MLI | REF | 29 | TRA | 08 | A | I | CFC | 14.8 | 14.8 | 0 | 0 | 1999-11-01 | 2001-02-01 | 2001-06-01 |  | 2002-05-01 | 2005-01-01 | 60000 | -18414 | 41586 | 41586 | 100% | 0 | 0 |  | 7800 | -2393.82 | 5406.18 | 0 | 0 |  |  |  | 2002-12-01
FIN | UNDP | Implementation of the RMP: national programme for recovery and recycling of refrigerants | RMP-Component | AFR | MLI | REF | 32 | TAS | 09 | A | I | CFC | 25.2 | 25.2 | 0 | 0 | 2000-12-01 | 2002-05-01 | 2004-01-01 |  | 2003-12-01 | 2004-01-01 | 102658 | -3517.7 | 99140.3 | 99140 | 100% | 0.3 | 0 | 0 | 13345.54 | -457.2 | 12888.3015 | 0.038519 | 0 | Completed in 2003. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Implementation of the RMP: monitoring the activities in the refrigerant management plan | RMP-Component | AFR | MLI | REF | 32 | TAS | 10 | A | I | No_ODP | 3.8 | 3.8 | 0 | 0 | 2000-12-01 | 2002-07-01 | 2004-01-01 |  | 2005-07-01 | 2007-03-01 | 15455 | -237 | 15218 | 15218 | 100% | 0 | 0 | 0 | 2009.15 | -30.81 | 1978.3423 | -0.0023 | 0 | Completed in 2005. Financially completed in 2007. |  | 2000 |  | Non-Investment
FIN | UNEP | Preparation of the RMP update | RMP update | AFR | MLI | REF | 43 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2009-02-01 | 2005-07-01 |  | 2005-11-01 | 2009-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0
FIN | UNDP | Implementation of the RMP update: supplementary training and spares to the national programme for recovery and recycling of refrigerants | RMP-Component | AFR | MLI | REF | 45 | TAS | 16 | N | I | CFC | 12.3 | 12.3 | 0 | 0 | 2005-04-01 | 2007-09-01 | 2007-04-01 |  | 2007-12-01 | 2013-07-01 | 50000 | -1390.13 | 48609.87 | 48610 | 100% | -0.13 | 0 | 0 | 4500 | -125.11 | 4374.9 | -0.01 | 0 | Financially completed in 2013. |  | 2005 |  | Non-Investment
FIN | UNEP | Implementation of the RMP update: monitoring of the activities in the RMP | Individual | AFR | MLI | REF | 45 | TAS | 19 | A | I | CFC | 4.9 | 4.9 | 0 | 0 | 2005-04-01 | 2005-08-01 | 2007-04-01 |  | 2008-12-01 | 2009-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0
FIN | UNEP | Implementation of the RMP update: training programme for customs officers (phase II) | Individual | AFR | MLI | REF | 45 | TRA | 17 | A | I | CFC | 7.3 | 7.3 | 0 | 0 | 2005-04-01 | 2005-08-01 | 2006-10-01 |  | 2007-09-01 | 2008-12-01 | 29546 | 0 | 29546 | 29546 | 100% | 0 | 0 |  | 3841 | 0 | 3841 | 0 | 0
FIN | UNEP | Implementation of the RMP update: training programme for refrigeration service technicians (phase II) | Individual | AFR | MLI | REF | 45 | TRA | 18 | A | I | CFC | 6.1 | 6.1 | 0 | 0 | 2005-04-01 | 2005-08-01 | 2006-10-01 |  | 2008-12-01 | 2009-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0
FIN | UNEP | Country programme preparation | Individual | AFR | MLI | SEV | 19 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-08-01 |  | 1998-05-01 | 1999-06-01 | 43000 | 0 | 43000 | 43000 | 100% | 0 | 0 |  | 5590 | 0 | 5590 | 0 | 0
FIN | UNEP | Institutional strengthening project for Mali | Individual | AFR | MLI | SEV | 24 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-08-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project | Individual | AFR | MLI | SEV | 35 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-03-01 | 2004-01-01 |  | 2004-03-01 | 2007-06-01 | 46667 | 0 | 46667 | 46667 | 100% | 0 | 0 |  | 6067 | 0 | 6067 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | AFR | MLI | SEV | 44 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-04-01 | 2006-12-01 |  | 2006-12-01 | 2008-12-01 | 60677 | 0 | 60677 | 60677 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | MLI | SEV | 50 | INS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2008-11-01 |  | 2008-11-01 | 2009-11-01 | 60677 | 0 | 60677 | 60677 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | AFR | MLI | SEV | 56 | INS | 26 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-12-01 | 2010-12-01 |  | 2010-06-01 | 2011-06-01 | 60677 | 0 | 60677 | 60677 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VI) | Individual | AFR | MLI | SEV | 63 | INS | 31 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-12-01 | 2013-03-01 |  | 2012-12-01 | 2013-12-01 | 60677 | 0 | 60677 | 60677 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of the institutional strengthening project (phase VII: 7/2013-6/2015) | Individual | AFR | MLI | SEV | 70 | INS | 32 | A | I |  | 0 |  | 0 |  | 2013-07-01 | 2014-02-01 | 2015-06-01 |  | 2015-12-01 |  | 60677 | 0 | 60677 | 49196.7 | 81.08% | 11480.3 | 11480.3 | 11480 | 0 | 0 | 0 | 0 | 0 | Project completed. | Project completed.
ONG | UNEP | Extension of the institutional strengthening project (phase VIII: 7/2015-6/2017) | Individual | AFR | MLI | SEV | 74 | INS | 34 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-04-01 | 2017-06-01 | 2017-12-01 |  |  | 60677 | 0 | 60677 | 362.66 | 0.5977% | 60314.34 | 60314.34 | 6031.434 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): NOU coordinated training of 50 Refrigeration technicians trained on good practices and safe handling of hydrocarbon in 2016; and training of 20 customs officers trained on identification of HCFCs and HCFC based equipment in 2016. Legal arrangements (actual/planned): Agreement signed in March 2016. All activities under the SSFA are completed (as planned) NO__ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in April 2016 __ All funds disbursed (yes/no):NO _ Final payment _ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Brief progress report (actual/planned): Legal arrangements (actual/planned): Agreement signed in March 2016. NOU coordinated training of 50 Refrigeration technicians trained on good practices and safe handling of hydrocarbon in 2016; and training of 20 customs officers trained on identification of HCFCs and HCFC based equipment in 2016. All activities under the SSFA are completed (as planned) NO__ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in April 2016 __ All funds disbursed (yes/no):NO _ Final payment _ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | AFR | MLI | SEV | 75 | TAS | 35 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-10-01 | 2016-12-01 | 2017-10-01 |  |  | 70000 | 0 | 70000 | 0 | 0% | 70000 | 70000 | 7000 | 9100 | 0 | 0 | 9100 | 9100 | Brief progress report (actual/planned): _Local consultants recruited in May 2016 and National survey on ODS alternatives started in June 2016. Legal arrangements (actual/planned): signed in April 2016 (Yes/No): No_ First mission (actual/planned): __n/a_ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): October 2016___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _YES_ If Yes, reasons for delay & action plan to resolve: NO__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): _Local consultants recruited in May 2016 and National survey on ODS alternatives started in June 2016. NOU sent the draft survey report in January 2017, the report was revised and commented by UNEP. It was sent back by UNEP because of many issues to be further addressed. Legal arrangements (actual/planned): signed in April 2016 (Yes/No): No_ First mission (actual/planned): __n/a_ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): October 2016___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _YES_ If Yes, reasons for delay & action plan to resolve: NO__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__
FIN | UNDP | Project preparation in the foam sector | Individual | AFR | MLW | FOA | 21 | PRP | 06 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1998-05-01 | 1997-12-01 |  | 1998-05-01 | 2002-03-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | AFR | MLW | FOA | 22 | PRP | 07 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-06-01 | 1997-12-01 |  | 1998-04-01 | 2002-03-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 650 | 0 | 650 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Robry Ltd. | Individual | AFR | MLW | FOA | 26 | INV | 12 | A | I | CFC | 33 | 33 | 0 | 0 | 1998-11-01 | 1999-07-01 | 2000-12-01 |  | 2004-12-01 | 2005-11-01 | 156500 | -17548 | 138952 | 138952 | 100% | 0 | 0 | 0 | 20345 | -2281.24 | 18063.76 | -2.4e-05 | 0 | Completed in 2004. Financially completed in 2005. |  | 1998 |  | Investment
FIN | UNDP | Project preparation for a methyl bromide (tobacco) alternative demonstration project | Individual | AFR | MLW | FUM | 24 | PRP | 09 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1999-02-01 | 1998-12-01 |  | 2000-12-01 | 2001-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organizations in methyl bromide communication | Individual | AFR | MLW | FUM | 30 | TAS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9242 | 15758 | 15758 | 100% | 0 | 0 |  | 3250 | -1201.46 | 2048.54 | 0 | 0
FIN | UNDP | Phaseout of all non-essential and non-QPS methyl bromide (release of first tranche) | Multi-Year | AFR | MLW | FUM | 32 | DEM | 15 | N | I | MeBr | 19.3 | 19.3 | 0 | 0 | 2000-12-01 | 2001-05-01 | 2001-12-01 |  | 2001-12-01 | 2011-12-01 | 400000 | 0 | 400000 | 400000 | 100% | 0 | 0 | 0 | 52000 | 0 | 52000 | 0 | 0 | Completed in 2001. Financially completed in 2011. |  | 2000 |  | Investment
FIN | UNDP | Second payment under the national programme for the phaseout of all non-essential and non-quarantine and pre-shipment applications of methyl bromide | Multi-Year | AFR | MLW | FUM | 34 | INV | 16 | N | I | MeBr | 20.9 | 20.9 | 0 | 0 | 2001-07-01 | 2002-04-01 | 2002-08-01 |  | 2004-12-01 | 2011-12-01 | 1000000 | 0 | 1000000 | 1000000 | 100% | 0 | 0 | 0 | 120000 | 0 | 120000 | 0 | 0 | Completed in 2004. Financially completed in 2011. |  | 2001 |  | Investment
FIN | UNDP | Phase-out of all non-essential and non-QPS methyl bromide (release of third tranche) | Multi-Year | AFR | MLW | FUM | 40 | INV | 18 | N | I | MeBr | 41.1 | 41.1 | 0 | 0 | 2003-07-01 | 2004-07-01 | 2004-07-01 |  | 2004-12-01 | 2011-12-01 | 750000 | 0 | 750000 | 750000 | 100% | 0 | 0 | 0 | 56250 | 0 | 56250 | 0 | 0 | Completed in 2004. Financially completed in 2011. |  | 2003 |  | Investment
FIN | UNDP | Phase-out of all non-essential and non-QPS methyl bromide (fourth tranche) | Multi-Year | AFR | MLW | FUM | 43 | INV | 21 | N | I | MeBr | 47.7 | 47.7 | 0 | 0 | 2004-07-01 | 2004-07-01 | 2005-07-01 |  | 2006-12-01 | 2011-12-01 | 849824 | -11520.51 | 838303.49 | 838303 | 100% | 0.49 | 0 | 0 | 63737 | -864.04 | 62872.9222 | 0.03775 | 0 | Completed in 2006. Financially completed in 2011. |  | 2004 |  | Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | MLW | PHA | 50 | PRP | 23 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2007-11-01 |  | 2007-02-01 | 2007-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNDP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | MLW | PHA | 53 | INV | 25 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-07-01 | 2009-11-01 |  | 2009-12-01 | 2013-02-01 | 125500 | 0 | 125500 | 125500 | 100% | 0 | 0 | 0 | 11295 | 0 | 11295 | 0 | 0 | Financially completed in 2013. |  | 2007 |  | Investment
FIN | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-year | AFR | MLW | PHA | 53 | TAS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-03-01 |  | 2009-03-01 | 2010-12-01 | 95000 | 0 | 95000 | 95000 | 100% | 0 | 0 |  | 12350 | 0 | 12350 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | MLW | PHA | 55 | PRP | 27 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-02-01 | 2009-07-01 |  | 2010-12-01 | 2011-03-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 |  | 11050 | 0 | 11050 | 0 | 0
FIN | UNDP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | MLW | PHA | 57 | INV | 29 | N | I | CFC | 8.7 | 8.7 | 0 | 0 | 2009-04-01 | 2010-03-01 | 2011-03-01 |  | 2011-12-01 | 2012-10-01 | 47500 | -1244.51 | 46255.49 | 46255 | 100% | 0.49 | 0 | 0 | 4275 | -112.01 | 4162.95 | 0.04 | 0 | Financially completed in 2012. | Financially completed in 2012. | 2009 |  | Investment
FIN | UNEP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | MLW | PHA | 57 | TAS | 28 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-07-01 | 2010-03-01 |  | 2011-12-01 | 2011-12-01 | 77000 | 0 | 77000 | 77000 | 100% | 0 | 0 |  | 10010 | 0 | 10010 | 0 | 0
FIN | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | MLW | PHA | 62 | INV | 32 | A | I |  | 0 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2013-12-31 |  | 2013-05-01 | 2014-07-01 | 60000 | -1250 | 58750 | 58750.33 | 100% | -0.33 | 0 |  | 5400 | -113 | 5288 | -1 | 0 | FIN |  |  |  | INV
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | MLW | PHA | 62 | TAS | 31 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-05-01 | 2013-12-01 |  | 2013-12-01 | 2014-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | AFR | MLW | PHA | 70 | TAS | 34 | A | I |  | 0.7 |  | 0 |  | 2013-07-01 | 2014-02-01 | 2016-07-01 | 2017-10-01 |  |  | 55000 | 0 | 55000 | 16759.5 | 30.47% | 38240.5 | 38240.5 | 3824.05 | 7150 | 0 | 2178.735 | 4971.265 | 4971.265 | Brief progress report (actual/planned): The NOU implemented a number of activities under the HPMP including trainings for law enforcement officers and refrigeration technicians, and public awareness. The NOU conducted two training sessions for law enforcement officers where a total of 30 officers were trained on control and enforcement of the legislations governing ODS in the country. The officers were drawn from Customs Department, Police, Clearing Agents and Malawi Bureau of Standards officers from central region of Malawi. The officers acquired skills and knowledge on ODS identification procedures and were also oriented on the control measures in place for the importation of HCFCs and other refrigerants. The trainings have enhanced the capacity of the law enforcement officers on motoring illegal trade. The NOU conducted two regional refrigeration training sessions on implementation of good refrigeration practices including use of hydrocarbons. The trainings took place at Zomba Works Training Centre and Mzuzu Trade Testing Centers where a total of 40 refrigeration technicians were trained. The technicians have played a complimentary critical role in the dissemination of HCFCs phase-out information to the consumers, advising them on the type of refrigeration equipment and refrigerants that are legally accepted and the phase-out plan in the country. There is regular collaboration and sharing of information between the NOU and the refrigeration technicians in the country. In addition, the NOU conducted two meetings of the Refrigeration Association of Malawi (RAM) which were held in Zomba and Mzuzu. The RAM meetings centered on the role of technicians on the HCFC phase-out process and enforcement of best practices in the refrigeration sector. Legal arrangements (actual/planned): The SSFA was drafted and signed by UNEP and the Government of Malawi in February, 2014.___ First mission (actual/planned): __Yes_ TOR completed(actual/planned): _Yes__ First disbursement date (actual/planned): First disbursement was made in February 2014___ All funds disbursed (yes/no): No___ Any delay? (yes/no): _No__ If Yes, reasons for delay & action plan to resolve: N/A___ If Yes, will delay have impact on project completion date (yes/no): __N/A_ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: __N/A_ | Brief progress report (actual/planned): The NOU conducted a train the trainer’s workshop at Blantyre Trade Testing Centre from 8-10 March 2017. A total of 20 refrigeration technicians drawn from technical colleges teaching refrigeration mechanics as well as seasoned technicians were trained. The training was facilitated by Joseph Kibet Regut from Kenya along with our national expert. |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor the low disbursement rate of approved funds.
ONG | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Individual | AFR | MLW | PHA | 71 | TAS | 35 | A | I |  | 0 |  | 0 |  | 2013-12-01 | 2016-04-01 | 2016-05-01 | 2017-03-01 |  |  | 30000 | 0 | 30000 | 20127.8 | 67.09% | 9872.2 | 9872.2 | 987.22 | 3900 | 0 | 2616.614 | 1283.386 | 1283.386 | Brief progress report (actual/planned):The Terms of Reference (ToR) for hiring the international consultant was prepared, cleared by the management and advertised in Feb 2016. The international consultant was recruited by UNEP to verify the national consumption in relation to the targets as set out in the Agreement between ExCom and Government of Ethiopia, following the relevant decisions of the ExCom and guidelines for the verification of national consumption targets for the multi-year agreements. The consultant prepared and presented the draft work plan which included timeline for conducting the verification as well as tasks and roles and responsibilities of each concerned stakeholders in the verification process. The consultant also informed the NOU about support/cooperation that was required from various stakeholders. The consultant also reviewed official statistics on import and export maintained by different sources and analyzed and compare those statistics. In addition, the consultant conducted the necessary on-site visits and interviews, and analyzed and cross-check various data collected from different sources. The reports was produced in English and provides detailed data demonstrating and confirming whether the consumption targets in the Agreement were achieved, whether there is existence of an operational licensing and quota system for HCFC imports and exports and whether the system is capable to ensure the country's compliance with the targets as set out in the Agreement between Malawi and the ExCom.The verification report was finalised and submitted to Ex-com 77 | The project was completed.NOU is implementing the recommendations from the verification report
ONG | UNIDO | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | AFR | MLW | PHA | 77 | INV | 40 | A | I | HCFC | 1.3 | 0 |  |  | 2016-11-01 |  | 2019-12-31 | 2019-12-31 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 10000 | 5400 | 0 | 0 | 5400 | 0 | Approved on the understanding that U NEP will report on the progress in implementing the recommendations in the verification report in the next tranche submission; and if Malawi were to decide to proceed with retrofits and associated servicing to flammable and toxic refrigerants in refrigeration and air-conditioning equipment originally designed for non-flammable substances, it would do so assuming all associated responsibilities and risks and only in accordance with the relevant standards and protocols. | Approved on the understanding that U NEP will report on the progress in implementing the recommendations in the verification report in the next tranche submission; and if Malawi were to decide to proceed with retrofits and associated servicing to flammable and toxic refrigerants in refrigeration and air-conditioning equipment originally designed for non-flammable substances, it would do so assuming all associated responsibilities and risks and only in accordance with the relevant standards and protocols. 'Milestone 1: Working arrangements agreed -List of equipment expected from NOU
ONG | UNEP | HCFC phase-out management plan (stage I, third tranche) | Multi-year | AFR | MLW | PHA | 77 | TAS | 39 | A | I |  | 0 |  | 0 |  | 2016-12-01 |  | 2018-12-01 | 2018-12-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 0 | 4000 | 5200 | 0 | 0 | 5200 | 0 | Newly approved project. | Brief progress report (actual/planned): The project was approved in Dec 2016. The licensing and quota system are in place and operational. The NOU continues to monitor imports and trade of ODS and ODS related equipment. Collection of the 2016 data on ODS imports and consumption has been completed and is being analyzed for submission. NOU commenced preparation of national legislative requirement processes in planning for ratification of Kigali amendment. ___ Legal arrangements (actual/planned): The SSFA was drafted and sent to the Government of Malawi for signature. ___Initial stages of project implementation (actual/planned): __Yes_ Intermediate goals achieved (actual/planned): _No__ Project completion and follow up: _Yes__ First disbursement date (actual/planned): __No ____. All funds disbursed (yes/no): No__ Any delay? (yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: __N/A_
FIN | UNDP | Preparation of a recovery and recycling project | Individual | AFR | MLW | REF | 17 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-10-01 | 1996-01-01 |  | 1996-06-01 | 1998-12-01 | 12500 | 0 | 12500 | 12500 | 100% | 0 | 0 | 0 | 1625 | 0 | 1625 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | AFR | MLW | REF | 19 | TAS | 05 | A | I | CFC | 7.2 | 7.2 | 0 | 0 | 1996-05-01 | 1997-03-01 | 1997-11-01 |  | 1997-12-01 | 2000-12-01 | 106320 | -311 | 106009 | 106009 | 100% | 0 | 0 | 0 | 13821.6 | -40.43 | 13781.17 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1996 |  | Investment
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | MLW | REF | 23 | PRP | 08 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1998-03-01 |  | 1998-07-01 | 2000-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | MLW | REF | 26 | TAS | 11 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2003-12-01 | 2004-05-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted
FIN | Germany | Project preparation for a refrigerant management update | RMP Update | AFR | MLW | REF | 37 | PRP | 17 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-08-01 | 2003-08-01 |  | 2004-05-01 | 2004-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | RMP approved in June 04
FIN | Germany | Implementation of the RMP update: refrigeration and air-conditioning sector | Individual | AFR | MLW | REF | 43 | TAS | 20 | A | I |  | 49 | 0 | 0 |  | 2004-07-01 | 2004-10-01 | 2007-07-01 |  | 2007-12-01 | 2009-01-01 | 100000 | -561 | 99439 | 99439 | 100% | 0 | 0 | 0 | 13000 | -73 | 12927 | 0 | 0 | Project completed. PCR was submitted in September 2008. Remaining funds will be returned to the secretariat.
FIN | UNEP | Country programme preparation | Individual | AFR | MLW | SEV | 06 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-05-01 | 1993-05-01 |  | 1994-03-01 | 1994-12-01 | 30000 | -5000 | 25000 | 25000 | 100% | 0 | 0 |  | 3900 | -650 | 3250 | 0 | 0
FIN | UNEP | Institutional strengthening, creation of an Ozone Unit | Individual | AFR | MLW | SEV | 12 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-01-01 | 1997-03-01 |  | 1998-10-01 | 1999-10-01 | 77000 | 0 | 77000 | 77000 | 100% | 0 | 0 |  | 10010 | 0 | 10010 | 0 | 0
FIN | UNDP | Project preparation assistance | Individual | AFR | MLW | SEV | 18 | PRP | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-11-01 | 1998-12-01 | 7000 | 0 | 7000 | 7000 | 100% | 0 | 0 | 0 | 910 | 0 | 910 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNEP | Request for renewal of institutional strengthening | Individual | AFR | MLW | SEV | 25 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-12-01 | 2000-06-01 |  | 2000-12-01 | 2003-12-01 | 51350 | 0 | 51350 | 51350 | 100% | 0 | 0 |  | 6676 | 0 | 6676 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening (Phase III) | Individual | AFR | MLW | SEV | 31 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2000-07-01 | 2001-10-01 | 2002-08-01 |  | 2004-01-01 | 2005-12-01 | 51300 | 0 | 51300 | 51300 | 100% | 0 | 0 |  | 6669 | 0 | 6669 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project: phase 4 | Individual | AFR | MLW | SEV | 41 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-11-01 | 2005-12-01 |  | 2005-12-01 | 2007-01-01 | 66733 | 0 | 66733 | 66733 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase V) | Individual | AFR | MLW | SEV | 47 | INS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-06-01 | 2007-12-01 |  | 2007-12-01 | 2008-01-01 | 66733 | 0 | 66733 | 66733 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase VI) | Individual | AFR | MLW | SEV | 53 | INS | 26 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-11-01 |  | 2010-12-01 | 2011-12-01 | 66733 | 0 | 66733 | 66733 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase VII) | Individual | AFR | MLW | SEV | 59 | INS | 30 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2009-12-01 | 2011-11-01 |  | 2012-12-01 | 2013-12-01 | 36147 | 30586 | 66733 | 66733 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase VIII: 4/2012-3/2014) | Individual | AFR | MLW | SEV | 66 | INS | 33 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 | 2012-12-01 | 2014-03-01 |  | 2014-12-01 | 2015-02-01 | 66733 | 0 | 66733 | 66733 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of institutional strengthening project (phase IX: 4/2014-3/2016) | Individual | AFR | MLW | SEV | 72 | INS | 36 | A | I |  | 0 |  | 0 |  | 2014-05-01 | 2015-04-01 | 2016-03-01 | 2018-03-01 |  |  | 66733 | 0 | 66733 | 51550 | 77.25% | 15183 | 15183 |  | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): _ The licensing and quota system are in place and functioning. The NOU advertised in the print media HCFC quota application for 2016 imports on 19th December 2015. The NOU organized a project steering committee meeting for HCFC quota allocation, held in Blantyre on 20th January 2016. Eleven registered companies were approved to import R22 based on their applications. The NOU trained a total of 20 customs officers in April 2016 at custom training school. These customs officers came from various border stations in the country. The training equipped the officers with skills and knowledge of identification and control of HCFCs and other ODS. The NOU conducted four enforcement compliance monitoring inspections at Dedza , Mchinji, Songwe and Mwanza border stations in June 2016. The inspections were aimed at checking whether enforcement officers were enforcing the ODS regulations. Most officers are aware of the existence of the regulations but require frequent training especially on HS coding and use of identifier. The NOU collected, processed and submitted 2015 Country Programme and Article 7 Data reports. The NOU organized four quarterly Project Steering committee meetings to review progress on implementation of project activities. The meetings were held in January, April, August and December 2016 in Lilongwe. Progress on implementation of project actives was reviewed and guidance for improvements was provided. The NOU conducted two RAC Association meetings held on 8th January 2016 and 11th September, 2016 in Mzuzu and Zomba respectively. The meetings urged the technicians to comply with ODS regulations during their operations. The NOU conducted awareness meetings to District Subcommittee on Environment (DESC) to raise awareness on phase-out of HCFCs and availability of low GWP, energy efficient and climate friendly alternatives. The meetings were conducted in Mwanza, Mzimba and Kasungu district councils. The meetings encouraged DESC members to intensify awareness on ozone issues to the local communities. The NOU commemorated the World Ozone Day on 16th September, 2016. Awareness messages inform of comedies that promote use of ODS alternatives were aired on TVs during the commemoration. The NOU Produced and distributed awareness materials on the phase-out of ODS to key stakeholders and general public. These awareness materials included T-shirts, leaflets, stickers and desk calenders. The NOU participated in all Montreal Protocol meetings organized in 2016.__ Legal arrangements (actual/planned): The SSFA was drafted and signed by UNEP and the Government of Malawi in March 2015. Initial stages of project implementation(actual/planned): Yes___ Intermediate goals achieved (actual/planned): __yes_ Project completion and follow up: No___ First disbursement date (actual/planned): _April 2015__ All funds disbursed (yes/no): _No__ Any delay?(yes/no): ___ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): No___ If Yes, is any action required by ExCom: __N/A | Brief progress report (actual/planned): The NOU continues to monitor imports and trade of ODS and ODS related equipment. Collection of the 2016 data on ODS imports and consumption has been completed and is being analyzed for submission. NOU commenced preparation of national legislative requirement processes in planning for ratification of Kigali amendment
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | AFR | MLW | SEV | 74 | TAS | 37 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-03-01 | 2016-05-01 | 2017-05-01 |  |  | 70000 | 0 | 70000 | 32.49 | 0.04641% | 69967.51 | 66887.3 | 6996.751 | 9100 | 0 | 4.2237 | 9095.7763 | 8695.349 | Brief progress report (actual/planned): The first stakeholders meeting was organized by the NOU on 4-6 May 2016 at Chikho Lodge in Kasungu. The workshop obtained support of main national stakeholders in the RAC sector and was attended by 15 participants including representatives of major importers and distributors as well as members of RAM with the main goal to agree on the plan for the Survey of ODS alternatives at the national level and obtain support of main national stakeholders. One National Consultant as hired by the NOU to support the data collection. The National Consultant assisted the NOU in the identification of the current use of ODS alternatives by substance/sector and collection of import/export data for the substances for the past a couple of years. The National Consultant also provided support in establishing growth patterns in use by substance/sector and in compiling data on available ODS alternatives for various applications. The NOU and the National Consultant drafted and cross checked the information to ensure the completion of end-user surveys, collection, analysis, and aggregation of consumption data. The various sections of the report were drafted. The second stakeholders meeting was organized by the NOU in November 2016 with the main goal to organise consultations with representatives of the government and private sector to finalize the outcomes of the Survey of ODS alternatives and discuss potential opportunities for introduction of those alternatives in the country. The draft report was prepared by the NOU and the National Consultant. It was reviewed and finalized based on the format approved by ExCom decision 75/67 as contained in document UNEP/OzL.Pro/ExCom/75/77/Rev.1 after incorporating inputs/ comments raised during National Stakeholders’ workshop. The final report has been submitted to UNEP for final review and submission to MLFS. The NOU participated in the ODS Alternative Thematic workshop held in December 2016 to refine the draft report according to the revised template for the report. The report has been finally submitted to UNEP.___ Legal arrangements(actual/planned):The SSFA was drafted and signed by UNEP and the Government of Malawi in February 2016. ____Initial stages of project implementation(actual/planned): _Yes__ Intermediate goals achieved (actual/planned): Yes___ Project completion and follow up: _No__ First disbursement date (actual/planned): _Feb 2016__ All funds disbursed (yes/no): No___ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): __N/A_ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): The NOU incorporated comments from UNEP ROA and Paris and re-submitted final ODS survey report.
ONG | UNEP | Extension of institutional strengthening project (phase X: 4/2016-3/2018) | Individual | AFR | MLW | SEV | 76 | INS | 38 | A | I |  | 0 |  | 0 |  | 2016-05-01 |  | 2018-03-01 | 2018-03-01 |  |  | 85418 | 0 | 85418 | 0 | 0% | 85418 | 0 | 8541.8 | 0 | 0 | 0 | 0 | 0 | Newly approved project. | Brief progress report (actual/planned): The project was approved in May 2016. The licensing and quota system are in place and operational. The NOU monitored enforcement of ODS regulations within the refrigeration sector. The NOU visited 7 workshops to monitor compliance to the ODS legislation by technicians. The NOU collected 2016 data on consumption of ODS in the country. The data will be submitted to the secretariat by end of March 2017 . The NOU conducted awareness campaigns on ODS phase-out process through print and electronic media. TV programmes on ODS were produced and performed ___ Legal arrangements (actual/planned): The SSFA was drafted and sent to the Government of Malawi for signature. ___Initial stages of project implementation (actual/planned): __Yes_ Intermediate goals achieved (actual/planned): _No__ Project completion and follow up: _Yes__ First disbursement date (actual/planned): __No ____. All funds disbursed (yes/no): No__ Any delay? (yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: __N/A_
FIN | UNIDO | Terminal phase-out plan for CFCs (first tranche) | Multi-Year | EUR | MOG | PHA | 53 | INV | 03 | A | I | CFC | 3 | 3 |  |  | 2007-11-01 | 2008-04-01 | 2009-03-01 |  | 2009-12-01 | 2013-10-01 | 175000 | -418 | 174582 | 174582.41 | 100% | -0.41 | 0 |  | 13125 | -31 | 13094 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | EUR | MOG | PHA | 55 | PRP | 05 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2009-04-01 | 2009-07-31 |  | 2009-12-01 | 2012-02-01 | 85000 | -767 | 84233 | 84233.23 | 100% | -0.23 | 0 |  | 6375 | -58 | 6317 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Terminal phase-out plan for CFCs (second tranche) | Multi-Year | EUR | MOG | PHA | 58 | INV | 06 | A | I | CFC | 2.2 | 2.2 |  |  | 2009-07-01 | 2009-12-01 | 2010-07-31 |  | 2013-12-01 | 2015-03-01 | 95295 | -14 | 95281 | 95281.04 | 100% | -0.04 | 0 |  | 7147 | -1 | 7146 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | EUR | MOG | PHA | 63 | INV | 08 | A | I |  | 0 | 0 |  |  | 2011-04-01 | 2011-10-01 | 2013-03-31 |  | 2013-12-01 | 2015-03-01 | 155000 | 0 | 155000 | 154999.98 | 100% | 0.02 | 0 |  | 11625 | 0 | 11625 | 0 | 0 | FIN |  |  |  | INV
COM | UNIDO | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | EUR | MOG | PHA | 71 | INV | 09 | A | I | HCFC | 0.1 | 0.1 |  |  | 2013-12-01 | 2014-01-01 | 2015-12-31 |  | 2016-12-01 |  | 100000 | 0 | 100000 | 98317.22 | 98.32% | 1682.78 | 120 | 1 | 7500 | 0 | 7374 | 126 | 9 | Brief report: Public awareness campaign/training conducted Milestones achieved: Milestone 1: Legal arrangements – Yes Milestone 2: Intermediate goals achieved – Yes Milestone 3: Public awareness campaign conducted - Yes Activities planned but not implemented: No Actions towards next goal: Further improvement and enforcement of the legislation by the NOU in cooperation with other Ministries and counterparts. Was any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any actions required by Executive Committee? No | Project completed. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | EUR | MOG | PHA | 75 | INV | 11 | A | I |  | 0 | 0 |  |  | 2015-11-01 | 2016-01-01 | 2019-12-01 | 2019-12-01 |  |  | 98500 | 0 | 98500 | 14310.71 | 14.53% | 84189.29 | 0 | 25000 | 7388 | 0 | 0 | 7388 | 0 | Brief report: Public awareness campaign conducted Milestones achieved: Milestone 1: Legal arrangements – Yes Milestone 2: Intermediate goals achieved – Yes Milestone 3: Public awareness campaign conducted - Yes Activities planned but not implemented: No Actions towards next goal: Improvement and enforcement of the legislation by the NOU in cooperation with other Ministries and counterparts. Was any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any actions required by Executive Committee? No | Brief report: The improvement and enforcement of the legislation by the NOU in cooperation with Ministries and counterparts Milestones achieved: Milestone 1: Legal arrangements – Yes Milestone 2: Intermediate goals achieved – Yes Milestone 3: Public awareness campaign conducted - Yes Activities planned but not implemented: No Actions towards next goal: Further improvement and enforcement of the legislation by the NOU in cooperation with other Ministries and counterparts. Was any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any actions required by Executive Committee? No |  |  | INV
FIN | UNIDO | Project preparation for a country programme and a terminal phase-out plan | Individual | EUR | MOG | SEV | 51 | CPG | 01 | A | I |  | 0 | 0 |  |  | 2007-03-01 | 2007-06-01 | 2008-03-01 |  | 2008-04-01 | 2009-09-01 | 40000 | -826 | 39174 | 39174.1 | 100% | -0.1 | 0 |  | 3600 | -74 | 3526 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Establishment of the ozone unit | Individual | EUR | MOG | SEV | 51 | INS | 02 | N | I |  | 0 | 0 |  |  | 2007-03-01 | 2007-10-01 | 2008-03-01 |  | 2008-12-01 | 2011-09-01 | 30000 | -8112 | 21888 | 21888.39 | 100% | -0.39 | 0 |  | 2250 | -608 | 1642 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Institutional strengthening project (Phase I) | Individual | EUR | MOG | SEV | 55 | INS | 04 | N | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-11-01 | 2010-06-30 |  | 2010-12-01 | 2013-12-01 | 60000 | -1324 | 58676 | 58676.08 | 100% | -0.08 | 0 |  | 4500 | -99 | 4401 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Institutional strengthening project (phase II) | Individual | EUR | MOG | SEV | 61 | INS | 07 | N | I |  | 0 | 0 |  |  | 2010-07-01 | 2010-12-01 | 2012-06-30 |  | 2013-12-01 | 2015-03-01 | 60000 | -1655 | 58345 | 58344.92 | 100% | 0.08 | 0 |  | 4500 | -124 | 4376 | 0 | 0 | FIN |  |  |  | NON-INV
COM | UNIDO | Survey of ODS alternatives at the national level | Individual | EUR | MOG | SEV | 74 | TAS | 10 | A | I |  | 0 | 0 |  |  | 2015-05-01 | 2016-03-01 | 2016-05-31 |  | 2016-12-01 |  | 40000 | 0 | 40000 | 33578.41 | 83.95% | 6421.59 | 6042.71 | 6000 | 3600 | 0 | 0 | 3600 | 543.8439 | Survey was carried out and the report was finalized. | The last disbursements and FIN closure are being processed. Survey was submitted in January. |  |  | NON-INV
FIN | UNDP | MDI transition strategy | Individual | EUR | MOL | ARS | 54 | TAS | 20 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2008-04-01 | 2009-08-01 | 2009-09-01 |  | 2010-12-01 | 2012-07-01 | 30000 | -18.36 | 29981.64 | 29982 | 100% | -0.36 | 0 | 0 | 2700 | -1.65 | 2698.38 | -0.03 | 0 | Financially completed in 2012. |  | 2008 |  | Non-Investment
FIN | Canada | Initiating early phase-out of methyl bromide through awareness raising, policy development and demonstration/training activities | Individual | EUR | MOL | FUM | 30 | TAS | 06 | A | I |  | 0 |  | 0 |  | 2000-03-01 | 2001-04-01 | 2002-03-01 |  | 2004-04-01 | 2004-04-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed in April 2004. PCR submitted |  | 2000 |  | Non-Inv.
FIN | UNIDO | Training and awareness workshop in the fumigants sector (methyl bromide) | Individual | EUR | MOL | FUM | 45 | TAS | 13 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2006-05-01 | 2006-04-01 |  | 2006-12-01 | 2009-04-01 | 30000 | -1838 | 28162 | 28161.61 | 100% | 0.39 | 0 |  | 2700 | -165 | 2535 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | EUR | MOL | PHA | 48 | PRP | 15 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2006-11-01 | 2007-04-01 |  | 2007-12-01 | 2011-11-01 | 12000 | -2380.8 | 9619.2 | 9619 | 100% | 0.2 | 0 | 0 | 900 | -178.56 | 721.425 | 0.015 | 0 | Completed in 2007. |  | 2006 |  | Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | EUR | MOL | PHA | 48 | PRP | 16 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2008-02-01 | 2007-04-01 |  | 2008-04-01 | 2010-12-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 |  | 2340 | 0 | 2340 | 0 | 0
FIN | UNDP | Terminal CFC phase-out management plan (first tranche) | Multi-Year | EUR | MOL | PHA | 52 | INV | 18 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-10-01 | 2009-07-01 |  | 2008-11-01 | 2013-01-01 | 152500 | 0 | 152500 | 152500 | 100% | 0 | 0 | 0 | 11438 | 0 | 11438 | 0 | 0 | Financially completed in 2013. |  | 2007 |  | Investment
FIN | UNEP | Terminal CFC phase-out management plan (first tranche) | Multi-year | EUR | MOL | PHA | 52 | TAS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-02-01 | 2008-07-01 |  | 2009-12-01 | 2010-12-01 | 74500 | 0 | 74500 | 74500 | 100% | 0 | 0 |  | 9685 | 0 | 9685 | 0 | 0
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | EUR | MOL | PHA | 55 | PRP | 21 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2010-12-01 | 2012-07-01 | 85000 | -3117.49 | 81882.51 | 81883 | 100% | -0.49 | 0 | 0 | 6375 | -233.81 | 6141.2249 | -0.03495 | 0 | Financially completed in 2012. |  | 2008 |  | Investment
FIN | UNDP | Terminal CFC phase-out management plan (second tranche) | Multi-Year | EUR | MOL | PHA | 56 | INV | 23 | N | I | CFC | 10 | 10 | 0 | 0 | 2008-11-01 | 2009-10-01 | 2009-11-01 |  | 2010-12-01 | 2012-07-01 | 152500 | -159.02 | 152340.98 | 152341 | 100% | -0.02 | 0 | 0 | 11438 | -11.93 | 11426.0745 | -0.0045001 | 0 | Financially completed in 2012. |  | 2008 |  | Investment
FIN | UNEP | Terminal CFC phase-out management plan (second tranche) | Multi-Year | EUR | MOL | PHA | 56 | TAS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-05-01 | 2009-11-01 |  | 2010-06-01 | 2000-06-01 | 140500 | 0 | 140500 | 140500 | 100% | 0 | 0 |  | 18265 | 0 | 18265 | 0 | 0
COM | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | EUR | MOL | PHA | 63 | INV | 25 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-08-01 | 2014-12-01 |  | 2015-11-01 |  | 79200 | 0 | 79200 | 78252 | 98.8% | 948 | 0 | 805.8 | 7128 | 0 | 7042.68 | 85.32 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2015. |  | 2011 |  | Investment
FIN | UNEP | Preparation of a HCFC phase-out management plan (stage II) | Individual | EUR | MOL | PHA | 72 | PRP | 27 | A | I |  | 0 |  | 0 |  | 2014-05-01 | 2015-03-01 | 2015-05-01 |  | 2016-11-01 | 2016-11-01 | 10000 | 0 | 10000 | 6000 | 60% | 4000 | 0 |  | 1300 | 0 | 780 | 520 | 0 | Brief progress report (actual/planned): The lead agency UNDP and National Ozone Unit agreed to submit Moldova HPMP stage II and its tranche 1 to ExCom 77 in November 2016 when HPMP stage I is expected to be near to completion. A final review of the proposal is scheduled for June / July 2016 to allow early submission. Legal arrangements (actual/planned): SSA with a national consultant was signed in November of 2014. Initial stages of project implementation (actual/planned): N.a. Intermediate goals achieved (actual/planned): N.a. Project completion and follow up: November 2016 TOR completed (actual/planned): Yes - TOR for national consultant. First Disbursement date (actual/planned): March 2015 All funds disbursed (yes/no): No Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolved: Lead agency and National Ozone Unit agreed to submit the proposal to ExCom 77 in November 2016 when HPMP stage I is expected to be near to completion. If Yes, will delay have impact on project completion date (yes/no): Yes Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N.a. | Project financially completed. Balance to be returned USD 4,000.
ONG | UNDP | Preparation of a HCFC phase-out management plan (stage II) | Individual | EUR | MOL | PHA | 72 | PRP | 29 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 | 2015-02-01 | 2016-05-01 | 2017-03-01 |  |  | 20000 | 0 | 20000 | 19834 | 99.17% | 166 | 0 | 66.4 | 1400 | 0 | 1388.38 | 11.62 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Project team was recruited to enable formulation of HPMP-II documentation. Required data collection processed and stakeholder workshops held to discuss HCFC control policies and HPMP-II design. HPMP-II was prepared, submitted and approved at the 77th ExCom. Prodoc signed (actual/planned, yes/no and date):1/1. Yes. Agreement signed earlier Missions undertaken (actual/planned):1/1: Mission fielded to support HPMP-II discussion with stakeholders and design of components. TOR for consultants/subcontracts completed (actual/planned): 4/4: Four national experts recruited to assist with HPMP-II formulation Contract/PO/MOA agreements signed: 0/0: No procurement was expected in PRP stage First disbursement date (actual/planned): 42036Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | No any activities in this period due closure of the project. |  |  | Investment
ONG | UNDP | Verification report for stage I of HCFC phase-out management plan | Individual | EUR | MOL | PHA | 73 | TAS | 30 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-11-01 | 2015-04-01 | 2016-11-01 | 2017-11-01 |  |  | 30000 | 0 | 30000 | 21238 | 70.79% | 8762 | 0 | 3504.8 | 2700 | 0 | 1911.42 | 788.58 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Independent verifier was recruited earlier and locally. Verification report was completed, discussed with stakeholders and submitted to the MLF Secretariat. Prodoc signed (actual/planned, yes/no and date):1/1. Yes. Agreement has been signed earlier Missions undertaken (actual/planned):1/1: One mission fielded TOR for consultants/subcontracts completed (actual/planned): 1/1: TOR for national verifier was drafted and announced Contract/PO/MOA agreements signed: 0/0: No procurement required in the verification process First disbursement date (actual/planned): 42095Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | No any activities in this period due closure of the project. | 2014 |  | Non-Investment
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | EUR | MOL | PHA | 74 | INV | 31 | N | I | HCFC | 0 | 0 | 0 | 0 | 2015-05-01 | 2016-01-01 | 2017-05-01 | 2017-05-01 |  |  | 8800 | 0 | 8800 | 8649.29 | 98.29% | 150.71 | 0 | 60.284 | 792 | 0 | 778.4361 | 13.5639 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): One workshop was held for 25 Ecological Inspectors with specific training on HCFC policies and control measures; Three workshops -arranged for 60 RAC technicians who were trained and certified in line with updated national technician certification system; In terms of awareness raising a technical guide on HCFC refrigerant alternatives was printed in 300 issues. Prodoc signed (actual/planned, yes/no and date):1/1. Yes. Agreement signed earlier Missions undertaken (actual/planned):1/1: One mission fielded to assist with required awareness raising on HCFC control measures and implementation of HPMP-I programme TOR for consultants/subcontracts completed (actual/planned): 1/1: One national expert was recruited earlier to assist with HPMP-I implementation Contract/PO/MOA agreements signed: 0/0: No procurement of R&R tools and equipment was planned in 2016 workplan. First disbursement date (actual/planned): 42370Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:Release of the 2nd tranche was conditioned by the availability of verification report. Verification report was submitted in the second half of 2015 and eventually accepted in November 2015. DOA sent in December 2015. | Due to almost complete disbursement of funds in 2016, no more activities planned in this period. The project is set for operational closure. | 2015 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage II, first tranche) | Multi-year | EUR | MOL | PHA | 77 | INV | 34 | N | I | HCFC | 0.2 | 0 | 0 | 0 | 2016-12-01 |  | 2019-12-01 | 2017-12-01 |  |  | 104850 | 0 | 104850 | 0 | 0% | 104850 | 0 | 41940 | 9437 | 0 | 0 | 9437 | 0 | Newly Approved | Once funds from the fund were received, DOA was prepared and sent to UNDP and NOU-Moldova in February 2017. UNDP Project document drafted, along with 2017 workplan, and submitted for signature with the Government. Signature expected in April/May 2017 to allow to start with implementation of workplans, TORs etc. | 2016 |  | Investment
ONG | UNEP | HCFC phase-out management plan (stage II, first tranche) | Multi-Year | EUR | MOL | PHA | 77 | TAS | 35 | A | I |  | 0 |  | 0 |  | 2016-12-01 |  | 2018-12-01 | 2018-12-01 |  |  | 26100 | 0 | 26100 | 0 | 0% | 26100 | 0 | 2610 | 3393 | 0 | 0 | 3393 | 0 | Project newly approved by ExCom 77. | Brief progress report (actual/planned): Project newly approved by ExCom 77. Legal arrangements (actual/planned): SSFA with the Ministry of Environment submitted for internal clearance and signature in January 2017. First mission (actual/planned): N.a. TOR completed (actual/planned): N.a. First disbursement date (actual/planned): Pending All funds disbursed (yes/no): No Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: The time required for the transfer and programming of project funds and the release of payments. If Yes, will delay have impact on project completion date (yes/no): No Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N.a.
FIN | UNDP | Implementation of the RMP: National programme for recovery and recycling of refrigerants | RMP-Component | EUR | MOL | REF | 25 | TAS | 02 | A | I | CFC | 21.9 | 21.9 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 2002-05-01 | 2002-11-01 | 254150 | -304 | 253846 | 253846 | 100% | 0 | 0 | 0 | 33039.5 | -39.52 | 32999.98 | 0 | 0 | Completed in 2002. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNEP | Implementation of the RMP: train the trainers programme for good practices in the refrigeration sector | Individual | EUR | MOL | REF | 25 | TRA | 03 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-09-01 | 1999-08-01 |  | 2003-12-01 | 2005-12-01 | 66000 | -11000 | 55000 | 55000 | 100% | 0 | 0 |  | 8580 | -1430 | 7150 | 0 | 0 |  |  |  | 2001-06-01
FIN | UNEP | Implementation of the RMP: training on monitoring and control of CFC and CFC using equipment | Individual | EUR | MOL | REF | 25 | TRA | 04 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 2001-06-01 | 1999-08-01 |  | 2004-12-01 | 2008-01-01 | 66550 | -7349 | 59201 | 59201 | 100% | 0 | 0 |  | 8652 | -955 | 7697 | 0 | 0 |  |  |  | 2002-01-01
FIN | UNDP | Project preparation for the RMP proposal | RMP-Component | EUR | MOL | REF | 41 | PRP | 08 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-07-01 | 2004-12-01 |  | 2004-12-01 | 2005-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 1875 | 0 | 1875 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2003 |  | Investment
FIN | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | EUR | MOL | REF | 44 | TAS | 11 | A | I | CFC | 6.4 | 6.4 | 0 | 0 | 2004-12-01 | 2005-04-01 | 2006-12-01 |  | 2007-04-01 | 2010-12-01 | 19885 | -4233.91 | 15651.09 | 15651.09 | 100% | 0 | 0 |  | 2585 | -550.41 | 2034.59 | 0 | 0
FIN | UNDP | Implementation of the RMP: technical assistance programme | RMP-Component | EUR | MOL | REF | 44 | TAS | 12 | N | I | CFC | 55.9 | 55.9 | 0 | 0 | 2004-12-01 | 2005-02-01 | 2006-12-01 |  | 2007-12-01 | 2009-07-01 | 173495 | -3 | 173492 | 173492 | 100% | 0 | 0 | 0 | 15615 | -0.27 | 15614.73 | 0 | 0 | Completed in 2007.Financially completed in 2009. |  | 2004 |  | Investment
FIN | UNEP | Country programme | Individual | EUR | MOL | SEV | 25 | CPG | 05 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 |  | 1998-07-01 |  | 1998-07-01 | 1998-07-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 |  | 0
FIN | UNEP | Establishment of a National Ozone Unit | Individual | EUR | MOL | SEV | 25 | INS | 01 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2001-07-01 |  | 2002-07-01 | 2004-05-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening projects (Phase II) | Individual | EUR | MOL | SEV | 36 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2004-01-01 | 2004-04-01 |  | 2004-07-01 | 2007-06-01 | 69334 | 0 | 69334 | 69334 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (phase III) | Individual | EUR | MOL | SEV | 43 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2005-02-01 | 2006-07-01 |  | 2006-03-01 | 2007-03-01 | 69334 | 0 | 69334 | 69334 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | EUR | MOL | SEV | 48 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2006-07-01 | 2008-04-01 |  | 2008-04-01 | 2009-04-01 | 69334 | 0 | 69334 | 69334 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | EUR | MOL | SEV | 54 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-08-01 | 2010-07-01 |  | 2011-12-01 | 2011-12-01 | 69334 | 0 | 69334 | 69334 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VI) | Individual | EUR | MOL | SEV | 61 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-02-01 | 2012-06-01 |  | 2012-12-01 | 2013-12-01 | 69334 | 0 | 69334 | 69334 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VII: 7/2012-6/2014) | Individual | EUR | MOL | SEV | 67 | INS | 26 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2012-09-01 | 2014-06-01 |  | 2015-08-01 | 2016-03-01 | 69334 | 0 | 69334 | 69334 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
ONG | UNEP | Extension of the institutional strengthening project (phase VIII: 7/2014-6/2016) | Individual | EUR | MOL | SEV | 72 | INS | 28 | A | I |  | 0 |  | 0 |  | 2014-05-01 | 2014-11-01 | 2016-06-01 | 2017-03-01 |  |  | 69334 | 0 | 69334 | 27651.69 | 39.88% | 41682.31 | 22625 | 4168.231 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): National Steering Committee meeting in January 2016, workshop on technologies and safety standards for alternative refrigerants in Chisinau in January 2016 (as part of HPMP), national HCFC phase-out plan for the period 2016-2040 approved by Government on 13 July 2016, legal documentation of the training and certification system for RAC technicians developed, mandatory log-books for RAC equipment introduced, training manual for RAC technicians and code of good practice in RAC sector up-dated, cooperation the Technical University and the national RAC association, customs codes adjusted to facilitate monitoring of ODS trade, training materials for customs officers up-dated, customs data collected on a quarterly basis, 60 RAC technicians trained and certificated, 25 ecological inspectors trained, reporting of Country Programme and Article 7 data for 2015 as per schedule, monitoring trade in ODS through the licensing system, quota allocation and iPIC, outreach of information and awareness raising through TV, radio, newspapers, up-dated website, IOD celebrations, participation in ECA customs cooperation and network meeting in Ashgabat, 24-27 May 2016, hosting the ECA thematic meeting on HPMP implementation and ODS alternatives surveys in Chisinau, 11-13 October 2016, coordinating and reporting on Montreal Protocol projects (HPMP stage I tranches, survey on ODS alternatives), and preparing HPMP stage II and IS phase 9 projects (both approved by ExCom 77). Legal arrangements (actual/planned): SSFA with the Ministry of Environment signed by both parties in November 2014 and amended in February 2016 to extend its validity to July 2017. Initial stages of project implementation (actual/planned): N.a. Intermediate goals achieved (actual/planned): N.a. Project completion and follow up: N.a. First disbursement date (actual/planned): November 2014 All funds disbursed (yes/no): No Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: Clarification of expenditures with UNDP Moldova as well as complex approval procedures and slow disbursement delayed the second payment creating major problems for the NOU Moldova. The second payment was finally released in March 2016. If Yes, will delay have impact on project completion date (yes/no): Yes Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N.a. | Brief progress report (actual/planned): NOU Moldova coordinated the ODS alternatives survey (with UNDP as implementing agency) and submitted the final report to the MFS in February 2017. Legal arrangements (actual/planned): SSFA with the Ministry of Environment signed by both parties in November 2014 and amended in February 2016 to extend its validity to July 2017. Initial stages of project implementation (actual/planned): N.a. Intermediate goals achieved (actual/planned): N.a. Project completion and follow up: N.a. First disbursement date (actual/planned): November 2014 All funds disbursed (yes/no): No Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: Clarification of expenditures with UNDP Moldova as well as complex approval procedures and slow disbursement delayed the second payment creating major problems for the NOU Moldova. The second payment was finally released in March 2016. If Yes, will delay have impact on project completion date (yes/no): Yes Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N.a.
TRF | UNEP | Survey of ODS alternatives at the national level | Individual | EUR | MOL | SEV | 74 | TAS | 32 | A | I |  | 0 |  | 0 |  | 2015-05-01 |  | 2015-11-01 |  |  | 2015-11-01 | 20000 | -20000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 2600 | -2600 |  | 0
ONG | UNDP | Survey of ODS alternatives at the national level | Individual | EUR | MOL | SEV | 75 | TAS | 33 | N | I | HCFC | 0 | 0 | 0 | 0 | 2015-11-01 | 2016-04-01 | 2016-05-01 | 2017-03-01 |  |  | 20000 | 0 | 20000 | 19362.31 | 96.81% | 637.69 | 0 | 255.076 | 1800 | 0 | 1742.6079 | 57.3921 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Project team was set up (4 consultants by sectors, and 1 international expert). Data collected and analysed. ODS alternative survey report drafted and presented in one workshop to stakeholders to validate data. Prodoc signed (actual/planned, yes/no and date):1/1. Yes. Agreement signed earlier Missions undertaken (actual/planned):1/1: One mission fielded to support work of NOU and consultants. TOR for consultants/subcontracts completed (actual/planned): 5/5: 4 national and 1 international experts recruited Contract/PO/MOA agreements signed: 0/0: No procurement plans were in place in this data collection project First disbursement date (actual/planned): 42461Any delays/problems (yes/no): If Yes, reasons for delay & action plan to resolve: | - | 2015 |  | Non-Investment
ONG | UNEP | Extension of the institutional strengthening project (phase IX: 1/2017-12/2018) | Individual | EUR | MOL | SEV | 77 | INS | 36 | A | I |  | 0 |  | 0 |  | 2016-12-01 |  | 2018-12-01 | 2018-12-01 |  |  | 88748 | 0 | 88748 | 0 | 0% | 88748 | 0 | 8874.8 | 0 | 0 | 0 | 0 | 0 | Project newly approved by ExCom 77. | Brief progress report (actual/planned): Project newly approved by ExCom 77. Legal arrangements (actual/planned): SSFA with the Ministry of Environment submitted for internal clearance and signature in January 2017. Initial stages of project implementation (actual/planned): N.a. Intermediate goals achieved (actual/planned): N.a. Project completion and follow up: N.a. First disbursement date (actual/planned): Pending All funds disbursed (yes/no): No Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: The time required for the transfer and programming of project funds and the release of payments. If Yes, will delay have impact on project completion date (yes/no): No Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N.a.
FIN | Japan | Preparation for HCFC phase-out investment activities (XPS foam manufacturing sector) |  | ASP | MON | FOA | 60 | PRP | 16 | A | I | HCFC | 0 |  | 0 |  | 2010-04-01 | 2010-11-01 | 2011-04-01 |  | 2011-04-01 | 2011-04-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0
FIN | Japan | Preparation of a terminal phase-out management plan | Individual | ASP | MON | PHA | 45 | PRP | 09 | A | I |  | 0 |  | 0 |  | 2005-04-01 | 2005-08-01 | 2006-04-01 |  | 2005-10-01 | 2006-04-01 | 33900 | 0 | 33900 | 33900 | 100% | 0 | 0 | 0 | 4407 | 0 | 4407 | 0 | 0 | The prpposal document was developed and submitted.
FIN | Japan | Terminal phase-out management plan: first tranche | Multi-Year | ASP | MON | PHA | 47 | INV | 10 | N | I | CFC | 1.8 | 1.8 | 0 |  | 2005-11-01 | 2006-07-01 | 2007-12-01 |  | 2010-09-01 | 2011-01-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 | 0 | 19500 | 0 | 19500 | 0 | 0 | Financial completion in Jan 2011.
FIN | Japan | Terminal phase-out management plan (second tranche) | Multi-Year | ASP | MON | PHA | 53 | INV | 12 | A | I | CFC | 1.5 | 1.5 | 0 |  | 2007-11-01 | 2009-11-01 | 2009-11-01 |  | 2010-12-01 | 2011-01-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 | 0 | 7150 | 0 | 7150 | 0 | 0 | Financial completion in Jan 2011.
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | MON | PHA | 55 | PRP | 14 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-11-01 | 2009-07-01 |  | 2011-03-01 | 2011-08-01 | 85000 | -13023 | 71977 | 71977 | 100% | 0 | 0 |  | 11050 | -1692.99 | 9357.01 | 0 | 0
COM | Japan | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | MON | PHA | 63 | INV | 18 | A | I | HCFC-22 | 0.5 | 0.5 | 0 |  | 2011-04-01 | 2012-08-01 | 2013-03-01 |  | 2016-12-01 |  | 130000 | 0 | 130000 | 130000 | 100% | 0 | 0 | 0 | 16900 | 0 | 16900 | 0 | 0 | The inspection and verification has been done in 15 September 2016, then finalised the verification report and closed the project. | PCR will be submitted by the end of 2017.
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | MON | PHA | 63 | TAS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-10-01 | 2013-03-01 |  | 2013-12-01 | 2014-12-01 | 65000 | 0 | 65000 | 65000 | 100% | 0 | 0 |  | 8450 | 0 | 8450 | 0 | 0
COM | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Individual | ASP | MON | PHA | 71 | TAS | 21 | A | I |  | 0 |  | 0 |  | 2013-12-01 | 2015-04-01 | 2016-11-01 |  | 2016-10-01 |  | 30000 | 0 | 30000 | 29258.76 | 97.53% | 741.24 | 0 | 741 | 3900 | 0 | 3803.6388 | 96.3612 | 0 | Project completed | Project completed
COM | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | ASP | MON | PHA | 71 | TAS | 22 | A | I |  | 0.1 |  | 0 |  | 2013-12-01 | 2014-06-01 | 2016-12-01 |  | 2016-12-01 |  | 65000 | 0 | 65000 | 55000 | 84.62% | 10000 | 8727.35 | 10000 | 8450 | 0 | 7150 | 1300 | 1134.5555 | Brief progress report (actual/planned): ANnual quota distributed. Ipic system updated. Initial setup for online licensing system. Updated University curriculum on Standards for Refrigerants. Awareness raising activities. Legal arrangement (actual/ planned): SSFA completed- First mission (actual/planned): ______ TOR completed (actual/planned): First disbursement date (actual/planned): Yes All funds disbursed (yes/no): Yes Any delay? (yes/no): ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___ | Project is completed
ONG | UNEP | HCFC phase-out management plan (stage I, third tranche) | Multi-year | ASP | MON | PHA | 77 | TAS | 25 | A | I |  | 0.4 |  | 0 |  | 2016-12-01 |  | 2019-12-01 | 2019-12-01 |  |  | 69000 | 0 | 69000 | 0 | 0% | 69000 | 0 | 6900 | 8970 | 0 | 0 | 8970 | 0 | Newly approved project | Brief progress report (actual/planned): SSFA agreed with the country. One stakeholder workshop planned on national certification system for RAC technicians for June 2017. Legal arrangements(actual/planned): SSFA being signed by UNEP First mission (actual/planned): planned for June 2017 TOR completed(actual/planned): ___ First disbursement date (actual/planned): ___ All funds disbursed (yes/no): ___ Any delay? (yes/no): ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___
FIN | UNEP | Implementation of the RMP: train the trainer programme for refrigeration service technicians | Individual | ASP | MON | REF | 32 | TRA | 03 | A | I | CFC | 2.4 | 2.4 | 0 | 0 | 2000-12-01 | 2001-04-01 | 2002-01-01 |  | 2003-10-01 | 2005-01-01 | 65970 | -15423 | 50547 | 50547 | 100% | 0 | 0 |  | 8576 | -2003.95 | 6572.05 | 0 | 0
FIN | UNEP | Implementation of the RMP: training of custom officers, ODS inspectorate and NOU staff | Individual | ASP | MON | REF | 32 | TRA | 04 | A | I | CFC | 2.8 | 2.8 | 0 | 0 | 2000-12-01 | 2001-04-01 | 2002-01-01 |  | 2003-06-01 | 2003-06-01 | 77200 | -15003 | 62197 | 62197 | 100% | 0 | 0 |  | 10036 | -1950.39 | 8085.61 | 0 | 0
FIN | UNDP | Preparation of a refrigerant recycling project | Individual | ASP | MON | REF | 33 | PRP | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Implementation of the RMP: recovery and recycling of CFC-12 refrigerant | RMP-Component | ASP | MON | REF | 35 | TAS | 06 | A | I | CFC | 3.9 | 3.9 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-01-01 |  | 2004-12-01 | 2005-11-01 | 108600 | 0 | 108600 | 108600 | 100% | 0 | 0 | 0 | 14118 | 0 | 14118 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNEP | Country programme formulation | Individual | ASP | MON | SEV | 20 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1996-12-01 | 1997-11-01 |  | 1999-05-01 | 1999-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0 |  |  |  | 1999-05-01
FIN | UNEP | Establishment of the Ozone Unit | Individual | ASP | MON | SEV | 28 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 1999-12-01 | 2002-08-01 |  | 2002-08-01 | 2003-09-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 |  | 8580 | 0 | 8580 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (Phase II) | Individual | ASP | MON | SEV | 36 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-10-01 | 2004-04-01 |  | 2004-04-01 | 2004-12-01 | 57200 | 0 | 57200 | 57200 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (phase III) | Individual | ASP | MON | SEV | 43 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-10-01 | 2006-07-01 |  | 2006-07-01 | 2007-07-01 | 57200 | -2 | 57198 | 57198 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (phase IV) | Individual | ASP | MON | SEV | 50 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2008-11-01 |  | 2008-06-01 | 2008-06-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (phase V) | Individual | ASP | MON | SEV | 55 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-11-01 | 2010-12-01 |  | 2010-12-01 | 2011-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (phase VI) | Individual | ASP | MON | SEV | 60 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-09-01 | 2011-12-01 |  | 2011-12-01 | 2012-12-01 | 42500 | 0 | 42500 | 42500 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (phase VII: 1/2012-12/2013) | Individual | ASP | MON | SEV | 64 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2011-12-01 | 2013-12-01 |  | 2013-12-01 | 2014-03-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (phase VIII: 1/2014-12/2015) | Individual | ASP | MON | SEV | 70 | INS | 20 | A | I |  | 0 |  | 0 |  | 2013-07-01 | 2014-03-01 | 2015-12-01 |  | 2015-12-01 | 2016-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed | Project financially completed
ONG | UNEP | Renewal of the institutional strengthening project (phase IX: 1/2016-12/2017) | Individual | ASP | MON | SEV | 74 | INS | 23 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-04-01 | 2017-12-01 | 2017-12-01 |  |  | 60000 | 0 | 60000 | 32597 | 54.33% | 27403 | 27403 | 2740.3 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Quota distibution approved. Customs capacity buidling, technicians training ongoing, awareness raising activities Legal arrangement (actual/planned): SSFA in place Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date(actual/planned): actual Apr 2016 All funds disbursed (yes/no): No Any delay?(yes/no): ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): CA and A7 data being prepared. Kigali Amendment translated and consultation for its ratifcation intiated. Legal arrangement (actual/planned): SSFA in place Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date(actual/planned): actual Apr 2016 All funds disbursed (yes/no): No Any delay?(yes/no): ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | ASP | MON | SEV | 74 | TAS | 24 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-05-01 | 2016-05-01 | 2017-06-01 |  |  | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Brief progress report( actual/planned): ToR developed and consultant recruited. Survey conducted. Stakeholder consultations meetings held, one during the mission by UNEP in Oct 2016. Full draft of the survey report submitted for review by UNEP. Legal arrangements(actual/planned): SSFA in place Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date(actual/planned): actual May 2016 All funds disbursed (yes/no): No Any delay?(yes/no): If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___ | Brief progress report( actual/planned): Comments on the first draft sent by UNEP Feb 2017. Comments are currently being incorporated into the final draft of the survey report. Legal arrangements(actual/planned): SSFA in place Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date(actual/planned): actual May 2016 All funds disbursed (yes/no): No Any delay?(yes/no): If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___
FIN | UNIDO | Preparation of investment project in the aerosol sector | Individual | AFR | MOR | ARS | 27 | PRP | 31 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-10-01 | 1999-12-01 |  | 2000-12-01 | 2001-09-01 | 20000 | -7939 | 12061 | 12061.37 | 100% | -0.37 | 0 |  | 2600 | -1035 | 1566 | -1 | 0 | FIN
FIN | UNDP | Phase out of CFCs in the manufacture of integral skin and cold cured molded PUF products at Maghreb Elastoplast | Individual | AFR | MOR | FOA | 20 | INV | 04 | A | D | CFC | 13 | 13 | 0 | 0 | 1996-10-01 | 1997-09-01 | 1998-09-01 |  | 1997-09-01 | 2000-07-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 | 0 | 0 | 15600 | -0.43 | 15599.57 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | AFR | MOR | FOA | 21 | PRP | 06 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-05-01 | 2002-03-01 | 80000 | -13195 | 66805 | 66805 | 100% | 0 | 0 | 0 | 10400 | -1715 | 8685 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1997 |  | Investment
CLO | UNDP | Phase out of CFC in the manufacture of flexible foam (slabstock) at Richbond S.A. | Individual | AFR | MOR | FOA | 22 | INV | 08 | A | I | CFC | 150 | 150 | 0 | 0 | 1997-05-01 | 1998-04-01 | 1999-06-01 |  |  | 2004-12-01 | 470625 | -40035.82 | 430589.18 | 430589 | 100% | 0.18 | 0 | 0 | 61181.25 | -5204.64 | 55976.5913 | 0.0187 | 0 | Canceled in 2004. Financially completed in 2004. |  | 1997 |  | Investment
CLO | UNDP | Phase out of CFC in the manufacture of flexible foam (slabstock) at Dolidol | Individual | AFR | MOR | FOA | 22 | INV | 10 | A | I | CFC | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-02-01 | 1999-06-01 |  |  | 2003-12-01 | 475822 | -61553 | 414269 | 414269 | 100% | 0 | 0 | 0 | 61856.86 | -8002 | 53854.86 | 0 | 0 | Canceled in 2001. Financially completed in 2003. |  | 1997 |  | Investment
CLO | UNDP | Phase out of CFC in the manufacture of flexible foam (slabstock) at Sodiflex and Tiznit Plastic S.A. | Individual | AFR | MOR | FOA | 23 | INV | 12 | A | I | CFC | 85 | 85 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  |  | 2005-09-01 | 517300 | -5023 | 512277 | 512277 | 100% | 0 | 0 | 0 | 67249 | -652.99 | 66596.01 | 0 | 0 | Canceled in 2004. Financially completed in 2005. |  | 1997 |  | Investment
CLO | UNDP | Phase out of CFC in the manufacture fo flexible foam (slabstock) at Salidor S.A. | Individual | AFR | MOR | FOA | 23 | INV | 13 | A | I | CFC | 48 | 48 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  |  | 2004-12-01 | 299000 | 0 | 299000 | 299000 | 100% | 0 | 0 | 0 | 38870 | 0 | 38870 | 0 | 0 | Canceled in 2004. Financially completed in 2004. |  | 1997 |  | Investment
FIN | UNDP | Phase out of CFC in the manufacture of flexible foam (slabstock) at Richdor S.A. | Individual | AFR | MOR | FOA | 23 | INV | 14 | A | I | CFC | 10 | 10 | 0 | 0 | 1997-11-01 | 2000-06-01 | 1999-12-01 |  | 2000-08-01 | 2004-01-01 | 62300 | 0 | 62300 | 62300 | 100% | 0 | 0 | 0 | 8099 | 0 | 8099 | 0 | 0 | Completed in 2000. Financially completed in 2004. |  | 1997 |  | Investment
FIN | UNDP | Phase out of CFC in the manufacture of rigid foam at Panaf Isolation S.A. | Individual | AFR | MOR | FOA | 23 | INV | 15 | A | I | CFC | 17.5 | 17.5 | 0 | 0 | 1997-11-01 | 1999-06-01 | 1999-12-01 |  | 1999-09-01 | 2001-12-01 | 137000 | -3191 | 133809 | 133809 | 100% | 0 | 0 | 0 | 17810 | -415 | 17395 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Phase out of CFC in the manufacture of flexible foam (slabstock) at Molen Industrie S.A. | Individual | AFR | MOR | FOA | 23 | INV | 16 | A | I | CFC | 9 | 9 | 0 | 0 | 1997-11-01 | 2000-12-01 | 1999-12-01 |  | 2002-06-01 | 2003-11-01 | 56070 | 0 | 56070 | 56070 | 100% | 0 | 0 | 0 | 7289.1 | 0 | 7289.1 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1997 |  | Investment
CLO | UNDP | Phase out of CFC in the manufacture of flexible foam (slabstock) at Mousse d'Or S.A. | Individual | AFR | MOR | FOA | 23 | INV | 19 | A | I | CFC | 45 | 45 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  |  | 2004-12-01 | 280350 | 0 | 280350 | 280350 | 100% | 0 | 0 | 0 | 36445.5 | 0 | 36445.5 | 0 | 0 | Canceled in 2004. Financially completed in 2004. |  | 1997 |  | Investment
FIN | UNDP | Project preparation for 2 projects in the foam sector | Individual | AFR | MOR | FOA | 24 | PRP | 21 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1998 |  | Investment
CLO | UNDP | Conversion to LCD technology in the manufacture of flexible foam (slabstock) to replace CFC-11 at Bonbino Confort | Individual | AFR | MOR | FOA | 25 | INV | 22 | A | I | CFC | 90 | 90 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  |  | 2004-12-01 | 490200 | 0 | 490200 | 490200 | 100% | 0 | 0 | 0 | 63726 | 0 | 63726 | 0 | 0 | Canceled in 2004. Financially completed in 2004. |  | 1998 |  | Investment
FIN | UNDP | Conversion to HCFC-141b/water technology in the manufacture of rigid polyurethane spray foam at Batcomar S.A. | Individual | AFR | MOR | FOA | 25 | INV | 23 | A | I | CFC | 9.2 | 9.2 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 1999-07-01 | 2002-03-01 | 72000 | -10826 | 61174 | 61174 | 100% | 0 | 0 | 0 | 9360 | -1407.38 | 7952.62 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam at Interfer by conversion to a combination of water and HCFC-141b based systems | Individual | AFR | MOR | FOA | 32 | INV | 43 | A | I | CFC | 10.1 | 10.1 | 0 | 0 | 2000-12-01 | 2002-03-01 | 2004-01-01 |  | 2003-06-01 | 2004-01-01 | 78973 | 0 | 78973 | 78973 | 100% | 0 | 0 | 0 | 10266.49 | 0 | 10266.49 | 0 | 0 | Completed in 2003. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam at Engequife by conversion to a combination of water and HCFC-141b based systems | Individual | AFR | MOR | FOA | 32 | INV | 44 | A | I | CFC | 7.2 | 7.2 | 0 | 0 | 2000-12-01 | 2001-09-01 | 2004-01-01 |  | 2003-06-01 | 2004-01-01 | 56391 | -146.41 | 56244.59 | 56245 | 100% | -0.41 | 0 | 0 | 7330.83 | -19.03 | 7311.8496 | -0.0496 | 0 | Completed in 2003. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNIDO | Preparation for HCFC phase-out investment activities (foam sector) | Individual | AFR | MOR | FOA | 60 | PRP | 64 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-07-01 | 2011-04-30 |  | 2010-12-01 | 2011-04-01 | 60000 | -65 | 59935 | 59934.64 | 100% | 0.36 | 0 |  | 4500 | -5 | 4495 | 0 | 0 | FIN
FIN | UNIDO | Conversion from HCFC-141b in the manufacture of polyurethane rigid insulation foam for domestic refrigerators at Manar | Multi-Year | AFR | MOR | FOA | 62 | INV | 67 | A | I | HCFC | 11 | 11 |  |  | 2010-12-01 | 2010-12-01 | 2012-12-31 |  | 2013-12-01 | 2015-03-01 | 951740 | -2581 | 949159 | 949159.41 | 100% | -0.41 | 0 |  | 71381 | -194 | 71187 | 0 | 0 | FIN |  |  |  | INV
ONG | UNIDO | Preparation for HCFC phase-out investment activities (stage II) (foam sector) | Individual | AFR | MOR | FOA | 73 | PRP | 71 | A | I |  | 0 | 0 |  |  | 2014-11-01 | 2015-08-01 | 2016-12-30 | 2018-12-01 |  |  | 100000 | 0 | 100000 | 3457.52 | 3.458% | 96542.48 | 0 | 5000 | 7000 | 0 | 242 | 6758 | 0 | - UNIDO and NOU agreed on a plan of action for the preparation of the II stage HPMP. However, it was agreed to put the project preparation in stand-by waiting for the results from the DEMO project on low-volume pentane foam technology. Milestones achieved: Milestone 1: First mission/Working arrangements agreed - Yes Actions towards next goals: Wait for the outcomes of the DEMO project on low-volume pentane foam technology. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | UNIDO awaiting feedback from NOU. |  |  | NON-INV
COM | UNIDO | Preparation of a demonstration project on the use of compact high-pressure foaming equipment for the safe introduction of pentane technology to SMEs | Individual | AFR | MOR | FOA | 74 | PRP | 72 | A | I |  | 0 | 0 |  |  | 2015-05-01 | 2015-08-01 | 2016-12-30 |  | 2015-12-01 |  | 40000 | 0 | 40000 | 39548.81 | 98.87% | 451.19 | 0 | 1 | 2800 | 0 | 0 | 2800 | 0 | The project was operationally completed. |  |  |  | NON-INV
ONG | UNIDO | Demonstration of the use of low cost pentane foaming technology for the conversion to non-ODS technologies in polyurethane foams at small and medium enterprises | Individual | AFR | MOR | FOA | 75 | DEM | 74 | A | I |  | 0 | 0 |  |  | 2015-11-01 | 2016-11-01 | 2017-12-01 | 2018-06-01 |  |  | 280500 | 0 | 280500 | 11551.59 | 4.118% | 268948.41 | 6154.81 | 20000 | 19635 | 0 | 0 | 19635 | 430.8367 | Work plan discussed and agreed upon with NOU. Consultant recruited. Mission to visit beneficiary arranged and took place in October. Working arrangement agreed upon. Study tours to take place in 2017 due to belated mission. Was there any delay during the reporting year? Yes, as above. Any recurring problem? No Any impact on project completion date: Yes Any action required by Executive Committee? No | Potential suppliers of c5 systems contacted. Study tour under preparation. Date selection pending feedback from NOU |  |  | INV
FIN | UNIDO | Demonstration project - four alternatives to the use of methyl bromide: steam pasteurization, non-soil cultivation, solarization and low-dose chemicals in combination with an integrated pesticide management system | Individual | AFR | MOR | FUM | 22 | DEM | 11 | A | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-10-01 | 1999-06-01 |  | 2000-12-01 | 2002-08-01 | 487300 | -7238 | 480062 | 480062.23 | 100% | -0.23 | 0 |  | 63349 | -1040 | 62309 | 0 | 0 | FIN
FIN | Germany | Three alternatives to the use of methyl bromide: enemy plants, organic amendments and grafting on resistant rootstocks in combination with an integrated pest management system in tomatoes and curcubits | Individual | AFR | MOR | FUM | 26 | DEM | 26 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-04-01 | 2000-12-01 |  | 2001-10-01 | 2003-10-01 | 229523 | 0 | 229523 | 229523 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PCR submitted to 41st ExCom
FIN | UNIDO | Preparation of investment project in the fumigants/methyl bromide sector (bananas) | Individual | AFR | MOR | FUM | 27 | PRP | 28 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-06-01 | 1999-12-01 |  | 2000-01-01 | 2002-05-01 | 15000 | -482 | 14518 | 14518.35 | 100% | -0.35 | 0 |  | 1950 | -66 | 1884 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the fumigants/methyl bromide sector (flowers) | Individual | AFR | MOR | FUM | 27 | PRP | 29 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-06-01 | 1999-12-01 |  | 2000-01-01 | 2002-05-01 | 15000 | -148 | 14852 | 14852.35 | 100% | -0.35 | 0 |  | 1950 | -22 | 1928 | 0 | 0 | FIN
FIN | France | Phase-out of methyl bromide use in the cut flower and banana production |  | AFR | MOR | FUM | 29 | INV | 37 | A | I | MBR | 61 | 61 | 0 |  | 1999-11-01 | 2002-06-01 | 2003-12-01 |  | 2008-07-01 | 2012-12-01 | 1006652 | -78440 | 928212 | 931437 | 100.3% | -3225 |  |  | 120732 | -9408 | 111764 | -440 |  | This project was implemented through UNIDO on behalf of France. It is completed. |  |  | 2005-04-01
FIN | UNIDO | Preparation of phase-out project in the methyl bromide sector | Individual | AFR | MOR | FUM | 30 | PRP | 39 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-06-01 | 2001-04-01 |  | 2000-12-01 | 2002-09-01 | 30000 | -260 | 29740 | 29739.89 | 100% | 0.11 | 0 |  | 3900 | -40 | 3860 | 0 | 0 | FIN
FIN | UNIDO | Phase out of methyl bromide for soil fumigation in strawberry production | Individual | AFR | MOR | FUM | 32 | INV | 41 | A | I | MBR | 155 | 155 |  |  | 2000-12-01 | 2001-01-01 | 2006-01-01 |  | 2007-12-01 | 2008-12-01 | 2189729 | 0 | 2189729 | 2189728.97 | 100% | 0.03 | 0 |  | 250870 | 0 | 250870 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of methyl bromide for soil fumigation in tomato production (first tranche) | Multi-Year | AFR | MOR | FUM | 34 | INV | 44 | A | I | MBR | 0 | 0 |  |  | 2001-07-01 | 2002-10-01 | 2002-12-01 |  | 2005-09-01 | 2008-09-01 | 400000 | 0 | 400000 | 399999.97 | 100% | 0.03 | 0 |  | 52000 | 0 | 52000 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of methyl bromide used for soil fumigation in tomato production (balance of the first tranche) | Multi-Year | AFR | MOR | FUM | 44 | INV | 52 | A | I | MBR | 34.1 | 34.1 |  |  | 2004-12-01 | 2005-07-01 | 2005-12-01 |  | 2006-10-01 | 2007-12-01 | 607513 | -236 | 607277 | 607277.03 | 100% | -0.03 | 0 |  | 45563 | -17 | 45546 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of methyl bromide used for soil fumigation in tomato production (third tranche) | Multi-Year | AFR | MOR | FUM | 47 | INV | 54 | A | I | MBR | 39 | 39 |  |  | 2005-11-01 | 2006-02-01 | 2006-12-01 |  | 2008-12-01 | 2009-12-01 | 1670995 | 0 | 1670995 | 1670995 | 100% | 0 | 0 |  | 125325 | 0 | 125325 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of methyl bromide used for soil fumigation in tomato production (fourth tranche) | Multi-Year | AFR | MOR | FUM | 50 | INV | 55 | A | I | MBR | 56.4 | 56.4 |  |  | 2006-11-01 | 2007-05-01 | 2007-11-01 |  | 2008-12-01 | 2009-12-01 | 411633 | 0 | 411633 | 411633.01 | 100% | -0.01 | 0 |  | 30872 | 0 | 30872 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project preparation for a methyl bromide phase-out plan (green beans and cucumber) | Individual | AFR | MOR | FUM | 51 | PRP | 56 | A | I |  | 0 | 0 |  |  | 2007-03-01 | 2007-07-01 | 2008-03-01 |  | 2008-06-01 | 2009-05-01 | 35000 | -133 | 34867 | 34866.96 | 100% | 0.04 | 0 |  | 2625 | -10 | 2615 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Phase-out of methyl bromide used for soil fumigation in tomato production (fifth tranche) | Multi-Year | AFR | MOR | FUM | 53 | INV | 58 | A | I | MBR | 78 | 78 |  |  | 2007-11-01 | 2008-02-01 | 2008-11-30 |  | 2010-12-01 | 2010-12-01 | 424381 | 0 | 424381 | 424380.99 | 100% | 0.01 | 0 |  | 31829 | 0 | 31829 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of methyl bromide for soil fumigation in tomato production (sixth tranche) | Multi-Year | AFR | MOR | FUM | 56 | INV | 60 | A | I | MBR | 182.4 | 182.4 |  |  | 2008-11-01 | 2009-03-01 | 2010-11-30 |  | 2011-12-01 | 2013-12-01 | 398427 | -11389 | 387038 | 387037.51 | 100% | 0.49 | 0 |  | 29882 | -854 | 29028 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of methyl bromide used as a soil fumigant in the production of green beans and curcurbits (first tranche) | Multi-Year | AFR | MOR | FUM | 56 | INV | 61 | A | I | MBR | 35 | 35 |  |  | 2008-11-01 | 2008-12-01 | 2012-11-30 |  | 2012-10-01 | 2014-05-01 | 690000 | 0 | 690000 | 689999.98 | 100% | 0.02 | 0 |  | 51750 | 0 | 51750 | 0 | 0 | FIN |  |  |  | INV
FIN | Italy | Phase-out of methyl bromide used as a soil fumigant in the production of green beans and curcurbits (first tranche) | Multi-Year | AFR | MOR | FUM | 56 | INV | 62 | A | I | MBR | 15 | 15 | 0 |  | 2008-11-01 | 2009-07-01 | 2012-11-01 |  | 2014-12-01 | 2016-12-01 | 310000 | -2499 | 307501 | 307501 | 100% | 0 | 0 | 0 | 40300 | -325 | 39975 | 0 | 0 | The project was financially closed and the balance was reported to the 76th ExCom. | Balances (and interests accrued) have been reported to the 77th ExCom and have been returned in cash in April 2017 in light of ExCom decision 77/2(a)(iii) | 2008 |  | Investment
FIN | UNIDO | Phase-out of methyl bromide used as a soil fumigant in the production of green beans and cucurbits (second tranche) | Multi-Year | AFR | MOR | FUM | 62 | INV | 66 | A | I | MBR | 94.9 | 94.9 |  |  | 2010-12-01 | 2010-12-01 | 2012-12-31 |  | 2014-12-08 | 2016-03-01 | 437594 | -174 | 437420 | 437420.27 | 100% | -0.27 | 0 |  | 32820 | -13 | 32807 | 0 | 0 | The project was financially completed and the balance was returned at the 76th ExCom. |  |  |  | INV
FIN | Germany | Project preparation/technical assistance in the halon sector | Individual | AFR | MOR | HAL | 31 | PRP | 40 | A | I |  | 0 |  | 0 |  | 2000-07-01 | 2000-08-01 | 2001-01-01 |  | 2004-12-01 | 2005-06-01 | 10520 | 0 | 10520 | 10520 | 100% | 0 | 0 | 0 | 1368 | 0 | 1368 | 0 | 0 | Project proposal completed and with consent of NOU transferred to UNIDO for implementation.
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | AFR | MOR | PHA | 55 | PRP | 59 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-09-01 | 2009-07-31 |  | 2011-12-01 | 2013-12-01 | 150000 | -677 | 149323 | 149323.05 | 100% | -0.05 | 0 |  | 11250 | -51 | 11199 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | AFR | MOR | PHA | 65 | INV | 68 | A | I |  | 0 | 0 |  |  | 2011-11-01 | 2012-03-01 | 2012-11-30 | 2018-12-01 |  |  | 80000 | 0 | 80000 | 25384.1 | 31.73% | 54615.9 | 100 | 10000 | 6000 | 0 | 1904 | 4096 | 8 | A mission was undertaken in October during which pending issues were discussed. NOU is to resume contact with the beneficiary to enable implementation. UNIDO awaiting feedback from NOU. Was there any delay during the reporting year? Yes, as above. Any recurring problem? No Any impact on project completion date: Yes. Any action required by Executive Committee? No | UNIDO awaiting feedback from NOU. |  |  | INV |  | To request the submission of additional status report to the 79th meeting to monitor the completion of the audit.
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | Multi-Year | AFR | MOR | PHA | 68 | INV | 69 | A | I |  | 0 | 0 |  |  | 2012-12-01 | 2013-12-01 | 2017-12-31 | 2019-03-01 |  |  | 220000 | 0 | 220000 | 10893.05 | 4.951% | 209106.95 | 0 | 10000 | 16500 | 0 | 817 | 15683 | 0 | A mission was undertaken in October during which pending issues were discussed. NOU is to resume contact with the beneficiary to enable implementation. UNIDO awaiting feedback from NOU. Was there any delay during the reporting year? Yes, as above. Any recurring problem? No Any impact on project completion date: Yes. Any action required by Executive Committee? No | UNIDO awaiting feedback from NOU. |  |  | INV |  | To request the submission of additional status report to the 79th meeting to monitor the completion of the training of custom authorities and the audit of HCFC consumption.
ONG | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | Individual | AFR | MOR | PHA | 73 | PRP | 70 | A | I |  | 0 | 0 |  |  | 2014-11-01 | 2015-08-01 | 2016-12-30 | 2018-12-01 |  |  | 70000 | 0 | 70000 | 3457.52 | 4.939% | 66542.48 | 0 | 5000 | 4900 | 0 | 242 | 4658 | 0 | - UNIDO and NOU agreed on a plan of action for the preparation of the II stage HPMP. However, it was agreed to put the project preparation in stand-by waiting for the results from the DEMO project on low-volume pentane foam technology. Milestones achieved: Milestone 1: First mission/Working arrangements agreed - Yes Actions towards next goals: Wait for the outcomes of the DEMO project on low-volume pentane foam technology. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | UNIDO awaiting feedback from NOU. |  |  | NON-INV
FIN | France | Project preparation for the formulation of a project to implement a recycling network for CFC-11, CFC-12 and HCFC-22 |  | AFR | MOR | REF | 19 | PRP | 02 | A | D |  | 0 |  | 0 |  | 1996-05-01 | 1996-06-01 | 1996-11-01 |  | 1997-04-01 | 1997-09-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Projet achevé.
FIN | France | Technical assistance on alternative technologies for cold storage facilities |  | AFR | MOR | REF | 20 | TAS | 05 | A | I |  | 0 |  | 0 |  | 1996-10-01 | 1996-11-01 | 1997-10-01 |  | 1999-10-01 | 1999-11-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed
FIN | France | Implementation of an ODS recovery and recycling network | Recovery and recycling | AFR | MOR | REF | 23 | TAS | 17 | A | I | CFC | 22 | 22 | 0 |  | 1997-11-01 | 2003-09-01 | 1998-12-01 |  | 2011-06-01 | 2012-12-01 | 355867 | 0 | 355867 | 355867 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed. |  |  | 2002-11-01
FIN | France | Training of refrigeration technicians on recovery and recycling methodologies |  | AFR | MOR | REF | 23 | TRA | 18 | A | D |  | 0 |  | 0 |  | 1997-11-01 | 1999-02-01 | 1998-06-01 |  | 2000-12-01 | 2000-12-01 | 53361 | 0 | 53361 | 53361 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed
FIN | UNIDO | Preparation of investment project in the commercial refrigeration sector for Allom du Nord and others | Individual | AFR | MOR | REF | 24 | PRP | 20 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-07-01 | 1999-04-01 |  | 1999-09-01 | 2001-03-01 | 15000 | -4090 | 10910 | 10910 | 100% | 0 | 0 |  | 1950 | -534 | 1416 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-12 with HFC-134a for commercial refrigeration at Alom du Nord | Individual | AFR | MOR | REF | 25 | INV | 24 | A | I | CFC | 7.7 | 7.7 |  |  | 1998-07-01 | 1999-03-01 | 1999-08-01 |  | 2000-04-01 | 2002-09-01 | 99402 | -12788 | 86614 | 86614.26 | 100% | -0.26 | 0 |  | 12922 | -1680 | 11242 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-12 with HFC-134a for commercial refrigeration at Batinox | Individual | AFR | MOR | REF | 25 | INV | 25 | A | I | CFC | 4.5 | 4.5 |  |  | 1998-07-01 | 1999-03-01 | 1999-08-01 |  | 2000-05-01 | 2002-09-01 | 32920 | -341 | 32579 | 32578.65 | 100% | 0.35 | 0 |  | 4280 | -51 | 4228 | 1 | 0 | FIN
FIN | UNIDO | Replacement of CFC-12 with HFC-134a for commercial refrigeration at Smifam | Individual | AFR | MOR | REF | 26 | INV | 27 | A | I | CFC | 4.9 | 4.9 |  |  | 1998-11-01 | 1999-03-01 | 1999-12-01 |  | 2000-04-01 | 2002-09-01 | 62447 | -2267 | 60180 | 60179.88 | 100% | 0.12 | 0 |  | 8118 | -307 | 7811 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the commercial refrigeration sector | Individual | AFR | MOR | REF | 27 | PRP | 30 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 2000-09-01 | 1999-12-01 |  | 2001-04-01 | 2001-10-01 | 7000 | -1517 | 5483 | 5483.21 | 100% | -0.21 | 0 |  | 910 | -198 | 712 | 0 | 0 | FIN
FIN | UNEP | Preparation of a refrigerant management plan | RMP | AFR | MOR | REF | 27 | PRP | 32 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 2000-04-01 |  | 2007-12-01 | 2009-12-01 | 30000 | -4984 | 25016 | 25016 | 100% | 0 | 0 |  | 3900 | -647.92 | 3252.08 | 0 | 0
FIN | UNIDO | Conversion of HCFC-141b technology (rigid foam) and HFC-134a (refrigeration) in the manufacture of domestic refrigerators and freezers at Manar | Individual | AFR | MOR | REF | 29 | INV | 33 | A | R | CFC | 38.6 | 38.6 |  |  | 1999-11-01 | 2000-04-01 | 2000-07-01 |  | 1999-12-01 | 2000-11-01 | 434183 | 0 | 434183 | 434183 | 100% | 0 | 0 |  | 26051 | 0 | 26051 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment at Siafmo | Individual | AFR | MOR | REF | 29 | INV | 34 | A | I | CFC | 8.7 | 8.7 |  |  | 1999-11-01 | 2000-04-01 | 2001-06-01 |  | 2001-12-01 | 2003-02-01 | 126240 | -3250 | 122990 | 122990.02 | 100% | -0.02 | 0 |  | 16411 | -448 | 15963 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment at Mafidec | Individual | AFR | MOR | REF | 29 | INV | 35 | A | I | CFC | 5.6 | 5.6 |  |  | 1999-11-01 | 2000-04-01 | 2001-06-01 |  | 2001-12-01 | 2003-05-01 | 117360 | -7879 | 109481 | 109480.65 | 100% | 0.35 | 0 |  | 15257 | -1047 | 14210 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment at Sonyafroid | Individual | AFR | MOR | REF | 29 | INV | 36 | A | I | CFC | 13.1 | 13.1 |  |  | 1999-11-01 | 2000-04-01 | 2001-06-01 |  | 2001-12-01 | 2003-02-01 | 275895 | -2567 | 273328 | 273327.76 | 100% | 0.24 | 0 |  | 35866 | -390 | 35476 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of domestic commercial refrigeration equiment at Comafro | Individual | AFR | MOR | REF | 29 | INV | 38 | A | I | CFC | 6.5 | 6.5 |  |  | 1999-11-01 | 2000-04-01 | 2001-06-01 |  | 2001-12-01 | 2003-05-01 | 134750 | -1142 | 133608 | 133608.19 | 100% | -0.19 | 0 |  | 17518 | -177 | 17342 | -1 | 0 | FIN
FIN | France | Technical assistance for cold storage equipment (training and demonstration project) |  | AFR | MOR | REF | 32 | TAS | 42 | A | I |  | 0 |  | 0 |  | 2000-12-01 | 2004-01-01 | 2003-01-01 |  | 2005-08-01 | 2012-12-01 | 114337 | 0 | 114337 | 114337 | 100% | 0 |  | 0 | 5717 | 0 | 5717 | 0 |  | Project completed
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Climatisation et Froid Loudaya (CFL) | Individual | AFR | MOR | REF | 35 | INV | 45 | A | I | CFC | 15 | 15 |  |  | 2001-12-01 | 2002-02-01 | 2004-01-01 |  | 2003-12-01 | 2004-09-01 | 177312 | -847 | 176465 | 176464.91 | 100% | 0.09 | 0 |  | 23051 | -147 | 22904 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at First Clim Co. | Individual | AFR | MOR | REF | 35 | INV | 46 | A | I | CFC | 9 | 9 |  |  | 2001-12-01 | 2002-03-01 | 2004-01-01 |  | 2003-12-01 | 2004-09-01 | 135258 | -980 | 134278 | 134277.6 | 100% | 0.4 | 0 |  | 17584 | -156 | 17428 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Etablissement Lahdar | Individual | AFR | MOR | REF | 35 | INV | 47 | A | I | CFC | 7.4 | 7.4 |  |  | 2001-12-01 | 2002-06-01 | 2004-01-01 |  | 2003-12-01 | 2005-09-01 | 101451 | -1363 | 100088 | 100087.56 | 100% | 0.44 | 0 |  | 13189 | -198 | 12991 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at the terminal umbrella group of commercial refrigeration manufactures. | Individual | AFR | MOR | REF | 43 | INV | 50 | A | I | CFC | 18.4 | 18.4 |  |  | 2004-07-01 | 2004-11-01 | 2006-07-01 |  | 2006-12-01 | 2007-12-01 | 359864 | 0 | 359864 | 359863.76 | 100% | 0.24 | 0 |  | 26990 | 0 | 26990 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation for HCFC phase-out investment activities (refrigeration and air conditioning sectors) | Individual | AFR | MOR | REF | 60 | PRP | 65 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-09-01 | 2011-04-30 |  | 2011-12-01 | 2013-12-01 | 40000 | -254 | 39746 | 39746.38 | 100% | -0.38 | 0 |  | 3000 | -19 | 2981 | 0 | 0 | FIN
FIN | UNEP | Country programme preparation | Individual | AFR | MOR | SEV | 19 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1996-05-01 |  | 1996-05-01 | 1996-05-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 |  | 0
FIN | UNEP | Creation of Ozone Unit | Individual | AFR | MOR | SEV | 19 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1999-05-01 |  | 2004-07-01 | 2007-02-01 | 179000 | 0 | 179000 | 179000 | 100% | 0 | 0 |  | 23270 | 0 | 23270 | 0 | 0 |  |  |  | 1999-12-01
FIN | UNIDO | Project formulation of investment projects in domestic refrigeration and methyl bromide sectors | Individual | AFR | MOR | SEV | 21 | PRP | 07 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-06-01 | 1997-06-01 |  | 1999-09-01 | 2000-12-01 | 22150 | -1502 | 20648 | 20648 | 100% | 0 | 0 |  | 2880 | -200 | 2680 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNDP | Project preparation | Individual | AFR | MOR | SEV | 22 | PRP | 09 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-04-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNIDO | Country programme update | Individual | AFR | MOR | SEV | 38 | CPG | 48 | A | I |  | 0 | 0 |  |  | 2002-11-01 | 2003-03-01 | 2003-12-01 |  | 2003-12-01 | 2005-05-01 | 40000 | -1747 | 38253 | 38253.07 | 100% | -0.07 | 0 |  | 5200 | -235 | 4965 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNEP | Renewal of the institutional strengthening project (phase II) | Individual | AFR | MOR | SEV | 43 | INS | 49 | A | I | CFC | 12.8 | 0 | 0 | 0 | 2004-07-01 | 2005-08-01 | 2006-07-01 |  | 2007-12-01 | 2008-12-01 | 155000 | 0 | 155000 | 155000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (phase III) | Individual | AFR | MOR | SEV | 53 | INS | 57 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-02-01 | 2009-11-01 |  | 2015-12-01 | 2016-12-01 | 156000 | 0 | 156000 | 117820 | 75.53% | 38180 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed as no activities undertaken since 2013. Balance to be returned. | Project financially completed as no activities undertaken since 2013. Balance to be returned.
COM | UNEP | Renewal of the institutional strengthening project (phase IV) | Individual | AFR | MOR | SEV | 59 | INS | 63 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 |  | 2011-11-01 |  | 2015-12-01 |  | 84500 | 71500 | 156000 | 0 | 0% | 156000 | 51512.49 | 0 | 0 | 0 | 0 | 0 | 0 | Project financially completed as no activities undertaken since 2013. Balance to be returned. | Project financially completed as no activities undertaken since 2013. Balance to be returned.
FIN | UNEP | Survey of ODS alternatives at the national level | Individual | AFR | MOR | SEV | 75 | TAS | 73 | A | I |  | 0 |  | 0 |  | 2015-11-01 |  | 2016-12-01 |  | 2015-12-01 | 2016-12-01 | 110000 | 0 | 110000 | 0 | 0% | 110000 | 0 | 0 | 14300 | 0 | 0 | 14300 | 0 | Project financially completed as no activities undertaken since 2013. Balance to be returned. | Project financially completed as no activities undertaken since 2013. Balance to be returned.
FIN | UNIDO | Training and awareness workshop in the solvent and process agents (CTC & TCA ) sectors | Individual | AFR | MOR | SOL | 45 | TAS | 53 | A | I | CTC | 0.1 | 0.1 |  |  | 2005-04-01 | 2005-09-01 | 2006-04-01 |  | 2006-12-01 | 2007-12-01 | 40000 | -591 | 39409 | 39409.32 | 100% | -0.32 | 0 |  | 3600 | -53 | 3547 | 0 | 0 | FIN |  |  |  | INV
CLO | UNDP | Preparation of a methyl bromide alternative project in soil fumigation (tobacco) | Individual | AFR | MOZ | FUM | 27 | PRP | 08 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 |  | 2000-04-01 |  |  | 2000-12-01 | 20000 | -20000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 2600 | -2600 | 0 | 0 | 0 | Canceled in 2000. Financially Completed in 2000. |  | 1999 |  | Investment
FIN | UNIDO | Technical assistance for the elimination of controlled uses of methyl bromide in soil fumigation | Individual | AFR | MOZ | FUM | 60 | TAS | 20 | A | I |  | 0.4 | 0.4 |  |  | 2010-04-01 | 2010-12-01 | 2011-04-30 |  | 2015-12-01 | 2016-10-01 | 40000 | -378 | 39622 | 39622.03 | 100% | -0.03 | 0 |  | 3600 | -34 | 3566 | 0 | 0 | The project was financially completed and the balance was returned at the 77th ExCom.
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | MOZ | PHA | 50 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-03-01 | 2007-11-01 |  | 2007-11-01 | 2008-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | MOZ | PHA | 55 | PRP | 14 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-03-01 | 2009-07-01 |  | 2011-12-01 | 2011-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | MOZ | PHA | 56 | INV | 15 | N | I | CFC | 2.3 | 2.3 | 0 | 0 | 2008-11-01 | 2010-10-01 | 2010-11-01 |  | 2011-12-01 | 2012-02-01 | 100500 | 0 | 100500 | 100500 | 100% | 0 | 0 | 0 | 9045 | 0 | 9045 | 0 | 0 | Financially completed in 2012. | Completed in 2011. | 2008 |  | Investment
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | MOZ | PHA | 56 | TAS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-05-01 | 2010-11-01 |  | 2009-11-01 | 2011-03-01 | 75000 | -7550 | 67450 | 67450 | 100% | 0 | 0 |  | 9750 | -981.5 | 8768.5 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan (additional funding) | RMP | AFR | MOZ | PHA | 58 | PRP | 17 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2009-12-01 | 2010-07-01 |  | 2012-12-01 | 2013-12-01 | 55000 | -15987 | 39013 | 39013 | 100% | 0 | 0 |  | 7150 | -2078.31 | 5071.69 | 0 | 0
FIN | UNDP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | MOZ | PHA | 59 | INV | 19 | N | I | CFC | 0 | 0 | 0 | 0 | 2009-11-01 | 2009-12-01 | 2011-11-01 |  | 2011-12-01 | 2012-02-01 | 17000 | -1129.1 | 15870.9 | 15871 | 100% | -0.1 | 0 | 0 | 1530 | -101.62 | 1428.39 | -0.01 | 0 | Financially completed in 2012. | Completed in 2011. | 2009 |  | Investment
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | MOZ | PHA | 59 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-02-01 | 2011-11-01 |  | 2013-09-01 | 2014-12-01 | 59000 | 0 | 59000 | 59000 | 100% | 0 | 0 |  | 7670 | 0 | 7670 | 0 | 0
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | MOZ | PHA | 66 | INV | 23 | A | I | HCFC | 0.3 | 0 |  |  | 2012-04-01 | 2014-09-01 | 2016-04-30 | 2018-02-18 |  |  | 75000 | 0 | 75000 | 9050.04 | 12.07% | 65949.96 | 0 | 30000 | 6750 | 0 | 815 | 5935 | 0 | There has been a refocus of the scope from being only vocational schools to cover also equipment for customs. For this reason disbursement level is still low. Scope agreed and technical specifications under review by local expert. Procurement started Q4/2016; and equipment delivery planned for Q1 and Q2 2017. '- No delay in implementation - No recurring problem - Impact on project completion date: No - No action required by Executive Committee | The equipment will be delivered trough two purchase orders. One has shipped in Q1 and the other is planned to be finalized and shipped Q2 2017. '- No delay in implementation - No recurring problem - Impact on project completion date: No - No action required by Executive Committee |  |  | INV
COM | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | AFR | MOZ | PHA | 66 | TAS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 | 2013-06-01 | 2014-04-01 |  | 2015-03-01 | 2015-09-01 | 40000 | 0 | 40000 | 3974.78 | 9.937% | 36025.22 | 0 | 17025 | 5200 | 0 | 516.7214 | 4683.2786 | 0
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | AFR | MOZ | PHA | 73 | TAS | 25 | A | I |  | 0 |  | 0 |  | 2014-11-01 | 2015-12-01 | 2016-06-01 | 2017-10-01 |  |  | 35000 | 0 | 35000 | 0 | 0% | 35000 | 0 | 3500 | 4550 | 0 | 0 | 4550 | 0 | Brief progress report (actual/planned): The NOU implemented a number of activities including trainings conducting two customs training where a total of 30 officers were trained on control and enforcement of the legislations. The NOU trained 50 RAC technicians on implementation of good refrigeration practices including use of hydrocarbons. __ Legal arrangements (actual/planned): The SSFA was drafted and signed by UNEP and the Government of Mozambique in May 2016. Initial stages of project implementation(actual/planned): __Yes_ Intermediate goals achieved (actual/planned): _yes__ Project completion and follow up: _No__ First disbursement date (actual/planned): _No__ All funds disbursed (yes/no): __No_ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): The NOU continues to monitor imports and trade of ODS and ODS related equipment. Collection of the 2016 data on ODS imports and consumption has been completed and is being analyzed for submission. NOU commenced preparation of national legislative requirement processes in planning for ratification of Kigali amendment |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor the completion of the procurement of equipment.
ONG | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Individual | AFR | MOZ | PHA | 77 | TAS | 28 | A | I |  | 0 |  | 0 |  | 2016-12-01 |  | 2018-06-01 | 2018-06-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 3000 | 3900 | 0 | 0 | 3900 | 0 | Newly approved project. | Brief progress report (actual/planned): The project is new as it was approved in Dec 2016. The licensing and quota system are in place and operational. UNEP is preparing to hire a consultant for the verification. TORs for verification consultancy have been drafted and being reviewed ___ Legal arrangements (actual/planned): N/A. ___Initial stages of project implementation (actual/planned): __N/A_ Intermediate goals achieved (actual/planned): _No__ Project completion and follow up: _Yes__ First disbursement date (actual/planned): __N/A___. All funds disbursed (yes/no): N/A_ Any delay? (yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: __N/A_
FIN | UNIDO | Preparation of projects in commercial refrigeration | Individual | AFR | MOZ | REF | 15 | PRP | 02 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-03-01 | 1995-06-01 |  | 1996-08-01 | 1998-08-01 | 15000 | -1697 | 13303 | 13303 | 100% | 0 | 0 |  | 1950 | -223 | 1727 | 0 | 0 | FIN
CLO | UNIDO | Phasing out of CFCs at INDATEC/Industria de aplicacoes technico-domesticas Ltd. | Individual | AFR | MOZ | REF | 18 | INV | 04 | A | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-06-01 | 1997-03-01 |  |  | 2002-04-01 | 581515 | -246871 | 334644 | 334644 | 100% | 0 | 0 |  | 75597 | -32162 | 43435 | 0 | 0 | CLO |  |  | 1999-11-01
FIN | UNDP | Project preparation in refrigeration recycling | Individual | AFR | MOZ | REF | 21 | PRP | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2002-03-01 | 20000 | -1643 | 18357 | 18357 | 100% | 0 | 0 | 0 | 2600 | -213.59 | 2386.41 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | AFR | MOZ | REF | 22 | TAS | 06 | A | I | CFC | 6.9 | 6.9 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1999-06-01 | 2001-12-01 | 115809 | -138 | 115671 | 115671 | 100% | 0 | 0 | 0 | 15055.17 | -17.94 | 15037.2275 | 0.0025 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | MOZ | REF | 26 | TAS | 07 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2004-12-01 | 2005-09-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. RMP update approved.
FIN | Germany | Project preparation for a refrigerant management plan update | RMP Update | AFR | MOZ | REF | 37 | PRP | 09 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-06-01 | 2003-08-01 |  | 2004-11-01 | 2004-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | RMP-update was approved at 44th ExCom
FIN | France | Refrigerant management plan update | RMP Update | AFR | MOZ | REF | 44 | TAS | 12 | A | I | CFC | 15.5 |  | 0 |  | 2004-12-01 | 2005-12-01 | 2007-12-01 |  | 2009-12-01 | 2012-12-01 | 104512 | -33312 | 71200 | 72566 | 101.9% | -1366 |  | 0 | 13587 | -4331 | 9460 | -204 |  | The French contribution was implmented by GTZ-Proklima. The project is completed.
FIN | UNEP | Country programme | Individual | AFR | MOZ | SEV | 15 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-12-01 |  | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 |  | 0
FIN | UNEP | Institutional strengthening | Individual | AFR | MOZ | SEV | 15 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1997-12-01 |  | 2003-12-01 | 2005-12-01 | 92400 | 0 | 92400 | 92400 | 100% | 0 | 0 |  | 12012 | 0 | 12012 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project: phase 2 | Individual | AFR | MOZ | SEV | 41 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2005-03-01 | 2005-12-01 |  | 2007-01-01 | 2008-12-01 | 80080 | 0 | 80080 | 80080 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | AFR | MOZ | SEV | 50 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-08-01 | 2008-11-01 |  | 2009-07-01 | 2010-12-01 | 80800 | 0 | 80800 | 80800 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | MOZ | SEV | 57 | INS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-09-01 | 2011-03-01 |  | 2011-06-01 | 2011-12-01 | 80800 | 0 | 80800 | 80800 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase V: 7/2011-6/2013) | Individual | AFR | MOZ | SEV | 64 | INS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-06-01 | 2013-06-01 |  | 2013-06-01 | 2014-12-01 | 80800 | 0 | 80800 | 80800 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of the institutional strengthening project (phase VI: 7/2013-6/2015) | Individual | AFR | MOZ | SEV | 70 | INS | 24 | A | I |  | 0 |  | 0 |  | 2013-07-01 | 2014-02-01 | 2015-06-01 | 2017-12-01 |  |  | 80800 | 0 | 80800 | 37743.13 | 46.71% | 43056.87 | 43056.87 | 4305.687 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): _ The licensing and quota system are in place and functioning. The NOU conducted stakeholder’s workshop to allocate HCFCs licenses and quotas. The NOU conducted regular inspection activities to ensure compliance and distributed tools to RAC technicians. The NOU conducted trainings for 40 Custom Officers and 30 RAC technicians. The NOU collected, processed and submitted 2015 Country Programme and Article 7 Data reports. The NOU celebrated 2016 International Ozone Day and conducted several awareness activities. The NOU participated in all Montreal Protocol meetings organized in 2016. project activities are completed_ Legal arrangements (actual/planned): The SSFA was drafted and signed by UNEP and the Government of Mozambique in January 2014.___Initial stages of project implementation(actual/planned): _Yes__ Intermediate goals achieved (actual/planned): Yes___ Project completion and follow up: Yes_ First disbursement date (actual/planned): The first disbursement was made in May 2014.___ All funds disbursed (yes/no): _Yes__ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): __N/A_ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: __N/A_ | Brief progress report (actual/planned): _ The licensing and quota system are in place and functioning. The NOU conducted stakeholder’s workshop to allocate HCFCs licenses and quotas. The NOU conducted regular inspection activities to ensure compliance and distributed tools to RAC technicians. The NOU conducted trainings for 40 Custom Officers and 30 RAC technicians. The NOU collected, processed and submitted 2015 Country Programme and Article 7 Data reports. The NOU celebrated 2016 International Ozone Day and conducted several awareness activities. The NOU participated in all Montreal Protocol meetings organized in 2016. project activities are completed_ Legal arrangements (actual/planned): The SSFA was drafted and signed by UNEP and the Government of Mozambique in January 2014.___Initial stages of project implementation(actual/planned): _Yes__ Intermediate goals achieved (actual/planned): Yes___ Project completion and follow up: Yes_ First disbursement date (actual/planned): The first disbursement was made in May 2014.___ All funds disbursed (yes/no): _Yes__ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): __N/A_ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: __N/A_
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | AFR | MOZ | SEV | 74 | TAS | 26 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-04-01 | 2016-05-01 | 2017-05-01 |  |  | 70000 | 0 | 70000 | 51.74 | 0.07391% | 69948.26 | 35000 | 6994.826 | 9100 | 0 | 6.7262 | 9093.2738 | 4550 | Brief progress report (actual/planned): The first stakeholders meeting was organized by the NOU in April 2016 in Maputo with the main goal to agree on the plan for the Survey of ODS alternatives at the national level and obtain support of main national stakeholders. The meeting was attended by 40 participants. One National Consultant was hired in June 2016 by the NOU to support the data collection. The National Consultant assisted the NOU in the identification of the current use of ODS alternatives by substance/sector and collection of import/export data for the substances for the past a couple of years. The National Consultant also provided support in establishing growth patterns in use by substance/sector and in compiling data on available ODS alternatives for various applications.The NOU and the National Consultant drafted and cross checked the information to ensure the completion of end-user surveys, collection, analysis, and aggregation of consumption data. The various sections of the report were drafted. The second stakeholders meeting was organized by the NOU in November 2016 in Maputo with the main goal to organise consultations with representatives of the government and private sector to finalize the outcomes of the Survey of ODS alternatives and discuss potential opportunities for introduction of those alternatives in the country. The draft report was prepared by the NOU and the National Consultant. It was reviewed and finalized based on the format approved by ExCom decision 75/67 as contained in document UNEP/OzL.Pro/ExCom/75/77/Rev.1 after incorporating inputs/ comments raised during National Stakeholders’ workshop. The final report has been submitted to UNEP for final review and submission to MLFS. The NOU participated in the ODS Alternative Thematic workshop held in December 2016 to refine the draft report according to the revised template for the report. The report has been finally submitted to UNEP. Legal arrangements(actual/planned): The SSFA was drafted and signed by UNEP and the Government of Mozambique in March 2016___Initial stages of project implementation(actual/planned): _Yes__ Intermediate goals achieved (actual/planned): Yes___ Project completion and follow up: _No__ First disbursement date (actual/planned): _April 2016__ All funds disbursed (yes/no): No___ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): __N/A_ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): The NOU incorporated comments from UNEP ROA and Paris and re-submitted final ODS survey report.
ONG | UNEP | Extension of the institutional strengthening project (phase VII: 4/2016-3/2018) | Individual | AFR | MOZ | SEV | 76 | INS | 27 | A | I |  | 0 |  | 0 |  | 2016-05-01 | 2016-12-01 | 2018-03-01 | 2018-03-01 |  |  | 103424 | 0 | 103424 | 51.74 | 0.05003% | 103372.26 | 103372.26 | 10337.226 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Newly approved. The licensing and quota systems are in place and operational. The NOU registered all importers of HCFC for 2016, advertised for quota allocation for 2016 HCFC importation and conducted two inspection visits to various boarders to check how customs officers are enforcing the control measures of HCFC importation. The NOU trained 30 custom officers and 40 RAC technicians. The NOU submitted 2015 Country Programme and Article 7 Data reports. The NOU celebrated 2016 International Ozone Day and conducted several awareness activities, printed 300 T shirts and organized Radio Talk-shows. The NOU also participated in all Montreal Protocol meetings organized in 2016.___ Legal arrangements(actual/planned): The SSFA was drafted and signed by UNEP and the Government of Mozambique in November 2016__Initial stages of project implementation(actual/planned): _Yes__ Intermediate goals achieved (actual/planned): _Yes__ Project completion and follow up: No___ First disbursement date (actual/planned): _December 2016__ All funds disbursed (yes/no): _NO__ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: __N/A_ If Yes, will delay have impact on project completion date (yes/no): _Yes__ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): The NOU continues to monitor imports and trade of ODS and ODS related equipment. Collection of the 2016 data on ODS imports and consumption has been completed and is being analyzed for submission. NOU commenced preparation of national legislative requirement processes in planning for ratification of Kigali amendment.
FIN | UNEP | Preparation of a terminal phase-out management plan | RMP | ASP | MYA | PHA | 55 | PRP | 08 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2008-12-01 |  | 2011-06-01 | 2011-12-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 |  | 0
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | ASP | MYA | PHA | 57 | PRP | 09 | A | I |  | 0 | 0 |  |  | 2009-04-01 | 2009-06-01 | 2010-03-31 |  | 2012-12-01 | 2014-07-01 | 42500 | -889 | 41611 | 41610.75 | 100% | 0.25 | 0 |  | 3188 | -67 | 3121 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | MYA | PHA | 57 | PRP | 10 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-12-01 | 2010-03-01 |  | 2011-12-01 | 2012-12-01 | 42500 | -9747 | 32753 | 32753 | 100% | 0 | 0 |  | 5525 | -1266.93 | 4258.07 | 0 | 0
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | ASP | MYA | PHA | 68 | TAS | 14 | A | I |  | 0.4 | 0 | 0 | 0 | 2012-12-01 | 2016-04-01 | 2015-12-01 | 2017-12-01 |  |  | 159000 | 0 | 159000 | 14573.76 | 9.166% | 144426.24 | 91565.66 | 14442.624 | 20670 | 0 | 1894.5888 | 18775.4112 | 11903.5358 | Brief progress report (actual/planned): The new SSFA with update timeline for implementation was signed and effective in February 2016 and the first payment was made to the country in April 2016. A technical consultant was hired to coordinate and assist the NOU inthe implementation of the HPMP. The Train-the-Trainer workshop for RAC servicing was organized by the NOU from 28 November-1 December 2016, back-to-back with the second custom training from 5-6 December 2016. UNEP participated in these workshops to deliver training to Myanmar's customs and enforcement officers as well as RAC trainers, and faciliated south-south coopration with Thailand, China respectively to support the delivery of the two training workshops. NOU had agreed with the Ministry of Industry to serve as the training center under HPMP. Procurement is under process and purchase order will be issued by June 2017. 2015 CP data was submitted to MLFS. Legal arrangements (actual/planned): The SSFA was signed in February 2016. First Mission: Feb 2014. First disbursement date: April 2016. All funds disbursed (yes/no): No. Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: The limited implementation capacity of the NOU to implement HPMP. UNEP maintained regular communications and had missions to build the capacity of the NOU/stakeholders and get the country prepared for the implementation. UNEP urged the government to hire the technical consultant to support the day-to-day operation. If Yes, will delay have impact on project completion date (yes/no): Yes Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: No. | Brief progress report (actual/planned): The Environmental Conservation Department (ECD) has set up the training plan in the first quarter of 2017. One RAC training workshop was organized from 16-17 February 2017. Two more training are planned in March 2017. ECD is discussing with the Customs Department to prepare the training plan for the Customs and enforcement officers.
ONG | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Multi-Year | ASP | MYA | PHA | 73 | TAS | 16 | A | I |  | 0 |  | 0 |  | 2014-11-01 |  | 2015-05-01 | 2017-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 3000 | 3900 | 0 | 0 | 3900 | 0 | Brief progress report (actual/planned): The approach to conduct verification has been finalized with the NOU. It was agreed that UN Environment will contract the consultant, who can audit the government document, directly. The Terms of Reference (ToR) for hiring the international consultant was prepared. However, UINEP has not received list of potential auditor as of December 2016. Legal arrangements(actual/planned): Not yet. Initial stages of project implementation(actual/planned): Not yet. Intermediate goals achieved (actual/planned): Not yet. Project completion and follow up: Not applicable. First disbursement date (actual/planned): not yet. All funds disbursed (yes/no): _No__ Any delay?(yes/no): Yes If Yes, reasons for delay & action plan to resolve: Delay in finalizing implementation arrangement and obtaining list of private auditing companies If Yes, will delay have impact on project completion date (yes/no): Yes, the report should be available in 2017. Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): The list of potential auditors were submitted to UNEP in February 2017. The international consultant will be recruited by UNEP to verify the national consumption in relation to the targets as set out in the Agreement between ExCom and Government of Myanmar, following the relevant decisions of the ExCom and guidelines for the verification of national consumption targets for the multi-year agreements.
FIN | UNEP | Preparation of a refrigerant management plan | RMP | ASP | MYA | REF | 29 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2003-06-01 | 2000-12-01 |  | 2005-04-01 | 2011-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
CLO | UNDP | Formulation of the investment components of theRMP | Individual | ASP | MYA | REF | 39 | PRP | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  |  | 2005-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 1500 | 0 | 1500 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2003 |  | Investment
FIN | UNEP | Implementation of the RMP: preparation of ozone regulations for control of ODSs | Individual | ASP | MYA | REF | 45 | TAS | 05 | A | I | CFC | 5.2 | 0 | 0 | 0 | 2005-04-01 | 2008-05-01 | 2005-11-01 |  | 2011-01-01 | 2011-11-01 | 13000 | 0 | 13000 | 13000 | 100% | 0 | 0 |  | 1690 | 0 | 1690 | 0 | 0
FIN | UNEP | Implementation of the RMP: monitoring implementation of the RMP | Individual | ASP | MYA | REF | 45 | TAS | 06 | A | I | CFC | 8.8 | 0 | 0 | 0 | 2005-04-01 | 2008-03-01 | 2008-04-01 |  | 2011-01-01 | 2011-11-01 | 22000 | 0 | 22000 | 22000 | 100% | 0 | 0 |  | 2860 | 0 | 2860 | 0 | 0
FIN | UNIDO | Implementation of the RMP: establishing conversion practice of domestic refrigerators | Individual | ASP | MYA | REF | 45 | TAS | 07 | A | I | CFC | 32.1 | 32.1 |  |  | 2005-04-01 | 2005-10-01 | 2006-10-01 |  | 2007-11-01 | 2008-07-01 | 80000 | -15 | 79985 | 79984.53 | 100% | 0.47 | 0 |  | 7200 | -1 | 7199 | 0 | 0 | FIN |  |  |  | INV
FIN | UNEP | Country programme preparation | Individual | ASP | MYA | SEV | 12 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-09-01 | 1995-06-01 |  | 1999-11-01 | 1999-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0 |  |  |  | 1999-05-01
FIN | UNEP | Establishment of the national Ozone Cell for implementing the phase out of ODSs under the Montreal Protocol | Individual | ASP | MYA | SEV | 29 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2007-07-01 | 2002-12-01 |  | 2009-12-01 | 2011-03-01 | 76000 | 0 | 76000 | 76000 | 100% | 0 | 0 |  | 9880 | 0 | 9880 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase II) | Individual | ASP | MYA | SEV | 58 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2010-07-01 | 2010-12-01 |  | 2011-03-01 | 2011-11-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase II, second year) | Individual | ASP | MYA | SEV | 62 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-11-01 | 2011-12-01 |  | 2011-12-01 | 2012-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of institutional strengthening project (phase III: 1/2012-12/2013) | Individual | ASP | MYA | SEV | 64 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2013-08-01 | 2013-12-01 | 2017-12-01 |  |  | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The operation of the NOU was going on well. A technical consultant was recruited in July 2016 to support dialy operation of the Environmental Conservation Department (ECD). However, another position has not yet been filled. Myanmar continued to enforce its licensing and quota system through the 2014 Ozone Order. An importer meeting was organized end of 2016 by the ECD to allocate quota for 2017. ECD coordinated and facilitated the implementation of HPMP, ODS Alternative Survey and verification of HCFC consumption. ECD also organized the 2016 ozone day celebration, and actively joined the regional and global ozone related meetings e.g. the network meeting, OEWG and the MOP meetings. 2015 Article 7 and CP data were submitted to the Ozone Secretariat and MLFS respectively. The SSFA was extended to end of December 2017 to accommodate the release of the last payment. Legal arrangements (actual/planned): The SSFA was signed in November 2012, then renewed in April 2015, and further amended in Dec 2016. Initial stages of project implementation (actual/planned): Nov/Nov 2012. Intermediate goals achieved (actual/planned): Yes, data reported to the Multilateral Fund and Ozone Secretariat; Ozone Order was enforced. First disbursement date: August 2013 All funds disbursed (yes/no): No. Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: Delay in obtaining the payment under the renewed SSFA affected the government 's planned activities. If Yes, will delay have impact on project completion date (yes/no) Yes. Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): ECD continues enforcing the licensing and quota system. The second payment under the renewed SSFA of IS project phase III has been requested to transfer to the country. As there is one more payment left, UNEP is working closely with the ECD to complete the agreed activities and close the SSFA.
ONG | UNEP | Extension of institutional strengthening project (phase IV: 1/2014-12/2015) | Individual | ASP | MYA | SEV | 71 | INS | 15 | A | I |  | 0 |  | 0 |  | 2013-12-01 |  | 2015-12-01 | 2018-12-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Following a long delay in reviewing the draft SSFA, Environmental Conservation Department (ECD) confirmed the approval of SSFA by the Cabinet in December 2016. The SSFA was immediately processed for signing by the management of UNEP. Legal arrangements(actual/planned): Not yet. Initial stages of project implementation(actual/planned): Not yet. Intermediate goals achieved (actual/planned): Not yet. Project completion and follow up: Not applicable. First disbursement date (actual/planned): not yet. All funds disbursed (yes/no): _No__ Any delay?(yes/no): Yes If Yes, reasons for delay & action plan to resolve: Delay in obtaining agreement from the country in signing the SSFA. If Yes, will delay have impact on project completion date (yes/no): Yes, the completing date has to be extended. Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): The SSFA was signed by UNEP in February 2017. The SSFA was transmitted to the country for countersigning. The first payment will be made after signing of the SSFA and closure of IS Project phase III.
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | ASP | MYA | SEV | 74 | TAS | 17 | A | I |  | 0 |  | 0 |  | 2015-05-01 |  | 2016-05-01 | 2017-06-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 0 | 4000 | 5200 | 0 | 0 | 5200 | 0 | Brief progress report (actual/planned): The SSFA, which was submitted to the country since 2015, was still under final review by the Government in 2016 due to the long internal process. In the meantime, UNEP conducted a mission and had the stakeholder workshop organized by the NOU in December 2016 with the main goal to agree on the plan for the Survey of ODS alternatives at the national level and obtain support of main national stakeholders. The local consultant has been identified by the NOU also joined the workshop. Term of Reference for the local consultant has been prepared and the contract could be signed after the SSFA signing. Legal arrangements(actual/planned): Not yet Initial stages of project implementation(actual/planned): Not yet Intermediate goals achieved (actual/planned): Not applicable. Project completion and follow up: Not applicable. First disbursement date (actual/planned): not yet. All funds disbursed (yes/no): _No__ Any delay?(yes/no): Yes If Yes, reasons for delay & action plan to resolve: The depay in signing SSFA by country. If Yes, will delay have impact on project completion date (yes/no): Yes. Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: N/A | The NOU confirmed agreement with the draft SSFA, which has been signed by UNEP in February 2017. The SSFA is with the government for counter-signature.
FIN | Germany | Project preparation for a terminal ODS phase-out management plan | Individual | AFR | NAM | PHA | 37 | PRP | 08 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2002-12-01 | 2003-08-01 |  | 2003-09-01 | 2004-08-01 | 50250 | 0 | 50250 | 50250 | 100% | 0 | 0 | 0 | 6533 | 0 | 6533 | 0 | 0 | Project completed and TPMP approved at 41st Excom
FIN | Germany | Terminal phase-out management plan for CFCs | Multi-Year | AFR | NAM | PHA | 41 | INV | 10 | A | I | CFC | 9 | 10.5 | 0 |  | 2003-12-01 | 2004-05-01 | 2005-12-01 |  | 2007-12-01 | 2008-05-01 | 160000 | 0 | 160000 | 160000 | 100% | 0 | 0 | 0 | 20800 | 0 | 20800 | 0 | 0 | Namibia continues to maintain zero imports in keeping with the TPMP targets. In 2007, 3 additional customs training were organised to maintain vigilance and update the ASCUYDA ++ system. Incentive scheme is being implemented successfully with 42 cold rooms being retrofitted mainly at hospitals and schools (hostels). A total of 312 kgs of ODS has been phased out |  |  | 2006-12-01
FIN | Germany | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | NAM | PHA | 50 | INV | 12 | A | I | CFC | 3 | 3 | 0 |  | 2006-11-01 | 2007-04-01 | 2008-11-01 |  | 2010-06-01 | 2012-12-01 | 92500 | 0 | 92500 | 92500 | 100% | 0 | 0 | 0 | 12025 | 0 | 12025 | 0 | 0 | All conversions under the incentive scheme have been completed. The project is completed and the final report is being drafted.
FIN | Germany | Preparation of a HCFC phase-out management plan | Individual | AFR | NAM | PHA | 55 | PRP | 14 | A | I | HCFC | 0 |  | 0 |  | 2008-07-01 | 2008-11-01 | 2009-07-01 |  | 2010-12-01 | 2012-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | HPMP submitted as planned in Dec 2010
FIN | Germany | Preparation of a HCFC phase-out management plan (additional funding) |  | AFR | NAM | PHA | 57 | PRP | 15 | A | I | HCFC | 0 |  | 0 |  | 2009-04-01 | 2009-08-01 | 2010-03-01 |  | 2010-12-01 | 2012-12-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 | 0 | 7150 | 0 | 7150 | 0 | 0 | HPMP submitted as planned in Dec 2010
COM | Germany | HCFC phase-out management plan (first tranche) | Multi-Year | AFR | NAM | PHA | 63 | INV | 17 | A | I | HCFC | 0.9 | 1.4 | 0 |  | 2011-04-01 | 2011-06-01 | 2014-03-01 |  | 2015-10-01 |  | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 | 0 | 36333 | 0 | 36333 | 0 |  | Purchase of equipment for training centres, 3 customs trainings were completed under the tranche | Trache funds completed.
ONG | Germany | HCFC phase-out management plan (second tranche) | Multi-Year | AFR | NAM | PHA | 71 | INV | 19 | A | I | HCFC | 4.6 |  | 0 |  | 2013-12-01 | 2015-05-01 | 2017-12-01 | 2017-12-01 |  |  | 240000 | 0 | 240000 | 106844 | 44.52% | 133156 | 0 | 133156 | 29067 | 0 | 14861 | 14206 |  | 3 customs trainings were conducted, 2 stakeholder workshops involving industry were conducted. NOU and Trainer attended Cool training in Germany | Equipment list has been submitted for purchase. |  |  | INV
ONG | Germany | Verification report for stage I of HCFC phase-out management plan | Individual | AFR | NAM | PHA | 74 | TAS | 21 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-05-01 | 2017-05-01 | 2017-05-01 |  |  | 30000 | 0 | 30000 | 3592 | 11.97% | 26408 | 0 | 26408 | 3900 | 0 | 467 | 3433 |  | Discussions with NOU on approach, idenitifying consultant and hiring process was completed in 2016 | Verification to be completed for the submission for the 1st meeting in 2017 along with the next tranche request.
FIN | Finland | Implementation of a training programme for recovery and recycling of refrigerants | Individual | AFR | NAM | REF | 20 | TRA | 03 | A | I | CFC | 5.4 | 5.4 | 0 |  | 1996-10-01 | 1997-01-01 | 1998-10-01 |  | 1998-10-01 | 1999-10-01 | 103440 | 0 | 103440 | 103440 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed |  | 1997
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | NAM | REF | 23 | PRP | 04 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-03-01 |  | 1998-07-01 | 2000-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation
FIN | Germany | Recuperation and recycling of CFC-12 integrated with the introduction of hydrocarbon technology in the service sector | Individual | AFR | NAM | REF | 24 | TAS | 05 | N | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-05-01 | 1998-06-01 |  | 1998-06-01 | 2000-01-01 | 34400 | -244 | 34156 | 34156 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Completed, final report submitted
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | NAM | REF | 26 | TAS | 06 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2003-08-01 | 2004-05-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | project completed. PCR submitted. TPMP approved in Dec 2003
FIN | UNEP | Country programme preparation | Individual | AFR | NAM | SEV | 15 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-04-01 | 1996-03-01 |  | 1995-10-01 | 1995-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNEP | Establishment of a National Ozone Office | Individual | AFR | NAM | SEV | 18 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-09-01 | 1998-11-01 |  | 2000-02-01 | 2001-12-01 | 61765 | 0 | 61765 | 61765 | 100% | 0 | 0 |  | 8029 | 0 | 8029 | 0 | 0 |  |  |  | 1998-11-01
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | AFR | NAM | SEV | 31 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2000-07-01 | 2001-07-01 | 2002-08-01 |  | 2003-12-01 | 2004-12-01 | 41177 | 0 | 41177 | 41177 | 100% | 0 | 0 |  | 5353 | 0 | 5353 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project: phase 3 | Individual | AFR | NAM | SEV | 41 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-10-01 | 2005-12-01 |  | 2005-12-01 | 2007-03-01 | 53530 | 0 | 53530 | 53530 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | AFR | NAM | SEV | 47 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-02-01 | 2007-12-01 |  | 2007-12-01 | 2009-01-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase V) | Individual | AFR | NAM | SEV | 53 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-11-01 |  | 2009-11-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of institutional strengthening project (phase VI) | Individual | AFR | NAM | SEV | 59 | INS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-09-01 | 2011-11-01 |  | 2013-11-01 | 2015-12-01 | 32500 | 27500 | 60000 | 46500 | 77.5% | 13500 | 13500 | 13500 | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of institutional strengthening project (phase VII: 4/2012-3/2014) | Individual | AFR | NAM | SEV | 66 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 | 2013-01-01 | 2014-03-01 |  | 2014-07-01 | 2016-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed | Project financially completed
ONG | UNEP | Extension of institutional strengthening project (phase VIII: 12/2014-11/2016) | Individual | AFR | NAM | SEV | 73 | INS | 20 | A | I |  | 0 |  | 0 |  | 2014-11-01 | 2016-01-01 | 2016-11-01 | 2017-09-01 |  |  | 60000 | 0 | 60000 | 2843.37 | 4.739% | 57156.63 | 57156.63 | 5715.663 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The licensing and quota systems are in place and functioning. The NOU registered all importers of HCFCs and organized one stakeholders meeting in Feb 2016 to coordinate and allocate licenses and quotas. The NOU organized several trainings in various regions to equip refrigeration technicians with knowledge and skills in the hydrocarbon field and good refrigeration practices. A total of 53 refrigeration technicians were trained. The training focused on safety in handling alternative refrigerants and minimum standards to be followed by any technicians involved in handling alternative refrigerants. The technicians were also trained on the choices of refrigerants that could be used for specific equipment. The NOU organized two training workshops for Customs and Enforcement Officers. The NOU commemorated the 2016 Ozone Day with the 3rd year students of Environmental Sociology at the University of Namibia The NOU collected, compiled and submitted 2015 Country Programme data and Article 7 data to the Ozone Secretariat. The NOU participated in all Montreal Protocol meetings organized in 2016___ Legal arrangements (actual/planned): The SSFA was drafted and signed by UNEP and the Government of Namibia in Sept 2015; Initial stages of project implementation(actual/planned): _Yes__ Intermediate goals achieved (actual/planned): _Yes__ Project completion and follow up: _No__ First disbursement date (actual/planned): The first disbursement was made in January 2016 ___ All funds disbursed (yes/no): No___ Any delay?(yes/no): __No_ If Yes, reasons for delay & action plan to resolve: __N/A_ If Yes, will delay have impact on project completion date (yes/no): __N/A_ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: __N/A_ | Brief progress report (actual/planned): The NOU continues to monitor imports and trade of ODS and ODS related equipment. Collection of the 2016 data on ODS imports and consumption has been completed and is being analyzed for submission. NOU commenced preparation of national legislative requirement processes in planning for ratification of Kigali amendment |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor project implementation progress and the disbursement rate of approved funds.
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | AFR | NAM | SEV | 74 | TAS | 22 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-03-01 | 2016-05-01 | 2017-05-01 |  |  | 70000 | 0 | 70000 | 0 | 0% | 70000 | 65000 | 7000 | 9100 | 0 | 0 | 9100 | 8450 | Brief progress report (actual/planned): The first stakeholders meeting was organized by the NOU on 11th May, 2016 at Protea Hotel in Walvis Bay and 25 participants from the ODS Alternative user sectors and importers attended. The main goal of the meeting was to sensitize the government and industry on the survey and agree on the plan for the Survey of ODS alternatives at the national level and obtain support of main national stakeholders. Three technicians from the Vocational Training Centers (VTC) were contracted in March 2016 by the NOU to carry out the data collection process of the survey and support the data collection. The VCT Technicians assisted the NOU in the identification of the current use of ODS alternatives by substance/sector and collection of import/export data for the substances for the past a couple of years. The VCT Technicians also provided support in establishing growth patterns in use by substance/sector and in compiling data on available ODS alternatives for various applications. The NOU and the VCT Technicians drafted and cross checked the information to ensure the completion of end-user surveys, collection, analysis, and aggregation of consumption data. The various sections of the report were drafted. The second stakeholders meeting was organized by the NOU in November 2016 in Windhoek with the main goal to organise consultations with representatives of the government and private sector to finalize the outcomes of the Survey of ODS alternatives and discuss potential opportunities for introduction of those alternatives in the country. A total of 30 participants from the sectors using ODS Alternatives were in attendance. The draft report was prepared by the NOU and the VCT Technicians. It was reviewed and finalized based on the format approved by ExCom decision 75/67 as contained in document UNEP/OzL.Pro/ExCom/75/77/Rev.1 after incorporating inputs/ comments raised during National Stakeholders’ workshop. The final report was submitted to UNEP in November 2016 for final review and submission to MLFS. The NOU participated in the ODS Alternative Thematic workshop held in December 2016 to refine the draft report according to the revised template for the report. The report has been finally submitted to UNEP. Legal arrangements(actual/planned): The SSFA was drafted and signed by UNEP and the Government of Namibia in February 2016___Initial stages of project implementation(actual/planned): _Yes__ Intermediate goals achieved (actual/planned): Yes___ Project completion and follow up: _No__ First disbursement date (actual/planned): _March 2016__ All funds disbursed (yes/no): No___ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): __N/A_ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): The NOU incorporated comments from UNEP ROA and Paris and re-submitted final ODS survey report.
ONG | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, first tranche, Nauru) | Multi-Year | ASP | NAU | PHA | 63 | TAS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-12-01 | 2015-03-01 | 2017-12-01 |  |  | 45625 | 0 | 45625 | 41884.6 | 91.8% | 3740.4 | 0 | 374.04 | 5931 | 0 | 5444.7685 | 486.2315 | 0 | Brief progress report (actual/planned): UNEP conducted a mission to Nauru in March 2016 to discuss with the government on the way forward and support the country on the implementation of Montreal Protocol activities and projects in Nauru. UNEP also maintained regular communications with the management level of the Ministry to explore the way forward to expedite project implementation and maintained constant communication with interim senior management encouraging the recruitment of required staff. Due to the absence of sitting NOO since 2014, the implementation could not be implemented at the ground level. However, Nauru was able to meet 2015 obligations under the Montreal Protocol and maximum allowable consumption as agreed with the ExCom. 2015 CP data was submitted to the MLFS. Legal arrangement: The SSFA was signed in August 2012. First Mission: August 2014 TOR completed: Not applicable. First disbursement date: December 2011 All funds disbursed (yes/no): No. Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: L ost of NOU since May 2014. No defined nationally assigned resources (human nor instituional) to allow for continunity. UNEP CAP regularly communicate the management level of the Ministry for their advice on the way forward and maintained constant communication with interim senior management encouraging the recruitment of required staff . If Yes, will delay have impact on project completion date (yes/no): Yes Any ongoing problems (yes/no): Yes If Yes, is any action required by ExCom: To encourage country to expedite appointment of NOO and Montreal Protocol project implementation | Brief progress report (actual/planned): UNEP maintains regular communication with the country. A mission to Nauru is planned in 2017. |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor the appointment of a national ozone officer.
ONG | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, second tranche, Nauru) | Multi-year | ASP | NAU | PHA | 74 | TAS | 10 | A | I |  | 0 |  | 0 |  | 2015-05-01 |  | 2020-05-01 | 2020-12-01 |  |  | 20975 | 0 | 20975 | 0 | 0% | 20975 | 0 | 2097.5 | 2727 | 0 | 0 | 2727 | 0 | Brief progress report (actual/planned): The SSFA for the second tranche has been prepared based on the tranche approval by the ExCom. However, SSFA has not yet been signed due to the absence of sitting NOOs to implement the project. UNEP conducted a mission to Nauru in March 2016 to discuss with the government on the way forward and support the country on the implementation of Montreal Protocol activities and projects in Nauru. UNEP also maintained regular communications with the management level of the Ministry to explore the way forward to expedite project implementation and maintained regular communication with interim senior management encouraging the recruitment of required staff. However, Nauru was able to meet 2015 obligations under the Montreal Protocol and maximum allowable consumption as agreed with the ExCom. 2015 CP data was submitted to the MLFS. Legal arrangement: Not yet. First Mission: March 2016. TOR completed: Not applicable. First disbursement date: Not yet. All funds disbursed (yes/no): No. Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: L ost of NOU since May 2014. No defined nationally assigned resources (human nor instituional) to allow for continunity. UNEP CAP regularly communicated the management level of the Ministry for their advice on the way forward and maintained regular communication with interim senior management encouraging the recruitment of required staff . If Yes, will delay have impact on project completion date (yes/no): Yes Any ongoing problems (yes/no): Yes If Yes, is any action required by ExCom: To encourage country to expedite appointment of NOO and Montreal Protocol project implementation | Brief progress report (actual/planned): UNEP maintains regular communication with the country. A mission to Nauru is planned in 2017. |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor the signing of the agreement by the Government and UNEP.
FIN | UNEP | Implementation of the PIC strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | NAU | REF | 44 | TAS | 01 | A | I | CFC | 0.2 | 0 | 0 | 0 | 2004-12-01 | 2005-03-01 | 2006-12-01 |  | 2008-12-01 | 2010-12-01 | 8000 | -2000 | 6000 | 6000 | 100% | 0 | 0 |  | 1040 | -260 | 780 | 0 | 0
FIN | UNEP | Implementation of the PIC strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | NAU | REF | 44 | TAS | 03 | A | I | CFC | 0.3 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2006-12-01 |  | 2007-12-01 | 2010-12-01 | 14000 | 0 | 14000 | 14000 | 100% | 0 | 0 |  | 1820 | 0 | 1820 | 0 | 0
FIN | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | NAU | SEV | 44 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-03-01 | 2005-12-01 |  | 2006-12-01 | 2007-01-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (2nd year of phase I) | Individual | ASP | NAU | SEV | 50 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2009-01-01 | 2007-11-01 |  | 2008-11-01 | 2009-11-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase II, first year) | Individual | ASP | NAU | SEV | 53 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2009-04-01 | 2008-11-01 |  | 2010-03-01 | 2010-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | ASP | NAU | SEV | 60 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-11-01 | 2011-12-01 |  | 2012-01-01 | 2013-12-01 | 52500 | 0 | 52500 | 52500 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of the institutional strengthening project (phase IV: 8/2012-7/2014) | Individual | ASP | NAU | SEV | 67 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2013-04-01 | 2014-07-01 | 2017-12-01 |  |  | 60000 | 0 | 60000 | 41443.82 | 69.07% | 18556.18 | 16000 | 1855.618 | 0 | 0 | 0 | 0 | 0 | Brief progress report: No dedicated NOO since May of 2014. Assigned staff of the Environment division attended Regional Ozone Officers Network meeting in Fiji in June 2016. UNEP conducted a mission to Nauru in March 2016 to discuss with the government on the way forward and support the country on the implementation of Montreal Protocol activities and projects in Nauru. UNEP also maintained regular communications with the management level of the Ministry to explore the way forward to expedite project implementation and maintained constant communication with interim senior management encouraging the recruitment of required staff. However, Nauru was able to meet 2015 obligations under the Montreal Protocol and maximum allowable consumption as agreed with the ExCom. 2015 Article 7 and CP data were submitted to the Ozone Secretariat and MLFS respectively. Legal arrangements(actual/planned): The SSFA was signed in March 2013. Initial stages of project implementation(actual/planned): Aug 2012/Mar 2013 Intermediate goals achieved (actual/planned): _Project was delayed due to non submission of required progress and financial reports. UNEP has made many atempts to encourage country to make the required submission: First disbursement date (actual/planned): April 2013. All funds disbursed (yes/no): No. Any delay?(yes/no): Yes. If Yes, reasons for delay & action plan to resolve: No assigned NOO since May 2014, no assigned national for the implementation of the Montreal Protocol, UNEP continued to inform high level offices (Environment and Foreign Affairs) on the status of implementation and required action. UNEP also liase with the One-UN office locate in Nauru seeking to encourage attention on this subject. If Yes, will delay have impact on project completion date (yes/no): Yes, the SSFA is now expired. New agreement will have to be established once country has submitted the required reports and informed on readyness to resume implementation. Any ongoing problems (yes/no): Yes, UNEP continued to have very close follow-up with the NOO and senior managment addressing the delays in implementation. If Yes, is any action required by ExCom: To encourage country to expedite appointment of NOO and Montreal Protocol project implementation. | Brief progress report: UNEP maintains regular communication with the country. A mission to Nauru is planned in 2017. |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor project implementation progress and the disbursement rate of approved funds.
ONG | UNEP | Extension of the institutional strengthening project (phase V: 8/2014-7/2016) | Individual | ASP | NAU | SEV | 72 | INS | 09 | A | I |  | 0 |  | 0 |  | 2014-05-01 |  | 2016-07-01 | 2018-12-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): SSFA for IS project V has not yet signed as there are pending payments/reports/activities under Phase IV. No disbursement from IS project phase V as of December 2016. Legal arrangements(actual/planned): Not yet. Initial stages of project implementation(actual/planned): Not yet. Intermediate goals achieved (actual/planned): Not yet. All funds disbursed (yes/no): No. Any delay?(yes/no): Yes. If Yes, reasons for delay & action plan to resolve: SSFA has not yet signed. No assigned NOO since May 2014, no assigned national for the implementation of the Montreal Protocol, UNEP continued to inform high level offices (Environment and Foreign Affairs) on the status of implementation and required action. UNEP also liase with the One-UN office locate in Nauru seeking to encourage attention on this subject. If Yes, will delay have impact on project completion date (yes/no): Yes. Agreement will have to be established once country has submitted the required reports from Phave IV . Any ongoing problems (yes/no): Yes, UNEP continued to have very close follow-up with the NOO and senior managment addressing the delays in implementation. If Yes, is any action required by ExCom: o encourage country to expedite appointment of NOO and Montreal Protocol project implementation. | Brief progress report (actual/planned): UNEP maintains regular communication with the country. A mission to Nauru is planned in 2017. |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor project implementation progress and the disbursement rate of approved funds.
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | ASP | NAU | SEV | 75 | TAS | 11 | A | I |  | 0 |  | 0 |  | 2015-11-01 |  | 2016-12-01 | 2017-06-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 0 | 4000 | 5200 | 0 | 0 | 5200 | 0 | Brief progress report (actual/planned): UNEP conducted country mission in March of 2016 seeking to reach high level attention for conducting the ODS alternative survey as was approved by the 75th ExCom . Country at the levels of Directors of Environment, Commece and Climate attended the ODS alternative survey regional Thematic workshop in Fiji in June 2016. In the margins of this June 2016 meetings this was further discussion were held on the national approach for conducting the ODS alternative surveys- Country has indicated limited national capacity and is suggesting that UNEP seek to conduct direct implementation on the management of the ODS alternative survey. Legal arrangements(actual/planned): Not yet. Initial stages of project implementation(actual/planned): Not yet. Intermediate goals achieved (actual/planned): Not applicable. Project completion and follow up: Not applicable. First disbursement date (actual/planned): Not yet. All funds disbursed (yes/no): No. Any delay?(yes/no): Yes. If Yes, reasons for delay & action plan to resolve: Lost of NOU since May 2014. No defined nationally assigned resources (human nor instituional) to allow for continunity and limited national capacity to conduct the survey. Country advised to use direct implementation approach to implement this project. If Yes, will delay have impact on project completion date (yes/no): N/o. Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): UNEP regularly communicates with the government on the project implementation. UNEP's consultant visited Nauru in the third week of February to conduct national data collection, which will be used for the analysis and preparation of the report.
ONG | UNEP | Destruction of confiscated ODS | Individual | ASP | NEP | DES | 59 | TAS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-03-01 | 2011-05-01 | 2017-12-01 |  |  | 157200 | 0 | 157200 | 155175.75 | 98.71% | 2024.25 | 2024.25 | 202.425 | 20436 | 0 | 20172.8475 | 263.1525 | 263.1525 | Brief progresss report: A final report looking at the establishing a national system for ODS desctruction is beeing prepared. Legal arrangements(actual/planned): ___ Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): ___ All funds disbursed (yes/no): ___ Any delay?(yes/no): ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___ | Brief progresss report: A final report looking at the establishing a national system for ODS desctruction is beeing prepared. Legal arrangements(actual/planned): ___ Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): ___ All funds disbursed (yes/no): ___ Any delay?(yes/no): ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | ASP | NEP | PHA | 50 | PRP | 19 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-11-01 | 2007-11-01 |  | 2008-01-01 | 2008-01-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | ASP | NEP | PHA | 50 | PRP | 20 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-05-01 | 2007-11-01 |  | 2007-07-01 | 2011-11-01 | 15000 | -10146 | 4854 | 4854 | 100% | 0 | 0 | 0 | 1125 | -760.95 | 364.05 | 0 | 0 | Completed in 2007. |  | 2006 |  | Investment
FIN | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | ASP | NEP | PHA | 52 | INV | 22 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-07-01 | 2009-06-01 | 2009-07-01 |  | 2010-12-01 | 2011-06-01 | 75000 | -86.06 | 74913.94 | 74914 | 100% | -0.06 | 0 | 0 | 6750 | -7.75 | 6742.26 | -0.01 | 0 | Completed in 2009. Financially completed in 2011. |  | 2007 |  | Investment
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-year | ASP | NEP | PHA | 52 | TAS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2008-04-01 | 2008-07-01 |  | 2009-04-01 | 2010-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 |  | 4550 | 0 | 4550 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | NEP | PHA | 55 | PRP | 23 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-10-01 | 2009-07-01 |  | 2011-01-01 | 2012-12-01 | 85000 | -13954 | 71046 | 71046 | 100% | 0 | 0 |  | 11050 | -1814.02 | 9235.98 | 0 | 0
FIN | UNDP | Terminal phase-out management plan (second tranche) | Multi-Year | ASP | NEP | PHA | 57 | INV | 26 | N | I | CFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2011-09-01 | 2011-03-01 |  | 2013-12-01 | 2014-06-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 2250 | 0 | 2250 | 0 | 0 | Financially completed in 2014. | Completed in 2013. Second and final disbursement under LoA expected to be made in Q2 of 2014 after respective milestone is achieved. | 2009 |  | Investment
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | ASP | NEP | PHA | 57 | TAS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-07-01 | 2010-03-01 |  | 2010-03-01 | 2011-03-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 |  | 4550 | 0 | 4550 | 0 | 0
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | ASP | NEP | PHA | 66 | INV | 30 | N | I | HCFC | 0.1 | 0.1 | 0 | 0 | 2012-04-01 | 2015-06-01 | 2015-04-01 | 2017-06-01 |  |  | 42000 | 0 | 42000 | 8000 | 19.05% | 34000 | 0 | 13600 | 3780 | 0 | 720 | 3060 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): In 2016 much progress has not been done due to New Ozone Officer and Country settling after earth quake. Prodoc signed (actual/planned, yes/no and date):LoA signed December 2013 and revised on 24th April 2015 Missions undertaken (actual/planned):- TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: Contract signed First disbursement date (actual/planned): 42156Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:Due to natural calamities and New Ozone officer. | Douments sent to NOO for signature and pending for approval. | 2012 |  | Investment |  | To request the submission of additional status report to the 79th meeting to monitor the delivery of the equipment.
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | NEP | PHA | 66 | TAS | 29 | A | I |  | 0.2 | 0 | 0 | 0 | 2012-04-01 | 2012-10-01 | 2015-04-01 | 2017-03-01 |  |  | 63000 | 0 | 63000 | 30800.5 | 48.89% | 32199.5 | 32199.5 | 3219.95 | 8190 | 0 | 4004.065 | 4185.935 | 4185.935 | Brief progress report (actual/planned): technician training in Dec 2016, ODS survey workshops in 2016. As part of feasibility study report for the destruction project submitted in July 2016, stockpiles of 13MT of ODS confiscated by customs will be adjusted against the annual quota for 2017-2018 Legal arrangement (actual/ planned): Amended to end March 2017 First mission (actual/planned): Dec 2016 TOR completed (actual/planned): First disbursement date (actual/planned): ___ All funds disbursed (yes/no): No Any delay? (yes/no): ___ If Yes, reasons for delay & action plan to resolve: The DG has assumed the role of Ozone Officer who is assisted by a team of 3 in NBSM to handle Ozone matters. During the recent mission to Nepal in December 2016, the DG has been advised to appoint a full time Ozone officer. If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): Annual quota being issued taking into account the confiscated amount of 13MT of ODS. Legal arrangement (actual/ planned): Amended to end March 2017 First mission (actual/planned): Dec 2016 TOR completed (actual/planned): First disbursement date (actual/planned): ___ All funds disbursed (yes/no): No Any delay? (yes/no): ___ If Yes, reasons for delay & action plan to resolve: The DG has assumed the role of Ozone Officer who is assisted by a team of 3 in NBSM to handle Ozone matters. During the recent mission to Nepal in December 2016, the DG has been advised to appoint a full time Ozone officer. If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___ |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor the appointment of a national ozone officer.
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | ASP | NEP | PHA | 75 | INV | 35 | N | I | HCFC | 0.1 | 0 | 0 | 0 | 2015-11-01 |  | 2019-12-01 | 2017-12-01 |  |  | 33600 | 0 | 33600 | 0 | 0% | 33600 | 0 | 13440 | 3024 | 0 | 0 | 3024 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Waiting for signature from NOO Prodoc signed (actual/planned, yes/no and date):Letter of Authorisation sent 18 November 2016 Missions undertaken (actual/planned):- TOR for consultants/subcontracts completed (actual/planned): Contract/PO/MOA agreements signed: First disbursement date (actual/planned): Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | Douments sent to NOO for signature and pending for approval. | 2015 |  | Investment
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | ASP | NEP | PHA | 75 | TAS | 34 | A | I |  | 0.2 |  | 0 |  | 2015-11-01 | 2016-10-01 | 2019-12-01 | 2021-07-01 |  |  | 50400 | 0 | 50400 | 0 | 0% | 50400 | 50400 | 5040 | 6552 | 0 | 0 | 6552 | 6552 | Brief progress report (actual/planned): Border dialogue in december 2016, Participation in customs training in India with NACEN in Dec 2016. Technician trainings planned. Legal arrangement (actual/ planned): SSFA in place First mission (actual/planned): Dec 2016 TOR completed (actual/planned): First disbursement date (actual/planned): actual Oct 2016 All funds disbursed (yes/no): No Any delay? (yes/no): ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): Activities for introducing the standards for flammable and toxic refrigerants planned. Activities for tourism and hotel industry planned. Legal arrangement (actual/ planned): SSFA in place First mission (actual/planned): Dec 2016 TOR completed (actual/planned): First disbursement date (actual/planned): actual Oct 2016 All funds disbursed (yes/no): No Any delay? (yes/no): ___ If Yes, reasons for delay & action plan to resolve: The DG has assumed the role of Ozone Officer who is assisted by a team of 3 in NBSM to handle Ozone matters. During the recent mission to Nepal in December 2016, the DG has been advised to appoint a full time Ozone officer. If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___ |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor the appointment of a national ozone officer.
FIN | UNEP | Development of refrigerant management plan | RMP | ASP | NEP | REF | 24 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1999-02-01 |  | 1999-06-01 | 2000-06-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0
FIN | UNDP | Preparation of a refrigeration recovery and recycling project | Individual | ASP | NEP | REF | 27 | PRP | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-01 | 2000-04-01 |  | 1999-07-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1999 |  | Investment
FIN | UNDP | Project preparation in the commercial refrigeration subsector | Individual | ASP | NEP | REF | 27 | PRP | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-04-01 | 2001-12-01 | 20000 | -15000 | 5000 | 5000 | 100% | 0 | 0 | 0 | 2600 | -1950 | 650 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1999 |  | Investment
FIN | UNEP | Implementation of the RMP: policy development and related information dissemination | Individual | ASP | NEP | REF | 28 | TAS | 06 | A | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-06-01 | 2000-08-01 |  | 2001-12-01 | 2002-10-01 | 6000 | 0 | 6000 | 6000 | 100% | 0 | 0 |  | 780 | 0 | 780 | 0 | 0 |  |  |  | 2001-12-01
FIN | UNDP | Implementation of the RMP: monitoring activities included in the RMP | RMP-Component | ASP | NEP | REF | 28 | TAS | 07 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-07-01 | 2005-01-01 | 2002-02-01 |  | 2005-12-01 | 2007-03-01 | 8894 | -3329 | 5565 | 5565 | 100% | 0 | 0 | 0 | 1156.22 | -432.69 | 723.5324 | -0.0024 | 0 | Completed in 2005. Financially completed in 2007. |  | 1999 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: national programme for recovery and recycling of refrigerants | RMP-Component | ASP | NEP | REF | 28 | TAS | 08 | A | I | CFC | 6 | 6 | 0 | 0 | 1999-07-01 | 2001-05-01 | 2002-02-01 |  | 2003-10-01 | 2003-11-01 | 88577 | -1 | 88576 | 88576 | 100% | 0 | 0 | 0 | 11515.01 | 0 | 11515.01 | 0 | 0 | Completed in 2003. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNEP | Implementation of the RMP: training of trainers in refrigeration | Individual | ASP | NEP | REF | 28 | TRA | 09 | A | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-04-01 | 2001-02-01 |  | 2004-03-01 | 2004-10-01 | 70000 | -29000 | 41000 | 41000 | 100% | 0 | 0 |  | 9100 | -3770 | 5330 | 0 | 0
FIN | UNEP | Implementation of the RMP: training in monitoring and control of CFC and establishment of import/export licensing system | Individual | ASP | NEP | REF | 28 | TRA | 10 | A | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-06-01 | 2001-08-01 |  | 2004-07-01 | 2006-02-01 | 44400 | -19400 | 25000 | 25000 | 100% | 0 | 0 |  | 5772 | -2522 | 3250 | 0 | 0 |  |  |  | 2002-12-01
FIN | UNDP | Project preparation for the refrigerant management plan update | Individual | ASP | NEP | REF | 43 | PRP | 12 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-07-01 | 2005-07-01 |  | 2005-07-01 | 2006-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 1500 | 0 | 1500 | 0 | 0 | Completed in 2005. Financially completed in 2006. |  | 2004 |  | Investment
FIN | UNEP | Implementation of the RMP: assistance to remain in compliance with the Montreal Protocol | Individual | ASP | NEP | REF | 44 | TAS | 15 | A | I | CFC | 10.8 | 5.4 | 0 | 0 | 2004-12-01 | 2005-05-01 | 2007-12-01 |  | 2008-01-01 | 2008-10-01 | 51440 | 0 | 51440 | 51440 | 100% | 0 | 0 |  | 6687 | 0 | 6687 | 0 | 0
FIN | UNDP | Implementation of the RMP: recovery and recycling, retrofit and their monitoring | RMP-Component | ASP | NEP | REF | 44 | TAS | 16 | N | I | CFC | 12.1 | 12.1 | 0 | 0 | 2004-12-01 | 2009-05-01 | 2007-12-01 |  | 2009-12-01 | 2011-11-01 | 57495 | -6049.7 | 51445.3 | 51445 | 100% | 0.3 | 0 | 0 | 5175 | -544.52 | 4630.4527 | 0.027302 | 0 | Completed in 2009. |  | 2004 |  | Investment
FIN | UNEP | Country programme preparation | Individual | ASP | NEP | SEV | 19 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1997-05-01 | 1997-08-01 |  | 1998-11-01 | 1999-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Establishment of an Ozone Unit | Individual | ASP | NEP | SEV | 26 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-07-01 | 2001-12-01 |  | 2002-05-01 | 2003-12-01 | 62000 | 0 | 62000 | 62000 | 100% | 0 | 0 |  | 8060 | 0 | 8060 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (Phase 2) | Individual | ASP | NEP | SEV | 37 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2002-12-01 | 2004-08-01 |  | 2004-08-01 | 2007-06-01 | 53733 | 0 | 53733 | 53733 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | ASP | NEP | SEV | 44 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-03-01 | 2006-12-01 |  | 2006-12-01 | 2007-01-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | ASP | NEP | SEV | 50 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2008-11-01 |  | 2008-11-01 | 2008-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | ASP | NEP | SEV | 56 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-02-01 | 2010-11-01 |  | 2010-11-01 | 2011-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VI) | Individual | ASP | NEP | SEV | 61 | INS | 28 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2010-12-01 | 2012-11-01 |  | 2012-11-01 | 2013-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VII: 12/2012-11/2014) | Individual | ASP | NEP | SEV | 67 | INS | 31 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2013-03-01 | 2014-11-01 |  | 2015-09-01 | 2016-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed | Project financially completed
ONG | UNEP | Extension of the institutional strengthening project (phase VIII: 12/2014-11/2016) | Individual | ASP | NEP | SEV | 72 | INS | 32 | A | I |  | 0 |  | 0 |  | 2014-05-01 | 2015-12-01 | 2016-11-01 | 2017-12-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 60000 | 6000 | 0 | 0 | 0 | 0 | 0 | Brief progress report(actual/planned): Quota system implemented. Continued monitoring with enforcement authorities and customs. 2 Technicians training conducted. Awareness raising activities on alternatives conducted. Terminal request for extension to phase IX prepared and submitted. Legal arrangements(actual/planned): SSFA ongoing till Dec 2017 Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): ____ Project completion and follow up: First disbursement date(actual/planned): actual Apr 2016 All funds disbursed (yes/no): No 2 more Any delay?(yes/no): slow progress overall in the country due to low capacity and ongoing reconstruction efforts after the earthquake If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___ | Brief progress report(actual/planned): A7 and CP data being submitted. Due to the Earthquake and no Ozone Officer in place the progress has been very slow. 40 percent funds have been disbursed Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): ____ Project completion and follow up: First disbursement date(actual/planned): actual Apr 2016 All funds disbursed (yes/no): No 2 more Any delay?(yes/no): slow progress overall in the country due to low capacity and ongoing reconstruction efforts after the earthquake If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___ |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor project implementation progress and the disbursement rate of approved funds.
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | ASP | NEP | SEV | 74 | TAS | 33 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-05-01 | 2016-05-01 | 2017-06-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 40000 | 4000 | 5200 | 0 | 0 | 5200 | 5200 | Brief progress report(actual/planned): ToR developed and consultant recruited. Survey conducted. Stakeholder consultations meetings held, one during the mission by UNEP in Oct 2016. Full draft of the survey report submitted for review by UNEP. Legal arrangements(actual/planned): SSFA and amended to extend to Dec 2017 Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date(actual/planned): actual May 2016 All funds disbursed (yes/no): No Any delay?(yes/no): ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___ | Brief progress report(actual/planned): Comments on the first draft sent by UNEP Feb 2017. Comments are currently being incorporated into the final draft of the survey report. Legal arrangements(actual/planned): SSFA amended to extend activities Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date(actual/planned): actual May 2016 All funds disbursed (yes/no): No Any delay?(yes/no): ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___
ONG | UNEP | Extension of the institutional strengthening project (phase IX: 12/2016-11/2018) | Individual | ASP | NEP | SEV | 77 | INS | 36 | A | I |  | 0 |  | 0 |  | 2016-12-01 |  | 2018-11-01 | 2018-11-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | Newly approved project | Brief progress report (actual/planned): Detailed work plan developed and agreed. Legal arrangements(actual/planned): SSFA in the process of being signed by UNEP Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): planned in May 2017 All funds disbursed (yes/no): ___ Any delay?(yes/no): ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___
FIN | UNEP | Technical assistance in CTC management | Individual | ASP | NEP | SOL | 47 | TAS | 17 | A | I | CTC | 0.9 | 0.9 | 0 | 0 | 2005-11-01 | 2006-02-01 | 2007-12-01 |  | 2008-01-01 | 2008-06-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0
TRF | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | AFR | NER | PHA | 48 | PRP | 17 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 |  | 2007-04-01 |  |  | 2007-12-01 | 12000 | -12000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 900 | -900 | 0 | 0 | 0 | Transferred in 2007. Financially Completed in 2007. |  | 2006 |  | Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | NER | PHA | 48 | PRP | 18 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-01-01 | 2007-04-01 |  | 2008-11-01 | 2009-11-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 |  | 2340 | 0 | 2340 | 0 | 0
FIN | UNIDO | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | AFR | NER | PHA | 53 | PRP | 20 | A | I |  | 0 | 0 |  |  | 2007-11-01 | 2008-04-01 | 2009-03-01 |  | 2008-12-01 | 2009-03-01 | 12000 | -6598 | 5402 | 5401.91 | 100% | 0.09 | 0 |  | 900 | -495 | 405 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | NER | PHA | 54 | INV | 21 | A | I |  | 0 | 0 |  |  | 2008-04-01 | 2009-12-01 | 2010-03-31 |  | 2010-12-01 | 2012-12-01 | 131000 | -185 | 130815 | 130814.51 | 100% | 0.49 | 0 |  | 11790 | -17 | 11773 | 0 | 0 | FIN |  |  |  | INV
FIN | UNEP | Terminal phase out management plan (first tranche) | Multi-Year | AFR | NER | PHA | 54 | TAS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-09-01 | 2010-03-01 |  | 2010-04-01 | 2011-03-01 | 81000 | -1000 | 80000 | 80000 | 100% | 0 | 0 |  | 10530 | -130 | 10400 | 0 | 0
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | AFR | NER | PHA | 55 | PRP | 22 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-10-01 | 2009-07-31 |  | 2011-07-01 | 2013-12-01 | 85000 | -7688 | 77312 | 77311.52 | 100% | 0.48 | 0 |  | 6375 | -577 | 5798 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Terminal phase out management plan (second tranche) | Multi-Year | AFR | NER | PHA | 58 | INV | 23 | A | I | CFC | 4.8 | 4.8 |  |  | 2009-07-01 | 2010-12-01 | 2010-07-31 |  | 2012-02-01 | 2012-12-01 | 53000 | -17 | 52983 | 52983.49 | 100% | -0.49 | 0 |  | 4770 | -1 | 4769 | 0 | 0 | FIN |  |  |  | INV
FIN | UNEP | Terminal phase out management plan (second tranche) | Multi-Year | AFR | NER | PHA | 58 | TAS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2009-10-01 | 2010-07-01 |  | 2010-12-01 | 2012-07-01 | 68000 | 0 | 68000 | 68000 | 100% | 0 | 0 |  | 8840 | 0 | 8840 | 0 | 0
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | NER | PHA | 66 | INV | 28 | A | I | HCFC | 1.7 | 1.7 |  |  | 2012-04-01 | 2012-11-01 | 2016-04-30 | 2017-06-01 |  |  | 175000 | 0 | 175000 | 69051.37 | 39.46% | 105948.63 | 93158 | 100000 | 13125 | 0 | 5179 | 7946 | 6986.85 | Equipment delivery was achieved and training in connection with equipment use and calibration took place in September 2016. Closure of the project will be achieved in 2017, remaining tranche balance will ensure HPMP coordination activities in the country first half of 2017. Was there any delay during the reporting year? No Any impact on project completion date: Yes, actual completion is planned for Jun 17 in order to ensure that the funds are utilized to monitor and coordinated activities in the first half of 2017 in preparation for the next tranche. Any action required by Executive Committee? No | Remaining balance of the tranche one ensures monitoring coordination activities first quarter of 2017, since tranche II will be submitted for consideration by 79 ExCom. |  |  | INV |  | To request the submission of additional status report to the 79th meeting to monitor the completion of the calibration of the equipment.
COM | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | NER | PHA | 66 | TAS | 27 | A | I |  | 1 | 0 | 0 | 0 | 2012-04-01 | 2012-12-01 | 2016-04-01 |  | 2015-12-01 |  | 100000 | 0 | 100000 | 64089.58 | 64.09% | 35910.42 | 35000 | 35910 | 13000 | 0 | 8331.6454 | 4668.3546 | 4550 | Brief progress report (actual/planned): Legal arrangements (actual/planned): Agreement signed in July 2012. SSFA expired in May 2014. SSFA amended for extension until January 2017 with a balance of US $ 20,000. All activities under the SSFA are completed (as planned) YES___ First mission (actual/planned): _ July 2012 - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in July 2012 __ All funds disbursed (yes/no): No__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: | Brief progress report (actual/planned): Legal arrangements (actual/planned): Agreement signed in July 2012. SSFA expired in May 2014. SSFA amended for extension until January 2017 with a balance of US $ 20,000. All activities under the SSFA are completed (as planned) YES___ First mission (actual/planned): _ July 2012 - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in July 2012 __ All funds disbursed (yes/no): No__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom:
ONG | UNIDO | Verification report for stage I of HCFC phase-out management plan | Individual | AFR | NER | PHA | 71 | TAS | 29 | A | I |  | 0 | 0 |  |  | 2013-12-01 | 2016-12-01 | 2016-05-31 | 2017-12-01 |  |  | 30000 | 0 | 30000 | 2044.91 | 6.816% | 27955.09 | 0 | 20000 | 2700 | 0 | 184 | 2516 | 0 | Contracts with national counterpart were issued; Consultants were selected at national level; elaboration of the Verification report is ongoing. Data verification covers years 2014 and 2015. Was there any delay during the reporting year? No Any impact on project completion date: Yes, The additional funding for verification report has been approved 2 years in advance of the HPMP tranche submission, while the report is required with the tranche submission (scheduled in the year 2017 as per the Agreement between ExCom and Gov of Niger). Any action required by Executive Committee? No | Data verification report to address 2016 consumption data has been initiated. Project will be completed in 2017. |  |  | NON-INV
FIN | UNDP | Project preparation in refrigeration recycling | Individual | AFR | NER | REF | 21 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1999-03-01 | 2002-03-01 | 20000 | -3085 | 16915 | 16915 | 100% | 0 | 0 | 0 | 2600 | -401 | 2199 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNEP | Implementation of the RMP: customs officers training programme | Individual | AFR | NER | REF | 27 | TAS | 05 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-08-01 | 2000-10-01 |  | 2003-12-01 | 2005-02-01 | 63000 | -24000 | 39000 | 39000 | 100% | 0 | 0 |  | 8190 | -3120 | 5070 | 0 | 0
FIN | UNDP | Implementation of the RMP: Monitoring of the activities included in the RMP | RMP-Component | AFR | NER | REF | 27 | TAS | 06 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 2002-01-01 | 2001-04-01 |  | 2004-12-01 | 2005-11-01 | 15455 | -3305 | 12150 | 12150 | 100% | 0 | 0 | 0 | 2009.15 | -429.62 | 1579.5321 | -0.0021 | 0 | Completed in 2004. Financially completed in 2005. |  | 1999 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: National programme for recovery and recycling of refrigerants | RMP-Component | AFR | NER | REF | 27 | TAS | 07 | A | I | CFC | 5.8 | 5.8 | 0 | 0 | 1999-03-01 | 2001-06-01 | 2001-04-01 |  | 2003-08-01 | 2003-10-01 | 87603 | -8661 | 78942 | 78942 | 100% | 0 | 0 | 0 | 11388.39 | -1126 | 10262.39 | 0 | 0 | Completed in 2003. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNEP | Implementation of the RMP: train the trainers programme in the refrigeration sector | Individual | AFR | NER | REF | 27 | TAS | 08 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-08-01 | 2000-10-01 |  | 2002-05-01 | 2003-05-01 | 41500 | 0 | 41500 | 41500 | 100% | 0 | 0 |  | 5395 | 0 | 5395 | 0 | 0
FIN | UNDP | Preparation of the refrigerant management plan update | Individual | AFR | NER | REF | 37 | PRP | 10 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-07-01 | 2002-08-01 | 2003-08-01 |  | 2003-11-01 | 2005-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNEP | Implementation of the RMP update: monitoring of the activities | Individual | AFR | NER | REF | 42 | TAS | 15 | A | I | CFC | 6 | 6 | 0 | 0 | 2004-04-01 | 2004-08-01 | 2006-04-01 |  | 2007-04-01 | 2007-12-01 | 23000 | 0 | 23000 | 23000 | 100% | 0 | 0 |  | 2990 | 0 | 2990 | 0 | 0
FIN | UNEP | Implementation of the RMP update: training for customs technicians | Individual | AFR | NER | REF | 42 | TRA | 13 | A | I | CFC | 6.6 | 6.6 | 0 | 0 | 2004-04-01 | 2004-08-01 | 2005-04-01 |  | 2007-04-01 | 2007-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0
FIN | UNEP | Implementation of the RMP update: train the trainer programme for refrigeration service technicians | Individual | AFR | NER | REF | 42 | TRA | 14 | A | I | CFC | 14.6 | 14.6 | 0 | 0 | 2004-04-01 | 2004-08-01 | 2005-10-01 |  | 2006-12-01 | 2008-06-01 | 55747 | -1501 | 54246 | 54246 | 100% | 0 | 0 |  | 7247 | -195.13 | 7051.87 | 0 | 0
FIN | UNEP | Country programme preparation | Individual | AFR | NER | SEV | 11 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1995-02-01 |  | 1994-12-01 | 1995-12-01 | 43000 | 0 | 43000 | 43000 | 100% | 0 | 0 |  | 5590 | 0 | 5590 | 0 | 0
FIN | UNEP | Creation of an Ozone Secretariat | Individual | AFR | NER | SEV | 15 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-12-01 | 1997-12-01 |  | 1999-05-01 | 1999-10-01 | 74800 | 0 | 74800 | 74800 | 100% | 0 | 0 |  | 9724 | 0 | 9724 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project | Individual | AFR | NER | SEV | 26 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2000-12-01 |  | 2001-06-01 | 2003-01-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (Phase III) | Individual | AFR | NER | SEV | 33 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-06-01 | 2003-04-01 |  | 2003-12-01 | 2004-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Policy and technical assistance | Individual | AFR | NER | SEV | 37 | TAS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-01-01 | 2003-08-01 |  | 2004-01-01 | 2007-01-01 | 10000 | -1995 | 8005 | 8005 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project: phase 4 | Individual | AFR | NER | SEV | 41 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-08-01 | 2005-12-01 |  | 2005-12-01 | 2007-01-01 | 64827 | 0 | 64827 | 64827 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase V) | Individual | AFR | NER | SEV | 47 | INS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-04-01 | 2007-12-01 |  | 2007-12-01 | 2008-12-01 | 64827 | 0 | 64827 | 64827 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase VI) | Individual | AFR | NER | SEV | 53 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-11-01 |  | 2010-03-01 | 2011-03-01 | 64827 | -545 | 64282 | 64282 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase VII) | Individual | AFR | NER | SEV | 59 | INS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-02-01 | 2011-11-01 |  | 2011-12-01 | 2011-12-01 | 35115 | 29713 | 64828 | 64828 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase VIII: 1/2012-12/2013) | Individual | AFR | NER | SEV | 65 | INS | 26 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-04-01 | 2013-12-01 |  | 2013-08-01 | 2014-08-01 | 64828 | 0 | 64828 | 64828 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of institutional strengthening project (phase IX: 1/2014-12/2015) | Individual | AFR | NER | SEV | 71 | INS | 30 | A | I |  | 0 |  | 0 |  | 2013-12-01 | 2014-05-01 | 2015-12-01 |  | 2015-12-01 | 2016-12-01 | 64828 | 0 | 64828 | 64828 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Legal arrangements (actual/planned): Agreement signed in May 2014. Country reported 2015. Art5 data and CP data for 2015. NOU trained 74 RAC technicians and 40 custom officers. All activities under the SSFA are completed (as planned) YES_ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in June 2014 __ All funds disbursed (yes/no): _ Yes, last payment sent in September 2015_ Any delay? (yes/no): no, SSFA expired with balance US $ 0.___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Project financially completed.
ONG | UNIDO | Survey of ODS alternatives at the national level | Individual | AFR | NER | SEV | 74 | TAS | 31 | A | I |  | 0 | 0 |  |  | 2015-05-01 |  | 2016-05-31 | 2017-12-01 |  |  | 70000 | 0 | 70000 | 0 | 0% | 70000 | 50000 | 60000 | 6300 | 0 | 0 | 6300 | 4500 | ToR reviewed and developed and contractual arrangement concluded based on the Guidelines released by MLF Secretariat. IC was contracted for assisting data collection process executed by national consultants. | Draft survey is under elaboration and will be submitted to the 80th ExCom. |  |  | NON-INV
ONG | UNEP | Extension of institutional strengthening project (phase X: 1/2016-12/2017) | Individual | AFR | NER | SEV | 75 | INS | 32 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-04-01 | 2017-12-01 | 2017-12-01 |  |  | 85000 | 0 | 85000 | 15586 | 18.34% | 69414 | 69414 | 6941.4 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): SSFA signed in March 2016 and First payment sent in April 2016. Country reported 2015 Art5 data and CP data for 2015. Legal arrangements (actual/planned): Agreement signed in March 2016. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _April 2016 - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in April 2016 __ All funds disbursed (yes/no): _ Final payment _ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Brief progress report (actual/planned): SSFA signed in March 2016 and First payment sent in April 2016. Country reported 2015 Art5 data and CP data for 2015. Legal arrangements (actual/planned): Agreement signed in March 2016. NOU trained 74 RAC technicians and 40 custom officers. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _April 2016 - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in April 2016 __ All funds disbursed (yes/no): _ Final payment _ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
FIN | UNDP | Project preparation for the formulation of transitional strategy for aerosol inhalant drug products | Individual | LAC | NIC | ARS | 42 | PRP | 11 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2005-07-01 | 2005-04-01 |  | 2008-03-01 | 2009-07-01 | 30000 | -44 | 29956 | 29956 | 100% | 0 | 0 | 0 | 2250 | -3.3 | 2246.7 | 0 | 0 | Completed in 2008.Financially completed in 2009. |  | 2004 |  | Investment
FIN | UNIDO | Preparation of a project for the phase-out of methyl bromide soil fumigation | Individual | LAC | NIC | FUM | 34 | PRP | 07 | A | I |  | 0 | 0 |  |  | 2001-07-01 | 2001-09-01 | 2002-08-01 |  | 2003-05-01 | 2003-12-01 | 30000 | -27242 | 2758 | 2757.82 | 99.99% | 0.18 | 0 |  | 3900 | -3542 | 358 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Training and awareness workshop in the fumigants sector (methyl bromide) | Individual | LAC | NIC | FUM | 45 | TAS | 12 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2006-05-01 | 2006-04-01 |  | 2006-12-01 | 2007-12-01 | 30000 | -275 | 29725 | 29725.16 | 100% | -0.16 | 0 |  | 2700 | -25 | 2675 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNDP | Project preparation for a terminal phase-out management plan | Individual | LAC | NIC | PHA | 49 | PRP | 18 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2006-07-01 | 2008-02-01 | 2007-07-01 |  | 2008-09-01 | 2010-01-01 | 15000 | -1041.83 | 13958.17 | 13958 | 100% | 0.17 | 0 | 0 | 1125 | -78.14 | 1046.85 | 0.00995 | 0 | Financially completed in 2010. |  | 2006 |  | Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | LAC | NIC | PHA | 49 | PRP | 19 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2008-06-01 | 2007-07-01 |  | 2009-03-01 | 2010-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | LAC | NIC | PHA | 55 | PRP | 21 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 |  | 2011-12-01 | 2011-12-01 | 85000 | -130 | 84870 | 84869.65 | 100% | 0.35 | 0 |  | 6375 | -10 | 6365 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNDP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | NIC | PHA | 56 | INV | 23 | N | I | CFC | 3.7 | 3.7 | 0 | 0 | 2008-11-01 | 2009-05-01 | 2010-11-01 |  | 2010-11-01 | 2013-02-01 | 320000 | -42.35 | 319957.65 | 319958 | 100% | -0.35 | 0 | 0 | 24000 | -3.18 | 23996.8499 | -0.02995 | 0 | Financially completed in 2013. |  | 2008 |  | Investment
FIN | UNEP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | NIC | PHA | 56 | TAS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-09-01 | 2010-11-01 |  | 2012-06-01 | 2013-12-01 | 130000 | 0 | 130000 | 130000 | 100% | 0 | 0 |  | 16900 | 0 | 16900 | 0 | 0
FIN | UNEP | Terminal phase-out management plan for Annex A Group I substances (second tranche) | Multi-Year | LAC | NIC | PHA | 60 | TAS | 25 | A | I | CFC-12 | 2 | 2 | 0 | 0 | 2010-04-01 | 2011-09-01 | 2011-04-01 |  | 2012-04-01 | 2013-12-01 | 70000 | -2940.5 | 67059.5 | 67059.5 | 100% | 0 | 0 |  | 9100 | -382.27 | 8717.73 | 0 | 0
COM | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | NIC | PHA | 66 | INV | 27 | A | I | HCFC | 0.5 | 0.5 |  |  | 2012-04-01 | 2012-09-01 | 2015-04-30 |  | 2015-12-01 |  | 96500 | 0 | 96500 | 94199.05 | 97.62% | 2300.95 | 0 | 1 | 8685 | 0 | 8478 | 207 | 0 | The project was operationally completed. |  |  |  | INV
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | LAC | NIC | PHA | 66 | TAS | 26 | A | I |  | 0.2 | 0 | 0 | 0 | 2012-04-01 | 2013-07-01 | 2015-04-01 |  | 2016-12-01 |  | 38000 | 0 | 38000 | 38000 | 100% | 0 | 0 |  | 4940 | 0 | 4940 | 0 | 0 | Brief progress report: Monitoring of the HPMP implementation carried out as planned. Legal arrangements (actual/planned): The legal agreement (SSFA) signed in 2013 has expired. A new SSFA to complete the implementation of this project was signed in February 2016. First mission (actual/planned): N/A. TOR completed(actual/planned): N/A. First disbursement date (actual/planned): July 2013/October 2012. All funds disbursed (yes/no): Yes. Remaining budget transferred to the Government in April 2016. Any delay? (yes/no): No significant delays. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date (yes/no): Yes. Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom? No. | Project completed in 2016
COM | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Multi-Year | LAC | NIC | PHA | 73 | TAS | 30 | A | I |  | 0 |  | 0 |  | 2014-11-01 | 2015-04-03 | 2015-11-01 |  | 2016-12-01 |  | 30000 | 0 | 30000 | 21765 | 72.55% | 8235 | 0 | 30000 | 3900 | 0 | 2829.45 | 1070.55 | 0 | Project completed. PCR delivered. | Project completed. PCR delivered.
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | NIC | PHA | 74 | INV | 32 | A | I |  | 0 | 0 |  |  | 2015-05-01 |  | 2018-05-31 | 2018-11-17 |  |  | 50000 | 0 | 50000 | 0 | 0% | 50000 | 17314.35 | 25000 | 4500 | 0 | 0 | 4500 | 1558.2915 | - A reclaiming facility will be established in the country and the tools and machines were purchased. Expected delivery was August 2016, however due to administrative issues with the Customs Authorities the equipment was not released in 2016. - Local expert contracted to support the implementing activities. - No delay in implementation - No recurring problem - Project completion date changed in line with the approval of the next tranche - No action required by Executive Committee | Equipment was released from customs after months. It was not possible to obtain the tax exemption and customs duties were paid from project funds. Action towards next goals: It is expected to commission the reclaiming unit in April 2017 and continue with the project activates. - Delay in implementation - No recurring problem - Project completion date changed in line with the approval of the next tranche - No action required by Executive Committee |  |  | INV
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | NIC | PHA | 74 | TAS | 31 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-04-01 | 2018-05-01 | 2018-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 20500 | 3000 | 3900 | 0 | 0 | 3900 | 2665 | Brief progress report: In 2016, project implementation advanced according to Annual Implementation Plan. Country made progress in: a) prevention of ODS illegal trade and ODSs-based equipment smuggling, b) monitoring the ODSs importers facilities, c) promoting the recovery and recycling of refrigerants and the use of HCFCs alternatives. First mission (actual/planned): N/A. TOR completed (actual/planned): N/A. First disbursement date: April 2016/Planned for November 2015. All funds disbursed? (yes/no): No. Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: Carry over of delays caused by the transformation of financial system in UNEP from IMIS to UMOJA. This project was approved during the UMOJA black out period; which prevented the timely programming of all new projects' budget. The staff’s learning curves of this new financial platform as well as the definition of users profile to enter and approve data were gradually improved during the year. If Yes, will delay have impact on project completion date? Yes. Expected project completion date has been postponed 6 months. Any ongoing problems? No. If Yes, is any action required by ExCom? N/A. | Brief progress report: In 2017, project implementation is progressing as planned. First mission (actual/planned): N/A. TOR completed (actual/planned): N/A. First disbursement date: April 2016/Planned for November 2015. All funds disbursed? (yes/no): No. Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: Carry over of delays caused by the transformation of financial system in UNEP from IMIS to UMOJA. This project was approved during the UMOJA black out period; which prevented the timely programming of all new projects' budget. The staff’s learning curves of this new financial platform as well as the definition of users profile to enter and approve data were gradually improved during the year. If Yes, will delay have impact on project completion date? Yes. Expected project completion date has been postponed 6 months. Any ongoing problems? No. If Yes, is any action required by ExCom? N/A.
FIN | UNIDO | Project formulation of investment projects in the refrigeration sector | Individual | LAC | NIC | REF | 21 | PRP | 02 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-10-01 | 1997-08-01 |  | 1998-05-01 | 2001-12-01 | 50000 | -8349 | 41651 | 41651.46 | 100% | -0.46 | 0 |  | 6500 | -1094 | 5406 | 0 | 0 | FIN
CLO | UNIDO | Preparation of refrigerant management plan | Individual | LAC | NIC | REF | 24 | PRP | 04 | A | I |  | 0 | 0 |  |  | 1998-03-01 |  | 1999-04-01 |  |  | 2001-07-01 | 30000 | -30000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 3900 | -3900 | 0 | 0 | 0 | CLO
FIN | UNIDO | Phasing out of CFC-11 and CFC-12 with HCFC-141b and HFC 134a at Fogel S.A. in the manufacture of commercial refrigeration equipment | Individual | LAC | NIC | REF | 25 | INV | 05 | A | R | CFC | 9.6 | 9.6 |  |  | 1998-07-01 | 1998-10-01 | 1999-08-01 |  | 1999-12-01 | 2001-03-01 | 130027 | 0 | 130027 | 130027 | 100% | 0 | 0 |  | 16904 | -22 | 16882 | 0 | 0 | FIN
FIN | Finland | Implementation of the RMP: assistance in the design of policies and regulations | Individual | LAC | NIC | REF | 25 | TAS | 06 | A | I | CFC | 12.8 |  | 0 |  | 1998-07-01 | 2001-09-01 | 2000-07-01 |  | 2005-12-01 | 2009-07-01 | 225430 | -76855 | 148575 | 148575 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed |  | 1998
FIN | UNEP | Preparation of the RMP update proposal | RMP update | LAC | NIC | REF | 41 | PRP | 09 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-10-01 | 2004-12-01 |  | 2005-02-01 | 2007-01-01 | 15000 | -900 | 14100 | 14100 | 100% | 0 | 0 |  | 1950 | -117 | 1833 | 0 | 0
FIN | UNDP | Preparation of the RMP update proposal (investment component) | RMP-Component | LAC | NIC | REF | 41 | PRP | 10 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-07-01 | 2004-12-01 |  | 2005-12-01 | 2008-11-01 | 15000 | -36 | 14964 | 14964 | 100% | 0 | 0 | 0 | 1125 | -2.7 | 1122.3 | 0 | 0 | Completed in 2005. Financially Completed in 2008. |  | 2003 |  | Investment
FIN | UNDP | Implementation of the RMP update: incentive programme to promote good practices in refrigeration | RMP-Component | LAC | NIC | REF | 45 | TAS | 13 | N | I | CFC | 35.2 | 35.2 | 0 | 0 | 2005-04-01 | 2005-12-01 | 2008-04-01 |  | 2007-12-01 | 2009-07-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 7650 | 0 | 7650 | 0 | 0 | Completed in 2007.Financially completed in 2009. |  | 2005 |  | Investment
FIN | UNEP | Implementation of the RMP update: programme for prevention of illegal CFC trade | Individual | LAC | NIC | REF | 45 | TAS | 15 | A | I | CFC | 6.2 | 0 | 0 | 0 | 2005-04-01 | 2007-03-01 | 2008-04-01 |  | 2011-12-01 | 2012-12-01 | 15000 | -6000 | 9000 | 9000 | 100% | 0 | 0 |  | 1950 | -780 | 1170 | 0 | 0
FIN | UNEP | Implementation of the RMP update: monitoring the activities of the RMP | Individual | LAC | NIC | REF | 45 | TAS | 16 | A | I | CFC | 12.4 | 12.4 | 0 | 0 | 2005-04-01 | 2007-01-01 | 2008-04-01 |  | 2009-06-01 | 2010-12-01 | 30000 | -1065 | 28935 | 28935 | 100% | 0 | 0 |  | 3900 | -138.45 | 3761.55 | 0 | 0
FIN | UNEP | Implementation of the RMP update: licensing and certification system for refrigeration technicians | Individual | LAC | NIC | REF | 45 | TRA | 14 | A | I | CFC | 16.6 | 16.6 | 0 | 0 | 2005-04-01 | 2005-11-01 | 2008-04-01 |  | 2009-06-01 | 2010-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNEP | Country programme preparation | Individual | LAC | NIC | SEV | 13 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1995-10-01 | 1995-10-01 |  | 1996-11-01 | 1999-03-01 | 40000 | -3825 | 36175 | 36175 | 100% | 0 | 0 |  | 5200 | -497.25 | 4702.75 | 0 | 0
FIN | UNEP | Establishment of the Technical Ozone Office | Individual | LAC | NIC | SEV | 22 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-02-01 | 2000-05-01 |  | 2000-12-01 | 2002-01-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 |  | 8580 | 0 | 8580 | 0 | 0 |  |  |  | 2000-05-01
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | LAC | NIC | SEV | 31 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2000-07-01 | 2001-03-01 | 2002-08-01 |  | 2003-09-01 | 2003-12-01 | 44000 | 0 | 44000 | 44000 | 100% | 0 | 0 |  | 5720 | 0 | 5720 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase 3) | Individual | LAC | NIC | SEV | 39 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-10-01 | 2005-04-01 |  | 2007-03-01 | 2007-12-01 | 57200 | 0 | 57200 | 57200 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase IV) | Individual | LAC | NIC | SEV | 49 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2008-02-01 | 2008-06-01 |  | 2009-09-01 | 2013-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase V) | Individual | LAC | NIC | SEV | 59 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-09-01 | 2011-12-01 |  | 2012-03-01 | 2013-12-01 | 30000 | 30000 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase VI: 4/2012-3/2014) | Individual | LAC | NIC | SEV | 66 | INS | 28 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 | 2012-10-01 | 2014-03-01 |  | 2014-03-01 | 2014-08-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Renewal of institutional strengthening project (phase VII: 1/2014-12/2015) | Individual | LAC | NIC | SEV | 71 | INS | 29 | A | I |  | 0 |  | 0 |  | 2013-12-01 | 2014-08-01 | 2015-12-01 |  | 2016-12-01 |  | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The SSFA (agreement) implementation was completed without significant delays. Third cash advance released in February 2016. 100% of total project budget has been transferred to the country. NOU has submitted the reports corresponding to all cash advances received. Legal arrangements (actual/planned): July 2014/May 2014. Initial stages of project implementation (actual/planned): N/A. Intermediate goals achieved (actual/planned): Goals achieved as planned for the year. NOO has been collecting ODS data and cross-checking information to prepare the 2015 Country Programme and Article 7 reports. The HCFCs license system continues being managed by the NOU. NOU is responsible for the HPMP implementation. Project completion and follow up: Project completed due to all expenditures are already recorded and final progress report dully submitted by the Government. First payment date (actual/planned): August 2014/Planned for June 2014. All funds disbursed? (yes/no): Yes. Any delay? (yes/no): No significant delays. If Yes, will delay have impact on project completion date? (yes/no): Yes. However, Project renewal to be submitted to the 75 ExCom meeting. Any ongoing problems? (yes/no): No. If Yes, is any action required by ExCom? N/A. | Awaiting approval of expenditure report in UMOJA before closing of project accounts
ONG | UNIDO | Survey of ODS alternatives at the national level | Individual | LAC | NIC | SEV | 74 | TAS | 33 | A | I |  | 0 | 0 |  |  | 2015-05-01 | 2015-11-01 | 2016-05-31 | 2017-11-17 |  |  | 70000 | 0 | 70000 | 18956.23 | 27.08% | 51043.77 | 39358.01 | 51000 | 6300 | 0 | 0 | 6300 | 3542.2209 | The preparation of the survey was underway in 2016, however it hasn't been completed. Reason for the delay: Government requested to change the supplier for the survey and the contract was cancelled. New bidding was opened and supplier selected. The survey is being completed. - No recurring problem - Impact on project completion date: Yes - No action required by Executive Committee | Survey was carried out and the final report is under preparation. Submission is expected to the 79th Meeting of the ExCom. |  |  | NON-INV
ONG | UNEP | Renewal of institutional strengthening project (phase VIII: 4/2016-3/2018) | Individual | LAC | NIC | SEV | 75 | INS | 34 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-09-01 | 2017-12-01 | 2018-06-01 |  |  | 85000 | 0 | 85000 | 70092.07 | 82.46% | 14907.93 | 14907.93 | 1490.793 | 0 | 0 | 0 | 0 | 0 | Brief progress report: Some progress. Legal arrangements (actual/planned): August 2016/March 2016. Initial stages of project implementation (actual/planned): Project implementation re-scheduled for last quarter of 2016 . Intermediate goals achieved (actual/planned): The NOU was responsible for Multilateral Fund project implementation. Project completion and follow up: N/A. First disbursement date (actual/planned): September 2016/May 2016. All funds disbursed (yes/no): No. Any delay?(yes/no): Yes. If Yes, reasons for delay & action plan to resolve: There were funds available from the IS Project phase VII. NOU speeded up the expenditure of this funds and did follow up to the agreement signature to implement the renewed project phase. If Yes, will delay have impact on project completion date (yes/no): Yes. Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: N/A. | Brief progress report: Project is progressing satisfactorily. Second cash advance is expected to June 2017. Legal arrangement (actual/planned): signed in August 2016/initially planned for March 2016. Initial stages of project implementation(actual/planned): Project currently ongoing. Intermediate goals achieved (actual/planned): Goals are achieved as planned for the year: NOO has been collecting ODS data and cross-checking information to prepare the 2016 Country Programme and Article 7 reports. The HCFCs license system continues being managed by the NOU. Project completion and follow up: Project ongoing. First disbursement date (actual/planned): September 2016/May 2016. All funds disbursed? (yes/no): No. Any delay? (yes/no): Some delays. If Yes, reasons for delay & action plan to resolve: Project is already progressing. There were funds available from the IS Project phase VII. NOU speeded up the expenditure of this funds and did follow up to the agreement signature to implement the renewed (phase VIII). If Yes, will delay have impact on project completion date? (yes/no): Yes, six months of delays are expected. Any ongoing problems? (yes/no): No. If Yes, is any action required by ExCom?N/A.
FIN | UNIDO | Preparation of investment project in the aerosols sector | Individual | AFR | NIR | ARS | 30 | PRP | 61 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-05-01 | 2001-04-01 |  | 2000-10-01 | 2001-09-01 | 25000 | -9266 | 15734 | 15733.87 | 100% | 0.13 | 0 |  | 3250 | -1208 | 2042 | 0 | 0 | FIN
FIN | UNIDO | Preparation for a pilot demonstration project on ODS waste management and disposal | Individual | AFR | NIR | DES | 60 | PRP | 126 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-08-01 | 2011-04-30 |  | 2012-12-01 | 2012-12-01 | 60000 | -480 | 59520 | 59520.33 | 100% | -0.33 | 0 |  | 4500 | -36 | 4464 | 0 | 0 | FIN
ONG | UNIDO | Demonstration project for disposal of unwanted ODS | Individual | AFR | NIR | DES | 67 | DEM | 133 | A | I |  | 0 | 0 |  |  | 2012-07-01 | 2013-06-01 | 2014-07-31 | 2018-07-18 |  |  | 911724 | 0 | 911724 | 217417.13 | 23.85% | 694306.87 | 46713.66 | 50000 | 63821 | 0 | 15219 | 48602 | 3269.9562 | Milestone 1: Additional stocks collected from the National Agency for Food and Drugs Administration and Control Activities planned but not implemented, reasons and strategy: Low amounts of wastes found. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Since the amounts of waste are low and the carbon markets are not viable, it has been discussed with the government to carry out destruction in-country and implement a refrigerator-dismantling programme with remaining funds and assistance from the GEF as part of an e-waste project. PIF already with the GEF. There is interest from Ghana to destroy wastes in Nigeria. Any recurring problem? Yes If yes, description of the problem/s: Levels of found wastes still low. Any impact on project completion date: Yes If yes, implications: Planned completion date: extended to July 2018 to allow for destruction of wastes. Any action required by Executive Committee? No | Milestone 1: Additional stocks collected from the National Agency for Food and Drugs Administration and Control Activities planned but not implemented, reasons and strategy: Low amounts of wastes found. Was there any delay during the reporting year? Yes If yes, reasons and action plan: Since the amounts of waste are low and the carbon markets are not viable, it has been discussed with the government to carry out destruction in-country and implement a refrigerator-dismantling programme with remaining funds and assistance from the GEF as part of an e-waste project. PIF already with the GEF. There is interest from Ghana to destroy wastes in Nigeria. -More halon waste was found than CFC-12, however this is not eligible -Bids will be prepared and requested for in-country destruction of CFC-12 wastes from 2nd quarter of 2017 Any recurring problem? Yes If yes, description of the problem/s: Levels of found wastes still low. Any impact on project completion date: Yes If yes, implications: Planned completion date: extended to July 2018 to allow for destruction of wastes Any action required by Executive Committee? No |  |  | INV
FIN | UNDP | Conversion to CFC free technology in the manufacture of flexible polyurethane foam at Royal Foam Products | Individual | AFR | NIR | FOA | 20 | INV | 12 | A | D | CFC | 43 | 43 | 0 | 0 | 1996-10-01 | 1998-08-01 | 1998-09-01 |  | 1998-10-01 | 2000-12-01 | 34000 | -600 | 33400 | 33400 | 100% | 0 | 0 | 0 | 4420 | -78 | 4342 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Conversion to CFC free technology in the manufacture of flexible polyurethane foam at Teju Industries Limited | Individual | AFR | NIR | FOA | 20 | INV | 13 | A | D | CFC | 47 | 47 | 0 | 0 | 1996-10-01 | 1997-03-01 | 1998-09-01 |  | 1998-10-01 | 2003-01-01 | 75000 | -6859 | 68141 | 68141 | 100% | 0 | 0 | 0 | 9750 | -891.67 | 8858.33 | 0 | 0 | Completed in 1998. Financially completed in 2003. |  | 1996 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PU foam for thermoware in Eleganza Industries Ltd. at Ikeja, Lagos | Individual | AFR | NIR | FOA | 20 | INV | 14 | A | I | CFC | 48.3 | 48.3 | 0 | 0 | 1996-10-01 | 1997-05-01 | 1998-09-01 |  | 1998-10-01 | 2000-12-01 | 314000 | -4065 | 309935 | 309935 | 100% | 0 | 0 | 0 | 40820 | -528.45 | 40291.55 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Conversion to CFC free technology in the manufacture of flexible polyurethane foam at Sara Products Limited | Individual | AFR | NIR | FOA | 20 | INV | 15 | A | D | CFC | 27.7 | 27.7 | 0 | 0 | 1996-10-01 | 1997-03-01 | 1998-09-01 |  | 1999-07-01 | 2001-12-01 | 107000 | -2075 | 104925 | 104925 | 100% | 0 | 0 | 0 | 13910 | -270.36 | 13639.6363 | 0.0037 | 0 | Completed in 1999. Financially completed in 2001. |  | 1996 |  | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | AFR | NIR | FOA | 21 | PRP | 16 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2002-03-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 | 0 | 7150 | 0 | 7150 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam at Winco Foam Industries Ltd. | Individual | AFR | NIR | FOA | 23 | INV | 21 | A | I | CFC | 19.1 | 19.1 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-12-01 | 2001-08-01 | 117200 | -321 | 116879 | 116879 | 100% | 0 | 0 | 0 | 15236 | -41.73 | 15194.27 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam at Bajabure Industrial Complex Ltd. | Individual | AFR | NIR | FOA | 23 | INV | 22 | A | I | CFC | 32.3 | 32.3 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 2000-11-01 | 2002-11-01 | 135400 | -11117 | 124283 | 124283 | 100% | 0 | 0 | 0 | 17602 | -1445 | 16157 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam at Elico Industries Ltd. | Individual | AFR | NIR | FOA | 23 | INV | 23 | A | I | CFC | 25.7 | 25.7 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-12-01 | 2004-01-01 | 133900 | -13658 | 120242 | 120242 | 100% | 0 | 0 | 0 | 17407 | -1775.54 | 15631.46 | 0 | 0 | Completed in 1999. Financially completed in 2004. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam at Mouka Ltd. | Individual | AFR | NIR | FOA | 23 | INV | 24 | A | I | CFC | 30.3 | 30.3 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1999-11-01 | 2004-01-01 | 143600 | -3462 | 140138 | 140138 | 100% | 0 | 0 | 0 | 18668 | -450.06 | 18217.94 | 0 | 0 | Completed in 1999. Financially completed in 2004. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam at Safa Foam Products (Nig) Ltd. | Individual | AFR | NIR | FOA | 23 | INV | 25 | A | I | CFC | 24.4 | 24.4 | 0 | 0 | 1997-11-01 | 2000-01-01 | 1999-12-01 |  | 2003-08-01 | 2006-10-01 | 146400 | 0 | 146400 | 146400 | 100% | 0 | 0 | 0 | 19032 | 0 | 19032 | 0 | 0 | Completed in 2003. Financially completed in 2006. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFCs in the manuyfacture of rigid PUF insulation products at Aluminium Manufacturing Company of Nigeria Plc (Alumaco) | Individual | AFR | NIR | FOA | 23 | INV | 26 | A | I | CFC | 11.5 | 11.5 | 0 | 0 | 1997-11-01 | 2000-02-01 | 1999-12-01 |  | 2001-11-01 | 2002-11-01 | 38000 | -400 | 37600 | 37600 | 100% | 0 | 0 | 0 | 4940 | -52 | 4888 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF for thermoware in 3 enterprises of the Eleganza Group (Eleganza Cooler and Household Industries Ltd., Eleganza Ceramics and Cooler Industries Ltd.) | Individual | AFR | NIR | FOA | 23 | INV | 27 | A | I | CFC | 73.8 | 73.8 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 1999-12-01 | 2004-01-01 | 568000 | -25762 | 542238 | 542238 | 100% | 0 | 0 | 0 | 73840 | -3349.06 | 70490.94 | 0 | 0 | Completed in 1999. Financially completed in 2004. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam at Ugochukwu Chemical Industries Ltd. | Individual | AFR | NIR | FOA | 23 | INV | 28 | A | I | CFC | 118.6 | 118.6 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 2001-07-01 | 2002-11-01 | 407600 | 0 | 407600 | 407600 | 100% | 0 | 0 | 0 | 52988 | 0 | 52988 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Elimination of CFCs in the manufacture of rigid PUF spray insulation at Polyurethane Manufacturers Ltd. (Polyma) | Individual | AFR | NIR | FOA | 23 | INV | 29 | A | I | CFC | 18.5 | 18.5 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2000-12-01 | 2004-01-01 | 80500 | -339 | 80161 | 80161 | 100% | 0 | 0 | 0 | 10465 | -44.07 | 10420.93 | 0 | 0 | Completed in 2000. Financially completed in 2004. |  | 1997 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Orbit Foam Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 31 | A | I | CFC | 25.1 | 25.1 | 0 | 0 | 1998-11-01 | 2000-05-01 | 2000-12-01 |  | 2003-07-01 | 2003-11-01 | 135200 | -1 | 135199 | 135199 | 100% | 0 | 0 | 0 | 17576 | 0 | 17576 | 0 | 0 | Completed in 2003. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Olufoam and Plastic Industries Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 32 | A | I | CFC | 21 | 21 | 0 | 0 | 1998-11-01 | 2001-10-01 | 2000-12-01 |  | 2004-12-01 | 2005-11-01 | 84600 | 0 | 84600 | 84600 | 100% | 0 | 0 | 0 | 10998 | 0 | 10998 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 1998 | 2003-12-01 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Okin Foam Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 33 | A | I | CFC | 25.3 | 25.3 | 0 | 0 | 1998-11-01 | 2000-01-01 | 2000-12-01 |  | 2001-11-01 | 2002-11-01 | 133200 | 0 | 133200 | 133200 | 100% | 0 | 0 | 0 | 17316 | 0 | 17316 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Marta Industries (Nig.) Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 34 | A | I | CFC | 32 | 32 | 0 | 0 | 1998-11-01 | 1999-11-01 | 2000-12-01 |  | 2000-12-01 | 2001-08-01 | 130600 | -1299 | 129301 | 129301 | 100% | 0 | 0 | 0 | 16978 | -168.87 | 16809.13 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Confidence Products and Services Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 35 | A | I | CFC | 27.3 | 27.3 | 0 | 0 | 1998-11-01 | 2000-01-01 | 2000-12-01 |  | 2004-12-01 | 2005-11-01 | 142300 | -1210 | 141090 | 141090 | 100% | 0 | 0 | 0 | 18499 | -157.3 | 18341.7 | -2.8e-05 | 0 | Completed in 2004. Financially completed in 2005. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Chemical and Wire Manufacturers Nig. Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 36 | A | I | CFC | 37.1 | 37.1 | 0 | 0 | 1998-11-01 | 2000-01-01 | 2000-12-01 |  | 2000-01-01 | 2003-11-01 | 164500 | 0 | 164500 | 164500 | 100% | 0 | 0 | 0 | 21385 | 0 | 21385 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1998 | 2003-07-01 | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Bodefoam Industries Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 37 | A | I | CFC | 35.3 | 35.3 | 0 | 0 | 1998-11-01 | 2000-06-01 | 2000-12-01 |  | 2001-07-01 | 2002-11-01 | 136400 | 0 | 136400 | 136400 | 100% | 0 | 0 | 0 | 17732 | 0 | 17732 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Group Enterprises Nig. Ltd. (Polly Foam) | Individual | AFR | NIR | FOA | 26 | INV | 38 | A | I | CFC | 26 | 26 | 0 | 0 | 1998-11-01 | 2000-03-01 | 2000-12-01 |  | 2001-07-01 | 2002-11-01 | 128900 | -2349 | 126551 | 126551 | 100% | 0 | 0 | 0 | 16757 | -305.37 | 16451.63 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Pesaco Chemical Industries Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 39 | A | I | CFC | 23.4 | 23.4 | 0 | 0 | 1998-11-01 | 2000-08-01 | 2000-12-01 |  | 2001-12-01 | 2003-04-01 | 126400 | 0 | 126400 | 126400 | 100% | 0 | 0 | 0 | 16432 | 0 | 16432 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Yinka-Oba Foam Nig. Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 42 | A | I | CFC | 30 | 30 | 0 | 0 | 1998-11-01 | 2000-02-01 | 2000-12-01 |  | 2003-08-01 | 2005-10-01 | 185300 | -629 | 184671 | 184671 | 100% | 0 | 0 | 0 | 24089 | -81.77 | 24007.23 | -1e-05 | 0 | Completed in 2003. Financially completed in 2005. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Universal Foam Ltd. | Individual | AFR | NIR | FOA | 26 | INV | 43 | A | I | CFC | 30.6 | 30.6 | 0 | 0 | 1998-11-01 | 2000-03-01 | 2000-12-01 |  | 2000-12-01 | 2002-11-01 | 135300 | 0 | 135300 | 135300 | 100% | 0 | 0 | 0 | 17589 | 0 | 17589 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Project preparation | Individual | AFR | NIR | FOA | 26 | PRP | 41 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-11-01 | 1998-12-01 | 1999-12-01 |  | 1999-12-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Preparation of three projects in general foam subsector | Individual | AFR | NIR | FOA | 27 | PRP | 45 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2002-04-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Preparation of seven projects in general foam subsector | Individual | AFR | NIR | FOA | 27 | PRP | 60 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-04-01 | 2002-04-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam (slabstock) at United Foam Products Nig. Ltd. | Individual | AFR | NIR | FOA | 28 | INV | 46 | A | I | CFC | 25 | 25 | 0 | 0 | 1999-07-01 | 2001-10-01 | 2002-02-01 |  | 2003-08-01 | 2007-01-01 | 137310 | -6098 | 131212 | 131212 | 100% | 0 | 0 | 0 | 17850.3 | -792.73 | 17057.5733 | -0.0033 | 0 | Completed in 2003. Financially completed in 2007. |  | 1999 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam (slabstock) at Tinuola Bay Industries Nig. Ltd. | Individual | AFR | NIR | FOA | 28 | INV | 47 | A | I | CFC | 21 | 21 | 0 | 0 | 1999-07-01 | 2000-01-01 | 2002-02-01 |  | 2001-09-01 | 2003-09-01 | 119410 | 0 | 119410 | 119410 | 100% | 0 | 0 | 0 | 15523.3 | 0 | 15523.3 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam (slabstock) at Diamond Foam Nigeria Ltd. | Individual | AFR | NIR | FOA | 28 | INV | 49 | A | I | CFC | 22.7 | 22.7 | 0 | 0 | 1999-07-01 | 2001-08-01 | 2002-02-01 |  | 2001-11-01 | 2002-11-01 | 112150 | 0 | 112150 | 112150 | 100% | 0 | 0 | 0 | 14579.5 | 0 | 14579.5 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to liquid carbon dioxide blown technology in the manufacture of molded flexible polyurethane foam at Automotive Component Industries Ltd. | Individual | AFR | NIR | FOA | 28 | INV | 50 | A | I | CFC | 37 | 37 | 0 | 0 | 1999-07-01 | 2000-03-01 | 2002-02-01 |  | 2000-11-01 | 2002-11-01 | 204761 | 0 | 204761 | 204761 | 100% | 0 | 0 | 0 | 26618.93 | 0 | 26618.93 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Rubez (Nig.) Ltd. (Current Foam) | Individual | AFR | NIR | FOA | 29 | INV | 55 | A | I | CFC | 21.9 | 21.9 | 0 | 0 | 1999-11-01 | 2002-04-01 | 2002-12-01 |  | 2003-08-01 | 2005-11-01 | 89803 | -65 | 89738 | 89738 | 100% | 0 | 0 | 0 | 11674.39 | -8 | 11666.39 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 1999 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Jafco Industries Limited | Individual | AFR | NIR | FOA | 29 | INV | 56 | A | I | CFC | 34.2 | 34.2 | 0 | 0 | 1999-11-01 | 2001-10-01 | 2002-12-01 |  | 2002-12-01 | 2006-06-01 | 58559 | 0 | 58559 | 58559 | 100% | 0 | 0 | 0 | 7612.67 | 0 | 7612.67 | 0 | 0 | Completed in 2002. Financially completed in 2006. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Vono Products PLC | Individual | AFR | NIR | FOA | 29 | INV | 57 | A | I | CFC | 56.5 | 56.5 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2001-12-01 | 2003-05-01 | 173782 | 0 | 173782 | 173782 | 100% | 0 | 0 | 0 | 22591.66 | 0 | 22591.66 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Phase out of CFC-11 by conversion to methylene chloride blown technology in the manufacture of flexible polyurethane foam at Betaday Industries Ltd. | Individual | AFR | NIR | FOA | 29 | INV | 58 | A | I | CFC | 30 | 30 | 0 | 0 | 1999-11-01 | 2000-11-01 | 2002-12-01 |  | 2001-11-01 | 2002-11-01 | 104495 | -1 | 104494 | 104494 | 100% | 0 | 0 | 0 | 13584.35 | -0.13 | 13584.22 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Phase-out of CFC-11 by conversion to mehtylene chloride in the manufacture of flexible polyurethane foam at Vito Company (Nig.) Ltd., Victory Foam | Individual | AFR | NIR | FOA | 29 | INV | 59 | A | I | CFC | 26 | 26 | 0 | 0 | 1999-11-01 | 2001-02-01 | 2002-12-01 |  | 2001-11-01 | 2002-11-01 | 133560 | -188 | 133372 | 133372 | 100% | 0 | 0 | 0 | 17362.8 | -24.44 | 17338.36 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Preparation of 8 projects in the general foam subsector | Individual | AFR | NIR | FOA | 30 | PRP | 63 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2000-12-01 | 2006-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 2000. Financially completed in 2006. |  | 2000 |  | Investment
CLO | UNDP | Preparation of 2 projects in the rigid foam subsector | Individual | AFR | NIR | FOA | 30 | PRP | 64 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 |  | 2001-04-01 |  |  | 2001-12-01 | 30000 | -30000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 3900 | -3900 | 0 | 0 | 0 | Canceled in 2000. Financially Completed in 2001. |  | 2000 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Sokoto Foam Factory (Nig.) Ltd. | Individual | AFR | NIR | FOA | 31 | INV | 65 | A | I | CFC | 26.1 | 26.1 | 0 | 0 | 2000-07-01 | 2001-05-01 | 2003-08-01 |  | 2002-12-01 | 2005-09-01 | 141421 | -4328 | 137093 | 137093 | 100% | 0 | 0 | 0 | 18384.73 | -563 | 17821.73 | 0 | 0 | Completed in 2002. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manfuacture of flexible slabstock foam by conversion to methylene chloride at Abeokuta Commercial and Industrial Co. Ltd. | Individual | AFR | NIR | FOA | 31 | INV | 66 | A | I | CFC | 23.3 | 23.3 | 0 | 0 | 2000-07-01 | 2001-07-01 | 2003-08-01 |  | 2002-11-01 | 2004-01-01 | 118468 | -382 | 118086 | 118086 | 100% | 0 | 0 | 0 | 15400.84 | -49.66 | 15351.18 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam by conversion to a combination of water and HCFC-141b based systems at Celplas Industries Limited | Individual | AFR | NIR | FOA | 31 | INV | 67 | A | I | CFC | 27.5 | 27.5 | 0 | 0 | 2000-07-01 | 2001-04-01 | 2003-08-01 |  | 2002-11-01 | 2002-12-01 | 215325 | 0 | 215325 | 215325 | 100% | 0 | 0 | 0 | 27992.25 | 0 | 27992.25 | 0 | 0 | Completed in 2002. Financially completed in 2002. |  | 2000 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Climax Ind. Ltd. (Ely Foam) | Individual | AFR | NIR | FOA | 31 | INV | 68 | A | I | CFC | 29.7 | 29.7 | 0 | 0 | 2000-07-01 | 2001-09-01 | 2003-08-01 |  | 2002-11-01 | 2004-01-01 | 173362 | -575 | 172787 | 172787 | 100% | 0 | 0 | 0 | 22537.06 | -74.75 | 22462.31 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Wappah Foam Limited | Individual | AFR | NIR | FOA | 31 | INV | 69 | A | I | CFC | 24 | 24 | 0 | 0 | 2000-07-01 | 2001-09-01 | 2003-08-01 |  | 2001-12-01 | 2002-11-01 | 130081 | -4 | 130077 | 130077 | 100% | 0 | 0 | 0 | 16910.53 | -1 | 16909.53 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 2000 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Jafa Foam Products Nig. Ltd. | Individual | AFR | NIR | FOA | 31 | INV | 70 | A | I | CFC | 34.2 | 34.2 | 0 | 0 | 2000-07-01 | 2001-04-01 | 2003-08-01 |  | 2002-12-01 | 2006-10-01 | 124667 | -9881 | 114786 | 114786 | 100% | 0 | 0 | 0 | 16206.71 | -1285 | 14921.71 | 0 | 0 | Completed in 2002. Financially completed in 2006. |  | 2000 |  | Investment
FIN | Japan | Phasing out of CFC-11 in the manufacture of flexible slabstock foam at Eastern Wrought Iron Limited by conversion to methylene chloride | Individual | AFR | NIR | FOA | 32 | INV | 73 | A | I | CFC | 27.1 | 27.1 | 0 |  | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2004-11-01 | 2006-05-01 | 109345 | -3207 | 106138 | 106138 | 100% | 0 | 0 | 0 | 14215 | -417 | 13798 | 0 | 0 | Operationally completed November 2004. COC issued. Final revision issued but unspent balance and corresponding support cost still to be returned in 2007. |  | 2000 |  | investment
FIN | Japan | Phasing out of CFC-11 in the manufacture of flexible slabstock foam at Mac-Vico (Nig.) Limited by conversion to methylene chloride | Individual | AFR | NIR | FOA | 32 | INV | 74 | A | I | CFC | 28.4 | 28.4 | 0 |  | 2000-12-01 | 2002-03-01 | 2004-01-01 |  | 2003-07-01 | 2003-10-01 | 105209 | 0 | 105209 | 105209 | 100% | 0 | 0 | 0 | 13677 | 0 | 13677 | 0 | 0 | Operationally completed July 2003, financially completed October 2003 |  | 2000 |  | investment
FIN | Japan | Phasing out of CFC-11 in the manufacture of flexible slabstock foam at Martchem Industries Limited (at 2 plants) by conversion to methylene chloride | Individual | AFR | NIR | FOA | 32 | INV | 75 | A | I | CFC | 38.4 | 38.4 | 0 |  | 2000-12-01 | 2002-10-01 | 2004-01-01 |  | 2003-03-01 | 2003-10-01 | 175121 | 0 | 175121 | 175121 | 100% | 0 | 0 | 0 | 22766 | 0 | 22766 | 0 | 0 | Operationally and financially completed 2003 |  | 2000 |  | investment
CLO | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | AFR | NIR | FOA | 33 | PRP | 78 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 |  | 2002-04-01 |  |  | 2003-09-01 | 10000 | -10000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 1300 | -1300 | 0 | 0 | 0 | Canceled in 2001. Financially Completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Project preparation in the rigid polyurethane foam sector | Individual | AFR | NIR | FOA | 33 | PRP | 79 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-09-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
CLO | UNDP | Project preparation in the flexible polyurethane foam sector | Individual | AFR | NIR | FOA | 33 | PRP | 81 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 |  | 2002-04-01 |  |  | 2003-09-01 | 10000 | -10000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 1300 | -1300 | 0 | 0 | 0 | Canceled in 2001. Financially Completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Project preparation in the flexible polyurethane foam sector | Individual | AFR | NIR | FOA | 33 | PRP | 82 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-09-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Atuchukwu Chemical Ind., Ltd. | Individual | AFR | NIR | FOA | 34 | INV | 83 | A | I | CFC | 22.2 | 22.2 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-05-01 |  | 2002-12-01 | 2003-11-01 | 118488 | -1 | 118487 | 118487 | 100% | 0 | 0 | 0 | 15403.44 | 0 | 15403.44 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Apaco Foam and Chemical Ind., Ltd. | Individual | AFR | NIR | FOA | 34 | INV | 84 | A | I | CFC | 27.7 | 27.7 | 0 | 0 | 2001-07-01 | 2002-05-01 | 2004-05-01 |  | 2002-12-01 | 2003-11-01 | 147018 | 0 | 147018 | 147018 | 100% | 0 | 0 | 0 | 19112.34 | 0 | 19112.34 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Gasfa Industries Nig., Ltd. (Meka Foam) | Individual | AFR | NIR | FOA | 34 | INV | 85 | A | I | CFC | 40.5 | 40.5 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-05-01 |  | 2003-08-01 | 2005-09-01 | 238843 | -9895 | 228948 | 228948 | 100% | 0 | 0 | 0 | 31049.59 | -1286 | 29763.59 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam by conversion to a combination of water and HCFC-141b based systems at Adig Plastics Ltd. | Individual | AFR | NIR | FOA | 34 | INV | 86 | A | I | CFC | 14.3 | 14.3 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-08-01 |  | 2002-12-01 | 2003-04-01 | 112050 | 0 | 112050 | 112050 | 100% | 0 | 0 | 0 | 14566.5 | 0 | 14566.5 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Phasing out CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Rima Foam Products Ltd. | Individual | AFR | NIR | FOA | 34 | INV | 88 | A | I | CFC | 23 | 23 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-05-01 |  | 2002-12-01 | 2006-06-01 | 119036 | -582 | 118454 | 118454 | 100% | 0 | 0 | 0 | 15474.68 | -76 | 15398.68 | 0 | 0 | Completed in 2002. Financially completed in 2006. |  | 2001 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Harmony Foam Nigeria Ltd. | Individual | AFR | NIR | FOA | 34 | INV | 89 | A | I | CFC | 22.3 | 22.3 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-05-01 |  | 2004-12-01 | 2005-11-01 | 126531 | -13568 | 112963 | 112963 | 100% | 0 | 0 | 0 | 16449.03 | -1763.84 | 14685.1932 | -0.003233 | 0 | Completed in 2004. Financially completed in 2005. |  | 2001 |  | Investment
CLO | UNDP | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam by conversion to a combination of water and HCFC-141b based systems at Global Plastic Industries, Ltd. | Individual | AFR | NIR | FOA | 34 | INV | 91 | A | I | CFC | 4.7 | 4.7 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-05-01 |  |  | 2005-09-01 | 36801 | -3512 | 33289 | 33289 | 100% | 0 | 0 | 0 | 4784.13 | -457 | 4327.13 | 0 | 0 | Canceled in 2004. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Bibafoam Ind., Ltd. | Individual | AFR | NIR | FOA | 34 | INV | 92 | A | I | CFC | 26 | 26 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2004-05-01 |  | 2002-12-01 | 2006-10-01 | 114685 | 0 | 114685 | 114685 | 100% | 0 | 0 | 0 | 14909.05 | 0 | 14909.05 | 0 | 0 | Completed in 2002. Financially completed in 2006. |  | 2001 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Bamako Industrial, Ltd. | Individual | AFR | NIR | FOA | 35 | INV | 94 | A | I | CFC | 24 | 24 | 0 | 0 | 2001-12-01 | 2002-11-01 | 2004-10-01 |  | 2003-12-01 | 2005-11-01 | 114510 | -3460 | 111050 | 111050 | 100% | 0 | 0 | 0 | 14886.3 | -450 | 14436.3 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam by conversion to a combination of water and HCFC-141b based systems at Agric Services (Nig.), Ltd. | Individual | AFR | NIR | FOA | 35 | INV | 95 | A | I | CFC | 43.7 | 43.7 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2004-01-01 |  | 2003-08-01 | 2005-10-01 | 239160 | -263 | 238897 | 238897 | 100% | 0 | 0 | 0 | 31090.8 | -34.19 | 31056.6098 | 0.000181 | 0 | Completed in 2003. Financially completed in 2005. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to methylene chloride (MC) technology in the manufacture of flexible polyurethane at ten box-foam enterprises in Lagos area | Individual | AFR | NIR | FOA | 35 | INV | 96 | A | I | CFC | 199.2 | 199.2 | 0 | 0 | 2001-12-01 | 2002-11-01 | 2004-10-01 |  | 2003-12-01 | 2007-02-01 | 1062808 | 0 | 1062808 | 1062808 | 100% | 0 | 0 | 0 | 126908.9 | 0 | 126908.9 | 0 | 0 | Completed in 2003. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Preparation of a terminal programme in the foam sector | Individual | AFR | NIR | FOA | 36 | PRP | 100 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2002-12-01 | 2005-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 2002. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | AFR | NIR | FOA | 57 | PRP | 123 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-01-01 | 2010-03-01 |  | 2010-12-01 | 2012-10-01 | 50000 | -19883 | 30117 | 30117 | 100% | 0 | 0 | 0 | 3750 | -1491.43 | 2258.5657 | 0.0043 | 0 | Completed. Foam sector plan submitted as part of the HPMP approved at 62nd ExCom meeting. Final invoices expected in 2011. |  | 2009 |  | Investment
ONG | UNDP | Preparation for HCFC phase-out investment activities (stage II) (foam sector) | Individual | AFR | NIR | FOA | 72 | PRP | 139 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 |  | 2016-05-01 | 2017-09-01 |  |  | 80000 | 0 | 80000 | 0 | 0% | 80000 | 5649 | 32000 | 5600 | 0 | 0 | 5600 | 395.43 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): An international consultant initiated work on the coordination of the HPMP Stage 2 preparation process, and conducted one mission in July 2016. National consultant collected data, being reviewed. Prodoc signed (actual/planned, yes/no and date):0/0 No Missions undertaken (actual/planned):Yes by international consultant working on the national surveys. TOR for consultants/subcontracts completed (actual/planned): 1/1 yes. Contract/PO/MOA agreements signed: 0/0: No First disbursement date (actual/planned): 42552Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:Data collection challenges for the surveys. | A stakeholders' workshop on Stage 2 HPMP was held on 15 March 2017. |  |  | Non-Investment
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organizations in methyl bromide communication | Individual | AFR | NIR | FUM | 34 | TAS | 90 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2002-07-01 |  | 2003-07-01 | 2004-09-01 | 25000 | -16990 | 8010 | 8010 | 100% | 0 | 0 |  | 3250 | -2208.7 | 1041.3 | 0 | 0
FIN | Germany | Project preparation/technical assistance for the halon sector | Individual | AFR | NIR | HAL | 34 | PRP | 87 | A | I |  | 0 |  | 0 |  | 2001-07-01 | 2001-08-01 | 2002-01-01 |  | 2002-06-01 | 2003-07-01 | 19420 | 0 | 19420 | 19420 | 100% | 0 | 0 | 0 | 2525 | 0 | 2525 | 0 | 0 | Project proposal submitted and approved by MF (37th ExCom).
FIN | Germany | Sectoral phase-out programme: establishing a halon bank | Individual | AFR | NIR | HAL | 37 | TAS | 103 | A | I | HAL | 285.3 | 285.3 | 0 |  | 2002-07-01 | 2002-12-01 | 2005-08-01 |  | 2007-08-01 | 2008-10-01 | 499000 | 0 | 499000 | 499000 | 100% | 0 | 0 | 0 | 64870 | 0 | 64870 | 0 | 0 | Project is completed. PCR has been submitted to the MLF in October 2008.
FIN | UNIDO | National CFC phase-out plan: refrigeration manufacturing | Multi-Year | AFR | NIR | PHA | 38 | INV | 105 | A | I | CFC | 42.9 | 42.9 |  |  | 2002-11-01 | 2003-03-01 | 2005-06-01 |  | 2006-03-01 | 2008-09-01 | 682386 | 0 | 682386 | 682385.99 | 100% | 0.01 | 0 |  | 82521 | 0 | 82521 | 0 | 0 | FIN |  |  | 2005-06-01 | INV
FIN | UNDP | National CFC phase-out plan: foam sector and refrigeration servicing sector (first tranche) | Multi-Year | AFR | NIR | PHA | 38 | INV | 106 | N | I | CFC | 0 | 0 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2003-12-01 |  | 2006-12-01 | 2013-10-01 | 5013929 | 0 | 5013929 | 5013929 | 100% | 0 | 0 | 0 | 449318 | 0 | 449318 | 0 | 0 | Financially completed in 2013. |  | 2002 | 2005-12-01 | Investment
FIN | UNDP | National CFC phase-out plan (second tranche) | Multi-Year | AFR | NIR | PHA | 41 | INV | 108 | N | I | CFC | 830 | 830 | 0 | 0 | 2003-12-01 | 2007-03-01 | 2004-12-01 |  | 2007-12-01 | 2013-10-01 | 2976827 | 0 | 2976827 | 2976827 | 100% | 0 | 0 | 0 | 264834 | 0 | 264834 | 0 | 0 | Financially completed in 2013. |  | 2003 |  | Investment
FIN | UNIDO | National CFC phase-out plan (aerosol sector) | Multi-Year | AFR | NIR | PHA | 41 | INV | 109 | A | I | CFC | 57.9 | 57.9 |  |  | 2003-12-01 | 2004-07-01 | 2005-12-01 |  | 2008-03-01 | 2008-06-01 | 255000 | -2 | 254998 | 254998.02 | 100% | -0.02 | 0 |  | 33150 | 0 | 33150 | 0 | 0 | FIN |  |  |  | INV
FIN | UNDP | National CFC phase-out plan (third tranche) | Multi-Year | AFR | NIR | PHA | 44 | INV | 112 | N | I | CFC | 850.7 | 850.7 | 0 | 0 | 2004-12-01 | 2008-01-01 | 2005-12-01 |  | 2008-09-01 | 2013-10-01 | 2077141 | 0 | 2077141 | 2077141 | 100% | 0 | 0 | 0 | 183863 | 0 | 183863 | 0 | 0 | Financially completed in 2013. |  | 2004 |  | Investment
FIN | UNIDO | Terminal ODS phase-out umbrella project in the solvent sector (3rd tranche) | Multi-Year | AFR | NIR | PHA | 49 | INV | 115 | A | I |  | 0 | 0 |  |  | 2006-07-01 | 2006-11-01 | 2007-07-01 |  | 2007-12-01 | 2011-12-01 | 425000 | 0 | 425000 | 425000.01 | 100% | -0.01 | 0 |  | 31875 | 0 | 31875 | 0 | 0 | FIN |  |  |  | INV
FIN | UNDP | National CFC phase-out plan (fourth and fifth tranches) | Multi-Year | AFR | NIR | PHA | 54 | INV | 117 | N | I | CFC | 1179.8 | 1179.8 | 0 | 0 | 2008-04-01 | 2009-05-01 | 2010-03-01 |  | 2011-09-01 | 2013-10-01 | 1286303 | 0 | 1286303 | 1286303 | 100% | 0 | 0 | 0 | 111407 | 0 | 111407 | 0 | 0 | Financially completed in 2013. | Completed in 2011. | 2008 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | AFR | NIR | PHA | 55 | PRP | 119 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2010-12-01 | 2012-04-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 6375 | 0 | 6375 | 0 | 0 | Financially completed in 2012. | Financially completed in 2012. | 2008 |  | Investment
FIN | UNIDO | Preparation of a HCFC phase-out management plan (additional funding) | Individual | AFR | NIR | PHA | 56 | PRP | 120 | A | I |  | 0 | 0 |  |  | 2008-11-01 | 2009-05-01 | 2009-11-30 |  | 2010-12-01 | 2010-12-01 | 20000 | -4 | 19996 | 19996.09 | 100% | -0.09 | 0 |  | 1500 | 0 | 1500 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNDP | Preparation of a HCFC phase-out management plan (additional funding) | Individual | AFR | NIR | PHA | 56 | PRP | 121 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-11-01 | 2010-01-01 | 2009-11-01 |  | 2010-12-01 | 2012-04-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 3375 | 0 | 3375 | 0 | 0 | Financially completed in 2012. | Financially completed in 2012. | 2008 |  | Investment
FIN | UNDP | National CFC phase-out plan (sixth tranche) | Multi-Year | AFR | NIR | PHA | 57 | INV | 122 | N | I | CFC | 200 | 200 | 0 | 0 | 2009-04-01 | 2010-05-01 | 2011-03-01 |  | 2011-11-01 | 2013-10-01 | 385000 | 0 | 385000 | 385000 | 100% | 0 | 0 | 0 | 32770 | 0 | 32770 | 0 | 0 | Financially completed in 2013. | Completed in 2011. | 2009 |  | Investment
FIN | UNDP | National CFC phase-out plan (seventh and eighth tranche) | Multi-Year | AFR | NIR | PHA | 59 | INV | 125 | N | I | CFC | 264.6 | 264.6 | 0 | 0 | 2009-11-01 | 2011-05-01 | 2011-11-01 |  | 2012-12-01 | 2013-10-01 | 454200 | -18258.99 | 435941.01 | 435941 | 100% | 0.01 | 0 | 0 | 36518 | -1468.04 | 35049.9635 | -0.0035359 | 0 | Financially completed in 2013. | Completed in 2012. | 2009 |  | Investment
FIN | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | NIR | PHA | 62 | INV | 128 | N | I | HCFC | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-03-01 | 2011-12-01 |  | 2012-10-01 | 2013-03-01 | 855603 | 0 | 855603 | 855603 | 100% | 0 | 0 | 0 | 64170 | 0 | 64170 | 0 | 0 | Financially completed in 2013. |  | 2010 |  | Investment
COM | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | NIR | PHA | 62 | INV | 129 | A | I |  | 0 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2011-12-31 |  | 2013-12-01 |  | 550000 | 0 | 550000 | 548844.11 | 99.79% | 1155.89 | 988 | 1 | 41250 | 0 | 41163 | 87 | 74 | The project was operationally completed. |  |  |  | INV
COM | UNIDO | HCFC phase-out management plan (stage I, second tranche) (refrigeration air-conditioning manufacturing and coordination) | Multi-Year | AFR | NIR | PHA | 66 | INV | 131 | A | I |  | 0 | 0 |  |  | 2012-04-01 | 2013-02-01 | 2013-04-30 |  | 2015-12-01 |  | 550000 | 0 | 550000 | 544195.88 | 98.94% | 5804.12 | 5658.4 | 1 | 41250 | 0 | 40815 | 435 | 424.38 | The project was operationally completed. |  |  |  | INV
FIN | UNDP | HCFC phase-out management plan (stage I, second tranche) (foam, refrigeration air-conditioning servicing and coordination) | Multi-year | AFR | NIR | PHA | 66 | INV | 132 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-04-01 | 2012-11-01 | 2013-04-01 |  | 2014-11-01 | 2015-01-01 | 836515 | 0 | 836515 | 836515 | 100% | 0 | 0 | 0 | 62739 | 0 | 62739 | 0 | 0 | Financially completed in 2015. | A monitoring mission by International consultant and UNDP is planned for May 2014, on the occasion of the launch of production at refrigerant and foam factories. This will also support the kick-off of activities under Tranche 3. | 2012 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, third tranche) (foam) | Multi-Year | AFR | NIR | PHA | 71 | INV | 135 | N | I | HCFC | 0 | 0 | 0 | 0 | 2013-12-01 | 2014-11-01 | 2015-12-01 | 2017-12-01 |  |  | 503829 | 0 | 503829 | 419110.52 | 83.19% | 84718.48 | 0 | 33887.392 | 37787 | 0 | 31433.1434 | 6353.8566 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Last activities planned in this tranche and commitments were completed, related to the completion of the System House at Vitapur. Prodoc signed (actual/planned, yes/no and date):1/1. Yes. Agreement signed earlier. Missions undertaken (actual/planned):1/1 Yes - May 2016 TOR for consultants/subcontracts completed (actual/planned): 0/0 Contract/PO/MOA agreements signed: 0/0 No First disbursement date (actual/planned): 41944Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | Activities for that tranche completed. | 2013 |  | Investment |  | To request the submission of additional status report to the 79th meeting to monitor delays in the establishment of the licensing process for the pilot plant.
ONG | UNIDO | HCFC phase-out management plan (stage I, third tranche) (refrigeration air-conditioning manufacturing and coordination) | Multi-Year | AFR | NIR | PHA | 71 | INV | 136 | A | I |  | 0 | 0 |  |  | 2013-12-01 | 2015-07-01 | 2016-06-01 | 2017-12-31 |  |  | 645172 | 0 | 645172 | 11065.24 | 1.715% | 634106.76 | 632531 | 500000 | 48388 | 0 | 830 | 47558 | 47439.825 | Commissioning and trial runs planned for last quarter of 2016. Milestones achieved: Milestone 1: Schedule for installation and trial runs developed and circulated -Installation/training: No Was there any delay during the reporting year? Yes If yes, reasons and action plan: Some beneficiaries were not prepared for installation exercise due to currency crisis in the country. Installation could not take place as planned. Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Completion date changed to July 2017 to allow for installation and training. Any action required by Executive Committee? No | Milestones achieved: Milestone 1: Schedule for installation and trial runs developed and circulated Installation/training planned for May to June 2017 Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Completion date extended to ensure that installation and training can be completed also in case of slight delays. Any action required by Executive Committee? No |  |  | INV |  | To request the submission of additional status report to the 79th meeting to monitor the procurement and/or delivery of the equipment.
ONG | UNDP | Preparation of a HCFC phase-out management plan (stage II) | Individual | AFR | NIR | PHA | 72 | PRP | 138 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 | 2016-06-01 | 2016-05-01 | 2017-09-01 |  |  | 90000 | 0 | 90000 | 53323.69 | 59.25% | 36676.31 | 0 | 14670.524 | 6300 | 0 | 3732.6583 | 2567.3417 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): National consultants in the refrigeration servicing provided draft surveys, which were reviewed by international consultants and being refined. Prodoc signed (actual/planned, yes/no and date):0/0 No Missions undertaken (actual/planned):1/1 Yes - May 2016 TOR for consultants/subcontracts completed (actual/planned): Yes (national consultants) Contract/PO/MOA agreements signed: 0/0 No First disbursement date (actual/planned): 42522Any delays/problems (yes/no):Challenges in data collection If Yes, reasons for delay & action plan to resolve:Intensified support form international consultants. | A stakeholders' workshop on Stage 2 HPMP was held on 15 March 2017. |  |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, fourth tranche) | Multi-Year | AFR | NIR | PHA | 73 | INV | 140 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-11-01 | 2015-04-01 | 2016-11-01 | 2017-06-01 |  |  | 503829 | 0 | 503829 | 104000 | 20.64% | 399829 | 0 | 159931.6 | 37787 | 0 | 7799.9639 | 29987.0361 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Activities focused on the completion of the system house at Vitapur in particular and the preparation of the training on methyl formate to replace HCFC 141b. Technical support visit by Rigifoam was completed to prepare for the launch of the system house. Participation in international meetings of relevance for the HPMP were completed. Further work with end users and their preparation to use alternatives to HCFCs were conducted. One verification study for HCFC consumption was completed. Prodoc signed (actual/planned, yes/no and date):1/1. Yes. Agreement signed earlier. Missions undertaken (actual/planned):1/2 - May 20016. Another mission in August had to be cancelled by the MPOU staff. TOR for consultants/subcontracts completed (actual/planned): Contract/PO/MOA agreements signed: No procurement. First disbursement date (actual/planned): 42095Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:there were caused 1. by the general economic situation in Nigeria and 2. a payment delayed to the Rigifoam South African companies. It w as solved eventually. | Mission led in March 2017 by staff and international consultant. | 2014 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, fifth tranche) (foam sector and refrigeration servicing) | Multi-year | AFR | NIR | PHA | 75 | INV | 143 | N | I | HCFC | 56 | 0 | 0 | 0 | 2015-11-01 |  | 2017-11-01 | 2017-11-01 |  |  | 299974 | 0 | 299974 | 0 | 0% | 299974 | 0 | 119989.6 | 22498 | 0 | 0 | 22498 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Though disbursements have not started, the activities have been prepared and will relate in particular to the conversions of end users to the new Methyl-formate base products. Prodoc signed (actual/planned, yes/no and date):1/1. Yes. Agreement signed earlier. Missions undertaken (actual/planned):1/1 Yes - May 2016. Another one conducted by International consultant in Aug2016. TOR for consultants/subcontracts completed (actual/planned): 0 / 0 Contract/PO/MOA agreements signed: 1 / 0. Technical agreement with Rigifoam was sihned. First disbursement date (actual/planned): NAAny delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:Due to the sequence of the launch of the system house, this tranche had to wait for completion of prior activities. | - | 2015 |  | Investment
ONG | UNIDO | HCFC phase-out management plan (stage I, fifth tranche) (refrigeration air-conditioning manufacturing sector) | Multi-Year | AFR | NIR | PHA | 75 | TAS | 144 | A | I | HCFC | 34.1 | 0 |  |  | 2015-11-01 |  | 2018-12-01 | 2019-03-01 |  |  | 193908 | 0 | 193908 | 0 | 0% | 193908 | 92215 | 50000 | 14543 | 0 | 0 | 14543 | 6916.125 | Some of this tranche will be given as IOC to the last 45 beneficiaries in the form of chemicals for formulation. The remaining proposed beneficiaries will be supported with training on formulation. Activities for this last set of beneficiaries will start in the last quarter of 2017. Milestone 1: Bids prepared and requested Milestone 2: Contracts awarded Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: Yes Any action required by Executive Committee? No | Chemicals for IOC were procured in 2016. Milestone 1: Bids prepared and requested Milestone 2: Contracts awarded' Milestone 3: Chemicals for formulation delivered in January 2017 - Training on formulation to commence in 3rd quarter 2017 Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: Yes Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Preparation of CFC phase out strategy for refrigeration and A/C industries and services | Individual | AFR | NIR | REF | 11 | TAS | 07 | A | I |  | 0 | 0 |  |  | 1993-11-01 | 1994-11-01 | 1994-11-01 |  | 1999-12-01 | 2000-08-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0 | FIN |  |  | 1999-12-01 | NON-INV
FIN | UNIDO | Phasing out of CFCs at Debo Industries Ltd. Nigeria | Individual | AFR | NIR | REF | 18 | INV | 10 | A | I | CFC | 52 | 52 |  |  | 1995-11-01 | 1996-12-01 | 1997-05-01 |  | 1998-12-01 | 2003-05-01 | 1048053 | 0 | 1048053 | 1048052.6 | 100% | 0.4 | 0 |  | 136247 | -44 | 136203 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs at Thermocool Eng. Co. Ltd. | Individual | AFR | NIR | REF | 18 | INV | 11 | A | I | CFC | 82 | 82 |  |  | 1995-11-01 | 1997-07-01 | 1997-05-01 |  | 1998-12-01 | 2003-05-01 | 1465750 | 0 | 1465750 | 1465750.06 | 100% | -0.06 | 0 |  | 190548 | -10 | 190538 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with cyclopentane in the manufacture of domestic refrigeration appliances at A.G. Leventis | Individual | AFR | NIR | REF | 26 | INV | 30 | A | I | CFC | 19.1 | 19.1 |  |  | 1998-11-01 | 1999-11-01 | 2000-12-01 |  | 2003-03-01 | 2004-04-01 | 190420 | 0 | 190420 | 190420.01 | 100% | -0.01 | 0 |  | 24755 | 0 | 24755 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with cyclopentane in the manufacture of domestic refrigeration appliances at New Ltd. | Individual | AFR | NIR | REF | 26 | INV | 40 | A | I | CFC | 20.9 | 20.9 |  |  | 1998-11-01 | 1999-11-01 | 2000-12-01 |  | 2000-12-01 | 2003-05-01 | 361770 | 0 | 361770 | 361769.86 | 100% | 0.14 | 0 |  | 47030 | 0 | 47030 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with cyclopentane in the manufacture of domestic refrigeration appliances at Kolinton Technical Industries | Individual | AFR | NIR | REF | 26 | INV | 44 | A | I | CFC | 39.5 | 39.5 |  |  | 1998-11-01 | 1999-11-01 | 2000-06-01 |  | 2003-12-01 | 2004-06-01 | 674348 | -902 | 673446 | 673445.54 | 100% | 0.46 | 0 |  | 84178 | -216 | 83962 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of domestic refrigeration at Soesons Ltd. | Individual | AFR | NIR | REF | 28 | INV | 48 | A | I | CFC | 16.1 | 16.1 |  |  | 1999-07-01 | 2000-05-01 | 2001-02-01 |  | 2003-02-01 | 2003-08-01 | 221353 | 0 | 221353 | 221353 | 100% | 0 | 0 |  | 28776 | 0 | 28776 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of domestic refrigeration at Onward Electrical Industry Ltd. | Individual | AFR | NIR | REF | 28 | INV | 51 | A | I | CFC | 10.7 | 10.7 |  |  | 1999-07-01 | 2000-08-01 | 2001-02-01 |  | 2003-12-01 | 2004-04-01 | 146927 | 0 | 146927 | 146927 | 100% | 0 | 0 |  | 19101 | 0 | 19101 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of domestic refrigeration at United Technologies Ltd. | Individual | AFR | NIR | REF | 28 | INV | 52 | A | I | CFC | 9.6 | 9.6 |  |  | 1999-07-01 | 2000-05-01 | 2001-02-01 |  | 2003-02-01 | 2003-12-01 | 130579 | 0 | 130579 | 130578.84 | 100% | 0.16 | 0 |  | 16975 | -6 | 16969 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of domestic refrigeration equipment at De Johnson Ltd. | Individual | AFR | NIR | REF | 29 | INV | 53 | A | I | CFC | 9 | 9 |  |  | 1999-11-01 | 2000-09-01 | 2001-06-01 |  | 2001-12-01 | 2003-12-01 | 123816 | 0 | 123816 | 123816 | 100% | 0 | 0 |  | 16096 | 0 | 16096 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 withHCFC-141b in the manufacture of commercial refrigeration at Austin-Laz & Co. Ltd | Individual | AFR | NIR | REF | 29 | INV | 54 | A | I | CFC | 11.6 | 11.6 |  |  | 1999-11-01 | 2000-10-01 | 2001-06-01 |  | 2002-08-01 | 2003-07-01 | 147181 | 0 | 147181 | 147181 | 100% | 0 | 0 |  | 19134 | 0 | 19134 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the commercial refrigeration sector | Individual | AFR | NIR | REF | 30 | PRP | 62 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-07-01 | 2001-04-01 |  | 2001-02-01 | 2002-09-01 | 25000 | -2212 | 22788 | 22787.85 | 100% | 0.15 | 0 |  | 3250 | -292 | 2958 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC=12 withHFC-134a, and foam flowing agent CFC-11 withHCFC-141b in the manufacture of commercial refrigeration equipment at Bosmak Nigeria Ltd. | Individual | AFR | NIR | REF | 32 | INV | 71 | A | I | CFC | 10.8 | 10.8 |  |  | 2000-12-01 | 2001-09-01 | 2003-07-01 |  | 2003-10-01 | 2004-06-01 | 154245 | -420 | 153825 | 153825.48 | 100% | -0.48 | 0 |  | 20052 | -86 | 19966 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a, and foam flowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment at Coldcare Nigeria Ltd. | Individual | AFR | NIR | REF | 32 | INV | 76 | A | I | CFC | 11.4 | 11.4 |  |  | 2000-12-01 | 2001-09-01 | 2003-07-01 |  | 2002-12-01 | 2003-12-01 | 173200 | 0 | 173200 | 173200 | 100% | 0 | 0 |  | 22516 | 0 | 22516 | 0 | 0 | FIN
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a, and foam flowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment at Akocen Nigeria Ltd. | Individual | AFR | NIR | REF | 32 | INV | 77 | A | I | CFC | 12.1 | 12.1 |  |  | 2000-12-01 | 2001-09-01 | 2003-07-01 |  | 2002-10-01 | 2003-10-01 | 157894 | 0 | 157894 | 157894.01 | 100% | -0.01 | 0 |  | 20526 | 0 | 20526 | 0 | 0 | FIN
FIN | UNDP | Technical assistance to prepare a refrigeration management plan (RMP) | RMP-Component | AFR | NIR | REF | 32 | TAS | 72 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-05-01 | 2003-01-01 |  | 2002-12-01 | 2003-11-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2000 |  | Non-Investment
FIN | UNIDO | Project preparation for three projects in the commercial refrigeration sector | Individual | AFR | NIR | REF | 33 | PRP | 80 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-08-01 | 2002-04-01 |  | 2001-11-01 | 2002-12-01 | 20000 | -1718 | 18282 | 18282.2 | 100% | -0.2 | 0 |  | 2600 | -227 | 2373 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134 and foam blowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment at Polade | Individual | AFR | NIR | REF | 35 | INV | 97 | A | I | CFC | 8.3 | 8.3 |  |  | 2001-12-01 | 2002-03-01 | 2004-05-01 |  | 2004-06-01 | 2005-03-01 | 70382 | 0 | 70382 | 70381.99 | 100% | 0.01 | 0 |  | 9150 | -4 | 9146 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment at Ristian | Individual | AFR | NIR | REF | 35 | INV | 98 | A | I | CFC | 11 | 11 |  |  | 2001-12-01 | 2002-09-01 | 2004-05-01 |  | 2004-06-01 | 2005-12-01 | 143729 | -706 | 143023 | 143023.47 | 100% | -0.47 | 0 |  | 18685 | -122 | 18564 | -1 | 0 | FIN |  |  |  | INV
FIN | UNDP | Preparation of a refrigerant management plan | Individual | AFR | NIR | REF | 36 | PRP | 99 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-12-01 | 2003-11-01 | 40000 | -1 | 39999 | 39999 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2002 |  | Investment
FIN | UNIDO | Preparation for HCFC phase-out investment activities (refrigeration manufacturing sector) | Individual | AFR | NIR | REF | 58 | PRP | 124 | A | I |  | 0 | 0 |  |  | 2009-07-01 | 2009-12-01 | 2010-07-31 |  | 2010-12-01 | 2012-10-01 | 50000 | -2342 | 47658 | 47658.44 | 100% | -0.44 | 0 |  | 3750 | -176 | 3574 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | Japan | Preparation for a demonstration project to validate the trans-critical CO2 refrigeration technology for application to ice-block makers at Austin Laz | Individual | AFR | NIR | REF | 61 | PRP | 127 | A | I | HCFC-22 | 0 |  | 0 |  | 2010-07-01 | 2010-11-01 | 2011-07-01 |  | 2012-07-01 | 2013-12-01 | 30000 | -2648 | 27352 | 27352 | 100% | 0 | 0 | 0 | 3900 | -344 | 3556 | 0 | 0 | Financial completion in Dec 2013. Refund was reported to 71st ExCom, Dec 2013. FIN. |  | 2010
ONG | UNIDO | Preparation for HCFC phase-out investment activities (stage II) (refrigeration and air-conditioning manufacturing sector) | Individual | AFR | NIR | REF | 72 | PRP | 137 | A | I |  | 0 | 0 |  |  | 2014-05-01 | 2014-08-01 | 2015-05-31 | 2017-12-31 |  |  | 150000 | 0 | 150000 | 101009 | 67.34% | 48991 | 6830.62 | 30000 | 10500 | 0 | 7071 | 3429 | 478 | - Surveys were completed in the ice-machine and AC manufacturing sectors for the preparation of Stage II of the HPMP. -Milestone 1: UNIDO stakeholder and survey validation meeting was held in 2016 Was there any delay during the reporting year? Yes. The survey of the spray foam sector under UNDP was not completed so the submission is delayed. Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Completion date changed to December 2017. Any action required by Executive Committee? No | '- Surveys were completed in the ice-machine and AC manufacturing sectors for the preparation of Stage II of the HPMP. Milestone 1: UNIDO stakeholder and survey validation meeting was held in 2016 '- Stakeholder consultation meeting held with UNDP in March 2017 -Submission planned for 79th ExCom Was there any delay during the reporting year? No Any recurring problem? No Any action required by Executive Committee? No |  |  | NON-INV
FIN | IBRD | Country programme preparation (1991) | Individual | AFR | NIR | SEV | 04 | CPG | 02 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1993-02-01 |  | 1991-12-01 | 1991-12-01 | 129981 | -44959 | 85022 | 85022 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
CLO | IBRD | Preparation of investment projects (1991) |  | AFR | NIR | SEV | 04 | PRP | 20 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1992-06-01 |  |  | 1992-06-01 | 82821 | -82821 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | National seminar on industry and protection of the ozone layer | Individual | AFR | NIR | SEV | 04 | TRA | 01 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1992-06-01 | 1992-11-01 |  | 1992-12-01 | 1997-12-01 | 49650 | -23201 | 26449 | 26449 | 100% | 0 | 0 | 0 | 6454.5 | -3016.13 | 3438.37 | 0 | 0 | Completed in 1992. Financially completed in 1997. |  | 1991 |  | Non-Investment
FIN | IBRD | Country programme preparation (1992) | Individual | AFR | NIR | SEV | 06 | CPG | 03 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 271255 | -214838 | 56417 | 56417 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
CLO | IBRD | Preparation of investment projects (1992) |  | AFR | NIR | SEV | 06 | PRP | 04 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1993-02-01 |  |  | 1992-12-01 | 144078 | -144078 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Country programme preparation (1993) | Individual | AFR | NIR | SEV | 09 | CPG | 17 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 35100 | -11028 | 24072 | 24072 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Institutional strengthening | Individual | AFR | NIR | SEV | 09 | INS | 06 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1995-01-01 | 1996-03-01 |  | 2001-01-01 | 2003-09-01 | 300000 | 0 | 300000 | 300000 | 100% | 0 | 0 | 0 | 39000 | 0 | 39000 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1993 | 1999-12-01 | Non-Investment
CLO | IBRD | Preparation of investment projects (1993) |  | AFR | NIR | SEV | 09 | PRP | 05 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 |  | 1994-03-01 |  |  | 1993-12-01 | 62500 | -62500 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Country programme preparation (1994) | Individual | AFR | NIR | SEV | 12 | CPG | 18 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 150000 | -143520 | 6480 | 6480 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
CLO | IBRD | Preparation of investment projects (1994) |  | AFR | NIR | SEV | 12 | PRP | 08 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1995-12-01 |  |  | 1995-12-01 | 100000 | -100000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | IBRD | Country programme preparation (1995) | Individual | AFR | NIR | SEV | 16 | CPG | 19 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-31 | 1996-03-01 |  | 1997-06-01 | 1997-06-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | UNDP | Project preparation assistance | Individual | AFR | NIR | SEV | 17 | PRP | 09 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-03-01 | 1996-07-01 |  | 1996-12-01 | 1998-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Renewal of institutional strengthening project (phase II) | Individual | AFR | NIR | SEV | 34 | INS | 93 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2003-08-01 |  | 2003-08-01 | 2009-07-01 | 200000 | -851 | 199149 | 199149 | 100% | 0 | 0 | 0 | 26000 | -110.63 | 25889.37 | 0 | 0 | Completed in 2003.Financially completed in 2009. |  | 2001 |  | Non-Investment
FIN | UNDP | Country programme update | Individual | AFR | NIR | SEV | 36 | CPG | 102 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-10-01 |  | 2007-12-01 | 2011-11-01 | 241493 | -10289.19 | 231203.81 | 231204 | 100% | -0.19 | 0 | 0 | 31394.09 | -1337.59 | 30056.5238 | -0.0238 | 0 | Completed in 2007. |  | 2002 |  | Non-Investment
COM | Japan | Assistance for a national information, education and communication campaign for compliance with the Montreal Protocol | Individual | AFR | NIR | SEV | 38 | TAS | 104 | A | I | CFC | 5.6 |  | 0 |  | 2002-11-01 | 2004-12-01 | 2003-11-01 |  | 2008-10-01 |  | 68000 | -60900 | 7100 | 7100 | 100% | 0 | 25000 | 60900 | 8840 | -7917 | 923 | 0 | 3250 | The remaining fund will be used for mission of the NOU and relevant national expert to Japan to review the program. |  | 2002
FIN | UNDP | Extension of institutional strengthening project | Individual | AFR | NIR | SEV | 40 | INS | 107 | N | I | No_ODP | 21.5 | 21.5 | 0 | 0 | 2003-07-01 | 2004-07-01 | 2005-07-01 |  | 2006-12-01 | 2012-04-01 | 260000 | -100.24 | 259899.76 | 259900 | 100% | -0.24 | 0 | 0 | 19500 | -7.52 | 19492.5 | -0.02 | 0 | Financially completed in 2012. |  | 2003 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | NIR | SEV | 48 | INS | 114 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2006-07-01 | 2008-04-01 |  | 2007-12-01 | 2012-04-01 | 260000 | -195.2 | 259804.8 | 259805 | 100% | -0.2 | 0 | 0 | 19500 | -14.64 | 19485.375 | -0.015 | 0 | Financially completed in 2012. |  | 2006 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase V) | Individual | AFR | NIR | SEV | 54 | INS | 118 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-05-01 | 2010-03-01 |  | 2010-12-01 | 2013-03-01 | 260000 | -3766.54 | 256233.46 | 256233 | 100% | 0.46 | 0 | 0 | 19500 | -282.49 | 19217.475 | 0.035 | 0 | Financially completed in 2013. |  | 2008 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VI) | Individual | AFR | NIR | SEV | 62 | INS | 130 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-03-01 | 2012-11-01 |  | 2013-07-01 | 2014-02-01 | 260000 | -2008.09 | 257991.91 | 257992 | 100% | -0.09 | 0 | 0 | 19500 | -150.61 | 19349.4001 | -0.01005 | 0 | Financially Completed in 2014. | Completed in 2013. | 2010 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VII: 12/2012-11/2014) | Individual | AFR | NIR | SEV | 68 | INS | 134 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-04-01 | 2014-11-01 |  | 2014-12-01 | 2016-02-01 | 260000 | 0 | 260000 | 260000 | 100% | 0 | 0 | 0 | 18200 | 0 | 18200 | 0 | 0 | Financially completed in 2016. | Delegation of Authority issued, implementation will be initiated shortly, with the Project Document revision. | 2012 |  | Non-investment
ONG | UNDP | Extension of the institutional strengthening project (phase VIII: 12/2014-11/2016) | Individual | AFR | NIR | SEV | 73 | INS | 141 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-11-01 | 2015-01-01 | 2016-11-01 | 2017-11-01 |  |  | 260000 | 0 | 260000 | 254432.45 | 97.86% | 5567.55 | 0 | 2227.02 | 18200 | 0 | 17810.2715 | 389.7285 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Data reporting, awareness raising, support to national Montreal Protocol Projects were achieved in 2016. Prodoc signed (actual/planned, yes/no and date):1/1. Yes. Agreement signed earlier. Missions undertaken (actual/planned):0/0 TOR for consultants/subcontracts completed (actual/planned): ToR completed earlier Contract/PO/MOA agreements signed: No First disbursement date (actual/planned): NAAny delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | - | 2014 |  | Non-Investment
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | AFR | NIR | SEV | 74 | TAS | 142 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-03-01 | 2016-05-01 | 2017-05-01 |  |  | 65000 | 0 | 65000 | 45450 | 69.92% | 19550 | 0 | 1955 | 8450 | 0 | 5908.5 | 2541.5 | 0 | Brief progress report (actual/planned): The first stakeholders meeting was organized by the NOU on 7th June, 2016 at the Federal Ministry of Environment Zonal Office, Lagos, where 35 participants from the ODS Alternative user sectors and importers attended. The main goal of the meeting was to sensitize the government and industry on the survey and agree on the plan for the Survey of ODS alternatives at the national level and obtain support of main national stakeholders. One National Consultant was hired in April 2016 by the NOU to support the data collection. The National Consultant assisted the NOU in the identification of the current use of ODS alternatives by substance/sector and collection of import/export data for the substances for the past a couple of years. The National Consultant also provided support in establishing growth patterns in use by substance/sector and in compiling data on available ODS alternatives for various applications. The NOU and the National Consultant drafted and cross checked the information to ensure the completion of end-user surveys, collection, analysis, and aggregation of consumption data. The various sections of the report were drafted. The second stakeholders meeting was organized by the NOU in 20th December, 2016 at the Federal Ministry of Environment Zonal Office, Lagos, with the main goal to organise consultations with representatives of the government and private sector to finalize the outcomes of the Survey of ODS alternatives and discuss potential opportunities for introduction of those alternatives in the country. A total of 30 participants from the sectors using ODS Alternatives were in attendance. The draft report was prepared by the NOU and the National Consultant. It was reviewed and finalized based on the format approved by ExCom decision 75/67 as contained in document UNEP/OzL.Pro/ExCom/75/77/Rev.1 after incorporating inputs/ comments raised during National Stakeholders’ workshop. The final report was submitted to UNEP in December 2016 for final review and submission to MLFS. The NOU participated in the ODS Alternative Thematic workshop held in December 2016 to refine the draft report according to the revised template for the report. The report has been finally submitted to UNEP. Legal arrangements(actual/planned): N/A___Initial stages of project implementation(actual/planned): _Yes__ Intermediate goals achieved (actual/planned): Yes___ Project completion and follow up: _No__ First disbursement date (actual/planned): _N/A__ All funds disbursed (yes/no): No___ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): __N/A_ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): The NOU incorporated comments from UNEP ROA and Paris and re-submitted final ODS survey report in February 2017. The NOU continues to monitor imports and trade of ODS and ODS related equipment.
ONG | UNDP | Extension of the institutional strengthening project (phase X: 12/2016-11/2018) | Individual | AFR | NIR | SEV | 76 | INS | 145 | N | I | HCFC | 0 | 0 | 0 | 0 | 2016-05-01 |  | 2018-11-01 | 2017-11-01 |  |  | 332800 | 0 | 332800 | 0 | 0% | 332800 | 0 | 133120 | 23296 | 0 | 0 | 23296 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): The project was set to start in December 2016. No expenditure was incurred during that month yet. Prodoc signed (actual/planned, yes/no and date):1/1 Yes October 2016 Missions undertaken (actual/planned):No TOR for consultants/subcontracts completed (actual/planned): No Contract/PO/MOA agreements signed: No First disbursement date (actual/planned): Planned in January 2017Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | Project started as per planned activities, including data collection and planning for the 30th anniversary celebrations. |  |  | Non-Investment
FIN | UNIDO | Preparation of a sectoral phase-out plan in solvents | Individual | AFR | NIR | SOL | 36 | PRP | 101 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-09-01 | 2003-07-01 |  | 2004-06-01 | 2004-11-01 | 70000 | 0 | 70000 | 69999.95 | 100% | 0.05 | 0 |  | 9100 | -8 | 9092 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal ODS phase out umbrella project in the solvent sector (first tranche) | Multi-Year | AFR | NIR | SOL | 43 | INV | 110 | A | I | CTC | 152.1 | 152.1 |  |  | 2004-07-01 | 2004-12-01 | 2005-12-01 |  | 2005-12-01 | 2007-05-01 | 530000 | 0 | 530000 | 530000 | 100% | 0 | 0 |  | 39750 | 0 | 39750 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal ODS phase-out umbrella project in the solvent sector (2nd tranche) | Multi-Year | AFR | NIR | SOL | 46 | INV | 113 | A | I | CTC TCA | 0 | 0 |  |  | 2005-07-01 | 2005-11-01 | 2006-07-01 |  | 2006-07-01 | 2008-09-01 | 317000 | 0 | 317000 | 317000 | 100% | 0 | 0 |  | 23775 | 0 | 23775 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal ODS phase-out umbrella project in the solvent sector (fourth tranche) | Multi-Year | AFR | NIR | SOL | 52 | INV | 116 | A | I | CTC | 45.9 | 45.9 |  |  | 2007-07-01 | 2007-12-01 | 2010-01-01 |  | 2012-11-01 | 2015-03-01 | 303200 | -14387 | 288813 | 288812.68 | 100% | 0.32 | 0 |  | 22740 | -1079 | 21661 | 0 | 0 | FIN |  |  |  | INV
FIN | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, first tranche, Niue) | Multi-year | ASP | NIU | PHA | 63 | TAS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-10-01 | 2015-03-01 |  | 2016-05-01 | 2016-11-01 | 45625 | 0 | 45625 | 45625 | 100% | 0 | 0 |  | 5931 | 0 | 5931 | 0 | 0 | Brief progress report (actual/planned): Following the submission of final progress report in April 2016, the final payment of the first tranche implementation was transfererd to the country. The project was financially completed in 2016. Legal arrangement: The SSFA was signed in September 2011. First Mission: August 2013 TOR completed: Not applicable First disbursement date: October 2011 All funds disbursed (yes/no): Yes. Any delay? (yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/A | Project financially completed.
ONG | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, second tranche, Niue) | Multi-year | ASP | NIU | PHA | 74 | TAS | 10 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-05-01 | 2020-05-01 | 2020-12-01 |  |  | 20075 | 0 | 20075 | 8600 | 42.84% | 11475 | 9775 | 1147.5 | 2610 | 0 | 1118.1071 | 1491.8929 | 1270.8717 | Brief progress report (actual/planned): The SSFA was signed by UNEP and the Government of Niue in March 2016. The first payment under the second tranche was made to the country in May 2016. Niue has maintained zero consumption of HCFCs since 2011 and this achievement can be maintained in 2016. UNEP conducted a misison in September 2016 to follow-up project implementation and jointly delivered update training workshop for customs and enforcement officers. An update customs and enforcement training workshop was organized on 7 September 2016 with participation of 17 participants (including other stakeholders) to build awareness and local capacity in the prevention of smuggling and safe handling of flammable refrigerants, which has been available in the PIC region. A regional RAC expert was recruited to deliver update RAC training workshop. Niue organized an update RAC training workshops from 28-30 November 2016 (with 17 participants). UNEP worked closely with the NOU to engage multi-stakeholders in the implementation of HPMP, second tranche to synergize HPMP with other on-going environmental policies/projects e.g. PALS, Samoa Pathway. 2015 CP data was submitted to MLFS. UNEP is also facilitating capacity building through South/South cooperation. Legal arrangements (actual/planned): The SSFA was signed in March 2016. First Mission: September 2016. TOR completed: Not applicable First disbursement date: May 2016. All funds disbursed (yes/no): No. Any delay? (yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): UNEP keeps regular communications with the country to expedite HPMP implementation as per the agreed work plan. Niue has already submitted 2016 CP data to the MLFS through UNEP.
FIN | UNEP | Implementation of the PIC strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | NIU | REF | 44 | TAS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2006-12-01 |  | 2007-11-01 | 2009-12-01 | 14000 | -3277 | 10723 | 10723 | 100% | 0 | 0 |  | 1820 | -426.01 | 1393.99 | 0 | 0
FIN | UNEP | Implementation of the PIC strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | NIU | REF | 44 | TRA | 03 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2010-01-01 | 2006-12-01 |  | 2008-12-01 | 2010-12-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 | 0 |  | 1040 | 0 | 1040 | 0 | 0
FIN | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | NIU | SEV | 44 | INS | 01 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-03-01 | 2005-12-01 |  | 2006-06-01 | 2007-06-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (2nd year of phase I) | Individual | ASP | NIU | SEV | 50 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-08-01 | 2007-11-01 |  | 2008-11-01 | 2010-12-01 | 15000 | -4900 | 10100 | 10100 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase II) | Individual | ASP | NIU | SEV | 53 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-07-01 | 2009-11-01 |  | 2009-12-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | ASP | NIU | SEV | 59 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-08-01 | 2011-11-01 |  | 2011-12-01 | 2012-12-01 | 32500 | 27500 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV: 12/2011-11/2013) | Individual | ASP | NIU | SEV | 64 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-09-01 | 2013-11-01 |  | 2013-11-01 | 2014-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase V: 12/2013-11/2015) | Individual | ASP | NIU | SEV | 70 | INS | 09 | A | I |  | 0 |  | 0 |  | 2013-07-01 | 2014-05-01 | 2015-11-01 |  | 2016-09-01 | 2016-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The NOU has been responsible for the management of all Montreal Protocol activities. The operation of the NOU was going on well. In 2016, Niue was able to maintain the zero consumption since 2011. NOU also coordinated and facilitated the implementation of HPMP and ODS Alternative Survey. The NOU also organized the 2016 ozone day celebration, and actively joined the regional and global ozone related meetings e.g. the network meeting. 2015 Article 7 and CP data were submitted to the Ozone Secretariat and MLFS respectively. The IS project phase V was financially completed in 2016. Legal arrangements(actual/planned): The SSFA was signed in April 2014. Initial stages of project implementation(actual/planned): Dec 2013/Apr 2014. Intermediate goals achieved (actual/planned): Maintain zero consumption since 2011. First disbursement date (actual/planned): May 2014. All funds disbursed (yes/no): Yes. Any delay?(yes/no): No, the project was completed in 2016. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date (yes/no): The project was completed. Any ongoing problems (yes/no): No. NOO and Head of Environment is responsive to the dedicated support that UNEP CAP is providing. If Yes, is any action required by ExCom: N/A. | Project financially completed.
ONG | UNEP | Extension of the institutional strengthening project (phase VI: 12/2015-11/2017) | Individual | ASP | NIU | SEV | 75 | INS | 11 | A | I |  | 0 |  | 0 |  | 2015-11-01 |  | 2015-11-01 | 2018-12-01 |  |  | 85000 | 0 | 85000 | 30009.18 | 35.3% | 54990.82 | 0 | 5499.082 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The SSFA was signed by UNEP and the Government of niue in December 2016. Legal arrangements(actual/planned): The SSFA was signed in December 2016. Initial stages of project implementation(actual/planned): Dec 2015/Dec 2016. Intermediate goals achieved (actual/planned): Not yet. First disbursement date (actual/planned): Not yet. All funds disbursed (yes/no): No. Any delay?(yes/no): Yes. If Yes, reasons for delay & action plan to resolve: The project was behind the approved schedule due to the delay in closure of IS Phase V. If Yes, will delay have impact on project completion date (yes/no): Yes, the project will be closed one year behind the approved schedule. Any ongoing problems (yes/no): No. NOO and Head of Environment is responsive to the dedicated support that UNEP CAP is providing. If Yes, is any action required by ExCom: N/A. | Brief progress report (actual/planned): Country continues to enforce the licensing and quota system. The first payment under the IS Project phase VI has been requested, but not yet transferred from UNON to the country.
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | ASP | NIU | SEV | 75 | TAS | 12 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-10-01 | 2016-12-01 | 2017-06-01 |  |  | 40000 | 0 | 40000 | 10000 | 25% | 30000 | 5000 | 3000 | 5200 | 0 | 1300 | 3900 | 650 | Brief progress report (actual/planned): The SSFA was signed by UNEP and the Government of Niue in September 2016. The first payment was made to the country in October 2016. NOO attended the training for conducting natiional surveys as part of Thematic workshop for Asia and the Pacific in June 2016. The national stakeholder workshop was organzied during UNEP mission in September 2016. A regional expert was appointed by UNEP to provide support to the NOO in the planned, data collection and preparation of report. The survey methodology and questionnaire have been finalized and agreed. The regioanl consultant conducted a mission in November 2016 to support the NOO to lead the data collection. The local consultant was recruited by the Government to conduct the dada collection. The data collection and reviews are on-going. Legal arrangements(actual/planned): The SSFA was signed in September 2016 Initial stages of project implementation(actual/planned): June 2016 . Intermediate goals achieved (actual/planned): Not applicable. Project completion and follow up: Not applicable. First disbursement date (actual/planned): October 2016. All funds disbursed (yes/no): No. Any delay?(yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): With the guidance of UNEP, the regional consultant assisted the NOU and the local consultant in the identification of the current use of ODS alternatives by substance/sector and collection of import/export data for the substances for the past a couple of years. The regional consultant also provided support in establishing growth patterns in use by substance/sector and in compiling data on available ODS alternatives for various applications. The UNEP, NOU and regional consultant drafted and cross checked the information to ensure the completion of end-user surveys, collection, analysis, and aggregation of consumption data. The draft report will be prepared by the NOU and the regional consultant based on the format approved by ExCom decision 75/67 as contained in document UNEP/OzL.Pro/ExCom/75/77/Rev.1.
FIN | UNIDO | Awareness workshop and training on methyl bromide alternatives | Individual | ASP | OMA | FUM | 44 | TRA | 10 | A | I |  | 0 | 0 |  |  | 2004-12-01 | 2006-05-01 | 2005-12-01 |  | 2006-09-01 | 2007-10-01 | 35000 | -2078 | 32922 | 32921.71 | 100% | 0.29 | 0 |  | 3150 | -187 | 2963 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | Germany | Project preparation/technical assistance for the halon sector | Individual | ASP | OMA | HAL | 34 | PRP | 03 | A | I |  | 0 |  | 0 |  | 2001-07-01 | 2001-09-01 | 2002-01-01 |  | 2003-07-01 | 2003-12-01 | 17000 | 0 | 17000 | 17000 | 100% | 0 | 0 | 0 | 2210 | 0 | 2210 | 0 | 0 | Int.consultant visited Oman, nat. consultants identified, Implemenation of the projects will be done by World Bank on request of Oman, results transferred to WB Jul-03. WB TAS-Project approved 41st ExCom.
TRF | IBRD | Halon consumption phase-out through a technical assistance programme and a halon recycling | Halon Banking | ASP | OMA | HAL | 41 | TAS | 08 | N | I |  | 0 | 0 | 0 | 0 | 2003-12-01 |  | 2005-12-01 |  |  | 2005-07-01 | 64600 | -64600 | 0 | 0 | #DIV/0! | 0 | 0 |  | 5814 | -5814 | 0 | 0 | 0 | Project transferred to UNIDO at the 46th ExCom. |  |  |  | Non-INV | 0
FIN | UNIDO | Halon consumption phase-out through a technical assistance programme and a halon recycling | Individual | ASP | OMA | HAL | 46 | TAS | 12 | A | I | HAL | 6.85 | 6.85 |  |  | 2005-07-01 | 2007-02-01 | 2006-12-01 |  | 2010-12-01 | 2011-12-01 | 64600 | -4821 | 59779 | 59779.2 | 100% | -0.2 | 0 |  | 5814 | -434 | 5380 | 0 | 0 | FIN |  |  | 2008-02-01 | INV
FIN | UNIDO | Preparation of a terminal phase-out management plan | Individual | ASP | OMA | PHA | 46 | PRP | 13 | A | I |  | 0 | 0 |  |  | 2005-07-01 | 2006-02-01 | 2006-07-01 |  | 2007-03-01 | 2007-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 2250 | 0 | 2250 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Terminal phase-out management plan (first tranche) | Multi-Year | ASP | OMA | PHA | 52 | INV | 15 | A | I | CFC | 10 | 10 |  |  | 2007-07-01 | 2007-12-01 | 2009-12-31 |  | 2009-07-01 | 2012-12-01 | 305800 | 0 | 305800 | 305800.47 | 100% | -0.47 | 0 |  | 22935 | 0 | 22935 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | ASP | OMA | PHA | 55 | PRP | 16 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2009-02-01 | 2009-07-31 |  | 2011-12-01 | 2012-12-01 | 100000 | -292 | 99708 | 99708.42 | 100% | -0.42 | 0 |  | 7500 | -22 | 7478 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | OMA | PHA | 55 | PRP | 17 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2010-06-01 | 2009-07-01 |  | 2011-12-01 | 2014-05-01 | 50000 | -11000 | 39000 | 39000 | 100% | 0 | 0 |  | 6500 | -1430 | 5070 | 0 | 0
FIN | UNIDO | Terminal phase-out management plan (second tranche) | Multi-Year | ASP | OMA | PHA | 57 | INV | 19 | A | I | CFC | 25 | 25 |  |  | 2009-04-01 | 2009-11-01 | 2010-03-31 |  | 2011-12-01 | 2013-12-01 | 164200 | -37297 | 126903 | 126903.03 | 100% | -0.03 | 0 |  | 12315 | -2797 | 9518 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Audit for the terminal phase-out management plan | Individual | ASP | OMA | PHA | 57 | TAS | 20 | A | I |  | 0 | 0 |  |  | 2009-04-01 | 2010-09-01 | 2010-03-31 |  | 2010-12-01 | 2011-07-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 1800 | 0 | 1800 | 0 | 0 | FIN |  |  |  | NON-INV
COM | UNIDO | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | ASP | OMA | PHA | 65 | INV | 23 | A | I | HCFC | 2.3 | 2.3 |  |  | 2011-11-01 | 2013-01-01 | 2015-11-30 |  | 2015-06-01 |  | 210000 | 0 | 210000 | 209153.37 | 99.6% | 846.63 | 0 | 1 | 15750 | 0 | 15687 | 63 | 0 | The project was operationally completed. |  |  |  | INV
FIN | UNIDO | HCFC phase-out management plan (stage I, first tranche) (technical assistance for the foam sector) | Multi-Year | ASP | OMA | PHA | 65 | INV | 24 | A | I | HCFC | 2.3 | 2.3 |  |  | 2011-11-01 | 2012-05-01 | 2012-12-31 |  | 2014-06-01 | 2016-03-01 | 104120 | -574 | 103546 | 103545.66 | 100% | 0.34 | 0 |  | 7809 | -43 | 7766 | 0 | 0 | The project was financially completed and the balance was returned at the 76th ExCom. |  |  |  | INV
COM | UNEP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | ASP | OMA | PHA | 65 | TAS | 22 | A | I |  | 0.7 | 0 | 0 | 0 | 2011-11-01 | 2013-04-01 | 2015-11-01 |  | 2016-11-01 |  | 65000 | 0 | 65000 | 65000 | 100% | 0 | 0 |  | 8450 | 0 | 8450 | 0 | 0 | Brief progress report (actual/planned): The NOC held 3 meetings in 2016 and a meeting in Mar. 2017; A study tour organized to Jordan in May 2016 for two experts from the Occupational standards and Testing center entrusted with the implementation of the RAC certification scheme to exchange experiences with their peers in Jordan being the only country in the region with operational certification scheme for RAC technicians. Final progress report received from Oman on 26 May shows that all planned activities under this stage have been implemented successfully leading to full achievement of the planned objectives under stage I. Specifically, the country completed the remaining work for establishing a national e-licensing as well as the RAC certification scheme and will be fully operational in close cooperation with Customs Dept. during 2017. A training workshop for RAC technicians on good practices held in Muscat during 10-13 Oct. 2016 in partnership with OVSTC. Final steps are being taken to ensure full enforcement of the certification scheme in 2017. Legal arrangements (actual/planned): The SSFA agreement for the implementation of the first stage under HPMP was signed in Feb. 2013. mission (actual/planned): three missions to the country took place during 2016 with last in Oct. 2016 to follow up and expedite implementation of remained activities under the stage mainly the certification scheme and the e-licensing system - TOR completed (actual/planned): completed - CAP staff implementing directly with national concerned authorities First disbursement date (actual/planned): 1st disbursement done in Q2 2013 All funds disbursed (yes/no): No, the final payment under the SSFA was made and final financial and progress reports received. Any delay? (yes/no): No delay in the project, though of the delayed adoption of the e-LS and the certification scheme due to complexity. If Yes, reasons for delay & action plan to resolve: n/a If Yes, will delay have impact on project completion date (yes/no): n/a Any ongoing problems (yes/no): no If Yes, is any action required by ExCom: n/a | Brief progress report (actual/planned): The NOC held 1 meeting so far in Mar. 2017 with the main focus on the requirements for full enforcement of the certification scheme for RAC technicians; A study tour will be organized for the NOU staff and respective authorities to exchange experiences on the certification of RAC workshops. all planned activities under this stage have been implemented successfully leading to full achievement of the planned objectives under stage I. hence the work for operating the e-licensing as well as the RAC certification scheme and will be continued under stage II. Legal arrangements (actual/planned): The SSFA agreement for the implementation of the first stage under HPMP was signed in Feb. 2013 and closed in 2016. mission (actual/planned): one mission to the country took place in Mar. 2017 to follow up and expedite implementation of activities under stage i and stage II mainly the certification scheme and the e-licensing system - TOR completed (actual/planned): completed - CAP staff implementing directly with national concerned authorities First disbursement date (actual/planned): 1st disbursement done in Q2 2013; All funds disbursed (yes/no): No, the final payment under the SSFA was made in 2016 and final financial and progress reports received.the project will be closed financially by 2017. Any delay? (yes/no): No delay in the project, though of the delayed adoption of the e-LS and the certification scheme due to complexity. If Yes, reasons for delay & action plan to resolve: n/a If Yes, will delay have impact on project completion date (yes/no): n/a Any ongoing problems (yes/no): no If Yes, is any action required by ExCom: n/a |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor the adoption and enforcement of the e licensing system and certification scheme.
ONG | UNEP | Preparation of a HCFC phase-out management plan (stage II) | Multi-Year | ASP | OMA | PHA | 73 | PRP | 26 | A | I |  | 0 |  | 0 |  | 2014-11-01 | 2016-03-01 | 2015-11-01 | 2017-07-01 |  |  | 27000 | 0 | 27000 | 0 | 0% | 27000 | 19000 | 2700 | 3510 | 0 | 0 | 3510 | 2470 | Brief progress report (actual/planned: all planned activities have been completed and the project was submitted and approved by ExCom 75 in Nov. 2015. Legal arrangements (actual/planned): The agreement for the implementing the project was finalized and signed in June 2015. mission (actual/planned): two missions to the country took place during Feb and July 2015 to initiate the project and then finalize the project document- TOR completed (actual/planned): completed. First disbursement date (actual/planned): 1st disbursement done in March 2016. All funds disbursed (yes/no): No, second payment is pending due to late submission of financial progress report which is expected to be submitted in Mar. 2017. Any delay? (yes/no): No delay in the project,. If Yes, reasons for delay & action plan to resolve: n/a If Yes, will delay have impact on project completion date (yes/no): n/a Any ongoing problems (yes/no): no If Yes, is any action required by ExCom: n/a | Brief progress report (actual/planned: all planned activities have been implemented. Legal arrangements (actual/planned): The agreement with the NOU signed in June 2015. mission (actual/planned): two missions to the country took place during Feb and July 2015 to initiate the project and then finalize the project document- TOR completed (actual/planned): completed. First disbursement date (actual/planned): 1st disbursement done in March 2016. All funds disbursed (yes/no): No, second payment is pending due to late submission of financial progress report which is expected to be submitted in Mar. 2017 in order to close the project financially. Any delay? (yes/no): No delay in the project,. If Yes, reasons for delay & action plan to resolve: n/a If Yes, will delay have impact on project completion date (yes/no): n/a Any ongoing problems (yes/no): no If Yes, is any action required by ExCom: n/a
COM | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | Individual | ASP | OMA | PHA | 73 | PRP | 27 | A | I |  | 0 | 0 |  |  | 2014-11-01 | 2015-07-01 | 2016-06-30 |  | 2016-07-01 |  | 33000 | 0 | 33000 | 32778.61 | 99.33% | 221.39 | 0 | 1 | 2310 | 0 | 2295 | 15 | 0 | Project completed in Jul 2016. | Project completed. Financial closure is being processed. Remaining funds will be returned to the 79th ExCom. |  |  | NON-INV
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | ASP | OMA | PHA | 74 | INV | 28 | A | I |  | 0 | 0 |  |  | 2015-05-01 | 2015-08-01 | 2017-12-31 | 2017-12-01 |  |  | 35000 | 0 | 35000 | 20531.43 | 58.66% | 14468.57 | 658.19 | 10000 | 2625 | 0 | 0 | 2625 | 49.3642 | Brief report: Funds will be combined with Stage II funds to continue activities. Actions towards next goals: Recruitment of an international expert to implement the activities for the service sector. Combined with Stage II, first tranche. Was there any delay during the reporting year?: No | 'Brief report: Funds will be combined with Stage II funds to continue activities. Milestone 1: Outline of formal reclamation scheme completed Milestone 2: International expert recruited to implement the activities for the service sector. Combined with Stage II, first tranche. Was there any delay during the reporting year?: No |  |  | INV
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | ASP | OMA | PHA | 74 | TAS | 29 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-03-01 | 2016-05-01 | 2017-11-01 |  |  | 20000 | 0 | 20000 | 7452.71 | 37.26% | 12547.29 | 12547.29 | 1254.729 | 2600 | 0 | 968.8523 | 1631.1477 | 1631.1477 | Brief progress report (actual/planned): The tranche was approved to provide support for completing the activities initiated under the 1st tranche. Mainly with regards to adopting the RAC certification scheme and e-lisensing system. Full achievement of the planned objectives under stage I. Specifically, the country completed the remaining work for establishing a national e-licensing as well as the RAC certification scheme and will be fully operational in close cooperation with Customs Dept. during 2017. A training workshop for RAC technicians on good practices held in Muscat during 10-13 Oct. 2016 in partnership with OVSTC. Final steps are being taken to ensure full enforcement of the certification scheme in 2017. Legal arrangements (actual/planned): No SSFA agreement arranged for this tranche- direct implementation by CAP . mission (actual/planned): three missions to the country took place during 2016 with last in Oct. 2016 to follow up and expedite implementation of remained activities under the stage I tranches mainly the certification scheme and the e-licensing system - TOR completed (actual/planned): NA - CAP staff implementing directly with national concerned authorities First disbursement date (actual/planned): No. All funds disbursed (yes/no): No- funds will be disbursed in 2017. Any delay? (yes/no): No delay in the project, though of the delayed adoption of the e-LS and the certification scheme due to complexity. If Yes, reasons for delay & action plan to resolve: n/a If Yes, will delay have impact on project completion date (yes/no): n/a Any ongoing problems (yes/no): no If Yes, is any action required by ExCom: n/a | Brief progress report (actual/planned): The tranche was approved to provide support for completing the activities initiated under the 1st tranche. Mainly with regards to adopting the RAC certification scheme and e-lisensing system. Full achievement of the planned objectives under stage I. Specifically, the country completed the remaining work for establishing a national e-licensing as well as the RAC certification scheme and will be fully operational in close cooperation with Customs Dept. during 2017. A training workshop for RAC technicians on good practices held in Muscat during 10-13 Oct. 2016 in partnership with OVSTC and a training workshop is planned on Mar. 2017 as part of the efforts to promote the RAC certification scheme. Final steps are being taken to ensure full enforcement of the certification scheme in 2017. Legal arrangements (actual/planned): No SSFA agreement arranged for this tranche- direct implementation by CAP . mission (actual/planned): one mission in Mar. 2017 to follow up and expedite implementation of remained activities under the stage I tranches mainly the certification scheme and the e-licensing system - TOR completed (actual/planned): NA - CAP staff implementing directly with national concerned authorities First disbursement date (actual/planned): No. All funds disbursed (yes/no): No- funds will be disbursed in 2017. Any delay? (yes/no): No delay in the project, though of the delayed adoption of the e-LS and the certification scheme due to complexity. If Yes, reasons for delay & action plan to resolve: n/a If Yes, will delay have impact on project completion date (yes/no): n/a Any ongoing problems (yes/no): no If Yes, is any action required by ExCom: n/a
ONG | UNIDO | HCFC phase-out management plan (stage II, first tranche) | Multi-Year | ASP | OMA | PHA | 75 | INV | 32 | A | I |  | 0 | 0 |  |  | 2015-11-01 |  | 2018-12-01 | 2018-12-31 |  |  | 215000 | 0 | 215000 | 0 | 0% | 215000 | 149260 | 30000 | 15050 | 0 | 0 | 15050 | 10448.2 | Milestones achieved: Milestone 1: Yes, 1st mission, working arrangements agreed in July 2016. Milestone 2: - Bids prepared and requested Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | Milestones achieved: Milestone 1: Contracts awarded - Delivery of equipment expected in 3rd quarter of 2017 Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
ONG | UNEP | HCFC phase-out management plan (stage II, first tranche) | Multi-year | ASP | OMA | PHA | 75 | TAS | 33 | A | I |  | 0 |  | 0 |  | 2015-11-01 |  | 2016-12-01 | 2017-08-01 |  |  | 83500 | 0 | 83500 | 0 | 0% | 83500 | 27452.71 | 8350 | 10855 | 0 | 0 | 10855 | 3568.8523 | Brief progress report (actual/planned: Meeting with NOU and NOC organized in May 2016 to finalize and agree action plan for project implementation. required support provided to the NOU and related stakeholders to ensure timely delivery of planned activities including activities initiated under stage I. Legal arrangements (actual/planned): The agreement for the implementing the project has been arranged and signed in June 2016. Mission (actual/planned): two missions conducted. one in May 2016 to launch the project and agree action plan and one in Oct. 2016 to follow up implementation and organize RAC training- TOR completed (actual/planned): completed - CAP staff implementing directly. First disbursement date (actual/planned): 1st disbursement done. All funds disbursed (yes/no): No. Any delay? (yes/no): No delay in the project,. If Yes, reasons for delay & action plan to resolve: n/a If Yes, will delay have impact on project completion date (yes/no): n/a Any ongoing problems (yes/no): no. If Yes, is any action required by ExCom: n/a | Brief progress report (actual/planned: Meeting with NOU and NOC organized in Mar. 2017 to discuss required new policies including requirements for full enforcements of the e-licensing system and RAC certification scheme. required support provided to the NOU and related stakeholders to ensure timely delivery of planned activities including activities initiated under stage I. Legal arrangements (actual/planned): The agreement for the implementing the project has been arranged and signed in June 2016. Mission (actual/planned): 1 mission in Mar. 2017 to follow up implementation and organize RAC training- TOR completed (actual/planned): completed - CAP staff implementing directly. First disbursement date (actual/planned): 1st disbursement done. All funds disbursed (yes/no): No. Any delay? (yes/no): No delay in the project,. If Yes, reasons for delay & action plan to resolve: n/a If Yes, will delay have impact on project completion date (yes/no): n/a Any ongoing problems (yes/no): no. If Yes, is any action required by ExCom: n/a
FIN | UNIDO | Implementation of the RMP: Monitoring and evaluation of sub-projects in the RMP in particular the recovery and recycling | RMP Update | ASP | OMA | REF | 34 | TAS | 05 | A | I | CFC | 9 | 9 |  |  | 2001-07-01 | 2007-03-01 | 2004-08-01 |  | 2007-12-01 | 2008-09-01 | 20000 | -196 | 19804 | 19804 | 100% | 0 | 0 |  | 2600 | -25 | 2575 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Implementation of the RMP: Recovery and recycling project | RMP Update | ASP | OMA | REF | 34 | TAS | 06 | A | I | CFC | 103.3 | 103.3 |  |  | 2001-07-01 | 2002-03-01 | 2003-08-01 |  | 2005-12-01 | 2007-12-01 | 230000 | -502 | 229498 | 229498.29 | 100% | -0.29 | 0 |  | 29900 | -65 | 29835 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Implementation of the RMP: Training of trainers in good refrigerant management practices | RMP Update | ASP | OMA | REF | 34 | TRA | 02 | A | I | CFC | 80 | 80 |  |  | 2001-07-01 | 2002-06-01 | 2003-08-01 |  | 2004-12-01 | 2005-12-01 | 178000 | -1359 | 176641 | 176641.2 | 100% | -0.2 | 0 |  | 23140 | -213 | 22927 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Implementation of the RMP: Customs training programme | RMP Update | ASP | OMA | REF | 34 | TRA | 04 | A | I | CFC | 18.9 | 18.9 |  |  | 2001-07-01 | 2002-05-01 | 2003-08-01 |  | 2003-12-01 | 2004-09-01 | 42000 | -4469 | 37531 | 37530.63 | 100% | 0.37 | 0 |  | 5460 | -589 | 4871 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Country programme preparation | Individual | ASP | OMA | SEV | 29 | CPG | 01 | A | I |  | 0 | 0 |  |  | 1999-11-01 | 2000-04-01 | 2000-12-01 |  | 2000-12-01 | 2002-05-01 | 80000 | -1455 | 78545 | 78544.87 | 100% | 0.13 | 0 |  | 10400 | -205 | 10195 | 0 | 0 | FIN
FIN | UNIDO | Institutional Strengthening/Support to the National Ozone Unit in Oman | Individual | ASP | OMA | SEV | 32 | INS | 02 | N | I |  | 0 | 0 |  |  | 2000-12-01 | 2002-10-01 | 2004-01-01 |  | 2005-12-01 | 2006-02-01 | 79000 | 0 | 79000 | 78999.73 | 100% | 0.27 | 0 |  | 10270 | -1 | 10269 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNEP | Policy and technical assistance | Individual | ASP | OMA | SEV | 37 | TAS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-12-01 | 2003-08-01 |  | 2006-02-01 | 2008-12-01 | 10000 | -52 | 9948 | 9948 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNIDO | Renewal of institutional strengthening support (phase II) | Individual | ASP | OMA | SEV | 46 | INS | 14 | N | I |  | 0 | 0 |  |  | 2005-07-01 | 2007-03-01 | 2007-07-01 |  | 2007-12-01 | 2009-09-01 | 68467 | -73 | 68394 | 68394.4 | 100% | -0.4 | 0 |  | 5135 | -5 | 5130 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Renewal of institutional strengthening support (phase III) | Individual | ASP | OMA | SEV | 56 | INS | 18 | N | I |  | 0 | 0 |  |  | 2008-11-01 | 2011-02-01 | 2010-11-30 |  | 2011-11-01 | 2012-11-01 | 68467 | 0 | 68467 | 68467 | 100% | 0 | 0 |  | 5135 | 0 | 5135 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Renewal of institutional strengthening support (phase IV: 12/2011-11/2013) | Individual | ASP | OMA | SEV | 65 | INS | 21 | N | I |  | 0 | 0 |  |  | 2011-11-01 | 2012-02-01 | 2013-11-30 |  | 2013-12-01 | 2015-03-01 | 68467 | -192 | 68275 | 68274.86 | 100% | 0.14 | 0 |  | 5135 | -14 | 5121 | 0 | 0 | FIN |  |  |  | NON-INV
COM | UNIDO | Renewal of institutional strengthening support (phase V: 12/2013-11/2015) | Individual | ASP | OMA | SEV | 71 | INS | 25 | N | I |  | 0 | 0 |  |  | 2013-12-01 | 2014-06-01 | 2015-11-30 |  | 2015-11-01 | 2016-04-01 | 68467 | 0 | 68467 | 67511.39 | 98.6% | 955.61 | 0 | 1 | 4793 | 0 | 4726 | 67 | 0 | The project was operationally completed. |  |  |  | NON-INV
ONG | UNIDO | Renewal of institutional strengthening support (phase VI: 12/2015-11/2017) | Individual | ASP | OMA | SEV | 74 | INS | 30 | N | I |  | 0 | 0 |  |  | 2015-05-01 | 2015-12-01 | 2017-11-30 | 2017-11-01 |  |  | 68467 | 0 | 68467 | 809.91 | 1.183% | 67657.09 | 40000 | 40000 | 4793 | 0 | 0 | 4793 | 2800 | ToR for release of new contract was developed and agreed with counterpart. Contract for project execution at national level has been issued and signed. Implementation is progressing in line with the project document. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | NOU work plan for the year 2017 has been agreed. NOU is fully staffed and activities are progressing in line with the contract. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | NON-INV
ONG | UNIDO | Survey of ODS alternatives at the national level | Individual | ASP | OMA | SEV | 74 | TAS | 31 | A | I |  | 0 | 0 |  |  | 2015-05-01 | 2016-04-01 | 2016-05-31 | 2017-12-31 |  |  | 110000 | 0 | 110000 | 44086.67 | 40.08% | 65913.33 | 29064.66 | 60000 | 9900 | 0 | 0 | 9900 | 2615.8194 | Brief report: Desktop studies have been carried out. Survey is now ongoing. Milestones achieved Milestone 1: Survey contract awarded Milestone 2: Stakeholder workshop held in July 2016 Milestone 3: Survey completed Actions towards next goals: Review and report on survey's results. Was there any delay during the reporting year? No Any recurring problem? No | Brief report: Desktop studies have been carried out. Survey is now completed Milestones achieved Milestone 1: Survey contract awarded Milestone 2: Stakeholder workshop held in July 2016 Milestone 3: Survey completed Milestone 4: Draft report prepared, review ongoing Actions towards next goals: Submission expected to 79th ExCom Was there any delay during the reporting year? Yes. Review of report took longer than expected. Any recurring problem? No |  |  | NON-INV
FIN | UNIDO | Training and awareness workshop in the solvent sector (CTC) | Individual | ASP | OMA | SOL | 45 | TAS | 11 | A | I | CTC | 0.1 | 0.1 |  |  | 2005-04-01 | 2005-11-01 | 2006-04-01 |  | 2006-12-01 | 2008-05-01 | 35000 | 0 | 35000 | 34999.74 | 100% | 0.26 | 0 |  | 3150 | 0 | 3150 | 0 | 0 | FIN |  |  |  | INV
FIN | UNDP | Project preparation for a MDI investment project | Individual | ASP | PAK | ARS | 54 | PRP | 68 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-05-01 | 2009-03-01 |  | 2008-11-01 | 2011-11-01 | 60000 | -9095.82 | 50904.18 | 50904 | 100% | 0.18 | 0 | 0 | 4500 | -682.19 | 3817.8 | 0.01 | 0 | Completed in 2008. |  | 2008 |  | Investment
ONG | UNDP | Plan for phase-out of CFCs in the manufacture of pharmaceutical MDIs | Individual | ASP | PAK | ARS | 56 | INV | 71 | N | I | CFC | 83.8 | 83.8 | 0 | 0 | 2008-11-01 | 2011-03-01 | 2011-11-01 | 2017-06-01 |  |  | 449996 | 0 | 449996 | 128440 | 28.54% | 321556 | 0 | 128622.4 | 33750 | 0 | 9633.0856 | 24116.9144 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): The CFC free MDIs production yet to start in GSK as they have to get NOC from Ministry of National Health Services Regulation & Coordination, Islamabad. In 2016, the National Ozone Unit, MOCC visited GSK plant site along with the officials of Ministry of National Health Services Regulation & Coordination, Islamabad for inspection of plant installed. After the visit, the MOCC is in follow up with the Mo Health to approve the verification process in writing. Once it is done, the international consultant will visit the site and verify the facility. Lastly, the last instalment is released to GSK and the project will be closed.The main reason of delay is that many cases are piled up at the Ministry of Health for the verification and approvals and currently the cases being pursued at the Ministry are that of 2012-13. Prodoc signed (actual/planned, yes/no and date):40210 Missions undertaken (actual/planned):- TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: Contract signed First disbursement date (actual/planned): 40603Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:Delay in issuance of approval from Ministry of Health | Once the approval is obtain from Ministry of Health, The services of international technical Consultant for verification purpose will be taken. | 2008 |  | Investment |  | 1) 12 months delays. 2) To request the submission of additional status report to the 79th meeting to monitor project completion.
FIN | UNEP | National strategy for transition to non-CFC MDIs | Individual | ASP | PAK | ARS | 56 | TAS | 72 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-03-01 | 2011-11-01 |  | 2011-11-01 | 2012-11-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0
FIN | IBRD | Phaseout of CFC-11 in the manufacture of flexible PUF molded and integral skin at Master Group: (Master Enterprises Ltd., Durafoam Ltd., Khyber Plastic and Polymer Industries Ltd., Procon En) | Individual | ASP | PAK | FOA | 17 | INV | 06 | N | I | CFC | 205 | 205 | 0 | 0 | 1995-07-01 | 1999-08-01 | 1997-01-01 |  | 2005-02-01 | 2006-07-01 | 1247330 | -1030 | 1246300 | 1246300 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1999-09-01 | INV | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of molded and rigid PUF at Razi Sons | Individual | ASP | PAK | FOA | 18 | INV | 07 | N | I | CFC | 60 | 60 | 0 | 0 | 1995-11-01 | 1999-04-01 | 1997-05-01 |  | 2002-11-01 | 2003-08-01 | 493262 | 0 | 493262 | 493262 | 100% | 0 | 0 |  | 64124.06 | 0 | 64124.06 | 0 | 0 | Project and draft PCR completed. |  |  | 1999-09-01 | INV | 0
FIN | IBRD | Project preparation to phase out CFC consumption that is not accounted for in the country programme |  | ASP | PAK | FOA | 22 | PRP | 15 | A | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-06-30 | 1998-05-01 |  | 1997-12-01 | 1997-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of integral skin polyurethane foam at Synthetic Products Enterprises (Pvt) Ltd. (SPEL) | Individual | ASP | PAK | FOA | 23 | INV | 16 | N | I | CFC | 13.6 | 13.6 | 0 | 0 | 1997-11-01 | 2000-10-01 | 2000-03-01 |  | 2002-01-01 | 2003-10-01 | 160625 | -23796.5 | 136828.5 | 136828.5 | 100% | 0 | 0 |  | 20881 | -3093.5 | 17787.5 | 0 | 0 | Project completed and PCR submitted. |  |  |  | INV | 0
FIN | IBRD | Umbrella project: Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (thermoware) | Individual | ASP | PAK | FOA | 23 | INV | 20 | N | I | CFC | 239.6 | 239.6 | 0 | 0 | 1997-11-01 | 2002-12-01 | 2000-03-01 |  | 2006-10-01 | 2006-10-01 | 1600000 | -209475 | 1390525 | 1390525 | 100% | 0 | 0 |  | 208000 | -27231.75 | 180768.25 | 0 | 0 | Project completed. |  |  | 2001-12-01 | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of polyurethane foam (flexible slabstock, flexible moulded, rigid foam) at Diamond Group of Industries | Individual | ASP | PAK | FOA | 23 | INV | 22 | N | I | CFC | 64.1 | 64.1 | 0 | 0 | 1997-11-01 | 2001-09-01 | 2000-03-01 |  | 2005-02-01 | 2007-06-01 | 563339 | 0 | 563339 | 563339 | 100% | 0 | 0 |  | 73234 | 0 | 73234 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Terminal umbrella: Conversion to HCFC-141b and water blown technology in the manufacture of rigid polyurethane foam (thermoware) | Individual | ASP | PAK | FOA | 25 | INV | 25 | N | I | CFC | 105.65 | 105.65 | 0 | 0 | 1998-07-01 | 2002-12-01 | 2000-08-01 |  | 2006-10-01 | 2006-10-01 | 718900 | -161848 | 557052 | 557052 | 100% | 0 | 0 |  | 93457 | -21040.24 | 72416.76 | 0 | 0 | Project completed. |  |  | 2001-12-01 | INV | 0
FIN | IBRD | Elimination of CFC-11 through conversion to methylene chloride/LIA technology in the manufacture of flexible polyurethane slabstock foam at United Foam Industries | Individual | ASP | PAK | FOA | 26 | INV | 29 | N | I | CFC | 28.6 | 28.6 | 0 | 0 | 1998-11-01 | 2000-12-01 | 2000-12-01 |  | 2001-12-01 | 2002-01-01 | 178200 | 0 | 178200 | 178200 | 100% | 0 | 0 |  | 23166 | 0 | 23166 | 0 | 0 | Project completed and PCR submitted. |  |  |  | INV | 0
FIN | IBRD | Elimination of CFC-11 through conversion to water based technology in the manufacture of flexible molded polyurethane foam at Saleem Automotive Industries Ltd. | Individual | ASP | PAK | FOA | 26 | INV | 30 | N | I | CFC | 2.5 | 2.5 | 0 | 0 | 1998-11-01 | 2000-03-01 | 2000-06-01 |  | 1999-03-01 | 2000-12-01 | 33875 | -2272 | 31603 | 31603 | 100% | 0 | 0 |  | 4403.75 | -295.35 | 4108.4 | 0 | 0 | Project completed, PCR submitted June 2000. |  |  |  | INV | 0
FIN | IBRD | Conversion from CFC-11 to water-based technology in the manufacture of rigid polyurethane shoe soles at Jaguar Industries | Individual | ASP | PAK | FOA | 29 | INV | 34 | N | I | CFC | 40 | 40 | 0 | 0 | 1999-11-01 | 2004-09-01 | 2001-12-01 |  | 2005-06-01 | 2005-09-01 | 279280 | -5612.86 | 273667.14 | 273667.14 | 100% | 0 | 0 |  | 36306.4 | -729.68 | 35576.72 | 0 | 0 | Project completed. |  |  | 2003-12-01 | INV | 0
FIN | IBRD | Project preparation in the rigid polyurethane foam |  | ASP | PAK | FOA | 30 | PRP | 37 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 12000 | 0 | 12000 | 12000 | 100% | 0 | 0 |  | 1560 | 0 | 1560 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Phase-out of the use of CFCs in remaining foam enterprises: Pakistan Insulation, Simpson Wire, HEPCO, Indus Plastic, Workman and Thermocraft Engineering | Individual | ASP | PAK | FOA | 41 | INV | 58 | N | I | CFC | 106.9 | 106.9 | 0 | 0 | 2003-12-01 | 2005-11-01 | 2006-01-01 |  | 2006-12-01 | 2007-06-01 | 658973 | -12331 | 646642 | 646642 | 100% | 0 | 0 |  | 49423 | -801 | 48622 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | UNIDO | Preparation for HCFC phase-out investment activities (polyurethane foam sector) | Individual | ASP | PAK | FOA | 59 | PRP | 75 | A | I |  | 0 | 0 |  |  | 2009-11-01 | 2010-09-01 | 2010-11-30 |  | 2010-12-01 | 2012-12-01 | 80000 | -106 | 79894 | 79894.17 | 100% | -0.17 | 0 |  | 6000 | -8 | 5992 | 0 | 0 | FIN |  |  |  | NON-INV
COM | UNIDO | Phase-out of HCFC-141b from the manufacturing of insulation PU rigid foam at United Refrigeration, HNR (Haier), Varioline Intercool and Shadman Electronics companies | Multi-Year | ASP | PAK | FOA | 60 | INV | 77 | A | I | HCFC | 49.2 | 49.2 |  |  | 2010-04-01 | 2010-12-01 | 2012-04-30 |  | 2016-12-01 |  | 3559359 | 0 | 3559359 | 3555926.87 | 99.9% | 3432.13 | 2405.13 | 2000 | 266952 | 0 | 266695 | 257 | 180 | Project completed, unliquidated obligations are to be disbursed.
COM | UNIDO | Phase-out of HCFC-141b from the manufacturing of insulation PU rigid foam at Dawlance | Multi-Year | ASP | PAK | FOA | 60 | INV | 78 | A | I | HCFC | 22.4 | 22.4 |  |  | 2010-04-01 | 2010-12-01 | 2012-04-30 |  | 2015-12-01 |  | 1281490 | 0 | 1281490 | 1281245.38 | 99.98% | 244.62 | 0 | 1 | 96112 | 0 | 96093 | 19 | 0 | The project was operationally completed.
COM | UNIDO | Preparation for HCFC phase-out investment activities (stage II) (foam sector) | Individual | ASP | PAK | FOA | 72 | PRP | 87 | A | I |  | 0 | 0 |  |  | 2014-05-01 | 2015-09-01 | 2015-05-31 |  | 2016-12-01 |  | 50000 | 0 | 50000 | 46565.63 | 93.13% | 3434.37 | 2574 | 2000 | 3500 | 0 | 3260 | 240 | 180 | - Survey in the foam sector accomplished users of HCFC -141b and potential project beneficiaries of conversion investment projects identified. - Drafting of the investment component, HPMP Stage II for the foam sector in progress. Three investment components prepared for submission after pondering different Country phase-out scenario. - Study tour to China was successfully materialized. Participants from industries had unique opportunity to see new (hydrocarbon) technologies in full operation. - Project completed, HPMP Stage II first tranche in the foam sector was approved. Milestones achieved: Milestone 1: First mission/Working arrangements agreed - Yes Milestone 2: ToR for HCFC survey completed - Yes Milestone 3: Local institutions identified - Yes Milestone 4: Experts recruited - Yes Milestone 5: HCFC survey completed - Yes Milestone 6: All technical input completed - Yes Milestone 7: Draft document completed - Yes Actions towards next goals: Necessary accompanying documents for project document submission, Commitment letters from eligible counterparts and Government Letter of transmittal are being obtained. Project document was submitted and approved. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | Project completed. |  |  | NON-INV
FIN | UNIDO | Preparation of demonstration project (tobacco, tomatoes, strawberries) | Individual | ASP | PAK | FUM | 24 | PRP | 24 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-12-01 | 1999-04-01 |  | 2000-01-01 | 2000-07-01 | 30000 | -21118 | 8882 | 8882 | 100% | 0 | 0 |  | 3900 | -2747 | 1153 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a phase-out plan in the fumigants sector | Individual | ASP | PAK | FUM | 39 | PRP | 49 | A | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-07-01 | 2004-04-01 |  | 2004-04-01 | 2004-06-01 | 30000 | -9323 | 20677 | 20676.75 | 100% | 0.25 | 0 |  | 2250 | -702 | 1548 | 0 | 0 | FIN
FIN | UNIDO | Training and awareness workshop in the fumigants sector (methyl bromide) | Individual | ASP | PAK | FUM | 45 | TAS | 63 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2006-09-01 | 2006-04-01 |  | 2006-12-01 | 2008-05-01 | 30000 | -7149 | 22851 | 22850.78 | 100% | 0.22 | 0 |  | 2700 | -643 | 2057 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Project preparation for a halon sector phase-out plan | Individual | ASP | PAK | HAL | 40 | PRP | 53 | A | I |  | 0 | 0 |  |  | 2003-07-01 | 2003-08-01 | 2004-07-01 |  | 2003-12-01 | 2004-12-01 | 22000 | -780 | 21220 | 21219.63 | 100% | 0.37 | 0 |  | 1650 | -61 | 1589 | 0 | 0 | FIN
FIN | UNIDO | Plan for the phase-out of import and net consumption of halons in the fire fighting sector | Individual | ASP | PAK | HAL | 41 | TAS | 55 | A | I | HAL | 24.2 | 24.2 |  |  | 2003-12-01 | 2004-02-01 | 2006-12-01 |  | 2006-12-01 | 2007-12-01 | 209400 | -786 | 208614 | 208614.4 | 100% | -0.4 | 0 |  | 18846 | -71 | 18775 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of carbon tetrachloride as process solvent to 1,2-dichloroethane at Himont Chemicals Ltd. | Individual | ASP | PAK | PAG | 35 | INV | 42 | A | I | CTC | 80 | 80 |  |  | 2001-12-01 | 2002-04-01 | 2004-01-01 |  | 2008-10-01 | 2011-03-01 | 485701 | -3651 | 482050 | 482050.16 | 100% | -0.16 | 0 |  | 63141 | -474 | 62667 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Sector phase-out plan of CTC | Multi-Year | ASP | PAK | PHA | 41 | INV | 57 | A | I | CTC | 100 | 109.7 |  |  | 2003-12-01 | 2004-03-01 | 2004-12-01 |  | 2007-07-01 | 2010-12-01 | 1200000 | -542 | 1199458 | 1199458.28 | 100% | -0.28 | 0 |  | 90000 | -41 | 89959 | 0 | 0 | FIN |  |  | 2006-07-01 | INV
FIN | UNIDO | Sector phase-out plan of CTC (second tranche) | Multi-Year | ASP | PAK | PHA | 44 | INV | 62 | A | I | CTC | 326.5 | 326.5 |  |  | 2004-12-01 | 2005-08-01 | 2005-12-01 |  | 2007-07-01 | 2012-05-01 | 1300000 | -2137 | 1297863 | 1297862.63 | 100% | 0.37 | 0 |  | 97500 | -160 | 97340 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Sector phase-out plan of CTC (third tranche) | Multi-Year | ASP | PAK | PHA | 54 | INV | 67 | A | I | CTC | 62.5 | 62.5 |  |  | 2008-04-01 | 2008-10-01 | 2009-03-31 |  | 2009-12-01 | 2012-05-01 | 245665 | -912 | 244753 | 244752.62 | 100% | 0.38 | 0 |  | 25924 | -96 | 25828 | 0 | 0 | FIN |  |  |  | INV
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | PAK | PHA | 55 | PRP | 69 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-11-01 | 2009-07-01 |  | 2010-12-01 | 2011-12-01 | 60000 | -2945 | 57055 | 57055 | 100% | 0 | 0 |  | 7800 | -382.47 | 7417.53 | 0 | 0
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | ASP | PAK | PHA | 55 | PRP | 70 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 |  | 2010-12-01 | 2012-05-01 | 90000 | -5024 | 84976 | 84976.18 | 100% | -0.18 | 0 |  | 6750 | -377 | 6373 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan (additional funding) | Individual | ASP | PAK | PHA | 59 | PRP | 76 | A | I |  | 0 | 0 |  |  | 2009-11-01 | 2010-02-01 | 2010-11-30 |  | 2010-12-01 | 2012-06-01 | 45000 | -831 | 44169 | 44169.11 | 100% | -0.11 | 0 |  | 3375 | -62 | 3313 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | PAK | PHA | 62 | INV | 79 | A | I |  | 0 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2013-12-31 |  | 2013-03-01 | 2015-03-01 | 68000 | -1930 | 66070 | 66070.4 | 100% | -0.4 | 0 |  | 5100 | -145 | 4955 | 0 | 0 | FIN |  |  |  | INV
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | PAK | PHA | 62 | TAS | 80 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-06-01 | 2013-12-01 |  | 2013-12-01 | 2014-12-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 22235 | 26000 | 0 | 26000 | 0 | 0
COM | UNIDO | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | ASP | PAK | PHA | 70 | INV | 83 | A | I |  | 0 | 0 |  |  | 2013-07-01 | 2013-09-01 | 2014-07-31 |  | 2015-12-01 |  | 80000 | 0 | 80000 | 77537.29 | 96.92% | 2462.71 | 2058.73 | 1 | 6000 | 0 | 5815 | 185 | 154.4048 | The project was operationally completed. |  |  |  | INV
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | ASP | PAK | PHA | 70 | TAS | 84 | A | I |  | 0 |  | 0 |  | 2013-07-01 | 2014-03-01 | 2014-07-01 | 2017-12-01 |  |  | 200000 | 0 | 200000 | 177765.19 | 88.88% | 22234.81 | 0 |  | 26000 | 0 | 23109.4747 | 2890.5253 | 0 | Brief progress report (actual/planned): MOU with NAVTCC for technician training signed, Development of a national Customs Training Curriculum Legal arrangements(actual/planned): SSFA amended to extend to Dec 2017 First mission (actual/planned): July 2016 and Mar 2017 TOR completed (actual/planned): yes. First disbursement date (actual/planned): Yes actual Mar 2014 funds disbursed (yes/no): No Any delay? (yes/no):Yes If Yes, reasons for delay & action plan to resolve: Absence of Ozone Officer during most of 2015 delayed the implementation, Changes in Secretary and Minister level did not bring high level attention to the programme, Security situation contributes to further challenges If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): conduct of 3 trainings in Karachi, lahore and Islamabad on 25-29 April 2017. The MOU for technician training signed and planning the first TTT in February 2017 Legal arrangements(actual/planned): SSFA amended to extend to Dec 2017 First mission (actual/planned): ___ TOR completed (actual/planned): ______ First disbursement date (actual/planned): Yes actual Mar 2014 funds disbursed (yes/no): No Any delay? (yes/no):Yes If Yes, reasons for delay & action plan to resolve: Absence of Ozone Officer during most of 2015 delayed the implementation, Changes in Secretary and Minister level did not bring high level attention to the programme, Security situation contributes to further challenges If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___ |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor the signing of the memorandum of understanding for technician training.
COM | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | Individual | ASP | PAK | PHA | 72 | PRP | 85 | A | I |  | 0 | 0 |  |  | 2014-05-01 | 2015-05-01 | 2015-05-31 |  | 2016-12-01 |  | 42000 | 0 | 42000 | 6859.84 | 16.33% | 35140.16 | 34708 | 30000 | 2940 | 0 | 480 | 2460 | 2430 | - Survey in respective HCFC consuming sectors accomplished. - Users of HCFCs and potential project beneficiaries including government, non-governmental organizations, RAC associations and other stakeholders identified. - Consultative workshop with industries concerned and NOU organized prior to reaching agreement on final version of the project document. - Study tour to China was successfully materialized. Participants from industries had unique opportunity to see new (hydrocarbon) technologies in full operation. - Coordination meeting with UNEP (co-implementing agency) and NOU organized prior to submission of the project document. - HCFC consumption verification audit organized. - Project completed, HPMP Stage II first tranche in the refrigeration and air conditioning sector was approved. Milestones achieved: Milestone 1: First mission/Working arrangements agreed - Yes Milestone 2: ToR for HCFC survey completed - Yes Milestone 3: Local institutions identified - Yes Milestone 4: Experts recruited - Yes Milestone 5: HCFC survey completed - Yes Milestone 6: All technical input completed - Yes Milestone 7: Draft document completed - Yes Actions towards next goals: Necessary accompanying documents for project document submission are being obtained. Project document was submitted and approved. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Project completed - Open obligations will be paid |  |  | NON-INV
COM | UNEP | Preparation of a HCFC phase-out management plan (stage II) | Multi-Year | ASP | PAK | PHA | 72 | PRP | 88 | A | I |  | 0 |  | 0 |  | 2014-05-01 | 2014-10-01 | 2015-05-01 |  | 2016-12-01 |  | 48000 | 0 | 48000 | 37563.31 | 78.26% | 10436.69 | 0 | 10436.69 | 6240 | 0 | 4883.2303 | 1356.7697 | 0 | Project completed | Project completed
COM | UNIDO | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | ASP | PAK | PHA | 73 | INV | 89 | A | I | HCFC | 2 | 2 |  |  | 2014-11-01 | 2015-12-01 | 2015-11-30 |  | 2016-12-01 |  | 20000 | 0 | 20000 | 18672.36 | 93.36% | 1327.64 | 858 | 858 | 1500 | 0 | 1400 | 100 | 64 | - UNEP tranches not yet accomplished. - Pakistan however successfully controlled import of ODS through strong monitoring system. HCFC consumption verification audit organized prior to submission of HPMP Stage II. - Project completed by December 2016. Milestones achieved: Milestone 1: - Legal arrangements - Yes Milestone 2: - Initial stages of project implementation began - Yes Milestone 3: - Intermediate goals achieved - Yes Milestone 4:- Project completion and follow-up - Yes Actions towards next goals: NOU - UNEP SSAs to be accomplished. Was there any delay during the reporting year? UNEP delays Any recurring problem? No Any action required by Executive Committee? No | - UNIDO activities completed. |  |  | INV
ONG | UNEP | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | ASP | PAK | PHA | 73 | TAS | 90 | A | I | HCFC-22 | 5.4 |  | 0 |  | 2014-11-01 | 2016-05-01 | 2015-11-01 | 2017-03-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 0 | 4000 | 5200 | 0 | 0 | 5200 | 0 | Brief progress report (actual and planned): awareness workshops for industry and national stakeholders. Workshop with PSQCA to adopt ISO standards Discussions with PSQCA on standards. Awareness workshops with customs on illegal trade and Afghanistan Transit Trade. High level discussions with Federal Board of Revenue on including curriculum in mational training, on illegal trade issues and capapcity building. Discussions wiyh NAVTTC to desogn national technician training. Missions undertaken: July 2016 First mission (actual/planned): no TOR completed (actual/planned): yes. First disbursement date (actual/planned): Yes actual May 2016 funds disbursed (yes/no): No Any delay? (yes/no):Yes If Yes, reasons for delay & action plan to resolve: Absence of Ozone Officer during most of 2015 delayed the implementation, Changes in Secretary and Minister level did not bring high level attention to the programme, Security situation contributes to further challenges If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual and planned): ToT conducted in Jan 2017, 2 customs training Ozone2Climate Technology Roadshow and Industry Dialogue in Mar 2017
ONG | UNIDO | HCFC phase-out management plan (stage II, first tranche) (polyurethane foam sector) | Multi-Year | ASP | PAK | PHA | 76 | INV | 94 | A | I | HCFC | 57.3 | 0 |  |  | 2016-05-01 | 2016-08-01 | 2019-12-31 | 2019-12-31 |  |  | 2160200 | 0 | 2160200 | 6968.17 | 0.3226% | 2153231.83 | 30865.24 | 50000 | 151214 | 0 | 488 | 150726 | 2161 | - HPMP Stage II tranche approved in 2016 by the 76th Meeting of the ExCom; - PAD of the project established. - Agreements on implementation procedures, including Commitment Letters for each individual company in the sector of Thermoware (7 counterparts) and in the sector of sandwich panels (4 counterparts) have been prepared and countersigned by beneficiaries, NOU and UNIDO. - TORs for both groups/umbrellas were also prepared in close collaboration with beneficiaries and NOU. Milestones achieved: Milestone 1: First mission/Working arrangements (agreement/document signatures/PDA) agreed - Yes Milestone 2:Terms of reference (for equipment and/or services) completed - Yes Milestone 3:First disbursement made - Yes Milestone 4: Bidding completed, supplier selected - No Milestone 5: Equipment shipped/delivered/installed at site - No Milestone 6: Commissioning and trial runs completed - No Actions towards next goals: International bidding Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - After careful discussions with beneficiaries, and including NOU, the international bidding was initiated in February 2017. Actions towards next goals: Obtain offers, evaluate bids, select suppliers. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
ONG | UNEP | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | Multi-Year | ASP | PAK | PHA | 76 | TAS | 93 | A | I |  | 0 |  | 0 |  | 2016-05-01 |  | 2018-12-01 | 2018-12-01 |  |  | 200000 | 0 | 200000 | 3164.15 | 1.582% | 196835.85 | 126916.7 | 19683.585 | 25976 | 0 | 410.9598 | 25565.0402 | 16483.941 | Newly approved project | Brief progress report (actual/planned): No progress on this as waiting to finalize activities of Stage 1. Detailed workplan for SSFA discussed and agreed with Senior Management of Min. of Climate Change during the mission Mar 2017 Legal arrangements(actual/planned): ___ First mission (actual/planned): Mar 2017 TOR completed(actual/planned): ___ First disbursement date (actual/planned): ___ All funds disbursed (yes/no): ___ Any delay? (yes/no): ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___
ONG | UNIDO | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | Multi-Year | ASP | PAK | PHA | 76 | TAS | 95 | A | I |  | 0 | 0 |  |  | 2016-05-01 | 2016-12-01 | 2019-05-31 | 2019-05-31 |  |  | 190000 | 0 | 190000 | 4341.13 | 2.285% | 185658.87 | 1817.39 | 3000 | 13300 | 0 | 304 | 12996 | 127 | - Funds approved in 2016 at the 76th Meeting of the ExCom for UNIDO to support UNEP's activities with necessary equipment. - UNEP is responsible for non-investment activities. UNEP however has not yet accomplished even HPMP Stage I programmes, therefore this implementation may be delayed. Milestones achieved: Milestone 1: - Legal arrangements - Yes Milestone 2: - Initial stages of project implementation began - not yet Milestone 3: - Intermediate goals achieved - No Milestone 4:- Project completion and follow-up - No Actions towards next goals: Scope of equipment to be specified in coordination with UNEP. Was there any delay during the reporting year? Delay in UNEP's implementation of HPMP Stage I. Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | Planning and coordination meeting with UNEP and NOU took place in March 2017. It was agreed that UNEP's activities of HPMP Stage I should be accomplished first (to prepare PCR for Stage I); subsequently, UNEP will specify the scope of equipment for training according to UNEP's programme. Was there any delay during the reporting year? Delay in UNEP's implementation of HPMP Stage I. Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Strategy for ODS phase out in refrigeration industry | Individual | ASP | PAK | REF | 12 | TAS | 03 | A | I |  | 0 | 0 |  |  | 1994-03-01 | 1995-08-01 | 1994-06-01 |  | 1998-03-01 | 2000-07-01 | 50000 | -232 | 49768 | 49768 | 100% | 0 | 0 |  | 6500 | -40 | 6460 | 0 | 0 | FIN |  |  | 1999-02-01 | NON-INV
FIN | UNIDO | Phasing out ODS at the Chest Freezer Factory of Riaz Electric Co. Ltd. | Individual | ASP | PAK | REF | 19 | INV | 09 | A | I | CFC | 48.2 | 48.2 |  |  | 1996-05-01 | 1997-03-01 | 1997-11-01 |  | 2003-12-01 | 2005-12-01 | 822987 | -4083 | 818904 | 818903.75 | 100% | 0.25 | 0 |  | 106988 | -699 | 106289 | 0 | 0 | FIN |  |  | 1999-12-01
FIN | UNIDO | Phasing out ODS at the refrigerator and chest freezer plants of Pak Elektron Ltd. (PEL) | Individual | ASP | PAK | REF | 19 | INV | 10 | A | I | CFC | 68 | 68 |  |  | 1996-05-01 | 1997-03-01 | 1997-11-01 |  | 2003-10-01 | 2006-05-01 | 1210295 | -67215 | 1143080 | 1143080.24 | 100% | -0.24 | 0 |  | 157338 | -8973 | 148365 | 0 | 0 | FIN |  |  | 1999-12-01
CLO | IBRD | Conversion of refrigerator manufacture from CFC-11 to cyclopentane foam blowing agenct and CFC-12 to R-134a refrigerant at Domestic Appliances Ltd. (DAL) | Individual | ASP | PAK | REF | 19 | INV | 11 | N | I |  | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1997-11-01 |  |  | 1999-11-01 | 257650 | -257650 | 0 | 0 | #DIV/0! | 0 | 0 |  | 33494.5 | -33494.5 | 0 | 0 | 0 | Subproject cancelled. |  |  | 1998-12-01 | INV | 0
FIN | UNIDO | Phasing out ODS at the freezer factory of Hirra Farooq's (Pvt) Ltd. | Individual | ASP | PAK | REF | 23 | INV | 17 | A | I | CFC | 31.2 | 31.2 |  |  | 1997-11-01 | 1998-10-01 | 1999-06-01 |  | 2003-08-01 | 2003-12-01 | 521580 | -3110 | 518470 | 518469.84 | 100% | 0.16 | 0 |  | 67805 | -511 | 67294 | 0 | 0 | FIN
FIN | IBRD | Conversion to CFC-free technology in the manufacture of polyurethane foam at Kold Kraft Ltd. | Individual | ASP | PAK | REF | 23 | INV | 18 | N | I | CFC | 11.5 | 11.5 | 0 | 0 | 1997-11-01 | 2000-10-01 | 2000-03-01 |  | 2002-12-01 | 2003-02-01 | 175000 | 0 | 175000 | 175000 | 100% | 0 | 0 |  | 22750 | 0 | 22750 | 0 | 0 | Project completed and PCR submitted. |  |  |  | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of polyurethane foam (domestic refrigeration) at Cool Industries Ltd. (Waves) | Individual | ASP | PAK | REF | 23 | INV | 19 | N | I | CFC | 117.6 | 117.6 | 0 | 0 | 1997-11-01 | 2004-07-01 | 2000-03-01 |  | 2006-12-01 | 2006-12-01 | 841750 | 0 | 841750 | 841750 | 100% | 0 | 0 |  | 109428 | 0 | 109428 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of polyurethane foam at Singer Pakistan Ltd. | Individual | ASP | PAK | REF | 23 | INV | 21 | N | I | CFC | 17.8 | 17.8 | 0 | 0 | 1997-11-01 | 2002-12-01 | 2000-03-01 |  | 2004-07-01 | 2005-02-01 | 205893 | 0 | 205893 | 205893 | 100% | 0 | 0 |  | 26766 | 0 | 26766 | 0 | 0 | Project completed. |  |  |  | INV | 0
CLO | IBRD | Elimination of CFC-11 and CFC-12 by converting to HCFC-141b and HFC-134a in the manufacture of commercial refrigeration equipment at Dawlance P. Ltd. | Individual | ASP | PAK | REF | 25 | INV | 26 | N | I |  | 0 | 0 | 0 | 0 | 1998-07-01 |  | 2000-08-01 |  |  | 2001-03-01 | 477894 | -477894 | 0 | 0 | #DIV/0! | 0 | 0 |  | 62126.22 | -62126.33 | 0 | -0.11 | -0.11 | Project cancelled at the 33rd ExCom Meeting. |  |  |  | INV | 0
CLO | IBRD | Elimination of CFC-11 and CFC-12 converting to HCFC-141b and HFC-134a in the manufacture of refrigeration equipment at United Refrigeration Industries Ltd. | Individual | ASP | PAK | REF | 25 | INV | 27 | N | I |  | 0 | 0 | 0 | 0 | 1998-07-01 |  | 2000-08-01 |  |  | 2001-03-01 | 457815 | -457815 | 0 | 0 | #DIV/0! | 0 | 0 |  | 59515.95 | -59515.95 | 0 | 0 | 0 | Project cancelled at the 33rd ExCom Meeting. |  |  |  | INV | 0
FIN | IBRD | Elimination of CFC-11 and CFC-12 by converting to HCFC-141b and HFC134a in the manufacture of commercial refrigeration equipment at Shadman Electronic Industries P. Ltd. | Individual | ASP | PAK | REF | 25 | INV | 28 | N | I | CFC | 15.53 | 15.53 | 0 | 0 | 1998-07-01 | 2000-10-01 | 2000-08-01 |  | 2002-11-01 | 2003-02-01 | 236936 | 0 | 236936 | 236936 | 100% | 0 | 0 |  | 30801.68 | 0 | 30801.68 | 0 | 0 | Project completed and PCR submitted. |  |  |  | INV | 0
CLO | IBRD | Phaseout of CFC-11 and CFC-12 by conversion to HCFC-141b and HFC-134a in the manufacture of domestic refrigeration equipment at Refrigerators Manufacturing Company Pakistan Ltd. | Individual | ASP | PAK | REF | 26 | INV | 31 | N | I |  | 0 | 0 | 0 | 0 | 1998-11-01 |  | 2000-12-01 |  |  | 2001-12-31 | 127804 | -127804 | 0 | 0 | #DIV/0! | 0 | 0 |  | 16614.52 | -16614.52 | 0 | 0 | 0 | Project cancelled at the 35th ExCom Meeting. |  |  |  | INV | 0
FIN | UNIDO | Preparation of refrigerant management plan | Individual | ASP | PAK | REF | 27 | PRP | 32 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 2000-03-01 | 1999-12-01 |  | 2003-07-01 | 2003-10-01 | 30000 | -2206 | 27794 | 27794 | 100% | 0 | 0 |  | 3900 | -292 | 3608 | 0 | 0 | FIN |  |  | 2001-12-01
FIN | IBRD | Preparation of projects in the foam flexible sub-sector |  | ASP | PAK | REF | 30 | PRP | 35 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 9000 | 0 | 9000 | 9000 | 100% | 0 | 0 |  | 1170 | 0 | 1170 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation in the refrigeration sector (railway) |  | ASP | PAK | REF | 30 | PRP | 36 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 16000 | 0 | 16000 | 16000 | 100% | 0 | 0 |  | 2080 | 0 | 2080 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Pakistan Airconditioning Engineering Co. P. Ltd., (PAECO) | Individual | ASP | PAK | REF | 32 | INV | 39 | N | I | CFC | 19.7 | 19.7 | 0 | 0 | 2000-12-01 | 2004-12-01 | 2004-01-01 |  | 2005-08-01 | 2006-02-01 | 176681 | 0 | 176681 | 176681 | 100% | 0 | 0 |  | 22968.53 | 0 | 22968.53 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Mumtaz Engineers | Individual | ASP | PAK | REF | 32 | INV | 40 | N | I | CFC | 13.9 | 13.9 | 0 | 0 | 2000-12-01 | 2004-12-01 | 2004-01-01 |  | 2005-11-01 | 2007-06-01 | 204736 | -21870.06 | 182865.94 | 182865.94 | 100% | 0 | 0 |  | 26615.68 | -2843.1 | 23772.9 | -0.32 | -0.32 | Project completed. |  |  |  | INV | 0
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the production of domestic refrigeration equipment at Ideal Appliances, Ltd. | Individual | ASP | PAK | REF | 35 | INV | 43 | A | I | CFC | 12.9 | 12.9 |  |  | 2001-12-01 | 2002-03-01 | 2004-07-01 |  | 2004-07-01 | 2005-09-01 | 173101 | -1342 | 171759 | 171759.09 | 100% | -0.09 | 0 |  | 22503 | -210 | 22293 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a phase-out plan in the refrigeration sector (CFC manufacturing) | Individual | ASP | PAK | REF | 39 | PRP | 50 | A | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-10-01 | 2004-04-01 |  | 2004-04-01 | 2005-05-01 | 20000 | -168 | 19832 | 19831.68 | 100% | 0.32 | 0 |  | 1500 | -15 | 1485 | 0 | 0 | FIN
FIN | UNIDO | Implementation of the RMP (institutional framework, customs empowerment, training service technicians, recovery and recycling) (first tranche) | Multi-Year | ASP | PAK | REF | 41 | TAS | 56 | A | I | CFC | 55 | 55 |  |  | 2003-12-01 | 2004-04-01 | 2004-12-01 |  | 2004-12-01 | 2009-12-01 | 191000 | 0 | 191000 | 191000.21 | 100% | -0.21 | 0 |  | 14325 | 0 | 14325 | 0 | 0 | FIN |  |  |  | INV
FIN | IBRD | Phaseout of the use of CFC-11 and CFC-12 in the manufacture of refrigeration equipment at Dawlance, United Refrigeration, Ice Age and at 29 small enterprises | Individual | ASP | PAK | REF | 42 | INV | 59 | N | I | CFC | 181.3 | 181.3 | 0 | 0 | 2004-04-01 | 2005-08-01 | 2007-04-01 |  | 2006-12-01 | 2007-06-01 | 1126855 | -49164 | 1077691 | 1077691 | 100% | 0 | 0 |  | 84514 | -3195 | 81319 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | UNIDO | Implementation of the RMP (institutional framework, customs empowerment, training service technicians, recovery and recycling) (second tranche) | Multi-Year | ASP | PAK | REF | 44 | TAS | 61 | A | I | CFC | 80 | 80 |  |  | 2004-12-01 | 2005-08-01 | 2005-12-01 |  | 2007-05-01 | 2010-09-01 | 534200 | -3137 | 531063 | 531062.64 | 100% | 0.36 | 0 |  | 40065 | -235 | 39830 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Implementation of the RMP (institutional framework, customs empowerment, training service technicians, recovery and recycling) (third tranche) | Multi-Year | ASP | PAK | REF | 47 | INV | 64 | A | I | CFC | 80 | 80 |  |  | 2005-11-01 | 2006-10-01 | 2006-12-01 |  | 2008-09-01 | 2010-09-01 | 414300 | -1421 | 412879 | 412879.45 | 100% | -0.45 | 0 |  | 31073 | -107 | 30966 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation for HCFC phase-out investment activities (refrigeration and air-conditioning manufacturing sectors) | Individual | ASP | PAK | REF | 59 | PRP | 74 | A | I |  | 0 | 0 |  |  | 2009-11-01 | 2010-04-01 | 2010-11-30 |  | 2011-07-01 | 2014-05-01 | 120000 | -5074 | 114926 | 114926.12 | 100% | -0.12 | 0 |  | 9000 | -381 | 8619 | 0 | 0 | FIN |  |  |  | NON-INV
COM | UNIDO | Preparation for HCFC phase-out investment activities (stage II) (refrigeration and air-conditioning sector) | Individual | ASP | PAK | REF | 72 | PRP | 86 | A | I |  | 0 | 0 |  |  | 2014-05-01 | 2015-09-01 | 2015-05-31 |  | 2016-12-01 |  | 60000 | 0 | 60000 | 24334.06 | 40.56% | 35665.94 | 35432.64 | 30000 | 4200 | 0 | 1703 | 2497 | 2480 | - Project completed, HPMP Stage II tranche approved in 2016 by the 76th Meeting of the ExCom. - Survey in respective HCFC consuming sectors accomplished. - Users of HCFCs and potential project beneficiaries including government, non-governmental organizations, RAC associations and other stakeholders identified. - Consultancy on safety measures and standardization in the sector ensured. - Investment project for conversion technology from R-22 to R290 in air conditioners manufacturing prepared for submission. - Study tour to China was successfully materialized. Participants from industries had unique opportunity to see new (hydrocarbon) technologies in full operation. Milestones achieved: Milestone 1: First mission/Working arrangements agreed - Yes Milestone 2: ToR for HCFC survey completed - Yes Milestone 3: Local institutions identified - Yes Milestone 4: Experts recruited - Yes Milestone 5: HCFC survey completed - Yes Milestone 6: All technical input completed - Yes Milestone 7: Draft document completed - Yes Actions towards next goals: Necessary accompanying documents for project document submission were obtained. Project document was submitted and approved. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Project completed - Open obligations will be paid |  |  | NON-INV
FIN | UNEP | Country programme preparation | Individual | ASP | PAK | SEV | 09 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-05-01 | 1994-06-01 |  | 1996-06-01 | 1996-09-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0
FIN | IBRD | Project identification and preparation (1993) |  | ASP | PAK | SEV | 11 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-31 | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 100000 | -91044 | 8956 | 8956 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1994) |  | ASP | PAK | SEV | 12 | PRP | 04 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 133191 | -38871 | 94320 | 94320 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | UNDP | Institutional strengthening under the Multilateral Fund for the Implementation of the Montreal Protocol | Individual | ASP | PAK | SEV | 14 | INS | 05 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1994-09-01 | 1996-01-01 | 1997-09-01 |  | 2001-12-01 | 2003-05-01 | 259000 | -4042 | 254958 | 254958 | 100% | 0 | 0 | 0 | 33670 | -525.46 | 33144.54 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1994 | 1999-12-01 | Non-Investment
FIN | IBRD | Preparation of investment projects (1995) |  | ASP | PAK | SEV | 16 | PRP | 08 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 143009 | 0 | 143009 | 143009 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation |  | ASP | PAK | SEV | 18 | PRP | 38 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation in the foam and refrigeration sectors |  | ASP | PAK | SEV | 21 | PRP | 12 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 |  | 5850 | 0 | 5850 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation in the foam and refrigeration sectors |  | ASP | PAK | SEV | 24 | PRP | 23 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1998-12-01 | 1998-12-01 | 63000 | 0 | 63000 | 63000 | 100% | 0 | 0 |  | 8190 | 0 | 8190 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of projects in the foam and refrigeration sectors |  | ASP | PAK | SEV | 27 | PRP | 33 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-31 | 2001-01-01 |  | 2000-12-01 | 2000-12-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 |  | 8580 | 0 | 8580 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Renewal of the institutional strengthening project (phase II) | Individual | ASP | PAK | SEV | 35 | INS | 44 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-01-01 | 2004-01-01 |  | 2004-01-01 | 2007-06-01 | 172666 | -102 | 172564 | 172564 | 100% | 0 | 0 | 0 | 22446.58 | -13.26 | 22433.3237 | -0.0037 | 0 | Completed in 2004. Financially completed in 2007. |  | 2001 |  | Non-Investment
FIN | IBRD | Assistance for the country programme update | Individual | ASP | PAK | SEV | 36 | CPG | 46 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-12-01 | 2003-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 |  | 5850 | 0 | 5850 | 0 | 0 | CPU submitted and approved at the 41st ExCom Meeting. |  |  |  | Non-INV | 0
FIN | UNDP | Extension of institutional strengthening project: phase 3 | Individual | ASP | PAK | SEV | 41 | INS | 54 | N | I | No_ODP | 18.6 | 18.6 | 0 | 0 | 2003-12-01 | 2005-02-01 | 2005-12-01 |  | 2007-12-01 | 2008-11-01 | 224467 | -2476 | 221991 | 221991 | 100% | 0 | 0 | 0 | 16835 | -185.7 | 16649.3003 | -0.0003 | 0 | Completed in 2005. Financially Completed in 2008. |  | 2003 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase IV) | Individual | ASP | PAK | SEV | 51 | INS | 65 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2007-03-01 | 2007-03-01 | 2009-04-01 |  | 2008-09-01 | 2011-12-01 | 112233 | 0 | 112233 | 112233 | 100% | 0 | 0 | 0 | 8417.5 | 0 | 8417.5 | 0 | 0 | Completed in 2008. Financially completed in 2011. |  | 2007 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase IV, second year) | Individual | ASP | PAK | SEV | 53 | INS | 66 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-10-01 | 2008-11-01 |  | 2010-12-01 | 2011-12-01 | 112234 | -17570.62 | 94663.38 | 94663 | 100% | 0.38 | 0 | 0 | 8418 | -1317.87 | 7100.1046 | 0.025402 | 0 | Completed in 2010. Financially completed in 2011. |  | 2007 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase V) | Individual | ASP | PAK | SEV | 57 | INS | 73 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-02-01 | 2011-03-01 |  | 2011-06-01 | 2013-03-01 | 224467 | 0 | 224467 | 224467 | 100% | 0 | 0 | 0 | 16835 | 0 | 16835 | 0 | 0 | Financially completed in 2013. |  | 2009 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VI) | Individual | ASP | PAK | SEV | 62 | INS | 81 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-01-01 | 2013-03-01 |  | 2013-04-01 | 2013-12-01 | 224467 | 0 | 224467 | 224467 | 100% | 0 | 0 | 0 | 16835 | 0 | 16835 | 0 | 0 | Financially completed in 2013. |  | 2010 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VII: 4/2013-3/2015) | Individual | ASP | PAK | SEV | 68 | INS | 82 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-05-01 | 2015-03-01 |  | 2015-09-01 | 2016-09-01 | 224467 | 0 | 224467 | 224467 | 100% | 0 | 0 | 0 | 15713 | 0 | 15713 | 0 | 0 | Financially completed in 2016. | The IS Phase-VII has been operationallly completed in March 2015. The IS activities continue under the IS Phase-VIII. | 2012 |  | Non-investment
ONG | UNDP | Extension of the institutional strengthening project (phase VIII: 4/2015-3/2017) | Individual | ASP | PAK | SEV | 73 | INS | 91 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-11-01 | 2015-07-01 | 2017-03-01 | 2017-03-01 |  |  | 224467 | 0 | 224467 | 81166.53 | 36.16% | 143300.47 | 0 | 57320.188 | 15713 | 0 | 5681.7692 | 10031.2308 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Pakistan has successfully achieved the 10% reduction target of 2nd Generations of ODS i.e. HCFCs and is compliant to articles of Montreal Protocol, Timely submitted the A7 and Country Programme Reports to MLFS and UNEP Secretariat, HCFC Quota for 2016 was prepared and distributed among the importers / manufacturers as per their set criteria. HPMP Stage II submitted in 76th ExCom. Consultative meetings held with Govt/industry/importers/end users in June, Aug and Sep. Prodoc signed (actual/planned, yes/no and date):42036 Missions undertaken (actual/planned):- TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: Contract signed First disbursement date (actual/planned): 42186Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | Ongoing | 2014 |  | Non-Investment
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | ASP | PAK | SEV | 74 | TAS | 92 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-06-01 | 2016-05-01 | 2017-06-01 |  |  | 130000 | 0 | 130000 | 56173.21 | 43.21% | 73826.79 | 73826.79 | 7382.679 | 16900 | 0 | 7302.5173 | 9597.4827 | 9597.4827 | Brief progress report(actual/planned): ToR developed and consultant recruited. Survey conducted. Stakeholder consultations meetings held, one during the mission by UNEP in Oct 2016. Full draft of the survey report submitted for review by UNEP. Legal arrangements(actual/planned): SSFA amended to extend the duration Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date(actual/planned): actual Aug 2016 All funds disbursed (yes/no): No Any delay?(yes/no): ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___ | Brief progress report(actual/planned): Comments on the first draft sent by UNEP Feb 2017. Comments are currently being incorporated into the final draft of the survey report. Legal arrangements(actual/planned): SSFA amended to extend the duration Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date(actual/planned): actual Aug 2016 All funds disbursed (yes/no): No Any delay?(yes/no): ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___
ONG | UNDP | Extension of the institutional strengthening project (phase IX: 4/2017-3/2019) | Individual | ASP | PAK | SEV | 77 | INS | 96 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2016-12-01 |  | 2019-03-01 | 2017-03-01 |  |  | 287318 | 0 | 287318 | 0 | 0% | 287318 | 0 | 114927.2 | 20112 | 0 | 0 | 20112 | 0 | Newly Approved | DoA sent March 2017. Awaiting prodoc & AWP from CO for ASL request. | 2016 |  | Non-Investment
FIN | UNIDO | Conversion of ODS coating processes from CFC-113 to trichloroethylene and IPA at Treet Corporation Ltd., Hyderabad | Individual | ASP | PAK | SOL | 22 | INV | 13 | A | I | CFC | 18.9 | 18.9 |  |  | 1997-05-01 | 1997-10-01 | 1999-11-01 |  | 1999-12-01 | 2002-09-01 | 321172 | -3201 | 317971 | 317970.94 | 100% | 0.06 | 0 |  | 41752 | -481 | 41271 | 0 | 0 | FIN
FIN | UNIDO | Conversion of ODS cleaning and coating processes from CFC-113 to trichloroethylene and IPA at Treet Corporation Ltd., Lahore | Individual | ASP | PAK | SOL | 22 | INV | 14 | A | I | CFC | 40.7 | 40.7 |  |  | 1997-05-01 | 1997-10-01 | 1999-11-01 |  | 2002-06-01 | 2003-06-01 | 510162 | 0 | 510162 | 510162.15 | 100% | -0.15 | 0 |  | 66321 | -37 | 66284 | 0 | 0 | FIN
FIN | UNIDO | Project preparation for four projects in the solvent (CTC) sector | Individual | ASP | PAK | SOL | 33 | PRP | 41 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-09-01 | 2002-04-01 |  | 2003-12-01 | 2004-12-01 | 30000 | -7022 | 22978 | 22977.9 | 100% | 0.1 | 0 |  | 3900 | -918 | 2982 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of two projects in the solvents sector | Individual | ASP | PAK | SOL | 36 | PRP | 45 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-06-01 | 2003-04-01 |  | 2003-12-01 | 2004-09-01 | 20000 | -639 | 19361 | 19360.91 | 100% | 0.09 | 0 |  | 2600 | -87 | 2513 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of cleaning installations from carbon tetrachloride (CTC) to tetrachloroethylene (PER) at Riaz Electric Ltd., Lahore | Individual | ASP | PAK | SOL | 37 | INV | 47 | A | I | CTC | 10 | 10 |  |  | 2002-07-01 | 2004-10-01 | 2004-08-01 |  | 2005-12-01 | 2006-12-01 | 122078 | -665 | 121413 | 121412.8 | 100% | 0.2 | 0 |  | 15870 | -86 | 15784 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of investment projects in the solvents sector (CTC/TCA) | Individual | ASP | PAK | SOL | 39 | PRP | 48 | A | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-04-01 | 2004-12-01 | 25000 | -807 | 24193 | 24192.9 | 100% | 0.1 | 0 |  | 1875 | -63 | 1812 | 0 | 0 | FIN
FIN | UNIDO | Conversion of cleaning installations from carbon tetrachloride (CTC) and methyl chloroform (MCF) to tetrachloroethylene (PER) and water in combination with partial process modification at Hirra Farooq Ltd., Lahore | Individual | ASP | PAK | SOL | 40 | INV | 51 | A | I | CTC MCF | 37.5 | 37.5 |  |  | 2003-07-01 | 2003-12-01 | 2005-07-01 |  | 2005-12-01 | 2007-03-01 | 246493 | -536 | 245957 | 245956.64 | 100% | 0.36 | 0 |  | 22184 | -48 | 22136 | 0 | 0 | FIN
FIN | UNIDO | Conversion of cleaning installations from carbon tetrachloride (CTC), methyl chloroform (MCF) and CFC-113 to tetrachloroethylene (PER) and water in combination with process modification at Breeze Frost Industries Ltd., Lahore | Individual | ASP | PAK | SOL | 40 | INV | 52 | A | I | CTC MCF CFC | 33.2 | 33.2 |  |  | 2003-07-01 | 2003-12-01 | 2005-07-01 |  | 2005-12-01 | 2007-03-01 | 282056 | -204 | 281852 | 281852.22 | 100% | -0.22 | 0 |  | 21254 | -15 | 21239 | 0 | 0 | FIN
FIN | UNDP | Elimination of CFC-11 in the manufacture of flexible and rigid polyurethane foam at Plastifoam, S.A., Profomsa, and Thermofoam, S.A. | Individual | LAC | PAN | FOA | 13 | INV | 05 | A | I | CFC | 26 | 26 | 0 | 0 | 1994-07-01 | 1996-07-01 | 1995-07-01 |  | 1999-08-01 | 2002-10-01 | 155000 | -13140 | 141860 | 141860 | 100% | 0 | 0 | 0 | 20150 | -1708.2 | 18441.8 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1994 | 1999-12-01 | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | LAC | PAN | FOA | 21 | PRP | 08 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2000-12-01 | 15000 | -2637 | 12363 | 12363 | 100% | 0 | 0 | 0 | 1950 | -342.81 | 1607.19 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
CLO | UNDP | Elimination of CFCs in the manufacture of extruded polystyrene foam sheet at Productos Moldeados America S.R. Ltda. (Plasticos Modernos) | Individual | LAC | PAN | FOA | 22 | INV | 09 | A | I | CFC | 16.2 | 16 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  |  | 2003-11-01 | 339296 | -213326 | 125970 | 125970 | 100% | 0 | 0 | 0 | 44108.48 | -27732.38 | 16376.1 | 0 | 0 | Canceled in 2003. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | LAC | PAN | FOA | 57 | PRP | 30 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2011-04-01 | 2010-03-01 |  | 2013-12-01 | 2014-02-01 | 50000 | -48000 | 2000 | 2000 | 100% | 0 | 0 | 0 | 3750 | -3600 | 150 | 0 | 0 | Financially completed in 2014. | Completed in 2013. Remaining funds have been returned to MLF. | 2009 |  | Investment
COM | UNDP | Preparation for HCFC phase-out investment activities (stage II) (foam sector) | Individual | LAC | PAN | FOA | 72 | PRP | 37 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 | 2015-01-01 | 2016-05-01 |  | 2016-12-01 |  | 80000 | 0 | 80000 | 78589.71 | 98.24% | 1410.29 | 0 | 1198.7465 | 5600 | 0 | 5501.2797 | 98.7203 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Project was prepared and submitted to the MLF ExCom, it was approved at the 76th meeting. Discussion with stakeholders were conducted to discuss next steps and ProDoc preparation. Prodoc signed (actual/planned, yes/no and date):The agreement has been signed earlier. Missions undertaken (actual/planned):1 of 1 TOR for consultants/subcontracts completed (actual/planned): TOR completed earlier. Contract/PO/MOA agreements signed: The agreement has been signed earlier First disbursement date (actual/planned): 42005Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve:N/A | Completion and follow up process underway. |  |  | Non-Investment
FIN | UNIDO | Preparation of an awareness workshop on methyl bromide | Individual | LAC | PAN | FUM | 36 | TRA | 16 | A | I | MBR | 0 | 0 |  |  | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2002-10-01 | 2003-12-01 | 30000 | -5344 | 24656 | 24656.21 | 100% | -0.21 | 0 |  | 3900 | -700 | 3200 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | USA | Technical assistance in halon-1211 |  | LAC | PAN | HAL | 13 | TAS | 04 | A | I |  | 0 |  | 0 |  | 1994-07-01 |  | 1995-07-01 |  | 1995-07-01 | 1996-06-01 | 120000 | -42445 | 77555 | 77555 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | UNDP | National phase-out plan for Annex A (Group I) substances (first tranche) | Multi-Year | LAC | PAN | PHA | 44 | INV | 22 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-12-01 | 2006-04-01 | 2005-12-01 |  | 2008-12-01 | 2013-01-01 | 250152 | 0 | 250152 | 250152 | 100% | 0 | 0 | 0 | 18762 | 0 | 18762 | 0 | 0 | Financially completed in 2013. |  | 2004 |  | Investment
FIN | UNEP | National phase-out plan for Annex A (Group I) substances (first tranche) | Multi-Year | LAC | PAN | PHA | 44 | TAS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2008-01-01 | 2005-12-01 |  | 2009-12-01 | 2012-04-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0
FIN | UNDP | National phase-out plan for Annex A (Group I) substances (second tranche) | Multi-Year | LAC | PAN | PHA | 47 | INV | 24 | N | I | CFC | 36.4 | 36.4 | 0 | 0 | 2005-11-01 | 2008-02-01 | 2006-12-01 |  | 2009-12-01 | 2013-01-01 | 238000 | 0 | 238000 | 238000 | 100% | 0 | 0 | 0 | 17850 | 0 | 17850 | 0 | 0 | Financially completed in 2013. |  | 2005 |  | Investment
FIN | UNEP | National phase-out plan for Annex A (Group I) substances (second tranche) | Multi-year | LAC | PAN | PHA | 47 | TRA | 25 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2008-02-01 | 2006-12-01 |  | 2011-06-01 | 2011-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0
FIN | UNDP | National phase-out plan for Annex A (Group I) substances (third tranche) | Multi-Year | LAC | PAN | PHA | 50 | INV | 26 | N | I | CFC | 66 | 66 | 0 | 0 | 2006-11-01 | 2009-05-01 | 2008-11-01 |  | 2010-08-01 | 2013-01-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 15000 | 0 | 15000 | 0 | 0 | Financially completed in 2013. |  | 2006 |  | Investment
FIN | UNEP | National phase-out plan for Annex A (Group I) substances (third tranche) | Multi-year | LAC | PAN | PHA | 50 | TAS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2009-09-01 | 2007-11-01 |  | 2011-06-01 | 2011-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | PAN | PHA | 55 | PRP | 28 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2011-11-01 | 2013-11-01 | 150000 | -6455.12 | 143544.88 | 143545 | 100% | -0.12 | 0 | 0 | 11250 | -484.21 | 10765.799 | -0.0089999 | 0 | Financially completed in 2013. | Completed in 2011. HPMP approved by the 65th Executive Committee Meeting. Some final invoices pending. | 2008 |  | Investment
FIN | UNDP | National phase-out plan for Annex A (Group I) substances (fourth and fifth tranches) | Multi-Year | LAC | PAN | PHA | 56 | INV | 29 | N | I | CFC | 66 | 66 | 0 | 0 | 2008-11-01 | 2010-02-01 | 2009-11-01 |  | 2010-12-01 | 2012-07-01 | 255000 | -439.01 | 254560.99 | 254561 | 100% | -0.01 | 0 | 0 | 19125 | -32.93 | 19092.075 | -0.00505 | 0 | Financially completed in 2012. |  | 2008 |  | Investment
FIN | UNDP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-year | LAC | PAN | PHA | 65 | INV | 32 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-10-01 | 2016-10-01 |  | 2013-12-01 | 2014-09-01 | 132773 | 0 | 132773 | 132773 | 100% | 0 | 0 | 0 | 9958 | 0 | 9958 | 0 | 0 | Financially completed in 2014. | 2014 workplan and budget prepared and approved. HCFC quotas for 2014 established. 1 train-the-trainers workshop conducted. | 2011 |  | Investment
COM | UNEP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | LAC | PAN | PHA | 65 | TAS | 31 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-06-01 | 2013-11-01 |  | 2016-09-01 |  | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 |  | 4550 | 0 | 4550 | 0 | 0 | Brief progress report: The implementation of the tranche is completed. Country is a member of the i-PIC UNEP-database to exchange information on ODSs imports/exports previously before shipment arrives to the port. NOU is in close coordination with Customs Officer to detect ODSs illegal trade shipments and to exchange information related to HCFCs license system. Legal arrangements (actual/planned): Not applicable. Government of Panama asked for UNEP administrative support in the project implementation. First mission (actual/planned): N/A. Regional CAP staff is based in Panama. A coordination meeting carried out for providing support to NOU with planning of 2016 activities. TOR completed (actual/planned): N/A. Direct payments were issued to suppliers and contractors. First disbursement date: June 2012/Planned for May 2012. All funds disbursed? (yes/no): Yes. Any delay? (yes/no): Some delays. If Yes, reasons for delay & action plan to resolve: Administrative reasons related to the setup of UMOJA (new financial system of UNEP), which are already sorted out. If Yes, will delay have impact on project completion date? Yes. Any ongoing problems? (yes/no): No. If Yes, is any action required by ExCom: N/A. | Project completed in September 2016
FIN | UNDP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | LAC | PAN | PHA | 70 | INV | 34 | N | I | HCFC | 1.8 | 1.8 | 0 | 0 | 2013-07-01 | 2014-07-01 | 2015-07-01 |  | 2015-11-01 | 2016-11-01 | 100907 | 0 | 100907 | 100907 | 100% | 0 | 0 | 0 | 7568 | 0 | 7568 | 0 | 0 | Financially completed in 2016. | Second tranche implementation report and third tranche request were prepared and submitted. Implementation of 2015 workplan is underway, 2 workshops on good refrigeration practices were conducted; meetings with customs authorities, HCFC importerts and users have been carried out. | 2013 |  | Investment
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | PAN | PHA | 70 | TAS | 35 | A | I |  | 0.7 |  | 0 |  | 2013-07-01 | 2014-04-01 | 2015-07-01 | 2017-12-01 |  |  | 26600 | 0 | 26600 | 18046.2 | 67.84% | 8553.8 | 0 | 855.38 | 3458 | 0 | 2346.006 | 1111.994 | 0 | Brief progress report (actual/planned): The implementation of the tranche is progressing. National Consultant hired to support the Government with definition of safety standards for flammable refrigerants. A proposal was drafted and consulted with main stakeholders. In addition to that, one portable ODS identifier is included in the UNEP global bidding. Legal arrangements (actual/planned): Not applicable. Government of Panama asked for UNEP administrative support in the project implementation. Direct payments were issued to suppliers and contractors. First mission (actual/planned): N/A. Regional CAP staff is based in Panama. A coordination meeting among the RNC and the NOU carried out. TOR completed (actual/planned): TOR for hiring the national consultant agreed with the NOU and approved by the Head of the Branch in March 2016/October 2015. First disbursement date (actual/planned): January 2014/Planned for January 2014. All funds disbursed (yes/no): No. Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: Administrative reasons related to the set up of UMOJA (new financial system of UNEP), which are already sorted out. If Yes, will delay have impact on project completion date (yes/no): Yes. Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: No | Brief progress report (actual/planned): The implementation of the tranche is progressing. The procurement of one ODS identifier is under process and purchase order will be issued by June 2017. Legal arrangements (actual/planned): Not applicable. Government of Panama asked for UNEP administrative support in the project implementation. Direct payments were issued to suppliers and contractors. First mission (actual/planned): N/A. Regional CAP staff is based in Panama. A coordination meeting among the RNC and the NOU carried out. TOR completed (actual/planned): March 2016/October 2015. First disbursement date (actual/planned): January 2014/Planned for January 2014. All funds disbursed (yes/no): No. Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: Administrative reasons related to the set-up of UMOJA (new financial system of UNEP), which are already sorted out. If Yes, will delay have impact on project completion date (yes/no): Yes. Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: No
COM | UNDP | Preparation of a HCFC phase-out management plan (stage II) | Individual | LAC | PAN | PHA | 72 | PRP | 38 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 | 2015-01-01 | 2016-05-01 |  | 2016-12-01 |  | 60000 | 0 | 60000 | 36655.82 | 61.09% | 23344.18 | 0 | 19842.553 | 4200 | 0 | 2565.9074 | 1634.0926 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Project was prepared and submitted to the MLF ExCom, it was approved at the 76th meeting. Discussion with stakeholders were conducted to discuss next steps and ProDoc preparation. Prodoc signed (actual/planned, yes/no and date):The agreement has been signed earlier. Missions undertaken (actual/planned):1 of 1 TOR for consultants/subcontracts completed (actual/planned): TOR completed earlier. Contract/PO/MOA agreements signed: The agreement has been signed earlier First disbursement date (actual/planned): 42005Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve:N/A | Completion and follow up process underway. Pending payments in the process of being cleared. |  |  | Investment
COM | UNDP | HCFC phase-out management plan (stage I, third tranche) | Multi-year | LAC | PAN | PHA | 74 | INV | 39 | N | I | HCFC | 0 | 0 | 0 | 0 | 2015-05-01 | 2015-08-01 | 2017-05-01 |  | 2015-12-01 |  | 31865 | 0 | 31865 | 28546 | 89.58% | 3319 | 0 | 2821.15 | 2390 | 0 | 2141.062 | 248.938 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2015. |  | 2015 |  | Investment
ONG | UNEP | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | LAC | PAN | PHA | 74 | TAS | 40 | A | I |  | 0 |  | 0 |  | 2015-05-01 |  | 2016-12-01 | 2017-12-01 |  |  | 8400 | 0 | 8400 | 0 | 0% | 8400 | 0 | 840 | 1092 | 0 | 0 | 1092 | 0 | Brief progress report (actual/planned): The implementation of the tranche is slowly progressing. Two additional portable ODS identifiers were included in the UNEP global bidding. Legal arrangements (actual/planned): Not applicable. Government of Panama asked for UNEP administrative support in the project implementation. First mission (actual/planned): N/A. TOR completed (actual/planned): Yes, TOR of equipment were drafted. First disbursement date (actual/planned): No disbursements/November 2015. All funds disbursed (yes/no): No. Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: In 2015 there was a challenging transformation of financial system in UNEP from IMIs to UMOJA. This project was approved during the UMOJA black out period; which prevented the timely programming of all new projects' budget. The staff’s learning curves of this new financial platform as well as the definition of users profile to enter and approve data were gradually improved during the 2015. If Yes, will delay have impact on project completion date (yes/no): Yes. Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: No. | Brief progress report (actual/planned): The implementation of the tranche is slowly progressing. The procurement of two additional ODS identifiers is under process and purchase order will be issued by June 2017. Legal arrangements (actual/planned): Not applicable. Government of Panama asked for UNEP administrative support in the project implementation. First mission (actual/planned): N/A. TOR completed (actual/planned): Yes, TOR of equipment were drafted. First disbursement date (actual/planned): No disbursements/November 2015. All funds disbursed (yes/no): No. Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: In 2015 there was a challenging transformation of financial system in UNEP from IMIs to UMOJA. This project was approved during the UMOJA black out period; which prevented the timely programming of all new projects' budget. The staff’s learning curves of this new financial platform as well as the definition of users profile to enter and approve data were gradually improved during the 2015. If Yes, will delay have impact on project completion date (yes/no): Yes. Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: No.
ONG | UNDP | HCFC phase-out management plan (stage II, first tranche) (foam sector) | Multi-Year | LAC | PAN | PHA | 76 | INV | 44 | N | I | HCFC | 2.5 | 0 | 0 | 0 | 2016-05-01 |  | 2019-05-01 | 2017-05-01 |  |  | 118000 | 0 | 118000 | 0 | 0% | 118000 | 0 | 47200 | 8260 | 0 | 0 | 8260 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Project document prepared. Meetings with NOU to review estrategy and work plan. Prodoc signed (actual/planned, yes/no and date):No, March 2017 Missions undertaken (actual/planned):1 of 1 TOR for consultants/subcontracts completed (actual/planned): 0 of 0 Contract/PO/MOA agreements signed: 0 of 0 First disbursement date (actual/planned): 42826Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:Prodoc preparation has taken longer than initially expected. Meetings with the NOU were conducted to review drafts, a schedule was established and a consultatn hired for completing the writing of the document. | Final draft under review by stakeholders. |  |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | Multi-Year | LAC | PAN | PHA | 76 | TAS | 43 | N | I | HCFC | 0 | 0 | 0 | 0 | 2016-05-01 |  | 2019-05-01 | 2017-05-01 |  |  | 147100 | 0 | 147100 | 0 | 0% | 147100 | 0 | 58840 | 10297 | 0 | 0 | 10297 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Project document prepared. Meetings with NOU to review estrategy and work plan. Prodoc signed (actual/planned, yes/no and date):No, March 2017 Missions undertaken (actual/planned):1 of 1 TOR for consultants/subcontracts completed (actual/planned): 0 of 0 Contract/PO/MOA agreements signed: 0 of 0 First disbursement date (actual/planned): 42826Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:Prodoc preparation has taken longer than initially expected. Meetings with the NOU were conducted to review drafts, a schedule was established and a consultatn hired for completing the writing of the document. | Final draft under review by stakeholders. |  |  | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | PAN | REF | 18 | TAS | 06 | A | I | CFC | 17 | 17 | 0 | 0 | 1995-11-01 | 1996-02-01 | 1997-05-01 |  | 1999-07-01 | 2003-11-01 | 172465 | -10608 | 161857 | 161857 | 100% | 0 | 0 | 0 | 22420.45 | -1379.04 | 21041.41 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  | 1995 | 1999-07-01 | Investment
FIN | UNEP | Development of refrigerant management plans | RMP | LAC | PAN | REF | 24 | PRP | 10 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1999-02-01 |  | 1999-10-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | Finland | Implementation of the RMP: monitoring and evaluation of the RMP | Individual | LAC | PAN | REF | 29 | TAS | 11 | A | I | CFC | 0 |  | 0 |  | 1999-11-01 | 2002-02-01 | 2002-12-01 |  | 2008-12-01 |  | 33000 | -18690 | 14310 | 14310 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed in December 2008. |  | 2001
FIN | UNEP | Implementation of the RMP: monitoring on assistance to develop legislation | Individual | LAC | PAN | REF | 29 | TAS | 14 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2003-06-01 | 2002-12-01 |  | 2008-12-01 | 2009-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0
FIN | Finland | Implementation of the RMP: training programme for custom officers | Individual | LAC | PAN | REF | 29 | TRA | 12 | A | I | CFC | 0 |  | 0 |  | 1999-11-01 | 2003-05-01 | 2001-06-01 |  | 2007-12-01 |  | 70000 | -34022 | 35978 | 35978 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. Balances to be returned after all pending payments have been recorded |  | 2001 | 2002-12-01
FIN | UNEP | Implementation of the RMP: training and certification programme in refrigeration | Individual | LAC | PAN | REF | 29 | TRA | 13 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2001-12-01 | 2002-12-01 |  | 2008-12-01 | 2010-12-01 | 126200 | 0 | 126200 | 126200 | 100% | 0 | 0 |  | 16406 | 0 | 16406 | 0 | 0
FIN | UNDP | Project preparation for update of refrigerant management plan (investment components) | Individual | LAC | PAN | REF | 40 | PRP | 18 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-07-01 | 2003-08-01 | 2004-07-01 |  | 2005-12-01 | 2006-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1125 | 0 | 1125 | 0 | 0 | Completed in 2005. Financially completed in 2006. |  | 2003 |  | Investment
FIN | UNEP | Project preparation for refrigerant management plan update | RMP update | LAC | PAN | REF | 40 | PRP | 19 | A | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2004-03-01 | 2004-07-01 |  | 2004-10-01 | 2007-01-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0
FIN | UNEP | Country programme preparation | Individual | LAC | PAN | SEV | 06 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-04-01 | 1993-05-01 |  | 1993-06-01 | 1993-12-01 | 30000 | -3000 | 27000 | 27000 | 100% | 0 | 0 |  | 3900 | -390 | 3510 | 0 | 0
FIN | UNEP | Institutional strengthening: establishment of COGO | Individual | LAC | PAN | SEV | 10 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1995-04-01 | 1996-10-01 |  | 2000-12-01 | 2001-12-01 | 172500 | 0 | 172500 | 172500 | 100% | 0 | 0 |  | 22425 | 0 | 22425 | 0 | 0 |  |  |  | 1999-12-01
FIN | UNDP | Project preparation assistance | Individual | LAC | PAN | SEV | 11 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-01 | 1994-05-01 |  | 1995-09-01 | 1997-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1993 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | PAN | SEV | 18 | PRP | 07 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-09-01 | 1996-11-01 |  | 1996-11-01 | 1998-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | LAC | PAN | SEV | 31 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2000-07-01 | 2001-01-01 | 2002-08-01 |  | 2002-12-01 | 2004-10-01 | 115000 | 0 | 115000 | 115000 | 100% | 0 | 0 |  | 14950 | 0 | 14950 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening (phase 3) | Individual | LAC | PAN | SEV | 38 | INS | 17 | A | I | CFC | 12.4 | 12.4 | 0 | 0 | 2002-11-01 | 2004-01-01 | 2004-12-01 |  | 2007-01-01 | 2010-12-01 | 149500 | 0 | 149500 | 149500 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | LAC | PAN | SEV | 44 | INS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2009-09-01 | 2006-12-01 |  | 2011-12-01 | 2011-12-01 | 149500 | 0 | 149500 | 149500 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of institutional strengthening project (phase V: 11/2011-10/2013) | Individual | LAC | PAN | SEV | 65 | INS | 33 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2011-12-01 | 2013-08-01 |  | 2014-12-01 |  | 149500 | -3872 | 145628 | 128390 | 88.16% | 17238 | 0 | 17238 | 0 | 0 | 0 | 0 | 0
COM | UNDP | Extension of institutional strengthening project (phase VI: 12/2013-11/2015) | Individual | LAC | PAN | SEV | 71 | INS | 36 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2013-12-01 | 2014-08-01 | 2015-11-01 |  | 2016-06-01 |  | 149500 | 0 | 149500 | 149495.07 | 100% | 4.93 | 0 | 4.1905 | 10465 | 0 | 10464.6549 | 0.3451 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Institutional strengthening activities underway. ODS consumption reports prepared and submitted. Celebration of Ozone Day carried out. 2016 HCFC import quota set. NOU attended regional and global meetings. Prodoc signed (actual/planned, yes/no and date):The agreement has been signed earlier. Missions undertaken (actual/planned):1 of 1 TOR for consultants/subcontracts completed (actual/planned): TOR completed earlier. Contract/PO/MOA agreements signed: The agreement has been signed earlier First disbursement date (actual/planned): 41852Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve:N/A | Project completed. | 2013 |  | Non-Investment
ONG | UNDP | Survey of ODS alternatives at the national level | Individual | LAC | PAN | SEV | 74 | TAS | 41 | N | I | HFC | 0 | 0 | 0 | 0 | 2015-05-01 | 2016-04-01 | 2016-11-01 | 2017-02-01 |  |  | 110000 | 0 | 110000 | 14770.75 | 13.43% | 95229.25 | 17500 | 38091.7 | 9900 | 0 | 1329.3675 | 8570.6325 | 1575 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Project team hired. Methodology for conducting the survey was discussed and approved. Survey conducted and draft report prepared. Prodoc signed (actual/planned, yes/no and date):Yes, January 2016 Missions undertaken (actual/planned):1 of 1 TOR for consultants/subcontracts completed (actual/planned): 2 of 2 Contract/PO/MOA agreements signed: 1 of 2 First disbursement date (actual/planned): 42461Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve:N/A | Final report prepared. Excel tables with survey results completed and submitted. | 2015 |  | Non-Investment
ONG | UNDP | Extension of institutional strengthening project (phase VII: 12/2015-11/2017) | Individual | LAC | PAN | SEV | 75 | INS | 42 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2015-11-01 | 2016-08-01 | 2017-11-01 | 2017-11-01 |  |  | 191360 | 0 | 191360 | 29624.29 | 15.48% | 161735.71 | 0 | 64694.284 | 13395 | 0 | 2073.6693 | 11321.3307 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): ProDoc prepared and discussed with counterparts, it was signed on July 2016. Contract for the implementation team were prepared and signed. Prodoc signed (actual/planned, yes/no and date):Yes, July 2016 Missions undertaken (actual/planned):1 of 1 TOR for consultants/subcontracts completed (actual/planned): 2 of 2 Contract/PO/MOA agreements signed: 2 of 2 First disbursement date (actual/planned): 42583Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve:N/A | Annual work plan prepared. HCFC import quota set for 2017. | 2015 |  | Non-Investment
FIN | UNDP | Project preparation in the foam sector | Individual | LAC | PAR | FOA | 22 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1997-12-01 |  | 1998-04-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Terminal umbrella project: Conversion to CFC-free technology in the manufacture of polyurethane foam at Superspuma Del Paraguay SAIC, Suenolar, La Asuncena, and Industrias Cel | Individual | LAC | PAR | FOA | 23 | INV | 04 | A | I | CFC | 55.5 | 55.5 | 0 | 0 | 1997-11-01 | 1998-11-01 | 1999-12-01 |  | 1999-12-01 | 2002-10-01 | 405600 | -118208 | 287392 | 287392 | 100% | 0 | 0 | 0 | 52728 | -15366.78 | 37361.22 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1997 |  | Investment
COM | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | LAC | PAR | FOA | 57 | PRP | 21 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-07-01 | 2010-03-01 |  | 2016-12-01 |  | 60000 | 0 | 60000 | 53343.23 | 88.91% | 6656.77 | 0 | 5658.2545 | 4500 | 0 | 4000.7422 | 499.2577 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Project document prepared and submitted. Project was withdrawn after discussion with the MLFS. Prodoc signed (actual/planned, yes/no and date):The agreement has been signed earlier. Missions undertaken (actual/planned):0 of 0 TOR for consultants/subcontracts completed (actual/planned): TOR completed earlier. Contract/PO/MOA agreements signed: 0 of 0 First disbursement date (actual/planned): 39995Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve:N/A | No activities has been conducted. Pending payments in the process of being cleared. | 2009 |  | Investment
COM | Spain | Technical assistance to phase-out the use of methyl bromide | Individual | LAC | PAR | FUM | 47 | TAS | 15 | A | I | MBR | 0.2 | 0.2 | 0 | 0 | 2005-11-01 | 2007-07-01 | 2007-12-01 |  | 2009-07-01 |  | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 |  | 5200 |  | This Project was approved on ExCom 47th, December 2005. 100% of the activities have already been implemented and 100% of funds have been disbursed. Objectives of the project and MeBr phase-out were accomplished. Only signature of PCR is remaining and expectd by Jul 09. . 100% of the activities have already been implemented and 100% of funds have been disbursed. Objectives of the project and MeBr phase-out were accomplished. Only PCR remain for signature that is expected on July 2009. | Project is completed. All funds were exhausted. The balance of US$ 1500 is not real. Clarification of accounts between UNDP Country Office and UNEP is in progress
FIN | UNDP | Project preparation of a terminal phase-out management plan | Individual | LAC | PAR | PHA | 47 | PRP | 16 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-04-01 | 2006-12-01 |  | 2007-04-01 | 2011-11-01 | 30000 | -2720.43 | 27279.57 | 27280 | 100% | -0.43 | 0 | 0 | 2250 | -204.03 | 2045.9999 | -0.02995 | 0 | Completed in 2007. |  | 2005 |  | Investment
FIN | UNDP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | PAR | PHA | 51 | INV | 17 | N | I | CFC | 68.7 | 68.7 | 0 | 0 | 2007-03-01 | 2009-01-01 | 2010-12-01 |  | 2009-12-01 | 2013-12-01 | 160000 | 0 | 160000 | 160000 | 100% | 0 | 0 | 0 | 12000 | 0 | 12000 | 0 | 0 | Financially completed in 2013. |  | 2007 |  | Investment
FIN | UNEP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | PAR | PHA | 51 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2007-03-01 | 2007-11-01 | 2010-12-01 |  | 2010-12-01 | 2011-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | PAR | PHA | 55 | PRP | 20 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-05-01 | 2009-07-01 |  | 2011-04-01 | 2011-04-01 | 85000 | -6789 | 78211 | 78211 | 100% | 0 | 0 |  | 11050 | -882.57 | 10167.43 | 0 | 0
FIN | UNDP | Preparation of a HCFC phase-out management plan (additional funding) | Individual | LAC | PAR | PHA | 57 | PRP | 22 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-01-01 | 2010-03-01 |  | 2012-05-01 | 2014-03-01 | 65000 | -14983 | 50017 | 50017 | 100% | 0 | 0 | 0 | 4875 | -1123.73 | 3751.27 | 0 | 0 | Financially completed in 2014. | Completed in 2012. No activities in 2013. | 2009 |  | Investment
FIN | UNDP | Terminal phase-out management plan for Annex A Group I substances (second and third tranches) | Multi-Year | LAC | PAR | PHA | 58 | INV | 23 | N | I | CFC | 0 | 0 | 0 | 0 | 2009-07-01 | 2010-01-01 | 2011-07-01 |  | 2011-07-01 | 2013-07-01 | 190000 | 0 | 190000 | 190000 | 100% | 0 | 0 | 0 | 14250 | 0 | 14250 | 0 | 0 | Financially completed in 2013. |  | 2009 |  | Investment
FIN | UNEP | Terminal phase-out management plan for Annex A Group I substances (second and third tranches) | Multi-Year | LAC | PAR | PHA | 58 | TAS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2010-02-01 | 2011-07-01 |  | 2011-07-01 | 2011-12-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 |  | 11700 | 0 | 11700 | 0 | 0
FIN | UNDP | Terminal phase-out management plan for Annex A Group I substances (fourth tranche) | Multi-year | LAC | PAR | PHA | 60 | INV | 26 | N | I | CFC | 31.6 | 31.6 | 0 | 0 | 2010-04-01 | 2011-12-01 | 2011-04-01 |  | 2012-12-01 | 2014-12-01 | 21000 | -5 | 20995 | 20995 | 100% | 0 | 0 | 0 | 1575 | -0.38 | 1574.62 | 0 | 0 | Financially completed in 2014. | Completed in 2012. No activities in 2013. | 2010 |  | Investment
FIN | UNEP | Terminal phase-out management plan for Annex A Group I substances (fourth tranche) | Multi-Year | LAC | PAR | PHA | 60 | TAS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2011-10-01 | 2011-04-01 |  | 2011-12-01 | 2011-12-01 | 24000 | 0 | 24000 | 24000 | 100% | 0 | 0 |  | 3120 | 0 | 3120 | 0 | 0
FIN | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | PAR | PHA | 63 | INV | 29 | N | I | HCFC | 0.9 | 0.9 | 0 | 0 | 2011-04-01 | 2012-04-01 | 2013-03-01 |  | 2015-08-01 | 2016-09-01 | 168500 | 0 | 168500 | 168500 | 100% | 0 | 0 | 0 | 12638 | 0 | 12638 | 0 | 0 | Financially completed in 2016. | 1st tranche implementation report and 2nd tranche request prepared, submitted and approved. 1 workshop on good refrigeration practices and alternatives to HCFC was prepared and conducted by international expert. | 2011 |  | Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | PAR | PHA | 63 | TAS | 28 | A | I |  | 0.9 | 0 | 0 | 0 | 2011-04-01 | 2012-04-01 | 2013-03-01 | 2017-06-01 |  |  | 146500 | 0 | 146500 | 146500 | 100% | 0 | 0 |  | 19045 | 0 | 19045 | 0 | 0 | Brief progress report: Annual goals achieved as planned for the year 2016: Country made progress in: a) prevention of ODS illegal trade and ODSs-based equipment smuggling, b) monitoring the ODSs importers facilities, c) technical support to RAC technicians certifications, and, d) joint the committee of technical standards definition. Legal arrangements (actual/planned): signed in April 2012/planned April 2012. A new agreement to implement activities in 2015-2016 signed in November 2015. First mission (actual/planned): N/A. TOR completed (actual/planned): N/A. First disbursement date (actual/planned): April 2012/April 2012. All funds disbursed (yes/no): Yes. Remaining budget transferred to the Government in February 2016. Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: Administrative reasons related to the setup of UMOJA (new financial system of UNEP), which are already sorted out. Furthermore, the Government asked for a modification of some standard clauses of the legal agreement but after a long negotiation process the discrepancy was resolved with the intervention of the Head of the Branch. If Yes, will delay have impact on project completion date (yes/no): Yes. Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: No. | Brief progress report: 2016 Progress Report and financial statement processed in January 2017. Total expenditures reaches more than 90% of the tranche. Legal arrangements (actual/planned): signed in April 2012/planned April 2012. A new agreement to implement activities in 2015-2016 signed in November 2015. First mission (actual/planned): N/A. TOR completed (actual/planned): N/A. First disbursement date (actual/planned): April 2012/April 2012. All funds disbursed (yes/no): Yes. Remaining budget transferred to the Government in February 2016. Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: Administrative reasons related to the setup of UMOJA (new financial system of UNEP), which are already sorted out. Furthermore, the Government asked for a modification of some standard clauses of the legal agreement but after a long negotiation process the discrepancy was resolved with the intervention of the Head of the Branch. If Yes, will delay have impact on project completion date (yes/no): Yes. Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: No.
COM | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Multi-Year | LAC | PAR | PHA | 73 | TAS | 32 | A | I |  | 0 |  | 0 |  | 2014-11-01 | 2015-04-03 | 2015-05-01 |  | 2015-07-01 |  | 30000 | 0 | 30000 | 15588.16 | 51.96% | 14411.84 | 14411.84 | 14411.84 | 3900 | 0 | 2026.4608 | 1873.5392 | 1873.5392 | Project completed. Reconciliation of accounts between IMIS and UMOJA completed. PCR delivered. | All expenditures dully registered in UMOJA. Balance to be returned to the Multilateral Fund.
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | LAC | PAR | PHA | 74 | INV | 34 | N | I | HCFC | 2.1 | 0 | 0 | 0 | 2015-05-01 | 2016-03-01 | 2020-05-01 | 2017-05-01 |  |  | 131500 | 0 | 131500 | 15244.04 | 11.59% | 116255.96 | 0 | 46502.384 | 9862 | 0 | 1143.245 | 8718.755 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): In 2016, 476 RAC technicians were trained in GRP, 76 officers from the Customs Autorithy were trained on illicit trade prevention. Legal framework was updated. HCFC import quotas for 2016 were set. Prodoc signed (actual/planned, yes/no and date):Yes, February 2016. Missions undertaken (actual/planned):1 of 1 TOR for consultants/subcontracts completed (actual/planned): 1 of 1 Contract/PO/MOA agreements signed: 1 of 1 First disbursement date (actual/planned): 42430Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve:N/A | Annual work plan prepared. HCFC import quota set for 2017. | 2015 |  | Investment
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | LAC | PAR | PHA | 74 | TAS | 33 | A | I |  | 2.4 |  | 0 |  | 2015-05-01 | 2016-04-01 | 2020-05-01 | 2020-05-01 |  |  | 120500 | 0 | 120500 | 0 | 0% | 120500 | 46804.49 | 27638.16 | 15665 | 0 | 0 | 15665 | 6084.5837 | Brief progress report: In 2016, project implementation advanced according to Annual Implementation Plan. Country made progress in: a) prevention of ODS illegal trade and ODSs-based equipment smuggling, b) monitoring the ODSs importers facilities, c) promoting the recovery and recycling of refrigerants and the use of HCFCs alternatives. First mission (actual/planned): N/A. TOR completed (actual/planned): N/A. First disbursement date: April 2016/Planned for November 2015. All funds disbursed? (yes/no): No. Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: Carry over of delays caused by the transformation of financial system in UNEP from IMIS to UMOJA. This project was approved during the UMOJA black out period; which prevented the timely programming of all new projects' budget. The staff’s learning curves of this new financial platform as well as the definition of users profile to enter and approve data were gradually improved during the year. If Yes, will delay have impact on project completion date? Yes. Expected project completion date has been postponed 6 months. Any ongoing problems? No. If Yes, is any action required by ExCom? N/A. | Brief progress report: In 2017, project implementation is progressing as planned. First mission (actual/planned): N/A. TOR completed (actual/planned): N/A. First disbursement date: April 2016/Planned for November 2015. All funds disbursed? (yes/no): No. Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: Carry over of delays caused by the transformation of financial system in UNEP from IMIS to UMOJA. This project was approved during the UMOJA black out period; which prevented the timely programming of all new projects' budget. The staff’s learning curves of this new financial platform as well as the definition of users profile to enter and approve data were gradually improved during the year. If Yes, will delay have impact on project completion date? Yes. Expected project completion date has been postponed 6 months. Any ongoing problems? No. If Yes, is any action required by ExCom? N/A.
FIN | UNDP | Preparation of a refrigerant recycling project | Individual | LAC | PAR | REF | 27 | PRP | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-10-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNEP | Implementation of the RMP: monitoring and control of ODS and ODS based equipment, and training of customs officers and other inspection officers | Individual | LAC | PAR | REF | 32 | TAS | 06 | A | I | CFC | 15.2 | 15.2 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2001-12-01 |  | 2008-12-01 | 2010-12-01 | 44920 | 0 | 44920 | 44920 | 100% | 0 | 0 |  | 5840 | 0 | 5840 | 0 | 0 |  |  |  | 2003-06-01
FIN | UNDP | Implementation of the RMP: national programme for recovery and recyling of CFC-12 refrigerant | RMP-Component | LAC | PAR | REF | 32 | TAS | 08 | A | I | CFC | 96.3 | 96.3 | 0 | 0 | 2000-12-01 | 2001-06-01 | 2004-01-01 |  | 2004-12-01 | 2005-11-01 | 285158 | -8351 | 276807 | 276807 | 100% | 0 | 0 | 0 | 37070.54 | -1085.64 | 35984.8966 | 0.003443 | 0 | Completed in 2004. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNEP | Implementation of the RMP: policy dialogue programme on complementary policy and enforcement | Individual | LAC | PAR | REF | 32 | TAS | 10 | A | I | CFC | 3.4 | 3.4 | 0 | 0 | 2000-12-01 | 2004-01-01 | 2001-09-01 |  | 2008-12-01 | 2009-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0
FIN | UNEP | Implementation of the RMP: train of trainers and training of refrigeration service technicians | Individual | LAC | PAR | REF | 32 | TRA | 07 | A | I | CFC | 56.7 | 56.7 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-12-01 |  | 2008-12-01 | 2012-01-01 | 168020 | -2569 | 165451 | 165451 | 100% | 0 | 0 |  | 21843 | -333.97 | 21509.03 | 0 | 0
FIN | UNDP | Project preparation in the commercial refrigeration sector | Individual | LAC | PAR | REF | 33 | PRP | 11 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Terminal umbrella project to phase out CFC-11 and CFC-12 consumption in the manufacture of commercial refrigeration equipment by replacement with HCFC-141b and HFC-134a at 11 SMEs | Individual | LAC | PAR | REF | 34 | INV | 12 | A | I | CFC | 7.4 | 7.4 | 0 | 0 | 2001-07-01 | 2001-11-01 | 2005-02-01 |  | 2005-12-01 | 2007-03-01 | 410379 | -27448 | 382931 | 382931 | 100% | 0 | 0 | 0 | 53349.27 | -3568.22 | 49781.0481 | 0.0019 | 0 | Completed in 2005. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNEP | Country programme preparation | Individual | LAC | PAR | SEV | 17 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-09-01 | 1996-10-01 |  | 1996-10-01 | 1999-05-01 | 43000 | -4000 | 39000 | 39000 | 100% | 0 | 0 |  | 5590 | -520 | 5070 | 0 | 0
FIN | UNEP | Institutional strengthening | Individual | LAC | PAR | SEV | 21 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-06-01 | 2000-02-01 |  | 2001-07-01 | 2001-12-01 | 66300 | 0 | 66300 | 66300 | 100% | 0 | 0 |  | 8619 | 0 | 8619 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening | Individual | LAC | PAR | SEV | 32 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-07-01 | 2003-01-01 |  | 2003-01-01 | 2004-09-01 | 44200 | 0 | 44200 | 44200 | 100% | 0 | 0 |  | 5746 | 0 | 5746 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase 3) | Individual | LAC | PAR | SEV | 39 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2004-01-01 | 2005-04-01 |  | 2009-07-01 | 2010-12-01 | 57460 | 0 | 57460 | 57460 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | LAC | PAR | SEV | 53 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-12-01 | 2009-11-01 |  | 2011-12-01 | 2013-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase V) | Individual | LAC | PAR | SEV | 61 | INS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-02-01 | 2012-06-01 |  | 2013-03-01 | 2015-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of institutional strengthening project (phase VI: 7/2012-6/2014) | Individual | LAC | PAR | SEV | 66 | INS | 30 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 | 2012-12-01 | 2014-06-01 |  | 2014-06-01 |  | 60000 | 0 | 60000 | 45082.17 | 75.14% | 14917.83 | 0 | 14918 | 0 | 0 | 0 | 0 | 0 | Project Completed in December 2014. All funds disbursed. NOO submitted all progress and financial report. Cross checking of accounts between UNON and UNDP failed. The Inter Office Voucher (from UNDP) was charged to an incorrect budget line. Reversal of expenditure is pending. | UNEP is awaiting for UNDP Clearance Account to close this project's account.
ONG | UNEP | Extension of institutional strengthening project (phase VII: 7/2014-6/2016) | Individual | LAC | PAR | SEV | 72 | INS | 31 | A | I |  | 0 |  | 0 |  | 2014-05-01 | 2014-12-01 | 2016-06-01 | 2017-07-01 |  |  | 60000 | 0 | 60000 | 24333.51 | 40.56% | 35666.49 | 13296.27 | 3566.649 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): SSFA (agreement) implementation is progressing with minor delays. Second and third cash advances released respectively in February and November 2016. 100% of total project budget has been transferred to the country. Legal arrangements (actual/planned): April 2015/October 2014. Initial stages of project implementation (actual/planned): N/A since Project currently ongoing as planned. Intermediate goals achieved (actual/planned): Goals achieved as planned for the year. Intermediate goals achieved as planned for the year 2016: NOO has been collecting ODS data and cross-checking information to prepare the 2015 Country Programme and Article 7 reports. The HCFCs license system continues being managed by the NOU. NOU is responsible of the HPMP implementation. Project completion and follow up: Project ongoing First disbursement date (actual/planned): May 2015/November 2015. All funds disbursed? (yes/no): No. Any delay? (yes/no): 6 months of delays. If Yes, will delay have impact on project completion date? (yes/no): Yes. Any ongoing problems? (yes/no): No. If Yes, is any action required by ExCom? N/A. | Brief progress report (actual/planned): SSFA (agreement) implementation is progressing with minor delays. Legal arrangements (actual/planned): April 2015/October 2014. Initial stages of project implementation (actual/planned): N/A since Project currently ongoing as planned. Intermediate goals achieved (actual/planned): Goals achieved as planned for the year. Intermediate goals achieved as planned for the year 2017: NOO has been collecting ODS data and cross-checking information to prepare the 2016 Country Programme and Article 7 reports. The HCFCs license system continues being managed by the NOU. NOU is responsible of the HPMP implementation. Project completion and follow up: Project ongoing. UNEP is waiting for final progress report and financial statement to close project accounts .UNEP is awaiting for final progress report and finnancial statement. First disbursement date (actual/planned): May 2015/November 2015. All funds disbursed? (yes/no): No. Any delay? (yes/no): 6 months of delays. If Yes, will delay have impact on project completion date? (yes/no): Yes. Any ongoing problems? (yes/no): No. If Yes, is any action required by ExCom? N/A.
ONG | UNDP | Survey of ODS alternatives at the national level | Individual | LAC | PAR | SEV | 75 | TAS | 35 | N | I | HCFC | 0 | 0 | 0 | 0 | 2015-11-01 | 2016-06-01 | 2016-12-01 | 2017-02-01 |  |  | 70000 | 0 | 70000 | 33073.55 | 47.25% | 36926.45 | 0 | 14770.58 | 6300 | 0 | 2976.6195 | 3323.3805 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Project team hired. Methodology for conducting the survey was discussed and approved. Survey conducted and draft report prepared. Prodoc signed (actual/planned, yes/no and date):Yes, on May 2016. Missions undertaken (actual/planned):1 of 1 TOR for consultants/subcontracts completed (actual/planned): 3 of 3 Contract/PO/MOA agreements signed: 3 of 3 First disbursement date (actual/planned): 42522Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve:N/A | Final report prepared. Excel tables with survey results completed and submitted. | 2015 |  | Non-Investment
ONG | UNEP | Extension of institutional strengthening project (phase VIII: 1/2017-12/2018) | Individual | LAC | PAR | SEV | 77 | INS | 36 | A | I |  | 0 |  | 0 |  | 2016-12-01 |  | 2018-12-01 | 2019-06-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | Newly approved project | Brief progress report: Annual implementation plan drafted. Legal arrangement (actual/planned): to be signed in April 2017/initially planned for February 2017. Initial stages of project implementation (actual/planned): In progress. Intermediate goals achieved (actual/planned): N/A. Project completion and follow up: N/A. First disbursement date (actual/planned): None/May 2017. All funds disbursed? (yes/no): No. Any delay? (yes/no): Minor delays in signature of the agreement that would not affect the project implementation timetable. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date? (yes/no): No. Any ongoing problems? (yes/no): No. If Yes, is any action required by ExCom? N/A.
FIN | UNDP | Technical assistance for the phase-out of ODSs in the solvent sector | Individual | LAC | PAR | SOL | 45 | TAS | 14 | N | I | TCA/CTC | 2.4 | 2.4 | 0 | 0 | 2005-04-01 | 2006-04-01 | 2006-12-01 |  | 2008-12-01 | 2012-07-01 | 30000 | -106.51 | 29893.49 | 29893 | 100% | 0.49 | 0 | 0 | 2700 | -9.59 | 2690.37 | 0.04 | 0 | Financially completed in 2012. |  | 2005 | 2008-01-01 | Non-Investment
FIN | UNDP | Elimination of CFC-12 in the production of polystyrene foam at Productos Moldeados America SR, Ltd. (Promola) | Individual | LAC | PER | FOA | 17 | INV | 09 | A | D | CFC | 40 | 40 | 0 | 0 | 1995-07-01 | 1996-09-01 | 1996-07-01 |  | 1998-11-01 | 1999-12-01 | 294960 | 0 | 294960 | 294960 | 100% | 0 | 0 | 0 | 38344.8 | 0 | 38344.8 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1995 |  | Investment
FIN | UNDP | Preparation of a project in general foam subsector | Individual | LAC | PER | FOA | 27 | PRP | 24 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2001-12-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1999 |  | Investment
FIN | UNDP | Project preparation in the flexible polyurethane foam sector | Individual | LAC | PER | FOA | 33 | PRP | 29 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 650 | 0 | 650 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Foam sector ODS phaseout plan (covering 5 enterprises: Molflex; Zetaflex; EMSA; Metusa; Polishoes) | Individual | LAC | PER | FOA | 35 | INV | 30 | A | I | CFC | 33.8 | 33.8 | 0 | 0 | 2001-12-01 | 2002-10-01 | 2005-01-01 |  | 2006-12-01 | 2008-04-01 | 325277 | 0 | 325277 | 325277 | 100% | 0 | 0 | 0 | 42286.01 | 0 | 42286.01 | 0 | 0 | Completed in 2006. Financially completed in 2008. |  | 2001 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | LAC | PER | FOA | 57 | PRP | 43 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-04-01 | 2010-03-01 |  | 2013-08-01 | 2014-02-01 | 80000 | -26166 | 53834 | 53834 | 100% | 0 | 0 | 0 | 6000 | -1962.45 | 4037.55 | 0 | 0 | Financially completed in 2014. | Completed in 2013. Funds returned to the ExCom | 2009 |  | Investment
FIN | UNDP | Project preparation for a methyl bromide alternative demonstration project | Individual | LAC | PER | FUM | 24 | PRP | 22 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 2000-06-01 | 2002-12-01 | 25000 | -863 | 24137 | 24137 | 100% | 0 | 0 | 0 | 3250 | -112.19 | 3137.81 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Phase-out of methyl bromide in soil fumigation | One-off-Phaseout | LAC | PER | FUM | 31 | INV | 28 | N | I | MeBr | 4 | 4 | 0 | 0 | 2000-07-01 | 2001-03-01 | 2003-08-01 |  | 2004-12-01 | 2006-11-01 | 209770 | 0 | 209770 | 209770 | 100% | 0 | 0 | 0 | 27270.1 | 0 | 27270.1 | 0 | 0 | Completed in 2004. Financially completed in 2006. |  | 2000 |  | Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | LAC | PER | PHA | 50 | PRP | 38 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-11-01 | 2007-11-01 |  | 2009-03-01 | 2010-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | LAC | PER | PHA | 50 | PRP | 39 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2007-11-01 |  | 2007-12-01 | 2010-01-01 | 15000 | -2400 | 12600 | 12600 | 100% | 0 | 0 | 0 | 1125 | -180 | 945 | 0 | 0 | Financially completed in 2010. |  | 2006 |  | Investment
TRF | UNDP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-year | LAC | PER | PHA | 55 | INV | 41 | N | I | CFC | 0 | 0 | 0 | 0 | 2008-07-01 |  | 2010-12-01 |  |  | 2011-07-01 | 183500 | -183500 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 13763 | -13763 | 0 | 0 | 0 | TPMP transferred to UNIDO. | TPMP transferred to UNIDO. | 2008 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | PER | PHA | 55 | PRP | 40 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-05-01 | 2009-07-01 |  | 2012-12-01 | 2014-03-01 | 150000 | -28052 | 121948 | 121948 | 100% | 0 | 0 | 0 | 11250 | -2104 | 9146 | 0 | 0 | Financially completed in 2014. | Completed in 2012. Expert mission to take place in April 2013 to discuss pending approval of quota system for HCFCs. UNDP prodoc has been prepared. | 2008 |  | Investment
FIN | UNEP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | PER | PHA | 55 | TAS | 42 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-05-01 | 2010-12-01 |  | 2013-12-01 | 2013-12-01 | 77500 | -41234 | 36266 | 36266 | 100% | 0 | 0 |  | 10075 | -5360.42 | 4714.58 | 0 | 0
FIN | UNIDO | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | PER | PHA | 65 | INV | 44 | A | I | CFC | 15 | 15 |  |  | 2011-11-01 | 2012-01-01 | 2012-12-31 |  | 2014-04-15 | 2015-03-01 | 183500 | -73 | 183427 | 183426.83 | 100% | 0.17 | 0 |  | 13763 | -5 | 13757 | 1 | 0 | FIN |  |  |  | INV
COM | UNDP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing) | Multi-Year | LAC | PER | PHA | 68 | INV | 46 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-12-01 | 2015-08-01 | 2014-12-01 |  | 2016-05-01 |  | 108000 | 0 | 108000 | 108000 | 100% | 0 | 0 | 0 | 9720 | 0 | 9720 | 0 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Equipment purchase was completed in 2016. Prodoc signed (actual/planned, yes/no and date):Yes, on August 2015 Missions undertaken (actual/planned):0 of 0 TOR for consultants/subcontracts completed (actual/planned): 1 of 1 Contract/PO/MOA agreements signed: 0 of 0 First disbursement date (actual/planned): Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:Changes in Government personnel have caused delays on the implementation of the project. The Project has offered technical assistance through a consultant which has allowed the project to revcover some time. | In January 2017 equipment and tools was delivered at National training facilities. | 2012 |  | Investment
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing) | Multi-Year | LAC | PER | PHA | 68 | TAS | 47 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 |  | 2013-12-01 | 2017-07-01 |  |  | 25000 | 0 | 25000 | 0 | 0% | 25000 | 0 | 2500 | 3250 | 0 | 0 | 3250 | 0 | Brief Progress: (1st and 2nd Tranches are being implemented jointly to maximize results) Procurement process for multi-refrigerant identifiers is in progress and purchase order expected to be issued in June 2017. Consultations with the private sector on the ban of the use of HCFC-141b for flushing as took place. Legal Advisor was recruited and is supporting GOV to establish the ban. Legal Arrangements: direct execution, no need for SSFA. First mission (actual/planned): July 2013 / November 2012. TOR completed (actual/planned): 2/2. First disbursement date (actual/planned): no actual / Planned for Oct 2013 - All funds disbursed (yes/no): No. Any delay? (yes/no): Yes - If Yes, reasons for delay & action plan to resolve: delayes were reported in 2015 and these were incorporated in the new Agreement approved at the 75th ExCom. --- If Yes, will delay have impact on project completion date (yes/no): Yes. Any ongoing problems (yes/no): No - If Yes, is any action required by ExCom: No. | Brief Progress: 2017 HCFCs Quota System issued. No quota for bulk HCFC-141b was allowed (ban being executed). Technical Advisor being recruited to support implementation on HCFC-22 phase-out issues and replacement for flammable refrigerants. Legal Arrangements: direct execution, no need for SSFA. First mission (actual/planned): July 2013 / November 2012. TOR completed (actual/planned): 2/2. First disbursement date (actual/planned): Estimated for May 2017 / Planned for Oct 2013 - All funds disbursed (yes/no): No. Any delay? (yes/no): Yes - If Yes, reasons for delay & action plan to resolve: delays were reported in 2015 and these were incorporated in the new Agreement approved at the 75th ExCom. --- If Yes, will delay have impact on project completion date (yes/no): Yes. Any ongoing problems (yes/no): No - If Yes, is any action required by ExCom: No.
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | Multi-year | LAC | PER | PHA | 75 | INV | 48 | N | I | HCFC | 2.2 | 0 | 0 | 0 | 2015-11-01 | 2016-05-01 | 2017-11-01 | 2017-11-01 |  |  | 100000 | 0 | 100000 | 66909.59 | 66.91% | 33090.41 | 0 | 13236.164 | 9000 | 0 | 6021.8631 | 2978.1369 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Over 150 technicians were received training in best practices by national and international consultants. Prodoc signed (actual/planned, yes/no and date):Yes, on August 2015 Missions undertaken (actual/planned):5 of 5 TOR for consultants/subcontracts completed (actual/planned): 2 of 2 Contract/PO/MOA agreements signed: 0 of 0 First disbursement date (actual/planned): Any delays/problems (yes/no):Yes. If Yes, reasons for delay & action plan to resolve:Changes in Government personnel have caused delays on the implementation of the project. The Project has offered technical assistance through a consultant which has allowed the project to revcover some time. | Trainings continue throughout 2017 on the use of alternatives to HCFC141b for fushing | 2015 |  | Investment
ONG | UNDP | Preparation of a HCFC phase-out management plan (stage II) | Individual | LAC | PER | PHA | 75 | PRP | 51 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2015-11-01 |  | 2017-11-01 | 2017-11-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 24000 | 4200 | 0 | 0 | 4200 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): A consultant was hired for the development of the HPMP Phase II. Information gathering began. Prodoc signed (actual/planned, yes/no and date):N/A Missions undertaken (actual/planned):1 of 1 TOR for consultants/subcontracts completed (actual/planned): 1 of 1 Contract/PO/MOA agreements signed: 0 of 0 First disbursement date (actual/planned): Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:The start up of the preparation process has taken more time than what was originally anticipated. | A local consultant has been hired in 2017 for revision and validation of data for the phase II which will be finalized by May 2017 and presented at the November meeting | 2015 |  | Non-Investment
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | Multi-year | LAC | PER | PHA | 75 | TAS | 49 | A | I |  | 0.5 |  | 0 |  | 2015-11-01 |  | 2016-12-01 | 2018-06-01 |  |  | 20000 | 0 | 20000 | 0 | 0% | 20000 | 0 | 2000 | 2600 | 0 | 0 | 2600 | 0 | Brief Progress: (1st and 2nd Tranches are being implemented jointly to maximize results) Procurement process for multi-refrigerant identifiers is in progress and purchase order expected to be issued in June 2017. Consultations with the private sector aonthe ban on the use of HCFC-141b for flushing as took place. Legal Advisor was recruited and is supporting GOV to establish the ban. Legal Arrangements: direct execution, no need for SSFA. First mission (actual/planned): July 2013 / November 2012. TOR completed(actual/planned): 2/2. First disbursement date (actual/planned): no actual / Planned for Oct 2013 - All funds disbursed (yes/no): No. Any delay? (yes/no): Yes - If Yes, reasons for delay & action plan to resolve: delays were reported in 2015 and these were incorporated in the new Agreement approved at the 75th ExCom. --- If Yes, will delay have impact on project completion date (yes/no): Yes. Any ongoing problems (yes/no): No - If Yes, is any action required by ExCom: No. | Brief Progress: 2017 HCFCs Quota System issued. No quota for bulk HCFC-141b was allowed (ban being executed). Technical Advisor being recruited to support implementation on HCFC-22 phase-out issues and replacement for flammable refrigerants. Legal Arrangements: direct execution, no need for SSFA. First mission (actual/planned): July 2013 / November 2012. TOR completed (actual/planned): 2/2. First disbursement date (actual/planned): Estimated for June 2017/ Planned for Oct 2013 - All funds disbursed (yes/no): No. Any delay? (yes/no): Yes - If Yes, reasons for delay & action plan to resolve: delays were reported in 2015 and these were incorporated in the new Agreement approved at the 75th ExCom. --- If Yes, will delay have impact on project completion date (yes/no): Yes. Any ongoing problems (yes/no): No - If Yes, is any action required by ExCom: No.
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Industrias Alfa S.A. | Individual | LAC | PER | REF | 15 | INV | 03 | A | I | CFC | 7 | 7 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  | 1999-09-01 | 2000-12-01 | 252727 | -567 | 252160 | 252160 | 100% | 0 | 0 | 0 | 32854.51 | -73.71 | 32780.8 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1994 | 1999-02-01 | Investment
CLO | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Andina Industrial S.A. | Individual | LAC | PER | REF | 15 | INV | 04 | A | I | CFC | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  |  | 2002-06-01 | 229816 | -75350 | 154466 | 154466 | 100% | 0 | 0 | 0 | 29876.08 | -9795 | 20081.08 | 0 | 0 | Canceled in 2000. Financially completed in 2002. |  | 1994 | 1997-09-01 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Coldex S.A. | Individual | LAC | PER | REF | 15 | INV | 05 | A | I | CFC | 67.4 | 67.4 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  | 1998-01-01 | 2000-12-01 | 748966 | -102197 | 646769 | 646769 | 100% | 0 | 0 | 0 | 97365.58 | -13285.61 | 84079.97 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Industrias Lenche S.A. (Inlensa) | Individual | LAC | PER | REF | 15 | INV | 06 | A | I | CFC | 6 | 6 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  | 2002-09-01 | 2003-11-01 | 201443 | -29670 | 171773 | 171773 | 100% | 0 | 0 | 0 | 26187.59 | -3857.1 | 22330.49 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1994 | 1997-12-01 | Investment
CLO | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Industrias Reunidas S.A. (Inresa) | Individual | LAC | PER | REF | 15 | INV | 07 | A | D | CFC | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-12-01 | 1996-06-01 |  |  | 2003-01-01 | 267641 | -91077 | 176564 | 176564 | 100% | 0 | 0 | 0 | 34793.33 | -11840 | 22953.33 | 0 | 0 | Canceled in 1999. Financially completed in 2003. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Industrial Selva S.A. (Indusel) | Individual | LAC | PER | REF | 15 | INV | 08 | A | I | CFC | 34.9 | 34.9 | 0 | 0 | 1994-12-01 | 1995-11-01 | 1996-06-01 |  | 1999-12-01 | 2002-03-01 | 412098 | -331 | 411767 | 411767 | 100% | 0 | 0 | 0 | 53572.74 | -43.03 | 53529.71 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of chest freezers at Master Service, S.A. | Individual | LAC | PER | REF | 19 | INV | 13 | A | I | CFC | 9.4 | 9.4 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  | 1999-02-01 | 2002-04-01 | 140000 | -10839 | 129161 | 129161 | 100% | 0 | 0 | 0 | 18200 | -1409.07 | 16790.93 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1996 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of chest feezers at Compañia Peruana de Máquinas para Coser S.A. (Copemaco) | Individual | LAC | PER | REF | 19 | INV | 14 | A | I | CFC | 12.9 | 12.9 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  | 1999-12-01 | 2001-12-01 | 193834 | 0 | 193834 | 193834 | 100% | 0 | 0 | 0 | 25198.42 | 0 | 25198.42 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1996 |  | Investment
CLO | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of chest freezers and refrigerators at Formetal | Individual | LAC | PER | REF | 19 | INV | 15 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  |  | 2001-12-01 | 118000 | -64335 | 53665 | 53665 | 100% | 0 | 0 | 0 | 15340 | -8363.55 | 6976.45 | 0 | 0 | Canceled in 1999. Financially completed in 2001. |  | 1996 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of chest freezers at Col-Frio S.A. | Individual | LAC | PER | REF | 19 | INV | 16 | A | I | CFC | 11.7 | 11.7 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1999-12-01 | 2001-12-01 | 175000 | -468 | 174532 | 174532 | 100% | 0 | 0 | 0 | 22750 | -60.86 | 22689.1412 | -0.0012 | 0 | Completed in 1999. Financially completed in 2001. |  | 1996 |  | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | PER | REF | 19 | TAS | 17 | A | I | CFC | 28.6 | 28.6 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 2001-12-01 | 2003-04-01 | 342695 | -53108 | 289587 | 289587 | 100% | 0 | 0 | 0 | 44550.35 | -6904.04 | 37646.31 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1996 | 1999-12-01 | Investment
FIN | UNEP | National train the trainer programme on refrigeration management plan and good practices in refrigeration | Individual | LAC | PER | REF | 21 | TRA | 21 | A | I | CFC | 44.8 | 44.8 | 0 | 0 | 1997-02-01 | 1997-04-01 | 1999-02-01 |  | 2002-12-01 | 2003-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0
FIN | UNEP | Implementation of the RMP: support for a licensing system | Individual | LAC | PER | REF | 27 | TAS | 25 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-10-01 | 2000-10-01 |  | 2002-02-01 | 2003-06-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0
FIN | UNEP | Implementation of the RMP: code of good practices in refrigeration | Individual | LAC | PER | REF | 27 | TAS | 26 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-12-01 | 2000-10-01 |  | 2002-02-01 | 2003-07-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0
FIN | UNEP | Implementation of the RMP: custom officers training programme | Individual | LAC | PER | REF | 27 | TRA | 23 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-10-01 | 2000-10-01 |  | 2004-05-01 | 2005-12-01 | 34000 | -13000 | 21000 | 21000 | 100% | 0 | 0 |  | 4420 | -1690 | 2730 | 0 | 0 |  |  |  | 2001-12-01
FIN | UNEP | Preparation of the refrigerant management plan update proposal | RMP Update | LAC | PER | REF | 37 | PRP | 32 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2004-02-01 | 2003-08-01 |  | 2004-07-01 | 2008-12-01 | 15000 | -3000 | 12000 | 12000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNDP | Formulation of the investment components of the RMP | Individual | LAC | PER | REF | 39 | PRP | 33 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2005-12-01 | 2006-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1125 | 0 | 1125 | 0 | 0 | Completed in 2005. Financially completed in 2006. |  | 2003 |  | Investment
FIN | UNEP | Implementation of the RMP update: monitoring of the activities in the RMP | Individual | LAC | PER | REF | 43 | TAS | 34 | A | I | CFC | 30.9 | 0 | 0 | 0 | 2004-07-01 | 2005-02-01 | 2007-12-01 |  | 2011-10-01 | 2012-10-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNEP | Implementation of the RMP update: refrigeration technicians certification and licensing system | Individual | LAC | PER | REF | 43 | TAS | 35 | A | I | CFC | 66.4 | 66.4 | 0 | 0 | 2004-07-01 | 2007-09-01 | 2007-12-01 |  | 2009-12-01 | 2011-03-01 | 86000 | 0 | 86000 | 86000 | 100% | 0 | 0 |  | 11180 | 0 | 11180 | 0 | 0
FIN | UNEP | Implementation of the RMP update: technical assistance for prevention of illegal CFC trade | Individual | LAC | PER | REF | 43 | TAS | 36 | A | I | CFC | 20.1 | 20.1 | 0 | 0 | 2004-07-01 | 2007-09-01 | 2007-12-01 |  | 2010-06-01 | 2011-03-01 | 26000 | 0 | 26000 | 26000 | 100% | 0 | 0 |  | 3380 | 0 | 3380 | 0 | 0
FIN | UNDP | Implementation of the RMP update: technical assistance for the refrigeration sector | RMP-Component | LAC | PER | REF | 43 | TAS | 37 | N | I | CFC | 94.9 | 94.9 | 0 | 0 | 2004-07-01 | 2007-02-01 | 2007-12-01 |  | 2009-12-01 | 2011-12-01 | 123000 | -1847.14 | 121152.86 | 121153 | 100% | -0.14 | 0 | 0 | 11070 | -166.24 | 10903.77 | -0.01 | 0 | Completed in 2009. Financially completed in 2011. |  | 2004 |  | Investment
FIN | UNEP | Country programme preparation | Individual | LAC | PER | SEV | 11 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-02-01 | 1995-02-01 |  | 1995-07-01 | 1995-12-01 | 53000 | 0 | 53000 | 53000 | 100% | 0 | 0 |  | 6890 | 0 | 6890 | 0 | 0
FIN | UNDP | Project preparation assistance | Individual | LAC | PER | SEV | 13 | PRP | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-08-01 | 1996-07-01 |  | 1995-09-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Investment
FIN | UNEP | Establishment of the Technical Ozone Office | Individual | LAC | PER | SEV | 17 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-12-01 | 1998-10-01 |  | 2000-08-01 | 2001-08-01 | 154000 | 0 | 154000 | 154000 | 100% | 0 | 0 |  | 20020 | 0 | 20020 | 0 | 0 |  |  |  | 1999-12-01
FIN | UNDP | Project preparation assistance | Individual | LAC | PER | SEV | 18 | PRP | 12 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-03-01 | 1997-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1996. Financially completed in 1997. |  | 1995 |  | Investment
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | LAC | PER | SEV | 29 | INS | 27 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-08-01 | 2001-12-01 |  | 2002-06-01 | 2011-03-01 | 102700 | -30102 | 72598 | 72598 | 100% | 0 | 0 |  | 13351 | -3913 | 9438 | 0 | 0
COM | UNEP | Renewal of institutional strengthening project (Phase 3) | Individual | LAC | PER | SEV | 37 | INS | 31 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2011-06-01 | 2004-08-01 |  | 2016-12-01 |  | 133510 | 0 | 133510 | 133510 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Brief Report: (Phases III and IV incorporated in the same SSFA to maximize implementation). Administrative Assistant recruited. 3 sensitization workshops took place on issues of HCFCs control and HCFCs low GWP replacement. Legal Arrangements: SSFA signed in February 2016 (joint remaining Phase III and IV) First mission (actual/planned): June 2016 / May 2016. TOR completed (actual/planned): 3/3. First disbursement date (actual/planned): May 2016 / March 2016 - All funds disbursed (yes/no): Yes. Project completion and follow up: Project completed due to all expenditures are already recorded and final progress report dully submitted by the Government. Any delay? (yes/no): Yes - If Yes, reasons for delay & action plan to resolve: delays reported in 2015 report. Currently, the project is completed. If Yes, will delay have impact on project completion date (yes/no): Yes Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: No. | Waiting approval of expenditure report in UMOJA before closing of project accounts
ONG | UNEP | Renewal of institutional strengthening project (phase IV: 1/2013-12/2014) | Individual | LAC | PER | SEV | 68 | INS | 45 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2016-05-01 | 2014-12-01 | 2018-06-01 |  |  | 133510 | 0 | 133510 | 3191.29 | 2.39% | 130318.71 | 130318.51 | 13031.871 | 0 | 0 | 0 | 0 | 0 | Brief Report: (Phases III and IV incorporated in the same SSFA to maximize implementation). TOR Awareness Consultant cleared by GOV. Legal Arrangements: SSFA signed in February 2016 (joint remaining Phase III and IV) First mission (actual/planned): June 2016 / May 2016. TOR completed (actual/planned): 3/3. First disbursement date (actual/planned): May 2016 / March 2016 - All funds disbursed (yes/no): No. Any delay? (yes/no): Yes - If Yes, reasons for delay & action plan to resolve: delays reported in 2015 report. Currently, the project is progressing as planned. If Yes, will delay have impact on project completion date (yes/no): Yes Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: No. | Brief Report: (Phases III and IV incorporated in the same SSFA to maximize implementation). Awareness Consultant being recruited. Support being delivered to establish ban on imports for bulk HCFC-141b. 2017 Work Plan prepared. Legal Arrangements: SSFA signed in February 2016 (joint remaining Phase III and IV) First mission (actual/planned): June 2016 / May 2016. TOR completed (actual/planned): 3/3. First disbursement date (actual/planned): May 2016 / March 2016 - All funds disbursed (yes/no): No. Any delay? (yes/no): Yes - If Yes, reasons for delay & action plan to resolve: delays reported in 2015 report. Currently, the project is progressing as planned. If Yes, will delay have impact on project completion date (yes/no): Yes Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: No.
ONG | UNDP | Survey of ODS alternatives at the national level | Individual | LAC | PER | SEV | 75 | TAS | 50 | N | I | HCFC | 0 | 0 | 0 | 0 | 2015-11-01 | 2016-05-01 | 2016-12-01 | 2017-10-01 |  |  | 110000 | 0 | 110000 | 13341.36 | 12.13% | 96658.64 | 4950 | 38663.456 | 9900 | 0 | 1200.7224 | 8699.2776 | 445.5 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): A consultant was hired for the development of the HPMP Phase II. Prodoc signed (actual/planned, yes/no and date):N/A Missions undertaken (actual/planned):0 of 0 TOR for consultants/subcontracts completed (actual/planned): 1 of 1 Contract/PO/MOA agreements signed: 0 of 0 First disbursement date (actual/planned): Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:The start up of the preparation process has taken more time than what was originally anticipated. | The hiring of a team for local support and validation of information has been prepared and will conclude in April. Report expected to be concluded by the end of 2017. | 2015 |  | Non-Investment
FIN | UNIDO | Project preparation assistance in solvent sector | Individual | LAC | PER | SOL | 17 | PRP | 10 | A | I |  | 0 | 0 |  |  | 1995-07-01 | 1996-04-01 | 1996-01-01 |  | 1999-12-01 | 2001-07-01 | 30000 | -8097 | 21903 | 21903 | 100% | 0 | 0 |  | 3900 | -1057 | 2843 | 0 | 0 | FIN |  |  | 1999-01-01
FIN | UNIDO | Elimination of 1,1,1 trichloroethane at Faber Castell | Individual | LAC | PER | SOL | 20 | INV | 18 | A | I | TCA | 0.5 | 0.5 |  |  | 1996-10-01 | 1998-11-01 | 1997-10-01 |  | 1998-09-01 | 2000-12-01 | 16409 | -4827 | 11582 | 11582 | 100% | 0 | 0 |  | 2133 | -630 | 1503 | 0 | 0 | FIN
FIN | UNIDO | Elimination of 1,1,1 trichloroethane at Carbolan | Individual | LAC | PER | SOL | 20 | INV | 19 | A | I | TCA | 0.4 | 0.4 |  |  | 1996-10-01 | 1998-06-01 | 1997-10-01 |  | 1998-12-01 | 2000-12-01 | 31457 | -7307 | 24150 | 24150 | 100% | 0 | 0 |  | 4089 | -954 | 3135 | 0 | 0 | FIN
FIN | UNIDO | Elimination of 1,1,1 trichloroethane at Papeles Industriales | Individual | LAC | PER | SOL | 20 | INV | 20 | A | I | TCA | 0.5 | 0.5 |  |  | 1996-10-01 | 1998-12-01 | 1997-10-01 |  | 1998-12-01 | 2000-12-01 | 47953 | -957 | 46996 | 46996 | 100% | 0 | 0 |  | 6234 | -134 | 6100 | 0 | 0 | FIN
CLO | UNIDO | Preparation of investment project in the aerosol sector | Individual | ASP | PHI | ARS | 27 | PRP | 58 | A | I |  | 0 | 0 |  |  | 1999-03-01 |  | 1999-12-01 |  |  | 2001-07-01 | 25000 | -25000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 3250 | -3250 | 0 | 0 | 0 | CLO
FIN | IBRD | Preparation for pilot demonstration project on ODS waste management and disposal |  | ASP | PHI | DES | 57 | PRP | 85 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2013-12-01 | 2010-12-31 |  | 2014-06-01 | 2014-06-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 3750 | 0 | 3750 | 0 | 0 | A study on 'The Establishment of a Public-Private Financing System for Disposal of ODS for the Philippines' was completed and accepted by the client in June 2014. The report was submitted to the 71st ExCom as an information document. |  |  |  | Non-INV | 0
FIN | UNDP | Elimination of CFC-use at small manufacturers of flexible foam | Individual | ASP | PHI | FOA | 12 | INV | 26 | N | I | CFC | 35 | 35 | 0 | 0 | 1994-03-01 | 1995-07-01 | 1995-03-01 |  | 1999-12-01 | 2003-04-01 | 745000 | -262154 | 482846 | 482846 | 100% | 0 | 0 | 0 | 96850 | -34080.02 | 62769.98 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  | 1994 | 1999-07-01 | Investment
FIN | UNDP | Phase-out of the residual use of CFC in the manufacture of extruded polystyrene foam sheet in 3 companies: Concept Packaging Co., Amtes Co., and Q.C. Styropackaging Co. | Individual | ASP | PHI | FOA | 12 | INV | 27 | A | I | CFC | 24 | 24 | 0 | 0 | 1994-03-01 | 1994-12-01 | 1995-03-01 |  | 1997-12-01 | 1999-05-01 | 505000 | -230578 | 274422 | 274422 | 100% | 0 | 0 | 0 | 65650 | -29975.14 | 35674.86 | 0 | 0 | Completed in 1997. Financially completed in 1999. |  | 1994 |  | Investment
FIN | UNDP | Phase-out of the use of CFC in the manufacture of rigid PUF for thermoware at Nikkon Industrial Corporation | Individual | ASP | PHI | FOA | 12 | INV | 28 | A | I | CFC | 15 | 15 | 0 | 0 | 1994-03-01 | 1995-03-01 | 1995-03-01 |  | 1995-09-01 | 1998-12-01 | 315000 | -46523 | 268477 | 268477 | 100% | 0 | 0 | 0 | 40950 | -6048 | 34902 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Phase out of CFC in the manufacture of flexible polyurethane foam at Foamcraft Incorporated | Individual | ASP | PHI | FOA | 13 | INV | 31 | A | I | CFC | 90 | 90 | 0 | 0 | 1994-07-01 | 1995-04-01 | 1995-07-01 |  | 1998-05-01 | 2001-12-01 | 185000 | -19094.3 | 165905.7 | 165906 | 100% | -0.3 | 0 | 0 | 24050 | -2482.26 | 21567.78 | -0.04 | 0 | Completed in 1998. Financially completed in 2001. |  | 1994 |  | Investment
FIN | UNDP | Phase out of CFC in the manufacture of polyurethane insulated building elements at Metal Forming Co. | Individual | ASP | PHI | FOA | 13 | INV | 32 | A | I | CFC | 50 | 50 | 0 | 0 | 1994-07-01 | 1995-04-01 | 1995-06-01 |  | 1997-12-01 | 2000-12-01 | 305000 | -16698 | 288302 | 288302 | 100% | 0 | 0 | 0 | 39650 | -2170.74 | 37479.26 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of the residual use of CFC in the manufacture of extruded polystyrene foam sheet at Styrotech Co. | Individual | ASP | PHI | FOA | 13 | INV | 34 | A | I | CFC | 25 | 25 | 0 | 0 | 1994-07-01 | 1994-12-01 | 1995-06-01 |  | 1997-12-01 | 2000-12-01 | 60000 | -2296.7 | 57703.3 | 57703 | 100% | 0.3 | 0 | 0 | 7800 | -298.57 | 7501.39 | 0.04 | 0 | Completed in 1997. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Residual phaseout of CFCs in the manufacture of flexible polyurethane (slabstock) at Mandaue Foam Industries Inc. | Individual | ASP | PHI | FOA | 17 | INV | 37 | A | I | CFC | 80 | 80 | 0 | 0 | 1995-07-01 | 1995-08-01 | 1996-12-01 |  | 1997-06-01 | 2000-07-01 | 217000 | -9332 | 207668 | 207668 | 100% | 0 | 0 | 0 | 28210 | -1213.16 | 26996.84 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Residual phaseout of CFCs in the manufacture of PUF foam at RGC Foam Group (Polyfoam/Uratex) | Individual | ASP | PHI | FOA | 18 | INV | 62 | A | I | CFC | 70 | 70 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1997-05-01 |  | 1997-06-01 | 2000-07-01 | 650000 | -3624 | 646376 | 646376 | 100% | 0 | 0 | 0 | 84500 | -471 | 84029 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Phaseout of the use of CFCs in the manufacture of PU foam for insulation and structural purposes at Himalaya Mfg. Corp. | Individual | ASP | PHI | FOA | 19 | INV | 43 | A | D | CFC | 17 | 17 | 0 | 0 | 1996-05-01 | 1996-09-01 | 1997-05-01 |  | 1996-09-01 | 2000-12-01 | 101000 | -4879 | 96121 | 96121 | 100% | 0 | 0 | 0 | 13130 | -634 | 12496 | 0 | 0 | Completed in 1996. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at PU Rigid Insulation Contractor | Individual | ASP | PHI | FOA | 22 | INV | 48 | N | I | CFC | 24.2 | 24.2 | 0 | 0 | 1997-05-01 | 1998-09-01 | 1999-06-01 |  | 1999-12-01 | 2003-11-01 | 189290 | -14221 | 175069 | 175069 | 100% | 0 | 0 | 0 | 24607.7 | -1848.73 | 22758.97 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at MBA Urethane Products Contractor | Individual | ASP | PHI | FOA | 22 | INV | 50 | N | I | CFC | 14.5 | 14.5 | 0 | 0 | 1997-05-01 | 1998-01-01 | 1999-06-01 |  | 1999-12-01 | 2003-08-01 | 113574 | -22017 | 91557 | 91557 | 100% | 0 | 0 | 0 | 14764.62 | -2862.21 | 11902.41 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of polyurethane foam at Soutech | Individual | ASP | PHI | FOA | 23 | INV | 51 | N | I | CFC | 20 | 20 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1999-12-01 |  | 1999-12-01 | 2003-04-01 | 326750 | -1799 | 324951 | 324951 | 100% | 0 | 0 | 0 | 42477.5 | -233.87 | 42243.63 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Umbrella project: Conversion to CFC-free technology in small CFC consuming enterprises using CFC in the manufacture of rigid polyurethane foam (Ashlar Industrial Corporation, Alen International, Zegal | Individual | ASP | PHI | FOA | 23 | INV | 52 | N | I | CFC | 5.1 | 5.1 | 0 | 0 | 1997-11-01 | 1998-06-01 | 1999-12-01 |  | 2000-12-01 | 2003-04-01 | 39930 | -13985 | 25945 | 25945 | 100% | 0 | 0 | 0 | 5190.9 | -1818.05 | 3372.85 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Preparation of a project in the flexible foam subsector | Individual | ASP | PHI | FOA | 30 | PRP | 60 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-04-01 | 2003-01-01 | 15000 | -3090.84 | 11909.16 | 11909 | 100% | 0.16 | 0 | 0 | 1950 | -401.45 | 1548.534 | 0.015979 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture or rigid polyurethane foam (sprayfoam) at Prescon Construction and Development | Individual | ASP | PHI | FOA | 31 | INV | 64 | N | I | CFC | 31.7 | 31.7 | 0 | 0 | 2000-07-01 | 2001-07-01 | 2002-10-01 |  | 2002-09-01 | 2005-04-01 | 187926 | -25246 | 162680 | 162680 | 100% | 0 | 0 | 0 | 24430.38 | -3282 | 21148.38 | 0 | 0 | Completed in 2002. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNIDO | Preparation for HCFC phase-out investment activities (foam sector) | Individual | ASP | PHI | FOA | 59 | PRP | 86 | A | I |  | 0 | 0 |  |  | 2009-11-01 | 2009-12-01 | 2010-11-30 |  | 2010-12-01 | 2012-04-01 | 70000 | -5751 | 64249 | 64249.09 | 100% | -0.09 | 0 |  | 5250 | -431 | 4819 | 0 | 0 | FIN |  |  |  | NON-INV
COM | UNIDO | Sector plan to phase out HCFC-141b in the foam sector | Multi-Year | ASP | PHI | FOA | 62 | INV | 90 | A | I | HCFC | 40 | 40 |  |  | 2010-12-01 | 2010-12-01 | 2012-12-31 |  | 2015-12-01 |  | 1770650 | 0 | 1770650 | 1713422.95 | 96.77% | 57227.05 | 15953.04 | 1 | 132799 | 0 | 128507 | 4292 | 1196 | The project was operationally completed. |  |  |  | INV
COM | Japan | Sector plan to phase out HCFC-141b in the foam sector | Individual | ASP | PHI | FOA | 62 | INV | 91 | A | I | HCFC-141b | 0 |  | 0 |  | 2010-12-01 | 2011-06-01 | 2012-12-01 |  | 2015-12-01 |  | 317350 | 0 | 317350 | 309561.06 | 97.55% | 7788.94 | 7960.99 | 7000 | 41256 | 0 | 40242.9378 | 1013.0622 | 1034.9287 | Project completed. | Financial completion is being initiated. | 2010
ONG | IBRD | Preparation for HCFC phase-out investment activities (stage II) (air-conditioning sector) |  | ASP | PHI | FOA | 73 | PRP | 97 | A | I |  | 0 | 0 | 0 | 0 | 2014-11-01 | 2015-12-01 | 2015-12-31 | 2017-06-01 |  |  | 150000 | 0 | 150000 | 2045 | 1.363% | 147955 | 147955 | 100000 | 10500 | 0 | 143.15 | 10356.85 | 10356.85 | Local consulting firm selected and preparation started in Aug 2016. | Stage II HPMP, including the AC sector plan, finalized and submitted to the ExCom on 27 Mar 2017 for consideration at the 79th ExCom Meeting. Upon approval in Jul 17, preparation of WB - Philippines Grant Agreement for AC sector plan and Stage II implementation will be stepped up. |  |  | Non-INV | 0
FIN | UNDP | Project preparation for a methyl bromide alternative demonstration project | Individual | ASP | PHI | FUM | 25 | PRP | 55 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-09-01 | 1999-08-01 |  | 2000-12-01 | 2004-12-01 | 30000 | -358 | 29642 | 29642 | 100% | 0 | 0 | 0 | 3900 | -46.54 | 3853.46 | 0 | 0 | Completed in 2000. Financially completed in 2004. |  | 1998 |  | Investment
FIN | UNDP | Demonstration, training and policy development on alternatives to methyl bromide for banana soil fumigation | Individual | ASP | PHI | FUM | 26 | DEM | 57 | N | I | MeBr | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-07-01 | 2000-12-01 |  | 2003-07-01 | 2003-07-01 | 231000 | -214534 | 16466 | 16466 | 100% | 0 | 0 | 0 | 30030 | -27889 | 2141 | 0 | 0 | Completed in 2003. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organizations in methyl bromide communication | Individual | ASP | PHI | FUM | 30 | TAS | 61 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-12-01 | 25000 | -8880 | 16120 | 16120 | 100% | 0 | 0 |  | 3250 | -1154 | 2096 | 0 | 0
FIN | IBRD | Preparation of a methyl bromide phase-out plan |  | ASP | PHI | FUM | 39 | PRP | 70 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2004-12-01 | 2004-09-01 |  | 2004-09-01 | 2004-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 3750 | 0 | 3750 | 0 | 0 | Meetings and workshops with Fertilizer and Pesticide Authority, a TWG and affected groups prior conducted. MBr consumption survey forwarded to Ozone Secretariat to support country’s request to lift potential non-compliance status. Proposed National MBr Strategy approved at the 45th ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | Technical assistance for a national methyl bromide phase-out strategy | One off phaseout | ASP | PHI | FUM | 44 | TAS | 76 | N | I | MBR | 9 | 9 | 0 | 0 | 2004-12-01 | 2005-12-01 | 2008-12-01 |  | 2010-12-01 | 2010-12-01 | 330000 | 0 | 330000 | 330000 | 100% | 0 | 0 |  | 24750 | 0 | 24750 | 0 | 0 | Project was extended to allow transfer of activities to regular personnel of the implementing agency to ensure sustainability of MB phaseout in non-QPS applications and prevent return of stockholders to use of MB in non-QPS after project completion; facilitate coordination of activities of the FPA and BPI in monitoring QPS use of MB, Administrative Order No. 17 series of 2010 on "Guidelines for the Bureau of Plant Industry and Fertilizer and Pesticides Authority (FPA) on the Implementation of a Logbook System for Methyl Bromide QPS Uses" signed 16 Aug 2010. Regular inspection and monitoring visits conducted in selected regions; follow-thru workshops for database establishment for FPA regions held; verification and on-the-spot inspection of QPS MB consumption also conducted; consumption verification audits for 2008-2009 completed. |  |  |  | INV | 0
FIN | UNDP | Umbrella project for the conversion of production of portable halon fire extinguishers of members companies of Fire Protectors Federation Inc. | Individual | ASP | PHI | HAL | 18 | INV | 38 | N | I | Halon | 77 | 77 | 0 | 0 | 1995-11-01 | 1996-09-01 | 1997-05-01 |  | 2000-09-01 | 2003-04-01 | 114108 | -8935 | 105173 | 105173 | 100% | 0 | 0 | 0 | 14834.04 | -1161.55 | 13672.49 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1995 | 1999-06-01 | Investment
FIN | IBRD | Conversion of tobacco fluffing process to carbon dioxide at Fortune Tobacco corporation | Individual | ASP | PHI | OTH | 09 | INV | 18 | N | I | CFC | 350 | 350 | 0 | 0 | 1993-03-01 | 1996-05-01 | 1995-03-01 |  | 1999-08-01 | 2000-08-01 | 4720000 | -267640 | 4452360 | 4452360 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project fully completed on Dec. 30, 1999. Decommissioning of the G -13 Plant was done from Jan. 10 to May 7, 2000. PCR was endorsed to WB on August 2, 2000. Grant fund fully disbursed. |  |  | 1997-09-01 | INV | 0
FIN | IBRD | Preparation of a national CFC phaseout plan |  | ASP | PHI | PHA | 35 | PRP | 65 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2001-12-31 | 2002-12-01 |  | 2002-11-01 | 2002-11-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0 | Completed. NCPP approved at the 38th ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | National CFC phase out plan: manufacturing sector (first tranche) | Multiyear | ASP | PHI | PHA | 38 | INV | 69 | N | I |  | 89.3 | 89.3 | 0 | 0 | 2002-11-01 | 2003-12-01 | 2003-12-01 |  | 2003-12-01 | 2012-04-01 | 2858473 | 0 | 2858473 | 2858473 | 100% | 0 | 0 |  | 248663 | 0 | 248663 | 0 | 0 | Transfer of $1.8 million balance of the overall NCPP done in Apr 12 by the WB. UNEP will continue as IA for remaining NCPP servicing sector component. |  |  |  | INV | 0
FIN | Sweden | National CFC phase out plan: servicing sector (first tranche) | Multi-Year | ASP | PHI | PHA | 38 | TAS | 68 | A | I |  | 0 |  | 0 |  | 2002-11-01 | 2003-02-01 | 2003-12-01 |  | 2005-12-01 | 2012-04-01 | 152400 | 0 | 152400 | 152400 | 100% | 0 |  |  | 11316 | 0 | 11316 | 0 | 0 | The original plan to establish a functioning Reclamation Facility in partnership with PARII was deemed not financially-viable and economically-feasible by PARII due to low amounts of reclaimable refrigerants from the servicing sector. Hence, an alternative model to establish an ODS management plan, including the collection, transport, and storage of recovered refrigerants and unwanted ODS was proposed by the PMU and included in the 2010-2011 Biennual Plan of the NCPP approved at the 60th ExCom Meeting. Procurement and selection process for equipment which complements that already procured under the reclamation scheme, as well as for contractors for ODS collection, transport and storage was not completed until 2010. Delsa Chemicals and Multi-Products Inc (DCMI), a member of PARII, the refrigerant importer association, was the contractor selected for the collection, transport and storage of recovered refrigerants for the NCPP and has completed its work in 2011. Overall NCPP closed by the WB in Jun 2011. Reconciliation of the account indicate a total savings of US$114,046.05 for the Swedish component because disbursement for some activities under Sweden was posted under the overall NCPP under the WB instead. | Financial completion of the NCPP under the WB occurred on Apr. 12 upon return of the balance of the funds to the 66th ExCom. | 2002
FIN | IBRD | National CFC phase-out plan (manufacturing sector): 2004 annual programme | Multiyear | ASP | PHI | PHA | 41 | INV | 71 | N | I | CFC | 150 | 150 | 0 | 0 | 2003-12-01 | 2005-12-01 | 2004-12-01 |  | 2004-12-01 | 2012-04-01 | 1877418 | -23495 | 1853923 | 1853923 | 100% | 0 | 0 |  | 160968 | -2014 | 158953.56 | 0.44 | 0.44 | Transfer of $1.8 million balance of the overall NCPP done in Apr 12 by the WB. UNEP will continue as IA for remaining NCPP servicing sector component. |  |  |  | INV | 0
FIN | Sweden | National CFC phase-out plan servicing sector: 2004 annual programme | Multi-Year | ASP | PHI | PHA | 41 | TAS | 72 | A | I |  | 0 |  | 0 |  | 2003-12-01 | 2004-07-01 | 2004-12-01 |  | 2011-11-01 | 2012-04-01 | 166134 | -114046 | 52088 | 52088 | 100% | 0 | 0 | 0 | 12952 | 0 | 12952 | 0 | 0 | See remarks above. | See remarks above. | 2003 | 2006-12-01
FIN | IBRD | National CFC phase-out plan: 2005 annual programme | Multiyear | ASP | PHI | PHA | 44 | INV | 75 | N | I | CFC | 301 | 301 | 0 | 0 | 2004-12-01 | 2005-12-01 | 2005-12-01 |  | 2005-12-01 | 2012-04-01 | 2160071 | 0 | 2160071 | 2160071 | 100% | 0 | 0 |  | 186006 | 0 | 186006 | 0 | 0 | Transfer of $1.8 million balance of the overall NCPP done in Apr 12 by the WB. UNEP will continue as IA for remaining NCPP servicing sector component. |  |  |  | INV | 0
FIN | Sweden | National CFC phase-out plan servicing sector: 2005 annual programme | Multi-Year | ASP | PHI | PHA | 44 | TAS | 77 | A | I |  | 0 |  | 0 |  | 2004-12-01 | 2005-12-01 | 2007-12-01 |  | 2010-07-01 | 2012-04-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 2000 | 0 | 2000 | 0 | 0 | See remarks above. | See remarks above. | 2004
FIN | IBRD | National CFC phase-out plan: 2006 annual programme | Multiyear | ASP | PHI | PHA | 47 | INV | 79 | N | I | CFC | 149 | 149 | 0 | 0 | 2005-11-01 | 2006-12-01 | 2006-12-01 |  | 2011-06-01 | 2012-04-01 | 2873197 | -1683614 | 1189583 | 1189583 | 100% | 0 | 0 |  | 248588 | -145666 | 102922.3 | -0.3 | -0.3 | Transfer of $1.8 million balance of the overall NCPP done in Apr 12 by the WB. UNEP will continue as IA for remaining NCPP servicing sector component. |  |  |  | INV | 0
FIN | IBRD | National CFC phase-out plan: 2007 annual programme | Multiyear | ASP | PHI | PHA | 51 | INV | 81 | N | I | CFC | 907 | 907 | 0 | 0 | 2007-03-01 | 2007-12-01 | 2008-03-01 |  | 2011-06-01 | 2012-04-01 | 337717 | -18096 | 319621 | 319621.28 | 100% | -0.28 | -0.28 |  | 20795 | -1114 | 19680.75 | 0.25 | 0.25 | Transfer of $1.8 million balance of the overall NCPP done in Apr 12 by the WB. UNEP will continue as IA for remaining NCPP servicing sector component. |  |  |  | INV | 0
FIN | IBRD | National CFC phase-out plan: 2008 annual programme | Multiyear | ASP | PHI | PHA | 54 | INV | 82 | N | I | CFC | 421.3 | 421.3 | 0 | 0 | 2008-04-01 |  | 2009-03-31 |  | 2011-06-01 | 2012-04-01 | 110000 | -110000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 5500 | -5500 | 0 | 0 | 0 | Transfer of the $1.8 million balance of the overall NCPP done in Apr 12 by the WB. UNEP will continue as IA for remaining NCPP servicing sector component. |  |  |  | INV | 0
FIN | IBRD | Preparation of a HCFC phase-out management plan |  | ASP | PHI | PHA | 55 | PRP | 84 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2010-12-01 | 2009-12-31 |  | 2012-12-01 | 2012-12-01 | 195000 | 0 | 195000 | 195000 | 100% | 0 | 0 |  | 14625 | 0 | 14625 | 0 | 0 | HPMP resubmitted and approved at the 68th ExCom with UNEP as the lead IA. |  |  |  | Non-INV | 0
COM | UNEP | National CFC phase-out plan: Final implementation plan | Multi-Year | ASP | PHI | PHA | 66 | TAS | 94 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 | 2012-05-01 | 2014-03-01 |  | 2015-12-01 |  | 1835205 | -1033575 | 801630 | 541458.08 | 67.54% | 260171.92 | 234184 | 0 | 154294 | -66114 | 59560.8616 | 28619.1384 | 25760.4445 | Project completed. | Project completed.
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | PHI | PHA | 68 | TAS | 95 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2014-06-01 | 2015-12-01 | 2017-12-01 |  |  | 207000 | 1033575 | 1240575 | 384998.48 | 31.03% | 855576.52 | 252363.86 | 85557.652 | 26910 | 123693 | 46737.945 | 103865.055 | 30636.402 | Brief progress report (actual/planned): Revised Draft of 2013 and 2014 verification reports were received in 2016. UNEP reviewed and provided comments. Final verfication reports for reporting years 2013 and 2014 were accepted by UNEP and submitted to the MLFS. The Project Cooperation Agreement (PCA) has been expired since 31 December 2015. Therefore, there was no further payment made to the country in 2016. UNEP had explored the way forward for the Philippines HPMP. Legal arrangements: The PCA was signed in December 2013. First Mission: 2012. : N/A First disbursement date: June 2014. All funds disbursed (yes/no) No as PCA expired on Dec 31 2015. Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: Slow rate of implementation and expiration of the PCA. UNEP had explored the way forward for the Philippines HPMP. If Yes, will delay have impact on project completion date (yes/no): yes Any ongoing problems (yes/no): Yes If Yes, is any action required by ExCom: In light of the preparatory stages of Stage 2 HPMP, guidance is sought on the feasability of continuation of Stage 1 HPMP. | Brief progress report (actual/planned): UNEP proposed to undertake a high-level mission to Philippines in March 2017, and is working with the country to finalize the mission agenda. Further, with the Decision 74/2(b)(v), the total funding for the HPMP needs to be reduced and corrected in the Inventory. |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor the submission of technical and financial report.
ONG | IBRD | Preparation of a HCFC phase-out management plan (stage II) |  | ASP | PHI | PHA | 73 | PRP | 98 | A | I |  | 0 | 0 | 0 | 0 | 2014-11-01 | 2015-12-01 | 2015-12-31 | 2017-06-01 |  |  | 90000 | 0 | 90000 | 7844.97 | 8.717% | 82155.03 | 82155.03 | 60000 | 6300 | 0 | 549.14 | 5750.86 | 5750.86 | Local consulting firm selected and survey process started in Aug 2016. | Stage II HPMP finalized and submitted to the ExCom on 27 Mar 2017 for consideration at the 79th ExCom Meeting. Upon approval in Jul 17, preparation of WB - Philippines Grant Agreement for Stage II implementation will be stepped up. |  |  | Non-INV | 0
FIN | UNDP | Training programme in the refrigeration sector | RMP-Component | ASP | PHI | REF | 04 | TRA | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1992-04-01 | 1992-06-01 |  | 1992-12-01 | 1997-12-01 | 64000 | -1707 | 62293 | 62293 | 100% | 0 | 0 | 0 | 8320 | -222.39 | 8097.61 | 0 | 0 | Completed in 1992. Financially completed in 1997. |  | 1991 |  | Non-Investment
FIN | IBRD | Application of a reduced CFC blowing agent and non-CFC application preparation at Concepcion Industries | Individual | ASP | PHI | REF | 09 | INV | 07 | N | I | CFC | 40.8 | 78.3 | 0 | 0 | 1993-03-01 | 1996-01-01 | 1997-05-01 |  | 1998-10-01 | 1999-02-01 | 790000 | -46000 | 744000 | 744000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Full-production with C-pentane - Oct. 21, 1998. PCR was endorsed to WB on 01/12/99. Grant fund fully disbursed. No ODS eqpt. Dismantled - High pressure foam machine was used even at the start of operation. |  |  | 1997-07-01 | INV | 0
FIN | IBRD | Application of a reduced CFC blowing agent and non-CFC application preparation at Sanyo Philippines | Individual | ASP | PHI | REF | 09 | INV | 08 | N | D | CFC | 12.6 | 23.9 | 0 | 0 | 1993-03-01 | 1996-01-01 | 1997-03-01 |  | 1996-11-01 | 1999-01-01 | 660000 | -37061 | 622939 | 622939 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Phase 2 completed 11/96 - adoption of HCFC 141b foam. PCR was endorsed to WB on 10/12/98. Grant fund fully disbursed. Date ODS Eqpt. Dismantled - 12/19/95 |  |  | 1997-07-01 | INV | 0
FIN | IBRD | Application of a reduced CFC blowing agent and non-CFC application preparation at Transunion (formerly called Federal Electric Company) | Individual | ASP | PHI | REF | 09 | INV | 09 | N | I | CFC | 6.6 | 26.4 | 0 | 0 | 1993-03-01 | 1997-09-01 | 1997-05-01 |  | 1998-10-01 | 2000-12-01 | 770000 | -204218.75 | 565781.25 | 565781.34 | 100% | -0.09 | -0.09 |  | 0 | 0 | 0 | 0 | 0 | Full production with C-pentane - Oct.1, 1998. PCR was endorsed to WB on 2/2/99. Date ODS Eqpt. Dismantled - 12/02/98. All safety equipmpent and other items are installed and operational. Total grant fund disbursed is $547,732.15 only (excluding FI fees). Completed revision of PCR's Table 5. Revised PCR submitted to WB on 10 Jan |  |  | 1997-07-01 | INV | 0
FIN | IBRD | Application of a reduced CFC blowing agent and non-CFC application preparation at Philippines Appliance Corporation (Philacor) | Individual | ASP | PHI | REF | 09 | INV | 19 | N | I | CFC | 240 | 240 | 0 | 0 | 1993-03-01 | 1995-12-01 | 1997-05-01 |  | 1998-04-01 | 1999-02-01 | 1770000 | 0 | 1770000 | 1770000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR was endorsed to WB on 10/20/98. Date ODS Eqpt. Dismantled - 12/19/95. Grant fund fully disbursed. |  |  | 1997-07-01 | INV | 0
FIN | UNDP | Phase out of CFC in the manufacture of commercial refrigerators and ice boxes at Unimagna Philippines, Inc. | Individual | ASP | PHI | REF | 13 | INV | 33 | A | I | CFC | 29.5 | 29.5 | 0 | 0 | 1994-07-01 | 1995-07-01 | 1995-07-01 |  | 1996-09-01 | 2000-12-01 | 1015700 | -54324 | 961376 | 961376 | 100% | 0 | 0 | 0 | 132041 | -7062 | 124979 | 0 | 0 | Completed in 1996. Financially completed in 2000. |  | 1994 |  | Investment
FIN | USA | MACs servicing demonstration project |  | ASP | PHI | REF | 18 | DEM | 41 | A | I | CFC | 11 |  | 0 |  | 1995-11-01 | 1995-11-01 | 1996-11-01 |  | 1999-09-01 | 1999-09-01 | 285500 | 0 | 285500 | 285500 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | UNDP is working with the Government of the Philippines to complete the project. |  | 1995 | 1997-05-01
FIN | UNDP | Elimination of CFCs 11 and 12 in the manufacture of domestic refrigerators at Matsushita Electric Philippines Corporation (Mepco) | Individual | ASP | PHI | REF | 18 | INV | 39 | A | R | CFC | 47 | 47 | 0 | 0 | 1995-11-01 | 1996-06-01 | 1997-05-01 |  | 1996-09-01 | 2000-12-01 | 112244 | -4513 | 107731 | 107731 | 100% | 0 | 0 | 0 | 14591.72 | -586.69 | 14005.03 | 0 | 0 | Completed in 1996. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNIDO | Preparation of a recovery and recycling project in the refrigeration sector | Individual | ASP | PHI | REF | 18 | PRP | 40 | A | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-06-01 | 1996-01-01 |  | 1997-11-01 | 1998-08-01 | 15000 | 543 | 15543 | 15543 | 100% | 0 | 0 |  | 1950 | 71 | 2021 | 0 | 0 | FIN
FIN | UNDP | Umbrella project for conversion from CFC-11 foam blowing agent into HCFC-141b, and CFC-12 and R-502 refrigerants into HFC-134a and HFC-404a at Gomeco, Chee Puck and Well Built | Individual | ASP | PHI | REF | 19 | INV | 44 | N | I | CFC | 28 | 28 | 0 | 0 | 1996-05-01 | 1997-03-01 | 1998-04-01 |  | 2000-09-01 | 2003-04-01 | 156475 | -38769 | 117706 | 117706 | 100% | 0 | 0 | 0 | 20341.75 | -5039.97 | 15301.78 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1996 | 1999-06-01 | Investment
FIN | IBRD | Philacor, Concepcion, Sanyo and Transunion -- Engineering Design and Assistance for the Use of HFC-134a Refrigerant in Household Refrigerators | Individual | ASP | PHI | REF | 19 | INV | 45 | N | I | CFC | 91.9 | 27.1 | 0 | 0 | 1996-05-01 | 1997-10-01 | 1998-01-01 |  | 1998-05-01 | 1999-03-01 | 952000 | -485520 | 466480 | 466480 | 100% | 0 | 0 |  | 123760 | -58262.73 | 65497.27 | 0 | 0 | Project completed - HFC 134a refrigeration systems. PCRs endorsed to WB on 12/1/99. Grant fund fully disbursed. Philacor's Calamba Plant is not covered with grant funding. |  |  | 1997-07-01 | INV | 0
FIN | UNDP | Project preparation in the refrigeration sector | Individual | ASP | PHI | REF | 21 | PRP | 47 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1997-12-01 | 2000-12-01 | 35000 | -4264 | 30736 | 30736 | 100% | 0 | 0 | 0 | 4550 | -554.32 | 3995.68 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNIDO | National CFC recovery and recycling scheme | RMP | ASP | PHI | REF | 22 | TAS | 49 | A | I | CFC | 60 | 60 |  |  | 1997-05-01 | 1997-09-01 | 1999-06-01 |  | 1998-12-01 | 2002-05-01 | 557500 | -49 | 557451 | 557450.97 | 100% | 0.03 | 0 |  | 72475 | -121 | 72354 | 0 | 0 | FIN
FIN | Germany | Elimination of CFC-11 and CFC-12 in the manufacture of commercial refrigeration equipment at Azkcon Refrigeration Industries, Inc. | Individual | ASP | PHI | REF | 23 | INV | 53 | A | I | CFC | 18.9 | 18.9 | 0 |  | 1997-11-01 | 1998-07-01 | 1999-12-01 |  | 2000-12-01 | 2005-04-01 | 370258 | -75353 | 294905 | 294905 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project is completed, PCR drafted by UNDP for completion and submission by GTZ. Remaining balance and interest (USD 75.353) has been returned in Dec-04 to GTZ to be reported and returned to MLF at the 45th ExCom.
FIN | Sweden | Preparation of a government strategy to reduce and eliminate the use of CFC refrigerants for servicing and installations on-site | Individual | ASP | PHI | REF | 29 | PRP | 59 | A | I |  | 0 |  | 0 |  | 1999-11-01 | 2000-11-01 | 2001-12-01 |  | 2002-08-01 | 2002-11-01 | 141400 | 0 | 141400 | 141400 | 100% | 0 |  |  | 0 | 0 | 0 | 0 | 0 | Detailed discussions with the Philippine authority in charge, Department of Environment and Natural Resources (DENR), on the implementation took place May 2000. International and local consultants were contracted and in November 2000, the first meeting with the involved authorities and the private sector was conducted. The political situation in the Philippines during 2001 caused the project a delay. A RMP outline was adopted in October 2001. During 2002 the project was merged into a NCPP together with the WB. The NCPP was submitted jointly and approved in December 2002 with Sweden as co-implementing agency for TA activities related to the servicing sector. |  | 1999
FIN | UNEP | Training programme for customs officials and other key stakeholders | Individual | ASP | PHI | REF | 35 | TRA | 66 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-06-01 | 2004-01-01 |  | 2005-12-01 | 2006-11-01 | 170250 | -3588 | 166662 | 166662 | 100% | 0 | 0 |  | 22133 | -466 | 21667 | 0 | 0
FIN | UNDP | Preparation for HCFC phase-out investment activities (refrigeration and air-conditioning sectors except residential air conditioning) | Individual | ASP | PHI | REF | 59 | PRP | 87 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-11-01 | 2011-03-01 | 2010-11-01 |  | 2012-06-01 | 2014-02-01 | 65000 | -50058 | 14942 | 14942 | 100% | 0 | 0 | 0 | 4875 | -3754 | 1121 | 0 | 0 | Financially completed in 2014. | Completed in 2012. | 2009 |  | Investment
CLO | IBRD | Preparation for HCFC phase-out investment activities (domestic air-conditioning sector) |  | ASP | PHI | REF | 59 | PRP | 88 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 |  | 2010-12-01 |  |  | 2012-07-01 | 65000 | -65000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 4875 | -4875 | 0 | 0 | 0 | Preparation funding returned at the 67th ExCom meeting. |  |  | 1997-01-01 | Non-INV | 0
FIN | IBRD | Country programme preparation | Individual | ASP | PHI | SEV | 04 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 19952 | 17415 | 37367 | 37367 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1997-07-01 | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1991) |  | ASP | PHI | SEV | 04 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 10826 | 39489 | 50315 | 50315 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1998-01-01 | Non-INV | 0
FIN | IBRD | Controlled substances engineering project |  | ASP | PHI | SEV | 06 | PRP | 04 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-08-12 | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 400000 | -6325 | 393675 | 393675 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and closed. Balance of funds returned to Multilateral Fund. |  |  | 1998-01-01 | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1992) |  | ASP | PHI | SEV | 06 | PRP | 05 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 100000 | -57260 | 42740 | 42740 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Country programme preparation | Individual | ASP | PHI | SEV | 08 | CPG | 06 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1993-03-01 | 1993-10-01 |  | 1993-06-01 | 1997-12-01 | 39820 | 39820 | 79640 | 79640 | 100% | 0 | 0 | 0 | 5176.6 | 5176.6 | 10353.2 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | IBRD | Instititional strengthening for Ozone Desk Operations | Individual | ASP | PHI | SEV | 09 | INS | 10 | N | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1995-12-01 | 1996-03-01 |  | 1998-12-01 | 2002-05-01 | 209000 | 0 | 209000 | 209000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed physically and financially. |  |  | 1999-12-01 | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1993) |  | ASP | PHI | SEV | 09 | PRP | 20 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 194550 | -129221 | 65329 | 65329 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
TRF | IBRD | Information exchange programme | Individual | ASP | PHI | SEV | 09 | TAS | 16 | N | I |  | 0 | 0 | 0 | 0 | 1993-03-01 |  | 1993-11-01 |  |  | 1993-11-01 | 200000 | -200000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Closed. Funds transferred to UNEP for its implementation at the request of the Govt. |  |  |  | Non-INV | 0
FIN | IBRD | Technical assistance for the financial institution | Individual | ASP | PHI | SEV | 09 | TAS | 17 | N | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1995-08-01 | 1994-03-01 |  | 2000-04-01 | 2000-04-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project and PCR completed. |  |  | 1999-12-01 | Non-INV | 0
FIN | UNDP | Project preparation assistance | Individual | ASP | PHI | SEV | 11 | PRP | 21 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-01 | 1994-07-01 |  | 1994-11-01 | 1997-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1993 |  | Investment
CLO | IBRD | User-sector project identification and preparation (1993) |  | ASP | PHI | SEV | 11 | PRP | 24 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 |  | 1994-11-01 |  |  | 1994-12-01 | 150000 | -150000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Survey of ODS usage, data base generation and technical assistance for ODS phase-out for small-scale enterprises | Individual | ASP | PHI | SEV | 11 | TAS | 22 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-06-01 | 1994-11-01 |  | 1996-09-01 | 1998-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1993 |  | Non-Investment
FIN | UNEP | Information exchange programme | Individual | ASP | PHI | SEV | 11 | TAS | 23 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-06-01 | 1995-12-01 |  | 2000-12-01 | 2003-07-01 | 200000 | -1488 | 198512 | 198512 | 100% | 0 | 0 |  | 26000 | -193.44 | 25806.56 | 0 | 0
FIN | IBRD | Supervision of project implementation (1994) |  | ASP | PHI | SEV | 12 | PRP | 25 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 136027 | -93678 | 42349 | 42349 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
CLO | IBRD | Preparation of investment projects (1994) |  | ASP | PHI | SEV | 12 | PRP | 29 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1995-03-01 |  |  | 1994-12-01 | 94900 | -94900 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Project preparation assistance | Individual | ASP | PHI | SEV | 15 | PRP | 35 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1994-12-01 | 1995-12-01 |  | 1996-03-01 | 1997-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1996. Financially completed in 1997. |  | 1994 |  | Investment
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | ASP | PHI | SEV | 16 | PRP | 36 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1996-12-31 | 1996-12-01 | 169937 | -70000 | 99937 | 99937 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | UNDP | Project preparation assistance | Individual | ASP | PHI | SEV | 18 | PRP | 42 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-11-01 | 2002-05-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 5850 | 0 | 5850 | 0 | 0 | Completed in 1996. Financially completed in 2002. |  | 1995 |  | Investment
FIN | IBRD | Renewal of institutional strengthening |  | ASP | PHI | SEV | 28 | INS | 63 | N | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2001-08-01 |  | 2002-05-01 | 2002-05-01 | 139333 | 0 | 139333 | 139333 | 100% | 0 | 0 |  | 18113 | 0 | 18113 | 0 | 0 | Phase II completed and IS renewal approved at the 36th ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | Renewal of institutional strengthening project (Phase III) |  | ASP | PHI | SEV | 36 | INS | 67 | N | I | CFC | 14.97 | 14.97 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-04-01 |  | 2004-12-01 | 2005-01-01 | 181133 | 0 | 181133 | 181133 | 100% | 0 | 0 |  | 23547.29 | 0 | 23547.29 | 0 | 0 | Phase III completed and IS renewal approved at the 42nd ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | Extension of institutional strengthening project | Individual | ASP | PHI | SEV | 42 | INS | 73 | N | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-12-01 | 2005-04-01 |  | 2005-04-01 | 2005-05-01 | 90566 | 0 | 90566 | 90566 | 100% | 0 | 0 |  | 6792 | 0 | 6792 | 0 | 0 | First half of Phase IV of the IS project completed. |  |  |  | Non-INV | 0
FIN | IBRD | Extension of the institutional strengthening project (phase IV, second year) | Individual | ASP | PHI | SEV | 45 | INS | 78 | N | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-12-01 | 2006-04-01 |  | 2006-04-01 | 2006-05-01 | 90567 | 0 | 90567 | 90567 | 100% | 0 | 0 |  | 6793 | 0 | 6793 | 0 | 0 | Second half of Phase IV of the IS project completed. |  |  |  | Non-INV | 0
FIN | IBRD | Extension of institutional strengthening project (phase V) | Individual | ASP | PHI | SEV | 48 | INS | 80 | N | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2006-12-01 | 2008-04-01 |  | 2008-04-01 | 2008-12-01 | 181133 | 0 | 181133 | 181133 | 100% | 0 | 0 |  | 13585 | 0 | 13585 | 0 | 0 | Phase V completed and IS renewal approved at the 54th ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | Extension of institutional strengthening project (phase VI) | Individual | ASP | PHI | SEV | 54 | INS | 83 | N | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-12-01 | 2010-03-31 |  | 2010-06-01 | 2010-11-01 | 181133 | 0 | 181133 | 181133 | 100% | 0 | 0 |  | 13585 | 0 | 13585 | 0 | 0 | Phase VI completed. IS renewed at the 60th ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | Extension of institutional strengthening project (phase VII) | Individual | ASP | PHI | SEV | 60 | INS | 89 | N | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-12-01 | 2011-12-31 |  | 2011-06-01 | 2011-11-01 | 158491 | -64471 | 94020 | 94020 | 100% | 0 | 0 |  | 11887 | -4835 | 7052 | 0 | 0 | Balance of IS VII transferred to UNEP in Nov 11 subsequent to the closing of the overall ODS Grant Agreement between the Philippines and the WB. |  |  |  | Non-INV | 0
FIN | UNEP | Extension of institutional strengthening project (phase VIII: 1/2012-12/2013) | Individual | ASP | PHI | SEV | 64 | INS | 92 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2011-10-01 | 2013-12-01 |  | 2013-12-01 | 2014-12-01 | 181133 | 0 | 181133 | 181133 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase VII) | Individual | ASP | PHI | SEV | 65 | INS | 93 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-05-01 | 2012-12-01 |  | 2013-12-01 | 2014-12-01 | 64471 | 0 | 64471 | 64471 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of institutional strengthening project (phase IX: 1/2014-12/2015) | Individual | ASP | PHI | SEV | 70 | INS | 96 | A | I |  | 0 |  | 0 |  | 2013-07-01 | 2014-09-01 | 2015-12-01 |  | 2016-12-01 |  | 181133 | 0 | 181133 | 181133 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. | Project completed.
ONG | UNEP | Extension of institutional strengthening project (phase X: 1/2016-12/2017) | Individual | ASP | PHI | SEV | 74 | INS | 99 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-08-01 | 2017-12-01 | 2017-12-01 |  |  | 181133 | 0 | 181133 | 103654 | 57.23% | 77479 | 77479 | 7747.9 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The SSFA between UNEP and the Government of the Philippines was signed in February 2016. The Philippines Ozone Desk (POD) was operating normally. The implementation of the licensing scheme and quota system based on the revised Chemical Control Order (CCO) on ODS was continued. POD coordinated and facilitated the preparation of HPMP Stage II, ODS Alternative Survey and verification of HCFC consumption. POD also organized the 2016 ozone day celebration, and actively joined the regional and global ozone related meetings e.g. the network meeting, OEWG and the MOP meetings. 2015 Article 7 and CP data were submitted to the Ozone Secretariat and MLFS respectively. Legal arrangements(actual/planned): The SSFA was signed in February 2016. Initial stages of project implementation(actual/planned): Jan/Feb 2016 Intermediate goals achieved (actual/planned): Yes. Project completion and follow up: Not applicable. First disbursement date (actual/planned): August 2016. All funds disbursed (yes/no): No. Any delay?(yes/no): No_ If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): POD continues enforcing the licensing and quota system. UNEP is working closely with POD to release the second payment (from 3 payments) under the SSFA.
ONG | IBRD | Survey of ODS alternatives at the national level | Individual | ASP | PHI | SEV | 75 | TAS | 100 | A | I |  | 0 | 0 | 0 | 0 | 2015-11-01 | 2016-12-01 | 2016-12-31 | 2017-11-01 |  |  | 130000 | 0 | 130000 | 6955 | 5.35% | 123045 | 123045 | 123045 | 11700 | 0 | 625.95 | 11074.05 | 11074.05 | Survey of ODS alternatives is under implementation by an international consulting firm that will complete the data collection by early 2017. | WB mission held in Feb 17 to go over survey data and provide recommendations with the country to the consultant for survey completion. $20,865 disbursed in early 2017. Survey expected to be submitted to the 80th ExCom Meeting. |  |  | Non-INV | 0
FIN | IBRD | Conversion to semi-aqueous and aqueous cleaning solvents at Ionics Circuits, Inc. | Individual | ASP | PHI | SOL | 09 | INV | 11 | N | D |  | 85.7 | 85.7 | 0 | 0 | 1993-03-01 | 1996-08-01 | 1993-09-01 |  | 1995-09-01 | 1998-07-01 | 790000 | 0 | 790000 | 790000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR endorsement to WB - 10/12/98. Grant fund fullly disbursed. Date ODS Eqpt. Dismantled - 8/16/96 |  |  | 1995-09-01 | INV | 0
CLO | IBRD | Conversion to low-emission processing and organic solvents at Pacific Semiconductors, Inc. | Individual | ASP | PHI | SOL | 09 | INV | 12 | N | I |  | 0 | 0 | 0 | 0 | 1993-03-01 |  | 1993-09-01 |  |  | 1996-10-01 | 710000 | -710000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Enterprise decided not to proceed with project. Project cancelled. |  |  | 1993-09-01 | INV | 0
FIN | IBRD | Conversion to aqueous cleaning at Electronic Assemblies, Inc. | Individual | ASP | PHI | SOL | 09 | INV | 13 | N | I | CFC | 4 | 4.16 | 0 | 0 | 1993-03-01 | 1996-04-01 | 1993-09-01 |  | 1997-02-01 | 1998-07-01 | 710000 | -34141 | 675859 | 675859 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR endorsement to WB - 10/12/98. Grant fund fully disbursed. Date ODS Eqpt. Dismantled - 6/11/96 |  |  | 1997-02-01 | INV | 0
FIN | IBRD | Conversion to high-purity water cleaning at Integrated Microelectronic, Inc. | Individual | ASP | PHI | SOL | 09 | INV | 14 | N | D | CFC | 14.6 | 14.6 | 0 | 0 | 1993-03-01 | 1997-08-01 | 1993-09-01 |  | 1997-12-01 | 1998-12-01 | 430000 | -72997.88 | 357002.12 | 357002.12 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR endorsement to WB - 10/20/98. Grant fund fullly disbursed. Date ODS Eqpt. Dismantled - 5/19/98 |  |  | 1996-07-01 | INV | 0
CLO | IBRD | Conversion to semi-aqueous cleaning solvents at Ionics Circuits, Inc. | Individual | ASP | PHI | SOL | 09 | INV | 15 | N | I |  | 0 | 0 | 0 | 0 | 1993-03-01 |  | 1993-09-01 |  |  | 1997-02-01 | 70000 | -70000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Enterprise is no longer eligible for grant funding. Project cancelled. |  |  |  | INV | 0
FIN | UNDP | Elimination of the use of CFC-113, 1,1,1 trichloroethane (TCA), CFC-11 and CFC-12 at multiple corporations that manufacture special formulations for various industrial markets | Individual | ASP | PHI | SOL | 19 | INV | 46 | N | I | TCA/CFC | 53.6 | 53.6 | 0 | 0 | 1996-05-01 | 1997-03-01 | 1997-11-01 |  | 1998-06-01 | 2003-09-01 | 642800 | -181667 | 461133 | 461133 | 100% | 0 | 0 | 0 | 83564 | -23616.71 | 59947.29 | 0 | 0 | Completed in 1998. Financially completed in 2003. |  | 1996 |  | Investment
FIN | UNDP | Project preparation to prepare the second and final phase for phaseout of ODS by solvent blenders | Individual | ASP | PHI | SOL | 24 | PRP | 54 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-03-01 | 1998-12-01 |  | 1998-12-01 | 1999-11-01 | 25000 | -22120 | 2880 | 2880 | 100% | 0 | 0 | 0 | 3250 | -2875.6 | 374.4 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1998 |  | Investment
FIN | UNDP | Elimination of CFC-113, l,l,l trichloroethane and CFC-12 at multiple corporations that manufacture special formulations for industrial markets (Ariad Industrial Co., Cloisonne, Redisol, Rodler) | Individual | ASP | PHI | SOL | 25 | INV | 56 | A | I | TCA/CFC | 18.4 | 18.4 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-02-01 |  | 1999-12-01 | 2003-04-01 | 334600 | -93314 | 241286 | 241286 | 100% | 0 | 0 | 0 | 43498 | -12130.82 | 31367.18 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  | 1998 |  | Investment
FIN | Germany | Project preparation for the development of an ODS phase out action plan | Individual | ASP | PNG | PHA | 36 | PRP | 04 | A | I |  | 0 |  | 0 |  | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2003-04-01 | 2003-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | TPMP for PNG has been approved at the 39th ExCom
FIN | Germany | Terminal phase-out management plan for ODS (1st tranche) | Multi-Year | ASP | PNG | PHA | 39 | INV | 05 | A | I | CFC | 18 | 30.8 | 0 |  | 2003-04-01 | 2003-08-01 | 2005-12-01 |  | 2006-07-01 | 2006-12-01 | 480000 | 0 | 480000 | 480000 | 100% | 0 | 0 | 0 | 59700 | 0 | 59700 | 0 | 0 | PNG has successfully completed the 1st Action Plan of the TPMP and the country's consumption is well below the TPMP reduction targets.
FIN | Germany | Terminal phase-out management plan for ODS (2nd tranche) | Multi-Year | ASP | PNG | PHA | 48 | INV | 08 | A | I | CFC | 17 | 4.5 | 0 |  | 2006-04-01 | 2006-08-01 | 2008-12-01 |  | 2009-12-01 | 2012-12-01 | 220000 | 0 | 220000 | 220000 | 100% | 0 | 0 | 0 | 27300 | 0 | 27300 | 0 | 0 | PNG has maintained compliance of zero CFC-imports. PNG has completed the incentive scheme. The final report is under preparation.
FIN | Germany | Preparation of a HCFC phase-out management plan | Individual | ASP | PNG | PHA | 57 | PRP | 10 | A | I | HCFC | 0 |  | 0 |  | 2009-04-01 | 2009-10-01 | 2010-03-01 |  | 2010-12-01 | 2012-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | HPMP completed and approved
COM | Germany | HCFC phase-out management plan (first tranche) | Multi-Year | ASP | PNG | PHA | 63 | INV | 11 | A | I | HCFC | 0.2 | 0.2 | 0 |  | 2011-04-01 | 2011-07-01 | 2014-03-01 |  | 2016-03-01 |  | 350000 | 0 | 350000 | 350000 | 100% | 0 | 0 | 0 | 41300 | 0 | 41300 | 0 |  | Ozone day was celebrated successfully as only a limited funds were available under the tranche.
ONG | Germany | HCFC phase-out management plan (second tranche) | Multi-Year | ASP | PNG | PHA | 71 | INV | 12 | A | I | HCFC | 0.6 |  | 0 |  | 2013-12-01 | 2016-02-01 | 2016-12-01 | 2018-06-01 |  |  | 340000 | 0 | 340000 | 116994 | 34.41% | 223006 | 0 | 100000 | 40120 | 0 | 13805 | 26315 |  | TOT participation of 2 trainers and NOU on natural refrigerants. 2 stakeholder workshops were conducted. 10 recovery units were purchased including 20 recovery cylinders. 10 4 - way digital manifold sets were supplied. Drafting of standards to include natural refrigerants in the national curriculum. Upgrading of curriculum to reflect new standards. | Currently the curriculum is being finalised and related equipment ordered for purchase. |  |  | INV
COM | Germany | Verification report for stage I of HCFC phase-out management plan | Individual | ASP | PNG | PHA | 74 | TAS | 13 | A | I | HCFC | 0 |  | 0 |  | 2015-05-01 | 2016-04-01 | 2016-11-01 |  | 2016-11-01 |  | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 |  | Veriifcation was completed in 2016 and submitted along with the 3rd tranche request
ONG | Germany | HCFC phase-out management plan (third tranche) |  | ASP | PNG | PHA | 77 | INV | 15 | A | I | HCFC | 1.2 |  | 0 |  | 2016-12-01 |  | 2020-12-01 | 2020-12-01 |  |  | 301000 | 0 | 301000 | 0 | 0% | 301000 | 0 | 0 | 35518 | 0 |  | 35518 |  | Only approved in November 2016. There are still sufficient funds remaining under tranche 2 which need to be spent prior to accessing the funds available under 3rd tranche
TRF | UNEP | Assistance for formulation refrigeration management plan | RMP | ASP | PNG | REF | 21 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-09-01 |  |  | 2002-03-01 | 30000 | -30000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 3900 | -3900 |  | 0 |  |  |  |  | 1999-12-01
FIN | UNEP | Country programme preparation | Individual | ASP | PNG | SEV | 13 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1995-02-01 | 1995-10-01 |  | 1996-05-01 | 1999-04-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNEP | Creation of an Ozone Unit | Individual | ASP | PNG | SEV | 19 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1997-09-01 | 1999-05-01 |  | 2003-12-01 | 2009-10-01 | 45800 | -24715 | 21085 | 21085 | 100% | 0 | 0 |  | 5954 | -3212.95 | 2741.05 | 0 | 0 |  |  |  | 1999-05-01
FIN | Germany | Extension of institutional strengthening project | Individual | ASP | PNG | SEV | 41 | INS | 06 | N | I |  | 0 |  | 0 |  | 2003-12-01 | 2004-06-01 | 2005-12-01 |  | 2006-03-01 | 2006-06-01 | 39693 | 0 | 39693 | 39693 | 100% | 0 | 0 | 0 | 5160 | 0 | 5160 | 0 | 0 | ISP completed successfully.
FIN | Germany | Extension of the institutional strengthening project (phase III) | Individual | ASP | PNG | SEV | 48 | INS | 07 | A | I |  | 0 |  | 0 |  | 2006-04-01 | 2006-05-01 | 2008-04-01 |  | 2008-04-01 | 2008-06-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | ISP completed successfully.
FIN | Germany | Extension of the institutional strengthening project (phase IV) | Individual | ASP | PNG | SEV | 54 | INS | 09 | A | I |  | 0 |  | 0 |  | 2008-04-01 | 2008-07-01 | 2010-03-01 |  | 2010-12-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 7800 | 0 | 7800 | 0 | 0 | The ISP has been completed and the next phase is now part of the exisiting HPMP
ONG | Germany | Survey of ODS alternatives at the national level | Individual | ASP | PNG | SEV | 75 | TAS | 14 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-04-01 | 2016-11-01 | 2017-05-01 |  |  | 40000 | 0 | 40000 | 16200 | 40.5% | 23800 | 0 | 23800 | 5200 | 0 | 2106 | 3094 |  | Consultant was hired through a tender process in the 1st quarter of 2016. | The survey report has been submitted to MLF in April 2017
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | AFR | PRC | PHA | 48 | PRP | 13 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-11-01 | 2007-04-01 |  | 2007-12-01 | 2010-01-01 | 12000 | -11833 | 167 | 167 | 100% | 0 | 0 | 0 | 900 | -887.48 | 12.525 | -0.005 | 0 | Financially completed in 2010. |  | 2006 |  | Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | PRC | PHA | 48 | PRP | 14 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-05-01 | 2007-04-01 |  | 2008-11-01 | 2009-11-01 | 18000 | -9 | 17991 | 17991 | 100% | 0 | 0 |  | 2340 | -1.17 | 2338.83 | 0 | 0
FIN | UNIDO | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | PRC | PHA | 54 | INV | 17 | A | I |  | 0 | 0 |  |  | 2008-04-01 | 2008-07-01 | 2010-03-31 |  | 2010-12-01 | 2011-05-01 | 50000 | -73 | 49927 | 49927.32 | 100% | -0.32 | 0 |  | 4500 | -7 | 4493 | 0 | 0 | FIN |  |  |  | INV
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | PRC | PHA | 54 | TAS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-07-01 | 2010-03-01 |  | 2011-03-01 | 2012-03-01 | 68000 | 0 | 68000 | 68000 | 100% | 0 | 0 |  | 8840 | 0 | 8840 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | PRC | PHA | 55 | PRP | 18 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-08-01 | 2009-07-01 |  | 2011-12-01 | 2012-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 |  | 11050 | 0 | 11050 | 0 | 0
FIN | UNIDO | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | PRC | PHA | 60 | INV | 21 | A | I |  | 1.8 | 1.8 |  |  | 2010-04-01 | 2010-09-01 | 2011-04-30 |  | 2013-12-01 | 2014-04-01 | 45000 | -300 | 44700 | 44700.37 | 100% | -0.37 | 0 |  | 4050 | -27 | 4023 | 0 | 0 | FIN
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | PRC | PHA | 60 | TAS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-10-01 | 2011-04-01 |  | 2012-01-01 | 2013-12-01 | 42000 | 0 | 42000 | 42000 | 100% | 0 | 0 |  | 5460 | 0 | 5460 | 0 | 0
COM | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | PRC | PHA | 63 | INV | 23 | A | I |  | 0 | 0 |  |  | 2011-04-01 | 2013-03-01 | 2013-03-31 |  | 2015-12-01 |  | 100000 | 0 | 100000 | 98570.94 | 98.57% | 1429.06 | 0 | 1 | 9000 | 0 | 8871 | 129 | 0 | The project was operationally completed. |  |  |  | INV
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | PRC | PHA | 63 | TAS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-09-01 | 2013-03-01 |  | 2014-03-01 | 2016-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 |  | 5850 | 0 | 5850 | 0 | 0 | Project financially completed. Balances to be returned. | Project financially completed. Balances to be returned.
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | AFR | PRC | PHA | 71 | TAS | 26 | A | I |  | 0.4 |  | 0 |  | 2013-12-01 | 2014-06-01 | 2016-12-01 | 2017-12-01 |  |  | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | Brief progress report (actual/planned): One workshop on Good practice and safe handling for 25 refrigeration technicians organized in 2016. One workshop on identification of ODS for 25 Customs officers organized in 2016. All activities under the SSFA are completed (as planned) _yes_ First mission (actual/planned): _ - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in June 2014 __ All funds disbursed (yes/no): _No _ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Brief progress report (actual/planned): Legal arrangements (actual/planned): Agreement signed in June 2014. One workshop on Good practice and safe handling for 25 refrigeration technicians organized in 2016. One workshop on identification of ODS for 25 Customs officers organized in 2016. All activities under the SSFA are completed (as planned) _yes_ First mission (actual/planned): _ - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in June 2014 __ All funds disbursed (yes/no): _No _ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
COM | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Individual | AFR | PRC | PHA | 75 | TAS | 29 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-01-01 | 2017-03-01 |  | 2016-12-01 |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 30000 | 30000 | 3900 | 0 | 0 | 3900 | 3900 | Project completed. | Project completed.
ONG | UNIDO | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | AFR | PRC | PHA | 76 | INV | 31 | A | I | HCFC | 1.8 | 0 |  |  | 2016-05-01 |  | 2020-05-31 | 2020-05-01 |  |  | 75000 | 0 | 75000 | 0 | 0% | 75000 | 0 | 5000 | 6750 | 0 | 0 | 6750 | 0 | - Funds approved in 2016 at the 76th ExCom Meeting for UNIDO as co-implementing agency to support UNEP's (Lead IA) trainings and other didactic needs. Milestones achieved: Milestone 1: - Legal arrangements - Yes Milestone 2: - Initial stages of project implementation began - not yet Milestone 3: - Intermediate goals achieved - No Milestone 4:- Project completion and follow-up - No Actions towards next goals: Agreement on the scope of equipment to be purchased. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | Meeting with NOU and UNEP to take place in first semester. Actions towards next goals: Agreement on the scope of equipment to be purchased. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
ONG | UNEP | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | AFR | PRC | PHA | 76 | TAS | 30 | A | I |  | 0 |  | 0 |  | 2016-05-01 | 2016-12-01 | 2018-09-01 | 2018-09-01 |  |  | 40000 | 0 | 40000 | 25139.32 | 62.85% | 14860.68 | 14860.68 | 1486.068 | 5200 | 0 | 3268.1116 | 1931.8884 | 1931.8884 | Newly approved project | Brief progress report (actual/planned): Project newly approved. Agreement signed in Nov. 2016. Legal arrangements (actual/planned): Agreement signed in Nov. 2016. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st payment sent in February 2017__ All funds disbursed (yes/no): _ Final payment _no___ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerants | RMP-Component | AFR | PRC | REF | 20 | TAS | 04 | A | I | CFC | 19.2 | 19.2 | 0 | 0 | 1996-10-01 | 1998-10-01 | 1998-09-01 |  | 2001-12-01 | 2003-04-01 | 201200 | -13880 | 187320 | 187320 | 100% | 0 | 0 | 0 | 26156 | -1804.4 | 24351.6 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1996 | 1998-10-01 | Investment
FIN | UNEP | Preparation of a refrigerant management plan | RMP | AFR | PRC | REF | 27 | PRP | 05 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-01-01 | 2000-04-01 |  | 2000-12-01 | 2001-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Implementation of the RMP: assistance for information-sharing | Individual | AFR | PRC | REF | 32 | TAS | 07 | A | I | CFC | 0.8 | 0 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2002-01-01 |  | 2003-12-01 | 2005-02-01 | 16000 | -2967 | 13033 | 13033 | 100% | 0 | 0 |  | 2080 | -385.71 | 1694.29 | 0 | 0
FIN | UNEP | Implementation of the RMP: customs training programme | Individual | AFR | PRC | REF | 32 | TRA | 09 | A | I | CFC | 3.4 | 3.4 | 0 | 0 | 2000-12-01 | 2001-03-01 | 2004-12-01 |  | 2003-12-01 | 2005-01-01 | 69400 | -25378 | 44022 | 44022 | 100% | 0 | 0 |  | 9022 | -3299.14 | 5722.86 | 0 | 0
FIN | UNDP | Project preparation in the refrigeration sector | Individual | AFR | PRC | REF | 34 | PRP | 08 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2002-08-01 |  | 2003-09-01 | 2003-09-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2003. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Implementation of the RMP: centralized recovery and recycling of CFC-12 programme | RMP-Component | AFR | PRC | REF | 41 | TAS | 11 | N | I | CFC | 5.9 | 5.9 | 0 | 0 | 2003-12-01 | 2006-07-01 | 2006-12-01 |  | 2008-12-01 | 2011-12-01 | 118078 | 0 | 118078 | 118078 | 100% | 0 | 0 | 0 | 10627 | 0 | 10627 | 0 | 0 | Completed in 2008. Financially completed in 2011. |  | 2003 |  | Investment
FIN | UNEP | Country programme preparation | Individual | AFR | PRC | SEV | 17 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 |  | 1996-07-01 |  | 1995-07-01 | 1996-07-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 |  | 0
FIN | UNEP | Creation of an Ozone Bureau | Individual | AFR | PRC | SEV | 17 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-05-01 | 1998-07-01 |  | 2000-12-01 | 2001-12-01 | 62920 | 0 | 62920 | 62920 | 100% | 0 | 0 |  | 8180 | 0 | 8180 | 0 | 0 |  |  |  | 1999-12-01
FIN | UNDP | Project preparation assistance in recovery and recycling of refrigerant, foam and halon sectors | Individual | AFR | PRC | SEV | 18 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-11-01 | 1996-11-01 |  | 1996-11-01 | 1998-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNEP | Renewal of institutional strengthening | Individual | AFR | PRC | SEV | 32 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-11-01 | 2003-01-01 |  | 2003-04-01 | 2003-12-01 | 41950 | 0 | 41950 | 41950 | 100% | 0 | 0 |  | 5454 | 0 | 5454 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase 3) | Individual | AFR | PRC | SEV | 39 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-07-01 | 2005-04-01 |  | 2005-04-01 | 2005-12-01 | 54531 | 0 | 54531 | 54531 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extensionl of the institutional strengthening project (phase IV) | Individual | AFR | PRC | SEV | 45 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-08-01 | 2007-04-01 |  | 2007-04-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | AFR | PRC | SEV | 51 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2007-03-01 | 2007-07-01 | 2009-03-01 |  | 2009-03-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VI) | Individual | AFR | PRC | SEV | 57 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-12-01 | 2011-03-01 |  | 2010-12-01 | 2011-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VII: 7/2011-6/2013) | Individual | AFR | PRC | SEV | 64 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-06-01 | 2013-06-01 |  | 2013-10-01 | 2014-04-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of the institutional strengthening project (phase VIII: 1/2014-12/2015) | Individual | AFR | PRC | SEV | 71 | INS | 25 | A | I |  | 0 |  | 0 |  | 2013-12-01 | 2014-06-01 | 2015-12-01 |  | 2015-12-01 |  | 60000 | 0 | 60000 | 45084.2 | 75.14% | 14915.8 | 14915.8 | 14916 | 0 | 0 | 0 | 0 | 0 | Project completed | Project completed
ONG | UNEP | Extension of the institutional strengthening project (phase IX: 1/2015-12/2017) | Individual | AFR | PRC | SEV | 75 | INS | 27 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-05-01 | 2017-12-01 | 2017-12-01 |  |  | 85000 | 0 | 85000 | 36.1 | 0.04247% | 84963.9 | 84963.9 | 8496.39 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): SSFA signed in April 2016 and First payment sent in May 2016. Country reported 2015 Art5 data and CP data for 2015. Legal arrangements (actual/planned): Agreement signed in April 2016. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _n/a - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in May 2016__ All funds disbursed (yes/no): _ Final payment _ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Brief progress report (actual/planned): SSFA signed in April 2016 and First payment sent in May 2016. Country reported 2015 Art5 data and CP data for 2015. Legal arrangements (actual/planned): Agreement signed in April 2016. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _n/a - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in May 2016__ All funds disbursed (yes/no): _ Final payment _ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | AFR | PRC | SEV | 75 | TAS | 28 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-05-01 | 2016-12-01 | 2017-10-01 |  |  | 70000 | 0 | 70000 | 36.1 | 0.05157% | 69963.9 | 69963.9 | 6996.39 | 9100 | 0 | 4.693 | 9095.307 | 9095.307 | Brief progress report (actual/planned): Local consultants recruited in May 2016 and National survey on ODS alternatives started in June 2016, NOU hasn’t submitted the report yet. Legal arrangements (actual/planned): signed in April 2016 (Yes/No): No_ First mission (actual/planned): __n/a_ TOR completed (actual/planned): _N/A__ First disbursement date (actual/planned): May 2016___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _YES_ If Yes, reasons for delay & action plan to resolve: NO__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): Local consultants recruited in May 2016 and National survey on ODS alternatives started in June 2016, NOU hasn’t submitted the report yet. Country to submit first draft report by 15 April 2017. Legal arrangements (actual/planned): signed in April 2016 (Yes/No): No_ First mission (actual/planned): __n/a_ TOR completed (actual/planned): _N/A__ First disbursement date (actual/planned): May 2016___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _YES_ If Yes, reasons for delay & action plan to resolve: NO__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__
FIN | UNIDO | Preparation for HCFC phase-out investment activities (foam sector) | Individual | ASP | QAT | FOA | 60 | PRP | 16 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-12-01 | 2011-04-30 |  | 2011-12-01 | 2013-12-01 | 80000 | -891 | 79109 | 79108.51 | 100% | 0.49 | 0 |  | 6000 | -67 | 5933 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a terminal phase-out management plan | Individual | ASP | QAT | PHA | 46 | PRP | 07 | A | I |  | 0 | 0 |  |  | 2005-07-01 | 2006-10-01 | 2006-07-01 |  | 2007-12-01 | 2007-12-01 | 30000 | -97 | 29903 | 29903.3 | 100% | -0.3 | 0 |  | 2250 | -7 | 2243 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Terminal phase-out management plan (first tranche) | Multi-Year | ASP | QAT | PHA | 53 | INV | 09 | A | I | CFC | 3 | 3 |  |  | 2007-11-01 | 2008-02-01 | 2009-03-01 |  | 2013-12-01 | 2015-03-01 | 242500 | -786 | 241714 | 241713.97 | 100% | 0.03 | 0 |  | 18188 | -59 | 18129 | 0 | 0 | FIN |  |  |  | INV
COM | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | ASP | QAT | PHA | 53 | TAS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2009-07-01 | 2009-03-01 |  | 2014-07-01 |  | 65000 | -45000 | 20000 | 15000 | 75% | 5000 | 0 | 5000 | 8450 | -5850 | 1950 | 650 | 0
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | ASP | QAT | PHA | 55 | PRP | 11 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2009-05-01 | 2009-07-31 |  | 2011-12-01 | 2012-12-01 | 55000 | -1045 | 53955 | 53955.29 | 100% | -0.29 | 0 |  | 4125 | -78 | 4047 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | QAT | PHA | 55 | PRP | 12 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2011-01-01 | 2009-07-01 |  | 2011-08-01 | 2014-05-01 | 30000 | -1000 | 29000 | 29000 | 100% | 0 | 0 |  | 3900 | -130 | 3770 | 0 | 0
FIN | UNIDO | Terminal phase-out management plan (second tranche) | Multi-Year | ASP | QAT | PHA | 59 | INV | 13 | A | I | CFC | 12 | 12 |  |  | 2009-11-01 | 2010-12-01 | 2010-11-30 |  | 2013-12-01 | 2013-12-01 | 70000 | -896 | 69104 | 69104.43 | 100% | -0.43 | 0 |  | 5250 | -67 | 5183 | 0 | 0 | FIN |  |  |  | INV
COM | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | ASP | QAT | PHA | 59 | TAS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2014-12-01 | 2010-11-01 |  | 2014-12-01 |  | 55000 | 0 | 55000 | 0 | 0% | 55000 | 0 | 55000 | 7150 | 0 | 0 | 7150 | 0 | Project Completed, remaining funds transferred to HPMP as per Decision 65/45, respective progress is under the HPMP project | Project completed, remaining funds transferred to HPMP as per Decision 65/45, respective progress is under the HPMP project
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | ASP | QAT | PHA | 65 | INV | 18 | A | I | HCFC | 1.6 | 0 |  |  | 2011-11-01 | 2013-02-01 | 2013-11-30 | 2018-07-17 |  |  | 131157 | 0 | 131157 | 70957.01 | 54.1% | 60199.99 | 0 | 25000 | 9837 | 0 | 5322 | 4515 | 0 | UNIDO and UNEP have prepared the second tranche submission since the 73rd ExCom Meeting. Only recently a MP focal point has been appointed. UNIDO and UNEP conducted a mission August 2016. It was agreed to identify a suitable consultant to assist the government of Qatar in meeting obligations under Montreal Protocol; inclusive facilitating endorsement of submission of tranche submission. However, it was also agreed to combine 2nd and 3rd tranche and target submission for the 79th ExCom. '- Delay in implementation: Yes, due to lack of counterpart. - No recurring problem - Impact on project completion date: Yes, as per current progress completion is estimated for Jul 18 - No action required by Executive Committee | A consultant has been recruited to assist the government of Qatar in managing Montreal Protocol obligations. This includes also required actions to ensure submission of the HPMP stage-I, combined tranche 2 and 3. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (sector conversion from HCFC-142b/22 in the production of extruded polystyrene insulation boards to low GWP isobutene at Qatar Insulation, Orient Insulation and Al Kawthar Insulation) | Multi-Year | ASP | QAT | PHA | 65 | INV | 19 | A | I | HCFC | 19.1 | 19.1 |  |  | 2011-11-01 | 2012-09-01 | 2013-11-30 | 2017-07-17 |  |  | 914750 | 0 | 914750 | 914433.77 | 99.97% | 316.23 | 316.23 | 1 | 68606 | 0 | 68583 | 23 | 24 | The equipment was delivered in 2014. The installation and commissioning took place in 2015. One company, Qatar Insulation Factory, has completed the conversion. The second company, Orient, faced problems with the introduction of CO2 as co-blowing agent. A solution has been identified and this project is planned to be completed in 2017. '- Delay in implementation due to the above - No recurring problem - Impact on project completion date: Yes, as per current progress completion is estimated for Jul 17 - No action required by Executive Committee | Orient completed the installation during Q1/2017; and project to be completed during Q2/2017. - No recurring problem - No action required by Executive Committee |  |  | INV
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | ASP | QAT | PHA | 65 | TAS | 17 | A | I |  | 1.3 | 0 | 0 | 0 | 2011-11-01 | 2015-07-01 | 2013-11-01 | 2017-12-01 |  |  | 105000 | 0 | 105000 | 2370.75 | 2.258% | 102629.25 | 0 | 10262.925 | 13650 | 0 | 308.1975 | 13341.8025 | 0 | Brief progress report (actual/planned): Ministry of Environment merged with Ministry of Municipality and the ODS Officer is reinstated. Communication re-established with NOU and review of the work-plan as well as draft for the country contract are under preparation. The project committees that were established at the beginning of the project are being reformed and will start is it operation by 3rd quarter of 2016 • Legal arrangements(actual/planned): Planned by 3rd quarter of 2016 • Initial stages of project implementation(actual/planned): Started aim 2012 but stopped in 2014 without signing the country contract • Intermediate goals achieved (actual/planned): Planned by end of 2016 • Project completion and follow up: Planned by mid of 2017 • All funds disbursed (yes/no): No • Any delay?(yes/no): Yes • If Yes, reasons for delay & action plan to resolve: Internal organizational delays resulting in putting the project on hold for around 2 years • If Yes, will delay have impact on project completion date (yes/no): Yes, the original project completion is amended now to be end of 2017. Stage-I will be amended as well to be till end of 2017 instead of 2015 • Any ongoing problems (yes/no): Delay in signing the country contract • If Yes, is any action required by ExCom: No | Brief progress report (actual/planned): - Country contract drafted and expected to be signed by May 2017 - UNEP visited the country and provided technical assistance to revise the work plan and discuss implementation modality with local stakeholders - NOU put new work plan for all HPMP-1 activities and implementation starts end of April 2017 |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor the signing of the agreement by the Government and UNEP.
ONG | UNEP | Preparation of a HCFC phase-out management plan (stage II) | Multi-Year | ASP | QAT | PHA | 73 | PRP | 20 | A | I |  | 0 |  | 0 |  | 2014-11-01 |  | 2016-11-01 | 2017-12-01 |  |  | 20000 | 0 | 20000 | 0 | 0% | 20000 | 0 | 2000 | 2600 | 0 | 0 | 2600 | 0 | Brief progress report (actual/planned): - UNEP visited the country and developed work plan for the preparation of Stage-II including TORs for experts and survey teams - Country contract is drafted and being reviewed for signature - Project to be completed before end of 2017 | Brief progress report (actual/planned): - UNEP visited the country and developed work plan for the preparation of Stage-II including TORs for experts and survey teams - Country contract is drafted and being reviewed for signature - Project to be completed before end of 2017 |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor the signing of the agreements by the Government and UNEP.
ONG | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | Individual | ASP | QAT | PHA | 73 | PRP | 21 | A | I |  | 0 | 0 |  |  | 2014-11-01 | 2016-08-01 | 2016-11-30 | 2018-07-17 |  |  | 40000 | 0 | 40000 | 3163.71 | 7.909% | 36836.29 | 0 | 10000 | 2800 | 0 | 221 | 2579 | 0 | Planned submission for 81th ExCom. '-Delay in implementation due to stage I slower progress, as above. - No recurring problem - Impact on project completion date: Yes, as per current progress completion is estimated for Jul 18 - No action required by Executive Committee | A consultant has been recruited to assist the government of Qatar in managing Montreal Protocol obligations. This includes also required actions to ensure submission of the HPMP stage-II. 'Planned submission for 81th ExCom. |  |  | NON-INV
FIN | UNIDO | Implementation of the RMP: Monitoring and evaluation of sub-projects in the RMP in particular the recovery and recycling | RMP Update | ASP | QAT | REF | 34 | TAS | 02 | A | I | CFC | 3.7 | 3.7 |  |  | 2001-07-01 | 2006-03-01 | 2004-08-01 |  | 2007-12-01 | 2009-05-01 | 20000 | -3392 | 16608 | 16608.46 | 100% | -0.46 | 0 |  | 2600 | -441 | 2159 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Implementation of RMP: National recovery and recycling project | RMP Update | ASP | QAT | REF | 34 | TAS | 03 | A | I | CFC | 54.1 | 54.1 |  |  | 2001-07-01 | 2002-03-01 | 2003-08-01 |  | 2006-12-01 | 2007-12-01 | 295000 | -35 | 294965 | 294964.71 | 100% | 0.29 | 0 |  | 38350 | -5 | 38345 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Implementation of the RMP: Training of customs and Ozone Unit in monitoring and control of ODS | RMP Update | ASP | QAT | REF | 34 | TRA | 04 | A | I | CFC | 9.2 | 9.2 |  |  | 2001-07-01 | 2002-05-01 | 2003-08-01 |  | 2003-12-01 | 2004-12-01 | 50000 | -2501 | 47499 | 47499.48 | 100% | -0.48 | 0 |  | 6500 | -335 | 6165 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Implementation of RMP: Training of trainers and technicians training in good refrigerant management practices | RMP Update | ASP | QAT | REF | 34 | TRA | 05 | A | I | CFC | 19.3 | 19.3 |  |  | 2001-07-01 | 2002-08-01 | 2003-08-01 |  | 2003-12-01 | 2006-03-01 | 105000 | -5978 | 99022 | 99022.03 | 100% | -0.03 | 0 |  | 13650 | -798 | 12852 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of the Country Programme | Individual | ASP | QAT | SEV | 21 | CPG | 01 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-08-01 | 1998-02-01 |  | 1998-12-01 | 1999-09-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0 | FIN
FIN | UNIDO | Institutional Strengthening Project: Creation of the National Ozone Unit | Individual | ASP | QAT | SEV | 27 | INS | 02 | N | I |  | 0 | 0 |  |  | 1999-03-01 | 2000-11-01 | 2002-04-01 |  | 2004-10-01 | 2005-12-01 | 68450 | -4279 | 64171 | 64170.89 | 100% | 0.11 | 0 |  | 8899 | -570 | 8329 | 0 | 0 | FIN |  |  | 2002-04-01 | NON-INV
FIN | UNIDO | Extension of institutional strengthening project: phase 2 | Individual | ASP | QAT | SEV | 41 | INS | 06 | N | I |  | 0 | 0 |  |  | 2003-12-01 | 2004-11-01 | 2004-12-01 |  | 2006-09-01 | 2008-05-01 | 44500 | -1215 | 43285 | 43284.99 | 100% | 0.01 | 0 |  | 3338 | -92 | 3246 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Renewal of institutional strengthening project (phase II, second year funding) | Individual | ASP | QAT | SEV | 49 | INS | 08 | N | I |  | 0 | 0 |  |  | 2006-07-01 | 2007-01-01 | 2007-07-01 |  | 2009-06-01 | 2012-12-01 | 44500 | -1719 | 42781 | 42780.98 | 100% | 0.02 | 0 |  | 3338 | -129 | 3209 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | Renewal of institutional strengthening project (phase III) | Individual | ASP | QAT | SEV | 59 | INS | 15 | N | I |  | 0 | 0 |  |  | 2009-11-01 | 2010-12-01 | 2011-11-01 | 2017-12-01 |  |  | 48208 | 40792 | 89000 | 14484.04 | 16.27% | 74515.96 | 0 | 60000 | 3616 | 3059 | 1086 | 5589 | 0 | Progress was achieved as Qatar Government designated NOU responsible officer. Work plan on implementation and execution modalities were agreed in July 2016, back to back with MoP. UNIDO mission to train and assist NOU was organized in August 2016. NOU initiated identification of national consultants to be involved in the project execution. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | Draft terminal report in view of IS extension has been compiled and is under review. It is planned to submit IS extension request for the consideration of the 79 ExCom. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | NON-INV
FIN | UNIDO | Phasing out of CFCs at FARMEC SA | Individual | EUR | ROM | ARS | 18 | INV | 05 | A | I | CFC | 730 | 730 |  |  | 1995-11-01 | 1996-09-01 | 1997-11-01 |  | 1998-12-01 | 2001-07-01 | 895880 | -29399 | 866481 | 866481 | 100% | 0 | 0 |  | 116464 | -4000 | 112464 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of CFC-12 in the manufacture of pharmaceutical aerosols by conversion to HFC-134a propellant at MEBRA, Brasov (terminal aerosol sector project) | Individual | EUR | ROM | ARS | 44 | INV | 26 | A | I | CFC | 46.5 | 46.5 |  |  | 2004-12-01 | 2005-07-01 | 2007-02-01 |  | 2006-06-01 | 2007-09-01 | 204776 | -640 | 204136 | 204136 | 100% | 0 | 0 |  | 18430 | -58 | 18372 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparatory assistance for phase out of ODS at Spumotim flexible foam plant | Individual | EUR | ROM | FOA | 16 | PRP | 03 | A | I |  | 0 | 0 |  |  | 1995-03-01 | 1995-05-01 | 1995-06-01 |  | 1995-11-01 | 1996-05-01 | 15000 | 132 | 15132 | 15132 | 100% | 0 | 0 |  | 1950 | 17 | 1967 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 at S.C. Spumotim S.A. | Individual | EUR | ROM | FOA | 20 | INV | 09 | A | I | CFC | 30 | 30 |  |  | 1996-10-01 | 1997-02-01 | 1997-10-01 |  | 1997-12-01 | 2000-07-01 | 142293 | -83 | 142210 | 142210 | 100% | 0 | 0 |  | 18498 | -40 | 18458 | 0 | 0 | FIN
FIN | UNIDO | Preparation of an investment project in the foam sector | Individual | EUR | ROM | FOA | 23 | PRP | 13 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-09-01 | 1998-03-01 |  | 2000-05-01 | 2001-07-01 | 10000 | 1667 | 11667 | 11667 | 100% | 0 | 0 |  | 1300 | 214 | 1514 | 0 | 0 | FIN
FIN | UNIDO | Phase out of CFC 11 and CFC-12 in the manufacture of extruded polyethylene and polystyrene foams through the use of butane as a blowing agent at Romcarbon, S.A. | Individual | EUR | ROM | FOA | 27 | INV | 15 | A | I | CFC | 132.4 | 132.4 |  |  | 1999-03-01 | 2000-04-01 | 2000-10-01 |  | 2000-12-01 | 2003-05-01 | 516512 | 0 | 516512 | 516511.83 | 100% | 0.17 | 0 |  | 66816 | -11 | 66805 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a demonstration project in the methyl bromide sector | Individual | EUR | ROM | FUM | 23 | PRP | 12 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-06-01 | 1998-03-01 |  | 1999-03-01 | 2001-07-01 | 10000 | -780 | 9220 | 9220 | 100% | 0 | 0 |  | 1300 | -103 | 1197 | 0 | 0 | FIN |  |  | 1999-09-01
FIN | UNIDO | Preparation of a phase-out project in the methyl bromide sector | Individual | EUR | ROM | FUM | 30 | PRP | 18 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-05-01 | 2001-04-01 |  | 2001-10-01 | 2002-05-01 | 10000 | -322 | 9678 | 9678.05 | 100% | -0.05 | 0 |  | 1300 | -44 | 1256 | 0 | 0 | FIN
FIN | Italy | Phase out of methyl bromide in horticulture | Individual | EUR | ROM | FUM | 34 | INV | 19 | A | I | MBR | 93.9 | 93.9 | 0 |  | 2001-07-01 | 2002-02-01 | 2005-08-01 |  | 2006-12-01 | 2007-08-01 | 630517 | -996 | 629521 | 629521 | 100% | 0 | 0 | 0 | 79357 | -109.69 | 79247 | 0.31 | 0 | FIN |  | 2001 |  | Investment
FIN | UNIDO | Project preparation in the halon sector | Individual | EUR | ROM | HAL | 48 | PRP | 33 | A | I |  | 0 | 0 |  |  | 2006-04-01 | 2006-09-01 | 2007-04-01 |  | 2006-12-01 | 2007-04-01 | 15000 | -571 | 14429 | 14429.08 | 100% | -0.08 | 0 |  | 1125 | -43 | 1082 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Halon management programme | Individual | EUR | ROM | HAL | 50 | TAS | 37 | A | I | HAL | 3.5 | 3.5 |  |  | 2006-11-01 | 2007-11-01 | 2008-11-01 |  | 2008-06-01 | 2009-06-01 | 32500 | -447 | 32053 | 32053.47 | 100% | -0.47 | 0 |  | 2925 | -40 | 2885 | 0 | 0 | FIN |  |  |  | INV
CLO | UNIDO | Terminal phase-out management plan of CTC production/consumption for process agent uses | Individual | EUR | ROM | PAG | 50 | INV | 36 | A | I | CTC | 120.5 | 120.5 |  |  | 2006-11-01 | 2007-06-01 | 2007-11-01 |  |  | 2010-09-01 | 1389800 | -370032 | 1019768 | 1019768.14 | 100% | -0.14 | 0 |  | 104235 | -27752 | 76483 | 0 | 0 | CLO |  |  | 2009-12-01 | INV
FIN | UNIDO | Project preparation: CFC phase-out plan (aerosol and refrigeration) | Individual | EUR | ROM | PHA | 42 | PRP | 23 | A | I |  | 0 | 0 |  |  | 2004-04-01 | 2004-06-01 | 2006-10-01 |  | 2005-08-01 | 2005-08-01 | 10000 | -1012 | 8988 | 8988.31 | 100% | -0.31 | 0 |  | 750 | -77 | 673 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | Sweden | Assistance to prepare the national CFC phase-out plan (refrigeration servicing sector) | Individual | EUR | ROM | PHA | 43 | PRP | 24 | A | I |  | 0 |  | 0 |  | 2004-07-01 | 2004-12-01 | 2005-07-01 |  | 2005-04-01 | 2005-07-01 | 59400 | 0 | 59400 | 59400 | 100% | 0 |  |  | 7722 | 0 | 7722 | 0 | 0 | In July 2004, at the 43rd Meeting of the Executive Committee, the Government of Sweden received approval for the preparation of a national CFC phase-out plan for the servicing sector in Romania. After recruitment of consultants a mission was held in November 2004. The NCPP was prepared during the autumn 2004 and was approved at the 45th ExCom meeting in April 2005. |  | 2004
FIN | UNIDO | National CFC phase-out plan (first tranche) | Multi-Year | EUR | ROM | PHA | 45 | INV | 30 | A | I | CFC | 14.6 | 40 |  |  | 2005-04-01 | 2006-02-01 | 2006-04-01 |  | 2007-03-01 | 2010-12-01 | 159050 | 0 | 159050 | 159050.03 | 100% | -0.03 | 0 |  | 11929 | 0 | 11929 | 0 | 0 | FIN |  |  |  | INV
TRF | Sweden | National CFC phase-out plan (first tranche) | Multi-Year | EUR | ROM | PHA | 45 | TAS | 31 | A | I |  | 0 |  | 0 |  | 2005-04-01 | 2005-11-01 | 2007-04-01 |  |  | 2010-06-01 | 119500 | -83219 | 36281 | 36281 | 100% | 0 | 0 | 0 | 15535 | -10818 | 4717 | 0 | 0 | With ExCom decision 60/3 in April 2010, the remaining components of this project was formally handed over from Sweden to UNIDO and the contract with the international consultant was terminated. This progress report therefore only includes activities up to April 2010: The project has been suffering from a long delay even though a lot of progress was made during the last two years. The training of trainers for the vocation schools have been held and they have received the equipment needed for their training. Training of the existing workforce has also been conducted although in April 2010 a number of training sessions still remained to be undertaken. Up to April 2010, the Association of Refrigeration had given interim certificates to 19 Companies and 148 technicians (from which 89 are still under evaluation). A Governmental Decision had been sent for approval at all the signatory ministries and it was said that it would be published in the Official Journal no later than September 2010. The Governmental Decision was expected to be followed by a Ministerial Order which would establish the Association of Refrigeration as the interim certification body until 2011. With regards to the reuse scheme this activity is still not finalised. A number of seminars have been held to discuss the reuse scheme which raised a lot of interest. A survey was made of all the destruction facilities in the country to see which ones are incinerating based on the criteria of the Annex VI of the Regulation 1005/2009 regarding the ozone depleting substances. GreenWEEE was found to be the biggest integrated treatment plant for electric and electronic equipment waste (WEEE) in Romania and one of the most modern in Europe. They have 3 collection centers in the country (Lasi, Timisoara, Bucuresti). GreenWEEE can collect all the WEEE categories mentioned in the legislation (including large household appliances- refrigerators, freezers). The NOU has drafted a report for recycling systems in accordance with the EU existing legislation and based on the key aspects underlined by the consultation with the companies with interests in this field. Due to the existing economical situation the market is rather small. Also, meetings have been held with the customs and an draft instructions handbook was prepared based on the EU regulations. The additional delay is due to the initial long delay and the difficulties to speed up the process as much as needed to stick to the revised time plan. Also, the Governmental Decision was delayed and until September 2010 which further delayed the implementation of some of the measures proposed therein. Sweden also estimate that it will take time to get the reclamation system fully operational, something which will cause additional delay. Even if Romania had come quite far in April 2010 by holding stakeholder workshops and discussions and survey among the destruction facilities, this is much delayed already and it will take additional time to get it fully operational. The Project Completion Report (PCR) for the Swedish contribution was submitted to MLF in Dec 2010. |  | 2005 | 2008-12-01
FIN | UNIDO | National CFC phase-out plan (second tranche) | Multi-Year | EUR | ROM | PHA | 48 | INV | 34 | A | I | CFC | 35.8 | 35.8 |  |  | 2006-04-01 | 2006-11-01 | 2007-04-01 |  | 2010-12-01 | 2011-05-01 | 236750 | 0 | 236750 | 236750.01 | 100% | -0.01 | 0 |  | 17756 | 0 | 17756 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National CFC phase-out plan (third tranche) | Multi-Year | EUR | ROM | PHA | 51 | INV | 38 | A | I | CFC | 48.9 | 48.9 |  |  | 2007-03-01 | 2007-09-01 | 2008-03-01 |  | 2010-12-01 | 2010-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 2250 | 0 | 2250 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National CFC phase-out plan (first tranche, transferred from Sweden) | Multi-Year | EUR | ROM | PHA | 60 | TAS | 41 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-07-01 | 2011-04-01 |  | 2010-12-01 | 2012-02-01 | 83219 | -898 | 82321 | 82320.82 | 100% | 0.18 | 0 |  | 6241 | -67 | 6174 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a closure project in the production of CFC/CTC/MBR | Individual | EUR | ROM | PRO | 45 | PRP | 28 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-09-01 | 2006-04-01 |  | 2005-12-01 | 2006-12-01 | 25000 | -3848 | 21152 | 21151.72 | 100% | 0.28 | 0 |  | 1875 | -289 | 1586 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Sector plan for production sector | Multi-Year | EUR | ROM | PRO | 47 | INV | 32 | A | I | MBR | 0 | 0 | 5 | 5 | 2005-11-01 | 2006-04-01 | 2006-07-01 |  | 2006-12-01 | 2011-12-01 | 3200000 | -150 | 3199850 | 3199850.03 | 100% | -0.03 | 0 |  | 240000 | -11 | 239989 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Sector plan for production sector (second tranche) | Multi-Year | EUR | ROM | PRO | 50 | INV | 35 | A | I |  | 0 | 0 |  |  | 2006-11-01 | 2007-01-01 | 2007-11-01 |  | 2007-06-01 | 2012-10-01 | 900000 | -41472 | 858528 | 858528.16 | 100% | -0.16 | 0 |  | 67500 | -3110 | 64390 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Sector plan for production sector (third tranche) | Multi-Year | EUR | ROM | PRO | 52 | INV | 39 | A | I | CTC | 0 | 0 | 170 | 170 | 2007-07-01 | 2007-09-01 | 2008-07-31 |  | 2007-12-01 | 2008-07-01 | 1000000 | 0 | 1000000 | 1000000 | 100% | 0 | 0 |  | 75000 | 0 | 75000 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Sector plan for production sector (fourth tranche) | Multi-Year | EUR | ROM | PRO | 53 | INV | 40 | A | I |  | 0 | 0 |  |  | 2007-11-01 | 2008-06-01 | 2008-11-30 |  | 2010-12-01 | 2012-11-01 | 1200000 | 0 | 1200000 | 1199999.88 | 100% | 0.12 | 0 |  | 90000 | 0 | 90000 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of investment project for phasing out CFC-11 at refrigerator plant at mechanical enterprises SADU and ARCTIC | Individual | EUR | ROM | REF | 15 | PRP | 02 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-04-01 | 1995-06-01 |  | 1996-07-01 | 1998-08-01 | 50000 | -4907 | 45093 | 45093 | 100% | 0 | 0 |  | 6500 | -647 | 5853 | 0 | 0 | FIN
FIN | UNIDO | Phase out ODS at the domestic refrigeration factory Arctic S.A. | Individual | EUR | ROM | REF | 18 | INV | 06 | A | R | CFC | 206 | 206.7 |  |  | 1995-11-01 | 1996-10-01 | 1997-05-01 |  | 1997-05-01 | 2000-07-01 | 1095300 | -48009 | 1047291 | 1047291 | 100% | 0 | 0 |  | 142389 | -6457 | 135932 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in the domestic and commercial refrigeration sector | Individual | EUR | ROM | REF | 18 | PRP | 07 | A | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-03-01 | 1996-05-01 |  | 1999-03-01 | 2000-07-01 | 20000 | -808 | 19192 | 19192 | 100% | 0 | 0 |  | 2600 | -109 | 2491 | 0 | 0 | FIN |  |  | 1999-03-01
CLO | UNIDO | Conversion of commercial refrigeration equipment to phase out CFC-12, HCFC-502 and CFC-11 at Technofrig S.A. | Individual | EUR | ROM | REF | 19 | INV | 08 | A | I | CFC | 6.92 | 6.92 |  |  | 1996-05-01 | 1997-03-01 | 1999-06-01 |  |  | 2000-07-01 | 297768 | -255677 | 42091 | 42091 | 100% | 0 | 0 |  | 38710 | -33247 | 5463 | 0 | 0 | CLO |  |  | 1999-07-01
FIN | UNIDO | Phasing out CFC-11 and CFC-12 in the production of domestic refrigerators and replacing them by cyclopentane and HFC-134a at Ratmil, Uzine Mecanica Sadu | Individual | EUR | ROM | REF | 20 | INV | 10 | A | I | CFC | 73.3 | 73.3 |  |  | 1996-10-01 | 1997-09-01 | 1998-10-01 |  | 1998-12-01 | 2002-05-01 | 937859 | 0 | 937859 | 937859.21 | 100% | -0.21 | 0 |  | 121922 | 0 | 121922 | 0 | 0 | FIN
FIN | Austria | Establishment of a training centre for commercial refrigeration service technicians at Comservice S.A. |  | EUR | ROM | REF | 20 | TRA | 11 | A | I |  | 10 |  |  |  | 1996-10-01 |  | 1997-10-01 |  | 1999-02-01 | 1999-05-01 | 131790 | 0 | 131790 | 131790 | 100% | 0 |  | 0 |  |  |  | 0 |  |  |  | 1996
FIN | UNIDO | Preparation of a refrigerant management plan | Individual | EUR | ROM | REF | 24 | PRP | 14 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-09-01 | 1999-04-01 |  | 1998-09-01 | 2000-12-01 | 30000 | -1043 | 28957 | 28957 | 100% | 0 | 0 |  | 3900 | -142 | 3758 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: recovery and recycling | RMP | EUR | ROM | REF | 28 | TAS | 16 | A | I | CFC | 50 | 50 |  |  | 1999-07-01 | 2000-07-01 | 2002-02-01 |  | 2001-12-01 | 2003-04-01 | 373840 | 0 | 373840 | 373840.46 | 100% | -0.46 | 0 |  | 48599 | -69 | 48530 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: training of customs officers and development of criteria for ODS and ODS consuming equipment imports | RMP | EUR | ROM | REF | 28 | TRA | 17 | A | I |  | 0 | 0 |  |  | 1999-07-01 | 1999-11-01 | 2001-10-01 |  | 2002-08-01 | 2003-10-01 | 23100 | -1349 | 21751 | 21750.58 | 100% | 0.42 | 0 |  | 3003 | -180 | 2823 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: training for good practices in refrigeration | RMP | EUR | ROM | REF | 28 | TRA | 19 | A | I |  | 0 | 0 |  |  | 1999-07-01 | 1999-12-01 | 2001-06-01 |  | 2001-01-01 | 2001-06-01 | 70000 | 0 | 70000 | 70000.07 | 100% | -0.07 | 0 |  | 9100 | 0 | 9100 | 0 | 0 | FIN
FIN | UNIDO | Preparation of Country Programme | Individual | EUR | ROM | SEV | 11 | CPG | 01 | A | I |  | 0 | 0 |  |  | 1993-11-01 | 1994-11-01 | 1994-11-01 |  | 1995-07-01 | 1998-08-01 | 80000 | -23457 | 56543 | 56543 | 100% | 0 | 0 |  | 10400 | -3061 | 7339 | 0 | 0 | FIN
FIN | UNIDO | Creation of an Ozone Secretariat | Individual | EUR | ROM | SEV | 17 | INS | 04 | N | I |  | 0 | 0 |  |  | 1995-07-01 | 1997-12-01 | 1998-07-01 |  | 2003-12-01 | 2005-01-01 | 168443 | -80350 | 88093 | 88092.81 | 100% | 0.19 | 0 |  | 21898 | -10464 | 11434 | 0 | 0 | FIN |  |  | 2000-01-01 | NON-INV
FIN | UNIDO | Country programme update | Individual | EUR | ROM | SEV | 36 | CPG | 20 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-11-01 | 2003-07-01 |  | 2004-01-01 | 2004-04-01 | 60000 | -356 | 59644 | 59644 | 100% | 0 | 0 |  | 7800 | -59 | 7741 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Extension of institutional strengthening project: phase II | Individual | EUR | ROM | SEV | 45 | INS | 29 | N | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-11-01 | 2007-04-01 |  | 2007-12-01 | 2011-05-01 | 145984 | -981 | 145003 | 145003.27 | 100% | -0.27 | 0 |  | 10949 | -74 | 10875 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Preparation of investment projects in the solvent sector | Individual | EUR | ROM | SOL | 39 | PRP | 21 | A | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-10-01 | 2004-04-01 |  | 2004-10-01 | 2005-05-01 | 15000 | -785 | 14215 | 14215.32 | 100% | -0.32 | 0 |  | 1125 | -61 | 1064 | 0 | 0 | FIN
FIN | UNIDO | Terminal umbrella project for the phase-out of ODS solvents | Individual | EUR | ROM | SOL | 41 | INV | 22 | A | I | CTC | 11.1 | 11.1 |  |  | 2003-12-01 | 2004-05-01 | 2004-12-01 |  | 2005-12-01 | 2007-05-01 | 220615 | -6247 | 214368 | 214367.81 | 100% | 0.19 | 0 |  | 19855 | -562 | 19293 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a terminal umbrella project to phase out CTC | Individual | EUR | ROM | SOL | 44 | PRP | 27 | A | I |  | 0 | 0 |  |  | 2004-12-01 | 2005-04-01 | 2005-12-01 |  | 2006-12-01 | 2007-12-01 | 20000 | -900 | 19100 | 19099.72 | 100% | 0.28 | 0 |  | 1500 | -67 | 1432 | 1 | 0 | FIN
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | AFR | RWA | PHA | 48 | PRP | 10 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-04-01 | 2007-04-01 |  | 2007-12-01 | 2010-01-01 | 12000 | -3806 | 8194 | 8194 | 100% | 0 | 0 | 0 | 900 | -285.45 | 614.55 | 0 | 0 | Financially completed in 2010. |  | 2006 |  | Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | RWA | PHA | 48 | PRP | 11 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-06-01 | 2007-04-01 |  | 2008-11-01 | 2009-11-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 |  | 2340 | 0 | 2340 | 0 | 0
FIN | UNDP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | RWA | PHA | 53 | INV | 14 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-11-01 | 2009-11-01 |  | 2010-12-01 | 2013-06-01 | 124500 | 0 | 124500 | 124500 | 100% | 0 | 0 | 0 | 11205 | 0 | 11205 | 0 | 0 | Financially completed in 2013. |  | 2007 |  | Investment
FIN | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-year | AFR | RWA | PHA | 53 | TAS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-03-01 |  | 2009-03-01 | 2010-12-01 | 110000 | 0 | 110000 | 110000 | 100% | 0 | 0 |  | 14300 | 0 | 14300 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | RWA | PHA | 55 | PRP | 15 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-03-01 | 2009-07-01 |  | 2011-07-01 | 2012-07-01 | 85000 | -5000 | 80000 | 80000 | 100% | 0 | 0 |  | 11050 | -650 | 10400 | 0 | 0
FIN | UNDP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | RWA | PHA | 57 | INV | 17 | N | I | CFC | 4.6 | 4.6 | 0 | 0 | 2009-04-01 | 2010-04-01 | 2011-03-01 |  | 2012-12-01 | 2013-06-01 | 43500 | -11414.17 | 32085.83 | 32086 | 100% | -0.17 | 0 | 0 | 3915 | -1027.28 | 2887.74 | -0.02 | 0 | Financially completed in 2013. | Completed in 2012. | 2009 |  | Investment
FIN | UNEP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | RWA | PHA | 57 | TAS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-09-01 | 2010-03-01 |  | 2013-04-01 | 2014-06-01 | 67000 | -6987 | 60013 | 60013 | 100% | 0 | 0 |  | 8710 | -908.31 | 7801.69 | 0 | 0
COM | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | RWA | PHA | 64 | INV | 18 | A | I | HCFC | 0.2 | 0.2 |  |  | 2011-07-01 | 2012-11-01 | 2016-07-31 |  | 2016-12-01 |  | 55000 | 0 | 55000 | 52398.73 | 95.27% | 2601.27 | 0 | 1 | 4950 | 0 | 4716 | 234 | 0 | Project was successfully completed in Dec 16. | Financial closure is being initiated. |  |  | INV
COM | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | RWA | PHA | 64 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-04-01 | 2013-07-01 |  | 2016-12-01 |  | 42000 | 0 | 42000 | 42000 | 100% | 0 | 0 |  | 5460 | 0 | 5460 | 0 | 0 | Project completed | Project completed
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | AFR | RWA | PHA | 70 | TAS | 22 | A | I |  | 0.2 |  | 0 |  | 2013-07-01 | 2014-07-01 | 2016-07-01 | 2017-10-01 |  |  | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 | Brief progress report (actual/planned): The NOU implemented a number of activities under the HPMP including trainings for law enforcement officers and refrigeration technicians, and public awareness. The NOU conducted two training workshops for 30 custom officers to enhance the capacity of the law enforcement officers on motoring illegal trade. The NOU conducted training for 60 refrigerant technicians. The NOU procured equipment and distributed recovery kits to major workshops and key importers for testing the quality of the refrigerants before they purchase them. The NOU conducted monitoring of the HCFC quotas and illegal importation of ODSs. Legal arrangements (actual/planned): The SSFA was drafted and signed by UNEP and the Government of Rwanda in February, 2014.___ First mission (actual/planned): CAP visited the Country in June, 2014___ TOR completed(actual/planned):N/A ___ First disbursement date (actual/planned): First disbursement was made in July, 2014___ All funds disbursed (yes/no): No___ Any delay? (yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): N/A___ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: N/A___ | Brief progress report (actual/planned): The NOU registered all importers of HCFCs and organized one stakeholders meeting in Feb 2016 to coordinate and allocate licenses and quotas. The NOU continues to monitor imports and trade of ODS and ODS related equipment.
ONG | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Individual | AFR | RWA | PHA | 75 | TAS | 25 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-03-01 | 2017-03-01 | 2017-03-01 |  |  | 30000 | 0 | 30000 | 21185 | 70.62% | 8815 | 8815 | 881.5 | 3900 | 0 | 2754.05 | 1145.95 | 1145.95 | Brief progress report (actual/planned):The Terms of Reference (ToR) for hiring the international consultant was prepared, cleared by the management and advertised in January 2016. The international consultant was recruited by UNEP to verify the national consumption in relation to the targets as set out in the Agreement between ExCom and Government of Rwanda, following the relevant decisions of the ExCom and guidelines for the verification of national consumption targets for the multi-year agreements. The consultant prepared and presented the draft work plan which included timeline for conducting the verification as well as tasks and roles and responsibilities of each concerned stakeholders in the verification process. The consultant also informed the NOU about support/cooperation that was required from various stakeholders. The consultant also reviewed official statistics on import and export maintained by different sources and analyzed and compare those statistics. In addition, the consultant conducted the necessary on-site visits and interviews, and analyzed and cross-check various data collected from different sources. The reports was produced in English and provides detailed data demonstrating and confirming whether the consumption targets in the Agreement were achieved, whether there is existence of an operational licensing and quota system for HCFC imports and exports and whether the system is capable to ensure the country's compliance with the targets as set out in the Agreement between Rwanda and the ExCom. The verification report was finalised and submitted to Ex-com 77 | The project was completed.NOU is implementing the recommendations from the verification report
ONG | UNIDO | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | AFR | RWA | PHA | 77 | INV | 27 | A | I | HCFC | 0.2 | 0 |  |  | 2016-11-01 |  | 2020-12-31 | 2020-12-31 |  |  | 55000 | 0 | 55000 | 0 | 0% | 55000 | 0 | 10000 | 4950 | 0 | 0 | 4950 | 0 | Approved on the understanding that if Rwanda were to decide to proceed with retrofits and associated servicing using flammable and toxic refrigerants in refrigeration and air conditioning equipment originally designed for non flammable substances, it would do so assuming all associated responsibilities and risks and only in accordance with the relevant standards and protocols; and that UNEP would report on the progress made in implementing the recommendations in the verification report at the time of the next tranche submission. | Approved on the understanding that if Rwanda were to decide to proceed with retrofits and associated servicing using flammable and toxic refrigerants in refrigeration and air conditioning equipment originally designed for non flammable substances, it would do so assuming all associated responsibilities and risks and only in accordance with the relevant standards and protocols; and that UNEP would report on the progress made in implementing the recommendations in the verification report at the time of the next tranche submission. -Milestone 1: Working arrangements agreed -Milestone 2: Expert trained in refrigerant quality workshop in Tanzania
ONG | UNEP | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | AFR | RWA | PHA | 77 | TAS | 26 | A | I |  | 0 |  | 0 |  | 2016-12-01 |  | 2018-12-01 | 2018-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 3000 | 3900 | 0 | 0 | 3900 | 0 | Newly approved project. | Brief progress report (actual/planned): The project was approved in Dec 2016. The licensing and quota system are in place and operational. The NOU continues to monitor imports and trade of ODS and ODS related equipment. Collection of the 2016 data on ODS imports and consumption has been completed and is being analyzed for submission. NOU commenced preparation of national legislative requirement processes in planning for ratification of Kigali amendment ___ Legal arrangements (actual/planned): The SSFA was drafted and sent to the Government of Rwanda for signature. ___Initial stages of project implementation (actual/planned): __Yes_ Intermediate goals achieved (actual/planned): _No__ Project completion and follow up: ___ First disbursement date (actual/planned): __No ____. All funds disbursed (yes/no): No__ Any delay? (yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: __N/A_
FIN | UNDP | Formulation of a refrigerant management plan | Individual | AFR | RWA | REF | 36 | PRP | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-01-01 | 2003-04-01 |  | 2003-12-01 | 2005-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Formulation of the investment components of the RMP | Individual | AFR | RWA | REF | 39 | PRP | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2004-12-01 | 2005-12-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 375 | 0 | 375 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2003 |  | Investment
FIN | UNDP | Implementation of the RMP: refrigeration manufacturing and centralized recovery and recycling of refrigerants | RMP-Component | AFR | RWA | REF | 41 | TAS | 08 | N | I | CFC | 12.9 | 12.9 | 0 | 0 | 2003-12-01 | 2006-01-01 | 2006-12-01 |  | 2008-12-01 | 2010-01-01 | 118758 | -15641.68 | 103116.32 | 103116 | 100% | 0.32 | 0 | 0 | 10688 | -1407.72 | 9280.249 | 0.030999 | 0 | Financially completed in 2010. |  | 2003 |  | Investment
FIN | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | AFR | RWA | REF | 41 | TAS | 09 | A | I | CFC | 2.2 | 0 | 0 | 0 | 2003-12-01 | 2005-06-01 | 2006-12-01 |  | 2008-12-01 | 2012-01-01 | 20000 | -10000 | 10000 | 10000 | 100% | 0 | 0 |  | 2600 | -1300 | 1300 | 0 | 0
FIN | UNEP | Implementation of the RMP: train the trainer programme for refrigeration service technicians | Individual | AFR | RWA | REF | 41 | TRA | 06 | A | I | CFC | 5.4 | 5.4 | 0 | 0 | 2003-12-01 | 2004-08-01 | 2004-12-01 |  | 2006-12-01 | 2012-04-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Implementation of the RMP: training programme for customs officers | Individual | AFR | RWA | REF | 41 | TRA | 07 | A | I | CFC | 5.4 | 5.4 | 0 | 0 | 2003-12-01 | 2004-08-01 | 2004-12-01 |  | 2006-12-01 | 2013-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Formulation of national phase out strategy | Individual | AFR | RWA | SEV | 35 | TAS | 01 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-10-01 | 2003-08-01 |  | 2003-12-01 | 2007-03-01 | 50000 | -35000 | 15000 | 15000 | 100% | 0 | 0 |  | 6500 | -4550 | 1950 | 0 | 0
FIN | UNEP | Establishment of the Ozone Unit | Individual | AFR | RWA | SEV | 36 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2004-01-01 | 2003-04-01 |  | 2005-01-01 | 2007-03-01 | 22000 | 0 | 22000 | 22000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Establishment of the Ozone Unit | Individual | AFR | RWA | SEV | 41 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2007-02-01 | 2005-12-01 |  | 2007-12-01 | 2008-12-01 | 64600 | 0 | 64600 | 64600 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase II) | Individual | AFR | RWA | SEV | 50 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-12-01 | 2008-11-01 |  | 2008-12-01 | 2010-12-01 | 60000 | -3852.45 | 56147.55 | 56147.55 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | AFR | RWA | SEV | 57 | INS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-03-01 | 2011-03-01 |  | 2011-03-01 | 2011-06-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV: 7/2011-6/2013) | Individual | AFR | RWA | SEV | 64 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2011-12-01 | 2013-06-01 |  | 2013-04-01 | 2014-07-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase V: 7/2013-6/2015) | Individual | AFR | RWA | SEV | 70 | INS | 21 | A | I |  | 0 |  | 0 |  | 2013-07-01 | 2014-02-01 | 2015-06-01 |  | 2015-09-01 | 2015-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | AFR | RWA | SEV | 74 | TAS | 23 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-04-01 | 2016-05-01 | 2017-05-01 |  |  | 40000 | 0 | 40000 | 36.1 | 0.09025% | 39963.9 | 39963.9 | 3996.39 | 5200 | 0 | 4.693 | 5195.307 | 5195.307 | Brief progress report (actual/planned): The first stakeholders meeting was organized by the NOU in May 2016 in Kigali with the main goal to agree on the plan for the Survey of ODS alternatives at the national level and obtain support of main national stakeholders. The meeting was attended by 30 participants. One National Consultant was hired in June 2016 by the NOU to support the data collection. The National Consultant assisted the NOU in the identification of the current use of ODS alternatives by substance/sector and collection of import/export data for the substances for the past a couple of years. The National Consultant also provided support in establishing growth patterns in use by substance/sector and in compiling data on available ODS alternatives for various applications. The NOU and the National Consultant drafted and cross checked the information to ensure the completion of end-user surveys, collection, analysis, and aggregation of consumption data. The various sections of the report were drafted. The second stakeholders meeting was organized by the NOU in November 2016 in Kigali with the main goal to organise consultations with representatives of the government and private sector to finalize the outcomes of the Survey of ODS alternatives and discuss potential opportunities for introduction of those alternatives in the country. The draft report was prepared by the NOU and the National Consultant. It was reviewed and finalized based on the format approved by ExCom decision 75/67 as contained in document UNEP/OzL.Pro/ExCom/75/77/Rev.1 after incorporating inputs/ comments raised during National Stakeholders’ workshop. The final report has been submitted to UNEP for final review and submission to MLFS. The NOU participated in the ODS Alternative Thematic workshop held in December 2016 to refine the draft report according to the revised template for the report. The report has been finally submitted to UNEP. Legal arrangements(actual/planned): The SSFA was drafted and signed by UNEP and the Government of Rwanda in February 2016___Initial stages of project implementation(actual/planned): _Yes__ Intermediate goals achieved (actual/planned): Yes___ Project completion and follow up: _No__ First disbursement date (actual/planned): _April 2016__ All funds disbursed (yes/no): No___ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): __N/A_ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): The NOU incorporated comments from UNEP ROA and Paris and re-submitted final ODS survey report.
ONG | UNEP | Extension of the institutional strengthening project (phase VI: 12/2015-11/2017) | Individual | AFR | RWA | SEV | 75 | INS | 24 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-05-01 | 2017-11-01 | 2018-03-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 85000 | 8500 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): _ The licensing and quota systems are in place and operational. The NOU registered all importers of HCFC for 2016, advertised for quota allocation for 2016 HCFC importation and conducted two inspection visits to various boarders to check how customs officers are enforcing the control measures of HCFC importation. The NOU trained 40 custom officers and 60 RAC technicians. The NOU submitted 2015 Country Programme and Article 7 Data reports. The NOU celebrated 2016 International Ozone Day and conducted several awareness activities. The NOU also participated in all Montreal Protocol meetings organized in 2016.___ Legal arrangements(actual/planned): The SSFA was drafted and signed by UNEP and the Government of Rwanda in April 2016__Initial stages of project implementation(actual/planned): _Yes__ Intermediate goals achieved (actual/planned): _Yes__ Project completion and follow up: No___ First disbursement date (actual/planned): _May 2016__ All funds disbursed (yes/no): _No__ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: __N/A_ If Yes, will delay have impact on project completion date (yes/no): _Yes__ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): The NOU continues to monitor imports and trade of ODS and ODS related equipment. Collection of the 2016 data on ODS imports and consumption has been completed and is being analyzed for submission. NOU commenced preparation of national legislative requirement processes in planning for ratification of Kigali amendment.
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | ASP | SAM | PHA | 50 | PRP | 08 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2007-11-01 |  | 2008-06-01 | 2008-09-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | ASP | SAM | PHA | 53 | INV | 11 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 | 2009-10-01 | 2009-11-01 |  | 2010-12-01 | 2014-02-01 | 45000 | -1050 | 43950 | 43950 | 100% | 0 | 0 | 0 | 4050 | -94.5 | 3955.5 | 0 | 0 | Financially completed in 2014. |  | 2007 |  | Investment
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | ASP | SAM | PHA | 53 | TAS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-07-01 | 2009-03-01 |  | 2009-12-01 | 2010-12-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 |  | 7150 | 0 | 7150 | 0 | 0
FIN | UNDP | Terminal phase-out management plan (second tranche) | Multi-Year | ASP | SAM | PHA | 57 | INV | 13 | N | I | CFC | 0 | 0 | 0 | 0 | 2009-04-01 |  | 2011-03-01 |  | 2013-12-01 | 2014-05-01 | 30000 | -30000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 2700 | -2700 | 0 | 0 | 0 | Financially completed in 2014. | Completed in 2013. | 2009 |  | Investment
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | ASP | SAM | PHA | 57 | TAS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-07-01 | 2010-03-01 |  | 2010-12-01 | 2011-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0
COM | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, first tranche, Samoa) | Multi-Year | ASP | SAM | PHA | 63 | TAS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2012-04-01 | 2015-03-01 |  | 2014-12-01 |  | 76250 | 0 | 76250 | 71251.86 | 93.45% | 4998.14 | 0 | 4998 | 9913 | 0 | 9263.209 | 649.791 | 0 | Project completed. | Project completed.
ONG | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, second tranche, Samoa) | Multi-year | ASP | SAM | PHA | 74 | TAS | 18 | A | I |  | 0.1 |  | 0 |  | 2015-05-01 | 2016-04-01 | 2020-05-01 | 2020-12-01 |  |  | 57400 | 0 | 57400 | 0 | 0% | 57400 | 57400 | 5740 | 7462 | 0 | 0 | 7462 | 7462 | Brief progress report (actual/planned): The SSFA was signed by UNEP and the Government of Samoa in February 2016. The first payment under the second tranche was also made to the country in April 2016. The licensing and quota system was implemented in 2016. The NOU worked with concerned ministries to put in place the ban of HCFC-bsaed equipment. UNEP conducted a misison in September 2016 to follow-up project implementation and participated in update RAC training workshop, which was delivered by national trainers. UNEP worked closely with the NOU to engage multi-stakeholders in the implementation of HPMP, second tranche to synergize HPMP with other on-going environmental policies/projects e.g. PALS, Samoa Pathway. 2015 CP data was submitted to MLFS online. Legal arrangements (actual/planned): The SSFA was signed in February 2016. First Mission: September 2016. TOR completed: Not applicable First disbursement date: April 2016. All funds disbursed (yes/no): No. Any delay? (yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): UNEP keeps regular communications with the country to expedite HPMP implementation as per the agreed work plan.
FIN | UNEP | Implementation of the RMP: training of customs officials and NOU staff | Individual | ASP | SAM | REF | 32 | TRA | 03 | A | I | CFC | 2 | 2 | 0 | 0 | 2000-12-01 | 2001-03-01 | 2001-06-01 |  | 2003-09-01 | 2003-12-01 | 53500 | -9474 | 44026 | 44026 | 100% | 0 | 0 |  | 6955 | -1232 | 5723 | 0 | 0 |  |  |  | 2003-06-01
FIN | UNEP | Implementation of the RMP: training of refrigeration service technicians | Individual | ASP | SAM | REF | 32 | TRA | 04 | A | I | CFC | 1.8 | 1.8 | 0 | 0 | 2000-12-01 | 2001-03-01 | 2001-02-01 |  | 2002-10-01 | 2003-10-01 | 48800 | -5864 | 42936 | 42936 | 100% | 0 | 0 |  | 6344 | -762.32 | 5581.68 | 0 | 0 |  |  |  | 2002-12-01
FIN | UNEP | Country programme preparation | Individual | ASP | SAM | SEV | 12 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-10-01 | 1995-06-01 |  | 1997-05-01 | 1999-02-01 | 35000 | -4850 | 30150 | 30150 | 100% | 0 | 0 |  | 4550 | -630.5 | 3919.5 | 0 | 0
FIN | UNEP | Establishment of the National Ozone Committee | Individual | ASP | SAM | SEV | 22 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-04-01 | 2000-06-01 |  | 2003-04-01 | 2003-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Preparation of the refrigerant management plan | RMP | ASP | SAM | SEV | 25 | PRP | 05 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-05-01 | 2000-12-01 |  | 2000-12-01 | 2002-06-01 | 0 | 30000 | 30000 | 30000 | 100% | 0 | 0 |  | 0 | 3900 | 3900 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase 2) | Individual | ASP | SAM | SEV | 39 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-06-01 | 2005-04-01 |  | 2006-01-01 | 2009-05-01 | 26000 | 0 | 26000 | 26000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | ASP | SAM | SEV | 47 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-03-01 | 2007-12-01 |  | 2007-12-01 | 2007-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | ASP | SAM | SEV | 53 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-07-01 | 2009-11-01 |  | 2010-11-01 | 2011-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase V) | Individual | ASP | SAM | SEV | 58 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2009-12-01 | 2011-10-01 |  | 2011-12-01 | 2011-12-01 | 35000 | 25000 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase VI: 11/2011-10/2013) | Individual | ASP | SAM | SEV | 64 | INS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-07-01 | 2013-10-01 |  | 2013-12-01 | 2014-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase VII: 11/2013-10/2015) | Individual | ASP | SAM | SEV | 70 | INS | 17 | A | I |  | 0 |  | 0 |  | 2013-07-01 | 2014-05-01 | 2015-10-01 |  | 2015-12-01 | 2016-04-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
ONG | UNEP | Extension of institutional strengthening project (phase VIII: 11/2015-10/2017) | Individual | ASP | SAM | SEV | 74 | INS | 19 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-04-01 | 2017-10-01 | 2018-02-01 |  |  | 60000 | 0 | 60000 | 15023.6 | 25.04% | 44976.4 | 44976.4 | 4497.64 | 0 | 0 | 0 | 0 | 0 | Brief Progress report (actual/planned): The SSFA was signed between UNEP and the Government of Samoa in March 2016. The first payment was made to country in April 2016. The NOU has been responsible for the management of all Montreal Protocol activities. The operation of the NOU was going on well with stable and highly skilled NOO. The license/quota system has been enforced in 2016. NOU also coordinated and facilitated the implementation of HPMP and ODS Alternative Survey. Refrigeration Association registered and actively functioning. NOO organised and manged quarterly meetings held with national ozone steering committee. The NOU is institutionalised into as part of government and with the NOO supervised and managed under designated high level public sector officers. The NOU also organized the 2016 ozone day celebration, and actively joined the regional and global ozone related meetings e.g. the network meeting, OEWG and the MOP meetings. 2015 Article 7 and CP data were submitted to the Ozone Secretariat and MLFS respectively. Legal arrangements(actual/planned): The SSFA was signed in March 2016. Initial stages of project implementation(actual/planned): Nov 2015/Mar 2016. Intermediate goals achieved (actual/planned): Project progressing Satisfactorily, Compliance (2015) sustained. Project completion and follow up: Not applicable. First disbursement date (actual/planned): April 2016. All funds disbursed (yes/no): No. Any delay?(yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: N/A | Brief Progress report (actual/planned): Country continues to enforce the licensing and quota system. There are 2 remaining payments to be disbursed to the country. Projecct will be completed in January 2018.
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | ASP | SAM | SEV | 75 | TAS | 20 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-12-01 | 2016-12-01 | 2017-06-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 40000 | 4000 | 5200 | 0 | 0 | 5200 | 5200 | Brief progress report (actual/planned): The SSFA was signed by UNEP and the Government of Samoa in November 2016. The first payment was made to the country in December 2016. NOU attended the training for conducting natiional surveys as part of Thematic workshop for Asia and the Pacific in June 2016. The national stakeholder workshop was organzied during UNEP mission in September 2016. The survey methodology and questionnaire have been finalized and agreed. The consultant was recruited by the Government to conduct the dada collection. The data collection was on-going. Legal arrangements(actual/planned): the SSFA was signed in November 2016. Initial stages of project implementation(actual/planned): June 2016. Intermediate goals achieved (actual/planned): Not applicable. Project completion and follow up: Not applicable. First disbursement date (actual/planned): December 2016. All funds disbursed (yes/no): No. Any delay?(yes/no): Yes. If Yes, reasons for delay & action plan to resolve: Delay in drafting and signing of SSFA which is not duplicate with the EC project. If Yes, will delay have impact on project completion date (yes/no): No. Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): The local consultant assisted the NOU in the identification of the current use of ODS alternatives by substance/sector and collection of import/export data for the substances for the past a couple of years. The local consultant also provided support in establishing growth patterns in use by substance/sector and in compiling data on available ODS alternatives for various applications. The draft report will be prepared based on the format approved by ExCom decision 75/67 as contained in document UNEP/OzL.Pro/ExCom/75/77/Rev.1.
FIN | UNIDO | Preparation for HCFC phase-out investment activities (foam sector) | Individual | ASP | SAU | FOA | 60 | PRP | 07 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-06-01 | 2011-04-30 |  | 2010-12-01 | 2013-12-01 | 80000 | -681 | 79319 | 79319.34 | 100% | -0.34 | 0 |  | 6000 | -51 | 5949 | 0 | 0 | FIN
ONG | UNIDO | Phase-out of HCFC-22 and HCFC-142b from the manufacture of extruded polystyrene panel at Line #2 in Arabian Chemical Company | Multi-Year | ASP | SAU | FOA | 62 | INV | 11 | A | I | HCFC | 28.9 | 28.9 |  |  | 2010-12-01 | 2010-12-01 | 2012-12-31 | 2018-06-18 |  |  | 615323 | 0 | 615323 | 355570.68 | 57.79% | 259752.32 | 6010.87 | 50000 | 46149 | 0 | 26668 | 19481 | 451 | Activities planned but not implemented, reasons and strategy: As reported earlier, funds reallocated from the NPP to HPMP were partially used to cover the costs of this project in order to fulfill ExCom requirements to financially close the NPP, since the certification and code of practice conducted by UNEP was delayed. Remaining funds under this tranche will be used for the purpose approved by the ExCom when reallocation of funds was decided. Any impact on project completion date: Yes | Activities planned but not implemented, reasons and strategy: As reported earlier, funds reallocated from the NPP to HPMP were partially used to cover the costs of this project in order to fulfill ExCom requirements to financially close the NPP, since the certification and code of practice conducted by UNEP were delayed. Remaining funds under this tranche will be used for the purpose approved by the ExCom when reallocation of funds was decided. Any impact on project completion date: Yes |  |  | INV
COM | Japan | Phase-out of HCFC-22 and HCFC-142b from the manufacture of extruded polystyrene panel at Line #2 in Arabian Chemical Company | Individual | ASP | SAU | FOA | 62 | INV | 12 | A | I | HCFC-22,HCFC-142b | 5.2 |  | 0 |  | 2010-12-01 | 2015-05-01 | 2012-12-01 |  | 2015-12-01 |  | 110000 | 0 | 110000 | 110000 | 100% | 0 | 0 | 0 | 14300 | 0 | 14300 | 0 | 0 | Project completed. | Financial completion is being initiated. | 2010
ONG | UNIDO | Phase-out of HCFC-22 and HCFC-142b from the manufacture of extruded polystyrene panel at Al-Watania Plastics | Multi-Year | ASP | SAU | FOA | 62 | INV | 13 | A | I | HCFC | 19 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2012-12-31 | 2018-06-18 |  |  | 1103578 | 0 | 1103578 | 192471.65 | 17.44% | 911106.35 | 680417.5 | 200000 | 82768 | 0 | 14435 | 68333 | 51031 | Al Watania representative visited the supplier's facility in January 2016. The supplier visited AlWatania again in March 2016 to check the status of the works and urged for the shipment of the extruder dye. The shipment was initiated in July 2016 but after several delays was received by the supplier in November 2016. Milestones achieved: Milestone 1: Extruder dye shipped to the supplier - Yes Milestone 2: FAT Tests of the equipment- No Milestone 3: Machine shipped to the beneficiary-No Milestone 4: Installation/commission/start up - No Activities planned but not implemented, reasons and strategy: FAT acceptance tests - beneficiary urged to speed up the shipment of the extruder dye. Actions towards next goals: The supplier has prepared all other equipment at their site waiting just for the extruder dye. Was there any delay during the reporting year? Yes Any recurring problem? No Any impact on project completion date: Yes Any action required by Executive Committee? No | Milestones achieved: Milestone 1: Extruder dye shipped to the supplier - Yes Milestone 2: FAT Tests of the equipment- No Milestone 3: Machine shipped to the beneficiary-No Milestone 4: Installation/commission/start up - No Activities planned but not implemented, reasons and strategy: FAT acceptance tests - supplier facing delays in procuring necessary components for the retrofit, beneficiary facing delays in completion of new factory building. Actions towards next goals: The supplier and beneficiary urged to speed up works. Was there any delay during the reporting year? Yes Any recurring problem? No Any impact on project completion date: Yes Any action required by Executive Committee? No |  |  | INV
ONG | Japan | Phase-out of HCFC-22 and HCFC-142b from the manufacture of extruded polystyrene panel at Al-Watania Plastics | Individual | ASP | SAU | FOA | 62 | INV | 14 | A | I | HCFC-22,HCFC-142b | 1.9 |  | 0 |  | 2010-12-01 | 2015-11-01 | 2012-12-01 | 2017-12-01 |  |  | 110000 | 0 | 110000 | 109874 | 99.89% | 126 | 0 | 0 | 14300 | 0 | 14284 | 16 | 0 | - Al Watania representative visited the supplier's facility in January 2016. - The supplier visited Al Watania again in March 2016 to check the status of the works and urged for the shipment of the extruder dye. - The shipment was finally initiated in July 2016. - The extruder dye/static mixer reached the supplier's factory in November 2016. Activities planned but not implemented, reasons and strategy: FAT acceptance tests. The supply of equipment take longer than expected due to logistical issues. Was there any delay during the reporting year? Yes Any recurring problem? No Any impact on project completion date:Yes Any action required by Executive Committee? No | - The supplier is currently procuring necesssary part from sub-suppliers since the producer of the original static mixer no longer exists. - Waiting also for the completion of local works at the beneficiary. Actions towards next goals: Shipment of the retrofitted equipment, installation, commissioning. Expected completion date December 2017. Was there any delay during the reporting year? Yes (The producer of the original static mixer no longer exists.) Any recurring problem? No Any impact on project completion date: Yes Any action required by Executive Committee? No | 2010
COM | UNIDO | Preparation of a demonstration project on promoting HFO-based low-GWP refrigerants for air-conditioning sector in high ambient temperature | Individual | ASP | SAU | FOA | 74 | PRP | 22 | A | I |  | 0 | 0 |  |  | 2015-05-01 | 2016-01-01 | 2016-05-31 |  | 2016-12-01 |  | 30000 | 0 | 30000 | 28912.07 | 96.37% | 1087.93 | 1031.66 | 1032 | 2100 | 0 | 0 | 2100 | 72.2162 | Brief report: The project preparation was completed and the demo project has been approved by the 76th ExCom. Activities planned but not implemented: No Actions towards next goal: Development of the project Was any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any actions required by Executive Committee? No | Project completed. The last disbursement and FIN closure are being processed . |  |  | NON-INV
ONG | UNIDO | Demonstration project for the phase-out of HCFCs by using HFO as foam blowing agent in the spray foam applications in high ambient temperatures | Individual | ASP | SAU | FOA | 76 | DEM | 27 | A | I |  | 0 | 0 |  |  | 2016-05-01 | 2016-11-01 | 2017-10-30 | 2018-06-18 |  |  | 96250 | 0 | 96250 | 4658.49 | 4.84% | 91591.51 | 8472.75 | 30000 | 8663 | 0 | 419 | 8244 | 763 | Agreement with Sham Najd spray foaming company about implementation of the project was concluded in October. HFO-based systems was ordered from the UAE systems house Covestro in November and shipped in December 2016. Milestones achieved: Milestone 1: Agreement with Sham Najd - Yes Milestone 2: Procurement of HFO-based system- Yes Milestone 3: HFO-based system shipment-Yes Activities planned but not implemented, reasons and strategy: First round of testing. Actions towards next goals: Scheduling the first round testing. Was there any delay during the reporting year? Slight delay due to late delivery of the new HFO system. Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | First round of testing of the HFO-based system conducted in March 2017. Samples sent to Dubai Central Laboratory for official testing in March 2017. Further testing on site was not possible due to bad weather conditions. Waiting for Sham Najd to conduct further test spraying on site. Milestones achieved: Milestone 1: First testing at Sham Najd - Yes Milestone 2: Sample testing at Dubai Central Laboratory- Yes Milestone 3: Test spraying on site (roof) by Sham Najd -No Activities planned but not implemented, reasons and strategy: Test spraying on site (roof) delayed because of bad weather conditions. Actions towards next goals: Scheduling the second round testing. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: Yes Any action required by Executive Committee? No |  |  | NON-INV
FIN | UNIDO | National phase-out plan | Multi-Year | ASP | SAU | PHA | 53 | INV | 03 | A | I | CFC | 269.7 | 269.7 |  |  | 2007-11-01 | 2008-02-01 | 2009-03-01 |  | 2013-12-01 | 2015-09-01 | 1287000 | -3274 | 1283726 | 1283725.57 | 100% | 0.43 | 0 |  | 96525 | -246 | 96279 | 0 | 0 | FIN |  |  |  | INV
FIN | UNEP | National phase-out plan | Multi-Year | ASP | SAU | PHA | 53 | TAS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2009-01-01 | 2009-03-01 |  | 2014-12-01 | 2014-11-01 | 364500 | -131861 | 232639 | 232639 | 100% | 0 | 0 |  | 47385 | -17141.93 | 30243.07 | 0 | 0
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | ASP | SAU | PHA | 55 | PRP | 05 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2009-03-01 | 2009-07-31 |  | 2012-12-01 | 2013-12-01 | 130000 | -24 | 129976 | 129975.6 | 100% | 0.4 | 0 |  | 9750 | -2 | 9748 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | SAU | PHA | 55 | PRP | 06 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2011-02-01 | 2009-07-01 |  | 2013-12-01 | 2014-05-01 | 65000 | -9234 | 55766 | 55766 | 100% | 0 | 0 |  | 8450 | -1200.42 | 7249.58 | 0 | 0
FIN | UNIDO | National phase-out plan (second tranche) | Multi-Year | ASP | SAU | PHA | 61 | INV | 10 | A | I | CFC | 532 | 532 |  |  | 2010-07-01 | 2010-12-01 | 2011-07-31 |  | 2013-12-01 | 2013-12-01 | 143000 | -4506 | 138494 | 138493.69 | 100% | 0.31 | 0 |  | 10725 | -377 | 10387 | -39 | 0 | FIN |  |  |  | INV
FIN | UNEP | National phase-out plan (second tranche) | Multi-Year | ASP | SAU | PHA | 61 | TAS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-03-01 | 2011-07-01 |  | 2014-07-01 | 2014-11-01 | 40500 | -4296 | 36204 | 36203.77 | 100% | 0.23 | 0 |  | 5265 | -558.48 | 4706.4901 | 0.0299 | 0
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing and monitoring) | Multi-Year | ASP | SAU | PHA | 68 | INV | 17 | A | I |  | 0 | 0 |  |  | 2012-12-01 | 2013-06-01 | 2015-12-31 | 2017-12-01 |  |  | 341733 | 0 | 341733 | 341732.69 | 100% | 0.31 | -0.2 |  | 23921 | 0 | 23921 | 0 | -0.014 | Follow up train-the trainers workshop was organized in Jeddah on 28 February - 1 March 2016. Second follow-up train-the -trainers workshop was organized in Dammam in October 2016. Milestones achieved: Milestone 1: Follow-up train-the trainers workshop organized- Yes Milestone 2: Further training workshops organized - Yes Activities planned but not implemented, reasons and strategy: Further Follow-up workshop will be organized in the 1Q 2017. Was there any delay during the reporting year? Yes Any recurring problem? No Any impact on project completion date: Yes Any action required by Executive Committee? No | Follow up train-the trainers workshop was organized in Jeddah on 28 February - 1 March 2016. Second follow-up train-the -trainers workshop was organized in Dammam in October 2016. Milestones achieved: Milestone 1: Follow-up train-the trainers workshop organized- Yes Milestone 2: Further training workshops organized - Yes Activities planned but not implemented, reasons and strategy: Further Follow-up workshop will be organized in the 1Q 2017. Was there any delay during the reporting year? Yes Any recurring problem? No Any impact on project completion date: Yes Any action required by Executive Committee? No |  |  | INV |  | To request the submission of additional status report to the 79th meeting to monitor ongoing project with 100 per cent of funds disbursed.
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (polyurethane foam sector plan) | Multi-Year | ASP | SAU | PHA | 68 | INV | 19 | A | I | HCFC | 52.1 | 0 |  |  | 2012-12-01 | 2013-07-01 | 2015-12-31 | 2017-12-01 |  |  | 1827867 | 0 | 1827867 | 1560360.69 | 85.37% | 267506.31 | 190835.8 | 200000 | 127951 | 0 | 109225 | 18726 | 13358.506 | Two out of nine containers for Saptex were damaged during the protracted stay at the customs. Quotation from the supplier was obtained for the damaged parts for Saptex in September and contract was awarded in November 2016. Installation of the equipment that had been delivered to HESCO not possible since the factory was burned down in April 2016. UNIDO equipment undamaged in crates but waiting for the company to settle a claim with insurance company. Installation of equipment for SPF postponed until March 2017. Milestones achieved: Milestone 1: Quotation for the damaged parts (Saptex) - Yes Milestone 2: Contract for supply of the damaged parts (Saptex) - Yes Milestone 3: Shipment of damaged parts (Saptex) - No Milestone 4: Installation and commissioning - No Activities planned but not implemented, reasons and strategy: Shipment of replacement parts (Saptex) and installation for all three factories. Actions towards next goals: Supplier and beneficiaries urged to plan the installation. Was there any delay during the reporting year? Yes Any recurring problem? No Any impact on project completion date: Yes Any action required by Executive Committee? No | Installation and commissioning at SPF performed in April/May 2017. Shipment of replacement parts of equipment for Saptex started in April 2017 and installation to follow after customs clearance. Installation at HESCO postponed until the company settles insurance company claim. Milestones achieved: Milestone 1: Installation and commissioning at SPF - Yes Milestone 2: Shipment of replacement for the damaged parts (Saptex) - Yes Milestone 3: Installation and commissioning at Saptex - No Milestone 4: Installation and commissioning at HESCO- No Activities planned but not implemented, reasons and strategy: Actions towards next goals: Supplier and beneficiaries urged to plan installation. Was there any delay during the reporting year? Yes Any recurring problem? No Any impact on project completion date: Yes Any action required by Executive Committee? No |  |  | INV
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing, custom training and monitoring) | Multi-Year | ASP | SAU | PHA | 68 | TAS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-10-01 | 2015-12-01 | 2017-12-01 |  |  | 233674 | 0 | 233674 | 29167.85 | 12.48% | 204506.15 | 155674 | 20450.615 | 28946 | 0 | 3613.1216 | 25332.8784 | 19283.8724 | Brief progress report (actual/planned: 3 meetings with NOU and NOC organized in Feb and May and Oct. 2016 to expedite the pace of project implementation, mainly after having signed the agreement in Jan 2016. two training workshops for RAC technicinas have been organized in Fab. and May 2016 in close collaboration with TVTC and RAC industry. Additional two RAC training and certification workshops took place in Oct. 2016 where 34 technicians have certified according to F gas regulations out of 52 technicians trained. Several meetings held with key partners including customs Dept and TVTC and ministry of Labor to expedite the adoption of the updated regulations and certification scheme. Legal arrangements (actual/planned): The agreement for the implementing the project has been signed in Jan 2016. Mission (actual/planned): 3 missions in Feb., May and Oct. 2016 - TOR completed (actual/planned): completed - CAP staff implementing directly. First disbursement date (actual/planned): 1st disbursement is done. All funds disbursed (yes/no): No. Any delay? (yes/no): implementation delayed due to late signature of contract. If Yes, reasons for delay & action plan to resolve: late signature of the contract and thus lack of required funding for implementing the planned activities. along with complex procedures for adopting the updated policies, regulations and certification scheme. If Yes, will delay have impact on project completion date (yes/no): working with the NOU to expedite the pace of implementation to enable the country comply with agreed targets and ExCom conditions. Any ongoing problems (yes/no): long national procedures to adopt new policies and regulations. If Yes, is any action required by ExCom: n/a | Brief progress report (actual/planned: a meeting with NOU and NOC organized in Feb. 2017 to expedite the pace of project implementation and agreeing an action plan to comply with the ExCom conditions. Additional RAC training and certification workshop took place in Feb. 2017 where 24 technicians from AlEssa Co. have been trained. in parallel, several meetings held with key partners including customs Dept and TVTC and ministry of Labor to expedite project implementation. Legal arrangements (actual/planned): The agreement for the implementing the project has been signed in Jan 2016. Mission (actual/planned): 1 mission in Feb. 2017 - TOR completed (actual/planned): completed - CAP staff implementing directly. First disbursement date (actual/planned): 1st disbursement is done. All funds disbursed (yes/no): No. Any delay? (yes/no): implementation delayed due to late signature of contract. If Yes, reasons for delay & action plan to resolve: late signature of the contract and thus lack of required funding for implementing the planned activities. along with complex procedures for adopting the updated policies, regulations and certification scheme. If Yes, will delay have impact on project completion date (yes/no): working with the NOU to expedite the pace of implementation to enable the country comply with agreed targets and ExCom conditions. Any ongoing problems (yes/no): long national procedures to adopt new policies and regulations. If Yes, is any action required by ExCom: n/a |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor the completion of the required expenditures report.
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) (polyurethane foam sector plan) | Multi-Year | ASP | SAU | PHA | 68 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2014-07-01 | 2015-12-01 | 2017-12-01 |  |  | 56726 | 0 | 56726 | 4014.11 | 7.076% | 52711.89 | 42640 | 5271.189 | 7027 | 0 | 497.2526 | 6529.7474 | 5282.0802 | Brief progress report (actual/planned): The agreement with the government was signed in Jan 2016 and arrangements are being made to transfer funds for implementing planned activities. two consultation meetings with foam industry have been organized in Feb and May 2016 to identify the key policy and technical challenges facing the conversion of the sector towards the desired long term alternatives. The need for revisiting the national related standards either for foam products or that are related to the safe operation of production and storage facilities when handling flammable blowing agents has been identified. Work with the national standards organization and civil defense was initiated and a workshop is planned during 1st half 2017. The foam sector was invited to a regional workshop in Dubai in Nov. 2017 to discuss recent policy and technical developments and provide them with the required TA and advice in concert with the phase out investment activities that are being implemented in the foam sector. Legal arrangements (actual/planned): SSFA with the NOU for implementing project activities has been finalized for signature after having resolved the difficulties faced by the NOU in opening account for the project. (actual/planned): first mission in Feb 2013 to launch the HPMP with consultation meeting with the foam sector - TOR completed (actual/planned): completed - with CAP staff implementing directly key activities. First disbursement date (actual/planned): May 2014. All funds disbursed (yes/no): No, Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: delay in countersignature of the contract with uNEP for implementing project activities at national level. If Yes, will delay have impact on project completion date (yes/no): UNEP has been trying with the NOU to expedite implementation to absorb the delays faced so far. Any ongoing problems (yes/no): the country agreement is being signed. And efforts are being taken to comply with the planned ban of R-141b in 2018. If Yes, is any action required by ExCom: n/a- expedited implementation of planned activities in close cooperation with the LA. | Brief progress report (actual/planned): one consultation meeting with foam industry have been organized in Feb. 2017 to update the sector about the recent developments mainly with regards to Kigali amendment and discuss key challenges facing the sector to comply with the planned total ban of R-141b by end of 2017. The need for revisiting the national related standards either for foam products or that are related to the safe operation of production and storage facilities when handling flammable blowing agents has been identified. Work with the national standards organization and civil defense was initiated and a workshop is planned during 1st half 2017. UNEP continued to provide the required TA and advice in concert with the phase out investment activities that are being implemented in the foam sector. Legal arrangements (actual/planned): SSFA with the NOU for implementing project activities has been finalized for signature after having resolved the difficulties faced by the NOU in opening account for the project. (actual/planned): first mission in Feb 2013 to launch the HPMP with consultation meeting with the foam sector - TOR completed (actual/planned): completed - with CAP staff implementing directly key activities. First disbursement date (actual/planned): May 2014. All funds disbursed (yes/no): No, Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: delay in countersignature of the contract with uNEP for implementing project activities at national level. If Yes, will delay have impact on project completion date (yes/no): UNEP has been trying with the NOU to expedite implementation to absorb the delays faced so far. Any ongoing problems (yes/no): the country agreement is being signed. And efforts are being taken to comply with the planned ban of R-141b in 2018. If Yes, is any action required by ExCom: n/a- expedited implementation of planned activities in close cooperation with the LA. |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor the completion of the required expenditures report.
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing and monitoring) | Multi-Year | ASP | SAU | PHA | 72 | INV | 20 | A | I | HCFC | 2.6 | 0 |  |  | 2014-05-01 | 2015-12-01 | 2016-12-31 | 2019-12-01 |  |  | 270000 | 0 | 270000 | 112172.03 | 41.55% | 157827.97 | 0 | 40000 | 18900 | 0 | 7852 | 11048 | 0 | As for SAU/PHA/68/INV/17 above | As for SAU/PHA/68/INV/17 above |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) (polyurethane foam sector plan) | Multi-Year | ASP | SAU | PHA | 72 | INV | 21 | A | I | HCFC | 75.8 | 0 |  |  | 2014-05-01 | 2015-06-01 | 2016-12-31 | 2018-12-01 |  |  | 2701487 | -7813 | 2693674 | 1469078.31 | 54.54% | 1224595.69 | 415597.8 | 400000 | 189104 | -547 | 102835 | 85722 | 29092 | Shipment of PU foam equipment to the Alamdar Vapotherm completed in February 2016. Installation and commissioning for Alessa and Alamdar Vapothern completed in September and October 2016, respectively. Installation for ALBA Factory postponed until 2017 because of missing permissions from the authorities. Shipment of equipment for Jundi systems house completed in October 2016. Installation postponed until completion of local works scope of supply of the beneficiary. International expert visited two other systems houses (Succo and Saptex) and drafted Technical Specification for Succo. Procurement abandoned in October 2016 after consultation with MLFS since the items not considered incremental. Milestones achieved: Milestone 1: Shipment of PU eq. to Alamdar Vapotherm - Yes Milestone 2: Expert mission to visit SHs - Yes Milestone 3: Shipment of equipment for Jundi SH - Yes Milestone 4: Invitation to bidding for the 2nd SH - Yes Milestone 5: Installation and commissioning at Jundi - Not Milestone 6: Contract for equipment for the 2nd SH - Not Activities planned but not implemented, reasons and strategy: Jundi SH must complete the local works in preparation for the installation. Actions towards next goals: Procurement for the 2nd SH Was there any delay during the reporting year? Yes Any recurring problem? No Any impact on project completion date: Yes Any action required by Executive Committee? No | ALBA Factory decided to install the equipment at the old factory since they failed to get necessary permissions from authorities for handling flammable chemicals at the new factory. Installation scheduled for May 2017. In March 2017 mission , Jundi SH was visited by UNIDO PM and Technical Expert to check the progress of the local works. Milestones achieved: Milestone 1: Installation/commissioning at ALBA Factory - No Milestone 2: Installation/commissioning at Jundi SH - No Activities planned but not implemented, reasons and strategy: Jundi SH must complete the local works in preparation for the installation. Actions towards next goals: Procurement for the 2nd SH Was there any delay during the reporting year? Yes Any recurring problem? No Any impact on project completion date: Yes Any action required by Executive Committee? No |  |  | INV |  | To request the submission of additional status report to the 79th meeting to monitor the completion of the import tax exemption to facilitate the shipment of equipment.
ONG | UNIDO | HCFC phase-out management plan (stage I, third tranche) (polyurethane foam sector plan) | Multi-Year | ASP | SAU | PHA | 75 | INV | 24 | A | I | HCFC | 33.7 | 0 |  |  | 2015-11-01 | 2016-03-01 | 2018-12-01 | 2018-12-18 |  |  | 1100000 | 0 | 1100000 | 141251.47 | 12.84% | 958748.53 | 652636.02 | 200000 | 77000 | 0 | 0 | 77000 | 45684.5214 | International expert visited four remaining PU foam companies in February/March 2016 and drafted Technical Specifications. Since only two companies (Al Mutlak and Sahari Refrigeration) were prepared to go for the conversion the procurement for them started in April 2016. The best bidder was selected and contract was issued in September 2016. International expert visited 3 spray foam companies in May 2016 and drafted technical specification for their conversion. Bidding started in June but had to be abandoned after consultation with MLFS as spray foamers are not eligible to receive ICC. On recommendation of MLFS, contracts for provision of IOC to the three spray foaming companies were pursued. Milestones achieved: Milestone 1: Int. Expert visit of PU foam companies - Yes Milestone 2: Bidding for Al Mutlak and Sahari - Yes Milestone 3: Contract for supply to Al Mutlak and Sahari - Yes Milestone 4: Int. Expert visit of spray foam companies - Yes Milestone 5: Procurement for 3 spray foam companies - Cancelled Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | Shipment for AlMutlak and Sahari Refrigeration scheduled for May provided that the beneficiaries fulfill their obligations either to obtain import tax exemption or arrange for the import tax payment. UNIDO PM and NOU KSA visited the third PU foam company, namely IBSF, in March 2017. The company will make decision about the assistance from UNIDO/MLF. Installation for Jundi conducted in April/May 2017. Milestones achieved: Milestone 1: Customs clearance for Al Mutlak and Sahari arranged - Yes Milestone 2: Shipment for Al Mutlak and Sahari - Yes Milestone 3: Installation for Jundi - Yes Milestone 4: Procurement for IBSF - Not Activities planned but not implemented, reasons and strategy: Procurement for IBSF pending on company to take a decision about the assistance from UNIDO/MLF. Actions towards next goals: Shipment to 3 spray foam companies. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing and monitoring) | Multi-Year | ASP | SAU | PHA | 75 | INV | 25 | A | I |  | 0 | 0 |  |  | 2015-11-01 | 2016-08-01 | 2018-12-01 | 2020-12-18 |  |  | 100000 | 0 | 100000 | 48874.88 | 48.87% | 51125.12 | 12796.54 | 15000 | 7000 | 0 | 0 | 7000 | 895.7578 | As for SAU/PHA/68/INV/17 above | As for SAU/PHA/68/INV/17 above |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, fourth tranche) (polyurethane foam sector plan) | Multi-Year | ASP | SAU | PHA | 77 | INV | 31 | A | I | HCFC | 43.2 | 0 |  |  | 2016-11-01 |  | 2020-12-31 | 2020-12-31 |  |  | 989600 | 0 | 989600 | 0 | 0% | 989600 | 0 | 100000 | 69272 | 0 | 0 | 69272 | 0 | Noted with concern, the delay in the implementation of activities in the foam manufacturing and refrigeration servicing sectors; that the conditions of Appendix 8-A of the Agreement between the Government and the Executive Committee had not been met, and portions of the funding (US$777,000, plus agency support costs of US$54,390 for UNIDO and US$120,000, plus agency support costs of US$14,864 for UNEP) related to activities in the servicing sector could not be released as they were subject to the conditions. Approved, on an exceptional basis, the proposal to provide funding for the damaged equipment in accordance with subparagraph 7(a) of the Agreement as reflected in the implementation plan. UNIDO was requested to prepare a report outlining the resolution of issues related to customs clearance, such as duties, taxes, demurrage fees, and any damages to equipment purchased by the Multilateral Fund to be submitted together with the fifth tranche request. Allowed submission of fifth tranche once the following conditions had been met: (I) completion of the conversion, to the agreed technology, of all PU foam enterprises included in stage I of the HPMP, establishment of the ban on HCFC-141b; and completion of the conversion at Al-Watania, XPS foam enterprise, to a blend of isobutane, CO2 and HFO-1234ze; (ii) completion of conversion of all systems houses included in stage I of the HPMP to formulations with a low-GWP potential, and at least ten workshops held by systems houses for downstream foam users; and (iii) adoption of a code of practice and e-licensing scheme; establishment of mandatory recovery and recycling of HCFCs and other ODS refrigerants; and the establishment of a ban on disposable refrigerant cylinders. Requested the return, to the same meeting at which the fifth tranche was submitted, of funds associated with any foam enterprise or systems house in stage I of the HPMP that decided not to convert to the agreed technology or not to participate in the HPMP, after taking into account the funds needed for conversion at the two newly identified enterprises (Bayt Al Awazil and Sahari). Approved, on an exceptional basis, and on the understanding that the Treasurer would withhold the amount of US$966,254, consisting of US$777,000 plus agency support costs of US $54,390 for UNIDO, and US$120,000, plus agency support costs of US$14,864 for UNEP, until receipt of a comprehensive report demonstrating that the conditions specified in Appendix 8-A had been met, on the understanding that, if the report were not provided by the first regular meeting of 2018, the amount ofUS$966,254 would be returned to the Multilateral Fund, and that a request for those funds could be made by the Government only once the conditions in Appendix 8-A had been fully met. | Mission of UNIDO PM and Technical Expert to prepare TOR for equipment for Saptex systems house conducted in March 2017. Invitation for bidding published in April 2017, contract award expected in May 2017. Milestones achieved: Milestone 1`: Expert mission to visit Saptex SH - Yes Milestone 2: Bidding for Saptex systems house - Yes Milestone 3: Contract for equipment for Saptex SH - Not Milestone 4:Shipment of equipment for Saptex SH - Not
ONG | UNIDO | HCFC phase-out management plan (stage I, fourth tranche) (refrigeration servicing and monitoring) | Multi-Year | ASP | SAU | PHA | 77 | TAS | 30 | A | I | HCFC | 47.9 | 0 |  |  | 2016-11-01 |  | 2020-12-31 | 2020-12-31 |  |  | 777000 | 0 | 777000 | 0 | 0% | 777000 | 0 | 1 | 54390 | 0 | 0 | 54390 | 0 | Noted with concern, the delay in the implementation of activities in the foam manufacturing and refrigeration servicing sectors; that the conditions of Appendix 8-A of the Agreement between the Government and the Executive Committee had not been met, and portions of the funding (US$777,000, plus agency support costs of US$54,390 for UNIDO and US$120,000, plus agency support costs of US$14,864 for UNEP) related to activities in the servicing sector could not be released as they were subject to the conditions. Approved, on an exceptional basis, the proposal to provide funding for the damaged equipment in accordance with subparagraph 7(a) of the Agreement as reflected in the implementation plan. UNIDO was requested to prepare a report outlining the resolution of issues related to customs clearance, such as duties, taxes, demurrage fees, and any damages to equipment purchased by the Multilateral Fund to be submitted together with the fifth tranche request. Allowed submission of fifth tranche once the following conditions had been met: (i) completion of the conversion, to the agreed technology, of all PU foam enterprises included in stage I of the HPMP, establishment of the ban on HCFC-141b; and completion of the conversion at Al-Watania, XPS foam enterprise, to a blend of isobutane, CO2 and HFO-1234ze; (ii) completion of conversion of all systems houses included in stage I of the HPMP to formulations with a low-GWP potential, and at least ten workshops held by systems houses for downstream foam users; and (iii) adoption of a code of practice and e-licensing scheme; establishment of mandatory recovery and recycling of HCFCs and other ODS refrigerants; and the establishment of a ban on disposable refrigerant cylinders. Requested the return, to the same meeting at which the fifth tranche was submitted, of funds associated with any foam enterprise or systems house in stage I of the HPMP that decided not to convert to the agreed technology or not to participate in the HPMP, after taking into account the funds needed for conversion at the two newly identified enterprises (Bayt Al Awazil and Sahari). Approved, on an exceptional basis, and on the understanding that the Treasurer would withhold the amount of US$966,254, consisting of US$777,000 plus agency support costs of US $54,390 for UNIDO, and US$120,000, plus agency support costs of US$14,864 for UNEP, until receipt of a comprehensive report demonstrating that the conditions specified in Appendix 8-A had been met, on the understanding that, if the report were not provided by the first regular meeting of 2018, the amount ofUS$966,254 would be returned to the Multilateral Fund, and that a request for those funds could be made by the Government only once the conditions in Appendix 8-A had been fully met. | Funding withheld by MLFS.
ONG | UNEP | HCFC phase-out management plan (stage I, fourth tranche) (refrigeration servicing, custom training and monitoring) | Multi-Year | ASP | SAU | PHA | 77 | TAS | 32 | A | I |  | 43.2 |  | 0 |  | 2016-12-01 |  | 2017-12-01 | 2018-12-01 |  |  | 250400 | 0 | 250400 | 0 | 0% | 250400 | 0 | 25040 | 31018 | 0 | 0 | 31018 | 0 | New approval in Nov 2016 | Brief progress report (actual/planned: the tranche was approved in Nov. 2016 to continue implementing the activities initiated under 1st tranche. 1 meeting with NOU and NOC organized in Feb. 2017 to discuss and agree action plan for tranche implementation including action plan to comply with the ExCom conditions. Agreement reached with TVTC to take full responsibility in implementing the RAC training with the target to train 1000 technicians in 2017. A meeting with the NOC held in Feb. 2017 to discuss the final drafts of the updated ODS regulations and code of good practices. It is hoped that both documents will be adopted during 1st half of 2017 to facilitate compliance with ExCom conditions. A training workshop for RAC technicians took place in Feb. 2017. Several meetings held with key partners including customs Dept and TVTC and ministry of Labor to expedite the adoption of the updated regulations and certification scheme. Legal arrangements (actual/planned): The agreement for the implementing the project is being prepared for signature during 1st half 2017. Mission (actual/planned): 1 missions in Feb. 2017 - TOR completed (actual/planned): ToR is being prepared - CAP staff implementing directly. First disbursement date (actual/planned): No. All funds disbursed (yes/no): No. Any delay? (yes/no): NA- new approval. If Yes, will delay have impact on project completion date (yes/no): working with the NOU to expedite the pace of implementation to enable the country comply with agreed targets and ExCom conditions. Any ongoing problems (yes/no): long national procedures to adopt new policies and regulations. If Yes, is any action required by ExCom: n/a
FIN | UNIDO | Preparation for HCFC phase-out investment activities (refrigeration sector) | Individual | ASP | SAU | REF | 60 | PRP | 08 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-07-01 | 2011-04-30 |  | 2012-12-01 | 2013-12-01 | 80000 | -1008 | 78992 | 78992.44 | 100% | -0.44 | 0 |  | 6000 | -76 | 5924 | 0 | 0 | FIN
COM | UNIDO | Preparation of a demonstration project for the phase-out of HCFCs by using HFO as foam blowing agent in the spray foam applications in high ambient temperatures | Individual | ASP | SAU | REF | 74 | PRP | 23 | A | I |  | 0 | 0 |  |  | 2015-05-01 | 2015-11-01 | 2016-05-31 |  | 2016-06-01 |  | 30000 | 0 | 30000 | 30000.19 | 100% | -0.19 | 0 |  | 2100 | 0 | 0 | 2100 | 0 | Project completed in Jun 2016. | N.A. |  |  | NON-INV
ONG | UNIDO | Demonstration project on promoting HFO-based low-global warming potential refrigerants for air-conditioning sector in high ambient temperatures | Individual | ASP | SAU | REF | 76 | DEM | 28 | A | I |  | 0 | 0 |  |  | 2016-05-01 | 2016-09-01 | 2018-05-31 | 2019-12-31 |  |  | 1300000 | 0 | 1300000 | 12800 | 0.9846% | 1287200 | 19200 | 100000 | 91000 | 0 | 896 | 90104 | 1344 | Brief report: The demo project has been approved by the 76th ExCom. | Brief report: Contacts with new management established and experts recruited. Milestones achieved: Milestone 1: Local institution identified - Yes Milestone 2: Grant agreement signature - No Milestone 3: Legal arrangements – No Milestone 4: Initial stages of project implementation began - No Activities planned but not implemented: Yes Actions towards next goal: Procurement of equipment Was any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: Yes, completion date extended as per updated project plan. Any actions required by Executive Committee? No |  |  | NON-INV
ONG | IBRD | Demonstration project at air-conditioning manufacturers to develop window and packaged air-conditioners using low-global warming potential refrigerants | Individual | ASP | SAU | REF | 76 | DEM | 29 | A | I | HCFC | 3.6 | 0 | 0 | 0 | 2016-05-01 |  | 2017-05-31 | 2018-08-01 |  |  | 796400 | 0 | 796400 | 0 | 0% | 796400 | 796400 | 240000 | 55748 | 0 | 0 | 55748 | 55748 | Project approved in May 2016. Second half of 2016 used in part to develop a legal arrangement to disbursement funding to Saudi-based beneficiaries. | Mechanism determined and agreed by Bank management and with the beneficiaries by Apr 17. Consultancy contract to facilitate disbursement expected in Q2 2017, followed by commencement of demonstration implementation. Prototypes expected by end 2017 and preliminary results by Q1 2018. |  |  | INV | 0
FIN | UNIDO | Preparation of a country programme/national phase-out plan | Individual | ASP | SAU | SEV | 49 | CPG | 01 | A | I |  | 0 | 0 |  |  | 2006-07-01 | 2006-09-01 | 2008-01-01 |  | 2007-12-01 | 2008-12-01 | 65000 | -3270 | 61730 | 61729.79 | 100% | 0.21 | 0 |  | 4875 | -245 | 4630 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNEP | Institutional strengthening (establishment of Ozone Unit) | Individual | ASP | SAU | SEV | 53 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2010-04-01 | 2010-11-01 | 2017-12-01 |  |  | 300000 | 0 | 300000 | 250000 | 83.33% | 50000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Project completed but not financially closed with final payment (US$50,000) outstanding Legal arrangements (actual/planned): no valid legal instrument; Initial stages of project implementation (actual/planned): Not Applicable; Intermediate goals achieved (actual/planned): Article 7 and CP data collected and reports submitted up to 2015. Project completion and follow up: Project implemented, and balance funding will be merged in ISP Phase II into a new legal instrument. First disbursement date (actual/planned): First payment disbursed end 2008. All funds disbursed (yes/no): No. Will be merged in next IS phase legal instrument. Project ongoing & delayed Any delay? (yes/no): Yes. Project not closed with final payment outstanding of US$50,000. If Yes, reasons for delay & action plan to resolve: Country environment authority underwent major structural and management changes. The new management is aware of the problem and trying to give priority to resolve issue. If Yes, will delay have impact on project completion date (yes/no): Yes. Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: No. | Brief progress report (actual/planned): Project completed but not financially closed with final payment (US$50,000) outstanding Legal arrangements (actual/planned): no valid legal instrument; Initial stages of project implementation (actual/planned): Not Applicable; Intermediate goals achieved (actual/planned): Article 7 and CP data collected and reports submitted up to 2015. Project completion and follow up: Project implemented, and balance funding will be merged in ISP Phase II into a new legal instrument. First disbursement date (actual/planned): First payment disbursed end 2008. All funds disbursed (yes/no): No. Will be merged in next IS phase legal instrument. Project ongoing & delayed Any delay? (yes/no): Yes. Project not closed with final payment outstanding of US$50,000. If Yes, reasons for delay & action plan to resolve: Country environment authority underwent major structural and management changes. The new management is aware of the problem and trying to give priority to resolve issue. If Yes, will delay have impact on project completion date (yes/no): Yes. Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: No.
ONG | UNEP | Extension of the institutional strengthening project (phase II: 7/2012-6/2014) | Individual | ASP | SAU | SEV | 67 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 |  | 2014-07-01 | 2017-12-01 |  |  | 200000 | 0 | 200000 | 0 | 0% | 200000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Awaiting country new instruction to proceed Legal arrangements (actual/planned): no valid legal instrument; Initial stages of project implementation (actual/planned): Not Applicable; Intermediate goals achieved (actual/planned): n/a Project completion and follow up: n/a First disbursement date (actual/planned): none All funds disbursed (yes/no): No. Project ongoing & delayed Any delay? (yes/no): Not started. Awaiting instruction from new management. If Yes, reasons for delay & action plan to resolve: Country environment authority underwent major structural and management changes. The new management is aware of the problem and trying to give priority to resolve issue. If Yes, will delay have impact on project completion date (yes/no): Yes. Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: No. | Brief progress report (actual/planned): Awaiting country new instruction to proceed Legal arrangements (actual/planned): no valid legal instrument; Initial stages of project implementation (actual/planned): Not Applicable; Intermediate goals achieved (actual/planned): n/a Project completion and follow up: n/a First disbursement date (actual/planned): none All funds disbursed (yes/no): No. Project ongoing & delayed Any delay? (yes/no): Not started. Awaiting instruction from new management. If Yes, reasons for delay & action plan to resolve: Country environment authority underwent major structural and management changes. The new management is aware of the problem and trying to give priority to resolve issue. If Yes, will delay have impact on project completion date (yes/no): Yes. Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: No.
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | ASP | SAU | SEV | 75 | TAS | 26 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-04-01 | 2016-12-01 | 2017-08-01 |  |  | 190000 | 0 | 190000 | 21886.06 | 11.52% | 168113.94 | 109000 | 16811.394 | 24700 | 0 | 2845.1878 | 21854.8122 | 14170 | Brief progress report (actual/planned): the survey was initiated in early 2016 with active engagement of the NOU which established a national team to assist in survey implementation with necessary support provided by UNEP. Several meetings with the NOU and key stakeholders held in Feb and May 2016 to discuss and agree the set up and plan required for conducting the survey activities taking into account the short period for implementation. Legal arrangements (actual/planned): SSFA with the NOU for implementing project activities has been signed and and ToRs finalized for recruiting an international expert to assist in survey implementation. The expert was recruited in Sept. and the first stakeholders workshop was organized in Jeddah in Nov. 2016 and the second consultation workshop took place in Riyadh 2017. (actual/planned): first mission in May 2016 to launch the project and meet with key stakeholders to set the ground for data collection- TOR completed (actual/planned): completed - with CAP staff providing necessary technical and policy support. First disbursement date (actual/planned): May 2016. All funds disbursed (yes/no): No, Any delay? (yes/no): the survey took longer than expected due to the size of the country and associated complexity. If Yes, reasons for delay & action plan to resolve: size of the country and complex nature of surveyed sectors. If Yes, will delay have impact on project completion date (yes/no): UNEP will work with the NOU to expedite implementation to meet the set deadline. It is expected to complete the final report by April 2017. Any ongoing problems (yes/no): difficult to work during summer months due to harsh weather and holiday season. If Yes, is any action required by ExCom: n/a- | Brief progress report (actual/planned): the survey is progressing well with active engagement of the NOU and the national team and necessary support provided by UNEP. and the first stakeholders workshop was organized in Jeddah in Nov. 2016 and the second consultation workshop took place in Riyadh 2017. The final report is being finalized and expected to be ready by April 2017. Legal arrangements (actual/planned): SSFA with the NOU for implementing project activities has been signed and an international expert to assist in survey implementation was recruited in Sept. 2016 (actual/planned): first mission in May 2016 to launch the project and meet with key stakeholders to set the ground for data collection- TOR completed (actual/planned): completed - with CAP staff providing necessary technical and policy support. First disbursement date (actual/planned): May 2016. All funds disbursed (yes/no): No, Any delay? (yes/no): the survey took longer than expected due to the size of the country and associated complexity. If Yes, reasons for delay & action plan to resolve: size of the country and complex nature of surveyed sectors. If Yes, will delay have impact on project completion date (yes/no): UNEP will work with the NOU to expedite implementation to meet the set deadline. It is expected to complete the final report by April 2017. Any ongoing problems (yes/no): difficult to work during summer months due to harsh weather and holiday season. If Yes, is any action required by ExCom: n/a-
FIN | UNIDO | Preparation of an investment project in the foam sector | Individual | AFR | SEN | FOA | 18 | PRP | 05 | A | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-03-01 | 1996-01-01 |  | 1996-12-01 | 1998-08-01 | 10000 | -544 | 9456 | 9456 | 100% | 0 | 0 |  | 1300 | -73 | 1227 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a demonstration project (tobacco, peanuts) | Individual | AFR | SEN | FUM | 25 | PRP | 11 | A | I |  | 0 | 0 |  |  | 1998-07-01 | 1998-08-01 | 1999-08-01 |  | 1999-01-01 | 2001-07-01 | 30000 | -2341 | 27659 | 27659 | 100% | 0 | 0 |  | 3900 | -310 | 3590 | 0 | 0 | FIN
FIN | UNIDO | Phase out of methyl bromide used in peanut seed fumigation in Novasen Ltd. | Individual | AFR | SEN | FUM | 26 | INV | 12 | A | I | MBR | 0.7 | 0.7 |  |  | 1998-11-01 | 1999-12-01 | 2000-12-01 |  | 2001-12-01 | 2003-02-01 | 62945 | -3226 | 59719 | 59718.78 | 100% | 0.22 | 0 |  | 8183 | -432 | 7751 | 0 | 0 | FIN
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organizations in methyl bromide communication | Individual | AFR | SEN | FUM | 34 | TAS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2002-07-01 |  | 2003-07-01 | 2004-09-01 | 25000 | -9000 | 16000 | 16000 | 100% | 0 | 0 |  | 3250 | -1170 | 2080 | 0 | 0
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | SEN | PHA | 48 | PRP | 21 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2006-12-01 | 2007-04-01 |  | 2008-11-01 | 2009-11-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0
FIN | UNIDO | Preparation of a terminal phase-out management plan | Individual | AFR | SEN | PHA | 48 | PRP | 22 | A | I |  | 0 | 0 |  |  | 2006-04-01 | 2007-01-01 | 2007-04-01 |  | 2008-04-01 | 2010-12-01 | 15000 | -3043 | 11957 | 11957.21 | 100% | -0.21 | 0 |  | 1125 | -228 | 897 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | Italy | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | SEN | PHA | 52 | INV | 24 | A | I |  | 0 | 0 | 0 |  | 2007-07-01 | 2008-06-01 | 2008-07-01 |  | 2012-12-01 | 2013-12-01 | 220000 | 0 | 220000 | 220000 | 100% | 0 | 0 | 0 | 28600 | 0 | 28600 | 0 | 0 | Project financially completed in Dec 2013. |  | 2007 |  | Investment
FIN | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | SEN | PHA | 52 | TAS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-11-01 | 2008-07-01 |  | 2009-04-01 | 2010-12-01 | 109500 | -1000 | 108500 | 108500 | 100% | 0 | 0 |  | 14235 | -130 | 14105 | 0 | 0
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | AFR | SEN | PHA | 55 | PRP | 26 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 |  | 2011-07-01 | 2012-05-01 | 85000 | -1026 | 83974 | 83973.9 | 100% | 0.1 | 0 |  | 6375 | -77 | 6298 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | Italy | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | SEN | PHA | 57 | INV | 28 | A | I | CFC | 23.4 | 23.4 | 0 |  | 2009-04-01 | 2008-06-01 | 2010-03-01 |  | 2012-12-01 | 2014-12-01 | 135000 | -4594 | 130406 | 130406 | 100% | 0 | 0 | 0 | 17550 | -597 | 16953 | 0 | 0 | Balance will be reported to the 75th ExCom. | Balances (and interests accrued) have been reported to the 77th ExCom and have been returned in cash in April 2017 in light of ExCom decision 77/2(a)(iii) | 2009 |  | Investment
FIN | UNEP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | SEN | PHA | 57 | TAS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-07-01 | 2010-03-01 |  | 2010-12-01 | 2011-12-01 | 100500 | 0 | 100500 | 100500 | 100% | 0 | 0 |  | 13065 | 0 | 13065 | 0 | 0
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | SEN | PHA | 65 | INV | 31 | A | I | HCFC | 2.4 | 2.4 |  |  | 2011-11-01 | 2012-02-01 | 2014-11-30 | 2017-12-01 |  |  | 200000 | 0 | 200000 | 131843.43 | 65.92% | 68156.57 | 26.56 | 40000 | 15000 | 0 | 9888 | 5112 | 2 | Progress report and verification report were completed in 2016. Bidding for equipment purchase was initiated in 2016. Equipment delivery will take place in 2017, due to insufficient funds under tranche I to cover the equipment purchase. Was there any delay during the reporting year? Yes Any impact on project completion date: Yes, in order to combine the equipment purchase with the next tranche. Any action required by Executive Committee? No | Technical specification for equipment purchase has been revised first quarter 2017. Work plan for the year 2017 - 2018 is under development with NOU. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
COM | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | SEN | PHA | 65 | TAS | 30 | A | I |  | 1.2 | 0 | 0 | 0 | 2011-11-01 | 2011-12-01 | 2014-11-01 |  | 2015-12-01 |  | 100000 | 0 | 100000 | 94023 | 94.02% | 5977 | 0 | 5977 | 12887 | 0 | 12116.744 | 770.256 | 0 | Project financially completed. Balances to be returned. | Project financially completed. Balances to be returned.
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | AFR | SEN | PHA | 77 | INV | 36 | A | I |  | 0 | 0 |  |  | 2016-11-01 |  | 2019-12-31 | 2019-12-01 |  |  | 80000 | 0 | 80000 | 0 | 0% | 80000 | 0 | 20000 | 6000 | 0 | 0 | 6000 | 0 | Noted that the Agreement between the Government and the Executive Committee had been updated based on the revised starting point and funding level; and that the revised starting point for sustained aggregate reduction in HCFC consumption was 20.96 ODP tonnes, based on the verification report submitted to the 77th meeting, and that the revised funding level for stage I of the HPMP for Senegal was US$630,000 plus agency support costs, in accordance with decision 60/44(f)(xii). | Technical specification for equipment purchase has been revised first quarter 2017. Work plan for the year 2017 - 2018 is under development with NOU. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | AFR | SEN | PHA | 77 | TAS | 37 | A | I |  | 0 |  | 0 |  | 2016-12-01 |  | 2018-12-01 | 2018-12-01 |  |  | 80000 | 0 | 80000 | 0 | 0% | 80000 | 0 | 8000 | 10400 | 0 | 0 | 10400 | 0 | Newly approved project | Brief progress report (actual/planned): Project newly approved. Agreement not signed yet. Legal arrangements (actual/planned): Agreement not signed yet. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement _no __ All funds disbursed (yes/no): _ Final payment _no___ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
FIN | UNEP | Training and upgrading for repair technicians | Individual | AFR | SEN | REF | 11 | TRA | 04 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1995-11-01 |  | 1994-12-01 | 1995-12-01 | 58000 | 0 | 58000 | 58000 | 100% | 0 | 0 |  | 7540 | 0 | 7540 | 0 | 0
FIN | France | Project preparation for projects in the hotel and fisheries industries and recycling |  | AFR | SEN | REF | 19 | PRP | 06 | A | D |  | 0 |  | 0 |  | 1996-05-01 | 1996-09-01 | 1997-05-01 |  | 1996-12-01 | 1996-12-01 | 10000 | -248 | 9752 | 9752 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed
FIN | France | Training of technicians in domestic refrigeration and air conditioning |  | AFR | SEN | REF | 21 | TRA | 07 | A | I |  | 0 |  | 0 |  | 1997-02-01 | 1998-01-01 | 1997-08-01 |  | 1998-03-01 | 1998-06-01 | 16500 | 0 | 16500 | 16500 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Projet achevé. PCR soumis
FIN | UNIDO | Refrigerant recovery and recycling scheme | RMP | AFR | SEN | REF | 22 | TAS | 08 | A | I | CFC | 36.12 | 36.12 |  |  | 1997-05-01 | 1997-08-01 | 1999-06-01 |  | 1998-12-01 | 2000-03-01 | 136250 | 0 | 136250 | 136250 | 100% | 0 | 0 |  | 17713 | 0 | 17713 | 0 | 0 | FIN
FIN | UNEP | Development of refrigerant management plan | RMP | AFR | SEN | REF | 24 | PRP | 10 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-05-01 | 1999-02-01 |  | 2000-12-01 | 2001-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | Switzerland | Implementation of the RMP: demonstration project to retrofit domestic refrigerators for the use of hydrocarbon refrigerant | RMP | AFR | SEN | REF | 33 | TAS | 14 | A | I |  | 47 | 0 | 0 | 0 | 2001-03-01 | 2003-07-01 | 2001-11-01 |  | 2004-03-01 | 2004-06-01 | 71230 | 0 | 71230 | 71230 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2001
FIN | UNEP | Implementation of the RMP: activities for supporting and monitoring the RMP | Individual | AFR | SEN | REF | 33 | TAS | 15 | A | I | CFC | 29.4 | 29.4 | 0 | 0 | 2001-03-01 | 2001-07-01 | 2003-12-01 |  | 2002-05-01 | 2003-06-01 | 44500 | -37 | 44463 | 44463 | 100% | 0 | 0 |  | 5785 | -4.81 | 5780.19 | 0 | 0
FIN | UNIDO | Implementation of the RMP: Refrigerant recovery and recycling scheme | RMP Update | AFR | SEN | REF | 33 | TAS | 16 | A | I | CFC | 56.1 | 56.1 |  |  | 2001-03-01 | 2002-06-01 | 2002-04-01 |  | 2003-03-01 | 2004-04-01 | 85000 | -1970 | 83030 | 83030.13 | 100% | -0.13 | 0 |  | 11050 | -273 | 10777 | 0 | 0 | FIN |  |  |  | INV
FIN | UNEP | Country programme preparation | Individual | AFR | SEN | SEV | 11 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-11-01 | 1995-02-01 |  | 1993-11-01 | 1993-12-01 | 13000 | 0 | 13000 | 13000 | 100% | 0 | 0 |  | 1690 | 0 | 1690 | 0 | 0
FIN | UNEP | Ozone Focal Point | Individual | AFR | SEN | SEV | 11 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1995-07-01 | 1996-11-01 |  | 1997-12-01 | 1999-09-01 | 175000 | 0 | 175000 | 175000 | 100% | 0 | 0 |  | 22750 | 0 | 22750 | 0 | 0
FIN | UNEP | Expansion and upgrading of statistics networks for customs | Individual | AFR | SEN | SEV | 11 | TRA | 03 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-01-01 | 1994-10-01 |  | 1994-10-01 | 1994-12-01 | 26000 | 0 | 26000 | 26000 | 100% | 0 | 0 |  | 3380 | 0 | 3380 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening | Individual | AFR | SEN | SEV | 23 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-06-01 | 1999-12-01 |  | 2000-02-01 | 2000-02-01 | 117000 | 0 | 117000 | 117000 | 100% | 0 | 0 |  | 15210 | 0 | 15210 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening (Phase III) | Individual | AFR | SEN | SEV | 29 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-06-01 | 2001-12-01 |  | 2001-12-01 | 2003-12-01 | 117000 | 0 | 117000 | 117000 | 100% | 0 | 0 |  | 15210 | 0 | 15210 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening projects (Phase IV) | Individual | AFR | SEN | SEV | 36 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-05-01 | 2004-04-01 |  | 2003-12-01 | 2004-12-01 | 152100 | 0 | 152100 | 152100 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project: phase 5 | Individual | AFR | SEN | SEV | 41 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-08-01 | 2005-12-01 |  | 2005-12-01 | 2007-03-01 | 152100 | 0 | 152100 | 152100 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase VI) | Individual | AFR | SEN | SEV | 47 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-02-01 | 2007-12-01 |  | 2007-12-01 | 2008-12-01 | 152100 | 0 | 152100 | 152100 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase VII) | Individual | AFR | SEN | SEV | 53 | INS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-11-01 |  | 2009-11-01 | 2010-12-01 | 152100 | 0 | 152100 | 152100 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase VIII) | Individual | AFR | SEN | SEV | 59 | INS | 29 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-02-01 | 2011-11-01 |  | 2011-12-01 | 2011-12-01 | 82388 | 69713 | 152101 | 152101 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase IX: 1/2012-12/2013) | Individual | AFR | SEN | SEV | 65 | INS | 32 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-04-01 | 2013-12-01 |  | 2013-09-01 | 2013-09-01 | 152101 | 0 | 152101 | 152101 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of institutional strengthening project (phase X: 1/2014-12/2015) | Individual | AFR | SEN | SEV | 71 | INS | 33 | A | I |  | 0 |  | 0 |  | 2013-12-01 | 2014-08-01 | 2015-12-01 |  | 2015-12-01 |  | 152101 | 0 | 152101 | 91991 | 60.48% | 60110 | 60110 | 60110 | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
ONG | UNEP | Extension of institutional strengthening project (phase XI: 1/2016-12/2017) | Individual | AFR | SEN | SEV | 75 | INS | 34 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-04-01 | 2017-12-01 | 2017-12-01 |  |  | 194689 | 0 | 194689 | 0 | 0% | 194689 | 194689 | 19468.9 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Country signed the SSFA in February 2016. 2015 CP data and 2015 Art7 data reported. Ozone day celebrated. Legal arrangements (actual/planned): Agreement signed in February 2016.First payment: April 2016. All activities under the SSFA are completed (as planned) No__ First mission (actual/planned): _ N/A -TOR completed (actual/planned): _ Yes __ First disbursement date (actual/planned): _1st disbursement done in April 2016__ All funds disbursed (yes/no): _ No__ Any delay? (yes/no): No___ If Yes, reasons for delay & action plan to resolve: n/a___ If Yes, will delay have impact on project completion date (yes/no): _ No __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Brief progress report (actual/planned): Legal arrangements (actual/planned): Agreement signed in February 2016. First payment: April 2016. Country signed the SSFA in February 2016. 2015 CP data and 2015 Art7 data reported. Ozone day celebrated. NOU trained 215 RAC technicians and 47 custom officers in 2016. All activities under the SSFA are completed (as planned) No__ First mission (actual/planned): _ N/A -TOR completed (actual/planned): _ Yes __ First disbursement date (actual/planned): _1st disbursement done in April 2016__ All funds disbursed (yes/no): _ No__ Any delay? (yes/no): No___ If Yes, reasons for delay & action plan to resolve: n/a___ If Yes, will delay have impact on project completion date (yes/no): _ No __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | AFR | SEN | SEV | 75 | TAS | 35 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-05-01 | 2016-12-01 | 2017-10-01 |  |  | 110000 | 0 | 110000 | 0 | 0% | 110000 | 0 | 11000 | 14300 | 0 | 0 | 14300 | 0 | Brief progress report (actual/planned): Country signed the SSFA in April 2016. First payment sent in May 2016. Country recruited national consultants in June 2016. Legal arrangements (actual/planned): Agreement signed in April 2016. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in May 2016 __ All funds disbursed (yes/no): _ No.__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Brief progress report (actual/planned): Country signed the SSFA in April 2016. First payment sent in May 2016. Country submitted the darft Survey report in January 2017. Legal arrangements (actual/planned): Agreement signed in April 2016. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in May 2016 __ All funds disbursed (yes/no): _ No.__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
FIN | France | Project preparation for a terminal phase-out management plan |  | AFR | SEY | PHA | 49 | PRP | 11 | A | I | CFC | 0 |  | 0 |  | 2006-07-01 | 2006-09-01 | 2007-07-01 |  | 2007-03-01 | 2007-03-01 | 20000 | -5483 | 14517 | 14742 | 101.5% | -225 |  | 0 | 2600 | -713 | 1921 | -34 |  | The French contribution was implemented by GTZ. Project completed
FIN | France | Terminal ODS phase-out management plan (first tranche) | Multi-Year | AFR | SEY | PHA | 51 | INV | 12 | A | I | CFC | 0 | 0 | 0 |  | 2007-03-01 | 2007-06-01 | 2009-03-01 |  | 2009-06-01 | 2011-06-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 |  | 0 | 15600 | 0 | 15600 | 0 |  | The French contribution was implmented by GTZ-Proklima. Project completed.
FIN | France | Terminal ODS phase-out management plan (second tranche) | Multi-Year | AFR | SEY | PHA | 55 | INV | 14 | A | I | CFC | 0 |  | 0 |  | 2008-07-01 | 2009-05-01 | 2009-03-01 |  | 2010-12-01 | 2012-12-01 | 60000 | -40121 | 19879 | 21524 | 108.3% | -1645 |  | 0 | 7800 | -5216 | 2830 | -246 |  | The French contribution was implemented by GTZ-Proklima. Project completed.
FIN | Germany | Preparation of a HCFC phase-out management plan | Individual | AFR | SEY | PHA | 58 | PRP | 15 | A | I | HCFC | 0 | 0 | 0 |  | 2009-07-01 | 2009-09-01 | 2010-07-01 |  | 2010-12-01 | 2012-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | HPMP dafted and approved.
FIN | France | Terminal ODS phase-out management plan (third tranche) | Multi-Year | AFR | SEY | PHA | 59 | INV | 16 | A | I | CFC | 0.4 |  | 0 |  | 2009-11-01 |  | 2010-12-01 |  | 2010-12-01 | 2012-12-01 | 13000 | -13000 | 0 | 533 |  | -533 |  | 0 | 1690 | -1690 | 80 | -80 |  | The funds were not needed to complete the project.
FIN | Germany | HCFC phase-out management plan (first tranche) | Multi-Year | AFR | SEY | PHA | 63 | INV | 17 | A | I | HCFC | 0.4 | 0.4 | 0 |  | 2011-04-01 | 2011-06-01 | 2013-03-01 |  | 2014-09-01 | 2014-12-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 25333 | 0 | 25333 | 0 |  | Rather slow implementation since 2013. Office equipment and spares for the idenitfiers were requested, these were supplied. 2 technician trainings were conducted on best practices and safe use of HCs. Energy analysis was comissioned of the University building planned for demonstrating solar ACs was conducted.
ONG | Germany | HCFC phase-out management plan (second tranche) | Multi-Year | AFR | SEY | PHA | 70 | INV | 19 | A | I | HCFC | 0.4 |  | 0 |  | 2013-07-01 | 2014-10-01 | 2015-07-01 | 2017-07-01 |  |  | 160000 | 0 | 160000 | 115000 | 71.88% | 45000 | 0 | 45000 | 20267 | 0 | 14567 | 5700 |  | The country conducted 3 HC trainings mainly for the hotel industry on safe handling of HCs. A trainer and the NOU attended the Cool training in Germany to gain a better understanding of natural refrigerants. | R290 ACs are in the Country and will be installed in near future. The process has taken time to reach a conclusion on the most optimal solution. This additional delay was related to the supplier not being ready to supply the 19 units requested as per specifications of Seychelles government. |  |  | INV
ONG | Germany | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | AFR | SEY | PHA | 75 | INV | 23 | A | I | HCFC | 0.6 |  | 0 |  | 2015-11-01 |  | 2025-12-01 | 2025-12-01 |  |  | 180000 | 0 | 180000 | 0 | 0% | 180000 | 0 | 10000 | 22800 | 0 | 0 | 22800 |  | The funds from the previous tranche need to be disbursed before these funds are used.
COM | Germany | Verification report for stage I of HCFC phase-out management plan | Individual | AFR | SEY | PHA | 75 | TAS | 24 | A | I | HCFC | 0 |  | 0 |  | 2015-11-01 | 2015-12-01 | 2016-12-01 |  | 2016-03-01 |  | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 |  | Project completed in early 2016
FIN | UNIDO | Preparation of a project proposal for setting up a national refrigerant recovery and recycling centre, National Halon Bank | Individual | AFR | SEY | REF | 15 | PRP | 03 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-06-01 | 1995-06-01 |  | 1998-01-01 | 2000-07-01 | 15000 | -10846 | 4154 | 4154 | 100% | 0 | 0 |  | 1950 | -1411 | 539 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | SEY | REF | 23 | PRP | 04 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-03-01 |  | 1999-03-01 | 2001-01-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | SEY | REF | 26 | TAS | 05 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2002-08-01 | 2004-07-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | project completed. PCR submitted. RMP Update ongoing
FIN | Germany | Project preparation for a refrigerant management plan update | RMP Update | AFR | SEY | REF | 37 | PRP | 07 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-02-01 | 2003-08-01 |  | 2003-07-01 | 2004-05-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | RMP update approved
FIN | Germany | Phasing out ODS use in the refrigeration and air conditioning sector | Individual | AFR | SEY | REF | 40 | TAS | 08 | A | I |  | 2.4 | 2.4 | 0 |  | 2003-07-01 | 2003-10-01 | 2006-12-01 |  | 2006-12-01 | 2007-10-01 | 41607 | 0 | 41607 | 41607 | 100% | 0 | 0 | 0 | 5409 | 0 | 5409 | 0 | 0 | PCR has been submitted in October 2007.
FIN | UNEP | Country programme preparation | Individual | AFR | SEY | SEV | 11 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1994-02-01 | 1995-02-01 |  | 1994-07-01 | 1994-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Institutional strengthening | Individual | AFR | SEY | SEV | 13 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1995-03-01 | 1997-07-01 |  | 2000-07-01 | 2000-07-01 | 31900 | 0 | 31900 | 31900 | 100% | 0 | 0 |  | 4147 | 0 | 4147 | 0 | 0 |  |  |  | 1999-12-01
FIN | UNEP | Renewal of institutional strengthening (Phase II) | Individual | AFR | SEY | SEV | 31 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2000-07-01 | 2002-10-01 | 2002-08-01 |  | 2004-12-01 | 2005-12-01 | 21267 | 0 | 21267 | 21267 | 100% | 0 | 0 |  | 2765 | 0 | 2765 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | AFR | SEY | SEV | 44 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-04-01 | 2006-12-01 |  | 2007-12-01 | 2009-06-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | AFR | SEY | SEV | 53 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2009-06-01 | 2009-11-01 |  | 2011-07-01 | 2011-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase V) | Individual | AFR | SEY | SEV | 63 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-12-01 | 2011-03-01 |  | 2013-12-01 | 2014-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of institutional strengthening project (phase VI: 7/2013-6/2015) | Individual | AFR | SEY | SEV | 70 | INS | 20 | A | I |  | 0 |  | 0 |  | 2013-07-01 | 2014-02-01 | 2015-06-01 |  | 2016-12-01 |  | 60000 | 0 | 60000 | 46500 | 77.5% | 13500 | 13500 |  | 0 | 0 | 0 | 0 | 0 | Project completed | Project completed
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | AFR | SEY | SEV | 74 | TAS | 21 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-04-01 | 2016-05-01 | 2017-05-01 |  |  | 40000 | 0 | 40000 | 5086.1 | 12.72% | 34913.9 | 34913.9 | 3491.39 | 5200 | 0 | 661.193 | 4538.807 | 4538.807 | Brief progress report (actual/planned): The first stakeholders meeting was organized by the NOU in June 2016 in Victoria-Mahe with the main goal to agree on the plan for the Survey of ODS alternatives at the national level and obtain support of main national stakeholders. The meeting was attended by 30 participants. One National Consultant was hired in June 2016 by the NOU to support the data collection. The National Consultant assisted the NOU in the identification of the current use of ODS alternatives by substance/sector and collection of import/export data for the substances for the past a couple of years. The National Consultant also provided support in establishing growth patterns in use by substance/sector and in compiling data on available ODS alternatives for various applications. The NOU and the National Consultant drafted and cross checked the information to ensure the completion of end-user surveys, collection, analysis, and aggregation of consumption data. The various sections of the report were drafted. The second stakeholders meeting was organized by the NOU in November 2016 in Victoria-Mahe with the main goal to organise consultations with representatives of the government and private sector to finalize the outcomes of the Survey of ODS alternatives and discuss potential opportunities for introduction of those alternatives in the country. The draft report was prepared by the NOU and the National Consultant. It was reviewed and finalized based on the format approved by ExCom decision 75/67 as contained in document UNEP/OzL.Pro/ExCom/75/77/Rev.1 after incorporating inputs/ comments raised during National Stakeholders’ workshop. The final report has been submitted to UNEP for final review and submission to MLFS. The NOU participated in the ODS Alternative Thematic workshop held in December 2016 to refine the draft report according to the revised template for the report. The report has been finally submitted to UNEP. Legal arrangements(actual/planned): The SSFA was drafted and signed by UNEP and the Government of Seychelles in February 2016___Initial stages of project implementation(actual/planned): _Yes__ Intermediate goals achieved (actual/planned): Yes___ Project completion and follow up: _No__ First disbursement date (actual/planned): _April 2016__ All funds disbursed (yes/no): No___ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): __N/A_ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): The NOU incorporated comments from UNEP ROA and Paris and re-submitted final ODS survey report.
ONG | UNEP | Extension of institutional strengthening project (phase VII: 11/2015-10/2017) | Individual | AFR | SEY | SEV | 75 | INS | 22 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-07-01 | 2017-11-01 | 2018-05-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 85000 | 8500 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): _ The licensing and quota systems are in place and operational. The NOU registered all importers of HCFC for 2016, advertised for quota allocation for 2016 HCFC importation and conducted two inspection visits to various boarders to check how customs officers are enforcing the control measures of HCFC importation. The NOU trained 40 custom officers on illegal trade and 60 RAC technicians. The NOU submitted 2015 Country Programme and Article 7 Data reports. The NOU celebrated 2016 International Ozone Day and conducted several awareness activities. The NOU also participated in all Montreal Protocol meetings organized in 2016.___ Legal arrangements(actual/planned): The SSFA was drafted and signed by UNEP and the Government of Seychelles in May 2016__Initial stages of project implementation(actual/planned): _Yes__ Intermediate goals achieved (actual/planned): _Yes__ Project completion and follow up: No___ First disbursement date (actual/planned): _July 2016__ All funds disbursed (yes/no): _No__ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: __N/A_ If Yes, will delay have impact on project completion date (yes/no): _Yes__ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): The NOU continues to monitor imports and trade of ODS and ODS related equipment. Collection of the 2016 data on ODS imports and consumption has been completed and is being analyzed for submission. NOU commenced preparation of national legislative requirement processes in planning for ratification of Kigali amendment.
FIN | UNEP | Methyl bromide communication programme | Individual | AFR | SIL | FUM | 47 | TAS | 12 | A | I | MB | 0.4 | 0.4 | 0 | 0 | 2005-11-01 | 2006-03-01 | 2007-12-01 |  | 2010-11-01 | 2011-11-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNDP | Project preparation for a halon sectoral phase-out plan | Individual | AFR | SIL | HAL | 45 | PRP | 10 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-06-01 | 2006-04-01 |  | 2006-12-01 | 2011-11-01 | 16870 | -7907.55 | 8962.45 | 8962 | 99.99% | 0.45 | 0 | 0 | 1265 | -592.95 | 672.0172 | 0.032843 | 0 | Completed in 2006. |  | 2005 |  | Investment
FIN | UNDP | Technical assistance for awareness raising in the halon sector | Individual | AFR | SIL | HAL | 51 | TAS | 15 | N | I | Halons | 0 | 0 | 0 | 0 | 2007-03-01 | 2009-05-01 | 2008-09-01 |  | 2010-12-01 | 2012-05-01 | 15000 | -5.92 | 14994.08 | 14994 | 100% | 0.08 | 0 | 0 | 1350 | -0.53 | 1349.46 | 0.01 | 0 | Financially completed in 2012. |  | 2007 | 2010-01-01 | Non-Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | SIL | PHA | 48 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-02-01 | 2007-04-01 |  | 2008-12-01 | 2010-12-01 | 18000 | -4986 | 13014 | 13014 | 100% | 0 | 0 |  | 2340 | -648.18 | 1691.82 | 0 | 0
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | AFR | SIL | PHA | 48 | PRP | 14 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-03-01 | 2007-04-01 |  | 2008-12-01 | 2011-11-01 | 12000 | -1361.25 | 10638.75 | 10639 | 100% | -0.25 | 0 | 0 | 900 | -102.09 | 797.9249 | -0.01495 | 0 | Completed in 2008. |  | 2006 |  | Investment
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | SIL | PHA | 56 | PRP | 18 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-03-01 | 2009-11-01 |  | 2011-12-01 | 2011-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 |  | 11050 | 0 | 11050 | 0 | 0
FIN | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | SIL | PHA | 57 | INV | 20 | N | I | CFC | 12.2 | 12.2 | 0 | 0 | 2009-04-01 | 2010-03-01 | 2011-03-01 |  | 2010-12-01 | 2013-07-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 3600 | 0 | 3600 | 0 | 0 | Financially completed in 2013. |  | 2009 |  | Investment
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | SIL | PHA | 57 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-10-01 | 2010-06-01 |  | 2012-07-01 | 2013-12-01 | 95000 | 0 | 95000 | 95000 | 100% | 0 | 0 |  | 12350 | 0 | 12350 | 0 | 0
FIN | UNDP | Terminal phase-out management plan (second tranche) | Multi-year | AFR | SIL | PHA | 61 | INV | 22 | N | I | CFC | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-04-01 | 2011-07-01 |  | 2011-12-01 | 2013-07-01 | 20000 | -5284.81 | 14715.19 | 14715 | 100% | 0.19 | 0 | 0 | 1800 | -475.63 | 1324.35 | 0.02 | 0 | Financially completed in 2013. | Completed in 2011. Additional equipment has been distributed to the centres of excellence; the Kenema Polytechnic and the Magburuka Polytechnic (FEB 2012). Refresher trainings were also conducted for the Refrigerator Engineer Association on good refriger | 2010 |  | Investment
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | SIL | PHA | 61 | TAS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2012-01-01 | 2011-07-01 |  | 2013-12-01 | 2014-12-01 | 55000 | 0 | 55000 | 55000 | 100% | 0 | 0 |  | 7150 | 0 | 7150 | 0 | 0
COM | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | SIL | PHA | 65 | INV | 24 | A | I | HCFC | 0.1 | 0.1 |  |  | 2011-11-01 | 2013-05-01 | 2016-11-30 |  | 2016-12-01 |  | 50000 | 0 | 50000 | 47620 | 95.24% | 2380 | 0 | 1 | 4500 | 0 | 4286 | 214 | 0 | Remainder of funds were used for servicing tools. - Project is completed. | Project completed. Financial closure is being processed. |  |  | INV |  | To request the submission of additional status report to the 79th meeting to monitor the procurement and/or delivery of the equipment.
COM | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | SIL | PHA | 65 | TAS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-04-01 | 2013-11-01 |  | 2015-06-01 |  | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 | Project financially completed | Project financially completed
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | AFR | SIL | PHA | 70 | TAS | 27 | A | I |  | 0.1 |  | 0 |  | 2013-07-01 | 2014-05-01 | 2016-07-01 | 2017-10-01 |  |  | 23000 | 0 | 23000 | 22731.67 | 98.83% | 268.33 | 268.33 | 26.833 | 2990 | 0 | 2955.1171 | 34.8829 | 34.8829 | Brief progress report (actual/planned): The NOU registered all importers of HCFCs and organized one stakeholders meeting in Feb 2016 to coordinate and allocate licenses and quotas. The NOU issued 10 Licenses to ten 10 leading importers of refrigerants and refrigeration depending equipment as stipulated in the ODS regulation 2010. The NOU engaged the judiciary on the implementation of the 2010 ODS regulations. The NOU conducted two inspection visits on importers to assess compliance with allocated quotas. In addition, in January, 2016 one inspection visit was made at customs post in national port to verify consignment imported by licensed holders. The NOU conducted 2 Customs training workshops on 13th May, 2016 at the Gendema border post between Sierra Leone and Liberia and on 1st November 2016 at Gbalamuya border post between Sierra Leone and Guinea, to enhance capacity of Custom officers and other law enforcement agents in detecting illegal, where a total of 75 custom officers were trained. The NOU conducted one RAC training workshop on 6th May, 2016 at the Government Technical Institute, Kissy, Freetown, where 40 refrigeration and air conditioning technicians were trained on good refrigeration practices in HCFCs management and practical session was held at the workshop of the Technical Institute on recovery programs. The NOU conducted one RAC certification workshop where 33 RAC technicians were trained and certified under the RAC certification scheme. The NOU distributed 20 Recovery to Government RAC Technical institutes. Legal arrangements (actual/planned): The SSFA was drafted and signed by UNEP and the Government of Sierra Leone in March 2014. Any delay (Yes/No): No_ First mission (actual/planned): __NO._ TOR completed (actual/planned): _N/A__ First disbursement date (actual/planned): First disbursement was made in May, 2014____ All funds disbursed (yes/no): _No__ Any delay? (yes/no): _No_ If Yes, reasons for delay & action plan to resolve: __ If Yes, will delay have impact on project completion date (yes/no): _No__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): The NOU registered all importers of HCFCs and organized one stakeholders meeting in Feb 2016 to coordinate and allocate licenses and quotas. The NOU continues to monitor imports and trade of ODS and ODS related equipment.
ONG | UNIDO | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | AFR | SIL | PHA | 76 | INV | 31 | A | I | HCFC | 0.2 | 0 |  |  | 2016-05-01 |  | 2020-05-31 | 2020-05-31 |  |  | 50000 | 0 | 50000 | 0 | 0% | 50000 | 0 | 5000 | 4500 | 0 | 0 | 4500 | 0 | Approved by the 76th ExCom on the understanding that if the country were to decide to proceed with retrofits and associated servicing to flammable and toxic refrigerants in refrigeration and air conditioning equipment originally designed for non flammable substances, it would do so assuming all associated responsibilities and risks and only in accordance with the relevant standards and protocols. | Approved on the understanding that if the country were to decide to proceed with retrofits and associated servicing to flammable and toxic refrigerants in refrigeration and air conditioning equipment originally designed for non flammable substances, it would do so assuming all associated responsibilities and risks and only in accordance with the relevant standards and protocols. Milestone 1: Meeting held in 2016 with ozone officer. Working arrangements agreed '-Bids to be requested in 2nd quarter 2017 |  |  | INV
ONG | UNEP | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | AFR | SIL | PHA | 76 | TAS | 30 | A | I |  | 0 |  | 0 |  | 2016-05-01 |  | 2018-12-01 | 2018-12-01 |  |  | 20000 | 0 | 20000 | 0 | 0% | 20000 | 20000 | 2000 | 2600 | 0 | 0 | 2600 | 2600 | Brief progress report (actual/planned): Newly approved. The NOU registered importers of HCFCs and organized one stakeholders meeting in March 2016 to coordinate and allocate licenses and quotas. The NOU carried out 3 inspection visits to monitor distribution of HCFCs to check compliance with quotas allocated between June and November 2016. The NOU conducted two RAC training workshops and two custom training workshops, and trained 60 technicians and 30 custom officers respectively. The NOU conducted one steering committee meeting to monitor, and coordinate the operations of the NOU. Two public awareness meetings were organized and more than 50 participants. ___ Legal arrangements (actual/planned): The SSFA was drafted by UNEP and sent to the Government of Sierra Leone for signature. ___Initial stages of project implementation (actual/planned): __Yes_ Intermediate goals achieved (actual/planned): _No__ Project completion and follow up: _No__ First disbursement date (actual/planned): No. All funds disbursed (yes/no): No__ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: __N/A_ | Brief progress report (actual/planned): The NOU registered all importers of HCFCs and organized one stakeholders meeting in Feb 2016 to coordinate and allocate licenses and quotas. The NOU continues to monitor imports and trade of ODS and ODS related equipment.
ONG | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Individual | AFR | SIL | PHA | 77 | TAS | 32 | A | I |  | 0 |  | 0 |  | 2016-12-01 |  | 2018-06-01 | 2018-06-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 3000 | 3900 | 0 | 0 | 3900 | 0 | Newly approved project. | Brief progress report (actual/planned): The project was approved in Dec 2016. The licensing and quota system are in place and operational. UNEP is preparing to hire a consultant for the verification. TORs for verification consultancy have been drafted and being reviewed ___ Legal arrangements (actual/planned): N/A. ___Initial stages of project implementation (actual/planned): __N/A_ Intermediate goals achieved (actual/planned): _No__ Project completion and follow up: _Yes__ First disbursement date (actual/planned): __N/A___. All funds disbursed (yes/no): N/A_ Any delay? (yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: __N/A_
FIN | UNDP | Implementation of the RMP: improved servicing and maintenance within the refrigeration sector, and recovery and recycling project | RMP-Component | AFR | SIL | REF | 41 | TAS | 05 | N | I | CFC | 14.1 | 14.1 | 0 | 0 | 2003-12-01 | 2005-02-01 | 2006-12-01 |  | 2009-12-01 | 2013-02-01 | 92400 | 0 | 92400 | 92400 | 100% | 0 | 0 | 0 | 8316 | 0 | 8316 | 0 | 0 | Financially completed in 2013. |  | 2003 |  | Investment
FIN | UNDP | Implementation of the RMP: incentive programme for the commercial and industrial refrigeration end-user sector | RMP-Component | AFR | SIL | REF | 41 | TAS | 06 | N | I | CFC | 16.4 | 16.4 | 0 | 0 | 2003-12-01 | 2010-03-01 | 2008-12-01 |  | 2010-12-01 | 2013-02-01 | 107350 | 0 | 107350 | 107350 | 100% | 0 | 0 | 0 | 9661.5 | 0 | 9661.5 | 0 | 0 | Financially completed in 2013. |  | 2003 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: MAC recovery/recycling of CFC-12 | RMP-Component | AFR | SIL | REF | 41 | TAS | 07 | N | I | CFC | 9.4 | 9.4 | 0 | 0 | 2003-12-01 | 2010-03-01 | 2006-12-01 |  | 2010-12-01 | 2013-02-01 | 61858 | -18404.6 | 43453.4 | 43453 | 100% | 0.4 | 0 | 0 | 5567.22 | -1656.41 | 3910.77 | 0.04 | 0 | Financially completed in 2013. |  | 2003 |  | Investment
FIN | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | AFR | SIL | REF | 41 | TAS | 09 | A | I | CFC | 2.4 | 0 | 0 | 0 | 2003-12-01 | 2010-06-01 | 2006-12-01 |  | 2008-02-01 | 2010-12-01 | 15455 | 0 | 15455 | 15455 | 100% | 0 | 0 |  | 2009 | 0 | 2009 | 0 | 0
FIN | UNEP | Implementation of the RMP: training of trainers in code of good refrigeration practices/establishment of national refrigeration demonstration centre | Individual | AFR | SIL | REF | 41 | TRA | 04 | A | I | CFC | 18.2 | 18.2 | 0 | 0 | 2003-12-01 | 2004-11-01 | 2006-12-01 |  | 2008-12-01 | 2011-12-01 | 119460 | -39463 | 79997 | 79997 | 100% | 0 | 0 |  | 15530 | -5130.19 | 10399.81 | 0 | 0
FIN | UNEP | Implementation of the RMP: customs training programme | Individual | AFR | SIL | REF | 41 | TRA | 08 | A | I | CFC | 6.4 | 0 | 0 | 0 | 2003-12-01 | 2004-08-01 | 2005-12-01 |  | 2008-01-01 | 2011-03-01 | 41840 | -9826 | 32014 | 32014 | 100% | 0 | 0 |  | 5439 | -1277.02 | 4161.98 | 0 | 0
FIN | UNEP | Formulation of national phase out strategy | Individual | AFR | SIL | SEV | 35 | TAS | 01 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2002-08-01 |  | 2003-12-01 | 2011-06-01 | 40000 | -23000 | 17000 | 17000 | 100% | 0 | 0 |  | 5200 | -2990 | 2210 | 0 | 0
FIN | UNEP | Establishment of the Ozone Unit | Individual | AFR | SIL | SEV | 36 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-04-01 |  | 2003-12-01 | 2004-12-01 | 26000 | 0 | 26000 | 26000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Establishment of the Ozone Unit (phase I) | Individual | AFR | SIL | SEV | 41 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-02-01 | 2005-12-01 |  | 2005-12-01 | 2007-02-01 | 85800 | 0 | 85800 | 85800 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase II, one year) | Individual | AFR | SIL | SEV | 47 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-02-01 | 2006-12-01 |  | 2007-01-01 | 2008-12-01 | 48445 | 0 | 48445 | 48445 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase II, 2nd year) | Individual | AFR | SIL | SEV | 51 | INS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2007-03-01 | 2007-06-01 | 2008-03-01 |  | 2008-03-01 | 2009-03-01 | 48445 | 0 | 48445 | 48445 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | AFR | SIL | SEV | 54 | INS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-08-01 | 2010-03-01 |  | 2010-07-01 | 2011-07-01 | 85800 | 0 | 85800 | 85800 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of institutional strengthening project (phase IV) | Individual | AFR | SIL | SEV | 61 | INS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-04-01 | 2012-06-01 |  | 2016-12-01 |  | 85800 | 0 | 85800 | 65850 | 76.75% | 19950 | 19950 | 19950 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The licensing and quota systems are in place and functioning. The NOU registered all importers of HCFCs and organized one stakeholders meeting in Feb 2016 to coordinate and allocate licenses and quotas. The NOU conducted two inspection visits on importers to assess compliance with allocated quotas. The NOU trained 30 custom officers on identification of illegal trade and 40 RAC technicians to equip them with knowledge and skills in hydrocarbon and good refrigeration practices. The NOU submitted 2015 Country Programme and Article 7 Data reports. The NOU celebrated 2016 International Ozone Day and conducted several awareness activities including school essay competition. The NOU participated in all Montreal Protocol meetings organized in 2016___ Legal arrangements (actual/planned): The SSFA was drafted and signed by UNEP and the Government of Sierra Leone in April 2011. Initial stages of project implementation(actual/planned): _Yes__ Intermediate goals achieved (actual/planned): _Yes__ Project completion and follow up: _Yes__ First disbursement date (actual/planned): The first disbursement was made in May 2014 ___ All funds disbursed (yes/no): Yes___ Any delay?(yes/no): __No_ If Yes, reasons for delay & action plan to resolve: __N/A_ If Yes, will delay have impact on project completion date (yes/no): __N/A_ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: __N/A_ | An SSFA for USD 19,950 was signed with the country.
ONG | UNEP | Extension of institutional strengthening project (phase V: 4/2013-3/2015) | Individual | AFR | SIL | SEV | 69 | INS | 26 | A | I |  | 0 |  | 0 |  | 2013-04-01 | 2013-12-01 | 2015-03-01 | 2017-07-01 |  |  | 85800 | 0 | 85800 | 39900 | 46.5% | 45900 | 11679.48 | 4590 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The licensing and quota systems are in place and functioning. The NOU registered all importers of HCFCs and organized one stakeholders meeting in Feb 2016 to coordinate and allocate licenses and quotas. The NOU conducted two inspection visits on importers to assess compliance with allocated quotas. The NOU trained 30 custom officers on identification of illegal trade and 40 RAC technicians to equip them with knowledge and skills in hydrocarbon and good refrigeration practices. The NOU submitted 2015 Country Programme and Article 7 Data reports. The NOU celebrated 2016 International Ozone Day and conducted several awareness activities including school essay competition. The NOU participated in all Montreal Protocol meetings organized in 2016___ Legal arrangements (actual/planned): The SSFA was drafted and signed by UNEP and the Government of Sierra Leone in January 2011. Initial stages of project implementation(actual/planned): _Yes__ Intermediate goals achieved (actual/planned): _Yes__ Project completion and follow up: _Yes__ First disbursement date (actual/planned): The first disbursement was made in April 2011 ___ All funds disbursed (yes/no): Yes___ Any delay?(yes/no): __No_ If Yes, reasons for delay & action plan to resolve: __N/A_ If Yes, will delay have impact on project completion date (yes/no): __N/A_ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: __N/A_ | Project completed
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | AFR | SIL | SEV | 74 | TAS | 28 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-04-01 | 2016-05-01 | 2017-05-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 35788 | 4000 | 5200 | 0 | 0 | 5200 | 4652.44 | Brief progress report (actual/planned): The first stakeholders meeting was organized by the NOU in four regions, namely, on 24th June 2016 in Freetown attended by 40 participants; on 8th June, 2016, in Makeni, attended by 43 participants); on 9th June, 2016, in Kono, attended by 43 participants and on 10th June,2016, in Bo, attended by 35 participants, all from the ODS Alternative user sectors and importers attended. The main goal of the meeting was to sensitize the government and industry on the survey and agree on the plan for the Survey of ODS alternatives at the national level and obtain support of main national stakeholders. One National Consultant was hired in March 2016 by the NOU to support the data collection. The National Consultant assisted the NOU in the identification of the current use of ODS alternatives by substance/sector and collection of import/export data for the substances for the past a couple of years. The National Consultant also provided support in establishing growth patterns in use by substance/sector and in compiling data on available ODS alternatives for various applications.The NOU and the National Consultant drafted and cross checked the information to ensure the completion of end-user surveys, collection, analysis, and aggregation of consumption data. The various sections of the report were drafted. The second stakeholders meeting was organized by the NOU in November 2016 in Freetown with the main goal to organise consultations with representatives of the government and private sector to finalize the outcomes of the Survey of ODS alternatives and discuss potential opportunities for introduction of those alternatives in the country. A total of 60 participants from the sectors using ODS Alternatives were in attendance. The draft report was prepared by the NOU and the National Consultant. It was reviewed and finalized based on the format approved by ExCom decision 75/67 as contained in document UNEP/OzL.Pro/ExCom/75/77/Rev.1 after incorporating inputs/ comments raised during National Stakeholders’ workshop. The final report was submitted to UNEP in Decemberr 2016 for final review and submission to MLFS. The NOU participated in the ODS Alternative Thematic workshop held in December 2016 to refine the draft report according to the revised template for the report. The report has been finally submitted to UNEP. Legal arrangements(actual/planned): The SSFA was drafted and signed by UNEP and the Government of Sierra Leone in January 2016___Initial stages of project implementation(actual/planned): _Yes__ Intermediate goals achieved (actual/planned): Yes___ Project completion and follow up: _No__ First disbursement date (actual/planned): _April 2016__ All funds disbursed (yes/no): No___ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): __N/A_ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): The NOU incorporated comments from UNEP ROA and Paris and re-submitted final ODS survey report.
ONG | UNEP | Extension of institutional strengthening project (phase VI: 12/2015-11/2017) | Individual | AFR | SIL | SEV | 75 | INS | 29 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-12-01 | 2017-11-01 | 2018-03-01 |  |  | 109824 | 0 | 109824 | 0 | 0% | 109824 | 109824 | 10982.4 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The licensing and quota systems are in place and functioning. The NOU registered all importers of HCFCs and organized one stakeholders meeting in Feb 2016 to coordinate and allocate licenses and quotas. The NOU issued 10 Licenses to ten 10 leading importers of refrigerants and refrigeration depending equipment as stipulated in the ODS regulation 2010. The NOU engaged the judiciary on the implementation of the 2010 ODS regulations. The NOU conducted two inspection visits on importers to assess compliance with allocated quotas. In addition, in January, 2016 one inspection visit was made at customs post in national port to verify consignment imported by licensed holders. The NOU conducted 2 Customs training workshops on 13th May, 2016 at the Gendema border post between Sierra Leone and Liberia and on 1st November 2016 at Gbalamuya border post between Sierra Leone and Guinea, to enhance capacity of Custom officers and other law enforcement agents in detecting illegal, where a total of 75 custom officers were trained. The NOU conducted one RAC training workshop on 6th May, 2016 at the Government Technical Institute, Kissy, Freetown, where 40 refrigeration and air conditioning technicians were trained on good refrigeration practices in HCFCs management and practical session was held at the workshop of the Technical Institute on recovery programs. The NOU conducted one RAC certification workshop where 33 RAC technicians were trained and certified under the RAC certification scheme. The NOU distributed 20 Recovery to Government RAC Technical institutes. The NOU submitted 2015 Country Programme and Article 7 Data reports. The NOU celebrated 2016 International Ozone Day and conducted several awareness activities including distribution of Books to Schools and Nature clubs across the country and TV and radio discussions were held. The NOU participated in all Montreal Protocol meetings organized in 2016. The SSFA was drafted and signed by UNEP and the Government of Sierra Leone in November 2016. Initial stages of project implementation(actual/planned):Yes__ Intermediate goals achieved (actual/planned): __Yes_ Project completion and follow up: _No__ First disbursement date (actual/planned): The first payment was sent in December 2016,_ All funds disbursed (yes/no): No_ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A_ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __NO_ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): The NOU conducted 4 radio discussion held in January and February, 2017 on the Montreal protocol, Certification of all technicians operating in Sierra Leone, Import/export licensing and the Quota systems as per the ODS regulation 2010. The NOU conducted training of 40 Customs, other law enforcement officers and local authorities on combating illegal trade at the border between Sierra Leone and Guinea on 5th February, 2017. The NOU completed data collection for 2016 HCFCs awaiting submission to Ozone and Multilateral fund Secretariats after approval by the Government. NOU commenced preparation of national legislative requirement processes in planning for ratification of Kigali amendment.
FIN | IBRD | Country programme preparation and user sector pre-investment studies (1993) | Individual | EUR | SLO | SEV | 11 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 |  | 1994-11-01 |  | 1994-12-01 | 1994-12-01 | 50000 | -50000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1993) |  | EUR | SLO | SEV | 11 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 |  | 1995-03-01 |  | 1994-03-01 | 1994-03-01 | 100000 | -100000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Country programme preparation and user sector pre-investment studies (1994) | Individual | EUR | SLO | SEV | 12 | CPG | 04 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1994) |  | EUR | SLO | SEV | 12 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 100000 | -22085 | 77915 | 77915 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | A workshop held on project preparation and processing procedures earlier in the year has helped the preparation of 8 subprojects in the refrigeration, foam, aerosol and solvents sectors. |  |  |  | Non-INV | 0
FIN | UNIDO | Preparation for HCFC phase-out investment activities (polyurethane foam sector) | Individual | AFR | SOA | FOA | 59 | PRP | 02 | A | I |  | 0 | 0 |  |  | 2009-11-01 | 2010-02-01 | 2010-11-30 |  | 2012-12-01 | 2014-07-01 | 150000 | -2119 | 147881 | 147881.22 | 100% | -0.22 | 0 |  | 11250 | -159 | 11091 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (polyurethane foam sector plan) | Multi-Year | AFR | SOA | FOA | 67 | INV | 03 | A | I | HCFC | 24.9 | 24.9 |  |  | 2012-07-01 | 2013-02-01 | 2013-07-31 | 2017-12-31 |  |  | 1850224 | 0 | 1850224 | 1771277.9 | 95.73% | 78946.1 | 24585 | 75000 | 129516 | 0 | 123989 | 5527 | 1720.95 | Brief report: Assistance to SMEs to ease the transition to non-ODS, low-GWP alternatives provided. Milestone 1: Terms of reference for equipment completed - Yes Milestone 2: Bidding completed, supplier selected – Yes Milestone 3: Equipment shipped/delivered/installed at site - Yes Milestone 4: Tranche request prepared – Yes Milestone 5: Training conducted – Yes Activities planned but not implemented: No Actions towards next goal: Provide assistance to SMEs to ease the transition to non-ODS and low-GWP alternatives provided. Was any delay during the reporting year? Yes. The activities were combined with the next tranche. Any recurring problem? No Any impact on project completion date: Yes Any actions required by Executive Committee? No | Brief report: Assistance to SMEs to ease the transition to non-ODS, low-GWP alternatives provided. Milestone 1: Terms of reference for equipment completed - Yes Milestone 2: Bidding completed, supplier selected – Yes Milestone 3: Equipment shipped/delivered/installed at site - Yes Milestone 4: Tranche request prepared – Yes Milestone 5: Training conducted – Yes Activities planned but not implemented: No Actions towards next goal: Provide assistance to SMEs to ease the transition to non-ODS and low-GWP alternatives provided. Was any delay during the reporting year? Yes. The activities were combined with the next tranche Any recurring problem? No Any impact on project completion date: No Any actions required by Executive Committee? No |  |  | INV
COM | UNIDO | Preparation of a demonstration project on the technical and economic advantages of the vacuum assisted injection in discontinuous panel's plant retrofitted from HCFC-141b to pentane | Individual | AFR | SOA | FOA | 74 | PRP | 08 | A | I |  | 0 | 0 |  |  | 2015-05-01 | 2015-08-01 | 2016-05-30 |  | 2016-12-01 |  | 40000 | 0 | 40000 | 38974.6 | 97.44% | 1025.4 | 0 | 1 | 2800 | 0 | 0 | 2800 | 0 | - Project completed, demonstration project prepared, submitted and approved in 2016. - The project focuses on the introduction of new technology, thus no HCFC 141b phase out is accounted, since South Africa introduced ban on HCFC 141b import from 1 January 2016. - Necessary accompanying documents for project document submission obtained from NOU. Independent technical review obtained. Milestones achieved: Milestone 1: First mission/Working arrangements agreed - Yes Milestone 2: ToR for project formulation completed - Yes Milestone 3: Local institutions/project carrier identified - Yes Milestone 4: Experts recruited - Yes Milestone 6: All technical input completed - Yes Milestone 7: Draft document completed - Yes Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | Project completed. Balance will be returned to the 79th Meeting of the ExCom. |  |  | NON-INV
ONG | UNIDO | Demonstration project on the technical and economic advantages of the vacuum assisted injection in discontinuous panels plant retrofitted from HCFC-141b to pentane | Individual | AFR | SOA | FOA | 76 | DEM | 09 | A | I |  | 0 | 0 |  |  | 2016-05-01 | 2016-09-01 | 2017-09-30 | 2018-07-01 |  |  | 222200 | 0 | 222200 | 6531.09 | 2.939% | 215668.91 | 0 | 20000 | 19998 | 0 | 588 | 19410 | 0 | - This demo project was approved by 76th ExCom; - PAD of the project established. - Original concept of ODS phase out and demonstration of new technology was refused by MLFS, due to South Africa's early ban of HCFC 141b (Jan. 2016). - Agreement on the implementation procedures and TOR for the purchase of equipment prepared subsequently after PAD was established. - The procurement has been however hampered due to lengthy process of the beneficiary to make final decision on the cost sharing, though originally committed through the Agreement. - In December the beneficiary (Dalucon Co.) retreated and the procurement was interrupted. - The new beneficiary (M Projects) with identical programme and manufacturing technology for refrigerated trucks have been identified within a short period of time. - Agreement on the Implementation Procedures signed by M Projects. Milestones achieved: Milestone 1: First mission/Working arrangements (agreement/document signatures/PDA) agreed - Yes Milestone 2:Terms of reference (for equipment and/or services) completed - Yes Milestone 3:First disbursement made - Yes Milestone 4: Bidding completed, supplier selected - No Milestone 5: Equipment shipped/delivered/installed at site - No Milestone 6: Commissioning and trial runs completed - No Actions towards next goals: Identify new beneficiary and restart procurement procedure: obtain offers, evaluate bids, select supplier. Was there any delay during the reporting year? Yes, due to beneficiary's eventual decision not to pay cost sharing due to reduced funds by the MLFS. Any recurring problem? No Any impact on project completion date: Yes If yes, implications: New beneficiary plans to invest to completely new press to be equipped with necessary components for vacuum assisted injection, which may require longer lead time (including transport complications due to the size and weight). Any action required by Executive Committee? No | - Procurement resumed in March 2017. Actions towards next goals: Identify new beneficiary and restart procurement procedure: obtain offers, evaluate bids, select supplier. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | NON-INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | AFR | SOA | PHA | 55 | PRP | 01 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2009-06-01 | 2009-07-31 |  | 2012-12-01 | 2015-03-01 | 195000 | -519 | 194481 | 194481.15 | 100% | -0.15 | 0 |  | 14625 | -39 | 14586 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing, custom training and monitoring) | Multi-Year | AFR | SOA | PHA | 67 | TAS | 04 | A | I |  | 0 | 0 |  |  | 2012-07-01 | 2013-06-01 | 2013-07-31 | 2017-12-31 |  |  | 110005 | 0 | 110005 | 10185.06 | 9.259% | 99819.94 | 0 | 80000 | 7700 | 0 | 713 | 6987 | 0 | Brief report: Assistance to SMEs to ease the transition to non-ODS, low-GWP alternatives provided. Milestone 1: Terms of reference for equipment completed - Yes Milestone 2: Bidding completed, supplier selected – Yes Milestone 3: Equipment shipped/delivered/installed at site - Yes Milestone 4: Tranche request prepared – Yes Milestone 5: Training conducted – Yes Activities planned but not implemented: No Actions towards next goal: Provide assistance to SMEs to ease the transition to non-ODS and low-GWP alternatives provided. Was any delay during the reporting year? Yes. The activities were combined with the next tranche Any recurring problem? No Any impact on project completion date: Yes Any actions required by Executive Committee? No | Brief report: Assistance to SMEs to ease the transition to non-ODS, low-GWP alternatives provided. Milestone 1: Terms of reference for equipment completed - Yes Milestone 2: Bidding completed, supplier selected – Yes Milestone 3: Equipment shipped/delivered/installed at site - Yes Milestone 4: Tranche request prepared – Yes Milestone 5: Training conducted – Yes Activities planned but not implemented: No Actions towards next goal: Provide assistance to SMEs to ease the transition to non-ODS and low-GWP alternatives provided. Was any delay during the reporting year? Yes. The activities were combined with the next tranche Any recurring problem? No Any impact on project completion date: Yes Any actions required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, secondtranche) (polyurethane foam sector plan) | Multi-Year | AFR | SOA | PHA | 71 | INV | 05 | A | I | HCFC | 35.7 | 0 |  |  | 2013-12-01 | 2014-04-01 | 2016-06-01 | 2018-12-31 |  |  | 2042620 | 0 | 2042620 | 1272538.57 | 62.3% | 770081.43 | 542204.24 | 500000 | 142983 | 0 | 89078 | 53905 | 37954.2968 | Brief report: Assistance to SMEs to ease the transition to non-ODS, low-GWP alternatives provided. Milestone 1: Terms of reference for equipment completed - Yes Milestone 2: Bidding completed, supplier selected – Yes Milestone 3: Equipment shipped/delivered/installed at site - Yes Milestone 4: Tranche request prepared – Yes Milestone 5: Training conducted – Yes Activities planned but not implemented: No Actions towards next goal: Provide assistance to SMEs to ease the transition to non-ODS and low-GWP alternatives provided. Was any delay during the reporting year? Yes. The activities were combined with the previous tranche Any recurring problem? No Any impact on project completion date: Yes Any actions required by Executive Committee? No | Brief report: Assistance to SMEs to ease the transition to non-ODS, low-GWP alternatives provided. Milestone 1: Terms of reference for equipment completed - Yes Milestone 2: Bidding completed, supplier selected – Yes Milestone 3: Equipment shipped/delivered/installed at site - Yes Milestone 4: Tranche request prepared – Yes Milestone 5: Training conducted – Yes Activities planned but not implemented: No Actions towards next goal: Provide assistance to SMEs to ease the transition to non-ODS and low-GWP alternatives provided. Was any delay during the reporting year? Yes. The activities were combined with the previous tranche Any recurring problem? No Any impact on project completion date: Yes Any actions required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing, custom training and monitoring) | Multi-Year | AFR | SOA | PHA | 71 | INV | 06 | A | I | HCFC | 6.2 | 0 |  |  | 2013-12-01 | 2014-03-01 | 2016-06-01 | 2017-12-31 |  |  | 550000 | 0 | 550000 | 127284.53 | 23.14% | 422715.47 | 170418.43 | 250000 | 38500 | 0 | 8910 | 29590 | 11929.2901 | Brief report: Assistance to SMEs to ease the transition to non-ODS, low-GWP alternatives provided. Milestone 1: Terms of reference for equipment completed - Yes Milestone 2: Bidding completed, supplier selected – Yes Milestone 3: Equipment shipped/delivered/installed at site - Yes Milestone 4: Tranche request prepared – Yes Milestone 5: Training conducted – Yes Activities planned but not implemented: No Actions towards next goals: Provide assistance to SMEs to ease the transition to non-ODS and low-GWP alternatives provided. Was any delay during the reporting year? Yes. The activities were combined with the previous tranche Any recurring problem? No Any impact on project completion date: Yes Any actions required by Executive Committee? No | Brief report: Assistance to SMEs to ease the transition to non-ODS, low-GWP alternatives provided. Milestone 1: Terms of reference for equipment completed - Yes Milestone 2: Bidding completed, supplier selected – Yes Milestone 3: Equipment shipped/delivered/installed at site - Yes Milestone 4: Tranche request prepared – Yes Milestone 5: Training conducted – Yes Activities planned but not implemented: No Actions towards next goals: Provide assistance to SMEs to ease the transition to non-ODS and low-GWP alternatives provided. Was any delay during the reporting year? Yes. The activities were combined with the previous tranche Any recurring problem? No Any impact on project completion date: Yes Any actions required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, third tranche) (polyurethane foam sector plan) | Multi-Year | AFR | SOA | PHA | 76 | INV | 10 | A | I | HCFC | 21 | 0 |  |  | 2016-05-01 |  | 2019-12-31 | 2019-12-31 |  |  | 622437 | 0 | 622437 | 0 | 0% | 622437 | 0 | 50000 | 43571 | 0 | 0 | 43571 | 0 | The project was approved by the 76th ExCom. | Brief report: Assistance to SMEs to ease the transition to non-ODS and low-GWP alternatives. Milestone 1: Terms of reference for equipment completed - Yes Milestone 2: Bidding completed, supplier selected – No Milestone 3: Equipment shipped/delivered/installed at site - No Milestone 4: Tranche request prepared – n/a Milestone 5: Training conducted – No Activities planned but not implemented: No Actions towards next goal: Conduct training, and provide assistance to SMEs to ease the transition to non-ODS and low-GWP alternatives provided. Was any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any actions required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing, custom training and monitoring) | Multi-Year | AFR | SOA | PHA | 76 | TAS | 11 | A | I | HCFC | 6.4 | 0 |  |  | 2016-05-01 |  | 2019-12-31 | 2019-12-31 |  |  | 679898 | 0 | 679898 | 0 | 0% | 679898 | 0 | 50000 | 47593 | 0 | 0 | 47593 | 0 | The project was approved by the 76th ExCom. | Brief report: Assistance to SMEs to ease the transition to non-ODS and low-GWP alternatives. Milestone 1: Terms of reference for equipment completed - Yes Milestone 2: Bidding completed, supplier selected – No Milestone 3: Equipment shipped/delivered/installed at site - No Milestone 4: Tranche request prepared – n/a Milestone 5: Training conducted – No Activities planned but not implemented: No Actions towards next goal: Conduct training, provide assistance to SMEs to ease the transition to non-ODS and low-GWP alternatives provided. Was any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any actions required by Executive Committee? No |  |  | INV
FIN | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, first tranche, Solomon Islands) | Multi-Year | ASP | SOI | PHA | 63 | TAS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-09-01 | 2015-03-01 |  | 2016-06-01 | 2016-08-01 | 110250 | 0 | 110250 | 110250 | 100% | 0 | 0 |  | 14333 | 0 | 14333 | 0 | 0 | Brief progress report (actual/planned): The activities that were implemented in 2016 comprised of (i) implementation of licensing and quota system, (ii)permit system for handling, storage and sales of HCFCs, (iii) monitoring of refrigerant identifiers and RAC servicing tools and (iv) outreaching and awareness raising. NOU collaborated with the local counterparts to conduct a refresher training on "Best Practice in Refrigeration and Air-conditioning Sector" for RAC technicians on 23-24 March 2016 in Honiara. There were 25 RAC technicians with an additional five from the ministry of mines, energy and rural electrification attending the workshop. Activities under the first tranche were completed. The RAC Techncian training in Good refrigeration practices is now part of the curriculum of the Solomon National University (TVET). 2015 CP data was submitted to the MLFS online. The last payment was approved and made to the country. The project was financially completed in 2016. Legal arrangement: The SSFA was signed in August 2011. First Mission: March 2014 TOR completed: Not applicable. First disbursement date: September 2011 All funds disbursed (yes/no): Yes. Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/A | Project financially completed.
ONG | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, second tranche, Solomon Islands) | Multi-year | ASP | SOI | PHA | 74 | TAS | 11 | A | I |  | 0.7 |  | 0 |  | 2015-05-01 | 2016-08-01 | 2020-05-01 | 2020-12-01 |  |  | 65250 | 0 | 65250 | 9000 | 13.79% | 56250 | 33000 | 5625 | 8483 | 0 | 1170.069 | 7312.931 | 4290.2529 | Brief progress report (actual/planned): The SSFA was signed by UNEP and the Government of Solomon Islands in March 2016. The first payment under the second tranche was also made to the country in August 2016. The licensing and quota system was implemented in 2016. UNEP conducted a misison in September 2016 to follow-up project implementation and participated in update RAC training workshop, which was delivered by national trainers. UNEP worked closely with the NOU to engage multi-stakeholders in the implementation of HPMP, second tranche to synergize HPMP with other on-going environmental policies/projects e.g. PALS, Samoa Pathway. NOO is working closley with customs on the control on trade of ODS and ODS dependent technologies. 2015 CP data was submitted to MLFS online. Legal arrangements (actual/planned): The SSFA was signed in March 2016. First Mission: September 2016. TOR completed: Not applicable First disbursement date: August 2016. All funds disbursed (yes/no): No. Any delay? (yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): UNEP keeps regular communications with the country to expedite HPMP implementation as per the agreed work plan. The update customs and enforcement training is planned in 2017.
FIN | Australia | Implementation of the PIC Strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | SOI | REF | 36 | TAS | 02 | A | I |  | 0.3 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2005-04-01 |  | 2008-06-01 | 2012-05-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 | 0 | 0 | 1040 | 0 | 1040 | 0 | 0 | completed |  | 2002
FIN | Australia | Implementation of the PIC Strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | SOI | REF | 36 | TAS | 04 | A | I |  | 1.4 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2005-04-01 |  | 2008-06-01 | 2012-05-01 | 34000 | 0 | 34000 | 34000 | 100% | 0 | 0 | 0 | 4420 | 0 | 4420 | 0 | 0 | completed |  | 2002
FIN | UNEP | Country programme preparation | Individual | ASP | SOI | SEV | 17 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1997-01-01 | 1996-10-01 |  | 2002-03-01 | 2003-07-01 | 20000 | -7000 | 13000 | 13000 | 100% | 0 | 0 |  | 2600 | -910 | 1690 | 0 | 0 |  |  |  | 1999-12-01
FIN | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | SOI | SEV | 36 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-05-01 | 2005-04-01 |  | 2006-06-01 | 2010-12-01 | 20250 | 0 | 20250 | 20250 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase II) | Individual | ASP | SOI | SEV | 49 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2010-01-01 | 2007-12-01 |  | 2008-12-01 | 2010-12-01 | 6833 | 0 | 6833 | 6833 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase II, second year) | Individual | ASP | SOI | SEV | 53 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-12-01 | 2009-11-01 |  | 2010-03-01 | 2011-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase III) | Individual | ASP | SOI | SEV | 59 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-10-01 | 2011-11-01 |  | 2011-11-01 | 2011-12-01 | 32500 | 27500 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase IV: 12/2011-11/2013) | Individual | ASP | SOI | SEV | 64 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-05-01 | 2013-11-01 |  | 2013-12-01 | 2014-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase V: 12/2013-11/2015) | Individual | ASP | SOI | SEV | 70 | INS | 10 | A | I |  | 0 |  | 0 |  | 2013-07-01 | 2014-01-01 | 2015-11-01 |  | 2016-06-01 |  | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. | Project completed.
ONG | UNEP | Renewal of institutional strengthening project (phase VI: 12/2015-11/2017) | Individual | ASP | SOI | SEV | 74 | INS | 12 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-11-01 | 2017-11-01 | 2018-02-01 |  |  | 60000 | 0 | 60000 | 11000 | 18.33% | 49000 | 49000 | 4900 | 0 | 0 | 0 | 0 | 0 | Brief Progress report (actual/planned): The SSFA was signed between UNEP and the Government of Solomon Islands in March 2016. The first payment was made to country in November 2016. This late first payment was due to having to make first payment after closure of previous phase. The NOU has been responsible for the management of all Montreal Protocol activities in a large (6 major islands and 900 smaller islands). The operation of the NOU was going on well with stable NOO. The license/quota system has been enforced in 2016. All importation RAC technologies (ODS and non-ODS) are required to have import licenses. Country continued to enforce the import tax on refrigerant and RAC equipment including MAC. NOU also coordinated and facilitated the implementation of HPMP and ODS Alternative Survey. The NOU also organized the 2016 ozone day celebration, and actively joined the regional and global ozone related meetings e.g. the network meeting. 2015 Article 7 and CP data were submitted to the Ozone Secretariat and MLFS respectively. Legal arrangements(actual/planned): The SSFA was signed in March 2016. Initial stages of project implementation(actual/planned): Mar 2016. Intermediate goals achieved (actual/planned): Project progressing Satisfactorily, Compliance (2015) sustained. Project completion and follow up: Not applicable. First disbursement date (actual/planned): November 2016. All funds disbursed (yes/no): No. Any delay?(yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: N/A | Brief Progress report (actual/planned): Country continues to enforce the licensing and quota system. There are 2 remaining payments to be disbursed to the country. Projecct will be completed in February 2018. IS renewal planned to be submitted at the 80 Ex. Com.
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | ASP | SOI | SEV | 75 | TAS | 13 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-05-01 | 2016-12-01 | 2017-06-01 |  |  | 40000 | 0 | 40000 | 20000 | 50% | 20000 | 5000 | 2000 | 5200 | 0 | 2600 | 2600 | 650 | Brief progress report (actual/planned): The SSFA was signed by UNEP and the Government of Solomon Islands in May 2016. The first payment was made to the country in May 2016. NOO attended the training for conducting natiional surveys as part of Thematic workshop for Asia and the Pacific in June 2016. The national stakeholder workshop was organzied during UNEP mission in September 2016. The survey methodology and questionnaire have been finalized and agreed. The local consultant was recruited by the Government to conduct the dada collection. The data collection was on-going. Legal arrangements(actual/planned): the SSFA was signed in May 2016. Initial stages of project implementation(actual/planned): May 2016. Intermediate goals achieved (actual/planned): Not applicable. Project completion and follow up: Not applicable. First disbursement date (actual/planned): May 2016. All funds disbursed (yes/no): No. Any delay?(yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date (yes/no): N/o. Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): The local consultant assisted the NOU in the identification of the current use of ODS alternatives by substance/sector and collection of import/export data for the substances for the past a couple of years. The local consultant also provided support in establishing growth patterns in use by substance/sector and in compiling data on available ODS alternatives for various applications. UNEP's consultant will visit Solomon Islands to finalize the data collection and analysis in March 2017. The draft report will be prepared based on the format approved by ExCom decision 75/67 as contained in document UNEP/OzL.Pro/ExCom/75/77/Rev.1.
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | AFR | SOM | PHA | 60 | PRP | 07 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-12-01 | 2011-04-30 |  | 2012-12-01 | 2014-05-01 | 85000 | -4040 | 80960 | 80959.62 | 100% | 0.38 | 0 |  | 6375 | -303 | 6072 | 0 | 0 | FIN
COM | UNIDO | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | AFR | SOM | PHA | 67 | INV | 08 | A | I | HCFC | 0.5 | 0.5 |  |  | 2012-07-01 | 2013-02-01 | 2016-07-31 |  | 2016-12-01 |  | 133500 | 0 | 133500 | 133500.13 | 100% | -0.13 | -0.24 |  | 9345 | 0 | 9345 | 0 | -0.0168 | Brief report: The training, planned in the framework of the project, was successfully held. Milestone 1: Intermediate goals achieved – Yes Milestone 2: Training organized – Yes Milestone 3: Tranche request prepared - Yes Activities planned but not implemented: No Actions towards next goal: review country data reporting. Was any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any actions required by Executive Committee? No Tranche completed. | Financial closure is being initiated. |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (additional security) | Multi-Year | AFR | SOM | PHA | 67 | TAS | 09 | A | I |  | 0 | 0 |  |  | 2012-07-01 | 2013-02-01 | 2016-07-31 | 2017-12-31 |  |  | 40374 | 0 | 40374 | 21329.13 | 52.83% | 19044.87 | 5311.76 | 19000 | 2826 | 0 | 1493 | 1333 | 371.8232 | Brief report: The training, planned in the framework of the project, was successfully held. Milestone 1: Intermediate goals achieved – Yes Milestone 2: HCFC survey prepared – No Milestone 3: Training organized – Yes Milestone 4: Tranche request prepared - Yes Activities planned but not implemented: No Actions towards next goal: review country data reporting. Was any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: Yes Any actions required by Executive Committee? No | Brief report: The training, planned in the framework of the project, was successfully held. Milestone 1: Intermediate goals achieved – Yes Milestone 2: HCFC survey prepared – No Milestone 3: Training organized – Yes Milestone 4: Tranche request prepared - Yes Activities planned but not implemented: No Actions towards next goal: review country data reporting. Was any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: Yes Any actions required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | Multi-Year | AFR | SOM | PHA | 77 | INV | 12 | A | I | HCFC | 1.3 | 0 |  |  | 2016-11-01 |  | 2020-12-31 | 2019-12-31 |  |  | 141500 | 0 | 141500 | 0 | 0% | 141500 | 0 | 15000 | 9905 | 0 | 0 | 9905 | 0 | Noted that the Agreement between the Government and the Executive Committee had been updated based on the revised starting point and the change in monitoring institutions; and that the revised starting point for sustained aggregate reduction in HCFC consumption was 18.10 ODP tonnes, consisting of 16.42 ODP tonnes of HCFC-22 and 1.68 ODP tonnes of HCFC-141b contained in imported pre-blended polyols. | Brief report: Training of trainers for the servicing sector. Milestones achieved: Milestone 1: Selection of training location – No Milestone 2: Preparation of a training program – Yes Milestone 3: Procurement of equipment - No Activities planned but not implemented: No Actions towards next goal: Training of technicians. Was any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: Yes, completion date was changed as per updated project plan. Any actions required by Executive Committee? No
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) (additional security) | Multi-Year | AFR | SOM | PHA | 77 | TAS | 13 | A | I |  | 0 | 0 |  |  | 2016-11-01 |  | 2020-12-31 | 2019-12-31 |  |  | 45000 | 0 | 45000 | 0 | 0% | 45000 | 0 | 10000 | 3150 | 0 | 0 | 3150 | 0 | Approved, on an exceptional basis, the additional funding for the security-related costs to enable the implementation of the programme, in line with decision 67/28(h). | Brief report: Additional travel fund, due to the security situation
FIN | UNDP | Formulation of refrigerant management plan | Individual | AFR | SOM | REF | 36 | PRP | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2003-04-01 |  | 2005-11-01 | 2005-12-01 | 15000 | -14659 | 341 | 341 | 100% | 0 | 0 | 0 | 1950 | -1906 | 44 | 0 | 0 | Completed in 2005. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNEP | Formulation of national phase-out strategy | Individual | AFR | SOM | SEV | 35 | TAS | 01 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-03-01 | 2002-08-01 |  | 2010-12-01 | 2013-12-01 | 60000 | -24902 | 35098 | 35098 | 100% | 0 | 0 |  | 7800 | -3237.01 | 4562.99 | 0 | 0 |  |  |  | 2003-12-01
FIN | UNEP | Establishment of the Ozone Unit | Individual | AFR | SOM | SEV | 36 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2008-12-01 | 2009-12-01 | 26000 | 0 | 26000 | 26000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Establishment of the National Ozone Committee (institutional strengthening) | Individual | AFR | SOM | SEV | 44 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2008-12-01 | 2005-12-01 |  | 2010-07-01 | 2011-07-01 | 26000 | 0 | 26000 | 26000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Institutional strengthening (first phase) | Individual | AFR | SOM | SEV | 59 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2011-02-01 | 2011-12-01 |  | 2011-12-01 | 2012-12-01 | 30000 | 29995 | 59995 | 59995 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of the institutional strengthening project (phase II: 1/2013-12/2014) | Individual | AFR | SOM | SEV | 68 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-04-01 | 2014-11-01 | 2017-10-01 |  |  | 60000 | 0 | 60000 | 19500 | 32.5% | 40500 | 40500 | 4050 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The licensing and quota systems are in place and functioning. The NOU conducted public awareness activity to sensitize the public on HCFC phase-out. __ The NOU submitted 2015 Country Programme and Article 7 Data reports and celebrated 2015 International Ozone Day with several awareness activities. The NOU also participated in all Montreal Protocol meetings organized in 2016. Legal arrangements (actual/planned): The SSFA was drafted and signed by UNEP and the Government of Somalia in August 2013. Initial stages of project implementation(actual/planned):Yes__ Intermediate goals achieved (actual/planned): __Yes_ Project completion and follow up: _No_ First disbursement date (actual/planned): First disbursement was made in April 2013, _ All funds disbursed (yes/no): NO_ Any delay?(yes/no): _YES__ If Yes, reasons for delay & action plan to resolve: _There is delay in implementation of activities due to political instability in the country_ If Yes, will delay have impact on project completion date (yes/no): _Yes_ Any ongoing problems (yes/no): __Yes_ If Yes, is any action required by ExCom: No__ | Brief progress report (actual/planned): The NOU continues to monitor imports and trade of ODS and ODS related equipment. Collection of the 2016 data on ODS imports and consumption has been completed and is being analyzed for submission. NOU commenced preparation of national legislative requirement processes in planning for ratification of Kigali amendment.
ONG | UNEP | Extension of the institutional strengthening project (phase III: 12/2016-11/2018) | Individual | AFR | SOM | SEV | 77 | INS | 11 | A | I |  | 0 |  | 0 |  | 2016-12-01 |  | 2018-11-01 | 2018-11-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | Newly approved project. | Brief progress report (actual/planned): The project was approved in Dec 2016. The licensing and quota system are in place and operational. The NOU registered all importers of HCFCs and organized one stakeholders meeting in Feb 2017 to coordinate and allocate licenses and quotas. The NOU continues to monitor imports and trade of ODS and ODS related equipment. ___ Legal arrangements (actual/planned): The SSFA was drafted and sent to the Government of Somalia for signature. ___Initial stages of project implementation (actual/planned): __Yes_ Intermediate goals achieved (actual/planned): _No__ Project completion and follow up: _Yes__ First disbursement date (actual/planned): __No ____. All funds disbursed (yes/no): No__ Any delay? (yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: __N/A_
FIN | UNDP | Conversion to CFC-free hydrocarbon aerosol propellant technology at International Cosmetic Ltd. (ICL) | Individual | ASP | SRL | ARS | 18 | INV | 07 | A | I | CFC | 5 | 5 | 0 | 0 | 1995-11-01 | 1997-04-01 | 1996-11-01 |  | 2001-08-01 | 2003-11-01 | 38968 | -5599 | 33369 | 33369 | 100% | 0 | 0 | 0 | 5065.84 | -727.87 | 4337.97 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1995 | 1999-08-01 | Investment
FIN | UNDP | Project preparation assistance for the methyl bromide sector | Individual | ASP | SRL | FUM | 25 | PRP | 12 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-08-01 | 1999-08-01 |  | 1999-06-01 | 2004-12-01 | 25000 | -1090 | 23910 | 23910 | 100% | 0 | 0 | 0 | 3250 | -142.09 | 3107.91 | 0 | 0 | Completed in 1999. Financially completed in 2004. |  | 1998 |  | Investment
FIN | UNDP | Alternatives to methyl bromide for eradication of tea nematodes in Sri Lanka | Individual | ASP | SRL | FUM | 27 | DEM | 13 | A | I | MeBr | 3.9 | 3.9 | 0 | 0 | 1999-03-01 | 2000-07-01 | 2001-04-01 |  | 2007-10-01 | 2012-06-01 | 310200 | -7844.05 | 302355.95 | 302356 | 100% | -0.05 | 0 | 0 | 40326 | -1019.73 | 39306.28 | -0.01 | 0 | Financially completed in 2012. |  | 1999 |  | Investment
FIN | UNDP | Preparation of a terminal programme in the fumigant sector | Individual | ASP | SRL | FUM | 36 | PRP | 19 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-07-01 | 2003-04-01 |  | 2002-11-01 | 2005-11-01 | 25000 | -3638 | 21362 | 21362 | 100% | 0 | 0 | 0 | 3250 | -472.94 | 2777.06 | 0 | 0 | Completed in 2002. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Methyl bromide phase-out for all remaining uses excluding QPS applications | One-off-Phaseout | ASP | SRL | FUM | 38 | TAS | 21 | N | I | MeBr | 3.3 | 3.3 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2005-11-01 |  | 2007-10-01 | 2010-06-01 | 130000 | -1.55 | 129998.45 | 129998 | 100% | 0.45 | 0 | 0 | 16900 | -0.2 | 16899.74 | 0.06 | 0 | Financially completed in 2010. |  | 2002 | 2005-11-01 | Non-Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (foam and solvent sectors) | Individual | ASP | SRL | MUS | 57 | PRP | 35 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 |  | 2010-03-01 |  | 2012-06-01 | 2013-06-01 | 40000 | -40000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 3000 | -3000 | 0 | 0 | 0 | Financially completed in 2013. | Completed in 2012. | 2009 |  | Investment
FIN | UNEP | National compliance action plan: halon bank management | Individual | ASP | SRL | PHA | 43 | TAS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2005-06-01 | 2009-12-01 |  | 2009-08-01 | 2010-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 |  |  |  | 2007-12-01
FIN | Japan | National compliance action plan: incentive programme for commercial and industrial refrigeration end-users | Individual | ASP | SRL | PHA | 43 | TAS | 26 | A | I | CFC | 5 |  | 0 |  | 2004-07-01 | 2008-12-01 | 2005-12-01 |  | 2014-09-01 | 2016-05-01 | 144000 | 0 | 144000 | 144000 | 100% | 0 | 0 | 0 | 18720 | 0 | 18720 | 0 | 0 | The project was succesfully completed in Sept. 2014. |  | 2004 | 2007-12-01 | investment
FIN | Japan | National compliance action plan: MAC recovery/recycling and retrofit | Individual | ASP | SRL | PHA | 43 | TAS | 27 | A | I |  | 0 |  | 0 |  | 2004-07-01 | 2006-12-01 | 2005-12-01 |  | 2010-09-01 | 2015-12-01 | 123000 | 0 | 123000 | 123000 | 100% | 0 | 0 | 0 | 15990 | 0 | 15990 | 0 |  | The project was succesfully completed in Sept. 2010. |  | 2004 |  | investment
FIN | Japan | National compliance action plan: recovery and recycling programme | Individual | ASP | SRL | PHA | 43 | TAS | 28 | A | I |  | 0 |  | 0 |  | 2004-07-01 | 2008-10-01 | 2006-12-01 |  | 2010-09-01 | 2015-12-01 | 290400 | 0 | 290400 | 290400 | 100% | 0 | 0 | 0 | 37752 | 0 | 37752 | 0 |  | The project was succesfully completed in Sept. 2010. |  | 2004 |  | investment
FIN | Japan | National compliance action plan: monitoring the activities proposed in the plan | Individual | ASP | SRL | PHA | 43 | TAS | 29 | A | I |  | 0 |  | 0 |  | 2004-07-01 | 2005-11-01 | 2009-12-01 |  | 2010-09-01 | 2015-12-01 | 108000 | 0 | 108000 | 108000 | 100% | 0 | 0 | 0 | 14040 | 0 | 14040 | 0 | 0 | The project was succesfully completed in Sept. 2010. |  | 2004 |  | investment
FIN | UNEP | National compliance action plan: enhancement of national capacity to monitor trade and prevent illegal trade of ODS | Individual | ASP | SRL | PHA | 43 | TRA | 23 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-11-01 | 2009-12-01 |  | 2008-12-01 | 2009-12-01 | 135000 | 0 | 135000 | 135000 | 100% | 0 | 0 |  | 17550 | 0 | 17550 | 0 | 0
FIN | UNEP | National compliance action plan: extension training of the established refrigeration technicians | Individual | ASP | SRL | PHA | 43 | TRA | 25 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2004-11-01 | 2007-12-01 |  | 2008-12-01 | 2009-12-01 | 174600 | 0 | 174600 | 174600 | 100% | 0 | 0 |  | 22698 | 0 | 22698 | 0 | 0
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | ASP | SRL | PHA | 55 | PRP | 33 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2011-12-01 | 2013-06-01 | 112250 | -5028.54 | 107221.46 | 107221 | 100% | 0.46 | 0 | 0 | 8418.75 | -377.15 | 8041.5638 | 0.036199 | 0 | Financially completed in 2013. | Project targeted for financial closure in 2012 | 2008 |  | Investment
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | SRL | PHA | 55 | PRP | 34 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-10-01 | 2009-07-01 |  | 2010-12-01 | 2011-12-01 | 25000 | -5412 | 19588 | 19588 | 100% | 0 | 0 |  | 3250 | -703.56 | 2546.44 | 0 | 0
TRF | IBRD | Preparation of a HCFC phase-out management plan (refrigeration and air-conditioning sectors) |  | ASP | SRL | PHA | 57 | PRP | 36 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 |  | 2010-12-31 |  |  | 2010-07-01 | 60000 | -60000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 4500 | -4500 | 0 | 0 | 0 | Project preparation of HCFC phaseout in the refrigeration and AC sectors was transferred to UNDP at the 61st ExCom Meeting. |  |  |  | Non-INV | 0
FIN | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | SRL | PHA | 62 | INV | 40 | N | I | HCFC | 0.4 | 0.4 | 0 | 0 | 2010-12-01 | 2011-12-01 | 2014-12-01 |  | 2015-12-01 | 2016-12-01 | 180000 | 0 | 180000 | 180000 | 100% | 0 | 0 | 0 | 13500 | 0 | 13500 | 0 | 0 | Financially completed in 2016. | Actvities planned have been completed. Monitoring of the use of Recovery and Reclamation equipment which was distributed late 2014 has been continued. The operation mechanism of Recovery and Reclamation is being discussed and finalized with the stakeholders. The reclamation centre is expected to be operational in late 2015. | 2010 |  | Investment
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | SRL | PHA | 62 | TAS | 41 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-12-01 | 2014-12-01 |  | 2014-12-01 | 2016-09-01 | 125000 | 0 | 125000 | 125000 | 100% | 0 | 0 |  | 16250 | 0 | 16250 | 0 | 0 | Project financially completed | Project financially completed
ONG | UNDP | HCFC phase-out management plan (stage I, second tranche) | Multi-year | ASP | SRL | PHA | 70 | INV | 44 | N | I | HCFC | 0.4 | 0 | 0 | 0 | 2013-07-01 | 2014-04-01 | 2016-07-01 | 2017-07-01 |  |  | 60000 | 0 | 60000 | 37140.9 | 61.9% | 22859.1 | 0 | 9143.64 | 4500 | 0 | 2785.5675 | 1714.4325 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Continued implementation of Import Quota with the 10% of reduction target of HCFC phase out successfully. Provided Refrigerant Identifier to Sri Lanka Customs to prevent illegal import and sub standard refrigerant. Promoted and encourage Refrigeration & Air Conditioning technicians to use environment friendly technology for Recovery of refrigerant, Reclaim at the 8 Reclaim centres established in 2015and Reuse and reuse. Provided incentive payment of approximately US$ 11,230 to procure 62 units of Zero ODP and Low GWP Split Air Conditioners. Continue awareness campaign to the public and school in consultation with the concerned stakeholders. Prodoc signed (actual/planned, yes/no and date):41699 Missions undertaken (actual/planned):- TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: Contract signed First disbursement date (actual/planned): 41730Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:The bulk of the tranche II funds (44,000) was initially allocated to support the Incentive payment scheme for purchasing of Air Conditioners working with 0 ODP, low GWP alternatives such as HFC 32 and HC 290. this programme shows little progress due to (1) R 32 ACs was introduced by DAIKIN to the market in latter part of 2015 and still of high cost compared to R 22 and R 410. Therefore, the incentive scheme had a lessor effect; (2) DAIKIN is sole distributor for R 32 ACs and there is no competition; (3) Available capacities are limited up to 24,000 Btu/h and commercial ACs are not available; and (4) Propaganda by other brand importers about flammability of R 32. However, to persuade the purchase of 0 ODP, low GWP alternative ACs, the NOU has taken a decision to propose government through a Memorandum of Cabinet of Ministers to introduce new Custom Tariff for the import of ACs as follows; Increase existing Tax component by 30% for ACs working with R 22 from 01.01.2017 and ban from 01.01.2018; Reduce existing Tax (which is common to any type of AC) by 10% for ACS working with 0 ODP, low GWP (Less than 700) alternatives from 01.01.2017; Increase existing Tax by 10% for ACs working with 0 ODP but high GWP (Over 700) from 01.01.2017. Proposed new tariff will be incentive for whole country without limiting to 200 units of domestic and 10 units of commercial ACs as mentioned in the project proposal. This will automatically reduce the price of ACs working with R 32 and HC 290 and increase the price of rest of the ACs. Import of R 22 ACs will be dropped drastically. | Ongoing | 2013 |  | Investment
COM | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | ASP | SRL | PHA | 70 | TAS | 43 | A | I |  | 0.5 |  | 0 |  | 2013-07-01 | 2014-03-01 | 2016-07-01 |  | 2016-07-01 |  | 24000 | 0 | 24000 | 24000 | 100% | 0 | 0 |  | 3120 | 0 | 3120 | 0 | 0 | Project is completed | Project is completed
ONG | UNDP | Verification report for stage I of HCFC phase-out management plan | Individual | ASP | SRL | PHA | 71 | TAS | 45 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2013-12-01 | 2016-03-01 | 2016-05-01 | 2017-12-01 |  |  | 30000 | 0 | 30000 | 28784.05 | 95.95% | 1215.95 | 0 | 486.38 | 2700 | 0 | 2590.5645 | 109.4355 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Verification report submitted. The country is under compliance. Third Tranche is approved. Prodoc signed (actual/planned, yes/no and date):Letter of Authorisation sent 21 January 2016 Missions undertaken (actual/planned):- TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: Contract signed First disbursement date (actual/planned): 42430Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | Activity Completed. Tranche 3rd approved in 76th ExCom. Balance payment will be released if any. | 2013 |  | Non-Investment
ONG | UNDP | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | ASP | SRL | PHA | 76 | INV | 49 | N | I | HCFC | 2.1 | 0 | 0 | 0 | 2016-05-01 |  | 2019-12-01 | 2017-12-01 |  |  | 127766 | 0 | 127766 | 0 | 0% | 127766 | 0 | 51106.4 | 9582 | 0 | 0 | 9582 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Disbursement is planned in 2017 AWP Prodoc signed (actual/planned, yes/no and date):42614 Missions undertaken (actual/planned):- TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: Contract signed First disbursement date (actual/planned): Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | on going |  |  | Investment
ONG | UNEP | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | ASP | SRL | PHA | 76 | TAS | 50 | A | I |  | 1.3 |  | 0 |  | 2016-05-01 | 2016-10-01 | 2018-12-01 | 2018-12-01 |  |  | 75100 | 0 | 75100 | 0 | 0% | 75100 | 75100 | 7510 | 9763 | 0 | 0 | 9763 | 9763 | Brief progress report (actual/planned): 30% increase duty for imports of HCFC based equipment planned from Jan 2017. Refresher ToT for technicians organized in Aug 2016. Undertook a feasibility study for a system to recover and treat used fluorocarbons (with co-funding from Japan) through private public partnership with Daikin. Discussion with customs of Sri Lanka on single window system (including South- South cooperation with Maldives). Legal arrangements(actual/planned): SSFA First mission (actual/planned):Yes in Aug 2016 TOR completed(actual/planned): ___ First disbursement date (actual/planned): yes actual in Oct 2016 All funds disbursed (yes/no): No Any delay? (yes/no): ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): Green Building Guidelines approved promoting zero ODS and low GWP (<700) based equipment. Workshop organized in Jan 2017 to discuss the feasibility for a sytem for recovery and treatment of used florocarbons to introduce EE equipment with natural or low GWP refrigerant. Study tour organized for Maldives for reclamation and customs single window system Legal arrangements(actual/planned): SSFA First mission (actual/planned):Yes in Aug 2016 TOR completed(actual/planned): ___ First disbursement date (actual/planned): yes actual in Oct 2016 All funds disbursed (yes/no): No Any delay? (yes/no): ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___
FIN | UNDP | Elimination of CFC-11 and CFC-12 at Associated Electrical Corporation (AEC) Ltd. domestic refrigeration conversion | Individual | ASP | SRL | REF | 17 | INV | 04 | A | I | CFC | 7.3 | 7.3 | 0 | 0 | 1995-07-01 | 1996-01-01 | 1997-01-01 |  | 1998-08-01 | 2000-12-01 | 250114 | -912 | 249202 | 249202 | 100% | 0 | 0 | 0 | 32514.82 | -118.56 | 32396.26 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 at Glacio Ltd. domestic refrigeration conversion | Individual | ASP | SRL | REF | 17 | INV | 05 | A | I | CFC | 6.8 | 6.8 | 0 | 0 | 1995-07-01 | 1996-01-01 | 1997-01-01 |  | 1999-12-01 | 2001-12-01 | 239500 | -26842.62 | 212657.38 | 212657 | 100% | 0.38 | 0 | 0 | 31135 | -3489.82 | 27645.13 | 0.049999 | 0 | Completed in 1999. Financially completed in 2001. |  | 1995 | 1999-08-01 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 at Regnis (Lanka) Ltd. domestic refrigeration conversion | Individual | ASP | SRL | REF | 17 | INV | 06 | A | I | CFC | 6.3 | 6.3 | 0 | 0 | 1995-07-01 | 1996-01-01 | 1997-01-01 |  | 1999-12-01 | 2001-12-01 | 284324 | -18407 | 265917 | 265917 | 100% | 0 | 0 | 0 | 36962.12 | -2393 | 34569.12 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1995 |  | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerants | RMP-Component | ASP | SRL | REF | 20 | TAS | 08 | A | I | CFC | 31.2 | 31.2 | 0 | 0 | 1996-10-01 | 1997-05-01 | 1998-09-01 |  | 1999-12-01 | 2001-12-01 | 352400 | -1472 | 350928 | 350928 | 100% | 0 | 0 | 0 | 45812 | -191.45 | 45620.5477 | 0.0023 | 0 | Completed in 1999. Financially completed in 2001. |  | 1996 |  | Investment
FIN | UNDP | Implementation of the RMP: incentive programme for the commercial and industrial end-user refrigeration | RMP-Component | ASP | SRL | REF | 32 | TAS | 15 | N | I | CFC | 5 | 5 | 0 | 0 | 2000-12-01 | 2002-04-01 | 2006-01-01 |  | 2014-12-01 | 2015-04-01 | 250000 | -8176.65 | 241823.35 | 241823 | 100% | 0.35 | 0 | 0 | 32500 | -1062.96 | 31436.99 | 0.05 | 0 | Financially completed in 2015. | In Q1-2014, activities under implementation are being monitored. Project to be closed in 2014. | 2000 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: monitoring the activities included in the RMP | RMP-Component | ASP | SRL | REF | 32 | TAS | 18 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2003-02-01 | 2003-01-01 |  | 2008-12-01 | 2010-06-01 | 15455 | -2285.64 | 13169.36 | 13169 | 100% | 0.36 | 0 | 0 | 2009.15 | -297.11 | 1711.9922 | 0.047801 | 0 | Financially completed in 2010. |  | 2000 |  | Non-Investment
FIN | UNEP | Implementation of the RMP: customs training programme | Individual | ASP | SRL | REF | 32 | TRA | 16 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-04-01 | 2003-01-01 |  | 2005-04-01 | 2010-12-01 | 87000 | 0 | 87000 | 87000 | 100% | 0 | 0 |  | 11310 | 0 | 11310 | 0 | 0
FIN | UNEP | Implementation of the RMP: train the trainers and training of refrigeration service technicians including | Individual | ASP | SRL | REF | 32 | TRA | 17 | A | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-04-01 | 2003-12-01 |  | 2004-09-01 | 2009-12-01 | 219000 | -72008 | 146992 | 146992 | 100% | 0 | 0 |  | 28470 | -9360.52 | 19109.48 | 0 | 0
FIN | UNDP | Preparation for HCFC phase-out investment activities (refrigeration and air-conditioning sector) | Individual | ASP | SRL | REF | 61 | PRP | 39 | N | I | HCFC | 0 | 0 | 0 | 0 | 2010-07-01 |  | 2011-07-01 |  | 2012-05-01 | 2013-12-01 | 60000 | -60000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 4500 | -4500 | 0 | 0 | 0 | Financially completed in 2013. | Completed in 2012. | 2010 |  | Investment
CLO | IBRD | Country programme preparation |  | ASP | SRL | SEV | 04 | PRP | 09 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1992-06-01 |  |  | 1992-06-01 | 23339 | -23339 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Country programme preparation | Individual | ASP | SRL | SEV | 06 | CPG | 01 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-04-01 | 1993-09-01 |  | 1994-03-01 | 1997-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Institutional strengthening | Individual | ASP | SRL | SEV | 12 | INS | 02 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-06-01 | 1997-03-01 |  | 1997-10-01 | 2003-09-01 | 154680 | 0 | 154680 | 154680 | 100% | 0 | 0 | 0 | 20108.4 | 0 | 20108.4 | 0 | 0 | Completed in 1997. Financially completed in 2003. |  | 1994 |  | Non-Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | SRL | SEV | 14 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-09-01 | 1994-10-01 | 1995-06-01 |  | 1996-06-01 | 1998-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNDP | Renewal of institutional strengthening | Individual | ASP | SRL | SEV | 23 | INS | 10 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1997-11-01 | 1997-11-01 | 1999-12-01 |  | 1999-12-01 | 2003-09-01 | 103120 | 0 | 103120 | 103120 | 100% | 0 | 0 | 0 | 13405.6 | 0 | 13405.6 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  | 1997 |  | Non-Investment
FIN | UNDP | Renewal of the institutional strengthening project for the phase-out of ODSs under the Montreal Protocol (Phase III) | Individual | ASP | SRL | SEV | 29 | INS | 14 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1999-11-01 | 1999-12-01 | 2001-12-01 |  | 2002-02-01 | 2003-09-01 | 103120 | 0 | 103120 | 103120 | 100% | 0 | 0 | 0 | 13406 | 0 | 13406 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1999 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening project (Phase 4) | Individual | ASP | SRL | SEV | 37 | INS | 20 | N | I | No_ODP | 11.1 | 11.1 | 0 | 0 | 2002-07-01 | 2003-02-01 | 2004-08-01 |  | 2004-08-01 | 2010-06-01 | 134056 | -2677.85 | 131378.15 | 131378 | 100% | 0.15 | 0 | 0 | 17427.28 | -348.11 | 17079.1456 | 0.0244 | 0 | Financially completed in 2010. |  | 2002 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase V) | Individual | ASP | SRL | SEV | 43 | INS | 22 | N | I | No_ODP | 11.1 | 11.1 | 0 | 0 | 2004-07-01 | 2005-02-01 | 2006-07-01 |  | 2006-12-01 | 2008-10-01 | 134056 | -14 | 134042 | 134042 | 100% | 0 | 0 | 0 | 10054 | -1.05 | 10052.95 | 0 | 0 | Completed in 2006. Financially Completed in 2008. |  | 2004 |  | Non-Investment
FIN | UNDP | Assistance to carry out an HCFC survey | Individual | ASP | SRL | SEV | 45 | TAS | 30 | A | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-04-01 | 2006-12-01 |  | 2008-08-01 | 2009-12-01 | 36697 | -5478 | 31219 | 31219 | 100% | 0 | 0 | 0 | 3303 | -493.06 | 2809.9397 | 0.0003 | 0 | Completed in 2008. Financially completed in 2009. |  | 2005 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VI) | Individual | ASP | SRL | SEV | 50 | INS | 31 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-03-01 | 2008-11-01 |  | 2008-11-01 | 2011-01-01 | 134056 | -1295.2 | 132760.8 | 132761 | 100% | -0.2 | 0 | 0 | 10054 | -97.14 | 9956.8769 | -0.0169 | 0 | Completed in 2008. |  | 2006 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VII) | Individual | ASP | SRL | SEV | 55 | INS | 32 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-05-01 | 2010-12-01 |  | 2010-12-01 | 2011-11-01 | 134056 | -14374.2 | 119681.8 | 119682 | 100% | -0.2 | 0 | 0 | 10054 | -1078.04 | 8975.9714 | -0.0114 | 0 | Completed in 2010. Financially completed in 2011. |  | 2008 |  | Non-investment
FIN | UNDP | Extension of the institutional strengthening project (phase VIII) | Individual | ASP | SRL | SEV | 61 | INS | 38 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-03-01 | 2012-12-01 |  | 2012-12-01 | 2013-07-01 | 134056 | -456.01 | 133599.99 | 133600 | 100% | -0.01 | 0 | 0 | 10054 | -34.2 | 10019.8007 | -0.00068031 | 0 | Financially completed in 2013. | Completed in 2012. Monitoring of HPMP implementing and regulations, including licensing systems ongoing in Q1 of 2013. | 2010 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase IX: 1/2013-12/2014) | Individual | ASP | SRL | SEV | 67 | INS | 42 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2012-07-01 | 2013-06-01 | 2014-12-01 |  | 2014-12-01 | 2015-12-01 | 134056 | -1099.69 | 132956.31 | 132956 | 100% | 0.31 | 0 | 0 | 9384 | -76.98 | 9306.9993 | 0.0207 | 0 | Financially completed in 2015. | In Q1-2014, payments under performance based payment mechanism for Regnis was released. Other activities are being monitored. | 2012 |  | Non-Investment
ONG | UNDP | Extension of the institutional strengthening project (phase X: 1/2015-12/2016) | Individual | ASP | SRL | SEV | 72 | INS | 46 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2014-05-01 | 2015-05-01 | 2016-12-01 | 2017-01-01 |  |  | 134056 | 0 | 134056 | 129408.13 | 96.53% | 4647.87 | 0 | 1859.148 | 9384 | 0 | 9058.6463 | 325.3537 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Quota for 2017 evaluated, coordination with custom Sri Lanka, ODS consumption data At and CP 2015 submitted, coordinating committtee meeting held, 3 workshop held on low GWP, 8 reclamation centre established, 2016 Ozone day celebrated, joined Network meeting at Fiji, participated in MoP and OEWG. In August 2016 the Cabinet of Ministers approved the proposal submitted and continued the legal process. Disseminated information on ozone and climate friendly alternative and energy efficient technologies for relevant industries specially located in Investment Promotion Zones (IPZ) in Katunayake and Biyagama. Conducted at least 6 awareness programmes to general public, government officers, teachers, students and members of industry associations. Prodoc signed (actual/planned, yes/no and date):41974 Missions undertaken (actual/planned):- TOR for consultants/subcontracts completed (actual/planned): completed earlier Contract/PO/MOA agreements signed: Contract signed First disbursement date (actual/planned): 42125Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | AWP 2017-2018 XI finalized. |  |  | Non-Investment
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | ASP | SRL | SEV | 74 | TAS | 47 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-10-01 | 2016-05-01 | 2017-06-01 |  |  | 35000 | 0 | 35000 | 8843.31 | 25.27% | 26156.69 | 26156.69 | 2615.669 | 4550 | 0 | 1149.6303 | 3400.3697 | 3400.3697 | Brief progress report(actual/planned): ToR developed and consultant recruited. Survey conducted. Stakeholder consultations meetings held, one during the mission by UNEP in Oct 2016. Full draft of the survey report submitted for review by UNEP. Legal arrangements(actual/planned): SSFA in place Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date(actual/planned): actual Oct 2016 All funds disbursed (yes/no): No Any delay?(yes/no): ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___ | Brief progress report(actual/planned): Comments on the first draft sent by UNEP Feb 2017. Comments are currently being incorporated into the final draft of the survey report. Legal arrangements(actual/planned): SSFA in place Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date(actual/planned): actual Oct 2016 All funds disbursed (yes/no): No Any delay?(yes/no): ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___
ONG | UNDP | Extension of the institutional strengthening project (phase XI: 1/2017-12/2018) | Individual | ASP | SRL | SEV | 76 | INS | 48 | N | I | HCFC | 0 | 0 | 0 | 0 | 2016-05-01 |  | 2018-12-01 | 2017-12-01 |  |  | 171592 | 0 | 171592 | 0 | 0% | 171592 | 0 | 68636.8 | 12011 | 0 | 0 | 12011 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): AWP approved. Prodoc signed (actual/planned, yes/no and date):42552 Missions undertaken (actual/planned): TOR for consultants/subcontracts completed (actual/planned): Contract/PO/MOA agreements signed: First disbursement date (actual/planned): 42552Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | AWP signed |  |  | Non-Investment
FIN | UNDP | Project preparation for one project in the solvent sector | Individual | ASP | SRL | SOL | 24 | PRP | 11 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1998 |  | Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan (stage I) | Individual | AFR | SSD | PHA | 70 | PRP | 02 | A | I |  | 0 |  | 0 |  | 2013-07-01 | 2014-08-01 | 2013-07-01 | 2017-07-01 |  |  | 30000 | 0 | 30000 | 10010.41 | 33.37% | 19989.59 | 0 | 1998.959 | 3900 | 0 | 1301.3533 | 2598.6467 | 0 | Brief progress report (actual/planned): The Terms of Reference (ToR) for hiring the international consultant was prepared, cleared by the management and advertised in October, 2015. The SSFA was drafted and signed by UNEP and the Government of South Sudan in July 2014. The first stakeholders workshop was organized by the NOU in March 2016 with the main goal to sensitize major stakeholders about HCFC phase out schedule, data survey and the Government’s strategy for phasing out of HCFCs. National consultants were hired by the NOU for data surveys which includes appropriate methodology, data collection, evaluation and reporting. Consultants collected information on the current status and consumption of HCFCs in servicing sector using HCFC- 22 including industrial and commercial refrigeration sectors and end-user air conditioning, as well as on the ongoing refrigerant recovery and recycling practices. The Government of South Sudan and consultants in close consultation with implementing agency drafted a preliminary strategy taking into consideration the results of the surveys, data analysis, consultation meetings as well as the policy and legislation review. The draft covers policy, training, investment and capacity building needs of the country. The final HPMP project document was submitted to ExCom-77 and approved. (actual/planned): The SSFA signed(Yes/No): No_ First mission (actual/planned): __NO_ TOR completed(actual/planned): YES__ First disbursement date (actual/planned): Yes, July 2014___ All funds disbursed (yes/no): _NO_ Any delay? (yes/no): _No_ If Yes, reasons for delay & action plan to resolve: __ If Yes, will delay have impact on project completion date (yes/no): _N/a __ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _NO__ | Project completed
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | SSD | PHA | 77 | TAS | 04 | A | I |  | 0 |  | 0 |  | 2016-12-01 |  | 2018-12-01 | 2018-12-01 |  |  | 20000 | 0 | 20000 | 0 | 0% | 20000 | 0 | 2000 | 2600 | 0 | 0 | 2600 | 0 | Newly approved project. | Brief progress report (actual/planned): The project was approved in Dec 2016. The licensing and quota system are in place and operational.The NOU continues to monitor imports and trade of ODS and ODS related equipment. Collection of the 2016 data on ODS imports and consumption has been completed and is being analyzed for submission. Plan of Action is developped for implementation of HPMP stage 1 tranche 1. Legal arrangements (actual/planned): The SSFA was drafted and sent to the Government of South Sudaan for signature. ___Initial stages of project implementation (actual/planned): __Yes_ Intermediate goals achieved (actual/planned): _No__ Project completion and follow up: _Yes__ First disbursement date (actual/planned): __No ____. All funds disbursed (yes/no): No__ Any delay? (yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: __N/A_
ONG | UNEP | Institutional strengthening project (start-up cost) | Individual | AFR | SSD | SEV | 68 | INS | 01 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-08-01 | 2013-12-01 | 2017-10-01 |  |  | 40000 | 0 | 40000 | 25029.84 | 62.57% | 14970.16 | 14970.16 | 1497.016 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The licensing and quota systems are in place and functioning. The NOU registered all importers of HCFCs and organized stakeholders meeting to allocate HCFC licenses and quotas. The NOU conducted awareness raising workshop to sensitize the public on ODS phase out. The NOU submitted 2015 Country Programme and Article 7 Data reports and celebrated 2016 International Ozone Day with several awareness activities. The NOU also participated in all Montreal Protocol meetings organized in 2016. The implementation of activities has delayed due to political instability in the country. Legal arrangements (actual/planned): The SSFA was signed between the country and UNEP in February 2013. Initial stages of project implementation(actual/planned):Yes__ Intermediate goals achieved (actual/planned): __Yes_ Project completion and follow up: _Yes__ First disbursement date (actual/planned):The first payment ($25,000 was sent in April 2013. All funds disbursed (yes/no): NO_ Any delay?(yes/no): _YES__ If Yes, reasons for delay & action plan to resolve: _Political unrest_ If Yes, will delay have impact on project completion date (yes/no): _YES__ Any ongoing problems (yes/no): __YES . If Yes, is any action required by ExCom: _NO__ | Brief progress report (actual/planned): The NOU continues to monitor imports and trade of ODS and ODS related equipment. Collection of the 2016 data on ODS imports and consumption has been completed and is being analyzed for submission. NOU commenced preparation of national legislative requirement processes in planning for ratification of Kigali amendment.
ONG | UNEP | Institutional strengthening project (phase I: 5/2016-4/2018) | Individual | AFR | SSD | SEV | 76 | INS | 03 | A | I |  | 0 |  | 0 |  | 2016-05-01 |  | 2018-04-01 | 2018-04-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Newly approved. The licensing and quota systems are in place and operational. The NOU registered all importers of HCFC for 2016, advertised for quota allocation for 2016 HCFC importation and conducted two inspection visits to various boarders to check how customs officers are enforcing the control measures of HCFC importation. The NOU trained 30 custom officers and 40 RAC technicians. The NOU submitted 2015 Country Programme and Article 7 Data reports. The NOU celebrated 2016 International Ozone Day and conducted several awareness activities, printed 300 T shirts and organized Radio Talk-shows. The NOU also participated in all Montreal Protocol meetings organized in 2016.___ Legal arrangements(actual/planned): The SSFA was drafted and signed by UNEP and the Government of South Sudan in November 2016__Initial stages of project implementation(actual/planned): _Yes__ Intermediate goals achieved (actual/planned): _Yes__ Project completion and follow up: No___ First disbursement date (actual/planned): _December 2016__ All funds disbursed (yes/no): _Yes__ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: __N/A_ If Yes, will delay have impact on project completion date (yes/no): _Yes__ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): The NOU continues to monitor imports and trade of ODS and ODS related equipment. Collection of the 2016 data on ODS imports and consumption has been completed and is being analyzed for submission. NOU commenced preparation of national legislative requirement processes in planning for ratification of Kigali amendment.
FIN | UNEP | Technical assistance to phase out the use of methyl bromide | Individual | LAC | STK | FUM | 50 | TAS | 11 | A | I | MB | 0.8 | 0.8 | 0 | 0 | 2006-11-01 | 2009-05-01 | 2007-11-01 |  | 2009-12-01 | 2010-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 |  |  |  | 2008-12-01
FIN | UNDP | Terminal CFC phase-out management plan (first tranche) | Multi-Year | LAC | STK | PHA | 48 | TAS | 09 | N | I | CFC | 0 | 0 | 0 | 0 | 2006-04-01 | 2009-11-01 | 2009-12-01 |  | 2009-12-01 | 2013-03-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 4500 | 0 | 4500 | 0 | 0 | Financially completed in 2013. |  | 2006 |  | Investment
FIN | UNEP | Terminal CFC phase-out management plan (first tranche) | Multi-Year | LAC | STK | PHA | 48 | TAS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-06-01 | 2009-12-01 |  | 2010-06-01 | 2011-06-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNDP | Terminal CFC phase-out management plan (second and third tranches) | Multi-Year | LAC | STK | PHA | 56 | INV | 13 | N | I | CFC | 0 | 0 | 0 | 0 | 2008-11-01 |  | 2009-11-01 |  | 2014-01-01 | 2014-09-01 | 55000 | -55000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 4950 | -4950 | 0 | 0 | 0 | Financially completed in 2015. | NOU team is monitoring the supplier. Equipment is expected to be delivered by April/May 2014 (when financial obligation can be paid). | 2008 |  | Investment
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | STK | PHA | 56 | PRP | 14 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2010-12-01 | 2009-11-01 |  | 2013-12-01 | 2013-12-01 | 85000 | -17932 | 67068 | 67068 | 100% | 0 | 0 |  | 11050 | -2331.16 | 8718.84 | 0 | 0
FIN | UNEP | Terminal CFC phase-out management plan (second and third tranches) | Multi-Year | LAC | STK | PHA | 56 | TAS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-12-01 | 2009-11-01 |  | 2013-07-01 | 2013-07-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 |  | 11700 | 0 | 11700 | 0 | 0
ONG | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | STK | PHA | 64 | TAS | 16 | N | I | HCFC | 0.1 | 0 | 0 | 0 | 2011-07-01 |  | 2013-07-01 | 2017-01-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 0 | 16000 | 3600 | 0 | 0 | 3600 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): PRODOC signed in december 2016. Planning for procurement activities was started. Prodoc signed (actual/planned, yes/no and date):Yes, December 2016 Missions undertaken (actual/planned):0 of 0 TOR for consultants/subcontracts completed (actual/planned): 0 of 0 Contract/PO/MOA agreements signed: 0 of 0 First disbursement date (actual/planned): Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | The purchase of equipment is projected for 2017. | 2011 |  | Non-Investment |  | To request the submission of additional status report to the 79th meeting to monitor the signing of the agreement by the Government.
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | STK | PHA | 64 | TAS | 17 | A | I |  | 0.1 | 0 | 0 | 0 | 2011-07-01 | 2013-07-01 | 2015-07-01 |  | 2015-06-01 | 2015-12-01 | 58400 | 0 | 58400 | 58400 | 100% | 0 | 0 |  | 7592 | 0 | 7592 | 0 | 0 | Project financially completed | Project financially completed
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | STK | PHA | 74 | TAS | 20 | A | I |  | 0.1 |  | 0 |  | 2015-05-01 |  | 2020-05-01 | 2020-05-01 |  |  | 49200 | 0 | 49200 | 0 | 0% | 49200 | 49200 | 4920 | 6396 | 0 | 0 | 6396 | 6396 | Brief progress report (actual/planned): Mission held Sept-16. Workplan developed and priority areas identified. Meetings held with Customs Department and Permanent Secretary. Customs agreed to continue to cooperate with NOU and provide ASYCUDA access and training in addition to redflagging ODS and other products. NOU also met with legal team to identify plans under the legislative review and training with judiciary. During Mission, a meeting with held with the Ministry of Tourism to discuss ODS and their alternatives used on yachts and in the Tourism sector. Country to submit final HPMP Workplan.__ Legal arrangements(actual/planned): SSFA signed Oct-16. ___ First mission (actual/planned): Mission planned for last half of 2017.___ TOR completed(actual/planned): ___ First disbursement date (actual/planned): To be processed upon receipt of final HPMP Workplan.___ All funds disbursed (yes/no): No. ___ Any delay? (yes/no): ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): No.___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): Country to submit final HPMP Workplan. __ Legal arrangements(actual/planned): SSFA signed Oct-16. ___ First mission (actual/planned): Mission planned for last half of 2017.___ TOR completed(actual/planned): ___ First disbursement date (actual/planned): To be processed upon receipt of final HPMP Workplan.___ All funds disbursed (yes/no): No. ___ Any delay? (yes/no): ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): No.___ If Yes, is any action required by ExCom: ___
FIN | UNEP | Assistance for formulation refrigeration management plan | RMP | LAC | STK | REF | 21 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-09-01 | 1998-03-01 |  | 1998-03-01 | 1999-04-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | Canada | Implementation of the RMP including training programmes for refrigeration technicians and customs officers, assistance in the design of policies and regulations and recovery and recycling | RMP | LAC | STK | REF | 24 | TAS | 04 | A | I | CFC | 2 | 2 | 0 |  | 1998-03-01 | 1999-05-01 | 2001-03-01 |  | 2006-03-01 | 2006-03-01 | 124300 | 0 | 124300 | 124300 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | R&R workshop and customs training were delayed because legislation not yet place. However legislation was adopted in early 2004 and R&R project was completed. Phase I Customs Training also implemented. Final reports by country received in February 2006, |  | 1998 |  | Non-Inv.
FIN | UNEP | Preparation of a refrigerant management plan | RMP | LAC | STK | REF | 44 | PRP | 07 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-07-01 | 2005-12-01 |  | 2006-03-01 | 2008-12-01 | 15000 | -3460 | 11540 | 11540 | 100% | 0 | 0 |  | 1950 | -450 | 1500 | 0 | 0
FIN | UNEP | Country programme preparation | Individual | LAC | STK | SEV | 12 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-06-01 | 1995-06-01 |  | 1996-12-01 | 1999-12-01 | 35000 | -12500 | 22500 | 22500 | 100% | 0 | 0 |  | 4550 | -1625 | 2925 | 0 | 0
FIN | UNEP | Institutional strengthening | Individual | LAC | STK | SEV | 21 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 2000-02-01 |  | 2006-09-01 | 2007-09-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase II) | Individual | LAC | STK | SEV | 42 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2006-08-01 | 2005-04-01 |  | 2007-08-01 | 2008-12-01 | 13000 | 0 | 13000 | 13000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | LAC | STK | SEV | 47 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2008-02-01 | 2008-12-01 |  | 2009-12-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | LAC | STK | SEV | 59 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2009-12-01 | 2011-11-01 |  | 2013-07-01 | 2013-07-01 | 32500 | 27500 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of institutional strengthening project (phase V: 1/2013-12/2014) | Individual | LAC | STK | SEV | 68 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-05-01 | 2014-12-01 |  | 2015-05-01 |  | 60000 | 0 | 60000 | 24000 | 40% | 36000 | 36000 | 36000 | 0 | 0 | 0 | 0 | 0 | Project completed. The final payment is being processed in UMOJA and it requires additional time. The final expenditure report is received and needs some time to be processed in UMOJA. ALL funds are committed. | Project completed. The final payment is being processed in UMOJA and it requires additional time. The final expenditure report is received and needs some time to be processed in UMOJA. ALL funds are committed.
ONG | UNEP | Extension of institutional strengthening project (phase VI: 1/2015-12/2016) | Individual | LAC | STK | SEV | 73 | INS | 19 | A | I |  | 0 |  | 0 |  | 2014-11-01 |  | 2016-12-01 | 2018-12-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 60000 | 6000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): ISP workplan and priority areas identified. Mission held Sept-16 during reach important meetings with Customs and the Permanent Secretary was held. A meeting was also held with the Trainer for technicians, and the Ministry of Fisheries to discuss the issue of Flag Ships operating on the high seas. NOU attended Barbados Thematic Meeting in Dec-16.___ Legal arrangements(actual/planned): SSFA signed 3 Oct-16___Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): To be processed upon receipt of final financial report from phase V. ___ All funds disbursed (yes/no): No. ___ Any delay?(yes/no): No.___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): No.___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned):NOU working on data collection and verification for CP2016 data. Country reminded to submit final financial report for Phase V.___ Legal arrangements(actual/planned): SSFA signed 3 Oct-16___Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): To be processed upon receipt of final financial report from phase V. ___ All funds disbursed (yes/no): No. ___ Any delay?(yes/no): No.___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): No.___ If Yes, is any action required by ExCom: ___
FIN | Canada | Project preparation for a TPMP |  | LAC | STL | PHA | 48 | PRP | 10 | A | I |  | 0 |  | 0 |  | 2006-04-01 | 2006-09-01 | 2007-04-01 |  | 2007-04-01 | 2008-07-01 | 30000 | -7000 | 23000 | 23000 | 100% | 0 |  | 0 | 3900 | -910 | 2990 | 0 |  | TPMP proposal completed and submitted in April 2007 for ExCom 52. Not all funds were used. Remaining funds returned to Fund. |  | 2006 |  | Non-Inv.
FIN | Canada | Terminal phase-out management plan for the phase-out of ODS in the refrigeration and air conditioning sector (first tranche) | Multi-Year | LAC | STL | PHA | 52 | INV | 12 | A | I | CFC | 0 |  | 0 |  | 2007-07-01 | 2007-09-01 | 2009-07-01 |  | 2010-03-01 | 2011-07-01 | 156000 | -504 | 155496 | 155496 | 100% | 0 |  | 0 | 20280 | -10617 | 9663 | 0 |  | R&R equipment and tools delivered in March 2008 and distributed. Technicians and customs officers training were undertaken through 2008. Legal framework for R&AC Association and revised MP regulations was completed. A code of good practices in Refrigeration has been finalised. In 2009, additional training for technicians and customs officers took place. Project was completed in March 2010 with $504 unspent was returned to the Fund, along with $10,617 in unspent support costs, as noted at ExCom 64 in July 2011. |  | 2007 |  | Investment
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | STL | PHA | 55 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2010-02-01 | 2009-07-01 |  | 2012-12-01 | 2012-12-01 | 85000 | -2532 | 82468 | 82468 | 100% | 0 | 0 |  | 11050 | -329.16 | 10720.84 | 0 | 0
FIN | Canada | Terminal phase-out management plan for the phase-out of ODS in the refrigeration and air conditioning sector (second tranche) | Multi-Year | LAC | STL | PHA | 56 | INV | 15 | A | I | CFC | 1.2 | 1.2 | 0 |  | 2008-11-01 | 2009-12-01 | 2009-11-01 |  | 2012-03-01 | 2013-08-01 | 49000 | -1039 | 47961 | 47961 | 100% | 0 |  | 0 | 6370 | -135 | 6235 | 0 |  | Project completed in March 2012. 109 technicians and 85 customs officers trained, equipment purchased and distributed to workshops, and clearing house established for unwanted ODS. A balance of $1,039.16 in project costs and $135 in support cost were remaining and returned to the Fund at 70th meeting, which was when project was considered financially closed. |  | 2008 |  | Investment
FIN | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | STL | PHA | 64 | INV | 17 | A | I |  | 0 | 0 |  |  | 2011-07-01 | 2012-04-01 | 2012-07-31 |  | 2014-07-01 | 2014-07-01 | 88850 | -2 | 88848 | 88847.69 | 100% | 0.31 | 0 |  | 7997 | 0 | 7996 | 1 | 0 | FIN |  |  |  | INV
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | STL | PHA | 64 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-06-01 | 2012-07-01 |  | 2013-08-01 | 2013-08-01 | 13000 | 0 | 13000 | 13000 | 100% | 0 | 0 |  | 1690 | 0 | 1690 | 0 | 0
COM | UNIDO | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | STL | PHA | 68 | INV | 21 | A | I | HCFC | 0.1 | 0.1 |  |  | 2012-12-01 | 2013-06-01 | 2015-12-31 |  | 2016-12-01 |  | 11000 | 0 | 11000 | 6500 | 59.09% | 4500 | 4500 | 4500 | 990 | 0 | 585 | 405 | 405 | - National expert was hired for the training of trainers and to support the implementation of activities. - Training of trainers program was implemented in 2016: 30 trainers were trained in total. - Activities have been completed. Was there any delay during the reporting year? Yes, because of the reasons explained under remarks 2015. - Delay in implementation compared to the original activities timeline. Due to limited amount of the available budget, the training program could not be organized with the training institute identified in the first place. - No recurring problem - No impact on project completion date - No action required by Executive Committee | Project activities completed. |  |  | INV
COM | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | STL | PHA | 68 | TAS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2014-06-01 | 2015-12-01 |  | 2016-12-01 |  | 13150 | 0 | 13150 | 13150 | 100% | 0 | 0 |  | 1710 | 0 | 1710 | 0 | 0 | Brief progress report (actual/planned): The NOU initiated the development of the tranche 3 in cooperation with UNEP and UNIDO. The stakeholders discussions took place and the tranche was submitted and approved in ExCom-76. Final progress and financial reports of tranche 2 were prepared in Jul-16. Last disbursement has been processed in Aug-16. ___ Legal arrangements (actual/planned): Jun-14/Jun-13 ___ First mission (actual/planned): ___ TOR completed (actual/planned): ___ First disbursement date (actual/planned): Jun-14/Jun-13 ___ All funds disbursed (yes/no): yes ___ Any delay? (yes/no): no___ If Yes, reasons for delay & action plan to resolve:___ If Yes, will delay have impact on project completion date (yes/no): no ___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___ | Project completed
COM | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Individual | LAC | STL | PHA | 71 | TAS | 22 | A | I |  | 0 |  | 0 |  | 2013-12-01 | 2016-04-01 | 2015-05-01 |  | 2016-12-01 |  | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | Brief progress report (actual/planned): Verification report submitted together with 3rd tranche request and approved at ExCom 76. ___ Legal arrangements (actual/planned): ___ First mission (actual/planned): Apr-16/Apr-15___ TOR completed (actual/planned): Jan-16/Jul-15___ First disbursement date (actual/planned): Apr-16/Jul-15___ All funds disbursed (yes/no): yes ___ Any delay? (yes/no): no___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom:___ | Project completed
ONG | UNIDO | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | LAC | STL | PHA | 76 | INV | 26 | A | I | HCFC | 0.1 | 0 |  |  | 2016-05-01 | 2016-12-01 | 2020-05-31 | 2020-05-31 |  |  | 27500 | 0 | 27500 | 937.3 | 3.408% | 26562.7 | 7940 | 8000 | 2475 | 0 | 84 | 2391 | 715 | - The tranche was approved by the 76th Meeting of the ExCom in May 2016. - Activities under the second and third tranches have been combined. - Training was organized. - Two refrigerant identifiers were purchased. - Manuals for refrigeration technicians were reviewed and bound. - No delay in implementation - No recurring problem - No impact on project completion date - No action required by Executive Committee | - National expert reported on the success training activities in 2016. Action towards next goals: Project to be implemented as planned. - No delay in implementation - No recurring problem - No impact on project completion date - No action required by Executive Committee |  |  | INV
ONG | UNEP | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | LAC | STL | PHA | 76 | TAS | 25 | A | I |  | 0 |  | 0 |  | 2016-05-01 |  | 2018-05-01 | 2018-05-01 |  |  | 26300 | 0 | 26300 | 0 | 0% | 26300 | 26300 | 2630 | 3419 | 0 | 0 | 3419 | 3419 | Brief progress report (actual/planned): The NOU initiated the development of the tranche 3 in cooperation with UN Environment and UNIDO. The stakeholders discussions took place and the tranche was submitted together with the Verification Report. Tranche 3 approved in ExCom-76, May-16. SSFA text discussions started in Aug-16. SSFA signed in Oct-16. Workplan submitted by NOU in Dec-16 and first disbursement processed ___ Legal arrangements (actual/planned): Oct-16/Oct-16 ___ First mission (actual/planned): ___ TOR completed (actual/planned): ___ First disbursement date (actual/planned): ----/Oct-16 ___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): no___ If Yes, reasons for delay & action plan to resolve:___ If Yes, will delay have impact on project completion date (yes/no): no ___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): reprogramming of funds into 2017 completed in Feb-17. Activities will start once wire transfer is confirmed in recipients bank account. ___ Legal arrangements (actual/planned): Oct-16/Oct-16 ___ First mission (actual/planned): ___ TOR completed (actual/planned): ___ First disbursement date (actual/planned): ----/Oct-16 ___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): no___ If Yes, reasons for delay & action plan to resolve:___ If Yes, will delay have impact on project completion date (yes/no): no ___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___
FIN | UNEP | Development of a refrigeration management plan | RMP | LAC | STL | REF | 21 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1998-03-01 |  | 1997-10-01 | 1999-03-01 | 15000 | -1000 | 14000 | 14000 | 100% | 0 | 0 |  | 1950 | -130 | 1820 | 0 | 0
FIN | Canada | Implementation of the RMP | RMP | LAC | STL | REF | 23 | TAS | 04 | A | I | CFC | 3 | 3 | 0 |  | 1997-11-01 | 1998-03-01 | 2000-12-01 |  | 2003-12-01 | 2003-12-01 | 146900 | 0 | 146900 | 146900 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | All activities completed. Project Completion Report is currently being drafted. |  | 1997 |  | Non-Inv.
FIN | Canada | Preparation of update of refrigerant management plan | Individual | LAC | STL | REF | 35 | PRP | 06 | A | I |  | 0 |  | 0 |  | 2001-12-01 | 2002-06-01 | 2002-07-01 |  | 2003-11-01 | 2003-12-01 | 7500 | 0 | 7500 | 7500 | 100% | 0 |  | 0 | 975 | 0 | 975 | 0 |  | RMP Update was completed and project was submitted in Nov. 2003. |  | 2000 |  | Non-Inv.
FIN | Canada | Implementation of the RMP update | RMP Update | LAC | STL | REF | 41 | TAS | 08 | A | I |  | 7.1 | 7.1 | 0 |  | 2003-12-01 | 2004-05-01 | 2006-12-01 |  | 2007-05-01 | 2008-12-01 | 73450 | -122 | 73328 | 73328 | 100% | 0 |  | 0 | 9549 | -16 | 9533 | 0 |  | Project completed. 71 refrigeration technicians trained. Public service announcements were developed and broadcasted. Retrofit demonstration workshops concluded, including demonstrations of AC and vehicle retrofits. R&R equipment distributed. Though financial completion was previously reported to be May 2007, it was subsequently found that $122 were remaining. This amount, plus $16 in support costs, is to be returned to the Fund at the 58th ExCom Meeting. |  | 2003 |  | Non-Inv.
FIN | UNEP | Country programme preparation | Individual | LAC | STL | SEV | 13 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-09-01 | 1995-10-01 |  | 1995-07-01 | 1995-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Establishment of an Ozone Cell | Individual | LAC | STL | SEV | 21 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 2000-02-01 |  | 2000-08-01 | 2001-08-01 | 36580 | 0 | 36580 | 36580 | 100% | 0 | 0 |  | 4755 | 0 | 4755 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening | Individual | LAC | STL | SEV | 30 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-01-01 | 2002-04-01 |  | 2002-06-01 | 2003-07-01 | 24400 | 0 | 24400 | 24400 | 100% | 0 | 0 |  | 3172 | 0 | 3172 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (Phase 3) | Individual | LAC | STL | SEV | 37 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2002-12-01 | 2004-08-01 |  | 2004-06-01 | 2005-12-01 | 31200 | 0 | 31200 | 31200 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (phase IV) | Individual | LAC | STL | SEV | 43 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2004-07-01 | 2005-10-01 | 2006-07-01 |  | 2007-04-01 | 2009-09-01 | 31200 | -400 | 30800 | 30800 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase V) | Individual | LAC | STL | SEV | 49 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2006-12-01 | 2008-07-01 |  | 2009-07-01 | 2010-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase VI) | Individual | LAC | STL | SEV | 55 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-09-01 | 2010-07-01 |  | 2010-07-01 | 2011-07-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase VII) | Individual | LAC | STL | SEV | 62 | INS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-05-01 | 2012-11-01 |  | 2012-12-01 | 2013-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase VIII: 1/2013-12/2014) | Individual | LAC | STL | SEV | 68 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-05-01 | 2015-01-01 |  | 2014-12-01 | 2014-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Renewal of institutional strengthening project (phase IX: 1/2015-12/2016) | Individual | LAC | STL | SEV | 73 | INS | 23 | A | I |  | 0 |  | 0 |  | 2014-11-01 | 2016-04-01 | 2016-12-01 | 2017-12-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 60000 | 6000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): SSFA signed in Dec-2015. Programming of funds into 2016 completed in Feb-16. First disbursement subject to previous phase final financial report. Final report sent on Apr-16 and first disbursement processed. Licensing and quotas have been implemented. 2015 CP Data and Art.7 Data reported on time. Management of HPMP implementation, tranche request and ODS Alternatives Survey. Celebration of Ozone day activities and other realated awareness raising activities during 2016. NOU participated in the Joint Network Meeting in Chile, May-16 and in the Caribbean Thematic Meeting on ODS Alternatives Surveys in Barbados, Dec-16. ___Legal arrangements (actual/planned): Dec-15/Jul-15___ Initial stages of project implementation (actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): Apr-16/ Dec-15.___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): yes___ If Yes, reasons for delay & action plan to resolve: New NOO appointed in late 2015. Discussion of SSFA delayed its signature. UN Environment provided support and guidance to NOO periodically in order to build her capacities ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): no. ___ If Yes, is any action required by ExCom: . | Brief progress report (actual/planned): Country collecting information to report 2016 CP Data and Art.7 Data on time. Management of HPMP implementation third tranche. ___Legal arrangements (actual/planned): Dec-15/Jul-15___ Initial stages of project implementation (actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): Apr-16/ Dec-15.___ All funds disbursed (yes/no): no ___ Any delay? (yes/no): yes___ If Yes, reasons for delay & action plan to resolve: New NOO appointed in late 2015. Discussion of SSFA delayed its signature. UN Environment providing support and guidance to NOO periodically in order to build her capacities ___ If Yes, will delay have impact on project completion date (yes/no): yes. Completion date has been revised to reflect timeframe of SSFA signed and completion of activities. ___ Any ongoing problems (yes/no): no. ___ If Yes, is any action required by ExCom: . |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor project implementation progress and the disbursement rate of approved funds.
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | LAC | STL | SEV | 75 | TAS | 24 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-10-01 | 2016-12-01 | 2017-06-01 |  |  | 40000 | 0 | 40000 | 680 | 1.7% | 39320 | 37650 | 3932 | 5200 | 0 | 88.4 | 5111.6 | 4894.5 | Brief progress report (actual/planned): SSFA signed in Aug-16. Regional Consultant selected and contract signed in June-16. National consultant hired in Oct-16. Stakeholders meeting held in Nov-16. Collection of information completed in Nov-16. Report sent in Dec-16 ___. Legal arrangements (actual/planned): Aug-16/Jul-16 ___ First mission (actual/planned): Jul-16/Mar-16 ___ TOR completed (actual/planned): May-16/Feb-2016___ First disbursement date (actual/planned): Oct-16/Jul-16 ___ All funds disbursed (yes/no): No___ Any delay? (yes/no): no___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no):___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): Report review ongoing. Completion date revised to June-17 to reflect submission of the report to the second ExCom in 2017 ___. Legal arrangements (actual/planned): Aug-16/Jul-16 ___ First mission (actual/planned): Jul-16/Mar-16 ___ TOR completed (actual/planned): May-16/Feb-2016___ First disbursement date (actual/planned): Oct-16/Jul-16 ___ All funds disbursed (yes/no): No___ Any delay? (yes/no): no___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no):___ Any ongoing problems (yes/no): no___ If Yes, is any action required by ExCom: ___
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | STP | PHA | 50 | PRP | 12 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-07-01 | 2007-11-01 |  | 2008-06-01 | 2009-12-01 | 30000 | -8 | 29992 | 29992 | 100% | 0 | 0 |  | 3900 | -1.04 | 3898.96 | 0 | 0
FIN | UNIDO | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | STP | PHA | 54 | INV | 14 | A | I |  | 0 | 0 |  |  | 2008-04-01 | 2008-08-01 | 2010-03-31 |  | 2009-12-01 | 2011-05-01 | 66000 | -242 | 65758 | 65758.46 | 100% | -0.46 | 0 |  | 5940 | -22 | 5918 | 0 | 0 | FIN |  |  |  | INV
FIN | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | STP | PHA | 54 | TAS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-07-01 | 2010-03-01 |  | 2010-07-01 | 2011-07-01 | 54000 | 0 | 54000 | 54000 | 100% | 0 | 0 |  | 7020 | 0 | 7020 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | STP | PHA | 55 | PRP | 15 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-09-01 | 2009-07-01 |  | 2011-03-01 | 2012-03-01 | 85000 | -15000 | 70000 | 70000 | 100% | 0 | 0 |  | 11050 | -1950 | 9100 | 0 | 0
FIN | UNIDO | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | STP | PHA | 57 | INV | 17 | A | I | CFC | 0.7 | 0.7 |  |  | 2009-04-01 | 2009-08-01 | 2010-03-31 |  | 2011-12-01 | 2011-12-01 | 49000 | -479 | 48521 | 48520.81 | 100% | 0.19 | 0 |  | 4410 | -43 | 4367 | 0 | 0 | FIN |  |  |  | INV
FIN | UNEP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | STP | PHA | 57 | TAS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-08-01 | 2010-03-01 |  | 2010-12-01 | 2011-06-01 | 21000 | 0 | 21000 | 21000 | 100% | 0 | 0 |  | 2730 | 0 | 2730 | 0 | 0
FIN | UNEP | TPMP verification | Individual | AFR | STP | PHA | 57 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-08-01 | 2010-03-01 |  | 2010-12-01 | 2011-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | STP | PHA | 63 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2012-04-01 | 2013-03-01 |  | 2013-03-01 | 2014-03-01 | 44000 | -4988 | 39012 | 39012 | 100% | 0 | 0 |  | 5720 | -648.44 | 5071.56 | 0 | 0
COM | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | AFR | STP | PHA | 70 | TAS | 21 | A | I |  | 0 |  | 0 |  | 2013-07-01 | 2014-06-01 | 2016-07-01 |  | 2016-12-01 |  | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 |  | 4550 | 0 | 4550 | 0 | 0 | Brief progress report (actual/planned): Country signed SSFA in June 2014. 32 RAC technicians and 20 custom officers trained in 2016. Legal arrangements (actual/planned): Agreement signed in June 2014. All activities under the SSFA are completed (as planned) -yes___ First mission (actual/planned): _ N/A - Project Completed __yes__ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in June 2014__ All funds disbursed (yes/no): YES_ Final payment sent in September 2016. Any delay? (yes/no): Yes ___ If Yes, reasons for delay & action plan to resolve: Due to Umoja implementation, payments delayed ___ If Yes, will delay have impact on project completion date (yes/no): _ No __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Brief progress report (actual/planned): Country signed SSFA in June 2014. 32 RAC technicians and 20 custom officers trained in 2016. Legal arrangements (actual/planned): Agreement signed in June 2014. All activities under the SSFA are completed (as planned) -yes___ First mission (actual/planned): _ N/A - Project Completed __yes__ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in June 2014__ All funds disbursed (yes/no): YES_ Final payment sent in September 2016. Any delay? (yes/no): Yes ___ If Yes, reasons for delay & action plan to resolve: Due to Umoja implementation, payments delayed, but NOU implemented the planned activities ___ If Yes, will delay have impact on project completion date (yes/no): _ No __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
COM | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Individual | AFR | STP | PHA | 71 | TAS | 22 | A | I |  | 0 |  | 0 |  | 2013-12-01 | 2016-01-01 | 2016-05-01 |  | 2016-12-01 |  | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | Project completed | Project completed
ONG | UNEP | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | AFR | STP | PHA | 76 | TAS | 26 | A | I |  | 0 |  | 0 |  | 2016-05-01 | 2016-12-01 | 2018-12-01 | 2018-12-01 |  |  | 35000 | 0 | 35000 | 14550.89 | 41.57% | 20449.11 | 0 | 2044.911 | 4550 | 0 | 1891.6157 | 2658.3843 | 0 | Newly approved project | Brief progress report (actual/planned): Project newly approved. Agreement signed in Dec. 2016. Legal arrangements (actual/planned): Agreement signed in Dec. 2016. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st payment not sent yet__ All funds disbursed (yes/no): _ Final payment _no___ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
FIN | UNDP | Formulation of the investment components of the RMP | Individual | AFR | STP | REF | 39 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-05-01 | 2004-04-01 |  | 2005-06-01 | 2006-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1125 | 0 | 1125 | 0 | 0 | Completed in 2005. Financially completed in 2006. |  | 2003 |  | Investment
FIN | UNEP | Implementation of the RMP: assistance for development of a licensing system | Individual | AFR | STP | REF | 44 | TAS | 06 | A | I | CFC | 0.3 | 0 | 0 | 0 | 2004-12-01 | 2005-12-01 | 2005-06-01 |  | 2006-12-01 | 2009-01-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0
FIN | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | AFR | STP | REF | 44 | TAS | 09 | A | I | CFC | 0.3 | 0 | 0 | 0 | 2004-12-01 | 2006-12-01 | 2007-12-01 |  | 2007-12-01 | 2010-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0
FIN | UNDP | Implementation of the RMP: technical assistance for the refrigeration servicing sector | RMP-Component | AFR | STP | REF | 44 | TAS | 10 | N | I | CFC | 1.8 | 1.8 | 0 | 0 | 2004-12-01 | 2007-04-01 | 2006-12-01 |  | 2008-12-01 | 2011-12-01 | 110000 | -2.63 | 109997.37 | 109997 | 100% | 0.37 | 0 | 0 | 9900 | -0.24 | 9899.73 | 0.03 | 0 | Completed in 2008. |  | 2004 |  | Investment
FIN | UNEP | Implementation of the RMP: training programme for custom officers | Individual | AFR | STP | REF | 44 | TRA | 07 | A | I | CFC | 0.7 | 0 | 0 | 0 | 2004-12-01 | 2005-07-01 | 2005-12-01 |  | 2007-12-01 | 2010-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 |  | 5850 | 0 | 5850 | 0 | 0
FIN | UNEP | Implementation of the RMP: training programme for refrigeration service technicians | Individual | AFR | STP | REF | 44 | TRA | 08 | A | I | CFC | 0.9 | 0 | 0 | 0 | 2004-12-01 | 2005-08-01 | 2006-12-01 |  | 2008-12-01 | 2012-05-01 | 55000 | -11534 | 43466 | 43466 | 100% | 0 | 0 |  | 7150 | -1499.42 | 5650.58 | 0 | 0
FIN | UNEP | Preparation of country programme and refrigerant management plan | Individual | AFR | STP | SEV | 36 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2003-04-01 |  | 2004-12-01 | 2007-12-01 | 30000 | -3538 | 26462 | 26462 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Establishment of the Ozone Unit | Individual | AFR | STP | SEV | 38 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-02-01 | 2003-12-01 |  | 2005-12-01 | 2007-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Establishment of the Ozone Unit (institutional strengthening) | Individual | AFR | STP | SEV | 44 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2006-10-01 | 2006-12-01 |  | 2006-06-01 | 2008-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase II) | Individual | AFR | STP | SEV | 50 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-01-01 | 2008-12-01 |  | 2011-02-01 | 2012-06-01 | 60666 | 0 | 60666 | 60666 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of the institutional strengthening project (phase III) | Individual | AFR | STP | SEV | 63 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2012-04-01 | 2013-03-01 |  | 2013-03-01 |  | 60666 | 0 | 60666 | 33332 | 54.94% | 27334 | 26893.12 | 27334 | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of the institutional strengthening project (phase IV: 1/2014-12/2015) | Individual | AFR | STP | SEV | 71 | INS | 23 | A | I |  | 0 |  | 0 |  | 2013-12-01 | 2015-10-01 | 2015-12-01 | 2017-12-01 |  |  | 60666 | 0 | 60666 | 0 | 0% | 60666 | 60666 | 6066.6 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Country signed the SSFA in August 2015. 2015 CP data and 2015 Art7 data reported. Ozone day celebrated. Legal arrangements (actual/planned): Agreement signed in August 2015.First payment: October 2015. All activities under the SSFA are completed (as planned) No__ First mission (actual/planned): _ N/A -TOR completed (actual/planned): _ Yes __ First disbursement date (actual/planned): _1st disbursement done in October 2015__ All funds disbursed (yes/no): _ No__ Any delay? (yes/no): No___ If Yes, reasons for delay & action plan to resolve: n/a___ If Yes, will delay have impact on project completion date (yes/no): _ No __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Brief progress report (actual/planned): Legal arrangements (actual/planned): Agreement signed in August 2015. First payment: October 2015. Country signed the SSFA in August 2015. 2015 CP data and 2015 Art7 data reported. Ozone day celebrated. NOU trained 20 RAC technicians and 15 enforcement officers. All activities under the SSFA are completed (as planned) No__ First mission (actual/planned): _ N/A -TOR completed (actual/planned): _ Yes __ First disbursement date (actual/planned): _1st disbursement done in October 2015__ All funds disbursed (yes/no): _ No__ Any delay? (yes/no): No___ If Yes, reasons for delay & action plan to resolve: n/a___ If Yes, will delay have impact on project completion date (yes/no): _ No __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | AFR | STP | SEV | 74 | TAS | 24 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-04-01 | 2016-05-01 | 2017-10-01 |  |  | 40000 | 0 | 40000 | 27.58 | 0.06895% | 39972.42 | 30000 | 3997.242 | 5200 | 0 | 3.5854 | 5196.4146 | 3900 | Brief progress report (actual/planned):Country signed the SSFA in November 2015 . First payment sent in April 2016. Local consultants hired in June 2016 and survey activities started in June 2016. Legal arrangements (actual/planned): Agreement signed in November 2015. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in April 2016 __ All funds disbursed (yes/no): _ n/a.__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Brief progress report (actual/planned): Country signed the SSFA in November 2015 . First payment sent in April 2016. Local consultants hired in June 2016 and survey activities started in June 2016. Advanced draft of Survey report sent in April 2017. Legal arrangements (actual/planned): Agreement signed in November 2015. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in April 2016 __ All funds disbursed (yes/no): _ n/a.__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
ONG | UNEP | Extension of the institutional strengthening project (phase V: 7/2016-6/2018) | Individual | AFR | STP | SEV | 76 | INS | 25 | A | I |  | 0 |  | 0 |  | 2016-05-01 |  | 2018-06-01 | 2018-06-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | Newly approved project | Brief progress report (actual/planned): Project newly approved. Agreement signed in Dec. 2016. Legal arrangements (actual/planned): Agreement signed in Dec. 2016. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st payment not sent yet__ All funds disbursed (yes/no): _ Final payment _no___ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
FIN | UNDP | Terminal phase out management plan for CFCs (first phase) | Multi-Year | LAC | STV | PHA | 47 | INV | 11 | N | I | CFC | 1.3 | 1.3 | 0 | 0 | 2005-11-01 | 2007-08-01 | 2006-12-01 |  | 2008-12-01 | 2013-03-01 | 101000 | 0 | 101000 | 101000 | 100% | 0 | 0 | 0 | 9090 | 0 | 9090 | 0 | 0 | Financially completed in 2013. |  | 2005 |  | Investment
FIN | UNEP | Terminal phase out management plan for CFCs (first tranche) | Multi-Year | LAC | STV | PHA | 47 | TRA | 10 | A | I |  | 0 | 0 | 0 | 0 | 2005-11-01 | 2007-09-01 | 2006-12-01 |  | 2010-12-01 | 2011-06-01 | 67000 | 0 | 67000 | 67000 | 100% | 0 | 0 |  | 8710 | 0 | 8710 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | STV | PHA | 55 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-12-01 | 2009-07-01 |  | 2013-06-01 | 2013-06-01 | 85000 | -3537 | 81463 | 81463 | 100% | 0 | 0 |  | 11050 | -459.81 | 10590.19 | 0 | 0
FIN | UNDP | Terminal phase out management plan for CFCs (second and third tranches) | Multi-Year | LAC | STV | PHA | 56 | INV | 15 | N | I | CFC | 0.8 | 0.8 | 0 | 0 | 2008-11-01 | 2010-11-01 | 2009-11-01 |  | 2012-05-01 | 2014-02-01 | 27000 | -173 | 26827 | 26827 | 100% | 0 | 0 | 0 | 2430 | -15.57 | 2414.43 | 0 | 0 | Financially completed in 2014. | Completed in 2012. No activities in 2013. | 2008 |  | Investment
FIN | UNEP | Terminal phase out management plan for CFCs (second and third tranches) | Multi-Year | LAC | STV | PHA | 56 | TAS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-12-01 | 2009-11-01 |  | 2011-12-01 | 2011-12-01 | 28000 | 0 | 28000 | 28000 | 100% | 0 | 0 |  | 3640 | 0 | 3640 | 0 | 0
FIN | UNEP | Terminal phase out management plan for CFCs (fourth tranche) | Multi-Year | LAC | STV | PHA | 61 | TAS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-02-01 | 2011-07-01 |  | 2011-12-01 | 2011-12-01 | 14000 | 0 | 14000 | 14000 | 100% | 0 | 0 |  | 1820 | 0 | 1820 | 0 | 0
COM | UNIDO | HCFC phase-out management plan (first tranche) | Multi-Year | LAC | STV | PHA | 64 | INV | 20 | A | I | HCFC | 0.1 | 0.1 |  |  | 2011-07-01 | 2013-04-01 | 2014-12-31 |  | 2015-12-01 |  | 124115 | 0 | 124115 | 123352.44 | 99.39% | 762.56 | 679.7 | 1 | 11170 | 0 | 11102 | 68 | 61 | The project was operationally completed. |  |  |  | INV
FIN | UNEP | HCFC phase-out management plan (first tranche) | Multi-Year | LAC | STV | PHA | 64 | TAS | 19 | A | I |  | 0.1 | 0 | 0 | 0 | 2011-07-01 | 2012-10-01 | 2014-12-01 |  | 2014-12-01 | 2014-12-01 | 55809 | -817 | 54992 | 54992 | 100% | 0 | 0 |  | 7255 | -106 | 7149 | 0 | 0
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | STV | PHA | 75 | TAS | 23 | A | I |  | 0 |  | 0 |  | 2015-11-01 |  | 2018-12-01 | 2018-10-01 |  |  | 140000 | 0 | 140000 | 0 | 0% | 140000 | 0 | 14000 | 18200 | 0 | 0 | 18200 | 0 | Brief progress report (actual/planned): 16 RAC technicians in Good Practices in HC Refrigerants & Technologies. Country submitted first draft of HPMP Workplan Dec-16. To be finalized. ___ Legal arrangements(actual/planned): SSFA signed Nov-16___ First mission (actual/planned): ___ TOR completed(actual/planned): ___ First disbursement date (actual/planned): To be processed upon finalization of workplan.___ All funds disbursed (yes/no): No.___ Any delay? (yes/no): No.___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): No.___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): HPMP Workplan finalized. Closure of year delayed processing of first payment. ___ Legal arrangements(actual/planned): SSFA signed Nov-16___ First mission (actual/planned): Planned for first half of 2017.___ TOR completed(actual/planned): ___ First disbursement date (actual/planned): Being processed. Expected by Mar-17___ All funds disbursed (yes/no): No.___ Any delay? (yes/no): No.___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): No.___ If Yes, is any action required by ExCom: ___
ONG | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Individual | LAC | STV | PHA | 77 | TAS | 24 | A | I |  | 0 |  | 0 |  | 2016-12-01 |  | 2018-06-01 | 2018-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 3000 | 3900 | 0 | 0 | 3900 | 0 | Newly approved project | Brief progress report (actual/planned): Report to be submited with third HPMP Tranche request due in 2018. Generic Terms of Reference (ToR) for hiring the international consultant prepared. Specific TORs to be adapted for Country and submitted for approval during second half of 2017. ___ Legal arrangements(actual/planned): SSA to be prepared upon selection of consultant. ___Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): ___ All funds disbursed (yes/no): ___ Any delay?(yes/no): ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): ___ If Yes, is any action required by ExCom: ___
FIN | UNEP | Implementation of the RMP: training of trainers for good practices in refrigeration | Individual | LAC | STV | REF | 25 | TRA | 02 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-10-01 | 1999-08-01 |  | 2002-05-01 | 2003-06-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNEP | Implementation of the RMP: monitoring and control of ODS and ODS based equipment | Individual | LAC | STV | REF | 25 | TRA | 03 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 2004-03-01 | 2000-02-01 |  | 2005-02-01 | 2008-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0
FIN | UNEP | Preparation of refrigerant management plan update | RMP update | LAC | STV | REF | 44 | PRP | 08 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2005-12-01 |  | 2005-11-01 | 2010-12-01 | 20000 | -3250.32 | 16749.68 | 16749.68 | 100% | 0 | 0 |  | 2600 | -422.54 | 2177.46 | 0 | 0
FIN | UNEP | Country programme preparation | Individual | LAC | STV | SEV | 21 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-04-01 | 1998-08-01 |  | 1998-05-01 | 1999-07-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNEP | Creation of the National Ozone Unit | Individual | LAC | STV | SEV | 25 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-04-01 | 2001-06-01 |  | 2004-03-01 | 2005-12-01 | 30300 | 0 | 30300 | 30300 | 100% | 0 | 0 |  | 3939 | 0 | 3939 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase II) | Individual | LAC | STV | SEV | 42 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2005-03-01 | 2005-04-01 |  | 2005-03-01 | 2005-12-01 | 13130 | 0 | 13130 | 13130 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase II) | Individual | LAC | STV | SEV | 45 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-12-01 | 2006-04-01 |  | 2008-03-01 | 2008-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | LAC | STV | SEV | 50 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-10-01 | 2008-11-01 |  | 2010-01-01 | 2011-01-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | LAC | STV | SEV | 58 | INS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2010-01-01 | 2010-12-01 |  | 2011-03-01 | 2011-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV, additional funding) | Individual | LAC | STV | SEV | 62 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-07-01 | 2011-08-01 |  | 2011-12-01 | 2012-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase V: 4/2012-3/2014) | Individual | LAC | STV | SEV | 66 | INS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 | 2012-12-01 | 2014-03-01 |  | 2014-03-01 | 2014-03-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of the institutional strengthening project (phase VI: 11/2014-10/2016) | Individual | LAC | STV | SEV | 73 | INS | 22 | A | I |  | 0 |  | 0 |  | 2014-11-01 | 2016-07-01 | 2016-10-01 | 2017-04-01 |  |  | 60000 | 0 | 60000 | 29903.03 | 49.84% | 30096.97 | 30096.97 | 3009.697 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): NOU participated in a session on Environmental Issues conducted by the Sustainable Development Unit. Ozone kiddies & adult handbooks distributed. The Agency for Public Information on their weekly programme Inside Story" interviewed the NOOs and HPMP consultant/RAC Trainer on SVG's response to the MP. A tour of the RAC Lab was also conducted. Major achievements of SVG since ratification of the MP with other Ozone related information was published in the three Local Newspapers. NOU attended Barbados Thematic Meeting in Dec-16. ___ Legal arrangements(actual/planned): SSFA signed Apr-15___Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): Apr-15___ All funds disbursed (yes/no): No. ___ Any delay?(yes/no): ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): No.___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): NOU submitted A7 data becoming the first country to submit 2016 data. NOU registered 13 importers of refrigerants for 2017. Quotas to HCFCs 8 of the 13 registered importers. Continues to monitor the imports and exports of refrigerant through the enforcement of the LQS ___ Legal arrangements(actual/planned): SSFA signed Apr-15___Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): Apr-15___ All funds disbursed (yes/no): No. ___ Any delay?(yes/no): ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): No.___ If Yes, is any action required by ExCom: ___
FIN | UNIDO | Phasing out of CFCs at Sudanese Cosmetics and Household Products | Individual | AFR | SUD | ARS | 18 | INV | 04 | A | I | CFC | 281.5 | 281.5 |  |  | 1995-11-01 | 1996-09-01 | 1997-05-01 |  | 1997-12-01 | 2000-07-01 | 497613 | -297 | 497316 | 497316 | 100% | 0 | 0 |  | 64690 | -141 | 64549 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the aerosol sector | Individual | AFR | SUD | ARS | 27 | PRP | 08 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-05-01 | 1999-12-01 |  | 2000-09-01 | 2002-05-01 | 25000 | -7393 | 17607 | 17606.64 | 100% | 0.36 | 0 |  | 3250 | -965 | 2285 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs at Tag Cosmetics Ltd. | Individual | AFR | SUD | ARS | 28 | INV | 13 | A | I | CFC | 45.1 | 45.1 |  |  | 1999-07-01 | 2000-08-01 | 2001-02-01 |  | 2002-07-01 | 2002-12-01 | 131718 | 0 | 131718 | 131718 | 100% | 0 | 0 |  | 17123 | -8 | 17115 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 at Patra Foam Co. flexible polyurethane foam plant | Individual | AFR | SUD | FOA | 19 | INV | 05 | A | I | CFC | 16 | 16 |  |  | 1996-05-01 | 1997-02-01 | 1997-11-01 |  | 1997-12-01 | 2000-04-01 | 72227 | 0 | 72227 | 72227 | 100% | 0 | 0 |  | 9390 | -1 | 9389 | 0 | 0 | FIN
FIN | UNIDO | Preparation for HCFC phase-out investment activities (polyurethane foam sector) | Individual | AFR | SUD | FOA | 59 | PRP | 24 | A | I |  | 0 | 0 |  |  | 2009-11-01 | 2010-12-01 | 2010-11-30 |  | 2010-12-01 | 2012-12-01 | 40000 | -607 | 39393 | 39393.45 | 100% | -0.45 | 0 |  | 3000 | -45 | 2955 | 0 | 0 | FIN |  |  |  | NON-INV
COM | UNIDO | Umbrella project for the phase-out of HCFC-141b from the polyurethane (PU) rigid foam production in the manufacturing of domestic refrigerators, commercial refrigerators and PU insulated composite panels (Modern, Amin, Coldair, Akadabi) | Multi-Year | AFR | SUD | FOA | 62 | INV | 28 | A | I | HCFC | 11.9 | 11.9 |  |  | 2010-12-01 | 2010-12-01 | 2013-06-30 |  | 2015-12-01 |  | 1056341 | 0 | 1056341 | 1055099.31 | 99.88% | 1241.69 | 11.91 | 1 | 79226 | 0 | 79132 | 94 | 1 | The project was operationally completed. |  |  |  | INV
COM | UNIDO | Preparation for HCFC phase-out investment activities (stage II) (foam sector) | Individual | AFR | SUD | FOA | 72 | PRP | 34 | A | I |  | 0 | 0 |  |  | 2014-05-01 | 2015-04-01 | 2015-05-31 |  | 2016-07-01 |  | 40000 | 0 | 40000 | 39551.88 | 98.88% | 448.12 | 0 | 1 | 2800 | 0 | 2769 | 31 | 0 | - HPMP Stage I first tranche in the foam sector was approved. - Project completed in Jul 2016. - Financially completed | Balance will be returned to the 79th Meeting of the ExCom. |  |  | NON-INV
COM | UNIDO | Project preparation in the fumigants sector (post-harvest) | Individual | AFR | SUD | FUM | 71 | PRP | 31 | A | I |  | 0 | 0 |  |  | 2013-12-01 | 2014-04-01 | 2014-12-31 |  | 2014-12-31 |  | 30000 | 0 | 30000 | 28547.01 | 95.16% | 1452.99 | 0 | 1 | 2100 | 0 | 1998 | 102 | 0 | The project was operationally completed. |  |  |  | NON-INV
ONG | UNIDO | Technical assistance for the final phase-out of methyl bromide in the post harvest sector | Individual | AFR | SUD | FUM | 73 | TAS | 36 | A | I | MBR | 1.2 | 0 |  |  | 2014-11-01 | 2016-02-01 | 2016-12-30 | 2018-02-01 |  |  | 181610 | 0 | 181610 | 39479.19 | 21.74% | 142130.81 | 7420.08 | 80000 | 16345 | 0 | 3553 | 12792 | 668 | - UNIDO placed a monitoring mission to Sudan in April 2016. - UNIDO and NOU agreed on a number of activities to ensure installation of procured materials as well as purchase of remaining materials from local suppliers. - Fans procured internationally reached Port of Sudan. - Installation is expected to take place in early 2017. Milestones achieved: Milestone 1: Legal agreements - Yes Milestone 2: Initial stages of project implementation began - Yes Milestone 3: Intermediate goals achieved - Yes Milestone 4: Project completion and follow-up - No Activities planned but not implemented, reasons and strategy: None Actions towards next goals: Finalize the installation and commissioning. Ensure proper training. Implement awareness activities. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Installation of procured material started under the monitoring of a national expert and the local representative of the international supplier. Actions towards next goals: - Finalize the installation and commissioning. - Ensure proper training. - Implement awareness activities. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV |  | 12 months delays
FIN | UNIDO | Preparation of a national ODS phase-out plan | Individual | AFR | SUD | PHA | 41 | PRP | 15 | A | I |  | 0 | 0 |  |  | 2003-12-01 | 2004-08-01 | 2004-12-01 |  | 2004-12-01 | 2005-06-01 | 70000 | -294 | 69706 | 69706.47 | 100% | -0.47 | 0 |  | 5250 | -30 | 5220 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National CFC/CTC phase-out plan (first tranche) | Multi-Year | AFR | SUD | PHA | 44 | INV | 18 | A | I | CFC CTC | 17.4 | 17.4 |  |  | 2004-12-01 | 2005-03-01 | 2005-12-01 |  | 2006-12-01 | 2010-12-01 | 499480 | -105 | 499375 | 499375.19 | 100% | -0.19 | 0 |  | 37461 | -8 | 37453 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National CFC/CTC phase-out plan (second tranche) | Multi-Year | AFR | SUD | PHA | 50 | INV | 19 | A | I | CFC | 70 | 70 |  |  | 2006-11-01 | 2007-10-01 | 2007-11-01 |  | 2007-12-01 | 2009-05-01 | 220000 | -88 | 219912 | 219912.27 | 100% | -0.27 | 0 |  | 16500 | -7 | 16493 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National CFC/CTC phase-out plan (third tranche) | Multi-Year | AFR | SUD | PHA | 53 | INV | 20 | A | I | CFC | 65 | 65 |  |  | 2007-11-01 | 2008-03-01 | 2009-03-01 |  | 2011-12-01 | 2012-12-01 | 220000 | -298 | 219702 | 219701.7 | 100% | 0.3 | 0 |  | 16500 | -22 | 16478 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | AFR | SUD | PHA | 55 | PRP | 21 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 |  | 2010-12-01 | 2012-10-01 | 30000 | -2950 | 27050 | 27050.21 | 100% | -0.21 | 0 |  | 2250 | -221 | 2029 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | National CFC/CTC phase-out plan (fourth tranche) | Multi-Year | AFR | SUD | PHA | 58 | INV | 23 | A | I | CFC | 65.3 | 65.3 |  |  | 2009-07-01 | 2009-12-01 | 2011-07-31 |  | 2012-03-01 | 2013-10-01 | 200000 | -1130 | 198870 | 198869.69 | 100% | 0.31 | 0 |  | 15000 | -85 | 14915 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan (additional funding) | Individual | AFR | SUD | PHA | 59 | PRP | 26 | A | I |  | 0 | 0 |  |  | 2009-11-01 | 2009-12-01 | 2010-11-30 |  | 2012-12-01 | 2014-04-01 | 120000 | -402 | 119598 | 119597.9 | 100% | 0.1 | 0 |  | 9000 | -30 | 8970 | 0 | 0 | FIN |  |  |  | NON-INV
COM | UNIDO | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | AFR | SUD | PHA | 66 | INV | 29 | A | I |  | 0 | 0 |  |  | 2012-04-01 | 2013-05-01 | 2013-04-30 |  | 2015-12-01 |  | 250000 | 0 | 250000 | 249969.57 | 99.99% | 30.43 | 0 | 1 | 18750 | 0 | 18748 | 2 | 0 | The project was operationally completed. |  |  |  | INV
COM | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | Individual | AFR | SUD | PHA | 72 | PRP | 32 | A | I |  | 0 | 0 |  |  | 2014-05-01 | 2015-01-01 | 2015-05-31 |  | 2015-12-01 |  | 25000 | 0 | 25000 | 24683.78 | 98.74% | 316.22 | 0 | 1 | 1750 | 0 | 1728 | 22 | 0 | The project was operationally completed. |  |  |  | NON-INV
COM | UNIDO | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | Multi-Year | AFR | SUD | PHA | 73 | INV | 35 | A | I |  | 0 | 0 |  |  | 2014-11-01 | 2015-01-01 | 2017-12-31 |  | 2016-12-01 |  | 110000 | 0 | 110000 | 109883.52 | 99.89% | 116.48 | 0 | 1 | 7700 | 0 | 7692 | 8 | 0 | - Refrigerant identifiers for customs office purchased. - Monitoring of import of HCFC continued in joint collaboration of NOU and customs office. - Identification and collection of unwanted stock of refrigerants, confiscated or other way degraded/mixed. - Certification of service shops continued in collaboration with SUST, Khartoum Technical University. - Trainings on servicing, recovery and recycling, in collaboration with SUST, Khartoum Technical University and in line with their curricula, accomplished for the programme as had been scheduled for this tranche. Milestones achieved: Milestone 1: - Legal arrangements - Yes Milestone 2: - Initial stages of project implementation began - Yes Milestone 3: - Intermediate goals achieved - Yes Milestone 4:- Project completion and follow-up - Yes Actions towards next goals: Report and request of third tranche. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | Project accomplished. Implementation report and request for third (2017) tranche initiated. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage II, first tranche) (foam sector) | Multi-Year | AFR | SUD | PHA | 75 | INV | 38 | A | I | HCFC | 27.1 | 0 |  |  | 2015-11-01 | 2016-08-01 | 2020-12-01 | 2019-12-01 |  |  | 2383572 | 0 | 2383572 | 22523.79 | 0.945% | 2361048.21 | 296244.59 | 200000 | 166850 | 0 | 0 | 166850 | 20737.1213 | - Tranche approved by 75th ExCom; - PAD of the project established. - TOR for the procurement of the first package of equipment for the group of four counterparts in thermoware sub-sector was prepared. - Procurement of equipment in progress; expected delivery is April 2017. - Preparation of TOR for sandwich panel manufacturing company (Target Steel) accomplished, international bidding initiated. - TOR for domestic refrigerators manufacturing company in progress. Milestones achieved: Milestone 1: First mission/Working arrangements (agreement/document signatures/PDA) agreed - Yes Milestone 2:Terms of reference (for equipment and/or services) completed - Yes Milestone 3:First disbursement made - Yes Milestone 4: Bidding completed, supplier selected - Yes for four companies; in progress for two other companies Milestone 5: Equipment shipped/delivered/installed at site - No Milestone 6: Commissioning and trial runs completed - No Actions towards next goals: Obtain offers, evaluate bids, select supplier. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Bidding for sandwich panel company initiated. - Domestic refrigeration company (Mina company) decided to re-locate manufacturing facility to new industrial park to ensure safety requirements. - Company has been visited again; new site inspected; finalization of TOR has been on hold, however to be finalized latest by June 2017; nevertheless major implementation delay not expected. Actions towards next goals: - ToR to be finalized for the domestic refrigeration company - Obtain offers, evaluate bids, select supplier. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Phasing out of ODS at three small domestic refrigerator factories in Sudan (Coldair Refrigerator Factory, Modern Refrigerator + Metal furniture Co., Sheet Metal Industries Co. Refrigerator Factory) | Individual | AFR | SUD | REF | 19 | INV | 06 | A | I | CFC | 7.28 | 7.3 |  |  | 1996-05-01 | 1996-12-01 | 1997-05-01 |  | 2002-03-01 | 2003-05-01 | 100000 | -13637 | 86363 | 86363.36 | 100% | -0.36 | 0 |  | 13000 | -1791 | 11209 | 0 | 0 | FIN |  |  | 1997-08-01
FIN | UNIDO | Preparation of Refrigerant Management Plan | Individual | AFR | SUD | REF | 23 | PRP | 07 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-09-01 | 1998-03-01 |  | 1998-12-01 | 2000-04-01 | 10000 | 16173 | 26173 | 26173 | 100% | 0 | 0 |  | 1300 | 2097 | 3397 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: recovery and recycling | RMP | AFR | SUD | REF | 28 | TAS | 10 | A | I | CFC | 50 | 50 |  |  | 1999-07-01 | 2001-08-01 | 2002-02-01 |  | 2004-08-01 | 2006-09-01 | 350000 | -1732 | 348268 | 348268.38 | 100% | -0.38 | 0 |  | 45500 | -225 | 45275 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: training for good practices in refrigeration | RMP | AFR | SUD | REF | 28 | TRA | 09 | A | I | CFC | 0 | 0 |  |  | 1999-07-01 | 2000-07-01 | 2002-06-01 |  | 2003-12-01 | 2003-12-01 | 70000 | -510 | 69490 | 69490.04 | 100% | -0.04 | 0 |  | 9100 | -81 | 9019 | 0 | 0 | FIN
FIN | UNIDO | Refrigerant management plan: training of customs officers and development of criteria for ODS and ODS consuming equipment imports | RMP | AFR | SUD | REF | 28 | TRA | 11 | A | I | CFC | 0 | 0 |  |  | 1999-07-01 | 2001-08-01 | 2001-02-01 |  | 2002-10-01 | 2004-09-01 | 38250 | -1916 | 36334 | 36333.7 | 100% | 0.3 | 0 |  | 4973 | -257 | 4716 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in the domestic/commercial refrigeration sector | Individual | AFR | SUD | REF | 39 | PRP | 14 | A | I |  | 0 | 0 |  |  | 2003-04-01 | 2003-09-01 | 2004-04-01 |  | 2005-04-01 | 2005-08-01 | 20000 | -345 | 19655 | 19655.29 | 100% | -0.29 | 0 |  | 1500 | -28 | 1472 | 0 | 0 | FIN
FIN | UNIDO | Preparation for HCFC phase-out investment activities (refrigeration and air-conditioning manufacturing sectors) | Individual | AFR | SUD | REF | 59 | PRP | 25 | A | I |  | 0 | 0 |  |  | 2009-11-01 | 2010-11-01 | 2010-11-30 |  | 2012-12-01 | 2014-04-01 | 60000 | -290 | 59710 | 59710.36 | 100% | -0.36 | 0 |  | 4500 | -22 | 4478 | 0 | 0 | FIN |  |  |  | NON-INV
COM | UNIDO | Preparation for HCFC phase-out investment activities (stage II) (refrigeration and air-conditioning sector) | Individual | AFR | SUD | REF | 72 | PRP | 33 | A | I |  | 0 | 0 |  |  | 2014-05-01 | 2015-04-01 | 2015-05-31 |  | 2015-12-01 |  | 35000 | 0 | 35000 | 34672.85 | 99.07% | 327.15 | 0 | 1 | 2450 | 0 | 2427 | 23 | 0 | The project was operationally completed. |  |  |  | NON-INV
FIN | UNEP | Country programme preparation | Individual | AFR | SUD | SEV | 11 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-11-01 | 1995-02-01 |  | 1994-03-01 | 1994-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0
FIN | UNEP | Institutional strengthening, creation of an Ozone Unit | Individual | AFR | SUD | SEV | 12 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-04-01 | 1997-03-01 |  | 1999-07-01 | 1999-12-01 | 168300 | 0 | 168300 | 168300 | 100% | 0 | 0 |  | 21879 | 0 | 21879 | 0 | 0 |  |  |  | 1999-12-01
FIN | UNIDO | Preparation of investment projects in the refrigeration, aerosol and foam sectors | Individual | AFR | SUD | SEV | 14 | PRP | 03 | A | I |  | 0 | 0 |  |  | 1994-09-01 | 1995-03-01 | 1995-01-01 |  | 1998-04-01 | 1999-08-01 | 50000 | -5442 | 44558 | 44558 | 100% | 0 | 0 |  | 6500 | -717 | 5783 | 0 | 0 | FIN
FIN | UNEP | Renewal of institutional strengthening (phase II) | Individual | AFR | SUD | SEV | 28 | INS | 12 | A | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 1999-12-01 | 2001-08-01 |  | 2001-12-01 | 2001-12-01 | 112200 | 0 | 112200 | 112200 | 100% | 0 | 0 |  | 14586 | 0 | 14586 | 0 | 0 |  |  |  | 2001-06-01
FIN | UNEP | Renewal of institutional strengthening project | Individual | AFR | SUD | SEV | 34 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-03-01 | 2003-08-01 |  | 2004-12-01 | 2009-09-01 | 112200 | 0 | 112200 | 112200 | 100% | 0 | 0 |  | 14586 | 0 | 14586 | 0 | 0
FIN | UNEP | Extension of institutional strengthening: phase IV | Individual | AFR | SUD | SEV | 42 | INS | 16 | A | I | CFC | 12.1 | 12.1 | 0 | 0 | 2004-04-01 | 2009-06-01 | 2006-04-01 |  | 2009-06-01 | 2010-12-01 | 145860 | 0 | 145860 | 145860 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening: phase V | Individual | AFR | SUD | SEV | 58 | INS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2010-04-01 | 2010-12-01 |  | 2011-04-01 | 2012-04-01 | 109395 | 0 | 109395 | 109395 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening: phase VI | Individual | AFR | SUD | SEV | 62 | INS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2012-01-01 | 2012-12-01 |  | 2013-12-01 | 2014-12-01 | 145860 | 0 | 145860 | 145860 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of institutional strengthening (phase VII: 4/2013-3/2015) | Individual | AFR | SUD | SEV | 69 | INS | 30 | A | I |  | 0 |  | 0 |  | 2013-04-01 | 2013-12-01 | 2015-03-01 | 2017-10-01 |  |  | 145860 | 0 | 145860 | 110802.57 | 75.97% | 35057.43 | 14124.55 | 3505.743 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): _ The licensing and quota systems are in place and functioning. _ The NOU organized a stakeholders meeting at the Corinthia Hotel/ Khartoum attended by 60 participants, comprising of steering committee, RAC owners, industry members, governmental bodies and universities staff, during which the outlines of ODS alternatives survey report was overviewed and discussed among all audience and feedback was received. The NOU registered 22 importers in 2016, and set priority for meeting next reduction target. The NOU conducted 5 training workshops where 260 technicians were trained. Dates for the trainings are as follows: 100 technicians were trained in May in Kassala and ElGazira. Two sets of equipment for vocational center and University were distributed, and 15 sets of equipment to best practicing shops. 90 technicians were trained in July in Omdurman (2 training centers), and 2 sets of equipment for vocational centers were distributed. 70 technicians were trained in August 2016 at the Eastern region in Bahery and 1 set of equipment for 1 vocational center was distributed. The NOU submitted 2014 ODS data and CP report. The NOU submitted 2015 Country Programme and Article 7 Data reports. The NOU celebrated the 2016 International Ozone day. The celebration, attended by 80 different stakeholders, was carried out at Khartoum Botonic Garden and marked with several awareness activities, including: school speeches from Khartoum State (ElMogran region), presentations on climate change and ozone and speech by the Higher Council for the Environment and Natural Resources. The NOU participated in all Regional Network and Montreal Protocol meetings. _ Legal arrangements (actual/planned): The SSFA was drafted and signed by UNEP and the Government of Sudan in November 2013. Initial stages of project implementation (actual/planned):Yes__ Intermediate goals achieved (actual/planned): __Yes_ Project completion and follow up: _Yes__ First disbursement date (actual/planned) First payment was made in Dec 2013._ All funds disbursed (yes/no): No. _ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A_ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): Collection of the 2016 data on ODS imports and consumption has been completed and is being analyzed for submission. NOU commenced preparation of national legislative requirement processes in planning for ratification of Kigali amendment. The NOU has planned to carry out 5 Trainings on good practice in refrigeration and air conditioning sectors to improve required capacity for the change to the new technology and maintenance techniques. About 250 technicians will be trained. Commitment to protect the ozone layer maintained; reduced emissions and consumptions of ozone depleting substances; increased recovery and recycling of ozone depleting substances
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | AFR | SUD | SEV | 74 | TAS | 37 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-04-01 | 2016-05-01 | 2017-05-01 |  |  | 110000 | 0 | 110000 | 5082.49 | 4.62% | 104917.51 | 104917.51 | 10491.751 | 14300 | 0 | 660.7237 | 13639.2763 | 13639.2763 | Brief progress report (actual/planned): The first stakeholders meeting was organized by the NOU in July 2016 in Khartoum and 40 participants from the ODS Alternative user sectors and importers attended. The main goal of the meeting was to sensitize the government and industry on the survey and agree on the plan for the Survey of ODS alternatives at the national level and obtain support of main national stakeholders. One National Consultant was hired in March 2016 by the NOU to support the data collection. The National Consultant assisted the NOU in the identification of the current use of ODS alternatives by substance/sector and collection of import/export data for the substances for the past a couple of years. The National Consultant also provided support in establishing growth patterns in use by substance/sector and in compiling data on available ODS alternatives for various applications. The NOU and the National Consultant drafted and cross checked the information to ensure the completion of end-user surveys, collection, analysis, and aggregation of consumption data. The various sections of the report were drafted. The second stakeholders meeting was organized by the NOU in October 2016 in Khartoum with the main goal to organise consultations with representatives of the government and private sector to finalize the outcomes of the Survey of ODS alternatives and discuss potential opportunities for introduction of those alternatives in the country. A total of 40 participants from the sectors using ODS Alternatives were in attendance. The draft report was prepared by the NOU and the National Consultant. It was reviewed and finalized based on the format approved by ExCom decision 75/67 as contained in document UNEP/OzL.Pro/ExCom/75/77/Rev.1 after incorporating inputs/ comments raised during National Stakeholders’ workshop. The final report was submitted to UNEP in December 2016 for final review and submission to MLFS. The NOU participated in the ODS Alternative Thematic workshop held in December 2016 to refine the draft report according to the revised template for the report. The report has been finally submitted to UNEP. Legal arrangements(actual/planned): The SSFA was drafted and signed by UNEP and the Government of Sudan in February 2016___Initial stages of project implementation(actual/planned): _Yes__ Intermediate goals achieved (actual/planned): Yes___ Project completion and follow up: _No__ First disbursement date (actual/planned): _April 2016__ All funds disbursed (yes/no): No___ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): __N/A_ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): The NOU incorporated comments from UNEP ROA and Paris and re-submitted final ODS survey report.
ONG | UNEP | Extension of institutional strengthening (phase VIII: 12/2015-11/2017) | Individual | AFR | SUD | SEV | 75 | INS | 39 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-07-01 | 2017-11-01 | 2018-03-01 |  |  | 186701 | 0 | 186701 | 0 | 0% | 186701 | 186701 | 18670.1 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The licensing and quota systems are in place and functioning effectively, supporting all HCFCs phase-out programme. The NOU organized a stakeholders meeting at the Corinthia Hotel/ Khartoum attended by 60 participants, comprising of steering committee, RAC owners, industry members, governmental bodies and university staffs, during which the outlines of ODS alternatives survey report was reviewed and discussed among all audience and feedback was received. The NOU took extra step to phase-out HCFCs mainly R22, by registering 22 importers in 2016, and setting priority for meeting next reduction target by reducing the quantity of imports by 15% as from 2015. The NOU conducted 5 training workshops where 260 technicians were trained. Dates for the trainings are as follows: 100 technicians were trained in May in Kassala and ElGazira. Two sets of equipment for vocational center and University were distributed, and 15 sets of equipment to best practicing shops. 90 technicians were trained in July in Omdurman (2 training centers), and 2 sets of equipment for vocational centers were distributed. 70 technicians were trained in August 2016 at the Eastern region in Bahery and 1 set of equipment for 1 vocational center was distributed. The NOU submitted 2014 ODS data and CP report. The NOU submitted 2015 Country Programme and Article 7 Data reports. The NOU celebrated the 2016 International Ozone day. The celebration, attended by 80 different stakeholders, was carried out at Khartoum Botonic Garden and marked with several awareness activities, including: school speeches from Khartoum State (ElMogran region), presentations on climate change and ozone and speech by the Higher Council for the Environment and Natural Resources. The NOU participated in all Regional Network and Montreal Protocol meetings. _ Legal arrangements (actual/planned): The SSFA was drafted and signed by UNEP and the Government of Sudan in June 2016. Initial stages of project implementation (actual/planned):Yes__ Intermediate goals achieved (actual/planned): __Yes_ Project completion and follow up: _No__ First disbursement date (actual/planned) First payment was made in July 2016._ All funds disbursed (yes/no): No. _ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A_ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): The NOU completed data collection for 2016 HCFCs and HFCs and awaiting submission to Ozone and Multilateral fund Secretariats after approval by the Government. One National Steering Committee Meeting was convened in January to review the 2016 Annual report and approve the 2017 Workplan. NOU commenced preparation of national legislative requirement processes in planning for ratification of Kigali amendment.
ONG | UNIDO | Survey of ODS alternatives at the national level | Individual | AFR | SUD | SEV | 75 | TAS | 40 | A | I |  | 0 | 0 |  |  | 2015-11-01 | 2016-02-01 | 2017-12-01 | 2017-05-01 |  |  | 110000 | 0 | 110000 | 48627.75 | 44.21% | 61372.25 | 7142.29 | 40000 | 9900 | 0 | 0 | 9900 | 642.8061 | - After recruitment of international expert and creation of national team of experts, surveying activities progressed according to established plan. First draft survey completed in December 2016. Milestones achieved: Milestone 1: First mission/Working arrangements agreed - Yes Milestone 2: ToR for HFC survey completed - Yes Milestone 3: Local institutions identified - Yes Milestone 4: Experts recruited - Yes Milestone 5: HCFC survey completed - Yes Milestone 6: All technical input completed - Yes Milestone 7: Draft document completed - Yes, see above Actions towards next goals: Survey completed in December 2016. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Works finalized. Report endorsed by the Government and submitted to 78th ExCom. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | NON-INV
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | LAC | SUR | PHA | 50 | PRP | 12 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-07-01 | 2007-11-01 |  | 2008-12-01 | 2009-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | LAC | SUR | PHA | 50 | PRP | 13 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-02-01 | 2007-11-01 |  | 2008-12-01 | 2011-11-01 | 15000 | -2500 | 12500 | 12500 | 100% | 0 | 0 | 0 | 1125 | -187.5 | 937.5 | 0 | 0 | Completed in 2008. |  | 2006 |  | Investment
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | LAC | SUR | PHA | 55 | PRP | 14 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-11-01 | 2009-07-01 |  | 2011-07-01 | 2011-07-01 | 85000 | -2953 | 82047 | 82047 | 100% | 0 | 0 |  | 11050 | -384.37 | 10665.63 | 0 | 0
FIN | UNDP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | SUR | PHA | 56 | INV | 16 | N | I | CFC | 6.2 | 6.2 | 0 | 0 | 2008-11-01 | 2010-03-01 | 2010-06-01 |  | 2011-12-01 | 2013-06-01 | 125000 | -2.37 | 124997.63 | 124998 | 100% | -0.37 | 0 | 0 | 11250 | 0 | 11250.0333 | -0.033301 | 0 | Financially completed in 2013. | Remaining invoices have been paid. | 2008 |  | Investment
FIN | UNEP | Terminal phase-out management plan for Annex A Group I substances (first tranche) | Multi-Year | LAC | SUR | PHA | 56 | TAS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-08-01 | 2010-06-01 |  | 2013-12-01 | 2013-12-01 | 100000 | -527 | 99473 | 99473 | 100% | 0 | 0 |  | 13000 | -68.51 | 12931.49 | 0 | 0
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | SUR | PHA | 65 | INV | 18 | A | I | HCFC | 0.1 | 0.1 |  |  | 2011-11-01 | 2013-05-01 | 2016-11-30 | 2017-12-01 |  |  | 68000 | 0 | 68000 | 57178.4 | 84.09% | 10821.6 | 0 | 5000 | 6120 | 0 | 5146 | 974 | 0 | Actions towards next goals: Re-assess needs of service sector and combine funds with 2nd tranche to make interventions more effective. Was there any delay during the reporting year? Yes If yes, reasons and action plan: A new Ozone Officer was supposed to be appointed as the previous one was promoted. However, after a long wait, this did not happen and Ozone officer remains the same. Activities will continue under the current Ozone Officer and funds will be combined with 2nd tranche, which will be submitted to the 77th ExCom. Any recurring problem? Yes Lack of communication from ozone unit. Any impact on project completion date: No Any action required by Executive Committee? No | Actions towards next goals: Re-assess needs of service sector and combine funds with 2nd tranche to make interventions more effective. Was there any delay during the reporting year? Yes If yes, reasons and action plan: A new Ozone Officer was supposed to be appointed as the previous one was promoted. However, after a long wait, this did not happen and Ozone officer remains the same. Activities will continue under the current Ozone Officer and funds will be combined with 2nd tranche, which will be submitted to the 77th ExCom. -Continued failure of communication from ozone unit. Project should be closed and funds returned if not used by end 2017. Any recurring problem? Yes Lack of communication from ozone unit. Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV |  | To request the submission of additional status report to the 79th meeting to monitor the resumption of activities in the first quarter of 2017.
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | SUR | PHA | 65 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2011-11-01 |  | 2013-11-01 |  | 2014-12-01 | 2014-12-01 | 27000 | 0 | 27000 | 27000 | 100% | 0 | 0 |  | 3510 | 0 | 3510 | 0 | 0
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | SUR | PHA | 74 | TAS | 22 | A | I |  | 0.1 |  | 0 |  | 2015-05-01 | 2016-12-01 | 2018-05-01 | 2018-10-01 |  |  | 28500 | 0 | 28500 | 10003.91 | 35.1% | 18496.09 | 0 | 1849.609 | 3705 | 0 | 1300.5083 | 2404.4917 | 0 | Brief progress report (actual/planned): Country finally responded to SSFA negotiations; SSFA agreed upon. In addition, the creation of the S-Grant for Suriname HPMP is UMOJA encountered difficulties and delays. This delayed the actual signature of the SSFA by the RD and Country. ___ Legal arrangements(actual/planned): SSFA signed Oct-16.___ First mission (actual/planned): Mission planned for first half of 2017.___ TOR completed(actual/planned): ___ First disbursement date (actual/planned): ___ All funds disbursed (yes/no): No. ___ Any delay? (yes/no): No.___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): No.___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): NOU hosting training with technicians for first quarter of 2017. NOU to submit HPMP Workplan upon finalization. NOU noted recent in the Executive of the Association, disrupting their usual level of cooperation. ___ Legal arrangements(actual/planned): SSFA signed Oct-16.___ First mission (actual/planned): Mission planned for Feb-17 postponed to Jun/Aug-17 following discussion with NOU.___ TOR completed(actual/planned): ___ First disbursement date (actual/planned): to be processed following receipt of HPMP workplan.___ All funds disbursed (yes/no): No. ___ Any delay? (yes/no): No.___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): No.___ If Yes, is any action required by ExCom: ___ |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor the signing of the agreement by the Government and UNEP.
ONG | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Individual | LAC | SUR | PHA | 75 | TAS | 24 | A | I |  | 0 |  | 0 |  | 2015-11-01 |  | 2017-03-01 | 2018-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 30000 | 3000 | 3900 | 0 | 0 | 3900 | 3900 | Brief progress report (actual/planned): The Terms of Reference (ToR) for hiring the international consultant, which was joined with the consultancy for Dominica's verification report, was prepared and cleared by the management Nov-16. Advertisement of consultancy posted on Inspira 15 Feb-17. ___ Legal arrangements(actual/planned): SSA to be prepared upon selection of consultant. ___Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): ___ All funds disbursed (yes/no): No. ___ Any delay?(yes/no): No. ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): No.__ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): Advertisement of consultancy posted Inspira. ___ Legal arrangements(actual/planned): SSA to be prepared upon selection of consultant. ___Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): ___ All funds disbursed (yes/no): No. ___ Any delay?(yes/no): No. ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): No.__ If Yes, is any action required by ExCom: ___
FIN | UNDP | Project preparation in the recovery and recycling refrigeration sector | Individual | LAC | SUR | REF | 36 | PRP | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2003-04-01 |  | 2004-12-01 | 2005-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2004. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNEP | Implementation of the RMP: development and strengthening of policy and regulatory framework for acceleration of compliance with the Montreal Protocol | Individual | LAC | SUR | REF | 41 | TAS | 04 | A | I | CFC | 1.5 | 1.5 | 0 | 0 | 2003-12-01 | 2004-09-01 | 2004-12-01 |  | 2007-01-01 | 2009-06-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0
FIN | UNEP | Implementation of the RMP: training of customs officers and other relevant stakeholders in monitoring of ODS | Individual | LAC | SUR | REF | 41 | TRA | 05 | A | I | CFC | 3.2 | 3.2 | 0 | 0 | 2003-12-01 | 2004-09-01 | 2004-12-01 |  | 2007-10-01 | 2008-12-01 | 42000 | 0 | 42000 | 42000 | 100% | 0 | 0 |  | 5460 | 0 | 5460 | 0 | 0
FIN | UNEP | Implementation of the RMP: training of trainers in good practices of refrigeration | Individual | LAC | SUR | REF | 41 | TRA | 06 | A | I | CFC | 5.4 | 5.4 | 0 | 0 | 2003-12-01 | 2004-09-01 | 2005-07-01 |  | 2007-12-01 | 2008-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0
FIN | UNDP | Project preparation for the formulation of refrigerant management plan (investment component) | Individual | LAC | SUR | REF | 42 | PRP | 07 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2004-10-01 |  | 2005-07-01 | 2006-12-01 | 12000 | 0 | 12000 | 12000 | 100% | 0 | 0 | 0 | 900 | 0 | 900 | 0 | 0 | Completed in 2005. Financially completed in 2006. |  | 2004 |  | Investment
FIN | UNDP | Implementation of the RMP: technical assistance for the MAC and refrigeration service sectors | RMP-Component | LAC | SUR | REF | 44 | TAS | 09 | N | I | CFC | 23 | 23 | 0 | 0 | 2004-12-01 | 2007-04-01 | 2007-06-01 |  | 2011-12-01 | 2013-02-01 | 300430 | -572.6 | 299857.4 | 299857 | 100% | 0.4 | 0 | 0 | 22532 | -42.94 | 22489.0255 | 0.0345 | 0 | Financially completed in 2013. | Remaining invoices have been paid. | 2004 |  | Investment
FIN | UNDP | Implementation of the RMP: monitoring the activities within the RMP | RMP-Component | LAC | SUR | REF | 44 | TAS | 10 | N | I | CFC | 2 | 2 | 0 | 0 | 2004-12-01 | 2009-05-01 | 2007-06-01 |  | 2011-07-01 | 2013-06-01 | 25750 | -736.47 | 25013.53 | 25014 | 100% | -0.47 | 0 | 0 | 2318 | -66.3 | 2251.7457 | -0.045709 | 0 | Financially completed in 2013. | Completed in 2011. Monitoring activities are on-going to support the implementation of the RMP update in Suriname. | 2004 |  | Non-Investment
FIN | UNEP | Preparation of country programme | Individual | LAC | SUR | SEV | 30 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2001-06-01 |  | 2003-08-01 | 2005-05-01 | 50000 | -35000 | 15000 | 15000 | 100% | 0 | 0 |  | 6500 | -4550 | 1950 | 0 | 0 |  |  |  | 2003-07-01
FIN | UNEP | Institutional strengthening and capacity building: establishment of the Ozone Unit | Individual | LAC | SUR | SEV | 41 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-08-01 | 2006-12-01 |  | 2009-06-01 | 2010-12-01 | 110000 | 0 | 110000 | 110000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase II) | Individual | LAC | SUR | SEV | 50 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-02-01 | 2008-11-01 |  | 2010-04-01 | 2011-04-01 | 73333 | 0 | 73333 | 73333 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | LAC | SUR | SEV | 59 | INS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2011-03-01 | 2011-11-01 |  | 2012-12-01 | 2013-12-01 | 39722 | 33611 | 73333 | 73333 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV: 7/2012-6/2014) | Individual | LAC | SUR | SEV | 67 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2012-12-01 | 2014-06-01 |  | 2014-12-01 | 2016-12-01 | 73333 | 0 | 73333 | 73333 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed | Project financially completed
ONG | UNEP | Extension of the institutional strengthening project (phase V: 12/2014-11/2016) | Individual | LAC | SUR | SEV | 73 | INS | 21 | A | I |  | 0 |  | 0 |  | 2014-11-01 | 2016-05-01 | 2016-11-01 | 2018-10-01 |  |  | 73333 | 0 | 73333 | 29281.77 | 39.93% | 44051.23 | 44051.23 | 4405.123 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Owing to national priorities, Mission rescheduled to Feb-17. Mission to address: ISP and HPMP implementation as well as Capacity within the NOU. NOU has to cancel participation to Barbados Thematic Meeting at the last meeting owing to a High Level meeting requiring presence of NOA. NOU support undertaking and completion of ODS Alternatives Survey. ___ Legal arrangements(actual/planned): SSFA signed Dec-15.___Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): May-16.___ All funds disbursed (yes/no): No. ___ Any delay?(yes/no): ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): No.___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): Country undertaking 2016 Data collection and verification. Following consultation with country, Mission rescheduled to Jun/Aug-17. ___ Legal arrangements(actual/planned): SSFA signed Dec-15.___Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): May-16.___ All funds disbursed (yes/no): No. ___ Any delay?(yes/no): ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): No.___ If Yes, is any action required by ExCom: ___
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | LAC | SUR | SEV | 75 | TAS | 23 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-06-01 | 2016-12-01 | 2017-06-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 5000 | 4000 | 5200 | 0 | 0 | 5200 | 650 | Brief progress report (actual/planned): The first stakeholders meeting was organized by the NOU with the main goal to agree on the plan for the Survey of ODS alternatives at the national level and obtain support of main national stakeholders. National University hired to undertake data collection. They assisted the NOU in the identification of the current use of ODS alternatives by substance/sector and collection of import/export data for the substances for the past a couple of years. They also provided support in establishing growth patterns in use by substance/sector and in compiling data on available ODS alternatives for various applications. Awaiting submission of Report.___ Legal arrangements(actual/planned): SSFA signed Apr-16___Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): Mandatory table submitted Nov-16.___ Project completion and follow up: Continue to follow-up on status of final Report.___ First disbursement date (actual/planned): Jun-16___ All funds disbursed (yes/no): No. ___ Any delay?(yes/no): ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): No.___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): The University engaged by the NOU to support the data collection. The University assisted the NOU in the identification of the current use of ODS alternatives by substance/sector and collection of import/export data for the substances for the past a couple of years. The University also provided support in establishing growth patterns in use by substance/sector and in compiling data on available ODS alternatives for various applications. The NOU and the University drafted and cross checked the information to ensure the completion of end-user surveys, collection, analysis, and aggregation of consumption data. The various sections of the report were drafted..___ Legal arrangements(actual/planned): SSFA signed Apr-16___Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): Mandatory table submitted Nov-16.___ Project completion and follow up: Continue to follow-up on submission of final Report.___ First disbursement date (actual/planned): Jun-16___ All funds disbursed (yes/no): No. ___ Any delay?(yes/no): ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): No.___ If Yes, is any action required by ExCom: ___
ONG | UNEP | Extension of the institutional strengthening project (phase VI: 12/2016-11/2018) | Individual | LAC | SUR | SEV | 77 | INS | 25 | A | I |  | 0 |  | 0 |  | 2016-12-01 |  | 2018-11-01 | 2018-11-01 |  |  | 93866 | 0 | 93866 | 0 | 0% | 93866 | 0 | 9386.6 | 0 | 0 | 0 | 0 | 0 | Newly approved project | Brief progress report (actual/planned): To be programmed once Country has reports 80% expenditure of previous ISP Phase.___ Legal arrangements(actual/planned):Pending ___Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): ___ All funds disbursed (yes/no): No. ___ Any delay?(yes/no): ___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): No.___ If Yes, is any action required by ExCom: ___
FIN | UNDP | Preparation for a terminal phase-out management plan | Individual | AFR | SWA | PHA | 53 | PRP | 09 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-07-01 | 2008-11-01 |  | 2008-12-01 | 2011-11-01 | 15000 | -5090.73 | 9909.27 | 9909 | 100% | 0.27 | 0 | 0 | 1125 | -381.8 | 743.175 | 0.02505 | 0 | Completed in 2008. |  | 2007 |  | Investment
FIN | UNEP | Preparation for a terminal phase-out management plan | Individual | AFR | SWA | PHA | 53 | PRP | 10 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-04-01 | 2008-11-01 |  | 2008-11-01 | 2009-11-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0
FIN | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | SWA | PHA | 56 | INV | 12 | N | I | CFC | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-05-01 | 2010-11-01 |  | 2010-12-01 | 2013-06-01 | 81500 | 0 | 81500 | 81500 | 100% | 0 | 0 | 0 | 7335 | 0 | 7335 | 0 | 0 | Financially completed in 2013. |  | 2008 |  | Investment
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | SWA | PHA | 56 | PRP | 13 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-11-01 | 2009-11-01 |  | 2011-07-01 | 2012-07-01 | 85000 | -5001 | 79999 | 79999 | 100% | 0 | 0 |  | 11050 | -650.13 | 10399.87 | 0 | 0
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | SWA | PHA | 56 | TAS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-02-01 | 2010-11-01 |  | 2013-12-01 | 2014-12-01 | 75000 | -4984 | 70016 | 70016 | 100% | 0 | 0 |  | 9750 | -647.92 | 9102.08 | 0 | 0
FIN | UNDP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | SWA | PHA | 59 | INV | 16 | N | I | CFC | 3.7 | 3.7 | 0 | 0 | 2009-11-01 | 2011-01-01 | 2011-11-01 |  | 2011-11-01 | 2013-06-01 | 40000 | -7701.16 | 32298.84 | 32299 | 100% | -0.16 | 0 | 0 | 3600 | -693.1 | 2906.91 | -0.01 | 0 | Financially completed in 2013. | Completed in 2011. | 2009 |  | Investment
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | SWA | PHA | 59 | TAS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2011-06-01 | 2011-11-01 |  | 2013-06-01 | 2013-06-01 | 57000 | 0 | 57000 | 57000 | 100% | 0 | 0 |  | 7410 | 0 | 7410 | 0 | 0
FIN | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | SWA | PHA | 63 | INV | 19 | N | I | HCFC | 7.7 | 7.7 | 0 | 0 | 2011-04-01 | 2011-12-01 | 2013-09-01 |  | 2013-11-01 | 2014-03-01 | 667948 | -28 | 667920 | 667920 | 100% | 0 | 0 | 0 | 50096 | -2 | 50093.9 | 0.099991 | 0 | Financially Completed in 2014. | Completed in 2013. Two final wrap-up steps are planned for 2014: official signature of the HOP to be completeted in Q1, with invitations of stakeholders, including lead HPMP agency (UNEP). Some doors are still manufactured on old door line due to new lin | 2011 |  | Investment
COM | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | SWA | PHA | 63 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2012-05-01 | 2013-03-01 |  | 2016-12-01 |  | 75000 | 0 | 75000 | 49178.9 | 65.57% | 25821.1 | 0 | 25821 | 9750 | 0 | 6393.257 | 3356.743 | 0 | Project completed | Project completed
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | AFR | SWA | PHA | 70 | TAS | 20 | A | I |  | 0.2 |  | 0 |  | 2013-07-01 | 2014-04-01 | 2016-07-01 | 2017-10-01 |  |  | 55000 | 0 | 55000 | 19673.32 | 35.77% | 35326.68 | 19999.35 | 3532.668 | 7150 | 0 | 2557.5316 | 4592.4684 | 2599.9155 | Brief progress report (actual/planned): The NOU implemented a number of activities under the HPMP including trainings for law enforcement officers and refrigeration technicians, and public awareness. The NOU conducted two training workshops for 30 custom officers to enhance the capacity of the law enforcement officers on motoring illegal trade. The NOU conducted training for 60 refrigerant technicians. The NOU procured equipment and distributed recovery kits to major workshops and key importers for testing the quality of the refrigerants before they purchase them. The NOU conducted monitoring of the HCFC quotas and illegal importation of ODSs..Legal arrangements (actual/planned): The SSFA was drafted and signed by UNEP and the Government of Swaziland in January 2014. Any delay (Yes/No): No_ First mission (actual/planned): CAP visited the country in October 2014 to monitor implementation of second tranche and had meetings with the Refrigeration Association, customs officers and management of SEA__N/A_ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): First disbursement was made in April 2014.___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _No_ If Yes, reasons for delay & action plan to resolve: N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): The NOU registered all importers of HCFCs and organized one stakeholders meeting in Feb 2017 to coordinate and allocate licenses and quotas. The NOU continues to monitor imports and trade of ODS and ODS related equipment.
ONG | UNEP | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | AFR | SWA | PHA | 77 | TAS | 23 | A | I |  | 0 |  | 0 |  | 2016-12-01 |  | 2018-12-01 | 2018-12-01 |  |  | 50000 | 0 | 50000 | 0 | 0% | 50000 | 0 | 5000 | 6500 | 0 | 0 | 6500 | 0 | Newly approved project. | Brief progress report (actual/planned): The project was approved in Dec 2016. The licensing and quota system are in place and operational. The NOU continues to monitor imports and trade of ODS and ODS related equipment. Collection of the 2016 data on ODS imports and consumption has been completed and is being analyzed for submission. NOU commenced preparation of national legislative requirement processes in planning for ratification of Kigali amendment. ___ Legal arrangements (actual/planned): The SSFA was drafted and sent to the Government of Swaziland for signature. ___Initial stages of project implementation (actual/planned): __Yes_ Intermediate goals achieved (actual/planned): _No__ Project completion and follow up: _Yes__ First disbursement date (actual/planned): __No ____. All funds disbursed (yes/no): No__ Any delay? (yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: __N/A_
FIN | UNIDO | Preparatory assistance for phase out of ODS in the domestic refrigeration production at FridgeMaster | Individual | AFR | SWA | REF | 15 | PRP | 02 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-03-01 | 1995-06-01 |  | 1995-12-01 | 1996-05-01 | 25000 | -13308 | 11692 | 11692 | 100% | 0 | 0 |  | 3250 | -1733 | 1517 | 0 | 0 | FIN
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | SWA | REF | 23 | PRP | 04 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1998-03-01 |  | 1998-07-01 | 2000-04-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | SWA | REF | 26 | TAS | 05 | A | I | CFC | 4 | 1.5 | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2003-08-01 | 2004-05-01 | 90375 | 0 | 90375 | 90375 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed, PCR submitted. RMP update ongoing
FIN | Germany | Project preparation for a refrigerant management plan update | RMP Update | AFR | SWA | REF | 37 | PRP | 06 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-08-01 | 2003-08-01 |  | 2003-08-01 | 2004-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project completed. RMP update approved at 41st Excom
FIN | Germany | Implementation of the RMP update | RMP Update | AFR | SWA | REF | 41 | TAS | 08 | A | I |  | 20.9 | 20.9 | 0 |  | 2003-12-01 | 2004-05-01 | 2006-12-01 |  | 2009-10-01 | 2011-10-01 | 74295 | 0 | 74295 | 74295 | 100% | 0 | 0 | 0 | 9658 | 0 | 9658 | 0 | 0 | A new NOU was appointed in 2009. The final customs training as last outstanding project activity was completed. PCR sent in September 2010.
FIN | UNDP | Preparation for HCFC phase-out investment activities (refrigeration manufacturing) | Individual | AFR | SWA | REF | 57 | PRP | 14 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-05-01 | 2010-03-01 |  | 2010-12-01 | 2012-06-01 | 30000 | -13037.08 | 16962.92 | 16963 | 100% | -0.08 | 0 | 0 | 2250 | -977.78 | 1272.225 | -0.005 | 0 | Financially completed in 2012. |  | 2009 |  | Investment
FIN | UNEP | Country programme preparation | Individual | AFR | SWA | SEV | 12 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-09-01 | 1995-06-01 |  | 1994-12-01 | 1994-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNEP | Institutional strengthening | Individual | AFR | SWA | SEV | 15 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1996-06-01 | 1998-12-01 |  | 2003-12-01 | 2007-02-01 | 67320 | 0 | 67320 | 67320 | 100% | 0 | 0 |  | 8752 | 0 | 8752 | 0 | 0 |  |  |  | 1998-03-01
FIN | UNEP | Extension of institutional strengthening project: phase 2 | Individual | AFR | SWA | SEV | 41 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-03-01 | 2005-12-01 |  | 2007-12-01 | 2009-10-01 | 58344 | 0 | 58344 | 58344 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | AFR | SWA | SEV | 53 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-11-01 |  | 2011-12-01 | 2013-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of institutional strengthening project (phase IV) | Individual | AFR | SWA | SEV | 59 | INS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2011-06-01 | 2011-11-01 |  | 2016-12-01 |  | 32500 | 27500 | 60000 | 49500.39 | 82.5% | 10499.61 | 10500 | 10500 | 0 | 0 | 0 | 0 | 0 | Project returned to COM as an SSFA amendment was signed with the country. | Project completed
ONG | UNEP | Extension of institutional strengthening project (phase V: 12/2013-11/2015) | Individual | AFR | SWA | SEV | 71 | INS | 21 | A | I |  | 0 |  | 0 |  | 2013-12-01 | 2016-04-01 | 2015-11-01 | 2017-10-01 |  |  | 60000 | 0 | 60000 | -1.7479e-12 | -2.913e-15% | 60000 | 60000 | 6000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): _ The licensing and quota systems are in place and functioning. The NOU registered all importers of HCFCs and organized one stakeholders meeting in Feb 2016 to coordinate and allocate licenses and quotas. The NOU conducted two inspection visits on importers to assess compliance with allocated quotas. The NOU trained 30 custom officers and 50 RAC technicians. The NOU submitted 2015 Country Programme and Article 7 Data reports. The NOU celebrated 2016 International Ozone Day and conducted several awareness activities. The NOU also participated in all Montreal Protocol meetings organized in 2016. __ Legal arrangements (actual/planned): _ The SSFA was drafted and signed by UNEP and the Government of Swaziland in January 2016__Initial stages of project implementation(actual/planned): Yes___ Intermediate goals achieved (actual/planned): __Yes_ Project completion and follow up: _No__ First disbursement date (actual/planned): April 2016__ All funds disbursed (yes/no): _No__ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: __N/A_ If Yes, will delay have impact on project completion date (yes/no): __N/A_ Any ongoing problems (yes/no): No___ If Yes, is any action required by ExCom: __N/A_ | Brief progress report (actual/planned): The NOU registered all importers of HCFCs and organized one stakeholders meeting in Feb 2017 to coordinate and allocate licenses and quotas. The NOU continues to monitor imports and trade of ODS and ODS related equipment. |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor project implementation progress and the disbursement rate of approved funds.
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | AFR | SWA | SEV | 74 | TAS | 22 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-06-01 | 2016-05-01 | 2017-05-01 |  |  | 70000 | 0 | 70000 | 55.16 | 0.0788% | 69944.84 | 65000 | 6994.484 | 9100 | 0 | 7.1708 | 9092.8292 | 8450 | Brief progress report (actual/planned): The first stakeholders meeting was organized by the NOU in July 2016 in Mbabane with the main goal to agree on the plan for the Survey of ODS alternatives at the national level and obtain support of main national stakeholders. The meeting was attended by 40 participants. One National Consultant was hired in June 2016 by the NOU to support the data collection. The National Consultant assisted the NOU in the identification of the current use of ODS alternatives by substance/sector and collection of import/export data for the substances for the past a couple of years. The National Consultant also provided support in establishing growth patterns in use by substance/sector and in compiling data on available ODS alternatives for various applications. The NOU and the National Consultant drafted and cross checked the information to ensure the completion of end-user surveys, collection, analysis, and aggregation of consumption data. The various sections of the report were drafted. The second stakeholders meeting was organized by the NOU in November 2016 in Mbabane with the main goal to organise consultations with representatives of the government and private sector to finalize the outcomes of the Survey of ODS alternatives and discuss potential opportunities for introduction of those alternatives in the country. The draft report was prepared by the NOU and the National Consultant. It was reviewed and finalized based on the format approved by ExCom decision 75/67 as contained in document UNEP/OzL.Pro/ExCom/75/77/Rev.1 after incorporating inputs/ comments raised during National Stakeholders’ workshop. The final report has been submitted to UNEP for final review and submission to MLFS. The NOU participated in the ODS Alternative Thematic workshop held in December 2016 to refine the draft report according to the revised template for the report. The report has been finally submitted to UNEP. Legal arrangements(actual/planned): The SSFA was drafted and signed by UNEP and the Government of Swaziland in February 2016___Initial stages of project implementation(actual/planned): _Yes__ Intermediate goals achieved (actual/planned): Yes___ Project completion and follow up: _No__ First disbursement date (actual/planned): _June 2016__ All funds disbursed (yes/no): No___ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): __N/A_ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): The NOU incorporated comments from UNEP ROA and Paris and re-submitted final ODS survey report in February 2017. The NOU continues to monitor imports and trade of ODS and ODS related equipment
FIN | UNIDO | Preparation of an investment project in the aerosol sector | Individual | ASP | SYR | ARS | 18 | PRP | 10 | A | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-02-01 | 1996-05-01 |  | 1998-05-01 | 1999-08-01 | 25000 | -746 | 24254 | 24254 | 100% | 0 | 0 |  | 3250 | -102 | 3148 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Gaston Banna & Sons Co. | Individual | ASP | SYR | ARS | 19 | INV | 13 | A | I | CFC | 104 | 104 |  |  | 1996-05-01 | 1997-06-01 | 1997-11-01 |  | 1998-12-01 | 2000-04-01 | 299500 | 0 | 299500 | 299500 | 100% | 0 | 0 |  | 38935 | 0 | 38935 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Careesse Cosmetics | Individual | ASP | SYR | ARS | 21 | INV | 16 | A | I | CFC | 185 | 185 |  |  | 1997-02-01 | 1997-06-01 | 1998-04-01 |  | 1998-12-01 | 2000-12-01 | 272621 | -1208 | 271413 | 271413 | 100% | 0 | 0 |  | 35441 | -213 | 35228 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Al Yaman | Individual | ASP | SYR | ARS | 22 | INV | 20 | A | I | CFC | 95 | 95 |  |  | 1997-05-01 | 1997-11-01 | 1998-09-01 |  | 1998-12-01 | 2002-08-01 | 216128 | -2737 | 213391 | 213391.36 | 100% | -0.36 | 0 |  | 28097 | -400 | 27697 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Ahmed Ali Harsho Sons Co. | Individual | ASP | SYR | ARS | 22 | INV | 21 | A | I | CFC | 45 | 45 |  |  | 1997-05-01 | 1997-12-01 | 1998-09-01 |  | 1998-12-01 | 2001-12-01 | 175328 | -3796 | 171532 | 171532.15 | 100% | -0.15 | 0 |  | 22793 | -529 | 22264 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Taki Eddin & Co. | Individual | ASP | SYR | ARS | 22 | INV | 22 | A | I | CFC | 118.8 | 118.8 |  |  | 1997-05-01 | 1997-11-01 | 1998-09-01 |  | 1998-12-01 | 2001-12-01 | 244203 | 0 | 244203 | 244203.21 | 100% | -0.21 | 0 |  | 31746 | -44 | 31702 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Laboratories Kosmeto | Individual | ASP | SYR | ARS | 23 | INV | 23 | A | I | CFC | 59.9 | 59.9 |  |  | 1997-11-01 | 1998-10-01 | 1999-02-01 |  | 1999-10-01 | 2001-11-01 | 175062 | -1772 | 173290 | 173289.67 | 100% | 0.33 | 0 |  | 22758 | -266 | 22492 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Dina Cosmetics | Individual | ASP | SYR | ARS | 23 | INV | 24 | A | I | CFC | 70 | 70 |  |  | 1997-11-01 | 1998-10-01 | 1999-08-01 |  | 2000-07-01 | 2001-12-01 | 228477 | -456 | 228021 | 228021.2 | 100% | -0.2 | 0 |  | 29702 | -106 | 29596 | 0 | 0 | FIN
FIN | UNIDO | Preparation of at least three investment projects in the aerosol sector for phasing out ODS at three enterprises including Nweylati | Individual | ASP | SYR | ARS | 23 | PRP | 26 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-06-01 | 1998-03-01 |  | 2000-12-01 | 2001-05-01 | 10000 | 4480 | 14480 | 14480.39 | 100% | -0.39 | 0 |  | 1300 | 579 | 1879 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Mariza Co. | Individual | ASP | SYR | ARS | 25 | INV | 31 | A | I | CFC | 90 | 90 |  |  | 1998-07-01 | 1999-05-01 | 1999-12-01 |  | 2000-07-01 | 2002-05-01 | 207652 | -3210 | 204442 | 204442.48 | 100% | -0.48 | 0 |  | 26995 | -460 | 26535 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Al-Fajer Co. | Individual | ASP | SYR | ARS | 26 | INV | 36 | A | I | CFC | 44 | 44 |  |  | 1998-11-01 | 1999-10-01 | 2000-04-01 |  | 2000-06-01 | 2001-07-01 | 169985 | -1059 | 168926 | 168926 | 100% | 0 | 0 |  | 22098 | -172 | 21926 | 0 | 0 | FIN
FIN | UNIDO | Project preparation of investment projects in the aerosol sector | Individual | ASP | SYR | ARS | 27 | PRP | 44 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 2000-07-01 | 1999-12-01 |  | 2000-12-01 | 2001-09-01 | 8000 | -1359 | 6641 | 6640.69 | 100% | 0.31 | 0 |  | 1040 | -178 | 862 | 0 | 0 | FIN
CLO | UNIDO | Preparation of investment projects in the aerosol sector | Individual | ASP | SYR | ARS | 30 | PRP | 57 | A | I |  | 0 | 0 |  |  | 2000-03-01 |  | 2001-04-01 |  |  | 2001-07-01 | 20000 | -20000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 2600 | -2600 | 0 | 0 | 0 | CLO
FIN | UNIDO | Phase-out o fCFC-11 and 12 in the manufacture of hair lacquers by conversion to hydrocarbon propellant at Badran and Co. | Individual | ASP | SYR | ARS | 32 | INV | 71 | A | I | CFC | 15.6 | 15.6 |  |  | 2000-12-01 | 2001-11-01 | 2003-03-01 |  | 2004-06-01 | 2004-09-01 | 68640 | 0 | 68640 | 68639.82 | 100% | 0.18 | 0 |  | 8923 | -3 | 8920 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of CFC-12 in the manufacture of hair lacquers by conversion to hydrocarbon propellant at Mahmoud Hamida | Individual | ASP | SYR | ARS | 32 | INV | 72 | A | I | CFC | 10.5 | 10.5 |  |  | 2000-12-01 | 2001-11-01 | 2003-03-01 |  | 2004-06-01 | 2004-09-01 | 46200 | 0 | 46200 | 46200.14 | 100% | -0.14 | 0 |  | 6006 | -3 | 6003 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of CFC-11 and 12 in the manufacture of hair sprays by conversion to hydrocarbon propellant at Khadji and Zahka | Individual | ASP | SYR | ARS | 32 | INV | 73 | A | I | CFC | 11 | 11 |  |  | 2000-12-01 | 2001-11-01 | 2003-03-01 |  | 2004-06-01 | 2004-09-01 | 48400 | -31 | 48369 | 48369.2 | 100% | -0.2 | 0 |  | 6292 | -14 | 6278 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of CFC-12 in the manufacture of insecticides by conversion to hydrocarbon propellant at Cheikh Ghazal Insecticide Plant | Individual | ASP | SYR | ARS | 32 | INV | 74 | A | I | CFC | 36 | 36 |  |  | 2000-12-01 | 2001-11-01 | 2003-03-01 |  | 2004-06-01 | 2004-09-01 | 87298 | -770 | 86528 | 86527.74 | 100% | 0.26 | 0 |  | 11349 | -118 | 11231 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project for phasing out CFC-11 from the manufacturing of pre-fabricated sandwich panels at Krayem Cold Stores Co. | Individual | ASP | SYR | FOA | 15 | PRP | 07 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-03-01 | 1995-06-01 |  | 1996-06-01 | 1998-08-01 | 15000 | -1404 | 13596 | 13596 | 100% | 0 | 0 |  | 1950 | -185 | 1765 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects for phasing out of CFC-11 from the sub sector of flexible foams manufacturing | Individual | ASP | SYR | FOA | 15 | PRP | 08 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-02-01 | 1995-06-01 |  | 2000-06-01 | 2001-07-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNIDO | Phasing out CFC-11 at Dakkak Co. flexible polyurethane foam plant | Individual | ASP | SYR | FOA | 19 | INV | 14 | A | I | CFC | 17 | 17 |  |  | 1996-05-01 | 1996-10-01 | 1997-05-01 |  | 1998-12-01 | 2001-11-01 | 96553 | 0 | 96553 | 96552.94 | 100% | 0.06 | 0 |  | 12552 | -17 | 12535 | 0 | 0 | FIN
FIN | UNIDO | Investment project for phasing out CFCs at Krayem Cold Stores Co. | Individual | ASP | SYR | FOA | 19 | INV | 15 | A | I | CFC | 65 | 65 |  |  | 1996-05-01 | 1996-11-01 | 1997-09-01 |  | 1998-12-01 | 2001-07-01 | 644600 | -9228 | 635372 | 635371.9 | 100% | 0.1 | 0 |  | 83798 | -1331 | 82467 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Abdul Karim Sbei | Individual | ASP | SYR | FOA | 21 | INV | 17 | A | I | CFC | 61.7 | 61.7 |  |  | 1997-02-01 | 1997-06-01 | 1998-06-01 |  | 1998-12-01 | 2000-07-01 | 92256 | -1984 | 90272 | 90272 | 100% | 0 | 0 |  | 11993 | -276 | 11717 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Walid and Nabil Rankousi Ltd. | Individual | ASP | SYR | FOA | 21 | INV | 18 | A | I | CFC | 38.7 | 38.7 |  |  | 1997-02-01 | 1998-11-01 | 1998-06-01 |  | 1998-12-01 | 2000-07-01 | 86782 | -2175 | 84607 | 84607 | 100% | 0 | 0 |  | 11282 | -301 | 10981 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the flexible foam sector | Individual | ASP | SYR | FOA | 21 | PRP | 19 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-10-01 | 1997-06-01 |  | 2000-12-01 | 2002-09-01 | 10000 | -362 | 9638 | 9638.11 | 100% | -0.11 | 0 |  | 1300 | -49 | 1251 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 from flexible slabstock foam manufacturing at Akal Factory | Individual | ASP | SYR | FOA | 23 | INV | 25 | A | I | CFC | 101 | 101 |  |  | 1997-11-01 | 1999-07-01 | 1998-12-01 |  | 2002-10-01 | 2004-04-01 | 510130 | 0 | 510130 | 510130.14 | 100% | -0.14 | 0 |  | 66317 | -26 | 66291 | 0 | 0 | FIN |  |  | 1999-12-01
FIN | UNIDO | Preparation of investment projects for NPD in Damascus and others in rigid foam sector | Individual | ASP | SYR | FOA | 24 | PRP | 29 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-09-01 | 1999-04-01 |  | 2000-04-01 | 2002-09-01 | 15000 | -238 | 14762 | 14762.04 | 100% | -0.04 | 0 |  | 1950 | -34 | 1916 | 0 | 0 | FIN |  |  | 1999-09-01
FIN | UNIDO | Phasing out CFC-11 in manufacturing of flexible PU slabstock foam through the use of CO2 blowing technology at National Polyurethane Company (N.P.C.) | Individual | ASP | SYR | FOA | 26 | INV | 32 | A | I | CFC | 96 | 96 |  |  | 1998-11-01 | 1999-06-01 | 2000-06-01 |  | 2001-12-01 | 2003-12-01 | 543918 | 0 | 543918 | 543917.73 | 100% | 0.27 | 0 |  | 69831 | -3 | 69828 | 0 | 0 | FIN |  |  | 2001-12-01
FIN | UNIDO | Phasing out CFC-11 in the manufacture of flexible PU slabstock foam through the use of methylene chloride as blowing agent at Chaar Bros Co. | Individual | ASP | SYR | FOA | 26 | INV | 34 | A | I | CFC | 50 | 50 |  |  | 1998-11-01 | 1999-02-01 | 2000-04-01 |  | 2000-05-01 | 2001-07-01 | 98248 | -79 | 98169 | 98169 | 100% | 0 | 0 |  | 12772 | -30 | 12742 | 0 | 0 | FIN
CLO | UNDP | Preparation of one project in the flexible foam subsector | Individual | ASP | SYR | FOA | 27 | PRP | 42 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 |  | 2000-04-01 |  |  | 2004-01-01 | 15000 | -15000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 1950 | -1950 | 0 | 0 | 0 | Canceled in 2001. Financially Completed in 2004. |  | 1999 |  | Investment
FIN | UNIDO | Conversion from CFC-11 to cyclopenthane in the production of rigid foam panels at National Polyurethane Company (N.P.C.) | Individual | ASP | SYR | FOA | 31 | INV | 61 | A | I | CFC | 61.1 | 61.1 |  |  | 2000-07-01 | 2001-04-01 | 2002-08-01 |  | 2004-10-01 | 2005-04-01 | 426104 | 0 | 426104 | 426103.9 | 100% | 0.1 | 0 |  | 55394 | -46 | 55348 | 0 | 0 | FIN |  |  | 2003-11-01
FIN | UNIDO | Preparation of a project in the flexible foam sector | Individual | ASP | SYR | FOA | 31 | PRP | 62 | A | I |  | 0 | 0 |  |  | 2000-07-01 | 2001-03-01 | 2001-07-01 |  | 2001-12-01 | 2003-05-01 | 20000 | -27 | 19973 | 19973.47 | 100% | -0.47 | 0 |  | 2600 | -8 | 2592 | 0 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b in the production of rigid foam panels at Bassam Baghdan | Individual | ASP | SYR | FOA | 32 | INV | 68 | A | I | CFC | 16.4 | 16.4 |  |  | 2000-12-01 | 2001-11-01 | 2003-01-01 |  | 2005-12-01 | 2006-12-01 | 126862 | -2164 | 124698 | 124697.51 | 100% | 0.49 | 0 |  | 16492 | -281 | 16211 | 0 | 0 | FIN
FIN | UNIDO | Conversion from CFC-11 to methylene chloride in the production of flexible slabstock foam at Al-Muzayek | Individual | ASP | SYR | FOA | 34 | INV | 76 | A | I | CFC | 33.7 | 33.7 |  |  | 2001-07-01 | 2002-03-01 | 2004-08-01 |  | 2003-12-01 | 2004-12-01 | 106789 | 0 | 106789 | 106789.12 | 100% | -0.12 | 0 |  | 13883 | -9 | 13874 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of an investment project in the extruded polystyrene foam sector | Individual | ASP | SYR | FOA | 36 | PRP | 82 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-07-01 | 2003-04-01 |  | 2003-10-01 | 2004-09-01 | 15000 | -80 | 14920 | 14919.91 | 100% | 0.09 | 0 |  | 1950 | -14 | 1936 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phasing out of CFC-12 by conversion to n-butane as a blowing agent in the manufacture of extruded polystyrene (EPS) foam for packing purposes at Shanko and Partners Co. | Individual | ASP | SYR | FOA | 38 | INV | 88 | A | I | CFC | 16 | 16 |  |  | 2002-11-01 | 2003-11-01 | 2005-06-01 |  | 2004-08-01 | 2004-12-01 | 132200 | 0 | 132200 | 132200.18 | 100% | -0.18 | 0 |  | 17186 | -23 | 17163 | 0 | 0 | FIN |  |  |  | INV
ONG | UNIDO | Preparation for HCFC phase-out investment activities (foam sector) | Individual | ASP | SYR | FOA | 61 | PRP | 102 | A | I |  | 0 | 0 |  |  | 2010-07-01 | 2010-12-01 | 2011-07-31 | 2019-03-01 |  |  | 40000 | 0 | 40000 | 23387.53 | 58.47% | 16612.47 | 0 | 4000 | 3000 | 0 | 1754 | 1246 | 0 | No progress due to the situation in the country. | No progress due to the situation in the country. It is suggested to extend project duration. |  |  | NON-INV |  | To request the submission of additional status report to the 79th meeting to monitor the resumption of activities.
FIN | UNIDO | Preparation of a demonstration project in the methyl bromide sector | Individual | ASP | SYR | FUM | 23 | PRP | 27 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-01-01 | 1998-03-01 |  | 1999-01-01 | 2001-07-01 | 10000 | 13050 | 23050 | 23050 | 100% | 0 | 0 |  | 1300 | 1692 | 2992 | 0 | 0 | FIN
FIN | UNIDO | Alternatives to the use of methyl bromide for soil fumigation in horticulture and commodities fumigation | Individual | ASP | SYR | FUM | 24 | DEM | 30 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-07-01 | 2000-04-01 |  | 2001-05-01 | 2003-05-01 | 509850 | -33283 | 476567 | 476566.89 | 100% | 0.11 | 0 |  | 66281 | -4425 | 61856 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a project in the fumigant (methyl bromide) sector for grain fumigation | Individual | ASP | SYR | FUM | 31 | PRP | 63 | A | I |  | 0 | 0 |  |  | 2000-07-01 | 2000-09-01 | 2001-07-01 |  | 2001-10-01 | 2002-12-01 | 20000 | -5357 | 14643 | 14642.91 | 100% | 0.09 | 0 |  | 2600 | -699 | 1901 | 0 | 0 | FIN
FIN | Germany | Project preparation/technical assistance in soil fumigants (methyl bromide) | Individual | ASP | SYR | FUM | 32 | PRP | 70 | A | I |  | 0 |  | 0 |  | 2000-12-01 | 2001-04-01 | 2002-01-01 |  | 2001-09-01 | 2002-03-01 | 37200 | 0 | 37200 | 37200 | 100% | 0 | 0 | 0 | 4836 | 0 | 4836 | 0 | 0 | Project preparation led to project proposal for implementation, which was not accepted because of quantities of illegal MB. Syria is currently complying with its obligations. Only 8 ODP tons will still be eligeable in the future.
FIN | UNIDO | Phase-out of the use of methyl bromide in grain storage (first tranche) | Multi-Year | ASP | SYR | FUM | 34 | INV | 80 | A | I | MBR | 5 | 5 |  |  | 2001-07-01 | 2002-08-01 | 2002-12-01 |  | 2006-12-01 | 2008-12-01 | 300000 | 0 | 300000 | 299999.97 | 100% | 0.03 | 0 |  | 39000 | 0 | 39000 | 0 | 0 | FIN |  |  | 2005-12-01 | INV
FIN | UNIDO | Phase-out of methyl bromide in grain storage (second tranche) | Multi-Year | ASP | SYR | FUM | 41 | INV | 89 | A | I | MBR | 29.8 | 29.8 |  |  | 2003-12-01 | 2005-02-01 | 2004-12-01 |  | 2010-12-01 | 2010-12-01 | 351725 | -1572 | 350153 | 350152.88 | 100% | 0.12 | 0 |  | 26379 | -118 | 26261 | 0 | 0 | FIN |  |  | 2006-12-01 | INV
FIN | UNIDO | Phase-out methyl bromide in grain fumigation (third tranche) | Multi-Year | ASP | SYR | FUM | 47 | INV | 94 | A | I | MBR | 70.2 | 70.2 |  |  | 2005-11-01 | 2007-01-01 | 2006-12-01 |  | 2011-12-01 | 2013-10-01 | 432414 | -6506 | 425908 | 425907.91 | 100% | 0.09 | 0 |  | 32431 | -488 | 31943 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Methyl bromide national phase-out plan (soil fumigation) | Individual | ASP | SYR | FUM | 49 | TAS | 95 | A | I | MBR | 48 | 75 |  |  | 2006-07-01 | 2007-12-01 | 2010-07-01 |  | 2013-12-01 | 2015-03-01 | 240000 | -332 | 239668 | 239668.32 | 100% | -0.32 | 0 |  | 21600 | -30 | 21570 | 0 | 0 | FIN |  |  |  | INV
FIN | France | Development of a halon banking management plan |  | ASP | SYR | HAL | 29 | TAS | 50 | A | I |  | 0 |  | 0 |  | 1999-11-01 | 2004-04-01 | 2000-05-01 |  | 2001-05-01 | 2004-04-01 | 10736 | 0 | 10736 | 10736 | 100% | 0 |  |  | 536 | 0 | 536 | 0 |  | Project completed.
FIN | Germany | Development of halon banking management plan | Halon banking | ASP | SYR | HAL | 29 | TAS | 55 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 1999-12-01 | 2000-05-01 |  | 2000-05-01 | 2002-04-01 | 10736 | 0 | 10736 | 10736 | 100% | 0 | 0 | 0 | 1396 | 0 | 1396 | 0 | 0 | Project preparation led to project proposal for implementation
FIN | Germany | Establishing a halon bank and umbrella project for 63 manufacturers | Individual | ASP | SYR | HAL | 34 | TAS | 77 | A | I | HAL | 284.5 | 284.5 | 0 |  | 2001-07-01 | 2001-08-01 | 2004-08-01 |  | 2005-12-01 | 2007-12-01 | 161000 | 0 | 161000 | 161000 | 100% | 0 | 0 | 0 | 20930 | 0 | 20930 | 0 | 0 | Project is completed. PCR was submitted in 2007.
FIN | France | Establishing a halon bank and umbrella project for 63 manufacturers |  | ASP | SYR | HAL | 34 | TAS | 78 | A | I | HAL | 284.5 |  | 0 |  | 2001-07-01 | 2004-04-01 | 2004-08-01 |  | 2004-04-01 | 2005-01-01 | 161000 | 0 | 161000 | 161000 | 100% | 0 |  | 0 | 8050 | 0 | 8050 | 0 |  | Project completed.
CLO | UNIDO | Preparation of a national ODS phase-out plan | Individual | ASP | SYR | PHA | 36 | PRP | 85 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-10-01 | 2003-10-01 |  |  | 2003-05-01 | 60000 | -56845 | 3155 | 3155.02 | 100% | -0.02 | 0 |  | 7800 | -7390 | 410 | 0 | 0 | CLO |  |  |  | INV
FIN | UNIDO | Preparation of CFC-phase-out plan including methyl bromide | Individual | ASP | SYR | PHA | 45 | PRP | 92 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-07-01 | 2006-04-01 |  | 2006-12-01 | 2008-12-01 | 70000 | -1900 | 68100 | 68100.06 | 100% | -0.06 | 0 |  | 5250 | -142 | 5108 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | National CFC phase-out plan for Syria (first tranche) | Multi-Year | ASP | SYR | PHA | 49 | INV | 96 | A | I | CFC | 100 | 100 |  |  | 2006-07-01 | 2006-10-01 | 2008-07-01 |  | 2010-12-01 | 2013-10-01 | 430000 | -550 | 429450 | 429450.08 | 100% | -0.08 | 0 |  | 32250 | -41 | 32209 | 0 | 0 | FIN |  |  |  | INV
ONG | UNIDO | Preparation of a HCFC phase-out management plan | Individual | ASP | SYR | PHA | 55 | PRP | 97 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 | 2019-03-01 |  |  | 136250 | 0 | 136250 | 108362.56 | 79.53% | 27887.44 | 0 | 1000 | 10219 | 0 | 8127 | 2092 | 0 | No progress due to the situation in the country. | No progress due to the situation in the country. It is suggested to extend project duration. |  |  | NON-INV |  | To request the submission of additional status report to the 79th meeting to monitor the resumption of activities.
FIN | UNIDO | National CFC phase-out plan (second tranche) | Multi-Year | ASP | SYR | PHA | 56 | INV | 98 | A | I | CFC | 328.7 | 328.7 |  |  | 2008-11-01 | 2009-12-01 | 2009-11-30 |  | 2010-12-01 | 2012-10-01 | 170000 | 0 | 170000 | 169999.98 | 100% | 0.02 | 0 |  | 12750 | 0 | 12750 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National CFC phase-out plan (third tranche) | Multi-Year | ASP | SYR | PHA | 58 | INV | 99 | A | I | CFC | 70 | 70 |  |  | 2009-07-01 | 2010-09-01 | 2010-07-31 |  | 2013-12-01 | 2013-12-01 | 154050 | -130197 | 23853 | 23852.73 | 100% | 0.27 | 0 |  | 11554 | -9765 | 1789 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phasing out of CFCs at Al Hafez Refrigeration Co. | Individual | ASP | SYR | REF | 13 | INV | 04 | A | I | CFC | 106.7 | 100.7 |  |  | 1994-07-01 | 1996-03-01 | 1996-01-01 |  | 1996-12-01 | 2001-05-01 | 2883277 | 0 | 2883277 | 2883277 | 100% | 0 | 0 |  | 374826 | 0 | 374826 | 0 | 0 | FIN
FIN | UNIDO | Investment project for phasing out CFC at Penguin (Syrian Batric Co.) | Individual | ASP | SYR | REF | 15 | INV | 05 | A | I | CFC | 82.3 | 77.3 |  |  | 1994-12-01 | 1996-01-01 | 1996-06-01 |  | 1996-12-01 | 2000-12-01 | 1719900 | -1241 | 1718659 | 1718659 | 100% | 0 | 0 |  | 223587 | -515 | 223072 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC at Barada General Co. for Metallic Industry | Individual | ASP | SYR | REF | 15 | INV | 09 | A | I | CFC | 109 | 97 |  |  | 1994-12-01 | 1996-02-01 | 1996-06-01 |  | 1997-12-01 | 2001-07-01 | 989650 | -95593 | 894057 | 894057.23 | 100% | -0.23 | 0 |  | 128655 | -12612 | 116043 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project for phasing out CFC in manufacturing of refrigerators at Krayem Int. Co. | Individual | ASP | SYR | REF | 15 | PRP | 06 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-02-01 | 1995-06-01 |  | 1996-06-01 | 1998-08-01 | 15000 | -711 | 14289 | 14289 | 100% | 0 | 0 |  | 1950 | -95 | 1855 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs from Manufacturing of domestic and commercial refrigerators at Krayem Brothers Co. | Individual | ASP | SYR | REF | 18 | INV | 11 | A | I | CFC | 89 | 89 |  |  | 1995-11-01 | 1996-11-01 | 1997-05-01 |  | 1998-12-01 | 2002-09-01 | 1071575 | -13558 | 1058017 | 1058016.79 | 100% | 0.21 | 0 |  | 139305 | -1981 | 137324 | 0 | 0 | FIN
CLO | UNIDO | Preparation of an investment project in recovery and recycling sector | Individual | ASP | SYR | REF | 18 | PRP | 12 | A | I |  | 0 | 0 |  |  | 1995-11-01 |  | 1996-01-01 |  |  | 2001-07-01 | 15000 | -15000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 1950 | -1950 | 0 | 0 | 0 | CLO |  |  | 1999-12-01
FIN | UNEP | Assistance for formulation of a refrigerant management plan | RMP | ASP | SYR | REF | 23 | PRP | 28 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1998-11-01 |  | 1999-10-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at Ammar Industrial Establishment | Individual | ASP | SYR | REF | 26 | INV | 33 | A | I | CFC | 56 | 56 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2001-01-01 | 2003-05-01 | 331080 | -222 | 330858 | 330858 | 100% | 0 | 0 | 0 | 43040.4 | -28.86 | 43011.54 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a in the manufacture of domestic and commercial refrigeration equipment and foam sandwich panels at Ahmad Al-Hafez Al-Waha Refrigerator Co. | Individual | ASP | SYR | REF | 26 | INV | 38 | A | I | CFC | 28.2 | 28.2 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2001-01-01 | 2003-05-01 | 330486 | 0 | 330486 | 330486 | 100% | 0 | 0 | 0 | 42963.18 | 0 | 42963.18 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of domestic refrigerators at El-Effendi Refrigerator Plant | Individual | ASP | SYR | REF | 26 | INV | 39 | A | I | CFC | 13.3 | 13.3 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2003-08-01 | 2007-01-01 | 182802 | -25050 | 157752 | 157752 | 100% | 0 | 0 | 0 | 23764.26 | -3256.46 | 20507.7956 | 0.0044 | 0 | Completed in 2003. Financially completed in 2007. |  | 1998 |  | Investment
FIN | France | Project preparation in the commercial refrigeration sector |  | ASP | SYR | REF | 26 | PRP | 35 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-02-01 | 1999-12-01 |  | 1999-09-01 | 1999-12-01 | 25000 | -8828 | 16172 | 16172 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Préparation achevé
FIN | France | Technical assistance in the air-conditioning sector |  | ASP | SYR | REF | 26 | TAS | 37 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-02-01 | 1999-12-01 |  | 1999-09-01 | 1999-12-01 | 30000 | -4018 | 25982 | 25982 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Préparation achevé
FIN | UNIDO | Project preparation of investment projects in the domestic refrigeration sector | Individual | ASP | SYR | REF | 27 | PRP | 40 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-05-01 | 1999-12-01 |  | 2001-02-01 | 2002-09-01 | 20000 | -2856 | 17144 | 17143.74 | 100% | 0.26 | 0 |  | 2600 | -375 | 2225 | 0 | 0 | FIN
FIN | UNDP | Preparation of four projects in the commercial refrigeration subsector | Individual | ASP | SYR | REF | 27 | PRP | 41 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-12-01 | 2001-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1999 |  | Investment
FIN | UNDP | Preparation of three projects in the domestic refrigeration subsector | Individual | ASP | SYR | REF | 27 | PRP | 43 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 2000-12-01 | 2004-01-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 2000. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a in the production of refrigerators and freezers at Golden Penguin Co. | Individual | ASP | SYR | REF | 28 | INV | 45 | A | I | CFC | 18.4 | 18.4 |  |  | 1999-07-01 | 2000-07-01 | 2001-02-01 |  | 2001-12-01 | 2002-12-01 | 247481 | -52260 | 195221 | 195221.44 | 100% | -0.44 | 0 |  | 32173 | -6834 | 25339 | 0 | 0 | FIN
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Al-Ihsan Co. | Individual | ASP | SYR | REF | 28 | INV | 46 | A | I | CFC | 37.4 | 37.4 | 0 | 0 | 1999-07-01 | 2000-01-01 | 2002-02-01 |  | 2001-01-01 | 2003-05-01 | 497250 | -16958 | 480292 | 480292 | 100% | 0 | 0 | 0 | 64642.5 | -2204.54 | 62437.96 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a in the production of refrigerators and freezers at Alaman Co. | Individual | ASP | SYR | REF | 28 | INV | 60 | A | I | CFC | 15.9 | 15.9 |  |  | 1999-07-01 | 2000-07-01 | 2001-02-01 |  | 2001-12-01 | 2002-12-01 | 215910 | -36884 | 179026 | 179026.39 | 100% | -0.39 | 0 |  | 28068 | -4832 | 23237 | -1 | 0 | FIN
FIN | France | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Sarkisian Refrigerators |  | ASP | SYR | REF | 29 | INV | 48 | A | I | CFC | 3.8 |  | 0 |  | 1999-11-01 | 2007-03-01 | 2002-12-01 |  | 2007-12-01 | 2011-05-01 | 57783 | 0 | 57783 | 57783 | 100% | 0 |  | 0 | 2889 | 0 | 2889 | 0 |  | Project completed.
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigerarion equipment at seven enterprises | Individual | ASP | SYR | REF | 29 | INV | 52 | A | I | CFC | 51.9 | 51.9 | 0 | 0 | 1999-11-01 | 2000-12-01 | 2002-12-01 |  | 2003-08-01 | 2005-09-01 | 743419 | -20056 | 723363 | 723363 | 100% | 0 | 0 | 0 | 91776.09 | -2206.07 | 89570.02 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 1999 |  | Investment
CLO | France | Conversion from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Shoukairi and Co. |  | ASP | SYR | REF | 29 | INV | 53 | A | I | CFC | 2.5 |  | 0 |  | 1999-11-01 |  | 2002-12-01 |  |  | 2008-07-01 | 33359 | -33359 | 0 | 0 |  | 0 |  | 0 | 1668 | -1668 | 0 | 0 |  | Project cancelled (Decision 55/4)
FIN | France | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Bashar Refrigerators |  | ASP | SYR | REF | 29 | INV | 54 | A | I | CFC | 3.2 | 3.2 | 0 |  | 1999-11-01 | 2005-02-01 | 2002-12-01 |  | 2005-02-01 | 2005-10-01 | 49113 | -1615 | 47498 | 47498 | 100% | 0 |  | 0 | 2456 | -81 | 2375 | 0 |  | Project completed.
FIN | France | CFC emission reduction in central air conditioning |  | ASP | SYR | REF | 29 | INV | 56 | A | I | CFC | 0.9 |  | 0 |  | 1999-11-01 | 2006-09-01 | 2002-06-01 |  | 2006-12-01 | 2009-08-01 | 143000 | -36617 | 106383 | 106383 | 100% | 0 |  | 0 | 7150 | -1831 | 5319 | 0 |  | Project completed.
FIN | UNEP | Implementation of the RMP: assistance for the establishment of regulations and legislation | Individual | ASP | SYR | REF | 29 | TAS | 51 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2004-01-01 | 2001-06-01 |  | 2002-06-01 | 2007-01-01 | 25500 | -10000 | 15500 | 15500 | 100% | 0 | 0 |  | 3315 | -1300 | 2015 | 0 | 0
FIN | UNEP | Implementation of the RMP: training programme for custom officials | Individual | ASP | SYR | REF | 29 | TRA | 47 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2004-01-01 | 2001-06-01 |  | 2009-12-01 | 2014-05-01 | 72600 | 0 | 72600 | 72600 | 100% | 0 | 0 |  | 9438 | 0 | 9438 | 0 | 0 |  |  |  | 2002-12-01
FIN | UNEP | Implementation of the RMP: training for trainers and refrigeration technician on good service practices | Individual | ASP | SYR | REF | 29 | TRA | 49 | A | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2004-01-01 | 2002-12-01 |  | 2009-12-01 | 2014-05-01 | 201300 | -56100 | 145200 | 145200 | 100% | 0 | 0 |  | 26169 | -7292.78 | 18876.22 | 0 | 0
FIN | UNDP | Preparation of 4 projects in the commercial refrigeration subsector | Individual | ASP | SYR | REF | 30 | PRP | 58 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-12-01 | 2003-01-01 | 20000 | -4385 | 15615 | 15615 | 100% | 0 | 0 | 0 | 2600 | -570.05 | 2029.95 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | Germany | Implementation of the RMP: national recovery and recycling network | Individual | ASP | SYR | REF | 30 | TAS | 59 | A | I | CFC | 120 | 120 | 0 |  | 2000-03-01 | 2000-11-01 | 2002-04-01 |  | 2008-05-01 | 2009-12-01 | 742146 | 0 | 742146 | 742146 | 100% | 0 | 0 | 0 | 96479 | 0 | 96479 | 0 | 0 | All activities which were planned for 2007 (report, guide book version) were finalized and remaining project funds were allocated for additional refrigeration equipment. The project activities are completed and PCR was submitted to MLF in 2009.
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Al-Wattar Home Appliances Co. | Individual | ASP | SYR | REF | 31 | INV | 64 | A | I | CFC | 18.9 | 18.9 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2002-05-01 | 2004-01-01 | 235860 | 0 | 235860 | 235860 | 100% | 0 | 0 | 0 | 30661.8 | 0 | 30661.8 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Assalam Refrigerator Co. | Individual | ASP | SYR | REF | 31 | INV | 65 | A | I | CFC | 10.8 | 10.8 | 0 | 0 | 2000-07-01 | 2001-07-01 | 2003-08-01 |  | 2003-08-01 | 2005-10-01 | 144309 | 0 | 144309 | 144309 | 100% | 0 | 0 | 0 | 18760.17 | 0 | 18760.17 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Alfa Refrigerators Co. | Individual | ASP | SYR | REF | 31 | INV | 66 | A | I | CFC | 8.7 | 8.7 | 0 | 0 | 2000-07-01 | 2000-12-01 | 2003-08-01 |  | 2003-08-01 | 2007-03-01 | 114461 | -2201 | 112260 | 112260 | 100% | 0 | 0 | 0 | 14879.93 | -286.13 | 14593.7987 | 0.0013 | 0 | Completed in 2003. Financially completed in 2007. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of domestic and commercial refrigeration equipment at Dolphin Refrigerators | Individual | ASP | SYR | REF | 31 | INV | 67 | A | I | CFC | 8.4 | 8.4 | 0 | 0 | 2000-07-01 | 2001-07-01 | 2003-08-01 |  | 2003-08-01 | 2005-10-01 | 113045 | 0 | 113045 | 113045 | 100% | 0 | 0 | 0 | 14695.85 | 0 | 14695.85 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Al-Raed Refrigeration | Individual | ASP | SYR | REF | 32 | INV | 69 | A | I | CFC | 13.9 | 13.9 | 0 | 0 | 2000-12-01 | 2002-03-01 | 2004-01-01 |  | 2003-09-01 | 2005-11-01 | 211800 | 0 | 211800 | 211800 | 100% | 0 | 0 | 0 | 27534 | 0 | 27534 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2000 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Refrigeration House Co. | Individual | ASP | SYR | REF | 34 | INV | 79 | A | I | CFC | 17.5 | 17.5 | 0 | 0 | 2001-07-01 | 2002-11-01 | 2004-08-01 |  | 2003-09-01 | 2007-01-01 | 253653 | 0 | 253653 | 253653 | 100% | 0 | 0 | 0 | 32974.89 | 0 | 32974.89 | 0 | 0 | Completed in 2003. Financially completed in 2007. |  | 2001 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Al-Saad Refrigeration | Individual | ASP | SYR | REF | 35 | INV | 81 | A | I | CFC | 20.1 | 20.1 | 0 | 0 | 2001-12-01 | 2004-07-01 | 2004-07-01 |  | 2004-12-01 | 2006-06-01 | 166323 | -8826 | 157497 | 157497 | 100% | 0 | 0 | 0 | 21621.99 | -1147 | 20474.99 | 0 | 0 | Completed in 2004. Financially completed in 2006. |  | 2001 |  | Investment
CLO | UNIDO | Preparation of an investment project in the domestic refrigeration sector | Individual | ASP | SYR | REF | 36 | PRP | 83 | A | I |  | 0 | 0 |  |  | 2002-03-01 |  | 2003-04-01 |  |  | 2003-05-01 | 15000 | -15000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 1950 | -1950 | 0 | 0 | 0 | CLO |  |  |  | INV
FIN | UNDP | Project preparation in the manufacturing refrigeration sector (terminal phase-out) | Individual | ASP | SYR | REF | 36 | PRP | 84 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2002-09-01 | 2007-03-01 | 20000 | -6865 | 13135 | 13135 | 100% | 0 | 0 | 0 | 2600 | -892.45 | 1707.55 | 0 | 0 | Completed in 2002. Financially completed in 2007. |  | 2002 |  | Investment
FIN | UNDP | Sector phase out plan for CFCs in the refrigeration manufacturing sector (except domestic refrigeration) | Individual | ASP | SYR | REF | 38 | INV | 86 | A | I | CFC | 246.2 | 246.2 | 0 | 0 | 2002-11-01 | 2003-02-01 | 2006-12-01 |  | 2009-12-01 | 2013-05-01 | 1665188 | -565630.98 | 1099557.02 | 1099557 | 100% | 0.02 | 0 | 0 | 191422 | -65022.22 | 126399.7819 | -0.0019009 | 0 | Financially completed in 2013. |  | 2002 |  | Investment
FIN | UNIDO | Plan for elimination of CFCs in the refrigeration manufacturing sector (domestic refrigeration) | Individual | ASP | SYR | REF | 38 | INV | 87 | A | I | CFC | 51 | 51 |  |  | 2002-11-01 | 2003-06-01 | 2004-11-01 |  | 2006-12-01 | 2007-12-01 | 353100 | -527 | 352573 | 352573.39 | 100% | -0.39 | 0 |  | 40590 | -61 | 40529 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Demonstration project on the replacement of CFC centrifugal chillers | Individual | ASP | SYR | REF | 47 | DEM | 93 | A | I |  | 0 | 0 |  |  | 2005-11-01 | 2006-07-01 | 2008-12-01 |  | 2013-12-01 | 2013-12-01 | 585961 | -210532 | 375429 | 375428.74 | 100% | 0.26 | 0 |  | 43947 | -15790 | 28157 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation for HCFC phase-out investment activities (refrigeration manufacturing sector) | Individual | ASP | SYR | REF | 58 | PRP | 100 | A | I |  | 0 | 0 |  |  | 2009-07-01 | 2009-11-01 | 2010-07-31 |  | 2010-12-01 | 2011-12-01 | 60000 | -1229 | 58771 | 58770.71 | 100% | 0.29 | 0 |  | 4500 | -92 | 4408 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | Phase-out of HCFC-22 and HCFC-141b from the manufacture of unitary air-conditioning equipment and rigid polyurethane insulation panels at Al Hafez Group | Individual | ASP | SYR | REF | 62 | INV | 103 | A | I | HCFC | 12.9 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2013-06-30 | 2019-03-01 |  |  | 1465361 | 0 | 1465361 | 404013.04 | 27.57% | 1061347.96 | 0 | 5000 | 109902 | 0 | 30301 | 79601 | 0 | - The visit of Al Hafez to UNIDO Vienna was organized and a list of requirements was drafted to further prepare detailed TOR by UNIDO. Was there any delay during the reporting year? Yes Any recurring problem? Yes - Security situation Any impact on project completion date: Yes Any action required by Executive Committee? No | - TOR in progress. Actions towards next goal: Procurement of equipment to be initiated in first semester 2017. Was there any delay during the reporting year? Yes Any recurring problem? Yes - Security situation Any impact on project completion date: Yes Any action required by Executive Committee? No |  |  | INV |  | 12 months delays
FIN | UNEP | Country programme preparation | Individual | ASP | SYR | SEV | 04 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-10-01 | 1992-09-01 |  | 1993-11-01 | 1993-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0
FIN | UNIDO | Preparatory assistance for phase out of ODS in the domestic refrigeration industry | Individual | ASP | SYR | SEV | 09 | PRP | 02 | A | I |  | 0 | 0 |  |  | 1993-03-01 | 1993-11-01 | 1993-09-01 |  | 1994-12-01 | 1996-05-01 | 35000 | -5 | 34995 | 34995 | 100% | 0 | 0 |  | 4550 | -8 | 4542 | 0 | 0 | FIN
FIN | UNIDO | Support to strengthening the General Commission for Environmental Affairs to implement Montreal Protocol related activities | Individual | ASP | SYR | SEV | 10 | INS | 03 | N | I |  | 0 | 0 |  |  | 1993-06-01 | 1994-04-01 | 1996-06-01 |  | 2002-11-01 | 2003-06-01 | 235180 | -15273 | 219907 | 219907.1 | 100% | -0.1 | 0 |  | 30573 | -2030 | 28543 | 0 | 0 | FIN |  |  | 1999-10-01 | NON-INV
FIN | UNIDO | Renewal of institutional strengthening (Phase II) | Individual | ASP | SYR | SEV | 33 | INS | 75 | N | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-12-01 | 2003-04-01 |  | 2006-12-01 | 2009-09-01 | 195000 | -3117 | 191883 | 191882.56 | 100% | 0.44 | 0 |  | 25350 | -405 | 24945 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Extension of institutional strengthening: phase III | Individual | ASP | SYR | SEV | 45 | INS | 91 | N | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-09-01 | 2007-04-01 |  | 2009-12-01 | 2013-12-01 | 203823 | -1926 | 201897 | 201896.98 | 100% | 0.02 | 0 |  | 15287 | -145 | 15142 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNDP | Assistance to carry out an HCFC survey | Individual | ASP | SYR | SEV | 45 | TAS | 90 | A | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-04-01 | 2006-12-01 |  | 2008-08-01 | 2009-12-01 | 45872 | -6848 | 39024 | 39024 | 100% | 0 | 0 | 0 | 4128 | -616.25 | 3511.7517 | -0.0017 | 0 | Completed in 2008. Financially completed in 2009. |  | 2005 |  | Non-Investment
ONG | UNIDO | Extension of institutional strengthening (phase IV) | Individual | ASP | SYR | SEV | 58 | INS | 101 | N | I |  | 0 | 0 |  |  | 2009-07-01 | 2010-12-01 | 2010-12-01 | 2019-06-01 |  |  | 152867.25 | 0 | 152867.25 | 94392.01 | 61.75% | 58475.24 | 3258.85 | 1 | 11465 | 0 | 7079 | 4386 | 244.4137 | Activities implementation was restricted by the security situation in the country. In spite of difficulties, NOU has been maintained, data collection and consumption monitoring are ongoing. NC contracts and awareness activities cannot be executed due to security level and travel restrictions in the country. Project completion is pending on the security situation in the country. | Activities implementation was restricted by the security situation in the country. In spite of difficulties, NOU has been maintained, data collection and consumption monitoring are ongoing. NC contracts and awareness activities cannot be executed due to security level and travel restrictions in the country. Project completion is pending on the security situation in the country. |  |  | NON-INV
ONG | UNIDO | Extension of institutional strengthening (phase V: 1/2015- 12/2016) | Individual | ASP | SYR | SEV | 73 | INS | 104 | N | I |  | 0 | 0 |  |  | 2014-11-01 |  | 2016-12-31 | 2019-12-01 |  |  | 203823 | 0 | 203823 | 0 | 0% | 203823 | 0 | 1 | 14268 | 0 | 0 | 14268 | 0 | Activities implementation was restricted by the security situation in the country. In spite of difficulties, NOU has been maintained, data collection and consumption monitoring are ongoing. NC contracts and awareness activities cannot be executed due to security level and travel restrictions in the country. Project completion is pending on the security situation in the country. | Activities implementation was restricted by the security situation in the country. In spite of difficulties, NOU has been maintained, data collection and consumption monitoring are ongoing. NC contracts and awareness activities cannot be executed due to security level and travel restrictions in the country. Project completion is pending on the security situation in the country. |  |  | NON-INV |  | To request the submission of additional status report to the 79th meeting to monitor the low disbursement rates of approved funds.
FIN | UNDP | Safety and technical assistance programme to manufacturers of aerosol products | Individual | ASP | THA | ARS | 15 | TAS | 38 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-12-01 | 1995-12-01 |  | 1998-08-01 | 2002-03-01 | 127000 | -20 | 126980 | 126980 | 100% | 0 | 0 | 0 | 16510 | -3 | 16507 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1994 |  | Non-Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of aerosol products at Packserv Co. Ltd. | Individual | ASP | THA | ARS | 17 | INV | 45 | A | D | CFC | 155 | 155 | 0 | 0 | 1995-07-01 | 1995-11-01 | 1996-01-01 |  | 1995-11-01 | 1998-12-01 | 474705 | -1221 | 473484 | 473484 | 100% | 0 | 0 | 0 | 61711.65 | -159 | 61552.65 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of aerosol products at Sanit & Sons Co. Ltd. | Individual | ASP | THA | ARS | 17 | INV | 46 | A | I | CFC | 194 | 194 | 0 | 0 | 1995-07-01 | 1995-12-01 | 1996-12-01 |  | 2000-04-01 | 2002-03-01 | 582100 | 0 | 582100 | 582100 | 100% | 0 | 0 | 0 | 75673 | 0 | 75673 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1995 | 1999-09-01 | Investment
FIN | UNDP | P-Tech Manuchem Co. Ltd. conversion | Individual | ASP | THA | ARS | 23 | INV | 83 | A | I | CFC | 37.3 | 37.3 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1998-12-01 |  | 2000-07-01 | 2001-12-01 | 115830 | -8432 | 107398 | 107398 | 100% | 0 | 0 | 0 | 15057.9 | -1096 | 13961.9 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | J.M.T. Laboratories Co. Ltd. conversion | Individual | ASP | THA | ARS | 23 | INV | 84 | A | I | CFC | 36.6 | 36.6 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1998-12-01 |  | 2000-07-01 | 2003-11-01 | 127920 | -5082 | 122838 | 122838 | 100% | 0 | 0 | 0 | 16629.6 | -660.66 | 15968.94 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1997 |  | Investment
FIN | UNDP | Project preparation for 4 projects in the aerosol sector | Individual | ASP | THA | ARS | 24 | PRP | 89 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Standard Manufacturing Co. Ltd. conversion | Individual | ASP | THA | ARS | 25 | INV | 94 | A | I | CFC | 41 | 41 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 2000-07-01 | 2001-12-01 | 138380 | -5000 | 133380 | 133380 | 100% | 0 | 0 | 0 | 17989.4 | -650 | 17339.4 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Mary Manufacturing Co. Ltd. conversion | Individual | ASP | THA | ARS | 25 | INV | 96 | A | I | CFC | 40 | 40 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 2000-07-01 | 2001-12-01 | 136400 | -4295 | 132105 | 132105 | 100% | 0 | 0 | 0 | 17732 | -558 | 17174 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
FIN | IBRD | Replacement of CFC-11 with HCFC-141b as a foam blowing agent at Technic Foam, Ltd. | Individual | ASP | THA | FOA | 10 | INV | 23 | N | I | CFC | 50 | 50 | 0 | 0 | 1993-06-01 | 1999-09-01 | 1993-12-01 |  | 2000-01-01 | 2000-06-01 | 174000 | 0 | 174000 | 174000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR approved by the WB in Jun/2000. |  |  | 1999-08-01 | INV | 0
CLO | UNDP | Elimination of CFC-114 in the manufacture of extruded polystyrene foam sheet and profiles at Thermaflex Insulation Asia Co. Ltd. | Individual | ASP | THA | FOA | 11 | INV | 26 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 |  | 1995-07-01 |  |  | 2001-07-01 | 220000 | -220000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 28600 | -28600.08 | 0 | -0.08 | 0 | Canceled in 1995. Financially Completed in 2001. |  | 1993 |  | Investment
FIN | UNDP | Elimination of the use of CFC-12 and CFC-114 in the manufacture of extruded low density polyethylene foam sheet at Mic-Cell Co. Ltd. | Individual | ASP | THA | FOA | 12 | INV | 27 | A | I | CFC | 44 | 44 | 0 | 0 | 1994-03-01 | 1995-11-01 | 1995-03-01 |  | 1998-11-01 | 2001-12-01 | 339500 | -1725.9 | 337774.1 | 337774 | 100% | 0.1 | 0 | 0 | 44135 | -224.37 | 43910.62 | 0.01 | 0 | Completed in 1998. Financially completed in 2001. |  | 1994 |  | Investment
FIN | UNDP | Elimination of the use of CFC in the manufacture of laminated rigid polyurethane foam insulation panels at Modular Compound Co. Ltd. | Individual | ASP | THA | FOA | 12 | INV | 29 | A | I | CFC | 30 | 30 | 0 | 0 | 1994-03-01 | 1995-11-01 | 1995-03-01 |  | 1996-12-01 | 2000-12-01 | 508000 | -3349 | 504651 | 504651 | 100% | 0 | 0 | 0 | 66040 | -435.37 | 65604.63 | 0 | 0 | Completed in 1996. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of the use of CFC in the manufacture of extruded polystyrene foam sheet at 2 companies (Tahi Poly Seal Material Industries Co. Ltd, and Food Box Co. Ltd.): Phase I | Individual | ASP | THA | FOA | 12 | INV | 30 | A | R | CFC | 100 | 100 | 0 | 0 | 1994-03-01 | 1995-02-01 | 1995-03-01 |  | 1995-02-01 | 2000-12-01 | 455000 | -2639 | 452361 | 452361 | 100% | 0 | 0 | 0 | 59150 | -343 | 58807 | 0 | 0 | Completed in 1995. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Phase-out of the use of CFC-11 in the manufacture of laminated rigid polyurethane foam for insulation panels at Henger Panel | Individual | ASP | THA | FOA | 12 | INV | 31 | A | I | CFC | 15 | 15 | 0 | 0 | 1994-03-01 | 1995-11-01 | 1995-03-01 |  | 1998-06-01 | 2000-12-01 | 257500 | -509 | 256991 | 256991 | 100% | 0 | 0 | 0 | 33475 | -66.17 | 33408.83 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of the use of CFC in the manufacture of flexible polyurethane foam at Lucky Group | Individual | ASP | THA | FOA | 13 | INV | 35 | A | I | CFC | 187 | 187 | 0 | 0 | 1994-07-01 | 1997-12-01 | 1995-07-01 |  | 1999-11-01 | 2003-07-01 | 605000 | -1836 | 603164 | 603164 | 100% | 0 | 0 | 0 | 78650 | -238.68 | 78411.32 | 0 | 0 | Completed in 1999. Financially completed in 2003. |  | 1994 | 1999-06-01 | Investment
FIN | UNDP | Elimination of the use of CFC in the manufacture of extruded polystyrene foam sheet at Ponsri | Individual | ASP | THA | FOA | 13 | INV | 36 | A | I | CFC | 125 | 125 | 0 | 0 | 1994-07-01 | 1996-06-01 | 1995-07-01 |  | 1996-06-01 | 2002-03-01 | 340000 | -6035 | 333965 | 333965 | 100% | 0 | 0 | 0 | 44200 | -784.26 | 43415.74 | 0 | 0 | Completed in 1996. Financially completed in 2002. |  | 1994 |  | Investment
FIN | UNDP | Elimination of the use of CFC in the manufacture of flexible PUF cold cured mouldings, integral skin mouldings and rigid PUF articles at Thai Union PU Co. Ltd. | Individual | ASP | THA | FOA | 15 | INV | 41 | A | I | CFC | 45 | 45 | 0 | 0 | 1994-12-01 | 1995-12-01 | 1995-11-01 |  | 1996-12-01 | 2000-12-01 | 525000 | -72931 | 452069 | 452069 | 100% | 0 | 0 | 0 | 68250 | -9481.03 | 58768.97 | 0 | 0 | Completed in 1996. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of the use of CFC in the manufacture of flexible PUF slabstock and cold cured mouldings st Somboon Paisarn 85 Company Ltd. | Individual | ASP | THA | FOA | 15 | INV | 42 | A | I | CFC | 100 | 100 | 0 | 0 | 1994-12-01 | 1997-04-01 | 1995-11-01 |  | 1998-11-01 | 2000-12-01 | 225000 | -5000 | 220000 | 220000 | 100% | 0 | 0 | 0 | 29250 | -650 | 28600 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of the use of CFCs in the manufacture of flexible PUF slabstock at Karn Yang Yeen Yong Industry Ltd. | Individual | ASP | THA | FOA | 15 | INV | 44 | A | I | CFC | 110 | 110 | 0 | 0 | 1994-12-01 | 1997-09-01 | 1995-11-01 |  | 1999-04-01 | 2000-12-01 | 170000 | 0 | 170000 | 170000 | 100% | 0 | 0 | 0 | 22100 | 0 | 22100 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1994 | 1999-06-01 | Investment
FIN | UNDP | Phase out of the use of CFCs in the manufacture of rigid PUF foam for thermoware at Krieng Thavorn Containers Co. Ltd. | Individual | ASP | THA | FOA | 18 | INV | 47 | A | I | CFC | 65 | 65 | 0 | 0 | 1995-11-01 | 1997-12-01 | 1997-05-01 |  | 1997-12-01 | 2000-07-01 | 430000 | -32154 | 397846 | 397846 | 100% | 0 | 0 | 0 | 55900 | -4180.02 | 51719.98 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Phase out of the use of CFCs in the manufacture of rigid PUR foam for thermoware at Raengwa Standard Industry Co. Ltd. | Individual | ASP | THA | FOA | 19 | INV | 51 | A | I | CFC | 25 | 25 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1998-01-01 | 2000-12-01 | 181500 | -796 | 180704 | 180704 | 100% | 0 | 0 | 0 | 23595 | -103.48 | 23491.52 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1996 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at Dacron Trade Co. | Individual | ASP | THA | FOA | 20 | INV | 55 | A | I | CFC | 47.6 | 47.6 | 0 | 0 | 1996-10-01 | 1997-12-01 | 1998-09-01 |  | 1998-11-01 | 2001-12-01 | 277800 | -19551 | 258249 | 258249 | 100% | 0 | 0 | 0 | 36114 | -2541.63 | 33572.37 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1996 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at Siam Matee | Individual | ASP | THA | FOA | 20 | INV | 56 | A | I | CFC | 33.9 | 33.9 | 0 | 0 | 1996-10-01 | 1997-10-01 | 1998-09-01 |  | 1998-09-01 | 2001-12-01 | 198000 | -13800.8 | 184199.2 | 184199 | 100% | 0.2 | 0 | 0 | 25740 | -1794.1 | 23945.87 | 0.03 | 0 | Completed in 1998. Financially completed in 2001. |  | 1996 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid and integral skin polyurethane foam at Bangkok Foam Group | Individual | ASP | THA | FOA | 22 | INV | 63 | A | I | CFC | 90.6 | 90.6 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-05-01 |  | 2001-12-01 | 2001-12-01 | 480500 | 0 | 480500 | 480500 | 100% | 0 | 0 | 0 | 62465 | 0 | 62465 | 0 | 0 | Completed in 2001. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at Asia Container | Individual | ASP | THA | FOA | 22 | INV | 64 | A | I | CFC | 45 | 45 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1998-11-01 |  | 1999-11-01 | 2000-12-01 | 199000 | 0 | 199000 | 199000 | 100% | 0 | 0 | 0 | 25870 | 0 | 25870 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at Siriphan | Individual | ASP | THA | FOA | 22 | INV | 66 | A | I | CFC | 50 | 50 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1998-09-01 | 2001-12-01 | 215000 | -5001 | 209999 | 209999 | 100% | 0 | 0 | 0 | 27950 | -650.13 | 27299.87 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at Ocean Plastics | Individual | ASP | THA | FOA | 22 | INV | 67 | A | I | CFC | 82 | 82 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 1999-11-01 | 2001-12-01 | 287000 | -16390 | 270610 | 270610 | 100% | 0 | 0 | 0 | 37310 | -2130.7 | 35179.3 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible slabstock polyurethane foam at Chareon Porn | Individual | ASP | THA | FOA | 23 | INV | 68 | A | I | CFC | 15 | 15 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2000-12-01 | 2002-03-01 | 93500 | -29 | 93471 | 93471 | 100% | 0 | 0 | 0 | 12155 | -3.77 | 12151.23 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible slabstock polyurethane foam (boxfoam) at Thai International | Individual | ASP | THA | FOA | 23 | INV | 69 | A | I | CFC | 15 | 15 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-12-01 |  | 2000-12-01 | 2002-03-01 | 93500 | 0 | 93500 | 93500 | 100% | 0 | 0 | 0 | 12155 | 0 | 12155 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of integral skin polyurethane foam at Novochem | Individual | ASP | THA | FOA | 23 | INV | 70 | A | I | CFC | 19.7 | 19.7 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-12-01 |  | 2002-08-01 | 2004-01-01 | 196600 | 0 | 196600 | 196600 | 100% | 0 | 0 | 0 | 25558 | 0 | 25558 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 1997 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane boxfoam at Nun Charoen | Individual | ASP | THA | FOA | 23 | INV | 71 | A | I | CFC | 16.8 | 16.8 | 0 | 0 | 1997-11-01 | 1999-02-01 | 1999-12-01 |  | 1999-11-01 | 2000-12-01 | 105000 | 0 | 105000 | 105000 | 100% | 0 | 0 | 0 | 13650 | 0 | 13650 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1997 |  | Investment
CLO | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (panels) at Alcan Nikkei Thai Aluminum Co. Ltd. | Individual | ASP | THA | FOA | 23 | INV | 72 | N | R |  | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1999-11-01 |  |  | 1999-11-01 | 36500 | -36500 | 0 | 0 | #DIV/0! | 0 | 0 |  | 4745 | -4745 | 0 | 0 | 0 | Project cancelled. |  |  |  | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (containers) at Can Asia Products Co. Ltd. | Individual | ASP | THA | FOA | 23 | INV | 73 | N | I | CFC | 16.8 | 16.8 | 0 | 0 | 1997-11-01 | 1999-08-01 | 1999-11-01 |  | 1999-10-01 | 2000-06-01 | 84300 | 0 | 84300 | 84300 | 100% | 0 | 0 |  | 10959 | 0 | 10959 | 0 | 0 | Project completed. PCR submitted to the WB in May/2000. |  |  |  | INV | 0
FIN | IBRD | Conversion to CFC-free technology in rigid sprayfoam applications at Thermobond Co. Ltd. | Individual | ASP | THA | FOA | 23 | INV | 74 | N | I | CFC | 10.4 | 10.4 | 0 | 0 | 1997-11-01 | 1999-04-01 | 1999-11-01 |  | 1999-07-01 | 2000-04-01 | 81400 | -4613 | 76787 | 76787 | 100% | 0 | 0 |  | 10582 | -599.69 | 9982.31 | 0 | 0 | Project completed. PCR submitted to the WB in Mar/2000. |  |  |  | INV | 0
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (thermoware) at Century Plastics | Individual | ASP | THA | FOA | 23 | INV | 75 | A | D | CFC | 7.3 | 7.3 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1999-12-01 |  | 1998-09-01 | 2001-12-01 | 56750 | -2559.77 | 54190.23 | 54190 | 100% | 0.23 | 0 | 0 | 7377.5 | -332.77 | 7044.7 | 0.03 | 0 | Completed in 1998. Financially completed in 2001. |  | 1997 |  | Investment
FIN | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (thermoware) at Siam Chaicharoen Industry Co. Ltd. | Individual | ASP | THA | FOA | 23 | INV | 76 | N | I | CFC | 11.3 | 11.3 | 0 | 0 | 1997-11-01 | 1999-12-01 | 1999-11-01 |  | 2000-04-01 | 2000-06-01 | 88500 | 0 | 88500 | 88500 | 100% | 0 | 0 |  | 11505 | 0 | 11505 | 0 | 0 | Project completed. PCR submitted to the MLF Secretariat 30 June 2000. |  |  |  | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (thermoware) at General Injection Co. Ltd. | Individual | ASP | THA | FOA | 23 | INV | 77 | N | I | CFC | 15.4 | 15.4 | 0 | 0 | 1997-11-01 | 2000-01-01 | 1999-11-01 |  | 2000-06-01 | 2000-07-01 | 120580 | 0 | 120580 | 120580 | 100% | 0 | 0 |  | 15675 | 0 | 15675 | 0 | 0 | Project Completed. PCR submitted to the WB in Jun/2000. |  |  |  | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (containers) at Viriyakit Plastic Industry Co. Ltd. | Individual | ASP | THA | FOA | 23 | INV | 78 | N | I | CFC | 27.5 | 27.5 | 0 | 0 | 1997-11-01 | 1999-01-01 | 1999-11-01 |  | 1999-02-01 | 1999-06-01 | 142700 | 0 | 142700 | 142700 | 100% | 0 | 0 |  | 18551 | 0 | 18551 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Conversion to CFC-free technology in rigid spray foam applications at P.U. Foam Insulation and Trading Co. Ltd. | Individual | ASP | THA | FOA | 23 | INV | 79 | N | I | CFC | 58.1 | 58.1 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-11-01 |  | 1999-08-01 | 1999-09-01 | 225400 | 0 | 225400 | 225400 | 100% | 0 | 0 |  | 29302 | 0 | 29302 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (containers) at Treathaboon Industry Co. Ltd. | Individual | ASP | THA | FOA | 23 | INV | 86 | N | I | CFC | 22.7 | 22.7 | 0 | 0 | 1997-11-01 | 1999-12-01 | 1999-11-01 |  | 1999-02-01 | 1999-12-01 | 177750 | -20563 | 157187 | 157187 | 100% | 0 | 0 |  | 23108 | -2673.19 | 20434.81 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | UNDP | Project preparation for 3 projects in the foam sector | Individual | ASP | THA | FOA | 24 | PRP | 87 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Phaseout of CFC-11 by conversion to LCD technology (flexible) and water based technology (integral skin) in the manufacture of polyurethane foam at Duriflex | Individual | ASP | THA | FOA | 25 | INV | 90 | A | I | TCA/CFC | 21.2 | 21.2 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 1999-11-01 | 2001-12-01 | 278800 | -285 | 278515 | 278515 | 100% | 0 | 0 | 0 | 36244 | -37.05 | 36206.9456 | 0.0044 | 0 | Completed in 1999. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Conversion to low index/additive technology and methylene chloride in the manufacture of flexible polyurethane boxfoam at City Foam Co., Ltd. | Individual | ASP | THA | FOA | 25 | INV | 91 | A | I | CFC | 42 | 42 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 1999-11-01 | 2000-12-01 | 156100 | 0 | 156100 | 156100 | 100% | 0 | 0 | 0 | 20293 | 0 | 20293 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1998 |  | Investment
FIN | IBRD | Conversion to CFC-free technology in the manufacture of cold store polyurethane panels at Somerville | Individual | ASP | THA | FOA | 25 | INV | 95 | N | I | CFC | 18.1 | 18.13 | 0 | 0 | 1998-07-01 | 2000-04-01 | 2001-08-01 |  | 2000-03-01 | 2000-04-01 | 141957 | -21957 | 120000 | 120000 | 100% | 0 | 0 |  | 18454.41 | -2854.41 | 15600 | 0 | 0 | Project completed. PCR submitted to the WB in Mar/2000. |  |  |  | INV | 0
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Suwan Polymer L.P. | Individual | ASP | THA | FOA | 26 | INV | 100 | A | I | CFC | 58 | 58 | 0 | 0 | 1998-11-01 | 1999-10-01 | 2000-12-01 |  | 2000-10-01 | 2002-03-01 | 298370 | -1026 | 297344 | 297344 | 100% | 0 | 0 | 0 | 38788.1 | -133.38 | 38654.72 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Sahakij Comos L.P. | Individual | ASP | THA | FOA | 26 | INV | 101 | A | I | CFC | 48.7 | 48.7 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2000-10-01 | 2002-03-01 | 255850 | -11488 | 244362 | 244362 | 100% | 0 | 0 | 0 | 33260.5 | -1493.44 | 31767.06 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to methylene chloride/LIA technology in the manufacture of flexible polyurethane boxfoam at P. Chongcharoen | Individual | ASP | THA | FOA | 26 | INV | 102 | A | I | CFC | 24 | 24 | 0 | 0 | 1998-11-01 | 1998-12-01 | 2000-12-01 |  | 2000-12-01 | 2002-03-01 | 130500 | -256 | 130244 | 130244 | 100% | 0 | 0 | 0 | 16965 | -33.28 | 16931.72 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Lohr Trade and Consulting PTS Ltd. | Individual | ASP | THA | FOA | 26 | INV | 103 | A | I | CFC | 13.6 | 13.6 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2000-12-01 |  | 1999-11-01 | 2001-12-01 | 93210 | -137 | 93073 | 93073 | 100% | 0 | 0 | 0 | 12117.3 | -17.81 | 12099.487 | 0.003 | 0 | Completed in 1999. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to water based and HCFC-141b technology in the manufacture of polyurethane foam (flexible molded, integral skin) at World Plaster/Europlan Furniture Co. | Individual | ASP | THA | FOA | 26 | INV | 105 | A | I | CFC | 25.2 | 25.2 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2000-12-01 |  | 1999-11-01 | 2001-12-01 | 135800 | -5000 | 130800 | 130800 | 100% | 0 | 0 | 0 | 17654 | -650 | 17004 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Ohm Intertrade L.P. | Individual | ASP | THA | FOA | 26 | INV | 106 | A | I | CFC | 19 | 19 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2000-12-01 |  | 1999-11-01 | 2002-03-01 | 146350 | -6393 | 139957 | 139957 | 100% | 0 | 0 | 0 | 19025.5 | -831.09 | 18194.41 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to water based and HCFC-141b technology in the manufacture of polyurethane foam at J.S. Industry Co. Ltd. | Individual | ASP | THA | FOA | 26 | INV | 98 | A | I | CFC | 93.2 | 93.2 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2000-12-01 |  | 2000-10-01 | 2002-03-01 | 418800 | -15974 | 402826 | 402826 | 100% | 0 | 0 | 0 | 54444 | -2076.62 | 52367.38 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1998 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Urethane | Individual | ASP | THA | FOA | 26 | INV | 99 | A | I | CFC | 17.5 | 17.5 | 0 | 0 | 1998-11-01 | 1999-07-01 | 2000-12-01 |  | 2001-12-01 | 2004-01-01 | 98645 | 0 | 98645 | 98645 | 100% | 0 | 0 | 0 | 12823.85 | 0 | 12823.85 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 1998 |  | Investment
FIN | IBRD | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at P.E. Containers Supply Co. Ltd. | Individual | ASP | THA | FOA | 27 | INV | 108 | N | I | CFC | 29 | 29 | 0 | 0 | 1999-03-01 | 2000-06-01 | 1999-04-01 |  | 2000-09-01 | 2000-10-01 | 181883 | -8750 | 173133 | 173133 | 100% | 0 | 0 |  | 23644.79 | -1137.5 | 22507.29 | 0 | 0 | Project completed. PCR submitted to the MLF Secretariat January 2001. |  |  |  | INV | 0
CLO | IBRD | Conversion from CFC-11 to water blown and HCFC-141b technology in the manufacture of rigid foam (spray) at Bangkok Integrated Trading Co. | Individual | ASP | THA | FOA | 27 | INV | 109 | N | I |  | 0 | 0 | 0 | 0 | 1999-03-01 |  | 1999-04-01 |  |  | 2001-12-31 | 117923 | -117923 | 0 | 0 | #DIV/0! | 0 | 0 |  | 15329.99 | -15329.99 | 0 | 0 | 0 | Project cancelled July 2000. |  |  |  | INV | 0
FIN | IBRD | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Siam M.P. Co. Ltd. | Individual | ASP | THA | FOA | 27 | INV | 110 | N | I | CFC | 25.4 | 25.4 | 0 | 0 | 1999-03-01 | 2000-09-01 | 1999-04-01 |  | 2000-08-01 | 2000-10-01 | 164366 | -12500 | 151866 | 151866 | 100% | 0 | 0 |  | 21367.58 | -1625 | 19742.58 | 0 | 0 | Project completed. PCR submitted to the MLF Secretariat Nov. 2000. |  |  |  | INV | 0
FIN | IBRD | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Siam Steel International PLC | Individual | ASP | THA | FOA | 27 | INV | 111 | N | I | CFC | 27.1 | 27.1 | 0 | 0 | 1999-03-01 | 2001-08-01 | 2001-03-01 |  | 2001-05-01 | 2002-03-01 | 196981 | -200 | 196781 | 196781 | 100% | 0 | 0 |  | 25607.53 | -26 | 25581.53 | 0 | 0 | Project physically and financially completed. DIW has endorsed destruction of equipment and disposal plan. PCR sent to ENV/WB. |  |  | 2001-03-01 | INV | 0
FIN | IBRD | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid foam at Willich Sales & Contracting Co. Ltd. | Individual | ASP | THA | FOA | 27 | INV | 112 | N | I | CFC | 16.05 | 16.05 | 0 | 0 | 1999-03-01 | 2001-03-01 | 1999-04-01 |  | 2001-08-01 | 2002-11-01 | 58630 | 0 | 58630 | 58630 | 100% | 0 | 0 |  | 7621.9 | 0 | 7621.9 | 0 | 0 | Project physically and financially completed. DIW has endorsed destruction of equipment and disposal plan. PCR sent to ENV/WB. |  |  | 2000-06-01 | INV | 0
FIN | IBRD | Conversion from CFC-11 to water based and HCFC-141b technology in the manufacture of integral skin polyurethane foam and rigid moulded foam at Jennings Co. Ltd. | Individual | ASP | THA | FOA | 27 | INV | 113 | N | I | CFC | 14.35 | 14.35 | 0 | 0 | 1999-03-01 | 2000-05-01 | 2001-04-01 |  | 2001-02-01 | 2001-10-01 | 125249 | 0 | 125249 | 125249 | 100% | 0 | 0 |  | 16282.37 | 0 | 16282.37 | 0 | 0 | Project completed. PCR submitted to the WB in Sep. 01 |  |  |  | INV | 0
FIN | IBRD | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Plastmate Industry Co. Ltd. | Individual | ASP | THA | FOA | 27 | INV | 115 | N | I | CFC | 10.3 | 10.3 | 0 | 0 | 1999-03-01 | 2000-08-01 | 1999-04-01 |  | 2000-11-01 | 2000-11-01 | 80649 | -6500 | 74149 | 74149 | 100% | 0 | 0 |  | 10484.37 | -845 | 9639.37 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | UNDP | Preparation of six projects in general foam subsector | Individual | ASP | THA | FOA | 27 | PRP | 114 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-04-01 | 2000-04-01 |  | 1999-12-01 | 2000-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1999 |  | Investment
FIN | IBRD | Conversion to HCFC-141b technology in the manufacture of commercial refrigerator and display cabinets at Makassan Metal Works | Individual | ASP | THA | FOA | 28 | INV | 116 | N | I | CFC | 9.3 | 9.3 | 0 | 0 | 1999-07-01 | 2001-02-01 | 2002-02-01 |  | 2001-05-01 | 2002-07-01 | 72819 | 0 | 72819 | 72819 | 100% | 0 | 0 |  | 9466.47 | 0 | 9466.47 | 0 | 0 | Project physically and financially completed. DIW has endorsed destruction of equipment and disposal plan. PCR submitted. |  |  | 2004-02-01 | INV | 0
FIN | UNDP | Conversion from CFC-11 to water-based technology in the manufacture of rigid polyurethane foam at Thai Steel Door L.P. | Individual | ASP | THA | FOA | 28 | INV | 117 | A | I | CFC | 10 | 10 | 0 | 0 | 1999-07-01 | 2000-05-01 | 2002-02-01 |  | 2000-11-01 | 2004-01-01 | 78300 | 0 | 78300 | 78300 | 100% | 0 | 0 | 0 | 10179 | 0 | 10179 | 0 | 0 | Completed in 2000. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to low index additive (LIA) technology in the manufacture of flexible polyurethane foam at P.T. Foam Chiengmai L.P. | Individual | ASP | THA | FOA | 28 | INV | 118 | A | I | CFC | 12.7 | 12.7 | 0 | 0 | 1999-07-01 | 2000-01-01 | 2002-02-01 |  | 2000-12-01 | 2002-03-01 | 79120 | 0 | 79120 | 79120 | 100% | 0 | 0 | 0 | 10285.6 | 0 | 10285.6 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1999 |  | Investment
FIN | IBRD | Conversion from CFC-11 to HCFC-141b technology in the manufacture of commercial refrigeration equipment at Arco Industry Co., Ltd | Individual | ASP | THA | FOA | 28 | INV | 130 | N | I | CFC | 16.8 | 16.32 | 0 | 0 | 1999-07-01 | 2001-12-31 | 2002-02-01 |  | 2001-09-01 | 2002-02-01 | 131544 | -3759 | 127785 | 127785 | 100% | 0 | 0 |  | 17100.72 | -488.67 | 16612.05 | 0 | 0 | Project physically and financially completed. DIW has endorsed destruction of equipment and disposal plan. PCR submitted. |  |  | 2004-02-01 | INV | 0
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at S.K. Container Co., Ltd. | Individual | ASP | THA | FOA | 29 | INV | 119 | A | I | CFC | 10 | 10 | 0 | 0 | 1999-11-01 | 2001-01-01 | 2002-12-01 |  | 2001-12-01 | 2004-01-01 | 78300 | 0 | 78300 | 78300 | 100% | 0 | 0 | 0 | 10179 | 0 | 10179 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to LIA (flexible), to water-based technology (flexible molded, structural and integral skin) and HCFC-141b technology (rigid) at Great Foam Products, Co., Ltd. | Individual | ASP | THA | FOA | 29 | INV | 122 | A | I | CFC | 22.1 | 22.1 | 0 | 0 | 1999-11-01 | 2000-11-01 | 2002-12-01 |  | 2001-12-01 | 2003-11-01 | 231843 | -23 | 231820 | 231820 | 100% | 0 | 0 | 0 | 30139.59 | -2.99 | 30136.6 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNDP | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at P.S. Plastic Container L.P. | Individual | ASP | THA | FOA | 29 | INV | 123 | A | I | CFC | 9.7 | 9.7 | 0 | 0 | 1999-11-01 | 2000-11-01 | 2002-12-01 |  | 2001-12-01 | 2004-01-01 | 75951 | 0 | 75951 | 75951 | 100% | 0 | 0 | 0 | 9873.63 | 0 | 9873.63 | 0 | 0 | Completed in 2001. Financially completed in 2004. |  | 1999 |  | Investment
FIN | IBRD | Preparation of projects in the rigid polyurethane subsector |  | ASP | THA | FOA | 30 | PRP | 127 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Conversion from CFC-11 to water-based technology in the manufacture of integral skin and flexible molded polyurethane foam at Siam Chitose | Individual | ASP | THA | FOA | 31 | INV | 131 | N | I | CFC | 11.3 | 11.3 | 0 | 0 | 2000-07-01 | 2002-03-01 | 2003-08-01 |  | 2004-05-01 | 2005-02-01 | 51795 | -14902 | 36893 | 36893 | 100% | 0 | 0 |  | 6733.35 | -1936.91 | 4796.09 | 0.35 | 0.35 | Project completed and PCR under review. |  |  |  | INV | 0
FIN | IBRD | Conversion from CFC-11 to water-based technology in the manufacture of rigid polyurethane foam at Siam Cargo Containers | Individual | ASP | THA | FOA | 31 | INV | 132 | N | I | CFC | 22.7 | 22.7 | 0 | 0 | 2000-07-01 | 2005-03-01 | 2003-08-01 |  | 2004-08-01 | 2005-03-01 | 177741 | -79622 | 98119 | 98119 | 100% | 0 | 0 |  | 23106.33 | -10350.86 | 12755.47 | 0 | 0 | Project physically and financially completed. |  |  |  | INV | 0
FIN | IBRD | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam (sprayfoam and blocks) at Isotech | Individual | ASP | THA | FOA | 32 | INV | 133 | N | I | CFC | 22.7 | 22.7 | 0 | 0 | 2000-12-01 | 2001-10-01 | 2004-01-01 |  | 2001-11-01 | 2002-01-01 | 144943 | 0 | 144943 | 144943 | 100% | 0 | 0 |  | 18842.59 | 0 | 18842.59 | 0 | 0 | Project physically and financially completed. DIW has endorsed destruction of equipment and disposal plan. PCR sent to ENV/World Bank. |  |  |  | INV | 0
FIN | IBRD | Preparation for a HCFC foam sector plan |  | ASP | THA | FOA | 61 | PRP | 155 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-12-01 | 2011-07-01 |  | 2012-12-01 | 2012-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 7500 | 0 | 7500 | 0 | 0 | Sector plan approved at the 68th ExCom Meeting under overall HPMP. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of a demonstration project for low-global warming potential alternatives for foam system house |  | ASP | THA | FOA | 74 | PRP | 166 | A | I |  | 0 | 0 | 0 | 0 | 2015-05-01 | 2016-06-01 | 2016-05-30 |  | 2016-05-01 | 2016-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 2100 | 0 | 2100 | 0 | 0 | Project approved at the 76th ExCom. | Not applicable. |  |  | Non-INV | 0
ONG | IBRD | Demonstration project at foam system houses to formulate pre-blended polyol for spray polyurethane foam applications using low-global warming potential blowing agent | Individual | ASP | THA | FOA | 76 | DEM | 168 | N | I | HCFC | 3.88 | 0 | 0 | 0 | 2016-05-01 |  | 2017-05-31 | 2018-06-01 |  |  | 352550 | 0 | 352550 | 0 | 0% | 352550 | 352550 | 300000 | 24679 | 0 | 0 | 24679 | 24679 | Testing equipment specifications were reviewed and consultations with chemical suppliers were done in order to secure a supply of HFOs. This latter step has been the cause of the delay in project start-up. | Financial Intermediary that will sign with system houses cleared subproject proposal. Subgrant agreements with enterprises/system houses are in an advanced stage and expected to be signed by end of May. Preliminary results of the demo will be reported to the 79th Meeting of the ExCom if they are ready, but most likely this will be at the 80th Meeting. |  |  | INV | 0
ONG | IBRD | Preparation for HCFC phase-out investment activities (stage II) (foam sector) |  | ASP | THA | FOA | 77 | PRP | 173 | A | I |  | 0 | 0 | 0 | 0 | 2016-12-01 |  | 2018-06-30 | 2018-06-30 |  |  | 120000 | 0 | 120000 | 0 | 0% | 120000 | 120000 | 30000 | 8400 | 0 | 0 | 8400 | 8400 | Preparation funding just approved in Dec 16. Terms of reference for data collection under preparation. | TOR for data survey/HPMP preparation work completed. Consultant selection process will be launched by Q2 2017, with the expectation to have the data collection done before the end of the year. Foam sector plan preparation will follow. |  |  | Non-INV | 0
FIN | UNIDO | Project formulation in the methyl bromide sector | Individual | ASP | THA | FUM | 22 | PRP | 65 | A | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-07-01 | 1997-12-01 |  | 1998-05-01 | 2001-07-01 | 8000 | -624 | 7376 | 7376 | 100% | 0 | 0 |  | 1040 | -83 | 957 | 0 | 0 | FIN
FIN | UNIDO | Demonstration project - Alternatives to the use of methyl bromide ingrain storage (rice, maize, tapioca, feed grains and pulses) | Individual | ASP | THA | FUM | 25 | DEM | 97 | A | I | MBR | 0 | 0 |  |  | 1998-07-01 | 1999-04-01 | 2000-08-01 |  | 2003-07-01 | 2004-12-01 | 280500 | -21687 | 258813 | 258813.44 | 100% | -0.44 | 0 |  | 36465 | -2873 | 33592 | 0 | 0 | FIN |  |  | 2001-12-01
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organizations in methyl bromide communication | Individual | ASP | THA | FUM | 30 | TAS | 126 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2002-10-01 | 2003-10-01 | 25000 | -9096 | 15904 | 15904 | 100% | 0 | 0 |  | 3250 | -1182.48 | 2067.52 | 0 | 0
FIN | IBRD | Preparation of a methyl bromide phaseout strategy | Individual | ASP | THA | FUM | 33 | TAS | 135 | N | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2003-12-01 | 2002-09-01 |  | 2004-12-01 | 2005-03-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0 | Project preparation completed. Strategy approved at the 44th ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | National methyl bromide phase-out plan (first tranche) | Multiyear | ASP | THA | FUM | 44 | INV | 143 | N | I | MBR | 58.7 | 58.7 | 0 | 0 | 2004-12-01 | 2006-12-01 | 2006-12-01 |  | 2013-12-01 | 2014-04-01 | 546991 | -22160.08 | 524830.92 | 524830.92 | 100% | 0 | 0 |  | 41024 | -1661.99 | 39362.01 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | National methyl bromide phase-out plan (second tranche) | Multiyear | ASP | THA | FUM | 50 | INV | 147 | N | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-12-01 | 2008-11-01 |  | 2013-12-01 | 2014-04-01 | 1412214 | -508944.77 | 903269.23 | 903269.23 | 100% | 0 | 0 |  | 105916 | -38170.84 | 67745.16 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | National methyl bromide phase-out plan (third tranche) | Multiyear | ASP | THA | FUM | 57 | INV | 152 | N | I | MBR | 183.1 | 183.1 | 0 | 0 | 2009-04-01 | 2011-12-01 | 2012-12-31 |  | 2013-12-01 | 2014-04-01 | 942395 | -701762 | 240633 | 240633 | 100% | 0 | 0 |  | 70680 | -52632 | 18048 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | Sweden | Halon management programme, halon recovery, recycling and banking | Halon banking | ASP | THA | HAL | 29 | TAS | 120 | A | I |  | 135.9 |  | 0 |  | 1999-11-01 | 2004-11-01 | 2003-12-01 |  | 2010-09-01 | 2011-11-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 26000 | 0 | 26000 | 0 | 0 | Implementation of the halon management project completed in Sep 2010. Sweden disbursed the full project amount to the WB already in year 2000. Overall halon project financially completed Nov. 11 upon return of the savings by the WB to the 65th ExCom. |  | 1999
FIN | IBRD | Halon management programme, halon recovery, recycling and banking | Halon Banking | ASP | THA | HAL | 29 | TAS | 121 | N | I | HAL | 135.85 | 135.85 | 0 | 0 | 1999-11-01 | 2006-12-01 | 2003-12-01 |  | 2010-09-01 | 2011-11-01 | 220750 | -168490 | 52260 | 52260 | 100% | 0 | 0 |  | 28697.5 | -21904 | 6793.5 | 0 | 0 | Project completed and savings returned at the 65th ExCom. |  |  |  | INV | 0
FIN | IBRD | Preparation of projects in halon non-recycling |  | ASP | THA | HAL | 30 | PRP | 125 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 | 0 |  | 1040 | 0 | 1040 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Terminal halon-1211 and halon-1301 phaseout project for fire equipment manufacturers and suppliers converting to ABC powder, CO2, HFC-227ea and inert gases | Individual | ASP | THA | HAL | 32 | INV | 134 | N | I | HAL | 436 | 717.4 | 0 | 0 | 2000-12-01 | 2003-10-01 | 2004-02-01 |  | 2010-09-01 | 2011-11-01 | 568000 | -264529 | 303471 | 303471 | 100% | 0 | 0 |  | 72480 | -33755.4 | 38724.6 | 0 | 0 | Project completed and savings returned at the 65th ExCom. |  |  |  | INV | 0
FIN | IBRD | National CFC phaseout plan: 2002 Annual Programme | Multiyear | ASP | THA | PHA | 35 | INV | 137 | N | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2003-12-01 | 2002-12-01 |  | 2002-12-01 | 2014-04-01 | 540000 | 0 | 540000 | 540000 | 100% | 0 | 0 |  | 27000 | 0 | 27000 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | National CFC phase-out plan: release of second tranche for implementation of the 2002 annual plan | Multiyear | ASP | THA | PHA | 37 | INV | 138 | N | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-12-01 | 2003-08-01 |  | 2003-12-01 | 2014-04-01 | 5194380 | 0 | 5194380 | 5194380 | 100% | 0 | 0 |  | 459494 | 0 | 459494 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | National CFC phase-out plan: 2003 annual programme | Multiyear | ASP | THA | PHA | 41 | INV | 140 | N | I | CFC | 486 | 486 | 0 | 0 | 2003-12-01 | 2005-12-01 | 2004-12-01 |  | 2004-03-01 | 2014-04-01 | 4011846 | 0 | 4011846 | 4011846 | 100% | 0 | 0 |  | 353066 | 0 | 353066 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | National CFC phase-out plan: 2004 annual programme | Multiyear | ASP | THA | PHA | 42 | INV | 141 | N | I | CFC | 486 | 486 | 0 | 0 | 2004-04-01 | 2005-12-01 | 2005-04-01 |  | 2005-04-01 | 2014-04-01 | 1315400 | 0 | 1315400 | 1315400 | 100% | 0 | 0 |  | 118386 | 0 | 118386 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | National CFC phase-out plan: 2005 annual programme | Multiyear | ASP | THA | PHA | 45 | INV | 144 | N | I | CFC | 962.9 | 962.9 | 0 | 0 | 2005-04-01 | 2009-12-01 | 2006-04-01 |  | 2013-12-01 | 2014-04-01 | 1330400 | -103127 | 1227273 | 1227273 | 100% | 0 | 0 |  | 111736 | -8661.3 | 103074.7 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | National CFC phase-out plan: 2006 annual implementation plan | Multiyear | ASP | THA | PHA | 48 | INV | 146 | N | I | CFC | 243 | 243 | 0 | 0 | 2006-04-01 | 2009-12-01 | 2007-04-01 |  | 2013-12-01 | 2014-04-01 | 851600 | -502256 | 349344 | 349344 | 100% | 0 | 0 |  | 68644 | -40485 | 28159 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | National CFC phase-out plan: 2007 annual implementation plan | Multiyear | ASP | THA | PHA | 53 | INV | 149 | N | I | CFC | 209 | 209 | 0 | 0 | 2007-11-01 |  | 2009-11-30 |  | 2013-12-01 | 2014-04-01 | 550000 | -550000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 49500 | -49500 | 0 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | National CFC phase-out plan: 2008 annual implementation plan | Multiyear | ASP | THA | PHA | 55 | INV | 150 | N | I | CFC | 208 | 208 | 0 | 0 | 2008-07-01 |  | 2009-07-31 |  | 2013-12-01 | 2014-04-01 | 550000 | -550000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 49500 | -49500 | 0 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Preparation of a HCFC phase-out management plan |  | ASP | THA | PHA | 55 | PRP | 151 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2010-12-01 | 2009-12-31 |  | 2012-12-01 | 2012-12-01 | 195000 | 0 | 195000 | 195000 | 100% | 0 | 0 |  | 14625 | 0 | 14625 | 0 | 0 | HPMP approved at the 68th ExCom Meeting. |  |  |  | Non-INV | 0
FIN | IBRD | National CFC phase-out plan: 2010-2012 annual implementation plan | Multiyear | ASP | THA | PHA | 60 | INV | 154 | N | I | CFC | 501.6 | 501.6 | 0 | 0 | 2010-04-01 |  | 2011-04-30 |  | 2013-12-01 | 2014-04-01 | 385000 | -385000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 34650 | -34650 | 0 | 0 | 0 | Project completed. |  |  |  | INV | 0
ONG | IBRD | HCFC phase-out management plan (stage I, first tranche) (foam sector plan) | Multiyear | ASP | THA | PHA | 68 | INV | 161 | N | I | HCFC | 33.4 | 33.4 | 0 | 0 | 2012-12-01 | 2015-09-01 | 2013-11-30 | 2018-12-01 |  |  | 1319997 | 0 | 1319997 | 746750 | 56.57% | 573247 | 573247 | 350000 | 92399 | 0 | 52272.27 | 40126.73 | 40126.73 | Only $1,319,997 of 1st funding tranche should have been allocated for the foam sector - balance is part of funding for other components of the HPMP, namely TA/PMU. A total of 20 SGAs signed in 2016. These comprise of 3 SGAs in the A/C sector and another 17 in the foam sector. On regulations, Government has decided to promulgate the ban on HCFC-141b in all foam applications except in spray foam and ban HCFC-22 manufacturing of a/c with capacity of 5 TR and lower for the domestic market by Jun 17. Building code was amended to allow installation of up to 3 TR a/c with R-32 in buildings. A risk assessment study for larger units (3-5 TR a/c) in R-32 household. is under consideration. Another amendment to the code will be considered as a next step. | Foam enterprises will be provided time to decide to participate in a subproject through Jun 17, in addition, system houses will be funded to acquire equipment for manufacturing new foam formulations with non-ODS blowing agents. They will then work with small foam enterprises to modify production processes to accommodate new formulations. On TA, four activities commenced in early 17 (incl. through contract signing) for technical workshops, revision of standards, safety procedures and training manuals, and a train-the-trainer program for use of R-32. |  |  | INV | 0
ONG | IBRD | HCFC phase-out management plan (stage I, first tranche) (residential air-conditioning group project) | Multiyear | ASP | THA | PHA | 68 | INV | 162 | N | I | HCFC | 11.4 | 11.4 | 0 | 0 | 2012-12-01 | 2015-09-01 | 2013-11-30 | 2018-12-01 |  |  | 1008078 | 0 | 1008078 | 1003369 | 99.53% | 4709 | 4709 | 4709 | 70565 | 0 | 70235.83 | 329.17 | 329.17 | Only $1,008,078 of the first funding tranche was allocated for the A/C sector. The balance is for TA/PMU. A total of 20 SGAs signed in 2016. These comprise of 3 SGAs in the A/C sector and another 17 in the foam sector. On regulations, Government has decided to promulgate the ban on HCFC-141b in all foam applications except in spray foam and ban HCFC-22 manufacturing of a/c with capacity of 5 TR and lower for the domestic market by Jun 17. Building code was amended to allow installation of up to 3 TR a/c with R-32 in buildings. A risk assessment study for larger units (3-5 TR a/c) in R-32 household. is under consideration. Another amendment to the code will be considered as a next step. | Foam enterprises will be provided time to decide to participate in a subproject through Jun 17, in addition, system houses will be funded to acquire equipment for manufacturing new foam formulations with non-ODS blowing agents. They will then work with small foam enterprises to modify production processes to accommodate new formulations. On TA, four activities commenced in early 17 (incl. through contract signing) for technical workshops, revision of standards, safety procedures and training manuals, and a train-the-trainer program for use of R-32. |  |  | INV | 0
ONG | Japan | HCFC phase-out management plan (stage I, first tranche) (technical assistance) |  | ASP | THA | PHA | 68 | TAS | 158 | A | I | HCFC-22 | 4.2 |  | 0 |  | 2012-12-01 | 2015-12-01 | 2013-11-01 | 2017-12-01 |  |  | 302965 | 0 | 302965 | 93523.98 | 30.87% | 209441.02 | 209441.02 | 209441.02 | 39385 | 0 | 12157.9785 | 27227.0215 | 27227.0215 | Implementation of this activity progressed as planned in 2016 and was in an advanced stage by the end of 2016. | In early 2017, Daikin visited 9 a/c enterprises with conversions in an advanced stage where production line conversions had already been completed and trial production had already started. The objectives of these visits were to inspect the new HFC-32 a/c manufacturing lines in order to confirm that all required equipment including safety equipment and devices were properly installed and workers were properly trained to handle this new chemical. Pending visits of the last two enterprises will be conducted by end June 2017.
ONG | IBRD | HCFC phase-out management plan (stage I, first tranche) (technical assistance) | Multiyear | ASP | THA | PHA | 68 | TAS | 160 | N | I | HCFC | 1.3 | 1.3 | 0 | 0 | 2012-12-01 | 2015-09-01 | 2013-11-30 | 2018-12-01 |  |  | 1107950 | 0 | 1107950 | 135601 | 12.24% | 972349 | 972349 | 300000 | 77556 | 0 | 9492 | 68064 | 68064 | Total funding for TA activities is $1,107,950 however Secretariat assigned a different amount. TA activities implementation in 2016 included contract signing for R-32 A/C compressor development. A total of 20 SGAs signed in 2016. These comprise of 3 SGAs in the A/C sector and another 17 in the foam sector. On regulations, Government has decided to promulgate the ban on HCFC-141b in all foam applications except in spray foam and ban HCFC-22 manufacturing of a/c with capacity of 5 TR and lower for the domestic market by Jun 17. Building code was amended to allow installation of up to 3 TR a/c with R-32 in buildings. A risk assessment study for larger units (3-5 TR a/c) in R-32 household. is under consideration. Another amendment to the code will be considered as a next step. | A contract for TA activities for micro-foam enterprise and development of pre-blended polyol was signed in early 2017. Foam enterprises will be provided time to decide to participate in a subproject through Jun 17, in addition, system houses will be funded to acquire equipment for manufacturing new foam formulations with non-ODS blowing agents. They will then work with small foam enterprises to modify production processes to accommodate new formulations. On TA, four activities commenced in early 17 (incl. through contract signing) for technical workshops, revision of standards, safety procedures and training manuals, and a train-the-trainer program for use of R-32 |  |  | INV | 0 | To request the submission of additional status report to the 79th meeting to monitor ongoing project with 100 per cent of fund disbursement.
ONG | IBRD | HCFC phase-out management plan (stage I, first tranche) (project management unit) | Multiyear | ASP | THA | PHA | 68 | TAS | 163 | N | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2016-12-01 | 2013-11-30 | 2018-12-01 |  |  | 1381141 | 0 | 1381141 | 239731.91 | 17.36% | 1141409.09 | 1141409.09 | 450000 | 96680 | 0 | 16780.4 | 79899.6 | 79899.6 | Total funding for PMU is $1,381,141. This total amount is financed from the 1st tranche however Secretariat assigned a different amount. A total of 20 SGAs signed in 2016. These comprise of 3 SGAs in the A/C sector and another 17 in the foam sector. On regulations, Government has decided to promulgate the ban on HCFC-141b in all foam applications except in spray foam and ban HCFC-22 manufacturing of a/c with capacity of 5 TR and lower for the domestic market by Jun 17. Building code was amended to allow installation of up to 3 TR a/c with R-32 in buildings. A risk assessment study for larger units (3-5 TR a/c) in R-32 household. is under consideration. Another amendment to the code will be considered as a next step. | Foam enterprises will be provided time to decide to participate in a subproject through Jun 17, in addition, system houses will be funded to acquire equipment for manufacturing new foam formulations with non-ODS blowing agents. They will then work with small foam enterprises to modify production processes to accommodate new formulations. On TA, four activities commenced in early 17 (incl. through contract signing) for technical workshops, revision of standards, safety procedures and training manuals, and a train-the-trainer program for use of R-32. |  |  | Non-INV | 0
ONG | IBRD | HCFC phase-out management plan (stage I, second tranche) (foam sector plan) | Multiyear | ASP | THA | PHA | 74 | INV | 164 | N | I | HCFC | 66.29 | 0 | 0 | 0 | 2015-05-01 | 2015-09-01 | 2016-05-31 | 2018-12-01 |  |  | 4569386 | 0 | 4569386 | 1219460 | 26.69% | 3349926 | 3349926 | 1200000 | 319857 | 0 | 85362.25 | 234494.75 | 234494.75 | Only $4,569,386 of the second tranche is allocated for the foam sector. A total of 20 SGAs signed in 2016. These comprise of 3 SGAs in the A/C sector and another 17 in the foam sector. On regulations, Government has decided to promulgate the ban on HCFC-141b in all foam applications except in spray foam and ban HCFC-22 manufacturing of a/c with capacity of 5 TR and lower for the domestic market by Jun 17. Building code was amended to allow installation of up to 3 TR a/c with R-32 in buildings. A risk assessment study for larger units (3-5 TR a/c) in R-32 household. is under consideration. Another amendment to the code will be considered as a next step. | Foam enterprises will be provided time to decide to participate in a subproject through Jun 17, in addition, system houses will be funded to acquire equipment for manufacturing new foam formulations with non-ODS blowing agents. They will then work with small foam enterprises to modify production processes to accommodate new formulations. On TA, four activities commenced in early 17 (incl. through contract signing) for technical workshops, revision of standards, safety procedures and training manuals, and a train-the-trainer program for use of R-32. |  |  | INV | 0
ONG | IBRD | HCFC phase-out management plan (stage I, second tranche) (residential air-conditioning group project) | Multiyear | ASP | THA | PHA | 74 | INV | 165 | N | I | HCFC | 33.13 | 0 | 0 | 0 | 2015-05-01 | 2015-09-01 | 2016-05-31 | 2018-12-01 |  |  | 5136768 | 0 | 5136768 | 1884009.5 | 36.68% | 3252758.5 | 3252758.5 | 1700000 | 359574 | 0 | 131880.66 | 227693.34 | 227693.34 | $5,136,768 of the second tranche is allocated for the A/C sector per the submitted and approved annual program. Some of the intended AC sector funding went to the foam sector when the Secretariat assigned funds to codes. In addition $589,930 is allocated from the third tranche. $73,146.50 of the disbursement in 2016 is from the third tranche allocation. A total of 20 SGAs signed in 2016. These comprise of 3 SGAs in the A/C sector and another 17 in the foam sector. On regulations, Government has decided to promulgate the ban on HCFC-141b in all foam applications except in spray foam and ban HCFC-22 manufacturing of a/c with capacity of 5 TR and lower for the domestic market by Jun 17. Building code was amended to allow installation of up to 3 TR a/c with R-32 in buildings. A risk assessment study for larger units (3-5 TR a/c) in R-32 household. is under consideration. Another amendment to the code will be considered as a next step. | Foam enterprises will be provided time to decide to participate in a subproject through Jun 17, in addition, system houses will be funded to acquire equipment for manufacturing new foam formulations with non-ODS blowing agents. They will then work with small foam enterprises to modify production processes to accommodate new formulations. On TA, four activities commenced in early 17 (incl. through contract signing) for technical workshops, revision of standards, safety procedures and training manuals, and a train-the-trainer program for use of R-32. |  |  | INV | 0
ONG | IBRD | HCFC phase-out management plan (stage I, third tranche) (foam sector plan) | Multiyear | ASP | THA | PHA | 77 | INV | 169 | N | I | HCFC | 14.24 | 0 | 0 | 0 | 2016-12-01 | 2016-12-01 | 2017-12-31 | 2018-12-01 |  |  | 618803 | 0 | 618803 | 196038 | 31.68% | 422765 | 422765 | 150000 | 43316 | 0 | 13722.59 | 29593.41 | 29593.41 | $410,070 of this 3rd tranche is allocated for the foam sector. A total of 20 SGAs signed in 2016. These comprise of 3 SGAs in the A/C sector and another 17 in the foam sector. On regulations, Government has decided to promulgate the ban on HCFC-141b in all foam applications except in spray foam and ban HCFC-22 manufacturing of a/c with capacity of 5 TR and lower for the domestic market by Jun 17. Building code was amended to allow installation of up to 3 TR a/c with R-32 in buildings. A risk assessment study for larger units (3-5 TR a/c) in R-32 household. is under consideration. Another amendment to the code will be considered as a next step. | Foam enterprises will be provided time to decide to participate in a subproject through Jun 17, in addition, system houses will be funded to acquire equipment for manufacturing new foam formulations with non-ODS blowing agents. They will then work with small foam enterprises to modify production processes to accommodate new formulations. On TA, four activities commenced in early 17 (incl. through contract signing) for technical workshops, revision of standards, safety procedures and training manuals, and a train-the-trainer program for use of R-32. |  |  | INV | 0
ONG | IBRD | Preparation of a HCFC phase-out management plan (stage II) |  | ASP | THA | PHA | 77 | PRP | 171 | A | I |  | 0 | 0 | 0 | 0 | 2016-12-01 |  | 2018-06-30 | 2018-06-30 |  |  | 90000 | 0 | 90000 | 0 | 0% | 90000 | 90000 | 20000 | 6300 | 0 | 0 | 6300 | 6300 | Preparation funding just approved in Dec 16. Terms of reference for data collection under preparation. | TOR for data survey/HPMP preparation work completed. Consultant selection process will be launched by Q2 2017, with the expectation to have the data collection done before the end of the year. |  |  | Non-INV | 0
FIN | IBRD | CFC recycling in MAC | Individual | ASP | THA | REF | 07 | TAS | 07 | N | I | CFC | 250 | 86.93 | 0 | 0 | 1992-06-01 | 1999-01-01 | 1994-12-01 |  | 2003-12-01 | 2004-03-01 | 900000 | -74881 | 825119 | 825119 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 2001-12-01 | INV | 0
FIN | IBRD | Elimination of ODS used in the production of household refrigerators at Thai Toshiba Electric Industries Co. Ltd. (Phase I) | Individual | ASP | THA | REF | 10 | INV | 17 | N | D |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1997-12-01 | 1996-06-01 |  | 1997-01-01 | 1998-02-01 | 823000 | -131273 | 691727 | 691727 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Elimination of ODS used in the production of household refrigerators at Kang Yong Electric Co. Ltd. (Kye) | Individual | ASP | THA | REF | 10 | INV | 18 | N | R | CFC | 109 | 109 | 0 | 0 | 1993-06-01 | 1997-12-01 | 1996-06-01 |  | 1997-01-01 | 1997-12-01 | 1140000 | -256628 | 883372 | 883372 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Elimination of ODS used in the production of household refrigerators at Sanyo Universal Electric Co. Ltd. (Phase I) | Individual | ASP | THA | REF | 10 | INV | 19 | N | D | CFC | 0 | 0 | 0 | 0 | 1993-06-01 | 1997-12-01 | 1996-06-01 |  | 1997-01-01 | 1998-01-01 | 1864000 | -1269071 | 594929 | 594929 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Elimination of ODS used in the production of household refrigerators at Hitachi Consumer Products Co. Ltd. | Individual | ASP | THA | REF | 10 | INV | 20 | N | D | CFC | 132 | 132 | 0 | 0 | 1993-06-01 | 1997-08-01 | 1996-06-01 |  | 1996-12-01 | 1998-10-01 | 553000 | 128861 | 681861 | 681861 | 100% | 0 | 0 |  | 0 | 32939.53 | 32939.53 | 0 | 0 | Project completed. Phase I was financially completed in Aug '97. Phase II was financially completed in Oct. '98. |  |  | 1996-12-01 | INV | 0
FIN | IBRD | Conversion of compressor manufacture from CFC-12 to HFC-134a designs at Sanyo Universal Electric Co. Ltd. (Phase I) | Individual | ASP | THA | REF | 10 | INV | 21 | N | D | CFC | 0 | 0 | 0 | 0 | 1993-06-01 | 1996-09-01 | 1996-06-01 |  | 1997-01-01 | 1996-11-01 | 989000 | -330207 | 658793 | 658793 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Conversion of compressor manufacture from CFC-12 to HFC-134a designs at Kulthorn Kirby Co. Ltd. (Phase I) | Individual | ASP | THA | REF | 10 | INV | 22 | N | D | CFC | 0 | 0 | 0 | 0 | 1993-06-01 | 1997-01-01 | 1996-06-01 |  | 1995-12-01 | 1997-01-01 | 686000 | -85630 | 600370 | 600370 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | UNDP | Elimination in the use of CFC in the manufacture of commercial refrigerators at Sanden Refrigerator Co. Ltd. | Individual | ASP | THA | REF | 13 | INV | 33 | A | I | CFC | 21 | 21 | 0 | 0 | 1994-07-01 | 1995-12-01 | 1995-07-01 |  | 1998-06-01 | 1999-12-01 | 533800 | 0 | 533800 | 533800 | 100% | 0 | 0 | 0 | 69394 | 0 | 69394 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1994 |  | Investment
FIN | IBRD | Production of HFC-134a MAC parts at Nippodenso | Individual | ASP | THA | REF | 13 | INV | 37 | N | R | CFC | 0 | 0 | 0 | 0 | 1994-07-01 | 1997-03-01 | 1995-07-01 |  | 1993-12-01 | 1997-03-01 | 141500 | 0 | 141500 | 141500 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  |  | INV | 0
CLO | IBRD | Phase out of CFC-11 in the manufacturing of equipment for the food and beverage industry at Siam Stainless Steel Co. Ltd. | Individual | ASP | THA | REF | 19 | INV | 52 | N | I |  | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1996-09-01 |  |  | 1999-03-01 | 212900 | -212900 | 0 | 0 | #DIV/0! | 0 | 0 |  | 27677 | -27677 | 0 | 0 | 0 | Project cancelled. Funds returned to 27th meeting. |  |  | 1997-06-01 | INV | 0
FIN | IBRD | Conversion of compressor manufacture from CFC-12 to HFC-134a designs at Sanyo Universal Electric Co. Ltd. (Phase II) | Individual | ASP | THA | REF | 20 | INV | 58 | N | I | CFC | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-12-01 | 1997-04-01 |  | 1997-01-01 | 1998-05-01 | 673680 | 224477 | 898157 | 898157 | 100% | 0 | 0 |  | 87578.4 | 29181.85 | 116760.25 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Conversion of compressor manufacture from CFC-12 to HFC-134a designs at Kulthorn Kirby Co. Ltd. (Phase II) | Individual | ASP | THA | REF | 20 | INV | 60 | N | I | CFC | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-10-01 | 1997-10-01 |  | 1997-01-01 | 1997-10-01 | 808234 | -94003 | 714231 | 714231 | 100% | 0 | 0 |  | 105070.42 | 10323.11 | 115393.53 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Elimination of ozone depleting substances used in the production of household refrigerators at A.P. National Co. Ltd. | Individual | ASP | THA | REF | 21 | INV | 57 | N | R | CFC | 54 | 54 | 0 | 0 | 1997-02-01 | 1997-12-01 | 1998-02-01 |  | 1997-01-01 | 1997-12-01 | 311150 | 0 | 311150 | 311150 | 100% | 0 | 0 |  | 40449.5 | 0 | 40449.5 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Elimination of ODS used in the production of household refrigerators at Sanyo Universal Electric Co. Ltd. (Phase II) | Individual | ASP | THA | REF | 21 | INV | 61 | N | R | CFC | 436 | 436 | 0 | 0 | 1997-02-01 | 1998-08-01 | 1997-08-01 |  | 1997-01-01 | 1998-08-01 | 1467055 | -84285 | 1382770 | 1382770 | 100% | 0 | 0 |  | 190717.15 | -5722.05 | 184995.1 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Elimination of ODS used in the production of household refrigerators at Thai Toshiba Electric Industries Co. Ltd. (Phase II) | Individual | ASP | THA | REF | 21 | INV | 62 | N | R | CFC | 89 | 89 | 0 | 0 | 1997-02-01 | 1998-05-01 | 1998-02-01 |  | 1997-01-01 | 1998-05-01 | 316957 | -19224 | 297733 | 297733 | 100% | 0 | 0 |  | 41204.41 | -1236.1 | 39968.31 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Conversion of CFC-12 refrigerant to HFC-134a and CFC-11 to HCFC-141b as the blowing agent for foam insulation in the manufacture of water coolers at Sirithana | Individual | ASP | THA | REF | 23 | INV | 80 | N | I | CFC | 8.06 | 8.06 | 0 | 0 | 1997-11-01 | 1999-07-01 | 1999-05-01 |  | 1999-08-01 | 1999-12-01 | 122593 | 0 | 122593 | 122593 | 100% | 0 | 0 |  | 15937 | 0 | 15937 | 0 | 0 | Project completed. PCR submitted to the WB in Dec/1999. |  |  |  | INV | 0
FIN | IBRD | Conversion of CFC-12 commercial refrigeration to HC-134a, and CFC-11 to HCFC-141b as the blowing agent for foam insulation at Padriew Co. Ltd. | Individual | ASP | THA | REF | 23 | INV | 81 | N | I | CFC | 10.24 | 10.24 | 0 | 0 | 1997-11-01 | 1999-05-01 | 1999-05-01 |  | 1999-07-01 | 1999-08-01 | 135954 | 0 | 135954 | 135954 | 100% | 0 | 0 |  | 17674 | 0 | 17674 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Conversion of CFC-12 refrigerant to HFC-134a, and CFC-11 to HCFC-141b as the blowing agent for foam insulation in the manufacture of Water Coolers at Siam Cooler | Individual | ASP | THA | REF | 23 | INV | 82 | N | I | CFC | 26.38 | 12.38 | 0 | 0 | 1997-11-01 | 2000-04-01 | 1999-05-01 |  | 2000-08-01 | 2000-09-01 | 186545 | -8258 | 178287 | 178286.83 | 100% | 0.17 | 0.17 |  | 24251 | -1073.54 | 23177.46 | 0 | 0 | Project completed. PCR submitted to the World Bank 4 September 2000. |  |  |  | INV | 0
FIN | IBRD | Conversion of CFC-12 commercial refrigeration to HFC-134a, and CFC-11 to HCFC-141b as the blowing agent for foam insulation at Sahakarn Intercool Co. Ltd. | Individual | ASP | THA | REF | 23 | INV | 85 | N | I | CFC | 5.7 | 5.7 | 0 | 0 | 1997-11-01 | 2000-03-01 | 1999-05-01 |  | 2000-07-01 | 2001-12-31 | 86697 | 0 | 86697 | 86697 | 100% | 0 | 0 |  | 11271 | 0 | 11271 | 0 | 0 | Project completed. PCR submitted to the MLF Secretariat January 2001. |  |  |  | INV | 0
FIN | IBRD | Terminal umbrella project to convert CFC-12 commercial refrigeration to HFC-134a, and CFC-11 to HCFC-141b as the blowing agent for foam insulation at 224 small and medium sized enterprises | Individual | ASP | THA | REF | 25 | INV | 92 | N | I | CFC | 173 | 186.1 | 0 | 0 | 1998-07-01 | 1999-04-01 | 2002-12-01 |  | 2004-12-01 | 2006-07-01 | 750000 | 1717315 | 2467315 | 2467315 | 100% | 0 | 0 |  | 97500 | 208904 | 306404 | 0 | 0 | Project physically and financially completed. PCR submitted. |  |  |  | INV | 0
FIN | IBRD | Programme to reduce the usage of CFC-11 and CFC-12 in chiller servicing by replacing CFC-based chillers with HFC-134a and HCFC-123 chillers at Electricity Generating Authority (EGAT) | Individual | ASP | THA | REF | 26 | INV | 104 | N | I | CFC | 13.2 | 13.2 | 0 | 0 | 1998-11-01 |  | 2002-12-01 |  | 2003-09-01 | 2005-04-01 | 2475000 | -2475000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 282250 | -145520.83 | 136729.17 | 0 | 0 | Project completed. Funding of $1,198,947 was disbursed for replacing 17 chillers with the understanding that it would be paid back once energy savings were achieved. $1,198,947 was paid back in full by Thailand in 2007 directly to the Bank and was received as "other income." That amount was subsequently deducted by the Treasurer in new approvals at the 54th ExCom. |  |  |  | INV | 0
FIN | IBRD | Preparation for a HCFC refrigeration sector plan |  | ASP | THA | REF | 61 | PRP | 156 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-12-01 | 2011-07-31 |  | 2011-12-01 | 2011-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 7500 | 0 | 7500 | 0 | 0 | HCFC survey completed, stakeholder consultations completed, technical inputs provided and initial HPMP completed. Refrigeration information woven into HPMP. Commerical refrigeration enterprises consuming HCFC-141b were included in the foam sector plan, instead of a separate sector plan. Given a strong interest of the major industry in Thailand to adopt HC technology for the refrigeration circuits, however, components are not widely available at present, the decision was to address the refrigeration circuits under Stage II HPMP. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation for a HCFC air-conditioning sector plan |  | ASP | THA | REF | 61 | PRP | 157 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-12-01 | 2011-07-31 |  | 2012-12-01 | 2012-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 7500 | 0 | 7500 | 0 | 0 | Sector plan approved at the 68th ExCom Meeting under overall HPMP. |  |  |  | Non-INV | 0
ONG | IBRD | Preparation for HCFC phase-out investment activities (stage II) (commercial refrigeration sector) |  | ASP | THA | REF | 77 | PRP | 174 | A | I |  | 0 | 0 | 0 | 0 | 2016-12-01 |  | 2018-06-30 | 2018-06-30 |  |  | 90000 | 0 | 90000 | 0 | 0% | 90000 | 90000 | 20000 | 6300 | 0 | 0 | 6300 | 6300 | TOR for data survey/HPMP preparation work completed. Consultant selection process will be launched by Q2 2017, with the expectation to have the data collection done before the end of the year. | TOR for data survey/HPMP preparation work completed. Consultant selection process will be launched by Q2 2017, with the expectation to have the data collection done before the end of the year. Commercial refrigeration project proposal preparation will follow. |  |  | Non-INV | 0
FIN | IBRD | Country programme preparation | Individual | ASP | THA | SEV | 04 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-12-01 |  | 1992-12-01 | 1992-12-01 | 30909 | 220344 | 251253 | 251253 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1991) |  | ASP | THA | SEV | 04 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 32476 | 11678 | 44154 | 44154 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Training of Government technical staff | Individual | ASP | THA | SEV | 04 | TRA | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-09-01 | 1992-06-01 |  | 1992-12-01 | 1997-12-01 | 50000 | 3785 | 53785 | 53785 | 100% | 0 | 0 | 0 | 6500 | 492.05 | 6992.05 | 0 | 0 | Completed in 1992. Financially completed in 1997. |  | 1991 |  | Non-Investment
FIN | IBRD | Controlled substances engineering project |  | ASP | THA | SEV | 06 | PRP | 04 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-12-08 | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 390000 | -40 | 389960 | 389960 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Completed and closed. Balance returned to Multilateral Fund. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1992) |  | ASP | THA | SEV | 06 | PRP | 05 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 120000 | 12195 | 132195 | 132195 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Institutional strengthening of the Ozone Layer Protection Unit | Individual | ASP | THA | SEV | 09 | INS | 09 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-12-01 | 1996-03-01 |  | 2002-01-01 | 2003-05-01 | 400000 | 0 | 400000 | 400000 | 100% | 0 | 0 | 0 | 52000 | 0 | 52000 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1993 | 1997-12-01 | Non-Investment
FIN | IBRD | Preparation of investment projects (1993) |  | ASP | THA | SEV | 09 | PRP | 10 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 190000 | -10781 | 179219 | 179219 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Project preparation assistance | Individual | ASP | THA | SEV | 10 | PRP | 11 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-07-01 | 1994-06-01 |  | 1994-11-01 | 1997-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1993 |  | Investment
FIN | IBRD | User-sector pre-investment studies (1993) |  | ASP | THA | SEV | 10 | PRP | 24 | A | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-06-30 | 1994-06-01 |  | 1993-12-01 | 1993-12-01 | 150000 | -104309 | 45691 | 45691 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Supervision of project implementation (1994) |  | ASP | THA | SEV | 12 | PRP | 28 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 129433 | 3256 | 132689 | 132689 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Umbrella Grant Agreement signed. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1994) |  | ASP | THA | SEV | 12 | PRP | 32 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 81302 | -68062 | 13240 | 13240 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Project preparation assistance in foam, halon and aerosol sectors | Individual | ASP | THA | SEV | 15 | PRP | 39 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-01-01 | 1995-06-01 |  | 1996-06-01 | 1997-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1996. Financially completed in 1997. |  | 1994 |  | Investment
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | ASP | THA | SEV | 16 | PRP | 43 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1997-12-01 | 1997-12-01 | 267138 | 0 | 267138 | 267138 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Project preparation assistance | Individual | ASP | THA | SEV | 18 | PRP | 49 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-06-01 | 2002-05-01 | 3000 | 0 | 3000 | 3000 | 100% | 0 | 0 | 0 | 390 | 0 | 390 | 0 | 0 | Completed in 1996. Financially completed in 2002. |  | 1995 |  | Investment
FIN | IBRD | Project preparation |  | ASP | THA | SEV | 18 | PRP | 50 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation |  | ASP | THA | SEV | 21 | PRP | 129 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 125000 | 0 | 125000 | 125000 | 100% | 0 | 0 |  | 16250 | 0 | 16250 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Project preparation in the foam and refrigeration sectors | Individual | ASP | THA | SEV | 21 | PRP | 59 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-12-01 | 2001-12-01 | 100000 | -40377 | 59623 | 59623 | 100% | 0 | 0 | 0 | 13000 | -5249 | 7751 | 0 | 0 | Completed in 1998. Financially completed in 2001. |  | 1997 |  | Investment
FIN | IBRD | Project preparation in the foam, halon, commercial refrigeration (end users), and solvent sectors |  | ASP | THA | SEV | 24 | PRP | 88 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1999-06-01 | 1999-06-01 | 110000 | 0 | 110000 | 110000 | 100% | 0 | 0 |  | 14300 | 0 | 14300 | 0 | 0 | Completed |  |  |  | Non-INV | 0
FIN | UNDP | Renewal of institutional strengthening project for the phaseout of ODS under the Montreal Protocol | Individual | ASP | THA | SEV | 25 | INS | 93 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 2000-07-01 | 2000-07-01 |  | 2003-04-01 | 2003-05-01 | 266667 | -225128 | 41539 | 41539 | 100% | 0 | 0 | 0 | 34666.71 | -29266.64 | 5400.07 | 0 | 0 | Completed in 2003. Financially completed in 2003. |  | 1998 |  | Non-Investment
FIN | IBRD | Preparation of projects in the foam, halon, commercial refrigeration end-use and solvent sectors |  | ASP | THA | SEV | 27 | PRP | 107 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-06-30 | 2001-01-01 |  | 2000-12-01 | 2000-12-01 | 141000 | 0 | 141000 | 141000 | 100% | 0 | 0 |  | 18330 | 0 | 18330 | 0 | 0 | Ongoing |  |  |  | Non-INV | 0
FIN | IBRD | Renewal of institutional strengthening project for the phaseout of ODS under the Montreal Protocol |  | ASP | THA | SEV | 35 | INS | 136 | N | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2004-12-31 | 2003-07-01 |  | 2003-07-01 | 2004-12-01 | 0 | 225128 | 225128 | 225128 | 100% | 0 | 0 |  | 0 | 29267 | 29267 | 0 | 0 | Project was completed and a terminal report and extension request was submitted to ExCom in Jul. 03. Funding was advanced to cover costs which was not received until 43rd ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | Extension of institutional strengthening project | Individual | ASP | THA | SEV | 40 | INS | 139 | N | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2003-12-01 | 2005-07-01 |  | 2005-08-01 | 2005-08-01 | 346667 | 0 | 346667 | 346667 | 100% | 0 | 0 |  | 26000 | 0 | 26000 | 0 | 0 | Remaining budget was used for public awareness activities e.g. ozone road show, publications, etc. These PR activities were conducted to promote and ensure sustainable ODS phaseout. |  |  |  | Non-INV | 0
FIN | IBRD | Renewal of institutional strengthening project (phase IV) | Individual | ASP | THA | SEV | 46 | INS | 145 | N | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-12-01 | 2007-07-01 |  | 2007-09-01 | 2007-10-01 | 346668 | 0 | 346668 | 346668 | 100% | 0 | 0 |  | 26000 | 0 | 26000 | 0 | 0 | Phase IV of the IS project successfully completed. IS renewed at the 52nd ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | Extension of institutional strengthening project (phase V) | Individual | ASP | THA | SEV | 52 | INS | 148 | N | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-11-01 | 2009-06-30 |  | 2010-11-01 | 2010-11-01 | 346668 | 0 | 346668 | 346668 | 100% | 0 | 0 |  | 26000 | 0 | 26000 | 0 | 0 | Capacity of NOU and government agencies have been continuously enhanced. Phase V of the IS project successfully completed. IS renewed at the 58th ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | Extension of institutional strengthening project (phase VI) | Individual | ASP | THA | SEV | 58 | INS | 153 | N | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2010-12-01 | 2010-12-01 |  | 2012-12-01 | 2013-06-01 | 260001 | 0 | 260001 | 260001 | 100% | 0 | 0 |  | 19500 | 0 | 19500 | 0 | 0 | Import and export controls of HCFCs done thru licensing system. Quota for each HCFC importer was determined. Full compliance with reporting obligations under Art. 7 and Country Programme Implementation. A memo of understanding between Customs and the Office of Vocational Education Commission signed to set up a collaboration mechanism strengthening ODS phaseout efforts. NOU participated in MP-related meetings and coordinated with UNEP to facilitate the 25th MOP and 33rd OEWG meeting in Thailand in 2013. |  |  |  | Non-INV | 0
ONG | IBRD | Extension of institutional strengthening project (phase VII: 1/2013-12/2014) | Individual | ASP | THA | SEV | 68 | INS | 159 | N | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-12-01 | 2014-12-31 | 2017-04-01 |  |  | 346668 | 0 | 346668 | 257804.95 | 74.37% | 88863.05 | 88863.05 | 88863.05 | 24267 | 0 | 18046.52 | 6220.48 | 6220.48 | Total disbursement of $36,929.70 was made in CY2016. Quota for 2016 HCFC imports issued in a timely manner. Full compliance with reporting obligations under Art. 7 for 2016 ODS consumption and production data. Public awareness activities conducted including circulation of materials and annual celebration of Intl Ozone Day in order to maintain priority on ozone layer protection among government agencies and relevant stakeholders. NOU attended the OEWG meetings in Switzerland and Austria, the MOP in Rwanda, and network meetings in Fiji. Renewal of the IS project (ISP) was submitted to the 78th ExCom Meeting. | ISP activities continued in early 2017 as planned until phase VIII of the ISP starts. This included issuance of 2017 quotas for HCFCs. Disbursement of remaining IS funds expected by the first half of the year. |  |  | Non-INV | 0 | To request the submission of additional status report to the 79th meeting on the activities conducted in 2015 and 2016 by the national ozone unit since limited information was provided in the World Bank’s progress report.
ONG | IBRD | Survey of ODS alternatives at the national level | Individual | ASP | THA | SEV | 74 | TAS | 167 | A | I |  | 0 | 0 | 0 | 0 | 2015-05-01 |  | 2016-05-30 | 2017-06-01 |  |  | 120000 | 0 | 120000 | 0 | 0% | 120000 | 120000 | 110806.98 | 10800 | 0 | 827.37 | 9972.63 | 9972.63 | Survey of ODS alternatives is being implemented by an international consulting firm that will complete the data collection by Mar 17. | Survey is under preparation and expected to be submitted to the 80th ExCom Meeting. As of 3 Apr 17, another $35,300 has been disbursed to the consultant. |  |  | Non-INV | 0 | 12 months delays
ONG | IBRD | Extension of institutional strengthening project (phase VIII: 1/2017-12/2018) | Individual | ASP | THA | SEV | 77 | INS | 172 | N | I |  | 0 | 0 | 0 | 0 | 2016-12-01 |  | 2018-12-31 | 2018-12-31 |  |  | 443735 | 0 | 443735 | 0 | 0% | 443735 | 443735 | 20000 | 31061 | 0 | 0 | 31061 | 31061 | ISP Phase VIII was newly approved in Dec 16 and funds transferred to the WB in mid-Jan 17. | ISP VIII activities are expected to begin in the first half of 2017 once the current ISP completes. Planned activities include 2016 country programme reporting by the May deadline; participation of the NOU at the May 17 network meeting in Phuket and coordination support to UNEP as required; attendance at OEWG39 and the MOP; organization of 30 yr celebrations on Intl Ozone Day; Art. 7 data reporting, monitoring HCFC consumption and the ongoing HPMP; and contributing to Stage II preparation which will be launched in 2017. |  |  | Non-INV | 0
FIN | IBRD | Thai-Airways non-ODS metal cleaning |  | ASP | THA | SOL | 07 | PRP | 06 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1993-12-01 | 1994-06-01 |  | 1994-12-01 | 1994-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1994-12-01 | Non-INV | 0
FIN | USA | Follow-up activities of the USA/Thailand/Japan conference on conservation, containment and alternatives |  | ASP | THA | SOL | 08 | TAS | 08 | A | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1993-03-01 |  | 1993-03-01 | 1993-03-01 | 203000 | -67000 | 136000 | 136000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1992
FIN | IBRD | Conversion to wet media blasting and aqueous cleaning solvents at Hana (BKK) Co., Ltd. | Individual | ASP | THA | SOL | 10 | INV | 12 | N | D |  | 16.1 | 16.1 | 0 | 0 | 1993-06-01 | 1996-07-01 | 1994-03-01 |  | 1993-12-01 | 1997-08-01 | 1010000 | -232835 | 777165 | 777165 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Conversion to high-purity water cleaning at GSS Array | Individual | ASP | THA | SOL | 10 | INV | 13 | N | D | CFC | 16.1 | 16.1 | 0 | 0 | 1993-06-01 | 1996-03-01 | 1994-03-01 |  | 1993-12-01 | 1997-05-01 | 316000 | -41204 | 274796 | 274796 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Conversion to high-purity water cleaning at Saha Union's Sriracha facility | Individual | ASP | THA | SOL | 10 | INV | 14 | N | R | CFC | 27.2 | 21.76 | 0 | 0 | 1993-06-01 | 1996-06-01 | 1994-03-01 |  | 1993-05-01 | 1997-05-01 | 2573000 | -472605 | 2100395 | 2100395 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Conversion to aqueous cleaning at Thai Heat Exchange Co. Ltd. | Individual | ASP | THA | SOL | 10 | INV | 15 | N | I | TCA | 11 | 11 | 0 | 0 | 1993-06-01 | 1998-08-01 | 1994-03-01 |  | 1998-08-01 | 1998-08-01 | 268000 | -14000 | 254000 | 254000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1997-08-01 | INV | 0
FIN | IBRD | Conversion to aqueous cleaning at C.I. Group Co. Ltd. | Individual | ASP | THA | SOL | 10 | INV | 16 | N | R | TCA | 12.7 | 12.7 | 0 | 0 | 1993-06-01 | 1998-05-01 | 1994-03-01 |  | 1995-12-01 | 1998-05-01 | 277000 | 0 | 277000 | 277000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Conversion of electronic cleaning processes from CFC-113 to high-purity water cleaning at Team Tronics, Co. Ltd. | Individual | ASP | THA | SOL | 13 | INV | 34 | N | I | CFC | 12 | 11.5 | 0 | 0 | 1994-07-01 | 1998-05-01 | 1995-01-01 |  | 1999-08-01 | 1999-09-01 | 221760 | 0 | 221760 | 221760 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1999-02-01 | INV | 0
FIN | IBRD | Phase-out of ODS solvents at Thai Airways | Individual | ASP | THA | SOL | 15 | INV | 40 | N | I | CFC | 6 | 0 | 0 | 0 | 1994-12-01 | 1998-12-01 | 1996-06-01 |  | 1999-12-01 | 1999-12-01 | 463900 | -32600 | 431300 | 431300 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. |  |  | 1999-04-01 | INV | 0
FIN | IBRD | Conversion of plastic lens cleaning processes from CFC-113 and 1,1,1 TCA to aqueous cleaning at Crystal Lens Corporation Ltd. | Individual | ASP | THA | SOL | 18 | INV | 48 | N | R |  | 1.86 | 1.86 | 0 | 0 | 1995-11-01 | 1998-08-01 | 1996-05-01 |  | 1996-12-01 | 1998-08-01 | 39830 | 0 | 39830 | 39830 | 100% | 0 | 0 |  | 5177.9 | 0 | 5177.9 | 0 | 0 | Project completed. |  |  | 1996-12-01 | INV | 0
CLO | IBRD | Conversion of metal cleaning processes from 1,1,1 TCA to aqueous cleaning at BKJ Engineering Co. Ltd. (BKJ) | Individual | ASP | THA | SOL | 19 | INV | 53 | N | I |  | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1997-02-01 |  |  | 1998-07-01 | 186487 | -186487 | 0 | 0 | #DIV/0! | 0 | 0 |  | 24243.31 | -24243 | 0 | 0.31 | 0.31 | Project cancellation |  |  | 1997-12-01 | INV | 0
FIN | IBRD | Conversion of precision cleaning processes from CFC-113 to aqueous and alternative solvent cleaning and conversion of insulator applications from CFC-113 to perfluorocarbons at Thai CRT Co. Ltd. | Individual | ASP | THA | SOL | 19 | INV | 54 | N | R | CFC | 5 | 5 | 0 | 0 | 1996-05-01 | 1997-05-01 | 1996-05-01 |  | 1995-09-01 | 1997-05-01 | 99440 | 0 | 99440 | 99440 | 100% | 0 | 0 |  | 12927.2 | 0 | 12927.2 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | France | No clean process improvement training for electronic assemblers |  | ASP | THA | SOL | 29 | TRA | 124 | A | I |  | 0 |  | 0 |  | 1999-11-01 | 2001-01-01 | 2001-12-01 |  | 2002-12-01 | 2002-12-01 | 118140 | -2140 | 116000 | 116000 | 100% | 0 |  | 0 | 5907 | -107 | 5800 | 0 |  | Projet achevé
FIN | IBRD | Preparation of projects in the solvent (TCA) sector |  | ASP | THA | SOL | 30 | PRP | 128 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 |  |  |  |  | Non-INV | 0
ONG | IBRD | Preparation for HCFC phase-out investment activities (stage II) (solvent sector) |  | ASP | THA | SOL | 77 | PRP | 170 | A | I |  | 0 | 0 | 0 | 0 | 2016-12-01 |  | 2018-06-30 | 2018-06-30 |  |  | 90000 | 0 | 90000 | 0 | 0% | 90000 | 90000 | 20000 | 6300 | 0 | 0 | 6300 | 6300 | TOR for data survey/HPMP preparation work completed. Consultant selection process will be launched by Q2 2017, with the expectation to have the data collection done before the end of the year. | TOR for data survey/HPMP preparation work completed. Consultant selection process will be launched by Q2 2017, with the expectation to have the data collection done before the end of the year. Solvent sector plan preparation will follow. |  |  | Non-INV | 0
FIN | UNIDO | Preparation of a project for the elimination of methyl bromide in the post harvest sector | Individual | EUR | TKM | FUM | 53 | PRP | 02 | A | I |  | 0 | 0 |  |  | 2007-11-01 | 2008-05-01 | 2008-11-30 |  | 2009-12-01 | 2011-12-01 | 20000 | -609 | 19391 | 19391.34 | 100% | -0.34 | 0 |  | 1500 | -46 | 1454 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Technical assistance for the elimination of methyl bromide in post harvest sector | Individual | EUR | TKM | FUM | 59 | INV | 06 | A | I | MBR | 2.8 | 2.8 |  |  | 2009-11-01 | 2010-07-01 | 2013-12-01 |  | 2013-12-01 | 2015-03-01 | 179586 | -981 | 178605 | 178604.91 | 100% | 0.09 | 0 |  | 16163 | -88 | 16074 | 1 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | EUR | TKM | PHA | 55 | PRP | 05 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-09-01 | 2009-07-31 |  | 2010-12-01 | 2012-02-01 | 85000 | -909 | 84091 | 84090.6 | 100% | 0.4 | 0 |  | 6375 | -68 | 6307 | 0 | 0 | FIN |  |  |  | NON-INV
COM | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | EUR | TKM | PHA | 62 | INV | 08 | A | I |  | 0 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2012-12-31 |  | 2015-12-01 |  | 309050 | 0 | 309050 | 303564.63 | 98.23% | 5485.37 | 5415.59 | 1 | 23179 | 0 | 22767 | 412 | 406 | The project was operationally completed. |  |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | EUR | TKM | PHA | 71 | INV | 09 | A | I | HCFC | 0.7 | 0.7 |  |  | 2013-12-01 | 2014-07-01 | 2016-12-31 | 2017-12-31 |  |  | 94500 | 0 | 94500 | 84420.17 | 89.33% | 10079.83 | 4675.93 | 10000 | 7088 | 0 | 6332 | 756 | 350.6947 | Brief report: Tranche request prepared Milestone 1: Progress report prepared - Yes Milestone 2: Intermediate goals achieved - Yes Milestone 3: Tranche request prepared - Yes Activities planned but not implemented: No Actions towards next goals: Upgrading training centers/training. Was any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: Yes. The activities were combined with the next tranche. Any actions required by Executive Committee? No | Brief report: Tranche request approved Milestone 1: Progress report prepared - Yes Milestone 2: Intermediate goals achieved - Yes Milestone 3: Tranche request prepared - Yes Activities planned but not implemented: No Actions towards next goals: Upgrading training centers/training. Was any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: Yes. The activities were combined with the next tranche. Any actions required by Executive Committee? No |  |  | INV
COM | UNIDO | Verification report for stage I of HCFC phase-out management plan | Individual | EUR | TKM | PHA | 71 | TAS | 10 | A | I |  | 0 | 0 |  |  | 2013-12-01 | 2014-04-01 | 2016-05-31 |  | 2015-12-01 |  | 30000 | 0 | 30000 | 29700.6 | 99% | 299.4 | 0 | 1 | 2700 | 0 | 2673 | 27 | 0 | The project was operationally completed. |  |  |  | NON-INV
ONG | UNIDO | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | EUR | TKM | PHA | 76 | INV | 12 | A | I | HCFC | 1.7 | 0 |  |  | 2016-05-01 | 2016-10-01 | 2020-05-31 | 2019-12-31 |  |  | 215250 | 0 | 215250 | 3406.05 | 1.582% | 211843.95 | 0 | 15000 | 16144 | 0 | 255 | 15889 | 0 | 'The project was approved by the 76th ExCom. | Brief report: Training of trainers for the servicing sector. Milestones achieved: Milestone 1: Selection of training location – No Milestone 2: Preparation of a training program – Yes Milestone 3: Procurement of equipment - No Activities planned but not implemented: No Actions towards next goal: Training of technicians. Was any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: Yes. The activities were combined with the previous tranche Any actions required by Executive Committee? No |  |  | INV
FIN | UNEP | Institutional strengthening project (phase I) | Individual | EUR | TKM | SEV | 46 | INS | 01 | A | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-10-01 | 2008-07-01 |  | 2008-02-01 | 2010-12-01 | 115693 | 0 | 115693 | 115693 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase II) | Individual | EUR | TKM | SEV | 54 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-11-01 | 2010-04-01 |  | 2010-07-01 | 2011-07-01 | 92000 | 0 | 92000 | 92000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNIDO | Extension of the institutional strengthening project (phase II) | Individual | EUR | TKM | SEV | 54 | INS | 04 | N | I |  | 0 | 0 |  |  | 2008-04-01 | 2009-11-01 | 2009-03-31 |  | 2010-12-01 | 2012-02-01 | 15000 | -62 | 14938 | 14938.25 | 100% | -0.25 | 0 |  | 1125 | -5 | 1120 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | EUR | TKM | SEV | 61 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-01-01 | 2012-09-01 |  | 2012-09-01 | 2013-12-01 | 77000 | 0 | 77000 | 77000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | EUR | TKM | SEV | 74 | TAS | 11 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-12-01 | 2016-05-01 | 2017-06-01 |  |  | 70000 | 0 | 70000 | 32.49 | 0.04641% | 69967.51 | 69967.51 | 6996.751 | 9100 | 0 | 4.2237 | 9095.7763 | 9095.7763 | Brief progress report (actual/planned): In preparation of the survey, NOU Turkmenistan collected available data, prepared the TOR and contracts for the national experts, identified 82 key stakeholders to be involved in the survey and prepared the invitations for the first stakeholder consultation on 25 January 2017. NOU Turkmenistan also conducted a preliminary analysis of available data from State Customs and the Standardization Body for the years 2012, 2013, 2014 and 2015. Once the first payment under the SSFA was received in December 2016, the contracts with the national experts were signed. Legal arrangements (actual/planned): SSFA with the State Committee on Environment Protection and Land Resources (hereinafter State Committee) was signed in September 2016. Initial stages of project implementation (actual/planned): N.a. Intermediate goals achieved (actual/planned): N.a. Project completion and follow up: N.a. First disbursement date (actual/planned): December 2016 All funds disbursed (yes/no): No Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: Delay in establishing SSFA due to the fact that the name of the Ministry of Nature Protection changed to State Committee and complex approval and registration procedures. The first payment was released in December 2016 once the SSFA was officially registered by the Ministry of Economy and Development of Turkmenistan. Accordingly, the first stakeholder meeting has been re-scheduled to 25 January 2017. If Yes, will delay have impact on project completion date (yes/no): Yes Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N.a. | Brief progress report (actual/planned): Shortly after the release of the first payment, the State Committee on Environment Protection and Land Resources initiated the cooperation with key stakeholders. Official letters requesting cooperation on the survey and a detailed data collection questionnaire were sent to 82 key stakeholders, including importers, distributors of chemicals, industry and trade associations, companies servicing refrigeration and air conditioning systems and producers of ODS alternatives. The first stakeholder consultation was organized in Ashgabat on 25 January 2017. The 70 participants included representatives of relevant ministries, organizations, enterprises and other private sector entities. Legal arrangements (actual/planned): SSFA with the State Committee on Environment Protection and Land Resources (hereinafter State Committee) was signed in September 2016. Initial stages of project implementation (actual/planned): N.a. Intermediate goals achieved (actual/planned): N.a. Project completion and follow up: N.a. First disbursement date (actual/planned): December 2016 All funds disbursed (yes/no): No Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: Delay in establishing SSFA due to the fact that the name of the Ministry of Nature Protection changed to State Committee and complex approval and registration procedures. The first payment was released in December 2016 once the SSFA was officially registered by the Ministry of Economy and Development of Turkmenistan. Accordingly, the first stakeholder meeting has been re-scheduled to 25 January 2017. If Yes, will delay have impact on project completion date (yes/no): Yes Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N.a.
FIN | UNEP | Preparation of country programme | Individual | ASP | TLS | PHA | 59 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-06-01 | 2010-11-01 |  | 2011-03-01 | 2011-11-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0
FIN | UNEP | Preparation of HCFC phase-out management plan | RMP | ASP | TLS | PHA | 59 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-06-01 | 2010-11-01 |  | 2011-03-01 | 2011-11-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan (additional funding) | RMP | ASP | TLS | PHA | 61 | PRP | 05 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2010-06-01 | 2010-11-01 |  | 2011-12-01 | 2012-12-01 | 55000 | -1745 | 53255 | 53255 | 100% | 0 | 0 |  | 7150 | -226.85 | 6923.15 | 0 | 0
ONG | UNDP | CFC and HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | TLS | PHA | 63 | INV | 07 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-04-01 | 2012-10-01 | 2012-03-01 | 2017-12-01 |  |  | 96120 | 0 | 96120 | 61120 | 63.59% | 35000 | 20000 | 14000 | 8651 | 0 | 5500.9272 | 3150.0728 | 1800.0416 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): No procurment happened. Prodoc signed (actual/planned, yes/no and date):LoA signed 27 Jan 2012 Missions undertaken (actual/planned):1 TOR for consultants/subcontracts completed (actual/planned): Contract/PO/MOA agreements signed: First disbursement date (actual/planned): 41183Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:The amount quoted by supplier was high than that of allocated budget. | The procurement issue will be sorted out by May 2017 and procurement will start. It will be completed by 2017. | 2011 |  | Investment
ONG | UNEP | HCFC and CFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | TLS | PHA | 63 | TAS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2012-06-01 | 2012-03-01 | 2017-12-01 |  |  | 93500 | 0 | 93500 | 93500 | 100% | 0 | 0 |  | 12155 | 0 | 12155 | 0 | 0 | Brief progress report (actual/planned): The licensing/quota system was effectively enforced for import/export of HCFCs. Consultation meetings with the registered importer were organized to set annual quotas and agreement on management of this. The Government organized one Customs and enforcement officers training in August 2016 with 35 participants. Senior Customs officers also attended Custom training workshop in Surabaya, Indonesia in August 2016 to strengthen their enforcement capacity. NOU also collaborated with the Directorate General for Customs in the preparation of Memorandum of Cooperation (MOC), which would strengthen the cooperation between Ministry of Commerce, Industry and Environment and Ministry of Finance regarding the implementation of licensing system. The MOC was signed on 16 September 2016. One additional RAC training workshop was organized in November 2016 in Dili with 12 participants. Project was extended to December 2017 to accommodate the implementation of remaining activities. 2015 CP data was submitted online. Legal arrangements (actual/planned): The SSFA was signed in March 2012 and has been closed in December 2013. TOR completed: Not applicable. First disbursement date: June 2012 All funds disbursed (yes/no): No. Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: Slow implementation in follow up activities after the initial activities conducted by UNEP. If Yes, will delay have impact on project completion date (yes/no): Yes, the revised project completion date of HPMP Stage I is expected to be in December 2017. Any ongoing problems (yes/no): No, the implementation is progressing If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): The extension of SSFA has clearly indicated the activities to be implemented in 2017. NOU plans to organize the RAC technician training in the first quarter of 2017. Due to the limited equipment for the training of flammable alternatives, NOU has also coordinated with Indonasia to have their trainers trained in Indonesia on the flammamle refrigerants.
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | ASP | TLS | PHA | 69 | TAS | 09 | A | I |  | 0 |  | 0 |  | 2013-04-01 | 2014-06-01 | 2015-04-01 | 2017-12-01 |  |  | 55000 | 0 | 55000 | 11902.22 | 21.64% | 43097.78 | 43097.78 | 4309.778 | 7150 | 0 | 1547.2886 | 5602.7114 | 5602.7114 | Brief progress report (actual/planned): The licensing/quota system was effectively enforced for import/export of HCFCs. Consultation meetings with the registered importer were organized to set annual quotas and agreement on management of this. The Government organized one Customs and enforcement officers training in August 2016 with 35 participants. Senior Customs officers also attended Custom training workshop in Surabaya, Indonesia in August 2016 to strengthen their enforcement capacity. NOU also collaborated with the Directorate General for Customs in the preparation of Memorandum of Cooperation (MOC), which would strengthen the cooperation between Ministry of Commerce, Industry and Environment and Ministry of Finance regarding the implementation of licensing system. The MOC was signed on 16 September 2016. One additional RAC training workshop was organized in November 2016 in Dili with 12 participants. Project was extended to December 2017 to accommodate the implementation of remaining activities. 2015 CP data was submitted online. Legal arrangements (actual/planned): The SSFA was signed in June 2014. TOR completed: Not applicable. First disbursement date: June 2014 All funds disbursed (yes/no): No. Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: Slow implementation in follow up activities after the initial activities conducted by UNEP. If Yes, will delay have impact on project completion date (yes/no): Yes, the revised project completion date of HPMP Stage I is expected to be in December 2017. Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): The extension of SSFA has clearly indicated the activities to be implemented in 2017. NOU plans to organize the RAC technician training in the first quarter of 2017. Due to the limited equipment for the training of flammable alternatives, NOU has also coordinated with Indonasia to have their trainers trained in Indonesia on the flammamle refrigerants.
ONG | UNDP | Preparation of a HCFC phase-out management plan (stage II) | Individual | ASP | TLS | PHA | 72 | PRP | 11 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 | 2015-11-01 | 2016-05-01 | 2017-09-01 |  |  | 10000 | 0 | 10000 | 5000 | 50% | 5000 | 5000 | 2000 | 700 | 0 | 350 | 350 | 350 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Document prepared but could not be submitted. Prodoc signed (actual/planned, yes/no and date):LoA signed 23 Nov 2015 Missions undertaken (actual/planned):1 TOR for consultants/subcontracts completed (actual/planned): Contract/PO/MOA agreements signed: First disbursement date (actual/planned): 42309Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:Due to low disbursement it could not be submitted to ExCom | To start the procurement process |  |  | Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan (stage II) | Multi-Year | ASP | TLS | PHA | 72 | PRP | 12 | A | I |  | 0 |  | 0 |  | 2014-05-01 | 2015-12-01 | 2016-05-01 | 2017-09-01 |  |  | 20000 | 0 | 20000 | 0 | 0% | 20000 | 0 | 2000 | 2600 | 0 | 0 | 2600 | 0 | Brief progress report (actual/planned): The Government of Timor Leste and local consultant in close consultation with UNEP and UNDP drafted a preliminary strategy taking into consideration the results of the surveys, data analysis, consultation meetings as well as the policy and legislation review. UNEP and UNDP had a joint mission in July 2016 to attend stakeholders meeting , which was organized by the NOU on 28 July 2016 with the main goal to organise consultations with representatives of the government and major stakeholders to finalize HPMP project document. The key highlight was to limit the import of new HCFC-based room air-conditioners and ban the import of second hand HCFC-based room air-conditioners to prevent the growth of HCFC consumption, which was agreed in the meeting. The final HPMP project document was submitted to ExCom-77. Due to the slow rate of disbursement of HPMP Stage I, the approval of the HPMP Stage II was deferred. Legal arrangements(actual/planned): SSA with Consultant, 1 October 2015. Initial stages of project implementation(actual/planned): N/A Intermediate goals achieved (actual/planned): Consultant recruited and survey conducted. Project completion and follow up: Not applicable. First disbursement date (actual/planned): December 2015. All funds disbursed (yes/no): No_ Any delay?(yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): N/A. Any ongoing problems (yes/no): No. | Brief progress report (actual/planned): UNEP is coordinating with UNDP to expedite the disbursement of the HPMP Stage I. The HPMP stage II is scheduled for the submission to ExCom-80.
FIN | UNEP | Institutional strengthening project (start-up cost) | Individual | ASP | TLS | SEV | 56 | INS | 01 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-01-01 | 2009-11-01 |  | 2010-11-01 | 2011-06-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Institutional strengthening project (phase II, year 1) | Individual | ASP | TLS | SEV | 61 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2010-12-01 | 2011-12-01 |  | 2011-12-01 | 2011-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Institutional strengthening project (phase II, year 2: 1/2012-12/2012) | Individual | ASP | TLS | SEV | 64 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-03-01 | 2012-12-01 |  | 2013-12-01 | 2014-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of institutional strengthening (phase III: 4/2013-3/2015) | Individual | ASP | TLS | SEV | 69 | INS | 10 | A | I |  | 0 |  | 0 |  | 2013-04-01 | 2014-05-01 | 2015-03-01 | 2017-12-01 |  |  | 60000 | 0 | 60000 | 21061.22 | 35.1% | 38938.78 | 38938.78 | 3893.878 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The operation of the NOU was going on well. The licensing and quota system for ODS import/export was enforced, i.e.six importers or companies received quota of HCFCs in 2016. NOU regularly contacted the national stakeholders to enhance cooperation and strengthen the implementation e.g. the adoption of 2012 HS code to sttrengthen the import and export control. NOU collaborated with the Directorate General for Customs in the preparation of Memorandum of Cooperation (MOC), which would strengthen the cooperation between Ministry of Commerce, Industry and Industry and Ministry of Finance regarding the implementation of licensing system. The MOC was signed on 16 September 2016. NOU also coordinated and facilitated the implementation of HPMP, ODS Alternative Survey as well as the praparation of the HPMP Stage II to the 77th meeting of Excom. The NOU also organized the 2016 ozone day celebration, and actively joined the regional and global ozone related meetings e.g. the network meeting, OEWG and the MOP meetings. 2015 Article 7 and CP data were submitted to the Ozone Secretariat and MLFS respectively. The fourth payment under the SSFA was made to the country.Project was extended to December 2017 to accommodate the implementation of remaining activities. Legal arrangements (actual/planned): The SSFA was signed in March 2014. Initial stages of project implementation (actual/planned): Mar 13/Mar 14. Intermediate goals achieved (actual/planned): Yes. Project completion and follow up: Not applicable. First disbursement date: May 2014. All funds disbursed (yes/no): No Any delay? (yes/no): Yes. If Yes, reasons for delay & action plan to resolve: Limited experiences to plan, implement and monitor the project. If Yes, will delay have impact on project completion date (yes/no): Yes. Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: No. | Brief progress report (actual/planned): NOU continues enforcing the licensing and quota system. As there is one more payment left, UNEP is working closely with the NOU to complete the agreed activities and close the SSFA.
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | ASP | TLS | SEV | 74 | TAS | 13 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-05-01 | 2016-05-01 | 2017-06-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 36102.22 | 4000 | 5200 | 0 | 0 | 5200 | 4693.2886 | Brief progress report (actual/planned): The project was on track. A national consultant was hired by the NOU to support the data collection. The regional consultant contracted by UNEP conducted the mission in November 2016 to guide the consultant and finalize the methodology. The national consultant assisted the NOU in the identification of the current use of ODS alternatives by substance/sector and collection of import/export data for the substances for the past a couple of years. Data collection was at the final stage and expected to be completed in early 2017. Legal arrangements(actual/planned): The SSFA was signed in December 2015. Initial stages of project implementation(actual/planned): December 2015 Intermediate goals achieved (actual/planned): Not applicable. Project completion and follow up: Not applicable. First disbursement date (actual/planned): May 2016 All funds disbursed (yes/no): _No__ Any delay?(yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): The data collection is completed. The national consultant and NOU have started cross checking the information to ensure the completion of end-user surveys, collection, analysis, and aggregation of consumption data.
ONG | UNEP | Extension of institutional strengthening (phase IV: 1/2017-12/2018) | Individual | ASP | TLS | SEV | 76 | INS | 14 | A | I |  | 0 |  | 0 |  | 2016-05-01 |  | 2018-12-01 | 2018-12-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The project was approved at the 76th ExCom Meeting in May 2016. The SSFA was drafted in consultation with the country and signed by both UNEP and government in November 2016. The firsit payment has not yet been requested due to the need to close the on-going IS project III. Legal arrangements(actual/planned): The agreement was signed in November 2016. Initial stages of project implementation(actual/planned): Not yet. Intermediate goals achieved (actual/planned): Not yet. Project completion and follow up: Not applicable. First disbursement date (actual/planned): not yet. All funds disbursed (yes/no): _No__ Any delay?(yes/no): No. If Yes, will delay have impact on project completion date (yes/no): No. Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): The first payment will be made after signing of the SSFA and closure of IS Project phase III.
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | TOG | PHA | 48 | PRP | 12 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-01-01 | 2007-04-01 |  | 2008-06-01 | 2010-12-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 |  | 2340 | 0 | 2340 | 0 | 0
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | AFR | TOG | PHA | 48 | PRP | 13 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-04-01 | 2007-02-01 | 2007-04-01 |  | 2007-12-01 | 2010-01-01 | 12000 | -3712.5 | 8287.5 | 8288 | 100% | -0.5 | 0 | 0 | 900 | -278.44 | 621.6 | -0.04 | 0 | Financially completed in 2010. |  | 2006 |  | Investment
FIN | UNDP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | TOG | PHA | 54 | INV | 16 | N | I | CFC | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-11-01 | 2010-03-01 |  | 2010-12-01 | 2013-03-01 | 95000 | 0 | 95000 | 95000 | 100% | 0 | 0 | 0 | 8550 | 0 | 8550 | 0 | 0 | Financially completed in 2013. |  | 2008 |  | Investment
FIN | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | TOG | PHA | 54 | TAS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-06-01 | 2010-03-01 |  | 2010-07-01 | 2011-07-01 | 89000 | -292 | 88708 | 88708 | 100% | 0 | 0 |  | 11570 | -37.96 | 11532.04 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | TOG | PHA | 56 | PRP | 17 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-03-01 | 2009-11-01 |  | 2011-12-01 | 2012-12-01 | 85000 | -14308 | 70692 | 70692 | 100% | 0 | 0 |  | 11050 | -1860.04 | 9189.96 | 0 | 0
FIN | UNDP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | TOG | PHA | 57 | INV | 20 | N | I | CFC | 5.9 | 5.9 | 0 | 0 | 2009-04-01 | 2010-04-01 | 2011-03-01 |  | 2010-12-01 | 2013-03-01 | 62000 | -866.04 | 61133.96 | 61134 | 100% | -0.04 | 0 | 0 | 5580 | -77.94 | 5502.06 | 0 | 0 | Financially completed in 2013. |  | 2009 |  | Investment
FIN | UNEP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | TOG | PHA | 57 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-07-01 | 2010-03-01 |  | 2010-12-01 | 2011-06-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | TOG | PHA | 62 | INV | 22 | A | I |  | 0 | 0 |  |  | 2010-12-01 | 2010-12-01 | 2013-12-31 | 2017-12-01 |  |  | 200000 | 0 | 200000 | 155774.59 | 77.89% | 44225.41 | 0 | 30000 | 15000 | 0 | 11683 | 3317 | 0 | - Survey is completed. - Beneficiaries were identified in 2015. - Funds from the 2nd tranche, to be submitted to the 77th ExCom, would have to be combined with residual funds from 1st tranche for actual conversion. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Project is extended in order to combine the activities with the 2nd tranche Any action required by Executive Committee? No | -Milestone 1 Survey is completed. - Milestone 2: Potential Beneficiaries were identified in 2015. -Milestone 3: Proposal for conversion exercise developed Actions towards next goals: Visit of international expert to potential beneficiaries Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: Yes If yes, implications: Project is extended in order to combine the activities with the 2nd tranche Any action required by Executive Committee? No |  |  | INV
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | TOG | PHA | 62 | TAS | 21 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-05-01 | 2013-12-01 |  | 2013-12-01 | 2014-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | AFR | TOG | PHA | 71 | TAS | 25 | A | I |  | 0.9 |  | 0 |  | 2013-12-01 | 2016-05-01 | 2016-12-01 | 2018-07-01 |  |  | 45000 | 0 | 45000 | 22549.98 | 50.11% | 22450.02 | 22450.02 | 2245.002 | 5850 | 0 | 2931.4974 | 2918.5026 | 2918.5026 | Brief progress report (actual/planned): Country signed SSFA in February 2016. NOU supervised the training of 165 RAC technicians and 22 custom officers in 2016. Legal arrangements (actual/planned): Agreement signed in February 2016. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in May 2016__ All funds disbursed (yes/no): No_. YES_ Any delay? (yes/no): Yes ___ If Yes, reasons for delay & action plan to resolve: Due to NOO long sickness and death, the activities are delayed. Another NOO is appointed ___ If Yes, will delay have impact on project completion date (yes/no): _ No __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Brief progress report (actual/planned): Country signed SSFA in February 2016. NOU supervised the training of 165 RAC technicians and 22 custom officers in 2016. Legal arrangements (actual/planned): Agreement signed in February 2016. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in May 2016__ All funds disbursed (yes/no): No_. YES_ Any delay? (yes/no): Yes ___ If Yes, reasons for delay & action plan to resolve: Due to NOO long sickness and death, the activities are delayed. Another NOO is appointed ___ If Yes, will delay have impact on project completion date (yes/no): _ No __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a