FIN | UNEP | Development of a refrigerant management plan | RMP | AFR | TOG | REF | 35 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-06-01 | 2002-08-01 |  | 2002-10-01 | 2007-02-01 | 60000 | -20927 | 39073 | 39073 | 100% | 0 | 0 |  | 7800 | -2720.51 | 5079.49 | 0 | 0
FIN | UNDP | Project preparation in the recovery and recycling refrigeration sector | Individual | AFR | TOG | REF | 36 | PRP | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-04-01 | 2003-04-01 |  | 2003-01-01 | 2005-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2003. Financially completed in 2005. |  | 2002 |  | Investment
FIN | UNDP | Implementation of the RMP: monitoring of the activities included in the RMP | RMP-Component | AFR | TOG | REF | 38 | TAS | 05 | A | I | CFC | 1.3 | 1.3 | 0 | 0 | 2002-11-01 | 2005-02-01 | 2006-11-01 |  | 2007-12-01 | 2008-10-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2007. Financially completed in 2008. |  | 2002 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: incentive programme for the commercial and industrial end-user refrigeration sector | RMP-Component | AFR | TOG | REF | 38 | TAS | 06 | A | I | CFC | 9.7 | 9.7 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2006-11-01 |  | 2007-12-01 | 2011-11-01 | 110000 | -3067.85 | 106932.15 | 106932 | 100% | 0.15 | 0 | 0 | 14300 | -398.82 | 13901.16 | 0.02 | 0 | Completed in 2007. |  | 2002 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: recovery and recycling of refrigerants | RMP-Component | AFR | TOG | REF | 38 | TAS | 07 | A | I | CFC | 13.3 | 13.3 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2004-11-01 |  | 2007-12-01 | 2011-11-01 | 150000 | -575.31 | 149424.69 | 149425 | 100% | -0.31 | 0 | 0 | 19500 | -74.79 | 19425.25 | -0.04 | 0 | Completed in 2007. |  | 2002 |  | Investment
FIN | UNEP | Implementation of the RMP: training of refrigeration technicians | Individual | AFR | TOG | REF | 38 | TRA | 08 | A | I | CFC | 5.7 | 5.7 | 0 | 0 | 2002-11-01 | 2003-03-01 | 2004-05-01 |  | 2006-12-01 | 2007-02-01 | 64000 | 0 | 64000 | 64000 | 100% | 0 | 0 |  | 8320 | 0 | 8320 | 0 | 0
FIN | UNEP | Implementation of the RMP: training of customs officers | Individual | AFR | TOG | REF | 38 | TRA | 09 | A | I | CFC | 3.8 | 3.8 | 0 | 0 | 2002-11-01 | 2004-01-01 | 2004-05-01 |  | 2006-12-01 | 2008-02-01 | 43500 | -1003 | 42497 | 42497 | 100% | 0 | 0 |  | 5655 | -130.52 | 5524.48 | 0 | 0
FIN | UNEP | Country programme preparation | Individual | AFR | TOG | SEV | 06 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-02-01 | 1993-02-01 |  | 1995-07-01 | 1995-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNEP | Establishment of the National Ozone Office | Individual | AFR | TOG | SEV | 23 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1999-02-01 | 2000-12-01 |  | 2002-07-01 | 2004-06-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (Phase 2) | Individual | AFR | TOG | SEV | 37 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2004-01-01 | 2004-08-01 |  | 2004-08-01 | 2007-02-01 | 60667 | 0 | 60667 | 60667 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | AFR | TOG | SEV | 44 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-05-01 | 2006-12-01 |  | 2007-09-01 | 2009-03-01 | 60667 | 0 | 60667 | 60667 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | TOG | SEV | 50 | INS | 14 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-09-01 | 2008-11-01 |  | 2009-11-01 | 2010-12-01 | 60666 | 0 | 60666 | 60666 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | AFR | TOG | SEV | 56 | INS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2011-06-01 | 2010-12-01 |  | 2011-12-01 | 2012-12-01 | 60666 | 0 | 60666 | 60666 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VI) | Individual | AFR | TOG | SEV | 62 | INS | 23 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2012-01-01 | 2012-12-01 |  | 2012-12-01 | 2013-12-01 | 60666 | 0 | 60666 | 60666 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of the institutional strengthening project (phase VII: 1/2013-12/2014) | Individual | AFR | TOG | SEV | 68 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-03-01 | 2014-12-01 |  | 2015-12-01 |  | 60666 | 0 | 60666 | 60448.12 | 99.64% | 217.88 | 217.88 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
ONG | UNEP | Extension of the institutional strengthening project (phase VIII: 1/2015-12/2016) | Individual | AFR | TOG | SEV | 73 | INS | 26 | A | I |  | 0 |  | 0 |  | 2014-11-01 | 2015-12-01 | 2016-12-01 | 2017-12-01 |  |  | 60666 | 0 | 60666 | 60666 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Country signed the SSFA in April 2015. 2015 CP data and 2015 Art7 data reported. Ozone day celebrated. Legal arrangements (actual/planned): Agreement signed in April 2015.First payment: January 2016. All activities under the SSFA are completed (as planned) No__ First mission (actual/planned): _ N/A -TOR completed (actual/planned): _ Yes __ First disbursement date (actual/planned): _1st disbursement done in January 2016__ All funds disbursed (yes/no): _ No__ Any delay? (yes/no): No___ If Yes, reasons for delay & action plan to resolve: n/a___ If Yes, will delay have impact on project completion date (yes/no): _ No __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Brief progress report (actual/planned): Country signed the SSFA in April 2015. 2015 CP data and 2015 Art7 data reported. Ozone day celebrated. NOU supervised the training of 165 RAC technicians and 22 custom officers in 2016. Legal arrangements (actual/planned): Agreement signed in April 2015.First payment: January 2016. All activities under the SSFA are completed (as planned) No__ First mission (actual/planned): _ N/A -TOR completed (actual/planned): _ Yes __ First disbursement date (actual/planned): _1st disbursement done in January 2016__ All funds disbursed (yes/no): _ No__ Any delay? (yes/no): No___ If Yes, reasons for delay & action plan to resolve: n/a___ If Yes, will delay have impact on project completion date (yes/no): _ No __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | AFR | TOG | SEV | 74 | TAS | 27 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-05-01 | 2016-05-01 | 2017-10-01 |  |  | 35000 | 0 | 35000 | 0.49 | 0.0014% | 34999.51 | 35000 | 3499.951 | 4550 | 0 | 0.0637 | 4549.9363 | 4550 | Brief progress report (actual/planned): Country signed the SSFA in April 2016. First payment sent in May 2016. Local consultants hired in June 2016 and survey activities started in June 2016. Legal arrangements (actual/planned): Agreement signed in April 2016. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in May 2016 __ All funds disbursed (yes/no): _ n/a.__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a | Brief progress report (actual/planned): Country signed the SSFA in April 2016. First payment sent in May 2016. Local consultants hired in June 2016 and survey activities started in June 2016. NOU submitted the draft Survey report in January 2017. Legal arrangements (actual/planned): Agreement signed in April 2016. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement done in May 2016 __ All funds disbursed (yes/no): _ n/a.__ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
ONG | UNEP | Extension of the institutional strengthening project (phase IX: 1/2017-12/2018) | Individual | AFR | TOG | SEV | 77 | INS | 28 | A | I |  | 0 |  | 0 |  | 2016-12-01 |  | 2018-12-01 | 2018-12-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | Newly approved project | Brief progress report (actual/planned): Project newly approved. Agreement not signed yet. Legal arrangements (actual/planned): Agreement not signed yet. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ N/A - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _1st disbursement _no __ All funds disbursed (yes/no): _ Final payment _no___ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
FIN | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, first tranche, Tonga) | Multi-Year | ASP | TON | PHA | 63 | TAS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-09-01 | 2015-03-01 |  | 2015-09-01 | 2016-07-01 | 64750 | 0 | 64750 | 64750 | 100% | 0 | 0 | 0 | 8418 | 0 | 8418 | 0 | 0 | Project financially completed. | Project financially completed.
ONG | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, second tranche, Tonga) | Multi-year | ASP | TON | PHA | 74 | TAS | 10 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-04-01 | 2020-05-01 | 2020-12-01 |  |  | 49550 | 0 | 49550 | 5793 | 11.69% | 43757 | 21933 | 4375.7 | 6442 | 0 | 753.1485 | 5688.8515 | 2851.5113 | Brief progress report (actual/planned): The SSFA was signed by UNEP and the Government of Tonga in February 2016. The first payment under the second tranche was made to the country in April 2016. UNEP conducted a misison in September 2016 to follow-up project implementation and jointly delivered update training workshop for customs and enforcement officers. An update customs and enforcement training workshop was organized on 13-14 September 2016 with participation of 30 participants to build awareness and local capacity in the safe handling of flammable refrigerants, which has been available in the PIC region. A RAC expert was recruited to deliver update RAC training workshop. Tonga organized an update RAC training workshops from 9-11 November 2016. Tonga has put in place a regulation to can the import of HCFC-based air-conditioner from 1 January 2016. UNEP worked closely with the NOU to engage multi-stakeholders in the implementation of HPMP, second tranche to synergize HPMP with other on-going environmental policies/projects e.g. PALS, Samoa Pathway. 2015 CP data was submitted to MLFS online. Legal arrangements (actual/planned): The SSFA was signed in February 2016. First Mission: September 2016. TOR completed: Not applicable First disbursement date: April 2016. All funds disbursed (yes/no): No. Any delay? (yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): UNEP keeps regular communications with the country to expedite HPMP implementation as per the agreed work plan.
FIN | Australia | Implementation of the PIC Strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | TON | REF | 36 | TAS | 01 | A | I |  | 0.2 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2005-04-01 |  | 2010-06-01 | 2012-05-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 | 0 | 0 | 1040 | 0 | 1040 | 0 | 0 | completed |  | 2002
FIN | Australia | Implementation of the PIC Strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | TON | REF | 36 | TAS | 03 | A | I |  | 0.9 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2005-04-01 |  | 2008-06-01 | 2012-05-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | completed |  | 2002
FIN | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | TON | SEV | 36 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-03-01 | 2005-04-01 |  | 2006-06-01 | 2009-01-01 | 19700 | 0 | 19700 | 19700 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase II) | Individual | ASP | TON | SEV | 49 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2009-02-01 | 2007-03-01 |  | 2008-12-01 | 2009-01-01 | 6566 | 0 | 6566 | 6566 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase II, second year) | Individual | ASP | TON | SEV | 53 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2009-03-01 | 2008-11-01 |  | 2010-03-01 | 2011-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase III) | Individual | ASP | TON | SEV | 59 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-11-01 | 2011-11-01 |  | 2011-11-01 | 2011-12-01 | 32500 | 27500 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase IV: 12/2011-11/2013) | Individual | ASP | TON | SEV | 64 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-03-01 | 2013-11-01 |  | 2013-11-01 | 2014-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase V: 12/2013-11/2015) | Individual | ASP | TON | SEV | 70 | INS | 09 | A | I |  | 0 |  | 0 |  | 2013-07-01 | 2014-03-01 | 2015-11-01 |  | 2015-11-01 | 2016-02-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
ONG | UNEP | Renewal of institutional strengthening project (phase VI: 12/2015-11/2017) | Individual | ASP | TON | SEV | 74 | INS | 11 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-03-01 | 2017-11-01 | 2018-01-01 |  |  | 60000 | 0 | 60000 | 13657.7 | 22.76% | 46342.3 | 39077.9 | 4634.23 | 0 | 0 | 0 | 0 | 0 | Brief Progress report (actual/planned): The SSFA was signed between UNEP and the Government of Tonga in February 2016. The first payment was made to country in March 2016. The NOU has been responsible for the management of all Montreal Protocol activities. The operation of the NOU was going on well with stable, dedicated and high skilled NOO. The license/quota system has been enforced in 2016. Tong has banned the import of HCFC-based air-conditioner from 1 January 2016. The customs fully enforced this regulation as the HCFC-22 air-conditioners were seized by the customs. NOU also coordinated and facilitated the implementation of HPMP and ODS Alternative Survey. The NOU also organized the 2016 ozone day celebration, and actively joined the regional and global ozone related meetings e.g. the network meeting. 2015 Article 7 and CP data were submitted to the Ozone Secretariat and MLFS respectively. Legal arrangements(actual/planned): The SSFA was signed in February 2016. Initial stages of project implementation(actual/planned): Feb 2016. Intermediate goals achieved (actual/planned): Project progressing Satisfactorily, Compliance (2015) sustained. Project completion and follow up: Not applicable. First disbursement date (actual/planned): March 2016. All funds disbursed (yes/no): No. Any delay?(yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: N/A | Brief Progress report (actual/planned): Country continues to enforce the licensing and quota system and ban the import of HCFC-based air-conditioners. There are 2 remaining payments to be disbursed to the country. The interim progress report for the second payment has been submitted to UNEP for approval and releasing funds. Projecct will be completed in January 2018. IS renewal planned for Ex. Com 80
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | ASP | TON | SEV | 75 | TAS | 12 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-12-01 | 2016-12-01 | 2017-06-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 35000 | 4000 | 5200 | 0 | 0 | 5200 | 4550 | Brief progress report (actual/planned): The SSFA was signed by UNEP and the Government of Tonga in November 2016. The first payment was made to the country in December 2016. NOO attended the training for conducting natiional surveys as part of Thematic workshop for Asia and the Pacific in June 2016. The national stakeholder workshop was organzied during UNEP mission in September 2016. The survey methodology and questionnaire have been finalized and agreed. The local consultant was recruited by the Government to conduct the dada collection. The data collection was on-going. Legal arrangements(actual/planned): The SSFA was signed in November 2016 Initial stages of project implementation(actual/planned): June 2016 . Intermediate goals achieved (actual/planned): Not applicable. Project completion and follow up: Not applicable. First disbursement date (actual/planned): December 2016. All funds disbursed (yes/no): No. Any delay?(yes/no): Yes. If Yes, reasons for delay & action plan to resolve: Delay in drafting and signing of SSFA which is not duplicate with the EC project. If Yes, will delay have impact on project completion date (yes/no): No Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): The local consultant assisted the NOU in the identification of the current use of ODS alternatives by substance/sector and collection of import/export data for the substances for the past a couple of years. The local consultant also provided support in establishing growth patterns in use by substance/sector and in compiling data on available ODS alternatives for various applications. The historical use and forecast of ODS alternatives have been submitted to UNEP for review and comment. The draft report will be prepared based on UNEP comment and the format approved by ExCom decision 75/67 as contained in document UNEP/OzL.Pro/ExCom/75/77/Rev.1.
FIN | UNDP | Project preparation for 1 project in the aerosol sector | Individual | LAC | TRI | ARS | 24 | PRP | 11 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-04-01 | 1998-12-01 |  | 1998-07-01 | 2000-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1998 |  | Investment
FIN | UNDP | Project to phaseout use of CFCs in aerosol filling at Hand Arnold Industries Limited (HAIL) | Individual | LAC | TRI | ARS | 25 | INV | 12 | A | I | CFC | 18 | 18 | 0 | 0 | 1998-07-01 | 1999-09-01 | 2000-08-01 |  | 2004-12-01 | 2005-10-01 | 119570 | 0 | 119570 | 119570 | 100% | 0 | 0 | 0 | 15544.1 | 0 | 15544.1 | 0 | 0 | Completed in 2004. Financially completed in 2007. |  | 1998 |  | Investment
CLO | Canada | Technical assistance to phase out the use of methyl bromide | Individual | LAC | TRI | FUM | 49 | TAS | 19 | A | I | MBR | 0.1 |  | 0 |  | 2006-07-01 |  | 2008-01-01 |  |  | 2009-07-01 | 30000 | -30000 | 0 | 0 |  | 0 |  | 0 | 3900 | -3900 | 0 | 0 |  | Canada will ask for cancellation of project at 58th meeting and return all related funds. Country NOU has agreed to cancellation as it has not been possible for government to sign agreement for over 18 months. |  | 2006 |  | Investment
ONG | UNEP | Technical assistance to phase out the use of methyl bromide | Individual | LAC | TRI | FUM | 65 | TAS | 28 | A | I |  | 0.2 | 0 | 0 | 0 | 2011-11-01 | 2016-12-01 | 2012-11-01 | 2017-04-01 |  |  | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 | Brief progress report (actual/planned): Project experienced a short delay in implementation of activities as NOO was on end of contract leave from Jun to Sep. Country has proritized project and committed to completion within the shortest time possible, without compromising quality. NOU commenced training equipment procurement. ___ Legal arrangements(actual/planned): SSA signed Nov-16___Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): ___ Project completion and follow up: ___ First disbursement date (actual/planned): Dec-16 ___ All funds disbursed (yes/no): No. ___ Any delay?(yes/no): Project recovering from historic delay.___ If Yes, reasons for delay & action plan to resolve: Yes. Remidal action already taken.___ If Yes, will delay have impact on project completion date (yes/no): Project completion date adjusted.___ Any ongoing problems (yes/no): No. ___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): Further consultation with stakeholders held. Training equipment procurement nearing completion. Further areas of training identifed by stakeholders. NOU intends on extending the training beyond project life. another training session planned for Mar and Apr-17. NOU drafting policy in consultation with stakeholders. Complementary to the project (not funded by project), NOU is putting together technical information for the development of a quick tool to support the industry with applying MBr alternatives. ___ Legal arrangements(actual/planned): SSA signed Nov-16___Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned):Training held. Training equipment being procured. Draft policy being developed. ___ Project completion and follow up: ___ First disbursement date (actual/planned): Dec-16 ___ All funds disbursed (yes/no): No. ___ Any delay?(yes/no): Project recovering from historic delay.___ If Yes, reasons for delay & action plan to resolve: Yes. Remidal action already taken.___ If Yes, will delay have impact on project completion date (yes/no): Project completion date adjusted.___ Any ongoing problems (yes/no): No. ___ If Yes, is any action required by ExCom: No.___ |  |  |  |  | 12 and 18 months delays
FIN | UNDP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | LAC | TRI | PHA | 40 | INV | 16 | N | I | CFC | 42.9 | 42.9 | 0 | 0 | 2003-07-01 | 2004-07-01 | 2006-03-01 |  | 2006-12-01 | 2013-10-01 | 220000 | 0 | 220000 | 220000 | 100% | 0 | 0 | 0 | 16500 | 0 | 16500 | 0 | 0 | Financially completed in 2013. |  | 2003 |  | Investment
FIN | UNDP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | LAC | TRI | PHA | 49 | INV | 20 | N | I | CFC | 34.1 | 34.1 | 0 | 0 | 2006-07-01 | 2007-04-01 | 2008-12-01 |  | 2008-12-01 | 2013-10-01 | 240000 | -8413 | 231587 | 231587 | 100% | 0 | 0 | 0 | 18000 | -631 | 17369 | 0 | 0 | Financially completed in 2013. |  | 2006 |  | Investment
FIN | UNDP | Audit for an ongoing terminal phase-out management plan | Individual | LAC | TRI | PHA | 51 | TAS | 22 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-03-01 | 2008-10-01 | 2008-03-01 |  | 2008-12-01 | 2011-11-01 | 20000 | -7261.08 | 12738.92 | 12739 | 100% | -0.08 | 0 | 0 | 1500 | -544.58 | 955.425 | -0.005 | 0 | Completed in 2008. |  | 2007 |  | Non-Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | TRI | PHA | 55 | PRP | 23 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-06-01 | 2009-07-01 |  | 2011-07-01 | 2013-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 6375 | 0 | 6375 | 0 | 0 | Financially completed in 2013. | Completed in 2011. HPMP approved by the 64th Executive Committee Meeting. | 2008 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan (additional funding) | Individual | LAC | TRI | PHA | 59 | PRP | 25 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-11-01 | 2011-04-01 | 2010-11-01 |  | 2012-06-01 | 2013-12-01 | 65000 | -3297.47 | 61702.53 | 61703 | 100% | -0.47 | 0 | 0 | 4875 | -247.31 | 4627.725 | -0.035 | 0 | Financially completed in 2013. | Completed in 2012. No activities in 2013. | 2009 |  | Investment
ONG | UNDP | HCFC phase-out management plan (foam sector) (stage I, first tranche) | Multi-Year | LAC | TRI | PHA | 64 | INV | 26 | N | I | HCFC | 2.5 | 2.5 | 0 | 0 | 2011-07-01 | 2013-08-01 | 2013-07-01 | 2017-01-01 |  |  | 173800 | 0 | 173800 | 121831.68 | 70.1% | 51968.32 | 14250 | 20787.328 | 13035 | 0 | 9137.376 | 3897.624 | 1068.75 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Visit of international expert to TT. 2 reconversions have been completed. Still pending work for the remaining enterprises. Prodoc signed (actual/planned, yes/no and date):Signed earlier Missions undertaken (actual/planned):2 of 2 TOR for consultants/subcontracts completed (actual/planned): 1 of 1 Contract/PO/MOA agreements signed: 0 of 1 First disbursement date (actual/planned): Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | Technical assistance from distance provide to foam sector plan companies. | 2011 |  | Investment
FIN | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | TRI | PHA | 64 | INV | 27 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-12-01 | 2013-07-01 |  | 2015-06-01 | 2016-06-01 | 386100 | 0 | 386100 | 386100 | 100% | 0 | 0 | 0 | 28958 | 0 | 28958 | 0 | 0 | Financially completed in 2016. | Since 2014, local trainings were expanded to end-users. | 2011 |  | Investment
COM | UNDP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | TRI | PHA | 71 | TAS | 30 | N | I | HCFC | 4.2 | 0 | 0 | 0 | 2013-12-01 | 2015-01-01 | 2015-12-01 |  | 2016-12-01 |  | 198000 | 0 | 198000 | 190754.63 | 96.34% | 7245.37 | 860.87 | 6158.5645 | 14850 | 0 | 14306.5973 | 543.4027 | 64.5652 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Trinidad and Tobago has been successfully implementing the HPMP with several activities ongoing. There have been numerous training sessions of technicians (approx. 250) particularly in the use of hydrocarbons as a refrigerant alternative, procurement of refrigerant identifiers for use by the Trinidad and Tobago Bureau of Standards as well as recovery units and tanks for use by the sector, approval of Refrigerant Labelling standards and development of National Guidelines for the Air Conditioning and Refrigeration Sector. There has also been a lot of work done in the realization of the Professional Certification Scheme for Air Conditioning and Refrigeration Technicians which is to launched on April 12, 2017 Prodoc signed (actual/planned, yes/no and date):Signed earlier Missions undertaken (actual/planned):1 of 1 TOR for consultants/subcontracts completed (actual/planned): 2 of 2 Contract/PO/MOA agreements signed: 1 of 1 First disbursement date (actual/planned): Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | Pending payments cleared. | 2013 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage I, third tranche) | Multi-year | LAC | TRI | PHA | 75 | INV | 33 | N | I | HCFC | 0 | 0 | 0 | 0 | 2015-11-01 |  | 2017-12-01 | 2017-12-01 |  |  | 471833 | 0 | 471833 | 0 | 0% | 471833 | 0 | 188733.2 | 35387 | 0 | 0 | 35387 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Trinidad and Tobago has been successfully implementing the HPMP with several activities ongoing. There have been numerous training sessions of technicians (approx. 250) particularly in the use of hydrocarbons as a refrigerant alternative, procurement of refrigerant identifiers for use by the Trinidad and Tobago Bureau of Standards as well as recovery units and tanks for use by the sector, approval of Refrigerant Labelling standards and development of National Guidelines for the Air Conditioning and Refrigeration Sector. There has also been a lot of work done in the realization of the Professional Certification Scheme for Air Conditioning and Refrigeration Technicians which is to launched on April 12, 2017 Prodoc signed (actual/planned, yes/no and date):Signed earlier Missions undertaken (actual/planned):0 of 0 TOR for consultants/subcontracts completed (actual/planned): 0 of 0 Contract/PO/MOA agreements signed: NA First disbursement date (actual/planned): Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve: | Continued work with ARIA and training institutions in TT | 2015 |  | Investment
FIN | USA | MAC demonstration project |  | LAC | TRI | REF | 23 | DEM | 08 | A | I | CFC | 10 |  | 0 |  | 1997-11-01 | 1998-03-01 | 1998-12-01 |  | 1999-05-01 | 2000-05-01 | 117000 | 0 | 117000 | 117000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. Final report will be submitted May 2000. |  | 1997
FIN | UNDP | Implementation of the RMP: Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | LAC | TRI | REF | 23 | TAS | 09 | A | I | CFC | 18.5 | 18.5 | 0 | 0 | 1997-11-01 | 1998-11-01 | 2000-12-01 |  | 2000-12-01 | 2001-08-01 | 213990 | -12116 | 201874 | 201874 | 100% | 0 | 0 | 0 | 27818.7 | -1575.08 | 26243.62 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1997 |  | Investment
FIN | UNEP | Implementation of the RMP: training the trainers of technicians in the refrigeration sector | Individual | LAC | TRI | REF | 23 | TRA | 07 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-11-01 |  | 2002-09-01 | 2003-09-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
FIN | UNEP | Implementation of the RMP: training in monitoring and controlling of ODSs | Individual | LAC | TRI | REF | 23 | TRA | 10 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-01-01 | 1998-02-01 |  | 2002-04-01 | 2003-05-01 | 26500 | 0 | 26500 | 26500 | 100% | 0 | 0 |  | 3445 | 0 | 3445 | 0 | 0
FIN | UNDP | Project preparation for the RMP update | Individual | LAC | TRI | REF | 38 | PRP | 14 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2002-11-01 | 2002-12-01 | 2003-12-01 |  | 2003-07-01 | 2006-06-01 | 13500 | -3905 | 9595 | 9595 | 100% | 0 | 0 | 0 | 1755 | -508 | 1247 | 0 | 0 | Completed in 2003. Financially completed in 2006. |  | 2002 |  | Investment
CLO | IBRD | Preparation of investment projects (1991) |  | LAC | TRI | SEV | 04 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1991-12-01 |  |  | 1991-12-01 | 86843 | -86843 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
CLO | IBRD | Country programme preparation |  | LAC | TRI | SEV | 04 | PRP | 06 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1992-06-01 |  |  | 1992-06-01 | 107561 | -107561 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Training of Government technical staff and preliminary work on country programme | Individual | LAC | TRI | SEV | 04 | TRA | 01 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1992-01-01 | 1992-06-01 |  | 1995-07-01 | 1997-12-01 | 53800 | 102 | 53902 | 53902 | 100% | 0 | 0 | 0 | 6994 | 13.26 | 7007.26 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1991 |  | Non-Investment
FIN | UNDP | Country programme preparation | Individual | LAC | TRI | SEV | 06 | CPG | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-02-01 | 1992-12-01 |  | 1995-07-01 | 1997-12-01 | 25000 | 1200 | 26200 | 26200 | 100% | 0 | 0 | 0 | 3250 | 156 | 3406 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Institutional strengthening for the phase-out of ODSs under the Montreal Protocol | Individual | LAC | TRI | SEV | 20 | INS | 04 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-05-01 | 1998-10-01 |  | 2000-12-01 | 2003-06-01 | 66000 | -5223 | 60777 | 60777 | 100% | 0 | 0 | 0 | 8580 | -678.99 | 7901.01 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1996 | 1999-12-01 | Non-Investment
FIN | UNDP | Project preparation in the aerosol, refrigeration and solvent sectors | Individual | LAC | TRI | SEV | 21 | PRP | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1998-01-01 | 2000-12-01 | 40000 | -4596 | 35404 | 35404 | 100% | 0 | 0 | 0 | 5200 | -597.48 | 4602.52 | 0 | 0 | Completed in 1998. Financially completed in 2000. |  | 1997 |  | Investment
FIN | UNDP | Renewal of institutional strengthening (Phase II) | Individual | LAC | TRI | SEV | 32 | INS | 13 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2000-12-01 | 2001-01-01 | 2003-01-01 |  | 2003-01-01 | 2011-12-01 | 44000 | -3631.6 | 40368.4 | 40368 | 100% | 0.4 | 0 | 0 | 5720 | -472.11 | 5247.84 | 0.05 | 0 | Completed in 2003. |  | 2000 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase 3) | Individual | LAC | TRI | SEV | 38 | INS | 15 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2002-11-01 | 2004-07-01 | 2004-12-01 |  | 2006-12-01 | 2011-12-01 | 57200 | -506.64 | 56693.36 | 56693 | 100% | 0.36 | 0 | 0 | 7436 | -65.86 | 7370.09 | 0.05 | 0 | Completed in 2006. |  | 2002 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase IV) | Individual | LAC | TRI | SEV | 44 | INS | 18 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-12-01 | 2006-01-01 | 2006-12-01 |  | 2008-05-01 | 2011-12-01 | 60000 | -448.48 | 59551.52 | 59552 | 100% | -0.48 | 0 | 0 | 4500 | -34 | 4466.036 | -0.035997 | 0 | Completed in 2008. Financially completed in 2011. |  | 2004 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase V) | Individual | LAC | TRI | SEV | 50 | INS | 21 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2009-05-01 | 2008-11-01 |  | 2012-06-01 | 2014-02-01 | 60000 | -3073 | 56927 | 56927 | 100% | 0 | 0 | 0 | 4500 | -230.48 | 4269.52 | 0 | 0 | Financially completed in 2014. | Completed in 2012. No activities in 2013. | 2006 |  | Non-Investment
COM | UNDP | Extension of the institutional strengthening project (phase VI) | Individual | LAC | TRI | SEV | 59 | INS | 24 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2009-11-01 | 2012-10-01 | 2011-12-01 |  | 2013-12-01 |  | 30000 | 30000 | 60000 | 60000 | 100% | 0 | 0 | 0 | 2250 | 2250 | 4500 | 0 | 0 | Completed in 2013. |  | 2009 |  | Non-Investment
COM | UNDP | Extension of the institutional strengthening project (phase VII: 1/2013-12/2014) | Individual | LAC | TRI | SEV | 68 | INS | 29 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-08-01 | 2014-12-01 |  | 2015-12-01 |  | 60000 | 0 | 60000 | 59981 | 99.97% | 19 | 0 | 16.15 | 4200 | 0 | 4198.67 | 1.33 | 0 | Remarks (Short narrative description of progress made (actual/planned)):Completed in 2015. |  | 2012 |  | Non-investment
ONG | UNDP | Extension of the institutional strengthening project (phase VIII: 1/2015-12/2016) | Individual | LAC | TRI | SEV | 73 | INS | 31 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-11-01 | 2016-01-01 | 2016-12-01 | 2017-01-01 |  |  | 60000 | 0 | 60000 | 22575.43 | 37.63% | 37424.57 | 0 | 14969.828 | 4200 | 0 | 1580.2801 | 2619.7199 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Institutional strengthening activities underway. ODS consumption reports prepared and submitted. Celebration of Ozone Day carried out. 2016 HCFC import quota set. NOU attended regional and global meetings. Prodoc signed (actual/planned, yes/no and date):The agreement has been signed earlier. Missions undertaken (actual/planned):1 of 1 TOR for consultants/subcontracts completed (actual/planned): 2 of 2 Contract/PO/MOA agreements signed: 2 of 2 First disbursement date (actual/planned): 42370Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:Signature of prodoc took longer than expected due to changes in the Government | Annual work plan prepared and discussed with stakeholders. | 2014 |  | Non-Investment
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | LAC | TRI | SEV | 74 | TAS | 32 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-09-01 | 2016-05-01 | 2017-06-01 |  |  | 110000 | 0 | 110000 | 21083.12 | 19.17% | 88916.88 | 77767.94 | 8891.688 | 14300 | 0 | 2740.8056 | 11559.1944 | 10109.8322 | Brief progress report (actual/planned): Regional Consultant to assist country with Survey and Report contracted. Agreement with UNDP to adminster funds through UNDP agreed upon in Oct-16 (this is the traditional mode of operation for the Country). First payment sent via Financial Authorization Sep-16, however the FA required adjustments to allow UNDP to pay directly, vendors authorized by the NOU. Country undertook 2 National Consultations on Trinidad and on Tobago on 12 Dec and 14 Dec. The draft of report was prepared by the NOU and national consultants. It was reviewed and finalized based on the format approved by ExCom decision 75/67 as contained in document UNEP/OzL.Pro/ExCom/75/77/Rev.1. after incorporating inputs/ comments raised during National Stakeholders’ workshops. Final Report submitted 31 Dec. ___ Legal arrangements(actual/planned): SSFA signed Jun-16.___Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): Draft Report completed. Final Report submitted.___ Project completion and follow up: Finalize report through internal Revew and communicate results to country.___ First disbursement date (actual/planned): Sep-16.___ All funds disbursed (yes/no): No. ___ Any delay?(yes/no): No.___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): NO.___ If Yes, is any action required by ExCom: ___ | Brief progress report (actual/planned): Final Report being reveiwed by UN Environment Team. Country submitted request for second payment along with required financial and progress reports. ___ Legal arrangements(actual/planned): SSFA signed Jun-16.___Initial stages of project implementation(actual/planned): ___ Intermediate goals achieved (actual/planned): Final Report submitted.___ Project completion and follow up: Communicate any comments from reveiw, to country. Financially and technically close project.___ First disbursement date (actual/planned): Sep-16.___ All funds disbursed (yes/no): No. ___ Any delay?(yes/no): No.___ If Yes, reasons for delay & action plan to resolve: ___ If Yes, will delay have impact on project completion date (yes/no): ___ Any ongoing problems (yes/no): NO.___ If Yes, is any action required by ExCom: ___
COM | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, first tranche Palau) | Multi-Year | ASP | TTR | PHA | 63 | TAS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2012-04-01 | 2015-03-01 |  | 2014-12-01 |  | 62375 | 0 | 62375 | 60552.78 | 97.08% | 1822.22 | 0 | 1822 | 8109 | 0 | 7872.1041 | 236.8959 | 0 | Project financially completed. | Project financially completed.
ONG | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, second tranche, Palau) | Multi-year | ASP | TTR | PHA | 74 | TAS | 10 | A | I |  | 0.1 |  | 0 |  | 2015-05-01 | 2016-05-01 | 2020-05-01 | 2020-12-01 |  |  | 45625 | 0 | 45625 | 0 | 0% | 45625 | 45625 | 4562.5 | 5931 | 0 | 0 | 5931 | 5931 | Brief progress report (actual/planned): The SSFA was signed by UNEP and the Government of Palau in January 2016. The first payment under the second tranche was made to the country in May 2016. NOU organized a RAC technicians training, which focused on the best management and servicing of equipment using HFC alternative and Hydrocarbons. 25 RAC technicians were trained by the trainer attending the training in Fiji in June 2016 under the regional component. NOU and Custom counterpart also successfully trained 4 new custom officers on how to spot check containers and a proper use of the Identifier to check bulk refrigerant. UNEP worked closely with the NOU to engage multi-stakeholders in the implementation of HPMP, second tranche to synergize HPMP with other on-going environmental policies/projects e.g. PALS, Samoa Pathway. 2015 CP data was submitted to MLFS online. Legal arrangements (actual/planned): The SSFA was signed in January 2016. First Mission: Not yet. TOR completed: Not applicable First disbursement date: May 2016. All funds disbursed (yes/no): No. Any delay? (yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): UNEP keeps regular communications with the country to expedite HPMP implementation as per the agreed work plan. RAC training workshop and customs and enforcement officer training workshop planned for mid 2017. UNEP mission is planned in May 2017.
FIN | Australia | Implementation of the PIC Strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | TTR | REF | 36 | TAS | 01 | A | I |  | 0.3 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2005-04-01 |  | 2008-06-01 | 2012-05-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 | 0 | 0 | 1040 | 0 | 1040 | 0 | 0 | completed |  | 2002
FIN | Australia | Implementation of the PIC Strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | TTR | REF | 36 | TAS | 02 | A | I |  | 1.1 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2005-04-01 |  | 2008-06-01 | 2012-05-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | completed |  | 2002
FIN | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | TTR | SEV | 36 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-03-01 | 2005-04-01 |  | 2006-06-01 | 2010-12-01 | 34000 | 0 | 34000 | 34000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase II) | Individual | ASP | TTR | SEV | 49 | INS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2006-07-01 | 2010-01-01 | 2007-03-01 |  | 2008-12-01 | 2010-12-01 | 11333 | 0 | 11333 | 11333 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase II, second year) | Individual | ASP | TTR | SEV | 53 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-08-01 | 2009-11-01 |  | 2009-12-01 | 2010-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase III) | Individual | ASP | TTR | SEV | 59 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-09-01 | 2011-11-01 |  | 2011-11-01 | 2011-12-01 | 32500 | 27500 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase IV: 12/2011-11/2013) | Individual | ASP | TTR | SEV | 64 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-03-01 | 2013-11-01 |  | 2013-12-01 | 2014-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase V: 12/2013-11/2015) | Individual | ASP | TTR | SEV | 70 | INS | 09 | A | I |  | 0 |  | 0 |  | 2013-07-01 | 2014-04-01 | 2015-11-01 |  | 2015-11-01 | 2016-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
ONG | UNEP | Renewal of institutional strengthening project (phase VI: 12/2015-11/2017) | Individual | ASP | TTR | SEV | 74 | INS | 11 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-05-01 | 2017-11-01 | 2018-02-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 60000 | 6000 | 0 | 0 | 0 | 0 | 0 | Brief Progress report (actual/planned): The SSFA was signed between UNEP and the Government of Palau in January 2016. The first payment was made to country in May 2016. The NOU has been responsible for the management of all Montreal Protocol activities. The operation of the NOU was going on well with stable NOO. The license/quota system has been enforced in 2016. NOU regularly organzied meetings with the stakeholders e.g. customs, importers of ODS to monitor the situation of ODS import and RAC Association. NOU also coordinated and facilitated the implementation of HPMP and ODS Alternative Survey. The NOU also organized the 2016 ozone day celebration, and actively joined the regional and global ozone related meetings e.g. the network meeting. 2015 Article 7 and CP data were submitted to the Ozone Secretariat and MLFS respectively. Legal arrangements(actual/planned): The SSFA was signed in January 2016. Initial stages of project implementation(actual/planned): Dec 2015/Jan 2016. Intermediate goals achieved (actual/planned): Project progressing Satisfactorily, Compliance (2015) sustained. Project completion and follow up: Not applicable. First disbursement date (actual/planned): May 2016. All funds disbursed (yes/no): No. Any delay?(yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: N/A | Brief Progress report (actual/planned): Country continues to enforce the licensing and quota system. There are 2 remaining payments to be disbursed to the country. The interim progress report for the second payment has been submitted to UNEP for approval and releasing funds. Projecct will be completed in February 2018.
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | ASP | TTR | SEV | 75 | TAS | 12 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-07-01 | 2016-12-01 | 2017-06-01 |  |  | 40000 | 0 | 40000 | 5000 | 12.5% | 35000 | 35000 | 3500 | 5200 | 0 | 650 | 4550 | 4550 | Brief progress report (actual/planned): The SSFA was signed by UNEP and the Government of Palau in May 2016. The first payment was made to the country in July 2016. NOO attended the training for conducting natiional surveys as part of Thematic workshop for Asia and the Pacific in June 2016. The survey methodology and questionnaire have been finalized and agreed. The local consultant was recruited by the Government to conduct the dada collection. The data collection was on-going. Legal arrangements(actual/planned): the SSFA was signed in May 2016. Initial stages of project implementation(actual/planned): May 2016. Intermediate goals achieved (actual/planned): Not applicable. Project completion and follow up: Not applicable. First disbursement date (actual/planned): July 2016. All funds disbursed (yes/no): No. Any delay?(yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date (yes/no): N/o. Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): The local consultant assisted the NOU in the identification of the current use of ODS alternatives by substance/sector and collection of import/export data for the substances for the past a couple of years. The local consultant also provided support in establishing growth patterns in use by substance/sector and in compiling data on available ODS alternatives for various applications. The draft report will be prepared based on the format approved by ExCom decision 75/67 as contained in document UNEP/OzL.Pro/ExCom/75/77/Rev.1.
FIN | IBRD | Technical seminar and conversion to non-CFC technology in aerosol sector | Individual | AFR | TUN | ARS | 07 | INV | 04 | N | I | CFC | 50 | 50 | 0 | 0 | 1992-06-01 | 1996-07-01 | 1993-06-01 |  | 1998-03-01 | 1998-06-01 | 239995 | 50000 | 289995 | 289995 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. Completion report provided in June 1998 |  |  | 1997-06-01 | INV | 0
FIN | UNIDO | Phasing out CFCs at Jasminal Laboratories | Individual | AFR | TUN | ARS | 19 | INV | 14 | A | I | CFC | 86 | 86 |  |  | 1996-05-01 | 1997-05-01 | 1997-11-01 |  | 1998-12-01 | 2001-03-01 | 210000 | -77 | 209923 | 209923 | 100% | 0 | 0 |  | 27300 | -53 | 27247 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Satem Parfums et Produits Cosmetiques | Individual | AFR | TUN | ARS | 19 | INV | 15 | A | I | CFC | 29 | 29 |  |  | 1996-05-01 | 1997-04-01 | 1997-11-01 |  | 1998-12-01 | 2000-12-01 | 119500 | 0 | 119500 | 119500 | 100% | 0 | 0 |  | 15535 | 0 | 15535 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at CODIFA | Individual | AFR | TUN | ARS | 22 | INV | 19 | A | I | CFC | 60.25 | 60.25 |  |  | 1997-05-01 | 1997-09-01 | 1998-09-01 |  | 1999-12-01 | 2000-11-01 | 179986 | 0 | 179986 | 179986 | 100% | 0 | 0 |  | 23398 | 0 | 23398 | 0 | 0 | FIN
CLO | UNIDO | Phasing out CFCs at Alki S.A. | Individual | AFR | TUN | ARS | 22 | INV | 20 | A | I |  | 0 | 0 |  |  | 1997-05-01 |  | 1998-09-01 |  |  | 1999-12-01 | 74565 | -74565 | 0 | 0 | #DIV/0! | 0 | 0 |  | 9693 | -9693 | 0 | 0 | 0 | CLO |  |  | 1999-03-01
FIN | UNIDO | Phasing out CFCs at Sogepar | Individual | AFR | TUN | ARS | 22 | INV | 21 | A | I | CFC | 18.15 | 18.15 |  |  | 1997-05-01 | 1998-11-01 | 1998-09-01 |  | 2000-01-01 | 2001-07-01 | 68833 | 0 | 68833 | 68832.64 | 100% | 0.36 | 0 |  | 8948 | -4 | 8944 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFCs at Parhycos, Sfax, Tunisia | Individual | AFR | TUN | ARS | 23 | INV | 25 | A | I | CFC | 10 | 10 |  |  | 1997-11-01 | 1999-04-01 | 1999-02-01 |  | 1999-12-01 | 2001-03-01 | 41195 | 0 | 41195 | 41195 | 100% | 0 | 0 |  | 5355 | -2 | 5353 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs at Laboratoires Parcos | Individual | AFR | TUN | ARS | 28 | INV | 35 | A | I | CFC | 29.8 | 29.8 |  |  | 1999-07-01 | 2000-05-01 | 2001-02-01 |  | 2004-03-01 | 2004-09-01 | 76127 | -469 | 75658 | 75658.39 | 100% | -0.39 | 0 |  | 9897 | -77 | 9820 | 0 | 0 | FIN
FIN | IBRD | Technical assistance and demonstration of non-CFC technology in rigid and flexible foam production | Individual | AFR | TUN | FOA | 07 | INV | 05 | N | I | CFC | 45 | 45 | 0 | 0 | 1992-06-01 | 1995-11-01 | 1993-02-01 |  | 1998-03-01 | 1998-06-01 | 218354.28 | 0 | 218354.28 | 218354.28 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. Completion report provided in June 1998. This project is part of a line-of-grant approval. The total expenditure was covered by the $1.79 million approval. |  |  | 1997-06-01 | INV | 0
FIN | IBRD | Introduction of low-CFC and non-CFC in rigid foams in refrigeration insulation at Tabrid | Individual | AFR | TUN | FOA | 07 | INV | 06 | N | I | CFC | 60 | 60 | 0 | 0 | 1992-06-01 | 1995-11-01 | 1993-06-01 |  | 1997-07-01 | 1998-06-01 | 258844 | 0 | 258844 | 258844 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. Final PCR provided in June 1998 |  |  | 1997-06-01 | INV | 0
FIN | UNIDO | Phasing out CFC-11 at Meublatex | Individual | AFR | TUN | FOA | 19 | INV | 16 | A | I | CFC | 28 | 28 |  |  | 1996-05-01 | 1996-12-01 | 1997-11-01 |  | 1997-10-01 | 2000-07-01 | 105000 | -681 | 104319 | 104319 | 100% | 0 | 0 |  | 13650 | -110 | 13540 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Sud Inter Mousse flexible polyurethane foam plant | Individual | AFR | TUN | FOA | 23 | INV | 23 | A | I | CFC | 102 | 102 |  |  | 1997-11-01 | 1998-03-01 | 1998-12-01 |  | 2001-12-01 | 2003-08-01 | 546920 | -271 | 546649 | 546649.3 | 100% | -0.3 | 0 |  | 71100 | -148 | 70952 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Sotrapoc flexible polyurethane foam plant | Individual | AFR | TUN | FOA | 23 | INV | 24 | A | I | CFC | 20 | 20 |  |  | 1997-11-01 | 1999-07-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 90037 | -1704 | 88333 | 88332.94 | 100% | 0.06 | 0 |  | 11705 | -240 | 11465 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 at Polymousse flexible polyurethane foam plant | Individual | AFR | TUN | FOA | 23 | INV | 26 | A | I | CFC | 35 | 35 |  |  | 1997-11-01 | 1998-12-01 | 1998-12-01 |  | 1998-12-01 | 2001-12-01 | 104343 | -88 | 104255 | 104255.05 | 100% | -0.05 | 0 |  | 13565 | -33 | 13532 | 0 | 0 | FIN
FIN | IBRD | Project preparation in the foam sector |  | AFR | TUN | FOA | 24 | PRP | 28 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1998-12-01 | 1998-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Conversion to LCD technology in the manufacture of polyurethane flexible foam and HCFC-141b with water in polyurethane rigid foam at Sotim | Individual | AFR | TUN | FOA | 25 | INV | 32 | N | I | CFC | 95.3 | 95.3 | 0 | 0 | 1998-07-01 | 2000-11-01 | 2000-08-01 |  | 2004-12-01 | 2007-07-01 | 553400 | -131363.1 | 422036.9 | 422036.9 | 100% | 0 | 0 |  | 71942 | -17077.2 | 54864.79 | 0.01 | 0.01 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Phaseout of CFC-11 by conversion to liquid carbon dioxide technology in the manufacture of flexible polyurethane foam at Supermousse | Individual | AFR | TUN | FOA | 26 | INV | 33 | N | I | CFC | 93.5 | 93.5 | 0 | 0 | 1998-11-01 | 2000-01-01 | 2000-12-01 |  | 2004-12-01 | 2007-07-01 | 529490 | -107453.1 | 422036.9 | 422036.9 | 100% | 0 | 0 |  | 68243.9 | -13849.21 | 54394.68 | 0.01 | 0.01 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam at Coldeq by conversion to a combination of water and HCFC-141b based systems | Individual | AFR | TUN | FOA | 32 | INV | 36 | N | I | CFC | 8.8 | 8.8 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2005-01-01 | 2007-03-01 | 68917 | -4392 | 64525 | 64525 | 100% | 0 | 0 |  | 8959.21 | -570.96 | 8388.25 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam at Bafes by conversion to a combination of water and HCFC-141b based systems | Individual | AFR | TUN | FOA | 32 | INV | 37 | N | I | CFC | 11.7 | 11.7 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2005-01-01 | 2007-03-01 | 91477 | -5148 | 86329 | 86329 | 100% | 0 | 0 |  | 11892.01 | -669.24 | 11222.77 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam at Societe de Construction Industrialisee (SCI) by conversion to a combination of water and HCFC-141b based systems | Individual | AFR | TUN | FOA | 32 | INV | 38 | N | I | CFC | 8.3 | 8.3 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2005-01-01 | 2007-03-01 | 64700 | -5970 | 58730 | 58730 | 100% | 0 | 0 |  | 8411 | -776.1 | 7634.9 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam at Societe Nouvelle de Coupe Industrielle (SNCI) by conversion to a combination of water and HCFC-141b based systems | Individual | AFR | TUN | FOA | 32 | INV | 39 | N | I | CFC | 20.3 | 20.3 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2005-01-01 | 2007-03-01 | 156235 | -15623.5 | 140611.5 | 140611.5 | 100% | 0 | 0 |  | 20310.55 | -2031.06 | 18279.49 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam at Soften by conversion to a combination of water and HCFC-141b based systems | Individual | AFR | TUN | FOA | 32 | INV | 40 | N | I | CFC | 7.5 | 7.5 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 |  | 2005-01-01 | 2007-03-01 | 59079 | -995.9 | 58083.1 | 58083.1 | 100% | 0 | 0 |  | 7680.27 | -129.47 | 7550.8 | 0 | 0 | Project completed. |  |  |  | INV | 0
CLO | IBRD | Project preparation in the foam sector |  | AFR | TUN | FOA | 36 | PRP | 42 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 |  | 2003-04-01 |  |  | 2003-07-01 | 10000 | -10000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 1300 | -1300 | 0 | 0 | 0 | Project prep. cancelled at the 41st ExCom. |  |  |  | Non-INV | 0
FIN | UNIDO | Preparation for HCFC phase-out investment activities (polyurethane foam sector) | Individual | AFR | TUN | FOA | 58 | PRP | 50 | A | I |  | 0 | 0 |  |  | 2009-07-01 | 2010-10-01 | 2010-07-31 |  | 2014-05-01 | 2015-09-01 | 65000 | -2264 | 62736 | 62736.05 | 100% | -0.05 | 0 |  | 4875 | -170 | 4705 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | Preparation for HCFC phase-out investment activities (stage II) (polyurethane foam sector) | Individual | AFR | TUN | FOA | 77 | PRP | 72 | A | I |  | 0 | 0 |  |  | 2016-11-01 |  | 2018-06-30 | 2018-12-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 20000 | 4200 | 0 | 0 | 4200 | 0 | - Project approved at the 77th Meeting of the ExCom in 2016 - Project activities to be initiated first quarter of 2017 | - The identification of national experts and IC is currently taking place, in coordination with the NOU.
FIN | UNIDO | Alternatives to the use of methyl bromide in horticulture at Société Méditeranéene Fruitière | Individual | AFR | TUN | FUM | 24 | DEM | 29 | A | I | MBR | 0 | 0 |  |  | 1998-03-01 | 1998-09-01 | 2000-04-01 |  | 2001-02-01 | 2003-05-01 | 301730 | -11452 | 290278 | 290277.8 | 100% | 0.2 | 0 |  | 39225 | -1549 | 37676 | 0 | 0 | FIN
FIN | UNIDO | Project preparation in the fumigants (dates) sector | Individual | AFR | TUN | FUM | 33 | PRP | 41 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2002-06-01 | 2002-04-01 |  | 2011-12-01 | 2011-12-01 | 25000 | -12728 | 12272 | 12272 | 100% | 0 | 0 |  | 3250 | -1655 | 1595 | 0 | 0 | FIN |  |  |  | INV
COM | UNIDO | Project preparation in the fumigants sector (high moisture dates) | Individual | AFR | TUN | FUM | 71 | PRP | 55 | A | I |  | 0 | 0 |  |  | 2013-12-01 | 2014-04-01 | 2014-12-31 |  | 2014-12-31 |  | 35000 | 0 | 35000 | 31699.19 | 90.57% | 3300.81 | 2787.19 | 1 | 2450 | 0 | 2219 | 231 | 195.1033 | The project was operationally completed. |  |  |  | NON-INV
COM | Italy | Technical assistance for the final phase-out of methyl bromide in the palm dates sector |  | AFR | TUN | FUM | 73 | TAS | 62 | A | I | MBR | 2.2 |  | 0 |  | 2014-11-01 | 2015-12-01 | 2016-12-01 |  | 2016-12-01 |  | 132743 | 0 | 132743 | 132742.82 | 100% | 0.18 | 0 | 0 | 17257 | 0 | 17256.5666 | 0.4334 | 0 | In the year 2016, the bilateral component was primarily used for the purchase, installation, commissioning and related-training on the use of PH3-CO2 generators. 22 companies were identified with the support of the NOU and industrial association and assisted with direct support. The bilateral component was terminated before the year end and the grant is being financially completed. - No delay - No recurring problem - No impact on project completion date - No action required by Executive Committee | Project will be financially completed upon clearing obligations. Additional report to 79th ExCom should not be relevant anymore given the disbursement level has reached 100%. PCR will be prepared and submitted as soon as the UNIDO component is completed. | 2014 |  | Investment |  | To request the submission of additional status report to the 79th meeting to monitor the disbursement rate of approved funds.
ONG | UNIDO | Technical assistance for the final phase-out of methyl bromide in the palm dates sector | Individual | AFR | TUN | FUM | 73 | TAS | 63 | A | I | MBR | 4.4 | 4.4 |  |  | 2014-11-01 | 2015-12-01 | 2015-11-30 | 2017-11-01 |  |  | 267657 | 0 | 267657 | 166115.53 | 62.06% | 101541.47 | 48937.64 | 100000 | 18736 | 0 | 11628 | 7108 | 3426 | - Technology provider as well as international and national experts met continuously during installation of equipment (PH3-CO2 generators) during February and March 2016, under the continuous supervision by NOU and Association. - UNIDO has procured safety equipment (i.e. Ph3 meters and safety masks) for the proper application of the technology. Milestones achieved: Milestone 1: Grant agreement submitted to beneficiary - Yes Milestone 2: Grant agreement signature - Yes Milestone 3: Bids prepared and requested - Yes Milestone 4: Contracts awarded - Yes Milestone 5: Equipment delivered - Yes Milestone 6: Commissioning and trial runs - Yes Milestone 7: De-commissioning and/or destruction of redundant baseline equipment - NA Activities planned but not implemented, reasons and strategy: Some beneficiaries could not complete the conversion of all their chambers on time for the last campaign. Therefore, UNIDO and NOU propose to extend monitoring activities for few more years to make sure the conversion is finalized under control of the project. Actions towards next goals: Monitor beneficiaries and identify their last needs before the next campaign, starting in October. Was there any delay during the reporting year? Some beneficiaries could not complete the conversion of all their facilities on time before the last campaign. Any recurring problem? No Any impact on project completion date: Yes Any action required by Executive Committee? Endorse the extended completion date | - Monitoring mission took place in April 2017. - NOU, UNIDO and association decided to undergo a check at each beneficiary to verify the status of the conversions. Actions towards next goals: - Verify the status of conversions at each beneficiary. - The association has also planned to build a fumigation chamber for SMEs in the Southern part of the country using the same technology. UNIDO and international expert will assist and advise NOU and association on this matter. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV |  | 12 months delays
FIN | IBRD | National ODS phase-out plan (first tranche) | Multiyear | AFR | TUN | PHA | 49 | INV | 47 | N | I | CFC | 169.5 | 169.5 | 0 | 0 | 2006-07-01 | 2008-12-01 | 2008-07-31 |  | 2012-06-01 | 2012-10-01 | 790000 | -360123 | 429877 | 429877 | 100% | 0 | 0 |  | 59250 | -27009 | 32241 | 0 | 0 | Upon closure of the Tunisia ODS Umbrella Project, NCPP has been transferred to UNIDO. 2010 consumption audit submitted to, and balance of funds returned at the 68th Meeting. |  |  |  | INV | 0
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | AFR | TUN | PHA | 55 | PRP | 48 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-10-01 | 2009-07-31 |  | 2014-05-01 | 2015-09-01 | 150000 | -3410 | 146590 | 146590.02 | 100% | -0.02 | 0 |  | 11250 | -256 | 10994 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | IBRD | National ODS phase-out plan (second tranche) | Multiyear | AFR | TUN | PHA | 61 | INV | 51 | N | I | CFC | 172.5 | 172.5 | 0 | 0 | 2010-07-01 |  | 2011-12-31 |  | 2012-06-01 | 2012-10-01 | 345395 | -345395 | 0 | 0 | #DIV/0! | 0 | 0 |  | 25905 | -25905 | 0 | 0 | 0 | Upon closure of the Tunisia ODS Umbrella Project, NCPP has been transferred to UNIDO. 2010 consumption audit submitted to, and balance of funds returned at the 68th Meeting. |  |  |  | INV | 0
FIN | UNIDO | National ODS phase-out plan (second tranche) | Multi-Year | AFR | TUN | PHA | 68 | INV | 54 | A | I | CFC | 172.5 | 172.5 |  |  | 2012-12-01 | 2014-01-01 | 2013-12-31 |  | 2014-03-01 | 2016-04-01 | 705518 | -301571 | 403947 | 403946.95 | 100% | 0.05 | 0 |  | 52914 | -22618 | 30296 | 0 | 0 | The project was financially completed and the balance was returned at the 76th ExCom. |  |  |  | INV
ONG | France | HCFC phase-out management plan (stage I, first tranche) (residential air-conditioning manufacturing sector plan) | Multi-Year | AFR | TUN | PHA | 72 | INV | 57 | A | I | HCFC | 0.4 |  | 0 |  | 2014-05-01 | 2015-12-01 | 2017-05-01 | 2018-05-01 |  |  | 97690 | 0 | 97690 | 16860 | 17.26% | 80830 | 0 | 10000 | 12374 | 0 | 2192 | 10182 | 0 |  | - Selection of participants for the last training sessions. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: Yes Any action required by Executive Committee? No
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (solvent sector plan) | Multi-Year | AFR | TUN | PHA | 72 | INV | 58 | A | I | HCFC | 1.3 | 0 |  |  | 2014-05-01 | 2015-05-01 | 2017-05-31 | 2018-03-01 |  |  | 231920 | 0 | 231920 | 35720.83 | 15.4% | 196199.17 | 8107 | 50000 | 16234 | 0 | 2500 | 13734 | 567 | (-) SOFAP: pilot scale trials have been completed and Novec 71DE has proved to be an appropriate alternative to HCFC-141b. (-) SNCFT: flushing units delivered at beneficiary sites, training completed in March 2016. Milestones achieved: Milestone 1: Yes - SOFAP, laboratory testing yielded results on two alternatives and one of them selected for pilot-scale testing. This test has been completed Milestone 2: Yes - SNCFT, flushing units delivered and training completed . Actions towards next goals: (-) SOFAP: final decision on the technological alternative. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | (-) SOFAP: SOFAP received an offer from its supplier of technology to install a system which does not need to use any solvent. SOFAP will send technical information on this option. (-) SNCFT: flushing units delivered at beneficiary sites, training completed in March 2016. Milestones achieved: Milestone 1: Yes - SOFAP, laboratory testing yielded results on two alternatives and one of them selected for pilot-scale testing. This test has been completed; however, a new alternative has been proposed for the phase-out of HCFC-141b in the company. Actions towards next goals: (-) SOFAP: final decision on the technological alternative. Was there any delay during the reporting year? Yes, due to the proposal of a new alternative. Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | AFR | TUN | PHA | 72 | INV | 59 | A | I | HCFC | 1.4 | 0 |  |  | 2014-05-01 | 2015-02-01 | 2017-05-31 | 2017-12-01 |  |  | 175000 | 0 | 175000 | 116340.46 | 66.48% | 58659.54 | 41500 | 40000 | 12250 | 0 | 8144 | 4106 | 2905 | - Purchase and delivery of equipment and tools for vocational schools. - Train-the-trainers sessions conducted. - Meeting with stakeholders for the definition of Certificate scheme. Agreement on a continued cooperation to finalize a proposal in this sense. Milestones achieved: Milestone 1: Yes - provision of equipment and tools for vocational schools. Actions towards next goals: Provision of equipment and tools for vocational schools. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - ToR for the purchase of equipment and tools for vocational schools. - Work plan for executing project activities for the year 2017 is under development with NOU. Actions towards next goals: - International bidding - Additional train-the-trainers sessions Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
ONG | France | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | AFR | TUN | PHA | 72 | INV | 60 | A | I | HCFC | 0.5 |  | 0 |  | 2014-05-01 |  | 2017-05-01 | 2018-05-01 |  |  | 38000 | 0 | 38000 | 0 | 0% | 38000 |  | 20000 | 4813 | 0 | 0 | 4813 |  |  | - ToR for the purchase of equipment and tools for vocational schools. - Work plan for executing project activities for the year 2017 is under development with NOU. Actions towards next goals: - International bidding - Additional train-the-trainers sessions Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) (residential air-conditioning manufacturing sector plan) | Multi-Year | AFR | TUN | PHA | 72 | INV | 61 | A | I | HCFC | 0.5 | 0 |  |  | 2014-05-01 | 2014-09-01 | 2017-05-31 | 2018-05-31 |  |  | 105965 | 0 | 105965 | 56722.32 | 53.53% | 49242.68 | 0 | 20000 | 7418 | 0 | 3971 | 3447 | 0 | - Training for RAC manufacturing sector was planned and organized. - Meeting with stakeholders to discuss on the current situation of the sector. The issue of high prices of hydrocarbons was raised as the main barriers for the conversion of production lines. Agreement on the organization of a meeting with suppliers in order to negotiate prices. Milestones achieved: Milestone 1: Yes - provision of training. Milestones 2: Yes - discussion with companies on the schedule for conversion. Actions towards next goals: organization of a meeting with suppliers in order to negotiate prices. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: Yes Any action required by Executive Committee? No | - Study tour to China to meet technology suppliers for hydrocarbons based conversions. - Negotiations ongoing between beneficiaries and suppliers Actions towards next goals: UNIDO to rediscuss terms of conversions with the beneficiaries. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: Yes Any action required by Executive Committee? No |  |  | INV
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | AFR | TUN | PHA | 72 | TAS | 56 | A | I | HCFC-22 | 0.4 |  | 0 |  | 2014-05-01 | 2015-06-01 | 2017-05-01 | 2017-12-01 |  |  | 30000 | 0 | 30000 | 134.81 | 0.4494% | 29865.19 | 29865 | 2986.519 | 3900 | 0 | 17.5253 | 3882.4747 | 3882.45 | Brief progress report (actual/planned): Organization of for (4) training sessions in 2016 for customs officers on identification of ODS and ODS based equipment and the legislation. SSFA signed by country in April 2015. First payment sent in Jan. 2016. Legal arrangements (actual/planned): signed in April 2015 (Yes/No): No_ First mission (actual/planned): ___ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): Jan. 2016___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _No_ If Yes, reasons for delay & action plan to resolve: NO__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): Legal arrangements (actual/planned): signed in April 2015 Organization of for (4) training sessions in 2016 for customs officers on identification of ODS and ODS based equipment and the legislation. SSFA signed by country in April 2015. First payment sent in Jan. 2016. First mission (actual/planned): ___ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): Jan. 2016___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _No_ If Yes, reasons for delay & action plan to resolve: NO__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__
ONG | France | HCFC phase-out management plan (stage I, second tranche) (residential air-conditioning manufacturing sector plan) |  | AFR | TUN | PHA | 76 | INV | 66 | N | I |  | 1.5 |  | 0 |  | 2016-05-01 |  | 2018-06-01 |  |  |  | 356397 | 0 | 356397 |  | 0% | 356397 |  |  | 45144 | 0 |  | 45144
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector, project management and audit) | Multi-Year | AFR | TUN | PHA | 76 | INV | 67 | A | I | HCFC | 0.8 | 0 |  |  | 2016-05-01 |  | 2019-05-30 | 2019-07-07 |  |  | 122500 | 0 | 122500 | 0 | 0% | 122500 | 0 | 15000 | 8575 | 0 | 0 | 8575 | 0 | - Project approved at 76th ExCom in 2016. - Further progress depends on the execution of the activities of tranche one, currently ongoing Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | Further progress depends on the execution of the activities of tranche one, currently ongoing Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) (residential air-conditioning manufacturing sector plan) | Multi-Year | AFR | TUN | PHA | 76 | INV | 68 | A | I | HCFC | 1.5 | 0 |  |  | 2016-05-01 |  | 2019-05-30 | 2019-07-07 |  |  | 356396 | 0 | 356396 | 0 | 0% | 356396 | 0 | 10000 | 24948 | 0 | 0 | 24948 | 0 | - Project approved at 76th ExCom in 2016. - Further progress depends on the availability of hydrocarbons compressors on the market at competitive price and also, the execution will be correlated with the results of tranche I implementation, currently on-going Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | Further progress depends on the execution of the activities of tranche one, currently pending Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
ONG | France | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) |  | AFR | TUN | PHA | 76 | INV | 70 | N | I |  | 0.5 |  | 0 |  | 2016-05-01 |  | 2018-06-01 |  |  |  | 38000 | 0 | 38000 |  | 0% | 38000 |  |  | 4813 | 0 |  | 4813
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | Multi-Year | AFR | TUN | PHA | 76 | TAS | 69 | A | I |  | 0.7 |  | 0 |  | 2016-05-01 |  | 2018-06-01 | 2018-06-01 |  |  | 55000 | 0 | 55000 | 0 | 0% | 55000 | 135 | 5500 | 7150 | 0 | 0 | 7150 | 17.55 | Newly approved project | Brief progress report (actual/planned): SSFA drafted and sent to country for signature. Country reported 2015 Art5 data and CP data for 2015. Legal arrangements (actual/planned): not signed yet. All activities under the SSFA are completed (as planned) No___ First mission (actual/planned): _ - Project Completed __ TOR completed (actual/planned): _ n/a __ First disbursement date (actual/planned): _n/a __ All funds disbursed (yes/no): _ Final payment _ Any delay? (yes/no): no ___ If Yes, reasons for delay & action plan to resolve: n/a ___ If Yes, will delay have impact on project completion date (yes/no): _ n/a __ Any ongoing problems (yes/no): _ no __ If Yes, is any action required by ExCom: _ n/a
ONG | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | Individual | AFR | TUN | PHA | 77 | PRP | 71 | A | I |  | 0 | 0 |  |  | 2016-11-01 |  | 2018-06-30 | 2019-12-07 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 20000 | 4200 | 0 | 0 | 4200 | 0 | - Project approved at 77th ExCom in 2016. - Project activities to be initiated first quarter of 2017 | The identification of national experts and IC is currently taking place, in coordination with the NOU.
FIN | IBRD | Maintenance of domestic, commercial and industrial refrigeration systems | Individual | AFR | TUN | REF | 07 | TAS | 07 | N | I | CFC | 42 | 42 | 0 | 0 | 1992-06-01 | 1996-07-01 | 1997-06-01 |  | 1997-12-01 | 1998-06-01 | 32836 | 300000 | 332836 | 332836 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. PCR provided in June 1998 |  |  | 1997-06-01 | INV | 0
FIN | IBRD | Technical assistance for development of HFC-134a-based domestic refrigerators | Individual | AFR | TUN | REF | 08 | TAS | 08 | N | I | CFC | 30 | 30 | 0 | 0 | 1992-10-01 | 1995-11-01 | 1995-04-01 |  | 1997-06-01 | 1998-06-01 | 404658.6 | 0 | 404658.6 | 404658.6 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed. Final completion report provided in June 1998. This project is part of a line-of-grant approval. The total expenditure was covered by the $1.79 million approval. |  |  | 1997-06-01 | INV | 0
FIN | UNIDO | Umbrella project to phase out ODS at the six small refrigerator manufacturers | Individual | AFR | TUN | REF | 19 | INV | 17 | A | I | CFC | 78.5 | 78.5 |  |  | 1996-05-01 | 1996-12-01 | 1997-05-01 |  | 1997-05-01 | 2001-10-01 | 764557 | -124194 | 640363 | 640362.85 | 100% | 0.15 | 0 |  | 99392 | -16277 | 83115 | 0 | 0 | FIN
FIN | UNIDO | Terminal umbrella project to phase out ODS at 7 manufacturers of commercial and domestic refrigerators (Chahed Refrigeration, Sogima, Sotiem, Rei, Frigo BAF, Societe Moderne Refrigeration, Frigo Technique) | Individual | AFR | TUN | REF | 23 | INV | 27 | A | I | CFC | 29 | 29 |  |  | 1997-11-01 | 1998-11-01 | 1998-11-01 |  | 1998-12-01 | 2001-03-01 | 374111 | -1034 | 373077 | 373077 | 100% | 0 | 0 |  | 48634 | -211 | 48423 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a refrigerant management plan | Individual | AFR | TUN | REF | 24 | PRP | 30 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-08-01 | 1999-04-01 |  | 1998-12-01 | 2000-10-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | FIN
FIN | IBRD | Country programme preparation | Individual | AFR | TUN | SEV | 04 | CPG | 02 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-12-01 |  | 1992-12-01 | 1992-12-01 | 58363 | 105240 | 163603 | 163603 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1991) |  | AFR | TUN | SEV | 04 | PRP | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 64748 | -33533 | 31215 | 31215 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1992) |  | AFR | TUN | SEV | 06 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 50000 | -27623 | 22377 | 22377 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Implementation of Governmnet actions (institutional strengthening) | Individual | AFR | TUN | SEV | 08 | INS | 09 | N | I |  | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-07-01 | 1995-10-01 |  | 1998-06-01 | 1998-06-01 | 285312 | 0 | 285312 | 285312 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project complete. Final completion report provided in June 1998. This project is part of a line-of-grant approval. The total expenditure was covered by the $1.79 million approval. |  |  | 1997-06-01 | Non-INV | 0
FIN | IBRD | Country programme preparation | Individual | AFR | TUN | SEV | 09 | CPG | 22 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 8200 | 0 | 8200 | 8200 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1993) |  | AFR | TUN | SEV | 09 | PRP | 10 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 165800 | -3866 | 161934 | 161934 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Supervision of project implementation (1994) |  | AFR | TUN | SEV | 12 | PRP | 11 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 76296 | -26955 | 49341 | 49341 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | AFR | TUN | SEV | 16 | PRP | 12 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 35000 | -3418 | 31582 | 31582 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project supervision completed. |  |  |  | Non-INV | 0
FIN | UNIDO | Preparation of investment projects in the aerosol, foam, domestic refrigeration and solvent sectors | Individual | AFR | TUN | SEV | 17 | PRP | 13 | A | I |  | 0 | 0 |  |  | 1995-07-01 | 1995-11-01 | 1995-11-01 |  | 1998-03-01 | 1999-08-01 | 30000 | -1697 | 28303 | 28303 | 100% | 0 | 0 |  | 3900 | -226 | 3674 | 0 | 0 | FIN
FIN | UNIDO | Project formulation in the aerosol, foam, solvents and methyl bromide sectors | Individual | AFR | TUN | SEV | 21 | PRP | 18 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-09-01 | 1997-08-01 |  | 1999-05-01 | 2000-12-01 | 27150 | -1020 | 26130 | 26130 | 100% | 0 | 0 |  | 3530 | -138 | 3392 | 0 | 0 | FIN |  |  | 1999-12-01
FIN | IBRD | Phase out of ozone depleting substances (renewal of institutional strengthening) | Individual | AFR | TUN | SEV | 25 | INS | 31 | N | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-07-01 | 2000-07-01 |  | 2003-12-01 | 2003-12-01 | 186700 | 0 | 186700 | 186700 | 100% | 0 | 0 |  | 24271 | 0 | 24271 | 0 | 0 | Legislation was drafted, ongoing and completed projects monitored and public awareness campaign was continued. IS renewal requested and approved at the 39th ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | Renewal of institutional strengthening project | Individual | AFR | TUN | SEV | 39 | INS | 43 | N | I | CFC | 20.2 | 20.2 | 0 | 0 | 2003-04-01 | 2003-12-01 | 2005-04-01 |  | 2006-04-01 | 2006-04-01 | 242667 | 0 | 242667 | 242667 | 100% | 0 | 0 |  | 18200.03 | 0 | 18200.02 | 0.01 | 0.01 | Phase III IS completed and IS IV approved at the 48th ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of the country programme update | Individual | AFR | TUN | SEV | 42 | CPG | 44 | A | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-12-01 | 2004-12-01 |  | 2006-07-01 | 2006-07-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 7200 | 0 | 7200 | 0 | 0 | CPU completed and National ODS Phaseout Plan approved at the 49th ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | Extension of institutional strengthening project (phase IV) | Individual | AFR | TUN | SEV | 48 | INS | 46 | N | I | CFC | 20.05 | 20.05 | 0 | 0 | 2006-04-01 | 2008-11-01 | 2008-06-01 |  | 2008-12-01 | 2009-07-01 | 247270 | 0 | 247270 | 247270 | 100% | 0 | 0 |  | 18545 | 0 | 18545 | 0 | 0 | Completed. |  |  |  | Non-INV | 0
FIN | IBRD | Extension of institutional strengthening project (phase V) | Individual | AFR | TUN | SEV | 55 | INS | 49 | N | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-12-01 | 2010-06-30 |  | 2011-06-01 | 2011-09-01 | 247270 | 0 | 247270 | 247270 | 100% | 0 | 0 |  | 18545 | 0 | 18545 | 0 | 0 | Phase V IS completed. IS VI approved at the 61st ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | Extension of institutional strengthening project (phase VI) | Individual | AFR | TUN | SEV | 61 | INS | 52 | N | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2011-12-01 | 2012-06-30 |  | 2012-06-01 | 2012-10-01 | 247270 | 0 | 247270 | 247270 | 100% | 0 | 0 |  | 18545 | 0 | 18545 | 0 | 0 | Phase V completed. IS project transferred to UNIDO at the 66th ExCom meeting. |  |  |  | Non-INV | 0
COM | UNIDO | Extension of institutional strengthening project (phase VII: 7/2012-6/2014) | Individual | AFR | TUN | SEV | 66 | INS | 53 | N | I |  | 0 | 0 |  |  | 2012-04-01 | 2014-07-01 | 2014-06-30 |  | 2015-12-01 |  | 247270 | 0 | 247270 | 173228.77 | 70.06% | 74041.23 | 73500 | 1 | 18545 | 0 | 12992 | 5553 | 5512.5 | The project was operationally completed. |  |  |  | NON-INV
ONG | UNIDO | Extension of institutional strengthening project (phase VIII: 4/2015-4/2017) | Individual | AFR | TUN | SEV | 74 | INS | 64 | N | I |  | 0 | 0 |  |  | 2015-05-01 |  | 2017-04-30 | 2018-04-01 |  |  | 247270 | 0 | 247270 | 0 | 0% | 247270 | 0 | 60000 | 17309 | 0 | 0 | 17309 | 0 | - Implementation was initiated early 2016 since previous phase was still ongoing in 2015. - ToR for contract release were developed and agreed with counterpart. - Contract was issued | NOU is fully staffed and work plan for the year 2017 is under elaboration with counterpart. |  |  | NON-INV
ONG | UNIDO | Survey of ODS alternatives at the national level | Individual | AFR | TUN | SEV | 74 | TAS | 65 | A | I |  | 0 | 0 |  |  | 2015-05-01 | 2016-03-01 | 2016-05-31 | 2017-12-01 |  |  | 110000 | 0 | 110000 | 12961.15 | 11.78% | 97038.85 | 4385.54 | 90000 | 9900 | 0 | 0 | 9900 | 394.6986 | - National consultants were identified and data collection process initiated. - Work plan was reviewed and updated in July 2016 upon bilateral meeting with counterpart. - UNIDO mission took place in October 2016 to assess progress achieved. | - Data collection process continues - Work plan was reviewed and expected deadline was established in July 2017. - Interim reports will be provided until that date. |  |  | NON-INV
FIN | IBRD | Preparation of a project in the solvent sector |  | AFR | TUN | SOL | 27 | PRP | 34 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-31 | 2001-01-01 |  | 2000-12-01 | 2000-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNIDO | Training and awareness workshop in the solvents and process agents (CTC and TCA) sectors | Individual | AFR | TUN | SOL | 45 | TAS | 45 | A | I | CTC | 0.9 | 0.9 |  |  | 2005-04-01 | 2006-09-01 | 2006-04-01 |  | 2007-12-01 | 2009-12-01 | 50000 | -18930 | 31070 | 31070.38 | 100% | -0.38 | 0 |  | 4500 | -1704 | 2796 | 0 | 0 | FIN |  |  | 2007-06-01 | INV
FIN | IBRD | Preparation of investment projects in the aerosol sector |  | EUR | TUR | ARS | 30 | PRP | 60 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 | 0 |  | 1040 | 0 | 1040 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Conversion from CFCs and MCF into HAPs and CO2 for technical aerosols at Beta | Individual | EUR | TUR | ARS | 31 | INV | 66 | N | I |  | 31.2 | 31.2 | 0 | 0 | 2000-07-01 | 2001-02-01 | 2002-01-01 |  | 2001-01-01 | 2001-10-01 | 137456 | 0 | 137456 | 137456 | 100% | 0 | 0 |  | 8247 | 0 | 8247 | 0 | 0 | Project fully implemented and 100% non-CFC production started. Awaiting PCR. |  |  |  | INV | 0
FIN | UNIDO | Preparation of ODS disposal pilot project | Individual | EUR | TUR | DES | 57 | PRP | 92 | A | I |  | 0 | 0 |  |  | 2009-04-01 | 2009-11-01 | 2010-03-31 |  | 2012-05-01 | 2013-04-01 | 60000 | -1752 | 58248 | 58248.21 | 100% | -0.21 | 0 |  | 4500 | -131 | 4369 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | Demonstration project for disposal of unwanted ODS | Individual | EUR | TUR | DES | 66 | DEM | 99 | A | I |  | 0 | 0 |  |  | 2012-04-01 | 2012-06-01 | 2014-04-30 | 2017-12-01 |  |  | 1076250 | 0 | 1076250 | 567716.33 | 52.75% | 508533.67 | 491697.83 | 400000 | 80719 | 0 | 42579 | 38140 | 36877.3372 | We have reviewed the contractual arrangements in order to speed up the disposal of the ODS waste. Was there any delay during the reporting year? Yes Shipment related documentation for waste transportation were taking longer time than initially estimated due to administrative procedures. Actions towards next goals: Disposal of the available waste and completion of the project. Any impact on project completion date: Yes Any action required by Executive Committee? No | Disposal of the available waste is taking place. Project will be completed in 2017. |  |  | INV
FIN | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam insulation panels at Assan Demir ve Sac Sanayi A.S., Tuzla-Istanbul | Individual | EUR | TUR | FOA | 15 | INV | 14 | N | I | CFC | 180 | 250 | 0 | 0 | 1994-12-01 | 1996-04-01 | 1995-12-01 |  | 1998-04-01 | 1998-12-01 | 925000 | 0 | 925000 | 925000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed and fully disbursed in CY98. PCR submitted. |  |  | 1996-12-01 | INV | 0
FIN | UNIDO | Preparation of investment projects in ODS phase out in the foam sector | Individual | EUR | TUR | FOA | 15 | PRP | 11 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-03-01 | 1995-06-01 |  | 2000-04-01 | 2001-07-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | -6 | 6494 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | IBRD | Conversion to CFC-free technology in the mnufacture of rigid polyurethane foam isulation panels at Tek-iz Izolasyon ve Yapi Elemanlari Sanayii, Umnariye-Istanbul | Individual | EUR | TUR | FOA | 18 | INV | 17 | N | I | CFC | 155 | 177 | 0 | 0 | 1995-11-01 | 1996-11-01 | 1996-11-01 |  | 1998-04-01 | 1998-07-01 | 729650 | 0 | 729650 | 729650 | 100% | 0 | 0 |  | 94854.5 | 0 | 94854.5 | 0 | 0 | Project completed and fully disbursed in CY98. PCR submitted. |  |  | 1996-12-01 | INV | 0
CLO | UNIDO | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam insulation panels at Barlan Metal | Individual | EUR | TUR | FOA | 18 | INV | 18 | A | I |  | 0 | 0 |  |  | 1995-11-01 | 1996-07-01 | 1997-05-01 |  |  | 1997-09-01 | 804050 | -802115 | 1935 | 1935 | 100% | 0 | 0 |  | 104527 | -104276 | 251 | 0 | 0 | CLO
FIN | UNIDO | Phasing out of CFC-11 at Urosan Kimiya Sanayii A.S. | Individual | EUR | TUR | FOA | 20 | INV | 22 | A | I | CFC | 135 | 135 |  |  | 1996-10-01 | 1997-02-01 | 1997-10-01 |  | 1999-12-01 | 2002-04-01 | 643500 | -10955 | 632545 | 632544.84 | 100% | 0.16 | 0 |  | 83655 | -1555 | 82100 | 0 | 0 | FIN |  |  | 1999-04-01
FIN | IBRD | Conversion from CFC-11 into carbon dioxide and water for flexible molded foam at Suntas Foam and Mattress Industry and Commerce, Inc. | Individual | EUR | TUR | FOA | 22 | INV | 24 | N | I | CFC | 9.05 | 12.06 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1996-09-01 | 1998-07-01 | 148613 | -5177 | 143436 | 143436 | 100% | 0 | 0 |  | 19319.69 | -579.54 | 18740.15 | 0 | 0 | The project (retroactive) was fully implemented. 100% non-CFC production started. The project is completed and the final report has been submitted to the World Bank. |  |  |  | INV | 0
FIN | IBRD | Conversion from CFC-11 into HCFC-141b at Teba | Individual | EUR | TUR | FOA | 22 | INV | 28 | N | I | CFC | 3.51 | 3.51 | 0 | 0 | 1997-05-01 | 1998-07-01 | 1998-06-01 |  | 1998-11-01 | 1999-02-01 | 27468 | -104 | 27364 | 27364 | 100% | 0 | 0 |  | 3570.84 | -13.52 | 3557.32 | 0 | 0 | The project had been fully implemented. 100% non-CFC production started. The project is completed and the PCR has been submitted. |  |  |  | INV | 0
FIN | IBRD | Conversion from CFC-11 into LCD for flexible slabstock foam at Safas | Individual | EUR | TUR | FOA | 23 | INV | 29 | N | I | CFC | 93.83 | 93.83 | 0 | 0 | 1997-11-01 | 1998-05-01 | 1999-03-01 |  | 1999-09-01 | 1999-12-01 | 530000 | 0 | 530000 | 530000 | 100% | 0 | 0 |  | 68900 | 0 | 68900 | 0 | 0 | Project fully implemented, 100% non-CFC production started. Draft PCR submitted to the Bank. |  |  |  | INV | 0
FIN | UNIDO | Phasing out CFC-11 at Isbir Termoset Plastic San. A.S., Ankara, Turkey | Individual | EUR | TUR | FOA | 23 | INV | 30 | A | I | CFC | 130 | 130 |  |  | 1997-11-01 | 1999-03-01 | 1998-12-01 |  | 2001-04-01 | 2002-09-01 | 501350 | 0 | 501350 | 501350.19 | 100% | -0.19 | 0 |  | 65176 | -45 | 65131 | 0 | 0 | FIN
CLO | UNIDO | Phasing out CFC-11 at Go-Ya Sungar Ltd. Sti. | Individual | EUR | TUR | FOA | 23 | INV | 31 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-11-01 | 1998-12-01 |  |  | 2002-04-01 | 533400 | -313280 | 220120 | 220120.42 | 100% | -0.42 | 0 |  | 69342 | -40772 | 28570 | 0 | 0 | CLO
CLO | IBRD | Conversion from CFC-11 into all-water and HCFC-141b for integral skin foam at Polifleks Sentetik Maddeler Sanayii Ve Ticaret A.S. | Individual | EUR | TUR | FOA | 24 | INV | 33 | N | I |  | 0 | 0 | 0 | 0 | 1998-03-01 |  | 2000-04-01 |  |  | 1999-11-01 | 252558 | -252558 | 0 | 0 | #DIV/0! | 0 | 0 |  | 32832.54 | -32832.54 | 0 | 0 | 0 | Project was canceled. Ownership of the enterprise had changed to 100 % foreign before signing sub-agreement. Funds will be returned at 34th Meeting. |  |  |  | INV | 0
FIN | IBRD | Conversion from CFC-11 into all-water for flexible slabstock foam at IDAS | Individual | EUR | TUR | FOA | 24 | INV | 38 | N | I | CFC | 37 | 37 | 0 | 0 | 1998-03-01 | 1999-02-01 | 2000-04-01 |  | 1998-11-01 | 1999-07-01 | 230510 | -373 | 230137 | 230137 | 100% | 0 | 0 |  | 29966.3 | -48.49 | 29917.81 | 0 | 0 | The project had been fully implemented. 100% non-CFC production started. The project is completed and the PCR has been submitted. |  |  |  | INV | 0
FIN | IBRD | Phaseout of CFC-11 for flexible molded, integral skin and rigid foam at Purplast | Individual | EUR | TUR | FOA | 24 | INV | 39 | N | I | CFC | 54 | 54 | 0 | 0 | 1998-03-01 | 1998-12-01 | 2000-04-01 |  | 1999-11-01 | 2000-11-01 | 551101 | 0 | 551101 | 551101 | 100% | 0 | 0 |  | 71643.13 | 0 | 71643.13 | 0 | 0 | Project fully implemented, 100% non-CFC production started. PCR submitted Jan. 01. |  |  |  | INV | 0
FIN | IBRD | Conversion from CFC-11 into LCD for flexible moulded foam at Elele Doseme Sanayii Ve Ticaret A.S. | Individual | EUR | TUR | FOA | 24 | INV | 40 | N | I | CFC | 41.36 | 41.36 | 0 | 0 | 1998-03-01 | 1999-04-01 | 2000-10-01 |  | 1999-04-01 | 1999-07-01 | 311768 | 0 | 311768 | 311768 | 100% | 0 | 0 |  | 40529.84 | 0 | 40529.84 | 0 | 0 | 100% non-CFC production started. Draft PCR prepared. |  |  |  | INV | 0
FIN | IBRD | Conversion to non-CFC foam blowing agents in the production of polyurethane (PU) insulation panels, spray/in situ foam and one component foams at Izopoli Yapi Elemantari Taahhuet Sanayii ve Ticaret Lt | Individual | EUR | TUR | FOA | 24 | INV | 41 | N | I | CFC | 274 | 274 | 0 | 0 | 1998-03-01 | 1998-12-01 | 2001-04-01 |  | 2000-05-01 | 2000-05-01 | 1141500 | 0 | 1141500 | 1141500 | 100% | 0 | 0 |  | 148395 | 0 | 148395 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Conversion from CFC-11 into all-water for flexible moulded and HCFC-141b for integral skin foam at EPS Entegre Poliuretan Sunger Ve Koltuk San Tic. Ltd. Sti. | Individual | EUR | TUR | FOA | 24 | INV | 42 | N | I | CFC | 11.2 | 11.2 | 0 | 0 | 1998-03-01 | 1999-01-01 | 2000-04-01 |  | 1999-12-01 | 1999-12-01 | 188280 | -270 | 188010 | 188010 | 100% | 0 | 0 |  | 24476.4 | -35.12 | 24441.28 | 0 | 0 | 100% non-CFC production started. Waiting for PCR. |  |  |  | INV | 0
FIN | IBRD | Phase out of CFC-11 for flexible moulded, integral skin and rigid foam at Pimsa Poliuretan Imalat Sanayii Ve Ticaret A.S. | Individual | EUR | TUR | FOA | 24 | INV | 43 | N | I | CFC | 57.9 | 57.9 | 0 | 0 | 1998-03-01 | 1998-07-01 | 2000-04-01 |  | 1999-07-01 | 2000-11-01 | 551501 | 0 | 551501 | 551501 | 100% | 0 | 0 |  | 71695.13 | 0 | 71695.13 | 0 | 0 | Installation completed. 100% non-CFC production started. PCR submitted. |  |  |  | INV | 0
FIN | IBRD | Conversion from CFC-11 into methylene chloride and dop for flexible molded hot cured foam at Teknik Malzeme | Individual | EUR | TUR | FOA | 24 | INV | 44 | N | I | CFC | 17.2 | 17.2 | 0 | 0 | 1998-03-01 | 1998-09-01 | 1999-10-01 |  | 1998-06-01 | 1999-08-01 | 122443 | -22079 | 100364 | 100364 | 100% | 0 | 0 |  | 15917.59 | -2870.27 | 13047.32 | 0 | 0 | The project had been fully implemented. 100% non-CFC production started. The project is completed and the final report has been submitted to the World Bank. |  |  |  | INV | 0
FIN | UNIDO | Preparation of investment project in the rigid foam sub sector | Individual | EUR | TUR | FOA | 24 | PRP | 35 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-09-01 | 1999-04-01 |  | 2000-11-01 | 2001-05-01 | 15000 | -9583 | 5417 | 5417.06 | 100% | -0.06 | 0 |  | 1950 | -1247 | 703 | 0 | 0 | FIN |  |  | 1999-09-01
FIN | UNIDO | Preparation of investment projects in the foam sector (polyurethane) at Sungersan AS and Serra Sunger | Individual | EUR | TUR | FOA | 24 | PRP | 37 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-06-01 | 1999-04-01 |  | 1999-12-01 | 2000-05-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 in manufacturing of flexible polyurethane slabstock foam through the use of CO2 blowing technology at Serra Sunger | Individual | EUR | TUR | FOA | 25 | INV | 47 | A | I | CFC | 86 | 86 |  |  | 1998-07-01 | 1998-12-01 | 2000-02-01 |  | 2000-09-01 | 2001-08-01 | 454358 | 0 | 454358 | 454358.36 | 100% | -0.36 | 0 |  | 59067 | -16 | 59051 | 0 | 0 | FIN
FIN | IBRD | Conversion of CFC-12 to isobutane in the manufacture of polyethylene foam tubing at Thermaflex-Form | Individual | EUR | TUR | FOA | 26 | INV | 51 | N | R | CFC | 37.5 | 37.5 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 1996-08-01 | 1999-06-01 | 124219 | 0 | 124219 | 124219 | 100% | 0 | 0 |  | 16148.47 | 0 | 16148.47 | 0 | 0 | Company started non-CFC production in mid-1996. Subgrant agreement signed in Feb/99. PCR submitted Jan. 01. |  |  |  | INV | 0
FIN | UNIDO | Phasing out CFC-11 in the manufacturing of flexible polyurethane slabstock foam through the use of liquid CO2 blowing technology at Sungersan | Individual | EUR | TUR | FOA | 27 | INV | 52 | A | I | CFC | 78 | 78 |  |  | 1999-03-01 | 1999-12-01 | 2000-10-01 |  | 2000-12-01 | 2003-05-01 | 467397 | 0 | 467397 | 467397 | 100% | 0 | 0 |  | 60762 | 0 | 60762 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 in manufacturing of flexible PU molded foam through the use of CO2 blosing technology at Sungersan, Bursa | Individual | EUR | TUR | FOA | 27 | INV | 53 | A | I | CFC | 30 | 30 |  |  | 1999-03-01 | 1999-12-01 | 2000-10-01 |  | 2000-12-01 | 2002-05-01 | 327374 | 0 | 327374 | 327374.39 | 100% | -0.39 | 0 |  | 42559 | -9 | 42550 | 0 | 0 | FIN
FIN | IBRD | Conversion from CFC-11 into low index additive (LIA) technology for flexible slabstock foam at Elta | Individual | EUR | TUR | FOA | 28 | INV | 55 | N | I | CFC | 21.3 | 21.3 | 0 | 0 | 1999-07-01 | 2001-02-01 | 2001-08-01 |  | 2001-06-01 | 2001-10-01 | 130597 | -20000 | 110597 | 110597 | 100% | 0 | 0 |  | 16977.61 | -2600 | 14377.61 | 0 | 0 | Project fully implemented. 100% non-CFC production started. Awaiting PCR. |  |  |  | INV | 0
FIN | UNIDO | Phasing out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane panels for thermal insulation for cold rooms and cold storages at Izotek | Individual | EUR | TUR | FOA | 28 | INV | 65 | A | I | CFC | 74.8 | 74.8 |  |  | 1999-07-01 | 2000-08-01 | 2001-08-01 |  | 2001-08-01 | 2002-09-01 | 430721 | -4807 | 425914 | 425914.32 | 100% | -0.32 | 0 |  | 55994 | -713 | 55281 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the flexible foam sector | Individual | EUR | TUR | FOA | 30 | PRP | 57 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-05-01 | 2001-04-01 |  | 2001-10-01 | 2002-05-01 | 15000 | -10124 | 4876 | 4876.38 | 100% | -0.38 | 0 |  | 1950 | -1317 | 633 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the rigid foam sector | Individual | EUR | TUR | FOA | 30 | PRP | 58 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2001-09-01 | 2001-04-01 |  | 2002-03-01 | 2002-05-01 | 15000 | -941 | 14059 | 14058.97 | 100% | 0.03 | 0 |  | 1950 | -125 | 1825 | 0 | 0 | FIN
FIN | IBRD | Preparation of project proposal in the foam general sector |  | EUR | TUR | FOA | 30 | PRP | 61 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of projects in the rigid polyurethane foam subsector |  | EUR | TUR | FOA | 30 | PRP | 63 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNIDO | Phasing out CFC-11 in manufacturing of flexible polyurethane slabstock foam through the use of liquid CO2 blowing technology at Espol Sunger Company | Individual | EUR | TUR | FOA | 31 | INV | 68 | A | I | CFC | 95 | 95 |  |  | 2000-07-01 | 2001-09-01 | 2002-08-01 |  | 2004-02-01 | 2004-12-01 | 552297 | 0 | 552297 | 552297.4 | 100% | -0.4 | 0 |  | 70753 | -31 | 70722 | 0 | 0 | FIN
CLO | UNIDO | Preparation of investment project in the rigid foam sector | Individual | EUR | TUR | FOA | 31 | PRP | 67 | A | I |  | 0 | 0 |  |  | 2000-07-01 |  | 2001-07-01 |  |  | 2001-07-01 | 20000 | -20000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 2600 | -2600 | 0 | 0 | 0 | CLO
FIN | IBRD | Conversion from CFC-11 into all-water technology for flexible molded and integral skin foams at Urosan | Individual | EUR | TUR | FOA | 32 | INV | 70 | N | I | CFC | 39.5 | 39.5 | 0 | 0 | 2000-12-01 | 2002-12-01 | 2004-01-01 |  | 2003-03-01 | 2004-12-01 | 291641 | -815.56 | 290825.44 | 290825.44 | 100% | 0 | 0 |  | 37913.33 | -106.02 | 37807.31 | 0 | 0 | Project completed. |  |  | 2004-01-01 | INV | 0
FIN | IBRD | Conversion from CFC-11 into all-water technology for flexible molded and HCFC-141b for integral skin foams at 11 enterprises (Erdogan Rurmenler; KarakayaCelik; Una Polyuretan; Iksan Ltd; Ak-Kom; Karsan; Goldsit; Buoflex; Gervener; Yaris Kabin; Hisarlar) | Individual | EUR | TUR | FOA | 32 | INV | 71 | N | I | CFC | 48.5 | 48.5 | 0 | 0 | 2000-12-01 | 2002-12-01 | 2004-01-01 |  | 2003-06-01 | 2005-07-01 | 398378 | -277445.52 | 120932.48 | 120932.48 | 100% | 0 | 0 |  | 51789.14 | -36067.98 | 15721.22 | -0.06 | -0.06 | Project completed and non-ODS production at all 5 participating companies underway. |  |  | 2004-01-01 | INV | 0
FIN | UNIDO | Phase-out of CFC-11 consumption by conversion to HCFC-141b technology at Purtiz Co. in the manufacture of rigid polyurethane foam for insulating purposes | Individual | EUR | TUR | FOA | 32 | INV | 72 | A | I | CFC | 52.8 | 52.8 |  |  | 2000-12-01 | 2001-11-01 | 2004-01-01 |  | 2003-07-01 | 2004-09-01 | 301094 | -139 | 300955 | 300954.69 | 100% | 0.31 | 0 |  | 39142 | -80 | 39062 | 0 | 0 | FIN
FIN | UNIDO | Preparation for HCFC phase-out investment activities (polyurethane foam sector) | Individual | EUR | TUR | FOA | 58 | PRP | 94 | A | I |  | 0 | 0 |  |  | 2009-07-01 | 2010-04-01 | 2010-07-31 |  | 2011-12-01 | 2011-12-01 | 150000 | -23470 | 126530 | 126530.07 | 100% | -0.07 | 0 |  | 11250 | -1760 | 9490 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNDP | Validation of the use of HFO-1234ze as blowing agent in the manufacture of extruded polystyrene foam boardstock (phase I) | Individual | EUR | TUR | FOA | 60 | DEM | 96 | N | I | HCFC | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-07-01 | 2011-02-01 |  | 2011-12-01 | 2014-03-01 | 165000 | -391 | 164609 | 164609 | 100% | 0 | 0 | 0 | 14850 | -35.19 | 14814.81 | 0 | 0 | Financially completed in 2014. | Completed in 2011. All tests have been completed. An initial draft technology report was prepared in February 2012. The project is considered as completed. The final technology report will be submitted to 67th ExCom | 2010 |  | Investment
ONG | UNIDO | Umbrella project for the phase-out of HCFC-141b from the polyurethane (PU) rigid foam production in the manufacturing of PU insulated sandwich panels and phaseout HCFC-142b and HCFC-22 in the manufacture of extruded polystyrene boardstock | Multi-Year | EUR | TUR | FOA | 62 | INV | 97 | A | I | HCFC | 213.2 | 213.2 |  |  | 2010-12-01 | 2010-12-01 | 2013-06-30 | 2018-12-01 |  |  | 7713490 | 0 | 7713490 | 7275773.21 | 94.33% | 437716.79 | 234556.16 | 150000 | 578512 | 0 | 545683 | 32829 | 17592 | 6 of 7 companies conversion was completed. Completion of conversion at Alufrom is pending due to additional technical adjustments required at the supply system. Final tests were rescheduled for the second half of 2016. IOC contract can be released only after completion of the trials when new technology is operating. Because of that the This caused the completion date is rescheduled for 2017. Any delay in this reporting year: Yes, due to one company's additional adjustments required. Any impact on completion date: Yes. Any action required by Executive Committee? No | There are still technical issues due to required technical adjustments in one of the Companies. Meeting with equipment supplier was taking place in February 2017 at UNIDO HQ and solution for adjusting the raw materials supply piping is under discussion. The technical issues are related to the path of supply pipping system, which had to be deviated from the working area due to safety certification regulations requirements. IOC contract is expected to be paid in 2018 only. Was there any delay during the reporting year? No Any recurring problem? Yes: required technical adjustments at the companies Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
FIN | UNIDO | Preparation of a demonstration project (flowers, tobacco) | Individual | EUR | TUR | FUM | 24 | PRP | 36 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-04-01 | 1999-04-01 |  | 1998-05-01 | 2001-07-01 | 25000 | -1950 | 23050 | 23050 | 100% | 0 | 0 |  | 3250 | -258 | 2992 | 0 | 0 | FIN
FIN | UNIDO | Demonstration project: Alternatives to the use of methyl bromide as a soil fumigant in protected horticulture (tomatoes and cucumbers) and ornamental (carnations) crops | Individual | EUR | TUR | FUM | 25 | DEM | 46 | A | I | MBR | 0 | 0 |  |  | 1998-07-01 | 1999-02-01 | 2000-08-01 |  | 2001-05-01 | 2002-12-01 | 314600 | -9324 | 305276 | 305276.17 | 100% | -0.17 | 0 |  | 40898 | -1275 | 39623 | 0 | 0 | FIN
FIN | IBRD | Project preparation for methy bromide |  | EUR | TUR | FUM | 25 | PRP | 48 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-03-31 | 1999-08-01 |  | 1999-08-01 | 1999-08-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0 | Completed |  |  |  | Non-INV | 0
FIN | IBRD | Introduction of alternatives to methyl bromide in protected strawberry, pepper and eggplant in East Mediterranean region and in strawberry in Aydm province of Turkey | Individual | EUR | TUR | FUM | 29 | INV | 56 | N | I | MBR | 50 | 50 | 0 | 0 | 1999-11-01 | 2000-10-01 | 2002-12-01 |  | 2003-07-01 | 2003-08-01 | 366440 | 0 | 366440 | 366440 | 100% | 0 | 0 |  | 47637.2 | 0 | 47637.2 | 0 | 0 | Project fully implemented. Alternatives to MeBr use in strawberry, pepper and eggplant production determined and results published. |  |  |  | INV | 0
FIN | UNIDO | Preparation of an investment project in the methyl bromide sector (horticulture) | Individual | EUR | TUR | FUM | 30 | PRP | 59 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-07-01 | 2001-04-01 |  | 2001-10-01 | 2002-12-01 | 30000 | -787 | 29213 | 29213.03 | 100% | -0.03 | 0 |  | 3900 | -108 | 3792 | 0 | 0 | FIN
FIN | IBRD | Phase-out methyl bromide in the dried fig sector | Individual | EUR | TUR | FUM | 31 | INV | 69 | N | I | MBR | 30 | 30 | 0 | 0 | 2000-07-01 | 2001-06-02 | 2002-10-01 |  | 2006-06-01 | 2006-12-01 | 479040 | -1980.74 | 477059.26 | 477059.26 | 100% | 0 | 0 |  | 62275.2 | -257.5 | 62017.7 | 0 | 0 | Project completed both physically and financially. Currently, beneficiary uses CO2 and phosphine in fumigation. No more MeBr is in use. |  |  |  | INV | 0
FIN | UNIDO | Phase out of methyl bromide in protected tomato, cucumber and carnation crops (first tranche) | Multi-Year | EUR | TUR | FUM | 35 | INV | 74 | A | I | MBR | 29.2 | 29.2 |  |  | 2001-12-01 | 2002-08-01 | 2002-12-01 |  | 2003-12-01 | 2006-11-01 | 1000000 | 0 | 1000000 | 999999.99 | 100% | 0.01 | 0 |  | 120000 | 0 | 120000 | 0 | 0 | FIN |  |  |  | INV
CLO | IBRD | Project preparation in the methyl bromide sector (storage of hazelnut) |  | EUR | TUR | FUM | 36 | PRP | 77 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 |  | 2003-04-01 |  |  | 2004-12-01 | 40000 | -40000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 5200 | -5200 | 0 | 0 | 0 | Due to reorganization of MARA and personnel changes following a newly elected government funding is returned while Gov. weighs its options on a way forward. |  |  |  | Non-INV | 0
FIN | UNIDO | Phase-out of methyl bromide in protected tomato, cucumber and carnation crops (second tranche) | Multi-Year | EUR | TUR | FUM | 41 | INV | 82 | A | I | MBR | 58 | 58 |  |  | 2003-12-01 | 2005-04-01 | 2005-12-01 |  | 2008-12-01 | 2011-04-01 | 1000000 | -2624 | 997376 | 997375.92 | 100% | 0.08 | 0 |  | 75000 | -197 | 74803 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase-out of methyl bromide in protected tomato, cucumber and carnation crops (third and fourth tranches) | Multi-Year | EUR | TUR | FUM | 47 | INV | 88 | A | I | MBR | 205 | 205 |  |  | 2005-11-01 | 2006-06-01 | 2006-12-01 |  | 2009-11-01 | 2012-09-01 | 1408844 | -76709 | 1332135 | 1332135.31 | 100% | -0.31 | 0 |  | 105663 | -5753 | 99910 | 0 | 0 | FIN |  |  |  | INV
FIN | IBRD | Preparation of projects for the halon recycling |  | EUR | TUR | HAL | 30 | PRP | 62 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2001-12-01 |  | 2001-12-01 | 2001-12-01 | 15000 | -5000 | 10000 | 10000 | 100% | 0 | 0 |  | 1950 | -650 | 1300 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Halon management programme, halon recovery, recycling and banking | Halon Banking | EUR | TUR | HAL | 38 | TAS | 80 | N | I | HAL | 118 | 118 | 0 | 0 | 2002-11-01 | 2008-04-01 | 2005-11-01 |  | 2007-12-01 | 2008-04-01 | 439250 | -6992 | 432258 | 432258 | 100% | 0 | 0 |  | 57102.5 | -908.96 | 56193.54 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Total phase out of CFCs plan: 2001 and 2002 annual programmes | Multiyear | EUR | TUR | PHA | 35 | INV | 75 | N | I | CFC | 97 | 97 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2002-12-01 |  | 2002-12-01 | 2008-04-01 | 3500000 | 0 | 3500000 | 3500000 | 100% | 0 | 0 |  | 295000 | 0 | 295000 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Total phase out of CFCs plan: 2003 annual programme | Multiyear | EUR | TUR | PHA | 38 | INV | 79 | N | I | CFC | 375 | 375 | 0 | 0 | 2002-11-01 | 2003-12-01 | 2003-12-01 |  | 2003-12-01 | 2008-04-01 | 2500000 | 0 | 2500000 | 2500000 | 100% | 0 | 0 |  | 175000 | 0 | 175000 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Total phase-out of CFCs plan: 2004 annual programme | Multiyear | EUR | TUR | PHA | 41 | INV | 81 | N | I | CFC | 218 | 218 | 0 | 0 | 2003-12-01 | 2004-12-01 | 2004-12-01 |  | 2004-12-01 | 2008-04-01 | 1000000 | 0 | 1000000 | 1000000 | 100% | 0 | 0 |  | 150000 | 0 | 150000 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Total phase-out of CFCs plan: 2005 annual programme | Multiyear | EUR | TUR | PHA | 44 | INV | 85 | N | I | CFC | 150 | 166 | 0 | 0 | 2004-12-01 | 2005-01-01 | 2005-12-01 |  | 2005-12-01 | 2008-04-01 | 750000 | -434097 | 315903 | 315903 | 100% | 0 | 0 |  | 45000 | -26046 | 18954 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Total phase-out of CFCs plan: 2006 annual programme | Multiyear | EUR | TUR | PHA | 47 | INV | 87 | N | I | CFC | 150 | 150 | 0 | 0 | 2005-11-01 | 2006-12-01 | 2006-12-01 |  | 2007-12-01 | 2008-04-01 | 750000 | 0 | 750000 | 750000 | 100% | 0 | 0 |  | 30000 | 0 | 30000 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Total phase-out of CFCs plan: 2007 annual programme | Multiyear | EUR | TUR | PHA | 50 | INV | 89 | N | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-12-01 | 2007-11-01 |  | 2007-12-01 | 2008-04-01 | 500000 | 0 | 500000 | 500000 | 100% | 0 | 0 |  | 30000 | 0 | 30000 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | Total phase-out of CFCs plan: Implementation status of 2007AP and verification report for CFC consumption for 2007 | Multiyear | EUR | TUR | PHA | 53 | INV | 90 | N | I |  | 0 | 0 | 0 | 0 | 2007-11-01 |  | 2008-11-30 |  | 2012-06-01 | 2013-06-01 | 0 | 0 | 0 | 0 | #DIV/0! | 0 | 0 |  | 30000 | -10500 | 19500 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | EUR | TUR | PHA | 55 | PRP | 91 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 |  | 2012-12-01 | 2014-04-01 | 195000 | -6430 | 188570 | 188570.43 | 100% | -0.43 | 0 |  | 14625 | -482 | 14143 | 0 | 0 | FIN |  |  |  | NON-INV
COM | UNIDO | HCFC phase-out management plan (stage I, first tranche) (technical assistance for small and medium enterprises in the foam sector) | Multi-Year | EUR | TUR | PHA | 68 | INV | 102 | A | I |  | 16.3 | 16.3 |  |  | 2012-12-01 | 2013-07-01 | 2013-12-31 |  | 2016-12-01 |  | 658470 | 0 | 658470 | 450909.1 | 68.48% | 207560.9 | 207350 | 200000 | 46093 | 0 | 31564 | 14529 | 14514.5 | Equipment commissioning continued in 2016 and was completed by October 2016. Local contracts were agreed to execute SH companies downstream users on the use of new mixtures based on hydrocarbons. - The training programmes were developed and planned with substantive input from SH manufacturers and it included site demonstrations organized by the supplier of alternative mixtures and needs planning over one year to reach most of the users in Turkey. - Relevant activities are ongoing and will be completed in 2017 within the second tranche. | Project completed. Financial closure is ongoing. Activities continuing with the second tranche. |  |  | INV |  | To request the submission of additional status report to the 79th meeting to monitor the completion of training for the project.
COM | UNIDO | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing and monitoring) | Multi-Year | EUR | TUR | PHA | 68 | TAS | 100 | A | I | HCFC | 0 | 0 |  |  | 2012-12-01 | 2013-07-01 | 2013-12-31 |  | 2015-12-01 |  | 149280 | 0 | 149280 | 144419.45 | 96.74% | 4860.55 | 1155.01 | 1 | 10450 | 0 | 10109 | 341 | 80.8507 | The project was operationally completed. |  |  |  | INV
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing) | Multi-Year | EUR | TUR | PHA | 68 | TAS | 101 | A | I |  | 11 | 0 | 0 | 0 | 2012-12-01 | 2015-02-01 | 2017-12-01 | 2017-12-01 |  |  | 103450 | 0 | 103450 | 65075.79 | 62.91% | 38374.21 | 38374.21 | 3837.421 | 13449 | 0 | 8460.1672 | 4988.8328 | 4988.8328 | Brief progress report (actual/planned): Training of customs & enforcement officers was organized in Istanbul, 11-12 May of 2016 (25 participants from six customs points) and in Izmir, 27-28 December 2016 (38 participants from four customs points). That latter was followed by site visits of the Izmir customs zone and Aliaga customs office on 29 December 2016. The training was delivered by the trainers who were trained during previous train-the-trainers workshop and staff of the National Ozone Unit. The UNEP customs manual was translated into Turkish. Legal arrangements(actual/planned): SSFA with the Ministry of Environment and Urbanization of Turkey for the remaining HPMP activities was signed in February 2016. First mission (actual/planned): N.a. TOR completed(actual/planned): N.a. First disbursement date (actual/planned): February 2015 All funds disbursed (yes/no): No Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: N.a. If Yes, will delay have impact on project completion date (yes/no): N.a. Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: No | Brief progress report (actual/planned): Two additional training of customs & enforcement officers were organized in Trakya free zone and Ambarh customs office in Istanbul during the week 30 January - 3 February 2017. Legal arrangements(actual/planned): SSFA with the Ministry of Environment and Urbanization of Turkey for the remaining HPMP activities was signed in February 2016. First mission (actual/planned): N.a. TOR completed(actual/planned): N.a. First disbursement date (actual/planned): February 2015 All funds disbursed (yes/no): No Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: N.a. If Yes, will delay have impact on project completion date (yes/no): N.a. Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: No
ONG | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | Individual | EUR | TUR | PHA | 74 | PRP | 105 | A | I |  | 0 | 0 |  |  | 2015-05-01 |  | 2016-12-31 | 2018-12-01 |  |  | 90000 | 0 | 90000 | 0 | 0% | 90000 | 0 | 40000 | 6300 | 0 | 0 | 6300 | 0 | Data collection process initiated. Consultative meetings held with stakeholders to decide interim reduction steps and the strategy to reach final elimination of HCFCs before the MP schedule. NC identified. It is expected that a first draft of HPMP stage II will be available during the first quarter of 2017. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | IC and NCs selection process for compiling the draft of HPMP stage II project document is on-going in cooperation with the NOU. As there has been administrative restructuring, it is expected that HPMP Stage II will be completed and endorsed in 2018 |  |  | NON-INV
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing and monitoring) | Multi-Year | EUR | TUR | PHA | 75 | INV | 107 | A | I | HCFC | 30.7 | 0 |  |  | 2015-11-01 | 2016-11-01 | 2018-12-01 | 2019-03-01 |  |  | 1970550 | 0 | 1970550 | 13869.78 | 0.7039% | 1956680.22 | 0 | 50000 | 137939 | 0 | 0 | 137939 | 0 | Train the trainer component for service technicians was completed under tranche 1 and training programme for service technicians is pending on the nomination of competent authority in Turkey for technicians certification. Coordination meeting with NOU took place to identify execution of pilot demonstration activities for commercial refrigeration sector. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: Yes, completion date is estimated at Mar 2019. Any action required by Executive Committee? No | Terms of Reference for execution pilot conversions and awareness programme for commercial refrigeration have been achieved and bidding will be initiated for execution of the activities on local market. Sites identification is currently under assessment with the involvement of the Refrigeration Association in Turkey (SOSSIAD). In addition, technical specification was developed for purchase of equipment for servicing sector (bidding is estimated to be completed by July 2017). Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) (technical assistance for small and medium enterprises in the foam sector) | Multi-Year | EUR | TUR | PHA | 75 | INV | 108 | A | I | HCFC | 113.3 | 0 |  |  | 2015-11-01 | 2016-02-01 | 2018-12-01 | 2019-03-01 |  |  | 529450 | 0 | 529450 | 2319.49 | 0.4381% | 527130.51 | 76010 | 100000 | 37062 | 0 | 0 | 37062 | 5320.7 | Equipment commissioning continued in 2016. Local contracts were agreed to execute SH companies downstream users on the use of new mixtures based on hydrocarbons. The training programmes were developed and planned with substantive input from SH manufacturers and they include site demonstrations organized by the supplier of alternative mixtures and needs planning over one year to reach most of the users in Turkey. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: Yes, completion date is estimated at Mar 2019. Any action required by Executive Committee? No | Commissioning of equipment has been achieved early 2017. Training on alternatives is on-going for the down-stream users of 2 SH Companies (Purtek and Purtiz) and these are scheduled to be completed in August 2017. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
FIN | IBRD | Recovery and recycling of CFC-12 at a refrigeration production plant | Individual | EUR | TUR | REF | 07 | TAS | 03 | N | I | CFC | 4 | 4 | 0 | 0 | 1992-06-01 | 1994-05-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 65000 | 0 | 65000 | 65000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The project had been fully implemented, 100% non-CFC production started. The project is completed and the final report has been submitted to the World Bank. |  |  | 1994-12-01 | INV | 0
FIN | IBRD | Recovery and reclamation of CFC-12 from household refrigerators | Individual | EUR | TUR | REF | 07 | TAS | 04 | N | I | CFC | 1 | 0 | 0 | 0 | 1992-06-01 | 1996-10-01 | 1994-06-01 |  | 1996-12-01 | 1997-03-01 | 400000 | -82919.94 | 317080.06 | 317080.06 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The project had been fully implemented, 100% non-CFC production started. The project is completed and the final report has been submitted to the World Bank. |  |  | 1994-12-01 | INV | 0
FIN | IBRD | Introduction of non-ODS technologies in the production of domestic refrigerators at Arcelik A.S. | Individual | EUR | TUR | REF | 08 | INV | 07 | N | I | CFC | 750 | 750 | 0 | 0 | 1992-10-01 | 1994-05-01 | 1995-10-01 |  | 1996-06-01 | 1997-03-01 | 4900000 | -10484 | 4889516 | 4889516.31 | 100% | -0.31 | -0.62 |  | 0 | 0 | 0 | 0 | 0 | The project had been fully implemented, 100% non-CFC production started. The project is completed and the final report has been submitted to the World Bank. |  |  | 1994-12-01 | INV | 0
FIN | IBRD | Engineering assistance for the elimination of ODS used in the production of freezers and coolers at Klimasan Klima Sanayi ve Ticaret A.S. | Individual | EUR | TUR | REF | 15 | INV | 12 | N | I |  | 36.9 | 36.9 | 0 | 0 | 1994-12-01 | 1996-04-01 | 1995-12-01 |  | 1997-01-01 | 1996-12-01 | 690903 | 110665 | 801568 | 801568 | 100% | 0 | 0 |  | 0 | 16669.9 | 16669.9 | 0 | 0 | The project had been fully implemented, 100% non-CFC production started. The project is completed and the final report has been submitted to the world Bank. Additional funds approved for IOC fully disbursed Mar. 01 ($128,230). |  |  | 1994-12-01 | INV | 0
FIN | IBRD | Engineering assistance for the elimination of ODS used in the production of household refrigerators at PEG Profilo Elektrikli Gerecler Sanayii A.S. | Individual | EUR | TUR | REF | 15 | INV | 13 | N | I | CFC | 290 | 290 | 0 | 0 | 1994-12-01 | 1996-02-01 | 1995-12-01 |  | 1996-04-01 | 1996-03-01 | 1578000 | 257747 | 1835747 | 1835747.02 | 100% | -0.02 | -0.02 |  | 0 | 34340.02 | 34340 | 0.02 | 0.02 | The company has achieved 100% non-ODS production. The project is completed and the final report has been submitted to the World Bank. Additional funds approved for IOC fully disbursed Mar. 01 ($264,154). |  |  | 1994-12-01 | INV | 0
CLO | IBRD | Elimination of the use of CFCs in the manufacture of domestic refrigerators at Pekel Teknik Sanyi ve Ticaret A.S. | Individual | EUR | TUR | REF | 18 | INV | 19 | N | R |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1996-05-01 |  |  | 1996-10-01 | 500664 | -500664 | 0 | 0 | #DIV/0! | 0 | 0 |  | 65086.32 | -65086.32 | 0 | 0 | 0 | Project was canceled. Ownership of the enterprise had changed to 100 % foreign before signing sub-agreement. |  |  | 1994-12-01 | INV | 0
FIN | IBRD | Engineering assistance for the elimination of ODS used in the production of freezers, coolers, ice makers, and ice cream machines at UGUR Makinalari Sanayi ve Ticaret, A.S. | Individual | EUR | TUR | REF | 19 | INV | 21 | N | I | CFC | 64.3 | 64.3 | 0 | 0 | 1996-05-01 | 1997-04-01 | 1997-11-01 |  | 1999-03-01 | 1999-07-01 | 1166455 | 0 | 1166455 | 1166455 | 100% | 0 | 0 |  | 151639.15 | 0 | 151639.15 | 0 | 0 | 100% non-CFC production started. Waiting for PCR. |  |  | 1994-12-01 | INV | 0
FIN | IBRD | Conversion from CFC-11, CFC-12 into cyclopentane and HFC-134a for commercial refrigeration at S.F.A. Sogutma Urunleri Sanayi Ve Tekstil Pazariama Ltd. Sti. | Individual | EUR | TUR | REF | 22 | INV | 25 | N | I |  | 25.9 | 25.9 | 0 | 0 | 1997-05-01 | 1998-04-01 | 1999-02-01 |  | 1999-03-01 | 1999-12-01 | 389832 | 0 | 389832 | 389832 | 100% | 0 | 0 |  | 50678.16 | 0 | 50678.16 | 0 | 0 | 100% non-CFC production started. Waiting for PCR. |  |  | 1996-06-01 | INV | 0
FIN | IBRD | Conversion from CFC-11 and CFC-12 into HCFC-141b and HFC-134a at Gumaksan | Individual | EUR | TUR | REF | 22 | INV | 26 | N | I | CFC | 2.3 | 2.3 | 0 | 0 | 1997-05-01 | 1998-04-01 | 1998-06-01 |  | 1998-11-01 | 1999-01-01 | 35195 | 0 | 35195 | 35195 | 100% | 0 | 0 |  | 4575.35 | 0 | 4575.35 | 0 | 0 | Project fully implemented, 100% non-CFC production started. Draft PCR submitted to the Bank. |  |  | 1996-12-01 | INV | 0
FIN | IBRD | Conversion from CFC-11 and CFC-12 into HCFC-141b and HFC-134a at Kulahcioglu | Individual | EUR | TUR | REF | 22 | INV | 27 | N | I | CFC | 4 | 4 | 0 | 0 | 1997-05-01 | 1998-06-01 | 1998-06-01 |  | 1999-03-01 | 1999-06-01 | 60840 | 0 | 60840 | 60840 | 100% | 0 | 0 |  | 7909.2 | 0 | 7909.2 | 0 | 0 | The project is completed 100% non-CFC production started. Waiting for PCR. |  |  | 1996-12-01 | INV | 0
FIN | USA | MACs servicing demonstration project |  | EUR | TUR | REF | 23 | DEM | 32 | A | I | CFC | 12 |  | 0 |  | 1997-11-01 | 1998-04-01 | 1998-12-01 |  | 1999-05-01 | 2000-07-01 | 205000 | 0 | 205000 | 205000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Training workshop and equipment delivery planned for May 99. |  | 1997
FIN | IBRD | Project preparation for commercial refrigeration terminal umbrella project |  | EUR | TUR | REF | 25 | PRP | 45 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-03-31 | 1999-08-01 |  | 1999-08-01 | 1999-08-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 | 0 |  | 15600 | 0 | 15600 | 0 | 0 | Completed |  |  | 1996-04-01 | Non-INV | 0
FIN | UNIDO | Preparation for HCFC phase-out investment activities (refrigeration manufacturing sector) | Individual | EUR | TUR | REF | 58 | PRP | 95 | A | I |  | 0 | 0 |  |  | 2009-07-01 | 2010-09-01 | 2010-07-31 |  | 2012-12-01 | 2014-04-01 | 150000 | -1380 | 148620 | 148619.75 | 100% | 0.25 | 0 |  | 11250 | -104 | 11146 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | IBRD | Country programme preparation | Individual | EUR | TUR | SEV | 06 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1991-06-30 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 13515 | 55074 | 68589 | 68589 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1996-05-01 | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1992) |  | EUR | TUR | SEV | 06 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 217687 | -67459 | 150228 | 150228 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1998-09-01 | Non-INV | 0
FIN | IBRD | Demonstration activities in several sectors |  | EUR | TUR | SEV | 07 | PRP | 05 | N | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1994-10-01 | 1993-06-01 |  | 1999-12-01 | 2000-03-01 | 500000 | -18877 | 481123 | 481123 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 3 demo projects in solvent sector are implemented. 8 demo projects in refrigeration sector completed as of December 31, 1998. 6 demo projects in foam sector is completed as of March 31, 1999. Individual PCRs submitted separately per project code. |  |  |  | Non-INV | 0
FIN | IBRD | Institutional strengthening | Individual | EUR | TUR | SEV | 08 | INS | 06 | N | I |  | 0 | 0 | 0 | 0 | 1992-10-01 | 1995-06-01 | 1997-06-01 |  | 2000-04-01 | 2000-04-01 | 300000 | -33157 | 266843 | 266843 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | IS project extended to accommodate additional work program of ozone unit. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1993) |  | EUR | TUR | SEV | 09 | PRP | 08 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 140400 | 42164 | 182564 | 182564 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Supervision of project implementation (1994) |  | EUR | TUR | SEV | 12 | PRP | 09 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 30000 | -8823 | 21177 | 21177 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Funds utilized for supervision on project implementation. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1994) |  | EUR | TUR | SEV | 13 | PRP | 10 | A | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-09-30 | 1995-07-01 |  | 1994-12-01 | 1994-12-01 | 100000 | -79142 | 20858 | 20858 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation completed. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation/supervision of investment projects ODS I (1995) |  | EUR | TUR | SEV | 16 | PRP | 15 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 43966 | 0 | 43966 | 43966 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation completed. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation/supervision of investment projects ODS II (1995) |  | EUR | TUR | SEV | 16 | PRP | 16 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-31 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 80000 | -7373 | 72627 | 72627 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project preparation completed. |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation |  | EUR | TUR | SEV | 18 | PRP | 20 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-31 | 1996-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0 | Project preparation completed. |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation |  | EUR | TUR | SEV | 21 | PRP | 23 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 96000 | 0 | 96000 | 96000 | 100% | 0 | 0 |  | 12480 | 0 | 12480 | 0 | 0 | Project preparation completed. |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation in the aerosol, foam and recycling sectors |  | EUR | TUR | SEV | 24 | PRP | 34 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1999-06-01 | 1999-06-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0 | Completed |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects in the foam, commercial refrigeration, refrigeration/ recycling, halon, methyl bromide and a demonstration project for a national phase-out. |  | EUR | TUR | SEV | 27 | PRP | 54 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-31 | 2001-01-01 |  | 1999-12-31 | 1999-12-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 | 0 |  | 1040 | 0 | 1040 | 0 | 0 | Completed |  |  |  | Non-INV | 0
FIN | IBRD | Renewal of institutional strengthening | Individual | EUR | TUR | SEV | 32 | INS | 73 | N | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2002-12-01 | 2003-01-01 |  | 2007-12-01 | 2008-04-01 | 200000 | -3641 | 196359 | 196359.49 | 100% | -0.49 | -0.49 |  | 26000 | -473 | 25526.73 | 0.27 | 0.27 | All activities completed and project is physically and financially closed. |  |  |  | Non-INV | 0
FIN | IBRD | Extension of institutional strengthening project (phase III) | Individual | EUR | TUR | SEV | 44 | INS | 86 | N | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-12-01 | 2006-12-01 |  | 2007-12-01 | 2008-04-01 | 260000 | -23601 | 236399 | 236399.08 | 100% | -0.08 | -0.08 |  | 19500 | -1770 | 17729.93 | 0.07 | 0.07 | Field work and information dissemination via workshops and other meetings carried out by MARA. Training programs and other project components all completed. |  |  |  | Non-INV | 0
FIN | UNIDO | Extension of institutional strengthening project (phase IV) | Individual | EUR | TUR | SEV | 58 | INS | 93 | N | I |  | 0 | 0 |  |  | 2009-07-01 | 2009-12-01 | 2010-12-01 |  | 2011-12-01 | 2014-08-01 | 195000 | -7955 | 187045 | 187044.59 | 100% | 0.41 | 0 |  | 14625 | -597 | 14028 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Extension of institutional strengthening project (phase V) | Individual | EUR | TUR | SEV | 64 | INS | 98 | N | I |  | 0 | 0 |  |  | 2011-07-01 | 2012-01-01 | 2013-06-30 |  | 2014-03-01 | 2016-12-01 | 260000 | -6222 | 253778 | 253777.58 | 100% | 0.42 | 0 |  | 19500 | -467 | 19033 | 0 | 0 | The project was financially completed and the balance was returned at the 76th ExCom. |  |  |  | NON-INV
COM | UNIDO | Extension of institutional strengthening project (phase VI: 7/2013-6/2015) | Individual | EUR | TUR | SEV | 70 | INS | 103 | N | I |  | 0 | 0 |  |  | 2013-07-01 | 2013-09-01 | 2015-06-30 |  | 2015-12-01 |  | 260000 | 0 | 260000 | 251065.79 | 96.56% | 8934.21 | 9070.1 | 1 | 18200 | 0 | 17575 | 625 | 634.907 | The project was operationally completed. |  |  |  | NON-INV
ONG | UNIDO | Extension of institutional strengthening project (phase VII: 7/2015-6/2017) | Individual | EUR | TUR | SEV | 74 | INS | 106 | N | I |  | 0 | 0 |  |  | 2015-05-01 | 2015-10-01 | 2017-06-30 | 2017-12-01 |  |  | 260000 | 0 | 260000 | 78522.29 | 30.2% | 181477.71 | 14754.94 | 100000 | 18200 | 0 | 0 | 18200 | 1032.8458 | NOU staff and NC contract for the year 2016 released. Work plan for the year 2016 concluded and activities were executed as per the project document. Awareness activities for the year 2017 were planned. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: Yes, completion date is estimated at Dec 17. Any action required by Executive Committee? No | The NOU is fully staffed. Awareness activities were committed for the year 2017. IS terminal report and extension draft is currently under preparation in view of submission to the 79 ExCom. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | NON-INV
ONG | UNIDO | Survey of ODS alternatives at the national level | Individual | EUR | TUR | SEV | 74 | TAS | 104 | A | I |  | 0 | 0 |  |  | 2015-05-01 | 2016-12-01 | 2016-05-31 | 2017-12-01 |  |  | 130000 | 0 | 130000 | 430.32 | 0.331% | 129569.68 | 2305.43 | 100000 | 11700 | 0 | 0 | 11700 | 207.4887 | Due to administrative changes the process was delayed. 'National consultancy services for survey execution were identified with the involvement of the Refrigeration Association in Turkey. Survey is expected to be finalized in 2017. | National consultancy services for survey execution were identified with the involvement of the Refrigeration Association in Turkey. Bidding is currently organized for the compilation of the Survey and data assessment in regard of future ODS alternatives consumption trends. Survey is expected to be finalized in 2017. |  |  | NON-INV
FIN | IBRD | Umbrella project for 17 enterprises for phaseout of ODS used as solvents | Individual | EUR | TUR | SOL | 25 | INV | 49 | N | I |  | 11.97 | 11.97 | 0 | 0 | 1998-07-01 | 2000-03-01 | 1999-08-01 |  | 2000-10-01 | 2000-10-01 | 415312 | -20098 | 395214 | 395214 | 100% | 0 | 0 |  | 53990.56 | -2612.77 | 51377.79 | 0 | 0 | Project implemented and 100% non-CFC production started. Awaiting PCR. |  |  |  | INV | 0
FIN | IBRD | Conversion of an electronic defluxing process from ODS-solvent cleaning to hydrocarbon/surfactant (semi-aqueous) cleaning at Aselsan AS | Individual | EUR | TUR | SOL | 25 | INV | 50 | N | R | CFC | 3.9 | 3.9 | 0 | 0 | 1998-07-01 | 1999-02-01 | 1999-08-01 |  | 1995-10-01 | 1999-02-01 | 58517 | 0 | 58517 | 58517 | 100% | 0 | 0 |  | 7607.21 | 0 | 7607.21 | 0 | 0 | Company has achieved 100% non-ODS production. Project is completed and draft report submitted to the Bank. |  |  |  | INV | 0
FIN | IBRD | Preparation of projects in the solvent (TCA) sector |  | EUR | TUR | SOL | 30 | PRP | 64 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2001-12-01 |  | 2000-12-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Umbrella project for the phase-out of MCF used as solvent by water cleaning at 21 enterprises | Individual | EUR | TUR | SOL | 35 | INV | 76 | N | I | TCA | 15.4 | 15.4 | 0 | 0 | 2001-12-01 | 2003-11-01 | 2004-01-01 |  | 2005-02-01 | 2005-12-01 | 518693 | -45479.16 | 473213.84 | 473213.84 | 100% | 0 | 0 |  | 67056.23 | -5538.18 | 61517.82 | 0.23 | 0.23 | All 16 projects completed. |  |  |  | INV | 0
FIN | UNIDO | Preparation of a sectoral phase-out project in the solvents sector | Individual | EUR | TUR | SOL | 36 | PRP | 78 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2003-01-01 | 2003-07-01 |  | 2004-09-01 | 2004-12-01 | 50000 | 0 | 50000 | 50000.37 | 100% | -0.37 | 0 |  | 6500 | -2 | 6498 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Terminal umbrella project for phase-out of remaining ozone depleting solvents | Individual | EUR | TUR | SOL | 41 | INV | 83 | A | I | CTC | 24 | 24 |  |  | 2003-12-01 | 2004-05-01 | 2006-12-01 |  | 2005-12-01 | 2007-03-01 | 531644 | -52625 | 479019 | 479018.64 | 100% | 0.36 | 0 |  | 39873 | -3947 | 35926 | 0 | 0 | FIN |  |  |  | INV
FIN | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, first tranche, Tuvalu) | Multi-Year | ASP | TUV | PHA | 63 | TAS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-12-01 | 2015-03-01 |  | 2015-12-01 | 2016-12-01 | 47875 | 0 | 47875 | 47875 | 100% | 0 | 0 |  | 6224 | 0 | 6224 | 0 | 0 | Project financially completed. | Project financially completed.
ONG | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, second tranche, Tuvalu) | Multi-year | ASP | TUV | PHA | 74 | TAS | 11 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-05-01 | 2020-05-01 | 2020-12-01 |  |  | 34925 | 0 | 34925 | 2486.2 | 7.119% | 32438.8 | 20513.8 | 3243.88 | 4540 | 0 | 323.1882 | 4216.8118 | 2666.6472 | Brief progress report (actual/planned): The SSFA was signed by UNEP and the Government of Tuvalu in January 2016. The first payment under the second tranche was made to the country in May 2016. UNEP conducted a misison in September 2016 to follow-up project implementation and jointly delivered update training workshop for customs and enforcement officers. Over30 persons participated and representing both the public and private sectors as well as the customs brokers participated in the workoshop to build awareness and local capacity in the prevention of smuggling and safe handling of flammable refrigerants, which has been available in the PIC region. A RAC expert was recruited to deliver update RAC training workshop, which has been planned in early 2017. UNEP worked closely with the NOU to engage multi-stakeholders in the implementation of HPMP, second tranche to synergize HPMP with other on-going environmental policies/projects e.g. PALS, Samoa Pathway. 2015 CP data was submitted to MLFS online. Legal arrangements (actual/planned): The SSFA was signed in January 2016. First Mission: September 2016. TOR completed: Not applicable First disbursement date: May 2016. All funds disbursed (yes/no): No. Any delay? (yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): The update RAC training workshop was organized from 22-24 February 2017 to strengthen RAC technician capacity in the safe handling of flammable refrigerants, which has been available in the PIC region. UNEP keeps regular communications with the country to expedite HPMP implementation as per the agreed work plan.
FIN | Australia | Implementation of the PIC Strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | TUV | REF | 36 | TAS | 02 | A | I |  | 0.1 | 0 | 0 | 0 | 2002-03-01 | 2003-04-01 | 2005-04-01 |  | 2010-09-01 | 2012-05-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 | 0 | 0 | 1040 | 0 | 1040 | 0 | 0 | completed |  | 2002
FIN | Australia | Implementation of the PIC Strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | TUV | REF | 36 | TAS | 04 | A | I |  | 0.2 | 0 | 0 | 0 | 2002-03-01 | 2003-04-01 | 2005-04-01 |  | 2008-06-01 | 2012-05-01 | 18000 | 0 | 18000 | 18000 | 100% | 0 | 0 | 0 | 2340 | 0 | 2340 | 0 | 0 | completed |  | 2002
FIN | UNEP | Country programme preparation | Individual | ASP | TUV | SEV | 21 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1999-01-01 | 1998-08-01 |  | 2002-03-01 | 2005-12-01 | 40000 | -25000 | 15000 | 15000 | 100% | 0 | 0 |  | 5200 | -3250 | 1950 | 0 | 0 |  |  |  | 1999-12-01
FIN | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | TUV | SEV | 36 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2004-01-01 | 2005-04-01 |  | 2006-06-01 | 2007-06-01 | 17500 | 0 | 17500 | 17500 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (1st year of phase II) | Individual | ASP | TUV | SEV | 50 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-08-01 | 2007-11-01 |  | 2008-11-01 | 2010-12-01 | 7583 | 0 | 7583 | 7583 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (2nd year of phase II) | Individual | ASP | TUV | SEV | 56 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2010-04-01 | 2009-11-01 |  | 2011-01-01 | 2011-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | ASP | TUV | SEV | 62 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-07-01 | 2012-12-01 |  | 2013-12-01 | 2013-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV: 1/2013-12/2014) | Individual | ASP | TUV | SEV | 67 | INS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2013-11-01 | 2014-12-01 |  | 2014-12-01 | 2015-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of the institutional strengthening project (phase V: 1/2015-12/2016) | Individual | ASP | TUV | SEV | 72 | INS | 10 | A | I |  | 0 |  | 0 |  | 2014-05-01 | 2015-07-01 | 2016-12-01 | 2017-06-01 |  |  | 60000 | 0 | 60000 | 39700.92 | 66.17% | 20299.08 | 15799.08 | 2029.908 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The NOU has been responsible for the management of all Montreal Protocol activities. The operation of the NOU was going on well. Although the NOO has been appointed in 2015, the NOO has proven to be a fast learner and catch up all the issues. The license/quota system has been enforced in 2016. NOU also coordinated and facilitated the implementation of HPMP and ODS Alternative Survey. The NOU also organized the 2016 ozone day celebration, and actively joined the regional and global ozone related meetings e.g. the network meeting, OEWG and the MOP meetings. 2015 Article 7 and CP data were submitted to the Ozone Secretariat and MLFS respectively. Legal arrangements(actual/planned): The SSFA was signed April 2015. Initial stages of project implementation(actual/planned): Jan/Apr 2015_ Intermediate goals achieved (actual/planned): _Project progressing Satisfactorily, Compliance (2015) sustained . Project completion and follow up: Not applicable. First disbursement date (actual/planned):July 2015. _ All funds disbursed (yes/no): No. Any delay?(yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): Country continues to enforce the licensing and quota system. Only the fifth (final) payment is to be disbursed to the country upon completion of the IS project phase V. SSFA Phase V to being in March 2017
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | ASP | TUV | SEV | 75 | TAS | 12 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-06-01 | 2016-12-01 | 2017-06-01 |  |  | 40000 | 0 | 40000 | 13793.67 | 34.48% | 26206.33 | 11206.33 | 2620.633 | 5200 | 0 | 1793.1771 | 3406.8229 | 1456.8229 | Brief progress report (actual/planned): The SSFA was signed by UNEP and the Government of Tuvalu in April 2016. The first payment was made to the country in June 2016. NOO attended the training for conducting natiional surveys as part of Thematic workshop for Asia and the Pacific in June 2016. The national stakeholder workshop was organzied during UNEP mission in September 2016. The survey methodology and questionnaire have been finalized and agreed. The local consultant was recruited by the Government to conduct the dada collection. The data collection was on-going. Legal arrangements(actual/planned): The SSFA was signed in April 2016 Initial stages of project implementation(actual/planned): April 2016 . Intermediate goals achieved (actual/planned): Not applicable. Project completion and follow up: Not applicable. First disbursement date (actual/planned): June 2016. All funds disbursed (yes/no): No. Any delay?(yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): UNEP worked with the NOU in the identification of the current use of ODS alternatives by substance/sector and collection of import/export data for the substances for the past a couple of years. UNEP also provided support in establishing growth patterns in use by substance/sector and in compiling data on available ODS alternatives for various applications. The historical use and forecast of ODS alternatives have been submitted to UNEP for review and comment. The draft report will be prepared based on UNEP comment and the format approved by ExCom decision 75/67 as contained in document UNEP/OzL.Pro/ExCom/75/77/Rev.1.
ONG | UNEP | Extension of the institutional strengthening project (phase VI: 1/2017-12/2018) | Individual | ASP | TUV | SEV | 76 | INS | 13 | A | I |  | 0 |  | 0 |  | 2016-05-01 |  | 2018-12-01 | 2018-12-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The project was approved at the 76th ExCom Meeting in May 2016. The SSFA was drafted in consultation with the country. Legal arrangements(actual/planned): Not yet Initial stages of project implementation(actual/planned): Not yet Intermediate goals achieved (actual/planned): Not yet Project completion and follow up: Not applicable. First disbursement date (actual/planned): Not yet. All funds disbursed (yes/no): _No__ Any delay?(yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): UNEP is working with the NOU to finalize the SSFA for IS project phase VI. This is planned for signing in March of 2017
FIN | UNIDO | Preparation of an investment project in the methyl bromide sector | Individual | AFR | UGA | FUM | 30 | PRP | 08 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-10-01 | 2001-04-01 |  | 2001-10-01 | 2002-12-01 | 30000 | -560 | 29440 | 29440.08 | 100% | -0.08 | 0 |  | 3900 | -79 | 3821 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of methyl bromide in cut flowers | Individual | AFR | UGA | FUM | 34 | INV | 08 | A | I | MBR | 30 | 30 |  |  | 2001-07-01 | 2002-10-01 | 2006-12-01 |  | 2006-12-01 | 2006-12-01 | 228800 | -797 | 228003 | 228003.23 | 100% | -0.23 | 0 |  | 29744 | -104 | 29640 | 0 | 0 | FIN |  |  |  | INV
FIN | France | Project preparation for a terminal ODS phase-out management plan | Individual | AFR | UGA | PHA | 50 | PRP | 12 | A | I | CFC | 0 |  | 0 |  | 2006-11-01 | 2007-10-01 | 2007-11-01 |  | 2009-03-01 | 2012-12-01 | 30000 | -2264 | 27736 | 27829 | 100.3% | -93 |  | 0 | 3900 | -294 | 3620 | -14 |  | The French contribution was impelmented by GTZ; project completed.
FIN | France | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | UGA | PHA | 55 | INV | 13 | A | I | CFC | 0 |  | 0 |  | 2008-07-01 | 2008-12-01 | 2010-12-01 |  | 2010-09-01 | 2012-12-01 | 152500 | 0 | 152500 | 152500 | 100% | 0 |  | 0 | 19825 | 0 | 19825 | 0 |  | The French contribution was implemented by GTZ-Proklima. Project completed.
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | UGA | PHA | 56 | PRP | 14 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-08-01 | 2009-11-01 |  | 2013-07-01 | 2016-12-01 | 30000 | -14816 | 15184 | 15184 | 100% | 0 | 0 |  | 3900 | -1926.24 | 1973.76 | 0 | 0 | Project financially completed | Project financially completed
FIN | France | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | UGA | PHA | 59 | INV | 15 | A | I | CFC | 1.9 | 1.9 | 0 |  | 2009-11-01 | 2010-01-01 | 2010-11-01 |  | 2011-04-01 | 2012-12-01 | 62500 | -5571 | 56929 | 57157 | 100.4% | -228 |  | 0 | 8125 | -724 | 7435 | -34 |  | The French contribution was implemented by GTZ-Proklima. Project completed.
FIN | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | UGA | PHA | 68 | INV | 17 | A | I |  | 0 | 0 |  |  | 2012-12-01 | 2014-12-01 | 2016-12-31 |  | 2015-11-01 | 2016-04-01 | 40000 | -23 | 39977 | 39976.69 | 100% | 0.31 | 0 |  | 3600 | -2 | 3598 | 0 | 0 | The project was financially completed and the balance was returned at the 76th ExCom. |  |  |  | INV
COM | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | UGA | PHA | 68 | TAS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2014-12-01 | 2016-12-01 |  | 2016-12-01 |  | 40500 | 0 | 40500 | 9339.24 | 23.06% | 31160.76 | 0 | 6232.152 | 5265 | 0 | 1214.1012 | 4050.8988 | 0 | Brief progress report (actual/planned): The NOU implemented a number of activities under the HPMP. The NOU registered all importers of HCFCs and organized stakeholders meeting to allocate HCFC licenses and quotas. The NOU conducted two training workshops for 30 custom officers to enhance the capacity of the law enforcement officers in monitoring illegal trade. The NOU conducted training for 60 refrigerant technicians. The NOU procured equipment and distributed recovery kits to major workshops and key importers for testing the quality of the refrigerants before they purchase them. The NOU conducted monitoring of the HCFC quotas and illegal importation of ODSs._Legal arrangements (actual/planned The SSFA was drafted and signed by UNEP and the Government of Uganda in July 2013. Any delay (Yes/No): No_ First mission (actual/planned): __N/A_ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): First disbursement was made in October 2013.___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _No_ If Yes, reasons for delay & action plan to resolve: N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__ | Project completed
ONG | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Individual | AFR | UGA | PHA | 71 | TAS | 18 | A | I |  | 0 |  | 0 |  | 2013-12-01 | 2016-05-01 | 2016-05-01 | 2017-03-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 3000 | 3900 | 0 | 0 | 3900 | 0 | Brief progress report (actual/planned): The Terms of Reference (ToR) for hiring the international consultant was prepared, cleared by the management and advertised in 2015. The international consultant was recruited by UNEP to verify the national consumption in relation to the targets as set out in the Agreement between ExCom and Government of Uganda, following the relevant decisions of the ExCom and guidelines for the verification of national consumption targets for the multi-year agreements. The consultant prepared and presented the draft work plan which included timeline for conducting the verification as well as tasks and roles and responsibilities of each concerned stakeholders in the verification process. The consultant also informed the NOU about support/cooperation that was required from various stakeholders. The consultant also reviewed official statistics on import and export maintained by different sources and analyzed and compare those statistics. In addition, the consultant conducted the necessary on-site visits and interviews, and analyzed and cross-check various data collected from different sources. The reports was produced in English and provides detailed data demonstrating and confirming whether the consumption targets in the Agreement were achieved, whether there is existence of an operational licensing and quota system for HCFC imports and exports and whether the system is capable to ensure the country's compliance with the targets as set out in the Agreement between Uganda and the ExCom.The verification report was finalised and submitted to Ex-com 77 | Brief progress report (actual/planned): The project was completed. NOU is implementing the recommendations from the verification report
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | AFR | UGA | PHA | 77 | INV | 22 | A | I |  | 0 | 0 |  |  | 2016-11-01 |  | 2019-12-31 | 2019-12-31 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 0 | 10000 | 3600 | 0 | 0 | 3600 | 0 | Approved on the understanding that if Uganda were to decide to proceed with retrofits and associated servicing to flammable and toxic refrigerants in refrigeration and air-conditioning equipment originally designed for non-flammable substances, it would do so assuming all associated responsibilities and risks and only in accordance with the relevant standards and protocols. | -It is planned to purchase a reclaiming unit and establish a reclaiming center. - The TOR is being prepared. - No delay in implementation - No recurring problem - No impact on project completion date - No action required by Executive Committee
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | AFR | UGA | PHA | 77 | TAS | 21 | A | I |  | 0 |  | 0 |  | 2016-12-01 |  | 2019-12-01 | 2019-12-01 |  |  | 23500 | 0 | 23500 | 0 | 0% | 23500 | 0 | 2350 | 3055 | 0 | 0 | 3055 | 0 | Newly approved project. | Brief progress report (actual/planned): The project was approved in Dec 2016. The licensing and quota system are in place and operational. The NOU registered all importers of HCFCs and organized one stakeholders meeting in Feb 2017 to coordinate and allocate licenses and quotas. The NOU continues to monitor imports and trade of ODS and ODS related equipment. ___ Legal arrangements (actual/planned): The SSFA was drafted and sent to the Government of Uganda for signature. ___Initial stages of project implementation (actual/planned): __Yes_ Intermediate goals achieved (actual/planned): _No__ Project completion and follow up: _Yes__ First disbursement date (actual/planned): __No ____. All funds disbursed (yes/no): No__ Any delay? (yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: __N/A_
FIN | UNDP | Preparation of a recovery and recycling project | Individual | AFR | UGA | REF | 17 | PRP | 03 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-10-01 | 1996-01-01 |  | 1996-06-01 | 1998-12-01 | 12500 | 0 | 12500 | 12500 | 100% | 0 | 0 | 0 | 1625 | 0 | 1625 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | AFR | UGA | REF | 19 | TAS | 05 | A | I | CFC | 3.6 | 3.6 | 0 | 0 | 1996-05-01 | 1997-05-01 | 1997-11-01 |  | 1997-12-01 | 2000-12-01 | 56000 | -17 | 55983 | 55983 | 100% | 0 | 0 | 0 | 7280 | -2.21 | 7277.79 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1996 |  | Investment
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | UGA | REF | 23 | PRP | 06 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1998-03-01 |  | 1998-07-01 | 2000-03-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | UGA | REF | 26 | TAS | 07 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2003-12-01 | 2004-06-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. RMP update approved in Dec 2004
FIN | Germany | Project preparation for a refrigerant management plan update | RMP Update | AFR | UGA | REF | 37 | PRP | 09 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-06-01 | 2003-08-01 |  | 2004-11-01 | 2004-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Project completetd. RMP update approved at 44th ExCom
FIN | France | Implementation of the RMP update | RMP Update | AFR | UGA | REF | 44 | TAS | 11 | A | I | CFC | 10.9 |  | 0 |  | 2004-12-01 | 2005-07-01 | 2007-12-01 |  | 2009-12-01 | 2012-12-01 | 75000 | -12511 | 62489 | 63002 | 100.8% | -513 |  | 0 | 9750 | -1626 | 8202 | -78 |  | The French contribution is implemented by GTZ-Proklima. Project completed.
FIN | UNEP | Country programme preparation | Individual | AFR | UGA | SEV | 04 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-09-01 | 1992-09-01 |  | 1994-06-01 | 1994-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0
FIN | UNEP | Institutional strengthening (establishment of the ODS unit) | Individual | AFR | UGA | SEV | 13 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1995-04-01 | 1997-07-01 |  | 2014-12-01 | 2014-12-01 | 64515 | -34741 | 29774 | 29774 | 100% | 0 | 0 |  | 8387 | -4516 | 3871 | 0 | 0 |  |  |  | 1999-12-01
FIN | UNDP | Project preparation assistance | Individual | AFR | UGA | SEV | 18 | PRP | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-11-01 | 1998-12-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 650 | 0 | 650 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
ONG | UNEP | Institutional strengthening (phase II: 1/2015-12/2016) | Individual | AFR | UGA | SEV | 73 | INS | 19 | A | I |  | 0 |  | 0 |  | 2014-11-01 | 2016-03-01 | 2016-12-01 | 2017-12-01 |  |  | 37226 | 0 | 37226 | 0 | 0% | 37226 | 37226 | 3722.6 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The licensing and quota systems are in place and functioning. The NOU registered all importers of HCFCs and organized one stakeholders meeting in Feb 2016 to coordinate and allocate licenses and quotas. The NOU conducted two inspection visits on importers to assess compliance with allocated quotas. The NOU trained 30 Custom officers and 60 RAC technicians. The NOU submitted 2015 Country Programme and Article 7 Data reports. The NOU celebrated 2016 International Ozone Day and conducted several awareness activities. The NOU also participated in all Montreal Protocol meetings organized in 2016. Legal arrangements(actual/planned The SSFA was drafted and signed by UNEP and the Government of Uganda in December 2015. Initial stages of project implementation(actual/planned):N/A_ Intermediate goals achieved (actual/planned): __N/A_ Project completion and follow up: _N/A__ First disbursement date (actual/planned): March 2016. All funds disbursed (yes/no): NO_ Any delay?(yes/no): _NO__ If Yes, reasons for delay & action plan to resolve: _N/A_ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __NO_ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): The NOU registered all importers of HCFCs and organized one stakeholders meeting in Feb 2017 to coordinate and allocate licenses and quotas. The NOU continues to monitor imports and trade of ODS and ODS related equipment.
ONG | UNIDO | Survey of ODS alternatives at the national level | Individual | AFR | UGA | SEV | 74 | TAS | 20 | A | I |  | 0 | 0 |  |  | 2015-05-01 | 2016-02-01 | 2016-05-31 | 2017-06-01 |  |  | 40000 | 0 | 40000 | 22871.2 | 57.18% | 17128.8 | 5552.94 | 17100 | 3600 | 0 | 0 | 3600 | 499.7646 | National experts were hired and the survey was carried out in 2016. | Survey was submitted in 2017 to the 78th ExCom. |  |  | NON-INV
FIN | UNIDO | Preparation of investment project in aerosol sector at Mansoor Daya | Individual | AFR | URT | ARS | 15 | PRP | 03 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-03-01 | 1995-06-01 |  | 1996-06-01 | 1998-08-01 | 10000 | -1456 | 8544 | 8544 | 100% | 0 | 0 |  | 1300 | -191 | 1109 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFCs at Mansoor Daya Chemicals Ltd. | Individual | AFR | URT | ARS | 18 | INV | 05 | A | I | CFC | 150 | 150 |  |  | 1995-11-01 | 1996-12-01 | 1997-05-01 |  | 1997-12-01 | 1999-08-01 | 417163 | -2138 | 415025 | 415025 | 100% | 0 | 0 |  | 54231 | -363 | 53868 | 0 | 0 | FIN
FIN | UNDP | Project preparation to formulate one flexible foam sector project | Individual | AFR | URT | FOA | 24 | PRP | 09 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-09-01 | 1998-12-01 |  | 1998-12-01 | 2002-03-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1998. Financially completed in 2002. |  | 1998 |  | Investment
CLO | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at H.K. Foam Ltd. | Individual | AFR | URT | FOA | 26 | INV | 10 | A | I | CFC | 2 | 2 | 0 | 0 | 1998-11-01 | 2003-01-01 | 2000-12-01 |  |  | 2003-11-01 | 113700 | -105743 | 7957 | 7957 | 100% | 0 | 0 | 0 | 14781 | -13746.59 | 1034.41 | 0 | 0 | Canceled in 2003. Financially completed in 2003. |  | 1998 |  | Investment
CLO | UNDP | Phaseout of CFC-11 by conversion to methylene chloride in the manufacture of flexible polyurethane foam at Pan Africa Enterprises Ltd. | Individual | AFR | URT | FOA | 26 | INV | 11 | A | I | CFC | 35 | 35 | 0 | 0 | 1998-11-01 | 2000-01-01 | 2000-12-01 |  |  | 2004-03-01 | 213800 | 0 | 213800 | 213800 | 100% | 0 | 0 | 0 | 27794 | 0 | 27794 | 0 | 0 | Canceled in 2002. Financially completed in 2004. |  | 1998 |  | Investment
FIN | UNDP | Phasing out of CFC-11 in the manufacture of flexible slabstock foam by conversion to methylene chloride at Plyfoam Limited | Individual | AFR | URT | FOA | 31 | INV | 13 | A | I | CFC | 39.5 | 39.5 | 0 | 0 | 2000-07-01 | 2002-07-01 | 2003-08-01 |  | 2004-12-01 | 2006-10-01 | 175134 | 0 | 175134 | 175134 | 100% | 0 | 0 | 0 | 22767.42 | 0 | 22767.42 | 0 | 0 | Completed in 2004. Financially completed in 2006. |  | 2000 |  | Investment
CLO | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | AFR | URT | FOA | 57 | PRP | 25 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 |  | 2010-03-01 |  |  | 2010-12-01 | 50000 | -50000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 3750 | -3750 | 0 | 0 | 0 | No specific HCFC-141b consuming foam companies were identified by NOU during 2010 and, thus, no technical visits were to be fielded by UNDP, and the funds are to be returned to the MLF Secretariat in 2011 as PRP is cancelled. |  | 2009 |  | Investment
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | URT | PHA | 50 | PRP | 20 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2007-11-01 |  | 2008-11-01 | 2013-12-01 | 17000 | 0 | 17000 | 17000 | 100% | 0 | 0 |  | 2210 | 0 | 2210 | 0 | 0
FIN | UNDP | Project preparation for a terminal phase-out management plan in the refrigeration servicing sector | Individual | AFR | URT | PHA | 50 | PRP | 21 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-04-01 | 2007-11-01 |  | 2007-12-01 | 2011-11-01 | 12000 | -3240.25 | 8759.75 | 8760 | 100% | -0.25 | 0 | 0 | 900 | -243.02 | 656.9999 | -0.01995 | 0 | Completed in 2007. |  | 2006 |  | Investment
FIN | UNDP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | URT | PHA | 54 | INV | 23 | N | I | CFC | 15.9 | 15.9 | 0 | 0 | 2008-04-01 | 2008-12-01 | 2010-03-01 |  | 2013-12-01 | 2014-08-01 | 204000 | 0 | 204000 | 204000 | 100% | 0 | 0 | 0 | 15300 | 0 | 15300 | 0 | 0 | Financially completed in 2014. | Completed in 2013. UNDP supervision mission held in February 2014. Project is closed and PCR preparation works are underway. | 2008 |  | Investment
FIN | UNEP | Terminal phase-out management plan (first tranche) | Multi-Year | AFR | URT | PHA | 54 | TAS | 22 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-06-01 | 2010-03-01 |  | 2010-03-01 | 2011-06-01 | 131000 | 0 | 131000 | 131000 | 100% | 0 | 0 |  | 17030 | 0 | 17030 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | URT | PHA | 57 | PRP | 26 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-11-01 | 2010-03-01 |  | 2013-07-01 | 2014-07-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 |  | 11050 | 0 | 11050 | 0 | 0
FIN | UNDP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | URT | PHA | 58 | INV | 28 | N | I | CFC | 38.1 | 38.1 | 0 | 0 | 2009-07-01 | 2012-01-01 | 2011-07-01 |  | 2013-12-01 | 2014-02-01 | 72000 | -23802 | 48198 | 48198 | 100% | 0 | 0 | 0 | 5400 | -1785 | 3615 | 0 | 0 | Financially Completed in 2014. | Completed in 2013. UNDP supervision mission held in February 2014. Project is closed and PCR preparation works are underway. | 2009 |  | Investment
FIN | UNEP | Terminal phase-out management plan (second tranche) | Multi-Year | AFR | URT | PHA | 58 | TAS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2009-07-01 | 2009-12-01 | 2010-07-01 |  | 2013-12-01 | 2014-12-01 | 78000 | 0 | 78000 | 78000 | 100% | 0 | 0 |  | 10140 | 0 | 10140 | 0 | 0
FIN | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | URT | PHA | 67 | INV | 30 | A | I | HCFC | 0.1 | 0.1 |  |  | 2012-07-01 | 2013-12-01 | 2015-07-31 |  | 2014-12-14 | 2015-09-01 | 50000 | -125 | 49875 | 49875.09 | 100% | -0.09 | 0 |  | 4500 | -11 | 4489 | 0 | 0 | FIN |  |  |  | INV
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | URT | PHA | 67 | TAS | 31 | A | I |  | 0.1 | 0 | 0 | 0 | 2012-07-01 | 2013-02-01 | 2015-07-01 | 2017-10-01 |  |  | 55000 | 0 | 55000 | 35000 | 63.64% | 20000 | 0 | 2000 | 7150 | 0 | 4550 | 2600 | 0 | Brief progress report (actual/planned): The NOU implemented a number of activities under the HPMP. The NOU registered all importers of HCFCs and organized stakeholders meeting to allocate HCFC licenses and quotas. The NOU conducted two training workshops for 30 custom officers to enhance the capacity of the law enforcement officers in monitoring illegal trade. The NOU conducted training for 60 refrigerant technicians. The NOU procured equipment and distributed recovery kits to major workshops and key importers for testing the quality of the refrigerants before they purchase them. The NOU conducted monitoring of the HCFC quotas and illegal importation of ODSs.Legal arrangements (actual/planned): The SSFA was drafted and signed by UNEP and the Government of Tanzania in November 2012. Any delay (Yes/No): No_ First mission (actual/planned): __First mission by CAP to launch the HPMP and conduct training for technicians was made jointly done with UNIDO in June, 2013._ TOR completed(actual/planned): _N/A__ First disbursement date (actual/planned): First disbursement was made in February 2013.___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _No_ If Yes, reasons for delay & action plan to resolve: N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): The NOU registered all importers of HCFCs and organized one stakeholders meeting in Feb 2017 to coordinate and allocate licenses and quotas. The NOU continues to monitor imports and trade of ODS and ODS related equipment.
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | AFR | URT | PHA | 76 | INV | 35 | A | I | HCFC | 0.2 | 0 |  |  | 2016-05-01 | 2016-10-01 | 2020-05-31 | 2020-05-31 |  |  | 50000 | 0 | 50000 | 36.1 | 0.0722% | 49963.9 | 2000 | 20000 | 4500 | 0 | 3 | 4497 | 180 | Approved on the understanding that if the United Republic of Tanzania were to decide to proceed with retrofits and associated servicing to flammable and toxic refrigerants in refrigeration and air-conditioning equipment originally designed for non flammable substances, it would do so assuming all associated responsibilities and risks and only in accordance with the relevant standards and protocols. | - Mission took place in February 2017 and implementation plan was defined. Action towards next goals: - It is planned to purchase some additional tools for training centers and implement a project for end users. - Draft TORs, Conduct bidding - No delay in implementation - No recurring problem - No impact on project completion date - No action required by Executive Committee |  |  | INV
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | AFR | URT | PHA | 76 | TAS | 34 | A | I |  | 0.2 |  | 0 |  | 2016-05-01 |  | 2020-05-01 | 2020-05-01 |  |  | 33000 | 0 | 33000 | 0 | 0% | 33000 | 0 | 3300 | 4290 | 0 | 0 | 4290 | 0 | Brief progress report (actual/planned): Newly approved project. The NOU registered importers of HCFCs and organized one stakeholders meeting in March 2016 to coordinate and allocate licenses and quotas. The NOU carried out 3 inspection visits to monitor distribution of HCFCs to check compliance with quotas allocated between June and November 2016. The NOU conducted two RAC training workshops and two custom training workshops, and trained 40 technicians and 30 custom officers respectively. The NOU conducted one steering committee meeting to monitor, and coordinate the operations of the NOU. Two public awareness meetings were organized and more than 50 participants. ___ Legal arrangements (actual/planned): The SSFA was drafted by UNEP and sent to the Government of Tanzania for signature. ___Initial stages of project implementation (actual/planned): __Yes_ Intermediate goals achieved (actual/planned): _No__ Project completion and follow up: _No__ First disbursement date (actual/planned): No. All funds disbursed (yes/no): No__ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: __N/A_ | Brief progress report (actual/planned): The NOU registered all importers of HCFCs and organized one stakeholders meeting in Feb 2017 to coordinate and allocate licenses and quotas. The NOU continues to monitor imports and trade of ODS and ODS related equipment.
FIN | UNIDO | Preparatory assistance for phase out of ODS in the domestic refrigeration. production | Individual | AFR | URT | REF | 15 | PRP | 02 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-03-01 | 1995-06-01 |  | 1995-05-01 | 1996-05-01 | 10000 | -51 | 9949 | 9949 | 100% | 0 | 0 |  | 1300 | -9 | 1291 | 0 | 0 | FIN
CLO | UNIDO | Phasing out of CFCs at Tanzania Domestic Appliance Manufacturers Ltd. | Individual | AFR | URT | REF | 18 | INV | 06 | A | I | CFC | 0 | 0 |  |  | 1995-11-01 | 1996-03-01 | 1997-03-01 |  |  | 2002-12-01 | 592790 | -101002 | 491788 | 491788.45 | 100% | -0.45 | 0 |  | 77063 | -13232 | 63831 | 0 | 0 | CLO |  |  | 1999-12-01
CLO | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | AFR | URT | REF | 22 | TAS | 08 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  |  | 2001-12-01 | 161554 | -153795 | 7759 | 7759 | 100% | 0 | 0 | 0 | 21002.02 | -19993 | 1009.02 | 0 | 0 | Canceled in 2000. Financially completed in 2001. |  | 1997 |  | Investment
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | URT | REF | 26 | TAS | 12 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2004-12-01 | 2005-09-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted. RMP update approved.
FIN | Germany | Recovery and recycling of CFCs | Individual | AFR | URT | REF | 36 | TAS | 14 | A | I | CFC | 11.7 | 11.7 | 0 |  | 2002-03-01 | 2002-12-01 | 2004-04-01 |  | 2008-08-01 | 2009-12-01 | 164223 | -9924 | 154299 | 154299 | 100% | 0 | 0 | 0 | 21349 | -1290.12 | 20059 | -0.12 | 0 | Under the contract the only remaining activity is the construction of the recovery and recycling center. As the local partner cannot give a concrete date of finalization of the construction we suggested to declare the project completed and return the rest of the fund to the MLF. NOU agreed to the PCR in Nov-2008. PCR has been submitted to MLF in Apr-2009. Funds will be returned to MLF.
FIN | Germany | Project preparation for a refrigerant management update | RMP Update | AFR | URT | REF | 37 | PRP | 15 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-06-01 | 2003-08-01 |  | 2005-06-01 | 2007-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | A RMP update was submitted by Tanzania in 2005
FIN | France | Refrigerant management plan update | RMP Update | AFR | URT | REF | 46 | TAS | 18 | A | I | CFC | 68.3 |  | 0 |  | 2005-07-01 | 2005-09-01 | 2008-07-01 |  | 2009-12-01 | 2012-12-01 | 157252 | -43428 | 113824 | 113824 | 100% | 0 |  | 0 | 20443 | -5646 | 14797 | 0 |  | The French contribution was implemented by GIZ-Proklima. Project completed.
FIN | UNEP | Country programme preparation | Individual | AFR | URT | SEV | 11 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-01 | 1995-02-01 |  | 1996-07-01 | 1999-06-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0
FIN | UNDP | Project preparation assistance | Individual | AFR | URT | SEV | 17 | PRP | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-08-01 | 1996-07-01 |  | 1998-12-01 | 1999-12-01 | 47000 | 0 | 47000 | 47000 | 100% | 0 | 0 | 0 | 6110 | 0 | 6110 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1995 |  | Investment
FIN | UNEP | Institutional strengthening for the phase out of ODS and the establishment of a National Ozone Office | Individual | AFR | URT | SEV | 20 | INS | 07 | A | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-10-01 | 1999-10-01 |  | 2004-12-01 | 2007-02-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 |  | 8580 | 0 | 8580 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase II) | Individual | AFR | URT | SEV | 44 | INS | 17 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-06-01 | 2006-12-01 |  | 2006-12-01 | 2009-12-01 | 57200 | 0 | 57200 | 57200 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase III) | Individual | AFR | URT | SEV | 50 | INS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-02-01 | 2008-11-01 |  | 2008-11-01 | 2009-09-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | URT | SEV | 57 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2011-01-01 | 2011-03-01 |  | 2011-06-01 | 2011-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of the institutional strengthening project (phase V: 4/2012-3/2014) | Individual | AFR | URT | SEV | 66 | INS | 29 | A | I |  | 0 | 0 | 0 | 0 | 2012-04-01 | 2012-12-01 | 2014-03-01 | 2017-10-01 |  |  | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The licensing and quota systems are in place and functioning. The NOU registered all importers of HCFCs and organized one stakeholders meeting in January 2016 to coordinate and allocate licenses and quotas. The NOU conducted three inspection visits on importers to assess compliance with allocated quotas. The NOU trained 30 Custom officers and 60 RAC technicians. The NOU submitted 2015 Country Programme and Article 7 Data reports. The NOU celebrated 2016 International Ozone Day and conducted several awareness activities. The NOU also participated in all Montreal Protocol meetings organized in 2016. Legal arrangements (actual/planned): The SSFA was drafted and signed by UNEP and the Government of Tanzania in July 2012. Initial stages of project implementation(actual/planned):Yes__ Intermediate goals achieved (actual/planned): __Yes_ Project completion and follow up: _No__ First disbursement date (actual/planned):The first payment was sent in July 2012,_ All funds disbursed (yes/no): No_ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A_ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __NO_ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): The NOU registered all importers of HCFCs and organized one stakeholders meeting in Feb 2017 to coordinate and allocate licenses and quotas. The NOU continues to monitor imports and trade of ODS and ODS related equipment.
ONG | UNEP | Extension of the institutional strengthening project (phase VI: 4/2014-3/2016) | Individual | AFR | URT | SEV | 72 | INS | 32 | A | I |  | 0 |  | 0 |  | 2014-05-01 |  | 2016-03-01 | 2017-10-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 60000 | 6000 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The licensing and quota systems are in place and functioning. The NOU registered all importers of HCFCs and organized one stakeholders meeting in January 2016 to coordinate and allocate licenses and quotas. The NOU conducted one inspection visit on importers to assess compliance with allocated quotas. The NOU trained 30 Custom officers and 60 RAC technicians. The NOU submitted 2015 Country Programme and Article 7 Data reports. The NOU celebrated 2016 International Ozone Day and conducted several awareness activities. The NOU also participated in all Montreal Protocol meetings organized in 2016. Legal arrangements(actual/planned): The SSFA was drafted but not yet signed as the previous phase has still some balance of funds. Initial stages of project implementation(actual/planned):N/A_ Intermediate goals achieved (actual/planned): __N/A_ Project completion and follow up: _N/A__ First disbursement date (actual/planned):N/A_ All funds disbursed (yes/no): NO_ Any delay?(yes/no): _Yes__ If Yes, reasons for delay & action plan to resolve: _CAP is in consultation with the country to get the SSFA signed and get the previous phase completed . If Yes, will delay have impact on project completion date (yes/no): _YES__ Any ongoing problems (yes/no): __NO_ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): The NOU continues to monitor imports and trade of ODS and ODS related equipment. Collection of the 2016 data on ODS imports and consumption has been completed and is being analyzed for submission. NOU commenced preparation of national legislative requirement processes in planning for ratification of Kigali amendment.
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | AFR | URT | SEV | 74 | TAS | 33 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-03-01 | 2016-05-01 | 2017-10-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 35000 | 4000 | 5200 | 0 | 0 | 5200 | 4550 | Brief progress report (actual/planned): The first stakeholders meeting was organized by the NOU in April 2016 in Dar-es-Salaam with the main goal to agree on the plan for the Survey of ODS alternatives at the national level and obtain support of main national stakeholders. The meeting was attended by 30 participants. One National Consultant was hired in June 2016 by the NOU to support the data collection. The National Consultant assisted the NOU in the identification of the current use of ODS alternatives by substance/sector and collection of import/export data for the substances for the past a couple of years. The National Consultant also provided support in establishing growth patterns in use by substance/sector and in compiling data on available ODS alternatives for various applications. The NOU and the National Consultant drafted and cross checked the information to ensure the completion of end-user surveys, collection, analysis, and aggregation of consumption data. The various sections of the report were drafted. The second stakeholders meeting was organized by the NOU in November 2016 in Dar-es-Salaam with the main goal to organise consultations with representatives of the government and private sector to finalize the outcomes of the Survey of ODS alternatives and discuss potential opportunities for introduction of those alternatives in the country. The draft report was prepared by the NOU and the National Consultant. It was reviewed and finalized based on the format approved by ExCom decision 75/67 as contained in document UNEP/OzL.Pro/ExCom/75/77/Rev.1 after incorporating inputs/ comments raised during National Stakeholders’ workshop. The final report has been submitted to UNEP for final review and submission to MLFS. The NOU participated in the ODS Alternative Thematic workshop held in December 2016 to refine the draft report according to the revised template for the report. The report has been finally submitted to UNEP. Legal arrangements(actual/planned): The SSFA was drafted and signed by UNEP and the Government of Tanzania in February 2016___Initial stages of project implementation(actual/planned): _Yes__ Intermediate goals achieved (actual/planned): Yes___ Project completion and follow up: _No__ First disbursement date (actual/planned): _March 2016__ All funds disbursed (yes/no): No___ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): __N/A_ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): The NOU incorporated comments from UNEP ROA and Paris and re-submitted final ODS survey report.
FIN | UNDP | Total aerosol sector phaseout project (technical assistance) | Individual | LAC | URU | ARS | 18 | TAS | 16 | N | I | CFC | 16 | 16 | 0 | 0 | 1995-11-01 | 1996-12-01 | 1997-05-01 |  | 1999-12-01 | 2001-12-01 | 54000 | -1 | 53999 | 53999 | 100% | 0 | 0 | 0 | 7020 | -0.13 | 7019.87 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1995 | 1999-07-01 | Non-Investment
FIN | UNDP | Development of an MDI transition strategy | Individual | LAC | URU | ARS | 36 | TAS | 38 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-09-01 | 2003-04-01 |  | 2002-12-01 | 2004-04-01 | 30000 | -2577 | 27423 | 27423 | 100% | 0 | 0 | 0 | 3900 | -335 | 3565 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 2002 |  | Non-Investment
FIN | UNDP | Transition strategy for the phase-out of CFCs use in MDIs | Individual | LAC | URU | ARS | 38 | TAS | 40 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2002-11-01 | 2005-01-01 | 2009-12-01 |  | 2009-12-01 | 2011-02-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Completed in 2009. Financially completed in 2011. |  | 2002 |  | Non-Investment
FIN | UNDP | Phase-out of CFC consumption in the manufacture of aerosol metered dose inhalers (MDIs) | Individual | LAC | URU | ARS | 43 | INV | 42 | N | I | CFC | 10 | 10 | 0 | 0 | 2004-07-01 | 2006-04-01 | 2007-07-01 |  | 2009-12-01 | 2013-12-01 | 427023 | -5.85 | 427017.15 | 427017 | 100% | 0.15 | 0 | 0 | 32027 | 0 | 32026.9887 | 0.01125 | 0 | Financially completed in 2013. |  | 2004 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at 7 plants (Aislaciones de Uruguay, Metalizadora Uruguaya, Thermopur, Kubal SA, Kalisay SA, J.C. Scarone, Eraton SA) | Individual | LAC | URU | FOA | 13 | INV | 06 | N | I | CFC | 71 | 71 | 0 | 0 | 1994-07-01 | 1995-01-01 | 1995-07-01 |  | 1996-12-01 | 1999-12-01 | 665000 | 0 | 665000 | 665000 | 100% | 0 | 0 | 0 | 86450 | 0 | 86450 | 0 | 0 | Completed in 1996. Financially completed in 1999. |  | 1994 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam at 5 plants (Sudamtex del Uruguay, S.A., Ronit Ltd., Maxi, Divino S.A., Poliflex, Ltd.) | Individual | LAC | URU | FOA | 13 | INV | 09 | N | I | CFC | 17 | 17 | 0 | 0 | 1994-07-01 | 1995-07-01 | 1995-07-01 |  | 2001-12-01 | 2003-08-01 | 200000 | -5109 | 194891 | 194891 | 100% | 0 | 0 | 0 | 26000 | -664.17 | 25335.83 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 1994 | 1999-06-01 | Investment
CLO | IBRD | Elimination of the use of CFC-11 as blowing agent in rigid polyurethane foams used as insulation in thermal tanks at Tem, S.A. | Individual | LAC | URU | FOA | 15 | INV | 10 | N | I |  | 0 | 0 | 0 | 0 | 1994-12-01 |  | 1995-08-01 |  |  | 1996-04-01 | 220300 | -220300 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Tem S.A. has closed down. The project was cancelled by the government on 4/29/96. Funds returned to Multilateral Fund 20th Meeting. |  |  | 1997-01-01 | INV | 0
FIN | IBRD | Elimination of the use of CFC-11 as a blowing agent in rigid polyurethane foam used as insulation in thermal tanks at Etchepare-Gil S.A. | Individual | LAC | URU | FOA | 15 | INV | 14 | N | I | CFC | 3 | 3 | 0 | 0 | 1994-12-01 | 1998-08-01 | 1995-08-01 |  | 1999-09-01 | 2000-01-01 | 235050 | 0 | 235050 | 235050 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | The project was technically completed by September 99 and financially completed in January 00. |  |  | 1999-11-01 | INV | 0
FIN | IBRD | Terminal programme for the elimination of CFC-11 in the manufacture of polyurethane foam through the use of HCFC-141b technology in the foam sector in Uruguay by means of technical assistance and conversion to different companies | Individual | LAC | URU | FOA | 31 | INV | 34 | N | I | CFC | 4.35 | 4.35 | 0 | 0 | 2000-07-01 | 2001-11-01 | 2002-01-01 |  | 2003-05-01 | 2003-05-01 | 91300 | -80 | 91220 | 91220 | 100% | 0 | 0 |  | 11869 | -10 | 11858.6 | 0.4 | 0.4 | Project completed. |  |  |  | INV | 0
FIN | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | LAC | URU | FOA | 57 | PRP | 52 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-12-01 | 2010-03-01 |  | 2013-01-01 | 2013-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 4500 | 0 | 4500 | 0 | 0 | Financially completed in 2013. |  | 2009 |  | Investment
ONG | UNDP | Preparation for HCFC phase-out investment activities (stage II) (foam sector) | Individual | LAC | URU | FOA | 72 | PRP | 62 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 | 2015-01-01 | 2016-05-01 | 2017-01-01 |  |  | 68000 | 0 | 68000 | 8770.35 | 12.9% | 59229.65 | 0 | 23691.86 | 4760 | 0 | 613.9245 | 4146.0755 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Project prepared and discussed with counterparts. Documment submitted and approved by ExCom. Adjustment of approved document made. Prodoc signed (actual/planned, yes/no and date):The agreement has been signed earlier. Missions undertaken (actual/planned):2 of 2 TOR for consultants/subcontracts completed (actual/planned): 2 of 2 Contract/PO/MOA agreements signed: 2 of 2 First disbursement date (actual/planned): 42005Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve:N/A | Preparation of ProDoc conducted, discussion of work plan conducted with stakeholders. |  |  | Non-Investment
FIN | UNIDO | Preparation of a demonstration project (tomatoes, cucumber, strawberries, flowers) | Individual | LAC | URU | FUM | 24 | PRP | 26 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-05-01 | 1999-04-01 |  | 1998-05-01 | 2001-07-01 | 25000 | -1950 | 23050 | 23050 | 100% | 0 | 0 |  | 3250 | -258 | 2992 | 0 | 0 | FIN
FIN | UNIDO | Demonstration project: Alternatives to the use of methyl bromide as a soil fumigant in protected horticultural crops (cucumbers and peppers), seedbeds and nurseries (vegetables, tobacco and forestry) | Individual | LAC | URU | FUM | 25 | DEM | 28 | A | I |  | 0 | 0 |  |  | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 2001-12-01 | 2003-06-01 | 299200 | -1381 | 297819 | 297819.43 | 100% | -0.43 | 0 |  | 38896 | -241 | 38655 | 0 | 0 | FIN
FIN | UNIDO | Preparation of an investment project in the fumigants (methyl bromide) sector | Individual | LAC | URU | FUM | 30 | PRP | 33 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-06-01 | 2001-04-01 |  | 2001-10-01 | 2002-12-01 | 25000 | -935 | 24065 | 24065.16 | 100% | -0.16 | 0 |  | 3250 | -126 | 3124 | 0 | 0 | FIN
FIN | UNIDO | Phase-out of methyl bromide in horticulture (tomatoes and cut flowers) | Individual | LAC | URU | FUM | 34 | INV | 35 | A | I | MBR | 24 | 24 |  |  | 2001-07-01 | 2002-02-01 | 2012-12-01 |  | 2009-12-01 | 2010-12-01 | 469370 | -204 | 469166 | 469166.21 | 100% | -0.21 | 0 |  | 61018 | -26 | 60992 | 0 | 0 | FIN |  |  |  | INV
FIN | USA | Technical assistance in halon-1211 management |  | LAC | URU | HAL | 13 | TAS | 07 | A | I |  | 0 |  | 0 |  | 1994-07-01 |  | 1994-09-01 |  | 1994-09-01 | 1994-09-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | USA | Training in the halon sector |  | LAC | URU | HAL | 15 | TRA | 13 | A | I |  | 76.1 |  | 0 |  | 1994-12-01 | 1994-12-01 | 1995-06-01 |  | 1995-06-01 | 1995-06-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | UNDP | Conversion of production of halon-1211 fire extinguishers at Tornay and Mori | Individual | LAC | URU | HAL | 18 | INV | 17 | N | I | Halon | 2 | 2 | 0 | 0 | 1995-11-01 | 1997-05-01 | 1996-05-01 |  | 1997-09-01 | 1999-12-01 | 38150 | 0 | 38150 | 38150 | 100% | 0 | 0 | 0 | 4959.5 | 0 | 4959.5 | 0 | 0 | Completed in 1997. Financially completed in 1999. |  | 1995 |  | Investment
FIN | UNDP | Transfer of technology and conversion of production of halon-1211 fire extinguishers at Izeta López Fire Company | Individual | LAC | URU | HAL | 18 | INV | 18 | N | I | Halon | 2.7 | 2.7 | 0 | 0 | 1995-11-01 | 1996-12-01 | 1996-02-01 |  | 1996-12-01 | 1999-12-01 | 24225 | 0 | 24225 | 24225 | 100% | 0 | 0 | 0 | 3149.25 | 0 | 3149.25 | 0 | 0 | Completed in 1996. Financially completed in 1999. |  | 1995 |  | Investment
FIN | UNDP | Project preparation of a terminal phase-out management plan | Individual | LAC | URU | PHA | 47 | PRP | 44 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-04-01 | 2006-12-01 |  | 2007-03-01 | 2009-08-01 | 30000 | -18 | 29982 | 29982 | 100% | 0 | 0 | 0 | 2250 | -1.35 | 2248.65 | 0 | 0 | Completed in 2007.Financially completed in 2009. |  | 2005 |  | Investment
FIN | UNDP | Terminal phase-out management plan for Annex A Group I Substances (first tranche) | Multi-Year | LAC | URU | PHA | 50 | INV | 46 | N | I | CFC | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-01-01 | 2009-12-01 |  | 2008-12-01 | 2013-08-01 | 240000 | 0 | 240000 | 240000 | 100% | 0 | 0 | 0 | 18000 | 0 | 18000 | 0 | 0 | Financially completed in 2013. |  | 2006 |  | Investment
FIN | Canada | Terminal phase-out management plan for Annex A Group I Substances (first tranche) | Multi-Year | LAC | URU | PHA | 50 | TAS | 47 | A | I | CFC | 0 |  | 0 |  | 2006-11-01 | 2008-01-01 | 2007-11-01 |  | 2010-07-01 | 2011-07-01 | 160000 | 0 | 160000 | 160000 | 100% | 0 |  | 0 | 20800 | -9120 | 11680 | 0 |  | All project activities, including training and establishment of collaboration with enforcement, had been completed. Final report from NOU received. $9,120 remaining in support costs were returned to Fund, as noted at ExCom 64 in July 2011. |  | 2006 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | URU | PHA | 55 | PRP | 48 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-04-01 | 2009-07-01 |  | 2011-12-01 | 2013-07-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 | 0 | 11250 | 0 | 11250 | 0 | 0 | Financially completed in 2013. |  | 2008 |  | Investment
FIN | UNDP | Terminal phase-out management plan for Annex A Group I substances (second tranche) | Multi-Year | LAC | URU | PHA | 56 | INV | 50 | N | I | CFC | 69.7 | 69.7 | 0 | 0 | 2008-11-01 | 2010-01-01 | 2009-11-01 |  | 2010-12-01 | 2013-09-01 | 48000 | 0 | 48000 | 48000 | 100% | 0 | 0 | 0 | 3600 | 0 | 3600 | 0 | 0 | Financially completed in 2013. |  | 2008 |  | Investment
FIN | Canada | Terminal phase-out management plan for Annex A Group I Substances (second tranche) | Multi-Year | LAC | URU | PHA | 56 | TAS | 51 | A | I | CFC | 0 |  | 0 |  | 2008-11-01 | 2009-08-01 | 2009-11-01 |  | 2011-03-01 | 2011-03-01 | 42000 | 0 | 42000 | 42000 | 100% | 0 |  | 0 | 5460 | 0 | 5460 | 0 |  | Activities initiated in september 2009. 340 technicians trained. organization of 3 meetings with enforcement officials. Efforts to implement the technician certification scheme continued throughout the year. The online licensing system was implemented and one training workshop was held with stakeholders. Final training held in first quarter of 2011 and project completed by end of March 2011. $2,100 in support costs were erroneously reported as unspent in previous report and were in fact spent. |  | 2008 |  | Investment
FIN | UNDP | Terminal phase-out management plan for Annex A Group I Substances (third tranche) | Multi-year | LAC | URU | PHA | 60 | INV | 54 | N | I | CFC | 29.9 | 29.9 | 0 | 0 | 2010-04-01 | 2011-09-01 | 2011-04-01 |  | 2013-12-01 | 2013-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 3375 | 0 | 3375 | 0 | 0 | Financially completed in 2013. |  | 2010 |  | Investment
FIN | Canada | Terminal phase-out management plan for Annex A Group I Substances (third tranche) | Multi-Year | LAC | URU | PHA | 60 | TAS | 53 | A | I | CFC | 0 |  | 0 |  | 2010-04-01 | 2011-06-01 | 2011-04-01 |  | 2011-12-01 | 2012-04-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  | 0 | 3900 | 0 | 3900 | 0 |  | Activities were rapidly completed as they consisted mainly of 4 training workshops on good practices and strengthening of the certification system. Project completed by end of 2011 and remaining balance paid by Canada in April 2012 after final progress and expenditure reports were submitted. |  | 2010 |  | Investment
FIN | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | LAC | URU | PHA | 65 | INV | 57 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-09-01 | 2015-11-01 |  | 2013-06-01 | 2013-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | -1.4552e-11 | 0 | 7500 | 0 | 7500 | 0 | -1.0914e-12 | Financially completed in 2013. |  | 2011 |  | Investment
FIN | UNDP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | URU | PHA | 68 | INV | 58 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-03-01 | 2014-12-01 |  | 2014-10-01 | 2015-02-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 7500 | 0 | 7500 | 0 | 0 | Financially completed in 2015. | As planned, the milestone of preparing and approving the 2014 workplan and budget was achieved. Third tranche funds included in budget. HCFC quotas for 2014 were established. | 2012 |  | Investment
FIN | UNDP | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | LAC | URU | PHA | 71 | INV | 59 | N | I | HCFC | 0 | 0 | 0 | 0 | 2013-12-01 | 2014-08-01 | 2015-06-01 |  | 2015-12-01 | 2016-12-01 | 115000 | 0 | 115000 | 115000 | 100% | 0 | 0 | 0 | 8625 | 0 | 8625 | 0 | 0 | Financially completed in 2016. | Implementation of 2105 workplan is underway, meetings with customs authorities and technical counterpart (LATU) were conducted. 1 follow up mission was conducted. | 2013 |  | Investment
COM | UNDP | Preparation of a HCFC phase-out management plan (stage II) | Individual | LAC | URU | PHA | 72 | PRP | 61 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 | 2015-01-01 | 2016-05-01 |  | 2016-12-01 |  | 60000 | 0 | 60000 | 54084 | 90.14% | 5916 | 0 | 5028.6 | 4200 | 0 | 3785.88 | 414.12 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Project prepared and discussed with counterparts. Documment submitted and approved by ExCom. Adjustment of approved document made. Prodoc signed (actual/planned, yes/no and date):The agreement has been signed earlier. Missions undertaken (actual/planned):2 of 2 TOR for consultants/subcontracts completed (actual/planned): 1 of 1 Contract/PO/MOA agreements signed: 1 of 1 First disbursement date (actual/planned): 42005Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve:N/A | Preparation of ProDoc conducted, discussion of work plan conducted with stakeholders. |  |  | Investment
FIN | UNDP | HCFC phase-out management plan (stage I, fourth tranche) | Multi-Year | LAC | URU | PHA | 73 | INV | 63 | N | I | HCFC | 2.3 | 2.3 | 0 | 0 | 2014-11-01 | 2015-02-01 | 2016-11-01 |  | 2015-04-01 | 2016-04-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 1500 | 0 | 1500 | 0 | 0 | Financially completed in 2016. | Implementation of 2105 workplan is underway, meetings with customs authorities and technical counterpart (LATU) were conducted. 1 follow up mission was conducted. | 2014 |  | Investment
COM | UNDP | HCFC phase-out management plan (stage I, fifth tranche) | Multi-year | LAC | URU | PHA | 75 | INV | 66 | N | I | HCFC | 1.9 | 0 | 0 | 0 | 2015-11-01 | 2015-12-01 | 2016-12-01 |  | 2016-12-01 |  | 45004 | 0 | 45004 | 45004 | 100% | 0 | 0 | 0 | 3375 | 0 | 3375 | 0 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Annual work plan implemented. Meetings with the customs office were conducted to review and verified the license system for HCFC import. Continue discussion with HCFC importers on market trends and controls. Prodoc signed (actual/planned, yes/no and date):Yes, May 2016 Missions undertaken (actual/planned):1 of 1 TOR for consultants/subcontracts completed (actual/planned): 1 of 1 Contract/PO/MOA agreements signed: 1 of 1 First disbursement date (actual/planned): 42522Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve:N/A | Annual work plan prepared and discussed. | 2015 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage II, first tranche) (foam sector) | Multi-year | LAC | URU | PHA | 77 | INV | 67 | N | I | HCFC | 1 | 0 | 0 | 0 | 2016-12-01 |  | 2019-12-01 | 2017-12-01 |  |  | 100000 | 0 | 100000 | 0 | 0% | 100000 | 0 | 40000 | 7000 | 0 | 0 | 7000 | 0 | Newly Approved | DoA sent in February 2017. ProDoc is under preparation. | 2016 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | Multi-year | LAC | URU | PHA | 77 | TAS | 68 | N | I | HCFC | 0 | 0 | 0 | 0 | 2016-12-01 |  | 2019-12-01 | 2017-12-01 |  |  | 178200 | 0 | 178200 | 0 | 0% | 178200 | 0 | 71280 | 12474 | 0 | 0 | 12474 | 0 | Newly Approved | DoA sent in February 2017. ProDoc is under preparation. | 2016 |  | Investment
ONG | UNDP | HCFC phase-out management plan (stage II, first tranche) (implementation and monitoring) | Multi-year | LAC | URU | PHA | 77 | TAS | 69 | N | I | HCFC | 0 | 0 | 0 | 0 | 2016-12-01 |  | 2018-12-01 | 2017-12-01 |  |  | 35800 | 0 | 35800 | 0 | 0% | 35800 | 0 | 14320 | 2506 | 0 | 0 | 2506 | 0 | Newly Approved | DoA sent in February 2017. ProDoc is under preparation. | 2016 |  | Investment
FIN | UNDP | Conservation and demonstration programme for domestic and commercial refrigeration and installation of recovery and recycling equipment | RMP-Component | LAC | URU | REF | 12 | TAS | 04 | N | I | CFC | 22 | 22 | 0 | 0 | 1994-03-01 | 1994-09-01 | 1996-03-01 |  | 1996-12-01 | 2004-01-01 | 175000 | -96 | 174904 | 174904 | 100% | 0 | 0 | 0 | 22750 | -12.48 | 22737.52 | 0 | 0 | Completed in 1996. Financially completed in 2004. |  | 1994 |  | Investment
FIN | IBRD | Elimination of the use of CFC-11 as blowing agent in rigid polyurethane foams used as insulation in cold storage and substitution of CFC-12 used as refrigerant with HFC-134a at Colder S.R.L. | Individual | LAC | URU | REF | 15 | INV | 11 | N | I | CFC | 10.8 | 10.8 | 0 | 0 | 1994-12-01 | 1997-06-01 | 1995-08-01 |  | 1997-09-01 | 1998-08-01 | 325070 | 0 | 325070 | 325070 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Company signed Subgrant Agreement in November '96. Implementation began in Fall /96. Product testing started in Fall /97. The project was completed in August 98. |  |  | 1999-04-01 | INV | 0
CLO | IBRD | Elimination of the use of CFC-11 as a blowing agent in rigid polyurethane foams used as insulation for refrigerators and substitution of CFC-12 used as refrigerant at Indurnor S.A. | Individual | LAC | URU | REF | 15 | INV | 12 | N | I |  | 0 | 0 | 0 | 0 | 1994-12-01 |  | 1995-12-01 |  |  | 1999-07-01 | 448140 | -448140 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Indunor S.A. has closed down. The funds were returned to the Multilateral Fund on July 99 at the 28th Ex Com meeting |  |  | 2000-01-01 | INV | 0
FIN | IBRD | Recovery and recycling of CFC-12 in maintenance workshops for industrial refrigeration equipment | Individual | LAC | URU | REF | 18 | TAS | 19 | N | I | CFC | 4 | 0 | 0 | 0 | 1995-11-01 | 1998-07-01 | 1996-05-01 |  | 1999-10-01 | 2000-01-01 | 87647 | 0 | 87647 | 87647 | 100% | 0 | 0 |  | 11394.11 | 0 | 11394.11 | 0 | 0 | Implementation began in Fall'96. The funds were transferred to local UNDP office in September'97. During 1998 the equipment was purchased and the consultantwas paid. The equipment were distributed on March 99 . The project was completed by October 99. |  |  | 1999-12-01 | INV | 0
FIN | IBRD | Completing the elimination of CFC use in domestic refrigeration manufacturing by adoption of HCFC-141b as blowing agent and HFC-134a as refrigerant at Nevol S.A. | Individual | LAC | URU | REF | 19 | INV | 21 | N | I | CFC | 4.62 | 4.62 | 0 | 0 | 1996-05-01 | 1997-08-01 | 1997-07-01 |  | 2000-02-01 | 1999-07-01 | 141512 | 0 | 141512 | 141512 | 100% | 0 | 0 |  | 18396.56 | 0 | 18396.56 | 0 | 0 | The project was completed in July 99 |  |  | 1999-07-01 | INV | 0
FIN | UNEP | Assistance for formulation of a refrigerant management plan | RMP | LAC | URU | REF | 23 | PRP | 25 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-04-01 | 1998-11-01 |  | 1999-01-01 | 1999-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | Canada | Implementation of the RMP: implementation of a license/quota system for ODS | RMP | LAC | URU | REF | 27 | TAS | 31 | A | I |  | 0 |  | 0 |  | 1999-03-01 | 1999-12-01 | 2001-03-01 |  | 2001-11-01 | 2002-04-01 | 11300 | 0 | 11300 | 11300 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed and licensing developed as planned. PCR Submitted to Sect |  | 1999 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: custom officers training programme | RMP | LAC | URU | REF | 27 | TRA | 29 | A | I |  | 0 |  | 0 |  | 1999-03-01 | 1999-12-01 | 2000-10-01 |  | 2003-06-01 | 2004-05-01 | 71190 | 0 | 71190 | 71190 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed. PCR submitted. |  | 1999 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: train the trainers programme in the refrigeration sector | RMP | LAC | URU | REF | 27 | TRA | 30 | A | I |  | 0 |  | 0 |  | 1999-03-01 | 1999-12-01 | 2000-10-01 |  | 2001-06-01 | 2002-03-01 | 63280 | 0 | 63280 | 63280 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Train-the-technicians workshop complete, 150 technicians trained. PCR submitted to Sect. |  | 1999 |  | Non-Inv.
FIN | IBRD | Preparation of an investment project in the domestic refrigeration sector |  | LAC | URU | REF | 30 | PRP | 32 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2001-12-01 |  | 2000-12-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNEP | Implementation of the RMP: demonstration and training project for the use of hydrocarbons as refrigerants | Individual | LAC | URU | REF | 34 | TAS | 36 | A | I | CFC | 45.8 | 45.8 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2002-08-01 |  | 2007-03-01 | 2009-12-01 | 65000 | -2831 | 62169 | 62169 | 100% | 0 | 0 |  | 8450 | -368.03 | 8081.97 | 0 | 0
FIN | UNDP | Implementation of the RMP: Incentive programme for the commercial/industrial refrigeration end-user sector | RMP-Component | LAC | URU | REF | 34 | TAS | 37 | N | I | CFC | 109.1 | 109.1 | 0 | 0 | 2001-07-01 | 2003-01-01 | 2007-08-01 |  | 2009-12-01 | 2011-02-01 | 154934 | -191.65 | 154742.35 | 154742 | 100% | 0.35 | 0 | 0 | 20141.42 | -24.91 | 20116.46 | 0.05 | 0 | Completed in 2009. |  | 2001 |  | Investment
FIN | UNIDO | Preparation for HCFC phase-out investment activities (refrigeration manufacturing sector) | Individual | LAC | URU | REF | 60 | PRP | 55 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-07-01 | 2011-04-30 |  | 2015-09-01 | 2015-09-01 | 50000 | -422 | 49578 | 49578.1 | 100% | -0.1 | 0 |  | 3750 | -32 | 3718 | 0 | 0 | FIN
FIN | UNDP | Consultant mission to assess technical assistance requirement | Individual | LAC | URU | SEV | 04 | TAS | 01 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-08-01 | 1992-10-01 |  | 1992-12-01 | 1997-12-01 | 13050 | 992 | 14042 | 14042 | 100% | 0 | 0 | 0 | 1696.5 | 128.96 | 1825.46 | 0 | 0 | Completed in 1992. Financially completed in 1997. |  | 1991 |  | Non-Investment
FIN | UNDP | Country programme preparation | Individual | LAC | URU | SEV | 08 | CPG | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1992-12-01 | 1993-10-01 |  | 1993-06-01 | 1997-12-01 | 23894 | 1550 | 25444 | 25444 | 100% | 0 | 0 | 0 | 3106.22 | 201.5 | 3307.72 | 0 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Institutional strengthening: Establishment of COGO | Individual | LAC | URU | SEV | 10 | INS | 03 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-10-01 | 1996-12-01 |  | 1996-12-01 | 1999-12-01 | 173800 | 29000 | 202800 | 202800 | 100% | 0 | 0 | 0 | 22594 | 3770 | 26364 | 0 | 0 | Completed in 1996. Financially completed in 1999. |  | 1993 |  | Non-Investment
FIN | IBRD | Preparation of investment projects (1994) |  | LAC | URU | SEV | 12 | PRP | 05 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 100000 | -41688 | 58312 | 58312 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Project preparation assistance | Individual | LAC | URU | SEV | 13 | PRP | 08 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-08-01 | 1995-01-01 |  | 1995-09-01 | 1997-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Investment
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | LAC | URU | SEV | 16 | PRP | 15 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 81278 | 0 | 81278 | 81278 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Preparation is complete. Project is now under supervision. |  |  |  | Non-INV | 0
FIN | IBRD | Project preparation |  | LAC | URU | SEV | 18 | PRP | 20 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-31 | 1996-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | Project preparation completed. |  |  |  | Non-INV | 0
FIN | UNDP | Renewal of institutional strengthening | Individual | LAC | URU | SEV | 20 | INS | 22 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1996-10-01 | 1996-10-01 | 1998-10-01 |  | 1998-07-01 | 1999-12-01 | 116000 | 0 | 116000 | 116000 | 100% | 0 | 0 | 0 | 15080 | 0 | 15080 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1996 |  | Non-Investment
FIN | IBRD | Project preparation |  | LAC | URU | SEV | 21 | PRP | 23 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | Project preparation completed. |  |  |  | Non-INV | 0
FIN | IBRD | Market survey to develop a country-wide scheme to phase out remaining ODS | Individual | LAC | URU | SEV | 22 | TAS | 24 | N | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-06-01 | 1998-12-01 |  | 1998-07-01 | 1998-07-01 | 23000 | 0 | 23000 | 23000 | 100% | 0 | 0 |  | 2990 | 0 | 2990 | 0 | 0 | Time required for collecting and verifying consumption data was longer than originally anticipated. All disbursements have been made (US$ 23,000). Project completed. |  |  |  | Non-INV | 0
FIN | UNDP | Renewal of institutional strengthening | Individual | LAC | URU | SEV | 25 | INS | 27 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-01-01 | 2000-07-01 |  | 2000-07-01 | 2003-12-01 | 116000 | -19 | 115981 | 115981 | 100% | 0 | 0 | 0 | 15080 | -2 | 15078 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1998 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening (Phase IV) | Individual | LAC | URU | SEV | 31 | INS | 35 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2000-07-01 | 2000-08-01 | 2002-08-01 |  | 2002-07-01 | 2004-04-01 | 116000 | -196 | 115804 | 115804 | 100% | 0 | 0 | 0 | 15080 | -25 | 15055 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 2000 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening project (Phase 5) | Individual | LAC | URU | SEV | 37 | INS | 39 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-01-01 | 2004-08-01 |  | 2006-01-01 | 2009-08-01 | 150800 | 0 | 150800 | 150800 | 100% | 0 | 0 | 0 | 19604 | 0 | 19604 | 0 | 0 | Completed in 2006.Financially completed in 2009. |  | 2002 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VI) | Individual | LAC | URU | SEV | 43 | INS | 41 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-07-01 | 2005-07-01 | 2006-07-01 |  | 2007-12-01 | 2011-12-01 | 150800 | 0 | 150800 | 150800 | 100% | 0 | 0 | 0 | 11310 | 0 | 11310 | 0 | 0 | Completed in 2007. Financially completed in 2011. |  | 2004 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening project (phase VII) | Individual | LAC | URU | SEV | 49 | INS | 45 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2006-07-01 | 2008-02-01 | 2008-10-01 |  | 2010-08-01 | 2012-07-01 | 150800 | 0 | 150800 | 150800 | 100% | 0 | 0 | 0 | 11310 | 0 | 11310 | 0 | 0 | Financially completed in 2012. |  | 2006 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening project (phase VIII) | Individual | LAC | URU | SEV | 56 | INS | 49 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2008-11-01 | 2010-01-01 | 2010-10-01 |  | 2011-12-01 | 2013-02-01 | 150800 | 0 | 150800 | 150800 | 100% | 0 | 0 | 0 | 11310 | 0 | 11310 | 0 | 0 | Financially completed in 2013. |  | 2008 |  | Non-Investment
FIN | UNDP | Extension of institutional strengthening project (phase IX: 1/2012-12/2013) | Individual | LAC | URU | SEV | 65 | INS | 56 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-02-01 | 2013-12-01 |  | 2014-06-01 | 2015-12-01 | 150800 | -3.17 | 150796.83 | 150797 | 100% | -0.17 | 0 | 0 | 11310 | -0.24 | 11309.7749 | -0.01495 | 0 | Financially completed in 2015. | As planned, the 2014 workplan and budget prepared and approved. HCFC quotas for 2014 established. | 2011 |  | Non-investment
FIN | UNDP | Extension of institutional strengthening project (phase X: 1/2014-12/2015) | Individual | LAC | URU | SEV | 71 | INS | 60 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2013-12-01 | 2014-08-01 | 2015-12-01 |  | 2015-12-01 | 2016-12-01 | 150800 | 0 | 150800 | 150799.6 | 100% | 0.4 | 0 | 0 | 10556 | 0 | 10555.972 | 0.028 | 0 | Financially completed in 2016. | In 2015, HCFC quota allocation was set and informed to importers. Information about 2014 HCFC consumption was gathered and Country Programme report submitted. 1 follow up mission conducted. | 2013 |  | Non-Investment
ONG | UNIDO | Survey of ODS alternatives at the national level | Individual | LAC | URU | SEV | 74 | TAS | 64 | A | I |  | 0 | 0 |  |  | 2015-05-01 | 2016-04-01 | 2016-05-31 | 2017-12-31 |  |  | 110000 | 0 | 110000 | 7726.54 | 7.024% | 102273.46 | 13243.54 | 50000 | 9900 | 0 | 0 | 9900 | 1191.9186 | - Contract of the national consultant was processed - Data were collected - A second national expert was recruited to process the data collected and present them properly according to the requirements - Slight impact on the project completion date | Draft survey and tables are prepared. The finalization of the survey and the English translation is ongoing. To be submitted during the first half of 2017. |  |  | NON-INV
ONG | UNDP | Extension of institutional strengthening project (phase XI: 1/2016-12/2017) | Individual | LAC | URU | SEV | 75 | INS | 65 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2015-11-01 | 2016-04-01 | 2017-12-01 | 2017-12-01 |  |  | 193024 | 0 | 193024 | 80624.69 | 41.77% | 112399.31 | 0 | 44959.724 | 13512 | 0 | 5643.862 | 7868.138 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Institutional strengthening activities underway. ODS consumption reports prepared and submitted. Celebration of Ozone Day carried out. 2016 HCFC import quota set. NOU attended regional and global meetings. Prodoc signed (actual/planned, yes/no and date):Yes, April 2016. Missions undertaken (actual/planned):1 of 1 TOR for consultants/subcontracts completed (actual/planned): 3 of 3 Contract/PO/MOA agreements signed: 3 of 3 First disbursement date (actual/planned): 42461Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve:N/A | Annual work plan prepared. HCFC import quota set for 2017. | 2015 |  | Non-Investment
FIN | UNDP | Technical assistance for the phase-out of ODSs in the solvent sector | Individual | LAC | URU | SOL | 45 | TAS | 43 | N | I | TCA/CTC | 0.3 | 0.3 | 0 | 0 | 2005-04-01 | 2005-12-01 | 2006-12-01 |  | 2007-12-01 | 2009-08-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 2700 | 0 | 2700 | 0 | 0 | Completed in 2007.Financially completed in 2009. |  | 2005 |  | Non-Investment
COM | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, first tranche, Vanuatu) | Multi-Year | ASP | VAN | PHA | 63 | TAS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-08-01 | 2015-03-01 |  | 2016-12-01 |  | 76250 | 0 | 76250 | 76250 | 100% | 0 | 0 |  | 9913 | 0 | 9913 | 0 | 0 | Brief progress report (actual/planned): The activities that were implemented in 2016 comprised of (i) implementation of licensing and quota system, (ii) ppermit system for handling, storing and sales of HCFCs, (iii) monitoring of refrigerant identifiers and RAC servicing tools and (iv) outreaching and awareness raising. The country also put in place the import control of HCFC-based equipment into the country. In 2016, there was the rotation of officer-in-charge as the NOO, which resulted in the absence of dedicated NOO in the country. However, the government temporarily assigned former NOO to assist the project impelmentation on ad-hoc basis. The NOU organized 2 customs and enforcement training workshops on 4 Augist 2016 (Port Vila) and 2 September 2016 (Luganville Santo) with total 18 participants trained. NOU also organized 2 RAC training workshops on 18-19 and 30-31 August 2016 with 23 participants. 2015 CP data was submitted to the MLFS online. Project was completed as of Decembner 2016. The last payment to country was approved and the payment was requested in the UMOJA system. Legal arrangement: The SSFA was signed in August 2011. First Mission: May 2012 TOR completed: Not applicable First disbursement date: August 2011 All funds disbursed (yes/no): No. Any delay? (yes/no): No If Yes, reasons for delay & action plan to resolve: N/A . If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No, the project was completed in 2016. If Yes, is any action required by ExCom: N/A. | Project is completed. The request for the final payment has been approved and waiting to be transfer to the country. |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor the submission of required expenditure and progress reports from the Government to UNEP.
ONG | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, second tranche, Vanuatu) | Multi-year | ASP | VAN | PHA | 74 | TAS | 12 | A | I |  | 0.1 |  | 0 |  | 2015-05-01 | 2016-04-01 | 2020-05-01 | 2020-12-01 |  |  | 57400 | 0 | 57400 | 46415 | 80.86% | 10985 | 0 | 1098.5 | 7462 | 0 | 6033.95 | 1428.05 | 0 | Brief progress report (actual/planned): The SSFA was signed by UNEP and the Government of Vanuatu in February 2016. As the SSFA of the first tranche has not yet been closed until December 2016, the priority was given to the closure of the first tranche SSFA. The first payment under the second tranche was processed in December 2016 when the SSFA of the first tranche was closed. UNEP mission was conducted in September 2016 to plan for implementation of HPMP second tranche. 2015 CP data was submitted to MLFS online. Legal arrangements (actual/planned): The SSFA was signed in February 2016. First Mission: September 2016. TOR completed: Not applicable. First disbursement date: Not yet. All funds disbursed (yes/no): No. Any delay? (yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A. If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): Yes, limited capacity of the new NOO who was newly assigned by the government in 2017 If Yes, is any action required by ExCom: No. | Brief progress report (actual/planned): The first payment of the second tranche was transferred to the country in Januray 2017. UNEP keeps regular communications with the country to expedite HPMP implementation as per the agreed work plan. The capacity building activities for new NOO will be conducted as part of the PIC network meeting in 2017.
FIN | Australia | Implementation of the PIC Strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | VAN | REF | 36 | TAS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-04-01 | 2005-04-01 |  | 2010-06-01 | 2012-05-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 | 0 | 0 | 1040 | 0 | 1040 | 0 | 0 | completed |  | 2002
FIN | Australia | Implementation of the PIC Strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | VAN | REF | 36 | TAS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-04-01 | 2005-04-01 |  | 2008-06-01 | 2012-05-01 | 26000 | 0 | 26000 | 26000 | 100% | 0 | 0 | 0 | 3380 | 0 | 3380 | 0 | 0 | completed |  | 2002
FIN | UNEP | Country programme preparation | Individual | ASP | VAN | SEV | 17 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1997-01-01 | 1996-10-01 |  | 2002-03-01 | 2003-06-01 | 20000 | -7000 | 13000 | 13000 | 100% | 0 | 0 |  | 2600 | -910 | 1690 | 0 | 0 |  |  |  | 1999-12-01
FIN | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | VAN | SEV | 36 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2004-01-01 | 2005-04-01 |  | 2008-12-01 | 2009-11-01 | 20250 | 0 | 20250 | 20250 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase II) | Individual | ASP | VAN | SEV | 54 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2009-02-01 | 2009-03-01 |  | 2011-01-01 | 2011-06-01 | 6750 | 0 | 6750 | 6750 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase II, second year) | Individual | ASP | VAN | SEV | 59 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-07-01 | 2010-12-01 |  | 2011-03-01 | 2011-12-01 | 32500 | 0 | 32500 | 32500 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | ASP | VAN | SEV | 62 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-07-01 | 2012-12-01 |  | 2013-12-01 | 2013-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase IV: 1/2013-12/2014) | Individual | ASP | VAN | SEV | 67 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2013-03-01 | 2014-12-01 |  | 2014-12-01 | 2015-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of institutional strengthening project (phase V: 1/2015-12/2016) | Individual | ASP | VAN | SEV | 72 | INS | 11 | A | I |  | 0 |  | 0 |  | 2014-05-01 | 2015-04-01 | 2016-12-01 | 2017-06-01 |  |  | 60000 | 0 | 60000 | 12112 | 20.19% | 47888 | 47888 | 4788.8 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The NOU has been responsible for the management of all Montreal Protocol activities. In 2016, there was the rotation of officer-in-charge as the NOO, which resulted in the absence of dedicated NOO in the country. However, the government temporarily assigned former NOO to assist the project impelmentation on ad-hoc basis. The license/quota system has been enforced in 2016. NOU also coordinated and facilitated the implementation of HPMPand ODS Alternative Survey. The NOU also organized the 2016 ozone day celebration, and the Government actively joined the regional and global ozone related meetings e.g. the network meeting, OEWG and the MOP meetings. 2015 Article 7 and CP data were submitted to the Ozone Secretariat and MLFS respectively. Legal arrangements(actual/planned): The SSFA was signed in February 2015. Initial stages of project implementation(actual/planned): Jan/Feb 2015. Intermediate goals achieved (actual/planned): Compliance (2015) sustained : Project completion and follow up: Not applicable. First disbursement date (actual/planned): April 2015. All funds disbursed (yes/no): No. Any delay?(yes/no): Yes If Yes, reasons for delay & action plan to resolve: New NOO appointed in 2015 left yje NOU in 2016. There was no dedicated NOO. If Yes, will delay have impact on project completion date (yes/no): Yes, the completion date was extended to 31 June 2017. Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): Country continues to enforce the licensing and quota system. A new NOO has been assigned. UNEP kept regular communication with the new NOO to strengthen their Montreal Protocol knowledge and implementation capacity (from Bangkok through phone calls, emails, skype conference calls etc.). The capacity building activities for new NOO will be conducted as part of the PIC network meeting in 2017. Project is planned for completion in June 2017.
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | ASP | VAN | SEV | 75 | TAS | 13 | A | I |  | 0 |  | 0 |  | 2015-11-01 |  | 2016-12-01 | 2017-06-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 40000 | 4000 | 5200 | 0 | 0 | 5200 | 5200 | Brief progress report (actual/planned): It took longer time than other countries to develop and agreed on the draft SSFA the absence of dedicated NOO. However, the stakeholder meetings were organized during UNEP mission in September 2016. The survey methodology and questionnaire have been finalized and agreed. NOU had already started the data collection. Legal arrangements(actual/planned): Not yet. Initial stages of project implementation(actual/planned): June 2016 . Intermediate goals achieved (actual/planned): Not applicable. Project completion and follow up: Not applicable. First disbursement date (actual/planned): Not yet. All funds disbursed (yes/no): No. Any delay?(yes/no): Yes If Yes, reasons for delay & action plan to resolve: Delay in drafting and signing of SSFA which is not duplicate with the EC project and the lack of dedicated NOO in the country. If Yes, will delay have impact on project completion date (yes/no): No. Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): The SSFA was signed by UNEP and the Government of Vanuatu in January 2017. The first payment has been processed, but not yet transferred to the country. The country has just assigned a new NOO, who will also be in charge of this project. The preliminary data has been submitted to UNEP for review and comment. UNEP's consultant will visit Vanuatu to finalize the data collection and analysis in March 2017. The draft report will be prepared based on UNEP comment and the format approved by ExCom decision 75/67 as contained in document UNEP/OzL.Pro/ExCom/75/77/Rev.1.
ONG | UNEP | Extension of institutional strengthening project (phase VI: 1/2017-12/2018) | Individual | ASP | VAN | SEV | 77 | INS | 14 | A | I |  | 0 |  | 0 |  | 2016-12-01 |  | 2018-12-01 | 2018-12-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The project was approved at the 77th ExCom Meeting in December 2016. UNEP initiated the discussion with the NOU on the preparation of the SSFA. Legal arrangements(actual/planned): Not yet Initial stages of project implementation(actual/planned): Not yet Intermediate goals achieved (actual/planned): Not yet Project completion and follow up: Not applicable. First disbursement date (actual/planned): Not yet. All funds disbursed (yes/no): _No__ Any delay?(yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): _No_ If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): UNEP is working with the NOU to progress of the reports of Phase VI to allow for the preparation of the SSFA for IS project phase VI.
FIN | IBRD | Conversion of a CFC-12 polystyrene foam production facility to use hydrocarbons as blowing agent at Plásticos Molanca | Individual | LAC | VEN | FOA | 07 | INV | 05 | N | I | CFC | 259 | 259 | 0 | 0 | 1992-06-01 | 1993-06-01 | 1993-06-01 |  | 1995-12-01 | 1996-04-01 | 1300000 | -38322 | 1261678 | 1261678.18 | 100% | -0.18 | -0.36 |  | 0 | 0 | 0 | 0 | 0 | ICR issued in May/96. The final project cost amounted to about US$2 million. The overrun was absorbed by enterprise. |  |  | 1995-03-01 | INV | 0
FIN | UNIDO | Project formulation of investment projects in the foam sector | Individual | LAC | VEN | FOA | 21 | PRP | 51 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-04-01 | 1997-08-01 |  | 1998-12-01 | 2000-07-01 | 30000 | -927 | 29073 | 29073 | 100% | 0 | 0 |  | 3900 | -126 | 3774 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Decocar | Individual | LAC | VEN | FOA | 22 | INV | 54 | A | I | CFC | 16.2 | 16.2 |  |  | 1997-05-01 | 1997-12-01 | 1998-11-01 |  | 1998-12-01 | 2001-12-01 | 126614 | 0 | 126614 | 126614.49 | 100% | -0.49 | 0 |  | 16460 | -3 | 16457 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Veniber C.A. | Individual | LAC | VEN | FOA | 22 | INV | 56 | A | I | CFC | 21.6 | 21.6 |  |  | 1997-05-01 | 1997-08-01 | 1998-11-01 |  | 1998-12-01 | 2001-09-01 | 164592 | -62 | 164530 | 164529.74 | 100% | 0.26 | 0 |  | 21397 | -42 | 21355 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Daniven C.A. | Individual | LAC | VEN | FOA | 22 | INV | 57 | A | I | CFC | 18 | 18 |  |  | 1997-05-01 | 1998-11-01 | 1998-11-01 |  | 1998-12-01 | 2000-04-01 | 104030 | 0 | 104030 | 104030 | 100% | 0 | 0 |  | 13524 | -16 | 13508 | 0 | 0 | FIN
FIN | UNIDO | Phasing out ODS at Industrias Todos C.A., Caracas | Individual | LAC | VEN | FOA | 23 | INV | 61 | A | I | CFC | 17.8 | 17.8 |  |  | 1997-11-01 | 1998-10-01 | 1999-06-01 |  | 1998-12-01 | 2000-04-19 | 137520 | 0 | 137520 | 137520 | 100% | 0 | 0 |  | 17878 | 0 | 17878 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the foam sector (rigid polyurethane for Fanesi Barquisimeto | Individual | LAC | VEN | FOA | 24 | PRP | 62 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-09-01 | 1999-04-01 |  | 1998-09-01 | 2000-04-01 | 10000 | -56 | 9944 | 9944 | 100% | 0 | 0 |  | 1300 | -9 | 1291 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC -11 with HCFC-141b at TECNOFRIGO in the production of rigid PU panels | Individual | LAC | VEN | FOA | 25 | INV | 64 | A | I | CFC | 9 | 9 |  |  | 1998-07-01 | 1999-11-01 | 1999-08-01 |  | 2001-01-01 | 2002-09-01 | 71946 | 0 | 71946 | 71946.49 | 100% | -0.49 | 0 |  | 9353 | -13 | 9340 | 0 | 0 | FIN |  |  | 2000-11-01
FIN | UNIDO | Phasing out CFC-11 with HCFC-141b at Liderfrio in the production of rigid PU panels | Individual | LAC | VEN | FOA | 26 | INV | 66 | A | I | CFC | 13.9 | 13.9 |  |  | 1998-11-01 | 1999-12-01 | 2000-04-01 |  | 2000-12-01 | 2002-09-01 | 107850 | 0 | 107850 | 107849.94 | 100% | 0.06 | 0 |  | 14021 | -7 | 14014 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 with HCFC-141b in the production of rigid polyurethane panels at Fricava C.A. | Individual | LAC | VEN | FOA | 27 | INV | 73 | A | I | CFC | 15.3 | 15.3 |  |  | 1999-03-01 | 1999-12-01 | 2000-08-01 |  | 2000-12-01 | 2002-09-01 | 115382 | 0 | 115382 | 115382.29 | 100% | -0.29 | 0 |  | 15000 | -10 | 14990 | 0 | 0 | FIN
FIN | UNIDO | Phasing out of CFC-11 by 100% water blown system in the production of moulded integral skin flexible PU foam at Fanesi | Individual | LAC | VEN | FOA | 27 | INV | 74 | A | I | CFC | 11.4 | 11.4 |  |  | 1999-03-01 | 1999-06-01 | 2000-08-01 |  | 2001-06-01 | 2002-12-01 | 157882 | 0 | 157882 | 157882.27 | 100% | -0.27 | 0 |  | 20525 | 0 | 20525 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the foam sector (rigid polyurethane) | Individual | LAC | VEN | FOA | 27 | PRP | 68 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-11-01 | 1999-12-01 |  | 2000-06-01 | 2001-07-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | -2 | 1298 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the foam sector (integral skin) | Individual | LAC | VEN | FOA | 27 | PRP | 70 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-08-01 | 1999-12-01 |  | 2000-12-01 | 2002-01-01 | 20000 | 0 | 20000 | 19999.63 | 100% | 0.37 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the foam sector (polystyrene/ polyethylene) | Individual | LAC | VEN | FOA | 27 | PRP | 72 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-05-01 | 1999-12-01 |  | 2000-12-01 | 2002-05-01 | 20000 | -37 | 19963 | 19963.34 | 100% | -0.34 | 0 |  | 2600 | -9 | 2591 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-12 at Fandec C.A. (EPSR Foam) | Individual | LAC | VEN | FOA | 28 | INV | 82 | A | I | CFC | 45 | 45 |  |  | 1999-07-01 | 1999-11-01 | 2001-08-01 |  | 2003-12-01 | 2004-07-01 | 290481 | 0 | 290481 | 290480.82 | 100% | 0.18 | 0 |  | 37763 | -15 | 37748 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 with HCFC-141b at Novemeca in the production of rigid P.U. panels | Individual | LAC | VEN | FOA | 29 | INV | 77 | A | I | CFC | 16.2 | 16.2 |  |  | 1999-11-01 | 2000-01-01 | 2001-06-01 |  | 2000-11-01 | 2002-09-01 | 69886 | -632 | 69254 | 69254.09 | 100% | -0.09 | 0 |  | 9085 | -96 | 8989 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-11 with HCFC-141b at Amerio Industrial S.A. in the production of rigid P.U. panels | Individual | LAC | VEN | FOA | 29 | INV | 78 | A | I | CFC | 11.8 | 11.8 |  |  | 1999-11-01 | 2000-06-01 | 2001-06-01 |  | 2001-07-01 | 2002-09-01 | 88039 | -173 | 87866 | 87865.84 | 100% | 0.16 | 0 |  | 11445 | -40 | 11404 | 1 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the rigid foam sector | Individual | LAC | VEN | FOA | 30 | PRP | 80 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-05-01 | 2001-04-01 |  | 2001-04-01 | 2002-05-01 | 25000 | 0 | 25000 | 24999.54 | 100% | 0.46 | 0 |  | 3250 | 0 | 3250 | 0 | 0 | FIN
CLO | UNIDO | Phasing out CFC-11 with HCFC-141b at Friobox in the production of rigid P.U. panels | Individual | LAC | VEN | FOA | 31 | INV | 83 | A | I | CFC | 16.5 | 1.1 |  |  | 2000-07-01 | 2001-12-01 | 2002-01-01 |  |  | 2003-05-01 | 128387 | -119558 | 8829 | 8829 | 100% | 0 | 0 |  | 16690 | -15544 | 1146 | 0 | 0 | CLO
FIN | UNIDO | Phasing out CFC-11 with HCFC-141b at Nevecor in the production of rigid P.U. panels | Individual | LAC | VEN | FOA | 31 | INV | 84 | A | I | CFC | 36.4 | 36.4 |  |  | 2000-07-01 | 2001-12-01 | 2002-01-01 |  | 2002-11-01 | 2003-12-01 | 198374 | 0 | 198374 | 198374.15 | 100% | -0.15 | 0 |  | 25789 | -13 | 25776 | 0 | 0 | FIN
FIN | UNIDO | Project preparation for two umbrella projects in the rigid foam sector | Individual | LAC | VEN | FOA | 33 | PRP | 89 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-06-01 | 2002-04-01 |  | 2002-12-01 | 2003-12-01 | 20000 | -227 | 19773 | 19772.54 | 100% | 0.46 | 0 |  | 2600 | -34 | 2566 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phasing out CFC-11 by conversion to HCFC-141b as a blowing agent in the manufacture of rigid polyurethane foams (Umbrella No. 1: Frimac, Frizer, El Control, Incumaca, Frive, Lunger, Profibra, Recovenca, Refriven, Requiven, Tefiven and Vanger) | Individual | LAC | VEN | FOA | 34 | INV | 91 | A | I | CFC | 62.8 | 53.6 |  |  | 2001-07-01 | 2001-11-01 | 2003-08-01 |  | 2003-12-01 | 2005-02-01 | 438017 | -71323 | 366694 | 366694.41 | 100% | -0.41 | 0 |  | 56942 | -9347 | 47595 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phasing out CFC-11 by conversion to water system as a blowing agent in the manufacture of flexible polyurethane foams at Manufacturas Enveta, C.A. Cumana | Individual | LAC | VEN | FOA | 36 | INV | 94 | A | I | CFC | 32 | 32 |  |  | 2002-03-01 | 2003-12-01 | 2004-03-01 |  | 2004-06-01 | 2004-12-01 | 198882 | 0 | 198882 | 198881.59 | 100% | 0.41 | 0 |  | 25855 | -15 | 25840 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phasing out CFC-11 by conversion to HCFC-141b as a blowing agent in the manufacture of rigid p.u. foams: Umbrella No. 2 project. | Individual | LAC | VEN | FOA | 38 | INV | 96 | A | I | CFC | 135.5 | 135.5 |  |  | 2002-11-01 | 2003-04-01 | 2004-12-01 |  | 2005-03-01 | 2006-05-01 | 851432 | -86779 | 764653 | 764652.66 | 100% | 0.34 | 0 |  | 103658 | -9679 | 93978 | 1 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation for HCFC phase-out investment activities (foam sector) | Individual | LAC | VEN | FOA | 60 | PRP | 115 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-08-01 | 2011-04-30 |  | 2011-12-01 | 2013-10-01 | 100000 | -56 | 99944 | 99943.84 | 100% | 0.16 | 0 |  | 7500 | -4 | 7496 | 0 | 0 | FIN
COM | UNDP | Preparation for HCFC phase-out investment activities (stage II) (foam sector) | Individual | LAC | VEN | FOA | 72 | PRP | 126 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 | 2014-12-01 | 2016-05-01 |  | 2016-12-01 |  | 150000 | 0 | 150000 | 57184.3 | 38.12% | 92815.7 | 57874.65 | 78893.345 | 10500 | 0 | 4002.901 | 6497.099 | 4051.2255 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Project prepared and discussed with counterparts. Documment submitted and approved by ExCom. Adjustment of approved document made. Prodoc signed (actual/planned, yes/no and date):The agreement has been signed earlier. Missions undertaken (actual/planned):0 of 0 TOR for consultants/subcontracts completed (actual/planned): 1 of 1 Contract/PO/MOA agreements signed: 1 of 1 First disbursement date (actual/planned): 41974Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve:N/A | Pending payments in the process of being cleared |  |  | Non-Investment
FIN | UNIDO | Workshop on alternatives to methyl bromide in tobacco cultivation | Individual | LAC | VEN | FUM | 27 | TRA | 67 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-07-01 | 1999-12-01 |  | 1999-11-01 | 2001-03-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | -2 | 5198 | 0 | 0 | FIN
FIN | UNIDO | Training and awareness workshop in the fumigants sector (methyl bromide) | Individual | LAC | VEN | FUM | 45 | TAS | 104 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2006-07-01 | 2006-04-01 |  | 2007-12-01 | 2008-08-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 3600 | 0 | 3600 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNDP | Workshops for the recycling and banking of halons | Individual | LAC | VEN | HAL | 09 | TAS | 12 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1994-06-01 | 1997-12-01 | 26800 | -3700 | 23100 | 23100 | 100% | 0 | 0 | 0 | 3484 | -481 | 3003 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1993 |  | Non-Investment
FIN | Canada | Technical assistance in halon sector | Halon Banking | LAC | VEN | HAL | 11 | TAS | 18 | A | I |  | 0 |  | 0 |  | 1993-11-01 |  | 1997-11-01 |  | 1996-05-01 | 1996-05-01 | 414000 | -109500 | 304500 | 304500 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1993 | 2000-01-01 | Non-Inv.
FIN | USA | Technical assistance in halon-1211 management |  | LAC | VEN | HAL | 13 | DEM | 27 | A | I | HAL | 2 |  | 0 |  | 1994-07-01 |  | 1995-07-01 |  | 1995-07-01 | 1995-07-01 | 31000 | 3000 | 34000 | 34000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | Canada | Halon recycling and bank management (Phase II) | Halon Banking | LAC | VEN | HAL | 19 | TAS | 47 | A | I |  | 0 |  | 0 |  | 1996-05-01 | 1996-06-01 | 1998-05-01 |  | 1998-05-01 | 1998-09-01 | 352220 | -69864 | 282356 | 282356 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project successfully implemented. Adjustment results from lower equipment prices and exchange rate fluctuations. |  | 1996 | 1997-06-01 | Non-Inv.
FIN | UNIDO | Preparation of a national ODS phase-out plan | Individual | LAC | VEN | PHA | 36 | PRP | 93 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-03-01 | 2003-07-01 |  | 2004-04-01 | 2004-12-01 | 95000 | 0 | 95000 | 94999.88 | 100% | 0.12 | 0 |  | 12350 | -12 | 12338 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National CFC phase-out plan (first tranche) | Multi-Year | LAC | VEN | PHA | 42 | INV | 98 | A | I | CFC | 0 | 0 |  |  | 2004-04-01 | 2004-07-01 | 2005-04-01 |  | 2006-09-01 | 2008-05-01 | 1895062 | 0 | 1895062 | 1895062 | 100% | 0 | 0 |  | 142130 | 0 | 142130 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National CFC phase-out plan: 2nd tranche | Multi-Year | LAC | VEN | PHA | 45 | INV | 105 | A | I | CFC | 50 | 50 |  |  | 2005-04-01 | 2006-11-01 | 2006-04-01 |  | 2007-07-01 | 2010-05-01 | 1631831 | 0 | 1631831 | 1631831 | 100% | 0 | 0 |  | 122387 | 0 | 122387 | 0 | 0 | FIN |  |  | 2007-12-01 | INV
FIN | UNIDO | National CFC phase-out plan: 2006 work programme | Multi-Year | LAC | VEN | PHA | 51 | INV | 109 | A | I | CFC | 0 | 0 |  |  | 2007-03-01 | 2007-09-01 | 2008-03-01 |  | 2011-12-01 | 2012-12-01 | 2071831 | -286 | 2071545 | 2071545.2 | 100% | -0.2 | 0 |  | 155387 | -21 | 155366 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | LAC | VEN | PHA | 55 | PRP | 112 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-10-01 | 2009-07-31 |  | 2011-12-01 | 2012-12-01 | 173750 | -718 | 173032 | 173031.53 | 100% | 0.47 | 0 |  | 13031 | -54 | 12977 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | National CFC phase-out plan: 2009 work programme | Multi-Year | LAC | VEN | PHA | 57 | INV | 114 | A | I | CFC | 985 | 985 |  |  | 2009-04-01 | 2009-12-01 | 2010-03-31 |  | 2012-06-01 | 2013-12-01 | 513465 | -461.5 | 513003.5 | 513003.49 | 100% | 0.01 | 0 |  | 38510 | -35 | 38475 | 0 | 0 | FIN |  |  |  | INV
COM | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | VEN | PHA | 63 | INV | 118 | A | I |  | 0 | 0 |  |  | 2011-04-01 | 2011-07-01 | 2012-03-31 |  | 2015-12-01 |  | 654854 | 0 | 654854 | 654285.25 | 99.91% | 568.75 | 0 | 1 | 49114 | 0 | 49071 | 43 | 0 | The project was operationally completed. |  |  |  | INV
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | VEN | PHA | 63 | TAS | 119 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-11-01 | 2012-03-01 |  | 2014-12-01 | 2014-12-01 | 50646 | -39968 | 10678 | 10678 | 100% | 0 | 0 |  | 6584 | -5196 | 1388 | 0 | 0
COM | UNIDO | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | VEN | PHA | 67 | INV | 120 | A | I |  | 0 | 0 |  |  | 2012-07-01 | 2013-06-01 | 2013-07-31 |  | 2015-12-01 |  | 603339 | 0 | 603339 | 601903.3 | 99.76% | 1435.7 | 0 | 1 | 45250 | 0 | 45143 | 107 | 0 | The project was operationally completed. |  |  |  | INV
TRF | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | VEN | PHA | 67 | TAS | 121 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 |  | 2013-07-01 |  |  | 2014-12-01 | 46661 | -46661 | 0 | 0 | #DIV/0! | 0 | 0 |  | 6066 | -6066 |  | 0
COM | UNIDO | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | LAC | VEN | PHA | 70 | INV | 124 | A | I | HCFC | 4 | 4 |  |  | 2013-07-01 | 2014-04-01 | 2015-07-31 |  | 2015-12-01 | 2016-04-01 | 324875 | 0 | 324875 | 325004.97 | 100% | -129.97 | 0 |  | 24366 | 0 | 24375 | -9 | 0 | The project was operationally completed. |  |  |  | INV
TRF | UNEP | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | LAC | VEN | PHA | 70 | TAS | 123 | A | I |  | 0 |  | 0 |  | 2013-07-01 |  | 2015-07-01 |  |  | 2014-12-01 | 25125 | -25125 | 0 | 0 | #DIV/0! | 0 | 0 |  | 3266 | -3266 |  | 0
COM | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | Individual | LAC | VEN | PHA | 72 | PRP | 127 | A | I |  | 0 | 0 |  |  | 2014-05-01 | 2014-08-01 | 2015-05-31 |  | 2016-12-01 |  | 90000 | 0 | 90000 | 88143.9 | 97.94% | 1856.1 | 1856.1 | 1856 | 6300 | 0 | 6170 | 130 | 130 | Project activities completed. | Final payments are being issued and financial closure is in process. |  |  | NON-INV
ONG | UNIDO | HCFC phase-out management plan (stage I, fourth tranche) | Multi-Year | LAC | VEN | PHA | 75 | INV | 131 | A | I | HCFC | 19 | 0 |  |  | 2015-11-01 | 2016-04-01 | 2017-12-01 | 2019-03-01 |  |  | 189000 | 0 | 189000 | 73811.84 | 39.05% | 115188.16 | 8562.95 | 15000 | 14175 | 0 | 0 | 14175 | 642.2213 | Working arrangements were discussed with the NOU and project implementation started during the second semester of 2016. - No delay in implementation - No recurring problem - Project completion date changed due to political situation in the country - No action required by Executive Committee | Two reclaiming units purchased to be installed as pilot project for refrigerant reclaim. Training trainers in good practices and use of hydrocarbon as refrigerant using local produced R-290. - Expected delays in implementation due to the political unrests - No other recurring problem - Project completion date changed due to political situation in the country - No action required by Executive Committee |  |  | INV |  | To request the submission of additional status report to the 79th meeting to monitor the date of completion different from the completion date in tranche request.
ONG | UNIDO | HPMP Stage I - Transfer from UNEP | Multi-Year | LAC | VEN | PHA | 75 | TAS | 130 | A | I | HCFC | 0.3 | 0 |  |  | 2015-11-01 | 2016-04-01 | 2017-11-01 | 2017-12-01 |  |  | 111754 | 0 | 111754 | 23465.92 | 21% | 88288.08 | 86975 | 20000 | 8382 | 0 | 0 | 8382 | 6523.125 | - Contract for the activities was granted to FONDOIN and international expert hired for the program. - A contract for public awareness campaign was launched with Museo de los Niños. - No recurring problem - Project completion date changed due to political situation in the country - No action required by Executive Committee | Contract for training of custom officers and MOE staff is being implemented. - No delay in implementation - No recurring problem - No action required by Executive Committee |  |  | INV |  | To request the submission of additional status report to the 79th meeting to monitor the date of completion different from the completion date in tranche request.
ONG | UNDP | HCFC phase-out management plan (stage II, first tranche) (foam sector) | Multi-Year | LAC | VEN | PHA | 76 | INV | 133 | N | I | HCFC | 2.4 | 0 | 0 | 0 | 2016-05-01 |  | 2019-05-01 | 2017-05-01 |  |  | 76420 | 0 | 76420 | 0 | 0% | 76420 | 0 | 30568 | 5349 | 0 | 0 | 5349 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Project document prepared. Meetings with NOU to review estrategy and work plan. Prodoc signed (actual/planned, yes/no and date):No Missions undertaken (actual/planned):0 of 0 TOR for consultants/subcontracts completed (actual/planned): 0 of 0 Contract/PO/MOA agreements signed: 0 of 0 First disbursement date (actual/planned): 42826Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:Delay in the preparation of the project document due to change of personal (in some cases temporaly in other permanent) at local level (both UNDP CO and NOU). Information was shared with new personal. | Review of ProDoc draft and implementation arragements were conducted. |  |  | Investment
ONG | UNIDO | HCFC phase-out management plan (stage II, first tranche) (technical assistance in refrigeration and air-conditioning manufacturing sector) | Multi-Year | LAC | VEN | PHA | 76 | INV | 134 | A | I | HCFC | 3.2 | 0 |  |  | 2016-05-01 | 2016-08-01 | 2019-12-31 | 2019-12-31 |  |  | 245000 | 0 | 245000 | 8284.44 | 3.381% | 236715.56 | 4000 | 15000 | 17150 | 0 | 580 | 16570 | 280 | Approved in accordance with the Agreement between the Government and the Executive Committee for the period 2016 to 2020 to reduce HCFC consumption by 42 per cent of the baseline. Noted the commitment of the Government to reduce HCFC consumption by 42 per cent by 2020; issue a ban on imports, exports and use of HCFC-141b pure or contained in pre- blended polyols by 1 January 2020; issue a ban on import of refrigeration and air-conditioning (RAC) equipment operated with HCFCs and a ban on manufacturing and new installations of RAC equipment operating with HCFCs by 1 January 2020. The Government, UNIDO and UNDP were requested to deduct 64.41 ODP tonnes of HCFCs from the remaining HCFC consumption eligible for funding. | Local expert contracted to carry out a survey on the best way to implement the project. - No delay in implementation - No recurring problem - No impact on project completion date - No action required by Executive Committee |  |  | INV
ONG | UNIDO | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | Multi-Year | LAC | VEN | PHA | 76 | TAS | 132 | A | I |  | 0 | 0 |  |  | 2016-05-01 |  | 2019-12-31 | 2019-12-31 |  |  | 355000 | 0 | 355000 | 0 | 0% | 355000 | 133150 | 60000 | 24850 | 0 | 0 | 24850 | 9321 | - Contract for the second phase of the 'zero leak' initiative was granted to VENACOR (local chamber for refrigeration and ventilation). Approved in accordance with the Agreement between the Government and the Executive Committee for the period 2016 to 2020 to reduce HCFC consumption by 42 per cent of the baseline. Noted the commitment of the Government to reduce HCFC consumption by 42 per cent by 2020; issue a ban on imports, exports and use of HCFC-141b pure or contained in pre- blended polyols by 1 January 2020; issue a ban on import of refrigeration and air-conditioning (RAC) equipment operated with HCFCs and a ban on manufacturing and new installations of RAC equipment operating with HCFCs by 1 January 2020. The Government, UNIDO and UNDP were requested to deduct 64.41 ODP tonnes of HCFCs from the remaining HCFC consumption eligible for funding. | Contract granted to FONDOIN-NOU for support in the implementation activates. - No delay in implementation - No recurring problem - No impact on project completion date - No action required by Executive Committee |  |  | INV
FIN | IBRD | Project preparation for the CFC production phase out project |  | LAC | VEN | PRO | 41 | PRP | 97 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2003-12-01 | 2004-12-01 |  | 2004-04-01 | 2004-04-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 3000 | 0 | 3000 | 0 | 0 | Project was prepared and subsequently approved at the 44th ExCom in Dec. 04. |  |  |  | Non-INV | 0
FIN | IBRD | Phased reduction and closure of the entire CFC production: 2004 annual programme | Multiyear | LAC | VEN | PRO | 44 | INV | 101 | N | I | CFC | 0 | 0 | 1469 | 1469 | 2004-12-01 | 2005-12-01 | 2005-12-01 |  | 2005-12-01 | 2009-11-01 | 3300000 | 0 | 3300000 | 3300000 | 100% | 0 | 0 |  | 247500 | 0 | 247500 | 0 | 0 | Latest production audit for CY09 took place in Dec 09 to verify production closure of CFC-11/12. Based on onsite audit there was no production of CFC-11 nor CFC-12, and no consumption of CTC in 2009. Consumption of HF and CHCL33 were in line with HCFC-22 production standards, as was consumption of HCl with levels of HCFC-22 production and HF consumption. CFC production terminated in Dec 06. Operational and financial reports indicate that Produven only produced HCFC-22 in 2009. Final verification report was submitted to the 59th ExCom. |  |  |  | INV | 0
FIN | IBRD | National CFC production closure plan (second tranche) | Multiyear | LAC | VEN | PRO | 46 | INV | 106 | N | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-09-01 | 2006-07-01 |  | 2006-04-01 | 2009-11-01 | 8100000 | 0 | 8100000 | 8100000 | 100% | 0 | 0 |  | 607500 | 0 | 607500 | 0 | 0 | Latest production audit for CY09 took place in Dec 09 to verify production closure of CFC-11/12. Based on onsite audit there was no production of CFC-11 nor CFC-12, and no consumption of CTC in 2009. Consumption of HF and CHCL33 were in line with HCFC-22 production standards, as was consumption of HCl with levels of HCFC-22 production and HF consumption. CFC production terminated in Dec 06. Operational and financial reports indicate that Produven only produced HCFC-22 in 2009. Final verification report was submitted to the 59th ExCom. |  |  |  | INV | 0
FIN | IBRD | National CFC production closure plan (third tranche) | Multiyear | LAC | VEN | PRO | 48 | INV | 107 | N | I | CFC | 0 | 0 | 2931 | 2931 | 2006-04-01 | 2006-08-01 | 2007-04-01 |  | 2007-04-01 | 2009-11-01 | 1750000 | 0 | 1750000 | 1750000 | 100% | 0 | 0 |  | 131200 | 0 | 131200 | 0 | 0 | Latest production audit for CY09 took place in Dec 09 to verify production closure of CFC-11/12. Based on onsite audit there was no production of CFC-11 nor CFC-12, and no consumption of CTC in 2009. Consumption of HF and CHCL33 were in line with HCFC-22 production standards, as was consumption of HCl with levels of HCFC-22 production and HF consumption. CFC production terminated in Dec 06. Operational and financial reports indicate that Produven only produced HCFC-22 in 2009. Final verification report was submitted to the 59th ExCom. |  |  |  | INV | 0
FIN | IBRD | National CFC production closure plan (fourth tranche) | Multiyear | LAC | VEN | PRO | 52 | INV | 110 | N | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-09-01 | 2008-07-31 |  | 2009-01-01 | 2009-11-01 | 2300000 | 0 | 2300000 | 2300000 | 100% | 0 | 0 |  | 172500 | 0 | 172500 | 0 | 0 | Latest production audit for CY09 took place in Dec 09 to verify production closure of CFC-11/12. Based on onsite audit there was no production of CFC-11 nor CFC-12, and no consumption of CTC in 2009. Consumption of HF and CHCL33 were in line with HCFC-22 production standards, as was consumption of HCl with levels of HCFC-22 production and HF consumption. CFC production terminated in Dec 06. Operational and financial reports indicate that Produven only produced HCFC-22 in 2009. Final verification report was submitted to the 59th ExCom. |  |  |  | INV | 0
FIN | IBRD | National CFC production closure plan (fifth tranche) | Multiyear | LAC | VEN | PRO | 54 | INV | 111 | N | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-10-01 | 2009-03-31 |  | 2008-12-01 | 2009-11-01 | 1050000 | 0 | 1050000 | 1050000 | 100% | 0 | 0 |  | 78700 | 0 | 78700 | 0 | 0 | Latest production audit for CY09 took place in Dec 09 to verify production closure of CFC-11/12. Based on onsite audit there was no production of CFC-11 nor CFC-12, and no consumption of CTC in 2009. Consumption of HF and CHCL33 were in line with HCFC-22 production standards, as was consumption of HCl with levels of HCFC-22 production and HF consumption. CFC production terminated in Dec 06. Operational and financial reports indicate that Produven only produced HCFC-22 in 2009. Final verification report was submitted to the 59th ExCom. |  |  |  | INV | 0
FIN | UNDP | Technical assistance and training of servicing technicians in the refrigeration sector | RMP-Component | LAC | VEN | REF | 04 | TRA | 01 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-07-01 | 1992-06-01 |  | 1992-06-01 | 1997-12-01 | 30000 | -10980 | 19020 | 19020 | 100% | 0 | 0 | 0 | 3900 | -1427.4 | 2472.6 | 0 | 0 | Completed in 1992. Financially completed in 1997. |  | 1991 |  | Non-Investment
FIN | USA | Technical assistance and demonstration project in CFC recycling in MAC |  | LAC | VEN | REF | 08 | DEM | 06 | A | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1993-10-01 |  | 1995-07-01 | 1998-09-01 | 115000 | 0 | 115000 | 115000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1992
CLO | IBRD | Replacement of CFC by HFC-134a as a refrigerant in central air conditioning units at Instituto Venezolano de los Seguros Sociales | Individual | LAC | VEN | REF | 08 | INV | 08 | N | I |  | 0 | 0 | 0 | 0 | 1992-10-01 |  | 1994-04-01 |  |  | 1995-07-01 | 851000 | -851000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project Cancelled. |  |  | 1994-04-01 | INV | 0
FIN | IBRD | Replacement of CFC by HFC-134a as a refrigerant in central air conditioning units at Clínica Atias, Hospitalización y Servicios | Individual | LAC | VEN | REF | 08 | INV | 09 | N | I | CFC | 4 | 4 | 0 | 0 | 1992-10-01 | 1996-12-01 | 1994-04-01 |  | 1997-01-01 | 1997-02-01 | 115000 | 0 | 115000 | 115000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project Completed |  |  | 1997-01-01 | INV | 0
FIN | IBRD | Replacement of CFC by HFC-134a as a refrigerant in central air conditioning units at Instituto de Prevencion Social del Médico | Individual | LAC | VEN | REF | 08 | INV | 10 | N | D | CFC | 2 | 2 | 0 | 0 | 1992-10-01 | 1995-12-01 | 1994-04-01 |  | 1995-09-01 | 1997-02-01 | 69000 | 0 | 69000 | 69000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1995-09-01 | INV | 0
CLO | IBRD | Replacement of CFC by HFC-134a as a refrigerant in central air conditioning units at Congreso de la Republica | Individual | LAC | VEN | REF | 08 | INV | 11 | N | D |  | 0 | 0 | 0 | 0 | 1992-10-01 |  | 1994-04-01 |  |  | 1998-05-01 | 65000 | -65000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Retroactive project physically completed, but enterprise chose not to utilize MLF funds. Funds returned to MLF. |  |  | 1995-12-01 | INV | 0
FIN | UNDP | Workshops for identification of projects in the refrigeration and air conditioning sector | Individual | LAC | VEN | REF | 09 | PRP | 15 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1994-12-01 | 1997-12-01 | 19800 | 0 | 19800 | 19800 | 100% | 0 | 0 | 0 | 2574 | 0 | 2574 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1993 |  | Investment
FIN | UNDP | Workshops on conversion and installation of new central air conditioning systems using non-ODS | RMP-Component | LAC | VEN | REF | 09 | TAS | 16 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1994-06-01 | 1997-12-01 | 26200 | -13000 | 13200 | 13200 | 100% | 0 | 0 | 0 | 3406 | -1690 | 1716 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1993 |  | Non-Investment
FIN | UNDP | Pilot programme in recovery and recycling of CFC-12 in domestic refrigeration | RMP-Component | LAC | VEN | REF | 09 | TAS | 17 | A | I | CFC | 8 | 8 | 0 | 0 | 1993-03-01 | 1994-12-01 | 1994-03-01 |  | 1996-12-01 | 1998-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1993 |  | Investment
FIN | IBRD | MAC factory conversion for fabrication of HFC-134a heat exchangers at Fabrica de Aparatos de Aire Acondicionado, S.A. (Faaca) | Individual | LAC | VEN | REF | 11 | INV | 19 | N | I | CFC | 0 | 0 | 0 | 0 | 1993-11-01 | 1995-06-01 | 1995-11-01 |  | 1998-02-01 | 1998-02-01 | 3480000 | -380000 | 3100000 | 3100000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project Completed |  |  | 1997-09-01 | INV | 0
FIN | IBRD | MAC factory conversion for fabrication of HFC-134a compressors and heat exchangers at Aire Acondicionado Integral, S.A. (Aaisa) | Individual | LAC | VEN | REF | 11 | INV | 20 | N | I | CFC | 11 | 11 | 0 | 0 | 1993-11-01 | 1995-12-01 | 1996-09-01 |  | 1998-06-01 | 1998-10-01 | 620000 | 3800000 | 4420000 | 4420000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Complete. |  |  | 1997-09-01 | INV | 0
FIN | UNDP | Pilot programme in recovery and recycling of CFC-12 in MAC | RMP-Component | LAC | VEN | REF | 12 | DEM | 26 | A | I | CFC | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-05-01 | 1995-03-01 |  | 1995-03-01 | 1997-12-01 | 13400 | 0 | 13400 | 13400 | 100% | 0 | 0 | 0 | 1742 | 0 | 1742 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Non-Investment
FIN | USA | Demonstration project in MAC |  | LAC | VEN | REF | 13 | DEM | 28 | A | I | CFC | 25 |  | 0 |  | 1994-07-01 |  | 1995-07-01 |  | 1995-07-01 | 1998-09-01 | 53000 | 0 | 53000 | 53000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Project completed. |  | 1994
FIN | USA | Demonstration project in the refrigeration sector |  | LAC | VEN | REF | 15 | DEM | 30 | A | I |  | 0 |  | 0 |  | 1994-12-01 | 1995-01-01 | 1995-12-01 |  | 1995-12-01 | 1998-06-01 | 67000 | 0 | 67000 | 67000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Project completed. |  | 1994
FIN | UNDP | Preparatory assistance for the domestic and commercial refrigeration manufacturing sector | Individual | LAC | VEN | REF | 15 | PRP | 31 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-01-01 | 1995-06-01 |  | 1995-06-01 | 1997-12-01 | 40000 | 5445 | 45445 | 45445 | 100% | 0 | 0 | 0 | 5200 | 707.85 | 5907.85 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Investment
FIN | UNDP | Pilot project for recovery and recycling of CFC-12 in MAC (Phase II) | RMP-Component | LAC | VEN | REF | 15 | TAS | 32 | A | I | CFC | 75 | 75 | 0 | 0 | 1994-12-01 | 1995-05-01 | 1995-12-01 |  | 1996-12-01 | 2000-12-01 | 220000 | -13204.1 | 206795.9 | 206796 | 100% | -0.1 | 0 | 0 | 28600 | -1716.53 | 26883.48 | -0.01 | 0 | Completed in 1996. Financially completed in 2000. |  | 1994 |  | Investment
FIN | UNDP | Elimination of CFCs 11 and 12 in the manufacture of commercial refrigeration equipment at Pinova, S.A. | Individual | LAC | VEN | REF | 17 | INV | 38 | A | I | CFC | 25 | 25 | 0 | 0 | 1995-07-01 | 1996-07-01 | 1997-01-01 |  | 1999-12-01 | 2001-12-01 | 517500 | -149132 | 368368 | 368368 | 100% | 0 | 0 | 0 | 67275 | -19387.16 | 47887.84 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1995 | 1999-07-01 | Investment
FIN | UNDP | Conversion of CFC-12 to compressor production facilities at Vecomesa, S.A. to manufacture HFC-134a compressors | Individual | LAC | VEN | REF | 17 | INV | 39 | A | I | No_ODP | 0.7 | 0.7 | 0 | 0 | 1995-07-01 | 1997-07-01 | 1997-01-01 |  | 1999-12-01 | 2000-12-01 | 362000 | -193742 | 168258 | 168258 | 100% | 0 | 0 | 0 | 47060 | -25186.46 | 21873.54 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1995 | 1999-07-01 | Investment
FIN | UNDP | Elimination of CFCs 11 and 12 in the manufacture of commercial refrigeration equipment at Industrias Nutal, C.A. | Individual | LAC | VEN | REF | 17 | INV | 40 | A | I | CFC | 14.5 | 14.5 | 0 | 0 | 1995-07-01 | 1997-01-01 | 1997-01-01 |  | 2001-12-01 | 2002-03-01 | 123623 | 0 | 123623 | 123623 | 100% | 0 | 0 | 0 | 16070.99 | 0 | 16070.99 | 0 | 0 | Completed in 2001. Financially completed in 2002. |  | 1995 | 2000-12-01 | Investment
FIN | UNDP | Preparatory assistance for the domestic and comercial refrigeration manufacturing sector | Individual | LAC | VEN | REF | 17 | PRP | 37 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-08-01 | 1996-06-01 |  | 1996-03-01 | 1997-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1996. Financially completed in 1997. |  | 1995 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Grupo Frigilux, C.A. | Individual | LAC | VEN | REF | 18 | INV | 42 | A | I | CFC | 46 | 46 | 0 | 0 | 1995-11-01 | 1996-08-01 | 1997-05-01 |  | 1999-12-01 | 2000-12-01 | 953000 | -371693 | 581307 | 581307 | 100% | 0 | 0 | 0 | 123890 | -48320.41 | 75569.5856 | 0.0044 | 0 | Completed in 1999. Financially completed in 2000. |  | 1995 | 1999-09-01 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Coresmalt Valencia, C.A. | Individual | LAC | VEN | REF | 18 | INV | 43 | A | I | CFC | 65.5 | 65.5 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1997-05-01 |  | 2000-09-01 | 2002-03-01 | 685330 | -6585 | 678745 | 678745 | 100% | 0 | 0 | 0 | 89092.9 | -856.05 | 88236.85 | 0 | 0 | Completed in 2000. Financially completed in 2002. |  | 1995 | 1997-12-01 | Investment
CLO | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Manufacturera de Aparatos Domésticos, S.A. (Madosa) | Individual | LAC | VEN | REF | 18 | INV | 44 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1997-06-01 | 1997-05-01 |  |  | 2001-12-01 | 230274 | -51266 | 179008 | 179008 | 100% | 0 | 0 | 0 | 29935.62 | -6664.58 | 23271.04 | 0 | 0 | Canceled in 1999. Financially completed in 2001. |  | 1995 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of refrigerated display cases and bottle coolers at Neve Industrial, C.A. | Individual | LAC | VEN | REF | 19 | INV | 46 | A | I | CFC | 7.5 | 7.5 | 0 | 0 | 1996-05-01 | 1997-05-01 | 1997-11-01 |  | 1999-12-01 | 2002-03-01 | 112100 | -3498 | 108602 | 108602 | 100% | 0 | 0 | 0 | 14573 | -454.74 | 14118.26 | 0 | 0 | Completed in 1999. Financially completed in 2002. |  | 1996 | 1999-07-01 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of bottle coolers, freezers and water coolers at Tecnocongeladores Venezolanos (Tecoven), C.A. | Individual | LAC | VEN | REF | 19 | INV | 48 | A | I | CFC | 13.2 | 13.2 | 0 | 0 | 1996-05-01 | 1997-05-01 | 1997-11-01 |  | 1999-12-01 | 2001-12-01 | 190000 | -2599 | 187401 | 187401 | 100% | 0 | 0 | 0 | 24700 | -337.87 | 24362.13 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1996 | 1999-07-01 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of bottle coolers, freezers and water coolers at Hielomatic, C.A. | Individual | LAC | VEN | REF | 19 | INV | 49 | A | I | CFC | 11.1 | 11.1 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  | 2000-07-01 | 2001-12-01 | 162375 | -378.83 | 161996.17 | 161996 | 100% | 0.17 | 0 | 0 | 21108.75 | -49.25 | 21059.48 | 0.02 | 0 | Completed in 2000. Financially completed in 2001. |  | 1996 | 1998-04-01 | Investment
FIN | Canada | Implementation of a centralized reclamation plant for recovered refrigerants in the commercial refrigeration and air-conditioning sector | Individual | LAC | VEN | REF | 22 | TAS | 55 | A | I |  | 0 |  | 0 |  | 1997-05-01 | 1997-07-01 | 1999-06-01 |  | 1999-06-01 | 1999-06-01 | 495285 | -6685 | 488600 | 488600 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1997 |  | Non-Inv.
FIN | UNDP | Implementation of a recovery and reclamation of refrigerants | RMP-Component | LAC | VEN | REF | 22 | TAS | 58 | A | I | CFC | 172 | 172 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1999-06-01 |  | 2003-12-01 | 2003-12-01 | 931622 | -61553 | 870069 | 870069 | 100% | 0 | 0 | 0 | 121110.9 | -8002 | 113108.9 | 0 | 0 | Completed in 2003. Financially completed in 2003. |  | 1997 | 1999-06-01 | Investment
FIN | UNIDO | Phasing out CFC-11 and CFC-12 withHCFC-141b and HFC-134a at INVITREL in the manufacture of commercial refrigeration equipment | Individual | LAC | VEN | REF | 25 | INV | 63 | A | I | CFC | 46.4 | 46.4 |  |  | 1998-07-01 | 1998-12-01 | 2000-02-01 |  | 1999-12-01 | 2002-09-01 | 419094 | -1714 | 417380 | 417379.62 | 100% | 0.38 | 0 |  | 54482 | -309 | 54173 | 0 | 0 | FIN
CLO | UNDP | Preparation of one project in refrigeration MAC and compressors subsector | Individual | LAC | VEN | REF | 27 | PRP | 69 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 |  | 2000-04-01 |  |  | 2002-03-01 | 30000 | -30000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 3900 | -3900 | 0 | 0 | 0 | Canceled in 1999. Financially Completed in 2002. |  | 1999 |  | Investment
FIN | UNIDO | Preparation of investment projects in the commercial refrigeration sector | Individual | LAC | VEN | REF | 27 | PRP | 71 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-09-01 | 1999-12-01 |  | 2000-10-01 | 2001-10-01 | 25000 | -325 | 24675 | 24675.21 | 100% | -0.21 | 0 |  | 3250 | -47 | 3203 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment projects in the refrigeration/MACS and compressor sector | Individual | LAC | VEN | REF | 27 | PRP | 75 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-12-01 | 1999-12-01 |  | 2000-09-01 | 2002-09-01 | 20000 | -113 | 19887 | 19887.32 | 100% | -0.32 | 0 |  | 2600 | -19 | 2581 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-12 with HFC-134a and CFC-11 with HCFC-141b at five commercial refrigeration companies (umbrella project) | Individual | LAC | VEN | REF | 29 | INV | 76 | A | I | CFC | 30.9 | 30.9 |  |  | 1999-11-01 | 2000-11-01 | 2001-12-01 |  | 2001-12-01 | 2003-10-01 | 469140 | -64008 | 405132 | 405131.58 | 100% | 0.42 | 0 |  | 60988 | -8404 | 52584 | 0 | 0 | FIN
FIN | UNIDO | Phasing out CFC-12 with HFC-134a and CFC-11 with HCFC-141b at three domestic refrigeration companies (umbrella project) | Individual | LAC | VEN | REF | 29 | INV | 79 | A | I | CFC | 27 | 27 |  |  | 1999-11-01 | 2000-11-01 | 2001-12-01 |  | 2001-12-01 | 2003-10-01 | 371705 | -75965 | 295740 | 295740.37 | 100% | -0.37 | 0 |  | 48322 | -9937 | 38385 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the commercial refrigeration sector | Individual | LAC | VEN | REF | 30 | PRP | 81 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2001-11-01 | 2001-04-01 |  | 2002-06-01 | 2003-10-01 | 20000 | -124 | 19876 | 19875.84 | 100% | 0.16 | 0 |  | 2600 | -20 | 2580 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project in the refrigeration sector (domestic/commercial) | Individual | LAC | VEN | REF | 31 | PRP | 85 | A | I |  | 0 | 0 |  |  | 2000-07-01 | 2000-11-01 | 2002-05-01 |  | 2002-06-01 | 2003-05-01 | 30000 | -238 | 29762 | 29761.76 | 100% | 0.24 | 0 |  | 3900 | -37 | 3863 | 0 | 0 | FIN
FIN | UNIDO | Strategy for the preparation of an RMP | RMP | LAC | VEN | REF | 31 | TAS | 86 | A | I |  | 0 | 0 |  |  | 2000-07-01 | 2001-03-01 | 2001-07-01 |  | 2002-12-01 | 2003-10-01 | 70000 | -2912 | 67088 | 67087.78 | 100% | 0.22 | 0 |  | 9100 | -392 | 8708 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Phasing out CFC-12 with HFC-134a and CFC-11 with HCFC-141b at seven commercial refrigeration companies (umbrella project) | Individual | LAC | VEN | REF | 32 | INV | 88 | A | I | CFC | 32.3 | 32.3 |  |  | 2000-12-01 | 2001-10-01 | 2003-01-01 |  | 2005-05-01 | 2005-12-01 | 403590 | -84678 | 318912 | 318912.44 | 100% | -0.44 | 0 |  | 52467 | -11074 | 41393 | 0 | 0 | FIN
FIN | UNEP | Training of customs officers | Individual | LAC | VEN | REF | 34 | TRA | 92 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2003-12-01 |  | 2005-12-01 | 2009-12-01 | 120000 | -12164 | 107836 | 107836 | 100% | 0 | 0 |  | 15600 | -1581 | 14019 | 0 | 0
FIN | UNIDO | Preparation for HCFC phase-out investment activities (refrigeration and air conditioning manufacturing sector) | Individual | LAC | VEN | REF | 60 | PRP | 116 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-06-01 | 2011-04-30 |  | 2011-12-01 | 2013-10-01 | 100000 | -783 | 99217 | 99216.82 | 100% | 0.18 | 0 |  | 7500 | -59 | 7441 | 0 | 0 | FIN
COM | UNIDO | Update the preparation for HCFC phase-out investment activities (stage II) (refrigeration manufacturing sector) | Individual | LAC | VEN | REF | 72 | PRP | 125 | A | I |  | 0 | 0 |  |  | 2014-05-01 | 2014-12-01 | 2015-05-31 |  | 2016-12-01 |  | 50000 | 0 | 50000 | 48759.64 | 97.52% | 1240.36 | 289.96 | 290 | 3500 | 0 | 3413 | 87 | 20 | Project activities completed in 2015, HPMP Stage II 1st Tranche (technical assistance in refrigeration and air-conditioning manufacturing sector) was approved in 2016 at the 76th Meeting of the ExCom. | Project financial closure is in process. Funds will be returned when the open obligations will be cleared. |  |  | NON-INV
FIN | IBRD | Country programme preparation | Individual | LAC | VEN | SEV | 04 | CPG | 59 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 30313 | -27612 | 2701 | 2701 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1991) |  | LAC | VEN | SEV | 04 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 70419 | -57546 | 12873 | 12873 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Country programme preparation | Individual | LAC | VEN | SEV | 06 | CPG | 03 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1994-03-31 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 61591 | -36591 | 25000 | 25000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1992) |  | LAC | VEN | SEV | 06 | PRP | 04 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 107058 | 69729 | 176787 | 176787 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | USA | Assistance in country programme preparation |  | LAC | VEN | SEV | 08 | CPG | 07 | A | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1993-10-01 |  | 1993-10-01 | 1993-10-01 | 43000 | 0 | 43000 | 43000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1992
FIN | UNDP | Institutional strengthening of FONDOIN | Individual | LAC | VEN | SEV | 09 | INS | 13 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-06-01 | 1995-12-01 |  | 1995-12-01 | 1998-12-01 | 329192 | 0 | 329192 | 329192 | 100% | 0 | 0 | 0 | 42794.96 | 0 | 42794.96 | 0 | 0 | Completed in 1995. Financially completed in 1998. |  | 1993 |  | Non-Investment
FIN | IBRD | Preparation of investment projects (1993) |  | LAC | VEN | SEV | 09 | PRP | 14 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 156200 | 23305 | 179505 | 179505 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Finalization of the country programme | Individual | LAC | VEN | SEV | 11 | CPG | 21 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-01 | 1994-05-01 |  | 1995-06-01 | 1997-12-01 | 12000 | 0 | 12000 | 12000 | 100% | 0 | 0 | 0 | 1560 | 0 | 1560 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1993 |  | Non-Investment
FIN | IBRD | Supervision of Faaca project implementation (1994) |  | LAC | VEN | SEV | 12 | PRP | 22 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 47190 | -26845 | 20345 | 20345 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Technical mission completed project preparation during 1994. Project submitted and approved by the E.C. |  |  |  | Non-INV | 0
FIN | IBRD | Supervision of Aaisa project implementation (1994) |  | LAC | VEN | SEV | 12 | PRP | 23 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 47190 | -28772 | 18418 | 18418 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Technical mission completed project preparation during 1994. Project submitted and approved by the E.C. |  |  |  | Non-INV | 0
FIN | IBRD | Supervision of Plásticos Molanca project implementation (1994) |  | LAC | VEN | SEV | 12 | PRP | 24 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 83236 | 9685 | 92921 | 92921 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Funds utilized for finalizing project preparation and for project supervision. |  |  |  | Non-INV | 0
FIN | IBRD | Supervision of air conditioners project implementation (1994) |  | LAC | VEN | SEV | 12 | PRP | 25 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 28665 | -22792 | 5873 | 5873 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | USA | Training in all ODS sectors in Venezuelan Military |  | LAC | VEN | SEV | 15 | TRA | 29 | A | I |  | 0 |  | 0 |  | 1994-12-01 | 1995-01-01 | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 40000 | 3500 | 43500 | 43500 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | IBRD | Preparation/supervision of investment projects ODS V (Aaisa) (1995) |  | LAC | VEN | SEV | 16 | PRP | 33 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 22455 | 0 | 22455 | 22455 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | This activity is now complete. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation/supervision of investment projects ODS IV (Faaca) (1995) |  | LAC | VEN | SEV | 16 | PRP | 34 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 19121 | 0 | 19121 | 19121 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation/supervision of investment projects ODS I and II (1995) |  | LAC | VEN | SEV | 16 | PRP | 35 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 36430 | 0 | 36430 | 36430 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation/supervision of investment projects (central air chillers) (1995) |  | LAC | VEN | SEV | 16 | PRP | 36 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 23966 | 0 | 23966 | 23966 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Institutional strengthening of FONDOIN (renewal) | Individual | LAC | VEN | SEV | 17 | INS | 60 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-01-01 | 1996-12-01 |  | 1996-12-01 | 1999-12-01 | 54900 | 54900 | 109800 | 109800 | 100% | 0 | 0 | 0 | 7137 | 7137 | 14274 | 0 | 0 | Completed in 1996. Financially completed in 1999. |  | 1995 |  | Non-Investment
FIN | IBRD | Project preparation |  | LAC | VEN | SEV | 18 | PRP | 41 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-12-31 |  | 1996-12-31 | 1996-12-31 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 | Project has been dropped in FY97. |  |  |  | Non-INV | 0
FIN | UNDP | Project preparation assistance | Individual | LAC | VEN | SEV | 18 | PRP | 45 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-12-01 | 1998-12-01 | 43000 | 0 | 43000 | 43000 | 100% | 0 | 0 | 0 | 5590 | 0 | 5590 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Renewal of institutional strengthening | Individual | LAC | VEN | SEV | 20 | INS | 50 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-01-01 | 1998-10-01 |  | 1998-07-01 | 1999-12-01 | 219600 | 0 | 219600 | 219600 | 100% | 0 | 0 | 0 | 28548 | 0 | 28548 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1996 |  | Non-Investment
FIN | UNDP | Project preparation in commercial refrigeration recovery and recycling and in the production sector | Individual | LAC | VEN | SEV | 21 | PRP | 52 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1999-12-01 | 2000-12-01 | 155000 | -120000 | 35000 | 35000 | 100% | 0 | 0 | 0 | 20150 | -15600 | 4550 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1997 | 1999-07-01 | Investment
FIN | IBRD | Project preparation |  | LAC | VEN | SEV | 21 | PRP | 53 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | Project has been dropped in FY97. |  |  |  | Non-INV | 0
FIN | UNDP | Renewal of institutional strengthening | Individual | LAC | VEN | SEV | 25 | INS | 65 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-08-01 | 2000-07-01 |  | 2000-07-01 | 2001-12-01 | 219600 | 0 | 219600 | 219600 | 100% | 0 | 0 | 0 | 28548 | 0 | 28548 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening (Phase IV) | Individual | LAC | VEN | SEV | 31 | INS | 87 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2000-07-01 | 2000-08-01 | 2002-08-01 |  | 2002-12-01 | 2004-02-01 | 219600 | 0 | 219600 | 219600 | 100% | 0 | 0 | 0 | 28548 | 0 | 28548 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 2000 |  | Non-Investment
FIN | UNEP | Review of ODS license system and Decree 3220 related to control of these substances | Individual | LAC | VEN | SEV | 34 | TAS | 90 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2002-12-01 |  | 2005-12-01 | 2011-03-01 | 80000 | -40619 | 39381 | 39381 | 100% | 0 | 0 |  | 10400 | -5280.47 | 5119.53 | 0 | 0
FIN | UNDP | Renewal of institutional strengthening project (Phase 6) | Individual | LAC | VEN | SEV | 37 | INS | 95 | N | I | No_ODP | 23.6 | 23.6 | 0 | 0 | 2002-07-01 | 2003-01-01 | 2004-08-01 |  | 2004-12-01 | 2007-07-01 | 285480 | -981 | 284499 | 284499 | 100% | 0 | 0 | 0 | 37112.4 | -127 | 36985.4 | 0 | 0 | Completed in 2004. Financially completed in 2007. |  | 2002 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VII) | Individual | LAC | VEN | SEV | 43 | INS | 99 | N | I | No_ODP | 23.6 | 23.6 | 0 | 0 | 2004-07-01 | 2005-01-01 | 2006-07-01 |  | 2007-12-01 | 2011-12-01 | 285480 | 0 | 285480 | 285480 | 100% | 0 | 0 | 0 | 21411 | 0 | 21411 | 0 | 0 | Completed in 2007. Financially completed in 2011. |  | 2004 |  | Non-Investment
FIN | UNDP | Assistance to carry out an HCFC survey | Individual | LAC | VEN | SEV | 45 | TAS | 102 | A | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-04-01 | 2006-12-01 |  | 2008-08-01 | 2009-12-01 | 45872 | -27909 | 17963 | 17963 | 100% | 0 | 0 | 0 | 4128 | -2511.52 | 1616.482 | -0.002 | 0 | Completed in 2008. Financially completed in 2009. |  | 2005 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening project (phase VIII) | Individual | LAC | VEN | SEV | 49 | INS | 108 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-02-01 | 2008-07-01 |  | 2008-12-01 | 2011-10-01 | 285480 | -0.99 | 285479.01 | 285479 | 100% | 0.01 | 0 | 0 | 21411 | -0.07 | 21410.925 | 0.00505 | 0 | Completed in 2008. |  | 2006 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening project (phase IX) | Individual | LAC | VEN | SEV | 56 | INS | 113 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-01-01 | 2010-12-01 |  | 2010-12-01 | 2013-02-01 | 285480 | -2637.08 | 282842.92 | 282843 | 100% | -0.08 | 0 | 0 | 21411 | -197.78 | 21213.225 | -0.005 | 0 | Financially completed in 2013. |  | 2008 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening project (phase X) | Individual | LAC | VEN | SEV | 62 | INS | 117 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-04-01 | 2012-12-01 |  | 2013-03-01 | 2014-12-01 | 285480 | -22556 | 262924 | 262924 | 100% | 0 | 0 | 0 | 21411 | -1692 | 19719 | 0 | 0 | Financially completed in 2014. | Project completed in 2013. | 2010 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening project (phase XI: 1/2013-12/2014) | Individual | LAC | VEN | SEV | 68 | INS | 122 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-04-01 | 2014-12-01 |  | 2014-12-01 | 2015-12-01 | 285480 | -23.98 | 285456.02 | 285456 | 100% | 0.02 | 0 | 0 | 19984 | -1.68 | 19982.32 | 2.8002e-08 | 0 | Financially completed in 2015. | As planned, the 2014 workplan and budget was prepared and approved. HCFC quotas for 2014 established. | 2012 |  | Non-investment
ONG | UNDP | Renewal of institutional strengthening project (phase XII: 1/2015-12/2016) | Individual | LAC | VEN | SEV | 73 | INS | 128 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-11-01 | 2015-12-01 | 2016-12-01 | 2017-01-01 |  |  | 285480 | 0 | 285480 | 178450.94 | 62.51% | 107029.06 | 0 | 42811.624 | 19984 | 0 | 12491.8158 | 7492.1842 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Institutional strengthening activities underway. ODS consumption reports prepared and submitted. Celebration of Ozone Day carried out. 2016 HCFC import quota set. NOU attended regional and global meetings. Prodoc signed (actual/planned, yes/no and date):The agreement has been signed earlier. Missions undertaken (actual/planned):0 of 0 TOR for consultants/subcontracts completed (actual/planned): TOR completed earlier. Contract/PO/MOA agreements signed: 1 of 1 First disbursement date (actual/planned): 42339Any delays/problems (yes/no):Yes If Yes, reasons for delay & action plan to resolve:Due to devaluation of the Venezuelan Bolivar, budget implementation was slower than planned and adjustement to the annual work plan were made. | Annual work plan prepared. HCFC import quota set for 2017. | 2014 |  | Non-Investment
ONG | UNIDO | Survey of ODS alternatives at the national level | Individual | LAC | VEN | SEV | 74 | TAS | 129 | A | I |  | 0 | 0 |  |  | 2015-05-01 | 2016-07-01 | 2016-05-31 | 2017-12-31 |  |  | 130000 | 0 | 130000 | 49522.21 | 38.09% | 80477.79 | 3709.15 | 80000 | 11700 | 0 | 0 | 11700 | 333.8235 | Brief report: The survey is ongoing. Activities planned but not implemented: No Was any delay during the reporting year? Yes, due to the security situation in the country the data collection was delayed. Any recurring problem? No Any impact on project completion date: Yes Any actions required by Executive Committee? No | Brief report: The survey is ongoing. Activities planned but not implemented: No Actions towards next goal: completion of the survey till 3rd quarter 2017 Was any delay during the reporting year? Yes, due to the security situation in the country the data collection was delayed. Any recurring problem? No Any impact on project completion date: Yes Any actions required by Executive Committee? No |  |  | NON-INV
ONG | UNDP | Renewal of institutional strengthening project (phase XIII: 1/2017-12/2018) | Individual | LAC | VEN | SEV | 77 | INS | 135 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2016-12-01 |  | 2018-12-01 | 2017-12-01 |  |  | 365414 | 0 | 365414 | 0 | 0% | 365414 | 0 | 146165.6 | 25579 | 0 | 0 | 25579 | 0 | Newly Approved | DoA sent in February 2017. ProDoc signed, anual work plan was prepared. | 2016 |  | Non-Investment
FIN | UNIDO | Training and awareness workshop in the process agents (TCA) sector | Individual | LAC | VEN | SOL | 45 | TAS | 103 | A | I | TCA | 1.9 | 1.9 |  |  | 2005-04-01 | 2006-04-01 | 2006-04-01 |  | 2006-12-01 | 2007-12-01 | 40000 | -1005 | 38995 | 38994.65 | 100% | 0.35 | 0 |  | 3600 | -90 | 3510 | 0 | 0 | FIN |  |  |  | INV
FIN | UNDP | Conversion to hydrocarbon aerosol propellant technology at Saigon Cosmetics Company | Individual | ASP | VIE | ARS | 17 | INV | 07 | A | I | CFC | 80 | 80 | 0 | 0 | 1995-07-01 | 1995-12-01 | 1996-12-01 |  | 1998-08-01 | 2000-12-01 | 238430 | -2438.84 | 235991.16 | 235991 | 100% | 0.16 | 0 | 0 | 30995.9 | -317.05 | 30678.83 | 0.02 | 0 | Completed in 1998. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNDP | Conversion to CFC-free hydrocarbon aerosol propellant technology at Daso Company Ltd. | Individual | ASP | VIE | ARS | 18 | INV | 10 | A | I | CFC | 27 | 27 | 0 | 0 | 1995-11-01 | 1996-12-01 | 1996-11-01 |  | 1999-12-01 | 2001-08-01 | 110340 | -320 | 110020 | 110020 | 100% | 0 | 0 | 0 | 14344.2 | -41.6 | 14302.6 | 0 | 0 | Completed in 1999. Financially completed in 2001. |  | 1995 | 1999-06-01 | Investment
FIN | UNDP | Conversion to hydrocarbon aerosol propellant technology at Cosmetics Producing and Trading Company (CP & T) | Individual | ASP | VIE | ARS | 18 | INV | 11 | A | I | CFC | 85 | 85 | 0 | 0 | 1995-11-01 | 1997-05-01 | 1997-05-01 |  | 2002-05-01 | 2003-11-01 | 285120 | -2641 | 282479 | 282479 | 100% | 0 | 0 | 0 | 37065.6 | -343.33 | 36722.27 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 1995 | 1999-09-01 | Investment
FIN | UNDP | Project preparation for one project in the aerosol sector | Individual | ASP | VIE | ARS | 24 | PRP | 19 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-08-01 | 1998-12-01 |  | 2000-12-01 | 2001-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNDP | Preparation of a project in the aerosol sector | Individual | ASP | VIE | ARS | 30 | PRP | 25 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2000-12-01 | 2003-01-01 | 10000 | -2192 | 7808 | 7808 | 100% | 0 | 0 | 0 | 1300 | -284.96 | 1015.04 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Phase-out of CFC-12 in the manufacture of perfumes by conversion to hydrocarbon propellants at Nam Do Corporation | Individual | ASP | VIE | ARS | 31 | INV | 28 | A | I | CFC | 11.3 | 11.3 | 0 | 0 | 2000-07-01 | 2002-10-01 | 2003-08-01 |  | 2005-06-01 | 2008-10-01 | 49720 | 0 | 49720 | 49720 | 100% | 0 | 0 | 0 | 6463.6 | 0 | 6463.6 | 0 | 0 | Completed in 2005. Financially completed in 2008. |  | 2000 |  | Investment
FIN | UNDP | Project preparation in the aerosol sector | Individual | ASP | VIE | ARS | 33 | PRP | 31 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-11-01 | 2002-04-01 |  | 2002-12-01 | 2003-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Terminal umbrella project for the aerosol sector to phase-out ODS consumption in the manufacture of aerosols and perfumes by conversion to hydrocarbon propellant (Dong A and Thorakao Cosmetics Ltd.) | Individual | ASP | VIE | ARS | 37 | INV | 40 | A | I | CFC | 28.5 | 28.5 | 0 | 0 | 2002-07-01 | 2003-02-01 | 2005-04-01 |  | 2005-06-01 | 2007-03-01 | 125400 | 0 | 125400 | 125400 | 100% | 0 | 0 | 0 | 16302 | 0 | 16302 | 0 | 0 | Completed in 2005. Financially completed in 2007. |  | 2002 |  | Investment
FIN | UNDP | Preparation of two projects in general foam subsector | Individual | ASP | VIE | FOA | 27 | PRP | 21 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 2000-04-01 |  | 2000-12-01 | 2001-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1999 |  | Investment
FIN | UNDP | Preparation of a project in the foam general sector | Individual | ASP | VIE | FOA | 30 | PRP | 24 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-07-01 | 2003-01-01 | 20000 | -625 | 19375 | 19375 | 100% | 0 | 0 | 0 | 2600 | -81.25 | 2518.75 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | ASP | VIE | FOA | 33 | PRP | 32 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-07-01 | 2003-07-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 650 | 0 | 650 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | IBRD | Preparation of a HCFC foam sector plan |  | ASP | VIE | FOA | 60 | PRP | 54 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-12-01 | 2011-04-30 |  | 2011-04-01 | 2011-06-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 7500 | 0 | 7500 | 0 | 0 | Fully completed and disbursed. Foam sector plan and HPMP approved at the 63rd ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation for HCFC phase-out investment activities (stage II) (foam sector) |  | ASP | VIE | FOA | 72 | PRP | 66 | A | I |  | 0 | 0 | 0 | 0 | 2014-05-01 | 2015-12-01 | 2016-05-31 |  | 2016-05-01 | 2016-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 | 0 | 5600 | 0 | 5600 | 0 | 0 | PU foam sector plan including XPS, systems house and multiple subsectors using imported HCFC-based preblended polyol prepared, included in the Stage II HPMP and submitted end Jan 16. Project approved in May 2016. | Stage II foam sector plan completed and approved. |  |  | Non-INV | 0
FIN | UNIDO | Project formulation in the methyl bromide sector | Individual | ASP | VIE | FUM | 22 | PRP | 16 | A | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-12-01 | 1997-07-01 |  | 1999-01-01 | 2001-07-01 | 8000 | -624 | 7376 | 7376 | 100% | 0 | 0 |  | 1040 | -83 | 957 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNIDO | Alternatives to the use of methyl bromide on stacked bags of rice, grain in silos and timber on a warehouse under tarps at Vietnam Fumigation Company | Individual | ASP | VIE | FUM | 24 | DEM | 20 | A | I | MBR | 0 | 0 |  |  | 1998-03-01 | 1998-11-01 | 2000-04-01 |  | 2003-12-01 | 2004-12-01 | 411180 | -9744 | 401436 | 401435.78 | 100% | 0.22 | 0 |  | 53453 | -1349 | 52104 | 0 | 0 | FIN
FIN | IBRD | Project preparation for methyl bromide phase-out plan |  | ASP | VIE | FUM | 44 | PRP | 44 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-12-01 | 2005-12-01 |  | 2006-11-01 | 2006-11-01 | 65000 | 0 | 65000 | 65000 | 100% | 0 | 0 |  | 4875 | 0 | 4875 | 0 | 0 | Project prepared, submitted and approved at the 50th ExCom Meeting. |  |  |  | Non-INV | 0
FIN | IBRD | National phase-out plan of out methyl bromide (first tranche) | Multiyear | ASP | VIE | FUM | 50 | INV | 48 | N | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2009-12-01 | 2007-11-01 |  | 2011-11-01 | 2014-12-01 | 230000 | 0 | 230000 | 230000 | 100% | 0 | 0 |  | 17250 | 0 | 17250 | 0 | 0 | National MB Phase-out Plan completed. |  |  |  | INV | 0
FIN | IBRD | National phase-out plan of out methyl bromide (second tranche) | Multiyear | ASP | VIE | FUM | 59 | INV | 53 | N | I | MBR | 5.2 | 5.2 | 0 | 0 | 2009-11-01 | 2011-12-01 | 2011-11-30 |  | 2012-12-01 | 2014-12-01 | 650000 | 0 | 650000 | 650000 | 100% | 0 | 0 |  | 48750 | 0 | 48750 | 0 | 0 | National MB Phase-out Plan completed. |  |  |  | INV | 0
FIN | IBRD | National phase-out plan of methyl bromide (third tranche) | Multiyear | ASP | VIE | FUM | 65 | INV | 59 | N | I | MBR | 10 | 10 | 0 | 0 | 2011-11-01 | 2012-12-01 | 2013-11-30 |  | 2013-11-01 | 2014-12-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 | 0 |  | 9000 | 0 | 9000 | 0 | 0 | National MB Phase-out Plan completed. |  |  |  | INV | 0
FIN | IBRD | National phase-out plan of methyl bromide (fourth tranche) | Multiyear | ASP | VIE | FUM | 70 | INV | 61 | N | I | MBR | 20 | 20 | 0 | 0 | 2013-07-01 | 2013-12-01 | 2014-07-31 |  | 2014-12-01 | 2014-12-01 | 58284 | 0 | 58284 | 58284 | 100% | 0 | 0 |  | 4371 | 0 | 4371 | 0 | 0 | National MB Phase-out Plan completed. |  |  |  | INV | 0
FIN | IBRD | National phase-out plan of methyl bromide (fifth tranche) | Multiyear | ASP | VIE | FUM | 72 | INV | 67 | N | I | MBR | 50 | 50 | 0 | 0 | 2014-05-01 | 2014-12-01 | 2015-05-31 |  | 2014-12-01 | 2014-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 3000 | 0 | 3000 | 0 | 0 | National MB Phase-out Plan completed. |  |  |  | INV | 0
FIN | UNIDO | Technical assistance in preparation of the national halon bank management programme | Individual | ASP | VIE | HAL | 29 | TAS | 23 | A | I | HAL | 37.1 | 37.1 |  |  | 1999-11-01 | 2000-09-01 | 2000-12-01 |  | 2003-01-01 | 2003-12-01 | 25000 | -7148 | 17852 | 17851.65 | 100% | 0.35 | 0 |  | 3250 | -933 | 2317 | 0 | 0 | FIN |  |  |  | INV
FIN | IBRD | Preparation of a national CFC phase-out plan |  | ASP | VIE | PHA | 39 | PRP | 41 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-12-01 | 2004-09-01 |  | 2004-09-01 | 2004-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 |  | 4500 | 0 | 4500 | 0 | 0 | Project preparation completed and project approved at the 45th ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | National CFC and halon phase-out plan (first tranche) | Multiyear | ASP | VIE | PHA | 45 | INV | 45 | N | I | CFC | 40 | 40 | 0 | 0 | 2005-04-01 | 2006-11-01 | 2007-04-01 |  | 2008-07-01 | 2011-02-01 | 495537 | 0 | 495537 | 495537 | 100% | 0 | 0 |  | 37165 | 0 | 37165 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | National CFC and halon phase-out plan (second tranche) | Multiyear | ASP | VIE | PHA | 49 | INV | 47 | N | I | CFC | 165 | 165 | 0 | 0 | 2006-07-01 | 2008-12-01 | 2007-07-01 |  | 2009-06-01 | 2011-02-01 | 586000 | 0 | 586000 | 586000 | 100% | 0 | 0 |  | 43950 | 0 | 43950 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | National CFC and halon phase-out plan (third tranche) | Multiyear | ASP | VIE | PHA | 55 | INV | 51 | N | I | CFC | 58.7 | 58.7 | 0 | 0 | 2008-07-01 | 2009-12-01 | 2010-07-31 |  | 2010-12-01 | 2011-02-01 | 178463 | -551.92 | 177911.08 | 177911.08 | 100% | 0 | 0 |  | 13385 | -41.4 | 13343.6 | 0 | 0 | Project physically and financially completed. Unused amount of US$552 returned. |  |  |  | INV | 0
FIN | IBRD | Preparation of a HCFC phase-out management plan |  | ASP | VIE | PHA | 55 | PRP | 50 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2010-12-01 | 2009-12-31 |  | 2011-03-01 | 2011-06-01 | 195000 | 0 | 195000 | 195000 | 100% | 0 | 0 |  | 14625 | 0 | 14625 | 0 | 0 | Fully completed and disbursed. Project approved at the 63rd Meeting. |  |  |  | Non-INV | 0
ONG | IBRD | HCFC phase-out management plan (stage I, first tranche) (foam sector plan) | Multiyear | ASP | VIE | PHA | 63 | INV | 56 | N | I | HCFC | 44.7 | 44.7 | 0 | 0 | 2011-04-01 | 2013-12-01 | 2012-03-31 | 2017-06-01 |  |  | 2832518 | 0 | 2832518 | 2832518 | 100% | 0 | 0 | 0 | 212439 | 0 | 212439 | 0 | 0 | HCFC import quota for 2017 issued. Six of 11 subprojects completed as of end 2016. Implementation is in late stages for remaining companies, all having purchased equipment and most installed. Final tranche request approved at the 76th ExCom with agreement to substitute 12th original enterprise. However, due to late approval in Stage I and substantial cut in funding (less than a third eligible), the enterprise with the PMU have decided not to participate in the subproject. TA/PMU activities achieved in 2016 include one expert consultancy and, 11 training and awareness raising workshops on good practice in HCFC management and HCFC phaseout in refrigeration and AC. Two safety training workshops held in Jun and Aug 16 for foam beneficiaries and local agencies. Bulk HCFC-141b import has been banned since 2015. 79% of adjusted Stage I HPMP funds disbursed. | As of end Mar 17, an additional 4 enterprises have completed subprojects bringing the number up to 10. Final subproject is expected to be completed by Apr. 17. Two last TA/training activities planned before closing of the project which is scheduled for 30 Jun 2017. A policy recommendation by MONRE expected by Apr 17 to no longer issue licenses for new or expansion of existing foam production facilities that use HCFC-141b-based polyol. |  |  | INV | 0 | To request the submission of additional status report to the 79th meeting to monitor ongoing project with 100 per cent of fund disbursement.
ONG | IBRD | HCFC phase-out management plan (stage I, first tranche) (Technical assistance and project management) | Multiyear | ASP | VIE | PHA | 63 | TAS | 58 | N | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2013-12-01 | 2012-12-31 | 2017-06-01 |  |  | 221905 | 0 | 221905 | 221905 | 100% | 0 | 0 | 0 | 16643 | 0 | 16643 | 0 | 0 | HCFC import quota for 2017 issued. Six of 11 subprojects completed as of end 2016. Implementation is in late stages for remaining companies, all having purchased equipment and most installed. Final tranche request approved at the 76th ExCom with agreement to substitute 12th original enterprise. However, due to late approval in Stage I and substantial cut in funding (less than a third eligible), the enterprise with the PMU have decided not to participate in the subproject. TA/PMU activities achieved in 2016 include one expert consultancy and, 11 training and awareness raising workshops on good practice in HCFC management and HCFC phaseout in refrigeration and AC. Two safety training workshops held in Jun and Aug 16 for foam beneficiaries and local agencies. Bulk HCFC-141b import has been banned since 2015. 79% of adjusted Stage I HPMP funds disbursed. | As of end Mar 17, an additional 4 enterprises have completed subprojects bringing the number up to 10. Final subproject is expected to be completed by Apr. 17. Two last TA/training activities planned before closing of the project which is scheduled for 30 Jun 2017. A policy recommendation by MONRE expected by Apr 17 to no longer issue licenses for new or expansion of existing foam production facilities that use HCFC-141b-based polyol. |  |  | Non-INV | 0 | To request the submission of additional status report to the 79th meeting to monitor ongoing project with 100 per cent of fund disbursement.
ONG | IBRD | HCFC phase-out management plan (stage I, second tranche) (foam sector plan) | Multiyear | ASP | VIE | PHA | 71 | INV | 62 | N | I | HCFC | 89.4 | 89.4 | 0 | 0 | 2013-12-01 | 2014-12-01 | 2015-12-31 | 2017-06-01 |  |  | 5663016 | 0 | 5663016 | 4124893.2 | 72.84% | 1538122.8 | 1538122.8 | 1262223 | 424726 | 0 | 309366.84 | 115359.16 | 115359.16 | HCFC import quota for 2017 issued. Six of 11 subprojects completed as of end 2016. Implementation is in late stages for remaining companies, all having purchased equipment and most installed. Final tranche request approved at the 76th ExCom with agreement to substitute 12th original enterprise. However, due to late approval in Stage I and substantial cut in funding (less than a third eligible), the enterprise with the PMU have decided not to participate in the subproject. TA/PMU activities achieved in 2016 include one expert consultancy and, 11 training and awareness raising workshops on good practice in HCFC management and HCFC phaseout in refrigeration and AC. Two safety training workshops held in Jun and Aug 16 for foam beneficiaries and local agencies. Bulk HCFC-141b import has been banned since 2015. 79% of adjusted Stage I HPMP funds disbursed. | As of end Mar 17, an additional 4 enterprises have completed subprojects bringing the number up to 10. Final subproject is expected to be completed by Apr. 17. Two last TA/training activities planned before closing of the project which is scheduled for 30 Jun 2017. A policy recommendation by MONRE expected by Apr 17 to no longer issue licenses for new or expansion of existing foam production facilities that use HCFC-141b-based polyol. |  |  | INV | 0
COM | IBRD | Preparation of a HCFC phase-out management plan (stage II) |  | ASP | VIE | PHA | 72 | PRP | 65 | A | I |  | 0 | 0 | 0 | 0 | 2014-05-01 | 2014-12-01 | 2016-05-31 |  | 2016-07-01 |  | 90000 | 0 | 90000 | 58000 | 64.44% | 32000 | 32000 | 32000 | 6300 | 0 | 4060 | 2240 | 2240 | Stage II HPMP finalized and submitted to the ExCom by end Jan 16. Project approved in May 2016. | WB new Grant Agreement preparation mission conducted in Mar 17 which included discussion on implementation/funding modalities, project implementation procedures, safeguards and others. Balance of preparation funds disbursed. |  |  | Non-INV | 0
ONG | IBRD | HCFC phase-out management plan (stage II, first tranche) (polyurethane rigid foam sector) | Multiyear | ASP | VIE | PHA | 76 | INV | 70 | N | I | HCFC | 5.4 | 0 | 0 | 0 | 2016-05-01 |  | 2017-12-31 | 2018-12-01 |  |  | 396095 | 0 | 396095 | 0 | 0% | 396095 | 396095 | 20000 | 27727 | 0 | 0 | 27727 | 27727 | Preparation steps towards a new Grant Agreement between Vietnam and the WB initiated thru a WB mission on procurement and disbursement arrangements in Jul 16. Safeguards plan and other initial requirements prepared in draft by fall 2016. Step-wise process on both sides must be followed until GA approval, expected in 2017. | WB mission to Vietnam conducted in Mar 17 to continue Grant Agreement preparation between Vietnam and WB. Implementation/disbursement modalities for SMEs and system houses further discussed with NOU/PMU. Second GoV approval and project implementation manual, incl. with activity/consultant TORs expected end May 17 and last approval by end Jun 17. All WB and Vietnam approvals, negotiation and effectiveness expected by Fall 2017. |  |  | INV | 0
ONG | IBRD | HCFC phase-out management plan (stage I, third tranche) (foam sector plan) | Multiyear | ASP | VIE | PHA | 76 | INV | 72 | N | I | HCFC | 9.1 | 9.1 | 0 | 0 | 2016-05-01 |  | 2016-12-31 | 2017-06-01 |  |  | 407581 | 0 | 407581 | 0 | 0% | 407581 | 407581 | 407581 | 30569 | 0 | 0 | 30569 | 30569 | HCFC import quota for 2017 issued. Six of 11 subprojects completed as of end 2016. Implementation is in late stages for remaining companies, all having purchased equipment and most installed. Final tranche request approved at the 76th ExCom with agreement to substitute 12th original enterprise. However, due to late approval in Stage I and substantial cut in funding (less than a third eligible), the enterprise with the PMU have decided not to participate in the subproject. TA/PMU activities achieved in 2016 include one expert consultancy and, 11 training and awareness raising workshops on good practice in HCFC management and HCFC phaseout in refrigeration and AC. Two safety training workshops held in Jun and Aug 16 for foam beneficiaries and local agencies. Bulk HCFC-141b import has been banned since 2015. 79% of adjusted Stage I HPMP funds disbursed. | As of end Mar 17, an additional 4 enterprises have completed subprojects bringing the number up to 10. Final subproject is expected to be completed by Apr. 17. Two last TA/training activities planned before closing of the project which is scheduled for 30 Jun 2017. A policy recommendation by MONRE expected by Apr 17 to no longer issue licenses for new or expansion of existing foam production facilities that use HCFC-141b-based polyol. |  |  | INV | 0
ONG | Japan | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) |  | ASP | VIE | PHA | 76 | TAS | 71 | A | I | HCFC-22 | 0 |  | 0 |  | 2016-05-01 |  | 2017-12-01 | 2018-12-01 |  |  | 43250 | 0 | 43250 |  | 0% | 43250 |  | 10000 | 5623 | 0 |  | 5623 |  | Initial consultations on implementation arrangements undertaken. Activities will begin once the overarching agreement between Vietnam and the WB is concluded. A step-wise process on both sides must be followed until agreement approval, expected in 2017. | Mission to Vietnam conducted in Feb 17 by Japanese TA provider representatives to discuss TA, disbursement modalities and implementation arrangements with the NOU/PMU. Draft TOR prepared and an initial workshop with AC enterprises tentatively planned in anticipation of the effectiveness of new Vietnam-WB agreement in the fall of 2017.
FIN | UNIDO | Phasing out ODS at the Searefico and Searee industrial refrigeration plants of Seaprodex Co. | Individual | ASP | VIE | REF | 15 | INV | 04 | A | I | CFC | 40 | 40 |  |  | 1994-12-01 | 1995-12-01 | 1996-06-01 |  | 1996-12-01 | 2000-07-01 | 497070 | -2690 | 494380 | 494380 | 100% | 0 | 0 |  | 64619 | -452 | 64167 | 0 | 0 | FIN
FIN | UNIDO | Preparation of project proposals for the reduction of refrigerant emission and establishment of collection and reclaiming network in domestic refrigeration sector | Individual | ASP | VIE | REF | 15 | PRP | 05 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-09-01 | 1995-06-01 |  | 1996-12-01 | 1998-08-01 | 15000 | -14776 | 224 | 224 | 100% | 0 | 0 |  | 1950 | -1921 | 29 | 0 | 0 | FIN
FIN | UNIDO | Preparation of investment project for reduction of refrigerant emissions and conversion of food processing and other industrial refrigeration and A/C equipment to suitable alternatives | Individual | ASP | VIE | REF | 15 | PRP | 06 | A | I |  | 0 | 0 |  |  | 1994-12-01 | 1995-05-01 | 1995-06-01 |  | 1996-12-01 | 1998-08-01 | 20000 | -11168 | 8832 | 8832 | 100% | 0 | 0 |  | 2600 | -1454 | 1146 | 0 | 0 | FIN
FIN | UNDP | Demonstration project in CFC recycling and emissions reduction in the commercial refrigeration sector | RMP-Component | ASP | VIE | REF | 20 | DEM | 13 | A | I | CFC | 28.2 | 28.2 | 0 | 0 | 1996-10-01 | 1999-10-01 | 1998-09-01 |  | 2002-12-01 | 2004-09-01 | 168216 | -10238 | 157978 | 157978 | 100% | 0 | 0 | 0 | 21868.08 | -1330.94 | 20537.1449 | -0.0049 | 0 | Completed in 2002. Financially completed in 2004. |  | 1996 | 2000-07-01 | Non-Investment
FIN | Australia | Demonstration project CFC recycling and emissions reduction in the commercial refrigeration sector | Individual | ASP | VIE | REF | 20 | DEM | 14 | A | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1999-10-01 | 1997-12-01 |  | 2001-12-01 | 2005-06-01 | 282687 | -42162 | 240525 | 240525 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Completed |  | 1996 | 1997-12-01
FIN | USA | MAC servicing demonstration project |  | ASP | VIE | REF | 20 | DEM | 15 | A | I |  | 0 |  | 0 |  | 1996-10-01 | 1997-03-01 | 1998-12-01 |  | 1998-12-01 | 1998-12-01 | 300000 | -159091 | 140909 | 140909 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Terminated. |  | 1996 | 1998-12-01
FIN | France | Technical assistance on alternative technologies for cold storage facilities and project preparation |  | ASP | VIE | REF | 20 | TAS | 12 | A | I |  | 0 |  | 0 |  | 1996-10-01 | 1996-11-01 | 1997-10-01 |  | 1998-09-01 | 1999-05-01 | 40000 | -5500 | 34500 | 34500 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed
CLO | UNDP | Project preparation in the domestic refrigeration sub-sector | Individual | ASP | VIE | REF | 22 | PRP | 17 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 |  | 1997-12-01 |  |  | 1998-07-01 | 25000 | -25000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 3250 | -3250 | 0 | 0 | 0 | Canceled in 1998. Financially Completed in 1998. |  | 1997 |  | Investment
FIN | UNEP | Assistance for formulation of a refrigerant management plan | RMP | ASP | VIE | REF | 23 | PRP | 18 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1998-11-01 |  | 2001-07-01 | 2002-07-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 |  |  |  | 1999-12-01
FIN | France | CFC emission reductions in spinning halls air conditioning systems chillers (pilot project) |  | ASP | VIE | REF | 28 | INV | 22 | A | I | CFC | 3.6 | 3.6 | 0 |  | 1999-07-01 | 2001-06-01 | 2001-08-01 |  | 2002-12-01 | 2002-12-01 | 197340 | 0 | 197340 | 197340 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed |  |  | 2002-12-01
FIN | UNDP | Preparation of a project in the refrigeration recycling subsector | Individual | ASP | VIE | REF | 30 | PRP | 26 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2000-12-01 | 2003-01-01 | 5000 | -1096 | 3904 | 3904 | 100% | 0 | 0 | 0 | 650 | -142.48 | 507.52 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Preparation of a refrigerant recycling project | Individual | ASP | VIE | REF | 33 | PRP | 29 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 650 | 0 | 650 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNEP | Implementation of the RMP: workshop for finalization of regulations | Individual | ASP | VIE | REF | 34 | TAS | 33 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2001-10-01 |  | 2002-01-01 | 2003-06-01 | 4350 | 0 | 4350 | 4350 | 100% | 0 | 0 |  | 566 | 0 | 566 | 0 | 0
TRF | Australia | Implementation of the RMP: programme for recovery and recycling of CFC-12 refrigerant | Individual | ASP | VIE | REF | 34 | TAS | 34 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 |  | 2003-08-01 |  |  | 2001-12-01 | 290413 | -290413 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 37754 | -37754 | 0 | 0 | 0 | Transferred to UNDP- 35th ExCom |  | 2001
FIN | UNDP | Implementation of the RMP: MAC recovery and recycling of CFC-12 refrigerant | RMP-Component | ASP | VIE | REF | 34 | TAS | 35 | A | I | CFC | 5.8 | 5.8 | 0 | 0 | 2001-07-01 | 2002-12-01 | 2003-08-01 |  | 2003-08-01 | 2007-01-01 | 50500 | 0 | 50500 | 50500 | 100% | 0 | 0 | 0 | 6565 | 0 | 6565 | 0 | 0 | Completed in 2003. Financially completed in 2007. |  | 2001 |  | Non-Investment
FIN | Poland | Implementation of the RMP: Customs training programme | RMP Update | ASP | VIE | REF | 34 | TAS | 37 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 |  | 2003-01-01 |  | 2003-01-01 |  | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Reason for delays in completion of Phase I of the Project was a delay in the payment of Polish contribution covering a cost of the project because of problems with national budget. Payment of outstanding contribution was confirmed through a letter of 21 March 2002 from the UN Office in Nairobi (CP/4040-01-71).
FIN | UNDP | Implementation of the RMP: Monitoring the activities in the RMP | RMP-Component | ASP | VIE | REF | 34 | TAS | 38 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-07-01 | 2004-01-01 | 2004-08-01 |  | 2004-12-01 | 2007-01-01 | 21600 | -242 | 21358 | 21358 | 100% | 0 | 0 | 0 | 2808 | -31.46 | 2776.54 | 0 | 0 | Completed in 2004. Financially completed in 2007. |  | 2001 |  | Non-Investment
FIN | UNEP | Implementation of the RMP: train the trainer programme in the refrigeration servicing sector | Individual | ASP | VIE | REF | 34 | TRA | 36 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-10-01 | 2003-08-01 |  | 2003-12-01 | 2006-02-01 | 200000 | -40959 | 159041 | 159041 | 100% | 0 | 0 |  | 26000 | -5324.67 | 20675.33 | 0 | 0
FIN | UNDP | Implementation of the RMP: Programme for recovery and recycling of CFC-12 refrigerant | RMP-Component | ASP | VIE | REF | 35 | TAS | 39 | A | I | CFC | 17 | 17 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-01-01 |  | 2004-12-01 | 2007-03-01 | 290413 | -22502 | 267911 | 267911 | 100% | 0 | 0 | 0 | 37754 | -2925.28 | 34828.716 | 0.004 | 0 | Completed in 2004. Financially completed in 2007. |  | 2001 |  | Non-Investment
FIN | IBRD | Preparation of a HCFC refrigeration sector plan |  | ASP | VIE | REF | 60 | PRP | 55 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-12-01 | 2011-04-30 |  | 2011-04-01 | 2011-04-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 |  | 7500 | 0 | 7500 | 0 | 0 | Fully completed and disbursed. ExCom asked that the AC component be removed from the proposed HPMP and action plan at its 63rd meeting. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation for HCFC phase-out investment activities (stage II) (air-conditioning sector) |  | ASP | VIE | REF | 72 | PRP | 63 | A | I |  | 0 | 0 | 0 | 0 | 2014-05-01 | 2015-12-01 | 2016-05-31 |  | 2016-05-01 | 2016-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 4200 | 0 | 4200 | 0 | 0 | AC sector plan prepared, included in the Stage II HPMP and submitted end Jan 16. Project approved in May 2016. | Stage II AC sector plan completed and approved. |  |  | Non-INV | 0
FIN | IBRD | Preparation for HCFC phase-out investment activities (stage II) (refrigeration sector) |  | ASP | VIE | REF | 72 | PRP | 64 | A | I |  | 0 | 0 | 0 | 0 | 2014-05-01 | 2015-12-01 | 2016-05-31 |  | 2016-05-01 | 2016-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 4200 | 0 | 4200 | 0 | 0 | Refrigeration sector plan prepared, included in the Stage II HPMP and submitted end Jan 16. Only part of the refrigeration sector plan was approved in May 2016. | Stage II partial refrigeration sector plan completed and approved. |  |  | Non-INV | 0
FIN | UNDP | Project preparation assistance | Individual | ASP | VIE | SEV | 12 | PRP | 01 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-03-01 |  | 1996-06-01 | 1998-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNEP | Country programme preparation | Individual | ASP | VIE | SEV | 13 | CPG | 02 | A | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-11-01 | 1995-10-01 |  | 1996-05-01 | 1996-10-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | France | Country programme preparation |  | ASP | VIE | SEV | 13 | CPG | 03 | A | D |  | 0 |  | 0 |  | 1994-07-01 | 1994-08-01 | 1995-07-01 |  | 1995-07-01 | 1995-07-01 | 30000 | -8965 | 21035 | 21035 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed
FIN | UNEP | Establishment of the ozone unit (institutional strengthening) | Individual | ASP | VIE | SEV | 17 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-05-01 | 1998-07-01 |  | 1999-04-01 | 1999-11-01 | 137280 | 0 | 137280 | 137280 | 100% | 0 | 0 |  | 17846 | 0 | 17846 | 0 | 0 |  |  |  | 1999-12-01
FIN | UNEP | Technology cooperation workshop for ODS elimination | Individual | ASP | VIE | SEV | 17 | TRA | 09 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-09-01 | 1995-12-01 |  | 1996-06-01 | 1999-04-01 | 27000 | 0 | 27000 | 27000 | 100% | 0 | 0 |  | 3510 | 0 | 3510 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening (phase II) | Individual | ASP | VIE | SEV | 28 | INS | 27 | A | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 1999-10-01 | 2001-08-01 |  | 2001-06-01 | 2001-12-01 | 91520 | 0 | 91520 | 91520 | 100% | 0 | 0 |  | 11898 | 0 | 11898 | 0 | 0 |  |  |  | 2001-06-01
FIN | UNEP | Renewal of the institutional strengthening project (Phase III) | Individual | ASP | VIE | SEV | 33 | INS | 30 | A | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-08-01 | 2003-04-01 |  | 2003-07-01 | 2004-07-01 | 91520 | 0 | 91520 | 91520 | 100% | 0 | 0 |  | 11898 | 0 | 11898 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project | Individual | ASP | VIE | SEV | 40 | INS | 42 | A | I | CFC | 9.8 | 10.2 | 0 | 0 | 2003-07-01 | 2004-01-01 | 2005-07-01 |  | 2005-07-01 | 2007-12-01 | 118976 | -20 | 118956 | 118956 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of institutional strengthening project (phase V) | Individual | ASP | VIE | SEV | 46 | INS | 46 | A | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-08-01 | 2007-07-01 |  | 2007-07-01 | 2007-12-01 | 118976 | 0 | 118976 | 118976 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase VI) | Individual | ASP | VIE | SEV | 52 | INS | 49 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-12-01 | 2009-06-01 |  | 2009-06-01 | 2009-06-01 | 118976 | 0 | 118976 | 118976 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VII) | Individual | ASP | VIE | SEV | 57 | INS | 52 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-08-01 | 2011-06-01 |  | 2011-06-01 | 2011-11-01 | 118976 | 0 | 118976 | 118976 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VIII) | Individual | ASP | VIE | SEV | 63 | INS | 57 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-11-01 | 2013-06-01 |  | 2013-06-01 | 2014-06-01 | 118976 | 0 | 118976 | 118976 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IX: 7/2013-6/2015) | Individual | ASP | VIE | SEV | 68 | INS | 60 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2014-06-01 | 2015-06-01 |  | 2015-06-01 | 2016-12-01 | 118976 | 0 | 118976 | 118976 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Project financially completed. | Project financially completed.
ONG | UNEP | Extension of the institutional strengthening project (phase X: 7/2015-6/2017) | Individual | ASP | VIE | SEV | 73 | INS | 68 | A | I |  | 0 |  | 0 |  | 2014-11-01 | 2016-05-01 | 2017-06-01 | 2017-06-01 |  |  | 118976 | 0 | 118976 | 73093 | 61.44% | 45883 | 45883 | 4588.3 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Despite some delay in receiving the first payment, which took place in May 2016, the operation of NOU was oning on well especially the enforcement and monitoring of the licensing/quota sytem on import/export of ODS, and HCFC-141b based pre-blended polyol through close collaboration with the Customs. NOU also coordinated and facilitated the implementation of HPMP, ODS Alternative Survey and verification of HCFC consumption as well as the preparation of HPMP Stage II. The NOU also organized the 2016 ozone day celebration, and actively joined the regional and global ozone related meetings e.g. the network meeting, OEWG and the MOP meetings. 2015 Article 7 and CP data were submitted to the Ozone Secretariat and MLFS respectively. Based on this development. the second payment was made to the country in October 2016. Legal arrangements(actual/planned): The SSFA was siigned in October 2015 Initial stages of project implementation(actual/planned): July/Oct 2015. Intermediate goals achieved (actual/planned): Yes, enforcement of the licensing/quota sytem on import/export of ODS, and HCFC-141b based pre-blended polyol; Coordination of the HPMP implementation and stage II preparation; Submission of the A7 data report Project completion and follow up: Not applicable. First disbursement date (actual/planned): May 2016. All funds disbursed (yes/no): No. Any delay?(yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A If Yes, will delay have impact on project completion date (yes/no): N/A Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N/A. | Brief progress report (actual/planned): NOU continues enforcing the licensing and quota system. The third payment was transferred to the country in February 2017. With this, there is only last payment left to be released to the country. UNEP is working closely with the NOU to complete the agreed activities and close the SSFA. |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor project implementation progress and the disbursement rate of approved funds.
ONG | IBRD | Survey of ODS alternatives at the national level | Individual | ASP | VIE | SEV | 75 | TAS | 69 | A | I |  | 0 | 0 | 0 | 0 | 2015-11-01 | 2016-12-01 | 2016-12-31 | 2017-07-01 |  |  | 45000 | 0 | 45000 | 35000 | 77.78% | 10000 | 10000 | 10000 | 4050 | 0 | 3150 | 900 | 900 | Consulting firm on board in 2016. Survey strategy and questionnaires prepared. Regulatory framework assessment and gap analysis completed in May 2016. Survey launch workshop done Jul 16. Survey completed by Sep 16, including the survey by sectors (bottom-up data). First database version of data completed by local consultant Dec 16. Stakeholder workshop on data results held 20 Dec 16. Draft survey report submitted 30 Dec 16. | Revised versions of survey submitted Jan and Feb 17 and discussions held mid-Mar 17 with NOU/PMU and consultant. ODS alternative survey report is under finalization for submission to the 79th ExCom. |  |  | Non-INV | 0
ONG | UNEP | Extension of the institutional strengthening project (phase XI: 7/2017-6/2019) | Individual | ASP | VIE | SEV | 77 | INS | 73 | A | I |  | 0 |  | 0 |  | 2016-12-01 |  | 2019-06-01 | 2019-06-01 |  |  | 152289 | 0 | 152289 | 0 | 0% | 152289 | 0 | 15228.9 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The project was approved at the 77th ExCom Meeting in November 2016. The SSFA was drafted in consultation with the country. Legal arrangements(actual/planned): Not yet. Initial stages of project implementation(actual/planned): Not yet. Intermediate goals achieved (actual/planned): Not yet. Project completion and follow up: Not applicable. First disbursement date (actual/planned): not yet. All funds disbursed (yes/no): _No__ Any delay?(yes/no): No. If Yes, will delay have impact on project completion date (yes/no): No. Any ongoing problems (yes/no): No. If Yes, is any action required by ExCom: N/A | Brief progress report (actual/planned): UNEP is working with the NOU to finalize the SSFA for IS project phase XI.
FIN | UNIDO | Preparation of project in the aerosol sector | Individual | ASP | YEM | ARS | 27 | PRP | 04 | A | I |  | 0 | 0 |  |  | 1999-03-01 | 1999-08-01 | 1999-12-01 |  | 2000-12-01 | 2001-10-01 | 20000 | -2885 | 17115 | 17114.86 | 100% | 0.14 | 0 |  | 2600 | -379 | 2221 | 0 | 0 | FIN
FIN | UNIDO | Phase out of CFC-11, CFC-12 and CFC-114 in the manufacture of aerosols by conversion to hydrocarbon propellant at Arabia Felix Industries Ltd. | Individual | ASP | YEM | ARS | 34 | INV | 08 | A | R | CFC | 96.6 | 96.6 |  |  | 2001-07-01 | 2002-06-01 | 2003-10-01 |  | 2004-05-01 | 2005-12-01 | 366804 | -5910 | 360894 | 360893.99 | 100% | 0.01 | 0 |  | 34676 | -613 | 34063 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase out of CFC-12 in the manufacture of aerosols by conversion to hydrocarbon propellant at Al-Thowra Industrial Complex | Individual | ASP | YEM | ARS | 34 | INV | 10 | A | I | CFC | 82.7 | 82.7 |  |  | 2001-07-01 | 2002-06-01 | 2003-10-01 |  | 2004-04-01 | 2004-09-01 | 179508 | 0 | 179508 | 179507.91 | 100% | 0.09 | 0 |  | 23336 | -33 | 23303 | 0 | 0 | FIN |  |  |  | INV
CLO | UNIDO | Preparation of project in the foam sector | Individual | ASP | YEM | FOA | 27 | PRP | 03 | A | I |  | 0 | 0 |  |  | 1999-03-01 |  | 1999-12-01 |  |  | 2001-03-01 | 20000 | -20000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 2600 | -2600 | 0 | 0 | 0 | CLO
FIN | UNIDO | Preparation for HCFC phase-out investment activities (rigid polyurethane foam component) | Individual | ASP | YEM | FOA | 63 | PRP | 38 | A | I |  | 0 | 0 |  |  | 2011-04-01 | 2013-01-01 | 2012-03-31 |  | 2012-12-01 | 2014-04-01 | 60000 | -48664.5 | 11335.5 | 11335.71 | 100% | -0.21 | 0 |  | 4500 | -3650 | 850 | 0 | 0 | FIN |  |  |  | NON-INV
ONG | UNIDO | Preparation for HCFC phase-out investment activities (stage II) (foam sector) | Individual | ASP | YEM | FOA | 73 | PRP | 46 | A | I |  | 0 | 0 |  |  | 2014-11-01 |  | 2016-11-30 | 2019-12-18 |  |  | 80000 | 0 | 80000 | 0 | 0% | 80000 | 0 | 1 | 5600 | 0 | 0 | 5600 | 0 | No progress possible due to protracted unstable political and security situation in the country. | No progress possible due to protracted unstable political and security situation in the country. |  |  | NON-INV |  | To request the submission of additional status report to the 79th meeting to monitor the resumption of activities.
FIN | Germany | Preparation for phase-out investment project for methyl bromide sector | Individual | ASP | YEM | FUM | 34 | PRP | 09 | A | I |  | 0 |  | 0 |  | 2001-07-01 | 2002-05-01 | 2002-01-01 |  | 2003-12-01 | 2004-04-01 | 44000 | 0 | 44000 | 44000 | 100% | 0 | 0 | 0 | 5720 | 0 | 5720 | 0 | 0 | Project to reduce MB consumtion by 9.1 ODP tonnes approved at 41st ExCom.
FIN | Germany | Technical assistance programme for the phase-out of methyl bromide in agriculture | Individual | ASP | YEM | FUM | 41 | TAS | 21 | A | I | MBR | 9.1 | 17.1 | 0 |  | 2003-12-01 | 2004-05-01 | 2006-12-01 |  | 2008-04-01 | 2009-10-01 | 250000 | 0 | 250000 | 250000 | 100% | 0 | 0 | 0 | 32500 | 0 | 32500 | 0 | 0 | Farmers were trained in the usage of MB alternatives. More field visits to farmers promoting MB alternatives took place. All project activities were successfully completed. The PCR has been prepared.
COM | Germany | Terminal phase-out of methyl bromide (first tranche, part 1) | Multi-Year | ASP | YEM | FUM | 56 | INV | 32 | A | I | MBR | 5.9 | 4.8 | 0 |  | 2008-11-01 | 2008-11-01 | 2014-12-01 |  | 2010-12-01 |  | 109740 | 0 | 109740 | 109740 | 100% | 0 | 0 | 0 | 13896 | 0 | 13896 | 0 | 0 | During 2010 the following activities were conducted: 3 new farmers from Sana'a Governorate received materials to implement the solarization technology on their farms (thermal polyethylene – PE, humidity scale, thermometer). On-site trainings were held at each of the 3 farms, with 10 farmers participating at each one. Bio- fumigation with local radish seeds is still under implementation in Dhamar Governarate, at Al-Khupaji farm. Biofumigation is also recommended for Al-Shamhazi farm located near Atheen village which is one of the coldest areas in Yemen. In cooperation with Al-Reyada'a Women’s Association, a meeting on MB alternatives for decision makers was held in Dhamar Governorate. Fifteen officers from the local council and the Governor Office attended the meeting. A primary survey for Governorate of Abyan was carried out April – May 2010. MB is used for banana and garlic farms to treat soil infestations by nematodes. 2 meetings were held between Alakel Company and NOU to introduce Grafting Technology in Sadah. However, due to the tense security situation in the Sadah area, these activities were delayed until 2011.
COM | Germany | Terminal phase-out of methyl bromide (first tranche, part 2) | Multi-Year | ASP | YEM | FUM | 57 | INV | 33 | A | I | MBR | 0 | 5.4 | 0 |  | 2009-04-01 | 2009-05-01 | 2014-12-01 |  | 2010-12-01 |  | 91710 | 0 | 91710 | 91710 | 100% | 0 | 0 | 0 | 11613 | 0 | 11613 | 0 | 0 | During 2010 the following activities were conducted: 3 new farmers from Sana'a Governorate received materials to implement the solarization technology on their farms (thermal polyethylene – PE, humidity scale, thermometer). On-site trainings were held at each of the 3 farms, with 10 farmers participating at each one. Bio- fumigation with local radish seeds is still under implementation in Dhamar Governarate, at Al-Khupaji farm. Biofumigation is also recommended for Al-Shamhazi farm located near Atheen village which is one of the coldest areas in Yemen. In cooperation with Al-Reyada'a Women’s Association, a meeting on MB alternatives for decision makers was held in Dhamar Governorate. Fifteen officers from the local council and the Governor Office attended the meeting. A primary survey for Governorate of Abyan was carried out April – May 2010. MB is used for banana and garlic farms to treat soil infestations by nematodes. 2 meetings were held between Alakel Company and NOU to introduce Grafting Technology in Sadah. However, due to the tense security situation in the Sadah area, these activities were delayed until 2011.
COM | Germany | Terminal phase-out of methyl bromide (second tranche) | Multi-Year | ASP | YEM | FUM | 62 | INV | 37 | A | I | MBR | 10 | 8.5 | 0 |  | 2010-12-01 | 2011-12-01 | 2012-12-01 |  | 2013-08-01 |  | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 25325 | 0 | 25325 | 0 |  | Remaining funds from 2013 were spent in 2014
COM | Germany | Terminal phase-out of methyl bromide (third tranche) | Multi-Year | ASP | YEM | FUM | 68 | INV | 41 | A | I | MBR | 20 | 11 | 0 |  | 2012-12-01 | 2013-08-01 | 2014-12-01 |  | 2015-02-01 |  | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 25325 | 0 | 25325 | 0 |  | Distribution of the final alternatives materials was finalized in the beginning of February 2015, and all project financial obligations were completed and closed as at 28th February 2015. Commercial production of grafted nurses took place in second half of 2015. | For ensuring sustainability uses of MB substitutes in soil fumigation, ISP will continue monitoring and technically supporting the sector.
FIN | UNEP | Project preparation for a national phase-out management plan | RMP | ASP | YEM | PHA | 50 | PRP | 26 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-04-01 | 2007-11-01 |  | 2009-11-01 | 2010-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0
ONG | UNIDO | National ODS phase-out plan (first tranche) | Multi-Year | ASP | YEM | PHA | 55 | INV | 28 | A | I | CFC | 339.4 | 0 |  |  | 2008-07-01 | 2008-11-01 | 2010-12-31 | 2019-12-18 |  |  | 1137500 | 0 | 1137500 | 1105121.75 | 97.15% | 32378.25 | 27316.37 | 1 | 85313 | 0 | 82884 | 2429 | 2049 | -Uncertain political situation in the country. - No NOU in charge. - As per Dec 77/8 d): tranche funding frozen for the NPP (YEM/PHA/55/INV/28,YEM/PHA/55/INV/31 and YEM/PHA/60/INV/36) and stage I of the HCFC phase-out management plan (HPMP) (YEM/PHA/68/TAS/39 and YEM/PHA/68/TAS/40) | - Uncertain political situation in the country. - No NOU in charge. - - As per Dec 77/8 d): tranche funding frozen for the NPP (YEM/PHA/55/INV/28,YEM/PHA/55/INV/31 and YEM/PHA/60/INV/36) and stage I of the HCFC phase-out management plan (HPMP) (YEM/PHA/68/TAS/39 and YEM/PHA/68/TAS/40) |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | ASP | YEM | PHA | 55 | PRP | 29 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2009-05-01 | 2009-07-31 |  | 2012-12-01 | 2014-04-01 | 70000 | -1156 | 68844 | 68843.64 | 100% | 0.36 | 0 |  | 5250 | -87 | 5163 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | YEM | PHA | 55 | PRP | 30 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-10-01 | 2009-07-01 |  | 2013-12-01 | 2014-11-01 | 125000 | -108600 | 16400 | 16400 | 100% | 0 | 0 |  | 16250 | -14118 | 2132 | 0 | 0
ONG | UNEP | National ODS phase-out plan (first tranche) | Multi-Year | ASP | YEM | PHA | 55 | TAS | 31 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-11-01 | 2010-12-01 | 2017-12-01 |  |  | 315000 | -79053 | 235947 | 235946.71 | 100% | 0.29 | 0 | 0 | 40950 | -10276.89 | 30673.0723 | 0.0377 | 0 | Brief Progress: - There is one remaining payment and obligated procurement that could not be processed since mid of 2015 because of unrest in the country. - Remaining funds transferred to HPMP as per Decision 68/53, respective progress is under the HPMP project. - Decision 77/8 (d) freezes the project on the condition that the funding could be reinstated and the agreements reactivated once conditions in the country had improved and once the Government and relevant implementing agencies had submitted a revised plan of action taking into account the reallocation of the funding tranches of the agreements | Brief Progress: - There is one remaining payment and obligated procurement that could not be processed since mid of 2015 because of unrest in the country. - Remaining funds transferred to HPMP as per Decision 68/53, respective progress is under the HPMP project. - Decision 77/8 (d) freezes the project on the condition that the funding could be reinstated and the agreements reactivated once conditions in the country had improved and once the Government and relevant implementing agencies had submitted a revised plan of action taking into account the reallocation of the funding tranches of the agreements
ONG | UNIDO | National ODS phase-out plan (second tranche) | Multi-Year | ASP | YEM | PHA | 60 | INV | 36 | A | I |  | 268.7 | 0 |  |  | 2010-04-01 | 2010-07-01 | 2011-04-30 | 2019-12-19 |  |  | 233000 | 0 | 233000 | 172731.29 | 74.13% | 60268.71 | 9377.38 | 1 | 17475 | 0 | 12955 | 4520 | 703 | - Uncertain political situation in the country. - No NOU in charge. - As per Dec 77/8 d): tranche funding frozen for the NPP (YEM/PHA/55/INV/28,YEM/PHA/55/INV/31 and YEM/PHA/60/INV/36) and stage I of the HCFC phase-out management plan (HPMP) (YEM/PHA/68/TAS/39 and YEM/PHA/68/TAS/40) | - Uncertain political situation in the country. - No NOU in charge. - - As per Dec 77/8 d): tranche funding frozen for the NPP (YEM/PHA/55/INV/28,YEM/PHA/55/INV/31 and YEM/PHA/60/INV/36) and stage I of the HCFC phase-out management plan (HPMP) (YEM/PHA/68/TAS/39 and YEM/PHA/68/TAS/40)
COM | UNEP | National ODS phase-out plan (second tranche) | Multi-Year | ASP | YEM | PHA | 60 | TAS | 35 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 |  | 2011-04-01 |  | 2014-12-01 |  | 140000 | 0 | 140000 | 0 | 0% | 140000 | 0 | 0 | 18200 | 0 | 0 | 18200 | 0 | Brief Progress: - Project Completed, remaining funds transferred to HPMP as per Decision 68/53, respective progress is under the HPMP project - Decision 77/8 (d) freezes the project on the condition that the funding could be reinstated and the agreements reactivated once conditions in the country had improved and once the Government and relevant implementing agencies had submitted a revised plan of action taking into account the reallocation of the funding tranches of the agreements | Brief Progress: No any returns of balances as the Project Completed, remaining funds transferred to HPMP as per Decision 68/53, respective progress is under the HPMP project - Decision 77/8 (d) freezes the project on the condition that the funding could be reinstated and the agreements reactivated once conditions in the country had improved and once the Government and relevant implementing agencies had submitted a revised plan of action taking into account the reallocation of the funding tranches of the agreements
ONG | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | YEM | PHA | 68 | TAS | 39 | A | I |  | 0 | 0 |  |  | 2012-12-01 | 2014-10-01 | 2014-12-31 | 2019-12-19 |  |  | 410000 | 0 | 410000 | 176906.97 | 43.15% | 233093.03 | 0 | 1 | 28700 | 0 | 12383 | 16317 | 0 | - Uncertain political situation in the country. - No NOU in charge. - As per Dec 77/8 d): tranche funding frozen for the NPP (YEM/PHA/55/INV/28,YEM/PHA/55/INV/31 and YEM/PHA/60/INV/36) and stage I of the HCFC phase-out management plan (HPMP) (YEM/PHA/68/TAS/39 and YEM/PHA/68/TAS/40) | - Uncertain political situation in the country. - No NOU in charge. - - As per Dec 77/8 d): tranche funding frozen for the NPP (YEM/PHA/55/INV/28,YEM/PHA/55/INV/31 and YEM/PHA/60/INV/36) and stage I of the HCFC phase-out management plan (HPMP) (YEM/PHA/68/TAS/39 and YEM/PHA/68/TAS/40) |  |  | INV
ONG | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | YEM | PHA | 68 | TAS | 40 | A | I |  | 11.6 | 0 | 0 | 0 | 2012-12-01 |  | 2015-12-01 | 2017-12-01 |  |  | 215000 | 0 | 215000 | 0 | 0% | 215000 | 0 | 0 | 27950 | 0 | 0 | 27950 | 0 | Brief progress report (actual/planned): - Situation in 2016 remains as in previous year with instability and not NOU/agencies not being able to restart the projects in Yemen due to conflict and security situation - Decision 77/8 (d) freezes the project on the condition that the funding could be reinstated and the agreements reactivated once conditions in the country had improved and once the Government and relevant implementing agencies had submitted a revised plan of action taking into account the reallocation of the funding tranches of the agreements | Brief progress report (actual/planned): - Situation in 2016 remains as in previous year with instability and not NOU/agencies not being able to restart the projects in Yemen due to conflict and security situation - Decision 77/8 (d) freezes the project on the condition that the funding could be reinstated and the agreements reactivated once conditions in the country had improved and once the Government and relevant implementing agencies had submitted a revised plan of action taking into account the reallocation of the funding tranches of the agreements
ONG | UNEP | Preparation of a HCFC phase-out management plan (stage II) | Multi-Year | ASP | YEM | PHA | 73 | PRP | 44 | A | I |  | 0 |  | 0 |  | 2014-11-01 |  | 2016-11-01 | 2017-12-01 |  |  | 50000 | 0 | 50000 | 0 | 0% | 50000 | 0 | 0 | 6500 | 0 | 0 | 6500 | 0 | Brief progress report (actual/planned): - Situation in 2016 remains as in previous year with instability and not NOU/agencies not being able to restart the projects in Yemen due to conflict and security situation - Decision 77/8 (d) freezes the project on the condition that the funding could be reinstated and the agreements reactivated once conditions in the country had improved and once the Government and relevant implementing agencies had submitted a revised plan of action taking into account the reallocation of the funding tranches of the agreements | Brief progress report (actual/planned): - Situation in 2016 remains as in previous year with instability and not NOU/agencies not being able to restart the projects in Yemen due to conflict and security situation - Decision 77/8 (d) freezes the project on the condition that the funding could be reinstated and the agreements reactivated once conditions in the country had improved and once the Government and relevant implementing agencies had submitted a revised plan of action taking into account the reallocation of the funding tranches of the agreements |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor the resumption of the project.
ONG | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | Individual | ASP | YEM | PHA | 73 | PRP | 45 | A | I |  | 0 | 0 |  |  | 2014-11-01 |  | 2016-11-30 | 2019-12-19 |  |  | 20000 | 0 | 20000 | 0 | 0% | 20000 | 0 | 1 | 1400 | 0 | 0 | 1400 | 0 | - Uncertain political situation in the country. - No NOU in charge. - As per Dec 77/8 d): tranche funding frozen for the NPP (YEM/PHA/55/INV/28,YEM/PHA/55/INV/31 and YEM/PHA/60/INV/36) and stage I of the HCFC phase-out management plan (HPMP) (YEM/PHA/68/TAS/39 and YEM/PHA/68/TAS/40) | - Uncertain political situation in the country. - No NOU in charge. - - As per Dec 77/8 d): tranche funding frozen for the NPP (YEM/PHA/55/INV/28,YEM/PHA/55/INV/31 and YEM/PHA/60/INV/36) and stage I of the HCFC phase-out management plan (HPMP) (YEM/PHA/68/TAS/39 and YEM/PHA/68/TAS/40) |  |  | NON-INV |  | To request the submission of additional status report to the 79th meeting to monitor the resumption of activities.
FIN | UNEP | Preparation of a refrigerant management plan | RMP | ASP | YEM | REF | 27 | PRP | 05 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-08-01 | 2000-04-01 |  | 2001-12-01 | 2003-07-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 |  |  |  | 2001-09-01
FIN | UNDP | Preparation of a refrigerant recycling project | Individual | ASP | YEM | REF | 33 | PRP | 06 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2002-04-01 | 2003-07-01 | 15000 | -1934 | 13066 | 13066 | 100% | 0 | 0 | 0 | 1950 | -251.42 | 1698.58 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNIDO | Preparation of two projects in the commercial refrigeration sector | Individual | ASP | YEM | REF | 33 | PRP | 07 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-08-01 | 2002-04-01 |  | 2002-07-01 | 2003-10-01 | 20000 | -3268 | 16732 | 16732.05 | 100% | -0.05 | 0 |  | 2600 | -428 | 2172 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Nagman Co. | Individual | ASP | YEM | REF | 35 | INV | 11 | A | I | CFC | 7.3 | 7.3 |  |  | 2001-12-01 | 2002-04-01 | 2003-07-01 |  | 2003-12-01 | 2004-10-01 | 105641 | -1328 | 104313 | 104313.09 | 100% | -0.09 | 0 |  | 13733 | -194 | 13539 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Styrco | Individual | ASP | YEM | REF | 35 | INV | 12 | A | I | CFC | 6.1 | 6.1 |  |  | 2001-12-01 | 2002-05-01 | 2003-07-01 |  | 2003-12-01 | 2004-10-01 | 90231 | -1456 | 88775 | 88774.93 | 100% | 0.07 | 0 |  | 11730 | -208 | 11522 | 0 | 0 | FIN |  |  |  | INV
CLO | UNIDO | Preparation of a terminal investment project in commercial refrigeration sector | Individual | ASP | YEM | REF | 36 | PRP | 14 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2003-01-01 | 2003-04-01 |  |  | 2003-05-01 | 10000 | -2349 | 7651 | 7651 | 100% | 0 | 0 |  | 1300 | -307 | 993 | 0 | 0 | CLO |  |  |  | INV
FIN | UNDP | Implementation of the RMP: national recovery and recycling programme for refrigerants in the commercial and MAC sectors | RMP-Component | ASP | YEM | REF | 37 | TAS | 15 | A | I | CFC | 220 | 220 | 0 | 0 | 2002-07-01 | 2002-12-01 | 2005-08-01 |  | 2008-12-01 | 2012-06-01 | 1472730 | -36714.02 | 1436015.98 | 1436016 | 100% | -0.02 | 0 | 0 | 172000.3 | -4287.83 | 167712.4678 | 0.0021642 | 0 | Financially completed in 2012. |  | 2002 |  | Investment
FIN | UNEP | Implementation of the RMP: establishment of regulations and legislation | Individual | ASP | YEM | REF | 37 | TAS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-05-01 | 2004-01-01 |  | 2006-12-01 | 2011-06-01 | 25000 | -5000 | 20000 | 20000 | 100% | 0 | 0 |  | 3250 | -650 | 2600 | 0 | 0
FIN | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | ASP | YEM | REF | 37 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2007-10-01 | 2005-08-01 |  | 2010-12-01 | 2014-11-01 | 57750 | -12750 | 45000 | 45000 | 100% | 0 | 0 |  | 7508 | -1657.61 | 5850.39 | 0 | 0
FIN | UNEP | Implementation of the RMP: training programme on good practices in refrigeration | Individual | ASP | YEM | REF | 37 | TRA | 17 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-04-01 | 2005-08-01 |  | 2008-12-01 | 2010-12-01 | 189500 | 0 | 189500 | 189500 | 100% | 0 | 0 |  | 24635 | 0 | 24635 | 0 | 0
FIN | UNEP | Implementation of the RMP: training programme for customs officers | Individual | ASP | YEM | REF | 37 | TRA | 18 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-06-01 | 2004-08-01 |  | 2011-09-01 | 2011-12-01 | 91825 | 0 | 91825 | 91825 | 100% | 0 | 0 |  | 11937 | 0 | 11937 | 0 | 0
FIN | UNIDO | Preparation of a terminal umbrella project in refrigeration (CFC) | Individual | ASP | YEM | REF | 45 | PRP | 23 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-09-01 | 2006-04-01 |  | 2008-04-01 | 2008-09-01 | 30000 | -453 | 29547 | 29547.47 | 100% | -0.47 | 0 |  | 2250 | -34 | 2216 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNEP | Country programme preparation | Individual | ASP | YEM | SEV | 19 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-08-01 |  | 1998-11-01 | 1999-06-01 | 43000 | 0 | 43000 | 43000 | 100% | 0 | 0 |  | 5590 | 0 | 5590 | 0 | 0
FIN | UNEP | Establishment of a National Ozone Unit | Individual | ASP | YEM | SEV | 25 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-02-01 | 2001-06-01 |  | 2001-12-01 | 2003-12-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 | 0 |  | 15600 | 0 | 15600 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project | Individual | ASP | YEM | SEV | 35 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-04-01 | 2004-01-01 |  | 2003-12-01 | 2004-12-01 | 118000 | 0 | 118000 | 118000 | 100% | 0 | 0 |  | 15340 | 0 | 15340 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project: phase III | Individual | ASP | YEM | SEV | 41 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-04-01 | 2005-12-01 |  | 2005-12-01 | 2007-03-01 | 104000 | -391 | 103609 | 103609 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | ASP | YEM | SEV | 47 | INS | 24 | A | I | CFC | 8.6 | 8.6 | 0 | 0 | 2005-11-01 | 2006-05-01 | 2007-12-01 |  | 2007-12-01 | 2008-12-01 | 104000 | 0 | 104000 | 104000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV-supplementary request) | Individual | ASP | YEM | SEV | 48 | INS | 25 | A | I | CFC | 5.4 | 0 | 0 | 0 | 2006-04-01 | 2006-06-01 | 2007-04-01 |  | 2007-04-01 | 2007-12-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | ASP | YEM | SEV | 53 | INS | 27 | A | I | CFC | 14 | 14 | 0 | 0 | 2007-11-01 | 2008-08-01 | 2009-11-01 |  | 2009-11-01 | 2010-12-01 | 170000 | -392 | 169608 | 169608 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VI) | Individual | ASP | YEM | SEV | 59 | INS | 34 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-12-01 | 2011-11-01 |  | 2012-12-01 | 2013-12-01 | 92083 | 77916 | 169999 | 169999 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Extension of the institutional strengthening project (phase VII: 1/2013-12/2014) | Individual | ASP | YEM | SEV | 68 | INS | 42 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2014-01-01 | 2014-12-01 |  | 2014-12-01 |  | 169999 | 0 | 169999 | 110251.08 | 64.85% | 59747.92 | 59747.92 | 0 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): Project completed, but not financially closed. UNEP disbursed final payment 2 times and it got returned. Country has informed that NOU is still operational, once official communication is received, UNEP will process repayment of last installment. Legal arrangements (actual/planned): Agreement completed, but last payment returned to UNEP. Initial stages of project implementation (actual/planned): Implementation complete. Intermediate goals achieved (actual/planned): n/a Project completion and follow up: Project completed, but not financially closed. First disbursement date (actual/planned): First payment processed in Jan-2014. All funds disbursed (yes/no): No. Project ongoing & delayed Any delay? (yes/no): No. If Yes, reasons for delay & action plan to resolve: Upon official confirmation, UNEP to process the last payment once again. If Yes, will delay have impact on project completion date (yes/no): No. Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: No. | Awaiting instructions from country for reimbursement of last payment. UNEP cannot return funds as UNEP owes country last payment which was returned from intermediary banks due to security issue in YEM.
ONG | UNEP | Extension of the institutional strengthening project (phase VIII: 1/2015-12/2016) | Individual | ASP | YEM | SEV | 73 | INS | 43 | A | I |  | 0 |  | 0 |  | 2014-11-01 |  | 2016-12-01 | 2017-12-01 |  |  | 169999 | 0 | 169999 | 0 | 0% | 169999 | 5677.14 | 0 | 0 | 0 | 0 | 0 | 0 | No progress due to political and structural situation. Awaiting official communication. Country was in non-compliance with data reporting | No progress due to political and structural situation. Awaiting official communication. Country was in non-compliance with data reporting
FIN | UNIDO | Training and awareness workshop in the process agents (TCA) sector | Individual | ASP | YEM | SOL | 45 | TAS | 22 | A | I | TCA | 0.2 | 0.2 |  |  | 2005-04-01 | 2005-09-01 | 2006-04-01 |  | 2006-12-01 | 2007-09-01 | 35000 | -164 | 34836 | 34836.35 | 100% | -0.35 | 0 |  | 3150 | -15 | 3135 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of one investment project in the flexible foam sector | Individual | EUR | YUG | FOA | 34 | PRP | 10 | A | I |  | 0 | 0 |  |  | 2001-07-01 | 2001-10-01 | 2002-08-01 |  | 2004-03-01 | 2004-04-01 | 15000 | -15 | 14985 | 14984.86 | 100% | 0.14 | 0 |  | 1950 | -5 | 1945 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of one investment project in the rigid foam sector | Individual | EUR | YUG | FOA | 34 | PRP | 11 | A | I |  | 0 | 0 |  |  | 2001-07-01 | 2001-10-01 | 2002-08-01 |  | 2004-03-01 | 2004-09-01 | 15000 | -201 | 14799 | 14799.45 | 100% | -0.45 | 0 |  | 1950 | -29 | 1921 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Phase out of CFC-11 by conversion to n-pentane technology in the production of continuous rigid polyurethane foam insulating panels at Prva Iskra-Fim Co. | Individual | EUR | YUG | FOA | 35 | INV | 14 | A | I | CFC | 75 | 75 |  |  | 2001-12-01 | 2003-08-01 | 2004-07-01 |  | 2006-12-01 | 2011-05-01 | 475728 | -4430 | 471298 | 471297.59 | 100% | 0.41 | 0 |  | 61845 | -576 | 61269 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to methylene chloride in the production of flexible slab stock foam at Prva Iskra-Poliuretani | Individual | EUR | YUG | FOA | 35 | INV | 15 | A | I | CFC | 34.4 | 34.4 |  |  | 2001-12-01 | 2002-03-01 | 2004-01-01 |  | 2004-02-01 | 2004-12-01 | 100240 | -169 | 100071 | 100071.22 | 100% | -0.22 | 0 |  | 13031 | -42 | 12989 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project preparation in the fumigants sector (methyl bromide) | Individual | EUR | YUG | FUM | 45 | PRP | 26 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2006-09-01 | 2006-04-01 |  | 2009-09-01 | 2009-09-01 | 25000 | -9189 | 15811 | 15811.39 | 100% | -0.39 | 0 |  | 1875 | -689 | 1186 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Project preparation in the halon sector | Individual | EUR | YUG | HAL | 33 | PRP | 09 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-06-01 | 2002-04-01 |  | 2002-04-01 | 2003-05-01 | 20000 | -82 | 19918 | 19918.09 | 100% | -0.09 | 0 |  | 2600 | -15 | 2585 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Halon bank management programme | Individual | EUR | YUG | HAL | 35 | TAS | 16 | A | I | HAL | 370 | 370 |  |  | 2001-12-01 | 2002-03-01 | 2004-01-01 |  | 2004-12-01 | 2005-12-01 | 249700 | -4216 | 245484 | 245483.51 | 100% | 0.49 | 0 |  | 32461 | -599 | 31862 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Assistance to prepare a national CFC phase-out plan (manufacturing sector) | Individual | EUR | YUG | PHA | 40 | PRP | 20 | A | I |  | 0 | 0 |  |  | 2003-07-01 | 2003-12-01 | 2004-07-01 |  | 2005-04-01 | 2005-09-01 | 40000 | -7481 | 32519 | 32518.95 | 100% | 0.05 | 0 |  | 3000 | -565 | 2435 | 0 | 0 | FIN
FIN | Sweden | Assistance to prepare a national CFC phase-out plan (servicing sector) | Individual | EUR | YUG | PHA | 40 | PRP | 21 | A | I |  | 0 |  | 0 |  | 2003-07-01 | 2003-12-01 | 2004-07-01 |  | 2004-07-01 | 2004-11-01 | 65000 | 0 | 65000 | 65000 | 100% | 0 |  |  | 8450 | 0 | 8450 | 0 | 0 | The assistance to Serbia and Montenegro (SEM) to develop a NCPP for the servicing sector was completed in a joint undertaking with UNIDO during the spring 2004 and the plan was approved in July 2004. |  | 2003
TRF | Sweden | National CFC phase-out plan (first tranche) | Multi-Year | EUR | YUG | PHA | 43 | TAS | 22 | A | I |  | 0 |  | 0 |  | 2004-07-01 | 2005-11-01 | 2005-03-01 |  |  | 2010-06-01 | 148000 | -128678 | 19322 | 19322 | 100% | 0 | 0 | 0 | 19240 | -16728 | 2512 | 0 | 0 | The NCPP implementation was started with UNIDO as Lead Agency and Sweden as Cooperating Agency. Since the Swedish decision in 2006 to cease the bilateral window, UNIDO was the the sole implementing agency with Sweden supporting only through the already contracted Swedish consultants. With ExCom decision 60/3 in April 2010, however the full project was handed over from Sweden to UNIDO and the contract with the international consultant was terminated. The project struggled with serious delays from the start, partly due to the difficulties in making the PMU operational and frequent changes of staff at the NOU. The split with Montenegro also slowed down activities for a while. A new NOU manager was officially assigned as of Dec 2008 and a PMU manager was finally contracted during the autumn 2009. During early spring 2010, two additional experts were contracted making the PMU fully operational. As an immediate result of these recruitments, by April 2010 substantial progress had been made on a number of activities: Seven out of eight training sessions for customs had been undertaken; the new ODS regulation ("Official Gazette RS, No 36/09") was adopted which describes how the reclamation scheme should function (incl. financial structure, roles and responsibilities etc). The new regulation also had several important elements pertaining to the sustainable phase-out of ODS, such as how to handle re quest for Issuance of Export License (for importers/exporters) and request for issuance of license for import of controlled substances and equipment in emergency cases (for importers/exporters). Serbia did in April 2010 not yet have a Code of Good Practice in place, however the new Decree suggested that good practice in refrigeration should be followed, meaning there is support for this work once it has been developed. During the spring the NOU also started to work on an F-gas regulation. The reclamation scheme still remained to be established but an important milestone for getting that in place was met through the adoption of the new ODS regulation. Other important activities that still remained to be undertaken in April 2010 was the training of trainers and technicians. Three training centers were selected already in November 2009 but the contractual procedures was in April still not in place. During the autumn 2009, Sweden decided to put a final close to all its bilateral activities under the Montreal Protocol and with ExCom decision 60/3 (April 2010) the remaining Swedish responsibilities were officially transferred to UNIDO. The contract with the International Consultant was terminated and the remaining balance transferred to UNIDO via the MLF. This progress report constitutes the final progress report from Sweden. Project Completion Report (PCR) for the Swedish contribution was submitted to MLF in Dec 2010. |  | 2004 | 2006-12-01
FIN | UNIDO | National CFC phase-out plan (first tranche) | Multi-Year | EUR | YUG | PHA | 43 | TAS | 23 | A | I | CFC | 2 | 2 |  |  | 2004-07-01 | 2004-08-01 | 2005-03-01 |  | 2009-12-01 | 2013-10-01 | 474700 | -34974 | 439726 | 439725.51 | 100% | 0.49 | 0 |  | 35603 | -2624 | 32979 | 0 | 0 | FIN |  |  | 2006-07-01 | INV
FIN | UNIDO | National CFC phase-out plan (second tranche) | Multi-Year | EUR | YUG | PHA | 47 | INV | 28 | A | I | cFC | 18 | 18 |  |  | 2005-11-01 | 2006-10-01 | 2006-12-01 |  | 2013-12-01 | 2014-08-01 | 759000 | -623749 | 135251 | 135250.61 | 100% | 0.39 | 0 |  | 56925 | -46781 | 10144 | 0 | 0 | FIN |  |  |  | INV
TRF | Sweden | National CFC phase-out plan (second tranche) | Multi-Year | EUR | YUG | PHA | 47 | TAS | 29 | A | I |  | 0 |  | 0 |  | 2005-11-01 |  | 2006-12-01 |  |  | 2006-11-01 | 134000 | -134000 | 0 | 0 |  | 0 | 0 | 0 | 17420 | -17420 | 0 | 0 | 0 | This activity was transferred to UNIDO in 2006. |  | 2005
FIN | UNIDO | National CFC phase-out plan (third tranche) | Multi-Year | EUR | YUG | PHA | 50 | INV | 30 | A | I | CFC | 124 | 124 |  |  | 2006-11-01 | 2007-05-01 | 2007-11-01 |  | 2013-12-01 | 2014-04-01 | 1033344 | -12 | 1033332 | 1033331.99 | 100% | 0.01 | 0 |  | 77501 | -1 | 77500 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | National CFC phase-out plan (third tranche, transferred from Sweden) | Multi-Year | EUR | YUG | PHA | 51 | INV | 31 | A | I |  | 0 | 0 |  |  | 2007-03-01 | 2009-12-01 | 2008-03-01 |  | 2013-12-01 | 2014-04-01 | 222000 | -23917 | 198083 | 198083.19 | 100% | -0.19 | 0 |  | 16650 | -1794 | 14856 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | EUR | YUG | PHA | 55 | PRP | 32 | A | I |  | 0 | 0 |  |  | 2008-07-01 | 2008-12-01 | 2009-07-31 |  | 2011-07-01 | 2012-12-01 | 150000 | -955 | 149045 | 149044.87 | 100% | 0.13 | 0 |  | 11250 | -72 | 11178 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | National CFC phase-out plan (fourth and fifth tranches) | Multi-Year | EUR | YUG | PHA | 60 | INV | 36 | A | I |  | 268 | 268 |  |  | 2010-04-01 | 2010-12-01 | 2011-04-30 |  | 2014-06-01 | 2014-09-01 | 193500 | -145499 | 48001 | 48001.21 | 100% | -0.21 | 0 |  | 14513 | -10912 | 3600 | 1 | 0 | FIN
FIN | UNIDO | National CFC phase-out plan (first tranche, transferred from Sweden) | Multi-Year | EUR | YUG | PHA | 60 | TAS | 35 | A | I |  | 0 | 0 |  |  | 2010-04-01 | 2010-12-01 | 2011-04-01 |  | 2013-12-01 | 2013-12-01 | 40678 | -121 | 40557 | 40556.58 | 100% | 0.42 | 0 |  | 3051 | -9 | 3042 | 0 | 0 | FIN
COM | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | EUR | YUG | PHA | 62 | INV | 38 | A | I | HCFC | 2.3 | 2.3 |  |  | 2010-12-01 | 2010-12-01 | 2012-12-31 |  | 2016-12-01 |  | 360130 | 0 | 360130 | 353844.01 | 98.25% | 6285.99 | 0 | 1 | 27010 | 0 | 26538 | 472 | 0 | Training activities scheduled under tranche one were completed by end of 2016. Training programme will continue under tranche 2. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No Project completed as planned. | Financial closure is ongoing. Activities continuing with the second tranche. |  |  | INV
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | EUR | YUG | PHA | 62 | TAS | 39 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2012-02-01 | 2012-12-01 |  | 2014-12-01 | 2016-12-01 | 26000 | -970 | 25030 | 25030 | 100% | 0 | 0 | 0 | 3380 | -126.1 | 3253.9 | 0 | 0 | Project financially completed. | Project financially completed.
ONG | UNIDO | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | EUR | YUG | PHA | 71 | INV | 41 | A | I | HCFC | 2.7 | 0.12 |  |  | 2013-12-01 | 2016-09-01 | 2016-12-31 | 2018-12-01 |  |  | 444130 | 0 | 444130 | 77306.82 | 17.41% | 366823.18 | 186163.8 | 150000 | 33310 | 0 | 5798 | 27512 | 13962.285 | New legislation on certification scheme for servicing sector came into force in March 2016. Upgrade of certification curricula was achieved. Training programme following new certification scheme started in September 2016 and will continue in 2017. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: Yes, completion date is estimated at Dec 18. Any action required by Executive Committee? No | Local contractual arrangements for continuing execution of technicians certifications were released in the first quarter of 2017. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | INV
ONG | UNIDO | Verification report for stage I of HCFC phase-out management plan | Individual | EUR | YUG | PHA | 71 | TAS | 42 | A | I |  | 0 | 0 |  |  | 2013-12-01 | 2015-11-01 | 2016-11-30 | 2017-12-01 |  |  | 30000 | 0 | 30000 | 2173.01 | 7.243% | 27826.99 | 0 | 27000 | 2700 | 0 | 196 | 2504 | 0 | Verification report was elaborated in view of submission of tranche III of HPMP in 2017. Was there any delay during the reporting year? No Any impact on project completion date: Yes, in order to combine this verification report with the one for 2016 and 2017 and utilize the available funds. Any action required by Executive Committee? No | The available remaining budget will be used to compile verification report for the year 2016 and 2017. |  |  | NON-INV
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | EUR | YUG | PHA | 71 | TAS | 43 | A | I |  | 0.2 |  | 0 |  | 2013-12-01 | 2015-11-01 | 2016-12-01 | 2017-06-01 |  |  | 27500 | 0 | 27500 | 1919.57 | 6.98% | 25580.43 | 23280.77 | 2558.043 | 3575 | 0 | 249.5441 | 3325.4559 | 3026.5001 | Brief progress report (actual/planned): A the technology roundtable on ozone- and climate-friendly technologies and exhibition booth was jointly organized by the Ministry of Agriculture and Environmental Protection of Serbia, the Serbian HVAC&R Society and UN Environment as central part of the 47th International Congress of the Serbian HVAC&R Association KGH in Belgrade, 30 November -2 December 2016. The ECA network hold its thematic meeting in parallel to the congress allowing the participating ozone officers and RAC experts to attend the technology roundtable and to visit the exhibition. The training of customs officers and environment inspectors has been re-scheduled for the first half of 2017. Legal arrangements (actual/planned): UN2UN agency agreement with UNDP Serbia to provide logistical support for the remaining HPMP activities has been signed in July 2016. Ownership for the HPMP activities is with the Ministry of Agriculture and Environmental Protection of Serbia. First mission (actual/planned): Yes - UNEP staff attended the 46th KGH congress in Belgrade, 2-4 December 2015 and the 47th KGH congress in Belgrade, 30 November -2 December 2016. TOR completed (actual/planned): N.a. First disbursement date (actual/planned): November 2015 All funds disbursed (yes/no): No Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: Ministry of Agriculture and Environmental Protection of Serbia decided to re-schedule the training of customs officers and environment inspectors for the first half of 2017. If Yes, will delay have impact on project completion date (yes/no): Yes Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N.a. | Brief progress report (actual/planned): The training of environmental inspectors and customs officers has been scheduled for beginning of June 2017. Serbia HPMP stage I tranche 3 will be submitted to ExCom 79 in July 2017. Legal arrangements (actual/planned): UN2UN agency agreement with UNDP Serbia to provide logistical support for the remaining HPMP activities has been signed in July 2016. Ownership for the HPMP activities is with the Ministry of Agriculture and Environmental Protection of Serbia. First mission (actual/planned): Yes - UNEP staff attended the 46th KGH congress in Belgrade, 2-4 December 2015 and the 47th KGH congress in Belgrade, 30 November -2 December 2016. TOR completed (actual/planned): N.a. First disbursement date (actual/planned): November 2015 All funds disbursed (yes/no): No Any delay? (yes/no): Yes If Yes, reasons for delay & action plan to resolve: Ministry of Agriculture and Environmental Protection of Serbia decided to re-schedule the training of customs officers and environment inspectors for the first half of 2017. If Yes, will delay have impact on project completion date (yes/no): Yes Any ongoing problems (yes/no): No If Yes, is any action required by ExCom: N.a. |  |  |  |  | To request the submission of additional status report to the 79th meeting to monitor the completion of training for customs officers and environmental inspectors.
FIN | UNIDO | Preparation of an investment project in the refrigeration sector for phasing out ODS at Obod | Individual | EUR | YUG | REF | 23 | PRP | 04 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-07-01 | 1998-03-01 |  | 1999-12-01 | 2000-07-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | -1 | 1299 | 0 | 0 | FIN
FIN | UNIDO | Preparation of a refrigerant management plan | Individual | EUR | YUG | REF | 24 | PRP | 06 | A | I |  | 0 | 0 |  |  | 1998-03-01 | 1998-06-01 | 1999-04-01 |  | 1998-06-01 | 2000-03-31 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | FIN
FIN | UNIDO | Preparation of two projects in the commercial refrigeration sector | Individual | EUR | YUG | REF | 33 | PRP | 10 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2001-06-01 | 2002-04-01 |  | 2001-11-01 | 2002-12-01 | 10000 | -2325 | 7675 | 7674.59 | 99.99% | 0.41 | 0 |  | 1300 | -304 | 996 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment at seven enterprises (Jugostroj, Frigozika, Prva Petoletka, EIAD, BS Inzenjering, Soko and Alfa Klima) | Individual | EUR | YUG | REF | 34 | INV | 12 | A | I | CFC | 59.6 | 59.6 |  |  | 2001-07-01 | 2001-11-01 | 2004-02-01 |  | 2003-12-01 | 2005-09-01 | 755162 | -19150 | 736012 | 736012.22 | 100% | -0.22 | 0 |  | 93068 | -2235 | 90833 | 0 | 0 | FIN |  |  |  | INV
FIN | Italy | Replacement of CFC-11 with cyclopentane foam blowing agent and CFC-12 with HFC-134a refrigerant in the manufacture of domestic refrigerators and freezers at Obod Elektroindustria | Individual | EUR | YUG | REF | 34 | INV | 13 | A | I | CFC | 94.9 | 94.9 | 0 |  | 2001-07-01 | 2002-09-01 | 2003-10-01 |  | 2007-04-01 | 2008-12-01 | 1683135 | -91120 | 1592015 | 1592015 | 100% | 0 | 0 | 0 | 180348 | -10023.45 | 170325 | -0.45 | 0 | FIN |  | 2001 |  | Investment
FIN | UNIDO | Preparation of an umbrella investment project in the commercial refrigeration sector | Individual | EUR | YUG | REF | 36 | PRP | 17 | A | I |  | 0 | 0 |  |  | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2003-07-01 | 2004-12-01 | 20000 | -119 | 19881 | 19881.28 | 100% | -0.28 | 0 |  | 2600 | -19 | 2581 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Umbrella refrigeration project 2, replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment at three enterprises | Individual | EUR | YUG | REF | 37 | INV | 18 | A | I | CFC | 10.9 | 10.9 |  |  | 2002-07-01 | 2003-04-01 | 2005-01-01 |  | 2004-10-01 | 2005-12-01 | 150109 | -1869 | 148240 | 148239.7 | 100% | 0.3 | 0 |  | 19514 | -273 | 19241 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Conversion of CFC-12 to HFC-134a in the manufacture of open compressors at Prva Petoletka - Kocna Tehnika Co. | Individual | EUR | YUG | REF | 38 | INV | 19 | A | I | CFC | 2 | 2 |  |  | 2002-11-01 | 2003-06-01 | 2005-06-01 |  | 2006-06-01 | 2007-09-01 | 223412 | -44 | 223368 | 223367.9 | 100% | 0.1 | 0 |  | 29044 | -6 | 29038 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Preparation for HCFC phase-out investment activities (refrigeration air-conditioning manufacturing sector) | Individual | EUR | YUG | REF | 61 | PRP | 37 | A | I |  | 0 | 0 |  |  | 2010-07-01 | 2010-11-01 | 2011-07-31 |  | 2011-07-01 | 2011-12-01 | 60000 | -388 | 59612 | 59611.83 | 100% | 0.17 | 0 |  | 4500 | -29 | 4471 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | IBRD | Country programme preparation |  | EUR | YUG | SEV | 04 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 20302 | -14877 | 5425 | 5425 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
CLO | IBRD | Preparation of investment projects (1991) |  | EUR | YUG | SEV | 04 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1992-06-01 |  |  | 1992-06-01 | 21432 | -21432 | 0 | 0 | #DIV/0! | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNIDO | Country Programme preparation | Individual | EUR | YUG | SEV | 21 | CPG | 01 | A | I |  | 0 | 0 |  |  | 1997-02-01 | 1997-06-01 | 1998-02-01 |  | 1998-08-01 | 1999-09-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0 | FIN
FIN | UNIDO | Creation of Ozone Secretariat | Individual | EUR | YUG | SEV | 25 | INS | 07 | N | I |  | 0 | 0 |  |  | 1998-07-01 | 1998-12-01 | 2001-07-01 |  | 2004-10-01 | 2005-09-01 | 151500 | 0 | 151500 | 151500.04 | 100% | -0.04 | 0 |  | 19695 | -5 | 19690 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Extension of institutional strengthening project (phase II) | Individual | EUR | YUG | SEV | 44 | INS | 25 | N | I |  | 0 | 0 |  |  | 2004-12-01 | 2006-07-01 | 2006-12-01 |  | 2009-12-01 | 2011-12-01 | 131300 | -7175 | 124125 | 124124.73 | 100% | 0.27 | 0 |  | 9848 | -539 | 9309 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Extension of institutional strengthening project (phase III) | Individual | EUR | YUG | SEV | 59 | INS | 34 | N | I |  | 0 | 0 |  |  | 2009-11-01 | 2010-07-01 | 2011-11-01 |  | 2011-11-01 | 2015-09-01 | 71121 | 48817 | 119938 | 119937.54 | 100% | 0.46 | 0 |  | 5334 | 3661 | 8995 | 0 | 0 | FIN |  |  |  | NON-INV
COM | UNIDO | Extension of institutional strengthening project (phase IV: 12/2011-11/2013) | Individual | EUR | YUG | SEV | 65 | INS | 40 | N | I |  | 0 | 0 |  |  | 2011-11-01 | 2013-01-01 | 2013-11-30 |  | 2015-12-01 |  | 131300 | 0 | 131300 | 131199.73 | 99.92% | 100.27 | 0 | 1 | 9848 | 0 | 9840 | 8 | 0 | The project was operationally completed. |  |  |  | NON-INV
ONG | UNIDO | Extension of institutional strengthening project (phase V: 12/2013-11/2015) | Individual | EUR | YUG | SEV | 71 | INS | 44 | N | I |  | 0 | 0 |  |  | 2013-12-01 | 2014-06-01 | 2015-11-30 | 2017-12-01 |  |  | 131300 | 0 | 131300 | 36985.13 | 28.17% | 94314.87 | 8845.01 | 80000 | 9191 | 0 | 2589 | 6602 | 619.1507 | NOU is partially staffed due to administrative restructuring in 2016. Work has been progressing without delay by involvement of short-term technical consultants. Awareness activities were scheduled and organized in line with the project document Office equipment has been delivered in 2016. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: Yes, completion date is estimated at Dec 17. Any action required by Executive Committee? No | Work plan for the year 2017 activities was agreed upon mission of NOU to UNIDO HQ. Terminal report and request for IS extension will be addressed to the 80th ExCom Meeting |  |  | NON-INV
COM | UNIDO | Survey of ODS alternatives at the national level | Individual | EUR | YUG | SEV | 74 | TAS | 45 | A | I |  | 0 | 0 |  |  | 2015-05-01 | 2016-05-01 | 2016-05-31 |  | 2016-12-01 |  | 70000 | 0 | 70000 | 69317.34 | 99.02% | 682.66 | 0 | 1 | 6300 | 0 | 0 | 6300 | 0 | - After recruitment of international expert and creation of national team of experts, surveying activities progressed according to established plan. - First draft survey completed in December 2016 Milestones achieved: Milestone 1: First mission/Working arrangements agreed - Yes Milestone 2: ToR for HFC survey completed - Yes Milestone 3: Local institutions identified - Yes Milestone 4: Experts recruited - Yes Milestone 5: HCFC survey completed - Yes Milestone 6: All technical input completed - Yes Milestone 7: Draft document completed - Yes, see above Actions towards next goals: Survey completed in December 2016. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | - Works are finalized; report submitted as scheduled. Balance will be returned to the 79th Meeting of the ExCom. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No |  |  | NON-INV
FIN | UNIDO | Preparation of an investment project in the solvent sector for phasing out ODS at Hemofarm | Individual | EUR | YUG | SOL | 23 | PRP | 05 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-09-01 | 1998-03-01 |  | 2000-02-01 | 2001-07-01 | 10000 | -2587 | 7413 | 7413.15 | 100% | -0.15 | 0 |  | 1300 | -338 | 962 | 0 | 0 | FIN
FIN | UNIDO | Replacement of CFC-113 as solvent for dyaliser cleaning by water and steam at Hemomed Ltd. | Individual | EUR | YUG | SOL | 26 | INV | 08 | A | R | CFC | 54.6 | 54.6 |  |  | 1998-11-01 | 1999-02-01 | 1999-06-01 |  | 1998-12-01 | 1999-09-01 | 608729 | 0 | 608729 | 608729 | 100% | 0 | 0 |  | 76960 | 0 | 76960 | 0 | 0 | FIN
FIN | UNIDO | Project preparation for the terminal phase-out in the solvent sector (CTC) | Individual | EUR | YUG | SOL | 45 | PRP | 27 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2006-11-01 | 2006-04-01 |  | 2008-12-01 | 2009-06-01 | 15000 | -1991 | 13009 | 13009.15 | 100% | -0.15 | 0 |  | 1125 | -149 | 976 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | Italy | Terminal CTC phase-out project | Individual | EUR | YUG | SOL | 56 | INV | 33 | A | I | CTC | 2.6 | 2.6 | 0 |  | 2008-11-01 | 2009-04-01 | 2009-11-01 |  | 2010-06-01 | 2011-12-01 | 49324 | -338 | 48986 | 48986 | 100% | 0 | 0 | 0 | 6412 | -43.82 | 6368 | 0.18 | 0 | FIN |  | 2008 |  | Investment
CLO | UNIDO | Preparation of a demonstration project (tobacco, flowers) | Individual | AFR | ZAM | FUM | 27 | PRP | 09 | A | I |  | 0 | 0 |  |  | 1999-03-01 |  | 1999-12-01 |  |  | 2001-03-01 | 30000 | -30000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 3900 | -3900 | 0 | 0 | 0 | CLO
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organizations in methyl bromide communication | Individual | AFR | ZAM | FUM | 30 | TAS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9259 | 15741 | 15741 | 100% | 0 | 0 |  | 3250 | -1203.67 | 2046.33 | 0 | 0
FIN | UNIDO | Project preparation in the fumigants sector (soil fumigation) | Individual | AFR | ZAM | FUM | 54 | PRP | 20 | A | I |  | 0 | 0 |  |  | 2008-04-01 | 2008-09-01 | 2009-03-31 |  | 2008-12-01 | 2011-09-01 | 35000 | -9714 | 25286 | 25285.83 | 100% | 0.17 | 0 |  | 2625 | -729 | 1896 | 0 | 0 | FIN |  |  |  | NON-INV
COM | UNIDO | Technical assistance for the total phase out of methyl bromide in tobacco, cut flowers, horticulture and post harvest uses | Individual | AFR | ZAM | FUM | 56 | INV | 21 | A | I | MBR | 7.4 | 7.4 |  |  | 2008-11-01 | 2009-12-01 | 2011-11-30 |  | 2016-12-01 |  | 289548 | 0 | 289548 | 259157.5 | 89.5% | 30390.5 | 14202.12 | 14202.12 | 21716 | 0 | 19437 | 2279 | 1065 | Project closed on 31 December 2016, as per ExCom Decision. |  |  |  | INV |  | 12 months delays
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | ZAM | PHA | 50 | PRP | 17 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-03-01 | 2007-11-01 |  | 2007-12-01 | 2013-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0
FIN | UNDP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | ZAM | PHA | 53 | INV | 19 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 | 2009-10-01 | 2009-11-01 |  | 2011-12-01 | 2013-02-01 | 109000 | -30489.76 | 78510.24 | 78510 | 100% | 0.24 | 0 | 0 | 9810 | -2744.08 | 7065.9 | 0.02 | 0 | Financially completed in 2013. | Completed in 2011. | 2007 |  | Investment
FIN | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | ZAM | PHA | 53 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-03-01 |  | 2009-03-01 | 2010-12-01 | 94000 | 0 | 94000 | 94000 | 100% | 0 | 0 |  | 12220 | 0 | 12220 | 0 | 0
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | ZAM | PHA | 56 | PRP | 22 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-02-01 | 2009-11-01 |  | 2013-04-01 | 2014-04-01 | 85000 | -5000 | 80000 | 80000 | 100% | 0 | 0 |  | 11050 | -650 | 10400 | 0 | 0
FIN | UNEP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | ZAM | PHA | 57 | TAS | 23 | A | I | CFC-12 | 4.1 | 4.1 | 0 | 0 | 2009-04-01 | 2009-09-01 | 2010-03-01 |  | 2012-03-01 | 2013-03-01 | 42000 | -5000 | 37000 | 37000 | 100% | 0 | 0 |  | 5460 | -650 | 4810 | 0 | 0
FIN | UNEP | TPMP verification | Individual | AFR | ZAM | PHA | 57 | TAS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-09-01 | 2010-03-01 |  | 2013-04-01 | 2014-07-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 |  |  |  | 2011-12-01
COM | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | ZAM | PHA | 64 | INV | 26 | A | I | HCFC | 0.4 | 0.4 |  |  | 2011-07-01 | 2013-02-01 | 2016-07-31 |  | 2015-12-01 |  | 70000 | 0 | 70000 | 69224.89 | 98.89% | 775.11 | 0 | 1 | 6300 | 0 | 6230 | 70 | 0 | The project was operationally completed. |  |  |  | INV
COM | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | ZAM | PHA | 64 | TAS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-06-01 | 2013-07-01 |  | 2013-07-01 |  | 40000 | -1365 | 38635 | 25635 | 66.35% | 13000 | 13000 | 2600 | 5200 | -177.45 | 3332.55 | 1690 | 1690
ONG | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | AFR | ZAM | PHA | 71 | TAS | 28 | A | I |  | 0.3 |  | 0 |  | 2013-12-01 | 2016-04-01 | 2016-12-01 | 2018-01-01 |  |  | 40000 | 0 | 40000 | 25.72 | 0.0643% | 39974.28 | 39974.28 | 3997.428 | 5200 | 0 | 3.3436 | 5196.6564 | 5196.6564 | Brief progress report (actual/planned): The NOU conducted two training workshops for 30 custom officers to enhance capacity of the law enforcement officers in monitoring illegal trade. The NOU conducted training for 60 refrigerant technicians. The NOU developed and updated database of all importers of refrigerants and refrigeration equipment. The NOU procured equipment and distributed to RAC Association for Refrigerant testing. The NOU conducted monitoring of the HCFC quotas and illegal importation of ODSs. Legal arrangements (actual/planned): The SSFA was drafted and signed by UNEP and the Government Zambia in January 2016.___ First mission (actual/planned): No___ TOR completed(actual/planned):N/A ___ First disbursement date (actual/planned): First disbursement was made in April 2016___ All funds disbursed (yes/no): No___ Any delay? (yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): N/A___ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: N/A___ | Brief progress report (actual/planned): The NOU registered all importers of HCFCs and organized one stakeholders meeting in Feb 2017 to coordinate and allocate licenses and quotas. The NOU continues to monitor imports and trade of ODS and ODS related equipment.
ONG | UNIDO | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | AFR | ZAM | PHA | 77 | INV | 33 | A | I | HCFC | 0.4 | 0 |  |  | 2016-11-01 |  | 2019-12-31 | 2019-12-31 |  |  | 70000 | 0 | 70000 | 0 | 0% | 70000 | 0 | 3500 | 6300 | 0 | 0 | 6300 | 0 | Approved on the understanding that if Zambia were to decide to proceed with retrofits and associated servicing to flammable and toxic refrigerants in refrigeration and air-conditioning equipment originally designed for non-flammable substances, it would do so assuming all associated responsibilities and risks and only in accordance with the relevant standards and protocols. | - UNIDO will initiate a dialogue with the NOU on the best way to ensure an efficient identification of country's needs for tranche 3. Actions towards next goals: To continue activities implemented under the first and second tranches of the HPMP. Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No
ONG | UNEP | HCFC phase-out management plan (stage I, third tranche) | Multi-year | AFR | ZAM | PHA | 77 | TAS | 32 | A | I |  | 0 |  | 0 |  | 2016-12-01 |  | 2018-12-01 | 2018-12-01 |  |  | 35000 | 0 | 35000 | 0 | 0% | 35000 | 0 | 3500 | 4550 | 0 | 0 | 4550 | 0 | Newly approved project. | Brief progress report (actual/planned): The project was approved in Dec 2016. The licensing and quota system are in place and operational. The NOU registered all importers of HCFCs and organized one stakeholders meeting in Feb 2017 to coordinate and allocate licenses and quotas. The NOU continues to monitor imports and trade of ODS and ODS related equipment. ___ Legal arrangements (actual/planned): The SSFA was drafted and sent to the Government of Zambia for signature. ___Initial stages of project implementation (actual/planned): __Yes_ Intermediate goals achieved (actual/planned): _No__ Project completion and follow up: _Yes__ First disbursement date (actual/planned): __No ____. All funds disbursed (yes/no): No__ Any delay? (yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: __N/A_
FIN | UNIDO | Preparation of training and certification programmes for refrigeration technicians and preparation of investment projects for the refrigeration sector | Individual | AFR | ZAM | REF | 15 | TAS | 03 | A | I |  | 0 | 17.7 |  |  | 1994-12-01 | 1996-02-01 | 1995-06-01 |  | 1996-12-01 | 1999-08-01 | 82100 | -5625 | 76475 | 76475 | 100% | 0 | 0 |  | 10673 | -747 | 9926 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | AFR | ZAM | REF | 19 | TAS | 06 | A | I | CFC | 7.2 | 7.2 | 0 | 0 | 1996-05-01 | 1997-05-01 | 1997-11-01 |  | 1997-12-01 | 2000-12-01 | 106320 | -240 | 106080 | 106080 | 100% | 0 | 0 | 0 | 13821.6 | -31.2 | 13790.4 | 0 | 0 | Completed in 1997. Financially completed in 2000. |  | 1996 |  | Investment
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | ZAM | REF | 23 | PRP | 07 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 2002-05-01 | 1998-03-01 |  | 1998-07-01 | 2000-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | ZAM | REF | 26 | TAS | 08 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2001-05-01 | 2004-07-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | RMP completed, RMP update approved in 42nd Excom
FIN | Germany | Project preparation for a refrigerant management plan update | RMP Update | AFR | ZAM | REF | 37 | PRP | 12 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-05-01 | 2003-08-01 |  | 2004-01-01 | 2004-05-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | RMP update approved at the 42nd meeting
FIN | Germany | Refrigerant management plan update: refrigeration and air conditioning sector | RMP Update | AFR | ZAM | REF | 42 | TAS | 13 | A | I |  | 23.3 | 23.3 | 0 |  | 2004-04-01 | 2004-07-01 | 2007-04-01 |  | 2009-10-01 | 2011-12-01 | 136000 | -7474 | 128526 | 128526 | 100% | 0 | 0 | 0 | 17680 | -971.62 | 16708 | 0.38 | 0 | funds returned to MLF at 65th meeting (UNEP/ozL.Pro/ExCom/65/60 Annex IV
FIN | UNEP | Country programme preparation | Individual | AFR | ZAM | SEV | 04 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-09-01 | 1992-09-01 |  | 1992-10-01 | 1992-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0
FIN | UNEP | Institutional strengthening | Individual | AFR | ZAM | SEV | 09 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1994-12-01 | 1996-03-01 |  | 1999-12-01 | 2004-05-01 | 75600 | 0 | 75600 | 75600 | 100% | 0 | 0 |  | 9828 | 0 | 9828 | 0 | 0 |  |  |  | 1999-12-01
FIN | UNDP | Project preparation assistance | Individual | AFR | ZAM | SEV | 17 | PRP | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-10-01 | 1996-03-01 |  | 1996-06-01 | 1998-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | AFR | ZAM | SEV | 18 | PRP | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-11-01 | 1998-12-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 650 | 0 | 650 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNEP | Renewal of institutional strengthening | Individual | AFR | ZAM | SEV | 30 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2004-08-01 | 2002-07-01 |  | 2004-12-01 | 2008-12-01 | 50400 | 0 | 50400 | 50400 | 100% | 0 | 0 |  | 6552 | 0 | 6552 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | AFR | ZAM | SEV | 44 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-09-01 | 2006-12-01 |  | 2009-03-01 | 2011-03-01 | 65520 | 0 | 65520 | 65520 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | ZAM | SEV | 57 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2011-11-01 | 2011-03-01 |  | 2012-03-01 | 2013-12-01 | 65520 | 0 | 65520 | 65520 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
ONG | UNEP | Extension of the institutional strengthening project (phase V: 12/2013-11/2015) | Individual | AFR | ZAM | SEV | 71 | INS | 29 | A | I |  | 0 |  | 0 |  | 2013-12-01 | 2016-04-01 | 2015-11-01 | 2018-01-01 |  |  | 65520 | 0 | 65520 | 0 | 0% | 65520 | 65520 | 6552 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The licensing and quota system are in place and functioning. The NOU organized four meetings with the Steering committee to review ODS Regulation including HCFC and HFC control measures and to plan for customs and refrigeration technician trainings and general enforcement of ODS regulations especially HCFCs control measures. The NOU registered all importers of HCFCs and organized one stakeholders meeting in January 2016 to coordinate and allocate licenses and quotas. The NOU conducted stakeholders workshop among importers of ODS, in particular HCFCs, where a total of 50 participants attended. The NOU is preparing to commence implementation of Demonstration Project on Refrigerant Quality as Zambia is among the countries selected from the Southern and Eastern Africa to implement the project. The NOU conducted two training workshops in January 2016 and July 2016 for custom officers in the Southern and Northern regions, building their capacity in recording ODS data. A total of 40 customs officers were trained. The NOU conducted 3 training sessions for refrigeration technicians where a total of 60 technicians were trained; 20 RAC technicians from each of the Southern, Central and Northern region in February, May, and October 2016. The NOU organised a train the trainer sessions for 10 customs officers in Lusaka in June 2016 and 15 refrigeration technicians in Lusaka in August 2016. Equipment for strengthening of the centres of excellence for HPMP activities were procured. The NOU conducted awareness programmes on radio, TV, and newspapers articles about ozone issues. The NOU submitted 2015 Country Programme and Article 7 Data reports and celebrated 2016 International Ozone Day with several awareness activities. The NOU conducted a Road show on Ozone Day to raise awareness on Ozone and Climate issues; the print and electronic media also disseminated information on the issues. The NOU also participated in all Montreal Protocol meetings organized in 2016. Legal arrangements (actual/planned): The SSFA was drafted and signed by UNEP and the Government of Zambia in January 2016. Any delay (Yes/No): No_ First mission (actual/planned): __NO._ TOR completed (actual/planned): _N/A__ First disbursement date (actual/planned): April 2016___ All funds disbursed (yes/no): _NO__ Any delay? (yes/no): _YES_ If Yes, reasons for delay & action plan to resolve: __ If Yes, will delay have impact on project completion date (yes/no): _NO__ Any ongoing problems (yes/no): __No_ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): The NOU registered all importers of HCFCs and organized one stakeholders meeting in Feb 2017 to coordinate and allocate licenses and quotas. The NOU continues to monitor imports and trade of ODS and ODS related equipment.
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | AFR | ZAM | SEV | 74 | TAS | 30 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-04-01 | 2016-05-01 | 2017-05-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 35000 | 4000 | 5200 | 0 | 0 | 5200 | 4550 | Brief progress report (actual/planned): The first stakeholders meeting was organized by the NOU in April 2016 in Lusaka with the main goal to sensitize the government and industry on the survey and agree on the plan for the Survey of ODS alternatives at the national level and obtain support of main national stakeholders. The meeting was attended by 40 participants. One National Consultant was hired in March 2016 by the NOU to support the data collection. The National Consultant assisted the NOU in the identification of the current use of ODS alternatives by substance/sector and collection of import/export data for the substances for the past a couple of years. The National Consultant also provided support in establishing growth patterns in use by substance/sector and in compiling data on available ODS alternatives for various applications.The NOU and the National Consultant drafted and cross checked the information to ensure the completion of end-user surveys, collection, analysis, and aggregation of consumption data. The various sections of the report were drafted. The second stakeholders meeting was organized by the NOU in July 2016 in Chisamba District with the main goal to organise consultations with representatives of the government and private sector to finalize the outcomes of the Survey of ODS alternatives and discuss potential opportunities for introduction of those alternatives in the country. The meeting was attended by 20 participants. The draft report was prepared by the NOU and the National Consultant. It was reviewed and finalized based on the format approved by ExCom decision 75/67 as contained in document UNEP/OzL.Pro/ExCom/75/77/Rev.1 after incorporating inputs/ comments raised during National Stakeholders’ workshop. The final report was submitted to UNEP in August 2016 for final review and submission to MLFS. The NOU participated in the ODS Alternative Thematic workshop held in Kenya in December 2016 to refine the draft report according to the revised template for the report. The report has been finally submitted to UNEP. Legal arrangements(actual/planned): The SSFA was drafted and signed by UNEP and the Government of Zambia in January 2016___Initial stages of project implementation(actual/planned): _Yes__ Intermediate goals achieved (actual/planned): Yes___ Project completion and follow up: _Yes__ First disbursement date (actual/planned): _April 2016__ All funds disbursed (yes/no): No___ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): __N/A_ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): The NOU incorporated comments from UNEP ROA and Paris and re-submitted final ODS survey report in February 2017. The NOU continues to monitor imports and trade of ODS and ODS related equipment
ONG | UNEP | Extension of the institutional strengthening project (phase VI: 12/2016-11/2018) | Individual | AFR | ZAM | SEV | 77 | INS | 31 | A | I |  | 0 |  | 0 |  | 2016-12-01 |  | 2018-11-01 | 2018-11-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | Newly approved project. | Brief progress report (actual/planned): The project was approved in Dec 2016. The licensing and quota system are in place and operational. The NOU registered all importers of HCFCs and organized one stakeholders meeting in Feb 2017 to coordinate and allocate licenses and quotas. The NOU continues to monitor imports and trade of ODS and ODS related equipment. ___ Legal arrangements (actual/planned): The SSFA was drafted and sent to the Government of Zambia for signature. ___Initial stages of project implementation (actual/planned): __Yes_ Intermediate goals achieved (actual/planned): _No__ Project completion and follow up: _Yes__ First disbursement date (actual/planned): __No ____. All funds disbursed (yes/no): No__ Any delay? (yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: __N/A_
FIN | UNIDO | Training and awareness workshop in the solvents and process agents (CTC and TCA) sectors | Individual | AFR | ZAM | SOL | 45 | TAS | 16 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-09-01 | 2006-04-01 |  | 2006-12-01 | 2008-05-01 | 40000 | -1745 | 38255 | 38254.73 | 100% | 0.27 | 0 |  | 3600 | -157 | 3443 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | Germany | Preparation for HCFC phase-out investment activities (foam sector) | Individual | AFR | ZIM | FOA | 63 | PRP | 43 | A | I | HCFC | 0 |  | 0 |  | 2011-04-01 | 2011-05-01 | 2012-03-01 |  | 2011-12-01 | 2012-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 |  | Zimbabwe identified foam manufacturers who were using pre-blended polyols and a conversion project for the manufacturers was developed and included into the HPMP, which was approved by the Excom at the 65th Excom.
FIN | UNIDO | Project formulation in the methyl bromide sector | Individual | AFR | ZIM | FUM | 22 | PRP | 11 | A | I |  | 0 | 0 |  |  | 1997-05-01 | 1997-06-01 | 1997-07-01 |  | 1999-01-01 | 2001-07-01 | 8000 | -624 | 7376 | 7376 | 100% | 0 | 0 |  | 1040 | -83 | 957 | 0 | 0 | FIN |  |  | 1999-02-01
FIN | UNIDO | Demonstration project - Two alternatives to the use of methyl bromide in the production of tobacco drought-resistant seedlings: non-soil cultivation and low-dose chemicals | Individual | AFR | ZIM | FUM | 23 | DEM | 13 | A | I |  | 0 | 0 |  |  | 1997-11-01 | 1998-06-01 | 1999-11-01 |  | 2000-12-01 | 2002-09-01 | 370700 | -17402 | 353298 | 353297.55 | 100% | 0.45 | 0 |  | 48191 | -2335 | 45856 | 0 | 0 | FIN
FIN | UNDP | Project preparation for a methyl bromide alternative demonstration project | Individual | AFR | ZIM | FUM | 24 | PRP | 14 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-05-01 | 1998-12-01 |  | 1998-12-01 | 2003-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1998. Financially completed in 2003. |  | 1998 |  | Investment
FIN | UNDP | Alternatives to the use of methyl bromide on stacked bags of maize under gas proof PVC sheets and plastic cocoons (storage) | Individual | AFR | ZIM | FUM | 27 | DEM | 17 | N | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-09-01 | 2000-04-01 |  | 2000-12-01 | 2003-04-01 | 212850 | -10142 | 202708 | 202708 | 100% | 0 | 0 | 0 | 27670.5 | -1318.52 | 26351.98 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNIDO | Preparation of a phase-out project in the methyl bromide sector (cut flowers) | Individual | AFR | ZIM | FUM | 30 | PRP | 18 | A | I |  | 0 | 0 |  |  | 2000-03-01 | 2000-06-01 | 2001-04-01 |  | 2000-12-01 | 2002-09-01 | 30000 | -570 | 29430 | 29430.39 | 100% | -0.39 | 0 |  | 3900 | -80 | 3820 | 0 | 0 | FIN
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organizations in methyl bromide communication | Individual | AFR | ZIM | FUM | 30 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -2765 | 22235 | 22235 | 100% | 0 | 0 |  | 3250 | -359 | 2891 | 0 | 0
FIN | UNIDO | Phase-out of methyl bromide in cut flowers | Individual | AFR | ZIM | FUM | 31 | INV | 21 | A | I | MBR | 132 | 132 |  |  | 2000-07-01 | 2001-03-01 | 2004-08-01 |  | 2006-12-01 | 2010-03-01 | 904200 | -10989 | 893211 | 893211.37 | 100% | -0.37 | 0 |  | 109462 | -1209 | 108253 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project preparation in the fumigants (tobacco) sector | Individual | AFR | ZIM | FUM | 33 | PRP | 22 | A | I |  | 0 | 0 |  |  | 2001-03-01 | 2002-02-01 | 2002-04-01 |  | 2002-12-01 | 2004-03-01 | 30000 | -600 | 29400 | 29399.78 | 100% | 0.22 | 0 |  | 3900 | -84 | 3816 | 0 | 0 | FIN |  |  |  | INV
FIN | UNDP | Project preparation in the fumigation storage sector | Individual | AFR | ZIM | FUM | 33 | PRP | 23 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNIDO | Project preparation in the fumigants (methyl bromide) sector (phase out in tobacco seedling) | Individual | AFR | ZIM | FUM | 45 | PRP | 30 | A | I |  | 0 | 0 |  |  | 2005-04-01 | 2005-06-01 | 2006-04-01 |  | 2005-12-01 | 2005-12-01 | 15000 | -599 | 14401 | 14401.14 | 100% | -0.14 | 0 |  | 1125 | -47 | 1078 | 0 | 0 | FIN |  |  |  | NON-INV
CLO | UNDP | Project preparation for a fumigant (methyl bromide) project | Individual | AFR | ZIM | FUM | 45 | PRP | 31 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2005-04-01 |  | 2006-04-01 |  |  | 2006-12-01 | 20000 | -20000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 1500 | -1500 | 0 | 0 | 0 | Canceled in 2006. Financially completed in 2006. |  | 2005 |  | Investment
FIN | UNIDO | Total phase-out of methyl bromide used in tobacco seedlings (first tranche) | Multi-Year | AFR | ZIM | FUM | 47 | INV | 32 | A | I | MBR | 50 | 50 |  |  | 2005-11-01 | 2006-02-01 | 2007-12-01 |  | 2007-12-01 | 2009-09-01 | 1862486 | 0 | 1862486 | 1862486.01 | 100% | -0.01 | 0 |  | 139686 | 0 | 139686 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Project preparation in the fumigant sector (grain storage) | Individual | AFR | ZIM | FUM | 48 | PRP | 33 | A | I |  | 0 | 0 |  |  | 2006-04-01 | 2006-08-01 | 2007-03-01 |  | 2006-12-01 | 2007-03-01 | 20000 | -806.5 | 19193.5 | 19193.5 | 100% | 0 | 0 |  | 1500 | -60 | 1440 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | UNIDO | Total phase-out of methyl bromide used in grain fumigation | Individual | AFR | ZIM | FUM | 50 | INV | 36 | A | I | MBR | 10.2 | 10.2 |  |  | 2006-11-01 | 2007-01-01 | 2010-11-01 |  | 2008-12-01 | 2011-05-01 | 192073 | -246 | 191827 | 191826.75 | 100% | 0.25 | 0 |  | 17287 | -23 | 17264 | 0 | 0 | FIN |  |  |  | INV
FIN | UNIDO | Total phase-out of methyl bromide used in tobacco seedlings (second tranche) | Multi-Year | AFR | ZIM | FUM | 51 | INV | 37 | A | I | MBR | 120 | 120 |  |  | 2007-03-01 | 2007-11-01 | 2009-12-01 |  | 2008-12-01 | 2010-09-01 | 1862486 | -2 | 1862484 | 1862483.73 | 100% | 0.27 | 0 |  | 139686 | 0 | 139686 | 0 | 0 | FIN |  |  |  | INV
FIN | Germany | Project preparation for a terminal ODS phase-out management plan | Individual | AFR | ZIM | PHA | 37 | PRP | 25 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-09-01 | 2003-08-01 |  | 2004-10-01 | 2004-12-01 | 62760 | 0 | 62760 | 62760 | 100% | 0 | 0 | 0 | 8159 | 0 | 8159 | 0 | 0 | TPMP first tranche approved at 44th ExCom
FIN | Germany | Terminal phase-out management plan for CFCs (first tranche) | Individual | AFR | ZIM | PHA | 44 | INV | 29 | A | I |  | 0 |  | 0 |  | 2004-12-01 | 2005-03-01 | 2006-12-01 |  | 2007-06-01 | 2007-10-01 | 280000 | 0 | 280000 | 280000 | 100% | 0 | 0 | 0 | 36400 | 0 | 36400 | 0 | 0 | Project was completed and the 2nd tranche approved in March 2007
FIN | Germany | National phase-out of Annex A (Group I) substances (phase II, first tranche) | Multi-Year | AFR | ZIM | PHA | 51 | INV | 38 | A | I |  | 25 | 25 | 0 |  | 2007-03-01 | 2007-04-01 | 2009-12-01 |  | 2008-07-01 | 2008-10-01 | 175000 | 0 | 175000 | 175000 | 100% | 0 | 0 | 0 | 22347 | 0 | 22347 | 0 | 0 | Phase completed and 3rd tranche approved
FIN | Germany | National phase-out of Annex A (Group I) substances (phase II, second tranche) | Multi-Year | AFR | ZIM | PHA | 54 | INV | 39 | A | I | CFC | 20 | 20 | 0 |  | 2008-04-01 | 2008-05-01 | 2009-03-01 |  | 2009-03-01 | 2009-03-01 | 175000 | 0 | 175000 | 175000 | 100% | 0 | 0 | 0 | 22347 | 0 | 22347 | 0 | 0 | 20 additional conversions under the incentive scheme were completed and 3 customs trainings were conducted.
FIN | Germany | National phase-out of Annex A (Group I) substances (phase II, third tranche) | Multi-Year | AFR | ZIM | PHA | 57 | INV | 40 | A | I | CFC | 20 |  | 0 |  | 2009-04-01 | 2009-04-01 | 2010-03-01 |  | 2010-06-01 | 2010-06-01 | 175000 | 0 | 175000 | 175000 | 100% | 0 | 0 | 0 | 22347 | 0 | 22347 | 0 | 0 | 4 customs officers were trained. 61 technicans were trained in state of the art refrigeration servicing. 160 commercial refrigeration units were converted under the incentive scheme. 785 kgs of CFC refrigerant were recovered.
FIN | Germany | Preparation of a HCFC phase-out management plan | Individual | AFR | ZIM | PHA | 59 | PRP | 42 | A | I | HCFC | 0 |  | 0 |  | 2009-11-01 | 2010-05-01 | 2010-11-01 |  | 2011-12-01 | 2011-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | A comprehensive survey of the R&AC use was conducted and information put together into the HPMP which included both foam and R&AC components. The project was approved at the 65th Excom.
FIN | Germany | National phase-out of Annex A (Group I) substances (phase II, fourth tranche) | Multi-Year | AFR | ZIM | PHA | 60 | INV | 42 | A | I | CFC | 0 |  | 0 |  | 2010-04-01 | 2010-05-01 | 2011-04-01 |  | 2011-04-01 | 2011-04-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5108 | 0 | 5108 | 0 | 0 | Zimbabwe conducted 2 technican trainings targetting 27 participants as well as 1 customs training for 21 officers on the use of idenitifers capable of monitoring blends.
FIN | Germany | HCFC phase-out management plan (stage I, first tranche) (conversion of the foam manufacturing sector:Capri Refrigeration, Ref Air, Commercial Refrigeration, Delfy Enterprises and Freezing Modern Way) | Multi-Year | AFR | ZIM | PHA | 65 | INV | 44 | A | I | HCFC | 6.1 | 4 | 0 |  | 2011-11-01 | 2011-12-01 | 2013-11-01 |  | 2014-06-01 | 2014-12-01 | 3737 | 311173 | 314910 | 314910 | 100% | 0 | 0 | 0 | 486 | 37213 | 37699 | 0 |  | 3 companies received the planned equipment to phase out HCFC use.
FIN | Germany | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | AFR | ZIM | PHA | 65 | INV | 45 | A | I | HCFC | 0 | 3.6 | 0 |  | 2011-11-01 | 2012-01-01 | 2013-11-01 |  | 2014-06-01 | 2014-12-01 | 3737 | 108244 | 111981 | 111981 | 100% | 0 | 0 | 0 | 486 | 12945 | 13431 | 0 |  | 8 VTCs received the training equipment which was requested to conduct hands-on training. Zimbabwe trainers also participated in the regional train the trainers programme in Mauritius and have conducted 4 technician training courses. | Project has been completed. 2nd tranche has been approved at the 71st excom.
FIN | Germany | HCFC phase-out management plan (stage I, second tranche) (conversion of the foam manufacturing sector: Capri Refrigeration, Ref Air, Commercial Refrigeration, Delfy Enterprises and Freezing Modern Way) | Multi-Year | AFR | ZIM | PHA | 71 | INV | 47 | A | I | HCFC | 2.1 | 2.1 | 0 |  | 2013-12-01 | 2014-07-01 | 2015-12-01 |  | 2015-12-01 | 2016-05-01 | 166762 | 0 | 166762 | 166762 | 100% | 0 | 0 | 0 | 19949 | 0 | 19949 | 0 |  | R141b use in pre blended polyols has been now banned in the country and the companies have moved to alternatives.
FIN | Germany | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | Multi-Year | AFR | ZIM | PHA | 71 | INV | 48 | A | I | HCFC | 1.8 |  | 0 |  | 2013-12-01 | 2014-07-01 | 2015-12-01 |  | 2015-12-01 | 2016-05-01 | 109165 | 0 | 109165 | 109165 | 100% | 0 | 0 | 0 | 13059 | 0 | 13059 | 0 |  | Project conducted 2 HC trainings in Karibba and Chiredzi. Also conducted 4 1-day post trainings at the border for customs officers to complete the funds available under the tranche. |  |  |  | INV
ONG | Germany | HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing sector) | Multi-Year | AFR | ZIM | PHA | 75 | INV | 51 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-01-01 | 2017-12-01 | 2017-12-01 |  |  | 112000 | 0 | 112000 | 56720 | 50.64% | 55280 | 0 | 55280 | 13398 | 0 | 6785 | 6613 |  | Customs trainings were done at 5 border posts, 3 technician trainings on safe handling were conducted. Additionally NOU has worked to approve standards for certification of technicians. This has been done to ensure that each RAC technician has an idenitficiation card that allows him/her to do specific work in the RAC sector based on skills and qualification. | Discussions are ongoing for more training of both technicians and customs. Curriculum update is currently being proposed to be completed in 2017.
ONG | Germany | Verification report for stage I of HCFC phase-out management plan | Individual | AFR | ZIM | PHA | 75 | TAS | 52 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2016-11-01 | 2016-12-01 | 2017-06-01 |  |  | 30000 | 0 | 30000 | 5300 | 17.67% | 24700 | 0 | 24700 | 3900 | 0 | 689 | 3211 |  | The process for shortlisting consultants was started in 2016. | Tthe verification was initiated in January 2017 and is nearing completion and expected to be completed by June 2017
FIN | UNIDO | CFC refrigerant recovery and reclaim project | RMP | AFR | ZIM | REF | 17 | TAS | 04 | A | I | CFC | 47 | 47 |  |  | 1995-07-01 | 1996-03-01 | 1996-07-01 |  | 1996-12-01 | 1998-08-01 | 312300 | -143 | 312157 | 312157 | 100% | 0 | 0 |  | 40599 | -83 | 40516 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | IBRD | Conversion of CFC-12 commercial refrigeration equipment production to HFC-134a and HCFC-22 refrigerant, and CFC-11 to HCFC-141b as the blowing agent for foam insulation at Ref-air Refrigeration | Individual | AFR | ZIM | REF | 20 | INV | 06 | N | I | CFC | 5.3 | 5.3 | 0 | 0 | 1996-10-01 | 1999-03-01 | 2000-10-01 |  | 2000-11-01 | 2000-11-01 | 43382 | 0 | 43382 | 43382 | 100% | 0 | 0 |  | 5639.66 | 0 | 5639.66 | 0 | 0 | Because of economic difficulties in Zimbabwe (including significant local currency devaluation and unavailability of forex), not much progress was made until CY00 and the project was completed by 11/00. |  |  | 1999-12-01 | INV | 0
FIN | IBRD | Conversion of CFC-12 commercial refrigeration equipment production to HFC-134a and HCFC-22 refrigerant, and CFC-11 to HCFC-141b as the blowing agent for foam insulation at Commercial Refrigeration | Individual | AFR | ZIM | REF | 20 | INV | 07 | N | I | CFC | 6.9 | 6.9 | 0 | 0 | 1996-10-01 | 1999-03-01 | 2000-10-01 |  | 2001-08-01 | 2001-08-01 | 156636 | -15061 | 141575 | 141575 | 100% | 0 | 0 |  | 20363 | -1957.93 | 18405.07 | 0 | 0 | Project completed. |  |  | 1999-12-01 | INV | 0
FIN | IBRD | Conversion of CFC-12 refrigerator production to HFC-134a refrigerant and CFC-11 to HCFC-141b as the blowing agent for foam insulation at Capri Refrigeration | Individual | AFR | ZIM | REF | 20 | INV | 08 | N | I | CFC | 5.9 | 5.9 | 0 | 0 | 1996-10-01 | 1998-05-01 | 1998-10-01 |  | 1999-11-01 | 1999-11-01 | 106695 | 0 | 106695 | 106695 | 100% | 0 | 0 |  | 13870 | 0 | 13870 | 0 | 0 | CFC-11 portion completed 2/97 and CFC-12 portion completed 6/99, but because of the economic difficulties in Zimbabwe (including significant local currency devaluation) and the change of ownership of the company, not much progress was made during CY98. The project was completed in 08/99. |  |  | 1999-12-01 | INV | 0
FIN | IBRD | Conversion of CFC-12 refrigerator production to HFC-134a refrigerant and CFC-11 to cyclopentane as the blowing agent for foam insulation at Imperial Derby Refrigeration Ltd. | Individual | AFR | ZIM | REF | 20 | INV | 09 | N | I | CFC | 14 | 12.85 | 0 | 0 | 1996-10-01 | 1998-01-01 | 1997-12-01 |  | 1996-03-01 | 2001-05-01 | 310000 | -88275 | 221725 | 221725 | 100% | 0 | 0 |  | 40300 | -11476 | 28824.25 | -0.25 | -0.25 | Project completed. Funds returned at the 35th ExCom. |  |  | 1999-12-01 | INV | 0
FIN | IBRD | Conversion of CFC-12 commercial refrigeration equipment production to HFC-134a and HCFC-22 refrigerant, and CFC-11 to HCFC-141b as the blowing agent for foam insulation at Ajax Refrigeration | Individual | AFR | ZIM | REF | 20 | INV | 10 | N | I | CFC | 3.5 | 3.5 | 0 | 0 | 1996-10-01 | 1999-03-01 | 2001-10-01 |  | 1997-01-01 | 2001-08-01 | 61966 | 0 | 61966 | 61966 | 100% | 0 | 0 |  | 8056 | 0 | 8056 | 0 | 0 | Company taken over by Commercial Refrigeration and now treated as 2nd production line at Commercial. Project combined with that of Commercial Refrigeration as approved. Financial completion date is the same as Commercial. |  |  | 1999-12-01 | INV | 0
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | ZIM | REF | 23 | PRP | 12 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1998-03-01 |  | 1998-07-01 | 2000-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation
CLO | Germany | Project preparation for phasing out of ODS at the domestic refrigeration factory Fridgemaster | Individual | AFR | ZIM | REF | 26 | PRP | 16 | N | I |  | 0 | 0 | 0 | 0 | 1998-11-01 |  | 1999-12-01 |  |  | 1999-03-01 | 25000 | -25000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project will not be implemented.
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | ZIM | REF | 26 | TAS | 15 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2003-08-01 | 2004-07-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted
FIN | UNEP | Country programme preparation | Individual | AFR | ZIM | SEV | 09 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-05-01 | 1994-06-01 |  | 1994-06-01 | 1994-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0
FIN | UNEP | Institutional strengthening for the phase out of ODS and the establishment of an Ozone Office | Individual | AFR | ZIM | SEV | 13 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1996-06-01 | 1997-07-01 |  | 1999-10-01 | 2000-12-01 | 171050 | 0 | 171050 | 171050 | 100% | 0 | 0 |  | 22237 | 0 | 22237 | 0 | 0 |  |  |  | 1999-05-01
FIN | UNIDO | Preparation of investment projects in the refrigeration, air conditioning and recovery/recycling | Individual | AFR | ZIM | SEV | 14 | PRP | 03 | A | I |  | 0 | 0 |  |  | 1994-09-01 | 1995-02-01 | 1995-03-01 |  | 1997-11-01 | 1999-08-01 | 40000 | -463 | 39537 | 39537 | 100% | 0 | 0 |  | 5200 | -68 | 5132 | 0 | 0 | FIN |  |  |  | NON-INV
FIN | IBRD | Project preparation |  | AFR | ZIM | SEV | 18 | PRP | 05 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-31 | 1996-12-31 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0 |  |  |  | 1999-12-01 | Non-INV | 0
FIN | UNEP | Renewal of institutional strengthening (phase II) | Individual | AFR | ZIM | SEV | 28 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 1999-10-01 | 2001-08-01 |  | 2001-12-01 | 2003-06-01 | 114033 | 0 | 114033 | 114033 | 100% | 0 | 0 |  | 14824 | 0 | 14824 | 0 | 0 |  |  |  | 2001-06-01
FIN | UNEP | Renewal of institutional strengthening project | Individual | AFR | ZIM | SEV | 34 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-01-01 | 2003-08-01 |  | 2004-07-01 | 2004-12-01 | 114033 | 0 | 114033 | 114033 | 100% | 0 | 0 |  | 14824 | 0 | 14824 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (phase IV) | Individual | AFR | ZIM | SEV | 43 | INS | 27 | A | I | CFC | 12.2 | 12.2 | 0 | 0 | 2004-07-01 | 2004-10-01 | 2006-07-01 |  | 2006-11-01 | 2009-06-01 | 148242 | 0 | 148242 | 148242 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (phase V) | Individual | AFR | ZIM | SEV | 50 | INS | 34 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2009-06-01 | 2008-11-01 |  | 2011-07-01 | 2011-12-01 | 148242 | 0 | 148242 | 148242 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
FIN | UNEP | Renewal of the institutional strengthening project (phase VI) | Individual | AFR | ZIM | SEV | 59 | INS | 41 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2011-05-01 | 2011-11-01 |  | 2013-03-01 | 2014-03-01 | 80297 | 67944 | 148241 | 148241 | 100% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
COM | UNEP | Renewal of the institutional strengthening project (phase VII: 4/2013-3/2015) | Individual | AFR | ZIM | SEV | 69 | INS | 46 | A | I |  | 0 |  | 0 |  | 2013-04-01 | 2013-11-01 | 2015-03-01 |  | 2016-08-01 |  | 148242 | 0 | 148242 | 122645.31 | 82.73% | 25596.69 | 131.87 | 5119.338 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The licensing and quota systems are in place and functioning. The NOU registered all importers of HCFCs and organized one stakeholders meeting in January 2016 to coordinate and allocate licenses and quotas. The NOU held four Steering Committee Meetings quarterly to monitor and coordinate implementation of ozone activities. The NOU conducted one Training Workshop for Customs Officers and a total of 22 Customs Officers from all the major ports of entry were trained. The NOU conducted eight training workshops for refrigeration and air conditioning technicians and a total of 225 technicians were trained in safe use of Hydrocarbon refrigerants as replacements for CFCs, HCFCs and HFCs. The NOU collected, verified and reported 2015 consumption data before the deadlines stipulated by the Ozone and Multilateral Fund Secretariats. The NOU celebrated 2016 International Ozone Day and conducted several awareness activities. The NOU also participated in all Montreal Protocol meetings organized in 2016. The SSFA was drafted and signed by UNEP and the Government of Zimbabwe in November, 2013. Initial stages of project implementation(actual/planned):Yes__ Intermediate goals achieved (actual/planned): __Yes_ Project completion and follow up: _Yes__ First disbursement date (actual/planned):The first payment was sent in November, 2013,_ All funds disbursed (yes/no): Yes_ Any delay?(yes/no): _NO__ If Yes, reasons for delay & action plan to resolve: _N/A_ If Yes, will delay have impact on project completion date (yes/no): _N/A__ Any ongoing problems (yes/no): __NO_ If Yes, is any action required by ExCom: _N/A__ | Project completed
ONG | UNEP | Renewal of the institutional strengthening project (phase VIII: 4/2015-3/2017) | Individual | AFR | ZIM | SEV | 74 | INS | 49 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-02-01 | 2017-03-01 | 2018-03-01 |  |  | 148242 | 0 | 148242 | 42057.42 | 28.37% | 106184.58 | 106184.58 | 10618.458 | 0 | 0 | 0 | 0 | 0 | Brief progress report (actual/planned): The licensing and quota systems are in place and functioning. The NOU held four Steering Committee Meetings quarterly to review ODS regulations and to incorporate phased out substances such as methyl chloroform and methyl bromide as well as greenhouse gases such as HFCs and HFC blends being controlled under the Kigali Amendment. The new regulations (S. I. 131 of 2016) were promulgated at the end of October 2016. The NOU conducted eight training workshops for refrigeration and air conditioning technicians and a total of 225 technicians were trained in safe use of Hydrocarbon refrigerants as replacements for CFCs, HCFCs and HFCs. Eighteen demonstrations were carried out on converting air conditioning appliances from use of HCFC-22 and HFC-410A to HC-290. The adoption of HC-290 is being promoted as it is safe to both the ozone layer and global climate system. The challenges noted were that HCs are flammable and those not trained risk getting burnt as was witnessed in some areas such as Bulawayo and Chiredzi. A new standard on certification of refrigeration and air conditioning (RAC) practitioners was developed and published by the Standards Association of Zimbabwe (SAZ ZWE 1012:2016). This will minimize cases of fires during servicing and repairing of RAC appliances. The NOU conducted one Training Workshop for Customs Officers and a total of 22 Customs Officers from all the major ports of entry were trained. The NOU collected, verified and reported 2015 ODS consumption data before the submission deadlines stipulated by the Ozone and Multilateral Fund Secretariats. As part of the 2016 Ozone Day commemorations, the NOU conducted the Ozone Schools Competitions. Pupils from all the Provinces in the country participated and the winning pupils were awarded prizes and certificates. An Ozone Day Symposium was held where Stakeholders collaborating with the NOU in phasing out HCFCs and HFCs and sustaining methyl bromide phase out demonstrated their achievement. A total of 50 participants attended the Symposium which was held at the ZESA Training Centre in Belvedere, Harare on the 16th September, 2016. The Hon Minister and the Permanent Secretary attended the Symposium. Disbursements for Phase VII and Phase VIII were done smoothly and efficiently after the adoption of the UMOJA System by UNEP and activities were implemented without delays. Legal arrangements (actual/planned): The SSFA was drafted and signed by UNEP and the Government of Zimbabwe in February 2016__Initial stages of project implementation(actual/planned): Yes___ Intermediate goals achieved (actual/planned): __Yes_ Project completion and follow up: _No__ First disbursement date (actual/planned): February 2016___ All funds disbursed (yes/no): _No__ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): __N/A_ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): The NOU completed data collection for 2016 HCFCs and HFCs and awaiting submission to Ozone and Multilateral fund Secretariats after approval by the Government. One National Steering Committee Meeting was convened on the 10th January to review the 2016 Annual report and approve the 2017 Workplan. NOU commenced preparation of national legislative requirement processes in planning for ratification of Kigali amendment.
ONG | UNEP | Survey of ODS alternatives at the national level | Individual | AFR | ZIM | SEV | 74 | TAS | 50 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-03-01 | 2016-05-01 | 2017-05-01 |  |  | 70000 | 0 | 70000 | 51.74 | 0.07391% | 69948.26 | 65000 | 6994.826 | 9100 | 0 | 6.7262 | 9093.2738 | 8450 | Brief progress report (actual/planned): The first stakeholders meeting was organized by the NOU in April 2016 in Darwendale at ZIPAM and 40 participants from the ODS Alternative user sectors and importers attended. The main goal of the meeting was to sensitize the government and industry on the survey and agree on the plan for the Survey of ODS alternatives at the national level and obtain support of main national stakeholders. One National Consultant was hired in March 2016 by the NOU to support the data collection. The National Consultant assisted the NOU in the identification of the current use of ODS alternatives by substance/sector and collection of import/export data for the substances for the past a couple of years. The National Consultant also provided support in establishing growth patterns in use by substance/sector and in compiling data on available ODS alternatives for various applications.The NOU and the National Consultant drafted and cross checked the information to ensure the completion of end-user surveys, collection, analysis, and aggregation of consumption data. The various sections of the report were drafted. The second stakeholders meeting was organized by the NOU in October 2016 at the ZIPAM Training Centre in Darwendale with the main goal to organise consultations with representatives of the government and private sector to finalize the outcomes of the Survey of ODS alternatives and discuss potential opportunities for introduction of those alternatives in the country. A total of 45 participants from the sectors using ODS Alternatives were in attendance. The draft report was prepared by the NOU and the National Consultant. It was reviewed and finalized based on the format approved by ExCom decision 75/67 as contained in document UNEP/OzL.Pro/ExCom/75/77/Rev.1 after incorporating inputs/ comments raised during National Stakeholders’ workshop. The final report was submitted to UNEP in November 2016 for final review and submission to MLFS. The NOU participated in the ODS Alternative Thematic workshop held in December 2016 to refine the draft report according to the revised template for the report. The report has been finally submitted to UNEP. Legal arrangements(actual/planned): The SSFA was drafted and signed by UNEP and the Government of Zimbabwe in January 2016___ Initial stages of project implementation(actual/planned): _Yes__ Intermediate goals achieved (actual/planned): Yes___ Project completion and follow up: _Yes__ First disbursement date (actual/planned): _March 2016__ All funds disbursed (yes/no): Yes___ Any delay?(yes/no): _No__ If Yes, reasons for delay & action plan to resolve: _N/A__ If Yes, will delay have impact on project completion date (yes/no): __N/A_ Any ongoing problems (yes/no): _No__ If Yes, is any action required by ExCom: _N/A__ | Brief progress report (actual/planned): The NOU incorporated comments from UNEP ROA and Paris and re-submitted final ODS survey report.
FIN | UNDP | Project preparation for the re-formulation of solvent technical assistance | Individual | AFR | ZIM | SOL | 42 | PRP | 26 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2005-04-01 |  | 2006-12-01 | 2006-12-01 | 24000 | 0 | 24000 | 24000 | 100% | 0 | 0 | 0 | 1800 | 0 | 1800 | 0 | 0 | Completed in 2006. Financially completed in 2006. |  | 2004 |  | Investment
FIN | UNDP | Technical assistance for the phase-out of ODS in the solvent/sterilant sector | Individual | AFR | ZIM | SOL | 50 | TAS | 35 | N | I | TCA/CTC | 3.9 | 3.9 | 0 | 0 | 2006-11-01 | 2008-07-01 | 2008-05-01 |  | 2009-12-01 | 2011-10-01 | 60000 | -1229.02 | 58770.98 | 58771 | 100% | -0.02 | 0 | 0 | 5400 | -111 | 5289.0018 | -0.0017999 | 0 | Completed in 2009. Financially completed in 2011. |  | 2006 | 2010-01-01 | Non-Investment
Note on AG7: Dagmar Habermehl: should read 6485 US$
Note on AH7: Dagmar Habermehl: should be 4565 (4132+433 from 2nd tranche) hence adjustment should be 6485? Noch mal darüber nachdenken!
Note on AH9: Dagmar Habermehl: should be 0, because 433 USD were spent under the first tranche