ONG | UNEP | Extension of the institutional strengthening project (phase VII: 7/2019-6/2021) | Individual | AFR | URT | SEV | 83 | INS | 39 | A | I |  | 0 |  | 0 |  | 2019-05-01 |  | 2021-06-01 | 2021-06-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 34000 | 0 | 0 | 0 | 0 | 0 | The SSFA for a total of USD 85,000 was drafted and sent to country for signature. The Licensing system fully operational. The quota for the year 2019 was issued to 10 of importers. Importers complied with issued quotas for the year 2019. Article A7 and CP data for the year 2018 were submitted in March, 2019. The NOU conducted 2 Steering Committee meetings in Feb 2019 and July 2019. NOU conducted 2 inspections of importers/exporters or market or end-users. NOU conducted training for 20 enforcement officers on 12 – 13 February, 2019 at BOT Conference Hall, Dar es salaam region. Training for 20 enforcement officers on prevention of illegal trade organized on 10 May, 2019 at Karimjee Hall in Dar es salaam region. The NOU conducted one training for 15 members of industry associations in August, 2019. The NOU celebrated International Ozone Day for 2019, marked with the following activities:public sensitization through press release in the country news papers; press conference conducted by the Minister of State in the Vice President’s Office – Environment to reporter of different news media; conducting training workshop for refrigeration technicians from Dar es salaam. The NOU conducted one awareness raising meeting for 30 participants. The NOU participated in the following meetings: Second Global Inter-Regional Thematic meetings back to back with Parallel K-CEP Twinning Workshops, 17--22, 2019, Paris, France; Pilot NOU training workshop and back to back with Enabling Activities Project Workshop, 17-21 June, 2019, Seychelles; 31st Meeting of the Parties, 4-8 November, 2019, Rome, Italy. | NOU continues to monitor imports and trade of ODS and ODS related equipment. The Licensing system is fully operational. The NOU registered all importers of HCFCs and organized one stakeholder meeting in Feb 2020 to coordinate and allocate licenses and quotas. The NOU conducted one training for 20 RAC technicians on 27 -31 January, 2020 at NIMR Conference Hall, Dar es salaam. Delays in project activities are to be expected due to measures taken by the country related to COVID-19 outbreak, which resulted in postponing all meetings/ events planned in the first half of the year. | [6 empty] | 0 | 0
FIN | UNDP | Consultant mission to assess technical assistance requirement | Individual | LAC | URU | SEV | 04 | TAS | 01 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-08-01 | 1992-10-01 |  | 1992-12-01 | 1997-12-01 | 13050 | 992 | 14042 | 14042 | 100% | 0 | 0 | 0 | 1697 | 129 | 1825.46 | 0.54 | 0 | Completed in 1992. Financially completed in 1997. |  | 1991 |  | Non-Investment
FIN | UNDP | Country programme preparation | Individual | LAC | URU | SEV | 08 | CPG | 02 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1992-10-01 | 1992-12-01 | 1993-10-01 |  | 1993-06-01 | 1997-12-01 | 23894 | 1550 | 25444 | 25444 | 100% | 0 | 0 | 0 | 3106 | 202 | 3307.72 | 0.28 | 0 | Completed in 1993. Financially completed in 1997. |  | 1992 |  | Non-Investment
FIN | UNDP | Institutional strengthening: Establishment of COGO | Individual | LAC | URU | SEV | 10 | INS | 03 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-10-01 | 1996-12-01 |  | 1996-12-01 | 1999-12-01 | 173800 | 29000 | 202800 | 202800 | 100% | 0 | 0 | 0 | 22594 | 3770 | 26364 | 0 | 0 | Completed in 1996. Financially completed in 1999. |  | 1993 |  | Non-Investment
FIN | UNDP | Conservation and demonstration programme for domestic and commercial refrigeration and installation of recovery and recycling equipment | RMP-Component | LAC | URU | REF | 12 | TAS | 04 | N | I | CFC | 22 | 22 | 0 | 0 | 1994-03-01 | 1994-09-01 | 1996-03-01 |  | 1996-12-01 | 2004-01-01 | 175000 | -96 | 174904 | 174904 | 100% | 0 | 0 | 0 | 22750 | -12 | 22737.52 | 0.48 | 0 | Completed in 1996. Financially completed in 2004. |  | 1994 |  | Investment
FIN | IBRD | Preparation of investment projects (1994) |  | LAC | URU | SEV | 12 | PRP | 05 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-01 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 100000 | -41688 | 58312 | 58312 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at 7 plants (Aislaciones de Uruguay, Metalizadora Uruguaya, Thermopur, Kubal SA, Kalisay SA, J.C. Scarone, Eraton SA) | Individual | LAC | URU | FOA | 13 | INV | 06 | N | I | CFC | 71 | 71 | 0 | 0 | 1994-07-01 | 1995-01-01 | 1995-07-01 |  | 1996-12-01 | 1999-12-01 | 665000 | 0 | 665000 | 665000 | 100% | 0 | 0 | 0 | 86450 | 0 | 86450 | 0 | 0 | Completed in 1996. Financially completed in 1999. |  | 1994 |  | Investment
FIN | USA | Technical assistance in halon-1211 management |  | LAC | URU | HAL | 13 | TAS | 07 | A | I |  | 0 |  | 0 |  | 1994-07-01 |  | 1994-09-01 |  | 1994-09-01 | 1994-09-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | UNDP | Project preparation assistance | Individual | LAC | URU | SEV | 13 | PRP | 08 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-08-01 | 1995-01-01 |  | 1995-09-01 | 1997-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Investment
FIN | UNDP | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam at 5 plants (Sudamtex del Uruguay, S.A., Ronit Ltd., Maxi, Divino S.A., Poliflex, Ltd.) | Individual | LAC | URU | FOA | 13 | INV | 09 | N | I | CFC | 17 | 17 | 0 | 0 | 1994-07-01 | 1995-07-01 | 1995-07-01 |  | 2001-12-01 | 2003-08-01 | 200000 | -5109 | 194891 | 194891 | 100% | 0 | 0 | 0 | 26000 | -664 | 25335.83 | 0.17 | 0 | Completed in 2001. Financially completed in 2003. |  | 1994 | 1999-06-01 | Investment
CLO | IBRD | Elimination of the use of CFC-11 as blowing agent in rigid polyurethane foams used as insulation in thermal tanks at Tem, S.A. | Individual | LAC | URU | FOA | 15 | INV | 10 | N | I |  | 0 | 0 | 0 | 0 | 1994-12-01 |  | 1995-08-01 |  |  | 1996-04-01 | 220300 | -220300 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Tem S.A. has closed down. The project was cancelled by the government on 4/29/96. Funds returned to Multilateral Fund 20th Meeting. |  |  | 1997-01-01 | INV | 0
FIN | IBRD | Elimination of the use of CFC-11 as blowing agent in rigid polyurethane foams used as insulation in cold storage and substitution of CFC-12 used as refrigerant with HFC-134a at Colder S.R.L. | Individual | LAC | URU | REF | 15 | INV | 11 | N | I | CFC | 10.8 | 10.8 | 0 | 0 | 1994-12-01 | 1997-06-01 | 1995-08-01 |  | 1997-09-01 | 1998-08-01 | 325070 | 0 | 325070 | 325070 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Company signed Subgrant Agreement in November '96. Implementation began in Fall /96. Product testing started in Fall /97. The project was completed in August 98. |  |  | 1999-04-01 | INV | 0
CLO | IBRD | Elimination of the use of CFC-11 as a blowing agent in rigid polyurethane foams used as insulation for refrigerators and substitution of CFC-12 used as refrigerant at Indurnor S.A. | Individual | LAC | URU | REF | 15 | INV | 12 | N | I |  | 0 | 0 | 0 | 0 | 1994-12-01 |  | 1995-12-01 |  |  | 1999-07-01 | 448140 | -448140 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Indunor S.A. has closed down. The funds were returned to the Multilateral Fund on July 99 at the 28th Ex Com meeting |  |  | 2000-01-01 | INV | 0
FIN | USA | Training in the halon sector |  | LAC | URU | HAL | 15 | TRA | 13 | A | I |  | 76.1 |  | 0 |  | 1994-12-01 | 1994-12-01 | 1995-06-01 |  | 1995-06-01 | 1995-06-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | IBRD | Elimination of the use of CFC-11 as a blowing agent in rigid polyurethane foam used as insulation in thermal tanks at Etchepare-Gil S.A. | Individual | LAC | URU | FOA | 15 | INV | 14 | N | I | CFC | 3 | 3 | 0 | 0 | 1994-12-01 | 1998-08-01 | 1995-08-01 |  | 1999-09-01 | 2000-01-01 | 235050 | 0 | 235050 | 235050 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The project was technically completed by September 99 and financially completed in January 00. |  |  | 1999-11-01 | INV | 0
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | LAC | URU | SEV | 16 | PRP | 15 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 81278 | 0 | 81278 | 81278 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Preparation is complete. Project is now under supervision. |  |  |  | Non-INV | 0
FIN | UNDP | Total aerosol sector phaseout project (technical assistance) | Individual | LAC | URU | ARS | 18 | TAS | 16 | N | I | CFC | 16 | 16 | 0 | 0 | 1995-11-01 | 1996-12-01 | 1997-05-01 |  | 1999-12-01 | 2001-12-01 | 54000 | -1 | 53999 | 53999 | 100% | 0 | 0 | 0 | 7020 | 0 | 7019.87 | 0.13 | 0 | Completed in 1999. Financially completed in 2001. |  | 1995 | 1999-07-01 | Non-Investment
FIN | UNDP | Conversion of production of halon-1211 fire extinguishers at Tornay and Mori | Individual | LAC | URU | HAL | 18 | INV | 17 | N | I | Halon | 2 | 2 | 0 | 0 | 1995-11-01 | 1997-05-01 | 1996-05-01 |  | 1997-09-01 | 1999-12-01 | 38150 | 0 | 38150 | 38150 | 100% | 0 | 0 | 0 | 4960 | 0 | 4959.5 | 0.5 | 0 | Completed in 1997. Financially completed in 1999. |  | 1995 |  | Investment
FIN | UNDP | Transfer of technology and conversion of production of halon-1211 fire extinguishers at Izeta López Fire Company | Individual | LAC | URU | HAL | 18 | INV | 18 | N | I | Halon | 2.7 | 2.7 | 0 | 0 | 1995-11-01 | 1996-12-01 | 1996-02-01 |  | 1996-12-01 | 1999-12-01 | 24225 | 0 | 24225 | 24225 | 100% | 0 | 0 | 0 | 3149 | 0 | 3149.25 | -0.25 | 0 | Completed in 1996. Financially completed in 1999. |  | 1995 |  | Investment
FIN | IBRD | Recovery and recycling of CFC-12 in maintenance workshops for industrial refrigeration equipment | Individual | LAC | URU | REF | 18 | TAS | 19 | N | I | CFC | 4 | 0 | 0 | 0 | 1995-11-01 | 1998-07-01 | 1996-05-01 |  | 1999-10-01 | 2000-01-01 | 87647 | 0 | 87647 | 87647 | 100% | 0 | 0 | 0 | 11394 | 0 | 11394 | 0 | 0 | Implementation began in Fall'96. The funds were transferred to local UNDP office in September'97. During 1998 the equipment was purchased and the consultantwas paid. The equipment were distributed on March 99 . The project was completed by October 99. |  |  | 1999-12-01 | INV | 0
FIN | IBRD | Project preparation |  | LAC | URU | SEV | 18 | PRP | 20 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-01 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Project preparation completed. |  |  |  | Non-INV | 0
FIN | IBRD | Completing the elimination of CFC use in domestic refrigeration manufacturing by adoption of HCFC-141b as blowing agent and HFC-134a as refrigerant at Nevol S.A. | Individual | LAC | URU | REF | 19 | INV | 21 | N | I | CFC | 4.6 | 4.6 | 0 | 0 | 1996-05-01 | 1997-08-01 | 1997-07-01 |  | 2000-02-01 | 1999-07-01 | 141512 | 0 | 141512 | 141512 | 100% | 0 | 0 | 0 | 18397 | 0 | 18397 | 0 | 0 | The project was completed in July 99 |  |  | 1999-07-01 | INV | 0
FIN | UNDP | Renewal of institutional strengthening | Individual | LAC | URU | SEV | 20 | INS | 22 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1996-10-01 | 1996-10-01 | 1998-10-01 |  | 1998-07-01 | 1999-12-01 | 116000 | 0 | 116000 | 116000 | 100% | 0 | 0 | 0 | 15080 | 0 | 15080 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1996 |  | Non-Investment
FIN | IBRD | Project preparation |  | LAC | URU | SEV | 21 | PRP | 23 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Project preparation completed. |  |  |  | Non-INV | 0
FIN | IBRD | Market survey to develop a country-wide scheme to phase out remaining ODS | Individual | LAC | URU | SEV | 22 | TAS | 24 | N | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-06-01 | 1998-12-01 |  | 1998-07-01 | 1998-07-01 | 23000 | 0 | 23000 | 23000 | 100% | 0 | 0 | 0 | 2990 | 0 | 2990 | 0 | 0 | Time required for collecting and verifying consumption data was longer than originally anticipated. All disbursements have been made (US$ 23,000). Project completed. |  |  |  | Non-INV | 0
FIN | UNEP | Assistance for formulation of a refrigerant management plan | RMP | LAC | URU | REF | 23 | PRP | 25 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-04-01 | 1998-11-01 |  | 1999-01-01 | 1999-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | [8 empty] | 0 | 0
FIN | UNIDO | Preparation of a demonstration project (tomatoes, cucumber, strawberries, flower) | Individual | LAC | URU | FUM | 24 | PRP | 26 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-05-01 | 1999-04-01 |  | 1998-05-01 | 2001-07-01 | 25000 | -1950 | 23050 | 23050 | 100% | 0 | 0 |  | 3250 | -258 | 2992 | 0 | 0
FIN | UNDP | Renewal of institutional strengthening | Individual | LAC | URU | SEV | 25 | INS | 27 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-01-01 | 2000-07-01 |  | 2000-07-01 | 2003-12-01 | 116000 | -19 | 115981 | 115981 | 100% | 0 | 0 | 0 | 15080 | -2 | 15078 | 0 | 0 | Completed in 2000. Financially completed in 2003. |  | 1998 |  | Non-Investment
FIN | UNIDO | Alternatives to the use of methyl bromide as a soil fumigant in protected horticultural crops (cucumbers and peppers), seedbeds, and nurseries (vegetables, tobacco and forestry) | Individual | LAC | URU | FUM | 25 | DEM | 28 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-08-01 |  | 2001-12-01 | 2003-06-01 | 299200 | -1381 | 297819 | 297819 | 100% | 0 | 0 |  | 38896 | -240.89 | 38655 | 0.11 | 0
FIN | Canada | Implementation of the RMP: custom officers training programme | RMP | LAC | URU | REF | 27 | TRA | 29 | A | I |  | 0 |  | 0 |  | 1999-03-01 | 1999-12-01 | 2000-10-01 |  | 2003-06-01 | 2004-05-01 | 71190 | 0 | 71190 | 71190 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed. PCR submitted. |  | 1999 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: train the trainers programme in the refrigeration sector | RMP | LAC | URU | REF | 27 | TRA | 30 | A | I |  | 0 |  | 0 |  | 1999-03-01 | 1999-12-01 | 2000-10-01 |  | 2001-06-01 | 2002-03-01 | 63280 | 0 | 63280 | 63280 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Train-the-technicians workshop complete, 150 technicians trained. PCR submitted to Sect. |  | 1999 |  | Non-Inv.
FIN | Canada | Implementation of the RMP: implementation of a license/quota system for ODS | RMP | LAC | URU | REF | 27 | TAS | 31 | A | I |  | 0 |  | 0 |  | 1999-03-01 | 1999-12-01 | 2001-03-01 |  | 2001-11-01 | 2002-04-01 | 11300 | 0 | 11300 | 11300 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project completed and licensing developed as planned. PCR Submitted to Sect |  | 1999 |  | Non-Inv.
FIN | IBRD | Preparation of an investment project in the domestic refrigeration sector |  | LAC | URU | REF | 30 | PRP | 32 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-01 | 2001-12-01 |  | 2000-12-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNIDO | Preparation of an investment project in the methyl bromide sector | Individual | LAC | URU | FUM | 30 | PRP | 33 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-06-01 | 2001-04-01 |  | 2001-10-01 | 2002-12-01 | 25000 | -935 | 24065 | 24065 | 100% | 0 | 0 |  | 3250 | -126.49 | 3124 | -0.49 | 0
FIN | IBRD | Terminal programme for the elimination of CFC-11 in the manufacture of polyurethane foam through the use of HCFC-141b technology in the foam sector in Uruguay by means of technical assistance and conversion to different companies | Individual | LAC | URU | FOA | 31 | INV | 34 | N | I | CFC | 4.3 | 4.4 | 0 | 0 | 2000-07-01 | 2001-11-01 | 2002-01-01 |  | 2003-05-01 | 2003-05-01 | 91300 | -80 | 91220 | 91220 | 100% | 0 | 0 | 0 | 11869 | -10 | 11859 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | UNDP | Renewal of institutional strengthening (Phase IV) | Individual | LAC | URU | SEV | 31 | INS | 35 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2000-07-01 | 2000-08-01 | 2002-08-01 |  | 2002-07-01 | 2004-04-01 | 116000 | -196 | 115804 | 115804 | 100% | 0 | 0 | 0 | 15080 | -25 | 15055 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 2000 |  | Non-Investment
FIN | UNIDO | Phase-out of methyl bromide in horticulture (tomatoes and cut flowers) | Individual | LAC | URU | FUM | 34 | INV | 35 | A | I | MBR | 24 | 24 | 0 | 0 | 2001-07-01 | 2002-02-01 | 2012-12-01 |  | 2009-12-01 | 2010-12-01 | 469370 | -203.79 | 469166.21 | 469166 | 100% | 0.21 | 0 |  | 61018 | -26 | 60991.58 | 0.42 | 0 |  |  |  |  | INV
FIN | UNEP | Implementation of the RMP: demonstration and training project for the use of hydrocarbons as refrigerants | Individual | LAC | URU | REF | 34 | TAS | 36 | A | I | CFC | 45.8 | 45.8 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2002-08-01 |  | 2007-03-01 | 2009-12-01 | 65000 | -2831 | 62169 | 62169 | 100% | 0 | 0 | 0 | 8450 | -368.03 | 8081.97 | 0 | 0 | [8 empty] | 0 | 0
FIN | UNDP | Implementation of the RMP: Incentive programme for the commercial/industrial refrigeration end-user sector | RMP-Component | LAC | URU | REF | 34 | TAS | 37 | N | I | CFC | 109.1 | 109.1 | 0 | 0 | 2001-07-01 | 2003-01-01 | 2007-08-01 |  | 2009-12-01 | 2011-02-01 | 154934 | -192 | 154742 | 154742 | 100% | 0 | 0 | 0 | 20141 | -25 | 20116.46 | -0.46 | 0 | Completed in 2009. |  | 2001 |  | Investment
FIN | UNDP | Development of an MDI transition strategy | Individual | LAC | URU | ARS | 36 | TAS | 38 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-09-01 | 2003-04-01 |  | 2002-12-01 | 2004-04-01 | 30000 | -2577 | 27423 | 27423 | 100% | 0 | 0 | 0 | 3900 | -335 | 3565 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 2002 |  | Non-Investment
FIN | UNDP | Renewal of institutional strengthening project (Phase 5) | Individual | LAC | URU | SEV | 37 | INS | 39 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-01-01 | 2004-08-01 |  | 2006-01-01 | 2009-08-01 | 150800 | 0 | 150800 | 150800 | 100% | 0 | 0 | 0 | 19604 | 0 | 19604 | 0 | 0 | Completed in 2006.Financially completed in 2009. |  | 2002 |  | Non-Investment
FIN | UNDP | Transition strategy for the phase-out of CFCs use in MDIs | Individual | LAC | URU | ARS | 38 | TAS | 40 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2002-11-01 | 2005-01-01 | 2009-12-01 |  | 2009-12-01 | 2011-02-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | Completed in 2009. Financially completed in 2011. |  | 2002 |  | Non-Investment
FIN | UNDP | Extension of the institutional strengthening project (phase VI) | Individual | LAC | URU | SEV | 43 | INS | 41 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2004-07-01 | 2005-07-01 | 2006-07-01 |  | 2007-12-01 | 2011-12-01 | 150800 | 0 | 150800 | 150800 | 100% | 0 | 0 | 0 | 11310 | 0 | 11310 | 0 | 0 | Completed in 2007. Financially completed in 2011. |  | 2004 |  | Non-Investment
FIN | UNDP | Phase-out of CFC consumption in the manufacture of aerosol metered dose inhalers (MDIs) | Individual | LAC | URU | ARS | 43 | INV | 42 | N | I | CFC | 10 | 10 | 0 | 0 | 2004-07-01 | 2006-04-01 | 2007-07-01 |  | 2009-12-01 | 2013-12-01 | 427023 | -6 | 427017 | 427017 | 100% | 0 | 0 | 0 | 32027 | 0 | 32026.9887 | 0.01125 | 0 | Financially completed in 2013. |  | 2004 |  | Investment
FIN | UNDP | Technical assistance for the phase-out of ODSs in the solvent sector | Individual | LAC | URU | SOL | 45 | TAS | 43 | N | I | TCA/CTC | 0.3 | 0.3 | 0 | 0 | 2005-04-01 | 2005-12-01 | 2006-12-01 |  | 2007-12-01 | 2009-08-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 2700 | 0 | 2700 | 0 | 0 | Completed in 2007.Financially completed in 2009. |  | 2005 |  | Non-Investment
FIN | UNDP | Project preparation of a terminal phase-out management plan | Individual | LAC | URU | PHA | 47 | PRP | 44 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2005-11-01 | 2006-04-01 | 2006-12-01 |  | 2007-03-01 | 2009-08-01 | 30000 | -18 | 29982 | 29982 | 100% | 0 | 0 | 0 | 2250 | -1 | 2248.65 | 0.35 | 0 | Completed in 2007.Financially completed in 2009. |  | 2005 |  | Investment
FIN | UNDP | Renewal of institutional strengthening project (phase VII) | Individual | LAC | URU | SEV | 49 | INS | 45 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2006-07-01 | 2008-02-01 | 2008-10-01 |  | 2010-08-01 | 2012-07-01 | 150800 | 0 | 150800 | 150800 | 100% | 0 | 0 | 0 | 11310 | 0 | 11310 | 0 | 0 | Financially completed in 2012. |  | 2006 |  | Non-Investment
FIN | UNDP | Terminal phase-out management plan for Annex A Group I Substances (first tranche) | Multi-Year | LAC | URU | PHA | 50 | INV | 46 | N | I | CFC | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-01-01 | 2009-12-01 |  | 2008-12-01 | 2013-08-01 | 240000 | 0 | 240000 | 240000 | 100% | 0 | 0 | 0 | 18000 | 0 | 18000 | 0 | 0 | Financially completed in 2013. |  | 2006 |  | Investment
FIN | Canada | Terminal phase-out management plan for Annex A Group I Substances (first tranche) | Multi-Year | LAC | URU | PHA | 50 | TAS | 47 | A | I | CFC | 0 |  | 0 |  | 2006-11-01 | 2008-01-01 | 2007-11-01 |  | 2010-07-01 | 2011-07-01 | 160000 | 0 | 160000 | 160000 | 100% | 0 |  | 0 | 20800 | -9120 | 11680 | 0 |  | All project activities, including training and establishment of collaboration with enforcement, had been completed. Final report from NOU received. $9,120 remaining in support costs were returned to Fund, as noted at ExCom 64 in July 2011. |  | 2006 |  | Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan | Individual | LAC | URU | PHA | 55 | PRP | 48 | N | I | HCFC | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-04-01 | 2009-07-01 |  | 2011-12-01 | 2013-07-01 | 150000 | 0 | 150000 | 150000 | 100% | 0 | 0 | 0 | 11250 | 0 | 11250 | 0 | 0 | Financially completed in 2013. |  | 2008 |  | Investment
FIN | UNDP | Renewal of institutional strengthening project (phase VIII) | Individual | LAC | URU | SEV | 56 | INS | 49 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2008-11-01 | 2010-01-01 | 2010-10-01 |  | 2011-12-01 | 2013-02-01 | 150800 | 0 | 150800 | 150800 | 100% | 0 | 0 | 0 | 11310 | 0 | 11310 | 0 | 0 | Financially completed in 2013. |  | 2008 |  | Non-Investment
FIN | UNDP | Terminal phase-out management plan for Annex A Group I substances (second tranche) | Multi-Year | LAC | URU | PHA | 56 | INV | 50 | N | I | CFC | 69.7 | 69.7 | 0 | 0 | 2008-11-01 | 2010-01-01 | 2009-11-01 |  | 2010-12-01 | 2013-09-01 | 48000 | 0 | 48000 | 48000 | 100% | 0 | 0 | 0 | 3600 | 0 | 3600 | 0 | 0 | Financially completed in 2013. |  | 2008 |  | Investment
FIN | Canada | Terminal phase-out management plan for Annex A Group I Substances (second tranche) | Multi-Year | LAC | URU | PHA | 56 | TAS | 51 | A | I | CFC | 0 |  | 0 |  | 2008-11-01 | 2009-08-01 | 2009-11-01 |  | 2011-03-01 | 2011-03-01 | 42000 | 0 | 42000 | 42000 | 100% | 0 |  | 0 | 5460 | 0 | 5460 | 0 |  | Activities initiated in september 2009. 340 technicians trained. organization of 3 meetings with enforcement officials. Efforts to implement the technician certification scheme continued throughout the year. The online licensing system was implemented and one training workshop was held with stakeholders. Final training held in first quarter of 2011 and project completed by end of March 2011. $2,100 in support costs were erroneously reported as unspent in previous report and were in fact spent. |  | 2008 |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (foam sector) | Individual | LAC | URU | FOA | 57 | PRP | 52 | N | I | HCFC | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-12-01 | 2010-03-01 |  | 2013-01-01 | 2013-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 4500 | 0 | 4500 | 0 | 0 | Financially completed in 2013. |  | 2009 |  | Investment
FIN | Canada | Terminal phase-out management plan for Annex A Group I Substances (third tranche) | Multi-Year | LAC | URU | PHA | 60 | TAS | 53 | A | I | CFC | 0 |  | 0 |  | 2010-04-01 | 2011-06-01 | 2011-04-01 |  | 2011-12-01 | 2012-04-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 |  | 0 | 3900 | 0 | 3900 | 0 |  | Activities were rapidly completed as they consisted mainly of 4 training workshops on good practices and strengthening of the certification system. Project completed by end of 2011 and remaining balance paid by Canada in April 2012 after final progress and expenditure reports were submitted. |  | 2010 |  | Investment
FIN | UNDP | Terminal phase-out management plan for Annex A Group I Substances (third tranche) | Multi-year | LAC | URU | PHA | 60 | INV | 54 | N | I | CFC | 29.9 | 29.9 | 0 | 0 | 2010-04-01 | 2011-09-01 | 2011-04-01 |  | 2013-12-01 | 2013-12-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 3375 | 0 | 3375 | 0 | 0 | Financially completed in 2013. |  | 2010 |  | Investment
FIN | UNIDO | Preparation for HCFC phase-out investment activities (refrigeration manufacturing sector) | Individual | LAC | URU | REF | 60 | PRP | 55 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-07-01 | 2011-04-01 |  | 2015-09-01 | 2015-09-01 | 50000 | -421.96 | 49578.04 | 49578.1 | 100% | -0.06 | 0 |  | 3750 | -32 | 3718.3575 | -0.3575 | 0
FIN | UNDP | Extension of institutional strengthening project (phase IX: 1/2012-12/2013) | Individual | LAC | URU | SEV | 65 | INS | 56 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-02-01 | 2013-12-01 |  | 2014-06-01 | 2015-12-01 | 150800 | -3 | 150797 | 150797 | 100% | 0 | 0 | 0 | 11310 | 0 | 11309.7749 | 0.22505 | 0 | Financially completed in 2015. |  | 2011 |  | Non-investment
FIN | UNDP | HCFC phase-out management plan (stage I, first tranche) | Multi-year | LAC | URU | PHA | 65 | INV | 57 | N | I | HCFC | 0 | 0 | 0 | 0 | 2011-11-01 | 2012-09-01 | 2015-11-01 |  | 2013-06-01 | 2013-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 7500 | 0 | 7500 | 0 | 0 | Financially completed in 2013. |  | 2011 |  | Investment |  |  | 2016-12-01
FIN | UNDP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | URU | PHA | 68 | INV | 58 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-03-01 | 2014-12-01 |  | 2014-10-01 | 2015-02-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 7500 | 0 | 7500 | 0 | 0 | Financially completed in 2015. |  | 2012 |  | Investment |  |  | 2016-12-01
FIN | UNDP | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | LAC | URU | PHA | 71 | INV | 59 | N | I | HCFC | 0 | 0 | 0 | 0 | 2013-12-01 | 2014-08-01 | 2015-06-01 |  | 2015-12-01 | 2016-12-01 | 115000 | 0 | 115000 | 115000 | 100% | 0 | 0 | 0 | 8625 | 0 | 8625 | 0 | 0 | Financially completed in 2016. |  | 2013 |  | Investment |  |  | 2016-12-01
FIN | UNDP | Extension of institutional strengthening project (phase X: 1/2014-12/2015) | Individual | LAC | URU | SEV | 71 | INS | 60 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2013-12-01 | 2014-08-01 | 2015-12-01 |  | 2015-12-01 | 2016-12-01 | 150800 | 0 | 150800 | 150800 | 100% | 0 | 0 | 0 | 10556 | 0 | 10555.972 | 0.028 | 0 | Financially completed in 2016. |  | 2013 |  | Non-Investment
FIN | UNDP | Preparation of a HCFC phase-out management plan (stage II) | Individual | LAC | URU | PHA | 72 | PRP | 61 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 | 2015-01-01 | 2016-05-01 |  | 2016-12-01 | 2019-01-01 | 60000 | -4 | 59996 | 59996 | 100% | 0 | 0 | 0 | 4200 | 0 | 4199.72 | 0.28 | 0 | Remarks1 - upto 31 Dec 2016 (Short narrative description of progress made (actual/planned)): Project prepared and discussed with counterparts. Documment submitted and approved by ExCom. Adjustment of approved document made. Prodoc signed (actual/planned, yes/no and date):The agreement has been signed earlier. Missions undertaken (actual/planned):2 of 2 TOR for consultants/subcontracts completed (actual/planned): 1 of 1 Contract/PO/MOA agreements signed: 1 of 1 First disbursement date (actual/planned): 42005Any delays/problems (yes/no):No If Yes, reasons for delay & action plan to resolve:N/A |  |  |  | Investment
FIN | UNDP | Preparation for HCFC phase-out investment activities (stage II) (foam sector) | Individual | LAC | URU | FOA | 72 | PRP | 62 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 | 2015-01-01 | 2016-05-01 |  | 2017-01-01 | 2019-02-01 | 68000 | 0 | 68000 | 68000 | 100% | 0 | 0 | 0 | 4760 | 0 | 4760 | 0 | 0 | Remarks1 - upto 31 Dec 2017 (Short narrative description of progress made (actual/planned)): HPMP 2nd phase ProDoc prepared and discussed with stakeholders. Prodoc signed (actual/planned, yes/no and date): Agreement has been signed earlier. Missions undertaken (actual/planned): 1 of 1. TOR for consultants/subcontracts completed (actual/planned): TOR completed earlier. Contract/PO/MOA agreements signed: 0 of 0. First disbursement date (actual/planned): Jan 2015. Any delays/problems (yes/no): No. If Yes, reasons for delay & action plan to resolve: N/A |  |  |  | Non-Investment
FIN | UNDP | HCFC phase-out management plan (stage I, fourth tranche) | Multi-Year | LAC | URU | PHA | 73 | INV | 63 | N | I | HCFC | 2.3 | 2.3 | 0 | 0 | 2014-11-01 | 2015-02-01 | 2016-11-01 |  | 2015-04-01 | 2016-04-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 1500 | 0 | 1500 | 0 | 0 | Financially completed in 2016. |  | 2014 |  | Investment |  |  | 2016-12-01
FIN | UNIDO | Survey of ODS alternatives at the national level | Individual | LAC | URU | SEV | 74 | TAS | 64 | A | I |  | 0 | 0 | 0 | 0 | 2015-05-01 | 2016-04-01 | 2016-05-01 |  | 2017-12-01 | 2018-10-24 | 110000 | -7489 | 102511 | 102511.28 | 100% | -0.28 | 0 |  | 9900 | -674 | 9226.0152 | -0.0152 | 0 |  |  |  |  | NON-INV
FIN | UNDP | Extension of institutional strengthening project (phase XI: 1/2016-12/2017) | Individual | LAC | URU | SEV | 75 | INS | 65 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2015-11-01 | 2016-04-01 | 2017-12-01 |  | 2017-12-01 | 2018-12-01 | 193024 | 0 | 193024 | 193024 | 100% | 0 | 0 | 0 | 13512 | 0 | 13511.993 | 0.0070002 | 0 | Financially completed in 2018. |  | 2015 |  | Non-Investment
FIN | UNDP | HCFC phase-out management plan (stage I, fifth tranche) | Multi-year | LAC | URU | PHA | 75 | INV | 66 | N | I | HCFC | 1.9 | 1.9 | 0 | 0 | 2015-11-01 | 2015-12-01 | 2016-12-01 |  | 2016-12-01 | 2017-12-01 | 45004 | 0 | 45004 | 45004 | 100% | 0 | 0 | 0 | 3375 | 0 | 3375 | 0 | 0 | Financially completed in 2017. |  | 2015 |  | Investment |  |  | 2016-12-01
ONG | UNDP | HCFC phase-out management plan (stage II, first tranche) (foam sector) | Multi-year | LAC | URU | PHA | 77 | INV | 67 | N | I | HCFC | 1 | 0 | 0 | 0 | 2016-12-01 | 2017-08-01 | 2019-12-01 | 2020-11-01 |  |  | 100000 | 0 | 100000 | 38101 | 38.1% | 61899 | 0 | 18569.583 | 7000 | 0 | 2667.0973 | 4332.9027 | 0 | National consultant hired. The project conducted meetings with local suppliers of BASF, DOW, Plasfi, Synthesia, Inov (Shanghai Dongda polyurethane Co. from China) and Huntsman. Memorandum of agreement signed with James to conduct conversion to HCFC-free alternatives. | 1 memorandum of agreement signed with a the main consumer of HCFC-141b in the country, conversion under way. Test protocols discussed with suppliers and end-users. | 2016 |  | Investment |  |  | 2021-12-01
FIN | UNDP | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | Multi-year | LAC | URU | PHA | 77 | TAS | 68 | N | I | HCFC | 0 | 0 | 0 | 0 | 2016-12-01 | 2017-08-01 | 2019-12-01 |  | 2018-12-01 | 2019-12-01 | 178200 | 0 | 178200 | 178200 | 100% | 0 | 0 | 0 | 12474 | 0 | 12474 | 0 | 0 | Financially completed in 2019. |  | 2016 |  | Investment |  |  | 2021-12-01
COM | UNDP | HCFC phase-out management plan (stage II, first tranche) (implementation and monitoring) | Multi-year | LAC | URU | PHA | 77 | TAS | 69 | N | I | HCFC | 0 | 0 | 0 | 0 | 2016-12-01 | 2017-08-01 | 2018-12-01 |  | 2018-12-01 |  | 35800 | 0 | 35800 | 28152 | 78.64% | 7648 | 0 | 5353.796 | 2506 | 0 | 1970.6204 | 535.3796 | 0 | Remarks1 - up to 31 Dec 2018: Second tranche request prepared and submitted. Annual reports prepared and presented to national authorities and UNDP country office. |  | 2016 |  | Investment |  |  | 2021-12-01
COM | UNDP | Extension of institutional strengthening project (phase XII: 1/2018-12/2019) | Individual | LAC | URU | SEV | 80 | INS | 70 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2017-11-01 | 2018-03-01 | 2019-12-01 |  | 2019-12-01 |  | 193024 | 0 | 193024 | 193024 | 100% | 0 | 0 | 0 | 13512 | 0 | 13512 | 0 | 0 | Institutional strengthening activities conducted, follow up to Multilateral Fund-financed projects portfolio; 2019 Ozone day celebration conducted. HCFC quota distributed among interested importers. CP anf Art. 7 reports prepared and submitted to MLFS and Ozone Secretariat, respectively. Phase XIII prepared and requested. |  | 0
ONG | UNDP | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector and implementation and monitoring) | Multi-Year | LAC | URU | PHA | 82 | TAS | 71 | N | I | HCFC | 0 | 0 | 0 | 0 | 2018-12-01 |  | 2021-12-01 | 2021-12-01 |  |  | 257000 | 0 | 257000 | 0 | 0% | 257000 | 0 | 77100 | 17990 | 0 | 0 | 17990 | 0 | 2 specialized workshops on the use of Ammonia were carried out, with the participation of 16 trainers, engineers and decision-makers. 2 training sessions for customs officer, 50 participants. 2 2-week long campaings to promote GRP and alternative substances. 1 train-the-trainer seminar was conducted with the participation of 10 trainers from technical institutes, universities and LATU. Awareness raising activities to promote the adoption of alternatives to HCFCs. | Meetings with customs office to review HCFC import control procedures conducted, international consultant hired; virtual meetings carried out. Verification report prepared. Third tranche request prepared and submitted. | 0 |  | Investment |  |  | 2021-12-01
ONG | UNDP | HCFC phase-out management plan (stage II, second tranche) (foam sector) | Multi-Year | LAC | URU | PHA | 82 | INV | 72 | N | I | HCFC | 4.7 | 1 | 0 | 0 | 2018-12-01 | 2019-03-01 | 2021-12-01 | 2021-12-01 |  |  | 422889 | 0 | 422889 | 123041 | 29.1% | 299848 | 0 | 89954.484 | 29602 | 0 | 8612.7835 | 20989.2165 | 0 | Visits to beneficiary companies to identify current consumption and needs to adopt alternative blowing agents.The project with the beneficiary companies are preparing a testing protocol to promote the adoption of HFO-based PU systems. | Meeting with the international consultant to review test protocols and availability of HFO-based system conducted. Visits to beneficiary users conducted by project team, due to COVId-19 additional visits were posponed. | 0 |  | Investment |  |  | 2021-12-01
ONG | UNDP | Preparation of a HCFC phase-out management plan (stage III) | Individual | LAC | URU | PHA | 83 | PRP | 73 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2019-05-01 |  | 2021-06-01 | 2021-06-01 |  |  | 60000 | 0 | 60000 | 0 | 0% | 60000 | 0 | 60000 | 4200 | 0 | 0 | 4200 | 0 | International consultant recruited, initial meetings with NOU conducted to review workplan and guidelines. | Project proposal under preparation, information on HCFC consumption was gathered and analyzed and meetings with stakeholders carried out. Due to COVID-19 validation workshops were virtually conducted |  |  | Non-Investment
ONG | UNDP | Extension of institutional strengthening project (phase XIII: 1/2020-12/2021) | Individual | LAC | URU | SEV | 84 | INS | 74 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2019-12-01 |  | 2021-12-01 | 2021-12-01 |  |  | 193024 | 0 | 193024 | 0 | 0% | 193024 | 0 | 57907.2 | 13512 | 0 | 0 | 13512 | 0 | Newly Approved | ProDoc developed and signed, work plan and budget approved. |  |  | Non-Investment
FIN | UNEP | Country programme preparation | Individual | ASP | VAN | SEV | 17 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1997-01-01 | 1996-10-01 |  | 2002-03-01 | 2003-06-01 | 20000 | -7000 | 13000 | 13000 | 100% | 0 | 0 | 0 | 2600 | -910 | 1690 | 0 | 0 |  |  |  | 1999-12-01 |  |  |  |  | 0 | 0
FIN | Australia | Implementation of the PIC Strategy: assistance for enforcing ODS regulations and training programme for customs officers | Individual | ASP | VAN | REF | 36 | TAS | 02 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-04-01 | 2005-04-01 |  | 2010-06-01 | 2012-05-01 | 8000 | 0 | 8000 | 8000 | 100% | 0 | 0 | 0 | 1040 | 0 | 1040 | 0 | 0 | completed |  | 2002
FIN | UNEP | Establishment of a National Compliance Centre (institutional strengthening) | Individual | ASP | VAN | SEV | 36 | INS | 03 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2004-01-01 | 2005-04-01 |  | 2008-12-01 | 2009-11-01 | 20250 | 0 | 20250 | 20250 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
FIN | Australia | Implementation of the PIC Strategy: training programme for refrigeration technicians including MAC recovery and recycling equipment | Individual | ASP | VAN | REF | 36 | TAS | 04 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-04-01 | 2005-04-01 |  | 2008-06-01 | 2012-05-01 | 26000 | 0 | 26000 | 26000 | 100% | 0 | 0 | 0 | 3380 | 0 | 3380 | 0 | 0 | completed |  | 2002
FIN | UNEP | Extension of institutional strengthening project (phase II) | Individual | ASP | VAN | SEV | 54 | INS | 05 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2009-02-01 | 2009-03-01 |  | 2011-01-01 | 2011-06-01 | 6750 | 0 | 6750 | 6750 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase II, second year) | Individual | ASP | VAN | SEV | 59 | INS | 06 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-07-01 | 2010-12-01 |  | 2011-03-01 | 2011-12-01 | 32500 | 0 | 32500 | 32500 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | ASP | VAN | SEV | 62 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-07-01 | 2012-12-01 |  | 2013-12-01 | 2013-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
FIN | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, first tranche, Vanuatu) | Multi-Year | ASP | VAN | PHA | 63 | TAS | 09 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-08-01 | 2015-03-01 |  | 2016-12-01 | 2017-12-01 | 76250 | 0 | 76250 | 76250 | 100% | 0 | 0 | 0 | 9913 | 0 | 9913 | 0 | 0 | [7 empty] | 2021-12-01 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase IV: 1/2013-12/2014) | Individual | ASP | VAN | SEV | 67 | INS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2013-03-01 | 2014-12-01 |  | 2014-12-01 | 2015-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
FIN | UNEP | Extension of institutional strengthening project (phase V: 1/2015-12/2016) | Individual | ASP | VAN | SEV | 72 | INS | 11 | A | I |  | 0 |  | 0 |  | 2014-05-01 | 2015-04-01 | 2016-12-01 |  | 2018-06-01 | 2018-12-01 | 60000 | 0 | 60000 | 60000.21 | 100% | -0.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
ONG | UNEP | HCFC phase-out management plan for PIC countries through regional approach (stage I, second tranche, Vanuatu) | Multi-year | ASP | VAN | PHA | 74 | TAS | 12 | A | I |  | 0.1 |  | 0 |  | 2015-05-01 | 2017-01-01 | 2020-05-01 | 2020-12-01 |  |  | 57400 | 0 | 57400 | 40859 | 71.18% | 16541 | 16541 | 40859 | 7462 | 0 | 5311.67 | 2150.33 | 2150.33 | The SSFA was signed in February 2016. The first payment was released to the country in January 2017. The second payment was released to the country in April 2019. NOU continued to implement the licensing and quota system and conducted joint inspections with Department of Energy and Customs for all RAC equipment imported to Vanuatu. One case of CFC-12 domestic refrigerator being imported by returning citizen; the refrigerator was confiscated. The second case involved the confiscation of 44 x R-22 based air-conditioners by one unregistered importer who imported without an import permit issued by NOU. The Ozone Layer Protection Act has been amended and the NOU was awaiting endorsement by Parliament. The amended Act includes banning of HCFC-based equipment. The importer was penalised and advised to comply with the national legislation. The government reviewed the national legislations taking into account the banning of HCFC based equipment and control of HFC based equipment. NOU continued to liaise with RAC sector to revive the association and worked in collaboration with the Port Vila Vocational Training Centre (PVTC) and Vanuatu Qualifications Authority (VQA) to facilitate the 1 RAC training in October 2019 for 21 participants. NOU organized 1 training workshops for customs officers for a total of 13 participants in March 2019. | The Parliament approved the Amendment Bill, which includes provision to ban the import of HCFC-based equipment. The safe handling and management of flammable and toxic refrigerants has also been included in the amendment. NOU continued to provide support to the PVTC and VAQ to sustain the RAC training. Support provided to RAC Sector and NOU continues its effort to revive the RAC Association. NOU in collaboration with the Port Vila Vocational Training Centre (PVTC) and Vanuatu Qualifications Authority (VQA) organized a RAC training workshop on Management of Refrigerants and Best Practices in February 2020 for 18 participants. | [5 empty] | 2021-12-01 | 12541 | 1630.33
FIN | UNEP | Survey of ODS alternatives at the national level | Individual | ASP | VAN | SEV | 75 | TAS | 13 | A | I |  | 0 |  | 0 |  | 2015-11-01 | 2017-03-01 | 2016-12-01 |  | 2017-09-01 | 2018-12-01 | 40000 | -5841.16 | 34158.84 | 34159 | 100% | -0.16 | 0 | 0 | 5200 | -759.35 | 4440.6708 | -0.0208 | 0 | [8 empty] | 0 | 0
ONG | UNEP | Extension of institutional strengthening project (phase VI: 1/2017-12/2018) | Individual | ASP | VAN | SEV | 77 | INS | 14 | A | I |  | 0 |  | 0 |  | 2016-12-01 | 2018-05-01 | 2018-12-01 | 2020-06-01 |  |  | 85000 | 0 | 85000 | 62736 | 73.81% | 22264 | 22264 | 62736 | 0 | 0 | 0 | 0 | 0 | The SSFA was signed in April 2018. The first payment was released to the country in May 2018. The second payment was released to the country in September 2019. The license and quota system have been effectively enforced in 2019. The iPIC tools have been effectively used through email communications with the exporting countries. The Ozone Layer Protection Act has been amended and the NOU was awaiting endorsement by Parliament. The amended Act includes controlling of HFCs as per the Kigali Amendment. The NOU also worked with Customs Department for the development of a single electronic system to facilitate data tracking by the customs including ODS. The collection of data was undertaken to report CP data for the year 2018. CP data for 2018 were reported to MLFS in April 2019. A7 data for 2018 will be reported to Ozone Secretariat by June 2019. NOO Assistant participated on one-week work attachment with the Fiji Ozone Office in January 2019 to learn the operation of the NOU and adopting suitable operating mechanisms to improve the operations/enforcement system. NOO conducted awareness programmes for 4 senior secondary schools on the island of Santo. Students in grade 11 to 13 attended the sessions. This was done in collaboration with Energy Department and Climate Change Department. During the World Ozone Day, T-shirts containing Ozone theme written on them was shared to participants, brochures were distributed. PVTC demonstrated and explained the importance of handling ODS, an interview was also done live through FM 96 to communicate the importance of the WOD to the wider public. Over 300 people participated in these events. The NOU participated at the Second Global Inter- Regional Meeting and Parallel Network Meeting for National Ozone Officers and the Twinning of NOO and Energy Policymakers for Energy Efficient and Climate-friendly Cooling in Paris, France in February 2019 and the PIC Thematic Meeting on Compliance with the Montreal Protocol Post Kigali, Twinning Workshop for the PIC Ozone and Customs Officers on Strengthening Monitoring and Enforcement Mechanism for ODS and HFC Trade Control in August 2019. NOU also participated at the Open-ended Working Group Meeting in Bangkok, Thailand in July 2019 and Meeting of the Parties in Rome, Italy in November 2019. The SSFA was amended to end in June 2020 to complete remaining activities, in accordance with the newly IS project phase VII, which was approved to start from July 2020. | The amended Ozone Layer Protection Act was finally enacted by Parliament and the NOU had commenced with the enforcement of the requirements of the law. As per the new inspection requirements under the OLP, NOU conducted 4 inspections to RAC retail outlets and 1 servicing company to check and remind importers to apply for import permits both for HCFC and HFC including import of RAC equipment. NOU continued to promote the revival of the RAC Association. Based on discussion, the industry has showed slight interest in the formation of a RAC Association. However, RAC Industry slowly showing support and NOU continued to encourage formation of a RAC Association. The collection of data was undertaken to report A7 and CP data for the year 2019. The CP data for 2019 was reported to MLFS in April 2020. NOU is in the process of submitting the A7 data to the Ozone Secretariat by June 2020. NOU also coordinated 2 customs brokers workshop in Santo and Port Vila to educate different HS codes for the HCFCs and HFCs and equipment with emphasis on the importance of proper declaration during import transactions. | [6 empty] | 17264 | 0
ONG | UNEP | Extension of institutional strengthening project (phase VII: 7/2020-6/2022) | Individual | ASP | VAN | SEV | 84 | INS | 15 | A | I |  | 0 |  | 0 |  | 2019-12-01 |  | 2022-06-01 | 2022-06-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 0 | 21250 | 0 | 0 | 0 | 0 | 0 | Newly approved project | UNEP discussed with the government to develop the workplan of the IS Project Phase VII which was used to prepare the SSFA. Following NOU confirmation on the agreement with the SSFA, the SSFA was signed in April 2020 with the starting date from 1 July 2020. The first payment will be released to country in June 2020 in line with the approval date from July 2020. | [6 empty] | 0 | 0
ONG | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Individual | ASP | VAN | PHA | 84 | TAS | 16 | A | I |  | 0 |  | 0 |  | 2019-12-01 |  | 2021-12-01 | 2021-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 0 | 7500 | 3900 | 0 | 0 | 3900 | 0 | Newly approved project | UNEP had virtual meeting with the government to explain implementation modality for verification of HCFC consumption including (i) guidelines for the verification of national HCFC consumption targets for the multi-year agreements, (ii) year covered under verification, (iii) data and supporting document required for international consultant to conduct verification and (iv) expected timeline for verification. UNEP is following-up with the NOU to prepare data from different sources, NOU, importers and Customs Department and documentations such as Bill of Lading, Commercial Invoice, packaging list and other documents as required. The Terms of Reference (ToR) for hiring the regional consultant was prepared, cleared by the management and advertised in April 2020. Although consultant was selected, the contract could not be processed due to COVID-19 pandemic related constraints until a way forward on verification could be identified. | [6 empty] | 0 | 0
FIN | UNDP | Technical assistance and training of servicing technicians in the refrigeration sector | RMP-Component | LAC | VEN | REF | 04 | TRA | 01 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-07-01 | 1992-06-01 |  | 1992-06-01 | 1997-12-01 | 30000 | -10980 | 19020 | 19020 | 100% | 0 | 0 | 0 | 3900 | -1427 | 2472.6 | 0.4 | 0 | Completed in 1992. Financially completed in 1997. |  | 1991 |  | Non-Investment
FIN | IBRD | Preparation of investment projects (1991) |  | LAC | VEN | SEV | 04 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-01 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 70419 | -57546 | 12873 | 12873 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Country programme preparation | Individual | LAC | VEN | SEV | 06 | CPG | 03 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1994-03-01 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 61591 | -36591 | 25000 | 25000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of investment projects (1992) |  | LAC | VEN | SEV | 06 | PRP | 04 | A | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-01 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 107058 | 69729 | 176787 | 176787 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Conversion of a CFC-12 polystyrene foam production facility to use hydrocarbons as blowing agent at Plásticos Molanca | Individual | LAC | VEN | FOA | 07 | INV | 05 | N | I | CFC | 259 | 259 | 0 | 0 | 1992-06-01 | 1993-06-01 | 1993-06-01 |  | 1995-12-01 | 1996-04-01 | 1300000 | -38322 | 1261678 | 1261678 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ICR issued in May/96. The final project cost amounted to about US$2 million. The overrun was absorbed by enterprise. |  |  | 1995-03-01 | INV | 0
FIN | USA | Technical assistance and demonstration project in CFC recycling in MAC |  | LAC | VEN | REF | 08 | DEM | 06 | A | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1993-10-01 |  | 1995-07-01 | 1998-09-01 | 115000 | 0 | 115000 | 115000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1992
FIN | USA | Assistance in country programme preparation |  | LAC | VEN | SEV | 08 | CPG | 07 | A | I |  | 0 |  | 0 |  | 1992-10-01 |  | 1993-10-01 |  | 1993-10-01 | 1993-10-01 | 43000 | 0 | 43000 | 43000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1992
CLO | IBRD | Replacement of CFC by HFC-134a as a refrigerant in central air conditioning units at Instituto Venezolano de los Seguros Sociales | Individual | LAC | VEN | REF | 08 | INV | 08 | N | I |  | 0 | 0 | 0 | 0 | 1992-10-01 |  | 1994-04-01 |  |  | 1995-07-01 | 851000 | -851000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Cancelled. |  |  | 1994-04-01 | INV | 0
FIN | IBRD | Replacement of CFC by HFC-134a as a refrigerant in central air conditioning units at Clínica Atlas, Hospitalización y Servicios | Individual | LAC | VEN | REF | 08 | INV | 09 | N | I | CFC | 4 | 4 | 0 | 0 | 1992-10-01 | 1996-12-01 | 1994-04-01 |  | 1997-01-01 | 1997-02-01 | 115000 | 0 | 115000 | 115000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Completed |  |  | 1997-01-01 | INV | 0
FIN | IBRD | Replacement of CFC by HFC-134a as a refrigerant in central air conditioning units at Instituto de Prevencion Social del Médico | Individual | LAC | VEN | REF | 08 | INV | 10 | N | D | CFC | 2 | 2 | 0 | 0 | 1992-10-01 | 1995-12-01 | 1994-04-01 |  | 1995-09-01 | 1997-02-01 | 69000 | 0 | 69000 | 69000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed |  |  | 1995-09-01 | INV | 0
CLO | IBRD | Replacement of CFC by HFC-134a as a refrigerant in central air conditioning units at Congreso de la Republica | Individual | LAC | VEN | REF | 08 | INV | 11 | N | D |  | 0 | 0 | 0 | 0 | 1992-10-01 |  | 1994-04-01 |  |  | 1998-05-01 | 65000 | -65000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Retroactive project physically completed, but enterprise chose not to utilize MLF funds. Funds returned to MLF. |  |  | 1995-12-01 | INV | 0
FIN | UNDP | Workshops for the recycling and banking of halons | Individual | LAC | VEN | HAL | 09 | TAS | 12 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1994-06-01 | 1997-12-01 | 26800 | -3700 | 23100 | 23100 | 100% | 0 | 0 | 0 | 3484 | -481 | 3003 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1993 |  | Non-Investment
FIN | UNDP | Institutional strengthening of FONDOIN | Individual | LAC | VEN | SEV | 09 | INS | 13 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-06-01 | 1995-12-01 |  | 1995-12-01 | 1998-12-01 | 329192 | 0 | 329192 | 329192 | 100% | 0 | 0 | 0 | 42795 | 0 | 42794.96 | 0.04 | 0 | Completed in 1995. Financially completed in 1998. |  | 1993 |  | Non-Investment
FIN | IBRD | Preparation of investment projects (1993) |  | LAC | VEN | SEV | 09 | PRP | 14 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-01 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 156200 | 23305 | 179505 | 179505 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Workshops for identification of projects in the refrigeration and air conditioning sector | Individual | LAC | VEN | REF | 09 | PRP | 15 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1994-12-01 | 1997-12-01 | 19800 | 0 | 19800 | 19800 | 100% | 0 | 0 | 0 | 2574 | 0 | 2574 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1993 |  | Investment
FIN | UNDP | Workshops on conversion and installation of new central air conditioning systems using non-ODS | RMP-Component | LAC | VEN | REF | 09 | TAS | 16 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-04-01 | 1994-03-01 |  | 1994-06-01 | 1997-12-01 | 26200 | -13000 | 13200 | 13200 | 100% | 0 | 0 | 0 | 3406 | -1690 | 1716 | 0 | 0 | Completed in 1994. Financially completed in 1997. |  | 1993 |  | Non-Investment
FIN | UNDP | Pilot programme in recovery and recycling of CFC-12 in domestic refrigeration | RMP-Component | LAC | VEN | REF | 09 | TAS | 17 | A | I | CFC | 8 | 8 | 0 | 0 | 1993-03-01 | 1994-12-01 | 1994-03-01 |  | 1996-12-01 | 1998-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1993 |  | Investment
FIN | Canada | Technical assistance in halon sector | Halon Banking | LAC | VEN | HAL | 11 | TAS | 18 | A | I |  | 0 |  | 0 |  | 1993-11-01 |  | 1997-11-01 |  | 1996-05-01 | 1996-05-01 | 414000 | -109500 | 304500 | 304500 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1993 | 2000-01-01 | Non-Inv.
FIN | IBRD | MAC factory conversion for fabrication of HFC-134a heat exchangers at Fabrica de Aparatos de Aire Acondicionado, S.A. (Faaca) | Individual | LAC | VEN | REF | 11 | INV | 19 | N | I | CFC | 0 | 0 | 0 | 0 | 1993-11-01 | 1995-06-01 | 1995-11-01 |  | 1998-02-01 | 1998-02-01 | 3480000 | -380000 | 3100000 | 3100000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project Completed |  |  | 1997-09-01 | INV | 0
FIN | IBRD | MAC factory conversion for fabrication of HFC-134a compressors and heat exchangers at Aire Acondicionado Integral, S.A. (Aaisa) | Individual | LAC | VEN | REF | 11 | INV | 20 | N | I | CFC | 11 | 11 | 0 | 0 | 1993-11-01 | 1995-12-01 | 1996-09-01 |  | 1998-06-01 | 1998-10-01 | 620000 | 3800000 | 4420000 | 4420000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete. |  |  | 1997-09-01 | INV | 0
FIN | UNDP | Finalization of the country programme | Individual | LAC | VEN | SEV | 11 | CPG | 21 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-01 | 1994-05-01 |  | 1995-06-01 | 1997-12-01 | 12000 | 0 | 12000 | 12000 | 100% | 0 | 0 | 0 | 1560 | 0 | 1560 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1993 |  | Non-Investment
FIN | IBRD | Supervision of Faaca project implementation (1994) |  | LAC | VEN | SEV | 12 | PRP | 22 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-01 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 47190 | -26845 | 20345 | 20345 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Technical mission completed project preparation during 1994. Project submitted and approved by the E.C. |  |  |  | Non-INV | 0
FIN | IBRD | Supervision of Aaisa project implementation (1994) |  | LAC | VEN | SEV | 12 | PRP | 23 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-01 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 47190 | -28772 | 18418 | 18418 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Technical mission completed project preparation during 1994. Project submitted and approved by the E.C. |  |  |  | Non-INV | 0
FIN | IBRD | Supervision of Plásticos Molanca project implementation (1994) |  | LAC | VEN | SEV | 12 | PRP | 24 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-01 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 83236 | 9685 | 92921 | 92921 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Funds utilized for finalizing project preparation and for project supervision. |  |  |  | Non-INV | 0
FIN | IBRD | Supervision of air conditioners project implementation (1994) |  | LAC | VEN | SEV | 12 | PRP | 25 | A | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-01 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 28665 | -22792 | 5873 | 5873 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Pilot programme in recovery and recycling of CFC-12 in MAC | RMP-Component | LAC | VEN | REF | 12 | DEM | 26 | A | I | CFC | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-05-01 | 1995-03-01 |  | 1995-03-01 | 1997-12-01 | 13400 | 0 | 13400 | 13400 | 100% | 0 | 0 | 0 | 1742 | 0 | 1742 | 0 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Non-Investment
FIN | USA | Technical assistance in halon-1211 management |  | LAC | VEN | HAL | 13 | DEM | 27 | A | I | HAL | 2 |  | 0 |  | 1994-07-01 |  | 1995-07-01 |  | 1995-07-01 | 1995-07-01 | 31000 | 3000 | 34000 | 34000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | USA | Demonstration project in MAC |  | LAC | VEN | REF | 13 | DEM | 28 | A | I | CFC | 25 |  | 0 |  | 1994-07-01 |  | 1995-07-01 |  | 1995-07-01 | 1998-09-01 | 53000 | 0 | 53000 | 53000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Project completed. |  | 1994
FIN | USA | Training in all ODS sectors in Venezuelan Military |  | LAC | VEN | SEV | 15 | TRA | 29 | A | I |  | 0 |  | 0 |  | 1994-12-01 | 1995-01-01 | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 40000 | 3500 | 43500 | 43500 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Completed. |  | 1994
FIN | USA | Demonstration project in the refrigeration sector |  | LAC | VEN | REF | 15 | DEM | 30 | A | I |  | 0 |  | 0 |  | 1994-12-01 | 1995-01-01 | 1995-12-01 |  | 1995-12-01 | 1998-06-01 | 67000 | 0 | 67000 | 67000 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Project completed. |  | 1994
FIN | UNDP | Preparatory assistance for the domestic and commercial refrigeration manufacturing sector | Individual | LAC | VEN | REF | 15 | PRP | 31 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-01-01 | 1995-06-01 |  | 1995-06-01 | 1997-12-01 | 40000 | 5445 | 45445 | 45445 | 100% | 0 | 0 | 0 | 5200 | 708 | 5907.85 | 0.15 | 0 | Completed in 1995. Financially completed in 1997. |  | 1994 |  | Investment
FIN | UNDP | Pilot project for recovery and recycling of CFC-12 in MAC (Phase II) | RMP-Component | LAC | VEN | REF | 15 | TAS | 32 | A | I | CFC | 75 | 75 | 0 | 0 | 1994-12-01 | 1995-05-01 | 1995-12-01 |  | 1996-12-01 | 2000-12-01 | 220000 | -13204 | 206796 | 206796 | 100% | 0 | 0 | 0 | 28600 | -1717 | 26883.48 | -0.48 | 0 | Completed in 1996. Financially completed in 2000. |  | 1994 |  | Investment
FIN | IBRD | Preparation/supervision of investment projects ODS V (Aaisa) (1995) |  | LAC | VEN | SEV | 16 | PRP | 33 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 22455 | 0 | 22455 | 22455 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | This activity is now complete. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation/supervision of investment projects ODS IV (Faaca) (1995) |  | LAC | VEN | SEV | 16 | PRP | 34 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 19121 | 0 | 19121 | 19121 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation/supervision of investment projects ODS I and II (1995) |  | LAC | VEN | SEV | 16 | PRP | 35 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 36430 | 0 | 36430 | 36430 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Preparation/supervision of investment projects (central air chillers) (1995) |  | LAC | VEN | SEV | 16 | PRP | 36 | A | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 23966 | 0 | 23966 | 23966 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Preparatory assistance for the domestic and comercial refrigeration manufacturing sector | Individual | LAC | VEN | REF | 17 | PRP | 37 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-08-01 | 1996-06-01 |  | 1996-03-01 | 1997-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | Completed in 1996. Financially completed in 1997. |  | 1995 |  | Investment
FIN | UNDP | Elimination of CFCs 11 and 12 in the manufacture of commercial refrigeration equipment at Pinova, S.A. | Individual | LAC | VEN | REF | 17 | INV | 38 | A | I | CFC | 25 | 25 | 0 | 0 | 1995-07-01 | 1996-07-01 | 1997-01-01 |  | 1999-12-01 | 2001-12-01 | 517500 | -149132 | 368368 | 368368 | 100% | 0 | 0 | 0 | 67275 | -19387 | 47887.84 | 0.16 | 0 | Completed in 1999. Financially completed in 2001. |  | 1995 | 1999-07-01 | Investment
FIN | UNDP | Conversion of CFC-12 to compressor production facilities at Vecomesa, S.A. to manufacture HFC-134a compressors | Individual | LAC | VEN | REF | 17 | INV | 39 | A | I | No_ODP | 0.7 | 0.7 | 0 | 0 | 1995-07-01 | 1997-07-01 | 1997-01-01 |  | 1999-12-01 | 2000-12-01 | 362000 | -193742 | 168258 | 168258 | 100% | 0 | 0 | 0 | 47060 | -25186 | 21873.54 | 0.46 | 0 | Completed in 1999. Financially completed in 2000. |  | 1995 | 1999-07-01 | Investment
FIN | UNDP | Elimination of CFCs 11 and 12 in the manufacture of commercial refrigeration equipment at Industrias Nutal, C.A. | Individual | LAC | VEN | REF | 17 | INV | 40 | A | I | CFC | 14.5 | 14.5 | 0 | 0 | 1995-07-01 | 1997-01-01 | 1997-01-01 |  | 2001-12-01 | 2002-03-01 | 123623 | 0 | 123623 | 123623 | 100% | 0 | 0 | 0 | 16071 | 0 | 16070.99 | 0.01 | 0 | Completed in 2001. Financially completed in 2002. |  | 1995 | 2000-12-01 | Investment
FIN | IBRD | Project preparation |  | LAC | VEN | SEV | 18 | PRP | 41 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-01 | 1996-12-01 |  | 1996-12-01 | 1996-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | Project has been dropped in FY97. |  |  |  | Non-INV | 0
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Grupo Frigilux, C.A. | Individual | LAC | VEN | REF | 18 | INV | 42 | A | I | CFC | 46 | 46 | 0 | 0 | 1995-11-01 | 1996-08-01 | 1997-05-01 |  | 1999-12-01 | 2000-12-01 | 953000 | -371693 | 581307 | 581307 | 100% | 0 | 0 | 0 | 123890 | -48320 | 75569.5856 | 0.4144 | 0 | Completed in 1999. Financially completed in 2000. |  | 1995 | 1999-09-01 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Coresmalt Valencia, C.A. | Individual | LAC | VEN | REF | 18 | INV | 43 | A | I | CFC | 65.5 | 65.5 | 0 | 0 | 1995-11-01 | 1997-01-01 | 1997-05-01 |  | 2000-09-01 | 2002-03-01 | 685330 | -6585 | 678745 | 678745 | 100% | 0 | 0 | 0 | 89093 | -856 | 88236.85 | 0.15 | 0 | Completed in 2000. Financially completed in 2002. |  | 1995 | 1997-12-01 | Investment
CLO | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of domestic refrigerators at Manufacturera de Aparatos Domésticos, S.A. (Madosa) | Individual | LAC | VEN | REF | 18 | INV | 44 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1997-06-01 | 1997-05-01 |  |  | 2001-12-01 | 230274 | -51266 | 179008 | 179008 | 100% | 0 | 0 | 0 | 29936 | -6665 | 23271.04 | -0.04 | 0 | Canceled in 1999. Financially completed in 2001. |  | 1995 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | LAC | VEN | SEV | 18 | PRP | 45 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-12-01 | 1998-12-01 | 43000 | 0 | 43000 | 43000 | 100% | 0 | 0 | 0 | 5590 | 0 | 5590 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of refrigerated display cases and bottle coolers at Neve Industrial, C.A. | Individual | LAC | VEN | REF | 19 | INV | 46 | A | I | CFC | 7.5 | 7.5 | 0 | 0 | 1996-05-01 | 1997-05-01 | 1997-11-01 |  | 1999-12-01 | 2002-03-01 | 112100 | -3498 | 108602 | 108602 | 100% | 0 | 0 | 0 | 14573 | -455 | 14118.26 | -0.26 | 0 | Completed in 1999. Financially completed in 2002. |  | 1996 | 1999-07-01 | Investment
FIN | Canada | Halon recycling and bank management (Phase II) | Halon Banking | LAC | VEN | HAL | 19 | TAS | 47 | A | I |  | 0 |  | 0 |  | 1996-05-01 | 1996-06-01 | 1998-05-01 |  | 1998-05-01 | 1998-09-01 | 352220 | -69864 | 282356 | 282356 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  | Project successfully implemented. Adjustment results from lower equipment prices and exchange rate fluctuations. |  | 1996 | 1997-06-01 | Non-Inv.
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of bottle coolers, freezers and water coolers at Tecnocongeladores Venezolanos (Tecoven), C.A. | Individual | LAC | VEN | REF | 19 | INV | 48 | A | I | CFC | 13.2 | 13.2 | 0 | 0 | 1996-05-01 | 1997-05-01 | 1997-11-01 |  | 1999-12-01 | 2001-12-01 | 190000 | -2599 | 187401 | 187401 | 100% | 0 | 0 | 0 | 24700 | -338 | 24362.13 | -0.13 | 0 | Completed in 1999. Financially completed in 2001. |  | 1996 | 1999-07-01 | Investment
FIN | UNDP | Elimination of CFC-11 and CFC-12 in the manufacture of bottle coolers, freezers and water coolers at Hielomatic, C.A. | Individual | LAC | VEN | REF | 19 | INV | 49 | A | I | CFC | 11.1 | 11.1 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  | 2000-07-01 | 2001-12-01 | 162375 | -379 | 161996 | 161996 | 100% | 0 | 0 | 0 | 21109 | -49 | 21059.48 | 0.52 | 0 | Completed in 2000. Financially completed in 2001. |  | 1996 | 1998-04-01 | Investment
FIN | UNDP | Renewal of institutional strengthening | Individual | LAC | VEN | SEV | 20 | INS | 50 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-01-01 | 1998-10-01 |  | 1998-07-01 | 1999-12-01 | 219600 | 0 | 219600 | 219600 | 100% | 0 | 0 | 0 | 28548 | 0 | 28548 | 0 | 0 | Completed in 1998. Financially completed in 1999. |  | 1996 |  | Non-Investment
FIN | UNIDO | Project formulation of investment projects in the foam sector | Individual | LAC | VEN | FOA | 21 | PRP | 51 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-04-01 | 1997-08-01 |  | 1998-12-01 | 2000-07-01 | 30000 | -927 | 29073 | 29073 | 100% | 0 | 0 |  | 3900 | -126.49 | 3774 | -0.49 | 0
FIN | UNDP | Project preparation in commercial refrigeration recovery and recycling and in the production sector | Individual | LAC | VEN | SEV | 21 | PRP | 52 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-05-01 | 1997-12-01 |  | 1999-12-01 | 2000-12-01 | 155000 | -120000 | 35000 | 35000 | 100% | 0 | 0 | 0 | 20150 | -15600 | 4550 | 0 | 0 | Completed in 1999. Financially completed in 2000. |  | 1997 | 1999-07-01 | Investment
FIN | IBRD | Project preparation |  | LAC | VEN | SEV | 21 | PRP | 53 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-01 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 | 0 | 1300 | 0 | 1300 | 0 | 0 | Project has been dropped in FY97. |  |  |  | Non-INV | 0
FIN | UNIDO | Phasing out ODS at Decocar C.A. | Individual | LAC | VEN | FOA | 22 | INV | 54 | A | I | CFC | 16.2 | 16.2 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1998-11-01 |  | 1998-12-01 | 2001-12-01 | 126614 | 0 | 126614 | 126614 | 100% | 0 | 0 |  | 16460 | -2.73 | 16457 | 0.27 | 0
FIN | Canada | Implementation of a centralized reclamation plant for recovered refrigerants in the commercial refrigeration and air-conditioning sector | Individual | LAC | VEN | REF | 22 | TAS | 55 | A | I |  | 0 |  | 0 |  | 1997-05-01 | 1997-07-01 | 1999-06-01 |  | 1999-06-01 | 1999-06-01 | 495285 | -6685 | 488600 | 488600 | 100% | 0 |  | 0 | 0 | 0 | 0 | 0 |  |  |  | 1997 |  | Non-Inv.
FIN | UNIDO | Phasing out ODS at Veniber C.A. | Individual | LAC | VEN | FOA | 22 | INV | 56 | A | I | CFC | 21.6 | 21.6 | 0 | 0 | 1997-05-01 | 1997-08-01 | 1998-11-01 |  | 1998-12-01 | 2001-09-01 | 164592 | -62 | 164530 | 164530 | 100% | 0 | 0 |  | 21397 | -41.99 | 21355 | 0.01 | 0
FIN | UNIDO | Phasing out ODS at Daniven C.A. | Individual | LAC | VEN | FOA | 22 | INV | 57 | A | I | CFC | 18 | 18 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1998-11-01 |  | 1998-12-01 | 2000-04-01 | 104030 | 0 | 104030 | 104030 | 100% | 0 | 0 |  | 13524 | -16.25 | 13508 | -0.25 | 0
FIN | UNDP | Implementation of a recovery and reclamation of refrigerants | RMP-Component | LAC | VEN | REF | 22 | TAS | 58 | A | I | CFC | 172 | 172 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1999-06-01 |  | 2003-12-01 | 2003-12-01 | 931622 | -61553 | 870069 | 870069 | 100% | 0 | 0 | 0 | 121111 | -8002 | 113108.9 | 0.1 | 0 | Completed in 2003. Financially completed in 2003. |  | 1997 | 1999-06-01 | Investment
FIN | IBRD | Country programme preparation | Individual | LAC | VEN | SEV | 04 | CPG | 59 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-01 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 30313 | -27612 | 2701 | 2701 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNDP | Institutional strengthening of FONDOIN (renewal) | Individual | LAC | VEN | SEV | 17 | INS | 60 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-01-01 | 1996-12-01 |  | 1996-12-01 | 1999-12-01 | 54900 | 54900 | 109800 | 109800 | 100% | 0 | 0 | 0 | 7137 | 7137 | 14274 | 0 | 0 | Completed in 1996. Financially completed in 1999. |  | 1995 |  | Non-Investment
FIN | UNIDO | Phasing out ODS at Industrias Todos C.A., Caracas | Individual | LAC | VEN | FOA | 23 | INV | 61 | A | I | CFC | 17.8 | 17.8 | 0 | 0 | 1997-11-01 | 1998-10-01 | 1999-06-01 |  | 1998-12-01 | 2000-04-19 | 137520 | 0 | 137520 | 137520 | 100% | 0 | 0 |  | 17878 | 0 | 17877.6 | 0.4 | 0
FIN | UNIDO | Preparation of investment project in the foam sector (rigid polyurethane) for Fanesi Barquisimeto | Individual | LAC | VEN | FOA | 24 | PRP | 62 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-09-01 | 1999-04-01 |  | 1998-09-01 | 2000-04-01 | 10000 | -56 | 9944 | 9944 | 100% | 0 | 0 |  | 1300 | -9.36 | 1291 | -0.36 | 0
FIN | UNIDO | Phasing out CFC-11 and CFC-12 with HCFC-141b and HFC-134a at Invitrel in the manufacture of commercial refrigeration equipment | Individual | LAC | VEN | REF | 25 | INV | 63 | A | I | CFC | 46.4 | 46.4 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2000-02-01 |  | 1999-12-01 | 2002-09-01 | 419094 | -1714 | 417380 | 417380 | 100% | 0 | 0 |  | 54482 | -309 | 54173 | 0 | 0
FIN | UNIDO | Phasing out CFC-11 with HCFC-141b at Tecnofrigo in the production of rigid PU panels | Individual | LAC | VEN | FOA | 25 | INV | 64 | A | I | CFC | 9 | 9 | 0 | 0 | 1998-07-01 | 1999-11-01 | 1999-08-01 |  | 2001-01-01 | 2002-09-01 | 71946 | 0 | 71946 | 71946 | 100% | 0 | 0 |  | 9353 | -13 | 9340 | 0 | 0 |  |  |  | 2000-11-01
FIN | UNDP | Renewal of institutional strengthening | Individual | LAC | VEN | SEV | 25 | INS | 65 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-08-01 | 2000-07-01 |  | 2000-07-01 | 2001-12-01 | 219600 | 0 | 219600 | 219600 | 100% | 0 | 0 | 0 | 28548 | 0 | 28548 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Non-Investment
FIN | UNIDO | Phasing out CFC-11 with HCFC-141b at Liderfrio in the production of rigid polyurethane panels | Individual | LAC | VEN | FOA | 26 | INV | 66 | A | I | CFC | 13.9 | 13.9 | 0 | 0 | 1998-11-01 | 1999-12-01 | 2000-04-01 |  | 2000-12-01 | 2002-09-01 | 107850 | 0 | 107850 | 107850 | 100% | 0 | 0 |  | 14021 | -7 | 14014 | 0 | 0
FIN | UNIDO | Workshops on alternatives to methyl bromide in tobacco cultivation | Individual | LAC | VEN | FUM | 27 | TRA | 67 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-07-01 | 1999-12-01 |  | 1999-11-01 | 2001-03-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 5200 | -2.21 | 5198 | -0.21 | 0
FIN | UNIDO | Preparation of investment project in the foam sector (rigid polyurethane) | Individual | LAC | VEN | FOA | 27 | PRP | 68 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-11-01 | 1999-12-01 |  | 2000-06-01 | 2001-07-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | -2.08 | 1298 | -0.08 | 0
CLO | UNDP | Preparation of one project in refrigeration MAC and compressors subsector | Individual | LAC | VEN | REF | 27 | PRP | 69 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 |  | 2000-04-01 |  |  | 2002-03-01 | 30000 | -30000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 3900 | -3900 | 0 | 0 | 0 | Canceled in 1999. Financially Completed in 2002. |  | 1999 |  | Investment
FIN | UNIDO | Preparation of investment project in the foam sector (integral skin) | Individual | LAC | VEN | FOA | 27 | PRP | 70 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-08-01 | 1999-12-01 |  | 2000-12-01 | 2002-01-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0
FIN | UNIDO | Preparation of investment projects in the commercial refrigeration sector | Individual | LAC | VEN | REF | 27 | PRP | 71 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-09-01 | 1999-12-01 |  | 2000-10-01 | 2001-10-01 | 25000 | -325 | 24675 | 24675 | 100% | 0 | 0 |  | 3250 | -47.32 | 3203 | -0.32 | 0
FIN | UNIDO | Preparation of investment project in the foam sector (polystyrene/polyethylene) | Individual | LAC | VEN | FOA | 27 | PRP | 72 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 1999-12-01 |  | 2000-12-01 | 2002-05-01 | 20000 | -37 | 19963 | 19963 | 100% | 0 | 0 |  | 2600 | -8.97 | 2591 | 0.03 | 0
FIN | UNIDO | Phasing out CFC-11 with HCFC-141b in the production of rigid polyurethane panels at Fricava, C.A. | Individual | LAC | VEN | FOA | 27 | INV | 73 | A | I | CFC | 15.3 | 15.3 | 0 | 0 | 1999-03-01 | 1999-12-01 | 2000-08-01 |  | 2000-12-01 | 2002-09-01 | 115382 | 0 | 115382 | 115382 | 100% | 0 | 0 |  | 15000 | -10 | 14990 | 0 | 0
FIN | UNIDO | Phasing out of CFC-11 by 100% water blown system in the production of molded integral skin flexible polyurethane foam at Fanesi | Individual | LAC | VEN | FOA | 27 | INV | 74 | A | I | CFC | 11.4 | 11.4 | 0 | 0 | 1999-03-01 | 1999-06-01 | 2000-08-01 |  | 2001-06-01 | 2002-12-01 | 157882 | 0 | 157882 | 157882 | 100% | 0 | 0 |  | 20525 | 0 | 20524.66 | 0.34 | 0
FIN | UNIDO | Preparation of investment projects in the refrigeration/MACS and compressors sector | Individual | LAC | VEN | REF | 27 | PRP | 75 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-12-01 | 1999-12-01 |  | 2000-09-01 | 2002-09-01 | 20000 | -113 | 19887 | 19887 | 100% | 0 | 0 |  | 2600 | -19 | 2581 | 0 | 0
FIN | UNIDO | Umbrella project for phasing out CFC-12 with HFC-134a and CFC-11 with HCFC-141b at 5 commercial refrigeration companies: Unidas, Inrefrisa, Cold Front, Refrivenca and Europa | Individual | LAC | VEN | REF | 29 | INV | 76 | A | I | CFC | 30.9 | 30.9 | 0 | 0 | 1999-11-01 | 2000-11-01 | 2001-12-01 |  | 2001-12-01 | 2003-10-01 | 469140 | -64008 | 405132 | 405132 | 100% | 0 | 0 |  | 60988 | -8404.5 | 52584 | -0.5 | 0
FIN | UNIDO | Phasing out CFC-11 with HCFC-141b in the production of rigid polyurethane panels at Novemeca | Individual | LAC | VEN | FOA | 29 | INV | 77 | A | I | CFC | 16.2 | 16.2 | 0 | 0 | 1999-11-01 | 2000-01-01 | 2001-06-01 |  | 2000-11-01 | 2002-09-01 | 69886 | -632 | 69254 | 69254 | 100% | 0 | 0 |  | 9085 | -96 | 8989 | 0 | 0
FIN | UNIDO | Phasing out CFC-11 with HCFC-141b in the production of rigid polyurethane panels at Amerio Industrial, S.A. | Individual | LAC | VEN | FOA | 29 | INV | 78 | A | I | CFC | 11.8 | 11.8 | 0 | 0 | 1999-11-01 | 2000-06-01 | 2001-06-01 |  | 2001-07-01 | 2002-09-01 | 88039 | -173 | 87866 | 87866 | 100% | 0 | 0 |  | 11445 | -40 | 11405 | 0 | 0
FIN | UNIDO | Umbrella project for phasing out CFC-12 with HFC-134a and CFC-11 with HCFC-141b at 3 domestic refrigeration companies: Nordpol, Friocon and Tecobar | Individual | LAC | VEN | REF | 29 | INV | 79 | A | I | CFC | 27 | 27 | 0 | 0 | 1999-11-01 | 2000-11-01 | 2001-12-01 |  | 2001-12-01 | 2003-10-01 | 371705 | -75965 | 295740 | 295740 | 100% | 0 | 0 |  | 48322 | -9937.42 | 38385 | -0.42 | 0
FIN | UNIDO | Preparation of investment project in the rigid foam sector | Individual | LAC | VEN | FOA | 30 | PRP | 80 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-05-01 | 2001-04-01 |  | 2001-04-01 | 2002-05-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0
FIN | UNIDO | Preparation of investment project in the commercial refrigeration sector | Individual | LAC | VEN | REF | 30 | PRP | 81 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-11-01 | 2001-04-01 |  | 2002-06-01 | 2003-10-01 | 20000 | -124 | 19876 | 19876 | 100% | 0 | 0 |  | 2600 | -20.15 | 2580 | -0.15 | 0
FIN | UNIDO | Phasing out CFC-12 at Fandec C.A. (EPSR Foam) | Individual | LAC | VEN | FOA | 28 | INV | 82 | A | I | CFC | 45 | 45 | 0 | 0 | 1999-07-01 | 1999-11-01 | 2001-08-01 |  | 2003-12-01 | 2004-07-01 | 290481 | 0 | 290481 | 290481 | 100% | 0 | 0 |  | 37763 | -15.17 | 37748 | -0.17 | 0
CLO | UNIDO | Phasing out CFC-11 with HCFC-141b at Friobox in the production of rigid P.U. panels | Individual | LAC | VEN | FOA | 31 | INV | 83 | A | I | CFC | 16.5 | 1.1 | 0 | 0 | 2000-07-01 | 2001-12-01 | 2002-01-01 |  |  | 2003-05-01 | 128387 | -119558 | 8829 | 8829 | 100% | 0 | 0 |  | 16690 | -15544.36 | 1146 | -0.36 | 0
FIN | UNIDO | Phasing out CFC-11 with HCFC-141b at Nevecor in the production of rigid P.U. panels | Individual | LAC | VEN | FOA | 31 | INV | 84 | A | I | CFC | 36.4 | 36.4 | 0 | 0 | 2000-07-01 | 2001-12-01 | 2002-01-01 |  | 2002-11-01 | 2003-12-01 | 198374 | 0 | 198374 | 198374 | 100% | 0 | 0 |  | 25789 | -13 | 25776 | 0 | 0
FIN | UNIDO | Preparation of investment project in the refrigeration sector (domestic/commercial) | Individual | LAC | VEN | REF | 31 | PRP | 85 | A | I |  | 0 | 0 | 0 | 0 | 2000-07-01 | 2000-11-01 | 2002-05-01 |  | 2002-06-01 | 2003-05-01 | 30000 | -238 | 29762 | 29762 | 100% | 0 | 0 |  | 3900 | -37.05 | 3863 | -0.05 | 0
FIN | UNIDO | Strategy for the preparation of an RMP | RMP | LAC | VEN | REF | 31 | TAS | 86 | A | I |  | 0 | 0 | 0 | 0 | 2000-07-01 | 2001-03-01 | 2001-07-01 |  | 2002-12-01 | 2003-10-01 | 70000 | -2912 | 67088 | 67088 | 100% | 0 | 0 |  | 9100 | -392.34 | 8708 | -0.34 | 0 |  |  |  |  | NON-INV
FIN | UNDP | Renewal of institutional strengthening (Phase IV) | Individual | LAC | VEN | SEV | 31 | INS | 87 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2000-07-01 | 2000-08-01 | 2002-08-01 |  | 2002-12-01 | 2004-02-01 | 219600 | 0 | 219600 | 219600 | 100% | 0 | 0 | 0 | 28548 | 0 | 28548 | 0 | 0 | Completed in 2002. Financially completed in 2004. |  | 2000 |  | Non-Investment
FIN | UNIDO | Phasing out CFC-12 with HFC-134a and CFC-11 with HCFC-141b at 7 commercial refrigeration companies (Vikingo, Eterna, Indarelca, J.R. Refrigeración, Inelmem, Couttenye and Refrinaza) | Individual | LAC | VEN | REF | 32 | INV | 88 | A | I | CFC | 32.3 | 32.3 | 0 | 0 | 2000-12-01 | 2001-10-01 | 2003-01-01 |  | 2005-05-01 | 2005-12-01 | 403590 | -84678 | 318912 | 318912 | 100% | 0 | 0 |  | 52467 | -11073.92 | 41393 | 0.08 | 0
FIN | UNIDO | Project preparation for 2 umbrella projects in the rigid foam sector | Individual | LAC | VEN | FOA | 33 | PRP | 89 | A | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-06-01 | 2002-04-01 |  | 2002-12-01 | 2003-12-01 | 20000 | -227 | 19773 | 19773 | 100% | 0 | 0 |  | 2600 | -33.54 | 2566 | 0.46 | 0 |  |  |  |  | INV
FIN | UNEP | Review of ODS license system and Decree 3220 related to control of these substances | Individual | LAC | VEN | SEV | 34 | TAS | 90 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2002-12-01 |  | 2005-12-01 | 2011-03-01 | 80000 | -40619 | 39381 | 39381 | 100% | 0 | 0 | 0 | 10400 | -5280.47 | 5119.53 | 0 | 0 | [8 empty] | 0 | 0
FIN | UNIDO | Phasing out CFC-11 by conversion to HCFC-141b as a blowing agent in the manufacture of rigid polyurethane foams (Umbrella No. 1) (Frimac, Frizer, El Control, Incumaca, Frive, Lunger, Profibra, Recovenca, Refriven, Requiven, Tefiven and Vanger) | Individual | LAC | VEN | FOA | 34 | INV | 91 | A | I | CFC | 62.8 | 53.6 | 0 | 0 | 2001-07-01 | 2001-11-01 | 2003-08-01 |  | 2003-12-01 | 2005-02-01 | 438017 | -71323 | 366694 | 366694 | 100% | 0 | 0 |  | 56942 | -9347 | 47595 | 0 | 0 |  |  |  |  | INV
FIN | UNEP | Training of customs officers | Individual | LAC | VEN | REF | 34 | TRA | 92 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2003-12-01 |  | 2005-12-01 | 2009-12-01 | 120000 | -12164 | 107836 | 107836 | 100% | 0 | 0 | 0 | 15600 | -1581 | 14019 | 0 | 0 | [8 empty] | 0 | 0
FIN | UNIDO | Preparation of a national ODS phase-out plan | Individual | LAC | VEN | PHA | 36 | PRP | 93 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-03-01 | 2003-07-01 |  | 2004-04-01 | 2004-12-01 | 95000 | 0 | 95000 | 95000 | 100% | 0 | 0 |  | 12350 | -12 | 12338 | 0 | 0 |  |  |  |  | INV
FIN | UNIDO | Phasing out CFC-11 by conversion to water system as a blowing agent in the manufacture of flexible polyurethane foams at Manufacturas Enveta, C.A. Cumana | Individual | LAC | VEN | FOA | 36 | INV | 94 | A | I | CFC | 32 | 32 | 0 | 0 | 2002-03-01 | 2003-12-01 | 2004-03-01 |  | 2004-06-01 | 2004-12-01 | 198882 | 0 | 198882 | 198882 | 100% | 0 | 0 |  | 25855 | -15 | 25840 | 0 | 0 |  |  |  |  | INV
FIN | UNDP | Renewal of institutional strengthening project (Phase 6) | Individual | LAC | VEN | SEV | 37 | INS | 95 | N | I | No_ODP | 23.6 | 23.6 | 0 | 0 | 2002-07-01 | 2003-01-01 | 2004-08-01 |  | 2004-12-01 | 2007-07-01 | 285480 | -981 | 284499 | 284499 | 100% | 0 | 0 | 0 | 37112 | -127 | 36985.4 | -0.4 | 0 | Completed in 2004. Financially completed in 2007. |  | 2002 |  | Non-Investment
FIN | UNIDO | Phasing out CFC-11 by conversion to HCFC-141b as a blowing agent in the manufacture of rigid polyurethane foams (umbrella project No. 2) | Individual | LAC | VEN | FOA | 38 | INV | 96 | A | I | CFC | 135.5 | 135.5 | 0 | 0 | 2002-11-01 | 2003-04-01 | 2004-12-01 |  | 2005-03-01 | 2006-05-01 | 851432 | -86779 | 764653 | 764653 | 100% | 0 | 0 |  | 103658 | -9679.01 | 93979 | -0.01 | 0 |  |  |  |  | INV
FIN | IBRD | Project preparation for the CFC production phase out project |  | LAC | VEN | PRO | 41 | PRP | 97 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2003-12-01 | 2004-12-01 |  | 2004-04-01 | 2004-04-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 3000 | 0 | 3000 | 0 | 0 | Project was prepared and subsequently approved at the 44th ExCom in Dec. 04. |  |  |  | Non-INV | 0
FIN | UNIDO | National CFC phase-out plan: 2004 work programme | Multi-Year | LAC | VEN | PHA | 42 | INV | 98 | A | I | CFC | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2005-04-01 |  | 2006-09-01 | 2008-05-01 | 1895062 | 0 | 1895062 | 1895062 | 100% | 0 | 0 |  | 142130 | 0 | 142129.65 | 0.35 | 0 |  |  |  |  | INV
FIN | UNDP | Extension of the institutional strengthening project (phase VII) | Individual | LAC | VEN | SEV | 43 | INS | 99 | N | I | No_ODP | 23.6 | 23.6 | 0 | 0 | 2004-07-01 | 2005-01-01 | 2006-07-01 |  | 2007-12-01 | 2011-12-01 | 285480 | 0 | 285480 | 285480 | 100% | 0 | 0 | 0 | 21411 | 0 | 21411 | 0 | 0 | Completed in 2007. Financially completed in 2011. |  | 2004 |  | Non-Investment
FIN | IBRD | Phased reduction and closure of the entire CFC production: 2004 annual programme | Multiyear | LAC | VEN | PRO | 44 | INV | 101 | N | I | CFC | 0 | 0 | 1469 | 1469 | 2004-12-01 | 2005-12-01 | 2005-12-01 |  | 2005-12-01 | 2009-11-01 | 3300000 | 0 | 3300000 | 3300000 | 100% | 0 | 0 | 0 | 247500 | 0 | 247500 | 0 | 0 | Latest production audit for CY09 took place in Dec 09 to verify production closure of CFC-11/12. Based on onsite audit there was no production of CFC-11 nor CFC-12, and no consumption of CTC in 2009. Consumption of HF and CHCL33 were in line with HCFC-22 production standards, as was consumption of HCl with levels of HCFC-22 production and HF consumption. CFC production terminated in Dec 06. Operational and financial reports indicate that Produven only produced HCFC-22 in 2009. Final verification report was submitted to the 59th ExCom. |  |  |  | INV | 0
FIN | UNDP | Assistance to carry out an HCFC survey | Individual | LAC | VEN | SEV | 45 | TAS | 102 | A | I | HCFC | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-04-01 | 2006-12-01 |  | 2008-08-01 | 2009-12-01 | 45872 | -27909 | 17963 | 17963 | 100% | 0 | 0 | 0 | 4128 | -2512 | 1616.482 | -0.482 | 0 | Completed in 2008. Financially completed in 2009. |  | 2005 |  | Non-Investment
FIN | UNIDO | Training and awareness workshop in the process agents (TCA) sector | Individual | LAC | VEN | SOL | 45 | TAS | 103 | A | I | TCA | 1.9 | 1.9 | 0 | 0 | 2005-04-01 | 2006-04-01 | 2006-04-01 |  | 2006-12-01 | 2007-12-01 | 40000 | -1005 | 38995 | 38995 | 100% | 0 | 0 |  | 3600 | -90 | 3509.55 | 0.45 | 0 |  |  |  |  | INV
FIN | UNIDO | Training and awareness workshop in the fumigants sector (methyl bromide) | Individual | LAC | VEN | FUM | 45 | TAS | 104 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-07-01 | 2006-04-01 |  | 2007-12-01 | 2008-08-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 |  | 3600 | 0 | 3600 | 0 | 0 |  |  |  |  | NON-INV
FIN | UNIDO | National CFC phase-out plan: 2005 work programme | Multi-Year | LAC | VEN | PHA | 45 | INV | 105 | A | I | CFC | 50 | 50 | 0 | 0 | 2005-04-01 | 2006-11-01 | 2006-04-01 |  | 2007-07-01 | 2010-05-01 | 1631831 | 0 | 1631831 | 1631831 | 100% | 0 | 0 |  | 122387 | 0 | 122387.325 | -0.325 | 0 |  |  |  | 2007-12-01 | INV
FIN | IBRD | National CFC production closure plan (second tranche) | Multiyear | LAC | VEN | PRO | 46 | INV | 106 | N | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-09-01 | 2006-07-01 |  | 2006-04-01 | 2009-11-01 | 8100000 | 0 | 8100000 | 8100000 | 100% | 0 | 0 | 0 | 607500 | 0 | 607500 | 0 | 0 | Latest production audit for CY09 took place in Dec 09 to verify production closure of CFC-11/12. Based on onsite audit there was no production of CFC-11 nor CFC-12, and no consumption of CTC in 2009. Consumption of HF and CHCL33 were in line with HCFC-22 production standards, as was consumption of HCl with levels of HCFC-22 production and HF consumption. CFC production terminated in Dec 06. Operational and financial reports indicate that Produven only produced HCFC-22 in 2009. Final verification report was submitted to the 59th ExCom. |  |  |  | INV | 0
FIN | IBRD | National CFC production closure plan (third tranche) | Multiyear | LAC | VEN | PRO | 48 | INV | 107 | N | I | CFC | 0 | 0 | 2931 | 2931 | 2006-04-01 | 2006-08-01 | 2007-04-01 |  | 2007-04-01 | 2009-11-01 | 1750000 | 0 | 1750000 | 1750000 | 100% | 0 | 0 | 0 | 131200 | 0 | 131200 | 0 | 0 | Latest production audit for CY09 took place in Dec 09 to verify production closure of CFC-11/12. Based on onsite audit there was no production of CFC-11 nor CFC-12, and no consumption of CTC in 2009. Consumption of HF and CHCL33 were in line with HCFC-22 production standards, as was consumption of HCl with levels of HCFC-22 production and HF consumption. CFC production terminated in Dec 06. Operational and financial reports indicate that Produven only produced HCFC-22 in 2009. Final verification report was submitted to the 59th ExCom. |  |  |  | INV | 0
FIN | UNDP | Renewal of institutional strengthening project (phase VIII) | Individual | LAC | VEN | SEV | 49 | INS | 108 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2006-07-01 | 2007-02-01 | 2008-07-01 |  | 2008-12-01 | 2011-10-01 | 285480 | -1 | 285479 | 285479 | 100% | 0 | 0 | 0 | 21411 | 0 | 21410.925 | 0.07505 | 0 | Completed in 2008. |  | 2006 |  | Non-Investment
FIN | UNIDO | National CFC phase-out plan: 2006 work programme | Multi-Year | LAC | VEN | PHA | 51 | INV | 109 | A | I | CFC | 0 | 0 | 0 | 0 | 2007-03-01 | 2007-09-01 | 2008-03-01 |  | 2011-12-01 | 2012-12-01 | 2071831 | -285.8 | 2071545.2 | 2071545.2 | 100% | 0 | 0 |  | 155387 | -21 | 155365.89 | 0.11 | 0 |  |  |  |  | INV
FIN | IBRD | National CFC production closure plan (fourth tranche) | Multiyear | LAC | VEN | PRO | 52 | INV | 110 | N | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-09-01 | 2008-07-01 |  | 2009-01-01 | 2009-11-01 | 2300000 | 0 | 2300000 | 2300000 | 100% | 0 | 0 | 0 | 172500 | 0 | 172500 | 0 | 0 | Latest production audit for CY09 took place in Dec 09 to verify production closure of CFC-11/12. Based on onsite audit there was no production of CFC-11 nor CFC-12, and no consumption of CTC in 2009. Consumption of HF and CHCL33 were in line with HCFC-22 production standards, as was consumption of HCl with levels of HCFC-22 production and HF consumption. CFC production terminated in Dec 06. Operational and financial reports indicate that Produven only produced HCFC-22 in 2009. Final verification report was submitted to the 59th ExCom. |  |  |  | INV | 0
FIN | IBRD | National CFC production closure plan (fifth tranche) | Multiyear | LAC | VEN | PRO | 54 | INV | 111 | N | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-10-01 | 2009-03-01 |  | 2008-12-01 | 2009-11-01 | 1050000 | 0 | 1050000 | 1050000 | 100% | 0 | 0 | 0 | 78700 | 0 | 78700 | 0 | 0 | Latest production audit for CY09 took place in Dec 09 to verify production closure of CFC-11/12. Based on onsite audit there was no production of CFC-11 nor CFC-12, and no consumption of CTC in 2009. Consumption of HF and CHCL33 were in line with HCFC-22 production standards, as was consumption of HCl with levels of HCFC-22 production and HF consumption. CFC production terminated in Dec 06. Operational and financial reports indicate that Produven only produced HCFC-22 in 2009. Final verification report was submitted to the 59th ExCom. |  |  |  | INV | 0
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | LAC | VEN | PHA | 55 | PRP | 112 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-10-01 | 2009-07-01 |  | 2011-12-01 | 2012-12-01 | 173750 | -718.47 | 173031.53 | 173031.53 | 100% | 0 | 0 |  | 13031 | -54 | 12977.3648 | -0.36475 | 0 |  |  |  |  | NON-INV
FIN | UNDP | Renewal of institutional strengthening project (phase IX) | Individual | LAC | VEN | SEV | 56 | INS | 113 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-01-01 | 2010-12-01 |  | 2010-12-01 | 2013-02-01 | 285480 | -2637 | 282843 | 282843 | 100% | 0 | 0 | 0 | 21411 | -198 | 21213.225 | -0.225 | 0 | Financially completed in 2013. |  | 2008 |  | Non-Investment
FIN | UNIDO | National CFC phase-out plan: 2009 work programme | Multi-Year | LAC | VEN | PHA | 57 | INV | 114 | A | I | CFC | 985 | 985 | 0 | 0 | 2009-04-01 | 2009-12-01 | 2010-03-01 |  | 2012-06-01 | 2013-12-01 | 513465 | -461.51 | 513003.49 | 513003.49 | 100% | 0 | 0 |  | 38510 | -35 | 38475.2617 | -0.26175 | 0 |  |  |  |  | INV
FIN | UNIDO | Preparation for HCFC phase-out investment activities (foam sector) | Individual | LAC | VEN | FOA | 60 | PRP | 115 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-08-01 | 2011-04-01 |  | 2011-12-01 | 2013-10-01 | 100000 | -56.16 | 99943.84 | 99943.84 | 100% | 0 | 0 |  | 7500 | -4 | 7495.788 | 0.212 | 0
FIN | UNIDO | Preparation for HCFC phase-out investment activities (refrigeration and air conditioning manufacturing sector) | Individual | LAC | VEN | REF | 60 | PRP | 116 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-06-01 | 2011-04-01 |  | 2011-12-01 | 2013-10-01 | 100000 | -783.18 | 99216.82 | 99216.82 | 100% | 0 | 0 |  | 7500 | -59 | 7441.2615 | -0.2615 | 0
FIN | UNDP | Renewal of institutional strengthening project (phase X) | Individual | LAC | VEN | SEV | 62 | INS | 117 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2010-12-01 | 2011-04-01 | 2012-12-01 |  | 2013-03-01 | 2014-12-01 | 285480 | -22556 | 262924 | 262924 | 100% | 0 | 0 | 0 | 21411 | -1692 | 19719 | 0 | 0 | Financially completed in 2014. |  | 2010 |  | Non-Investment
FIN | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | VEN | PHA | 63 | INV | 118 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-07-01 | 2012-03-01 |  | 2015-12-01 | 2017-05-17 | 654854 | -579 | 654275 | 654275.2 | 100% | -0.2 | 0 |  | 49114 | -43 | 49070.64 | 0.36 | 0 |  |  |  |  | INV |  |  | 2016-12-01
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | LAC | VEN | PHA | 63 | TAS | 119 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-11-01 | 2012-03-01 |  | 2014-12-01 | 2014-12-01 | 50646 | -39968 | 10678 | 10678 | 100% | 0 | 0 | 0 | 6584 | -5196 | 1388 | 0 | 0 | [7 empty] | 2016-12-01 | 0 | 0
FIN | UNIDO | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | VEN | PHA | 67 | INV | 120 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 | 2013-06-01 | 2013-07-01 |  | 2015-12-01 | 2017-03-01 | 603339 | -1196.46 | 602142.54 | 602142.55 | 100% | -0.01 | -0.01 |  | 45250 | -89 | 45160.6913 | 0.30875 | -0.00075 |  |  |  |  | INV |  |  | 2016-12-01
TRF | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | LAC | VEN | PHA | 67 | TAS | 121 | A | I |  | 0 | 0 | 0 | 0 | 2012-07-01 |  | 2013-07-01 |  |  | 2014-12-01 | 46661 | -46661 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 6066 | -6066 | 0 | 0 | 0 | [7 empty] | 2016-12-01 | 0 | 0
FIN | UNDP | Renewal of institutional strengthening project (phase XI: 1/2013-12/2014) | Individual | LAC | VEN | SEV | 68 | INS | 122 | N | I | HCFC | 0 | 0 | 0 | 0 | 2012-12-01 | 2013-04-01 | 2014-12-01 |  | 2014-12-01 | 2015-12-01 | 285480 | -24 | 285456 | 285456 | 100% | 0 | 0 | 0 | 19984 | -2 | 19982.32 | -0.32 | 0 | Financially completed in 2015. |  | 2012 |  | Non-investment
TRF | UNEP | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | LAC | VEN | PHA | 70 | TAS | 123 | A | I |  | 0 |  | 0 |  | 2013-07-01 |  | 2015-07-01 |  |  | 2014-12-01 | 25125 | -25125 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 3266 | -3266 | 0 | 0 | 0 | [7 empty] | 2016-12-01 | 0 | 0
FIN | UNIDO | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | LAC | VEN | PHA | 70 | INV | 124 | A | I | HCFC | 4 | 4 | 0 | 0 | 2013-07-01 | 2014-04-01 | 2015-07-01 |  | 2015-12-01 | 2016-04-01 | 324875 | 0 | 324875 | 324875 | 100% | 0 | 0 |  | 24366 | 0 | 24365.625 | 0.375 | 0 |  |  |  |  | INV |  |  | 2016-12-01
FIN | UNIDO | Preparation for HCFC phase-out investment activities (stage II) (refrigeration manufacturing sector) | Individual | LAC | VEN | REF | 72 | PRP | 125 | A | I |  | 0 | 0 | 0 | 0 | 2014-05-01 | 2014-12-01 | 2015-05-01 |  | 2016-12-01 | 2017-07-01 | 50000 | -1462.09 | 48537.91 | 48537.91 | 100% | 0 | 0 |  | 3500 | -102 | 3397.6537 | 0.3463 | 0 |  |  |  |  | NON-INV
FIN | UNDP | Preparation for HCFC phase-out investment activities (stage II) (foam sector) | Individual | LAC | VEN | FOA | 72 | PRP | 126 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-05-01 | 2014-12-01 | 2016-05-01 |  | 2016-12-01 | 2018-12-01 | 150000 | -13991 | 136009 | 136009 | 100% | 0 | 0 | 0 | 10500 | -979 | 9520.6265 | 0.3735 | 0 | Financially completed in 2018. |  |  |  | Non-Investment
FIN | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | Individual | LAC | VEN | PHA | 72 | PRP | 127 | A | I |  | 0 | 0 | 0 | 0 | 2014-05-01 | 2014-08-01 | 2015-05-01 |  | 2016-12-01 | 2017-08-01 | 90000 | -1535.25 | 88464.75 | 88464.74 | 100% | 0.01 | 0.01 |  | 6300 | -107 | 6192.5318 | 0.4682 | 0.0007 |  |  |  |  | NON-INV
FIN | UNDP | Renewal of institutional strengthening project (phase XII: 1/2015-12/2016) | Individual | LAC | VEN | SEV | 73 | INS | 128 | N | I | HCFC | 0 | 0 | 0 | 0 | 2014-11-01 | 2015-12-01 | 2016-12-01 |  | 2017-12-01 | 2018-12-01 | 285480 | -107028 | 178452 | 178452 | 100% | 0 | 0 | 0 | 19984 | -7492 | 12491.8578 | 0.14216 | 0 | Financially completed in 2018. |  | 2014 |  | Non-Investment
FIN | UNIDO | Survey of ODS alternatives at the national level | Individual | LAC | VEN | SEV | 74 | TAS | 129 | A | I |  | 0 | 0 | 0 | 0 | 2015-05-01 | 2016-07-01 | 2016-05-01 |  | 2017-12-01 | 2018-06-25 | 130000 | -5625 | 124375 | 124375.11 | 100% | -0.11 | 0 |  | 11700 | -506 | 11193.7599 | 0.2401 | 0 |  |  |  |  | NON-INV
FIN | UNIDO | HCFC phase-out management plan (stage I, transfer first, second third tranche from UNEP) | Multi-Year | LAC | VEN | PHA | 75 | TAS | 130 | A | I | HCFC | 0.3 | 0.3 | 0 | 0 | 2015-11-01 | 2016-04-01 | 2017-12-01 |  | 2017-12-01 | 2018-11-27 | 111754 | 0 | 111754 | 111753.99 | 100% | 0.01 | 0.01 |  | 8381 | 0 | 8381 | 0 | 0.00075 |  |  |  |  | INV |  |  | 2016-12-01
FIN | UNIDO | HCFC phase-out management plan (stage I, fourth tranche) | Multi-Year | LAC | VEN | PHA | 75 | INV | 131 | A | I | HCFC | 19 | 19.03 | 0 | 0 | 2015-11-01 | 2016-04-01 | 2017-12-01 |  | 2018-05-18 | 2019-03-27 | 189000 | -4444 | 184556 | 184556.04 | 100% | -0.04 | 0 | 0 | 14175 | -333 | 13841.703 | 0.297 | 0 | Project was financially closed in March 2019. Funds were returned at the 83rd meeting in May 2019. | N/A |  |  | INV |  |  | 2016-12-01
ONG | UNIDO | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) | Multi-Year | LAC | VEN | PHA | 76 | TAS | 132 | A | I |  | 0 | 0 | 0 | 0 | 2016-05-01 | 2017-04-01 | 2019-12-01 | 2021-12-21 |  |  | 355000 | 0 | 355000 | 228173.25 | 64.27% | 126826.75 | 0 | 1 | 24850 | 0 | 15972.1275 | 8877.8725 | 0 | Demonstration of R-290 based chiller carried out successfully. Small local activities implemented like training and workshops for customs and technicians. Milestones achieved: Trainings organized: Yes Actions towards next goals: Was there any delay during the reporting year? YES Any recurring problem? YES Any impact on project completion date: YES Any action required by Executive Committee? No | No project activities during the present year. It is not possible to implement the projects due to political instability. |  |  | INV |  |  | 2021-12-01
CLO | UNDP | HCFC phase-out management plan (stage II, first tranche) (foam sector) | Multi-Year | LAC | VEN | PHA | 76 | INV | 133 | N | I | HCFC | 2.4 | 0 | 0 | 0 | 2016-05-01 |  | 2019-05-01 |  |  | 2018-12-01 | 76420 | -76420 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 5349 | -5349 | 0 | 0 | 0 | Remarks1 - up to 31 Dec 2018: Project cancelled due to economic constrains of the beneficiary companies. |  |  |  | Investment |  |  | 2021-12-01
ONG | UNIDO | HCFC phase-out management plan (stage II, first tranche) (technical assistance in refrigeration and air-conditioning manufacturing sector) | Multi-Year | LAC | VEN | PHA | 76 | INV | 134 | A | I | HCFC | 3.2 | 3.2 | 0 | 0 | 2016-05-01 | 2016-08-01 | 2019-12-01 | 2021-12-21 |  |  | 245000 | 0 | 245000 | 157474.06 | 64.28% | 87525.94 | 5758.71 | 11200 | 17150 | 0 | 11023.1842 | 6126.8158 | 403.1097 | Study tour was carried out. Nine participants visited different centers like reclaiming, foam, training and factories in Colombia during 10 days. Participants from Fondoin and technical staff also attended. Some R-290 air conditioners were purchased and delivered to the country. Actions towards next goals: Was there any delay during the reporting year? YES Any recurring problem? YES Any impact on project completion date: YES Any action required by Executive Committee? No | No project activities during the present year due to the overall political situation in the country. |  |  | INV |  |  | 2021-12-01
COM | UNDP | Renewal of institutional strengthening project (phase XIII: 1/2017-12/2018) | Individual | LAC | VEN | SEV | 77 | INS | 135 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2016-12-01 | 2017-03-01 | 2018-12-01 |  | 2019-03-01 |  | 365414 | 0 | 365414 | 340419 | 93.16% | 24995 | 21556.11 | 17496.423 | 25579 | 0 | 23829.3563 | 1749.6437 | 1508.9289 | Institutional strengthening activities conducted, follow up to Multilateral Fund-financed projects portfolio; HCFC quota distributed among interested importers. CP anf Art. 7 reports prepared and submitted to MLFS and Ozone Secretariat, respectively. |  | 2016 |  | Non-Investment
ONG | UNDP | Renewal of institutional strengthening project (phase XIV: 1/2019-12/2020) | Individual | LAC | VEN | SEV | 82 | INS | 136 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2018-12-01 | 2019-03-01 | 2020-12-01 | 2021-04-01 |  |  | 365414 | 0 | 365414 | 12133 | 3.32% | 353281 | 0 | 105984.3 | 25579 | 0 | 849.3107 | 24729.6893 | 0 | Project document signed. Workplan and procurement plan reviewed and agreed by NOU and UNDP. 2019 Ozone day celebration conducted. Awareness rising activities carried out. | Standard IS activities being implemented (licensing and quota system, awareness raising campaign, collaboration with customs, etc.). Due to COVID-19, NOU is working from home with some communication limitations. | 0 |  | Non-Investment
FIN | UNDP | Project preparation assistance | Individual | ASP | VIE | SEV | 12 | PRP | 01 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-04-01 | 1995-03-01 |  | 1996-06-01 | 1998-12-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1994 |  | Investment
FIN | UNEP | Country programme preparation | Individual | ASP | VIE | SEV | 13 | CPG | 02 | A | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-11-01 | 1995-10-01 |  | 1996-05-01 | 1996-10-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | [8 empty] | 0 | 0
FIN | France | Country programme preparation |  | ASP | VIE | SEV | 13 | CPG | 03 | A | D |  | 0 |  | 0 |  | 1994-07-01 | 1994-08-01 | 1995-07-01 |  | 1995-07-01 | 1995-07-01 | 30000 | -8965 | 21035 | 21035 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed
FIN | UNIDO | Phasing out ODS at the Searefico and Searee industrial refrigeration plants of Seaprodex Co. | Individual | ASP | VIE | REF | 15 | INV | 04 | A | I | CFC | 40 | 40 | 0 | 0 | 1994-12-01 | 1995-12-01 | 1996-06-01 |  | 1996-12-01 | 2000-07-01 | 497070 | -2690 | 494380 | 494380 | 100% | 0 | 0 |  | 64619 | -451.62 | 64167 | 0.38 | 0
FIN | UNIDO | Preparation of project proposals for the reduction of refrigerant emission and establishment of collection and reclaiming network in domestic refrigeration sector | Individual | ASP | VIE | REF | 15 | PRP | 05 | A | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-09-01 | 1995-06-01 |  | 1996-12-01 | 1998-08-01 | 15000 | -14776 | 224 | 224 | 100% | 0 | 0 |  | 1950 | -1920.88 | 29.12 | -1.1369e-13 | 0
FIN | UNIDO | Preparation of investment project for reduction of refrigerant emissions and conversion of food processing and other industrial refrigeration and A/C equipment to suitable alternatives | Individual | ASP | VIE | REF | 15 | PRP | 06 | A | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1995-05-01 | 1995-06-01 |  | 1996-12-01 | 1998-08-01 | 20000 | -11168 | 8832 | 8832 | 100% | 0 | 0 |  | 2600 | -1453.66 | 1146 | 0.34 | 0
FIN | UNDP | Conversion to hydrocarbon aerosol propellant technology at Saigon Cosmetics Company | Individual | ASP | VIE | ARS | 17 | INV | 07 | A | I | CFC | 80 | 80 | 0 | 0 | 1995-07-01 | 1995-12-01 | 1996-12-01 |  | 1998-08-01 | 2000-12-01 | 238430 | -2439 | 235991 | 235991 | 100% | 0 | 0 | 0 | 30996 | -317 | 30678.83 | 0.17 | 0 | Completed in 1998. Financially completed in 2000. |  | 1995 |  | Investment
FIN | UNEP | Establishment of the ozone unit (institutional strengthening) | Individual | ASP | VIE | SEV | 17 | INS | 08 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-05-01 | 1998-07-01 |  | 1999-04-01 | 1999-11-01 | 137280 | 0 | 137280 | 137280 | 100% | 0 | 0 | 0 | 17846 | 0 | 17846 | 0 | 0 |  |  |  | 1999-12-01 |  |  |  |  | 0 | 0
FIN | UNEP | Technology cooperation workshop for ODS elimination | Individual | ASP | VIE | SEV | 17 | TRA | 09 | A | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-09-01 | 1995-12-01 |  | 1996-06-01 | 1999-04-01 | 27000 | 0 | 27000 | 27000 | 100% | 0 | 0 | 0 | 3510 | 0 | 3510 | 0 | 0 | [8 empty] | 0 | 0
FIN | UNDP | Conversion to CFC-free hydrocarbon aerosol propellant technology at Daso Company Ltd. | Individual | ASP | VIE | ARS | 18 | INV | 10 | A | I | CFC | 27 | 27 | 0 | 0 | 1995-11-01 | 1996-12-01 | 1996-11-01 |  | 1999-12-01 | 2001-08-01 | 110340 | -320 | 110020 | 110020 | 100% | 0 | 0 | 0 | 14344 | -42 | 14302.6 | -0.6 | 0 | Completed in 1999. Financially completed in 2001. |  | 1995 | 1999-06-01 | Investment
FIN | UNDP | Conversion to hydrocarbon aerosol propellant technology at Cosmetics Producing and Trading Company (CP & T) | Individual | ASP | VIE | ARS | 18 | INV | 11 | A | I | CFC | 85 | 85 | 0 | 0 | 1995-11-01 | 1997-05-01 | 1997-05-01 |  | 2002-05-01 | 2003-11-01 | 285120 | -2641 | 282479 | 282479 | 100% | 0 | 0 | 0 | 37066 | -343 | 36722.27 | 0.73 | 0 | Completed in 2002. Financially completed in 2003. |  | 1995 | 1999-09-01 | Investment
FIN | France | Technical assistance on alternative technologies for cold storage facilities and project preparation |  | ASP | VIE | REF | 20 | TAS | 12 | A | I |  | 0 |  | 0 |  | 1996-10-01 | 1996-11-01 | 1997-10-01 |  | 1998-09-01 | 1999-05-01 | 40000 | -5500 | 34500 | 34500 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed
FIN | UNDP | Demonstration project in CFC recycling and emissions reduction in the commercial refrigeration sector | RMP-Component | ASP | VIE | REF | 20 | DEM | 13 | A | I | CFC | 28.2 | 28.2 | 0 | 0 | 1996-10-01 | 1999-10-01 | 1998-09-01 |  | 2002-12-01 | 2004-09-01 | 168216 | -10238 | 157978 | 157978 | 100% | 0 | 0 | 0 | 21868 | -1331 | 20537.1449 | -0.1449 | 0 | Completed in 2002. Financially completed in 2004. |  | 1996 | 2000-07-01 | Non-Investment
FIN | Australia | Demonstration project CFC recycling and emissions reduction in the commercial refrigeration sector | Individual | ASP | VIE | REF | 20 | DEM | 14 | A | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1999-10-01 | 1997-12-01 |  | 2001-12-01 | 2005-06-01 | 282687 | -42162 | 240525 | 240525 | 100% | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Completed |  | 1996 | 1997-12-01
FIN | USA | MAC servicing demonstration project |  | ASP | VIE | REF | 20 | DEM | 15 | A | I |  | 0 |  | 0 |  | 1996-10-01 | 1997-03-01 | 1998-12-01 |  | 1998-12-01 | 1998-12-01 | 300000 | -159091 | 140909 | 140909 | 100% | 0 |  | 0 | 0 | 0 |  | 0 |  | Terminated. |  | 1996 | 1998-12-01
FIN | UNIDO | Project formulation in the methyl bromide sector | Individual | ASP | VIE | FUM | 22 | PRP | 16 | A | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1997-07-01 |  | 1999-01-01 | 2001-07-01 | 8000 | -624 | 7376 | 7376 | 100% | 0 | 0 |  | 1040 | -82.68 | 957 | 0.32 | 0 |  |  |  | 1999-02-01
CLO | UNDP | Project preparation in the domestic refrigeration sub-sector | Individual | ASP | VIE | REF | 22 | PRP | 17 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1997-05-01 |  | 1997-12-01 |  |  | 1998-07-01 | 25000 | -25000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 3250 | -3250 | 0 | 0 | 0 | Canceled in 1998. Financially Completed in 1998. |  | 1997 |  | Investment
FIN | UNEP | Assistance for formulation of a refrigerant management plan | RMP | ASP | VIE | REF | 23 | PRP | 18 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1998-11-01 |  | 2001-07-01 | 2002-07-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 |  |  |  | 1999-12-01 |  |  |  |  | 0 | 0
FIN | UNDP | Project preparation for one project in the aerosol sector | Individual | ASP | VIE | ARS | 24 | PRP | 19 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-08-01 | 1998-12-01 |  | 2000-12-01 | 2001-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1998 |  | Investment
FIN | UNIDO | Alternatives to the use of methyl bromide on stacked bags of rice, grain in silos, and timber on a warehouse under tarps at Vietnam Fumigation Company | Individual | ASP | VIE | FUM | 24 | DEM | 20 | A | I | MBR | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-11-01 | 2000-04-01 |  | 2003-12-01 | 2004-12-01 | 411180 | -9744 | 401436 | 401436 | 100% | 0 | 0 |  | 53453 | -1349 | 52104 | 0 | 0
FIN | UNDP | Preparation of two projects in general foam subsector | Individual | ASP | VIE | FOA | 27 | PRP | 21 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-05-01 | 2000-04-01 |  | 2000-12-01 | 2001-12-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2000. Financially completed in 2001. |  | 1999 |  | Investment
FIN | France | CFC emission reductions in spinning halls air conditioning systems chillers (pilot project) |  | ASP | VIE | REF | 28 | INV | 22 | A | I | CFC | 3.6 | 3.6 | 0 |  | 1999-07-01 | 2001-06-01 | 2001-08-01 |  | 2002-12-01 | 2002-12-01 | 197340 | 0 | 197340 | 197340 | 100% | 0 |  |  | 0 | 0 | 0 | 0 |  | Project completed |  |  | 2002-12-01
FIN | UNIDO | Technical assistance in preparation of the national halon bank management programme | Individual | ASP | VIE | HAL | 29 | TAS | 23 | A | I | HAL | 37.1 | 37.1 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2000-12-01 |  | 2003-01-01 | 2003-12-01 | 25000 | -7148 | 17852 | 17852 | 100% | 0 | 0 |  | 3250 | -932.88 | 2317 | 0.12 | 0 |  |  |  |  | INV
FIN | UNDP | Preparation of a project in the foam general sector | Individual | ASP | VIE | FOA | 30 | PRP | 24 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2001-07-01 | 2003-01-01 | 20000 | -625 | 19375 | 19375 | 100% | 0 | 0 | 0 | 2600 | -81 | 2518.75 | 0.25 | 0 | Completed in 2001. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Preparation of a project in the aerosol sector | Individual | ASP | VIE | ARS | 30 | PRP | 25 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2000-12-01 | 2003-01-01 | 10000 | -2192 | 7808 | 7808 | 100% | 0 | 0 | 0 | 1300 | -285 | 1015.04 | -0.04 | 0 | Completed in 2000. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNDP | Preparation of a project in the refrigeration recycling subsector | Individual | ASP | VIE | REF | 30 | PRP | 26 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-04-01 | 2001-04-01 |  | 2000-12-01 | 2003-01-01 | 5000 | -1096 | 3904 | 3904 | 100% | 0 | 0 | 0 | 650 | -142 | 507.52 | 0.48 | 0 | Completed in 2000. Financially completed in 2003. |  | 2000 |  | Investment
FIN | UNEP | Renewal of institutional strengthening (phase II) | Individual | ASP | VIE | SEV | 28 | INS | 27 | A | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 1999-10-01 | 2001-08-01 |  | 2001-06-01 | 2001-12-01 | 91520 | 0 | 91520 | 91520 | 100% | 0 | 0 | 0 | 11898 | 0 | 11898 | 0 | 0 |  |  |  | 2001-06-01 |  |  |  |  | 0 | 0
FIN | UNDP | Phase-out of CFC-12 in the manufacture of perfumes by conversion to hydrocarbon propellants at Nam Do Corporation | Individual | ASP | VIE | ARS | 31 | INV | 28 | A | I | CFC | 11.3 | 11.3 | 0 | 0 | 2000-07-01 | 2002-10-01 | 2003-08-01 |  | 2005-06-01 | 2008-10-01 | 49720 | 0 | 49720 | 49720 | 100% | 0 | 0 | 0 | 6464 | 0 | 6463.6 | 0.4 | 0 | Completed in 2005. Financially completed in 2008. |  | 2000 |  | Investment
FIN | UNDP | Preparation of a refrigerant recycling project | Individual | ASP | VIE | REF | 33 | PRP | 29 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-07-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 650 | 0 | 650 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNEP | Renewal of the institutional strengthening project (Phase III) | Individual | ASP | VIE | SEV | 33 | INS | 30 | A | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-08-01 | 2003-04-01 |  | 2003-07-01 | 2004-07-01 | 91520 | 0 | 91520 | 91520 | 100% | 0 | 0 | 0 | 11898 | 0 | 11898 | 0 | 0 | [8 empty] | 0 | 0
FIN | UNDP | Project preparation in the aerosol sector | Individual | ASP | VIE | ARS | 33 | PRP | 31 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-11-01 | 2002-04-01 |  | 2002-12-01 | 2003-07-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | Completed in 2002. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNDP | Project preparation in the foam sector | Individual | ASP | VIE | FOA | 33 | PRP | 32 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-07-01 | 2003-07-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 650 | 0 | 650 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNEP | Implementation of the RMP: workshop for finalization of regulations | Individual | ASP | VIE | REF | 34 | TAS | 33 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2001-10-01 |  | 2002-01-01 | 2003-06-01 | 4350 | 0 | 4350 | 4350 | 100% | 0 | 0 | 0 | 566 | 0 | 566 | 0 | 0 | [8 empty] | 0 | 0
TRF | Australia | Implementation of the RMP: programme for recovery and recycling of CFC-12 refrigerant | Individual | ASP | VIE | REF | 34 | TAS | 34 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 |  | 2003-08-01 |  |  | 2001-12-01 | 290413 | -290413 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 37754 | -37754 | 0 | 0 | 0 | Transferred to UNDP- 35th ExCom |  | 2001
FIN | UNDP | Implementation of the RMP: MAC recovery and recycling of CFC-12 refrigerant | RMP-Component | ASP | VIE | REF | 34 | TAS | 35 | A | I | CFC | 5.8 | 5.8 | 0 | 0 | 2001-07-01 | 2002-12-01 | 2003-08-01 |  | 2003-08-01 | 2007-01-01 | 50500 | 0 | 50500 | 50500 | 100% | 0 | 0 | 0 | 6565 | 0 | 6565 | 0 | 0 | Completed in 2003. Financially completed in 2007. |  | 2001 |  | Non-Investment
FIN | UNEP | Implementation of the RMP: train the trainer programme in the refrigeration servicing sector | Individual | ASP | VIE | REF | 34 | TRA | 36 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-10-01 | 2003-08-01 |  | 2003-12-01 | 2006-02-01 | 200000 | -40959 | 159041 | 159041 | 100% | 0 | 0 | 0 | 26000 | -5324.67 | 20675.33 | 0 | 0 | [8 empty] | 0 | 0
FIN | Poland | Implementation of the RMP: Customs training programme | RMP Update | ASP | VIE | REF | 34 | TAS | 37 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 |  | 2003-01-01 |  | 2003-01-01 |  | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 13000 | 0 | 13000 | 0 | 0 | Reason for delays in completion of Phase I of the Project was a delay in the payment of Polish contribution covering a cost of the project because of problems with national budget. Payment of outstanding contribution was confirmed through a letter of 21 March 2002 from the UN Office in Nairobi (CP/4040-01-71).
FIN | UNDP | Implementation of the RMP: Monitoring the activities in the RMP | RMP-Component | ASP | VIE | REF | 34 | TAS | 38 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-07-01 | 2004-01-01 | 2004-08-01 |  | 2004-12-01 | 2007-01-01 | 21600 | -242 | 21358 | 21358 | 100% | 0 | 0 | 0 | 2808 | -31 | 2776.54 | 0.46 | 0 | Completed in 2004. Financially completed in 2007. |  | 2001 |  | Non-Investment
FIN | UNDP | Implementation of the RMP: Programme for recovery and recycling of CFC-12 refrigerant | RMP-Component | ASP | VIE | REF | 35 | TAS | 39 | A | I | CFC | 17 | 17 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2005-01-01 |  | 2004-12-01 | 2007-03-01 | 290413 | -22502 | 267911 | 267911 | 100% | 0 | 0 | 0 | 37754 | -2925 | 34828.716 | 0.284 | 0 | Completed in 2004. Financially completed in 2007. |  | 2001 |  | Non-Investment
FIN | UNDP | Terminal umbrella project for the aerosol sector to phase-out ODS consumption in the manufacture of aerosols and perfumes by conversion to hydrocarbon propellant (Dong A and Thorakao Cosmetics Ltd.) | Individual | ASP | VIE | ARS | 37 | INV | 40 | A | I | CFC | 28.5 | 28.5 | 0 | 0 | 2002-07-01 | 2003-02-01 | 2005-04-01 |  | 2005-06-01 | 2007-03-01 | 125400 | 0 | 125400 | 125400 | 100% | 0 | 0 | 0 | 16302 | 0 | 16302 | 0 | 0 | Completed in 2005. Financially completed in 2007. |  | 2002 |  | Investment
FIN | IBRD | Preparation of a national CFC phase-out plan |  | ASP | VIE | PHA | 39 | PRP | 41 | A | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-12-01 | 2004-09-01 |  | 2004-09-01 | 2004-11-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 4500 | 0 | 4500 | 0 | 0 | Project preparation completed and project approved at the 45th ExCom. |  |  |  | Non-INV | 0
FIN | UNEP | Extension of institutional strengthening project | Individual | ASP | VIE | SEV | 40 | INS | 42 | A | I | CFC | 9.8 | 10.2 | 0 | 0 | 2003-07-01 | 2004-01-01 | 2005-07-01 |  | 2005-07-01 | 2007-12-01 | 118976 | -20 | 118956 | 118956 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
FIN | IBRD | Project preparation for methyl bromide phase-out plan |  | ASP | VIE | FUM | 44 | PRP | 44 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-12-01 | 2005-12-01 |  | 2006-11-01 | 2006-11-01 | 65000 | 0 | 65000 | 65000 | 100% | 0 | 0 | 0 | 4875 | 0 | 4875 | 0 | 0 | Project prepared, submitted and approved at the 50th ExCom Meeting. |  |  |  | Non-INV | 0
FIN | IBRD | National CFC and halon phase-out plan (first tranche) | Multiyear | ASP | VIE | PHA | 45 | INV | 45 | N | I | CFC | 40 | 40 | 0 | 0 | 2005-04-01 | 2006-11-01 | 2007-04-01 |  | 2008-07-01 | 2011-02-01 | 495537 | 0 | 495537 | 495537 | 100% | 0 | 0 | 0 | 37165 | 0 | 37165 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | UNEP | Renewal of institutional strengthening project (phase V) | Individual | ASP | VIE | SEV | 46 | INS | 46 | A | I |  | 0 | 0 | 0 | 0 | 2005-07-01 | 2005-08-01 | 2007-07-01 |  | 2007-07-01 | 2007-12-01 | 118976 | 0 | 118976 | 118976 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
FIN | IBRD | National CFC and halon phase-out plan (second tranche) | Multiyear | ASP | VIE | PHA | 49 | INV | 47 | N | I | CFC | 165 | 165 | 0 | 0 | 2006-07-01 | 2008-12-01 | 2007-07-01 |  | 2009-06-01 | 2011-02-01 | 586000 | 0 | 586000 | 586000 | 100% | 0 | 0 | 0 | 43950 | 0 | 43950 | 0 | 0 | Project completed. |  |  |  | INV | 0
FIN | IBRD | National phase-out plan of out methyl bromide (first tranche) | Multiyear | ASP | VIE | FUM | 50 | INV | 48 | N | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2009-12-01 | 2007-11-01 |  | 2011-11-01 | 2014-12-01 | 230000 | 0 | 230000 | 230000 | 100% | 0 | 0 | 0 | 17250 | 0 | 17250 | 0 | 0 | National MB Phase-out Plan completed. |  |  |  | INV | 0
FIN | UNEP | Extension of institutional strengthening project (phase VI) | Individual | ASP | VIE | SEV | 52 | INS | 49 | A | I |  | 0 | 0 | 0 | 0 | 2007-07-01 | 2007-12-01 | 2009-06-01 |  | 2009-06-01 | 2009-06-01 | 118976 | 0 | 118976 | 118976 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
FIN | IBRD | Preparation of a HCFC phase-out management plan |  | ASP | VIE | PHA | 55 | PRP | 50 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2010-12-01 | 2009-12-01 |  | 2011-03-01 | 2011-06-01 | 195000 | 0 | 195000 | 195000 | 100% | 0 | 0 | 0 | 14625 | 0 | 14625 | 0 | 0 | Fully completed and disbursed. Project approved at the 63rd Meeting. |  |  |  | Non-INV | 0
FIN | IBRD | National CFC and halon phase-out plan (third tranche) | Multiyear | ASP | VIE | PHA | 55 | INV | 51 | N | I | CFC | 58.7 | 58.7 | 0 | 0 | 2008-07-01 | 2009-12-01 | 2010-07-01 |  | 2010-12-01 | 2011-02-01 | 178463 | -551.92 | 177911.08 | 177911 | 100% | 0.08 | 0 | 0 | 13385 | -41.4 | 13344 | -0.4 | 0 | Project physically and financially completed. Unused amount of US$552 returned. |  |  |  | INV | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VII) | Individual | ASP | VIE | SEV | 57 | INS | 52 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2009-08-01 | 2011-06-01 |  | 2011-06-01 | 2011-11-01 | 118976 | 0 | 118976 | 118976 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
FIN | IBRD | National phase-out plan of out methyl bromide (second tranche) | Multiyear | ASP | VIE | FUM | 59 | INV | 53 | N | I | MBR | 5.2 | 5.2 | 0 | 0 | 2009-11-01 | 2011-12-01 | 2011-11-01 |  | 2012-12-01 | 2014-12-01 | 650000 | 0 | 650000 | 650000 | 100% | 0 | 0 | 0 | 48750 | 0 | 48750 | 0 | 0 | National MB Phase-out Plan completed. |  |  |  | INV | 0
FIN | IBRD | Preparation of a HCFC foam sector plan |  | ASP | VIE | FOA | 60 | PRP | 54 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-12-01 | 2011-04-01 |  | 2011-04-01 | 2011-06-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 7500 | 0 | 7500 | 0 | 0 | Fully completed and disbursed. Foam sector plan and HPMP approved at the 63rd ExCom. |  |  |  | Non-INV | 0
FIN | IBRD | Preparation of a HCFC refrigeration sector plan |  | ASP | VIE | REF | 60 | PRP | 55 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-12-01 | 2011-04-01 |  | 2011-04-01 | 2011-04-01 | 100000 | 0 | 100000 | 100000 | 100% | 0 | 0 | 0 | 7500 | 0 | 7500 | 0 | 0 | Fully completed and disbursed. ExCom asked that the AC component be removed from the proposed HPMP and action plan at its 63rd meeting. |  |  |  | Non-INV | 0
FIN | IBRD | HCFC phase-out management plan (stage I, first tranche) (foam sector plan) | Multiyear | ASP | VIE | PHA | 63 | INV | 56 | N | I | HCFC | 44.7 | 44.7 | 0 | 0 | 2011-04-01 | 2013-12-01 | 2012-03-01 |  | 2017-06-01 | 2017-10-01 | 2832518 | 0 | 2832518 | 2832518 | 100% | 0 | 0 | 0 | 212439 | 0 | 212439 | 0 | 0 | Stage I HPMP completed physically and financially. | Project completed. |  |  | INV | 0 |  | 2016-12-01
FIN | UNEP | Extension of the institutional strengthening project (phase VIII) | Individual | ASP | VIE | SEV | 63 | INS | 57 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2011-11-01 | 2013-06-01 |  | 2013-06-01 | 2014-06-01 | 118976 | 0 | 118976 | 118976 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
FIN | IBRD | HCFC phase-out management plan (stage I, first tranche) (Technical assistance and project management) | Multiyear | ASP | VIE | PHA | 63 | TAS | 58 | N | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2013-12-01 | 2012-12-01 |  | 2017-06-01 | 2017-10-01 | 221905 | 0 | 221905 | 221905 | 100% | 0 | 0 | 0 | 16643 | 0 | 16643 | 0 | 0 | Stage I HPMP completed physically and financially. | Project completed. |  |  | Non-INV | 0 |  | 2016-12-01
FIN | IBRD | National phase-out plan of methyl bromide (third tranche) | Multiyear | ASP | VIE | FUM | 65 | INV | 59 | N | I | MBR | 10 | 10 | 0 | 0 | 2011-11-01 | 2012-12-01 | 2013-11-01 |  | 2013-11-01 | 2014-12-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 | 0 | 0 | 9000 | 0 | 9000 | 0 | 0 | National MB Phase-out Plan completed. |  |  |  | INV | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IX: 7/2013-6/2015) | Individual | ASP | VIE | SEV | 68 | INS | 60 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2014-06-01 | 2015-06-01 |  | 2015-06-01 | 2016-12-01 | 118976 | 0 | 118976 | 118976 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
FIN | IBRD | National phase-out plan of methyl bromide (fourth tranche) | Multiyear | ASP | VIE | FUM | 70 | INV | 61 | N | I | MBR | 20 | 20 | 0 | 0 | 2013-07-01 | 2013-12-01 | 2014-07-01 |  | 2014-12-01 | 2014-12-01 | 58284 | 0 | 58284 | 58284 | 100% | 0 | 0 | 0 | 4371 | 0 | 4371 | 0 | 0 | National MB Phase-out Plan completed. |  |  |  | INV | 0
FIN | IBRD | HCFC phase-out management plan (stage I, second tranche) (foam sector plan) | Multiyear | ASP | VIE | PHA | 71 | INV | 62 | N | I | HCFC | 89.4 | 89.4 | 0 | 0 | 2013-12-01 | 2014-12-01 | 2015-12-01 |  | 2017-06-01 | 2017-10-01 | 5663016 | -511837 | 5151179 | 5151179 | 100% | 0 | 0 | 0 | 424726 | -38388 | 386338 | 0 | 0 | Stage I HPMP completed physically and financially. | Project completed. |  |  | INV | 0 |  | 2016-12-01
FIN | IBRD | Preparation for HCFC phase-out investment activities (stage II) (air-conditioning sector) |  | ASP | VIE | REF | 72 | PRP | 63 | A | I |  | 0 | 0 | 0 | 0 | 2014-05-01 | 2015-12-01 | 2016-05-01 |  | 2016-05-01 | 2016-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 4200 | 0 | 4200 | 0 | 0 | AC sector plan prepared, included in the Stage II HPMP and submitted end Jan 16. Project approved in May 2016. | Stage II AC sector plan completed and approved. |  |  | Non-INV | 0
FIN | IBRD | Preparation for HCFC phase-out investment activities (stage II) (refrigeration sector) |  | ASP | VIE | REF | 72 | PRP | 64 | A | I |  | 0 | 0 | 0 | 0 | 2014-05-01 | 2015-12-01 | 2016-05-01 |  | 2016-05-01 | 2016-12-01 | 60000 | 0 | 60000 | 60000 | 100% | 0 | 0 | 0 | 4200 | 0 | 4200 | 0 | 0 | Refrigeration sector plan prepared, included in the Stage II HPMP and submitted end Jan 16. Only part of the refrigeration sector plan was approved in May 2016. | Stage II partial refrigeration sector plan completed and approved. |  |  | Non-INV | 0
FIN | IBRD | Preparation of a HCFC phase-out management plan (stage II) |  | ASP | VIE | PHA | 72 | PRP | 65 | A | I |  | 0 | 0 | 0 | 0 | 2014-05-01 | 2014-12-01 | 2016-05-01 |  | 2016-07-01 | 2017-12-01 | 90000 | 0 | 90000 | 90000 | 100% | 0 | 0 | 0 | 6300 | 0 | 6300 | 0 | 0 | WB new Grant Agreement preparation mission conducted in Mar 17 which included discussion on implementation/funding modalities, project implementation procedures, safeguards and others. Balance of preparation funds disbursed. | Preparation completed. |  |  | Non-INV | 0
FIN | IBRD | Preparation for HCFC phase-out investment activities (stage II) (foam sector) |  | ASP | VIE | FOA | 72 | PRP | 66 | A | I |  | 0 | 0 | 0 | 0 | 2014-05-01 | 2015-12-01 | 2016-05-01 |  | 2016-05-01 | 2016-12-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 | 0 | 5600 | 0 | 5600 | 0 | 0 | PU foam sector plan including XPS, systems house and multiple subsectors using imported HCFC-based preblended polyol prepared, included in the Stage II HPMP and submitted end Jan 16. Project approved in May 2016. | Stage II foam sector plan completed and approved. |  |  | Non-INV | 0
FIN | IBRD | National phase-out plan of methyl bromide (fifth tranche) | Multiyear | ASP | VIE | FUM | 72 | INV | 67 | N | I | MBR | 50 | 50 | 0 | 0 | 2014-05-01 | 2014-12-01 | 2015-05-01 |  | 2014-12-01 | 2014-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 3000 | 0 | 3000 | 0 | 0 | National MB Phase-out Plan completed. |  |  |  | INV | 0
FIN | UNEP | Extension of the institutional strengthening project (phase X: 7/2015-6/2017) | Individual | ASP | VIE | SEV | 73 | INS | 68 | A | I |  | 0 |  | 0 |  | 2014-11-01 | 2016-05-01 | 2017-06-01 |  | 2017-07-01 | 2018-12-01 | 118976 | 0 | 118976 | 118976 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
FIN | IBRD | Survey of ODS alternatives at the national level | Individual | ASP | VIE | SEV | 75 | TAS | 69 | A | I |  | 0 | 0 | 0 | 0 | 2015-11-01 | 2016-12-01 | 2016-12-01 |  | 2017-11-01 | 2017-11-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 4050 | 0 | 4050 | 0 | 0 | Revised versions of survey submitted Jan and Feb 17 and discussions held mid-Mar 17 with NOU/PMU and consultant. ODS alternative survey report is under finalization for submission to the 79th ExCom. | Survey submitted to the 80th ExCom, as well as to the CCAC (as an HFC Inventory) which provided $84,000 in funding. |  |  | Non-INV | 0
ONG | IBRD | HCFC phase-out management plan (stage II, first tranche) (polyurethane rigid foam sector) | Multiyear | ASP | VIE | PHA | 76 | INV | 70 | N | I | HCFC | 5.4 |  | 0 | 0 | 2016-05-01 | 2019-08-01 | 2017-12-01 | 2020-12-01 |  |  | 396095 | -93358 | 302737 | 167348.97 | 55.28% | 135388.03 | 135388.03 | 135388.03 | 27727 | -6535 | 11714.58 | 9477.42 | 9477.42 | Overall project approved by the WB in Jan 19 after internal GoV approval. Grant Agreement signed and countersigned on 7th Mar 19. Project implementation manual (PIM) cleared in Apr 19, PMU was fully staffed by Aug 19, and disbursement started thereafter. Kick-off workshop held in Sep. 16. Contracts awarded to firms to determine enterprise eligibility, conduct technical and financial subproject appraisal, and help enterprises prepare and implement subprojects. Contracts awarded to individual consultants to provide TA to industrial refrigeration end-users, train-the-trainer training, selection and distribution of toolkits to vocational center/schools and servicing shops, development of training curriculum on R&AC using flammable refrigerants and development of a national standard for using flammable blowing agents in foam production. Consumption verification consultant for 2016-18 also selected and consumption verification implemented. Two technical workshops held in Nov 19 to inform 19 enterprises total about MLF support and subproject requirements. Memorandum of Understanding for cooperation and strengthening of vocational schools' capacity was signed with the Directorate of Vocational Education and Training in Dec 19, and initial communication established with Customs to agree on required training activities. | Subproject proposal submissions for target manufacturing sectors (A/C, PU foam and refrigeration) have experienced delays due to slow response rates. WB mission in Feb 20 met 7 enterprises to help support a way forward. As a result, project disbursement procedures (including in PIM) under revision to reflect more realistic grant disbursement schedules to enterprises. An MOU between DCC and the General Department of Customs signed in Feb 20. Consumption verification for 2019 conducted. Arrangements for implementing Japan TA on R-32 in AC manufacturing agreed by Apr 20. Consultants are assisting 6 enterprises develop subprojects in foam, refrigeration and AC sectors and subgrant agreement signing expected by Jun 20. Six training events for Customs officers, servicing sector trainers, and servicing technicians planned for 2020 with a total of 180 persons targeted. Procurement packages expected to be accomplished in Q3 2020 include: trainer training material; training curriculum on handling flammable refrigerants for vocational technicians; review, assessment and selection of toolkits for vocational schools/centers and service shops; development of draft technical standard for flammable blowing agent use in foam manufacturing for review and submission to MONRE. By Q3 2020, contract on Japanese TA for AC manufacturers; TA to identify potential eligible enterprises for subprojects; and, independent financial audit for 2019-21 all will be initiated. |  |  | INV |  |  | 2022-12-01
ONG | Japan | HCFC phase-out management plan (stage II, first tranche) (refrigeration servicing sector) |  | ASP | VIE | PHA | 76 | TAS | 71 | A | I | HCFC-22 | 0.5 |  | 0 |  | 2016-05-01 |  | 2017-12-01 | 2020-12-01 |  |  | 43250 | 0 | 43250 | 0 | 0% | 43250 | 43250 | 10000 | 5623 | 0 | 0 | 5623 | 5623 | Overarching grant agreement between Vietnam and the WB became effective by Q2 2019 and HPMP kick-off held in Sep. 19. PMU, WB and Japan spent time finalizing procurement arrangements (as there is only one provider of key knowledge) and TOR for TA finalized and accepted by GoV by Q4 2019. | Subproject proposal finalization for AC manufacturing sector experienced delay due to enterprise capacity for preparing subprojects. Japan-WB mission in Feb 20 met enterprises to help support a way forward while further discussing the TA TOR and selection arrangements. WB procurement is seeking clarifications on the method of procurement and arrangements further delayed. However, the work is in the PMU's procurement plan and launch of the TA is expected in Sep. 20. |  |  | Non-INV |  |  | 2022-12-01
FIN | IBRD | HCFC phase-out management plan (stage I, third tranche) (foam sector plan) | Multiyear | ASP | VIE | PHA | 76 | INV | 72 | N | I | HCFC | 9.1 | 9.1 | 0 | 0 | 2016-05-01 |  | 2016-12-01 |  | 2017-06-01 | 2017-10-01 | 407581 | -407581 | 0 | 0 |  | 0 | 0 | 0 | 30569 | -30569 | 0 | 0 | 0 | Stage I HPMP completed physically and financially. | Project completed. |  |  | INV | 0 |  | 2016-12-01
FIN | UNEP | Extension of the institutional strengthening project (phase XI: 7/2017-6/2019) | Individual | ASP | VIE | SEV | 77 | INS | 73 | A | I |  | 0 |  | 0 |  | 2016-12-01 | 2017-07-01 | 2019-06-01 |  | 2019-06-01 | 2019-12-01 | 152289 | 0 | 152289 | 152288.6 | 100% | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The SSFA was signed in April 2017 with effective date from 1 July 2017 as per the Executive Committee approval. The first and second payment was processed in 2017; the third and fourth payment were released to the country in 2018. The quota for the year 2019 was issued. The NOU strictly enforced HCFC import and export quota and licensing system including the control and licensing of the HCFC-141b in pre-blended polyol, improved HS code clarification and maintained good cooperation with relevant government agencies. The collection of data was undertaken to report CP data for the year 2018. CP data for 2018 was reported to the MLFS on 26 April 2019. Article 7 was submitted to the Ozone Secretariat in June 2019. The NOU conducted two customs trainings on HS Code and HCFC Import Control in April and June 2019 attended by 14 and 16 customs officers, respectively from various departments of Customs Authority. NOU participated at the Second Global Inter- Regional Meeting and Parallel Network Meeting for NOO and the Twinning of NOO and Energy Policymakers for Energy Efficient and Climate-friendly Cooling in Paris, France in February 2019, the Thematic Workshop on the Integration of Good Servicing Practices in the National TVET for Refrigeration Servicing Technicians in June 2019 and the Open-ended Working Group Meeting in Bangkok, in July 2019. Project was completed in June 2019. The final payment was released to the country in August 2019. Project financially completed. | Project financially completed | [6 empty] | 0 | 0
ONG | UNEP | Extension of the institutional strengthening project (phase XII: 7/2019-6/2021) | Individual | ASP | VIE | SEV | 82 | INS | 74 | A | I |  | 0 |  | 0 |  | 2018-12-01 | 2019-11-01 | 2021-06-01 | 2021-06-01 |  |  | 152289 | 0 | 152289 | 17431.13 | 11.45% | 134857.87 | 134858 | 67428.935 | 0 | 0 | 0 | 0 | 0 | The workplan of IS project phase XII was finalized and agreed by the Government. The SSFA was drafted and transmitted to the Government in January 2019 for review and agreement, which was signed in June 2019. There was a change of the NOO from 1 July 2019. The NOU therefore requested UNEP to create a new SSFA to reflect the change of NOO. Finally, the new SSFA was signed by Government in October 2019 with retroactive clause effected from 1 July 2019. As there was a change in banking detail for fund transfer after signing of SSFA in October 2019, first payment could not be made immediately. NOU continued to implement the licensing system carried over from IS phase XI. The NOU also coordinated HPMP Stage II implementation, organized public awareness activities including World Ozone Day celebration in September 2019. NOU participated at the 31st Meeting of the Parties in Rome, Italy in November 2019. Viet Nam ratified the Kigali Amendment on 27 September 2019. | First payment was relased to the country in February 2020. The NOU strictly enforced HCFC import and export licensing system including the control and licensing of the HCFC-141b in pre-blended polyol, improved HS code clarification and maintained good cooperation with relevant government agencies. NOU is working with the Ministry of Trade to establish detail criteria for HCFC quota from 2020 onwards. The collection of data was undertaken to report CP data for 2020, which was reported to the MLFS in April 2020. Article 7 will be submitted to the Ozone Secretariat by June 2020. NOU is also working the national stakeholders to amend the regulation to include HFC import and export control. | [6 empty] | 55569 | 0
ONG | Japan | HCFC phase-out management plan (stage II, second tranche) (refrigeration servicing sector) |  | ASP | VIE | PHA | 84 | INV | 75 | A | I | HCFC-22 | 1.88 |  | 0 |  | 2019-12-01 |  | 2022-12-01 | 2022-12-31 |  |  | 163980 | 0 | 163980 | 0 | 0% | 163980 | 163980 | 20000 | 21317 | 0 | 0 | 21317 | 21317 | Overarching grant agreement between Vietnam and the WB became effective by Q2 2019 and HPMP kick-off held in Sep. 19. PMU, WB and Japan spent time finalizing procurement arrangements (as there is only one provider of key knowledge) and TOR for TA finalized and accepted by GoV by Q4 2019. | Subproject proposal finalization for AC manufacturing sector experienced delay due to enterprise capacity for preparing subprojects. Japan-WB mission in Feb 20 met enterprises to help support a way forward while further discussing the TA TOR and selection arrangements. WB procurement is seeking clarifications on the method of procurement and arrangements further delayed. However, the work is in the PMU's procurement plan and launch of the TA is expected in Sep. 20. |  |  | Non-INV |  |  | 2022-12-01
ONG | IBRD | HCFC phase-out management plan (stage II, second tranche) | Multiyear | ASP | VIE | PHA | 84 | INV | 76 | N | I | HCFC | 42.15 |  | 0 | 0 | 2019-12-01 |  | 2022-12-01 | 2022-12-01 |  |  | 2179193 | 0 | 2179193 | 0 | 0% | 2179193 | 2179193 | 1634395 | 152544 | 0 | 0 | 152544 | 152544 | Newly approved in Dec. 2019. | Subproject proposal submissions for target manufacturing sectors (A/C, PU foam and refrigeration) have experienced delays due to slow response rates. WB mission in Feb 20 met 7 enterprises to help support a way forward. As a result, project disbursement procedures (including in PIM) under revision to reflect more realistic grant disbursement schedules to enterprises. An MOU between DCC and the General Department of Customs signed in Feb 20. Consumption verification for 2019 conducted. Arrangements for implementing Japan TA on R-32 in AC manufacturing agreed by Apr 20. Consultants are assisting 6 enterprises develop subprojects in foam, refrigeration and AC sectors and subgrant agreement signing expected by Jun 20. Six training events for Customs officers, servicing sector trainers, and servicing technicians planned for 2020 with a total of 180 persons targeted. Procurement packages expected to be accomplished in Q3 2020 include: trainer training material; training curriculum on handling flammable refrigerants for vocational technicians; review, assessment and selection of toolkits for vocational schools/centers and service shops; development of draft technical standard for flammable blowing agent use in foam manufacturing for review and submission to MONRE. By Q3 2020, contract on Japanese TA for AC manufacturers; TA to identify potential eligible enterprises for subprojects; and, independent financial audit for 2019-21 all will be initiated. |  |  | INV |  |  | 2022-12-01
FIN | UNEP | Country programme preparation | Individual | ASP | YEM | SEV | 19 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1996-05-01 | 1996-12-01 | 1997-08-01 |  | 1998-11-01 | 1999-06-01 | 43000 | 0 | 43000 | 43000 | 100% | 0 | 0 | 0 | 5590 | 0 | 5590 | 0 | 0 | [8 empty] | 0 | 0
FIN | UNEP | Establishment of a National Ozone Unit | Individual | ASP | YEM | SEV | 25 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-02-01 | 2001-06-01 |  | 2001-12-01 | 2003-12-01 | 120000 | 0 | 120000 | 120000 | 100% | 0 | 0 | 0 | 15600 | 0 | 15600 | 0 | 0 | [8 empty] | 0 | 0
CLO | UNIDO | Preparation of project in the foam sector | Individual | ASP | YEM | FOA | 27 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 |  | 1999-12-01 |  |  | 2001-03-01 | 20000 | -20000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 2600 | -2600 | 0 | 0 | 0
FIN | UNIDO | Preparation of project in the aerosol sector | Individual | ASP | YEM | ARS | 27 | PRP | 04 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-08-01 | 1999-12-01 |  | 2000-12-01 | 2001-10-01 | 20000 | -2885 | 17115 | 17115 | 100% | 0 | 0 |  | 2600 | -378.56 | 2221 | 0.44 | 0
FIN | UNEP | Preparation of a refrigerant management plan | RMP | ASP | YEM | REF | 27 | PRP | 05 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-08-01 | 2000-04-01 |  | 2001-12-01 | 2003-07-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 |  |  |  | 2001-09-01 |  |  |  |  | 0 | 0
FIN | UNDP | Preparation of a refrigerant recycling project | Individual | ASP | YEM | REF | 33 | PRP | 06 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2002-04-01 | 2003-07-01 | 15000 | -1934 | 13066 | 13066 | 100% | 0 | 0 | 0 | 1950 | -251 | 1698.58 | 0.42 | 0 | Completed in 2002. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNIDO | Preparation of 2 projects in the commercial refrigeration sector | Individual | ASP | YEM | REF | 33 | PRP | 07 | A | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-08-01 | 2002-04-01 |  | 2002-07-01 | 2003-10-01 | 20000 | -3268 | 16732 | 16732 | 100% | 0 | 0 |  | 2600 | -428.35 | 2172 | -0.35 | 0 |  |  |  |  | INV
FIN | UNIDO | Phase-out of CFC-11, CFC-12 and CFC-114 in the manufacture of aerosols by conversion to hydrocarbon propellant at Arabia Felix Industries Ltd. | Individual | ASP | YEM | ARS | 34 | INV | 08 | A | R | CFC | 96.6 | 96.6 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2003-10-01 |  | 2004-05-01 | 2005-12-01 | 366804 | -5910 | 360894 | 360894 | 100% | 0 | 0 |  | 34676 | -612.78 | 34063 | 0.22 | 0 |  |  |  |  | INV
FIN | Germany | Preparation for phase-out investment project for methyl bromide sector | Individual | ASP | YEM | FUM | 34 | PRP | 09 | A | I |  | 0 |  | 0 |  | 2001-07-01 | 2002-05-01 | 2002-01-01 |  | 2003-12-01 | 2004-04-01 | 44000 | 0 | 44000 | 44000 | 100% | 0 | 0 | 0 | 5720 | 0 | 5720 | 0 | 0 | Project to reduce MB consumtion by 9.1 ODP tonnes approved at 41st ExCom.
FIN | UNIDO | Phase-out of CFC 12 in the manufacture of aerosols by conversion to hydrocarbon propellant at Al-Thowra Industrial Complex | Individual | ASP | YEM | ARS | 34 | INV | 10 | A | I | CFC | 82.7 | 82.7 | 0 | 0 | 2001-07-01 | 2002-06-01 | 2003-10-01 |  | 2004-04-01 | 2004-09-01 | 179508 | 0 | 179508 | 179508 | 100% | 0 | 0 |  | 23336 | -32.63 | 23303 | 0.37 | 0 |  |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Nagman Co. | Individual | ASP | YEM | REF | 35 | INV | 11 | A | I | CFC | 7.3 | 7.3 | 0 | 0 | 2001-12-01 | 2002-04-01 | 2003-07-01 |  | 2003-12-01 | 2004-10-01 | 105641 | -1328 | 104313 | 104313 | 100% | 0 | 0 |  | 13733 | -194 | 13539 | 0 | 0 |  |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to HCFC-141b and CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Styrco | Individual | ASP | YEM | REF | 35 | INV | 12 | A | I | CFC | 6.1 | 6.1 | 0 | 0 | 2001-12-01 | 2002-05-01 | 2003-07-01 |  | 2003-12-01 | 2004-10-01 | 90231 | -1456 | 88775 | 88775 | 100% | 0 | 0 |  | 11730 | -208 | 11522 | 0 | 0 |  |  |  |  | INV
FIN | UNEP | Renewal of the institutional strengthening project | Individual | ASP | YEM | SEV | 35 | INS | 13 | A | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-04-01 | 2004-01-01 |  | 2003-12-01 | 2004-12-01 | 118000 | 0 | 118000 | 118000 | 100% | 0 | 0 | 0 | 15340 | 0 | 15340 | 0 | 0 | [8 empty] | 0 | 0
CLO | UNIDO | Preparation of a terminal investment project in commercial refrigeration sector | Individual | ASP | YEM | REF | 36 | PRP | 14 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-01-01 | 2003-04-01 |  |  | 2003-05-01 | 10000 | -2349 | 7651 | 7651 | 100% | 0 | 0 |  | 1300 | -306.93 | 993 | 0.07 | 0 |  |  |  |  | INV
FIN | UNDP | Implementation of the RMP: national recovery and recycling programme for refrigerants in the commercial and MAC sectors | RMP-Component | ASP | YEM | REF | 37 | TAS | 15 | A | I | CFC | 220 | 220 | 0 | 0 | 2002-07-01 | 2002-12-01 | 2005-08-01 |  | 2008-12-01 | 2012-06-01 | 1472730 | -36714 | 1436016 | 1436016 | 100% | 0 | 0 | 0 | 172000 | -4288 | 167712.4678 | -0.46784 | 0 | Financially completed in 2012. |  | 2002 |  | Investment
FIN | UNEP | Implementation of the RMP: establishment of regulations and legislation | Individual | ASP | YEM | REF | 37 | TAS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-05-01 | 2004-01-01 |  | 2006-12-01 | 2011-06-01 | 25000 | -5000 | 20000 | 20000 | 100% | 0 | 0 | 0 | 3250 | -650 | 2600 | 0 | 0 | [8 empty] | 0 | 0
FIN | UNEP | Implementation of the RMP: training programme on good practices in refrigeration | Individual | ASP | YEM | REF | 37 | TRA | 17 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-04-01 | 2005-08-01 |  | 2008-12-01 | 2010-12-01 | 189500 | 0 | 189500 | 189500 | 100% | 0 | 0 | 0 | 24635 | 0 | 24635 | 0 | 0 | [8 empty] | 0 | 0
FIN | UNEP | Implementation of the RMP: training programme for customs officers | Individual | ASP | YEM | REF | 37 | TRA | 18 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-06-01 | 2004-08-01 |  | 2011-09-01 | 2011-12-01 | 91825 | 0 | 91825 | 91825 | 100% | 0 | 0 | 0 | 11937 | 0 | 11937 | 0 | 0 | [8 empty] | 0 | 0
FIN | UNEP | Implementation of the RMP: monitoring the activities in the RMP | Individual | ASP | YEM | REF | 37 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2007-10-01 | 2005-08-01 |  | 2010-12-01 | 2014-11-01 | 57750 | -12750 | 45000 | 45000 | 100% | 0 | 0 | 0 | 7508 | -1657.61 | 5850.39 | 0 | 0 | [7 empty] | 2016-12-01 | 0 | 0
FIN | UNEP | Extension of institutional strengthening project: phase III | Individual | ASP | YEM | SEV | 41 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-04-01 | 2005-12-01 |  | 2005-12-01 | 2007-03-01 | 104000 | -391 | 103609 | 103609 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
FIN | Germany | Technical assistance programme for the phase-out of methyl bromide in agriculture | Individual | ASP | YEM | FUM | 41 | TAS | 21 | A | I | MBR | 9.1 | 17.1 | 0 |  | 2003-12-01 | 2004-05-01 | 2006-12-01 |  | 2008-04-01 | 2009-10-01 | 250000 | 0 | 250000 | 250000 | 100% | 0 | 0 | 0 | 32500 | 0 | 32500 | 0 | 0 | Farmers were trained in the usage of MB alternatives. More field visits to farmers promoting MB alternatives took place. All project activities were successfully completed. The PCR has been prepared.
FIN | UNIDO | Training and awareness workshop in the process agents (TCA) sector | Individual | ASP | YEM | SOL | 45 | TAS | 22 | A | I | TCA | 0.2 | 0.2 | 0 | 0 | 2005-04-01 | 2005-09-01 | 2006-04-01 |  | 2006-12-01 | 2007-09-01 | 35000 | -164 | 34836 | 34836 | 100% | 0 | 0 |  | 3150 | -15 | 3135.24 | -0.24 | 0 |  |  |  |  | INV
FIN | UNIDO | Preparation of a terminal umbrella project in refrigeration (CFC) | Individual | ASP | YEM | REF | 45 | PRP | 23 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-09-01 | 2006-04-01 |  | 2008-04-01 | 2008-09-01 | 30000 | -453 | 29547 | 29547 | 100% | 0 | 0 |  | 2250 | -34 | 2216.025 | -0.025 | 0 |  |  |  |  | NON-INV
FIN | UNEP | Extension of institutional strengthening project (phase IV) | Individual | ASP | YEM | SEV | 47 | INS | 24 | A | I | CFC | 8.6 | 8.6 | 0 | 0 | 2005-11-01 | 2006-05-01 | 2007-12-01 |  | 2007-12-01 | 2008-12-01 | 104000 | 0 | 104000 | 104000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV-supplementary request) | Individual | ASP | YEM | SEV | 48 | INS | 25 | A | I | CFC | 5.4 | 0 | 0 | 0 | 2006-04-01 | 2006-06-01 | 2007-04-01 |  | 2007-04-01 | 2007-12-01 | 66000 | 0 | 66000 | 66000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
FIN | UNEP | Project preparation for a national phase-out management plan | RMP | ASP | YEM | PHA | 50 | PRP | 26 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2008-04-01 | 2007-11-01 |  | 2009-11-01 | 2010-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 | [8 empty] | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase V) | Individual | ASP | YEM | SEV | 53 | INS | 27 | A | I | CFC | 14 | 14 | 0 | 0 | 2007-11-01 | 2008-08-01 | 2009-11-01 |  | 2009-11-01 | 2010-12-01 | 170000 | -392 | 169608 | 169608 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
CLO | UNIDO | National ODS phase-out plan (first tranche) | Multi-Year | ASP | YEM | PHA | 55 | INV | 28 | A | I | CFC | 339.4 | 0 | 0 | 0 | 2008-07-01 | 2008-11-01 | 2010-12-01 |  |  | 2019-06-11 | 1137500 | -32218 | 1105282 | 1105281.62 | 100% | 0.38 | 0 | 0 | 85313 | -2417 | 82896.1215 | -0.1215 | 0 | Project was financially closed in June 2019. Remaining fund balances were returned at the 84th ExCom meeting in December 2019. |  |  |  | INV |  |  | 2016-12-01
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | ASP | YEM | PHA | 55 | PRP | 29 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-05-01 | 2009-07-01 |  | 2012-12-01 | 2014-04-01 | 70000 | -1155.98 | 68844.02 | 68843.64 | 100% | 0.38 | 0 |  | 5250 | -87 | 5163.273 | -0.273 | 0 |  |  |  |  | NON-INV
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | ASP | YEM | PHA | 55 | PRP | 30 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-10-01 | 2009-07-01 |  | 2013-12-01 | 2014-11-01 | 125000 | -108600 | 16400 | 16400 | 100% | 0 | 0 | 0 | 16250 | -14118 | 2132 | 0 | 0 | [8 empty] | 0 | 0
FIN | UNEP | National ODS phase-out plan (first tranche) | Multi-Year | ASP | YEM | PHA | 55 | TAS | 31 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2009-11-01 | 2010-12-01 |  | 2018-12-01 | 2018-12-01 | 315000 | -79053 | 235947 | 235947 | 100% | 0 | 0 | 0 | 40950 | -10276.89 | 30673.11 | 0 | 0 | [7 empty] | 2016-12-01 | 0 | 0
FIN | Germany | Terminal phase-out of methyl bromide (first tranche, part 1) | Multi-Year | ASP | YEM | FUM | 56 | INV | 32 | A | I | MBR | 5.9 | 4.8 | 0 |  | 2008-11-01 | 2008-11-01 | 2014-12-01 |  | 2010-12-01 | 2015-12-01 | 109740 | 0 | 109740 | 109740 | 100% | 0 | 0 | 0 | 13896 | 0 | 13896 | 0 | 0 | During 2010 the following activities were conducted: 3 new farmers from Sana'a Governorate received materials to implement the solarization technology on their farms (thermal polyethylene – PE, humidity scale, thermometer). On-site trainings were held at each of the 3 farms, with 10 farmers participating at each one. Bio- fumigation with local radish seeds is still under implementation in Dhamar Governarate, at Al-Khupaji farm. Biofumigation is also recommended for Al-Shamhazi farm located near Atheen village which is one of the coldest areas in Yemen. In cooperation with Al-Reyada'a Women’s Association, a meeting on MB alternatives for decision makers was held in Dhamar Governorate. Fifteen officers from the local council and the Governor Office attended the meeting. A primary survey for Governorate of Abyan was carried out April – May 2010. MB is used for banana and garlic farms to treat soil infestations by nematodes. 2 meetings were held between Alakel Company and NOU to introduce Grafting Technology in Sadah. However, due to the tense security situation in the Sadah area, these activities were delayed until 2011.
FIN | Germany | Terminal phase-out of methyl bromide (first tranche, part 2) | Multi-Year | ASP | YEM | FUM | 57 | INV | 33 | A | I | MBR | 0 | 5.4 | 0 |  | 2009-04-01 | 2009-05-01 | 2014-12-01 |  | 2010-12-01 | 2015-12-01 | 91710 | 0 | 91710 | 91710 | 100% | 0 | 0 | 0 | 11613 | 0 | 11613 | 0 | 0 | During 2010 the following activities were conducted: 3 new farmers from Sana'a Governorate received materials to implement the solarization technology on their farms (thermal polyethylene – PE, humidity scale, thermometer). On-site trainings were held at each of the 3 farms, with 10 farmers participating at each one. Bio- fumigation with local radish seeds is still under implementation in Dhamar Governarate, at Al-Khupaji farm. Biofumigation is also recommended for Al-Shamhazi farm located near Atheen village which is one of the coldest areas in Yemen. In cooperation with Al-Reyada'a Women’s Association, a meeting on MB alternatives for decision makers was held in Dhamar Governorate. Fifteen officers from the local council and the Governor Office attended the meeting. A primary survey for Governorate of Abyan was carried out April – May 2010. MB is used for banana and garlic farms to treat soil infestations by nematodes. 2 meetings were held between Alakel Company and NOU to introduce Grafting Technology in Sadah. However, due to the tense security situation in the Sadah area, these activities were delayed until 2011.
FIN | UNEP | Extension of the institutional strengthening project (phase VI) | Individual | ASP | YEM | SEV | 59 | INS | 34 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-12-01 | 2011-11-01 |  | 2012-12-01 | 2013-12-01 | 92083 | 77916 | 169999 | 169999 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
FIN | UNEP | National ODS phase-out plan (second tranche) | Multi-Year | ASP | YEM | PHA | 60 | TAS | 35 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2015-06-01 | 2011-04-01 |  | 2014-12-01 | 2018-12-01 | 140000 | 0 | 140000 | 140000 | 100% | 0 | 0 | 0 | 18200 | 0 | 18200 | 0 | 0 | [7 empty] | 2016-12-01 | 0 | 0
CLO | UNIDO | National ODS phase-out plan (second tranche) | Multi-Year | ASP | YEM | PHA | 60 | INV | 36 | A | I |  | 268.7 | 0 | 0 | 0 | 2010-04-01 | 2010-07-01 | 2011-04-01 |  |  | 2019-03-25 | 233000 | -60366 | 172634 | 172633.53 | 100% | 0.47 | 0 | 0 | 17475 | -4528 | 12947.5148 | -0.51475 | 0 | Project was financially closed in March 2019. Funds were returned at the 83rd meeting in May 2019. | [6 empty] | 2016-12-01
FIN | Germany | Terminal phase-out of methyl bromide (second tranche) | Multi-Year | ASP | YEM | FUM | 62 | INV | 37 | A | I | MBR | 10 | 8.5 | 0 |  | 2010-12-01 | 2011-12-01 | 2012-12-01 |  | 2013-08-01 | 2015-12-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 25325 | 0 | 25325 | 0 |  | Remaining funds from 2013 were spent in 2014
FIN | UNIDO | Preparation for HCFC phase-out investment activities (rigid polyurethane foam component) | Individual | ASP | YEM | FOA | 63 | PRP | 38 | A | I |  | 0 | 0 | 0 | 0 | 2011-04-01 | 2013-01-01 | 2012-03-01 |  | 2012-12-01 | 2014-04-01 | 60000 | -48664.67 | 11335.33 | 11335 | 100% | 0.33 | 0 |  | 4500 | -3650 | 850.125 | -0.125 | 0 |  |  |  |  | NON-INV
CLO | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | YEM | PHA | 68 | TAS | 39 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2014-10-01 | 2014-12-01 |  |  | 2019-06-11 | 410000 | -250471 | 159529 | 159529.13 | 100% | -0.13 | 0 | 0 | 28700 | -17533 | 11167.0391 | -0.0391 | 0 | Project was financially closed in June 2019. Remaining fund balances were returned at the 84th ExCom meeting in December 2019. |  |  |  | INV
CLO | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | ASP | YEM | PHA | 68 | TAS | 40 | A | I |  | 11.6 | 11.6 | 0 | 0 | 2012-12-01 |  | 2015-12-01 |  |  | 2019-12-01 | 215000 | -215000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 27950 | -27950 | 0 | 0 | 0 | Project closed | Project closed | [6 empty] | 0 | 0
FIN | Germany | Terminal phase-out of methyl bromide (third tranche) | Multi-Year | ASP | YEM | FUM | 68 | INV | 41 | A | I | MBR | 20 | 11 | 0 |  | 2012-12-01 | 2013-08-01 | 2014-12-01 |  | 2015-02-01 | 2015-12-01 | 200000 | 0 | 200000 | 200000 | 100% | 0 | 0 | 0 | 25325 | 0 | 25325 | 0 |  | Distribution of the final alternatives materials was finalized in the beginning of February 2015, and all project financial obligations were completed and closed as at 28th February 2015. Commercial production of grafted nurses took place in second half of 2015. | For ensuring sustainability uses of MB substitutes in soil fumigation, ISP will continue monitoring and technically supporting the sector.
FIN | UNEP | Extension of the institutional strengthening project (phase VII: 1/2013-12/2014) | Individual | ASP | YEM | SEV | 68 | INS | 42 | A | I |  | 0 | 0 | 0 | 0 | 2012-12-01 | 2014-01-01 | 2014-12-01 |  | 2014-12-01 | 2018-12-01 | 169999 | -59748 | 110251 | 110251 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
ONG | UNEP | Extension of the institutional strengthening project (phase VIII: 1/2015-12/2016) | Individual | ASP | YEM | SEV | 73 | INS | 43 | A | I |  | 0 |  | 0 |  | 2014-11-01 |  | 2016-12-01 | 2020-12-01 |  |  | 169999 | 0 | 169999 | 0 | 0% | 169999 | 0 | 50999.7 | 0 | 0 | 0 | 0 | 0 | No progress due to the war | No progress due to the war |  |  |  |  | To request a status report to the 86th meeting on progress in implementation |  | 0 | 0
CLO | UNEP | Preparation of a HCFC phase-out management plan (stage II) | Individual | ASP | YEM | PHA | 73 | PRP | 44 | A | I |  | 0 |  | 0 |  | 2014-11-01 |  | 2016-11-01 |  |  | 2019-12-01 | 50000 | -50000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 6500 | -6500 | 0 | 0 | 0 | Project closed | Project closed | [6 empty] | 0 | 0
CLO | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | Individual | ASP | YEM | PHA | 73 | PRP | 45 | A | I |  | 0 | 0 | 0 | 0 | 2014-11-01 |  | 2016-11-01 |  |  | 2019-03-27 | 20000 | -20000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 1400 | -1400 | 0 | 0 | 0 | Project was financially closed in March 2019. Funds were returned at the 83rd meeting in May 2019. |  |  |  | NON-INV
CLO | UNIDO | Preparation for HCFC phase-out investment activities (stage II) (foam sector) | Individual | ASP | YEM | FOA | 73 | PRP | 46 | A | I |  | 0 | 0 | 0 | 0 | 2014-11-01 |  | 2016-11-01 |  |  | 2019-03-27 | 80000 | -80000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 5600 | -5600 | 0 | 0 | 0 | Project was financially closed in March 2019. Funds were returned at the 83rd meeting in May 2019. |  |  |  | NON-INV
FIN | UNIDO | Country programme preparation | Individual | EUR | YUG | SEV | 21 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-06-01 | 1998-02-01 |  | 1998-08-01 | 1999-09-01 | 80000 | 0 | 80000 | 80000 | 100% | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0
FIN | IBRD | Country programme preparation |  | EUR | YUG | SEV | 04 | PRP | 02 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-01 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 20302 | -14877 | 5425 | 5425 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
CLO | IBRD | Preparation of investment projects (1991) |  | EUR | YUG | SEV | 04 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1992-06-01 |  |  | 1992-06-01 | 21432 | -21432 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | UNIDO | Preparation of an investment project in the refrigeration sector for phasing out ODS at Obod | Individual | EUR | YUG | REF | 23 | PRP | 04 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-07-01 | 1998-03-01 |  | 1999-12-01 | 2000-07-01 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | -1 | 1299 | 0 | 0
FIN | UNIDO | Preparation of an investment project in the solvent sector for phasing out ODS at Hemofarm | Individual | EUR | YUG | SOL | 23 | PRP | 05 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-09-01 | 1998-03-01 |  | 2000-02-01 | 2001-07-01 | 10000 | -2587 | 7413 | 7413 | 100% | 0 | 0 |  | 1300 | -337.87 | 962 | 0.13 | 0
FIN | UNIDO | Preparation of refrigerant management plan | Individual | EUR | YUG | REF | 24 | PRP | 06 | A | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-01 | 1999-04-01 |  | 1998-06-01 | 2000-03-31 | 10000 | 0 | 10000 | 10000 | 100% | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0
FIN | UNIDO | Institutional strengthening (establishment of the Ozone Unit) | Individual | EUR | YUG | SEV | 25 | INS | 07 | N | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-12-01 | 2001-07-01 |  | 2004-10-01 | 2005-09-01 | 151500 | 0 | 151500 | 151500 | 100% | 0 | 0 |  | 19695 | -4.55 | 19690 | 0.45 | 0 |  |  |  |  | NON-INV
FIN | UNIDO | Replacement of CFC-113 as solvent for dialyses cleaning by water and steam at Hemomed Ltd. | Individual | EUR | YUG | SOL | 26 | INV | 08 | A | R | CFC | 54.6 | 54.6 | 0 | 0 | 1998-11-01 | 1999-02-01 | 1999-06-01 |  | 1998-12-01 | 1999-09-01 | 608729 | 0 | 608729 | 608729 | 100% | 0 | 0 |  | 76960 | 0 | 76960 | 0 | 0
FIN | UNIDO | Project preparation in the halon sector | Individual | EUR | YUG | HAL | 33 | PRP | 09 | A | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-06-01 | 2002-04-01 |  | 2002-04-01 | 2003-05-01 | 20000 | -82 | 19918 | 19918 | 100% | 0 | 0 |  | 2600 | -14.82 | 2585 | 0.18 | 0 |  |  |  |  | INV
FIN | UNIDO | Preparation of one investment project in the flexible foam sector | Individual | EUR | YUG | FOA | 34 | PRP | 10 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-10-01 | 2002-08-01 |  | 2004-03-01 | 2004-04-01 | 15000 | -15 | 14985 | 14985 | 100% | 0 | 0 |  | 1950 | -5 | 1945 | 0 | 0 |  |  |  |  | INV
FIN | UNIDO | Preparation of 2 projects in the commercial refrigeration sector | Individual | EUR | YUG | REF | 33 | PRP | 10 | A | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-06-01 | 2002-04-01 |  | 2001-11-01 | 2002-12-01 | 10000 | -2325 | 7675 | 7675 | 100% | 0 | 0 |  | 1300 | -303.81 | 996 | 0.19 | 0 |  |  |  |  | INV
FIN | UNIDO | Preparation of one investment project in the rigid foam sector | Individual | EUR | YUG | FOA | 34 | PRP | 11 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-10-01 | 2002-08-01 |  | 2004-03-01 | 2004-09-01 | 15000 | -201 | 14799 | 14799 | 100% | 0 | 0 |  | 1950 | -29.12 | 1921 | -0.12 | 0 |  |  |  |  | INV
FIN | UNIDO | Replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment at 7 enterprises (Jugostroj, Frigozika, Prva Petoletka, EIAD, BS Inzenjering, Soko and Alfa Klima) | Individual | EUR | YUG | REF | 34 | INV | 12 | A | I | CFC | 59.6 | 59.6 | 0 | 0 | 2001-07-01 | 2001-11-01 | 2004-02-01 |  | 2003-12-01 | 2005-09-01 | 755162 | -19150 | 736012 | 736012 | 100% | 0 | 0 |  | 93068 | -2234.87 | 90833 | 0.13 | 0 |  |  |  |  | INV
FIN | Italy | Replacement of CFC-11 with cyclopentane foam blowing agent and CFC-12 with HFC-134a refrigerant in the manufacture of domestic refrigerators and freezers at Obod Elektroindustria | Individual | EUR | YUG | REF | 34 | INV | 13 | A | I | CFC | 94.9 | 94.9 | 0 |  | 2001-07-01 | 2002-09-01 | 2003-10-01 |  | 2007-04-01 | 2008-12-01 | 1683135 | -91120 | 1592015 | 1592015 | 100% | 0 | 0 | 0 | 180348 | -10023.45 | 170325 | -0.45 | 0 | FIN |  | 2001 |  | Investment
FIN | UNIDO | Phase-out of CFC-11 by conversion to n-pentane technology in the production of continuous rigid polyurethane foam insulating panels at Prva Iskra-Fim, Co. | Individual | EUR | YUG | FOA | 35 | INV | 14 | A | I | CFC | 75 | 75 | 0 | 0 | 2001-12-01 | 2003-08-01 | 2004-07-01 |  | 2006-12-01 | 2011-05-01 | 475728 | -4430.41 | 471297.59 | 471297.59 | 100% | 0 | 0 |  | 61845 | -576 | 61268.6867 | 0.3133 | 0 |  |  |  |  | INV
FIN | UNIDO | Conversion from CFC-11 to methylene chloride in the production of flexible slabstock foam at Prva Iskra-Poliuretani | Individual | EUR | YUG | FOA | 35 | INV | 15 | A | I | CFC | 34.4 | 34.4 | 0 | 0 | 2001-12-01 | 2002-03-01 | 2004-01-01 |  | 2004-02-01 | 2004-12-01 | 100240 | -169 | 100071 | 100071 | 100% | 0 | 0 |  | 13031 | -42 | 12989 | 0 | 0 |  |  |  |  | INV
FIN | UNIDO | Halon bank management programme | Individual | EUR | YUG | HAL | 35 | TAS | 16 | A | I | HAL | 370 | 370 | 0 | 0 | 2001-12-01 | 2002-03-01 | 2004-01-01 |  | 2004-12-01 | 2005-12-01 | 249700 | -4216 | 245484 | 245484 | 100% | 0 | 0 |  | 32461 | -598.65 | 31862 | 0.35 | 0 |  |  |  |  | INV
FIN | UNIDO | Preparation of an umbrella investment project in the commercial refrigeration sector | Individual | EUR | YUG | REF | 36 | PRP | 17 | A | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-05-01 | 2003-04-01 |  | 2003-07-01 | 2004-12-01 | 20000 | -119 | 19881 | 19881 | 100% | 0 | 0 |  | 2600 | -19 | 2581 | 0 | 0 |  |  |  |  | INV
FIN | UNIDO | Umbrella refrigeration project 2, replacement of refrigerant CFC-12 with HFC-134a and foam blowing agent CFC-11 with HCFC-141b in the manufacture of commercial refrigeration equipment at three enterprises | Individual | EUR | YUG | REF | 37 | INV | 18 | A | I | CFC | 10.9 | 10.9 | 0 | 0 | 2002-07-01 | 2003-04-01 | 2005-01-01 |  | 2004-10-01 | 2005-12-01 | 150109 | -1869 | 148240 | 148240 | 100% | 0 | 0 |  | 19514 | -272.52 | 19241 | 0.48 | 0 |  |  |  |  | INV
FIN | UNIDO | Conversion of CFC-12 to HFC-134a in the manufacture of open compressors at Prva Petoletka - Kocna Tehnika Co. | Individual | EUR | YUG | REF | 38 | INV | 19 | A | I | CFC | 2 | 2 | 0 | 0 | 2002-11-01 | 2003-06-01 | 2005-06-01 |  | 2006-06-01 | 2007-09-01 | 223412 | -44 | 223368 | 223368 | 100% | 0 | 0 |  | 29044 | -6 | 29037.84 | 0.16 | 0 |  |  |  |  | INV
FIN | UNIDO | Assistance to prepare a national CFC phase-out plan (manufacturing sector) | Individual | EUR | YUG | PHA | 40 | PRP | 20 | A | I |  | 0 | 0 | 0 | 0 | 2003-07-01 | 2003-12-01 | 2004-07-01 |  | 2005-04-01 | 2005-09-01 | 40000 | -7481 | 32519 | 32519 | 100% | 0 | 0 |  | 3000 | -564.98 | 2435 | 0.02 | 0
FIN | Sweden | Assistance to prepare a national CFC phase-out plan (servicing sector) | Individual | EUR | YUG | PHA | 40 | PRP | 21 | A | I |  | 0 |  | 0 |  | 2003-07-01 | 2003-12-01 | 2004-07-01 |  | 2004-07-01 | 2004-11-01 | 65000 | 0 | 65000 | 65000 | 100% | 0 |  |  | 8450 | 0 | 8450 | 0 | 0 | The assistance to Serbia and Montenegro (SEM) to develop a NCPP for the servicing sector was completed in a joint undertaking with UNIDO during the spring 2004 and the plan was approved in July 2004. |  | 2003
TRF | Sweden | National CFC phase-out plan (first tranche) | Multi-Year | EUR | YUG | PHA | 43 | TAS | 22 | A | I |  | 0 |  | 0 |  | 2004-07-01 | 2005-11-01 | 2005-03-01 |  |  | 2010-06-01 | 148000 | -128678 | 19322 | 19322 | 100% | 0 | 0 | 0 | 19240 | -16728 | 2512 | 0 | 0 | The NCPP implementation was started with UNIDO as Lead Agency and Sweden as Cooperating Agency. Since the Swedish decision in 2006 to cease the bilateral window, UNIDO was the the sole implementing agency with Sweden supporting only through the already contracted Swedish consultants. With ExCom decision 60/3 in April 2010, however the full project was handed over from Sweden to UNIDO and the contract with the international consultant was terminated. The project struggled with serious delays from the start, partly due to the difficulties in making the PMU operational and frequent changes of staff at the NOU. The split with Montenegro also slowed down activities for a while. A new NOU manager was officially assigned as of Dec 2008 and a PMU manager was finally contracted during the autumn 2009. During early spring 2010, two additional experts were contracted making the PMU fully operational. As an immediate result of these recruitments, by April 2010 substantial progress had been made on a number of activities: Seven out of eight training sessions for customs had been undertaken; the new ODS regulation ("Official Gazette RS, No 36/09") was adopted which describes how the reclamation scheme should function (incl. financial structure, roles and responsibilities etc). The new regulation also had several important elements pertaining to the sustainable phase-out of ODS, such as how to handle re quest for Issuance of Export License (for importers/exporters) and request for issuance of license for import of controlled substances and equipment in emergency cases (for importers/exporters). Serbia did in April 2010 not yet have a Code of Good Practice in place, however the new Decree suggested that good practice in refrigeration should be followed, meaning there is support for this work once it has been developed. During the spring the NOU also started to work on an F-gas regulation. The reclamation scheme still remained to be established but an important milestone for getting that in place was met through the adoption of the new ODS regulation. Other important activities that still remained to be undertaken in April 2010 was the training of trainers and technicians. Three training centers were selected already in November 2009 but the contractual procedures was in April still not in place. During the autumn 2009, Sweden decided to put a final close to all its bilateral activities under the Montreal Protocol and with ExCom decision 60/3 (April 2010) the remaining Swedish responsibilities were officially transferred to UNIDO. The contract with the International Consultant was terminated and the remaining balance transferred to UNIDO via the MLF. This progress report constitutes the final progress report from Sweden. Project Completion Report (PCR) for the Swedish contribution was submitted to MLF in Dec 2010. |  | 2004 | 2006-12-01
FIN | UNIDO | National CFC phase-out plan (first tranche) | Multi-Year | EUR | YUG | PHA | 43 | TAS | 23 | A | I | CFC | 2 | 2 | 0 | 0 | 2004-07-01 | 2004-08-01 | 2005-03-01 |  | 2009-12-01 | 2013-10-01 | 474700 | -34974.49 | 439725.51 | 439725.51 | 100% | 0 | 0 |  | 35603 | -2624 | 32979.4132 | -0.41325 | 0 |  |  |  | 2006-07-01 | INV
FIN | UNIDO | Extension of institutional strengthening project (phase II) | Individual | EUR | YUG | SEV | 44 | INS | 25 | N | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2006-07-01 | 2006-12-01 |  | 2009-12-01 | 2011-12-01 | 131300 | -7175.27 | 124124.73 | 124124.73 | 100% | 0 | 0 |  | 9848 | -539 | 9309.3548 | -0.35475 | 0 |  |  |  |  | NON-INV
FIN | UNIDO | Project preparation in the fumigants sector (methyl bromide) | Individual | EUR | YUG | FUM | 45 | PRP | 26 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-09-01 | 2006-04-01 |  | 2009-09-01 | 2009-09-01 | 25000 | -9188.61 | 15811.39 | 15811 | 100% | 0.39 | 0 |  | 1875 | -689 | 1185.825 | 0.175 | 0 |  |  |  |  | NON-INV
FIN | UNIDO | Project preparation for the terminal phase-out in the solvent sector (CTC) | Individual | EUR | YUG | SOL | 45 | PRP | 27 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2006-11-01 | 2006-04-01 |  | 2008-12-01 | 2009-06-01 | 15000 | -1990.85 | 13009.15 | 13009 | 100% | 0.15 | 0 |  | 1125 | -149 | 975.675 | 0.325 | 0 |  |  |  |  | NON-INV
FIN | UNIDO | National CFC phase-out plan (second tranche) | Multi-Year | EUR | YUG | PHA | 47 | INV | 28 | A | I | cFC | 18 | 18 | 0 | 0 | 2005-11-01 | 2006-10-01 | 2006-12-01 |  | 2013-12-01 | 2014-08-01 | 759000 | -623749.39 | 135250.61 | 135250.61 | 100% | 0 | 0 |  | 56925 | -46781 | 10143.7957 | 0.20425 | 0 |  |  |  |  | INV
TRF | Sweden | National CFC phase-out plan (second tranche) | Multi-Year | EUR | YUG | PHA | 47 | TAS | 29 | A | I |  | 0 |  | 0 |  | 2005-11-01 |  | 2006-12-01 |  |  | 2006-11-01 | 134000 | -134000 | 0 | 0 |  | 0 | 0 | 0 | 17420 | -17420 | 0 | 0 | 0 | This activity was transferred to UNIDO in 2006. |  | 2005
FIN | UNIDO | National CFC phase-out plan (third tranche) | Multi-Year | EUR | YUG | PHA | 50 | INV | 30 | A | I | CFC | 124 | 124 | 0 | 0 | 2006-11-01 | 2007-05-01 | 2007-11-01 |  | 2013-12-01 | 2014-04-01 | 1033344 | -12.01 | 1033331.99 | 1033331.99 | 100% | 0 | 0 |  | 77501 | -1 | 77499.8993 | 0.10075 | 0 |  |  |  |  | INV
FIN | UNIDO | National CFC phase-out plan (third tranche, transferred from Sweden) | Multi-Year | EUR | YUG | PHA | 51 | INV | 31 | A | I |  | 0 | 0 | 0 | 0 | 2007-03-01 | 2009-12-01 | 2008-03-01 |  | 2013-12-01 | 2014-04-01 | 222000 | -23916.81 | 198083.19 | 198083.19 | 100% | 0 | 0 |  | 16650 | -1794 | 14856.2393 | -0.23925 | 0 |  |  |  |  | INV
FIN | UNIDO | Preparation of a HCFC phase-out management plan | Individual | EUR | YUG | PHA | 55 | PRP | 32 | A | I |  | 0 | 0 | 0 | 0 | 2008-07-01 | 2008-12-01 | 2009-07-01 |  | 2011-07-01 | 2012-12-01 | 150000 | -955.13 | 149044.87 | 149044.87 | 100% | 0 | 0 |  | 11250 | -72 | 11178.3653 | -0.36525 | 0 |  |  |  |  | NON-INV
FIN | Italy | Terminal CTC phase-out project | Individual | EUR | YUG | SOL | 56 | INV | 33 | A | I | CTC | 2.6 | 2.6 | 0 |  | 2008-11-01 | 2009-04-01 | 2009-11-01 |  | 2010-06-01 | 2011-12-01 | 49324 | -338 | 48986 | 48986 | 100% | 0 | 0 | 0 | 6412 | -43.82 | 6368 | 0.18 | 0 | FIN |  | 2008 |  | Investment
FIN | UNIDO | Extension of institutional strengthening project (phase III) | Individual | EUR | YUG | SEV | 59 | INS | 34 | N | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2010-07-01 | 2011-11-01 |  | 2011-11-01 | 2015-09-01 | 71121 | 48816.55 | 119937.55 | 119937.54 | 100% | 0.01 | 0.01 |  | 5334 | 3661 | 8995.3155 | -0.3155 | 0.00075 |  |  |  |  | NON-INV
FIN | UNIDO | National CFC phase-out plan (first tranche) | Multi-Year | EUR | YUG | PHA | 60 | TAS | 35 | A | I |  | 0 | 0 | 0 | 0 | 2010-04-01 | 2010-12-01 | 2011-04-01 |  | 2013-12-01 | 2013-12-01 | 40678 | -121.42 | 40556.58 | 40556.58 | 100% | 0 | 0 |  | 3051 | -9 | 3041.7435 | 0.2565 | 0
FIN | UNIDO | National CFC phase-out plan (fourth and fifth tranches) | Multi-Year | EUR | YUG | PHA | 60 | INV | 36 | A | I |  | 268 | 268 | 0 | 0 | 2010-04-01 | 2010-12-01 | 2011-04-01 |  | 2014-06-01 | 2014-09-01 | 193500 | -145499 | 48001 | 48001.21 | 100% | -0.21 | 0 |  | 14513 | -10913 | 3600.0907 | -0.09075 | 0
FIN | UNIDO | Preparation for HCFC phase-out investment activities (refrigeration air-conditioning manufacturing sector) | Individual | EUR | YUG | REF | 61 | PRP | 37 | A | I |  | 0 | 0 | 0 | 0 | 2010-07-01 | 2010-11-01 | 2011-07-01 |  | 2011-07-01 | 2011-12-01 | 60000 | -388.17 | 59611.83 | 59611.83 | 100% | 0 | 0 |  | 4500 | -29 | 4470.8872 | 0.11275 | 0 |  |  |  |  | NON-INV
FIN | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | EUR | YUG | PHA | 62 | INV | 38 | A | I | HCFC | 2.3 | 2.3 | 0 | 0 | 2010-12-01 | 2010-12-01 | 2012-12-01 |  | 2016-12-01 | 2017-12-01 | 360130 | -5784 | 354346 | 354345.76 | 100% | 0.24 | 0 |  | 27010 | -434 | 26575.932 | 0.068 | 0 |  |  |  |  | INV |  |  | 2020-12-01
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | EUR | YUG | PHA | 62 | TAS | 39 | A | I |  | 0 | 0 | 0 | 0 | 2010-12-01 | 2012-02-01 | 2012-12-01 |  | 2014-12-01 | 2016-12-01 | 26000 | -970 | 25030 | 25030 | 100% | 0 | 0 | 0 | 3380 | -126.1 | 3253.9 | 0 | 0 | [7 empty] | 2020-12-01 | 0 | 0
FIN | UNIDO | Extension of institutional strengthening project (phase IV: 12/2011-11/2013) | Individual | EUR | YUG | SEV | 65 | INS | 40 | N | I |  | 0 | 0 | 0 | 0 | 2011-11-01 | 2013-01-01 | 2013-11-01 |  | 2015-12-01 | 2017-08-01 | 131300 | -4781.98 | 126518.02 | 126518.02 | 100% | 0 | 0 |  | 9848 | -359 | 9488.8515 | 0.1485 | 0 |  |  |  |  | NON-INV
COM | UNIDO | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | EUR | YUG | PHA | 71 | INV | 41 | A | I | HCFC | 2.7 | 2.7 | 0 | 0 | 2013-12-01 | 2016-09-01 | 2016-12-01 |  | 2018-12-01 |  | 444130 | 0 | 444130 | 443975.79 | 99.97% | 154.21 | 0 | 1 | 33310 | 0 | 33298.1842 | 11.8158 | 0 | Financial closure was processed. | Project was financially closed in April 2020. Fund balance was returned at the 85th meeting in 2020. |  |  | INV |  |  | 2020-12-01
FIN | UNIDO | Verification report for stage I of HCFC phase-out management plan | Individual | EUR | YUG | PHA | 71 | TAS | 42 | A | I |  | 0 | 0 | 0 | 0 | 2013-12-01 | 2015-11-01 | 2016-11-01 |  | 2017-12-01 | 2018-04-23 | 30000 | 0 | 30000 | 29999.99 | 100% | 0.01 | 0 |  | 2700 | 0 | 2699.9991 | 0.0009 | 0 |  |  |  |  | NON-INV
FIN | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | EUR | YUG | PHA | 71 | TAS | 43 | A | I |  | 0.2 | 0.2 | 0 |  | 2013-12-01 | 2015-11-01 | 2016-12-01 |  | 2018-12-01 | 2019-12-01 | 27500 | 0 | 27500 | 27499.81 | 100% | 0.19 | 0 | 0 | 3575 | 0 | 3574.9753 | 0.0247 | 0 | Project completed. | Project financially completed | [5 empty] | 2020-12-01 | 0 | 0
FIN | UNIDO | Extension of institutional strengthening project (phase V: 12/2013-11/2015) | Individual | EUR | YUG | SEV | 71 | INS | 44 | N | I |  | 0 | 0 | 0 | 0 | 2013-12-01 | 2014-06-01 | 2015-11-01 |  | 2017-12-01 | 2018-06-25 | 131300 | -55667 | 75633 | 75632.75 | 100% | 0.25 | 0 |  | 9191 | -3897 | 5294.2925 | -0.2925 | 0 |  |  |  |  | NON-INV
FIN | UNIDO | Survey of ODS alternatives at the national level | Individual | EUR | YUG | SEV | 74 | TAS | 45 | A | I |  | 0 | 0 | 0 | 0 | 2015-05-01 | 2016-05-01 | 2016-05-01 |  | 2016-12-01 | 2017-05-17 | 70000 | -421 | 69579 | 69578.95 | 100% | 0.05 | 0 |  | 6300 | -38 | 6262.1055 | -0.1055 | 0 |  |  |  |  | NON-INV
COM | UNIDO | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | EUR | YUG | PHA | 79 | INV | 46 | A | I |  | 0 | 0 | 0 | 0 | 2017-07-01 | 2018-05-01 | 2020-07-01 |  | 2019-12-31 |  | 67800 | 0 | 67800 | 65946.59 | 97.27% | 1853.41 | 0.03 | 1 | 5085 | 0 | 4945.9942 | 139.0057 | 0.00225 | Project operationally completed Dec 2019 | Financial closure in processing |  |  | INV |  |  | 2020-12-01
ONG | UNEP | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | EUR | YUG | PHA | 79 | TAS | 47 | A | I |  | 0 |  | 0 |  | 2017-07-01 | 2018-01-01 | 2020-07-01 | 2021-03-01 |  |  | 14450 | 0 | 14450 | 2672.48 | 18.49% | 11777.52 | 11777.52 | 8833.14 | 1879 | 0 | 347.5149 | 1531.4851 | 1531.4851 | Newly approved project | Progress January - May 2020: Ozone pages published in the quarterly journal of the Serbian RAC association SMEITS / KGH in February 2020, focusing on the ECA meeting with Montreal Protocol officers and RAC associations / experts in Belgrade in December 2019, the parallel technology roundtable and exhibition at the SMEITS / KGH congress, the site visit of a hospital with co-generation of heating, cooling and hot water production and the tracking table on RAC action, training materials, presentations, posters with tariff codes and brochures on mislabeling of refrigerant cylinders and counterfeit refrigerants have been prepared for a series of training events for customs officers. The training events are scheduled in September 2020 for about 80 customs officers from six different customs offices and will take place at four different locations. They will cover HCFCs and HFCs and be co-financed by projects approved for UNIDO and UNEP. The Government requests revision of the completion date in the agreement due to COVID-19 delays (until March 2021). | [5 empty] | 2020-12-01 | 11777.52 | 1531.4851
ONG | UNIDO | Extension of institutional strengthening project (phase VI: 12/2017-11/2019) | Individual | EUR | YUG | SEV | 80 | INS | 48 | N | I |  | 0 | 0 | 0 | 0 | 2017-11-01 | 2018-03-01 | 2019-11-01 | 2020-12-01 |  |  | 168064 | 0 | 168064 | 68750.62 | 40.91% | 99313.38 | 35320.94 | 50000 | 11764 | 0 | 4812.5434 | 6951.4566 | 2472.4658 | In 2019 activities were implemented as per NOU annual work plan. No delays have occurred. NOU was fully staffed, awareness activities and relevant meetings with stakeholders from central administration were held. IS Terminal report was submitted to 84 ExCom. Data reports submitted to the MLF and Ozone Secretariats. Milestone 1: Annual data reports submitted - Yes Milestone 2: NOU staff contracts released - Yes Milestone 3: Public awareness activities organized - Yes Was there any delay during the reporting year? No Any recurring problem? No Any impact on project completion date: No Any action required by Executive Committee? No | Activities scheduled for first quarter of 2020 slightly delayed due to COVID. |  |  | NON-INV
ONG | UNIDO | Verification report on the implementation of the HCFC phase-out management plan | Individual | EUR | YUG | PHA | 82 | TAS | 49 | A | I |  | 0 | 0 | 0 | 0 | 2018-12-01 | 2019-07-01 | 2020-12-01 | 2020-12-31 |  |  | 30000 | 0 | 30000 | 14713.27 | 49.04% | 15286.73 | 0 | 15000 | 2700 | 0 | 1324.1943 | 1375.8057 | 0 | Verification Report for the years 2018 and 2019 was contracted with NC. Verification Report for the year 2018 was submitted to 84 ExCom. | Verification Report for the year 2019 is pending since field trips could not be organized due to COVID and will be re-scheduled for the second half of 2020. |  |  | NON-INV
ONG | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | Individual | EUR | YUG | PHA | 82 | PRP | 50 | A | I |  | 0 | 0 | 0 | 0 | 2018-12-01 | 2019-01-01 | 2019-12-01 | 2020-12-20 |  |  | 30000 | 0 | 30000 | 25362.07 | 84.54% | 4637.93 | 0 | 4600 | 2100 | 0 | 1775.3449 | 324.6551 | 0 | HCFC survey completed, Stakeholders workshop held, national and international experts recruited. Project document is being prepared. Milestones achieved: HCFC survey completed? YES Stakeholders workshop held? YES Experts recruited? YES Draft document completed? Under preparation Actions towards next goals: Submit the project document at the 85th meeting in 2020. Was there any delay during the reporting year? YES Any recurring problem? YES Any impact on project completion date: YES Any action required by Executive Committee? NO | Project document was submitted at the 85th meeting and approved. |  |  | NON-INV
ONG | UNIDO | HCFC phase-out management plan (stage I, fourth tranche) | Multi-Year | EUR | YUG | PHA | 84 | INV | 51 | A | I |  | 0 | 0 | 0 |  | 2019-12-01 |  | 2020-12-01 | 2020-12-31 |  |  | 25700 | 0 | 25700 | 0 | 0% | 25700 | 0 | 5000 | 1928 | 0 | 0 | 1928 | 0 | Project approved at the 84th meeting in December 2019. | Work plan for the year 2020 developed and handbook for AC servicing sector technicians certification scheme is under development. Milestones achieved: PAD issued: Yes, January 2020 First mission/working arrangements agreed: Work plan - agreed Handbook for technicians: Under preparation Was there any delay during the reporting year? No. Any recurring problem? No. Any impact on project completion date: No. Any action required by Executive Committee? No. | [5 empty] | 2020-12-01
ONG | UNEP | HCFC phase-out management plan (stage I, fourth tranche) | Multi-Year | EUR | YUG | PHA | 84 | TAS | 52 | A | I |  | 0 |  | 0 |  | 2019-12-01 |  | 2020-12-01 | 2021-06-01 |  |  | 7550 | 0 | 7550 | 0 | 0% | 7550 | 0 | 1887.5 | 981 | 0 | 0 | 981 | 0 | Newly approved project | Progress January - May 2020: Agreement of USD 7,550 signed in February 2020. Cash advance payment released in May 2020. The Government requests revision of the completion date in the agreement due to COVID-19 delays (until March 2021). | [5 empty] | 2020-12-01 | 0 | 0
ONG | UNIDO | Extension of institutional strengthening project (phase VII: 12/2019-11/2021) | Individual | EUR | YUG | SEV | 84 | INS | 53 | N | I |  | 0 | 0 | 0 |  | 2019-12-01 |  | 2021-11-01 | 2021-11-01 |  |  | 168064 | 0 | 168064 | 0 | 0% | 168064 | 0 | 50000 | 11764 | 0 | 0 | 11764 | 0 | Project approved at the 84th meeting in December 2019. | Activities scheduled for first quarter of 2020 slightly delayed due to COVID.
FIN | UNEP | Country programme preparation | Individual | AFR | ZAM | SEV | 04 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-09-01 | 1992-09-01 |  | 1992-10-01 | 1992-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | [8 empty] | 0 | 0
FIN | UNEP | Institutional strengthening | Individual | AFR | ZAM | SEV | 09 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1994-12-01 | 1996-03-01 |  | 1999-12-01 | 2004-05-01 | 75600 | 0 | 75600 | 75600 | 100% | 0 | 0 | 0 | 9828 | 0 | 9828 | 0 | 0 |  |  |  | 1999-12-01 |  |  |  |  | 0 | 0
FIN | UNIDO | Preparation of a training and certification programmes for refrigeration technicians and preparation of investment projects for the refrigeration sector | Individual | AFR | ZAM | REF | 15 | TAS | 03 | A | I |  | 0 | 17.7 | 0 | 0 | 1994-12-01 | 1996-02-01 | 1995-06-01 |  | 1996-12-01 | 1999-08-01 | 82100 | -5625 | 76475 | 76475 | 100% | 0 | 0 |  | 10673 | -746.98 | 9926 | 0.02 | 0 |  |  |  |  | NON-INV
FIN | UNDP | Project preparation assistance | Individual | AFR | ZAM | SEV | 17 | PRP | 04 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-07-01 | 1995-10-01 | 1996-03-01 |  | 1996-06-01 | 1998-12-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Project preparation assistance | Individual | AFR | ZAM | SEV | 18 | PRP | 05 | A | I | No_ODP | 0 | 0 | 0 | 0 | 1995-11-01 | 1995-12-01 | 1996-11-01 |  | 1996-11-01 | 1998-12-01 | 5000 | 0 | 5000 | 5000 | 100% | 0 | 0 | 0 | 650 | 0 | 650 | 0 | 0 | Completed in 1996. Financially completed in 1998. |  | 1995 |  | Investment
FIN | UNDP | Implementation of a national programme for recovery and recycling of refrigerant | RMP-Component | AFR | ZAM | REF | 19 | TAS | 06 | A | I | CFC | 7.2 | 7.2 | 0 | 0 | 1996-05-01 | 1997-05-01 | 1997-11-01 |  | 1997-12-01 | 2000-12-01 | 106320 | -240 | 106080 | 106080 | 100% | 0 | 0 | 0 | 13822 | -31 | 13790.4 | 0.6 | 0 | Completed in 1997. Financially completed in 2000. |  | 1996 |  | Investment
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | ZAM | REF | 23 | PRP | 07 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 2002-05-01 | 1998-03-01 |  | 1998-07-01 | 2000-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | ZAM | REF | 26 | TAS | 08 | A | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2001-05-01 | 2004-07-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | RMP completed, RMP update approved in 42nd Excom
CLO | UNIDO | Preparation of a demonstration project (tobacco, flowers) | Individual | AFR | ZAM | FUM | 27 | PRP | 09 | A | I |  | 0 | 0 | 0 | 0 | 1999-03-01 |  | 1999-12-01 |  |  | 2001-03-01 | 30000 | -30000 | 0 | 0 | #DIV/0! | 0 | 0 |  | 3900 | -3900 | 0 | 0 | 0
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organizations in methyl bromide communication | Individual | AFR | ZAM | FUM | 30 | TAS | 10 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -9259 | 15741 | 15741 | 100% | 0 | 0 | 0 | 3250 | -1203.67 | 2046.33 | 0 | 0 | [8 empty] | 0 | 0
FIN | UNEP | Renewal of institutional strengthening | Individual | AFR | ZAM | SEV | 30 | INS | 11 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2004-08-01 | 2002-07-01 |  | 2004-12-01 | 2008-12-01 | 50400 | 0 | 50400 | 50400 | 100% | 0 | 0 | 0 | 6552 | 0 | 6552 | 0 | 0 | [8 empty] | 0 | 0
FIN | Germany | Project preparation for a refrigerant management plan update | RMP Update | AFR | ZAM | REF | 37 | PRP | 12 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-05-01 | 2003-08-01 |  | 2004-01-01 | 2004-05-01 | 15000 | 0 | 15000 | 15000 | 100% | 0 | 0 | 0 | 1950 | 0 | 1950 | 0 | 0 | RMP update approved at the 42nd meeting
FIN | Germany | Refrigerant management plan update: refrigeration and air conditioning sector | RMP Update | AFR | ZAM | REF | 42 | TAS | 13 | A | I |  | 23.3 | 23.3 | 0 |  | 2004-04-01 | 2004-07-01 | 2007-04-01 |  | 2009-10-01 | 2011-12-01 | 136000 | -7474 | 128526 | 128526 | 100% | 0 | 0 | 0 | 17680 | -971.62 | 16708 | 0.38 | 0 | Funds returned to MLF at 65th meeting (UNEP/ozL.Pro/ExCom/65/60 Annex IV
FIN | UNEP | Extension of institutional strengthening project (phase III) | Individual | AFR | ZAM | SEV | 44 | INS | 15 | A | I |  | 0 | 0 | 0 | 0 | 2004-12-01 | 2005-09-01 | 2006-12-01 |  | 2009-03-01 | 2011-03-01 | 65520 | 0 | 65520 | 65520 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
FIN | UNIDO | Training and awareness workshop in the solvents and process agents (CTC and TCA) sectors | Individual | AFR | ZAM | SOL | 45 | TAS | 16 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-09-01 | 2006-04-01 |  | 2006-12-01 | 2008-05-01 | 40000 | -1745 | 38255 | 38255 | 100% | 0 | 0 |  | 3600 | -157 | 3442.95 | 0.05 | 0 |  |  |  |  | NON-INV
FIN | UNEP | Project preparation for a terminal phase-out management plan | RMP | AFR | ZAM | PHA | 50 | PRP | 17 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2007-03-01 | 2007-11-01 |  | 2007-12-01 | 2013-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 | 0 | [8 empty] | 0 | 0
FIN | UNEP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | ZAM | PHA | 53 | TAS | 18 | A | I |  | 0 | 0 | 0 | 0 | 2007-11-01 | 2008-03-01 | 2009-03-01 |  | 2009-03-01 | 2010-12-01 | 94000 | 0 | 94000 | 94000 | 100% | 0 | 0 | 0 | 12220 | 0 | 12220 | 0 | 0 | [8 empty] | 0 | 0
FIN | UNDP | Terminal phase-out management plan for CFCs (first tranche) | Multi-Year | AFR | ZAM | PHA | 53 | INV | 19 | N | I | CFC | 0 | 0 | 0 | 0 | 2007-11-01 | 2009-10-01 | 2009-11-01 |  | 2011-12-01 | 2013-02-01 | 109000 | -30490 | 78510 | 78510 | 100% | 0 | 0 | 0 | 9810 | -2744 | 7065.9 | 0.1 | 0 | Financially completed in 2013. |  | 2007 |  | Investment
FIN | UNIDO | Project preparation in the fumigants sector (soil fumigation) | Individual | AFR | ZAM | FUM | 54 | PRP | 20 | A | I |  | 0 | 0 | 0 | 0 | 2008-04-01 | 2008-09-01 | 2009-03-01 |  | 2008-12-01 | 2011-09-01 | 35000 | -9714.17 | 25285.83 | 25285.83 | 100% | 0 | 0 |  | 2625 | -729 | 1896.4372 | -0.43725 | 0 |  |  |  |  | NON-INV
FIN | UNIDO | Technical assistance for the total phase-out of methyl bromide in tobacco, cut flowers, horticulture and post harvest uses | Individual | AFR | ZAM | FUM | 56 | INV | 21 | A | I | MBR | 7.4 | 7.4 | 0 | 0 | 2008-11-01 | 2009-12-01 | 2011-11-01 |  | 2016-12-01 | 2018-04-20 | 289548 | -2 | 289546 | 289545.5 | 100% | 0.5 | 0 |  | 21716 | 0 | 21715.9125 | 0.0875 | 0 |  |  |  |  | INV
FIN | UNEP | Preparation of a HCFC phase-out management plan | RMP | AFR | ZAM | PHA | 56 | PRP | 22 | A | I |  | 0 | 0 | 0 | 0 | 2008-11-01 | 2009-02-01 | 2009-11-01 |  | 2013-04-01 | 2014-04-01 | 85000 | -5000 | 80000 | 80000 | 100% | 0 | 0 | 0 | 11050 | -650 | 10400 | 0 | 0 | [8 empty] | 0 | 0
FIN | UNEP | Terminal phase-out management plan for CFCs (second tranche) | Multi-Year | AFR | ZAM | PHA | 57 | TAS | 23 | A | I | CFC-12 | 4.1 | 4.1 | 0 | 0 | 2009-04-01 | 2009-09-01 | 2010-03-01 |  | 2012-03-01 | 2013-03-01 | 42000 | -5000 | 37000 | 37000 | 100% | 0 | 0 | 0 | 5460 | -650 | 4810 | 0 | 0 | [8 empty] | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase IV) | Individual | AFR | ZAM | SEV | 57 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2011-11-01 | 2011-03-01 |  | 2012-03-01 | 2013-12-01 | 65520 | 0 | 65520 | 65520 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
FIN | UNEP | TPMP verification | Individual | AFR | ZAM | PHA | 57 | TAS | 25 | A | I |  | 0 | 0 | 0 | 0 | 2009-04-01 | 2010-09-01 | 2010-03-01 |  | 2013-04-01 | 2014-07-01 | 20000 | 0 | 20000 | 20000 | 100% | 0 | 0 | 0 | 2600 | 0 | 2600 | 0 | 0 |  |  |  | 2011-12-01 |  |  |  |  | 0 | 0
FIN | UNIDO | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | ZAM | PHA | 64 | INV | 26 | A | I | HCFC | 0.4 | 0.4 | 0 | 0 | 2011-07-01 | 2013-02-01 | 2016-07-01 |  | 2015-12-01 | 2017-05-01 | 70000 | -679.05 | 69320.95 | 69320.95 | 100% | 0 | 0 |  | 6300 | -61 | 6238.8855 | 0.1145 | 0 |  |  |  |  | INV |  |  | 2021-12-01
FIN | UNEP | HCFC phase-out management plan (stage I, first tranche) | Multi-Year | AFR | ZAM | PHA | 64 | TAS | 27 | A | I |  | 0 | 0 | 0 | 0 | 2011-07-01 | 2012-06-01 | 2013-07-01 |  | 2013-07-01 | 2019-12-01 | 40000 | -1365 | 38635 | 38635 | 100% | 0 | 0 | 0 | 5200 | -177.45 | 5022.55 | 0 | 0 | Project financially completed | Project financially completed | [5 empty] | 2021-12-01 | 0 | 0
FIN | UNEP | HCFC phase-out management plan (stage I, second tranche) | Multi-Year | AFR | ZAM | PHA | 71 | TAS | 28 | A | I |  | 0.3 |  | 0 |  | 2013-12-01 | 2016-04-01 | 2016-12-01 |  | 2017-12-01 | 2018-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | [7 empty] | 2021-12-01 | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase V: 12/2013-11/2015) | Individual | AFR | ZAM | SEV | 71 | INS | 29 | A | I |  | 0 |  | 0 |  | 2013-12-01 | 2016-04-01 | 2015-11-01 |  | 2019-05-01 | 2019-12-01 | 65520 | 0 | 65520 | 65520 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed | Project financially completed | [6 empty] | 0 | 0
FIN | UNEP | Survey of ODS alternatives at the national level | Individual | AFR | ZAM | SEV | 74 | TAS | 30 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-04-01 | 2016-05-01 |  | 2017-08-01 | 2018-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | [8 empty] | 0 | 0
FIN | UNEP | Extension of the institutional strengthening project (phase VI: 12/2016-11/2018) | Individual | AFR | ZAM | SEV | 77 | INS | 31 | A | I |  | 0 |  | 0 |  | 2016-12-01 | 2017-11-01 | 2018-11-01 |  | 2019-11-01 | 2019-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The final payment for SSFA with total amount of USD 85,000 was released to the country in December 2019. The Licensing system is fully operational. The quota for the year 2019 was issued to 4 importers and the Importers are complied with issued quotas for the year 2019. The NOU conducted two Steering Committee meetings in Feb 2019 and July 2019. Article 7 and CP data for the year 2019 was submitted. The NOU conducted 2 monitoring of importers and end-users. The NOU conducted training for 30 enforcement officers on prevention of illegal trade on 16th August in Ndola. Enforcement officers were equipped with one refrigerant identifier at the entry point. The Kigali Amendment was approved for ratification by the Zambian CABINET on 30th December 2019. The NOU conducted one meeting for 5 members of the industry associations management to discuss issues on World Refrigeration Day and the adopting of alternative to HFC technologies. The International Ozone Day for 2019 was commemorated in Chipata Town in the Eastern Region of the country. A stakeholder workshop was conducted and awareness match involving government, industry and Learning sectors. The NOU conducted one stakeholder awareness raising workshop for 50 participants to drum up support on the ratification of the Kigali Amendment. The media campaign was organized on the phase-down of HFCs as per Kigali amendment. The NOU participated in the following meetings: Second Global Inter-Regional Thematic meetings back to back with Parallel K-CEP Twinning Workshops, 17--22, 2019, Paris, France; Pilot NOU training workshop and back to back with Enabling Activities Project Workshop, 17-21 June, 2019, Seychelles; 31st Meeting of the Parties, 4-8 November, 2019, Rome, Italy. Project is completed satisfactorily. | Project financially completed | [6 empty] | 0 | 0
FIN | UNEP | HCFC phase-out management plan (stage I, third tranche) | Multi-year | AFR | ZAM | PHA | 77 | TAS | 32 | A | I |  | 0 |  | 0 |  | 2016-12-01 | 2017-11-01 | 2018-12-01 |  | 2018-12-01 | 2018-12-01 | 35000 | 0 | 35000 | 35000 | 100% | 0 | 0 | 0 | 4550 | 0 | 4550 | 0 | 0 | [7 empty] | 2021-12-01 | 0 | 0
ONG | UNIDO | HCFC phase-out management plan (stage I, third tranche) | Multi-Year | AFR | ZAM | PHA | 77 | INV | 33 | A | I | HCFC | 0.4 | 0 | 0 | 0 | 2016-12-01 |  | 2019-12-01 | 2021-12-31 |  |  | 70000 | 0 | 70000 | 0 | 0% | 70000 | 0 | 10000 | 6300 | 0 | 0 | 6300 | 0 | Feedback from NOU and UNEP (lead agency) is still pending. UNIDO contacted NOU Zambia requesting updates but no response received. Contact established with NOU Q2 2019. Follow up ongoing to finalize ToR. Milestones achieved: Milestone 1: First mission/Working arrangements (agreement/document signatures/PAD) PAD issued. Milestone 2: TOR -No Was there any delay during the reporting year? Yes - contact established Q2 2019. Any recurring problem? Yes - delayed responses in communication. Any impact on project completion date: No. Any action required by Executive Committee? No. | Contact established with NOU Q2 2019. Follow up is ongoing, mission delayed due to Covid-19 restrictions. Communication delayed. Milestones achieved: First mission undertaken/working arrangements agreed: No TOR completed/contract signed: No Beneficiaries identified: No Contract signed with beneficiaries: No Procurement contracts signed: No Equipment delivered to all beneficiaries: No Trainings organized: No Was there any delay during the reporting year? Yes, mission delayed due to Covid-19 restriction Any recurring problem? Yes, delayed responses in communication. Any impact on project completion date: No. Any action required by Executive Committee? No. |  |  | INV |  |  | 2021-12-01
ONG | UNEP | HCFC phase-out management plan (stage I, fourth tranche) | Multi-year | AFR | ZAM | PHA | 81 | TAS | 34 | A | I |  | 0.6 |  | 0 |  | 2018-06-01 |  | 2020-12-01 | 2020-12-01 |  |  | 30000 | 0 | 30000 | 0 | 0% | 30000 | 30000 | 15000 | 3900 | 0 | 0 | 3900 | 3900 | The SSFA was signed by the Government of Zambia in March 2019 with total amount of USD 30,000. The first payment was released to the country in April 2019. The first stakeholder’s workshop was organized by the NOU in June, 2019, Lusaka with the main goal to sensitize major stakeholders about HCFC phase out schedule, data survey and the Government’s strategy for phasing out of HCFCs. The second stakeholders meeting was organized by the NOU on 15 September,2019 in Chipata with the main goal to organise consultations with representatives of the government and major stakeholders. Three training workshops were organized for 75 RAC technicians on HCFC alternative technology in Ndola and Livingstone. Two Custom Officer’s training workshops/ were organized for 40 f Customs officers in August 2019 venue. The NOU and other Stakeholders reviewed and updated training curriculum for custom officers. The HPMP project progress is satisfactory implemented and it is on schedule. The Impact of these ozone protection activities is being felt due to the changes in technologies of cooling products. | The NOU continues to monitor imports and trade of ODS and ODS related equipment. Licensing system is fully operational. The quota for the year 2020 was issued to eligible importers. Delays in project activities are to be expected due to measures taken by the country related to COVID-19 outbreak, which resulted in postponing all meetings/ events planned in the first half of the year | [5 empty] | 2021-12-01 | 20000 | 2600
ONG | UNEP | Verification report on the implementation of the HCFC phase-out management plan | Individual | AFR | ZAM | PHA | 82 | TAS | 35 | A | I |  | 0 |  | 0 |  | 2018-12-01 | 2019-05-01 | 2020-12-01 | 2020-09-01 |  |  | 30000 | 0 | 30000 | 1191 | 3.97% | 28809 | 28000 | 14404.5 | 3900 | 0 | 154.83 | 3745.17 | 3640 | The Terms of Reference (ToR) for hiring the international consultant was prepared, cleared by the management and advertised in Nov 2019. The international consultant was recruited by UNEP to verify the national consumption in relation to the targets as set out in the Agreement between ExCom and Government of following the relevant decisions of the 64th ExCom and guidelines for the verification of national consumption targets for the multi-year agreements. The international consultant was recruited by UNEP to verify the national consumption in relation to the targets as set out in the Agreement between ExCom and Government of following the relevant decisions of the 64th ExCom and guidelines for the verification of national consumption targets for the multi-year agreements. The consultant prepared and presented the draft work plan which included timeline for conducting the verification as well as tasks and roles and responsibilities of each concerned stakeholders in the verification process. The consultant also informed the NOU about support/cooperation that was required from various stakeholders. The consultant reviewed the national legislation, policies and procedures on ODS import and export in Zambia and conducted an assessment of the existing licensing and quota system to control HCFC import and export. The consultant also reviewed official statistics on import and export maintained by different sources and analyzed and compare those statistics. In addition, the consultant conducted the necessary on-site visits and interviews, and analyzed and cross-check various data collected from different sources. The collected data was of 2016, 2017and 2018. The report was produced in English and provides detailed data demonstrating and confirming whether the consumption targets in the Agreement were achieved, whether there is existence of an operational licensing and quota system for HCFC imports and exports and whether the system is capable to ensure the country's compliance with the targets as set out in the Agreement between Zambia Government and the 64th ExCom. The project is progressing satisfactorily. | The consultant reviewed the national legislation, policies and procedures on ODS import and export in Zambia and conducted an assessment of the existing licensing and quota system to control HCFC import and export. The consultant also reviewed official statistics on import and export maintained by different sources and analyzed and compare those statistics. In addition, the consultant conducted the necessary on-site visits and interviews, and analyzed and cross-check various data collected from different sources. The collected data was of 2016, 2017, 2018and 2019. The report was produced in English and provided detailed data demonstrating and confirming whether the consumption targets in the Agreement were achieved, whether there is existence of an operational licensing and quota system for HCFC imports and exports and whether the system is capable to ensure the country's compliance with the targets as set out in the Agreement between Zambia Government and the 64th ExCom. The final draft report was prepared and sent to UNEP for further analysis and submission to MFS. The draft also included observations from the National Ozone Authority and comments from UNEP/CAP. | [6 empty] | 0 | 0
ONG | UNEP | Extension of the institutional strengthening project (phase VII: 7/2019-6/2021) | Individual | AFR | ZAM | SEV | 83 | INS | 36 | A | I |  | 0 |  | 0 |  | 2019-05-01 |  | 2021-06-01 | 2021-06-01 |  |  | 85000 | 0 | 85000 | 0 | 0% | 85000 | 85000 | 34000 | 0 | 0 | 0 | 0 | 0 | The SSFA was signed by the Government of Zambia in October 2019 with total amount of USD 85,000. The first payment was released to the country in October 2019. The Licensing system is fully operational. The quota for the year 2019 was issued to 4 importers and the Importers are complied with issued quotas for the year 2019. The NOU conducted two Steering Committee meetings in Feb 2019 and July 2019. Article 7 and CP data for the year 2019 was submitted. The NOU conducted 2 monitoring of importers and end-users. The NOU conducted training for 30 enforcement officers on prevention of illegal trade on 16th August in Ndola. Enforcement officers were equipped with one refrigerant identifier at the entry point. The Kigali Amendment was approved for ratification by the Zambian CABINET on 30th December 2019. The NOU conducted one meeting for 5 members of the industry associations management to discuss issues on World Refrigeration Day and the adopting of alternative to HFC technologies. The International Ozone Day for 2019 was commemorated in Chipata Town in the Eastern Region of the country. A stakeholder workshop was conducted and awareness match involving government, industry and Learning sectors. The NOU conducted one stakeholder awareness raising workshop for 50 participants to drum up support on the ratification of the Kigali Amendment. The media campaign was organized on the phase-down of HFCs as per Kigali amendment. The NOU participated in the following meetings: Second Global Inter-Regional Thematic meetings back to back with Parallel K-CEP Twinning Workshops, 17--22, 2019, Paris, France; NOU training workshop and back to back with Enabling Activities Project Workshop, 17-21 June, 2019, Seychelles; 31st Meeting of the Parties, 4-8 November, 2019, Rome, Italy. Project is progressing satisfactorily. | The NOU continues to monitor imports and trade of ODS and ODS related equipment. Licensing system fully operational and is in progress. Four importers have been issued with quotas for the year 2020. The NOU conducted one inspection visit to importers /suppliers in Lusaka. One training in monitoring of illegal ODS trade was conducted in Livingstone on 14th February 2020 and 15 Enforcement Officers trained. Delays in project activities are to be expected due to measures taken by the country related to COVID-19 outbreak, which resulted in postponing all meetings/ events planned in the first half of the year. | [6 empty] | 45000 | 0
ONG | UNIDO | Preparation of a HCFC phase-out management plan (stage II) | Individual | AFR | ZAM | PHA | 83 | PRP | 37 | A | I |  | 0 | 0 | 0 |  | 2019-05-01 |  | 2021-06-01 | 2021-06-30 |  |  | 10000 | 0 | 10000 | 0 | 0% | 10000 | 0 | 2000 | 700 | 0 | 0 | 700 | 0 | Project approved at the 83rd meeting in May 2019. Feedback from NOU and UNEP (lead agency) is still pending. UNIDO mission was planned for Q3/Q4 to agree on future implementation steps with NOU. UNIDO contacted NOU Zambia requesting updates but no response received. Contact established with NOU Q2 2019. Was there any delay during the reporting year? Yes. Any recurring problem? No. Any impact on project completion date: No. Project completion postponed to 2020 in line with lead agency submission plan. Any action required by Executive Committee? No. | Contact established with NOU. Follow up is ongoing. Coordination with LA on submission established. Follow up is ongoing, mission delayed due to Covid-19 restrictions. Communication delayed. Milestones achieved: HCFC survey completed? No Stakeholders workshop held? No Local institutions identified? No Experts recruited? No All technical input completed? No Draft document completed? No Actions towards next goals: Coordination and virtual meeting planning Was there any delay during the reporting year? Yes, mission delayed due to Covid-19 restriction Any recurring problem? Yes, delayed responses in communication. Any impact on project completion date: No. Any action required by Executive Committee? No.
ONG | UNEP | Preparation of a HCFC phase-out management plan (stage II) | Individual | AFR | ZAM | PHA | 83 | PRP | 38 | A | I |  | 0 |  | 0 |  | 2019-05-01 | 2019-10-01 | 2021-06-01 | 2021-06-01 |  |  | 20000 | 0 | 20000 | 5000 | 25% | 15000 | 15000 | 6000 | 2600 | 0 | 650 | 1950 | 1950 | The SSFA was signed by the Government of Zambia in October 2019 with total amount of USD 20,000. The first payment was released to the country in October 2019. The first stakeholder’s workshop was organized by the NOU in November 2019 with the main goal to sensitize major stakeholders about HCFC phase out schedule, data survey and the Government’s strategy for phasing out of HCFCs. Two national consultants were hired by the NOU for data surveys which includes appropriate methodology, data collection, evaluation and reporting. Consultants collected information on the current status and consumption of HCFCs in servicing sector using HCFC- 22 including industrial and commercial refrigeration sectors and end-user air conditioning sector. The Government of Zambia and consultants in close consultation with implementing agency drafted a preliminary strategy taking into consideration the results of the surveys, data analysis, consultation meetings as well as the policy and legislation review. The draft covers policy, training, investment and capacity building needs of the country. The project is progressing satisfactorily. | The second stakeholders meeting was organized by the NOU in Jan 2020 in Lusaka with the main goal to organise consultations with representatives of the government and major stakeholders to finalize the draft HPMP stage II project document. The HPMP was further refined and all comments were incorporated into the project document. The final HPMP stage II project document was submitted to Implementing Agency UNEP for review and further submission to Executive Committee. | [6 empty] | 7500 | 975
FIN | UNEP | Country programme preparation | Individual | AFR | ZIM | SEV | 09 | CPG | 01 | A | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-05-01 | 1994-06-01 |  | 1994-06-01 | 1994-12-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5200 | 0 | 5200 | 0 | 0 | [8 empty] | 0 | 0
FIN | UNEP | Institutional strengthening for the phase out of ODS and the establishment of an Ozone Office | Individual | AFR | ZIM | SEV | 13 | INS | 02 | A | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1996-06-01 | 1997-07-01 |  | 1999-10-01 | 2000-12-01 | 171050 | 0 | 171050 | 171050 | 100% | 0 | 0 | 0 | 22237 | 0 | 22237 | 0 | 0 |  |  |  | 1999-05-01 |  |  |  |  | 0 | 0
FIN | UNIDO | Preparation of projects in the refrigeration and halon sectors | Individual | AFR | ZIM | SEV | 14 | PRP | 03 | A | I |  | 0 | 0 | 0 | 0 | 1994-09-01 | 1995-02-01 | 1995-03-01 |  | 1997-11-01 | 1999-08-01 | 40000 | -463 | 39537 | 39537 | 100% | 0 | 0 |  | 5200 | -68.38 | 5132 | -0.38 | 0 |  |  |  |  | NON-INV
FIN | UNIDO | CFC refrigerant recovery and reclaim project | RMP | AFR | ZIM | REF | 17 | TAS | 04 | A | I | CFC | 47 | 47 | 0 | 0 | 1995-07-01 | 1996-03-01 | 1996-07-01 |  | 1996-12-01 | 1998-08-01 | 312300 | -143 | 312157 | 312157 | 100% | 0 | 0 |  | 40599 | -82.94 | 40516 | 0.06 | 0 |  |  |  |  | NON-INV
FIN | IBRD | Project preparation |  | AFR | ZIM | SEV | 18 | PRP | 05 | A | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-01 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 50000 | 0 | 50000 | 50000 | 100% | 0 | 0 | 0 | 6500 | 0 | 6500 | 0 | 0 |  |  |  |  | Non-INV | 0
FIN | IBRD | Conversion of CFC-12 commercial refrigeration equipment production to HFC-134a and HCFC-22 refrigerant, and CFC-11 to HCFC-141b as the blowing agent for foam insulation at Ref-air Refrigeration | Individual | AFR | ZIM | REF | 20 | INV | 06 | N | I | CFC | 5.3 | 5.3 | 0 | 0 | 1996-10-01 | 1999-03-01 | 2000-10-01 |  | 2000-11-01 | 2000-11-01 | 43382 | 0 | 43382 | 43382 | 100% | 0 | 0 | 0 | 5640 | 0 | 5640 | 0 | 0 | Because of economic difficulties in Zimbabwe (including significant local currency devaluation and unavailability of forex), not much progress was made until CY00 and the project was completed by 11/00. |  |  | 1999-12-01 | INV | 0
FIN | IBRD | Conversion of CFC-12 commercial refrigeration equipment production to HFC-134a and HCFC-22 refrigerant, and CFC-11 to HCFC-141b as the blowing agent for foam insulation at Commercial Refrigeration | Individual | AFR | ZIM | REF | 20 | INV | 07 | N | I | CFC | 6.9 | 6.9 | 0 | 0 | 1996-10-01 | 1999-03-01 | 2000-10-01 |  | 2001-08-01 | 2001-08-01 | 156636 | -15061 | 141575 | 141575 | 100% | 0 | 0 | 0 | 20363 | -1958 | 18405 | 0 | 0 | Project completed. |  |  | 1999-12-01 | INV | 0
FIN | IBRD | Conversion of CFC-12 refrigerator production to HFC-134a refrigerant and CFC-11 to HCFC-141b as the blowing agent for foam insulation at Capri Refrigeration | Individual | AFR | ZIM | REF | 20 | INV | 08 | N | I | CFC | 5.9 | 5.9 | 0 | 0 | 1996-10-01 | 1998-05-01 | 1998-10-01 |  | 1999-11-01 | 1999-11-01 | 106695 | 0 | 106695 | 106695 | 100% | 0 | 0 | 0 | 13870 | 0 | 13870 | 0 | 0 | CFC-11 portion completed 2/97 and CFC-12 portion completed 6/99, but because of the economic difficulties in Zimbabwe (including significant local currency devaluation) and the change of ownership of the company, not much progress was made during CY98. The project was completed in 08/99. |  |  | 1999-12-01 | INV | 0
FIN | IBRD | Conversion of CFC-12 refrigerator production to HFC-134a refrigerant and CFC-11 to cyclopentane as the blowing agent for foam insulation at Imperial Derby Refrigeration Ltd. | Individual | AFR | ZIM | REF | 20 | INV | 09 | N | I | CFC | 14 | 12.9 | 0 | 0 | 1996-10-01 | 1998-01-01 | 1997-12-01 |  | 1996-03-01 | 2001-05-01 | 310000 | -88275 | 221725 | 221725 | 100% | 0 | 0 | 0 | 40300 | -11475.65 | 28824 | 0.35 | 0 | Project completed. Funds returned at the 35th ExCom. |  |  | 1999-12-01 | INV | 0
FIN | IBRD | Conversion of CFC-12 commercial refrigeration equipment production to HFC-134a and HCFC-22 refrigerant, and CFC-11 to HCFC-141b as the blowing agent for foam insulation at Ajax Refrigeration | Individual | AFR | ZIM | REF | 20 | INV | 10 | N | I | CFC | 3.5 | 3.5 | 0 | 0 | 1996-10-01 | 1999-03-01 | 2001-10-01 |  | 1997-01-01 | 2001-08-01 | 61966 | 0 | 61966 | 61966 | 100% | 0 | 0 | 0 | 8056 | 0 | 8056 | 0 | 0 | Company taken over by Commercial Refrigeration and now treated as 2nd production line at Commercial. Project combined with that of Commercial Refrigeration as approved. Financial completion date is the same as Commercial. |  |  | 1999-12-01 | INV | 0
FIN | UNIDO | Project formulation in the methyl bromide sector | Individual | AFR | ZIM | FUM | 22 | PRP | 11 | A | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-06-01 | 1997-07-01 |  | 1999-01-01 | 2001-07-01 | 8000 | -624 | 7376 | 7376 | 100% | 0 | 0 |  | 1040 | -82.68 | 957 | 0.32 | 0 |  |  |  | 1999-02-01
FIN | Germany | Development of a refrigerant management plan | RMP | AFR | ZIM | REF | 23 | PRP | 12 | N | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-03-01 | 1998-03-01 |  | 1998-07-01 | 2000-06-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project preparation led to project proposal for implementation.
FIN | UNIDO | Two alternatives to the use of methyl bromide in the production of tobacco drought-resistant seedlings: non-soil cultivation and low-dose chemicals | Individual | AFR | ZIM | FUM | 23 | DEM | 13 | A | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 1998-06-01 | 1999-11-01 |  | 2000-12-01 | 2002-09-01 | 370700 | -17402 | 353298 | 353298 | 100% | 0 | 0 |  | 48191 | -2335 | 45856 | 0 | 0
FIN | UNDP | Project preparation for a methyl bromide alternative demonstration project | Individual | AFR | ZIM | FUM | 24 | PRP | 14 | N | I | No_ODP | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-05-01 | 1998-12-01 |  | 1998-12-01 | 2003-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 1998. Financially completed in 2003. |  | 1998 |  | Investment
FIN | Germany | Implementation of the RMP: assistance in the design of policies and regulations | RMP | AFR | ZIM | REF | 26 | TAS | 15 | A | I |  | 0 |  | 0 |  | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 2003-08-01 | 2004-07-01 | 45000 | 0 | 45000 | 45000 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project completed. PCR submitted.
CLO | Germany | Project preparation for phasing out of ODS at the domestic refrigeration factory Fridgemaster | Individual | AFR | ZIM | REF | 26 | PRP | 16 | N | I |  | 0 | 0 | 0 | 0 | 1998-11-01 |  | 1999-12-01 |  |  | 1999-03-01 | 25000 | -25000 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Project will not be implemented.
FIN | UNDP | Alternatives to the use of methyl bromide on stacked bags of maize under gas proof PVC sheets and plastic cocoons (storage) | Individual | AFR | ZIM | FUM | 27 | DEM | 17 | N | I | MeBr | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-09-01 | 2000-04-01 |  | 2000-12-01 | 2003-04-01 | 212850 | -10142 | 202708 | 202708 | 100% | 0 | 0 | 0 | 27671 | -1319 | 26351.98 | 0.02 | 0 | Completed in 2000. Financially completed in 2003. |  | 1999 |  | Investment
FIN | UNIDO | Preparation of a phase-out project in the methyl bromide sector (cut flowers) | Individual | AFR | ZIM | FUM | 30 | PRP | 18 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-06-01 | 2001-04-01 |  | 2000-12-01 | 2002-09-01 | 30000 | -570 | 29430 | 29430 | 100% | 0 | 0 |  | 3900 | -80 | 3820 | 0 | 0
FIN | UNEP | Enhancing the capability of local agricultural organizations and non-governmental organizations in methyl bromide communication | Individual | AFR | ZIM | FUM | 30 | TAS | 19 | A | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-11-01 | 2001-03-01 |  | 2001-12-01 | 2003-06-01 | 25000 | -2765 | 22235 | 22235 | 100% | 0 | 0 | 0 | 3250 | -359 | 2891 | 0 | 0 | [8 empty] | 0 | 0
FIN | UNEP | Renewal of institutional strengthening (phase II) | Individual | AFR | ZIM | SEV | 28 | INS | 20 | A | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 1999-10-01 | 2001-08-01 |  | 2001-12-01 | 2003-06-01 | 114033 | 0 | 114033 | 114033 | 100% | 0 | 0 | 0 | 14824 | 0 | 14824 | 0 | 0 |  |  |  | 2001-06-01 |  |  |  |  | 0 | 0
FIN | UNIDO | Phase-out of methyl bromide in cut flowers | Individual | AFR | ZIM | FUM | 31 | INV | 21 | A | I | MBR | 132 | 132 | 0 | 0 | 2000-07-01 | 2001-03-01 | 2004-08-01 |  | 2006-12-01 | 2010-03-01 | 904200 | -10988.63 | 893211.37 | 893211 | 100% | 0.37 | 0 |  | 109462 | -1209 | 108253 | 0 | 0 |  |  |  |  | INV
FIN | UNIDO | Project preparation in the fumigants (tobacco) sector | Individual | AFR | ZIM | FUM | 33 | PRP | 22 | A | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2002-02-01 | 2002-04-01 |  | 2002-12-01 | 2004-03-01 | 30000 | -600 | 29400 | 29400 | 100% | 0 | 0 |  | 3900 | -84 | 3816 | 0 | 0 |  |  |  |  | INV
FIN | UNDP | Project preparation in the fumigation storage sector | Individual | AFR | ZIM | FUM | 33 | PRP | 23 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-04-01 | 2002-04-01 |  | 2001-12-01 | 2003-12-01 | 25000 | 0 | 25000 | 25000 | 100% | 0 | 0 | 0 | 3250 | 0 | 3250 | 0 | 0 | Completed in 2001. Financially completed in 2003. |  | 2001 |  | Investment
FIN | UNEP | Renewal of institutional strengthening project | Individual | AFR | ZIM | SEV | 34 | INS | 24 | A | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-01-01 | 2003-08-01 |  | 2004-07-01 | 2004-12-01 | 114033 | 0 | 114033 | 114033 | 100% | 0 | 0 | 0 | 14824 | 0 | 14824 | 0 | 0 | [8 empty] | 0 | 0
FIN | Germany | Project preparation for a terminal ODS phase-out management plan | Individual | AFR | ZIM | PHA | 37 | PRP | 25 | A | I |  | 0 |  | 0 |  | 2002-07-01 | 2003-09-01 | 2003-08-01 |  | 2004-10-01 | 2004-12-01 | 62760 | 0 | 62760 | 62760 | 100% | 0 | 0 | 0 | 8159 | 0 | 8159 | 0 | 0 | TPMP first tranche approved at 44th ExCom.
FIN | UNDP | Project preparation for the re-formulation of solvent technical assistance | Individual | AFR | ZIM | SOL | 42 | PRP | 26 | A | I | No_ODP | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-07-01 | 2005-04-01 |  | 2006-12-01 | 2006-12-01 | 24000 | 0 | 24000 | 24000 | 100% | 0 | 0 | 0 | 1800 | 0 | 1800 | 0 | 0 | Completed in 2006. Financially completed in 2006. |  | 2004 |  | Investment
FIN | UNEP | Renewal of the institutional strengthening project (phase IV) | Individual | AFR | ZIM | SEV | 43 | INS | 27 | A | I | CFC | 12.2 | 12.2 | 0 | 0 | 2004-07-01 | 2004-10-01 | 2006-07-01 |  | 2006-11-01 | 2009-06-01 | 148242 | 0 | 148242 | 148242 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
FIN | Germany | Terminal phase-out management plan for CFCs (first tranche) | Individual | AFR | ZIM | PHA | 44 | INV | 29 | A | I |  | 0 |  | 0 |  | 2004-12-01 | 2005-03-01 | 2006-12-01 |  | 2007-06-01 | 2007-10-01 | 280000 | 0 | 280000 | 280000 | 100% | 0 | 0 | 0 | 36400 | 0 | 36400 | 0 | 0 | Project was completed and the 2nd tranche approved in March 2007.
FIN | UNIDO | Project preparation in the fumigants (methyl bromide) sector (phase out in tobacco seedling) | Individual | AFR | ZIM | FUM | 45 | PRP | 30 | A | I |  | 0 | 0 | 0 | 0 | 2005-04-01 | 2005-06-01 | 2006-04-01 |  | 2005-12-01 | 2005-12-01 | 15000 | -599 | 14401 | 14401 | 100% | 0 | 0 |  | 1125 | -46.65 | 1078 | 0.35 | 0 |  |  |  |  | NON-INV
CLO | UNDP | Project preparation for a fumigant (methyl bromide) project | Individual | AFR | ZIM | FUM | 45 | PRP | 31 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2005-04-01 |  | 2006-04-01 |  |  | 2006-12-01 | 20000 | -20000 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 1500 | -1500 | 0 | 0 | 0 | Canceled in 2006. Financially completed in 2006. |  | 2005 |  | Investment
FIN | UNIDO | Total phase-out of methyl bromide used in tobacco seedlings (first tranche) | Multi-Year | AFR | ZIM | FUM | 47 | INV | 32 | A | I | MBR | 50 | 50 | 0 | 0 | 2005-11-01 | 2006-02-01 | 2007-12-01 |  | 2007-12-01 | 2009-09-01 | 1862486 | 0 | 1862486 | 1862486 | 100% | 0 | 0 |  | 139686 | 0 | 139686.45 | -0.45 | 0 |  |  |  |  | INV
FIN | UNIDO | Project preparation in the fumigant sector (grain storage) | Individual | AFR | ZIM | FUM | 48 | PRP | 33 | A | I |  | 0 | 0 | 0 | 0 | 2006-04-01 | 2006-08-01 | 2007-03-01 |  | 2006-12-01 | 2007-03-01 | 20000 | -807 | 19193 | 19193 | 100% | 0 | 0 |  | 1500 | -60 | 1440 | 0 | 0 |  |  |  |  | NON-INV
FIN | UNEP | Renewal of the institutional strengthening project (phase V) | Individual | AFR | ZIM | SEV | 50 | INS | 34 | A | I |  | 0 | 0 | 0 | 0 | 2006-11-01 | 2009-06-01 | 2008-11-01 |  | 2011-07-01 | 2011-12-01 | 148242 | 0 | 148242 | 148242 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
FIN | UNDP | Technical assistance for the phase-out of ODS in the solvent/sterilant sector | Individual | AFR | ZIM | SOL | 50 | TAS | 35 | N | I | TCA/CTC | 3.9 | 3.9 | 0 | 0 | 2006-11-01 | 2008-07-01 | 2008-05-01 |  | 2009-12-01 | 2011-10-01 | 60000 | -1229 | 58771 | 58771 | 100% | 0 | 0 | 0 | 5400 | -111 | 5289.0018 | -0.0017999 | 0 | Completed in 2009. Financially completed in 2011. |  | 2006 | 2010-01-01 | Non-Investment
FIN | UNIDO | Total phase-out of methyl bromide used in grain fumigation | Individual | AFR | ZIM | FUM | 50 | INV | 36 | A | I | MBR | 10.2 | 10.2 | 0 | 0 | 2006-11-01 | 2007-01-01 | 2010-11-01 |  | 2008-12-01 | 2011-05-01 | 192073 | -246.25 | 191826.75 | 191827 | 100% | -0.25 | 0 |  | 17287 | -23 | 17264.43 | -0.43 | 0 |  |  |  |  | INV
FIN | UNIDO | Total phase-out of methyl bromide used in tobacco seedlings (second tranche) | Multi-Year | AFR | ZIM | FUM | 51 | INV | 37 | A | I | MBR | 120 | 120 | 0 | 0 | 2007-03-01 | 2007-11-01 | 2009-12-01 |  | 2008-12-01 | 2010-09-01 | 1862486 | -2 | 1862484 | 1862484 | 100% | 0 | 0 |  | 139686 | 0 | 139686.3 | -0.3 | 0 |  |  |  |  | INV
FIN | Germany | National phase-out of Annex A (Group I) substances (phase II, first tranche) | Multi-Year | AFR | ZIM | PHA | 51 | INV | 38 | A | I |  | 25 | 25 | 0 |  | 2007-03-01 | 2007-04-01 | 2009-12-01 |  | 2008-07-01 | 2008-10-01 | 175000 | 0 | 175000 | 175000 | 100% | 0 | 0 | 0 | 22347 | 0 | 22347 | 0 | 0 | Phase completed and 3rd tranche approved.
FIN | Germany | National phase-out of Annex A (Group I) substances (phase II, second tranche) | Multi-Year | AFR | ZIM | PHA | 54 | INV | 39 | A | I | CFC | 20 | 20 | 0 |  | 2008-04-01 | 2008-05-01 | 2009-03-01 |  | 2009-03-01 | 2009-03-01 | 175000 | 0 | 175000 | 175000 | 100% | 0 | 0 | 0 | 22347 | 0 | 22347 | 0 | 0 | 20 additional conversions under the incentive scheme were completed and 3 customs trainings were conducted.
FIN | Germany | National phase-out of Annex A (Group I) substances (phase II, third tranche) | Multi-Year | AFR | ZIM | PHA | 57 | INV | 40 | A | I | CFC | 20 |  | 0 |  | 2009-04-01 | 2009-04-01 | 2010-03-01 |  | 2010-06-01 | 2010-06-01 | 175000 | 0 | 175000 | 175000 | 100% | 0 | 0 | 0 | 22347 | 0 | 22347 | 0 | 0 | 4 customs officers were trained. 61 technicans were trained in state-of-the-art refrigeration servicing. 160 commercial refrigeration units were converted under the incentive scheme. 785 kgs of CFC refrigerant were recovered.
FIN | UNEP | Renewal of the institutional strengthening project (phase VI) | Individual | AFR | ZIM | SEV | 59 | INS | 41 | A | I |  | 0 | 0 | 0 | 0 | 2009-11-01 | 2011-05-01 | 2011-11-01 |  | 2013-03-01 | 2014-03-01 | 80297 | 67944 | 148241 | 148241 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
FIN | Germany | National phase-out of Annex A (Group I) substances (phase II, fourth tranche) | Multi-Year | AFR | ZIM | PHA | 60 | INV | 42 | A | I | CFC | 0 |  | 0 |  | 2010-04-01 | 2010-05-01 | 2011-04-01 |  | 2011-04-01 | 2011-04-01 | 40000 | 0 | 40000 | 40000 | 100% | 0 | 0 | 0 | 5108 | 0 | 5108 | 0 | 0 | Zimbabwe conducted 2 technican trainings targetting 27 participants as well as 1 customs training for 21 officers on the use of idenitifers capable of monitoring blends.
FIN | Germany | Preparation of a HCFC phase-out management plan | Individual | AFR | ZIM | PHA | 59 | PRP | 42 | A | I | HCFC | 0 |  | 0 |  | 2009-11-01 | 2010-05-01 | 2010-11-01 |  | 2011-12-01 | 2011-12-01 | 85000 | 0 | 85000 | 85000 | 100% | 0 | 0 | 0 | 11050 | 0 | 11050 | 0 | 0 | A comprehensive survey of the R&AC use was conducted and information put together into the HPMP, which included both foam and R&AC components. The project was approved at the 65th Excom.
FIN | Germany | Preparation for HCFC phase-out investment activities (foam sector) | Individual | AFR | ZIM | FOA | 63 | PRP | 43 | A | I | HCFC | 0 |  | 0 |  | 2011-04-01 | 2011-05-01 | 2012-03-01 |  | 2011-12-01 | 2012-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 |  | Zimbabwe identified foam manufacturers who were using pre-blended polyols and a conversion project for the manufacturers was developed and included into the HPMP, which was approved by the Excom at the 65th Excom.
FIN | Germany | HCFC phase-out management plan (stage I, first tranche) (conversion of the foam manufacturing sector:Capri Refrigeration, Ref Air, Commercial Refrigeration, Delfy Enterprises and Freezing Modern Way) | Multi-Year | AFR | ZIM | PHA | 65 | INV | 44 | A | I | HCFC | 6.1 | 4 | 0 |  | 2011-11-01 | 2011-12-01 | 2013-11-01 |  | 2014-06-01 | 2014-12-01 | 3737 | 311173 | 314910 | 314910 | 100% | 0 | 0 | 0 | 486 | 37213 | 37699 | 0 |  | 3 companies received the planned equipment to phase out HCFC use. | [6 empty] | 2021-12-01
FIN | Germany | HCFC phase-out management plan (stage I, first tranche) (refrigeration servicing sector) | Multi-Year | AFR | ZIM | PHA | 65 | INV | 45 | A | I | HCFC | 0 | 3.6 | 0 |  | 2011-11-01 | 2012-01-01 | 2013-11-01 |  | 2014-06-01 | 2014-12-01 | 3737 | 108244 | 111981 | 111981 | 100% | 0 | 0 | 0 | 486 | 12945 | 13431 | 0 |  | 8 VTCs received the training equipment, which was requested to conduct hands-on training. Zimbabwe trainers also participated in the regional TOT programme in Mauritius and have conducted 4 technician training courses. | Project has been completed. 2nd tranche has been approved at the 71st excom. | [5 empty] | 2021-12-01
FIN | UNEP | Renewal of the institutional strengthening project (phase VII: 4/2013-3/2015) | Individual | AFR | ZIM | SEV | 69 | INS | 46 | A | I |  | 0 |  | 0 |  | 2013-04-01 | 2013-11-01 | 2015-03-01 |  | 2016-08-01 | 2017-12-01 | 148242 | 0 | 148242 | 148242 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
FIN | Germany | HCFC phase-out management plan (stage I, second tranche) (conversion of the foam manufacturing sector: Capri Refrigeration, Ref Air, Commercial Refrigeration, Delfy Enterprises and Freezing Modern Way) | Multi-Year | AFR | ZIM | PHA | 71 | INV | 47 | A | I | HCFC | 2.1 | 2.1 | 0 |  | 2013-12-01 | 2014-07-01 | 2015-12-01 |  | 2015-12-01 | 2016-05-01 | 166762 | 0 | 166762 | 166762 | 100% | 0 | 0 | 0 | 19949 | 0 | 19949 | 0 |  | R141b use in pre-blended polyols has been now banned in the country and the companies have moved to alternatives. | [6 empty] | 2021-12-01
FIN | Germany | HCFC phase-out management plan (stage I, second tranche) (refrigeration servicing sector) | Multi-Year | AFR | ZIM | PHA | 71 | INV | 48 | A | I | HCFC | 1.8 |  | 0 |  | 2013-12-01 | 2014-07-01 | 2015-12-01 |  | 2015-12-01 | 2016-05-01 | 109165 | 0 | 109165 | 109165 | 100% | 0 | 0 | 0 | 13059 | 0 | 13059 | 0 |  | The project conducted 2 HC trainings in Karibba and Chiredzi. Furthermore, 4 one-day post trainings were condiucted at the border for customs officers to complete the funds available under the tranche. |  |  |  | INV |  |  | 2021-12-01
FIN | UNEP | Renewal of the institutional strengthening project (phase VIII: 4/2015-3/2017) | Individual | AFR | ZIM | SEV | 74 | INS | 49 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-02-01 | 2017-03-01 |  | 2017-12-01 | 2018-12-01 | 148242 | 0 | 148242 | 148242 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | 0
FIN | UNEP | Survey of ODS alternatives at the national level | Individual | AFR | ZIM | SEV | 74 | TAS | 50 | A | I |  | 0 |  | 0 |  | 2015-05-01 | 2016-03-01 | 2016-05-01 |  | 2017-08-01 | 2018-12-01 | 70000 | 0 | 70000 | 70000 | 100% | 0 | 0 | 0 | 9100 | 0 | 9100 | 0 | 0 | [8 empty] | 0 | 0
FIN | Germany | HCFC phase-out management plan (stage I, third tranche) (refrigeration servicing sector) | Multi-Year | AFR | ZIM | PHA | 75 | INV | 51 | A | I | HCFC | 0 |  | 0 |  | 2015-11-01 | 2016-01-01 | 2017-12-01 |  | 2018-05-01 | 2019-11-30 | 112000 | 0 | 112000 | 112000 | 100% | 0 | 0 | 0 | 13398 | 0 | 13398 | 0 |  | Activities in the country have been slow in implementation due to various restrictions related to bank accounts and transfers to the country. However, it was agreed to send additional 3 trainers from the local training institutes to attend basic refrigeration courses in ACRA which has allowed for 5/7 RAC training institutes to have standardised know-how and skills among their trainers. Additionally, 8 sets of training tools and equipment were requested to allow for trainers to conduct proper hands-on training courses in the institutions. These tools have also been provided. | The procured equipment was distributed to the training institutions. | [5 empty] | 2021-12-01
FIN | Germany | Verification report for stage I of HCFC phase-out management plan | Individual | AFR | ZIM | PHA | 75 | TAS | 52 | A | I | HCFC | 0 |  | 0 |  | 2015-11-01 | 2016-11-01 | 2016-12-01 |  | 2018-06-01 | 2019-01-31 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 3900 | 0 | 3900 | 0 |  | The verification report was accepted by the MLF and the following HPMP tranche approved in 2018.
FIN | UNEP | Renewal of the institutional strengthening project (phase IX: 7/2017-6/2019) | Individual | AFR | ZIM | SEV | 79 | INS | 53 | A | I |  | 0 |  | 0 |  | 2017-07-01 | 2018-03-01 | 2019-06-01 |  | 2019-06-01 | 2019-12-01 | 189750 | 0 | 189750 | 189750 | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | The final payment for SSFA with total amount of USD 189,750 was released to the country in November 2019. The HCFC quota licensing system is fully operational. The HCFC quota for 2019 was issued to 54 importers who responded to the NOU advertisement and were successfully vetted and licensed as importers. The total allowable quantity of HCFC was 180 MT. The database of licensed importers is kept by the NOU and shared with the Customs department. All licensed importers complied and imported within the allocated quotas. Eight inspection visits were made to the major licensed importers and end users in Harare, Bulawayo, Hwange, Mutare, Masvingo, Chiredzi, KweKwe, Gweru, Chinhoyi and Kariba. Two joint border dialogue workshops for Ozone Officers were held in 2019. The first one was held in January in Kasane, Botswana and comprised Ozone Officers and Customs officers from Botswana, Zambia and Zimbabwe. Zimbabwe sent 7 customs officers from Plumtree, Beit Bridge, Victoria Falls, Chirundu and Harare. The second Joint Border Workshop was held in Katima Mulilo in Nambia in September 2019 and comprised ozone officers and customs officers from Botswana, Eswatini, Lesotho, Namibia, Zambia and Zimbabwe. Zimbabwe sent 6 customs officers from Beit Bridge, Kazungula, Victoria Falls, Harare and Plumtree. The Joint Border dialogues provided an opportunity for Customs Officers from these neighbouring countries to share experience and exchange ideas on combating illegal ODS trade. The customs Officers were also taught how to use the refrigerant identifiers are in good working order and fully utilized by customs officers. An awareness workshop on the Kigali Amendment was conducted in February 2019 for the members of the Parliamentary Portfolio Committee on Environment, Climate, Water and Land Resettlement. 27 Members of Parliament attended and pledged to support the motion of ratification when introduced in Parliament. The CP and article 7 data for the 2018 was collected and reported on time. Five National Steering Committee meetings were convened in January, April, July, August and December in the Ministry’s 12th Floor Boardroom. The meetings were held to approve annual and quarterly work plans, monitor progress in implementation of activities, to prepare for the Ozone Day commemorations and to advise the Ministry on other policy and awareness programmes. One national Zimbabwe RAC Association meeting was held on the 28th May 2019 at the Lees Hotel in Masvingo and was attended by 42 members from all the association’s 10 Regions in the country. The Association agreed to hold an elective Annual General Meeting in 2019. Six training workshops were conducted in 2019 and a total of technicians were trained. These training workshops were conducted at Harare Polytechnic, KweKwe Polytechnic, Gweru Polytechnic, Tatenda Safari Lodge in Victoria Falls, Bulawayo Polytechnic, Tongaat Hullett in Chiredzi and at Zambezi Valley Hotel in Kariba. A total of 142 technicians were trained in 2019 and of these, 57 are women. The International Ozone Day for 2019 was celebrated at the Chinhoyi Caves Motel in Chinhoyi on the 16th September under the theme “32 Years and Healing”. The NOU organized a Symposium within which presentations were made from organizations that have adopted ozone friendly technology in refrigeration and air conditioning, agriculture and other sectors. 57 participants from the RAC Association as well as the people from Chinhoyi attended the Ozone Day commemorations. Two awareness raising meetings were held during the Zimbabwe International Trade Fair in Bulawayo in April 2019. More 200 people visited the NOU stand to collect pamphlets and other awareness materials. The second awareness raising campaigns was held at the Zimbabwe Agricultural Show Week in August 2019 at the Harare Show grounds in Harare. The NOU participated in the following meetings: Second Global Inter-Regional Thematic meetings back to back with Parallel K-CEP Twinning Workshops, 17--22, 2019, Paris, France; NOU training workshop and back to back with Enabling Activities Project Workshop, 17-21 June, 2019, Seychelles; 41st Open-Ended Working Group meeting held in Bangkok, Thailand; 31st Meeting of the Parties, 4-8 November, 2019, Rome, Italy. Project is completed satisfactorily. | Project financially completed | [6 empty] | 0 | 0
ONG | Germany | HCFC phase-out management plan (stage I, fourth tranche) (refrigeration servicing sector) | Multi-Year | AFR | ZIM | PHA | 80 | INV | 54 | A | I | HCFC | 2.3 |  | 0 |  | 2017-11-01 | 2018-08-01 | 2020-12-01 | 2021-12-01 |  |  | 168000 | 0 | 168000 | 34782 | 20.7% | 133218 | 6419 | 48826.5756 | 20097 | 0 | 4160.7968 | 15936.2033 | 768 | Focus was on completion of the previous tranche. Preparations and logistical support for the trainers to travel to ACRA in South Africa to attend the refrigerations courses. | Also in ZIM, implementation was interrupted by Corona. Currently preparations are ongoing for each of the institutions to conduct 2 trainings for working technicains to start in August 2020. | [5 empty] | 2021-12-01
ONG | UNDP | Conversion from HFC-134a to isobutane in the manufacture of domestic refrigerators at Capri (SME Harare) | Individual | AFR | ZIM | REF | 82 | INV | 55 | N | I | HFC | 11.1 | 0 | 0 | 0 | 2018-12-01 |  | 2020-12-01 | 2021-11-01 |  |  | 326954 | 0 | 326954 | 0 | 0% | 326954 | 0 | 98086.2 | 22887 | 0 | 0 | 22887 | 0 | The project document for UNDP part was endorsed with the government. A legal agreement between France and UNDP progressed in 2019 with involvement of legal and procurement departments. Once the legal agreement is concluded, more work can be planned in terms of announcing tenders for technology supply. A mission by international expert was fielded to discuss technology specifications, and factory layout schemes. An extension was requested to the MFS. | The legal agreement between the Government of France and UNDP was cleared and signed. Technical specifications for Capri's technological transition have been prepared, and once funds have been transferred, it will be possible to announce the planned international tender for equipment. The project was reported as requiring extension. | 0 |  | Investment
ONG | France | Conversion from HFC-134a to isobutane in the manufacture of domestic refrigerators at Capri (SME Harare) |  | AFR | ZIM | REF | 82 | INV | 56 | N | I | HFC-134a | 3.4 |  | 0 |  | 2018-12-01 |  | 2020-12-01 | 2022-06-01 |  |  | 100000 | 0 | 100000 | 0 | 0% | 100000 | 0 | 10000 | 13000 | 0 | 0 | 13000 | 0 | Project documentation for the MLF approved funding has been signed with the government, and the additional bilateral contribution is subject to the signature of a legal agreement between UNDP and the Government of France which has been cleared for signature after extensive bilateral consultations. This is the first agreement between France and UNDP and two legal departments have worked substantively on legal provisions to reach agreement. NOU, CAPRI and international refrigeration expert have discussed technical specifications for the technology transition to prepare for a tender. Once the legal agreement is endorsed, and the updated workplan for the bilateral contribution is signed by the Government of Zimbabwe, required tender processes will be announced. The project may require additional implementation time in this respect, and in light of the Covid-19 situation which may disrupt technology supply chain or further international visits to the country.
ONG | UNEP | Renewal of the institutional strengthening project (phase X: 7/2019-6/2021) | Individual | AFR | ZIM | SEV | 83 | INS | 57 | A | I |  | 0 |  | 0 |  | 2019-05-01 |  | 2021-06-01 | 2021-06-01 |  |  | 189750 | 0 | 189750 | 0 | 0% | 189750 | 189750 | 75900 | 0 | 0 | 0 | 0 | 0 | The SSFA was signed by the Government of Zimbabwe in October 2019 with total amount of USD 189,750. The first payment was released to the country in November 2019. The HCFC quota licensing system is fully operational. The HCFC quota for 2019 was issued to 54 importers who responded to the NOU advertisement and were successfully vetted and licensed as importers. The total allowable quantity of HCFC was 180 MT. The database of licensed importers is kept by the NOU and shared with the Customs department. All licensed importers complied and imported within the allocated quotas. Eight inspection visits were made to the major licensed importers and end users in Harare, Bulawayo, Hwange, Mutare, Masvingo, Chiredzi, KweKwe, Gweru, Chinhoyi and Kariba. Two joint border dialogue workshops for Ozone Officers were held in 2019. The first one was held in January in Kasane, Botswana and comprised Ozone Officers and Customs officers from Botswana, Zambia and Zimbabwe. Zimbabwe sent 7 customs officers from Plumtree, Beit Bridge, Victoria Falls, Chirundu and Harare. The second Joint Border Workshop was held in Katima Mulilo in Nambia in September 2019 and comprised ozone officers and customs officers from Botswana, Eswatini, Lesotho, Namibia, Zambia and Zimbabwe. Zimbabwe sent 6 customs officers from Beit Bridge, Kazungula, Victoria Falls, Harare and Plumtree. The Joint Border dialogues provided an opportunity for Customs Officers from these neighbouring countries to share experience and exchange ideas on combating illegal ODS trade. The customs Officers were also taught how to use the refrigerant identifiers are in good working order and fully utilized by customs officers. An awareness workshop on the Kigali Amendment was conducted in February 2019 for the members of the Parliamentary Portfolio Committee on Environment, Climate, Water and Land Resettlement. 27 Members of Parliament attended and pledged to support the motion of ratification when introduced in Parliament. The CP and article 7 data for the 2018 was collected and reported on time. Five National Steering Committee meetings were convened in January, April, July, August and December in the Ministry’s 12th Floor Boardroom. The meetings were held to approve annual and quarterly work plans, monitor progress in implementation of activities, to prepare for the Ozone Day commemorations and to advise the Ministry on other policy and awareness programmes. One national Zimbabwe RAC Association meeting was held on the 28th May 2019 at the Lees Hotel in Masvingo and was attended by 42 members from all the association’s 10 Regions in the country. The Association agreed to hold an elective Annual General Meeting in 2019. Six training workshops were conducted in 2019 and a total of technicians were trained. These training workshops were conducted at Harare Polytechnic, KweKwe Polytechnic, Gweru Polytechnic, Tatenda Safari Lodge in Victoria Falls, Bulawayo Polytechnic, Tongaat Hullett in Chiredzi and at Zambezi Valley Hotel in Kariba. A total of 142 technicians were trained in 2019 and of these, 57 are women. The International Ozone Day for 2019 was celebrated at the Chinhoyi Caves Motel in Chinhoyi on the 16th September under the theme “32 Years and Healing”. The NOU organized a Symposium within which presentations were made from organizations that have adopted ozone friendly technology in refrigeration and air conditioning, agriculture and other sectors. 57 participants from the RAC Association as well as the people from Chinhoyi attended the Ozone Day commemorations. Two awareness raising meetings were held during the Zimbabwe International Trade Fair in Bulawayo in April 2019. More 200 people visited the NOU stand to collect pamphlets and other awareness materials. The second awareness raising campaigns was held at the Zimbabwe Agricultural Show Week in August 2019 at the Harare Show grounds in Harare. The NOU participated in the following meetings: Second Global Inter-Regional Thematic meetings back to back with Parallel K-CEP Twinning Workshops, 17--22, 2019, Paris, France; Pilot NOU training workshop and back to back with Enabling Activities Project Workshop, 17-21 June, 2019, Seychelles; 41st Open-Ended Working Group meeting held in Bangkok, Thailand; 31st Meeting of the Parties, 4-8 November, 2019, Rome, Italy. Project is progressing satisfactorily. | The NOU continues to monitor imports and trade of ODS and ODS related equipment. Licensing system fully operational and is in progress. The HCFC quota for 2020 was issued to 50 importers. The total quantities allocated for 2020 is 180 metric tonnes of HCFCs. A joint visit by the NOU and Customs Department was made to Forbes, Beit Bridge and Plumtree in March 2020. The team found out that control measures for HCFCs and HFCs as well as appliances relying on these were in place and customs officers are aware of the control provisions. One Customs training workshop was conducted at the Zimbabwe Institute of Public Administration and Management (ZIPAM) in Darwendale, 90km from Harare in February 2020. A total of 22 customs officers from Forbes, Harare, Chirundu, Nyamapanda, KweKwe, Mount Selinda and Kariba attended the workshop which was officially opened by the Permanent Secretary, Mr Munodawafa. The participants were updated on the Kigali Amendment provisions, screening methods, customs checklists, HS Codes, smuggling schemes, labelling of controlled substances, and use of refrigerant identifiers. One National Steering Committee meeting was convened in January and approved the 2020 Annual Workplan and the First Quarter Workplan. One training workshop was conducted at the Harare Polytechnic from the 21st to 24th March 2020 and 35 technicians were trained. One Awareness workshop for importers and clearing agents was conducted at the Harare International Conference Centre in Harare on the 17th February 2020 and was attended by 42 participants. The participants were informed about the provisions of the Kigali Amendment and the need to adhere to the allocated quotas. Delays in project activities are to be expected due to measures taken by the country related to COVID-19 outbreak, which resulted in postponing all meetings/ events planned in the first half of the year | [6 empty] | 0 | 0
ONG | UNDP | Preparation of a HCFC phase-out management plan (stage II) | Individual | AFR | ZIM | PHA | 83 | PRP | 58 | N | I | No_ODP | 0 | 0 | 0 | 0 | 2019-05-01 |  | 2021-06-01 | 2021-06-01 |  |  | 20000 | 0 | 20000 | 0 | 0% | 20000 | 0 | 20000 | 1400 | 0 | 0 | 1400 | 0 | An international expert was recruited. Technical mission held in December 2019. Several stakeholders from the industry and servicing sector participated in the mission. Data collection is in process. | Findings from the mission were summarized, and analyzed jointly with NOU and UNDP. Inputs have been prepared for HPMP-II preparatory process. Once Covid-19 related restrictions are lifted, more activities will be planned. |  |  | Non-Investment
ONG | UNEP | Preparation of a HCFC phase-out management plan (stage II) | Individual | AFR | ZIM | PHA | 83 | PRP | 59 | A | I |  | 0 |  | 0 |  | 2019-05-01 | 2019-11-01 | 2021-06-01 | 2021-06-01 |  |  | 40000 | 0 | 40000 | 5000 | 12.5% | 35000 | 35000 | 14000 | 5200 | 0 | 650 | 4550 | 4550 | The SSFA was signed by the Government of Zimbabwe in October 2019 with total amount of USD 40,000. The first payment was released to the country in November 2019. | The first stakeholders workshop was organized by the NOU from 4-5 March 2020 at the ZIPAM Centre in Darwendale with the main goal to sensitize major stakeholders about HCFC phase out schedule, data survey and the Government’s strategy for phasing out of HCFCs. A total of 35 participants attended the workshop. Two national consultants were hired by the NOU for data surveys which includes appropriate methodology, data collection, evaluation and reporting. Consultants collected information on the current status and consumption of HCFCs in servicing sector using HCFC- 22 including industrial and commercial refrigeration sectors and end-user air conditioning, as well as on the ongoing refrigerant recovery and recycling practices. Delays in project activities are to be expected due to measures taken by the country related to COVID-19 outbreak, which resulted in postponing all meetings/ events planned in the first half of the year. | [6 empty] | 17500 | 2275

## HFC+Database
Status | Agency | Project Title | Multi-Year/Multi-Year Partial Phase-out/One-off Phase-Out/Individual/RMP/RMP Update/RMP for Non-LVC/Halon Banking | Region | Country | Sector | Mtg | Type | Num | A/N | IRDX | Chemical | Metric Tonnes to be Phased Out per Proposal | Metric Tonnes Phased Out | Date Approved | First Disbursment Date | Date of Compl per Proposal | Planned Date of Completion | Date Completed (Actual) | Date of Financial Completion | Approved Funding (US$) | Adjustment (US$) | Approved Funding plus Adjustments (US$) | Funds Disbursed (US$) | Per Cent of Funds Disbursed | Balance (US$) | Funds Committed (US$) | Estimated Disbursement in Current Year (US$) | Support Cost Approved (US$) | Support Cost Adjustment (US$) | Support Cost Disbursed (US$) | Support Cost Balance (US$) | Support Cost Committed (US$) | Remarks | Remarks (Latest information) | Disbursements made to final beneficiaries from FECO/ MEP | Implementation Delays/Status Report Decisions (85th Meeting) | Date of Completion per Agreements or per Decisions | Funds Transferred (US$) | Support Costs Transferred (US$)
ONG | UNEP | Enabling activities for HFC phase-down |  | ASP | AFG | SEV | 81 | TAS | 01+ | A | I | HFC | 0 |  | 2018-06-01 | 2019-03-01 | 2020-01-01 | 2021-01-01 |  |  | 150000 | 0 | 150000 | 67858.48 | 45.24% | 82141.52 | 78769 | 24891.3697 | 10500 | 0 | 4750.0936 | 5749.9064 | 5513.83 | The SSFA signed in Jan 2019. First payment transferred in March 2019. The second payment has been released to the country 17 December 2019. NOU hired a project coordinator, and a communication expert. National consultation process for ratification advancing, almost completed. Several consultation meetings were held in different provinces (Kabul on 23 June and 24 July 2019, Herat on 7 August 2019, Balkh 24 October 2019). Most of relevant line ministries shared letter of approval with NEPA. Data collection for country assessment completed. Four factsheets have been adapted and translated into local languages, designed, printed and distributed to relevant stakeholders. Specific awareness materials (leaflets) for HFC phase down developed and disseminated to the stakeholders and/or the public throughout 2019. One informative video on KA is translated and dubbed in Pashto and Dari. Public media campaign was launched in 2019 through social media. One custom stakeholder meeting held on 18 November 2019. One consultation meeting was held with relevant stakeholders on 18 December 2019 to get feedback and suggestions of the committee members to improve the licensing/ quota system. Four master trainers sent to Guangzhou for training on R290 in December 2019.Consulted with National Standard Authority (ANSA). Purchase of 7 standards completed. Status of ratification: Expected in ratification 2020. | One short term legal advisor is currently being hired Collection of approval letters from Ministries concluded. Package for ratification of the KA is developed and following legislative procedure (sessions with the Ministry of foreign affairs, Ministry of justice, Parliamentarians, and final step endorsement of the president). One consultation workshop postponed to Q3/4 as possible. Country Assessment Report final draft currently under revision. 6 New Factsheets translated to Dari language and 3 more translated in Pashto language. Translation of two further factsheets ongoing. One further video about HFCs is being dubbed. A local NGO was selected to assist with the remaining outreach activities. One further custom stakeholder meeting held on 21 January 2020. Customs formed committee with relevant ministry stakeholders to review and adapt the national HS code with interim national digits, discussion ongoing. Regulation revision document being finalized. Started legal drafting of new legislation. Two more end users workshops being organized in Kandahar and Jalalabad, for Q3/4 as possible. Two technicians training workshops being organized in country to create a small pool of master trainers, for Q3/4 as possible. Translation of relevant standards ongoing. |  |  | 2021-01-01 | 63769 | 4463.83
FIN | UNIDO | Enabling activities for HFC phase-down |  | EUR | ALB | SEV | 80 | TAS | 01+ | A | I |  | 0 | 0 | 2017-11-01 | 2018-02-01 | 2019-06-01 |  | 2019-06-01 | 2019-09-26 | 95000 | -22 | 94978 | 94978.26 | 100% | -0.26 | 0 | 0 | 6650 | -2 | 6648.4782 | -0.4782 | 0 | The country has ratified the Kigali Amendment on 18th of January 2019. Regarding the licensing system, Albania opted for delaying the actions by 1 Jan 2021. Project has been successfully completed and was financially closed in September 2019. Remaining fund balances were returned at the 84th ExCom meeting in December 2019. Actions towards next goals: Submit the final report. Was there any delay during the reporting year? NO Any recurring problem? NO Any impact on project completion date: NO Any action required by Executive Committee? NO | The final report has been submitted.
ONG | UNEP | Enabling activities for HFC phase-down |  | AFR | ANG | SEV | 80 | TAS | 01+ | A | I | HFC | 0 |  | 2017-11-01 | 2018-09-01 | 2019-06-01 | 2020-12-01 |  |  | 150000 | 0 | 150000 | 84586.76 | 56.39% | 65413.24 | 56750 | 19822.1939 | 10500 | 0 | 5921.0732 | 4578.9268 | 3972.5 | The second payment for SSFA with total amount of USD 135, 000 was released to the country in August, 2019. NOU is carrying out work to track the status of the Ratification of the KA and is currently working once again with the Exchange Office of the Ministry of Environment and the Direction of the Council of Ministers to speed up Ratification the Kigali Amendment which was approved by National Assembly in 2018. The NOU worked on the draft regulation and Quota instruction for HFCs and sent for contributions and support from the Legal Office of the Ministry of Environment and the National Customs Service. Angola carried out the first inventory of HFCs and SDO alternatives in 2016 and has been updating the established database. NOU organized two (2) Workshop on handling natural refrigerant gas for 100 Refrigeration and Air Conditioning Technicians. Overall assessment of project progress is satisfactory. All process for Kigali Amendment was done, just awaiting deposition of ratification instrument. | In February, 2020, NOU participated in an institutional training workshop to promote projects related to energy efficiency carried out by the Climate Change Office of Angola. "Delays in some projects activities are to be expected due to measures taken by the country related to Coronavirus outbreak, which resulted for example in postponing all meetings/ events planned in the first half of the year.” |  |  | 2020-06-01 | 51750 | 3622.5
ONG | UNIDO | Conversion project for replacement of HFC-134a with isobutane (R-600a)/propane (R-290)-based refrigerant in the manufacture of domestic and commercial refrigeration equipment at Briket, Bambi and Mabe-Kronen |  | LAC | ARG | REF | 81 | INV | 01+ | A | I | HFC | 96.6 | 0 | 2018-06-01 | 2018-12-01 | 2020-07-01 | 2021-06-30 |  |  | 1840755 | 0 | 1840755 | 681703.34 | 37.03% | 1159051.66 | 380771.14 | 380000 | 128853 | 0 | 47719.2338 | 81133.7662 | 26653.9798 | After technical evaluation and UNIDO's internal review and approval, there was a need for extended negotiation and reduction of scope, since each offer was higher than the approved budget. After several rounds of negotiations, the final scope has been agreed upon and contract was signed by UNIDO and the supplier in April and May respectively. A technical visit by the supplier together with UNIDO was organized early June to clarify all technical and safety related aspects of the conversions. Equipment arrived at Argentine port late December 2019. Milestones achieved: PAD issued: Yes, July 2018 ToR for equipment purchase agreed upon: Yes, September 2018 Bids prepared & requested: Yes, October 2018 Contract awarded: April 2019 Contract countersigned: May 2019 Equipment delivered & installed: No Commissioning & trial runs: No TUV certification: No Activities planned but not implemented, reasons and strategy: N/A. Actions towards next goals: Follow-up on equipment delivery DAP and preparation of project sites for installation+installation; Was there any delay during the reporting year? Yes, due to the limited budget and related negotiations and reduction of scope. Any recurring problem? No Any impact on project completion date: N/A. Any action required by Executive Committee? Consider higher cost effectiveness threshold. | Goods were cleared from customs in January and delivered to the site. Installation of equipment started in March, but had to be stopped due to the COVID lock-down and the supplier's technicians had to travel back to Italy. Companies are keen to finalize conversions, but the supplier is not allowed to travel to Argentina until further notice. Milestones achieved: PAD issued: Yes, July 2018 ToR for equipment purchase agreed upon: Yes, September 2018 Bids prepared & requested: Yes, October 2018 Contract awarded: April 2019 Contract countersigned: May 2019 Equipment delivered & installed: Delivered in January 2020; Installation done: No Commissioning & trial runs: No TUV certification: No Activities planned but not implemented, reasons and strategy: N/A. Actions towards next goals: Installation, trial runs and commissioning once international travel restrictions are lifted; Was there any delay during the reporting year? Yes, due to COVID19. Any recurring problem? No Any impact on project completion date: Yes. Any action required by Executive Committee? Extend the project.
ONG | UNIDO | Enabling activities for HFC phase-down |  | LAC | ARG | SEV | 81 | TAS | 02+ | A | I |  | 0 | 0 | 2018-06-01 | 2018-11-01 | 2020-01-01 | 2021-01-01 |  |  | 250000 | 0 | 250000 | 87081.13 | 34.83% | 162918.87 | 53345.37 | 40000 | 17500 | 0 | 6095.6791 | 11404.3209 | 3734.1759 | • Ratification of Kigali amendment: Yes (22nd of November 2019) • Status of implementation: project ongoing • Activities implemented: Review of licensing and data collection system for HFCs and reporting, institutional strengthening; assessment of the production sector and HFC-23 emissions as a by-product from HCFC-22 production; national regulatory analysis and standards. • Milestones achieved: -Work Plan Agreed with NOU: Yes; - UNIDO awareness-raising workshop organized: Yes organized in June 2019, named "Kigali in Action" and the NOU was invited, however, the country representative could not participate. The NOU from Argentina was provided with the documents and materials offered in the workshop as well as the report of the fruitful discussions between the country participants that are useful for the actions towards the next stage of the project. - Consultants recruited: Yes; - Specific deliverables and results reported: a) Enforced licensing and quota system: Yes (no quota system enforced) b) HFC data collection and monitoring system (decision 79/46): electronic licensing and monitoring system upgraded to include HFCs (in progress). c) A legal assessment of HFC-23 emissions as by-product of HCFC-22 production was developed. Scenarios of HFC-23 emission, regulatory control measures, and costs related were evaluated. d) The study of existing national and provincial regulations and standards related to HFC and its alternatives was initiated. • Overall assessment of project progress: Actions satisfactory developed during the reporting period as planned. Work plan was updated and some activities planned to be developed in 2020 • Impact of these activities: Significant progress of the internal processing of the ratification document, which completed inter-ministerial consultation. The country's HFC data reporting will be facilitated through the upgraded system. • Potential challenges in completing the projects and activities: Work plan for the remaining priority activities needs to be updated. • Key findings and lessons learned: The legal assessment and possible scenarios evaluated on HFC-23 emission allow the country to support the MLF project on HCFC-22 production at FIASA and to identify significant gaps in the regulatory framework on the HFC-23 control as contained substance or as an atmospheric pollutant (emission). | • Status of implementation: project ongoing • Activities implemented: Review of licensing and data collection system for HFCs and reporting, institutional strengthening; assessment of the production sector and HFC-23 emissions as a by-product from HCFC-22 production; national regulatory analysis and standards. • Milestones achieved: - Work Plan Agreed with NOU and updated - Specific deliverables and results reported: a) Electronic licensing and monitoring system upgraded to include HFCs (progressing). b) Landscape and gap analysis study was developed on the existing national and provincial regulations and standards applicable to flammable, toxic, high pressure, and low GWP alternatives. • Overall assessment of project progress: Actions satisfactory developed during the reporting period as planned. Some delays reported due to Covid-19 and travel restrictions. Workshops are postponed and reprogrammed. • Activities planned for the second part of 2020: Assessment report on national priorities and appropriate policies to facilitate the phase-down of HFCs and the introduction of low-GWP alternative technologies - inclusive “not-in-kind” options – with higher rates of energy efficiency. The licensing system is being upgraded to be adapted to the new technical developments. Awareness activities and results dissemination on actions developed will be carried out at the end of the year. The activity will be rearranged to be virtual in the applicable sessions, however, related site visits or events are expected to be undertaken in the second half of the year and after September 2020 if the travel restrictions are removed. • Potential challenges in completing the projects and activities: Based on the decision taken by UNIDO management to restrict official travel due to the ongoing outbreak of COVID-19 immediately and until further notice. The quarantine in Buenos Aires and restrictions on travel between jurisdictions have been extended until the end of June. Work plan for the remaining priority activities needs to be updated. An extension might required. |  |  | 2021-01-01
ONG | UNIDO | Enabling activities for HFC phase-down |  | EUR | ARM | SEV | 80 | TAS | 01+ | A | I |  | 0 | 0 | 2017-11-01 | 2018-03-01 | 2019-06-01 | 2020-06-01 |  |  | 150000 | 0 | 150000 | 131350.63 | 87.57% | 18649.37 | 17787.26 | 18415 | 10500 | 0 | 9194.5441 | 1305.4559 | 1245.1082 | The country ratified the Kigali Amendment on 2nd of May 2019. Project activities included establishing close contact with the climate change center, preparatory work with the stakeholders, preparation of the ratification package, all resulting in the KA ratification. Further on, amendments to the ODS legislation were drafted including the Bill on Saving the Ozone Layer and the by-laws. The Bill was adopted by the Parliament on 2 March 2020. Implementation of this project was in parallel with the establishment of the Regional Centre of Excellency in Armenia which opened wide possibilities for the demonstration of the new low-GWP technologies and training of technicians. Activities were implemented as planned. | National Consultants were involved in 2020 in awareness campaign and stakeholders consultation meetings held 1st quarter 2020. The project was operationally completed. |  |  | 2020-06-01
ONG | UNEP | Enabling activities for HFC phase-down |  | AFR | BEN | SEV | 81 | TAS | 01+ | A | I | HFC | 0 |  | 2018-06-01 | 2018-11-01 | 2020-01-01 | 2021-01-01 |  |  | 150000 | 0 | 150000 | 13583.78 | 9.056% | 136416.22 | 100584 | 41338.2485 | 10500 | 0 | 950.8646 | 9549.1354 | 7040.88 | The country ratified the Kigali amendment on 19 March 2018. National consultants are contracted to assist Customs Office in developing national custom codes for different HFCs and include them into the Customs Tarif in order to ensure proper monitoring and recording of imports/exports or re-export of individual HFCs. Comprehensive review of National licensing system for ODS, ODS alternatives and based-products was done in 2019. Analysis of existing policy and regulatory framework for HFCs was done in 2019. Stakeholders consultation meetings and awareness programmes to facilitate the ratification process at the national level were organised. Awareness material for HFC phase down was produced and disseminated to the stakeholders and the public. The development of Customs Harmonized Code was to be finalized by an international consultant by December 2019. It is delayed and will be finalized by July 2020. Two sensitization meetings for the servicing sector on safe handling of HFCs and alternatives will be organized in 2019. NOU attended the ECOWAS meeting for regional harmonization of Customs Harmonized Code regarding regulation of HFC imports/exports, in Bissau, December 2019. | In January -March 2020 Benin NOO participated in many exchanges that lead to the recrutment of an International Consultant and a Draft proposal for the extension of the subheadings 2903.39 and 3824.78 of the Tariff and Statis-tical Nomenclature (TSN) of the Common External Tariff (CET) of the Economic Community of West African States (ECOWAS) in order to facilitate the collection and comparison of data concerning the circulation of hydrofluorurocarbons (HFC) will be developed and submitted to WCO. |  |  | 2021-01-01 | 50000 | 3500
COM | UNDP | Conversion from HFC-134a to isobutane as refrigerant in manufacturing household refrigerator and of reciprocating compressor of HFC-134a to energy efficient compressor (isobutane) in Walton Hi-Tech Industries Limited | Individual | ASP | BGD | REF | 80 | INV | 01+ | N | I | HFC | 230.6 | 230.6 | 2017-11-01 | 2018-12-01 | 2019-12-01 |  | 2019-12-01 |  | 3131610 | 0 | 3131610 | 3126415 | 99.83% | 5195 | 0 | 3636.381 | 219213 | 0 | 218849.3614 | 363.6386 | 0 | Conversion of refrigerators and compressors lines were completed as per scheduled, Safety Audit took place. The process of signing ProDoc took long time, in this regard. GOV of Bangladesh agreed to allow UNDP act as implementing partner through Direct Implementation (DIM) Modality. One signature (UNDP only) ProDoc was established, so this issue was addressed.
ONG | UNEP | Enabling activities for HFC phase-down |  | LAC | BHA | SEV | 82 | TAS | 01+ | A | I | HFC | 0 |  | 2018-12-01 |  | 2020-06-01 | 2021-01-01 |  |  | 95000 | 0 | 95000 | 0 | 0% | 95000 | 95000 | 28787.8788 | 6650 | 0 | 0 | 6650 | 6650 | The SSFA was signed on 9 Sept 2019. The first payment has been released to the country 22 November 2019. | The SSFA was signed on 9 Sept 2019. The first payment has been released to the country 22 November 2019. Consultants identified and in final stages of contracting them to undertake the various activities. Draft Cabinet Note to ratify the KA prepared for submission once NOO gets the go ahead from the Director. Delays in some projects activities are to be expected due to measures taken by the country related to Coronavirus outbreak, which resulted for example in postponing all meetings/ events planned in the first half of the year. Additional 6 months for implementation are required as of May 2020. |  |  | 2021-06-01 | 50000 | 3500
ONG | UNIDO | Enabling activities for HFC phase-down |  | EUR | BHE | SEV | 80 | TAS | 01+ | A | I |  | 0 | 0 | 2017-11-01 | 2018-03-01 | 2019-06-01 | 2020-12-01 |  |  | 95000 | 0 | 95000 | 83747.38 | 88.16% | 11252.62 | 5934.07 | 4000 | 6650 | 0 | 5862.3166 | 787.6834 | 415.3849 | Support has been obtained from all relevant institutions and RAC sector; the Council of Ministers has adopted the proposal for ratification of the Kigali amendment on 30th January 2020. The conclusion was sent to BiH Presidency for consideration, the Decision on ratification should be adopted by BiH Presidency. There are certain political slow-downs in the process due to overall political situation and complex administration which involves 14 administrative levels in decision making process in BiH. Permits are required for import and export of HFCs. Data collection and monitoring system is in force. Trainings were organized for relevant stakeholders including administration in environment, energy efficiency, standards institutions, RAC sector, customs officers, which were crucial in obtaining better understanding of Kigali amendment ratification and implementation. This contributed to obtaining positive opinions in the process of consultations and procedures prescribed by relevant laws in BiH for the ratification of Kigali amendment. The Climate change authorities have been involved in the process and the cooling sector and F gasses are included in the BiH NDC. Administration from energy efficiency sector cooperates with BiH NOU and have participated at workshops related to energy efficiency organized by BiH NOU at national and regional level. Therefore, synergies for future activities are possible. So far, energy efficiency was considered only for buildings sector; cooling sector was recognized, but so far, no concrete actions were taken. NOU did institutional and legal analysis in context of Kigali amendment and energy efficiency in cooling sector and is at embryonic stage. On the other side, the academia is aware of the potential for energy efficiency through alternative technologies introduction and they are making efforts to introduce some energy efficient solutions, such as CO2 heat pumps and such solutions were presented during EA energy efficiency workshop. This aspect is very important also in context of combating with heavy pollution in BiH, and heat pumps are recognized by canton Sarajevo as one of measures to decrease air pollution. Relevant progress was achieved in implementation. National Consultants were contracted under NOU supervision and the implementation occurred in line with the work plan. | Remaining final activities could not be implemented due to the country lockdown. These activities are postponed to the second half of 2020. Was there any delay during the reporting year? - YES. Some activities could not be implemented as planned because of the restriction measures due to the Covid-19 pandemic. Any recurring problem? - No Any impact on project completion date? - YES Any action required by Executive Committee? - New decision has been granted, allowing implementing agencies to continue with the project implementation beyond the project end date as per decision. |  |  | 2020-06-01
ONG | UNEP | Enabling activities for HFC phase-down |  | ASP | BHU | SEV | 80 | TAS | 01+ | A | I | HFC | 0 |  | 2017-11-01 | 2018-12-01 | 2019-06-01 | 2020-12-01 |  |  | 50000 | 0 | 50000 | 28771.4 | 57.54% | 21228.6 | 20060 | 6432.9091 | 3500 | 0 | 2013.998 | 1486.002 | 1404.2 | The SSFA signed in Jul 2018. First payment made in Jul 2018. Draft ODS regulation amendnment under progress, an interministerial taskforce has been formed to review the proposal. One master trainer sent to Guangzhou for training on R290 in December 2019. Revised HS code adopted. Status of ratification: Ratified on 27 September 2019. | The second payment has been released to the country 20 January 2020. Country Assessment Report finalized. NOU planning RAC and MAC training in April 2020, postponed due to outbreak to Q3/4 as possible. Review ongoing, meetings delayed due to outbreak. NOU postponed further stakeholder consultations workshops to Q3/4. |  |  | 2020-06-01 | 60.1 | 4.207
ONG | UNIDO | Enabling activities for HFC phase-down |  | AFR | BKF | SEV | 80 | TAS | 01+ | A | I |  | 0 | 0 | 2017-11-01 | 2018-02-01 | 2019-06-01 | 2021-06-30 |  |  | 150000 | 0 | 150000 | 57908.13 | 38.61% | 92091.87 | 43220.79 | 92091.87 | 10500 | 0 | 4053.5691 | 6446.4309 | 3025.4553 | The country has ratified the Kigali Amendment on 26th of July 2018. HFC and equipment using HFC are subject to import authorization by the NOO. No license or quota per se, but control of import. HCF are monitored through import authorization but current HS code does not allow monitoring of individual gases, as HFCs and mixtures are covered by two HS code only. National survey of the RAC sector completed. Awareness raising campaign carried out. Control of HFC in place, but proper monitoring of individual HFC requires coordination at the ECOWAS level to include HFC regional tariffs, or waiting for the 2022 HS code revision which should include HFC-specific codes. The government (largest buyer in the country) does not purchase anymore RAC equipment with a COP below 3, against 2.5 before. It is expected to have positive impacts on national market dynamics, in particular import and practices of large users. The government is considering adapting the U4E Model Regulation nationally. - Milestone 6: National experts recruited - Milestone 7: ECOWAS coordination meeting on the update of HS code at the 41st OEWG meeting in Bangkok - Milestone 8: Extension of the EA until June 2020 has been requested and granted - Milestone 9: Further awareness raising campaign carried out - Milestone 10: Control of HFC in place, but proper monitoring of individual HFC requires coordination at the ECOWAS level to include HFC regional tariffs, or waiting for the 2022 HS code revision which should include HFC-specific codes. | - Milestone 11: National survey of the RAC sector completed; - Coordination at the ECOWAS level to include HFC regional tariffs ongoing; - Inputs to the UEMOA projects on energy efficiency (labels and norms for building) being formulated; - Support to the development of an approval/assent system for technicians (three components: skills, refrigerant quality, tools quality) being provided; - Discussions on national curriculum and needs identification ongoing; - Discussions on the need for a national set of guidelines for the installation and use of R290 equipment ongoing.AI141 Import/export control is expected to improve when electronic system "Sylvie" in place later in 2020. No HC-based equipment in the country, government would like to benefit from demonstration projects. |  |  | 2020-06-01
ONG | UNEP | Enabling activities for HFC phase-down |  | LAC | BOL | SEV | 82 | TAS | 01+ | A | I | HFC | 0 |  | 2018-12-01 | 2019-08-14 | 2020-06-01 | 2021-06-01 |  |  | 150000 | 0 | 150000 | 10437.96 | 6.959% | 139562.04 | 139562.04 | 42291.5273 | 10500 | 0 | 730.6572 | 9769.3428 | 9769.3428 | The SSFA was signed on July 04, 2019, the first cash advance issued of $60K on August 2019. Two Consultants for legislation review and strategy development were hired on September 2019. Two meetings were held in July and September 2019 with 70 refrigeration technicians, companies and government officials, where objectives and control measures to be implemented in Kigali were detailed. The Kigali amendment was approved by Parliament on October 10, 2019 and is expected that Bolivia will ratify the Kigali amendment soon. An assessment of alternatives, their availability, market trends and economic implications of different HFC alternatives and technologies to the national context was completed in December 2019. Consultants started with the preparation of training needs assessment for the servicing sector related to alternative technologies in November 2019. A registry system and HFCs database were developed in July 2019. The National Kigali Strategy was developed in June 2019. | Progress has been made in the planning of training activities in low-GWP alternatives for the refrigeration and air conditioning technicians, including topics on equipment, tools and safety standards, among others. Technical personnel has been hired to launch these activities by mid-June. The prepartion of regulations for the HFC licensing system and changes to the tariff headings are expected to start in June. An official request to the Multilateral Fund to extend the duration for this project an additional year, in order to allow the implementation of all the planned activities, was submitted for the consideration of the 85 ExCom. |  |  | 2021-06-01 | 49562.04 | 3469.3428
ONG | UNEP | Enabling activities for HFC phase-down |  | AFR | BOT | SEV | 81 | TAS | 01+ | A | I | HFC | 0 |  | 2018-06-01 | 2018-12-01 | 2020-01-01 | 2021-01-01 |  |  | 150000 | 0 | 150000 | 15200.13 | 10.13% | 134799.87 | 134800 | 40848.4455 | 10500 | 0 | 1064.0091 | 9435.9909 | 9436 | The SSFA was signed by the Government of Botswana in November 2018 with a total of USD 135,000. The first payment was released to the country in December 2018. Ratification of Kigali Amendment at OPs office for signature by the President; 24 RAC cresta lodges trained on good handling practices and 33 at Mine; border dialogue conducted for HFCs monitoring; regulation under review to apply HFCs quota system; importers/exporters awareness; customs and customs clearing agents workshops over the whole country; eight refrigerants analyzers were provided to custom ports of entry. Developed the energy efficiency strategy; RAC is recognized for EE improvements; Applied to GCF for assistance- in MEPS for RAC and distribution transformers; Developed an EE investment plan on Solar Water Heaters – awaiting for piloting its implementation. Currently: the NOU is in the process of developing the course outline for energy management Public Service College (BPSC) curriculum -provide training to public employees. Overall assessment of project progress is satisfactory. | Ratification of Kigali Amendment at OPs office for signature by the President. The NOU is in the process of conducting energy audit in 20 Government organizations and give recommendations on EE measures; In the process of developing EE standards through BOBS – to be incorporated into the building control regulation which is under review by Ministry of Infrastructure and Housing Development (MIH). "Delays in some projects activities are to be expected due to measures taken by the country related to Coronavirus outbreak, which resulted for example in postponing all meetings/ events planned in the first half of the year.” |  |  | 2021-01-01 | 80000 | 5600
ONG | UNEP | Enabling activities for HFC phase-down |  | ASP | BRU | SEV | 82 | TAS | 01+ | A | I | HFC | 0 |  | 2018-12-01 | 2019-06-01 | 2020-06-01 | 2021-06-01 |  |  | 150000 | 0 | 150000 | 4105.64 | 2.737% | 145894.36 | 5000 | 44210.4121 | 10500 | 0 | 287.3948 | 10212.6052 | 350 | The SSFA was drafted and transmitted to the Government in April 2019 for review and agreement. Following review by the Attorney General’s Chamber (AGC), The SSFA was signed on 7 December 2019. Identification of new partners completed. One inception stakeholders workshop done in July 2019 (1 of 3). NOU initiated a process to amend the existing regulation to control import and export of HFCs under the Customs Act - Prohibition and Restriction on Imports and Exports (Amendment) Order 2006. The request to include HFCs under the Second Schedule: Restriction on Import was submitted to RCED, forwarded to the Attorney General’s Chamber (AGC) in August 2019, was awaiting for gazette process for the new amendment to be enacted. One master trainer sent to Guangzhou for training on R290 in December 2019. Status of ratification: Expected in 2021. | The first payment was released to the country 29 January 2020. Recruitment of local consultant to support EA implementation completed. Data collection for Country Assessment Report started. NOU organizing local RAC trainings for second half of the year. NOU discussing with fire department on developing standard operating procedure guidelines for safe handling of flammable refrigerants to pave way for R32 into the country. Customs agreed to use subcodes, ongoing. |  |  | 2021-06-01 | 0 | 0
ONG | UNEP | Enabling activities for HFC phase-down |  | AFR | CBI | SEV | 82 | TAS | 01+ | A | I | HFC | 0 |  | 2018-12-01 | 2019-03-01 | 2020-06-01 | 2021-01-01 |  |  | 95000 | 0 | 95000 | 43884.13 | 46.19% | 51115.87 | 45006 | 15489.6576 | 6650 | 0 | 3071.8891 | 3578.1109 | 3150.42 | The country ratified the Kigali amendment on 19 March 2018. National consultants are contracted to assist Customs Office in developing national custom codes for different HFCs and include them into the Customs Tariff in order to ensure proper monitoring and recording of imports/exports or re-export of individual HFCs. Comprehensive review of National licensing system for ODS, ODS alternatives and based-products was done in 2019. Analysis of existing policy and regulatory framework for HFCs was done in 2019. Stakeholders consultation meetings and awareness programmes to facilitate the ratification process at the national level were organised. Awareness material for HFC phase down was produced and disseminated to the stakeholders and the public. The development of Customs Harmonized Code was to be finalized by an international consultant by December 2019. It is delayed and will be finalized by July 2020. Two sensitization meetings for the servicing sector on safe handling of HFCs and alternatives will be organized in 2019. NOU attended the ECOWAS meeting for regional harmonization of Customs Harmonized Code regarding regulation of HFC imports/exports, in Bissau, December 2019. | The country ratified the Kigali amendment on 19 March 2018. National consultants are contracted to assist Customs Office in developing national custom codes for different HFCs and include them into the Customs Tariff in order to ensure proper monitoring and recording of imports/exports or re-export of individual HFCs. Comprehensive review of National licensing system for ODS, ODS alternatives and based-products was done in 2019. Analysis of existing policy and regulatory framework for HFCs was done in 2019. Stakeholders consultation meetings and awareness programmes to facilitate the ratification process at the national level were organised. Awareness material for HFC phase down was produced and disseminated to the stakeholders and the public. The development of Customs Harmonized Code was to be finalized by an international consultant by December 2019. It is delayed and will be finalized by July 2020. Two sensitization meetings for the servicing sector on safe handling of HFCs and alternatives were organized in 2019. NOU attended the ECOWAS meeting for regional harmonization of Customs Harmonized Code regarding regulation of HFC imports/exports, in Bissau, December 2019. |  |  | 2021-06-01 | 0 | 0
ONG | UNEP | Enabling activities for HFC phase-down |  | AFR | CHD | SEV | 81 | TAS | 01+ | A | I | HFC | 0 |  | 2018-06-01 | 2018-11-01 | 2020-01-01 | 2021-01-01 |  |  | 150000 | 0 | 150000 | 59075 | 39.38% | 90925 | 54925 | 27553.0303 | 10500 | 0 | 4135.25 | 6364.75 | 3844.75 | The country ratified the Kigali amendment on 26 March 2019. National consultants are contracted to assist Customs Office in developing national custom codes for different HFCs and include them into the Customs Tariff in order to ensure proper monitoring and recording of imports/exports or re-export of individual HFCs. Comprehensive review of National licensing system for ODS, ODS alternatives and based-products was done in 2019. Analysis of existing policy and regulatory framework for HFCs was done in 2019. Stakeholders consultation meetings and awareness programmes to facilitate the ratification process at the national level were organised. Awareness material for HFC phase down was produced and disseminated to the stakeholders and the public. The development of Customs Harmonized Code was to be finalized by an international consultant by December 2019. It is delayed and will be finalized by July 2020. Two sensitization meetings for the servicing sector on safe handling of HFCs and alternatives will be organized in 2019. | The country ratified the Kigali amendment on 26 March 2019. National consultants are contracted to assist Customs Office in developing national custom codes for different HFCs and include them into the Customs Tariff in order to ensure proper monitoring and recording of imports/exports or re-export of individual HFCs. Comprehensive review of National licensing system for ODS, ODS alternatives and based-products was done in 2019. Analysis of existing policy and regulatory framework for HFCs was done in 2019. Stakeholders consultation meetings and awareness programmes to facilitate the ratification process at the national level were organised. Awareness material for HFC phase down was produced and disseminated to the stakeholders and the public. The development of Customs Harmonized Code was to be finalized by an international consultant by December 2019. It is delayed and will be finalized by July 2020. Two sensitization meetings for the servicing sector on safe handling of HFCs and alternatives were organized in 2019. |  |  | 2021-01-01 | 35925 | 2514.75
ONG | UNEP | Enabling activities for HFC phase-down |  | LAC | CHI | SEV | 80 | TAS | 01+ | A | I | HFC | 0 |  | 2017-11-01 | 2018-12-01 | 2019-06-01 | 2020-12-01 |  |  | 31000 | 0 | 31000 | 2192.8 | 7.074% | 28807.2 | 13430 | 8729.4545 | 2170 | 0 | 153.496 | 2016.504 | 940.1 | Some progress. Terms of reference drafted and approved in June 2019. Vacancy announcement approved, documentation uploaded in the system in July 2019. Consultant selected and contract signed in September 2019. Work plan submitted to UNEP as per the the conditions of the contract in October 2019. Activities in Chile scheduled to start in January 2020 as per the workplan submitted by consultant to UNEP. | Some progress. International expert mission to Chile from 13 to 17 January 2020, explored together with the NOU and the Customs Office, the current status of the control mechanisms in place to undertake risks analysis and make recommendations on potential risks management measures, in particular those of the HFCs. One training workshop for customs and enforcement officers was scheduled for February 2020 and had to be postponed due to national protests and COVID-19 outbreak. UNEP is currently discussing with country alternative online platforms and potential schedules to implement the training activities. |  |  | 2020-06-01 | 932 | 65.24
ONG | UNIDO | Enabling activities for HFC phase-down |  | LAC | CHI | SEV | 80 | TAS | 02+ | A | I |  | 0 | 0 | 2017-11-01 | 2018-03-01 | 2019-06-01 | 2021-06-01 |  |  | 86000 | 0 | 86000 | 10793.93 | 12.55% | 75206.07 | 0.02 | 74850.48 | 6020 | 0 | 755.5751 | 5264.4249 | 0.0014 | Ratification of Kigali amendment: Yes (2017-09-19) • Status of implementation: project on progress • Activities implemented: HFC licensing and quota system, data collection and monitoring (under UNEP component and NOU program); Public awareness; elaboration of information material for the different national actors with regard to the Kigali Amendment (under UNDP component and NOU program); Demonstration of non-investment activities and preliminary capacity building requirements for the implementation of the Kigali Amendment and its related matters (under UNIDO component). • Milestones achieved: .-Work Plan Agreed with NOU: Yes; .- UNIDO awareness-raising workshop organized: Yes organized in June 2019, named "Kigali in Action" and the NOU participated. .- Deliverables and results reported: a) Enforced licensing and quota system: Yes (no quota system enforced) b) HFC data collection and monitoring system (decision 79/46); Customs and enforcement officers were trained on obligations under the Kigali Amendment, including the revised import/export licensing systems (under UNEP and UNDP components). f) Training: Two specific training sessions on "Good practices to improve the energy efficiency of cold systems with low-GWP during the design, installation and maintenance phases" will be developed in 1- 4 October 2019; one session addressed to engineers and technicians of design/installation of systems and second training aimed at technicians of assembly/maintenance of refrigeration systems. • Overall assessment of project progress: The majority of the planned activities were executed, in line with approved activities for the project. • Impact of these activities: awareness activities and discussions were conducted with the main stakeholders, representing all relevant sectors s involved in the future implementation of the KA in Chile. The country's HFC data reporting was facilitated through the upgraded licensing system. The training prepared under the EA project represents a tool for capacity building. It shall guide Chile's action on sectoral approaches to phase down HFCs, considering improvements on the energy efficiency of cooling systems and use use of low-GWP refrigerants • Potential challenges in completing the projects and activities: A Study Tour in Europe was planned on March 2020 (1 week) for a selected group of authorities involved in the monitoring and control of HFCs and members of the RAC Chamber and stakeholders involved in promoting/adopting low GWP alternatives in Chile. It is expected that the last action under the UNIDO component can progress as expected. • Key findings and lessons learned: training developed in the project allowed to the NOU to identify potential actions at the regulation level as well as sectorial measures, including key elements on safety and standards on energy efficiency applicable for low GWP alternatives; aligning national programs and HPMP to facilitate the phase-down of HFCs and the introduction of low-GWP alternative technologies. | • Status of implementation: project ongoing • Activities implemented (or to be implemented): Demonstration of non-investment activity and preliminary capacity building requirements for the implementation of the Kigali Amendment and its related matters (under UNIDO component): Study Tour on HFCs monitoring and control planned for March 2020 postponed due to quarantine • Milestones achieved: - Work Plan Agreed with NOU was updated - Specific deliverables and results reported: a) Demonstration of non-investment activities in the UNIDO component (training): A Study Tour in Europe (to Austria, Belgium and Denmark) for a selected group of authorities involved in the monitoring and control of HFCs and members of RAC Chamber was organized to be held in March 2020 (postponed until September 2020 if the travel restrictions due to Covid-19 are removed). The objective of the training is to promote de adoption of low GWP alternatives in Chile and share lessons learned and experiences on the application of the EU F-gas regulation and good practices on climate-friendly technologies in relevant sectors. • Overall assessment of project progress: The majority of the planned activities were implemented and according to the approved UNIDO’s activities in the project. Only one action (the study Tour) was postponed due to the Covid-19 pandemic situation. • Activities planned for the second part of 2020: The study tour was planned to Austria, Belgium and Denmark and alternative formats are been explored, including virtual sessions. The site visits are postponed until there is guidance on international travel • Potential challenges in completing the projects and activities: Based on the decision taken by UNIDO management to restrict official travel due to the ongoing outbreak of COVID-19 immediately and until further notice. The schedule of the remaining activity needs to be updated. • Any action required by Executive Committee? Yes. In line with 85th meeting (intersessional) the project shall continue and UNIDO shall report on progress at the 86th meeting |  |  | 2020-06-01
ONG | UNDP | Enabling activities for HFC phase-down | Individual | LAC | CHI | SEV | 80 | TAS | 03+ | N | I | No_ODP | 0 | 0 | 2017-11-01 | 2018-03-01 | 2019-06-01 | 2020-06-01 |  |  | 33000 | 0 | 33000 | 8501 | 25.76% | 24499 | 0 | 7349.73 | 2310 | 0 | 595.063 | 1714.937 | 0 | 2 missions conducted by the international expert, meetings with stakeholders on the central and northern regions to increase awareness on the Kigali Amendment. Social protests during the last trimester of the year slowed down the implementation of the project, additional meetings were moved to 2020. An extension for an additional six months has been requested due to COVID-19. | Meetings with stakeholders were initially scheduled and later postponed due to Covid-19. Virtual meetings have been conducted between NOU and national stakeholders to discuss the implementation of the Kigali Amendment. |  |  | 2020-06-01
ONG | UNEP | Enabling activities for HFC phase-down |  | ASP | CKI | SEV | 82 | TAS | 01+ | A | I | HFC | 0 |  | 2018-12-01 | 2019-06-01 | 2020-06-01 | 2021-06-01 |  |  | 50000 | 0 | 50000 | 14887.63 | 29.78% | 35112.37 | 27000 | 10640.1121 | 3500 | 0 | 1042.1341 | 2457.8659 | 1890 | SSFA signed in May 2019. The first payment has been released to the country 12 June 2019. NOU recruited a local consultant to support EA implementation. One consultation with stakeholders organized in 2019. Identification of new partners is completed. Data collection for Country Assessment completed. NOU worked with legal consultant to amend the Ozone Layer Protection (OLP) regulation to include HFC control. Awareness rising ongoing, NOU produced materials (posters), and distributed relevant factsheets and leaflets to stakeholders. NOU worked with other Pacific Island Countries’ NOUs to jointly develop and submit the joint proposal to Oceania Customs Organization (OCO) for the amendment of the HS code under the Pacific Harmonized Commodity Description and Coding System 2017 (PACHS17) to assign specific HS code for HFCs and blends in accordance with WCO recommendation. The proposal for amendment was approved by the Review Committee in September 2019. Cook Islands ratified the Kigali Amendment on 22 August 2019. | NOU discussing with customs adoption of revised PACHS17 HS code that assigns specific HS code for HFCs and blends. Country Assessment Report drafting ongoing. NOU postponed RAC technicians training for Q3/4 as possible. |  |  | 2021-06-01 | 12000 | 840
ONG | UNIDO | Enabling activities for HFC phase-down |  | AFR | CMR | SEV | 80 | TAS | 01+ | A | I |  | 0 | 0 | 2017-11-01 | 2018-02-01 | 2019-06-01 | 2021-06-30 |  |  | 150000 | 0 | 150000 | 32176 | 21.45% | 117824 | 1209.61 | 50000 | 10500 | 0 | 2252.32 | 8247.68 | 84.6727 | Ratification endorsed by the Parliament in June. Law to ratify the Kigali Amendment adopted. Decree authorizing the President of the Republic to ratify issued. Reporting mechanism updated to include HFCs. Sensitization meeting held with custom officers. Project extension requested at the 83rd meeting and granted. Progress relatively slow. Actions towards next goals: Finalization of the ratification process and organization of workshop on safety. Was there any delay during the reporting year? - No Any recurring problem? - No Any impact on project completion date? - Yes, extension requested at the 83rd meeting Any action required by Executive Committee? - Extension requested and granted. | Ratification process at its final stage. The Minister of External Relations Submitted to the President the request to sign the Instrument of ratification. Licensing system for HFCs in operation. No quota. Workshop on safety postponed due to Covid-19. Ratification pending. Some planned activities have been postponed due to the Covid-19 pandemic. Project extension needed to complete remaining activities once the measures are eased. Was there any delay during the reporting year? - Yes, some activities could not be implemented due to the restrictions imposed. Any recurring problem? - No Any impact on project completion date? - Yes. Any action required by Executive Committee? - Yes, to allow the implementation of the project beyond the 30 months period. |  |  | 2020-06-01
ONG | UNEP | Enabling activities for HFC phase-down |  | AFR | COI | SEV | 81 | TAS | 01+ | A | I | HFC | 0 |  | 2018-06-01 | 2018-12-01 | 2020-01-01 | 2021-01-01 |  |  | 50000 | 0 | 50000 | 25409.93 | 50.82% | 24590.07 | 22300 | 7451.5364 | 3500 | 0 | 1778.6951 | 1721.3049 | 1561 | The country ratified the Kigali amendment on 16 November 2017. National consultants are contracted to assist Customs Office in developing national custom codes for different HFCs and include them into the Customs Tariff in order to ensure proper monitoring and recording of imports/exports or re-export of individual HFCs. Comprehensive review of National licensing system for ODS, ODS alternatives and based-products was done in 2019. Analysis of existing policy and regulatory framework for HFCs was done in 2019. Stakeholders consultation meetings and awareness programmes to facilitate the ratification process at the national level were organised. Awareness material for HFC phase down was produced and disseminated to the stakeholders and the public. The development of Customs Harmonized Code was to be finalized by an international consultant by December 2019. It is delayed and will be finalized by July 2020. Two sensitization meetings for the servicing sector on safe handling of HFCs and alternatives will be organized in 2020. | The country ratified the Kigali amendment on 16 November 2017. National consultants are contracted to assist Customs Office in developing national custom codes for different HFCs and include them into the Customs Tariff in order to ensure proper monitoring and recording of imports/exports or re-export of individual HFCs. Comprehensive review of National licensing system for ODS, ODS alternatives and based-products was done in 2019. Analysis of existing policy and regulatory framework for HFCs was done in 2019. Stakeholders consultation meetings and awareness programmes to facilitate the ratification process at the national level were organised. Awareness material for HFC phase down was produced and disseminated to the stakeholders and the public. The development of Customs Harmonized Code was to be finalized by an international consultant by December 2019. It is delayed and will be finalized by July 2020. Two sensitization meetings for the servicing sector on safe handling of HFCs and alternatives will be organized in 2020. |  |  | 2021-01-01 | 15000 | 1050
ONG | UNDP | Enabling activities for HFC phase-down | Individual | LAC | COL | SEV | 80 | TAS | 01+ | N | I | No_ODP | 0 | 0 | 2017-11-01 | 2018-10-01 | 2019-06-01 | 2020-06-01 |  |  | 250000 | 0 | 250000 | 106886 | 42.75% | 143114 | 14134.07 | 42934.197 | 17500 | 0 | 7482.0207 | 10017.9793 | 989.3849 | Kigali Amendment approved by congress, under review of the Constitutional Court; Participation in a regional workshop in Costa Rica to discuss the implementation of the Kigali Amendment. Awareness raising about the Kigali Amendment conducted around the country. An extension for an additional twelve months has been requested due to COVID-19. | ToR prepared for consultancies of different assessements related to the implementation of the Kigali Amendment were prepared. A workshop with importers of controlled substances were prepared and scheduled. |  |  | 2020-06-01
ONG | UNDP | Enabling activities for HFC phase-down | Individual | LAC | COS | SEV | 80 | TAS | 01+ | N | I | No_ODP | 0 | 0 | 2017-11-01 | 2018-03-01 | 2019-06-01 | 2020-06-01 |  |  | 150000 | 0 | 150000 | 103341 | 68.89% | 46659 | 15801.96 | 13997.592 | 10500 | 0 | 7233.8952 | 3266.1048 | 1106.1372 | HFCs included in licensing system. Participation in international workshop in New York in May to exchange experiences with other A5 countries. Organize natural refrigerant fair in Costa Rica with international participation. Organized and attended international workshop on Kigali amendment in Costa Rica. | Final report being prepared by the NOU in Costa Rica |  |  | 2020-06-01
ONG | UNEP | Enabling activities for HFC phase-down |  | ASP | CPR | SEV | 80 | TAS | 01+ | A | I | HFC | 0 |  | 2017-11-01 | 2018-06-01 | 2019-06-01 | 2020-12-01 |  |  | 85000 | 0 | 85000 | 4684.58 | 5.511% | 80315.42 | 79950 | 24338.0061 | 5950 | 0 | 327.9206 | 5622.0794 | 5596.5 | The SSFA was signed in June 2018, and the first payment was released to the country in June 2018. Consultations done with customs authorities on the licensing system for HFCs import/export control, sensitization of customs officers, on-site visit of HFC manufacturers. The Kigali Amendment and ratification progress were introduced at the training workshops for enforcement officers from local EEB and the two training workshops for ODS management officers from local EEB in 2019. NOU collected and reviewed awareness materials on Kigali Amendment and started preparation of various materials. | A consultation meeting was held on the new HS code for HFCs in accordance with the recommendations of the WCO in March 2020. A seminar followed in May 2020 to review and consider the new HS code for HFCs and its future management of one-to-one coding. NOU is preparing materials including translation of UNEP factsheet on Kigali Amendment. The first draft a R290 AC booklet has been completed; two rounds of modifications have been carried out for the HFC-23 brochure, and it is expected to be finalized and printed in Q3. |  |  | 2020-06-01 | 40000 | 2800
COM | UNDP | Project preparation for conversion from HFC-245fa to cyclopentane plus HFOs (C5+HFO) as a foam agent in a refrigerator manufacturer | Individual | ASP | CPR | FOA | 80 | PRP | 02+ | N | X | No_ODP | 0 | 0 | 2017-11-01 | 2018-03-01 | 2018-12-01 |  | 2019-06-01 |  | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0.46 | 2100 | 0 | 2099.9678 | 0.0322 | 0 | Project proposal submitted to 81st ExCom meeting and approval was deferred. Project approved at 82nd ExCom in December 2018. Project preparation activities completed June 2019. |  | 10241
FIN | UNDP | Project preparation for a demonstration project to convert HFC-23 by-product to valuable organic halides by reaction with hydrogen and carbon dioxide for Liaocheng Fuer New Material Technology Ltd. | Individual | ASP | CPR | PRO | 80 | PRP | 03+ | N | I | HFC | 0 | 0 | 2017-11-01 | 2018-01-01 | 2018-12-01 |  | 2018-06-01 | 2019-05-01 | 30000 | -25934 | 4066 | 4066 | 100% | 0 | 0 | 0 | 2100 | -1815 | 284.6 | 0.4 | 0 | Remarks1 - up to 31 Dec 2018: Project completed. UNDP facilitated discussions between a US-based technology provider and potential demonstration enterprise in China. Full project proposal could not be prepared due to the inability to reach an agreement between the technology provider and an enterprise in China. |  | 0
ONG | UNDP | Enabling activities for HFC phase-down | Individual | ASP | CPR | SEV | 80 | TAS | 04+ | N | X | No_ODP | 0 | 0 | 2017-11-01 | 2018-09-01 | 2019-06-01 | 2020-12-01 |  |  | 165000 | 0 | 165000 | 49520 | 30.01% | 115480 | 0 | 34644.012 | 11550 | 0 | 3466.3972 | 8083.6028 | 0 | MEE working closely with line ministries of National Leading Group on promoting ratification of Kigali Amendment. MEE and Import/Export Office working with General Administration of Customs to establish HFCs licensing and quota system and preparation of HS code for HFCs. FECO is consulting with industrial associations including automobile association to establish HFCs data reporting system. A preliminary HFC data collection system was established and data collected are being analyzed. Extension to December 2020 for project completion due to global health situation. | Project activities were limited during first quarter of 2020 due to COVID-19. MEE prepared assessment report on the impacts of ratifying the Kigali Amendment in China based on updated situation, kept close communication with and consulted other member ministries of the National Leading Group on ratification of the Kigali Amendment and preparation for HFC management. Draft version of research report on legal framework of HFCs management and initial research on HFCs phase-down national strategy completed. | 30897 |  | 2020-06-01
ONG | UNIDO | Preparation for converting from HFC-134a to HFOs+CO2 with gluing technology in an extruded polystyrene foam manufacturer |  | ASP | CPR | FOA | 81 | PRP | 05+ | A | I |  | 0 | 0 | 2018-06-01 | 2019-03-01 | 2019-07-01 | 2020-12-31 |  |  | 30000 | 0 | 30000 | 13626.5 | 45.42% | 16373.5 | 0 | 0 | 2100 | 0 | 953.855 | 1146.145 | 0 | Project submitted and withdrawn as per agreement with MLF. | It is planned to resubmit for the 86th ExCom.
ONG | UNDP | Conversion from C5+HFC-245fa to C5+HFOs in a domestic refrigerator manufacturer (Hisense Kelon) | Individual | ASP | CPR | FOA | 82 | INV | 06+ | N | X | HFC | 250 | 54.1 | 2018-12-01 | 2019-05-01 | 2020-12-01 | 2021-06-01 |  |  | 1275000 | 0 | 1275000 | 1018413 | 79.88% | 256587 | 0 | 76976.007 | 89250 | 0 | 71288.9317 | 17961.0683 | 0 | Project document signed April 2019, contract between FECO and beneficiary signed August 2019. On-site verification of the CD line conversion conducted November 2019. Hisenes-Kelon was in the process of finishing the line conversion and started trial production end 2019. | Project activities were stopped during the first quarter of 2020 due to COVID-19. Project implementation has now resumed and large-scale trial production has restarted based on order volume. | 380000
ONG | UNEP | Enabling activities for HFC phase-down |  | AFR | DJI | SEV | 81 | TAS | 01+ | A | I | HFC | 0 |  | 2018-06-01 | 2018-12-01 | 2020-01-01 | 2021-01-01 |  |  | 50000 | 0 | 50000 | 2351.69 | 4.703% | 47648.31 | 43800 | 14438.8818 | 3500 | 0 | 164.6183 | 3335.3817 | 3066 | Translation of the Kigali amendment into national language was done and presented in December 2019. The consultants for customs codes development were contracted in Dember 2019 in order to develop custom codes for different HFCs and include them into the Customs Tariff in order to ensure proper monitoring and recording of imports/exports or re-export of individual HFCs. | Te Kigali amendment document presented to the government autorities in January 2020. The consultants for customs codes development contracted in December 2019 continued the development of custom codes for different HFCs and include them into the Customs Tariff in order to ensure proper monitoring and recording of imports/exports or re-export of individual HFCs. |  |  | 2021-01-01 | 20000 | 1400
ONG | UNEP | Enabling activities for HFC phase-down |  | LAC | DMI | SEV | 80 | TAS | 01+ | A | I | HFC | 0 |  | 2017-11-01 |  | 2019-06-01 | 2021-06-01 |  |  | 50000 | 0 | 50000 | 0 | 0% | 50000 | 0 | 15151.5152 | 3500 | 0 | 0 | 3500 | 0 | SSFA was signed by UNEP in June 2019. The mission took place in July 2019. Government committed to the project and signature of the SSFA expected soon. Processing of first disbursement will occur thereafter. | SSFA was signed by UNEP in June 2019. The mission took place in July 2019. Country reported issues with having to change banking information and adminsitrative structures, folloiwng the passing of the Hurricane. The banking information and new PS and Mininsitry was officially sent in 17 Feb 2020. UNEP proceeded to record new coordinates and banking info in UMOJA which flagged a Grant Expiration date of July 2020. Project expiration date by ExCom decision is June 2020. The Governmnet is requesting a special extension date (until June 2021) request for DMI under these circumstances. COVID-19 has further strong impacs on this project. |  | To request a status report to the 86th meeting on the level of funds disbursement and on progress in implementation | 2020-06-01 | 0 | 0
COM | UNDP | Project preparation for conversion from HFC-134a to HC-290 in the manufacture of commercial refrigerators at Farco | Individual | LAC | DOM | REF | 80 | PRP | 01+ | N | I | No_ODP | 0 | 0 | 2017-11-01 | 2018-01-01 | 2018-12-01 |  | 2018-12-01 |  | 30000 | 0 | 30000 | 11572 | 38.57% | 18428 | 0 | 18428.25 | 2100 | 0 | 810.0225 | 1289.9775 | 0 | Remarks1 - up to 31 Dec 2018: International expert hired, 2 missions conducted to visit the plant. Project prepared and submitted to the 81st ExCom meeting. Pending payment of existing obligations.
ONG | UNEP | Enabling activities for HFC phase-down |  | LAC | DOM | SEV | 80 | TAS | 02+ | A | I | HFC | 0 |  | 2017-11-01 | 2018-12-01 | 2019-06-01 | 2020-12-01 |  |  | 150000 | 0 | 150000 | 97373.1 | 64.92% | 52626.9 | 29081.32 | 15947.5455 | 10500 | 0 | 6816.117 | 3683.883 | 2035.6924 | Project progressing satisfactorily. The SSFA for US$ 93,000 was signed in May 2018. The first payment has been released to the country in July 2018. While the HFC licensing system is in place, drafting other regulatory measures to promote the HFC phase-down and opening Customs Code to identify HFCs and its blends is in progress. Analysis on the current country use of HFC by sub-sectors in order to forecast HFC consumption scenarios and identify the critical route to achieve the national objectives of HFC phase-down. The Amendment to the Montreal Protocol adopted in Kigali, is awaiting approval by the Chamber of Deputies of the National Congress to be signed into law. Participation of the Ozone Program Coordinator and personnel from the Ministry of Defense as part of the work agreement with the Vocational Schools of the Armed Forces and the National Police in Madrid, Spain on June 2019. 2 workshops were held in November 2019 to train 350 technicians on the importance of HFC phasedown and adopting RAC technologies with lower GWP and more energy efficient. | In May must be ready a link for digital control of HFC requests on the website of the Ministry of Environment and Natural Resources, which will allow real-time monitoring on national consumption of controlled substances and alternatives, including HFCs. There are some delays due to COVID-19. |  |  | 2020-06-01 | 19743.88 | 1382.0716
ONG | UNEP | Enabling activities for HFC phase-down |  | AFR | DRC | SEV | 81 | TAS | 01+ | A | I | HFC | 0 |  | 2018-06-01 | 2018-11-01 | 2020-01-01 | 2021-01-01 |  |  | 150000 | 0 | 150000 | 11780.18 | 7.853% | 138219.82 | 104800 | 41884.7939 | 10500 | 0 | 824.6126 | 9675.3874 | 7336 | National consultants are contracted to assist Customs Office in developing national custom codes for different HFCs and include them into the Customs Tariff in order to ensure proper monitoring and recording of imports/exports or re-export of individual HFCs. The development of Customs Harmonized Code was to be finalized by an international consultant by December 2019. It is delayed and will be finalized by July 2020. Two sensitization meetings for the servicing sector on safe handling of HFCs and alternatives will be organized in 2020. | National consultants are contracted to assist Customs Office in developing national custom codes for different HFCs and include them into the Customs Tariff in order to ensure proper monitoring and recording of imports/exports or re-export of individual HFCs. The development of Customs Harmonized Code was to be finalized by an international consultant by December 2019. It is delayed and will be finalized by July 2020. Two sensitization meetings for the servicing sector on safe handling of HFCs and alternatives will be organized in 2020. |  |  | 2021-01-01 | 50000 | 3500
FIN | UNIDO | Project preparation for the phase-out of HFC-134a and R404a in the manufacturing sector at Ecasa |  | LAC | ECU | REF | 80 | PRP | 01+ | A | I |  | 0 | 0 | 2017-11-01 | 2018-02-01 | 2018-12-01 |  | 2018-12-18 | 2019-09-26 | 30000 | -63 | 29937 | 29936.69 | 100% | 0.31 | 0.01 | 0 | 2100 | -4 | 2095.5683 | 0.4317 | 0.0007 | Project was financially closed in September 2019. Remaining fund balances were returned at the 84th ExCom meeting in December 2019. | N/A
ONG | UNEP | Enabling activities for HFC phase-down |  | LAC | ECU | SEV | 80 | TAS | 02+ | A | I | HFC | 0 |  | 2017-11-01 | 2019-08-13 | 2019-06-01 | 2020-12-01 |  |  | 150000 | 0 | 150000 | 1040.11 | 0.6934% | 148959.89 | 45770.31 | 45139.3606 | 10500 | 0 | 72.8077 | 10427.1923 | 3203.9217 | Ecuador ratified the Kigali Amendment on January 22, 2018. By Resolution 023-2017 of August 23th, 2017, HFCs in pure and mixed form were included in the licensing system. Once the base line for consumption of these substances is established in 2024, it will be proposed to the Committee on Foreign Trade to establish the trade policy instrument that will allow for the progressive reduction of the import of these substances, through the allocation of import quotas. A national consultant was hired from May to December to support in the implementation of EAK, who carried out the following activities: May 2019: Elaboration of the initial proposal with the company FRACTALSOFT to automate the licensing system, including HFC reports. Presentation of the EA project to the white line sector and definition of support to implement policies for the elimination of HFCs in commercial refrigeration. June 2019: First meeting held with The Ecuadorian Technical Association of Air Conditioning and Refrigeration where the objectives of the project were presented, and a series of future actions were planned. July 2019 - August 2019: Elaboration of terms of reference for the hiring of an IT consultant to develop the licensing system automation platform. In August the official request was made to the regional office to start the selection process. September 2019 - October 2019: Elaboration of concept notes to request to UNEP the due financial authorizations to carry out the dialogue tables in the sectors that UTO has considered as priority. Elaboration of terms of reference for the hiring of a consultant to elaborate technical standards related to the labeling of cylinders and handling of HC in domestic and commercial refrigeration. November 2019 - December 2019: Preparation of terms of reference for hiring of a consultant to prepare a study on the penetration of alternatives to HFCs in the Ecuadorian market. All selection processes were managed in December 2019. In December was hired another consultant to provide technical assistance to the National Ozone Unit on Illegal Trade prevention and Training on Montreal Protocol controls. | In February a national consultant was hired for the automation of the import control system for substances controlled by the Montreal Protocol. Then in April two more national consultants were hired to advice to the relevant institutions on adoption and adaptation of technical standards for the safe handling of refrigerants, and assessment of the Kigali Amendment Enabling Activities in Ecuador. There are some delays due to COVID-19. |  |  | 2020-06-01 | 32890.31 | 2302.3217
COM | UNDP | Project preparation for conversion from HFC-134a to HFO-1234ze and other liquid HFOs in the manufacuture of polyurethane foam and spray foam | Individual | AFR | EGY | FOA | 80 | PRP | 01+ | N | I | No_ODP | 0 | 0 | 2017-11-01 | 2018-04-01 | 2018-12-01 |  | 2018-12-01 |  | 30000 | 0 | 30000 | 17964 | 59.88% | 12036 | 0 | 12036.42 | 2100 | 0 | 1257.4506 | 842.5494 | 0 | Remarks1 - up to 31 Dec 2018: The project document on HFC phase-out in PU foam industry was revised and resubmitted to the 82nd ExCom, but was not recommended by MLF and was not approved by the ExCom. It carried an added value on optimization of HFO technology in terms of performance and price reduction. This preparatory project is therefore completed, as no new re-submission is expected.
ONG | UNIDO | Enabling activities for HFC phase-down |  | AFR | EGY | SEV | 81 | TAS | 02+ | N | I |  | 0 | 0 | 2018-06-01 | 2019-01-01 | 2020-01-01 | 2021-01-01 |  |  | 105000 | 0 | 105000 | 17712.32 | 16.87% | 87287.68 | 2086.74 | 20000 | 7350 | 0 | 1239.8624 | 6110.1376 | 146.0718 | Ratification approved by the ministries of Environment, Foreign Affairs and Trade & Industry. National consultants identified for the Firefighting and MAC sectors and recruited. Survey of the firefighting sector undertaken. Survey of the MAC sector initiated. Workshop organized. Actions towards next goals: Completion of the firefighting and MAC sectors surveys. Was there any delay during the reporting year? - No Any recurring problem? - No Any impact on project completion date? - Yes, extension requested at the 84th meeting Any action required by Executive Committee? - Extension requested and granted. | Ratification of the Kigali amendment is in the final stage. Firefighting sector survey completed. MAC sector survey ongoing. Ongoing work on the update of local standards; Ongoing work for the preparation of a national cooling strategy. Progress has been satisfactory. |  |  | 2021-01-01
ONG | UNEP | Enabling activities for HFC phase-down |  | AFR | EGY | SEV | 81 | TAS | 03+ | A | I | HFC | 0 |  | 2018-06-01 | 2019-07-01 | 2020-01-01 | 2021-01-01 |  |  | 145000 | 0 | 145000 | 3986.77 | 2.749% | 141013.23 | 135000 | 42731.2818 | 10150 | 0 | 279.0739 | 9870.9261 | 9450 | The SSFA was signed in June 2019 with a total amount of USD 145,000. The first payment was released to the country in July 2019. The NOU translated the Kigali amendment support documents into Arabic Language. The NOU conducted training workshop for stakeholders and awareness raising campaigns for the public on HFCs environmental impact and their alternatives’ environmental and economical benefits. These key activities reduced the interest of the technicians, stakeholder and public on the usage of HFCs and other high WP refrigerants containing products. The customs also strengthen their controlling mechanism of fake refrigerants. Meaningful steps also initiated to revise the ODS legislation to incorporate license quotas for HFCs. Overall assessment of project progress is satisfactory. | The NOU is working with related companies to develop online software to help NOUs manage ODS Registry. Egyptian Environmental Affairs Agency is working with Egyptian Organization for Standardization in order to review and update local standards (equipment and containers ). Egyptian Environmental Affairs Agency is working with other stakeholders in order to prepare National Cooling Strategy. Delays in some projects activities are to be expected due to measures taken by the country related to Coronavirus outbreak, which resulted for example in postponing all meetings/ events planned in the first half of the year.” |  |  | 2021-01-01 | 80000 | 5600
ONG | UNEP | Enabling activities for HFC phase-down |  | AFR | EQG | SEV | 81 | TAS | 01+ | A | I | HFC | 0 |  | 2018-06-01 | 2018-11-01 | 2020-01-01 | 2021-01-01 |  |  | 150000 | 0 | 150000 | 98293.69 | 65.53% | 51706.31 | 51706.31 | 26764.0667 | 10500 | 0 | 6880.5583 | 3619.4417 | 3619.42 | National consultants are contracted to assist Customs Office in developing national custom codes for different HFCs and include them into the Customs Tariff in order to ensure proper monitoring and recording of imports/exports or re-export of individual HFCs. Comprehensive review of National licensing system for ODS, ODS alternatives and based-products was done in 2019. Analysis of existing policy and regulatory framework for HFCs was done in 2019. Stakeholders consultation meetings and awareness programmes to facilitate the ratification process at the national level were organised. Awareness material for HFC phase down was produced and disseminated to the stakeholders and the public. The development of Customs Harmonized Code was to be finalized by an international consultant by December 2019. It is delayed and will be finalized by July 2020. Two sensitization meetings for the servicing sector on safe handling of HFCs and alternatives will be organized in 2020. | National consultants are contracted to assist Customs Office in developing national custom codes for different HFCs and include them into the Customs Tariff in order to ensure proper monitoring and recording of imports/exports or re-export of individual HFCs. Comprehensive review of National licensing system for ODS, ODS alternatives and based-products was done in 2019. Analysis of existing policy and regulatory framework for HFCs was done in 2019. Stakeholders consultation meetings and awareness programmes to facilitate the ratification process at the national level were organised. Awareness material for HFC phase down was produced and disseminated to the stakeholders and the public. The development of Customs Harmonized Code was to be finalized by an international consultant by December 2019. It is delayed and will be finalized by July 2020. Two sensitization meetings for the servicing sector on safe handling of HFCs and alternatives will be organized in 2020. |  |  | 2021-01-01 | 35000 | 2450
ONG | UNEP | Enabling activities for HFC phase-down |  | AFR | ERI | SEV | 80 | TAS | 01+ | A | I | HFC | 0 |  | 2017-11-01 | 2018-12-01 | 2019-06-01 | 2020-12-01 |  |  | 95000 | 0 | 95000 | 1762 | 1.855% | 93238 | 85000 | 28253.9394 | 6650 | 0 | 123.34 | 6526.66 | 5950 | The SSFA was signed in November 2018 with a total amount of USD 95,000. The first payment was released to the country in December 2018. The NOU conducted training workshop for stakeholders and awareness raising campaigns of the public on HFCs environmental impact and their alternatives’ environmental and economical benefits. These key activities reduced the interest of the technicians, stakeholder and public on the usage of HFCs and other high WP refrigerants containing products. The customs also strengthen their controlling mechanism of fake refrigerants. Meaningful steps also initiated to revise the ODS legislation to incorporate license quotas for HFCs. The NOU conducted training on safe use of handling HCs and HFC on 23-24 July 2019 in Asmara (NCEW Hall) and 27 July-1t August 2019 in Massawa (MWVTC Hall) for 75 RAC technicians. Overall assessment of project progress is satisfactory. | The NOU of translated Kigali amendment supporting documents into the national language (Tigrina) in January 2020. The government of Eritrea along with its agencies have given keen attention to equipping RAC training centers with modernized demonstrations and tools. Various trainings for RAC technicians, stakeholders including the importers and other relevant institutions have been conducted on these training centers. These essential activities enhanced the overall capacity of nationals on this new technology for the nation and also assisted the youngster to development of various innovational products. Refrigerant check service is continuously given to importers, users at the entry points and headquarters. Delays in some projects activities are to be expected due to measures taken by the country related to Coronavirus outbreak, which resulted for example in postponing all meetings/ events planned in the first half of the year. |  |  | 2020-06-01 | 50000 | 3500
ONG | UNEP | Enabling activities for HFC phase-down |  | AFR | ETH | SEV | 81 | TAS | 01+ | A | I | HFC | 0 |  | 2018-06-01 | 2018-12-01 | 2020-01-01 | 2021-01-01 |  |  | 95000 | 0 | 95000 | 4158 | 4.377% | 90842 | 85000 | 27527.8788 | 6650 | 0 | 291.06 | 6358.94 | 5950 | The SSFA was signed by the Government of Ethiopia in December 2018 with a total amount of USD 95,000. The first payment was released to the country in December 2018. Kigali amendment is translated into the national language October 2019. The Law on ratification of the Kigali Amendment is drafted in January 2019. Package for ratification of the Kigali amendment is developed and the result was presented to the standing committee of the environment parliament. Kigali amendment was ratified by the Parliament on 2 April 2019. Awareness ongoing for different target groups including importers, Media Members of the Parliament particularly standing committee for Environment and Natural resource, Regional and city Administrations Environmental protection Authority and the public at large. Finalizing the licensing and quota system for HFCs including the control through Ozone depilating substance monitoring proclamation. Training of technicians on going for both R 600 and R290 in multiple batches for all sectors. Overall assessment of project progress is satisfactory | The NOU undertook the Draft Legislative revision of Customs code in February 12, 2020. The NOU is working in close collaboration with the Ministry of Water Irrigation and Electricity to address the Energy Efficiency Management Issue and to encourage the use of energy efficient appliances. Delays in some projects activities are to be expected due to measures taken by the country related to Coronavirus outbreak, which resulted for example in postponing all meetings/ events planned in the first half of the year. |  |  | 2021-01-01 | 50000 | 3500
ONG | UNDP | Enabling activities for HFC phase-down | Individual | ASP | FIJ | SEV | 80 | TAS | 01+ | N | I | No_ODP | 0 | 0 | 2017-11-01 | 2019-02-01 | 2019-06-01 | 2020-06-01 |  |  | 150000 | 0 | 150000 | 17511 | 11.67% | 132489 | 0 | 39746.796 | 10500 | 0 | 1225.7476 | 9274.2524 | 0 | Regulation for HFC licensing & quota system is under development. NOU currently provides consent letters for the importation of HFC refrigerants and equipment and does monitoring through Customs Department. HFC data collection is in final stage. Ratification is under process and at an advanced stage. | International consultants (technical and legal) could not travel to Fiji for stakeholder meeting. Draft report is being prrepared by consultant. Extension requested upto Dec 2020. |  |  | 2020-06-01
ONG | UNEP | Enabling activities for HFC phase-down |  | ASP | FSM | SEV | 81 | TAS | 01+ | A | I | HFC | 0 |  | 2018-06-01 | 2019-02-01 | 2020-01-01 | 2021-01-01 |  |  | 50000 | 0 | 50000 | 16234.64 | 32.47% | 33765.36 | 32965 | 10231.9273 | 3500 | 0 | 1136.4248 | 2363.5752 | 2307.55 | SSFA was signed in November 2018. The first payment was released to the country in February 2019. Data collection for Country Assessment completed. One stakeholder workshop done in October 2019 in Ponhnpei with 35 participants. Legislation review is in progress - one consultation meeting with FSM National Government Department of Justice. Revised PACHS17 HS code including HFCs adopted. One consultation meeting with Micronesian Productions for ozone and Kigali awareness campaign, NOU adapting UNEP materials for awareness raising. NOU worked with other Pacific Island Countries’ NOUs to jointly develop and submit the joint proposal to Oceania Customs Organization (OCO) for the amendment of the HS code under the Pacific Harmonized Commodity Description and Coding System 2017 (PACHS17) to assign specific HS code for HFCs and blends in accordance with WCO recommendation. The proposal for amendment was approved by the Review Committee in September 2019. Status of KA ratification, ratified on 12 May 2017. | Country Assessment Report final draft currently under revision. Drafting of amendment ongoing. NOU started working with international IT consultant to develop the online licensing system to facilitate application process. NOU postponed RAC technicians training for Q3/4 as possible. |  |  | 2021-01-01 | 11500 | 805
ONG | UNEP | Enabling activities for HFC phase-down |  | AFR | GAB | SEV | 80 | TAS | 01+ | A | I | HFC | 0 |  | 2017-11-01 | 2018-08-01 | 2019-06-01 | 2020-12-01 |  |  | 150000 | 0 | 150000 | 109234.65 | 72.82% | 40765.35 | 25000 | 12353.1364 | 10500 | 0 | 7646.4255 | 2853.5745 | 1750 | The country ratified the Kigali amendment on 2018-02-28 . In 2019, National consultants were contracted to assist Customs Office in developing national custom codes for different HFCs and include them into the Customs Tariff in order to ensure proper monitoring and recording of imports/exports or re-export of individual HFCs. Comprehensive review of National licensing system for ODS, ODS alternatives and based-products was done in 2019. Analysis of existing policy and regulatory framework for HFCs was done in 2019. Stakeholders consultation meetings and awareness programmes to facilitate the ratification process at the national level were organised. Awareness material for HFC phase down was produced and disseminated to the stakeholders and the public. | In January 2020 an Internatuional Consultant was identified to develop Customs Harmonized Code for Central African Countries. TOR developped in March 2020. There are delays due to COVID-19. |  |  | 2020-06-01 | 25000 | 1750
ONG | UNIDO | Enabling activities for HFC phase-down |  | AFR | GAM | SEV | 80 | TAS | 01+ | A | I |  | 0 | 0 | 2017-11-01 | 2018-03-01 | 2019-06-01 | 2020-12-30 |  |  | 95000 | 0 | 95000 | 73884.43 | 77.77% | 21115.57 | 20901.19 | 21000 | 6650 | 0 | 5171.9101 | 1478.0899 | 1463.0833 | Continued implementation as per agreed action plan. Activities related to ratification are ongoing. Milestones achieved: A variety of consultation and awareness raising meetings with the different involved ministries as well as national assembly members and environment groups took place. Workshops and capacity building activities on low-GWP refrigerant use in different sectors and servicing for stakeholders from the public and private sector took place. The ratification process is close to finalization (but is on hold since the covid-19 pandemic.) Overall assessment of project progress: - Some delays in project implementation. - Request for extension was approved at 83rd Excom with new end date 30 June 2020. - Activities progressing as per updated implementation plan. | NOU updated UNIDO that due to covid-19 pandemic the ratification process has been delayed, latest update received on 1 June that that the ministry has planned to table Kigali Amendment ratification before the National Assembly members in August and expected ratification shortly after. Milestones achieved: The draft reports for legal and for the country strategy are ready for the final review and stakeholder validation (date is pending due to covid-19). Actions towards next goals: Review of the draft reports and finalization of reports. Was there any delay during the reporting year? Yes. Activities have been delayed due to the covid-19 pandemic. Any recurring problem? No. Any impact on project completion date: Yes. Any action required by Executive Committee? Yes. The ExCom has already allowed implementing agencies at the 85th meeting to continue implementing the time-sensitive HFC related project. |  |  | 2020-06-01
ONG | UNEP | Enabling activities for HFC phase-down |  | AFR | GBS | SEV | 81 | TAS | 01+ | A | I | HFC | 0 |  | 2018-06-01 | 2018-11-01 | 2020-01-01 | 2021-01-01 |  |  | 95000 | 0 | 95000 | 36143.84 | 38.05% | 58856.16 | 39800 | 17835.2 | 6650 | 0 | 2530.0688 | 4119.9312 | 2786 | In May 2019, a consultants was hired to assist Customs Office in developing national custom codes for different HFCs and include them into the Customs Tariff in order to ensure proper monitoring and recording of imports/exports or re-export of individual HFCs. In December 2019, the country orgnised a consultation meeting for ECOWAS countries for the extension of the subheadings 2903.39 and 3824.78 of the Tariff and Statis-tical Nomenclature (TSN) of the Common External Tariff (CET) of the Economic Community of West African States (ECOWAS) in order to facilitate the collection and comparison of data concerning the circulation of hydrofluorurocarbons (HFC) | In January -March 2020 GBS NOO participated in many exchanges that lead to the recrutment of an International Consultant and a Draft proposal for the extension of the subheadings 2903.39 and 3824.78 of the Tariff and Statis-tical Nomenclature (TSN) of the Common External Tariff (CET) of the Economic Community of West African States (ECOWAS) in order to facilitate the collection and comparison of data concerning the circulation of hydrofluorurocarbons (HFC) will be developed and submitted to WCO. |  |  | 2021-01-01 | 25000 | 1750
ONG | UNEP | Enabling activities for HFC phase-down |  | EUR | GEO | SEV | 81 | TAS | 01+ | A | I | HFC | 0 |  | 2018-06-01 |  | 2020-01-01 | 2021-06-01 |  |  | 95000 | 0 | 95000 | 0 | 0% | 95000 | 95000 | 28787.8788 | 6650 | 0 | 0 | 6650 | 6650 | Progress January – December 2019: Georgia aims to ratify the Kigali Amendment in 2020. The agreement with REC Caucasus was signed in December 2018 and the first cash advance payment released in March 2019. An initial coordination meeting between REC Caucasus and the Ministry of Environment Protection and Agriculture took place in April 2019. Existing ozone- and climate-protection policies / legislation were analyzed and policy measures, technical assistance and investment activities recommended in October 2019. The implications and benefits of Kigali Amendment ratification were analyzed in December 2019. Awareness campaigns and meetings to raise the awareness of stakeholders and the general public on the importance and benefits of the Kigali Amendment were organized. Draft legislative frameworks for effective implementation of HFCs licensing and quota system as well as monitoring and reporting mechanism were prepared and first round of internal governmental hearings for adoption of proposed amendments initiated. The existing steering committee was used to consult relevant stakeholders including RAC sector, customs and academics. The first stakeholder consultation took place in November 2019 with the participation of UNEP. A detailed action plan was developed and agreed with national stakeholders. The draft resolution on “Amendments and Additions to the Resolution of the Government of Georgia” was developed and submitted to the ministry for consideration. An explanatory note was prepared to submit draft resolution and package of amendments to the law, which outlined the implications and benefits of Kigali Amendment ratification. ExCom 84 approved the extension of the project until December 2020 to allow the completion of activities. | Progress January – May 2020: Information sheets and a recommendation report on pros and cons of Kigali Amendment ratification were produced in January 2020. The second stakeholder consultation took place in March 2020. The training needs assessment of ministry staff, customs officers, servicing sector technicians, and other stakeholders was completed in April 2020. The first interim progress and financial reports were submitted in March 2020 and the second cash advance payment released in April 2020. Due to Covid-19 and the related travel restrictions, international experts cannot come to Georgia and RAC trainers cannot attend international training on the safe use of alternatives. Therefore, an extension of the project until June 2021 might be required to allow the completion of planned activities. |  |  | 2021-01-01 | 45000 | 3150
COM | UNEP | Enabling activities for HFC phase-down |  | AFR | GHA | SEV | 80 | TAS | 01+ | A | I | HFC | 0 |  | 2017-11-01 | 2018-12-01 | 2019-06-01 |  | 2019-12-01 |  | 150000 | 0 | 150000 | 147405.15 | 98.27% | 2594.85 | 0 | 2594.85 | 10500 | 0 | 10318.3605 | 181.6395 | 0 | Ghana ratified Kigali Amendment . Needs assessment report was prepared for RAC technicians, Customs Officers and NOU to implement Kigali Amendment. Awareness raising was conducted for different target groups including RAC technicians, importers, and the public at large. Training of technicians on the use of R290 in AC units was also conducted Already 410 R290 based Acs have been installed. Plans are underway to upscale and transform the AC market to 70% R290 AC units by 2030.The NOU worked in close collaboration with the Energy Commission of the Ministry of Energy and other stakeholders on the use of energy efficient refrigerants. Overall assessment of project progress is satisfactory. | The NOU worked in close collaboration with the Energy Commission of the Ministry of Energy and other stakeholders on the use of energy efficient refrigerants. Project completed. Delays in the preparation of the final report are to be expected due to measures taken by the country related to Coronavirus outbreak. |  |  | 2019-12-01 | 0 | 0
ONG | UNIDO | Enabling activities for HFC phase-down |  | LAC | GRN | SEV | 81 | TAS | 01+ | A | I |  | 0 | 0 | 2018-06-01 | 2019-01-01 | 2020-01-01 | 2020-01-01 |  |  | 50000 | 0 | 50000 | 11819.73 | 23.64% | 38180.27 | 34650 | 34650 | 3500 | 0 | 827.3811 | 2672.6189 | 2425.5 | The country ratified the Kigali Amendment on 29th of May 2018. All activities are complete except the last workshop. Codes, licensing and quota system for HFC updated. Harmonized tariff codes and standards finalized. Energy efficiency and national standards to meet the Kigali Amendment shared through the established inter-ministerial coordination mechanism. The final workshop was concluded. Was there any delay during the reporting year? NO. Any recurring problem? NO Any impact on project completion date: NO Any action required by Executive Committee? NO | Project completion and follow-up. The last workshop has been held and the final report was submitted before the project was closed.
ONG | UNEP | Enabling activities for HFC phase-down |  | LAC | GUA | SEV | 80 | TAS | 01+ | A | I | HFC | 0 |  | 2017-11-01 | 2018-12-01 | 2019-06-01 | 2020-12-01 |  |  | 150000 | 0 | 150000 | 89299.85 | 59.53% | 60700.15 | 36876.85 | 18393.9848 | 10500 | 0 | 6250.9895 | 4249.0105 | 2581.3795 | Project progressing satisfactorily. A SSFA was signed in June 2018. Last payment has been released to the country in October 2019. The process of ratification of the Kigali Amendment is in the Congress of the Republic of Guatemala was filed under No. 5593. Through Government Agreement 317-2019, which modifies Government Agreement 137-2016, a license is requested for all substances controlled by the Montreal Protocol, including HFCs, this applies both to refrigerants and to HCFC/HFC-based RAC equipment. HFCs will be considered for inclusion in the country's quota system. Workshops on the safe handling of alternative technologies that are flammable or toxic refrigerants were organized for 676 technicians between July and December 2019. The Guatemalan Refrigeration Association (ASFRIGUA) supported to NOU in the development of the following studies: Evaluation of training needs for the service sector related to alternative technologies, analysis of availability of alternatives and market trends and formulation of the National Kigali Strategy, including baseline calculation. These studies were completed and assessment reports were delivered in October 2019. President of the Refrigeration Association of Guatemala (ASFRIGUA) participated in regional training "Safe use of hydrocarbon refrigerants for eco-efficient units" at the National Institute of Learning (INA) in San José, Costa Rica, on 3 to 7 June, 2019. | All advances of the SSFA issued to country. Project has a slow progress, since the Congress sessions to allow for the discussion and approval of the ratification instrument were cancelled. ASFRIGUA refrigeration association carried out an energy efficiency comparative analysis for different RAC equipment installed in the country market, which has been presented to RAC end users and technicians in February 2020. Awareness materials related to the HFC phase down were produced in the form of 1000 bulletins and were disseminated to the stakeholders between January and April, 2020. Consultant for the design of the database including controls of imports of HFCs, managing of quotas and preparing of national consumption reports was hired in April 2020, and as of May 2020 is creating, configuring and installing quality assurance environments. Two training workshops were held for RAC technicians at INTECAP facilities, on energy efficiency of the HC-based equipment in March 2020. There are some delays due to COVID-19. |  |  | 2020-06-01 | 36876.85 | 2581.3795
ONG | UNEP | Enabling activities for HFC phase-down |  | LAC | GUY | SEV | 81 | TAS | 01+ | A | I | HFC | 0 |  | 2018-06-01 |  | 2020-01-01 | 2021-01-01 |  |  | 95000 | 0 | 95000 | 0 | 0% | 95000 | 95000 | 28787.8788 | 6650 | 0 | 0 | 6650 | 6650 | The SSFA was signed on 12 December 2018. The first payment has been released to the country 23 April 2019. The Country, hosted a one week Technical Meeting for RAC Technicians, on Alternative Technologies including energy efficient alternatives, focusing on addressing Kigali challenges, during the period December 2-6, 2019. | The SSFA was signed on 12 December 2018. The first payment has been released to the country 23 April 2019. NOU in the process of hiring a Consultant to undertake national consultations on the regulatory and other measures needed for Guyana to fulfill its obligations to the KA. |  |  | 2021-01-01 | 55000 | 3850
ONG | UNEP | Enabling activities for HFC phase-down |  | LAC | HON | SEV | 81 | TAS | 01+ | A | I | HFC | 0 |  | 2018-06-01 | 2019-07-19 | 2020-01-01 | 2021-01-01 |  |  | 150000 | 0 | 150000 | 2155.64 | 1.437% | 147844.36 | 109600 | 44801.3212 | 10500 | 0 | 150.8948 | 10349.1052 | 7672 | The SSFA 2019-18 was signed in August 2019. The first payment has been released to the country in August 2019. Kigali amendment was ratified in January 2019. In accordance with Decree # 006/2012 (General Regulation on the use of Ozone Depleting Substances (ODS)), it is mandatory to obtain an Import/Export license for any type of regulated substance included in the Montreal Protocol. HFCs will be part of the country's quota system when appropriate. A regional consultant was hired by UNEP in November 2019 to support the NOU in the follow-up to the certification scheme in good practice and conduct training workshops for RAC technicians on safe-handling of ODS alternatives. 3 Workshops on safe handling of HC refrigerants were organized in October 2019 for 93 participants conducted by regional consultant and NOU officials. NOU coordinator participated in the regional training "Safe use of hydrocarbon refrigerants for eco-efficient units" at the National Institute of Learning (INA) in San José, Costa Rica, since on 3 to 7 June, 2019. | SSFA 2019-18 expired in January 2020. A new SSFA is under signatures as of May 2020. The total value of the new SSFA is US$75,000.00 payable in two cash advances. First cash advance will be processed once both parties sign the agreement. This SSFA will facilitate obtaining products and expected results as mentioned below: dissemination of results and further introduction of HFCs scenarios, prepare technical reports on the specificities and requirements of each alternative technology application to facilitate consultations by country stakeholders, identify the available alternatives (zero/low GWP, zero ODP and high energy efficiency) and analyze the environmental/socio-economic impacts of each one, among others the project documents approved by the Executive Committee. The licensing system including HFCs is in place. |  |  | 2021-01-01 | 40000 | 2800
ONG | IBRD | Enabling activities for HFC phase-down |  | ASP | IDS | SEV | 81 | TAS | 01+ | A | I | HFC | 0 |  | 2018-06-01 | 2019-09-20 | 2020-01-01 | 2021-01-31 |  |  | 250000 | 0 | 250000 | 17195 | 6.878% | 232805 | 232805 | 232805 | 17500 | 0 | 0 | 17500 | 17500 | National workshop for Indonesia Enabling Activity (EA) was organized on 28 Feb. 19 in Jakarta. Workshop participation included various stakeholders such as government and non-governmental institutions, private sector, academia. Workshop objective was to inform stakeholders of the significance of the HFC phase down under the Kigali Amendment and obtain stakeholder input. TOR for Indonesia National HFC Survey and Regulatory Framework Review finalized and selection of consulting firm completed in 2019. EA 12-month extension granted through Dec. 84/26 at the 84th Meeting. | The consultant mobilized and started work. Inception report submitted Jan 20 and accepted by the WB and NOU. Due to COVID-19 restrictions on travel and stakeholder consultations, a revised workplan was prepared to reflect delays of approx. 3 months. As of this report, final delivery of product in line with extension granted by ExCom at the 84th meeting is expected to be met. Consultant presented results of the analysis of customs data on 28 May 2020. Bottom-up inventory and consultations with users and importers is underway. |  |  | 2021-01-01
ONG | UNEP | Enabling activities for HFC phase-down |  | AFR | IVC | SEV | 81 | TAS | 01+ | A | I | HFC | 0 |  | 2018-06-01 | 2018-11-01 | 2020-01-01 | 2021-01-01 |  |  | 150000 | 0 | 150000 | 18267.45 | 12.18% | 131732.55 | 105300 | 39918.9545 | 10500 | 0 | 1278.7215 | 9221.2785 | 7371 | In March 2019, a consultants for customs codes development were contracted to assist Customs Office in developing national custom codes for different HFCs and include them into the Customs Tariff in order to ensure proper monitoring and recording of imports/exports or re-export of individual HFCs.Translation of the Kigali amendment into national language was done and presented to the parliament .Two senzitiation meetings for the members of the parliament on the Kigali Amendment were organised between march and June 2019. | In January -March 2020 Cote d`Ivoire NOO participated in many exchanges that lead to the recrutment of an International Consultant and a Draft proposal for the extension of the subheadings 2903.39 and 3824.78 of the Tariff and Statis-tical Nomenclature (TSN) of the Common External Tariff (CET) of the Economic Community of West African States (ECOWAS) in order to facilitate the collection and comparison of data concerning the circulation of hydrofluorurocarbons (HFC) will be developed and submitted to WCO. |  |  | 2021-01-01 | 50000 | 3500
ONG | UNDP | Enabling activities for HFC phase-down | Individual | LAC | JAM | SEV | 80 | TAS | 01+ | N | I | No_ODP | 0 | 0 | 2017-11-01 | 2018-04-01 | 2019-06-01 | 2020-06-01 |  |  | 150000 | 0 | 150000 | 115381 | 76.92% | 34619 | 0 | 10385.64 | 10500 | 0 | 8076.684 | 2423.316 | 0 | Ratification: Report for Ratification finalized in 2019. Due to legal restrictions, Jamaica will ratify when licensing & quota system will be in place. HFC licensing & quota system: Due to legal restrictions, Jamaica will ratify when licensing & quota system will be in place. HFC data collection and monitoring: Report finalized in 2019 Demonstrations: Participation on Regional Trainings for HFC phasedown and technical training of technicians on low GWP alternatives performed. | Strenghtening of Tariff codes for HFCs performed. Virtual training and awareness in progress |  |  | 2020-06-01
COM | UNEP | Enabling activities for HFC phase-down |  | ASP | KAM | SEV | 80 | TAS | 01+ | A | I | HFC | 0 |  | 2017-11-01 | 2018-07-01 | 2019-06-01 |  | 2019-06-01 |  | 150000 | 0 | 150000 | 147917.53 | 98.61% | 2082.47 | 2025.35 | 2082.47 | 10500 | 0 | 10354.2271 | 145.7729 | 141.7745 | The Country Assessment Report for HFC phase-down was finalized and widely shared among stakeholders, The Country Assessment Report includes a review of the national institutional arrangement and partnership, existing policy and regulations, technology penetration, the existing infrastructure of RAC and MAC servicing sector, existing awareness and communication, and assessment of the needs for the HFC phase-down. Stakeholders’ understanding of KA ratification implications, and of the work being done by the NOU to prepare the country for HFC phase-down, has been enhanced. Stakeholders actively participated in the consultations, and both the servicing sector and the big end users participated in roundtables on low-GWP alternatives. The existing Sub-decree on ODS Management was reviewed through a widely participated process. The name was amended to be Sub-decree on ODS and Refrigerant Management. In addition to HFC licensing and quota, the Revised Sub-decree also restricts the sale of all types of refrigerant to only registered workshops or certified technicians, requires RAC/MAC servicing workshop to have at least one certified technician for registration/renewal of a business license. Furthermore, the revised sub-decree sets a total ban of HCFC-based equipment imports. The Revised Sub-decree was submitted to the council of Minister for approval. The online licensing system was finalized, tested and launched in June 2019, it is now fully operational, it is the mandatory entry point for licenses application as of January 2020. The NOU, customs Officers, importers, and customs brokers were trained and have been able to use the system The EA project was completed in June 2019. Final payment was released to the country in October 2019. The project final report was submitted in October 2019. Status of KA ratification: Expected ratification in 2020 | Project completed. |  |  |  | 0 | 0
ONG | UNEP | Enabling activities for HFC phase-down |  | AFR | KEN | SEV | 81 | TAS | 01+ | A | I | HFC | 0 |  | 2018-06-01 | 2019-10-01 | 2020-01-01 | 2021-01-01 |  |  | 150000 | 0 | 150000 | 4248.28 | 2.832% | 145751.72 | 135000 | 44167.1879 | 10500 | 0 | 297.3796 | 10202.6204 | 9450 | The SSFA was signed in August 2019 with a total amount of USD 150,000. The first payment was released to the country in October 2019. Cabinet Memorandum on ratification of the Kigali amendment is in place. The NOU sensitized key stakeholders during workshops, meetings and public during world Ozone Day and other public forums on the phase down of HFCs and Kigali Amendment. Prepared and submitted Cabinet Memorandum on ratification of the Kigali Amendment. Organized RAC Technicians training workshops on safe use of hydrocarbons refrigerants. Established an ODS Task force for review of ODS Regulations. Overall assessment of project progress is satisfactory. | The NOU developed National Kigali Strategy paper developed. The NOU is at the initial stage of developing of National Green Cooling Action Plan as urged by the UN Secretary General during 2019 World Ozone Day. Delays in some projects activities are to be expected due to measures taken by the country related to Coronavirus outbreak, which resulted for example in postponing all meetings/ events planned in the first half of the year. |  |  | 2021-01-01 | 80000 | 5600
ONG | UNEP | Enabling activities for HFC phase-down |  | ASP | KIR | SEV | 81 | TAS | 01+ | A | I | HFC | 0 |  | 2018-06-01 | 2019-01-01 | 2020-01-01 | 2021-01-01 |  |  | 50000 | 0 | 50000 | 19445.47 | 38.89% | 30554.53 | 28403 | 9258.9485 | 3500 | 0 | 1361.1829 | 2138.8171 | 1988.21 | SSFA was signed in December 2018. First transfer of funds in January 2019. NOU recruited a local consultant to conduct data collection for Country Assessment Report. Data collection completed. One stakeholder consultation workshops completed in September 2019 in Christmas Island. NOU initiated desk review of the ODS Regulations to include HFC import and export control and will include the flammable and toxic refrigerants as controlled substances under the revised Regulation. NOU worked with other Pacific Island Countries’ NOUs to jointly develop and submit the joint proposal to Oceania Customs Organization (OCO) for the amendment of the HS code under the Pacific Harmonized Commodity Description and Coding System 2017 (PACHS17) to assign specific HS code for HFCs and blends in accordance with WCO recommendation. The proposal for amendment was approved by the Review Committee in September 2019. NOU discussed with customs adoption of revised PACHS17 that assigns specific HS code for HFCs and blends. Status of KA ratification, ratified on 26 October 2018. | Country Assessment Report drafting ongoing. NOU postponed RAC technicians training for Q3/4 as possible. NOU adapting UNEP materials for awareness rising. |  |  | 2021-01-01 | 8403 | 588.21
FIN | UNEP | Enabling activities for HFC phase-down |  | EUR | KYR | SEV | 80 | TAS | 01+ | A | I | HFC | 0 |  | 2017-11-01 | 2018-03-01 | 2019-06-01 |  | 2019-12-01 | 2019-12-01 | 95000 | 0 | 95000 | 95000 | 100% | 0 | 0 | 0 | 6650 | 0 | 6650 | 0 | 0 | Progress January – December 2019: The agreement was signed in February 2018. The second cash advance payment was released in March 2019. Kyrgyzstan aims to ratify the Kigali Amendment by June 2020. In 2019, the Parliament considered three major laws related to the Paris Agreement on climate change, to customs codes for HFCs / natural refrigerants as part of the legislation on ODS import / export, and to the Kigali Amendment ratification. Government resolution № 660 on the Kigali Amendment ratification was approved and submitted to the Parliament for adoption in December 2019. Several amendments to normative legal acts were completed including the law on ozone layer, the law on environment protection, the law on air protection, the legislation on ODS imports / exports and the criminal code, the code on administrative responsibilities and the state programme ODS phase-out 2016-2020. In 2019, seven training seminars were held on good servicing practices of RAC equipment, five seminars to introduce alternative / natural technologies in commercial refrigeration, and two workshops on energy-efficient buildings. Kigali Amendment ratification was the main topic of WOD celebrations in September 2019 and the Youth climate forum in November 2019. The Kigali amendment was explained at 17 awareness workshops focusing on cooling and climate change issues in different cities. A series of publications was produced, partly translated and disseminated including training materials, posters, factsheets, cold chain briefs, videos, applications, quick guides, e-learning tools. They covered topics related to the Kigali Amendment, ratification of the amendment, alternative technologies and energy-efficiency. Kyrgyzstan completed the enabling activities project in December 2019. For information, the final report on Kyrgyzstan’s enabling activities was submitted in March 2020. Government Resolution № 230 on new customs codes for HFCs and natural refrigerants as part of the legislation on ODS import / export was adopted in April 2020. The second reading in Parliament of the law on Kigali Amendment ratification took place in May 2020. The final reading and ratification by Parliament are expected in June 2020. The next steering committee meeting will take place shortly after ratification of the Kigali Amendment. | Project financially completed. |  |  | 2020-06-01 | 0 | 0
ONG | UNEP | Enabling activities for HFC phase-down |  | ASP | LAO | SEV | 81 | TAS | 01+ | A | I | HFC | 0 |  | 2018-06-01 | 2018-11-01 | 2020-01-01 | 2021-01-01 |  |  | 95000 | 0 | 95000 | 15504.83 | 16.32% | 79495.17 | 72025 | 24089.4455 | 6650 | 0 | 1085.3381 | 5564.6619 | 5041.75 | SSFA was signed in November 2018. The first payment was released to the country in November 2018. Recruitment of consultant to support EA implementation completed. Data collection for preparation of Country Assessment Report completed. NOU with support of the Justice Department collaborate with stakeholders to review and amend the existing regulation to control HFC import and exportt. Meetings organized in 2019 to review and draft the amendment. Restructuring of Steering Committee to include stakeholder under KA completed. NOU organized the National Steering Committee meeeting to sensitize major stakeholders about the KA and EA project. Meeting with stakeholder on establishment and implementation of certification for RAC technicians done in July 2019. Two master trainers sent to Guangzhou for training on R290 in December 2019. Status of KA ratification: Ratified on 17 November 2017. | NOU postponed workshop for Q3/4 as possible. Country Assessment Report drafting ongoing. NOU finalzied the draft amendment to the existing Ministerial Decision on ODS Management, which includes provisions to include HFCs import/export control and certification of RAC technicians in the proposed amendment. The consultation meeting was organized in January 2020 to present the final draft, which has been agreed in principle. The draft Amendment currently at Ministry for final review and endorsement. NOU postponed training for Q3/4 as possible. Additional meeting with RAC trainers, RAC Association, Ministry of Labour and Social Welfare was organized in January 2020 to follow-up disucssion on the existing certification system in Lao PDR. |  |  | 2021-01-01 | 27516.34 | 1926.1438
COM | UNIDO | Project preparation for HFC-related projects in the manufacturing sector at Lematic Industries to gain experience in ICCs and IOCs associated with the phase-down of HFCs in domestic refrigeration |  | ASP | LEB | REF | 80 | PRP | 01+ | A | I |  | 0 | 0 | 2017-11-01 | 2018-01-01 | 2018-12-01 |  | 2018-12-18 |  | 30000 | 0 | 30000 | 22425.81 | 74.75% | 7574.19 | 6681.19 | 5611 | 2100 | 0 | 1569.8067 | 530.1933 | 467.6833
ONG | UNDP | Enabling activities for HFC phase-down | Individual | ASP | LEB | SEV | 80 | TAS | 02+ | N | I | No_ODP | 0 | 0 | 2017-11-01 | 2019-10-01 | 2019-06-01 | 2020-06-01 |  |  | 150000 | 0 | 150000 | 28627 | 19.08% | 121373 | 0 | 36411.888 | 10500 | 0 | 2003.8928 | 8496.1072 | 0 | Country initiated activitias in 2019, supporting in particular the effort towards the ratification of the Amendment (accomplished at the Parliament in 2019, then transmitted to NY for deposit by 2020). A road map is set up for conclusion of all remaining activities by mid-June 2020, and will be assessed considering the current difficult national situation. | A final activity consisting in a specific, targeted procurement of equipment has been launched, and is expected to be completed in coming months. The date of June 2020 completion could not be met, due to the Covid-19 crisis. |  |  | 2020-06-01
ONG | UNIDO | Conversion from HFC-134a and HFC-404A to R-600a and R-290 in domestic refrigeration at Lematic Industries |  | ASP | LEB | REF | 81 | INV | 03+ | A | I | HFC | 112.5 | 0 | 2018-06-01 | 2019-01-01 | 2020-07-01 | 2020-12-31 |  |  | 1053858 | 0 | 1053858 | 841248.81 | 79.83% | 212609.19 | 204771.59 | 5179 | 73770 | 0 | 58887.4167 | 14882.5833 | 14334.0113
COM | Italy | Enabling activities for HFC phase-down | Individual | AFR | LES | SEV | 80 | TAS | 03+ | A | I | HFC | 0 | 0 | 2017-11-01 | 2019-09-01 | 2019-06-01 |  | 2019-12-01 |  | 40000 | 0 | 40000 | 35000 | 87.5% | 5000 | 5000 | 5000 | 2800 | 0 | 2450 | 350 | 350 | SSFA is being drafted and send to the country for review. Lesotho has started implementation of EA project with UNEP’s component (SSFA signed and the first payment is done). The project activities for the Government of Italy’s components are being planned for the second half of 2018.Legal expert was engaged to review the legal and policy framework on ozone including the revision of the national ODS legislation. The revised regulations allow for HFC phase down under the Kigali Amendment. The NOU conducted a stakeholder workshop to review the ODS Regulation to include HFCs consumption control from 17 to 20 December 2018. Final editing of the ODS regulations has been completed. The SSFA was signed and the first payment was released to the country at the amount of 25,000 USD. The Kigali Amendment text is currently undergoing translation into the local language from 20th June to 24th August 2019. The NOU organized 3 consultative meetings as follows: 15th May 2019 at Rio Guest House, 28th May, 2019 at Khali hotel on, and 13th June 2019 at Refiloe guest house The NOU organized Ozone Day preparation at the studio on the 27th July 2019 with aim to intigrate HFC issues. The reviewed and revised Ozone Depleting Substances Regulation 2012 was submitted to the cabinet on 22nd May 2019. Awareness material for HFC phase down have been produced and would be disseminated to stakeholders and the public on 14th September 2019, in preparation for Ozone Day celebration. Package for ratification of the Kigali amendment has been developed and is in legislative procedure with parliamentarians. Lesotho is planning to ratify Kigali Amendment on July/August 2019, and ratification instrument to be sent to UN house by August/September 2019. Analysis of availability of alternatives and market trends completed on 22nd May 2019. Analysis of economic implications of different HFC alternatives and technologies to local consuming sector was completed by May 2019. Existing barriers (technical, economic and political) for the adoption of alternative to the HFC in the refrigeration and air conditioning sector were identified after analysis on 24 May 2019. Consultants have started with the preparation of training needs assessment for the servicing sector related to alternative technologies from 1 June to 30th September 2019. The first disbursement of US$25,000 was made in April 2019. The country has submitted all required reports and requested for the final payment of US$15,000 (as the cash advance). The cash advance is being processed by UN Environment. The project is on track. | Lesotho ratified the Kigali Amendment and conducted Training Needs Assessment for RAC technicians, customs officers and NOU. ODS Regulation were reviewed to include HFC and is awaiting for approval process. Awareness raising activities for different stakeholders were conducted. Analysis of availability of alternatives and market trends completed on 22nd May 2019. Analysis of economic implications of different HFC alternatives and technologies to local consuming sector was completed by May 2019. Existing barriers (technical, economic and political) for the adoption of alternative to the HFC in the refrigeration and air conditioning sector were identified after analysis on 24 May 2019. Preparation of training needs assessment for the servicing sector related to alternative technologies was also conducted and finalised. All funds have been disbursed.The project implementation was completed in December 2019. The country is drafting the final report and the Assessment report. Both reports have delayed due to restrictions imposed by COVID-19 |  |  | 2019-12-01
COM | UNEP | Enabling activities for HFC phase-down |  | AFR | LES | SEV | 80 | TAS | 04+ | A | I | HFC | 0 |  | 2017-11-01 | 2018-07-01 | 2019-06-01 |  | 2019-12-01 |  | 55000 | 0 | 55000 | 50492.12 | 91.8% | 4507.88 | 0 | 4507.88 | 3850 | 0 | 3534.4484 | 315.5516 | 0 | The final payment for SSFA of the amount of USD 45,000 was released to the country in Dec 2019. Lesotho ratified the Kigali on 7 October 2019 and conducted Training Needs Assessment for RAC technicians, customs officers and NOU. Assessment report is finalized on 20 December 2019. ODS Regulation reviewed to include HFC and is awaiting for approval. Awareness raising activities for different stakeholders were conducted. Overall assessment of project progress is satisfactory. | The NOU worked closely with the Ministry of Trade (Standards) and Department of Energy and Climate Change Focal Points and they attended a number of trainings and awareness raising meetings to ensure that energy efficiency is considered in all the activities. Project is completed. |  |  | 2019-12-01 | 0 | 0
ONG | UNIDO | Enabling activities for HFC phase-down |  | AFR | LIB | SEV | 81 | TAS | 01+ | N | I |  | 0 | 0 | 2018-06-01 | 2019-06-01 | 2020-01-01 | 2021-12-01 |  |  | 150000 | 0 | 150000 | 5481.62 | 3.654% | 144518.38 | 0 | 20000 | 10500 | 0 | 383.7134 | 10116.2866 | 0 | Selection of an International consultant has been in progress to work with NOU and UNIDO on the basis of a remote correspondence to build on the documented ODS Alternatives Survey. | Unstable situation in the country did not allow any activity within the country. |  |  | 2021-01-01
ONG | Germany | Enabling activities for HFC phase-down |  | AFR | LIR | SEV | 80 | TAS | 01+ | A | I | HFC | 0 |  | 2017-11-01 | 2018-03-01 | 2019-06-01 | 2020-12-01 |  |  | 95000 | 0 | 95000 | 47290 | 49.78% | 47710 | 9324 | 47710 | 6650 | 0 | 3310.3 | 3339.7 | 652.68 | The Standards ISO 5149 have been adopted by Liberia allowing for safe handling of refrigerants. Regulation amendment is ready but approval has been delayed due to varied internal reasons. | Ratification has been completed. |  |  | 2020-06-01
ONG | UNEP | Enabling activities for HFC phase-down |  | AFR | MAG | SEV | 81 | TAS | 01+ | A | I | HFC | 0 |  | 2018-06-01 | 2018-10-01 | 2020-01-01 | 2021-01-01 |  |  | 150000 | 0 | 150000 | 55453.94 | 36.97% | 94546.06 | 61354 | 28650.3212 | 10500 | 0 | 3881.7758 | 6618.2242 | 4294.78 | National consultants are contracted to assist Customs Office in developing national custom codes for different HFCs and include them into the Customs Tariff in order to ensure proper monitoring and recording of imports/exports or re-export of individual HFCs. Comprehensive review of National licensing system for ODS, ODS alternatives and based-products was done in 2019. Analysis of existing policy and regulatory framework for HFCs was done in 2019. Stakeholders consultation meetings and awareness programmes to facilitate the ratification process at the national level were organised. Awareness material for HFC phase down was produced and disseminated to the stakeholders and the public. The development of Customs Harmonized Code was to be finalized by an international consultant by December 2019. It is delayed and will be finalized by July 2020. Two sensitization meetings for the servicing sector on safe handling of HFCs and alternatives will be organized in 2020. | Stakeholders consultation meetings and awareness programmes to facilitate the ratification process at the national level were organised. Awareness material for HFC phase down was produced and disseminated to the stakeholders and the public. The development of Customs Harmonized Code was to be finalized by an international consultant by December 2019. It is delayed and will be finalized by July 2020. |  |  | 2021-01-01 | 50000 | 3500
ONG | IBRD | Enabling activities for HFC phase-down |  | ASP | MAL | SEV | 80 | TAS | 01+ | A | I | HFC | 0 | 0 | 2017-11-01 | 2017-12-01 | 2019-06-01 | 2020-12-01 |  |  | 250000 | 0 | 250000 | 193318 | 77.33% | 56682 | 56682 | 56682 | 17500 | 0 | 13532 | 3968 | 3968 | Survey launch workshop held Jan. 19 in KL and survey conducted between Feb-Apr. 19. Interim report on survey findings and assessment of Customs data, comparative assessment of data received and projection of baseline completed by Jun 19. Draft final survey report was submitted 20 Jul 19. WB technical mission conducted 23-25 Jul. 19 during the 2nd stakeholder workshop on survey findings. Final revised consultant survey report submitted to GoM and the WB in Oct. 19. Data analysis and assessment of phase-down cost impacts, policy options and technology pathways/scenarios started. Strategy document for GoM's ratification of the Kigali Amendment to be delivered by Q2 20. Dec. 83/40 extended the activity until Jun 2020. | Models and tools developed in early 2020 to determine growth scenarios against BAU and technology pathways for each scenario. Analayses conducted and draft strategic document, including possible policy options for initial Kigali Amendment implementation (and for licensing and quota systems), prepared by Mar 20. Cost-benefit analysis completed end Apr 20. Final draft document discussed with GoM, revised and presented in the Bank and to the GoM by end May 20. Next step will be vetting the document among industry and government stakeholders in Malaysia. Means to do so within the EA implementation period is under consideration given the pandemic. |  |  | 2020-06-01
ONG | UNEP | Enabling activities for HFC phase-down |  | ASP | MAS | SEV | 81 | TAS | 01+ | A | I | HFC | 0 |  | 2018-06-01 | 2019-01-01 | 2020-01-01 | 2021-01-01 |  |  | 50000 | 0 | 50000 | 13828.94 | 27.66% | 36171.06 | 35831 | 10960.9273 | 3500 | 0 | 968.0258 | 2531.9742 | 2508.17 | SSFA was signed in December 2018. First transfer of funds in January 2019. Recruitment of consultant to support EA implementation completed. Data collection for preparation of Country Assessment Report completed. One meeting with national stakeholders was conducted to sensitize them on HFC phase-down and discuss implementation of EA. NOU initiated reviewing of the regulation will amend the regulation to include HFCs. NOU worked with other Pacific Island Countries’ NOUs to jointly develop and submit the joint proposal to Oceania Customs Organization (OCO) for the amendment of the HS code under the Pacific Harmonized Commodity Description and Coding System 2017 (PACHS17) to assign specific HS code for HFCs and blends in accordance with WCO recommendation. The proposal for amendment was approved by the Review Committee in September 2019. Status of KA ratification, ratified on 15 May 2017. | Country Assessment Report drafting ongoing. NOU postponed RAC technicians training for Q3/4 as possible. NOU adapting UNEP materials for awareness rising. |  |  | 2021-01-01 | 15000 | 1050
ONG | UNEP | Enabling activities for HFC phase-down |  | AFR | MAU | SEV | 81 | TAS | 01+ | A | I | HFC | 0 |  | 2018-06-01 | 2018-11-01 | 2020-01-01 | 2021-01-01 |  |  | 150000 | 0 | 150000 | 2468.06 | 1.645% | 147531.94 | 99800 | 44706.6485 | 10500 | 0 | 172.7642 | 10327.2358 | 6986 | Translation of the Kigali amendment into national language was done and presented. The consultants for customs codes development were contracted. The consultants will assist Customs Office in developing national custom codes for different HFCs and include them into the Customs Tariff in order to ensure proper monitoring and recording of imports/exports or re-export of individual HFCs. In May 2019, Selection of a National Consultant to develop a Customs Harmonized Code .NOU attended the ECOWAS meeting for regional harmonization of Customs Harmonized Code regarding regulation of HFC imports/exports, in Bissau, December 2019. | In January -March 2020 Mauritania contributed in the development of the TOR for the recrutment of an Internatuional Consultant to develop Customs Harmonized Code for ECOWAS countries. A proposal for the extension of the subheadings 2903.39 and 3824.78 of the Tariff and Statis-tical Nomenclature (TSN) of the Common External Tariff (CET) of the Economic Community of West African States (ECOWAS) in order to facilitate the collection and comparison of data concerning the circulation of hydrofluorurocarbons (HFC) will be developed and submitted to WCO. |  |  | 2021-01-01 | 50000 | 3500
ONG | UNIDO | Enabling activities for HFC phase-down |  | EUR | MDN | SEV | 80 | TAS | 01+ | A | I |  | 0 | 0 | 2017-11-01 | 2018-03-01 | 2019-06-30 | 2021-06-30 |  |  | 95000 | 0 | 95000 | 32084.19 | 33.77% | 62915.81 | 0 | 15000 | 6650 | 0 | 2245.8933 | 4404.1067 | 0 | Ratification process progress to reach final stage Inter-sector communication completed. Government received ratification documents in September. Consultation meeting on legislation for F Gases was organized in Skopje. NOU attended the workshop on Kigali organized by UNIDO in Vienna. Actions towards next goals: Organize workshop and finalize the ratification process. Was there any delay during the reporting year? - NO Any recurring problem? - NO Any impact on project completion date? - Yes, extension requested at the 83rd meeting Any action required by Executive Committee? - Extension requested and granted. | North Macedonia ratified the Kigali Amendment on 12 March 2020 Planned workshops postponed due to Covid-19. Was there any delay during the reporting year? - Yes, some activities had to be postponed due to the Covid-19 pandemic. Any recurring problem? - No Any impact on project completion date? - Yes, extension needed to complete remaining activities once the measures are eased. Any action required by Executive Committee? - Yes, allow project extension beyond the 30 months. |  |  | 2020-06-01
ONG | UNEP | Enabling activities for HFC phase-down |  | ASP | MDV | SEV | 80 | TAS | 01+ | A | I | HFC | 0 |  | 2017-11-01 | 2018-11-01 | 2019-06-01 | 2020-12-01 |  |  | 55000 | 0 | 55000 | 4801.4 | 8.73% | 50198.6 | 49950 | 15211.697 | 3850 | 0 | 336.098 | 3513.902 | 3496.5 | The SSFA signed in Jul 2018 and the first payment made in Nov 2018. Data collection for preparation of Country Assessment Report completed. One workshop in November 2019 (2 of 3). Targeted meetings for RAC servicing and fisheries sector organized. One meeting with customs done, HFCs included in revised HS code. Completed 1 training with RAC and fisheries so far. One master trainer sent to Guangzhou for training on R290 in December 2019. Status of KA ratification: Ratified Nov 2017. | The second payment has been released to the country 03 March 2020. Country Assessment Report final draft currently under revision. A workshop conducted in February to brief resorts on the implications of the Kigali Amendment on the tourism sector. UNEP quick guide on good servicing practices for flammable substances translated in local language. Draft Ozone Layer Protection act amenmend currently under review. Online import permit system completed and to be operationalised soon. Financial consultant recruited to conduct study and revision of bank loan scheme to encourage private companies to switch to low GWP alternatives |  |  | 2020-06-01 | 42500 | 2975
ONG | Italy | Enabling activities for HFC phase-down | Individual | ASP | MDV | SEV | 80 | TAS | 02+ | A | I | HFC | 0 | 0 | 2017-11-01 |  | 2019-06-01 | 2020-12-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 40000 | 20000 | 2800 | 0 | 0 | 2800 | 2800 | Detailed action plan and budget for the component funded by the Government of Italy as part of the Enabling Activities Project for HFC Phase-down was developed, discussed and agreed with the National Ozone Unit (NOU). On that basis it was included into the SSFA, the overall partnership agreement between UNEP and Government of Maldives signed for the implementation of activities and transfer of funds to the implementing partner. The SSFA signed in July 2018. The 1st payment is being disbursed. The component funded by Italy focuses on the fisheries sector, which is key in the national economy, with the objective of sensitizing the sector for the HFC phase-down and implementation of the Kigali Amendment. The activities of the component include: (1) detail survey of all the marine and land vessels in the fisheries sector for the use of HFC and alternatives and identifying the barriers; (2) Sector specific training for the fisheries sector technicians and RAC servicing technicians on theory and practical aspects; (3) Develop technical guidelines on the safety and handling of HFC alternatives in the sector; (4) Revise the proposed bank loans scheme to include options for promoting HFC alternatives, conduct additional consultation and raise awareness on bank loans (an output being developed through GEF funded low-carbon development project, focusing also on RAC sector) to encourage private companies to switch over to low GWP alternatives and (5) Assist selected fisheries companies to come up with an internal plan for switching to low GWP alternatives and to prevent introduction of HFCs in the sector. The Terms of Reference for a regional consultant to support the implementation of the Enabling Activities projects in Maldives and other countries of the Network were finalized and the vacancy was advertised. The recruitment is underway. The consultant will be assisting the NOU with technical aspects of the activities through providing guidance and review of outputs. The preparations are being made to conduct a detailed survey of marine and land vessels for their use of RAC technologies and potential for HFC alternatives building on the ODS Alternatives survey and HFC Inventory conducted in 2017. The technical guidelines are under preparation through taking stock of existing material and selecting the relevant ones for the adaptation. ToR for policy review and needs assessment and KA implications being drafted. The organization of the inception workshop for national stakeholders is underway. The SSFA signed and the first payment was made by UNEP to the country. KA translation completed and distributed. KA has been ratified by the country. Regional consultant to support the implementation of the project and provide technical support in place. Local consultant for data collection for the market assessment, including fisheries sector, and RSS needs assessment recruited. The first payment was transferred to the country in 2018 (this is the cash advance) and NOU is now preparing the second payment request, having spent the 80% of the first payment (as of August 2019). This requires the provision of the expenditure statement from the country, which will be then recorded by UNEP in the UMOJA system. The disbursement rate will be then 40% and the second cash advance will be transferred. With regard to the fisheries sector, which was identified for a dedicated project component under the EA project, it is one of the key end user sectors in the country for which NOU is collecting additional data in terms of their current profile, readiness and use of HFCs under the data collection and assessment activities of the NOU. Additional sector specific awareness activities are also conducted. The lessons learned from the HPMP demonstration project will be considered for future strategies for HFC phase down. There are two components at least that consider the revision and updating the current regulation to domesticate the Kigali Amendment and integrate HFC management into existing licensing and data management systems in Maldives (components on facilitation of early ratification of the Kigali Amendment and Online Data System) | The second payment has been released to the country 03 March 2020. The component funded by Italy focuses on the fisheries sector, with the objective of sensitizing the sector for the HFC phase-down and implementation of the KA. The activities of the component include: (1) detail survey of all the marine and land vessels in the fisheries sector for the use of HFC and alternatives and identifying the barriers - Completed, the data from the fisheries sector is being integrated in the Maldives Country Assessment Report for the implementation of the KA. The Country Assessment Report is at advanced draft stage and currently under revision. (2) Sector specific training for the fisheries sector technicians and RAC servicing technicians on theory and practical aspects - 2 out of 3 trainings completed, the remaining training is delayed due to response measures in place for COVID 19. (3) Develop technical guidelines on the safety and handling of HFC alternatives in the sector - UNEP quick guide on GSP for flammable substances identified as relevant guidance document, the translation is ongoing, almost completed. (4) Revise the proposed bank loans scheme to include options for promoting HFC alternatives, conduct additional consultation and raise awareness on bank loans (an output being developed through GEF funded low-carbon development project, focusing also on RAC sector) to encourage private companies to switch over to low GWP alternatives - Activity dependent on finalization of the GEF project output and the possibility to conduct meetings, delayed. The NOU is working to organize a virtual stakeholder meeting in Q3. (5) Assist selected fisheries companies to come up with an internal plan for switching to low GWP alternatives and to prevent introduction of HFCs in the sector - Activity dependent on the finalization of the country assessment report and the resume of stakeholders workshops, activities that are due for completion, therefore this activity is delayed. The project has two contributions: (1) UNEP contribution USD 45,000; and (2) Italy Contribution USD 40,000. The NOU received two payments until now. Due to administrative arrangements UNEP transferred each payment from a single budget line, as follows: The first payment was transferred from UNEP contribution. Upon reach of 80% of expenditure rate on that payment the NOU requested for the second payment. The second payment was transferred (03 March 2020) from Government of Italy contribution. Due to the lockdown in place from March only few activities were able to make progress since then. Out of 4 project components, component 2 is related to the fisheries sector and the Italian contribution. Due to the mentioned administrative procedure the funding for the UNEP component in the first period of project implementation contributed to the whole 4 components, including component 2, until the NOU received the 2nd payment. The low expenditure rate of Italy contribution is not due to the activities not being implemented; it is a reflection of the administrative arrangements. The budget contributions will be displaying a more accurate picture once we receive the expenditure reports relative to the second payment. COVID19 response situation update: the country has been in lockdown with restrictions of movement and prohibitions of social gatherings, including working from home arrangements for governments offices since March. All meetings and events planned in the first half of the year had to be postponed. NOU staff has been working from home during this period, with only essential employees allowed to work onsite at government premises, and most private offices closed. The NOU resumed working from office only on 6th July 2020. Restrictions to public gatherings and meetings are still effective. All sectorial meetings (including fisheries), general stakeholder meetings, and servicing trainings, are still not possible as of now. Restrictions response form NOU: Work on activities that are possible to conduct remotely continued during the lockdown period, the NOU is now working to organize virtual meeting with stakeholders and exploring the possibility to conduct also the remaining servicing training by virtual means. |  |  | 2020-06-01
ONG | UNEP | Enabling activities for HFC phase-down |  | LAC | MEX | SEV | 80 | TAS | 01+ | A | I | HFC | 0 |  | 2017-11-01 | 2018-12-01 | 2019-06-01 | 2020-12-01 |  |  | 30000 | 0 | 30000 | 10156.95 | 33.86% | 19843.05 | 180.63 | 6013.0455 | 2100 | 0 | 710.9865 | 1389.0135 | 12.6441 | No progress. Changes in the National Ozone Unit did not allow to implement planned customs training activities. | Some progress. During February and March 2020 a wide-national customs training workshop, for some 50 customs and enforcement officers from around the country was scheduled to be held in Manzanillo (main port of Mexico) in May 2020. Demonstration training sessions for customs and enforcement officers were planned to address the obligations under the Kigali Amendment, including the revised import/export licensing systems.The activity was postponed due to COVID-19 outbreak. |  |  | 2020-06-01 | 0 | 0
COM | UNIDO | Enabling activities for HFC phase-down |  | LAC | MEX | SEV | 80 | TAS | 02+ | A | I |  | 0 | 0 | 2017-11-01 | 2018-03-01 | 2019-06-01 |  | 2019-12-01 |  | 220000 | 0 | 220000 | 219624.48 | 99.83% | 375.52 | -0.02 | 1 | 15400 | 0 | 15373.7136 | 26.2864 | -0.0014 | • Ratification of Kigali amendment: Yes (25th September 2018) • Status of implementation: project completed • Activities implemented: Review of licensing and data collection system for HFCs and reporting, institutional strengthening; national policies and Regulations/standards analysis. Preparation of the Kigali Amendment Roadmap for Mexico; Preliminary capacity building requirements for the implementation of the Kigali Amendment and its related matters; Public awareness; elaboration of information material for the different national actors with regard to the Kigali Amendment • Milestones achieved: .-Work Plan Agreed with NOU: Yes; .- UNIDO awareness raising workshop organized: Yes organized in June 2019, named "Kigali in Action" and the NOU participated. .- Deliverables and results reported: a) Enforced licensing and quota system: Yes (no quota system enforced) b) HFC data collection and monitoring system (decision 79/46): HFC consumption survey was updated and upgraded; Licensing system to control HFCs was updated. c) Policies and Regulations: Feasibility study was prepared to identify control options of the imports of HFC based equipment and avoid its installation in México d) Customs and enforcement officers were trained on obligations under the Kigali Amendment, including the revised import/export licensing systems. e) Trainings: Train the trainer's course for the identification of all types of alternatives to the HFC (including other HFC and its blends); Training for National Ozone officers and other related stakeholders on energy efficiency developments in the RAC systems was conducted. f) Assessment report on the impact of the Phase-out of HCFC in the potential consumption of HFC was prepared. g) Assessment of the Energy efficiency policies and standards for RAC equipment, availability of new technologies, the potential energy savings per sector and feasible applications in the Mexican market. h) HFC phase-down Road map in Mexico developed and adopted by authorities i) Public awareness: national events were developed; last Workshop was held in November 2019 to present the HFC phase-down Roadmap to authorities and stakeholders in Mexico. j) Design and printing of notebooks, posters, handbook and other promotional materials regarding Kigali Amendment. k) Fact Sheets on Transitioning to Low-GWP alternatives in various Applications prepare and published. • Overall assessment of project progress: satisfactory- The majority of the planned activities were implemented with no delay. Actions developed during the reporting period as planned and accordingly to the approved UNIDO’s activities in the project. • Impact of these activities: Significant awareness activities and discussions were conducted with the main sectors involved in the future implementation of the KA in Mexico. The country's HFC data reporting was facilitated through the upgraded licensing system. The roadmap prepared under EA project represents a powerful tool to guide the country with sectorial approach and establishing general actions to phase down HFCs, based on: the national diagnosis on use, consumption and sectoral distribution of HFCs; ten (10) studies prepared by SEMARNAT/local team with UNIDO; the public policy instruments evaluated in the country. • Potential challenges in completing the projects and activities: N/A. • Key findings and lessons learned: studies and assessments developed in the project allowed to the NOU to identify policies and regulations, including safety codes and standards on energy efficiency and low GWP alternatives; enhancing the data collection system for the new reporting requirements under KA; aligning national programmes and HPMP to facilitate the phase-down of HFCs and the introduction of low-GWP alternative technologies. The National Roadmap has made an initial and general identification of the short, medium and long-term actions of four pillars of public policy on which the HFC phase-down will be supported: 1) regulation, 2) strategic planning, 3) implementation, 4) reporting and verification. | •Status of implementation: project completed •Activities implemented/ Overall assessment of project progress: All actions planned were developed until December 2019 and accordingly to the approved UNIDO’s activities in the project. |  |  | 2020-06-01
FIN | UNIDO | Project preparation for HFC-related projects in the manufacturing sector at Imbera enterprise to gain experience in ICCs and IOCs associated with the phase-down of HFCs |  | LAC | MEX | REF | 80 | PRP | 03+ | A | I |  | 0 | 0 | 2017-11-01 | 2018-04-01 | 2018-12-01 |  | 2018-12-01 | 2019-09-26 | 30000 | -182 | 29818 | 29817.58 | 100% | 0.42 | 0 | 0 | 2100 | -13 | 2087.2306 | -0.2306 | 0 | Project was financially closed in September 2019. Remaining fund balances were returned at the 84th ExCom meeting in December 2019. | n.a.
ONG | UNIDO | Conversion of commercial refrigeration manufacturing in two facilities from the use of HFC-134a and R-404A as the refrigerants to propane (R-290) and isobutane (R-600a) at Imbera |  | LAC | MEX | REF | 81 | INV | 04+ | A | I | HFC | 56 | 0 | 2018-06-01 |  | 2020-07-01 | 2021-06-30 |  |  | 1018123 | 0 | 1018123 | 0 | 0% | 1018123 | 750000 | 269767.33 | 71268 | 0 | 0 | 71268 | 52500 | Bidding deadline was extended until February, since suppliers requested for detailed layouts, which took some time until those could be provided to the interested suppliers. Bidding was closed end February. Technical evaluation was undertaken in cooperation with the beneficiaries and it was finalized in April. Due to the high costs, there have been extensive negotiations with the suppliers and the final offer based on reduced scope was received end June. Milestones achieved: PAD issued: Yes, July 2018 ToR for equipment purchase agreed upon: Yes, December 2018 Bids prepared & requested: Yes Contract awarded: Yes Contract countersigned: Yes Equipment delivered & installed: Not delivered Commissioning & trial runs: No TUV certification: No Activities planned but not implemented, reasons and strategy: equipment procured and installed Actions towards next goals: equipment importation and installation Was there any delay during the reporting year? No Any recurring problem? No. Any action required by Executive Committee? No | The equipment was delivered during the quarantine, arriving in the facilities on 6 and 7 of April 2020. All other activities had to be recently suspended due to the COVID-19 pandemic (contractor cannot travel to the project site for installation in the next few months). Additionally, the company is not ready to initiate the installation of the equipment due to: i) the current conditions of the facilities - some investment were required at the facilities, and ii) given the company´s financing constraints. Conversation continues with the company to determine possible investment scenarios. The commercial production of products using alternative technology has not started yet due to the suspension of the project. An extension until June 2021 is required and subject to progress in the investment decisions at the company. Detailed updates will be communicated to the Secretariat for the 86th ExCom. Milestones achieved: PAD issued: Yes, July 2018 ToR for equipment purchase agreed upon: Yes, December 2018 Bids prepared & requested: Yes Contract awarded: Yes Contract countersigned: Yes Equipment delivered & installed: Delivered in April 2020, could not be installed due to quarantine Commissioning & trial runs: No TUV certification: No Actions towards next goals: Continue discussion with the company to determine possible investment scenarios. Was there any delay during the reporting year? Yes, due to the Covid-19 pandemic, all investment activities are on hold Any recurring problem? No. Any action required by Executive Committee? Yes, project needs to be extended and implementation to be allowed beyond the 24 months.
ONG | UNEP | Enabling activities for HFC phase-down |  | AFR | MLI | SEV | 81 | TAS | 01+ | A | I | HFC | 0 |  | 2018-06-01 | 2018-11-01 | 2020-01-01 | 2021-01-01 |  |  | 150000 | 0 | 150000 | 30674.36 | 20.45% | 119325.64 | 117300 | 36159.2848 | 10500 | 0 | 2147.2052 | 8352.7948 | 8211 | Translation of the Kigali amendment into national language was done and presented to the Parliament and stakeholders . The consultants for customs codes development were contracted to assist Customs Office in developing national custom codes for different HFCs and include them into the Customs Tariff in order to ensure proper monitoring and recording of imports/exports or re-export of individual HFCs. Development of an HFC outlook in Januaray 2019. | In January -March 2020 Mali NOO participated in many exchanges that lead to the recrutment of an International Consultant and a Draft proposal for the extension of the subheadings 2903.39 and 3824.78 of the Tariff and Statis-tical Nomenclature (TSN) of the Common External Tariff (CET) of the Economic Community of West African States (ECOWAS) in order to facilitate the collection and comparison of data concerning the circulation of hydrofluorurocarbons (HFC) will be developed and submitted to WCO. |  |  | 2021-01-01 | 50000 | 3500
ONG | UNEP | Enabling activities for HFC phase-down |  | AFR | MLW | SEV | 81 | TAS | 01+ | A | I | HFC | 0 |  | 2018-06-01 | 2018-12-01 | 2020-01-01 | 2021-01-01 |  |  | 150000 | 0 | 150000 | 144904.23 | 96.6% | 5095.77 | 0 | 1544.1727 | 10500 | 0 | 10143.2961 | 356.7039 | 0 | The first payment for SSFA of the amount of USD 85,000 was released to the country in February 2019The Kigali Amendment was ratified in November 2017. National Kigali Strategy to guide the country on quick adoption of HFC-alternatives developed in June 2019. Enabling activities for the adoption of the Kigali Amendment implemented. These included; development of strategies for quick adoption of HFC alternatives, capacity building and awareness on HFCs and their alternatives, undertaking training needs assessments for enforcement officers and RAC technicians for smooth implementation of provisions under the Kigali Amendment on phase-down of HFCs, and review of legal frameworks to accommodate Kigali Amendment in national frameworks. Overall assessment of project progress is satisfactory. | The final payment for SSFA of the amount of USD 85,000 was released to the country in February 2020. Capacity of RAC technicians strengthened on handling energy efficiency RAC technologies. Importers, suppliers and end-users of RAC technologies sensitized on benefits of using energy efficiency RAC equipment. Regulations on controlled substances under the Montreal Protocol is being revised to promote uptake of RAC energy efficiency technologies. Delays in some projects activities are to be expected due to measures taken by the country related to Coronavirus outbreak, which resulted for example in postponing all meetings/ events planned in the first half of the year. |  |  | 2021-01-01 | 0 | 0
FIN | UNIDO | Enabling activities for HFC phase-down |  | EUR | MOG | SEV | 80 | TAS | 01+ | A | I |  | 0 | 0 | 2017-11-01 | 2018-02-01 | 2019-06-01 |  | 2019-06-01 | 2019-10-31 | 50000 | -27 | 49973 | 49972.83 | 100% | 0.17 | 0 | 0 | 3500 | -2 | 3498.0981 | -0.0981 | 0 | The country ratified the Kigali Amendment on 23rd of April 2019. HFC permit system is in place. Quota is planned under the new sub-law. HFC data collection is in place. Importers/exporters are obligated to submit report on imported/exported quantities per substance. The general conclusions focuses on: 1. importance of having training for RAC service technicians, customs officials, environmental inspectors; 2. having tariff codes for HFC substances/blends; 3. marking HFC cylinders-products and equipment; 4. having in place HFC logbooks (inventory) and equipment; 5. ban on non-refillable cylinders; 6. having e-license system for permit issuing. Possible areas to further discuss with stakeholder groups: tax on import of equipment, tax for leakage. In Montenegro, the Ministry of Economy is the competent authority regarding the issue of energy efficiency. However, under the EA project activities, information on EE was presented during the organized workshops/meetings. In addition, the EA project provided an opportunity to strengthen the cooperation with the Ministry of Economy, and other institutions. Project was financially closed in October 2019. Remaining fund balances were returned at the 84th ExCom meeting in December 2019. Final repot was submitted to the MLFS. Actions towards next goals: N/A Was there any delay during the reporting year? - NO Any recurring problem? NO Any impact on project completion date? - NO Any action required by Executive Committee? - NO | n.a.
ONG | UNEP | Enabling activities for HFC phase-down |  | ASP | MON | SEV | 80 | TAS | 01+ | A | I | HFC | 0 |  | 2017-11-01 | 2018-12-01 | 2019-06-01 | 2020-12-01 |  |  | 95000 | 0 | 95000 | 54058.09 | 56.9% | 40941.91 | 38755 | 12406.6394 | 6650 | 0 | 3784.0663 | 2865.9337 | 2712.85 | SSFA signed in Jul 2018. First payment made in Dec 2018. The second payment has been released to the country 26 August 2019. KA translated and distributed. Selected OzonAction Kigali Amendment factsheets were translated into Mongolian language and distributed. Data collection for preparation of Country Assessment Report completed. Two stakeholders consultation workshops conducted in second half of 2019. Revised HS code to include HFCs adopted. Amendment to existing licensing system to include HFC adopted. One master trainer sent to Guangzhou for training on R290 in December 2019. Conducted RAC training on operation of CO2 based systems with 33 participants, in addition to training on handling flammable refrigerants. Status of KA ratification: Expected in 2020 | Draft of the law on ratification of the Kigali Amendment and other relevant documents were developed and submitted to the Ministry of Environment and Tourism, currently under consideration. Country Assessment Report finalized. Held a virtual conference on safety and energy efficiency standards with 44 participants. Agreed with MASM to develop RAC Sub-committee by July. Conducted 2 RAC training on servicing of R32 and R290 based split AC systems with total 20 participants. |  |  | 2020-06-01 | 28505 | 1995.35
ONG | UNIDO | Enabling activities for HFC phase-down |  | AFR | MOR | SEV | 81 | TAS | 01+ | A | I |  | 0 | 0 | 2018-06-01 | 2019-01-01 | 2020-01-01 | 2021-01-01 |  |  | 150000 | 0 | 150000 | 7428.87 | 4.953% | 142571.13 | 0 | 15000 | 10500 | 0 | 520.0209 | 9979.9791 | 0 | Ratification process at final stage. NOU attended the workshop organized by UNIDO on the Kigali Amendment. National consultant identified. ToR prepared and recruitment initiated. Actions towards next goals: Conduct survey. Was there any delay during the reporting year? - No Any recurring problem? - No Any impact on project completion date? - Yes, extension requested at the 84th meeting Any action required by Executive Committee? - Extension requested and granted. | Ratification process at final stage. Consultants recruited. Survey underway. Ongoing work with customs authorities on licensing system. |  |  | 2021-01-01
ONG | UNEP | Enabling activities for HFC phase-down |  | AFR | MOZ | SEV | 81 | TAS | 01+ | A | I | HFC | 0 |  | 2018-06-01 | 2018-12-01 | 2020-01-01 | 2021-01-01 |  |  | 150000 | 0 | 150000 | 85440.39 | 56.96% | 64559.61 | 54800 | 19563.5182 | 10500 | 0 | 5980.8273 | 4519.1727 | 3836 | The second payment for SSFA of the amount of USD 135,000 was released to the country in August 2019. The sensitized key stakeholders during workshops, meetings and public forums on the phase down of HFCs and Kigali Amendment. Prepared and submitted Cabinet Memorandum on ratification of the Kigali Amendment and sensitization of Parliamentarians which lead to ratification of Kigali Amendment. Organized RAC Technicians training workshops on safe use of hydrocarbons refrigerants. Established an ODS Task force for review of ODS Regulations. Overall assessment of project progress is satisfactory. | In Mozambique, the elaboration of HFC regulation is ongoing and its procedures where the importers will be forced to fill application form before the importation and to request authorization in the Ministry of Land and Environment by submitting plan of importation. All these steps are written in the future HFC regulation. Delays in some projects activities are to be expected due to measures taken by the country related to Coronavirus outbreak, which resulted for example in postponing all meetings/ events planned in the first half of the year. |  |  | 2021-01-01 | 50000 | 3500
ONG | UNEP | Enabling activities for HFC phase-down |  | ASP | MYA | SEV | 81 | TAS | 01+ | A | I | HFC | 0 |  | 2018-06-01 | 2019-06-01 | 2020-01-01 | 2021-01-01 |  |  | 95000 | 0 | 95000 | 7753.14 | 8.161% | 87246.86 | 0 | 26438.4424 | 6650 | 0 | 542.7198 | 6107.2802 | 0 | UNEP closely-follow-up with the government of signing of SSFA. The Government confirmed agreement on signing of SSFA in Q3 of 2019. SSFA was signed by UNEP and submitted to government for signature. In 2019, the government finalized the ToRs for the consultant to be recruited under the EA project for preparing Country Assessment Report. One master trainer sent to Guangzhou for training on R290 in December 2019. NOU translated the Kigali Amendment into Burmese, which was submitted to concerned ministries for comments. Feedbacks have been received from all ministries. Status of KA ratification: Expeced ratification in 2021. | The SSFA was signed on 3 January 2020. The first payment was released to the country on 26 March 2020 Consultant for the Country Assessment recruited. Data collection started but difficult due to lockdown. The NOU postponed the first stakeholder consultation to Q3/4 as possible. NOU initiated discussion with Legal Division and conclude that HFC licensing system will be establsihed by amending the existing Ozone Order under environmental law. NOU following up with customs to advance HS revision. NOU hiring TVET expert to conduct study on RAC technicians certification. RAC trainings postponed to Q3/4 as possible. |  |  | 2021-01-01 | 0 | 0
ONG | UNEP | Enabling activities for HFC phase-down |  | AFR | NAM | SEV | 80 | TAS | 01+ | A | I | HFC | 0 |  | 2017-11-01 | 2018-11-01 | 2019-06-01 | 2020-12-01 |  |  | 150000 | 0 | 150000 | 86893.72 | 57.93% | 63106.28 | 55729 | 19123.1152 | 10500 | 0 | 6082.5604 | 4417.4396 | 3901.03 | The second payment for SSFA of the amount of USD 135,000 was released to the country in November 2019. Kigali amendment is ratified on 16 May 2019. The NOU conducted an analysis of Ozone and Climate Policies. 2) Conducted a National Consultative workshop to update the industry and Policy Makers of the Parliament of the Kigali Amendment. 3) Conducted Capacity building through a border dialogue for NOU and Customs & Excise officers from neighboring countries, on monitoring trade of HFCs. Review existing licensing system of controlled substances and products to include control of HFCs and consulted with stakeholders from all sectors. 4) Developed an Electronic Registry and reporting tool for all controlled substances (learned that it will also be beneficial if the tool can also be used to record all NOU Activities and have all databases). Overall assessment of project progress is satisfactory. | The NOU conducted an assessment of training needs for the service sector and participatory workshop on safe use of energy efficient technology (HFC alternatives). 2) Develop an economic value chain study to identify energy efficient technology in the market and a RAC projection & impact analysis 3) Establish an industrial rebates that are available for the Namibian manufacturing under the SACU regime. 4) Adopt ISO 5149 on flammable refrigeration and air conditioning equipment for Namibia. Delays in some projects activities are to be expected due to measures taken by the country related to Coronavirus outbreak, which resulted for example in postponing all meetings/ events planned in the first half of the year. |  |  | 2020-06-01 | 50729 | 3551.03
ONG | UNEP | Enabling activities for HFC phase-down |  | ASP | NAU | SEV | 81 | TAS | 01+ | A | I | HFC | 0 |  | 2018-06-01 | 2019-06-01 | 2020-01-01 | 2021-01-01 |  |  | 50000 | 0 | 50000 | 19838.98 | 39.68% | 30161.02 | 29450 | 9139.703 | 3500 | 0 | 1388.7286 | 2111.2714 | 2061.5 | The SSFA was signed on 6 June 2019. The first payment has been released to the country 27 June 2019. The NOU recruited the consultant to support preparation of Country Assessment Report. Parliament paper for the ratification of the KA drafted. Data collection for preparation of Country Assessment Report completed. A national stakeholder consultation done on 24th October 2019. NOU worked with other Pacific Island Countries’ NOUs to jointly develop and submit the joint proposal to Oceania Customs Organization (OCO) for the amendment of the HS code under the Pacific Harmonized Commodity Description and Coding System 2017 (PACHS17) to assign specific HS code for HFCs and blends in accordance with WCO recommendation. The proposal for amendment was approved by the Review Committee in September 2019. The NOU worked closely with Customs to adopt the updated HS code contained in the last revision of the PACHS17 assigning specific HS code for HFCs and blends. Status of KA ratification: Expeced ratification in 2020. | Country Assessment Report currently under review. NOU postponed RAC technicians training for Q3/4 as possible. |  |  | 2021-01-01 | 9450 | 661.5
ONG | UNEP | Enabling activities for HFC phase-down |  | ASP | NEP | SEV | 81 | TAS | 01+ | A | I | HFC | 0 |  | 2018-06-01 | 2018-11-01 | 2020-01-01 | 2021-01-01 |  |  | 95000 | 0 | 95000 | 23064.73 | 24.28% | 71935.27 | 69050 | 21798.5667 | 6650 | 0 | 1614.5311 | 5035.4689 | 4833.5 | SSFA signed in Oct 2018. First payment made in Nov 2018. NOU recrutied local consultant to support EA implementation. KA translated and distributed. Ratification justification document finalized. Distribution of selected OzonAction factsheets completed. Draft HS code prepared in consultation with Customs, currently under review for adoption. Relevant safety standards have been adopted, EE standards are being discussed with Alternative Energy Promotion Center. Two master trainers sent to Guangzhou for training on R290 in December 2019. Status of KA ratification: Expeced ratification in 2020. | KA ratification justification document shared with Ministry for consultations, currently under consideration. Data collection for preparation of Country Assessment Report completed. Country Assessment Report draft currenlty under review. NOU organizing stakeholder consultation in Q3 as possible. NOU recruiting a legal expert to draft the regulation amendment to include HFCs into the licensing system. NOU adapting further UNEP materials for awareness rising. |  |  | 2021-01-01 | 23050 | 1613.5
ONG | UNIDO | Enabling activities for HFC phase-down |  | AFR | NER | SEV | 81 | TAS | 01+ | A | I |  | 0 | 0 | 2018-06-01 | 2019-01-01 | 2020-01-01 | 2021-12-01 |  |  | 150000 | 0 | 150000 | 29482.49 | 19.65% | 120517.51 | 68053.11 | 40000 | 10500 | 0 | 2063.7743 | 8436.2257 | 4763.7177 | The contract for NOU to carry out subject activities have been facilitated in collaboration with Director NOU and his consultants. Two national experts, in the field of legislation and refrigeration have been recruited to work with the international consultant. Status of ratification of Kigali amendment: Amendment ratified 29 August 2018. Overall assessment of project progress: Progress. The collaboration of the international consultant with the national experts is ongoing. The works for standardization and national HS codes and licensing and quota are progressing. Awareness activities organized by NOU are progressing in accordance with relevant TOR. Impact of these activities: The country is an active member of the regional economic zone to control import and overall trade of the HFCs, through the participation in establishing/improvements Harmonized System (GHS) of customs tariff codes. | Joint works of the international consultant with the national experts are ongoing to finalize national strategies, to support relevant institutional arrangements, to enhance licensing and data reporting systems. Was there any delay during the reporting year? - Yes. Some activities have been delayed because of the restriction measures due to the Covid-19 pandemic. Any recurring problem? - No Any impact on project completion date? - Yes Any action required by Executive Committee? - New decision has been granted, allowing implementing agencies to continue with the project implementation beyond the project end date as per decision. |  |  | 2021-01-01
ONG | UNIDO | Enabling activities for HFC phase-down |  | LAC | NIC | SEV | 81 | TAS | 01+ | A | I |  | 0 | 0 | 2018-06-01 | 2018-10-01 | 2020-01-01 | 2021-01-01 |  |  | 150000 | 0 | 150000 | 116877.81 | 77.92% | 33122.19 | 23691.92 | 5000 | 10500 | 0 | 8181.4467 | 2318.5533 | 1658.4344 | • Ratification of Kigali amendment: No • Activities implemented: Support for the early ratification of the Kigali Amendment; institutional agreements and review of the licensing system; review and strengthening of data reporting systems, data reports on HFC consumption and production; preparatory actions to review existing national HFC policies • Milestones achieved: -Work Plan Agreed with NOU: Yes; - UNIDO awareness-raising workshop organized: Yes - organized in June 2019, named "Kigali in Action". All the NOU participated in the workshop. - Deliverables and results reported: a) Enforced licensing and quota system: Yes (no quota system enforced); b) Awareness raising of stakeholders on the reduction of HFCs. Coordination with government representatives; c) Support for national instruments of ratification; d) Review of institutional arrangements for control measures of HFCs and linkage with national strategies on the environment and mitigation of climate change; e) Improvement of the import and export licensing system to include HFCs (Article 4B) and other alternatives (initiated); f) Training of customs officers on HFC control; Training of environmental inspectors on HFC control and alternatives; g) Review and preparation of local tariff codes in accordance with HFC commitments, with special attention to HFC blends. • Overall assessment of project progress: The majority of the planned activities were implemented and according to the approved UNIDO’s activities in the project for the reported period. • Impact of these activities: Significant awareness activities and discussions were conducted with the main institutions involved in the HFC control in Nicaragua (NOU, Ministry of Environment and custom authorities). Relevant support for the ratification process of the Kigali Amendment. • Potential challenges in completing the projects and activities: some delays due to country context difficulties. • Key findings and lessons learned: evaluations and consultations developed in the project allowed the NOU to identify potential actions in regulatory and institutional framework; Trainings and meetings conduced under the EA project represented a powerful tool to capacity building in the main institutions involved in the control and reporting of HFCs phase-down. | • Activities implemented (to be implemented): Support for the early ratification of the Kigali Amendment; Activities aimed at initiating institutional support agreements and arrangements; HFC licensing system, and data collection and monitoring system; and demonstration of non-investment activities and preliminary capacity building requirements for the implementation of Kigali. • Milestones achieved: - Work Plan Agreed with NOU was updated - Specific deliverables and results reported: a) Improvements in vocational training centers and certification programs regarding the handling of flammable refrigerants (initiating); b) Updated database: Review of the national mechanisms used for the notification of ODS to include HFC consumption, especially taking into account the service sector (particularly the informal sector); c) HFC control records and tools and alternative substances in cooperation with customs authorities and interested parties were enhanced (ongoing); d) Identification of appropriate policies and regulations, including HCFC phase-out strategies, to facilitate the elimination of HFCs and the introduction of alternative low GWP technologies - including "not in kind" options - with higher energy efficiency rates (ongoing). • Overall assessment of project progress: The majority of the planned activities were implemented and according to the approved UNIDO’s activities in the project. Some actions (technical training with international experts, institutional consultations and other) are holding due to the Covid-19 pandemic situation. • Activities planned for the second part of 2020: HFC control records and tools and alternative substances in cooperation with customs authorities and interested parties were enhanced; awareness and institutional consultations. • Potential challenges in completing the projects and activities: Based on the decision taken by UNIDO management to restrict official travel due to the ongoing outbreak of COVID-19 immediately and until further notice. The schedule of the remaining activity needs to be updated. • Any action required by Executive Committee: Yes Considering the uncertain global situation due to COVID-19, it is required a decision on the possible extension of the EA project. |  |  | 2021-01-01
ONG | UNEP | Enabling activities for HFC phase-down |  | AFR | NIR | SEV | 80 | TAS | 01+ | A | I | HFC | 0 |  | 2017-11-01 | 2018-08-01 | 2019-06-01 | 2020-12-01 |  |  | 250000 | 0 | 250000 | 242485.3 | 96.99% | 7514.7 | 0 | 2277.1818 | 17500 | 0 | 16973.971 | 526.029 | 0 | Kigali Amendment was ratified, and instrument of ratification deposited with the UN Sec. Gen. All training needs assessments for Customs, RAC technicians and NOO concluded and report were produced and shared with all stakeholders and UNEP. The NOU conducted the HFCs alternative market and reports were also drafted and shared. The country created more awareness on the KA & HFC phase down through workshops/meetings. | The country conducted awareness creation on EE in close collaboration with the KCEP project. Delays in some projects activities are to be expected due to measures taken by the country related to Coronavirus outbreak, which resulted for example in postponing all meetings/ events planned in the first half of the year.” |  |  | 2020-06-01 | 0 | 0
ONG | UNEP | Enabling activities for HFC phase-down |  | ASP | NIU | SEV | 81 | TAS | 01+ | A | I | HFC | 0 |  | 2018-06-01 | 2019-01-01 | 2020-01-01 | 2021-01-01 |  |  | 50000 | 0 | 50000 | 17741.16 | 35.48% | 32258.84 | 31000 | 9775.4061 | 3500 | 0 | 1241.8812 | 2258.1188 | 2170 | SSFA was signed in December 2018. First transfer of funds in January 2019. Data collection for preparation of Country Assessment Report completed. NOU worked with other Pacific Island Countries’ NOUs to jointly develop and submit the joint proposal to Oceania Customs Organization (OCO) for the amendment of the HS code under the Pacific Harmonized Commodity Description and Coding System 2017 (PACHS17) to assign specific HS code for HFCs and blends in accordance with WCO recommendation. The proposal for amendment was approved by the Review Committee in September 2019. Revised PACHS17 HS code assigning specific HS code for HFCs and blends approved by Customs, needs parliamentary approva, in progress. Status of KA ratification, ratified on 20 April 2018. | Country Assessment Report drafting ongoing. NOU postponed RAC technicians training for Q3/4 as possible. NOU adapting UNEP materials for awareness rising. |  |  | 2021-01-01 | 11000 | 770
ONG | UNDP | Enabling activities for HFC phase-down | Individual | LAC | PAR | SEV | 81 | TAS | 01+ | N | I | HFC | 0 | 0 | 2018-06-01 | 2018-11-01 | 2020-01-01 | 2020-01-01 |  |  | 75000 | 0 | 75000 | 37867 | 50.49% | 37133 | 612 | 11139.852 | 5250 |  | 2650.7012 | 2599.2988 | 42.84 | Participation in workshops in New York, USA and San Jose, Costa Rica, to discuss the implementation of the Kigali Amendment. Meetings with stakeholders to rise awareness. Review of existing legal framework for ODS and HFC control. 2 meetings with refrigeration technicians to review the implication of the Kigali amendment in the certification on GRP. A workshop was conducted with RAC technicians to rise awareness on the Kigali Amendment, current controls to HFC and available alternatives. 1 mission by the international expert to review the road map for the implementation of the Enabling Activity project. An extension for an additional six months has been requested due to COVID-19. | Road map for the implementation of the Kigali Amendment developed, meetings with stakeholders conducted. Since the start of the COVID-19 pandemic in mid-March, meetings have been held from distance. |  |  | 2021-01-01
ONG | UNEP | Enabling activities for HFC phase-down |  | LAC | PAR | SEV | 81 | TAS | 02+ | A | I | HFC | 0 |  | 2018-06-01 |  | 2020-01-01 | 2021-01-01 |  |  | 75000 | 0 | 75000 | 0 | 0% | 75000 | 11890 | 22727.2727 | 5250 | 0 | 0 | 5250 | 832.3 | The SSFA was signed in December 2019 for an amount of US$ 49,000 and the processing of the first payment started in January 2020. Paraguay accepted the Kigali Amendment in November 2018 | The first payment of the signed SSFA was enabled in the country on March 6, 2020. The licensing system including HFCs is in place. An amendment to the regulations for the distribution of HFC quotas is currently under discussion with main stakeholders. The data collection system for HFCs is being enhanced and expected to be operational once the HFC quota mechanism is established. Training of customs officers on the identification and prevention of HFC illegal trade and awareness-raising workshops for importers and customs agents are planned during the first half of 2020, so UNEP is exploring ways to progress these activities virtually. |  |  | 2021-01-01 | 0 | 0
COM | UNDP | Enabling activities for HFC phase-down | Individual | LAC | PER | SEV | 80 | TAS | 01+ | N | I | No_ODP | 0 | 0 | 2017-11-01 | 2018-03-01 | 2019-06-01 |  | 2019-08-01 |  | 150000 | 0 | 150000 | 147582 | 98.39% | 2418 | 0 | 1692.558 | 10500 | 0 | 10330.7442 | 169.2558 | 0 | Peru ratified the Kigali Amendment. HFC licensing & quota system: Performed report and guidance for new Reporting requirements. Legal instrument for licensing system under evaluation – will be approved shortly. HFC data collection and monitoring: Customs controls for HFC management and training for Customs performed. Demonstrations: Performed trainings on good practices for HFC management as well as low-GWP alternatives. " |  |  |  | 2020-06-01
TRF | IBRD | Enabling activities for HFC phase-down |  | ASP | PHI | SEV | 80 | TAS | 01+ | A | I | HFC | 0 | 0 | 2017-11-01 | 2018-05-01 | 2019-06-01 |  |  | 2019-08-27 | 250000 | -225992 | 24008 | 24008 | 100% | 0 |  | - | 17500 | -15819 | 1681 | 0 | 0 | Government of Philippines requested transfer of the Enabling Activity on 3 Apr 19 which was completed at the 83rd ExCom. Balance returned to the Treasurer in Q3 19.
ONG | UNIDO | Enabling activities for HFC phase-down |  | ASP | PHI | SEV | 83 | TAS | 02+ | A | I |  | 0 | 0 | 2017-11-01 | 2019-08-01 | 2020-06-01 | 2020-12-30 |  |  | 225992 | 0 | 225992 | 50347.63 | 22.28% | 175644.37 | 8883.35 | 146000 | 15819 | 0 | 3524.3341 | 12294.6659 | 621.8345 | Project approved at the 83rd meeting in May 2019. Initial process before ratification of Kigali Amendment has been finalized and the bill is with the office of the president. Revision of regulations to enable control and monitor import and export of HFCs and HFC-blends is completed, several trainings and meetings for key public stakeholders finalized. Was there any delay during the reporting year? No. Any recurring problem? No. Any impact on project completion date: No. Any action required by Executive Committee? No. | The ratification was expected for April 2020, however, might be delayed due to Corona pandemic and shut down of activities in the country. Other key activities are still ongoing with support of national consultancy firm. E.g. Activities for promoting energy efficiency are still ongoing. Activities completed include special workshops and technical sessions on the importance and impact of EE in RAC equipment and cooling systems for different ministries and enforcement officers. Delays: Yes, some activities had to be postponed due to the covid-19 pandemic. The project completion will be slightly delayed. |  |  | 2020-06-01
ONG | Germany | Enabling activities for HFC phase-down |  | ASP | PNG | SEV | 80 | TAS | 01+ | A | I | HFC | 0 |  | 2017-11-01 | 2018-02-01 | 2019-06-01 | 2020-12-01 |  |  | 95000 | 0 | 95000 | 32221 | 33.92% | 62779 | 32000 | 62779 | 6650 | 0 | 2255.47 | 4394.53 | 2240 | Prescribed Activities Regulations has been approved. ODS regulations amendment are being finalised. Ratification documents have gone through the legal vetting process. | Foreign Affairs have received the ratification document and it is hoped that ratification will be completed in the next couple of months. |  |  | 2020-06-01
ONG | UNIDO | Enabling activities for HFC phase-down |  | AFR | PRC | SEV | 80 | TAS | 01+ | A | I |  | 0 | 0 | 2017-11-01 | 2018-04-01 | 2019-06-01 | 2021-06-30 |  |  | 150000 | 0 | 150000 | 62595.78 | 41.73% | 87404.22 | 73000 | 10000 | 10500 | 0 | 4381.7046 | 6118.2954 | 5110 | New NOU Director have been appointed. The contract for NOU for subject activities have been facilitated in collaboration with NOU and under support of the new DG for Environmental Issues at the Ministry of Tourism and Environment. Activities refreshed through resumed recruitments of national experts in the field of legislation, customs and refrigeration. Status of ratification of Kigali amendment: Preparatory works proceed in accordance to Congolese legislative system. Madame the Minister has sent a letter to the Government Secretariat regarding the ratification of the Kigali Agreement based on input from the NOU. The Secretariat sent the letter to the Supreme Court for review and comment. After clearance by the Supreme Court, the case will be sent to the two houses of Parliament (Assemblé ET Senat) for voting. Ratification envisaged in 2020. Activities implemented during the reporting period in terms of activity type: Activities in the Country, included mostly the consultations and professional support of consultants and joint work of NOU with UNIDO international consultant to elaborate techno-economic justification of Kigali Amendment, before submission of relevant documentation to decision makers. Overall assessment of project progress: delayed due to changes at the Ministry. Impact of these activities: not yet observed; delays resulted in the request for extension of the completion date of these EAs. | An interactive workshop for service technicians have been organized mostly to introduce new non-ODS and low GWP refrigerants in RAC sector and namely in relation to installation, long term testing and maintenance of R-290 AC split demo units. Was there any delay during the reporting year? - Yes. Some activities have been delayed because of the restriction measures due to the Covid-19 pandemic. Any recurring problem? - No Any impact on project completion date? - Yes Any action required by Executive Committee? - New decision has been granted, allowing implementing agencies to continue with the project implementation beyond the project end date as per decision. |  |  | 2020-06-01
ONG | Italy | Enabling activities for HFC phase-down | Individual | AFR | RWA | SEV | 80 | TAS | 01+ | A | I | HFC | 0 | 0 | 2017-11-01 |  | 2019-06-01 | 2020-12-01 |  |  | 40000 | 0 | 40000 | 0 | 0% | 40000 | 40000 | 25000 | 2800 | 0 | 0 | 2800 | 2800 | SSFA is being drafted and send to the country for review. Rwanda has started implementation of EA project with UNEP’s component (SSFA signed and the first payment is done). The project activities for the Government of Italy’s components are being planned for the second half of 2018. One consultative meeting was conducted with importers on the way forward in the implementation of Kigali Amendment including consultation meeting on the launch of Kigali Amendment and the celebration of Ozone day. The meeting took place on 29 August 2018 in Lemigo hotel. The final draft of the revised national ODS and climate legislation was completed and changes were drafted to allow for HFC phase- down. During the week of International Ozone day, the awareness was conducted to policy makers and other relevant key stakeholders and to all Rwandese on Kigali Amendment awareness through General Public outreach on: Radio and TV Spots from 05 to 16 September, 2018, Kinyarwanda TV & Radio Talk show between 10 to14 September, 2018; English TV & Radio Talk show (with a UNEP Representative, Rwanda Cooling Initiative and MoE staff) between 10 to 14 September, 2018; E-Billboard publication from 09 to 15 September, 2018; Web banners publication and awareness from 05 to 16 September, 2018, Mobile car communication in mainly areas of City of Kigali. Analysis of availability of alternatives and market trends were completed during the exhibition conducted 3 days before the celebration of ozone day, the main importers showed the HFC alternative refrigerants which is on the market currently such as R-600a, and based equipment, AC using R-290 and one of the big industry Bralirwa use R-717 (Ammonia) in their cooling system).The SSFA was signed. The first payment was released to the country at the amount of 25,000 USD. The final draft of the revised national ODS and climate legislation was completed in February 2019. The ministerial order is in Law reform commission for revision. All needed clarification and comments were addressed and waiting for the cabinet approval. Awareness material for HFC phase down were produced and disseminated to the stakeholders and the public. These include 100 Booklets, 260 Branded note pads, 50 caps sun hats, 60 Branded sports, Computer bags, 300 Magazines, 310 T-shirts, 150 bottles, 100 umbrella were produced and distributed during the Week of the World Environment Day from 27 May to 5 June 2019. Workshop on Refrigerant Driving License (RDL) Program aim to support local Refrigeration and Air conditioners (RAC) Technicians as appropriate through refining technics to build their capacities and to elevate their skills and competencies in RAC Sector in Kigali Amendment framework were organized from 24 to 27 June 2019 for 11 trainers. One custom stakeholder’s consultation meeting was organized and attended by Director in charge of training in the department of training of customs/RRA. Electronic licensing system for HFC and alternatives was developed and the system is on final stage. Rwanda adopted the National Cooling Strategy on 24 June 2019. The first disbursement of US$25,000 was made in April 2019. The country has submitted all required reports and requested for the final payment of US$15,000 (as the cash advance). The cash advance is being processed by UN Environment. The project is on track.The inventory of HFCs is carried out in all 30 districts of Rwanda, for determining current status of HFCs stored in Rwanda. The inventory is focusing on the collection of quantities of HFCs refrigerants and refrigeration based equipment in following areas: convention centre, commercial buildings, administrative buildings (private and government), airports, banks, hospitals, hotels above 2 stars, industries, milk collection centers. -Review of Ministerial order governing the use of substances that deplete the ozone layer and/or that may cause climate change by including HFCs in the licensing system. The ministerial order is sent to Law reform Commission for revision. All needed clarification and comments were addressed and waiting for the cabinet approval -The E-registry and reporting tool incorporated the licensing system for HFCs and HFC alternatives. | Rwanda has revised the ODS legislation to incorporate license quotas for HFCs which is currently awaiting approval by Cabinet; suppliers have been trained on Kigali amendment and its objectives to promote green technology that use low GWP a parallel to the energy efficient; RAC technicians have also been trained in the safe handling of flammable refrigerants; and the documentary film on the demonstration of green technology of using ammonia in one large industry in Rwanda has been produced. The country finalised the review of Ministerial order governing the use of substances that deplete the ozone layer and/or that may cause climate change by including HFCs in the licensing system. Rwanda finalised the establishing of the E-registry and reporting tool which incorporated the licensing system for HFCs and HFC alternatives. The implementation of activities is being completed. Delays are to be expected due to measures taken by the country related to Coronavirus outbreak, which resulted for example in closing of offices and restricted movements in the first half of the year. |  |  | 2020-06-01
ONG | UNEP | Enabling activities for HFC phase-down |  | AFR | RWA | SEV | 80 | TAS | 02+ | A | I | HFC | 0 |  | 2017-11-01 | 2018-07-01 | 2019-06-01 | 2020-12-01 |  |  | 55000 | 0 | 55000 | 46140.23 | 83.89% | 8859.77 | 2726 | 2684.7788 | 3850 | 0 | 3229.8161 | 620.1839 | 190.82 | The final payment for SSFA of the amount of USD 45,000 was released to the country in December 2019. Rwanda has ratified the Kigali amendment on 25 May, 2017. The NOU has revised the ODS legislation to incorporate license quotas for HFCs which currently is in the process of being approved by Cabinet; suppliers have been trained on Kigali amendment and its objectives to promote green technology that use low GWP a parallel to the energy efficient; RAC technicians have also been trained in the safe handling of flammable refrigerants; and the documentary film on the demonstration of green technology of using ammonia in one large industry in Rwanda has been produced. Overall assessment of project progress is satisfactory. | Rwanda is among the country that has adopted the National Cooling Strategy and currently, the stakeholders including the Suppliers, decision makers, relevant institutions, RAC technicians, etc. are going to be trained on the strategy and the awareness will start in the coming months. Delays in some projects activities are to be expected due to measures taken by the country related to Coronavirus outbreak, which resulted for example in postponing all meetings/ events planned in the first half of the year. |  |  | 2020-06-01 | 0 | 0
ONG | UNEP | Enabling activities for HFC phase-down |  | ASP | SAM | SEV | 81 | TAS | 01+ | A | I | HFC | 0 |  | 2018-06-01 | 2018-11-01 | 2020-01-01 | 2021-01-01 |  |  | 50000 | 0 | 50000 | 21938.41 | 43.88% | 28061.59 | 24000 | 8503.5121 | 3500 | 0 | 1535.6887 | 1964.3113 | 1680 | SSFA was signed in November 2018. First transfer of funds in November 2018. NOU recruited a local consultant to conduct data collection and drafting of Country Assessment Report.One stakeholder consultation completed in July 2019. NOU organized a GPR training in July 2019 with 15 technicians trained. Selected OzonAction factsheets were translated and distributed to key stakeholders. NOU adapting further UNEP materials for awareness raising. NOU worked with other Pacific Island Countries’ NOUs to jointly develop and submit the joint proposal to Oceania Customs Organization (OCO) for the amendment of the HS code under the Pacific Harmonized Commodity Description and Coding System 2017 (PACHS17) to assign specific HS code for HFCs and blends in accordance with WCO recommendation. The proposal for amendment was approved by the Review Committee in September 2019. Status of KA ratification, ratified on 23 March 2018. | The second payment has been released to the country 13 April 2020. One stakeholders consultation done in 2020. Country Assessment Report currently under review. Amendment drafted and currently under review. NOU is following up with customs on revised PACHS17 HS code adoption to assign specific HS code for HFCs and blends. |  |  | 2021-01-01 | 4000 | 280
ONG | UNEP | Enabling activities for HFC phase-down |  | AFR | SEN | SEV | 80 | TAS | 01+ | A | I | HFC | 0 |  | 2017-11-01 | 2018-11-01 | 2019-06-01 | 2020-12-01 |  |  | 150000 | 0 | 150000 | 107397.09 | 71.6% | 42602.91 | 30050 | 12909.9727 | 10500 | 0 | 7517.7963 | 2982.2037 | 2103.5 | Comprehensive review of National licensing system for ODS, ODS alternatives and based-products was done in 2019. Analysis of existing policy and regulatory framework for HFCs was done in 2019. Stakeholders consultation meetings and awareness programmes to facilitate the ratification process at the national level were organised. Awareness material for HFC phase down was produced and disseminated to the stakeholders and the public. The development and implementation an HFCs Outlook Model were to be finalized by an international consultant by end 2019. There are delayed and will be finalized by July 2020. The development of Customs Harmonized Code will be finalized by an international consultant by December 2019. It is delayed and will be finalized by July 2020. | In January -March 2020 Senegal participated in many exchanges that lead to the recrutment of an International Consultant and a Draft proposal for the extension of the subheadings 2903.39 and 3824.78 of the Tariff and Statis-tical Nomenclature (TSN) of the Common External Tariff (CET) of the Economic Community of West African States (ECOWAS) in order to facilitate the collection and comparison of data concerning the circulation of hydrofluorurocarbons (HFC) will be developed and submitted to WCO. Delays due to COVID-19 |  |  | 2020-06-01 | 47000 | 3290
ONG | Germany | Enabling activities for HFC phase-down |  | AFR | SEY | SEV | 80 | TAS | 01+ | A | I | HFC | 0 |  | 2017-11-01 | 2018-01-01 | 2019-06-01 | 2020-12-01 |  |  | 95000 | 0 | 95000 | 41814 | 44.01% | 53186 | 45000 | 53186 | 6650 | 0 | 2926.98 | 3723.02 | 3150 | Ratification has been completed. Consultants were hired to draft guidelines for the safe handling of HC and NH3 to be included into the amendment ODS regulations. | Technical workshop conducted on the ODS regulation amendment provisions. The country is hoping to have the amendment approved in the next quarter. requesting amendment of the ODS regulations. This has been approved and the process of drafting the amendment is currently ongoing. |  |  | 2020-06-01
ONG | UNEP | Enabling activities for HFC phase-down |  | AFR | SIL | SEV | 81 | TAS | 01+ | A | I | HFC | 0 |  | 2018-06-01 | 2018-12-01 | 2020-01-01 | 2021-01-01 |  |  | 95000 | 0 | 95000 | 5701.06 | 6.001% | 89298.94 | 85000 | 27060.2848 | 6650 | 0 | 399.0742 | 6250.9258 | 5950 | Kigali amendment was ratified in November 2019. Committee for the review of the ODS regulation has been constituted and first meeting held to commence the review process to establish a quota and licensing system for HFCs importation. Consultants started with the preparation of training needs assessment for the servicing sector related to alternative technologies April 2019. Survey on training needs assessment was completed in June 2019. Overall assessment of project progress is satisfactory. | Training and awareness raising on energy efficient RAC equipment has been conducted for Refrigeration and Air Conditioning servicing technicians across the country. Delays in some projects activities are to be expected due to measures taken by the country related to Coronavirus outbreak, which resulted for example in postponing all meetings/ events planned in the first half of the year. |  |  | 2021-01-01 | 50000 | 3500
ONG | UNIDO | Enabling activities for HFC phase-down |  | AFR | SOA | SEV | 82 | TAS | 01+ | A | I |  | 0 | 0 | 2018-12-01 | 2019-03-01 | 2020-06-01 | 2020-02-01 |  |  | 240000 | 0 | 240000 | 144287.34 | 60.12% | 95712.66 | 57217.62 | 26500 | 16800 | 0 | 10100.1138 | 6699.8862 | 4005.2334 | Activities implemented. Kigali ratified. The country ratified the Kigali Amendment on 1st of August 2019. DEFF proposes to have two permit types in RSA (1 - grandfathered permit: 80% of the total annual upper limit; 2 - special permit: 20% of the total annual upper limit). As stated by DEFF, the 80% split recognizes that the majority of importers of HFCs in the future will have imported in the past. Topic of data collection/management/verification was cancelled. HFC data verification with Customs and Industry was initiated. Information and demonstration on low-GWP technologies provided at meetings at study tour. Amendment to the ODS Regulation was initiated. Another area needing regulation as stated by DEFF is the labelling, imports and exports of products, equipment, components and technology where it relies on or contains HFCs. It was expressed that of importance is also to impose ban(s) or restrictions on imports – issue of dumping obsolete equipment relying on HFCs. In addition, it has been noted by DEFF that there is still need for research and technical developments and adjustments of the norms and standards are necessary. In addition, in order for market transformations to occur and barriers to be addressed/lifted, demonstration projects are appropriate and can yield interesting data on way forward. Uniform standardization is also required. It was also noted that the tariff classification of ODS blends and non-ODSs has been completed in January 2019 and in process now to verify whether it includes controlled HFCs under Kigali Amendment. DEFF advised by customs to conduct a tariff review. In RSA, Department of Mineral Resources and Energy (DMRE) is in charge of issue of energy efficiency. A GEF project focused on encouraging adoption of higher efficient appliances and technologies by implementing measures/interventions such as minimum energy performance standards (MEPS), labeling programs, and incentive programs. However, under the UNIDO implemented EA project activities, information on EE was presented during the organized workshop/meeting. In addition, the EA project provided an opportunity to strengthen the cooperation with the other relevant institutions and stakeholder groups. Actions towards next goals: Submit the final report. Was there any delay during the reporting year? - NO Any recurring problem? NO Any impact on project completion date? - NO Any action required by Executive Committee? - NO | Final report submitted to 85th meeting
ONG | UNEP | Enabling activities for HFC phase-down |  | ASP | SOI | SEV | 81 | TAS | 01+ | A | I | HFC | 0 |  | 2018-06-01 | 2018-12-01 | 2020-01-01 | 2021-01-01 |  |  | 95000 | 0 | 95000 | 28774.87 | 30.29% | 66225.13 | 60062 | 20068.2212 | 6650 | 0 | 2014.2409 | 4635.7591 | 4204.34 | SSFA was signed in December 2018. First transfer of funds in December 2018. One stekeholders consultation done in June 2019. Data collection for preparation of Country Assessment Report completed. NOU produced brochures and calendars on KA. NOU worked with Solomon Islands National University (SINU) in organizing one Train the trainers’ workshop under Pacific Technical and Vocational Education and Training (PAC-TVET) programme in preparation for the RAC Course in the country in August 2019 for 20 participants. NOU also worked with SINU and RAC Association to integrate the Good Practices in Refrigeration curriculum into the RAC certification system. Expert from Fiji attended the consultation workshop to share experiences regarding the implementation of certification system. NOU worked with other Pacific Island Countries’ NOUs to jointly develop and submit the joint proposal to Oceania Customs Organization (OCO) for the amendment of the HS code under the Pacific Harmonized Commodity Description and Coding System 2017 (PACHS17) to assign specific HS code for HFCs and blends in accordance with WCO recommendation. The proposal for amendment was approved by the Review Committee in September 2019. Status of KA ratification, expected ratification by 2020. | The NOU is working with relevant agencies in the ministry to prepare the document for ratification. One workshop with importers and custom brokers done in March 2020. Country Assessment Report currently under review. Legal expert contracted in March 2020 to prepare the regulation amendment to control HFC, drafting and consultations ongoing. NOU started working with international IT consultant to develop the online licensing system to facilitate application process. NOU is following up with customs on revised PACHS17 HS code adoption to assign specific HS code for HFCs and blends. NOU postponed RAC technicians training for Q3/4 as possible. Adaptation of further UNEP materials for awareness rising ongoing. |  |  | 2021-01-01 | 18062 | 1264.34
ONG | UNIDO | Enabling activities for HFC phase-down |  | AFR | SOM | SEV | 80 | TAS | 01+ | A | I |  | 0 | 0 | 2017-11-01 | 2018-03-01 | 2019-06-01 | 2020-12-01 |  |  | 150000 | 0 | 150000 | 30902.88 | 20.6% | 119097.12 | 77905.37 | 71000 | 10500 | 0 | 2163.2016 | 8336.7984 | 5453.3759 | The country ratified the Kigali Amendment on 27th of November 2019. Training for technicians has been organized. Actions towards next goals: Organize stakeholders meetings and trainings/workshops. Was there any delay during the reporting year? - No Any recurring problem? No Any impact on project completion date? - No Any action required by Executive Committee? - No | workshop planned, postponed. NOU requested extension Stakeholders meetings and workshops/trainings have been planned, however had to be postponed due to the COVID-19 pandemic. Once measures are esed, activities will resume. Was there any delay during the reporting year? - Yes, due to the COVID-19 pandemic, activities had to be postponed. Any recurring problem? No Any impact on project completion date? - Yes Any action required by Executive Committee? - Yes, allow project implementation beyond the 30 months implementation period. |  |  | 2020-06-01
ONG | UNEP | Enabling activities for HFC phase-down |  | ASP | SRL | SEV | 81 | TAS | 01+ | A | I | HFC | 0 |  | 2018-06-01 | 2019-01-01 | 2020-01-01 | 2021-01-01 |  |  | 150000 | 0 | 150000 | 16928.28 | 11.29% | 133071.72 | 127500 | 40324.7636 | 10500 | 0 | 1184.9796 | 9315.0204 | 8925 | SSFA signed in Dec 2018. First payment made in Jan 2019. Local consultant to conduct data collection and draft the Country Assessment Report recruited. Data collection completed. Selected OzonAction factsheets distributed. NOU is hiring to support awareness rising campaing. NOU adapting further UNEP materials for awareness rising. Two stakeholder workshops conducted. Two roundtable discussions on KA implications and low-GWP technologies conducted with importers, equipment importers, and large end users done in December 2019. One RDL training completed. Issued amendment to import export control act in August 2019 introducing HFC licensing together with revised HS national sub code. Status of KA ratification: Ratified Sep 2018. | Country Assessment Report final draft currently under review. NOU postponed stakeholders workshop for Q3/4 as possible. NOU postponed ammonia and CO2 training to Q3/4 as possible. NOU working with TVET to conduct study on implementation of RPL. NOU hiring consultant to conduct study on cold chain policy. NOU liaised with National Standards Institute for the adaptation of relevant safety standards, process ongoing. |  |  | 2021-01-01 | 55000 | 3850
ONG | UNEP | Enabling activities for HFC phase-down |  | AFR | SSD | SEV | 81 | TAS | 01+ | A | I | HFC | 0 |  | 2018-06-01 | 2019-09-01 | 2020-01-01 | 2021-01-01 |  |  | 95000 | 0 | 95000 | 4740.59 | 4.99% | 90259.41 | 0 | 27351.3364 | 6650 | 0 | 331.8413 | 6318.1587 | 0 | The country experienced delays due to unstable Political situation. Some activities have been postponed due to Corona virus situation. The training needs assessment for RAC technicians, customs officers and NOU is underway. Ratification materials prepared and submitted to Parliament for approval process. The revised ODS regulations that include HFCs drafted awaiting the approval process. | The SSFA was signed by country in January 2020 . The first payment was released to the country in February, 2020. The country is planning to finalise on the ratification process of the Kigali Amendment, organise different workshops and consultation meetings. Some activities have been postponed due to Corona virus situation. Delays in some projects activities are to be expected due to measures taken by the country related to Coronavirus outbreak, which resulted for example in postponing all meetings/ events planned in the first half of the year. |  |  | 2021-01-01 | 0 | 0
ONG | UNEP | Enabling activities for HFC phase-down |  | LAC | STK | SEV | 81 | TAS | 01+ | A | I | HFC | 0 |  | 2018-06-01 |  | 2020-01-01 | 2021-01-01 |  |  | 50000 | 0 | 50000 | 0 | 0% | 50000 | 50000 | 15151.5152 | 3500 | 0 | 0 | 3500 | 3500 | The SSFA was signed on 26 September 2018. The first payment has been released to the country 22 November 2019. | The SSFA was signed on 26 September 2018. The first payment has been released to the country 22 November 2019. Country in process on contracting consultants and experts to delivery services including training and other activities under the project. Consultations held with Legal Affairs on steps needed to ratify. Policy approach discussed to advance to ratification. Draft note on ratificationof KA which will go to Cabinet already prepared. Delays in some projects activities are to be expected due to measures taken by the country related to Coronavirus outbreak, which resulted for example in postponing all meetings/ events planned in the first half of the year |  |  | 2021-01-01 | 40000 | 2800
ONG | UNEP | Enabling activities for HFC phase-down |  | LAC | STL | SEV | 80 | TAS | 01+ | A | I | HFC | 0 |  | 2017-11-01 |  | 2019-06-01 | 2021-06-01 |  |  | 95000 | 0 | 95000 | 0 | 0% | 95000 | 95000 | 28787.8788 | 6650 | 0 | 0 | 6650 | 6650 | SSFA was signed in August 2018. The first payment was released in November 2018. The NOU continuing with undertaking an Analysis of existing Ozone and Climate policy/legislation to make adjustments to support implementation of the KA. The NOU commenced planning the assessment of training (and other) needs for the servicing sector, needed to support the transition to low GWP, higher energy efficient (EE) alternatives, such as natural refrigerants (and other not-in-kind alternatives) and standards. | SSFA was signed in August 2018. The first payment was released in November 2018. Country in process on contracting consultants and experts to delivery services including training and other activities under the project. Consultations held with Legal Affairs on steps needed to ratify. Policy approach discussed to advance to ratification. Delays in some projects activities are to be expected due to measures taken by the country related to Coronavirus outbreak, which resulted for example in postponing all meetings/ events planned in the first half of the year |  |  | 2020-06-01 | 57000 | 3990
ONG | UNEP | Enabling activities for HFC phase-down |  | AFR | STP | SEV | 81 | TAS | 01+ | A | I | HFC | 0 |  | 2018-06-01 | 2018-11-01 | 2020-01-01 | 2021-01-01 |  |  | 95000 | 0 | 95000 | 8950.8 | 9.422% | 86049.2 | 74800 | 26075.5152 | 6650 | 0 | 626.556 | 6023.444 | 5236 | The country ratified the Kigali amendment on 31 October 2019. National consultants are contracted to assist Customs Office in developing national custom codes for different HFCs and include them into the Customs Tariff in order to ensure proper monitoring and recording of imports/exports or re-export of individual HFCs. Comprehensive review of National licensing system for ODS, ODS alternatives and based-products was done in 2019. Analysis of existing policy and regulatory framework for HFCs was done in 2019. Stakeholders consultation meetings and awareness programmes to facilitate the ratification process at the national level were organised. Awareness material for HFC phase down was produced and disseminated to the stakeholders and the public. The development of Customs Harmonized Code was to be finalized by an international consultant by December 2019. It is delayed and will be finalized by July 2020 | The country ratified the Kigali amendment on 31 October 2019. In january 2020, two National consultants wereare contracted to assist Customs Office in developing national custom codes for different HFCs and include them into the Customs Tariff in order to ensure proper monitoring and recording of imports/exports or re-export of individual HFCs. Comprehensive review of National licensing system for ODS, ODS alternatives and based-products was done in 2019. Analysis of existing policy and regulatory framework for HFCs was done in 2019. Stakeholders consultation meetings and awareness programmes to facilitate the ratification process at the national level were organised. Awareness material for HFC phase down was produced and disseminated to the stakeholders and the public. The development of Customs Harmonized Code was to be finalized by an international consultant by December 2019. It is delayed and will be finalized by the end of 2020. |  |  | 2021-01-01 | 35000 | 2450
ONG | UNEP | Enabling activities for HFC phase-down |  | LAC | STV | SEV | 80 | TAS | 01+ | A | I | HFC | 0 |  | 2017-11-01 |  | 2019-06-01 | 2021-06-01 |  |  | 50000 | 0 | 50000 | 0 | 0% | 50000 | 0 | 15151.5152 | 3500 | 0 | 0 | 3500 | 0 | SSFA not yet signed owing to national challenges with funds management. The NOU progressed with drafting admendment to ODS licensing and quota system. The NOU completed a comprehensive review of the existing ODS licensing and quota system of towards including HFCs into the licensing system. The stakeholder consultations to facilitate the ratification process continue. | SSFA not yet signed owing to national challenges with funds management. Country requested funds to be allocated to their Association, and NGO. However they have yet to provide the requisite documents to allow for the Due Deligence procedure to be undertaken to allow for the SSA to be prepared and signed. Country preferred this route becuase they have been experiencing issues with expending funds from other projects owing to extreme scruinity by their accounts dept. and adminstration. Despite this the county been able to prepare the KA note for submission to Cabinet for consideration. A Technicians training on alternatives including EE alternatives was held. NOU currently working on the national standards for labelling of refrigerant containers. The revision of the national ODS and climate legislation was completed and changes are drafted to allow for HFC phase- down (list of controlled HFCs, licensing system, reporting requirements). The stakeholder consultations to facilitate the ratification process continue. Delays in some projects activities are to be expected due to measures taken by the country related to Coronavirus outbreak, which resulted for example in postponing all meetings/ events planned in the first half of the year. |  |  | 2020-06-01 | 0 | 0
ONG | UNIDO | Enabling activities for HFC phase-down |  | AFR | SUD | SEV | 80 | TAS | 01+ | A | I |  | 0 | 0 | 2017-11-01 | 2018-04-01 | 2019-06-01 | 2021-06-30 |  |  | 75000 | 0 | 75000 | 73564.72 | 98.09% | 1435.28 | 1023.93 | 411 | 5250 | 0 | 5149.5304 | 100.4696 | 71.6751 | Local consultants finalized core monitoring and data collection before anti government demonstrations took place in the country. Project is implemented jointly with UNEP. NOU reported delays in UNEP's activities. Coordination meeting had been planned however not materialized. International consultant worked with NOU and other stakeholders to prepare workshop and other awareness activities for government and service sector to support the ratification process. Two awareness workshops took place, in Kosti and in Khartoum. - Status of ratification of Kigali amendment: Preparatory works in progress. Ratification envisaged in 2020. - Activities implemented during the reporting period in terms of activity type: Activities in the Country slowed down. However international consultant continued preparations for standardization and national HS codes and licensing and quota. Preparations for Government awareness workshops and seminars were ongoing in collaboration with the NOU. Local experts finalized collection of relevant information to be provided to decision makers to justify the advantages of the KA for future compliance of the Country with MP as well as for future innovations in respective industrial- as well as servicing sectors to mitigate ODS and high GWP pollutions. - Overall assessment of project progress: slow progress. Coordinating meeting NOU - UNIDO - UNEP has not been materialized. - Impact of these activities: not yet observed, however the ratification is still envisaged in 2020. | Works completed at UNIDO side. |  |  | 2020-06-01
ONG | UNEP | Enabling activities for HFC phase-down |  | AFR | SUD | SEV | 80 | TAS | 02+ | A | I | HFC | 0 |  | 2017-11-01 | 2018-12-01 | 2019-06-01 | 2020-12-01 |  |  | 75000 | 0 | 75000 | 4022.52 | 5.363% | 70977.48 | 64800 | 21508.3273 | 5250 | 0 | 281.5764 | 4968.4236 | 4536 | The country experiencing delays due to Political unrest that was experienced in the country. The NOU could not work for some months as there was political unrest. Some activities have been postponed due to Corona virus situation. Consultative meetings with the RAC importers and distributors on the HFC licensing and quota system have been conducted; and RAC technicians have been trained on safe handling of HFCs and their alternatives. The ratification of the Kigali Amendment is at the Parliamentary stage. | The country conducted training on energy efficient operation of RAC equipment, inviting Energy Efficiency stakeholders to different workshops and consultation meetings conducted under the project. Delays in some projects activities are to be expected due to measures taken by the country related to Coronavirus outbreak, which resulted for example in postponing all meetings/ events planned in the first half of the year. |  |  | 2020-06-01 | 40000 | 2800
ONG | UNEP | Enabling activities for HFC phase-down |  | LAC | SUR | SEV | 80 | TAS | 01+ | A | I | HFC | 0 |  | 2017-11-01 |  | 2019-06-01 | 2021-06-01 |  |  | 95000 | 0 | 95000 | 0 | 0% | 95000 | 95000 | 28787.8788 | 6650 | 0 | 0 | 6650 | 6650 | The SSFA was signed on 20 August 2018. The first payment has been released to the country 25 January 2019. Assessment on ratification implications for the Country commenced. Package for ratification of the Kigali amendment being developed. | The SSFA was signed on 20 August 2018. The first payment has been released to the country 25 January 2019. NOU completed the assessment on ratification implications for the Country. Final consultations expected to take place in April 2020 with stakeholders (Min of Trade, Bureau of Standards, Office of the President, ARVAS, Importers and end users, persons involved in EE) delayed owing to COVID-19. A ratification note was prepared for submission to Parliament. Expected to ratify in the coming months. Delays in some projects activities are to be expected due to measures taken by the country related to Coronavirus outbreak, which resulted for example in postponing all meetings/ events planned in the first half of the year. |  |  | 2020-06-01 | 57000 | 3990
ONG | UNEP | Enabling activities for HFC phase-down |  | AFR | SWA | SEV | 81 | TAS | 01+ | A | I | HFC | 0 |  | 2018-06-01 | 2018-11-01 | 2020-01-01 | 2021-01-01 |  |  | 95000 | 0 | 95000 | 59708.52 | 62.85% | 35291.48 | 34800 | 10694.3879 | 6650 | 0 | 4179.5964 | 2470.4036 | 2436 | Awareness activities have been conducted with key stakeholders and end-users. The three studies, including legal review are on-going under NOU supervision. Joint Parliamentary workshop conducted and awaiting to make final decision on KA ratification. Project delayed due to newly introduced Procurement Regulatory Authority regulations and their requirement. NOU working hard to facilitate progress. | In collaboration with the Ministry of Natural Resources and Energy, the NOU is promoting the National Energy Policy which includes energy efficiency in the cooling sector. One trainer has participated in Cool training conducted by GIZ. Delays in some projects activities are to be expected due to measures taken by the country related to Coronavirus outbreak, which resulted for example in postponing all meetings/ events planned in the first half of the year. |  |  | 2021-01-01 | 30000 | 2100
ONG | UNEP | Enabling activities for HFC phase-down | Individual | ASP | SYR | SEV | 83 | TAS | 01+ | A | I | HFC | 0 |  | 2019-05-01 |  | 2020-12-01 | 2020-12-01 |  |  | 250000 | 0 | 250000 | 0 | 0% | 250000 | 0 | 75757.5758 | 17500 | 0 | 0 | 17500 | 0 | Newly approved project. | Two national consultation workshops were organised to launch the project. SSFA has been drafted and the plan of action was agreed between the Government and UNEP. SSFA signed by both parties in April 2020. Some delays are faced due to COVID-19 but the project is progressing well despite diificult circumstances in the country. |  |  |  | 0 | 0
ONG | IBRD | Enabling activities for HFC phase-down |  | ASP | THA | SEV | 80 | TAS | 01+ | A | I | HFC | 0 | 0 | 2017-11-01 | 2017-12-02 | 2019-06-01 | 2021-06-01 |  |  | 250000 | 0 | 250000 | 30000 | 12% | 220000 | 220000 | 175000 | 17500 | 0 | 2100 | 15400 | 15400 | TOR finalized for a consultant to collect 2016, 2017 and 2018 HFC consumption data; validate, supplement and reconcile import data of major HFCs from Customs; review the relevant regulatory framework; and, determine future HFC alternative availability and costs. Consultant selection completed by Q4 19 and begun work by the end of the year. Dec. 83/40 extended completion date to Jun 2020. | Import data of major HFCs from Customs has been updated and reconciled by Apr. 20. Industry stakeholder consultations completed between Mar-May 20 (virtually). Draft report with policy analysis, sectoral analysis, historic & projected HFCs/HCFCs consumption, GHG impact assessment and alternatives' review done by May 25, 20. Due to COVID-19, the enabling activity work, notably vetting the strategy document with stakeholders, will most likely not be completed by the ExCom agreed completion date of June 2020. It is expected that the activity will be completed by Dec 20 and hence an extension will be requested. |  |  | 2020-06-01
FIN | IBRD | Project preparation for conversion from HFC to HFO-based or other low-GWP alternatives in the production of commercial refrigeration equipment at Pattana Intercool |  | ASP | THA | REF | 80 | PRP | 02+ | A | I | HFC | 0 |  | 2017-11-01 | 2017-12-01 | 2018-12-01 |  | 2018-12-01 | 2018-12-01 | 30000 | 0 | 30000 | 30000 | 100% | 0 | 0 | 0 | 2100 | 0 | 2100 | 0 | 0 | Project proposal submitted to the 82nd Meeting and project approved.
ONG | IBRD | Conversion from HFC to propane (R-290) and isobutene (R-600a) as a refrigerant in manufacturing commercial refrigeration appliances in Pattana Intercool Co. Ltd. |  | ASP | THA | REF | 82 | INV | 03+ | N | I | HFC | 8.8 | 0 | 2018-12-03 |  | 2020-12-01 | 2020-12-01 |  |  | 183514 | 0 | 183514 | 0 | 0% | 183514 | 183514 | 183514 | 16516 | 0 | 0 | 16516 | 16516 | Pattana Cool completed conversion by end of Dec. 19 however there has been no disbursement as the overall Grant Agreement between Thailand and the Bank was not approved and signed. Equipment production with the newly converted facility expected by Jan. 20 | Equipment production with the newly converted facility started in Jan. 20. Retroactive funding will be provided upon effectiveness of the Thailand-Bank Grant Agreement expected in the second half of 2020.
ONG | UNEP | Enabling activities for HFC phase-down |  | EUR | TKM | SEV | 80 | TAS | 01+ | A | I | HFC | 0 |  | 2017-11-01 | 2019-06-01 | 2019-06-01 | 2021-06-01 |  |  | 150000 | 0 | 150000 | 27500.02 | 18.33% | 122499.98 | 120000 | 37121.2061 | 10500 | 0 | 1925.0014 | 8574.9986 | 8400 | Progress January – December 2019: Turkmenistan aims to ratify the Kigali Amendment in 2020. Five local consultants were engaged by UNEP in January 2019 (total contract value USD 76,000). An agreement with UNDP Turkmenistan of USD 70,000 has been signed in February 2019 to provide logistical support for arranging stakeholder meetings, translations etc. The local consultants worked on tasks related legislation, customs codes, licensing system, RAC servicing sector and project coordination including stakeholder consultations. They initiated consultations with importers and RAC technicians, the revision and formulation of legislation, the preparation of letters to request up-dated information on ODS alternatives and drafting of a new publication. The Montreal Protocol Unit of Turkmenistan provided the overall monitoring of the activities in consultation with UNEP. A series of meetings and stakeholder consultations took place in March 2019 on Kigali Amendment ratification and review of legislation, in April 2019 on the licensing system for ODS and HFCs, with decision-makers to review relevant documents, with the customs statistics department on national customs codes for HFCs, in May 2019 with RAC sector experts and industry representatives, on the development of national customs codes for HFCs, in July 2019 with customs officers and inspectors, in August 2019 with key stakeholders on the impact of HFC emissions and Kigali Amendment, in September / October 2019 with key stakeholders, Ozone Secretariat and UNEP on benefits of early ratification and review of project status, and in October 2019 on drafting revised legislation. The training needs assessment and related surveys were conducted during September - November 2019. National 3-digit HS codes for HFCs were approved and informed to customs in November 2019. ExCom 83 approved the extension of the project until June 2020 to allow the completion of activities. The interim progress and financial reports were submitted in November 2019. | Progress January – May 2020: A workshop for 50 RAC experts on good servicing practices and HFC alternatives took place in January 2020. The third stakeholder consultation for 50 Government representatives was held in March 2020 to discuss the relationship between the Kigali and Paris Agreements, ozone layer and climate related legislation in Turkmenistan, HFC alternatives, handing of flammable refrigerants and energy-efficiency. A training of 22 RAC experts on good servicing practices and HFC alternatives took place in April 2020. The consultation of the licensing expert with the specialists of the licensing department on separate codes for HFCs and natural refrigerants took place in May 2020. Due to Covid-19 and the related travel restrictions, international experts cannot come to Turkmenistan and RAC trainers cannot attend international training on the safe use of alternatives. Therefore, an extension of the project has been requested and the agreement with UNDP Turkmenistan is being amended to extend its validity date to June 2021 to allow the completion of planned activities. |  |  | 2020-06-01 | 23660.81 | 1656.2567
ONG | UNEP | Enabling activities for HFC phase-down |  | AFR | TOG | SEV | 80 | TAS | 01+ | A | I | HFC | 0 |  | 2017-11-01 | 2018-05-01 | 2019-06-01 | 2020-12-01 |  |  | 150000 | 0 | 150000 | 4487.97 | 2.992% | 145512.03 | 125149 | 44094.5545 | 10500 | 0 | 314.1579 | 10185.8421 | 8760.43 | The country ratified the Kigali amendment on 08 March 2018. National consultants are contracted to assist Customs Office in developing national custom codes for different HFCs and include them into the Customs Tariff in order to ensure proper monitoring and recording of imports/exports or re-export of individual HFCs. Comprehensive review of National licensing system for ODS, ODS alternatives and based-products was done in 2019. Analysis of existing policy and regulatory framework for HFCs was done in 2019. Stakeholders consultation meetings and awareness programmes to facilitate the ratification process at the national level were organised. Awareness material for HFC phase down was produced and disseminated to the stakeholders and the public. The development of Customs Harmonized Code was to be finalized by an international consultant by December 2019. It is delayed and will be finalized by July 2020. NOU attended the ECOWAS meeting for regional harmonization of Customs Harmonized Code regarding regulation of HFC imports/exports, in Bissau, December 2019. | In January -March 2020 Togo NOO participated in many exchanges that lead to the recrutment of an International Consultant and a Draft proposal for the extension of the subheadings 2903.39 and 3824.78 of the Tariff and Statis-tical Nomenclature (TSN) of the Common External Tariff (CET) of the Economic Community of West African States (ECOWAS) in order to facilitate the collection and comparison of data concerning the circulation of hydrofluorurocarbons (HFC) will be developed and submitted to WCO. Delays due to COVID-19 |  |  | 2020-06-01 | 60000 | 4200
COM | UNEP | Enabling activities for HFC phase-down |  | ASP | TON | SEV | 80 | TAS | 02+ | A | I | HFC | 0 |  | 2017-11-01 | 2018-07-01 | 2019-06-01 |  | 2019-06-01 |  | 50000 | 0 | 50000 | 43744.61 | 87.49% | 6255.39 | 4950 | 1255.39 | 3500 | 0 | 3062.1227 | 437.8773 | 346.5 | The SSFA was signed in July 2018. First transfer of funds in July 2018. The second payment has been released to the country 28 June 2019. Two concluding stakeholders workshops held in Vavau on 7 June and in Tongatapu on 20 June 2019. Country Assessment Report completed. The draft Ozone Layer Protection (Amendment) Act 2019 completed and finalized at country level. The document was ready for approval. One workshop for Custom Officers on Risk Profiling for HFCs was delivered on 25-26 July 2019. Training workshop on handling R-32 and R-600a systems was delivered on 27-28 June 2019. NOU worked with other Pacific Island Countries’ NOUs to jointly develop and submit the joint proposal to Oceania Customs Organization (OCO) for the amendment of the HS code under the Pacific Harmonized Commodity Description and Coding System 2017 (PACHS17) to assign specific HS code for HFCs and blends in accordance with WCO recommendation. The proposal for amendment was approved by the Review Committee in September 2019. Project completed in 2019. The project final report submitted to the MLFS in November 2019. The final payment has been released to the country 3 December 2019. Status of KA ratification, ratified on 17 September 2018. | Project completed. |  |  |  | 0 | 0
ONG | UNDP | Enabling activities for HFC phase-down | Individual | LAC | TRI | SEV | 80 | TAS | 01+ | N | I | No_ODP | 0 | 0 | 2017-11-01 | 2018-06-01 | 2019-06-01 | 2020-06-01 |  |  | 150000 | 0 | 150000 | 42371 | 28.25% | 107629 | 23064.03 | 32288.763 | 10500 | 0 | 2965.9553 | 7534.0447 | 1614.4821 | Trinidad and Tobago ratified the Kigali Amendment. HFC licensing & quota system: Recruitment of a Legal Consultant to assist in the development of a Framework to support Licensing and Certification of Refrigeration & Air-Conditioning Technicians in Trinidad & Tobago under the Kigali Amendment (ongoing). HFC data collection and monitoring: Performed in 2019. Including costs associated to HFC phaseout, per sector, particularly those associated to the handling of alternatives. Demonstrations: District cooling projects under implementation. Exchange missions and study tours on low-GWP alternatives. An extension for an additional six months has been requested due to COVID-19. | Development of Cost analysis of HFC phasedown per sector performed. |  |  | 2020-06-01
ONG | UNEP | Enabling activities for HFC phase-down |  | ASP | TTR | SEV | 80 | TAS | 01+ | A | I | HFC | 0 |  | 2017-11-01 | 2018-07-01 | 2019-06-01 | 2020-12-01 |  |  | 50000 | 0 | 50000 | 21000 | 42% | 29000 | 29000 | 8787.8788 | 3500 | 0 | 1470 | 2030 | 2030 | The SSFA was signed in June 2018. First transfer of funds in July 2018. Data collection completed. One RAC training on flammable refrigerants conducted in November 2019. NOU worked with the Customs Department and stakeholders to conduct review the existing licensing and quota system as well as reporting. NOU amended the existing Ozone Layer Protection Regulations to include HFC quota and licensing system. One public hearing on the draft amendment was organised. The Amendment was finalized under process for approval. NOU initiated outreach by introducing it to the general public through community meetings, radio talk shows and local newspaper advertisements. Brochures and flyers were published and distributed locally to promote low-GWP technologies, their benefits, and special attention on safety measures. NOU worked with other Pacific Island Countries’ NOUs to jointly develop and submit the joint proposal to Oceania Customs Organization (OCO) for the amendment of the HS code under the Pacific Harmonized Commodity Description and Coding System 2017 (PACHS17) to assign specific HS code for HFCs and blends in accordance with WCO recommendation. The proposal for amendment was approved by the Review Committee in September 2019. Status of KA ratification, ratified on 29 August 2017. | Country Assessment Report drafting was initiated by the consultant and need further revision. The NOU is taking responsibility on the finalziation of the CAR and following up on its completion. NOU is following up with customs on revised PACHS17 HS code adoption. |  |  | 2020-06-01 | 4000 | 280
ONG | Italy | Enabling activities for HFC phase-down | Individual | AFR | TUN | SEV | 80 | TAS | 01+ | A | I | HFC | 0 | 0 | 2017-11-01 | 2019-01-01 | 2019-06-01 | 2020-12-31 |  |  | 75000 | 0 | 75000 | 15768 | 21.02% | 59232 | 8676 | 46000 | 5250 | 0 | 1104 | 4146 | 607 | The ratification process is progressing and under the consultation to ministries. The update of the electronic data reporting system for imports of refrigerants is almost finalized. Awareness raising sessions took place and four reports have been drafted, focusing on codes and standards, technical and economic implications of the HFCs phase-down, regulatory and institutional framework for the implementation of the Kigali amendment, and a specific assessment on the capacities and needs of the servicing sector. | Was there any delay during the reporting year? No. Any recurring problem? No. Any impact on project completion date: No. Any action required by Executive Committee? No. |  |  | 2020-06-01
ONG | UNIDO | Enabling activities for HFC phase-down |  | AFR | TUN | SEV | 80 | TAS | 02+ | A | I |  | 0 | 0 | 2017-11-01 | 2018-03-01 | 2019-06-01 | 2020-12-30 |  |  | 75000 | 0 | 75000 | 26704.58 | 35.61% | 48295.42 | 1865.53 | 46000 | 5250 | 0 | 1869.3206 | 3380.6794 | 130.5871 | The ratification process is progressing and under the consultation to ministries. The update of the electronic data reporting system for imports of refrigerants is almost finalized. Awareness raising sessions took place and four reports have been drafted, focusing on codes and standards, technical and economic implications of the HFCs phase-down, regulatory and institutional framework for the implementation of the Kigali amendment, and a specific assessment on the capacities and needs of the servicing sector. Was there any delay during the reporting year? No. Any recurring problem? No. Any impact on project completion date: No. Any action required by Executive Committee? No. | The final report and stakeholder input and validation was planned for April and had to be cancelled, due to Corona pandemic. Updated work plan for the finalization steps is currently under discussion. Activities for promoting energy efficiency have been completed. This mainly included consumers awareness raising on energy efficiency improvement options for refrigeration and air-conditioning devices through several public events and publication distribution. Was there any delay during the reporting year? Yes, some activities had to be postponed due to the covid-19 pandemic. Any recurring problem? No. Any impact on project completion date: Yes. Any action required by Executive Committee? - Yes. The ExCom has already allowed implementing agencies at the 85th meeting to continue implementing the time-sensitive HFC related project. |  |  | 2020-06-01
ONG | UNIDO | Enabling activities for HFC phase-down |  | EUR | TUR | SEV | 80 | TAS | 01+ | A | I |  | 0 | 0 | 2017-11-01 | 2018-04-01 | 2019-06-01 | 2021-06-01 |  |  | 250000 | 0 | 250000 | 161083.39 | 64.43% | 88916.61 | 419.74 | 87000 | 17500 | 0 | 11275.8373 | 6224.1627 | 29.3818 | Kigali ratification is due for Parliament approval, being endorsed by relevant stakeholders in 2019. HFC data’s on export and import are already collecting from the Ministry of Trade annually for UNFCCC reporting, indeed an online monitoring system for HFCs are under development and it has been expected to be finalized by the end of 2020. Activities for HFC licensing and quota system have been initiated, but not completed yet. It is expected that they will be finalized by the end of 2020. NOU turkey has conducted 4 particular workshop for the purpose of raising awareness on obligations under Kigali amendment and strengthening institutional arrangements for the early ratification of the Kigali Amendment. The gaps and legal requirements have been detected and NOU Turkey is working on legal basis with public and sectoral stakeholders. Obligations of licensing system and specifications of custom codes of HFCs are studied with the Ministry of Trade closely and an official communiqué on licensing will be published at the end of 2020. Sectoral workshops took place in 2019, back to back with the EU F-gas Project. A workshop on energy efficiency, with the aim of starting a discussion on the potential available low GWP non HFC technologies in the cooling sector, the issue of energy efficiency under the Kigali Amendment as well as the necessary safety and standards while phasing-down HFCs under the Amendment; all the while, allowing for a platform for participants to elaborate on constructive modalities towards effective implementation in Turkey has been organized in Antalya between 16-18 September 2019. A focal point appointed from the Ministry of Energy, thus NOU is planning to coordinate trainings on energy efficient operation of RAC equipment and energy savings among natural refrigerants within national institutions. New legislation for HFCs certification was drafted and submitted for consideration. | Field workshops and Study tour could not take place due to COVID restrictions. All other activities were implemented in line with the work plan. As soon as conditions allow, the remaining activities will be organized. |  |  | 2020-06-01
ONG | UNEP | Enabling activities for HFC phase-down |  | ASP | TUV | SEV | 81 | TAS | 01+ | A | I | HFC | 0 |  | 2018-06-01 |  | 2020-01-01 | 2021-01-01 |  |  | 50000 | 0 | 50000 | 0 | 0% | 50000 | 35000 | 15151.5152 | 3500 | 0 | 0 | 3500 | 2450 | SSFA was signed in February 2019. First transfer of funds in February 2019. One stakeholders workshops done in September 2019. Data collection for preparation of Country Assessment Report completed. NOU worked with other Pacific Island Countries’ NOUs to jointly develop and submit the joint proposal to Oceania Customs Organization (OCO) for the amendment of the HS code under the Pacific Harmonized Commodity Description and Coding System 2017 (PACHS17) to assign specific HS code for HFCs and blends in accordance with WCO recommendation. The proposal for amendment was approved by the Review Committee in September 2019. Revised PACHS17 HS code that assigns specific HS code for HFCs and blends adopted by Customs. NOU produced local awareness materials (poster) and is currently adapting further OzonAction materials for awareness rising campaign. Status of KA ratification, ratified on 21 September 2017. | Country Assessment Report drafting ongoing. A local legal consultant is working on the amendment of the regulation to provide for HFC licensing. NOU postponed RAC technicians training for Q3/4 as possible. |  |  | 2021-01-01 | 15000 | 1050
ONG | UNEP | Enabling activities for HFC phase-down |  | AFR | UGA | SEV | 81 | TAS | 01+ | A | I | HFC | 0 |  | 2018-06-01 | 2019-10-01 | 2020-01-01 | 2021-01-01 |  |  | 50000 | 0 | 50000 | 3753.04 | 7.506% | 46246.96 | 45000 | 14014.2303 | 3500 | 0 | 262.7128 | 3237.2872 | 3150 | The SSFA was signed by country in August 2019 with a total amount of USD 50,000. The first payment was released to the country in October, 2019. Kigali Amendment was ratified in June, 2018. Training needs assessment was undertaken prior to the conduct of four training workshops in good refrigeration practices including handling of HFCs and aspects of energy efficiency were also incorporated in the training. This is undertaken for Vocational Training Colleges (VTCs). Curricula have been streamlined in theses VTCs to include RAC aspects, and this a significant achievement. There is still some ascertained about alternatives to HFCs as presently the consumers are still hustling with phasing out the use of HCFCs. More awareness is needed to somehow allay fears of consumers of HCFCs and HFCs, among others. One lesson learnt is that it is a vital thing to reassure the consumers of restricted substances in terms of available and affordable alternatives and related technologies. | Initial efforts to introduce energy efficiency aspects have been undertaken; notably during RAC training workshops undertaken in four VTCs and during designing of the project / manufacturing plant by a Ugandan entrepreneur who intends to produce Hydrocarbons (HC-600a) based refrigeration equipment. The latter is being supported by Ministry of Energy and Mineral Development (responsible for minimum performance standards) and Uganda National Bureau of Standards (responsible for quality control). Delays in some projects activities are to be expected due to measures taken by the country related to Coronavirus outbreak, which resulted for example in postponing all meetings/ events planned in the first half of the year. |  |  | 2021-01-01 | 20000 | 1400
ONG | UNEP | Enabling activities for HFC phase-down |  | AFR | URT | SEV | 81 | TAS | 01+ | A | I | HFC | 0 |  | 2018-06-01 | 2018-12-01 | 2020-01-01 | 2021-01-01 |  |  | 95000 | 0 | 95000 | 56155 | 59.11% | 38845 | 35000 | 11771.2121 | 6650 | 0 | 3930.85 | 2719.15 | 2450 | The SSFA was signed by country in December 2018 with a total amount of USD 95,000. The second payment was released to the country in August, 2019. Tanzania has ratified the Kigali Amendment and is in the final stages of depositing instrument of ratification; currently the Environmental Management (Control of ozone Depleting Substances) Regulations of 2007 have been reviewed to incorporate the Kigali amendment including HFC licensing and quota system and is waiting for adoption; Consultative meeting with the RAC importers and distributors on the HFC licensing and quota system have been conducted; and RAC technicians have been trained on safe handling of HFCs and their alternatives. Overall assessment of project progress is satisfactory. | The revision of the national ODS and climate legislation was completed on 8th April, 2020 and changes are drafted to allow for HFC phase- down (list of controlled HFCs, licensing system, reporting requirements). Tanzania have been conducting training on energy efficient operation of RAC equipment to various relevant stakeholders and capacity building of various national institutions so as to enhance energy efficiency in the refrigeration and air-conditioning and heat pump sectors while phasing down HFCs as required by the Kigali amendment. Training needs assessment for the servicing sector was finalized in January, 2020. Delays in some projects activities are to be expected due to measures taken by the country related to Coronavirus outbreak, which resulted for example in postponing all meetings/ events planned in the first half of the year. |  |  | 2021-01-01 | 30000 | 2100
ONG | UNIDO | Enabling activities for HFC phase-down |  | LAC | URU | SEV | 80 | TAS | 01+ | A | I |  | 0 | 0 | 2017-11-01 | 2018-04-01 | 2019-06-01 | 2021-06-01 |  |  | 50000 | 0 | 50000 | 43291.65 | 86.58% | 6708.35 | 997.78 | 5710.57 | 3500 | 0 | 3030.4155 | 469.5845 | 69.8446 | Remarks (Specify milestone achieved, remedial actions, and issues of relevance to ExCom) for year 2019 '• Ratification of Kigali amendment: Yes (2018-09-12) • Status of implementation: activities initiated and in progress • Activities implemented: HFC licensing and quota system, data collection and monitoring system, and demonstration of non-investment activities and preliminary capacity building requirements for the implementation of the Kigali Amendment and its related matters (under UNIDO component). • Milestones achieved: .-Work Plan Agreed with NOU: Yes; .- UNIDO awareness-raising workshop organized: Yes - organized in June 2019, named "Kigali in Action" and the NOU participated in the workshop. .- Deliverables and results reported: a) Enforced licensing and quota system: Yes (no quota system enforced) b) The Licensing system updated and other activities related to the management of HFC imports in customs were developed in the country. c) HFC consumption updated with additional data required to improve the HFC inventory in Uruguay. Detailed info/analysis to update the national GHG emissions inventory was conducted (considering IPPCC methodology) and including all the sectors using HFC d) Comprehensive proposal on tariff codes for HFC control (pure and blends) e) Customs and enforcement officers were trained on obligations under the Kigali Amendment, including the revised import/export licensing systems. f) Training and technical assistance on data management of HFC imports, customs control, and other related to data collection, reporting, and monitoring system. g) National Workshop on Kigali Amendment; workshop on prevention and response to illegal traffic of ODS and f-gases. •Overall assessment of project progress: The majority of the planned activities were implemented and according to the approved UNIDO’s activities in the project for the reported period. •Impact of these activities: awareness activities and discussions were conducted with the main stakeholders involved in the HFC control in Uruguay (NOU and custom authorities). The country's HFC data reporting was improved through the updated licensing system. The GHG inventory was updated to include detailed information on HFCs. The training prepared under the EA project represents a tool for capacity building for the main institutions involved in the control and reporting of HFCs phase-down. • Potential challenges in completing the projects and activities: a dedicated training was planned in March 2020 for NOU and stakeholders involved in the monitoring and control of HFCs and adopting low GWP alternatives in Uruguay. It is expected that the last action with the participation of two international experts under the UNIDO component can progress as expected. • Key findings and lessons learned: training developed in the project allowed the NOU to identify potential actions at the regulation level, particularly on custom areas as risk management, tariff classification, and control in the field, recommendations to current customs procedures. | '• Status of implementation: project ongoing • Activities implemented (to be executed): Demonstration of non-investment activity and preliminary capacity building requirements for the implementation of the Kigali Amendment and its related matters (under UNIDO component). Technical training with international experts on HFCs control and the application of climate-friendly technologies and their regulations in relevant sectors considering improvements on the energy efficiency of RAC systems with low-GWP. • Milestones achieved: - Work Plan Agreed with NOU was updated - Specific deliverables and results reported: a) Demonstration of non-investment activities in the UNIDO component (training): specialized training for the NOU and stakeholders involved in the monitoring and control of HFCs and promoting/adopting low GWP alternatives in Uruguay was planned for March 2020. The objective of the training is to promote the adoption of low GWP alternatives and energy efficiency technologies in Uruguay and share lessons learned and experiences on the application of climate-friendly technologies and their regulations in relevant sectors. The activity is postponed until the travel restrictions due to Covid-19 are revoked • Overall assessment of project progress: The majority of the planned activities were implemented and according to the approved UNIDO’s activities in the project. Only one action (technical training with international experts) is postponed due to the Covid-19 pandemic situation. • Activities planned for the second part of 2020: The training will be rearranged to virtual in the applicable sessions. The site visits are postponed until there is guidance on international travel • Potential challenges in completing the projects and activities: Based on the decision taken by UNIDO management to restrict official travel due to the ongoing outbreak of COVID-19 immediately and until further notice. The schedule of the remaining activity needs to be updated • Any action required by the Executive Committee? Yes . In line with 85th meeting (intersessional) the project shall continue and UNIDO shall report on progress at the 86th meeting |  |  | 2020-06-01
ONG | UNDP | Enabling activities for HFC phase-down | Individual | LAC | URU | SEV | 80 | TAS | 02+ | N | I | No_ODP | 0 | 0 | 2017-11-01 | 2018-09-01 | 2019-06-01 | 2020-06-01 |  |  | 100000 | 0 | 100000 | 55402 | 55.4% | 44598 | 0 | 13379.445 | 7000 | 0 | 3878.1295 | 3121.8705 | 0 | Participation in workshops in New York, USA and San Jose, Costa Rica, to discuss the implementation of the Kigali Amendment. National team established. Meetings with national stakeholders to rise awareness on the implementation of the Kigali Amendment. Visist of an international expert to meet with customs authorities for reviewing customs procedures for import and export of HFC. Review of exisiting legal framework to identify gaps and opportunities to control HFC consumption. An extension for an additional six months has been requested due to COVID-19. | Road map for the implementation of the Kigali Amendment under development, meetings with stakeholders conducted. Since the start of the COVID-19 pandemic in mid-March, meetings have been held from distance. |  |  | 2020-06-01
ONG | UNEP | Enabling activities for HFC phase-down |  | ASP | VAN | SEV | 81 | TAS | 01+ | A | I | HFC | 0 |  | 2018-06-01 | 2018-12-01 | 2020-01-01 | 2021-01-01 |  |  | 50000 | 0 | 50000 | 26079.76 | 52.16% | 23920.24 | 22979.46 | 7248.5576 | 3500 | 0 | 1825.5832 | 1674.4168 | 1608.5622 | SSFA was signed in November 2018. First transfer of funds in December 2018. The second payment has been released to the country 7 October 2019. NOU recruited one consultant to support EA implementation. Two workshops done in November 2019, one in Port Vila, one in Santo. One workshop to finalize the draft amendment done. The Ozone Layer Protection Act has been amended to control HFCs as per the Kigali Amendment and the NOU was awaiting endorsement by Parliament. NOU worked with other Pacific Island Countries’ NOUs to jointly develop and submit the joint proposal to Oceania Customs Organization (OCO) for the amendment of the HS code under the Pacific Harmonized Commodity Description and Coding System 2017 (PACHS17) to assign specific HS code for HFCs and blends in accordance with WCO recommendation. The proposal for amendment was approved by the Review Committee in September 2019. Status of KA ratification, ratified on 20 April 2018. | Draft amendment bill to Ozone Layer Protection (OLP) Act to include HFC, HFC-based equipment and permit of RAC technicians was finalized and has been approved by the Parliament. The Ozone Later Protection Act (Amendment) 2020 was gazetted in February 2020 with 3 months grace period. Country is developing national window system (NSW) under the World Bank Project, NOU has discussed with the customs and it was agreed that ODS and HFC control will be integrated in NWS. As a result, there will be no need to develop a separate online HFC licensing system. Two workshops with custom brokers done in February, one in Santo and one in Vila. One training on low GWP doin in february in Santo. Adaptation of UNEP outreach materials ongoing. |  |  | 2021-01-01 | 14215 | 995.05
ONG | UNIDO | Enabling activities for HFC phase-down |  | LAC | VEN | SEV | 81 | TAS | 01+ | A | I |  | 0 | 0 | 2018-06-01 | 2018-10-01 | 2020-01-01 | 2021-01-31 |  |  | 250000 | 0 | 250000 | 84869.77 | 33.95% | 165130.23 | 295.41 | 85000 | 17500 | 0 | 5940.8839 | 11559.1161 | 20.6787 | • Ratification of Kigali amendment: No • Activities implemented: Support for the early ratification of the Kigali Amendment; Activities aimed at initiating institutional support agreements and arrangements; HFC licensing system, and data collection and monitoring system; and demonstration of non-investment activities and preliminary capacity building requirements for the implementation of Kigali. • Milestones achieved: -Work Plan Agreed with NOU: Yes; - UNIDO awareness-raising workshop organized: Yes - organized in June 2019, named "Kigali in Action" and the NOU participated in the workshop. - Deliverables and results reported: a) Enforced licensing and quota system: Yes (no quota system enforced); b) Licensing system on revision and other activities related to the management of HFC imports in customs were developed in the country; c) 80% progress in the updating process of HFCs consumption data from 2016 to 2019 (monitoring system); d) Initial review on tariff codes for HFC control (pure and blends) and regulation; e) Training and technical assistance on data management of HFC imports, customs control, and other related to data collection, reporting and monitoring system; f) Assessment of institutional framework in Venezuela for the implementation and compliance of the Kigali Amendment. • Overall assessment of project progress: The majority of the planned activities were implemented and according to the approved UNIDO’s activities in the project for the reported period. • Impact of these activities: Significant awareness activities and discussions were conducted with the main institutions involved in the HFC control in Venezuela (NOU, Ministry of Environment and custom authorities). Project is allowing the NOU to automatize the licensing system. The trainings and meetings conduced under the EA project represented a powerful tool to capacity building in the main institutions involved in the control and reporting of HFCs phase-down. • Potential challenges in completing the projects and activities: some delays due to country context difficulties. • Key findings and lessons learned: training developed in the project allowed the NOU to identify potential actions in regulatory and institutional framework. | • Activities implemented (to be implemented): Support for the early ratification of the Kigali Amendment; Activities aimed at initiating institutional support agreements and arrangements; HFC licensing system, and data collection and monitoring system; and demonstration of non-investment activities and preliminary capacity building requirements for the implementation of Kigali. • Milestones achieved: - Work Plan Agreed with NOU was updated - Specific deliverables and results reported: a) Assessment developed to identify and analyze the existing legal and relevant regulatory framework in Venezuela for the implementation and compliance of the Kigali Amendment; b) Customs and enforcement officers were trained on obligations under the Kigali Amendment, including the revised import/export licensing systems; c) Proposal of regulation to regulate and control the consumption, production, import, export and use of halogenated substances that deplete the ozone layer or cause atmospheric heating (to include HFC control). • Overall assessment of project progress: The majority of the planned activities were implemented and according to the approved UNIDO’s activities in the project. Some actions (technical training with international experts, institutional consultations and other) were postponed due to the Covid-19 pandemic situation. • Activities planned for the second part of 2020: Workshop on alternative substances to HFCs, barriers and opportunities and energy efficiency” have been suspended until the prevailing circumstances are defined after the quarantine is lifted or removed. • Potential challenges in completing the projects and activities: Based on the decision taken by UNIDO management to restrict official travel due to the ongoing outbreak of COVID-19 immediately and until further notice. The schedule of the remaining activity needs to be updated. • Any action required by Executive Committee Yes Considering the uncertain global situation due to COVID-19, it is required a decision on the possible extension of the EA project. |  |  | 2021-01-01
COM | UNIDO | Enabling activities for HFC phase-down |  | ASP | VIE | SEV | 80 | TAS | 01+ | A | I |  | 0 | 0 | 2017-11-01 | 2018-01-01 | 2019-06-01 |  | 2019-06-01 |  | 250000 | 0 | 250000 | 249182.5 | 99.67% | 817.5 | 0 | 1 | 17500 | 0 | 17442.775 | 57.225 | 0 | All activities have been completed as planned by June 2019. A country roadmap to phase down including scenarios per sector has been developed. Key findings include: (1) Focus on dissemination of information and raising awareness about the HFC phase-out roadmap for producers, consumers and stakeholders to recognize and agree on the phase out schedules of HFCs. (2) Forbid to produce and import refrigeration equipment using HFCs in the domestic sector which has alternative technologies fully available at commercial size. (3) Develop a National Plan for Phase down Management of HFCs to approach and maximize the technical and financial supports from MLF. | Activities were completed by June 2019. Financial closure is being processed.
ONG | UNIDO | Enabling activities for HFC phase-down |  | EUR | YUG | SEV | 80 | TAS | 01+ | A | I |  | 0 | 0 | 2017-11-01 | 2018-03-01 | 2019-06-01 | 2020-12-31 |  |  | 150000 | 0 | 150000 | 83637.34 | 55.76% | 66362.66 | 1018.91 | 52000 | 10500 | 0 | 5854.6138 | 4645.3862 | 71.3237 | National actions continue to accelerate the process of ratification of the Kigali amendment. Import/export licensing system was reviewed and updated; Quota system is not mandatory, but it is drafted in the proposal of the new national F-gas Regulation; Assessment developed on “Institutional Framework of Kigali Implementation in the country” was conducted; Main regulation to control ODS consumption, import and use was updated including HFC was prepared with the main stakeholders; The manual for custom officer was updated and workshop with national customs were conducted. All new regulations and customs codes are included. Was there any delay during the reporting year? - NO Any recurring problem? No Any impact on project completion date? - NO Any action required by Executive Committee? - NO | Initially planned parliamentary elections were postponed due to the covid-19 pandemic. Elections were organized in June. The Kigali Amendment needs to be ratified by the Parliament. Activities continue with slowdown due to Covid19. Workshop is planned to be organized for service shops before the end of Enabling activities. The promotion of energy efficiency will be covered with the workshop, as well as GWP refrigerant use in servicing sector. Was there any delay during the reporting year? - YES. Some activities could not be implemented as planned because of the restriction measures due to the Covid-19 pandemic. Any recurring problem? - No Any impact on project completion date? - YES Any action required by Executive Committee? - New decision has been granted, allowing implementing agencies to continue with the project implementation beyond the project end date as per decision. |  |  | 2020-06-01
ONG | UNEP | Enabling activities for HFC phase-down |  | AFR | ZAM | SEV | 80 | TAS | 01+ | A | I | HFC | 0 |  | 2017-11-01 | 2018-09-01 | 2019-06-01 | 2020-12-01 |  |  | 95000 | 0 | 95000 | 64204 | 67.58% | 30796 | 25000 | 9332.1212 | 6650 | 0 | 4494.28 | 2155.72 | 1750 | The second payment for SSFA of the amount of USD 95,000 was released to the country in December 2019. Kigali amendment was approved by the Cabinet in Dec 2019 for ratification by Parliament. Stakeholder meetings on the Kigali Amendment and HFCs Phase down conducted; training of customs officers to control HFCs conducted; training of refrigeration technicians on low GWP refrigerants conducted. The process is underway to review the ODS legislation to include licensing and quota system for HFCs. A checklist with HFCs has been developed to be integrated in licensing system. An electronic system being developed to assist in the database as a reporting tool for the controlled substance. Overall assessment of project progress is satisfactory. | Translation into the national language of Kigali amendment is still in progress since January 2020. The National Licensing system is in progress the Zambia Environmental Management Agency (ZEMA), and the development of the licensing system is being tested and the HS codes for the establishment of the database to assist in reporting. The integrated licensing system in the electronic system at ZEMA is in an advanced stage to include ODS and HFCs and will assist in the database as a reporting tool for the controlled substance. Conducted two trainings on energy efficient operations of RAC equipment. The capacity building of the RAC training centers enhanced. Delays in some projects activities are to be expected due to measures taken by the country related to Coronavirus outbreak, which resulted for example in postponing all meetings/ events planned in the first half of the year. |  |  | 2020-06-01 | 20000 | 1400
COM | UNEP | Enabling activities for HFC phase-down |  | AFR | ZIM | SEV | 80 | TAS | 01+ | A | I | HFC | 0 |  | 2017-11-01 | 2018-07-01 | 2019-06-01 |  | 2019-12-01 |  | 150000 | 0 | 150000 | 85551 | 57.03% | 64449 | 55000 | 64449 | 10500 | 0 | 5988.57 | 4511.43 | 3850 | The second payment for SSFA of the amount of USD 135,000 was released to the country in April 2019. Project is completed and final report is being finalized. ODS Regulations were reviewed to incorporate HFC licensing for imports. Customs Officers are being training to control HFC imports. One Mindset Change Workshop for the RAC sector was conducted at the CHAS Redcliff Hotel in KweKwe from the 18th to 19th September 2019 and was attended by 35 participants from the RAC sector. Participants included importers, wholesalers and distributors of HFCs. A two day consultative meeting was held for Parliamentarians at the Montclair Hotel in Nyanga from the 2nd to the 3rd February 2019. The MPs pledged to support the ratification of the Kigali Amendment once the motion is introduced in Parliament. The parliamentary process documents are now with the Clerk of Parliament and the Minister responsible for Ozone and Climate. The ratification of the Kigali Amendment is at the Parliamentary stage. Overall assessment of project progress is satisfactory. | A motion of the Kigali Amendment ratification has already been drafted by the Legal Office and is awaiting resumption of the sitting of Parliamentarians. Training workshops are being conducted on safe use of low GWP refrigerants such as HCs which are energy efficient. A standard on certification of RAC technicians was published. This standard tests competency of technicians. The NOU is working with the Department of Energy on policy issues on energy efficiency as well as mandatory labelling. MEPS will be adopted. Project is completed and final report has been submitted to MLFS. |  |  | 2019-12-01 | 50000 | 3500
COM | UNDP | Project preparation for elimination of HFC-134a in the manufacture of domestic refrigerators at Capri | Individual | AFR | ZIM | REF | 80 | PRP | 02+ | N | I | No_ODP | 0 | 0 | 2017-11-01 | 2018-02-01 | 2018-12-01 |  | 2019-06-01 |  | 30000 | 0 | 30000 | 12309 | 41.03% | 17691 | 4000 | 17690.74 | 2100 | 0 | 861.6482 | 1238.3518 | 280 | The HFC phase-out project was approved at the 82nd ExCom meeting. Payments were processed to international experts who assisted in the formulation of the programme and the conversion plan.