## DataBase
Status | Agency | Project Title | Multi-Year/Multi-Year Partial Phase-out/One-off Phase-Out/Individual/RMP/RMP Update/RMP for Non-LVC/Halon Banking | Region | Country | Sector | Mtg | Type | Num | A/N | O/T | IRD | Chemical | Consumption ODP to be Phased Out per Proposal | Consumption ODP Phased Out | Production ODP to be Phased Out per Proposal | Production ODP Phased Out | Date Approved | First Disbursment Date | Date of Compl per Proposal | Planned Date of Completion | Date Completed (Actual) | Date of Financial Completion | Approved Funding (US$) | Adjustment (US$) | Approved Funding plus Adjustments (US$) | Funds Disbursed (US$) | Per Cent of Funds Disbursed | Balance (US$) | Funds Obligated (US$) | Estimated Disbursement in Current Year (US$) | Support Cost Approved (US$) | Support Cost Adjustment (US$) | Support Cost Disbursed (US$) | Support Cost Balance (US$) | Support Cost Obligated (US$) | Year Approved | Months from Approval to First Disbursement | Months from Approval to Completionper Proposal | Months from Approval to Planned Completion | Months from Approval to Completion | Remarks (Specify milestone achieved, remedial actions, and issues of relevance to ExCom | Remarks (continued) (for Multi-Year, One-off address provisions of agreement, RMPs; and implementation of conditions of agreements). | Year of Contribution | Com Imp Delay | Sum of AO and AP | ONG or COM AM | ONG or COM AM for CPG,TAS,TRA AND INS | Sum of AO and AP for CPG,TAS,TRA | Correct Code | 22nd Mtg Planned Date of Completion | 28th Mtg Planned Date of Completion | 31st Mtg Planned Date of Completion | 34th Mtg Planned Date of Completion | 37th Mtg Planned Date of Completion | 40th Mtg Planned Date of Completion | 43rd Mtg Planned Date of Completion | Year of Business Plan | Business Plan Allocation (Investment/Non-Investment) | Multi-Year Current Tranche - Consumption Performance Target (ODP Tonnes) | Multi-Year Current Tranche - Actual Consumption (ODP Tonnes) | Multi-Year Current Tranche - Production Performance Target (Odp Tonnes) | Multi-Year Current Tranche - Actual Production (ODP Tonnes) | Multi-Year Current Tranche Confirmation of Annual Performance Target - Annual Target Met as Reported by Country (Yes/No) | Multi-Year Current Tranche Confirmation of Annual Performance Target - Verification Completed (Yes/No) | Multi-Year Current Tranche Confirmation of Annual Performance Target - Verification Report to ExCom (Yes/No)
FIN | IBRD | Preparation of investment projects |  | AFR | ALG | SEV | 12 | PRP | 5 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 100000 | -93039 | 6961 | 6961 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ALG/SEV/12/PRP/5 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of a national CFC phase-out plan |  | LAC | ANT | PHA | 39 | PRP | 8 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2004-09-01 | 2004-09-01 |  | 2004-09-01 | 2004-09-01 | 15000 | 0 | 15000 | 15000 | 100 | 0 | 0 |  | 1125 | 0 | 1125 | 0 | 0 | 2003 | #NAME? | #NAME? | #NAME? | #NAME? | Project prepared, submitted and then approved at the 44th ExCom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ANT/PHA/39/PRP/8 | [7 empty] | 2003 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | CFC phase-out management plan | Multiyear | LAC | ANT | PHA | 44 | INV | 10 | N | O | I | CFC | 2 | 0 | 0 | 0 | 2004-12-01 |  | 2006-12-01 | 2006-12-01 |  |  | 69400 | 0 | 69400 | 0 | 0 | 69400 | 69400 | 10000 | 6246 | 0 | 0 | 6246 | 6246 | 2004 | #NAME? | #NAME? | #NAME? | #NAME? | Newly approved. A WB mission is scheduled for 2005. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ANT/PHA/44/INV/10 | [7 empty] | 2004 | INV | 1.8 | 0 | 0 | 0
COM | IBRD | Conversion from CFC-11, CFC-12, CFC-113 and MCF into HCFC for technical aerosols at Electroquimica Delta | Individual | LAC | ARG | ARS | 36 | INV | 128 | N | O | I | CFC | 60 | 60 | 0 | 0 | 2002-03-01 | 2004-08-01 | 2005-04-01 |  | 2004-12-01 |  | 264000 | 0 | 264000 | 190080 | 72 | 73920 | 73920 | 73920 | 34320 | 0 | 24710.4 | 9609.6 | 9609.6 | 2002 | #NAME? | #NAME? | #NAME? | #NAME? | Project physically completed. Financial completion expected Apr. 05. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ARG/ARS/36/INV/128 | [7 empty] | 2001 | INV | 0 | 0 | 0 | 0
ONG | IBRD | Conversion from CFC-11, CFC-12, CFC-113 and MCF into HCFC for technical aerosols at Servex S.R.L. | Individual | LAC | ARG | ARS | 38 | INV | 131 | N | O | I | CFC | 36.4 | 36.4 | 0 | 0 | 2002-11-01 | 2004-08-01 | 2005-11-01 | 2005-02-01 |  |  | 160160 | 0 | 160160 | 143240 | 89.43 | 16920 | 16920 | 16920 | 20820.8 | 0 | 18621.2 | 2199.6 | 2199.6 | 2002 | #NAME? | #NAME? | #NAME? | #NAME? | Project expected to be physically completed by Feb. 05 and financially completed by Mar. 05. Phaseout achieved. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ARG/ARS/38/INV/131 | [7 empty] | 2002 | INV | 0 | 0 | 0 | 0
ONG | IBRD | Preparation of one investment project in the aerosol filling industry |  | LAC | ARG | ARS | 39 | PRP | 135 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-04-01 |  | 2003-12-01 | 2003-12-01 |  |  | 10000 | 0 | 10000 | 0 | 0 | 10000 | 0 |  | 750 | 0 | 0 | 750 | 0 | 2003 | #NAME? | #NAME? | #NAME? | #NAME? | Full project prep. funds to be returned to the MLF. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ARG/ARS/39/PRP/135 | [7 empty] | 2003 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam in panels for thermal insulation at Arneg Raffo | Individual | LAC | ARG | FOA | 27 | INV | 81 | N | O | I | CFC | 67 | 67 | 0 | 0 | 1999-03-01 | 2001-02-20 | 2001-04-01 |  | 2002-07-01 | 2004-03-01 | 177960 | 0 | 177960 | 177960 | 100 | 0 | 0 |  | 23134.8 | 0 | 23134.8 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ARG/FOA/27/INV/81 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the rigid polyurethane foam sub-sector |  | LAC | ARG | FOA | 30 | PRP | 108 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-12-01 | 2001-06-01 |  | 2000-12-01 | 2000-12-01 | 7000 | 0 | 7000 | 7000 | 100 | 0 | 0 |  | 910 | 0 | 910 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ARG/FOA/30/PRP/108 | [7 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation for methyl bromide (citrus and cotton) demonstration project |  | LAC | ARG | FUM | 25 | PRP | 75 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-03-30 | 1999-08-01 |  | 1999-06-30 | 1999-06-01 | 50000 | 0 | 50000 | 50000 | 100 | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ARG/FUM/25/PRP/75 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Demonstration project for testing methyl bromide alternatives in post-harvest disinfestation for cotton and citrus (phase I) | Individual | LAC | ARG | FUM | 29 | DEM | 93 | N | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2004-08-01 | 2001-12-01 | 2006-07-01 |  |  | 375000 | 0 | 375000 | 110509 | 29.46 | 264491 | 264491 | 110509 | 48750 | 0 | 14366.17 | 34383.83 | 34383.83 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Project under full implementation and funds are being disbursed accordingly. First tests on alternatives conducted Oct.-Dec. 04 and will continue into Jan. 05. Most required equipment procured and received by INTA. First draft results expected to be produced Feb. 05. First round of results expected to be presented May 05. Timeframe for project implementation is based upon season for each crop. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ARG/FUM/29/DEM/93 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of an investment project in methyl bromide sector |  | LAC | ARG | FUM | 30 | PRP | 100 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2001-12-01 |  | 2001-12-01 | 2001-12-01 | 10000 | 0 | 10000 | 10000 | 100 | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ARG/FUM/30/PRP/100 | [7 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | National halon management programme to help eliminate the use of halon-1301 in new applications and to manage recovered halon-1301 | Individual | LAC | ARG | HAL | 26 | TAS | 80 | N | O | I | HAL | 200 | 0 | 0 | 0 | 1998-11-01 | 2002-02-01 | 2000-12-01 | 2005-05-01 |  |  | 290620 | 0 | 290620 | 136899.54 | 47.1 | 153720.46 | 153720.46 | 40000 | 37780.6 | 0 | 17796.94 | 19983.66 | 19983.66 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | All civil works completed. Portable gas chromatographs and R&R equipment are at INTI. Two additional courses are slated for early 2005. System is currently receiving halon but activities for R&R have not started yet. Legislation is in place and software designed to manage the bank is being discussed between government agencies. Halon bank expected to be fully operational May 05, once 2nd piece of R&R equipment is delivered. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | ARG/HAL/26/TAS/80 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation for the CFC production sector |  | LAC | ARG | PRO | 31 | PRP | 112 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-07-01 | 2000-03-31 | 2001-01-01 |  | 2000-12-01 | 2000-12-01 | 40000 | 0 | 40000 | 40000 | 100 | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ARG/PRO/31/PRP/112 | [7 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
COM | IBRD | CFC production closure plan (first tranche) | Multiyear | LAC | ARG | PRO | 38 | INV | 133 | N | O | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2004-12-01 | 2003-12-01 |  | 2003-12-01 |  | 500000 | 0 | 500000 | 53548 | 10.7 | 446452 | 446452 | 190000 | 20000 | 0 | 2141.92 | 17858.08 | 17858.08 | 2002 | #NAME? | #NAME? | #NAME? | #NAME? | Country has met its obligations under the annual plan. SGA signed in Nov 04 between FIASA and GoA. CFC production audit will be reviewed by the ExCom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ARG/PRO/38/INV/133 | [7 empty] | 2002 | INV | 0 | 0 | 3020 | 3018 | Yes | Yes | Yes
ONG | IBRD | Strategy for gradual phase-out of CFC-11 and CFC-12 production: 2004 annual programme | Multiyear | LAC | ARG | PRO | 44 | INV | 141 | N | O | I | CFC | 0 | 0 | 1373 | 0 | 2004-12-01 | 2004-12-01 | 2005-12-01 | 2005-12-01 |  |  | 3500000 | 0 | 3500000 | 1012000 | 28.91 | 2488000 | 2488000 | 2488000 | 200000 | 0 | 57828.57 | 142171.43 | 142171.43 | 2004 | #NAME? | #NAME? | #NAME? | #NAME? | Project is being implemented and production targts were met for 2002, 2003 and 2004. Audit report on 2004 results will be reviewed by the 45th Excom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ARG/PRO/44/INV/141 | [7 empty] | 2003 | INV | 0 | 0 | 3020 | 3016 | Yes | Yes | Yes
FIN | IBRD | Conversion to non-CFC technology in the production of heat exchangers for mobile air conditioning at Interclima, S.A. | Individual | LAC | ARG | REF | 15 | INV | 15 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1994-12-01 | 1997-07-01 | 1995-12-01 |  | 1999-06-01 | 1999-11-01 | 1983430 | -314039 | 1669391 | 1669391 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Completed. PCR was sent to ExCom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ARG/REF/15/INV/15 | 1997-07-01 | 1999-08-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to non-CFC technology in the production of condensers for mobile air conditioning at Simon Cachan, S.A. | Individual | LAC | ARG | REF | 15 | INV | 16 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1994-12-01 | 1997-09-01 | 1995-12-01 |  | 2001-01-01 | 2002-03-01 | 2738217 | -459396 | 2278821 | 2278821 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ARG/REF/15/INV/16 | 1997-07-01 | 1999-11-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to non-CFC technology in the production of complete mobile air conditioning systems at Mirgor, S.A. | Individual | LAC | ARG | REF | 15 | INV | 17 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1994-12-01 | 1999-06-01 | 1995-12-01 |  | 1999-06-01 | 1999-06-01 | 35632 | -4082 | 31550 | 31550 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Completed |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ARG/REF/15/INV/17 | 1997-07-01 | 1999-08-01 | [6 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of ODP in the production of household refrigerators at the Fribe La Rioja Plant | Individual | LAC | ARG | REF | 15 | INV | 18 | N | O | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1999-03-01 | 1997-06-01 |  |  | 1999-03-01 | 1488127 | -1444783 | 43344 | 43344 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Project cancelled due to bankruptcy. Funds returned at 27th meeting. |  |  | #NAME? | 0 | 0 | 0 | 0 | ARG/REF/15/INV/18 | 1999-03-01 | 1997-06-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC in two manufacturing plants of domestic refrigerators at Helametal S.A., and Helametal Catamarca S.A. | Individual | LAC | ARG | REF | 15 | INV | 19 | N | O | I | CFC | 62 | 62 | 0 | 0 | 1994-12-01 | 1997-09-01 | 1996-12-01 |  | 2003-10-01 | 2004-07-01 | 2959085 | -59591.29 | 2899493.71 | 2899493.71 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ARG/REF/15/INV/19 | 1999-03-01 | 1999-12-01 | [6 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of ODS in the production of domestic refrigerators in the Fribe, S.A. plant | Individual | LAC | ARG | REF | 15 | INV | 20 | N | O | I |  | 0 | 0 | 0 | 0 | 1994-12-01 | 1999-03-01 | 1997-06-01 |  |  | 1999-03-01 | 1822750 | -1769660 | 53090 | 53090 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Project cancelled due to bankruptcy. Funds returned to 27th meeting. |  |  | #NAME? | 0 | 0 | 0 | 0 | ARG/REF/15/INV/20 | 1999-03-01 | 1997-06-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC in the domestic refrigerator manufacturing plant of McLean | Individual | LAC | ARG | REF | 15 | INV | 21 | N | O | I | CFC | 74 | 74 | 0 | 0 | 1994-12-01 | 1998-02-01 | 1996-12-01 |  | 2001-01-01 | 2001-05-01 | 2440570 | -1567990 | 872580 | 872580 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | All pending payments were effected by May 2001. The project is complete and the PCR has been submitted to EXCOM. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ARG/REF/15/INV/21 | 1999-03-01 | 2000-03-01 | [6 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of CFCs in domestic refrigerator production plants in Aurora S.A. | Individual | LAC | ARG | REF | 18 | INV | 35 | N | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1997-11-01 |  |  | 2000-12-01 | 567590 | -567590 | 0 | 0 | 0 | 0 | 0 |  | 73786.7 | -73786.7 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project canceled at the 31st ExCom meeting. Funds returned at 32nd meeting. |  |  | #NAME? | 0 | 0 | 0 | 0 | ARG/REF/18/INV/35 | 1998-05-01 | [7 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of CFCs in 2 domestic refrigerator manufacturing plants at Piragua S.A., and Piragua San Luis | Individual | LAC | ARG | REF | 18 | INV | 36 | N | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1997-11-01 |  |  | 2000-12-01 | 1040264 | -1040264 | 0 | 0 | 0 | 0 | 0 |  | 135234.32 | -135234.32 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project canceled at the 31st ExCom meeting. Funds returned at 32nd meeting. |  |  | #NAME? | 0 | 0 | 0 | 0 | ARG/REF/18/INV/36 | 1998-05-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in domestic refrigerator production plant in Autosal, S.A. | Individual | LAC | ARG | REF | 18 | INV | 37 | N | O | I | CFC | 22 | 22 | 0 | 0 | 1995-11-01 | 1998-11-01 | 1997-11-01 |  | 2003-06-01 | 2004-03-01 | 797390 | 0 | 797390 | 797390 | 100 | 0 | 0 |  | 103660.7 | 0 | 103660.7 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ARG/REF/18/INV/37 | 1998-05-01 | 1999-11-01 |  | 2001-09-01 |  |  |  |  | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacturing plant of domestic refrigerators of Briket, S.A. | Individual | LAC | ARG | REF | 18 | INV | 38 | N | O | I | CFC | 30 | 30 | 0 | 0 | 1995-11-01 | 1998-02-01 | 1997-11-01 |  | 2001-10-01 | 2001-11-08 | 726400 | 0 | 726400 | 726400 | 100 | 0 | 0 |  | 94432 | 0 | 94432 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | The company has been producing without CFCs since Aug. 2001. Destruction of old equipment was completed Oct. 2001. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ARG/REF/18/INV/38 | 1998-05-01 | 1999-10-01 | [6 empty] | INV | 0 | 0 | 0 | 0
ONG | IBRD | Elimination of CFC in the manufacturing plant of domestic refrigerators of Neba, S.A. | Individual | LAC | ARG | REF | 18 | INV | 39 | N | O | I | CFC | 29 | 0 | 0 | 0 | 1995-11-01 | 1999-02-01 | 1997-11-01 | 2006-12-01 |  |  | 686370 | 0 | 686370 | 398318.4 | 58.03 | 288051.6 | 288051.6 | 144025.5 | 89228.1 | 0 | 51781.39 | 37446.71 | 37446.71 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Neba S.A. is again under new ownership and most legal paperwork to finalize process is completed. Progress is linked to negotiations between NEBA and Impianti for equipment delivery date. Situation will be assessed Mar. 05 during a WB mission. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ARG/REF/18/INV/39 | 1998-05-01 | 1999-10-01 |  | 2001-09-01 |  |  |  |  | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to non-CFC technology in the production of mobile air conditioning systems at Sistemaire, S.A. | Individual | LAC | ARG | REF | 18 | INV | 40 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1995-11-01 | 1998-08-01 | 1996-11-01 |  | 2000-09-01 | 2000-12-01 | 2370550 | -1400728 | 969822 | 969822 | 100 | 0 | 0 |  | 308171.5 | -182094.64 | 126076.5 | 0.36 | 0.36 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Completed. PCR submitted to ExCom. Savings returned to 34th ExCom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ARG/REF/18/INV/40 | 1998-05-01 | 1999-08-01 | 2000-11-01 | [5 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of CFC in the manufacturing plant of domestic refrigerators at Adzen S.A. C.I.F. | Individual | LAC | ARG | REF | 19 | INV | 43 | N | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1997-05-01 |  |  | 2003-12-01 | 356970 | -356970 | 0 | 0 | 0 | 0 | 0 |  | 46406 | -41051.45 | 5354.55 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Project cancelled at the 40th ExCom. |  |  | #NAME? | 0 | 0 | 0 | 0 | ARG/REF/19/INV/43 | 1997-11-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacturing plants of domestic refrigerators of Frimetal, Rosario | Individual | LAC | ARG | REF | 19 | INV | 44 | N | O | I | CFC | 89.7 | 89.7 | 0 | 0 | 1996-05-01 | 1998-03-01 | 1998-05-01 |  | 2004-09-01 | 2004-10-01 | 1855000 | 0 | 1855000 | 1855000 | 100 | 0 | 0 |  | 241150 | 0 | 241150 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Project financially and physically completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ARG/REF/19/INV/44 | 1998-11-01 | 2000-01-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in 1 manufacturing plant of domestic refrigerators of enterprise Whirlpool Argentina S.A. | Individual | LAC | ARG | REF | 23 | INV | 68 | N | O | I | CFC | 90.55 | 90.55 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-06-01 |  | 1999-12-01 | 2001-04-26 | 863879 | -99292 | 764587 | 764587 | 100 | 0 | 0 |  | 112304 | -12907.69 | 99396.31 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and funding disbursed. PCR submitted Dec. 01. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ARG/REF/23/INV/68 | [8 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of CFCs in the manufacturing plant of domestic refrigerators at Lobato San Luis S.A. | Individual | LAC | ARG | REF | 23 | INV | 69 | N | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1998-12-01 |  |  | 2002-11-01 | 410683 | -410683 | 0 | 0 | 0 | 0 | 0 |  | 53389 | -47229 | 6160 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Cancelled - 37th ExCom |  |  | #NAME? | 0 | 0 | 0 | 0 | ARG/REF/23/INV/69 | [8 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of CFCs in the manufacturing plants of domestic refrigerators at Gepasa S.A. and Gesal S.R.L. | Individual | LAC | ARG | REF | 23 | INV | 70 | N | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1999-12-01 |  |  | 2000-12-01 | 550400 | -550400 | 0 | 0 | 0 | 0 | 0 |  | 71552 | -71552 | 0 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project cancelled at 31st ExCom. Funds returnd at 32nd ExCom. |  |  | #NAME? | 0 | 0 | 0 | 0 | ARG/REF/23/INV/70 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Substituting CFCs by HCFC-141b and HFC-134a in manufacturing of domestic and commercial refrigerators at El Dorado, S.A. | Individual | LAC | ARG | REF | 25 | INV | 77 | N | O | I | CFC | 12.8 | 12.8 | 0 | 0 | 1998-07-01 | 1999-06-01 | 2000-08-01 |  | 2000-09-01 | 2000-06-01 | 176000 | 0 | 176000 | 176000 | 100 | 0 | 0 |  | 22880 | 0 | 22880 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Completed. PCR has been sent |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ARG/REF/25/INV/77 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the commercial refrigeration sector |  | LAC | ARG | REF | 30 | PRP | 107 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100 | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ARG/REF/30/PRP/107 | [7 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of CFC-11 by HCFC-141b in the manufacture of rigid polyurethane foam for domestic refrigerators and sandwich panels at MTH S.R.L. | Individual | LAC | ARG | REF | 32 | INV | 116 | N | O | I | CFC | 8 | 8 | 0 | 0 | 2000-12-01 | 2001-05-30 | 2002-12-01 |  | 2002-10-01 | 2004-03-01 | 82695 | 0 | 82695 | 82695 | 100 | 0 | 0 |  | 10750.35 | 0 | 10750.35 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ARG/REF/32/INV/116 | [7 empty] | 2000 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation | Individual | LAC | ARG | SEV | 6 | CPG | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 149337 | -59619 | 89718 | 89718 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | ARG/SEV/6/CPG/2 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1993) |  | LAC | ARG | SEV | 9 | PRP | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 63000 | -29084 | 33916 | 33916 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ARG/SEV/9/PRP/3 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | User-sector project identification and preparation (1993) |  | LAC | ARG | SEV | 10 | PRP | 4 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-06-30 | 1994-06-01 |  | 1993-12-01 | 1993-12-01 | 100000 | 65560 | 165560 | 165560 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ARG/SEV/10/PRP/4 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation | Individual | LAC | ARG | SEV | 12 | CPG | 59 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 30000 | 0 | 30000 | 30000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | The Country Program was completed and presented at the 13th E.C. meeting. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | ARG/SEV/12/CPG/59 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects in the refrigeration and foam sectors (1994) |  | LAC | ARG | SEV | 12 | PRP | 6 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 192929 | 4741 | 197670 | 197670 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ARG/SEV/12/PRP/6 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
TRF | IBRD | Institutional strengthening (establishment of OPROZ) | Individual | LAC | ARG | SEV | 13 | INS | 11 | N | O | D |  | 0 | 0 | 0 | 0 | 1994-07-01 |  | 1997-07-01 |  |  | 1994-07-01 | 359500 | -359500 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Transfered to UNDP |  |  | #NAME? | 0 | 0 | 0 | 0 | ARG/SEV/13/INS/11 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | LAC | ARG | SEV | 16 | PRP | 23 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-31 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 185000 | -4503 | 180497 | 180497 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ARG/SEV/16/PRP/23 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | LAC | ARG | SEV | 18 | PRP | 42 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 45000 | 0 | 45000 | 45000 | 100 | 0 | 0 |  | 5850 | 0 | 5850 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ARG/SEV/18/PRP/42 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | LAC | ARG | SEV | 21 | PRP | 53 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 45000 | 0 | 45000 | 45000 | 100 | 0 | 0 |  | 5850 | 0 | 5850 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ARG/SEV/21/PRP/53 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the refrigeration, halon and MAC sectors |  | LAC | ARG | SEV | 24 | PRP | 72 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1998-12-01 | 1998-12-01 | 60000 | 0 | 60000 | 60000 | 100 | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ARG/SEV/24/PRP/72 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects in the refrigeration and solvent cleaning sectors |  | LAC | ARG | SEV | 27 | PRP | 86 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-30 | 2001-01-01 |  | 1999-12-31 | 1999-12-01 | 16000 | 0 | 16000 | 16000 | 100 | 0 | 0 |  | 2080 | 0 | 2080 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ARG/SEV/27/PRP/86 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Replacement of 1,1,1-trichloethane sheet steel cleaning system on the steel sheet-cutting table with an aqueous-mechanical system in the steel enterprise Siderar, SAIC | Individual | LAC | ARG | SOL | 28 | INV | 90 | N | O | I |  | 0 | 0 | 0 | 0 | 1999-07-01 |  | 2001-08-01 |  |  | 2003-04-01 | 105147 | -105147 | 0 | 0 | 0 | 0 | 0 |  | 13669.11 | -11566 | 2103 | 0.11 | 0.11 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Cancelled - 38th ExCom |  |  | #NAME? | 0 | 0 | 0 | 0 | ARG/SOL/28/INV/90 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from MCF used as solvent to aqua based cleaning at Argelite La Rioja, SA; CIMCAM, SA; Grimoldi, SA; Heliodino SAIC; Integral Metalurgica, SA; Orbis Mertig SAIC; Trosh, SA Unisol, SA and Buffalo, S.A. | Individual | LAC | ARG | SOL | 28 | INV | 91 | N | O | I | TCA | 7.1 | 2.3 | 0 | 0 | 1999-07-01 | 2001-02-20 | 2000-08-01 |  | 2004-03-01 | 2004-03-01 | 272157 | -55440 | 216717 | 88550 | 40.85 | 128167 | 0 |  | 35380.41 | -7207.2 | 11511.5 | 16661.71 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Orbis and Buffalo have completed conversion. Argelite, Unisol and Cincam cancelled at the 39th ExCom. Grimoldi, Integral Metalurgica, Heliodino and Trosh were cancelled at the 44th ExCom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ARG/SOL/28/INV/91 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the solvent (TCA) sub-sector |  | LAC | ARG | SOL | 30 | PRP | 109 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2001-03-01 |  | 2001-12-01 | 2001-12-01 | 7000 | 0 | 7000 | 7000 | 100 | 0 | 0 |  | 910 | 0 | 910 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ARG/SOL/30/PRP/109 | [7 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in sterilization via ETO at Asisthos SRL | Individual | LAC | ARG | STE | 27 | INV | 82 | N | O | I | CFC | 20.69 | 20.69 | 0 | 0 | 1999-03-01 | 1999-06-01 | 2001-04-01 |  | 2000-09-01 | 2001-03-01 | 395095 | 0 | 395095 | 395095 | 100 | 0 | 0 |  | 51362.35 | 0 | 51362.35 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Completed. PCR submitted Feb. 01. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ARG/STE/27/INV/82 | [8 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Country programme preparation |  | ASP | BGD | SEV | 4 | PRP | 7 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1992-06-01 |  |  | 1992-06-01 | 25564 | -25564 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | 0 | 0 | 0 | 0 | BGD/SEV/4/PRP/7 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
COM | IBRD | Terminal phaseout management plan | Multiyear | LAC | BHA | PHA | 35 | INV | 8 | N | O | I | CFC | 18 | 18 | 0 | 0 | 2001-12-01 | 2004-11-01 | 2003-12-01 |  | 2003-12-01 |  | 240000 | 0 | 240000 | 240000 | 100 | 0 | 0 |  | 31200 | 0 | 31200 | 0 | 0 | 2001 | #NAME? | #NAME? | #NAME? | #NAME? | Grant Agreement between the Bank and the Bahamas became effective Jun. 04. WB mission conducted to confirm progress of TPMP implementation. Disbursement of funds from first tranche made, on a retroactive basis, upon approval of Progress Report and CFC consumption verification report. Audited account of expenditures and verification report confirmed that the Bahamas met all commitments, as per Excom agreement. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | BHA/PHA/35/INV/8 | [7 empty] | 2001 | INV | 48 | 48 | 0 | 0 | Yes | Yes | Yes
ONG | IBRD | Terminal phase-out management plan: 2004-2005 biennial programme | Multiyear | LAC | BHA | PHA | 44 | INV | 12 | N | O | I | CFC | 23 | 0 | 0 | 0 | 2004-12-01 |  | 2005-12-01 | 2005-12-01 |  |  | 200000 | 0 | 200000 | 0 | 0 | 200000 | 200000 | 200000 | 26000 | 0 | 0 | 26000 | 26000 | 2004 | #NAME? | #NAME? | #NAME? | #NAME? | Implementation of activities is ongoing as presented in 2004-2005 Biennial Work Plan. These include, among others, training of customs officials, training of technicians of refrigeration servicing centers, public awareness activities, and policy and regulatory montitoring and control. Disbursement of funds for 2nd tranche will take place, on a retroactive basis once all activities in biennial work plan are completed and verified, and once CFC consumption verification report approved by Excom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | BHA/PHA/44/INV/12 | [7 empty] | 2003 | INV | 36 | 0 | 0 | 0
FIN | IBRD | Conversion to reduced CFC technology in the manufacture of Refrigerators at Refrigeracao Parana S.A., Unidade Sao Carlos | Individual | LAC | BRA | FOA | 15 | INV | 16 | N | O | I | CFC | 96 | 96 | 0 | 0 | 1994-12-01 | 1996-01-01 | 1996-12-01 |  | 1999-06-01 | 1999-05-01 | 162603 | -12710 | 149893 | 149893 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. (Remaining "balance" has been disbursed to FA.) |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | BRA/FOA/15/INV/16 | 1997-12-01 | 1999-06-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Substitution of CFC-11 by HCFC-141b in the manufacture of polyurethane foams at Sao Rafael Ind. Com. | Individual | LAC | BRA | FOA | 18 | INV | 30 | N | O | I | CFC | 14 | 14 | 0 | 0 | 1995-11-01 | 1997-02-01 | 1996-10-01 |  | 1999-09-01 | 1998-02-01 | 82676 | -2016 | 80660 | 80660 | 100 | 0 | 0 |  | 10748 | -262.08 | 10485.8 | 0.12 | 0.12 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Complete. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | BRA/FOA/18/INV/30 | 1998-07-01 | [7 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Substitution of CFC-11 by HCFC-141b in the manufacture of polyurethane foams at Randon Implementos S.A. | Individual | LAC | BRA | FOA | 18 | INV | 31 | N | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1996-09-01 |  |  | 1999-07-01 | 92180 | -92180 | 0 | 0 | 0 | 0 | 0 |  | 11983 | -11983 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Cancelled. |  |  | #NAME? | 0 | 0 | 0 | 0 | BRA/FOA/18/INV/31 | 1998-06-01 | 1999-06-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Substitution of CFC-11 by HCFC-141b in the manufacture of polyurethane foams at Recrusul SEA | Individual | LAC | BRA | FOA | 18 | INV | 32 | N | O | I | CFC | 201 | 201 | 0 | 0 | 1995-11-01 | 1997-05-01 | 1996-11-01 |  | 1999-06-01 | 1999-08-01 | 1075650 | -121339 | 954311 | 954311 | 100 | 0 | 0 |  | 139835 | -15774.5 | 124060.5 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Complete. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | BRA/FOA/18/INV/32 | 1997-12-01 | 1999-06-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Substitution of CFC-11 by HCFC-141b in the manufacture of polyurethane foams at M. Agostini, S.A. | Individual | LAC | BRA | FOA | 18 | INV | 33 | N | O | I | CFC | 11 | 11 | 0 | 0 | 1995-11-01 | 1999-02-01 | 1996-08-01 |  | 1999-09-01 | 1999-02-01 | 85217 | -2078 | 83139 | 83139 | 100 | 0 | 0 |  | 11078 | -269.93 | 10808.07 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | All three foaming machines now installed and in routine operation. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | BRA/FOA/18/INV/33 | 1998-06-01 | 1999-06-01 | [6 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Substitution of CFC-11 by HCFC-141b in the manufacture of polyurethane foams at Termolar, S.A. | Individual | LAC | BRA | FOA | 18 | INV | 34 | N | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1996-08-01 |  |  | 1996-09-01 | 61716 | -61716 | 0 | 0 | 0 | 0 | 0 |  | 8023 | -8023 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Cancelled. |  |  | #NAME? | 0 | 0 | 0 | 0 | BRA/FOA/18/INV/34 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the foam sector |  | LAC | BRA | FOA | 22 | PRP | 75 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1999-03-31 | 1997-12-01 |  | 1999-12-01 | 1999-12-01 | 75000 | 0 | 75000 | 75000 | 100 | 0 | 0 |  | 9750 | 0 | 9750 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | BRA/FOA/22/PRP/75 |  | 1999-12-01 | [6 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the process agent sub-sector |  | LAC | BRA | PAG | 36 | PRP | 242 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2003-12-01 | 2003-09-01 |  | 2003-09-01 | 2003-12-01 | 50000 | -14819 | 35181 | 35181 | 100 | 0 | 0 |  | 6500 | -1926 | 4573.53 | 0.47 | 0.47 | 2002 | #NAME? | #NAME? | #NAME? | #NAME? | Upon confirmation of very low national CTC consumption, arrangements with Ministry of Environment are being made to transfer project to UNDP. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | BRA/PAG/36/PRP/242 | [7 empty] | 2002 | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Assembly line refitting for HFC-134a refrigerator compressor, commercial production | Individual | LAC | BRA | REF | 7 | INV | 6 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1995-06-01 |  |  | 1995-07-01 | 530000 | -530000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Cancelled. |  |  | #NAME? | 0 | 0 | 0 | 0 | BRA/REF/7/INV/6 | 1995-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation on converting CFC-11 central air conditioning units with HCFC-123 or HFC-134a |  | LAC | BRA | REF | 7 | PRP | 5 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1992-12-01 | 1993-06-01 |  | 1995-12-01 | 1995-12-01 | 400000 | 0 | 400000 | 400000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Complete. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | BRA/REF/7/PRP/5 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | CFC-12 collection, recycling and conservation programme for household refrigerator maintenance and repair shops | Individual | LAC | BRA | REF | 7 | TAS | 7 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1999-06-01 | 1995-06-01 |  |  | 2001-07-01 | 2000000 | -1980000 | 20000 | 20000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Cancelled. |  |  | #NAME? | 0 | 0 | 0 | 0 | BRA/REF/7/TAS/7 | 1995-06-01 | 1999-12-01 | [6 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects in the refrigeration sector (1994) |  | LAC | BRA | REF | 12 | PRP | 14 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 164380 | -53297 | 111083 | 111083 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | BRA/REF/12/PRP/14 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | System for storage and charging of ester oils used in the manufacture of HFC-134a compressors at Embraco | Individual | LAC | BRA | REF | 13 | INV | 15 | N | O | D | CFC | 0 | 0 | 0 | 0 | 1994-07-01 | 1995-05-01 | 1994-09-01 |  | 1994-07-01 | 1995-07-01 | 221200 | 0 | 221200 | 221200 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Project fully implemented resulting in savings of 270 tons per year ODP. Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | BRA/REF/13/INV/15 | 1994-07-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of CFC-11/12 to cyclopentane/HFC-134a foaming agent/refrigerant factory conversion at Metalfrio S.A. | Individual | LAC | BRA | REF | 15 | INV | 18 | N | O | I |  | 205.5 | 205.5 | 0 | 0 | 1994-12-01 | 1996-02-01 | 1996-06-01 |  | 1998-07-01 | 1999-05-01 | 2360360 | -776471 | 1583889 | 1583889 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Foaming process began operation in July 98 and refrigeration process in June 98. Final disbursement to Metalfrio was made on May 99. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | BRA/REF/15/INV/18 | 1997-12-01 | 1999-05-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 and CFC-12 in the manufacture of commercial chest freezers at Refrigeracao Parana S.A. Curitiba | Individual | LAC | BRA | REF | 18 | INV | 35 | N | O | I | CFC | 363 | 363 | 0 | 0 | 1995-11-01 | 1999-08-01 | 1996-11-01 |  | 1998-11-01 | 1999-08-01 | 1557613 | -210305.8 | 1347307.2 | 1347307 | 99.99 | 0.2 | 0.2 |  | 202490 | -27340.31 | 175149.69 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | The firm went ahead with its own funds and completed one line (vertical freezers) in July 97; and the other line (horizontal freezers) in Nov. 98. FINEP reimbursed the firm retroactively for capital and operating costs. Final reimbursement made on August 2, 1999. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | BRA/REF/18/INV/35 | 1997-12-01 | 1999-06-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 and CFC-12 in the production of commercial refrigeration equipment at Reubli, S.A. | Individual | LAC | BRA | REF | 19 | INV | 48 | N | O | I | CFC | 89.9 | 89.9 | 0 | 0 | 1996-05-01 | 1997-11-01 | 1997-11-01 |  | 1999-06-01 | 1999-06-01 | 901270 | -200188 | 701082 | 701082 | 100 | 0 | 0 |  | 117165 | -26024.34 | 91140.66 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Complete. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | BRA/REF/19/INV/48 | 1997-12-01 | 1999-06-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 and CFC-12 in the production of commercial refrigeration equipment at Geltec Comercio e Industria S.A. | Individual | LAC | BRA | REF | 19 | INV | 49 | N | O | I | CFC | 18.3 | 18.3 | 0 | 0 | 1996-05-01 | 1997-01-01 | 1997-11-01 |  | 1998-02-01 | 1998-02-01 | 228250 | -93750 | 134500 | 134500 | 100 | 0 | 0 |  | 29673 | -12188 | 17485 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Refrigeration equipment installed and operating. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | BRA/REF/19/INV/49 | 1997-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-11 to cyclopentane foam blowing agent and CFC-12 to HFC-134a refrigerant at Tecnomecanica Esmaltec Ltda. | Individual | LAC | BRA | REF | 19 | INV | 50 | N | O | I | CFC | 68.7 | 68.7 | 0 | 0 | 1996-05-01 | 1998-08-01 | 1997-11-01 |  | 2000-03-01 | 1999-06-01 | 924040 | 0 | 924040 | 924040 | 100 | 0 | 0 |  | 120125 | 0 | 120125 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | BRA/REF/19/INV/50 | 1998-06-01 | 1999-06-01 | [6 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of CFC-11 and CFC-12 in the production of commercial refrigeration equipment at Everest Refrigeracao Ind. e Comercio Ltda. | Individual | LAC | BRA | REF | 19 | INV | 51 | N | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1997-11-01 |  |  | 1998-07-01 | 149050 | -149050 | 0 | 0 | 0 | 0 | 0 |  | 19377 | -19377 | 0 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Cancelled. |  |  | #NAME? | 0 | 0 | 0 | 0 | BRA/REF/19/INV/51 | 1998-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 and CFC-12 in the production of commercial refrigeration equipment at Gelopar | Individual | LAC | BRA | REF | 20 | INV | 55 | N | O | I | CFC | 13.14 | 13.14 | 0 | 0 | 1996-10-01 | 1997-12-01 | 1998-04-01 |  | 1998-05-01 | 1998-05-01 | 200200 | -145442 | 54758 | 54758 | 100 | 0 | 0 |  | 26026 | -18907.46 | 7118.54 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Refrigeration equipment acquired and installed. 134a production began May 98. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | BRA/REF/20/INV/55 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-12 in the production of refrigeration equipment (drinking water fountains and coolers) at Industria Brasileira de Bebedouros Ltda. (IBBL) | Individual | LAC | BRA | REF | 20 | INV | 56 | N | O | I | CFC | 5.9 | 5.9 | 0 | 0 | 1996-10-01 | 1997-12-01 | 1998-04-01 |  | 1998-07-01 | 1998-05-01 | 82500 | -23113 | 59387 | 59387 | 100 | 0 | 0 |  | 10725 | -3004.69 | 7720.31 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | BRA/REF/20/INV/56 |  | 1999-06-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1991) |  | LAC | BRA | SEV | 4 | PRP | 1 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 114583 | -73761 | 40822 | 40822 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | BRA/SEV/4/PRP/1 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation | Individual | LAC | BRA | SEV | 6 | CPG | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1993-03-31 | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 123788 | -122316 | 1472 | 1472 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | BRA/SEV/6/CPG/2 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1992) |  | LAC | BRA | SEV | 6 | PRP | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 191878 | -89419 | 102459 | 102459 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | BRA/SEV/6/PRP/3 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1993) |  | LAC | BRA | SEV | 9 | PRP | 9 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 112000 | -20388 | 91612 | 91612 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | BRA/SEV/9/PRP/9 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation | Individual | LAC | BRA | SEV | 12 | CPG | 76 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 49000 | -45000 | 4000 | 4000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Brazil Country Program was completed, presented and approved at the 13th Meeting of the Executive Committee. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | BRA/SEV/12/CPG/76 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | LAC | BRA | SEV | 16 | PRP | 19 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 235906 | 0 | 235906 | 235906 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | BRA/SEV/16/PRP/19 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | LAC | BRA | SEV | 18 | PRP | 42 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 100000 | 0 | 100000 | 100000 | 100 | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | BRA/SEV/18/PRP/42 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Phase out of CFC-113 and of MCF used in vapor degreasers to clean aircraft parts at Embraer | Individual | LAC | BRA | SOL | 18 | INV | 38 | N | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1997-05-01 |  |  | 1998-07-01 | 308215 | -308215 | 0 | 0 | 0 | 0 | 0 |  | 40068 | -40068 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project cancelled. Enterprise unable to proceed with project as approved funding insufficient and no access to supplementary funds. |  |  | #NAME? | 0 | 0 | 0 | 0 | BRA/SOL/18/INV/38 | 1998-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of CFC-113 in medical parts cleaning and silicone deposition, and CFC-12 used in sterilization at Tecnobio | Individual | LAC | BRA | SOL | 19 | INV | 52 | N | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1997-05-01 |  |  | 1997-11-01 | 317492 | -317492 | 0 | 0 | 0 | 0 | 0 |  | 41274 | -41274 | 0 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Project cancelled. Enterprise unable to proceed with project as approved funding insufficient and no access to supplementary funds. |  |  | #NAME? | 0 | 0 | 0 | 0 | BRA/SOL/19/INV/52 | 1997-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | CFC phase out at Frigocar | Individual | LAC | CHI | FOA | 7 | INV | 19 | N | O | I | CFC | 0.6 | 0.6 | 0 | 0 | 1992-06-01 | 1996-10-01 | 1996-10-01 |  | 1996-10-01 | 1996-10-01 | 15784 | 0 | 15784 | 15784 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Completed. Foam project |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CHI/FOA/7/INV/19 | 1996-10-31 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | CFC phase out at Kifafi | Individual | LAC | CHI | FOA | 7 | INV | 20 | N | O | I | CFC | 0.9 | 0.8 | 0 | 0 | 1992-06-01 | 1997-05-01 | 1997-03-01 |  | 1997-02-01 | 1997-05-01 | 20000 | 0 | 20000 | 20000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Completed |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CHI/FOA/7/INV/20 | 1997-02-28 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | CFC phase out at Polimin | Individual | LAC | CHI | FOA | 7 | INV | 23 | N | O | I | CFC | 0.3 | 0.28 | 0 | 0 | 1992-06-01 | 1997-05-01 | 1997-03-01 |  | 1997-02-01 | 1997-05-01 | 9120 | 0 | 9120 | 9120 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Completed |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CHI/FOA/7/INV/23 | 1997-02-28 | [7 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | CFC phase out at Himmer & Himmer | Individual | LAC | CHI | FOA | 7 | INV | 28 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1997-03-01 |  |  | 1997-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Not funded. Eliminate from inventory |  |  | #NAME? | 0 | 0 | 0 | 0 | CHI/FOA/7/INV/28 | 1997-03-01 | [7 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | CFC phase out at SAAM, S.A. | Individual | LAC | CHI | FOA | 7 | INV | 29 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1997-03-01 |  |  | 1997-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Not funded. Eliminate from Inventory |  |  | #NAME? | 0 | 0 | 0 | 0 | CHI/FOA/7/INV/29 | 1997-03-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | CFC phase out at Instapanel (IPAC) | Individual | LAC | CHI | FOA | 7 | INV | 30 | N | O | I | CFC | 64.2 | 64.2 | 0 | 0 | 1992-06-01 | 1997-02-01 | 1997-03-01 |  | 1996-12-01 | 1997-02-01 | 131606.92 | 0 | 131606.92 | 131606.92 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Completed |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CHI/FOA/7/INV/30 | 1996-12-16 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | CFC phase out at Inversiones Overjuna (Metalcargo) | Individual | LAC | CHI | FOA | 7 | INV | 31 | N | O | I | CFC | 0.2 | 0.2 | 0 | 0 | 1992-06-01 | 1996-12-01 | 1997-03-01 |  | 1996-12-01 | 1996-12-01 | 4740 | 0 | 4740 | 4740 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Completed |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CHI/FOA/7/INV/31 | 1997-01-31 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the methyl bromide sector for tomatoes |  | LAC | CHI | FUM | 24 | PRP | 33 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1998-12-01 | 1998-12-01 | 25000 | 0 | 25000 | 25000 | 100 | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CHI/FUM/24/PRP/33 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Demonstration project for testing methyl bromide alternatives in soil treatment applications for tomatoes and peppers | Individual | LAC | CHI | FUM | 25 | DEM | 35 | N | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-06-01 | 2000-08-01 | 2005-03-01 |  |  | 348130 | 0 | 348130 | 330231 | 94.85 | 17899 | 17899 | 17899 | 45256.9 | 0 | 42930.03 | 2326.87 | 2326.87 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Project is in its final stage. All field activities completed. The only remaining activity is the completion of a consumption survey agreed between CONAMA and the Ministry of Agriculture/SAG. Results of this activity are expected to be completed by May 05. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CHI/FUM/25/DEM/35 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment project in the methyl bromide sector |  | LAC | CHI | FUM | 30 | PRP | 139 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2000-12-01 |  | 2001-12-01 | 2001-12-01 | 10000 | 0 | 10000 | 10000 | 100 | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CHI/FUM/30/PRP/139 | [7 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation for 2 projects in the methyl bromide sector |  | LAC | CHI | FUM | 33 | PRP | 145 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-12-01 | 2002-09-01 |  | 2001-12-01 | 2001-12-01 | 20000 | 0 | 20000 | 20000 | 100 | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | 2001 | #NAME? | #NAME? | #NAME? | #NAME? | The proposal is being prepare by the Bank and the INIA |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CHI/FUM/33/PRP/145 | [7 empty] | 2001 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of a national halon bank |  | LAC | CHI | HAL | 39 | PRP | 152 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-12-01 | 2003-12-01 |  | 2003-12-01 | 2003-12-01 | 40000 | 0 | 40000 | 40000 | 100 | 0 | 0 |  | 3000 | 0 | 3000 | 0 | 0 | 2003 | #NAME? | #NAME? | #NAME? | #NAME? | Proposal will be submitted to the 42nd ExCom Meeting. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CHI/HAL/39/PRP/152 | [7 empty] | 2003 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Halon consumption phase-out: technical assistant programme and halon recycling and recovery equipment | Halon Banking | LAC | CHI | HAL | 42 | TAS | 156 | N | O | I |  | 0 | 0 | 0 | 0 | 2004-04-01 |  | 2006-10-01 | 2006-10-01 |  |  | 60000 | 0 | 60000 | 0 | 0 | 60000 | 60000 | 10000 | 4500 | 0 | 0 | 4500 | 4500 | 2004 | #NAME? | #NAME? | #NAME? | #NAME? | As per ExCom approval, disbursement can only take place when import restrictions for halon is in place in the country. A law for regulating ODS use and import quotas in Chile will be submitted to Congress in Q1 2005. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | CHI/HAL/42/TAS/156 | [7 empty] | 2004 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Implementation of the Technology Conversion Financing Programme (Tecfin) | Individual | LAC | CHI | MUS | 7 | INV | 4 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1996-06-01 |  | 1998-07-01 | 2000-03-01 | 69548 | -69548 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Part of $1,206,000 line-of-grant project. Funding returnd at the 30th ExCom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CHI/MUS/7/INV/4 | 1997-04-30 | [7 empty] | INV | 0 | 0 | 0 | 0
COM | IBRD | Montreal Protocol implementation programme - phase II | Individual | LAC | CHI | MUS | 19 | INV | 14 | N | O | I | CFC | 400 | 216 | 0 | 0 | 1996-05-01 | 1998-12-01 | 2000-05-01 |  | 2004-12-01 |  | 1000000 | 0 | 1000000 | 1000000 | 100 | 0 | 0 |  | 130000 | 0 | 130000 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. PCR is under preparation by the NOU. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CHI/MUS/19/INV/14 | 1997-12-31 | 2000-05-01 | [6 empty] | INV | 0 | 0 | 0 | 0
COM | IBRD | Montreal Protocol implementation programme (Phase II, second tranche) | Individual | LAC | CHI | MUS | 26 | INV | 37 | N | O | I | CFC | 270 | 202.6 | 0 | 0 | 1998-11-01 | 2000-12-01 | 2000-12-01 |  | 2004-12-01 |  | 2800000 | -1000000 | 1800000 | 1605995 | 89.22 | 194005 | 194005 | 194005 | 318000 | -95000 | 186659.45 | 36340.55 | 36340.55 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and PCR under preparation. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CHI/MUS/26/INV/37 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Retrofit of freezing chambers at Frigorent Frigorifico Sociedad Limitada | Individual | LAC | CHI | REF | 7 | INV | 18 | N | O | I | CFC | 0.03 | 0.03 | 0 | 0 | 1992-06-01 | 1996-10-01 | 1996-09-01 |  | 1996-10-01 | 1996-10-01 | 20166.36 | 0 | 20166.36 | 20166.36 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Completed |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CHI/REF/7/INV/18 | 1996-10-31 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of CFCs at Mimet | Individual | LAC | CHI | REF | 7 | INV | 21 | N | O | I | CFC | 47.8 | 47.8 | 0 | 0 | 1992-06-01 | 1997-01-01 | 1996-12-01 |  | 1996-12-01 | 1997-01-01 | 93671.85 | 0 | 93671.85 | 93671.85 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Completed |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CHI/REF/7/INV/21 | 1996-12-23 | [7 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Replacement of ODS at Supermercado Gran Avenida | Individual | LAC | CHI | REF | 7 | INV | 24 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1997-03-01 |  |  | 1997-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Not funded. Eliminate from inventory |  |  | #NAME? | 0 | 0 | 0 | 0 | CHI/REF/7/INV/24 | 1997-03-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of ODS at Supermercado Vicuna McKenna | Individual | LAC | CHI | REF | 7 | INV | 25 | N | O | I | CFC | 0.64 | 0.05 | 0 | 0 | 1992-06-01 | 1997-06-01 | 1997-03-01 |  | 1997-02-01 | 1997-06-01 | 5558 | 0 | 5558 | 5558 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Completed. Refrigeration subproject |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CHI/REF/7/INV/25 | 1997-03-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of ODS at Supermercado Macul | Individual | LAC | CHI | REF | 7 | INV | 26 | N | O | I | CFC | 0.4 | 0.08 | 0 | 0 | 1992-06-01 | 1997-06-01 | 1997-03-01 |  | 1997-02-01 | 1997-06-01 | 2505 | 0 | 2505 | 2505 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Completed. Refrigeration subproject |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CHI/REF/7/INV/26 | 1997-03-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of ODS at Supermercado Plaza Egana | Individual | LAC | CHI | REF | 7 | INV | 27 | N | O | I | CFC | 0.32 | 0.03 | 0 | 0 | 1992-06-01 | 1997-06-01 | 1997-03-01 |  | 1997-02-01 | 1997-06-01 | 3300 | 0 | 3300 | 3300 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Completed. Refrigeration subproject |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CHI/REF/7/INV/27 | 1997-03-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Recovery and recycling programme at Central De Servicios Tecnicos (CST) | Individual | LAC | CHI | REF | 7 | TAS | 22 | N | O | I | CFC | 4 | 4 | 0 | 0 | 1992-06-01 | 1997-01-01 | 1997-03-01 |  | 1996-11-01 | 1997-05-01 | 120000 | 0 | 120000 | 120000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Completed |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | CHI/REF/7/TAS/22 | 1997-02-28 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation | Individual | LAC | CHI | SEV | 4 | CPG | 1 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 121166 | -115333 | 5833 | 5833 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | CHI/SEV/4/CPG/1 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1991) |  | LAC | CHI | SEV | 4 | PRP | 17 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 162736 | -134936 | 27800 | 27800 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CHI/SEV/4/PRP/17 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1992) |  | LAC | CHI | SEV | 6 | PRP | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 191878 | -134385 | 57493 | 57493 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CHI/SEV/6/PRP/3 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Establishment of the Ozone Team | Individual | LAC | CHI | SEV | 7 | INS | 8 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1994-09-01 | 1996-06-01 |  | 1996-10-01 | 1996-11-01 | 213000.03 | -2093 | 210907.03 | 210906.86 | 99.99 | 0.17 | 0.17 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Completed |  |  | #NAME? | #NAME? | #NAME? | #NAME? | 0 | CHI/SEV/7/INS/8 | 1996-10-31 | [7 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Ozone seal programme | Individual | LAC | CHI | SEV | 7 | TAS | 9 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1994-09-01 | 1993-06-01 |  | 1996-06-01 | 1996-06-01 | 8000 | -600 | 7400 | 7400 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Completed |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | CHI/SEV/7/TAS/9 | 1996-06-30 | [7 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Public awareness programme | Individual | LAC | CHI | SEV | 7 | TAS | 10 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1994-09-01 | 1996-06-01 |  | 1996-06-01 | 1996-07-01 | 378000 | -5932 | 372068 | 372067.8 | 99.99 | 0.2 | 0.2 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Completed |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | CHI/SEV/7/TAS/10 | 1996-07-31 | [7 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Implementation of a sector specific training programme | Individual | LAC | CHI | SEV | 7 | TRA | 11 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1996-01-01 | 1996-06-01 |  | 1997-10-01 | 1998-12-01 | 111000 | -14033 | 96967 | 96967 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Completed |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | CHI/SEV/7/TRA/11 | 1997-06-01 | [7 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1993) |  | LAC | CHI | SEV | 9 | PRP | 7 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 82890 | -10881 | 72009 | 72009 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CHI/SEV/9/PRP/7 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Supervision of project implementation (approved at the 7th ExCom meeting) |  | LAC | CHI | SEV | 12 | PRP | 5 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 30208 | 2849 | 33057 | 33057 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CHI/SEV/12/PRP/5 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects for ODS I and ODS II (1995) |  | LAC | CHI | SEV | 16 | PRP | 12 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1995-12-01 |  | 1995-12-31 | 1995-12-31 | 130312 | 0 | 130312 | 130312 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CHI/SEV/16/PRP/12 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | LAC | CHI | SEV | 18 | PRP | 13 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1997-03-01 | 1997-03-01 | 70000 | 0 | 70000 | 70000 | 100 | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Funds committed in CY96 were disbursed in CY97. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CHI/SEV/18/PRP/13 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Institutional strengthening II | Individual | LAC | CHI | SEV | 20 | INS | 16 | N | O | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-03-01 | 1998-10-01 |  | 1998-10-01 | 1998-10-01 | 113500 | 0 | 113500 | 113500 | 100 | 0 | 0 |  | 14755 | 0 | 14755 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Completed |  |  | #NAME? | #NAME? | #NAME? | #NAME? | 0 | CHI/SEV/20/INS/16 | 1998-10-31 | [7 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Ozone protection and institutional strengthening project (renewal) | Individual | LAC | CHI | SEV | 25 | INS | 36 | N | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-01-01 | 2000-07-01 |  | 2000-12-01 | 2000-12-01 | 143500 | 0 | 143500 | 143500 | 100 | 0 | 0 |  | 18655 | 0 | 18655 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Completed. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | 0 | CHI/SEV/25/INS/36 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation for the Phase II auction scheme |  | LAC | CHI | SEV | 25 | PRP | 34 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-09-30 | 1999-08-01 |  | 1998-12-01 | 1998-12-01 | 80000 | 0 | 80000 | 80000 | 100 | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Newly approved. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CHI/SEV/25/PRP/34 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Renewal of institutional strengthening |  | LAC | CHI | SEV | 32 | INS | 142 | N | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2002-12-01 | 2003-01-01 |  | 2003-01-01 | 2003-01-01 | 143500 | 0 | 143500 | 143500 | 100 | 0 | 0 |  | 18655 | 0 | 18655 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? | NOU completed the IS tranche with work on several activities: the RMP, methyl bromide demo. project, sterilization project, and methyl bromide phase out in the tree sub-sector. New IS approved at the 38th ExCom. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | 0 | CHI/SEV/32/INS/142 | [7 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Extension of institutional strengthening project |  | LAC | CHI | SEV | 38 | INS | 52 | N | T | I | CFC | 15.42 | 0 | 0 | 0 | 2002-11-01 | 2003-12-01 | 2004-12-01 | 2005-03-01 |  |  | 186550 | 0 | 186550 | 170000 | 91.12 | 16550 | 16550 | 16550 | 46800 | 0 | 42648.08 | 4151.92 | 4151.92 | 2002 | #NAME? | #NAME? | #NAME? | #NAME? | Program has covered activities to implement the ODS reduction program by, among other things, paying salaries of the NOU staff and some travel within Chile to monitor and implement projects as well as attendance at international meetings. The NOU changed its staff in Sep. 04 and the reorganization process is underway. Renewal is expected at the 45th ExCom Meeting. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | 0 | CHI/SEV/38/INS/52 | [7 empty] | 2002 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 in the manufacture of rigid polyurethane foam through the use of HCFC-141b technology at Daniel J. Fernandez and Cia. Ltd. | Individual | LAC | COL | FOA | 26 | INV | 28 | N | O | I | CFC | 22.2 | 22.2 | 0 | 0 | 1998-11-01 | 2000-12-01 | 2000-12-01 |  | 2002-02-01 | 2002-05-01 | 173822 | 0 | 173822 | 173822 | 100 | 0 | 0 |  | 22596.86 | 0 | 22596.86 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Project has been fully executed. PCR is being revised for submission. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | COL/FOA/26/INV/28 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 in manufacture of rigid polyurethane foam through the use of HCFC-141b technology at Friotermica S.A. | Individual | LAC | COL | FOA | 26 | INV | 29 | N | O | I | CFC | 8.6 | 8.6 | 0 | 0 | 1998-11-01 | 2001-12-01 | 2000-12-01 |  | 2002-09-01 | 2002-12-01 | 67338 | 0 | 67338 | 67338 | 100 | 0 | 0 |  | 8753.94 | 0 | 8753.94 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Project fully completed during the last trimester of 2002. PCR is being prepared. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | COL/FOA/26/INV/29 |  |  |  | 2002-12-01 |  |  |  |  | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC in manufacture of rigid polyurethane foam through the use of HCFC-141b technology at Indufrio | Individual | LAC | COL | FOA | 26 | INV | 30 | N | O | I | CFC | 9.65 | 9.65 | 0 | 0 | 1998-11-01 | 2002-12-01 | 2000-12-01 |  | 2003-10-01 | 2003-12-01 | 75548 | 0 | 75548 | 75548 | 100 | 0 | 0 |  | 9821.24 | 0 | 9821.24 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Project has been financially completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | COL/FOA/26/INV/30 | [8 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of CFC-11 in the manufacture of rigid polyurethane foam through the use of HCFC-22 technology at Master Cooler and Cia Ltd. | Individual | LAC | COL | FOA | 26 | INV | 31 | N | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 |  | 2000-12-01 |  |  | 2001-12-01 | 70862 | -70862 | 0 | 0 | 0 | 0 | 0 |  | 9212.06 | -9212 | 0 | 0.06 | 0.06 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Project cancelled and funds returned at the 35th ExCom. |  |  | #NAME? | 0 | 0 | 0 | 0 | COL/FOA/26/INV/31 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 in the manufacture of rigid polyurethane foam through the use of HCFC-141b technology at Rojas Hnos., Ltda. | Individual | LAC | COL | FOA | 28 | INV | 35 | N | O | R | CFC | 8.2 | 8.2 | 0 | 0 | 1999-07-01 | 2001-08-30 | 2001-08-01 |  | 2001-11-01 | 2001-12-01 | 64206 | 0 | 64206 | 64206 | 100 | 0 | 0 |  | 8346.78 | 0 | 8346.78 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | The project is completed, equipment destroyed and funding disbursed. PCR is expected May 2002. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | COL/FOA/28/INV/35 | [8 empty] | INV | 0 | 0 | 0 | 0
ONG | IBRD | Phase out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam at 29 Colombian enterprises | Individual | LAC | COL | FOA | 29 | INV | 39 | N | O | I | CFC | 56.6 | 37.6 | 0 | 0 | 1999-11-01 | 2002-09-01 | 2002-06-01 | 2005-05-01 |  |  | 584727 | 0 | 584727 | 411990.74 | 70.45 | 172736.26 | 2800 | 2800 | 74319.97 | 0 | 52364.85 | 21955.12 | 364 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Delays in obtaining "Liquidation Certificates" from all beneficiaries have not made it possible to complete project. Certificates are required, by law, and final disbursement to Group Coordinator is tied to receiving them. A Bank mission in Mar. 05 will be meeting with enterprises that have not submitted certificates. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | COL/FOA/29/INV/39 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the commercial refrigeration sector |  | LAC | COL | REF | 24 | PRP | 27 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1999-06-01 | 1999-06-01 | 90000 | 0 | 90000 | 90000 | 100 | 0 | 0 |  | 11700 | 0 | 11700 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | COL/REF/24/PRP/27 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of CFC-11 foam blowing agent with HCFC-141b and CFC-12 refrigerant with HFC-134a in the manufacture of commercial refrigerators and polyurethane sandwich panels at Polares Ltda. | Individual | LAC | COL | REF | 28 | INV | 34 | N | O | I | CFC | 4.64 | 4.64 | 0 | 0 | 1999-07-01 | 2001-09-11 | 2001-08-01 |  | 2002-03-01 | 2002-06-01 | 58109 | 0 | 58109 | 58109 | 100 | 0 | 0 |  | 7554.17 | 0 | 7554.17 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Project has been fully executed. PCR being prepared. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | COL/REF/28/INV/34 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of CFC-11 foam blowing agent with HCFC-141b and CFC-12 refrigerant with HFC-134a in the manufacture of commercial refrigerators and polyurethane sandwich panels at Industrias Supernórdico | Individual | LAC | COL | REF | 28 | INV | 44 | N | O | I | CFC | 9.6 | 9.7 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2001-08-01 |  | 2002-02-01 | 2002-06-01 | 128381 | 0 | 128381 | 128381 | 100 | 0 | 0 |  | 16689.53 | 0 | 16689.53 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Project has been fully executed. PCR has been prepared and is being evaluated. Actual phaseout as reported in the PCR and confirmed with enterprise, country and revised proposal. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | COL/REF/28/INV/44 |  |  |  | 2002-12-01 |  |  |  |  | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of projects in the commercial refrigeration subsector |  | LAC | COL | REF | 30 | PRP | 40 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2001-12-01 |  | 2001-12-01 | 2001-12-01 | 20000 | 0 | 20000 | 20000 | 100 | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | COL/REF/30/PRP/40 | [7 empty] | 2001 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in MACs and compressors project category |  | LAC | COL | REF | 30 | PRP | 43 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 25000 | 0 | 25000 | 25000 | 100 | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | COL/REF/30/PRP/43 | [7 empty] | 2001 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 to HFC-134a technology in the production of MAC systems at Thermo-coil, Calaires, Auto Aires, and Servi Aires | Individual | LAC | COL | REF | 34 | INV | 51 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-10-01 | 2003-08-01 |  | 2003-11-01 | 2003-12-01 | 1358647 | -13905 | 1344742 | 1344742.18 | 100 | -0.18 | -0.18 |  | 159451.17 | -1632 | 157819.3 | -0.13 | -0.13 | 2001 | #NAME? | #NAME? | #NAME? | #NAME? | Project physically and financially completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | COL/REF/34/INV/51 | [7 empty] | 2001 | INV | 0 | 0 | 0 | 0
ONG | IBRD | Umbrella project designed to phase out of the refrigerant CFC-12 by conversion to HFC-134a and replacement of the blowing agent CFC-11 by HCFC-141b in the manufacture of commercial refrigeration systems in 17 enterprises | Individual | LAC | COL | REF | 38 | INV | 57 | N | O | I | CFC | 25.8 | 0 | 0 | 0 | 2002-11-01 |  | 2004-12-01 | 2006-07-01 |  |  | 211636 | 0 | 211636 | 0 | 0 | 211636 | 211636 | 120000 | 27512.68 | 0 | 2115.73 | 25396.95 | 25396.95 | 2002 | #NAME? | #NAME? | #NAME? | #NAME? | Grant Agreement between Government and project Group Coordinator, Cabarria S.A., signed in 2004. SGAs with 2 enterprises signed; 4 others to be signed in early 2005. First order for equipment will be made once the first 6 enterprises have signed contracts. Major delays experienced due to difficulties obtaining insurance certificates for enterprises (which are v. small with insufficient documentation). A Bank mission will be conducted in Mar. 05, during which discussions will take place with reps from insurance companies and enterprises. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | COL/REF/38/INV/57 | [7 empty] | 2002 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation identification |  | LAC | COL | SEV | 21 | PRP | 24 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 15000 | 0 | 15000 | 15000 | 100 | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | COL/SEV/21/PRP/24 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of projects in the foam, commercial refrigeration and solvent sectors |  | LAC | COL | SEV | 27 | PRP | 33 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-06-30 | 2000-01-01 |  | 2000-12-01 | 2000-12-01 | 38000 | 0 | 38000 | 38000 | 100 | 0 | 0 |  | 4940 | 0 | 4940 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | COL/SEV/27/PRP/33 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of CFC-113 as solvent in the silicone coating process of needles and catheters at Laboratorios Rymco | Individual | LAC | COL | SOL | 31 | INV | 45 | N | O | I | CFC | 7.6 | 7.6 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2002-08-01 |  | 2004-12-01 | 2004-12-01 | 81579 | 0 | 81579 | 81579 | 100 | 0 | 0 |  | 10605.27 | 0 | 10605.27 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? | Project is physically and financially completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | COL/SOL/31/INV/45 | [7 empty] | 2000 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the CTC solvent sector |  | LAC | COL | SOL | 36 | PRP | 53 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-01-01 | 2003-01-01 | 20000 | -12000 | 8000 | 8000 | 100 | 0 | 0 |  | 2600 | -1560 | 1040 | 0 | 0 | 2002 | #NAME? | #NAME? | #NAME? | #NAME? | Difficulties experienced in obtaining reliable CTC consumption data have significantly delayed potential project prep. efforts. National CTC consumption is reported to be minimal with the exception of one identified enterprise. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | COL/SOL/36/PRP/53 | [7 empty] | 2002 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Shanghai CFC conversion to LPG propellant | Individual | ASP | CPR | ARS | 7 | INV | 14 | N | O | I | CFC | 6300 | 6300 | 0 | 0 | 1992-06-01 | 1994-05-01 | 1994-06-01 |  | 1996-09-01 | 1997-06-01 | 1900000 | 409000 | 2309000 | 2309000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | CFC consumption in aerosol banned as of Jan. 1, 1998. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/ARS/7/INV/14 | 1997-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Tianjin CFC conversion to LPG propellant | Individual | ASP | CPR | ARS | 7 | INV | 23 | N | O | I | CFC | 6300 | 6300 | 0 | 0 | 1992-06-01 | 1994-05-01 | 1994-06-01 |  | 1996-03-01 | 1997-06-01 | 2500000 | 270000 | 2770000 | 2770000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | CFC consumption in aerosol banned as of Jan. 1, 1998. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/ARS/7/INV/23 | 1997-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Zhongshan Fine Chemical Aerosol Filling Center CFC-12 substitution project | Individual | ASP | CPR | ARS | 13 | INV | 79 | N | O | I | CFC | 4067 | 4067 | 0 | 0 | 1994-07-01 | 1996-03-01 | 1996-07-01 |  | 1997-05-01 | 1998-10-01 | 1351360 | -319 | 1351041 | 1351041 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed; PCR submitted to 29th ExCom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/ARS/13/INV/79 | 1998-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Umbrella project to complete CFC phaseout in general purpose aerosols at NCLI and Fujiang Light Industry Co. | Individual | ASP | CPR | ARS | 24 | INV | 244 | N | O | I | CFC | 1224 | 1224 | 0 | 0 | 1998-03-01 | 2000-03-01 | 2000-04-01 |  | 2002-12-01 | 2004-05-01 | 547675 | 0 | 547675 | 547675 | 100 | 0 | 0 |  | 71197.75 | 0 | 71197.75 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Project financially completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/ARS/24/INV/244 |  |  |  | 2002-06-01 |  |  |  |  | INV | 0 | 0 | 0 | 0
ONG | IBRD | Project preparation for pharmaceutical aerosol |  | ASP | CPR | ARS | 43 | PRP | 415 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-07-01 |  | 2005-07-01 | 2005-07-01 |  |  | 135500 | 0 | 135500 | 0 | 0 | 135500 | 135500 | 93500 | 10163 | 0 | 0 | 10163 | 10163 | 2004 | #NAME? | #NAME? | #NAME? | #NAME? | China is preparing the sector plan. Preparation progress will be dicussed during the Feb. 05 WB China ODS mission. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/ARS/43/PRP/415 | [7 empty] | 2004 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Zhejiang foam plant conversion to butane | Individual | ASP | CPR | FOA | 7 | INV | 15 | N | O | I | CFC | 400 | 400 | 0 | 0 | 1992-06-01 | 1994-04-01 | 1994-06-01 |  | 1995-09-01 | 1996-09-01 | 1042000 | -49000 | 993000 | 993000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and commissioned. ODP phaseout target reached. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/7/INV/15 | 1995-09-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project I: 50% CFC foam | Individual | ASP | CPR | FOA | 7 | INV | 16 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1994-06-01 | 1994-06-01 |  | 1996-06-01 | 1996-06-01 | 645000 | 0 | 645000 | 645000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Fully disbursed and distributed to 50% foam projects that were approved a year after this approval. Disbursed amount appeared to exceed grant by $1000. Thru Dec. 37/14, the Bank was able to return the $1,000 to the MLF in the context of the reconciliation of the Accounts of the Fund at the 38th ExCom (Dec. 38/9). |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/7/INV/16 | 1996-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Liming Research and development of polyol and blended polyol production techniques for 50% reduced CFC foam | Individual | ASP | CPR | FOA | 10 | INV | 42 | N | O | D | CFC | 0 | 0 | 0 | 0 | 1993-06-01 | 1995-01-01 | 1995-06-01 |  | 1996-01-01 | 1996-09-01 | 457000 | 0 | 457000 | 457000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and commissioned. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/10/INV/42 | 1996-01-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Wuxi production of blended polyol for 50% reduced CFC foam | Individual | ASP | CPR | FOA | 10 | INV | 43 | N | O | D | CFC | 0 | 0 | 0 | 0 | 1993-06-01 | 1994-11-01 | 1995-06-01 |  | 1995-09-01 | 1997-05-01 | 264000 | 0 | 264000 | 264000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and commissioned. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/10/INV/43 | 1995-09-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Chengde conversion to 50% reduced CFC foam in insulation panel and in-situ foaming formulations | Individual | ASP | CPR | FOA | 10 | INV | 44 | N | O | D | CFC | 32 | 50 | 0 | 0 | 1993-06-01 | 1994-11-01 | 1997-06-01 |  | 1994-10-01 | 1996-09-01 | 163000 | 0 | 163000 | 163000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and commissioned. Actual ODP phaseout exceeded target. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/10/INV/44 | 1995-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Dalian conversion to 50% CFC reduced foam in insulation panel | Individual | ASP | CPR | FOA | 10 | INV | 45 | N | O | D | CFC | 14 | 30 | 0 | 0 | 1993-06-01 | 1995-01-01 | 1995-06-01 |  | 1996-06-01 | 1997-06-01 | 275000 | 0 | 275000 | 275000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and commissioned. Actual ODP phaseout exceeded target. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/10/INV/45 | 1996-03-01 | [7 empty] | INV | 0 | 0 | 0 | 0
TRF | IBRD | Tianjin conversion to 50% reduced CFC foam in insulation panel | Individual | ASP | CPR | FOA | 10 | INV | 46 | N | O | I |  | 0 | 0 | 0 | 0 | 1993-06-01 |  | 1995-06-01 |  |  | 1995-07-01 | 443000 | -443000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Project Transferred to UNDP. $443,000 credited to the MLF at 17th Meeting. |  |  | #NAME? | 0 | 0 | 0 | 0 | CPR/FOA/10/INV/46 | 1995-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Qindao Haier conversion to 50% reduced CFC foam in freezer cabinets | Individual | ASP | CPR | FOA | 10 | INV | 47 | N | O | D | CFC | 120 | 232 | 0 | 0 | 1993-06-01 | 1994-10-01 | 1995-06-01 |  | 1994-06-01 | 1997-06-01 | 476000 | 0 | 476000 | 476000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and commissioned. Actual ODP phaseout exceeded target. The factory also began developing 100% CFC-free technology. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/10/INV/47 | 1994-08-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Henan Xinfei conversion to 50% reduced CFC foam in refrigerators | Individual | ASP | CPR | FOA | 10 | INV | 48 | N | O | D | CFC | 103 | 250 | 0 | 0 | 1993-06-01 | 1995-01-01 | 1995-06-01 |  | 1994-10-01 | 1997-06-01 | 1042000 | 0 | 1042000 | 1042000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and commissioned. Actual ODP phaseout exceeded target. Funding approved for final conversion to non-ODS. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/10/INV/48 | 1996-11-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Shangling conversion to 50% reduced CFC foam in refrigerators | Individual | ASP | CPR | FOA | 10 | INV | 49 | N | O | I | CFC | 103 | 244.1 | 0 | 0 | 1993-06-01 | 1995-12-01 | 1995-06-01 |  | 1996-06-01 | 1997-06-01 | 958000 | 0 | 958000 | 958000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and commissioned. Actual ODP phaseout exceeded target. The factory also began developing 100% CFC-free technology. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/10/INV/49 | 1996-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Shuangyan conversion to 50% reduced CFC foam in refrigerators | Individual | ASP | CPR | FOA | 10 | INV | 50 | N | O | D | CFC | 28 | 63 | 0 | 0 | 1993-06-01 | 1994-10-01 | 1995-06-01 |  | 1993-06-01 | 1997-03-01 | 485000 | 0 | 485000 | 485000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and commissioned. Actual ODP phaseout exceeded target. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/10/INV/50 | 1994-03-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Shenyang production of blended polyol for 50% reduced CFC foam | Individual | ASP | CPR | FOA | 10 | INV | 51 | N | O | D | CFC | 0 | 0 | 0 | 0 | 1993-06-01 | 1994-09-01 | 1997-06-01 |  | 1994-08-01 | 1996-12-01 | 165000 | 0 | 165000 | 165000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and commissioned. By using the contingency fund, the factory went one step ahead to develop 100% CFC-free technology. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/10/INV/51 | 1995-09-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of extruded polyethylene and polystyrene foam at Shanghai No. 18 Plastic Product Plant | Individual | ASP | CPR | FOA | 13 | INV | 72 | N | O | I | CFC | 200 | 200 | 0 | 0 | 1994-07-01 | 1996-09-01 | 1995-07-01 |  | 1998-09-01 | 1998-09-01 | 450000 | 0 | 450000 | 450000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed; PCR submitted to the 27th ExCom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/13/INV/72 | 1997-02-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam at Shanghai No. 6 Plastic Product Plant | Individual | ASP | CPR | FOA | 13 | INV | 75 | N | O | I | CFC | 105 | 105 | 0 | 0 | 1994-07-01 | 1996-10-01 | 1995-07-01 |  | 1998-06-01 | 1998-12-01 | 687000 | -1292 | 685708 | 685708 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed; PCR submitted to 31th ExCom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/13/INV/75 | 1997-02-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam (slabstock) in Gaofeng Plastic Plant | Individual | ASP | CPR | FOA | 15 | INV | 108 | N | O | I | CFC | 180 | 180 | 0 | 0 | 1994-12-01 | 1996-10-01 | 1995-12-01 |  | 1999-01-01 | 2002-09-01 | 458400 | 0 | 458400 | 458400 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/15/INV/108 | 1997-12-01 | 1999-05-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam (slabstock) at Hebei Dongfeng Plastic Plant | Individual | ASP | CPR | FOA | 15 | INV | 109 | N | O | I | CFC | 110 | 110 | 0 | 0 | 1994-12-01 | 1996-11-01 | 1995-12-01 |  | 1999-05-01 | 1999-03-01 | 268600 | 0 | 268600 | 268600 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. PCR submitted to 30th ExCom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/15/INV/109 | 1997-12-01 | 1999-01-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of extruded polyethylene and polystyrene foam sheet at Lanzhou Plastic Packing Material Factory | Individual | ASP | CPR | FOA | 15 | INV | 83 | N | O | I | CFC | 200 | 200 | 0 | 0 | 1994-12-01 | 1996-08-01 | 1995-12-01 |  | 1997-08-01 | 1997-11-01 | 222100 | -37 | 222063 | 222063 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed; PCR submitted to ExCom in January 1999. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/15/INV/83 | 1997-03-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of extruded polyethylene and polystyrene foam sheet at Cangzhou No. 2 Plastic Plant | Individual | ASP | CPR | FOA | 15 | INV | 84 | N | O | I | CFC | 140 | 140 | 0 | 0 | 1994-12-01 | 1996-08-01 | 1995-12-01 |  | 1998-11-01 | 1999-04-01 | 394000 | 0 | 394000 | 394000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. PCR submitted to the 30th ExCom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/15/INV/84 | 1997-03-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam (slabstock) at Beijing Foam Plastic General Factory | Individual | ASP | CPR | FOA | 15 | INV | 85 | N | O | I | CFC | 100 | 100 | 0 | 0 | 1994-12-01 | 1996-10-01 | 1995-12-01 |  | 1999-11-01 | 1999-11-01 | 720000 | 0 | 720000 | 720000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. PCR submitted December 2000. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/15/INV/85 | 1997-06-01 | 1999-05-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in manufacture of extruded polyethylene and polystyrene foam sheet at Zhengzhou Plastic Plant | Individual | ASP | CPR | FOA | 15 | INV | 86 | N | O | I | CFC | 260 | 260 | 0 | 0 | 1994-12-01 | 1996-08-01 | 1995-12-01 |  | 2003-04-01 | 2004-05-01 | 267100 | 0 | 267100 | 267100 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Project financially completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/15/INV/86 | 1997-03-01 | 1999-09-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam (slabstock) at Yifeng Polyurethane Plastic Plant | Individual | ASP | CPR | FOA | 17 | INV | 122 | N | O | I | CFC | 90 | 60 | 0 | 0 | 1995-07-01 | 1998-01-01 | 1997-01-01 |  | 1998-04-01 | 1998-08-01 | 214600 | 0 | 214600 | 214600 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project complete; PCR submitted to 29th ExCom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/17/INV/122 | 1998-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible (slabstock) polyurethane foam at Liangzhu | Individual | ASP | CPR | FOA | 17 | INV | 137 | N | O | I | CFC | 120 | 120 | 0 | 0 | 1995-07-01 | 1997-11-01 | 1997-01-01 |  | 2000-08-01 | 2002-09-01 | 167800 | 0 | 167800 | 167800 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed, PCR submitted to ExCom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/17/INV/137 | 1997-12-01 | 1999-08-01 | [6 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion to CFC-free technology in the manufacture of flexible (slabstock) polyurethane foam at Zhenjiang No. 5 Plastic Factory | Individual | ASP | CPR | FOA | 17 | INV | 138 | N | O | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-12-01 | 1997-01-01 |  |  | 2001-03-01 | 276800 | -60003 | 216797 | 216797 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project cancelled. Remaining amount of $60,000 has been returned to ExCom. |  |  | #NAME? | 0 | 0 | 0 | 0 | CPR/FOA/17/INV/138 | 1998-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible polyurethane foam (slabstock) at Penglai Polyurethane Plastic Factory | Individual | ASP | CPR | FOA | 18 | INV | 140 | N | O | I | CFC | 70 | 70 | 0 | 0 | 1995-11-01 | 1998-01-01 | 1996-11-01 |  | 1998-06-01 | 1999-01-01 | 320583 | -83 | 320500 | 320500 | 100 | 0 | 0 |  | 41675.79 | -11 | 41665.63 | -0.84 | -0.84 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed; PCR submitted to the 30th ExCom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/18/INV/140 | 1997-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 foaming agent to cyclopentane at Chang Ling (Group) Co. Ltd. | Individual | ASP | CPR | FOA | 18 | INV | 146 | N | O | I | CFC | 190 | 190 | 0 | 0 | 1995-11-01 | 1997-12-01 | 1997-05-01 |  | 1999-12-01 | 1999-01-01 | 2062000 | 0 | 2062000 | 2062000 | 100 | 0 | 0 |  | 268060 | 0 | 268060 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed; PCR submitted December 2000. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/18/INV/146 | 1998-12-01 | 1999-06-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible (slabstock) polyurethane foam at Hangzhou Plastic Foam Factory | Individual | ASP | CPR | FOA | 19 | INV | 156 | N | O | I | CFC | 60 | 60 | 0 | 0 | 1996-05-01 | 1998-01-01 | 1997-11-01 |  | 1999-03-01 | 1999-08-01 | 317000 | 0 | 317000 | 317000 | 100 | 0 | 0 |  | 41210 | 0 | 41210 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Project complete; PCR submitted to 29th ExCom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/19/INV/156 | 1999-06-01 | 1999-03-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible (slabstock) polyurethane foam at Qingyang Chemical Corp. | Individual | ASP | CPR | FOA | 19 | INV | 157 | N | O | I | CFC | 90 | 90 | 0 | 0 | 1996-05-01 | 1999-08-01 | 1997-11-01 |  | 2001-09-01 | 2002-10-01 | 362000 | 0 | 362000 | 362000 | 100 | 0 | 0 |  | 47060 | 0 | 47060 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and PCR submitted to ExCom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/19/INV/157 | 1999-06-01 | 1999-12-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible (slabstock) polyurethane foam at Yinguang Chemical Group | Individual | ASP | CPR | FOA | 19 | INV | 158 | N | O | I | CFC | 85 | 85 | 0 | 0 | 1996-05-01 | 1997-10-01 | 1997-11-01 |  | 1999-05-01 | 2000-10-01 | 376000 | 0 | 376000 | 376000 | 100 | 0 | 0 |  | 48880 | 0 | 48880 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Project complete; PCR submitted to 29th ExCom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/19/INV/158 | 1999-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible (slabstock) polyurethane foam at Qinhuangdao No. 3 Plastic Plant | Individual | ASP | CPR | FOA | 19 | INV | 159 | N | O | I | CFC | 60 | 60 | 0 | 0 | 1996-05-01 | 1998-06-01 | 1997-11-01 |  | 1999-08-01 | 1998-10-01 | 370000 | 0 | 370000 | 370000 | 100 | 0 | 0 |  | 48100 | 0 | 48100 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. PCR will be submitted in January 2001. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/19/INV/159 | 1999-06-01 | 1999-06-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phaseout of CFCs in the manufacture of flexible slabstock PUF at Jinan Shiyan Plastic Plant | Individual | ASP | CPR | FOA | 19 | INV | 160 | N | O | I | CFC | 35 | 35 | 0 | 0 | 1996-05-01 | 1998-04-01 | 1997-05-01 |  | 1999-01-01 | 2001-11-23 | 209300 | 0 | 209300 | 209300.29 | 100 | -0.29 | -0.29 |  | 27209 | 0 | 27209.04 | -0.04 | -0.04 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed; PCR submitted. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/19/INV/160 | 1998-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible (slabstock) polyurethane foam at Zibo No. 3 Plastic Plant | Individual | ASP | CPR | FOA | 19 | INV | 162 | N | O | I | CFC | 100 | 55 | 0 | 0 | 1996-05-01 | 1997-12-01 | 1997-11-01 |  | 1999-01-01 | 2000-12-01 | 249000 | 0 | 249000 | 249000 | 100 | 0 | 0 |  | 32370 | 0 | 32370 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Project complete; PCR submitted to 29th ExCOM. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/19/INV/162 | 1999-06-01 | 1999-03-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of manufacturing facilities from CFC-11 foaming agent to cyclopentane at Hua Yi Electrical Appliance General Company | Individual | ASP | CPR | FOA | 19 | INV | 166 | N | O | I | CFC | 170 | 170 | 0 | 0 | 1996-05-01 | 1997-10-01 | 1997-02-01 |  | 1998-05-01 | 1998-09-01 | 972490 | 0 | 972490 | 972490 | 100 | 0 | 0 |  | 126423.7 | 0 | 126423.7 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed; PCR submitted to 29th ExCOM. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/19/INV/166 | 1997-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion of manufacturing facilities from CFC-11 foaming agent to cyclopentane at Shanghai Shuanglu Electrical Appliance Co. Ltd. | Individual | ASP | CPR | FOA | 20 | INV | 174 | N | O | I |  | 0 | 0 | 0 | 0 | 1996-10-01 |  | 1997-07-01 |  |  | 1999-07-01 | 1899230 | -1899230 | 0 | 0 | 0 | 0 | 0 |  | 246899.9 | -246900 | 0 | -0.1 | -0.1 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Project cancelled. Company bankrupt. Funds returned at 27th meeting. |  |  | #NAME? | 0 | 0 | 0 | 0 | CPR/FOA/20/INV/174 | 1998-06-01 | 1998-06-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of rigid PUF products at Handan Plastics No. 8 | Individual | ASP | CPR | FOA | 20 | INV | 177 | N | O | I | CFC | 101.64 | 101.64 | 0 | 0 | 1996-10-01 | 1998-05-01 | 1997-10-01 |  | 1999-05-01 | 2002-07-01 | 265000 | 0 | 265000 | 265000 | 100 | 0 | 0 |  | 34450 | 0 | 34450 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/20/INV/177 | 1997-12-01 | 1999-04-01 | [6 empty] | INV | 0 | 0 | 0 | 0
ONG | IBRD | Conversion to CFC-free technology in the manufacture of flexibe (slabstock) polyurethane foam at Chengdu Plastics No. 7 | Individual | ASP | CPR | FOA | 20 | INV | 179 | N | O | I | CFC | 120 | 120 | 0 | 0 | 1996-10-01 | 2001-01-01 | 1998-04-01 | 2005-03-01 |  |  | 301000 | 0 | 301000 | 265943.8 | 88.35 | 35056.2 | 35056.2 | 35056.2 | 39130 | 0 | 34572.69 | 4557.31 | 4557.31 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Trial runs completed. Equipment disposal certificate expected to be sent to the Bank by Mar. 05. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/20/INV/179 | 1998-04-01 | 2000-12-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of rigid and spray polyurethane foam manufacture from CFC-11 to HCFC-141b foam blowing agent at Yantai Moon Group Co. Ltd. | Individual | ASP | CPR | FOA | 23 | INV | 227 | N | O | I | CFC | 462.6 | 462.6 | 0 | 0 | 1997-11-01 | 2000-09-01 | 1999-12-01 |  | 2001-12-01 | 2002-11-01 | 1132682 | -2956 | 1129726 | 1129726 | 100 | 0 | 0 |  | 147249 | -370 | 146879 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. PCR submitted to ExCom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/23/INV/227 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of rigid and spray polyurethane foam manufacture from CFC-11 to HCFC-141b foam blowing agent at Shanghai General Machinery Company (SGMC) | Individual | ASP | CPR | FOA | 23 | INV | 230 | N | O | I | CFC | 88.3 | 88.3 | 0 | 0 | 1997-11-01 | 2000-09-01 | 1999-12-01 |  | 2002-12-01 | 2004-09-01 | 380300 | -1711.2 | 378588.8 | 378588.8 | 100 | 0 | 0 |  | 49439 | -171.12 | 49267.88 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Financially completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/23/INV/230 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture to forced cooling and methylene chloride at Wuxi New Type Raw Material Plant | Individual | ASP | CPR | FOA | 25 | INV | 252 | N | O | I | CFC | 231 | 231 | 0 | 0 | 1998-07-01 | 1999-04-01 | 2001-08-01 |  | 1999-10-01 | 2002-08-01 | 488150 | 0 | 488150 | 488150 | 100 | 0 | 0 |  | 63459.5 | 0 | 63459.5 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/25/INV/252 | [8 empty] | INV | 0 | 0 | 0 | 0
ONG | IBRD | Conversion of refrigerator manufacture from CFC-11 to pentane foam blowing agent in the production of PU insulation panels at Foshan Refrigeration Equipment General Factory | Individual | ASP | CPR | FOA | 26 | INV | 267 | N | O | I | CFC | 120.3 | 120.3 | 0 | 0 | 1998-11-01 | 2000-09-01 | 2001-12-01 | 2005-03-01 |  |  | 743500 | 0 | 743500 | 484592.4 | 65.17 | 258907.6 | 258907.6 | 258907.6 | 91785 | 0 | 59822.88 | 31962.12 | 31962.12 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Trial run completed, phaseout achieved. Disposal certificate to be sent to the Bank by Mar. 05. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/26/INV/267 | [8 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Handan Fuyang Chemical Corporation | Individual | ASP | CPR | FOA | 27 | INV | 269 | N | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 |  | 2002-10-01 |  |  | 2001-12-01 | 436100 | -436100 | 0 | 0 | 0 | 0 | 0 |  | 56693 | -55842.6 | 850.4 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Project cancelled at the 35th ExCom. |  |  | #NAME? | 0 | 0 | 0 | 0 | CPR/FOA/27/INV/269 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phaseout of CFC-11 in the manufacture of rigid polyurethane foam through the use of HCFC-141b at Qingdao Changlong Commercial Machinery Co. Ltd. | Individual | ASP | CPR | FOA | 27 | INV | 270 | N | O | I | CFC | 57.7 | 57.7 | 0 | 0 | 1999-03-01 | 2000-06-01 | 2002-04-01 |  | 2002-02-01 | 2003-10-01 | 451791 | -3921.96 | 447869.04 | 447869.04 | 100 | 0 | 0 |  | 58732.83 | -490.25 | 58242.58 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Physically and financially completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/27/INV/270 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology in Xiaoshan Polyurethane Foam Plant | Individual | ASP | CPR | FOA | 27 | INV | 271 | N | O | I | CFC | 111 | 111 | 0 | 0 | 1999-03-01 | 2001-01-01 | 2002-10-01 |  | 2003-12-01 | 2004-07-01 | 603058 | 0 | 603058 | 603058 | 100 | 0 | 0 |  | 76336.38 | 0 | 76336.38 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Project financially completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/27/INV/271 | [8 empty] | INV | 0 | 0 | 0 | 0
COM | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Shenyin Polyurethane Xinzhuang Plant | Individual | ASP | CPR | FOA | 27 | INV | 274 | N | O | I | CFC | 86.1 | 86.1 | 0 | 0 | 1999-03-01 | 2001-01-01 | 2002-10-01 |  | 2004-11-01 |  | 536403 | 0 | 536403 | 456426.1 | 85.09 | 79976.9 | 79976.9 | 79976.9 | 69004.33 | 0 | 58715.89 | 10288.44 | 10288.44 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Project physically completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/27/INV/274 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Henan Huojia Huashi Co. | Individual | ASP | CPR | FOA | 27 | INV | 275 | N | O | I | CFC | 109.5 | 109.5 | 0 | 0 | 1999-03-01 | 2001-01-01 | 2002-10-01 |  | 2003-12-01 | 2004-07-01 | 583186 | 0 | 583186 | 583186 | 100 | 0 | 0 |  | 74150.46 | 0 | 74150.46 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Project financially completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/27/INV/275 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phaseout of CFC-11 in the manufacture of rigid polyurethane foam through the use of HCFC-141b at Zhenjiang Commercial Refrigeration Equipment General Plant | Individual | ASP | CPR | FOA | 27 | INV | 276 | N | O | I | CFC | 30.81 | 30.81 | 0 | 0 | 1999-03-01 | 2000-01-01 | 2002-04-01 |  | 2002-10-01 | 2003-10-01 | 145376 | -4908 | 140468 | 140468 | 100 | 0 | 0 |  | 18899 | -490.8 | 18408.2 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/27/INV/276 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Jiangsu Haimen Foam plant | Individual | ASP | CPR | FOA | 27 | INV | 277 | N | O | I | CFC | 73 | 73 | 0 | 0 | 1999-03-01 | 2001-01-01 | 2002-04-01 |  | 2004-08-01 | 2004-12-01 | 454790 | 0 | 454790 | 454790 | 100 | 0 | 0 |  | 59122.7 | 0 | 59122.7 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Project financially completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/27/INV/277 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phaseout of CFC-11 in the manufacture of rigid polyurethane foam through the use of HCFC-141b at Shanghai Haiou Electric Appliance General Factory | Individual | ASP | CPR | FOA | 27 | INV | 280 | N | O | I | CFC | 33.34 | 33.34 | 0 | 0 | 1999-03-01 | 2000-09-01 | 2002-04-01 |  | 2002-09-01 | 2004-04-01 | 261052 | 0 | 261052 | 261052 | 100 | 0 | 0 |  | 33936.76 | 0 | 33936.76 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Financially completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/27/INV/280 | [8 empty] | INV | 0 | 0 | 0 | 0
COM | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology in Putuo Zhujiajian Rubber and Plastic Plant | Individual | ASP | CPR | FOA | 27 | INV | 281 | N | O | I | CFC | 112 | 112 | 0 | 0 | 1999-03-01 | 2001-01-01 | 2002-10-01 |  | 2004-07-01 |  | 525483 | 0 | 525483 | 501846.9 | 95.5 | 23636.1 | 23636.1 | 23636.1 | 67803.13 | 0 | 64753.36 | 3049.77 | 3049.77 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Physically completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/27/INV/281 | [8 empty] | INV | 0 | 0 | 0 | 0
COM | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Shanghai Shenyin Polyurethane Baoshan Plant | Individual | ASP | CPR | FOA | 27 | INV | 284 | N | O | I | CFC | 76 | 76 | 0 | 0 | 1999-03-01 | 2001-01-01 | 2002-04-01 |  | 2004-10-01 |  | 473480 | 0 | 473480 | 382256.5 | 80.73 | 91223.5 | 91223.5 | 91223.5 | 61552.4 | 0 | 49693.35 | 11859.05 | 11859.05 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Physically completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/27/INV/284 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Chengdu Jinjiang Foam General Plant | Individual | ASP | CPR | FOA | 27 | INV | 285 | N | O | I | CFC | 89 | 89 | 0 | 0 | 1999-03-01 | 2001-01-01 | 2002-10-01 |  | 2004-08-01 | 2004-11-01 | 554470 | 0 | 554470 | 554470 | 100 | 0 | 0 |  | 70991.7 | 0 | 70991.7 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Financially completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/27/INV/285 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Wuhan Commercial Machinery Factory | Individual | ASP | CPR | FOA | 28 | INV | 288 | N | O | I | CFC | 29.3 | 29.3 | 0 | 0 | 1999-07-01 | 2000-09-01 | 2002-08-01 |  | 2003-11-01 | 2004-11-01 | 149195 | 0 | 149195 | 149195 | 100 | 0 | 0 |  | 19395.35 | 0 | 19395.35 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Project financially completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/28/INV/288 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Heilongjiang Commercial Installation Corporation | Individual | ASP | CPR | FOA | 28 | INV | 292 | N | O | I | CFC | 52.6 | 52.6 | 0 | 0 | 1999-07-01 | 2000-09-01 | 2002-08-01 |  | 2001-11-01 | 2003-02-01 | 411858 | 0 | 411858 | 411858 | 100 | 0 | 0 |  | 53541.54 | 0 | 53541.54 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Project physically and financially completed and PCR submitted. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/28/INV/292 | [8 empty] | INV | 0 | 0 | 0 | 0
COM | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology in Changzhou Huangfa Co. Ltd., Foam Plant | Individual | ASP | CPR | FOA | 28 | INV | 293 | N | O | I | CFC | 70.7 | 70.7 | 0 | 0 | 1999-07-01 | 2001-01-01 | 2002-08-01 |  | 2004-06-01 |  | 440461 | 0 | 440461 | 396415 | 90 | 44046 | 44046 | 44046 | 57259.93 | 0 | 51533.95 | 5725.98 | 5725.98 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Physically completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/28/INV/293 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Jiangsu Taizhou Commercial Machiner General Factory | Individual | ASP | CPR | FOA | 28 | INV | 294 | N | O | I | CFC | 28.3 | 28.3 | 0 | 0 | 1999-07-01 | 2000-09-01 | 2002-08-01 |  | 2003-05-01 | 2004-09-01 | 192890 | -106.2 | 192783.8 | 192783.8 | 100 | 0 | 0 |  | 25075.7 | -10.62 | 25065.08 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Project financially completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/28/INV/294 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phaseout of CFC-11 by conversion to n-pentane technology in the manufacture of rigid polyurethane foam sandwich panels at Chengde Commercial Machinery Group Co. Ltd. | Individual | ASP | CPR | FOA | 28 | INV | 295 | N | O | I | CFC | 106 | 106 | 0 | 0 | 1999-07-01 | 2000-09-01 | 2002-08-01 |  | 2003-05-01 | 2004-07-01 | 829980 | 0 | 829980 | 829980 | 100 | 0 | 0 |  | 101297.8 | 0 | 101297.8 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Project financially completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/28/INV/295 | [8 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology in Shandong Tianhua (Group) Plastic Plant | Individual | ASP | CPR | FOA | 28 | INV | 296 | N | O | I |  | 0 | 0 | 0 | 0 | 1999-07-01 |  | 2002-08-01 |  |  | 2001-12-01 | 534534 | -534534 | 0 | 0 | 0 | 0 | 0 |  | 68798.74 | -67766.76 | 1031.98 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Project cancelled at the 35 th ExCom. |  |  | #NAME? | 0 | 0 | 0 | 0 | CPR/FOA/28/INV/296 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane foam at Guangdong Zhujiang Refrigeration and Air Conditioning Co. | Individual | ASP | CPR | FOA | 28 | INV | 299 | N | O | I | CFC | 87.7 | 87.7 | 0 | 0 | 1999-07-01 | 2000-09-01 | 2002-08-01 |  | 2002-02-01 | 2003-06-01 | 581230 | 0 | 581230 | 581230 | 100 | 0 | 0 |  | 73935.3 | 0 | 73935.3 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. PCR submitted. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/28/INV/299 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Chengde Machinery Installation Co. Qinghuangdao Branch | Individual | ASP | CPR | FOA | 29 | INV | 310 | N | O | I | CFC | 19.99 | 19.99 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2002-12-01 |  | 2001-12-01 | 2004-04-01 | 156600 | -5284 | 151316 | 151316 | 100 | 0 | 0 |  | 20358 | -660.5 | 19697.5 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Project financially completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/29/INV/310 | [8 empty] | INV | 0 | 0 | 0 | 0
ONG | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to methylene chloride and vertifoam from CFC-11 to liquid carbon dioxide technology at Shenzhou Foam Plant | Individual | ASP | CPR | FOA | 29 | INV | 311 | N | O | I | CFC | 134.9 | 0 | 0 | 0 | 1999-11-01 | 2001-10-01 | 2002-12-01 | 2005-06-01 |  |  | 609616 | 0 | 609616 | 521175.53 | 85.49 | 88440.47 | 88440.47 | 88440.47 | 77057.76 | 0 | 65878.55 | 11179.21 | 11179.21 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Trial run completed. Disposal certificate expected to be sent to the Bank by Jun. 05. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/29/INV/311 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Beijing Qianjin Polyurethane Corporation | Individual | ASP | CPR | FOA | 29 | INV | 317 | N | O | I | CFC | 64.77 | 64.77 | 0 | 0 | 1999-11-01 | 2002-12-01 | 2002-12-01 |  | 2002-08-01 | 2003-11-01 | 507109 | -79316 | 427793 | 427793 | 100 | 0 | 0 |  | 65781.99 | -10169 | 55613 | -0.01 | -0.01 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Project physically and financially completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/29/INV/317 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Beijing Hangxing Polyurethane Corporation | Individual | ASP | CPR | FOA | 29 | INV | 320 | N | O | I | CFC | 60.6 | 60.6 | 0 | 0 | 1999-11-01 | 2002-12-01 | 2002-12-01 |  | 2002-09-01 | 2004-09-01 | 471217 | -85471 | 385746 | 385746 | 100 | 0 | 0 |  | 61258.21 | -11111 | 50147.21 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Project financially completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/29/INV/320 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Yangzhou Tongli Refrigeration Container Co. Ltd. | Individual | ASP | CPR | FOA | 29 | INV | 321 | N | O | I | CFC | 14.63 | 14.63 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2002-12-01 |  | 2001-11-01 | 2003-06-01 | 114513 | 0 | 114513 | 114513 | 100 | 0 | 0 |  | 14886.69 | 0 | 14886.69 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Project physically and financially completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/29/INV/321 | [8 empty] | INV | 0 | 0 | 0 | 0
ONG | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology in Handan Fuxing Jiahe Foam Plant | Individual | ASP | CPR | FOA | 29 | INV | 322 | N | O | I | CFC | 136.67 | 0 | 0 | 0 | 1999-11-01 | 2002-12-01 | 2002-12-01 | 2005-01-01 |  |  | 515970 | 0 | 515970 | 500970 | 97.09 | 15000 | 15000 | 15000 | 66756.7 | 0 | 64815.99 | 1940.71 | 1940.71 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Trial run completed in Dec. 04. Equipment disposal expected in Jan. 05. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/29/INV/322 | [8 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology in Handan Huisheng Foam Plant | Individual | ASP | CPR | FOA | 29 | INV | 323 | N | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 |  | 2002-12-01 |  |  | 2003-12-01 | 522207 | -522207 | 0 | 0 | 0 | 0 | 0 |  | 67442.77 | -67443 | 0 | -0.23 | -0.23 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Project cancelled at the 40th ExCom. |  |  | #NAME? | 0 | 0 | 0 | 0 | CPR/FOA/29/INV/323 | [8 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion of polyurethane vertifoam manufacture from CFC-11 to liquid carbon dioxide technology in Tonxiang Shule Plastic Foam Plant | Individual | ASP | CPR | FOA | 29 | INV | 324 | N | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 |  | 2002-12-01 |  |  | 2001-12-01 | 498400 | -498400 | 0 | 0 | 0 | 0 | 0 |  | 64792 | -63820.12 | 971.88 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Project cancelled at the 35th ExCom. |  |  | #NAME? | 0 | 0 | 0 | 0 | CPR/FOA/29/INV/324 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b technology in the manufacture of rigid polyurethane insulation foam at Shanghai Furong Food Machinery Factory | Individual | ASP | CPR | FOA | 29 | INV | 335 | N | O | I | CFC | 23.1 | 23.1 | 0 | 0 | 1999-11-01 | 2000-09-01 | 2002-12-01 |  | 2002-06-01 | 2003-09-01 | 139379 | 0 | 139379 | 139379 | 100 | 0 | 0 |  | 18119.27 | 0 | 18119.27 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Physically completed. Draft PCR under review. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/29/INV/335 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the flexible polyurethane foam subsector |  | ASP | CPR | FOA | 30 | PRP | 342 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 20000 | 0 | 20000 | 20000 | 100 | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/30/PRP/342 | [7 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the foam flexible subsector |  | ASP | CPR | FOA | 30 | PRP | 349 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100 | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/30/PRP/349 | [7 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the foam (general) sector |  | ASP | CPR | FOA | 30 | PRP | 350 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2001-12-01 | 2001-12-01 | 300000 | 0 | 300000 | 300000 | 100 | 0 | 0 |  | 39000 | 0 | 39000 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/30/PRP/350 | [7 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the rigid polyurethane foam sub-sector |  | ASP | CPR | FOA | 30 | PRP | 353 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100 | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? | Completed |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/30/PRP/353 | [7 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
COM | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Qujing Plastic No. 2 Plant | Individual | ASP | CPR | FOA | 31 | INV | 358 | N | O | I | CFC | 99 | 99 | 0 | 0 | 2000-07-01 | 2003-04-01 | 2003-08-01 |  | 2004-09-01 |  | 600066 | 0 | 600066 | 535000 | 89.15 | 65066 | 65066 | 65066 | 76007.26 | 0 | 67765.69 | 8241.57 | 8241.57 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? | Physically completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/31/INV/358 | [7 empty] | 2000 | INV | 0 | 0 | 0 | 0
COM | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Wuxian Polyurethane Foam Plant | Individual | ASP | CPR | FOA | 31 | INV | 361 | N | O | I | CFC | 80 | 80 | 0 | 0 | 2000-07-01 | 2003-12-01 | 2003-08-01 |  | 2004-10-01 |  | 498400 | 0 | 498400 | 443655 | 89.01 | 54745 | 54745 | 54745 | 64792 | 0 | 57675.15 | 7116.85 | 7116.85 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? | Physically completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/31/INV/361 | [7 empty] | 2000 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Nantong Xinyuan Foam Plant | Individual | ASP | CPR | FOA | 31 | INV | 362 | N | O | I | CFC | 82 | 82 | 0 | 0 | 2000-07-01 | 2003-05-01 | 2003-08-01 |  | 2004-10-01 | 2004-12-01 | 510860 | 0 | 510860 | 510860 | 100 | 0 | 0 |  | 66194.6 | 0 | 66194.6 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? | Financially completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/31/INV/362 | [7 empty] | 2000 | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion of polyurethane slabstock manufacture from CFC-11 to liquid carbon dioxide technology at Jintan Tiaoxi Shuya Foam Plant | Individual | ASP | CPR | FOA | 31 | INV | 363 | N | O | I |  | 0 | 0 | 0 | 0 | 2000-07-01 |  | 2003-08-01 |  |  | 2001-12-01 | 420525 | -420525 | 0 | 0 | 0 | 0 | 0 |  | 54668.25 | -53848.23 | 820.02 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? | Project cancelled at the 35th ExCom. |  |  | #NAME? | 0 | 0 | 0 | 0 | CPR/FOA/31/INV/363 | [7 empty] | 2000 | INV | 0 | 0 | 0 | 0
COM | IBRD | Sector plan for phase-out of CFC-11 in the China foam sector: 2002 annual programme | Multiyear | ASP | CPR | FOA | 35 | INV | 380 | N | O | I | CFC | 2000 | 2000 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2002-12-01 |  | 2002-12-01 |  | 9940000 | 0 | 9940000 | 8044325.6 | 80.92 | 1895674.4 | 1895674.4 | 1895674.4 | 886600 | 0 | 717515 | 169085 | 169085 | 2001 | #NAME? | #NAME? | #NAME? | #NAME? | Three ODS conversion projects will be completed by Jun. 05. All TA activities have completed. SEPA will apply the last disburement in Feb. 05. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/35/INV/380 | [7 empty] | 2000 | INV | 14143 | 14143 | 0 | 0 | Yes | Yes | Yes
COM | IBRD | Sector plan for phase-out of CFC-11 in the China foam sector: 2003 annual programme | Multiyear | ASP | CPR | FOA | 38 | INV | 396 | N | O | I | CFC | 2500 | 2721 | 0 | 0 | 2002-11-01 | 2003-06-01 | 2003-12-01 |  | 2003-12-01 |  | 12570000 | 0 | 12570000 | 6405000 | 50.95 | 6165000 | 6165000 | 6165000 | 1115300 | 0 | 568297.26 | 547002.74 | 547002.74 | 2002 | #NAME? | #NAME? | #NAME? | #NAME? | Three conversion projects are expected to be completed by Jun. 06. All TA activities completed. China will apply the third disbursement of the 2003 AP in Feb. 05. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/38/INV/396 | [7 empty] | 2002 | INV | 13830 | 13830 | 0 | 0 | Yes | Yes | Yes
COM | IBRD | Sector plan for phase-out of CFC-11 in the China foam sector: 2004 annual programme | Multiyear | ASP | CPR | FOA | 41 | INV | 405 | N | O | I | CFC | 2500 | 2500 | 0 | 0 | 2003-12-01 | 2004-12-01 | 2004-12-01 |  | 2004-12-01 |  | 10903000 | 0 | 10903000 | 310000 | 2.84 | 10593000 | 10593000 | 8474400 | 961270 | 0 | 27331.35 | 933938.65 | 933938.65 | 2003 | #NAME? | #NAME? | #NAME? | #NAME? | 2004 AP has completed according to general obligations and with approval of the 2005 AP. Six conversion contracts signed within 2004 and are expected to be completed by Dec. 07. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/41/INV/405 | [7 empty] | 2003 | INV | 11666 | 11666 | 0 | 0 | Yes | No | No
ONG | IBRD | Sector plan for phase-out of CFC-11 in the China foam sector: 2005 annual programme | Multiyear | ASP | CPR | FOA | 44 | INV | 424 | N | O | I | CFC | 2500 | 0 | 0 | 0 | 2004-12-01 |  | 2005-12-01 | 2005-12-01 |  |  | 10903000 | 0 | 10903000 | 0 | 0 | 10903000 | 10903000 | 5659500 | 961270 | 0 | 0 | 961270 | 961270 | 2004 | #NAME? | #NAME? | #NAME? | #NAME? | Conversion contracts are under preparation. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/FOA/44/INV/424 | [7 empty] | 2004 | INV | 9000 | 0 | 0 | 0 |  | No | No
FIN | IBRD | Zhejiang halon extinguisher conversion | Individual | ASP | CPR | HAL | 7 | INV | 17 | N | O | I | HAL | 1200 | 1200 | 0 | 0 | 1992-06-01 | 1994-06-01 | 1993-12-01 |  | 1996-11-01 | 1996-01-01 | 797000 | -67000 | 730000 | 730000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and ODP phaseout target reached. The project was commissioned in May 97. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/HAL/7/INV/17 | 1996-11-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Beijing ABC powder production project | Individual | ASP | CPR | HAL | 7 | INV | 18 | N | O | I | HAL | 1200 | 1200 | 0 | 0 | 1992-06-01 | 1994-05-01 | 1993-06-01 |  | 1996-04-01 | 1996-08-01 | 403000 | 527000 | 930000 | 930000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Project complete. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/HAL/7/INV/18 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Additional preparation of halon sector approach |  | ASP | CPR | HAL | 20 | PRP | 184 | A | O | I |  | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-03-31 | 1997-08-01 |  | 1997-09-30 | 1997-09-30 | 132500 | 0 | 132500 | 132500 | 100 | 0 | 0 |  | 17225 | 0 | 17225 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/HAL/20/PRP/184 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the halon sector |  | ASP | CPR | HAL | 21 | PRP | 187 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-31 | 1997-12-31 | 133000 | -500 | 132500 | 132500 | 100 | 0 | 0 |  | 17290 | -65 | 17225 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/HAL/21/PRP/187 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
COM | IBRD | Sector plan for halon phaseout in China, 1998 Annual Programme | Individual | ASP | CPR | HAL | 23 | INV | 231 | N | O | I | HAL | 9939 | 9939 | 11739 | 11739 | 1997-11-01 | 1998-03-01 | 1998-12-01 |  | 1998-12-01 |  | 12400000 | 0 | 12400000 | 12400000 | 100 | 0 | 0 |  | 1240000 | 0 | 1240000 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | 1998 Annual Plan was successfully completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/HAL/23/INV/231 | [8 empty] | INV | 0 | 0 | 0 | 0
COM | IBRD | Sector plan for halon phaseout in China, 1999 Annual Programme | Multiyear | ASP | CPR | HAL | 26 | INV | 261 | N | O | I | HAL | 5370 | 5370 | 5826 | 5826 | 1998-11-01 | 1999-03-31 | 1999-12-01 |  | 1999-12-01 |  | 9700000 | 0 | 9700000 | 9700000 | 100 | 0 | 0 |  | 970000 | 0 | 970000 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | 1999 annual plan completed successfully. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/HAL/26/INV/261 | [8 empty] | INV | 19110 | 18880 | 24090 | 22735 | Yes | Yes | Yes
COM | IBRD | Sector plan for halon phaseout in China, 2000 Annual Programme | Multiyear | ASP | CPR | HAL | 29 | INV | 309 | N | O | I | HAL | 3712 | 3712 | 5970 | 5970 | 1999-11-01 | 2000-08-01 | 2000-12-01 |  | 2000-12-01 |  | 10600000 | 0 | 10600000 | 10600000 | 100 | 0 | 0 |  | 1060000 | 0 | 1060000 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Annual Program fully completed and disbursed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/HAL/29/INV/309 | [8 empty] | INV | 13740 | 14720 | 18120 | 16214 | Yes | Yes | Yes
COM | IBRD | Sector plan for halon phaseout in China, 2001 Annual Programme | Multiyear | ASP | CPR | HAL | 32 | INV | 364 | N | O | I | HAL | 1389 | 1389 | 1980 | 1980 | 2000-12-01 | 2002-12-01 | 2001-12-01 |  | 2001-12-01 |  | 4500000 | 0 | 4500000 | 4500000 | 100 | 0 | 0 |  | 450000 | 0 | 450000 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? | Completed and fully disbursed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/HAL/32/INV/364 | [7 empty] | 2000 | INV | 12351 | 10296 | 16131 | 11484 | Yes | Yes | Yes
COM | IBRD | Sector plan for halon phaseout in China, 2002 Annual Programme | Multiyear | ASP | CPR | HAL | 35 | INV | 383 | N | O | I | HAL | 2889 | 2889 | 2160 | 2160 | 2001-12-01 | 2002-12-01 | 2002-12-01 |  | 2002-12-01 |  | 3700000 | 0 | 3700000 | 3700000 | 100 | 0 | 0 |  | 370000 | 0 | 370000 | 0 | 0 | 2001 | #NAME? | #NAME? | #NAME? | #NAME? | Annual Program completed and final disbursement for the tranche made. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/HAL/35/INV/383 | [7 empty] | 2001 | INV | 9462 | 6492 | 13962 | 7408 | Yes | Yes | Yes
COM | IBRD | Sector plan for halon phaseout in China: 2003 annual programme | Multiyear | ASP | CPR | HAL | 38 | INV | 395 | N | O | I | HAL | 2292 | 2292 | 1992 | 1992 | 2002-11-01 | 2003-12-01 | 2003-12-01 |  | 2003-12-01 |  | 5900000 | 0 | 5900000 | 4766000 | 80.77 | 1134000 | 1134000 | 1134000 | 442500 | 0 | 357450 | 85050 | 85050 | 2002 | #NAME? | #NAME? | #NAME? | #NAME? | Annual Program completed and China has reported that production and consumption of halons were well within targets. Last disbursement (fouth one) will be finished in Mar. 05. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/HAL/38/INV/395 | [7 empty] | 2002 | INV | 7170 | 4945 | 11970 | 5654 | Yes | Yes | Yes
COM | IBRD | Sector plan for halon phase-out in China: 2004 annual programme | Multiyear | ASP | CPR | HAL | 41 | INV | 404 | N | O | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2004-09-01 | 2004-12-01 |  | 2004-12-01 |  | 1200000 | 0 | 1200000 | 120000 | 10 | 1080000 | 1080000 | 864000 | 90000 | 0 | 9000 | 81000 | 81000 | 2003 | #NAME? | #NAME? | #NAME? | #NAME? | Successfully completed. Disbursement has not completed yet. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/HAL/41/INV/404 | [7 empty] | 2003 | INV | 7170 | 4433 | 11970 | 5053 | Yes | No | No
ONG | IBRD | Sector plan for halon phase-out in China: 2005 annual programme | Multiyear | ASP | CPR | HAL | 44 | INV | 423 | N | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2005-12-01 | 2005-12-01 |  |  | 1800000 | 0 | 1800000 | 0 | 0 | 1800000 | 1800000 | 1000000 | 135000 | 0 | 0 | 135000 | 135000 | 2004 | #NAME? | #NAME? | #NAME? | #NAME? | Implementation of AP is underway. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/HAL/44/INV/423 | [7 empty] | 2004 | INV | 7170 | 0 | 7970 | 0 |  | No | No
FIN | IBRD | Project preparation in the solvent (process agent) sector |  | ASP | CPR | PAG | 30 | PRP | 354 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 100000 | 0 | 100000 | 100000 | 100 | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? | Completed |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/PAG/30/PRP/354 | [7 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation for the process agent sector plan |  | ASP | CPR | PAG | 34 | PRP | 374 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2002-06-01 |  | 2001-12-01 | 2001-12-01 | 122000 | 0 | 122000 | 122000 | 100 | 0 | 0 |  | 15860 | 0 | 15860 | 0 | 0 | 2001 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/PAG/34/PRP/374 | [7 empty] | 2001 | Non-INV | 0 | 0 | 0 | 0
COM | IBRD | Phase out the production and consumption of CTC for process agent and other non-identified uses (phase I): First tranche | Multiyear | ASP | CPR | PAG | 38 | INV | 397 | N | O | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-10-01 | 2003-12-01 |  | 2003-12-01 |  | 2000000 | 0 | 2000000 | 2000000 | 100 | 0 | 0 |  | 150000 | 0 | 150000 | 0 | 0 | 2002 | #NAME? | #NAME? | #NAME? | #NAME? | First tranche completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/PAG/38/INV/397 | [7 empty] | 2002 | INV | 0 | 0 | 0 | 0
COM | IBRD | Phase out the production and consumption of CTC for process agent and other non-identified uses (phase I): 2003 annual programme | Multi-Year Partial Phase-out | ASP | CPR | PAG | 39 | INV | 402 | N | O | I | CTC | 0 | 0 | 2638 | 2638 | 2003-04-01 | 2003-10-01 | 2004-04-01 |  | 2004-04-01 |  | 20000000 | 0 | 20000000 | 20000000 | 100 | 0 | 0 |  | 1500000 | 0 | 1500000 | 0 | 0 | 2003 | #NAME? | #NAME? | #NAME? | #NAME? | Annual Program completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/PAG/39/INV/402 | [7 empty] | 2003 | INV | 5066 | 5066 | 61514 | 61199 | Yes | Yes | Yes
ONG | IBRD | Project preparation for the second phase of process agents phase-out plan |  | ASP | CPR | PAG | 42 | PRP | 408 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-04-01 |  | 2004-12-01 | 2005-07-01 |  |  | 125000 | 0 | 125000 | 0 | 0 | 125000 | 125000 | 62500 | 9375 | 0 | 0 | 9375 | 9375 | 2004 | #NAME? | #NAME? | #NAME? | #NAME? | The CTC/PA sector plan is under development. A Feb. 05 mission will be conducted to finalize the sector plan for submission to the July Excom meeting for approval. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/PAG/42/PRP/408 | [7 empty] | 2003 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Phase out the production and consumption of CTC for process agent and other non-identified uses (phase I): 2004 annual programme | Multi-Year Partial Phase-out | ASP | CPR | PAG | 43 | INV | 416 | N | O | I | CTC | 0 | 0 | 6657 | 6657 | 2004-07-01 | 2004-10-01 | 2005-07-01 | 2005-07-01 |  |  | 16000000 | 0 | 16000000 | 8400000 | 52.5 | 7600000 | 7600000 | 7600000 | 1200000 | 0 | 630000 | 570000 | 570000 | 2004 | #NAME? | #NAME? | #NAME? | #NAME? | Implemented as planned. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/PAG/43/INV/416 | [7 empty] | 2004 | INV | 5063 | 5063 | 54857 | 52353 | Yes | Yes | No
FIN | IBRD | Production-sector pre-investment studies |  | ASP | CPR | PRO | 10 | PRP | 34 | N | O | D |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1994-06-28 | 1994-06-01 |  | 1996-03-01 | 1996-03-01 | 240000 | 80000 | 320000 | 320000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Project preparation activities are complete, including many proposals and six sector phaseout strategies. 26 foam projects, to be implemented by UNDP and the Bank, were prepared following first two workshops. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/PRO/10/PRP/34 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Halon 1211 production closure at Tongxiang Chemical Fertilizer Factory | Individual | ASP | CPR | PRO | 13 | INV | 76 | N | O | I | HAL | 0 | 0 | 1200 | 1200 | 1994-07-01 | 1996-08-01 | 1995-01-01 |  | 1994-12-01 | 1996-08-01 | 838000 | -730880 | 107120 | 107120 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed; PCR submitted to ExCom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/PRO/13/INV/76 | 1994-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects in the production sector for 1998 submission |  | ASP | CPR | PRO | 22 | PRP | 205 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-09-30 | 1998-12-01 |  | 1999-06-01 | 1999-06-01 | 350000 | 0 | 350000 | 350000 | 100 | 0 | 0 |  | 45500 | 0 | 45500 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/PRO/22/PRP/205 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
COM | IBRD | Sector plan for CFC production phaseout: 1999 annual programme | Multiyear | ASP | CPR | PRO | 27 | INV | 356 | N | O | I | CFC | 0 | 0 | 5497.6 | 5497.6 | 1999-03-01 | 1999-09-30 | 1999-12-01 |  | 1999-12-01 |  | 10000000 | 10000000 | 20000000 | 20000000 | 100 | 0 | 0 |  | 900000 | 900000 | 1800000 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | 1999 annual plan successfully completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/PRO/27/INV/356 | [8 empty] | INV | 0 | 0 | 44931 | 44793 | Yes | Yes | Yes
COM | IBRD | Sector plan for CFC production phaseout: 2000 annual programme | Multiyear | ASP | CPR | PRO | 30 | INV | 347 | N | O | I | CFC | 0 | 0 | 4931 | 4931 | 2000-03-01 | 2000-08-07 | 2000-12-01 |  | 2000-12-01 |  | 13000000 | 0 | 13000000 | 13000000 | 100 | 0 | 0 |  | 1170000 | 0 | 1170000 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? | Annual Program fully completed and disbursed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/PRO/30/INV/347 | [7 empty] | 2000 | INV | 0 | 0 | 40000 | 39990 | Yes | Yes | Yes
COM | IBRD | Sector plan for CFC production phaseout: 2001 annual programme | Multiyear | ASP | CPR | PRO | 33 | INV | 370 | N | O | I | CFC | 0 | 0 | 3800 | 3804 | 2001-03-01 | 2001-07-19 | 2001-12-01 |  | 2001-12-31 |  | 6500000 | 6500000 | 13000000 | 13000000 | 100 | 0 | 0 |  | 585000 | 585000 | 1170000 | 0 | 0 | 2001 | #NAME? | #NAME? | #NAME? | #NAME? | Annual Program fully completed and disbursed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/PRO/33/INV/370 | [7 empty] | 2001 | INV | 0 | 0 | 36200 | 36196 | Yes | Yes | Yes
COM | IBRD | Sector plan for CFC production phase-out: 2002 annual programme | Multiyear | ASP | CPR | PRO | 36 | INV | 391 | N | O | I | CFC | 0 | 0 | 3298 | 3300 | 2002-03-01 | 2002-12-01 | 2002-12-01 |  | 2002-12-01 |  | 13000000 | 0 | 13000000 | 13000000 | 100 | 0 | 0 |  | 910000 | 0 | 910000 | 0 | 0 | 2002 | #NAME? | #NAME? | #NAME? | #NAME? | Annual program completed. CFC production verified and confirmed to be within target. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/PRO/36/INV/391 | [7 empty] | 2002 | INV | 0 | 0 | 32900 | 32896 | Yes | Yes | Yes
FIN | IBRD | Project preparation funds for CTC and TCA production closure plan |  | ASP | CPR | PRO | 38 | PRP | 399 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-12-01 | 2003-12-01 |  | 2003-12-01 | 2003-12-01 | 150000 | 0 | 150000 | 150000 | 100 | 0 | 0 |  | 19500 | 0 | 19500 | 0 | 0 | 2002 | #NAME? | #NAME? | #NAME? | #NAME? | TCA Sector Plan will be submitted to the 43rd ExCom. CTC sector plan will be submitted for information purpose to the 42nd ExCom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/PRO/38/PRP/399 | [7 empty] | 2002 | Non-INV | 0 | 0 | 0 | 0
COM | IBRD | CFC production sector: 2003 annual programme | Multiyear | ASP | CPR | PRO | 39 | INV | 401 | N | O | I | CFC | 0 | 0 | 2900 | 2900 | 2003-04-01 | 2003-11-01 | 2003-12-01 |  | 2003-12-01 |  | 13000000 | 0 | 13000000 | 10400000 | 80 | 2600000 | 2600000 | 2600000 | 975000 | 0 | 780000 | 195000 | 195000 | 2003 | #NAME? | #NAME? | #NAME? | #NAME? | Annual Program completed. CFC production verified and confirmed to be within target. China will apply last disbursement in Feb. 05. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/PRO/39/INV/401 | [7 empty] | 2003 | INV | 0 | 0 | 30000 | 29986 | Yes | Yes | Yes
ONG | IBRD | Sector plan for CFC production phase-out: 2004 annual programme | Multiyear | ASP | CPR | PRO | 42 | INV | 411 | N | O | I | CFC | 0 | 0 | 4700 | 4700 | 2004-04-01 |  | 2004-12-01 | 2005-04-01 |  |  | 13000000 | 0 | 13000000 | 0 | 0 | 13000000 | 13000000 | 10400000 | 975000 | 0 | 0 | 975000 | 975000 | 2004 | #NAME? | #NAME? | #NAME? | #NAME? | Implementated as planned. But disbursement is slow. China will apply for a withdrawal application in Feb. 05 for the amount of US$6,500,000. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/PRO/42/INV/411 | [7 empty] | 2004 | INV | 0 | 0 | 25300 | 25285 | Yes | Yes | Yes
ONG | IBRD | Strategy for gradual phase-out of 1,1,1-trichlorethane (TCA) production (first stage programme) | Multiyear | ASP | CPR | PRO | 43 | INV | 417 | N | O | I | TCA | 0 | 0 | 33.8 | 0 | 2004-07-01 |  | 2008-07-01 | 2008-07-01 |  |  | 1400000 | 0 | 1400000 | 0 | 0 | 1400000 | 1400000 | 750000 | 105000 | 0 | 0 | 105000 | 105000 | 2004 | #NAME? | #NAME? | #NAME? | #NAME? | SEPA is preparing Project Implementation Manual for sector plan. PIM will be discussed during the coming Feb. 05 mission. SEPA will apply the first disbursement once agreement on the PIM is reached. SEPA is preparing TORs for TA activities under the sector plan. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/PRO/43/INV/417 | [7 empty] | 2003 | INV | 0 | 0 | 113 | 106 | Yes | Yes | No
FIN | IBRD | Pre-investment activities for Nanjing compressor and four refrigeration projects |  | ASP | CPR | REF | 8 | PRP | 24 | N | O | D | CFC | 0 | 0 | 0 | 0 | 1992-10-01 | 1993-09-30 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 300000 | 0 | 300000 | 300000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Project preparation activities are complete. In addition, a sector-wide phaseout strategy for the commercial refrigeration and air-conditioning sector was prepared (12,500 tons of CFCs). |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/REF/8/PRP/24 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Engineering assistance for conversion of refrigerator manufacture to use HFC-134a refrigerant with Tecumseh designed compressors at Hua Yi Electrical Appliances General Co. | Individual | ASP | CPR | REF | 13 | INV | 68 | N | O | I | CFC | 60 | 60 | 0 | 0 | 1994-07-01 | 1996-07-01 | 1996-07-01 |  | 1997-12-01 | 1998-09-01 | 1368000 | 0 | 1368000 | 1368000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Project complete; PCR submitted to 29th ExCom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/REF/13/INV/68 | 1997-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Engineering assistance for conversion of refrigerator manufacture to use HFC-152a refrigerant in conventional compressors at Wanbao Electrical Appliances Industrial Corporation | Individual | ASP | CPR | REF | 13 | INV | 69 | N | O | I | CFC | 80 | 80 | 0 | 0 | 1994-07-01 | 1996-12-01 | 1996-07-01 |  | 1999-07-01 | 2002-09-01 | 1360000 | 0 | 1360000 | 1360000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and PCR submitted to ExCom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/REF/13/INV/69 | 1997-12-01 | 1999-06-01 | [6 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Engineering assistance for conversion of refrigerator manufacture to a ternary blend refrigerant (MP-39) in conventional compressors at Shanghai Shuanglu Electrical Appliances Co. Ltd. | Individual | ASP | CPR | REF | 13 | INV | 70 | N | O | I | CFC | 70 | 64.3 | 0 | 0 | 1994-07-01 | 1996-05-01 | 1996-07-01 |  |  | 1998-09-01 | 1010000 | -82008 | 927992 | 927992 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Project cancelled due to financial difficulties. Undisbursed balance of $82,007.65 has been returned to MLF at the 30th ExCom Meeting. Four charging machines are proposed to be transferred to the new Shanghai Shangling project. PCR submitted. |  |  | #NAME? | 0 | 0 | 0 | 0 | CPR/REF/13/INV/70 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Engineering assistance for conversion of refrigerator manufacture to HFC-152a/HCFC-22 blended refrigerant in conventional compressors at Chang Ling Co. Ltd. | Individual | ASP | CPR | REF | 13 | INV | 71 | N | O | I | CFC | 70 | 70 | 0 | 0 | 1994-07-01 | 1996-03-01 | 1996-07-01 |  | 1997-09-01 | 1997-03-01 | 853000 | -10 | 852990 | 852990 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Project complete; PCR submitted to 26th ExCom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/REF/13/INV/71 | 1997-09-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Application development for conversion of compressor manufacturing to HFC-134a rotary compressor designs at Shanghai Refrigerator Compressor Co. Ltd. | Individual | ASP | CPR | REF | 13 | INV | 77 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1994-07-01 | 1996-07-01 | 1996-07-01 |  | 1997-05-01 | 1997-06-01 | 1280000 | 0 | 1280000 | 1280000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed; PCR submitted to ExCOM. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/REF/13/INV/77 | 1998-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Engineering assistance for conversion of refrigerator manufacture to HFC-134a with rotary compressor at Shanghai Shangling General Refrigerator Factory | Individual | ASP | CPR | REF | 13 | INV | 78 | N | O | I | CFC | 108 | 108 | 0 | 0 | 1994-07-01 | 1996-12-01 | 1996-07-01 |  | 2000-06-01 | 2002-09-01 | 1327000 | 0 | 1327000 | 1327000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/REF/13/INV/78 | 1998-01-01 | 1999-06-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of medium sized semi-hermetic CFC-12 air conditioning compressor production to HCFC-22 at Beijing Refrigerating Machinery Factory | Individual | ASP | CPR | REF | 15 | INV | 107 | N | O | I | CFC | 233 | 233 | 0 | 0 | 1994-12-01 | 1996-07-01 | 1997-12-01 |  | 2000-08-01 | 2002-04-01 | 3098000 | -1000 | 3097000 | 3097000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and PCR submitted. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/REF/15/INV/107 | 1999-06-01 | 1999-12-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of medium sized open-type CFC-12 refrigeration compressor production to HCFC-22 at Shanghai Refrigerating Machine Works (SRMW) | Individual | ASP | CPR | REF | 16 | INV | 110 | N | O | I | CFC | 162 | 162 | 0 | 0 | 1995-03-01 | 1996-07-01 | 1998-03-01 |  | 1998-09-01 | 1999-09-01 | 2710000 | 0 | 2710000 | 2710000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. PCR submitted to the ExCom March 2000. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/REF/16/INV/110 | 1999-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of small open-type CFC-12 refrigeration compressor production to HCFC-22 at Anhui Provincial Refrigerating Machinery Factory (APRMF) | Individual | ASP | CPR | REF | 16 | INV | 111 | N | O | I | CFC | 171 | 171 | 0 | 0 | 1995-03-01 | 1996-07-01 | 1998-03-01 |  | 2002-07-01 | 2004-04-01 | 2224000 | 0 | 2224000 | 2224000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project financially completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/REF/16/INV/111 | 1999-06-01 |  |  | 2001-06-01 |  |  |  |  | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of small semi-hermetic CFC-12 refrigeration compressor production to HCFC-22 at Jiangsu Taizhou Commercial Machinery Factory (JTCMF) | Individual | ASP | CPR | REF | 16 | INV | 112 | N | O | I | CFC | 285 | 285 | 0 | 0 | 1995-03-01 | 1996-10-01 | 1998-03-01 |  | 1999-12-01 | 2002-09-01 | 2797500 | 0 | 2797500 | 2797500 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/REF/16/INV/112 | 1999-06-01 | 1999-06-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of small semi-hermetic CFC-12 refrigeration compressor production to HCFC-22 at Nanjing Refrigerator General Works (NRGW) | Individual | ASP | CPR | REF | 16 | INV | 113 | N | O | I | CFC | 242 | 242 | 0 | 0 | 1995-03-01 | 1996-04-01 | 1998-03-01 |  | 1999-05-01 | 2002-04-01 | 2890000 | -27 | 2889973 | 2889973 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and PCR submitted. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/REF/16/INV/113 | 1998-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Production of small ammonia refrigerating compressor at Yantai Refrigerating Machinery Works (YRMW) | Individual | ASP | CPR | REF | 16 | INV | 114 | N | O | I | CFC | 240 | 240 | 0 | 0 | 1995-03-01 | 1996-12-01 | 1998-03-01 |  | 1999-05-01 | 2000-06-01 | 2874000 | 0 | 2874000 | 2874000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed.PCR and certificates were submitted to 30th ExCom Meeting. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/REF/16/INV/114 | 1999-06-01 | 1999-12-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-12 to HFC-134a MAC compressor at Shanghai Ek Chor General Machinery Co. Ltd. | Individual | ASP | CPR | REF | 17 | INV | 129 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-12-01 | 1996-07-01 |  | 1996-01-01 | 1998-06-01 | 961000 | 0 | 961000 | 961000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed; PCR submitted to the 30th ExCom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/REF/17/INV/129 | 1998-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-12 to HFC-134a MAC system at Yueyang Hengli Air Conditioning Equipment Co. Ltd. | Individual | ASP | CPR | REF | 18 | INV | 148 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-12-01 | 1997-11-01 |  | 1999-05-01 | 2000-02-01 | 1767961 | 0 | 1767961 | 1767961 | 100 | 0 | 0 |  | 229834.93 | 0 | 229834.93 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed; PCR submitted to the 31th ExCom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/REF/18/INV/148 | 1998-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-12 to HFC-134a MAC compressor at Guangzhou Haohua Automobile Parts Co. Ltd. | Individual | ASP | CPR | REF | 18 | INV | 149 | N | O | I |  | 0.65 | 0.65 | 0 | 0 | 1995-11-01 | 1996-11-01 | 1997-05-01 |  | 2001-03-01 | 2001-07-08 | 2212039 | -202829 | 2009210 | 2009210.43 | 100 | -0.43 | -0.43 |  | 287565.07 | -25353.62 | 262211.45 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed; Draft PCR is under review. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/REF/18/INV/149 | 1998-06-01 | 1999-12-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-12 to HFC-134a MAC system at Shanghai Automobile Air Conditioner Co. (SAAC) | Individual | ASP | CPR | REF | 18 | INV | 150 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-08-01 | 1996-11-01 |  | 1996-12-01 | 1997-03-01 | 1642330 | -30 | 1642300 | 1642300 | 100 | 0 | 0 |  | 213502.9 | -3.9 | 213499.15 | -0.15 | -0.15 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed; PCR submitted to the 30th ExCom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/REF/18/INV/150 | 1997-04-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of medium-sized semi-hermetic CFC-12 refrigerating compressor production to HCFC-22 production at Tianjin Tian Shan Refrigeration Equipment Co. | Individual | ASP | CPR | REF | 20 | INV | 175 | N | O | I | CFC | 275.5 | 275.5 | 0 | 0 | 1996-10-01 | 1997-11-01 | 2000-04-01 |  | 2003-05-01 | 2004-09-01 | 2256000 | 0 | 2256000 | 2256000 | 100 | 0 | 0 |  | 293280 | 0 | 293280 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Project financially completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/REF/20/INV/175 | 2000-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of manufacturing facilities from CFC-11 foaming agent to cyclopentane and CFC-12 refrigerant to HFC-134a at Gansu Changfeng Baoan Industry Co. Ltd. | Individual | ASP | CPR | REF | 20 | INV | 176 | N | O | I | CFC | 65.2 | 65.2 | 0 | 0 | 1996-10-01 | 1997-06-01 | 1998-10-01 |  | 2002-04-01 | 2004-07-01 | 634150 | 260000 | 894150 | 894150 | 100 | 0 | 0 |  | 82439.5 | 33800 | 116239.5 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Project financially completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/REF/20/INV/176 | 1999-06-01 |  | 2000-08-01 | [5 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of small semi-hermetic CFC-12 refrigerating compressor production at Shanghai General Machinery (Group) Corp. (SGMC) | Individual | ASP | CPR | REF | 20 | INV | 180 | N | O | I | CFC | 209 | 209 | 0 | 0 | 1996-10-01 | 1997-11-01 | 2000-04-01 |  | 2002-12-01 | 2004-04-01 | 2039800 | 0 | 2039800 | 2039800 | 100 | 0 | 0 |  | 265174 | 0 | 265174 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Project financially completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/REF/20/INV/180 | 2000-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-11 and CFC-12 centrifugal refrigerating compressor to HFC-134a centrifugal technology at Chongqing General Machinery Factory (CGMF) | Individual | ASP | CPR | REF | 20 | INV | 182 | N | O | I | CFC | 220 | 220 | 0 | 0 | 1996-10-01 | 1998-01-01 | 2000-04-01 |  | 2000-08-01 | 2002-03-01 | 2632000 | 0 | 2632000 | 2632000 | 100 | 0 | 0 |  | 342160 | 0 | 342160 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. PCR submitted to ExCom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/REF/20/INV/182 | 2000-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 small open-type and semi-hermetic refrigerating compressor to HCFC-22 refrigerating compressor at Zhenjiang Refrigerating Equipment Factory (ZREF) | Individual | ASP | CPR | REF | 20 | INV | 183 | N | O | I | CFC | 108.5 | 108.5 | 0 | 0 | 1996-10-01 | 1997-11-01 | 2000-04-01 |  | 2002-12-01 | 2004-04-01 | 1974000 | 0 | 1974000 | 1974000 | 100 | 0 | 0 |  | 256620 | 0 | 256620 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Project financially completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/REF/20/INV/183 | 2000-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 medium open-type refrigerating compressor to HCFC-22 compressor at Guangzhou Refrigerating Machinery Factory | Individual | ASP | CPR | REF | 22 | INV | 198 | N | O | I | CFC | 190 | 190 | 0 | 0 | 1997-05-01 | 1999-06-01 | 2000-06-01 |  | 2003-04-01 | 2004-09-01 | 1904769 | 0 | 1904769 | 1904769 | 100 | 0 | 0 |  | 247619.97 | 0 | 247619.97 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project financially completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/REF/22/INV/198 |  | 2000-06-01 |  | 2002-06-01 |  |  |  |  | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 small open-type refrigerating compressor to HCFC-22 refrigerating compressor at Subei Refrigeration Machinery Factory | Individual | ASP | CPR | REF | 22 | INV | 200 | N | O | I | CFC | 171 | 171 | 0 | 0 | 1997-05-01 | 1999-06-01 | 2000-06-01 |  | 2003-01-01 | 2004-04-01 | 1806908 | 0 | 1806908 | 1806908 | 100 | 0 | 0 |  | 234898.04 | 0 | 234898.04 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project financially completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/REF/22/INV/200 |  | 2000-06-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 medium open type refrigerating compressor at Wuhan New World Refrigeration Industrial Co. Ltd. | Individual | ASP | CPR | REF | 22 | INV | 208 | N | O | I | CFC | 209 | 209 | 0 | 0 | 1997-05-01 | 1999-09-01 | 2000-06-01 |  | 2003-08-01 | 2004-12-01 | 1459871 | 0 | 1459871 | 1459871 | 100 | 0 | 0 |  | 189783.23 | 0 | 189783.23 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project financially completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/REF/22/INV/208 |  | 2000-06-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 small open-type and semi-hermetic refrigerating compressor to HCFC-22 refrigerating compressor at Zhenjiang Refrigerating Equipment Factory (ZREF) | Individual | ASP | CPR | REF | 22 | INV | 209 | N | O | I | CFC | 186 | 186 | 0 | 0 | 1997-05-01 | 2001-12-31 | 2000-11-01 |  | 2002-12-01 | 2004-04-01 | 1048286 | 0 | 1048286 | 1048286 | 100 | 0 | 0 |  | 136277.18 | 0 | 136277.18 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project financially completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/REF/22/INV/209 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 small and medium open type refrigerating compressor production at Zhejiang Chunhui Company (Group) (ZCC) | Individual | ASP | CPR | REF | 22 | INV | 210 | N | O | I | CFC | 361 | 361 | 0 | 0 | 1997-05-01 | 1999-06-01 | 2000-06-01 |  | 2003-02-01 | 2004-05-01 | 3200394 | 0 | 3200394 | 3200394 | 100 | 0 | 0 |  | 416051.22 | 0 | 416051.22 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project is financially completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/REF/22/INV/210 |  | 2000-06-01 |  | 2002-06-01 |  |  |  |  | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 medium open type refrigerating compressor at Chongqing Bingyang Refrigerating Machine Co. | Individual | ASP | CPR | REF | 22 | INV | 214 | N | O | I | CFC | 190 | 190 | 0 | 0 | 1997-05-01 | 1999-06-01 | 2000-06-01 |  | 2003-12-01 | 2004-05-01 | 1805370 | 0 | 1805370 | 1805370 | 100 | 0 | 0 |  | 234698.1 | 0 | 234698.1 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project financially completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/REF/22/INV/214 |  | 2000-06-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 small open type refrigerating compressor production at Ningbo Refrigerating Machinery Factory | Individual | ASP | CPR | REF | 22 | INV | 215 | N | O | I | CFC | 171 | 171 | 0 | 0 | 1997-05-01 | 1999-06-01 | 2000-06-01 |  | 2002-10-01 | 2004-04-01 | 1786949 | 0 | 1786949 | 1786949 | 100 | 0 | 0 |  | 232303.37 | 0 | 232303.37 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project financially completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/REF/22/INV/215 |  | 2000-06-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Hefei General Machinery Research Institute (HGMRI): four technical assistance projects to support conversion of commercial refrigeration compressors | Individual | ASP | CPR | REF | 23 | INV | 218 | N | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 | 2000-06-01 | 2001-11-01 |  | 2002-11-01 | 2002-11-01 | 692400 | -39141 | 653259 | 653259 | 100 | 0 | 0 |  | 90012 | -4892.63 | 85119.37 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. Draft PCR underway. Savings to be returned to the MLF. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/REF/23/INV/218 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of refrigerator manufacture to HFC-134a refrigerant and cyclopentane foam blowing agent at Henan Xinfei Electric Co. Ltd. | Individual | ASP | CPR | REF | 23 | INV | 234 | N | O | I | CFC | 375 | 375 | 0 | 0 | 1997-11-01 | 1999-08-01 | 1999-12-01 |  | 1998-12-01 | 2000-09-01 | 1556490 | 0 | 1556490 | 1556490 | 100 | 0 | 0 |  | 202344 | 0 | 202344 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project was completed; PCR submitted to 30th ExCOM. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/REF/23/INV/234 | [8 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion of refrigerator manufacture to HFC-134a refrigerant and cyclopentane foam blowing agent at Shanghai Shangling Chang-An Refrigerator Co., Ltd (former Shanghai Yuandong Refrigerator Co. Ltd.) | Individual | ASP | CPR | REF | 23 | INV | 235 | N | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 |  | 2000-11-01 |  |  | 2000-12-01 | 1237663 | -1237663 | 0 | 0 | 0 | 0 | 0 |  | 160896 | -158482.56 | 2413.44 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project cancelled due to financial difficulties. |  |  | #NAME? | 0 | 0 | 0 | 0 | CPR/REF/23/INV/235 | [8 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion of refrigerator manufacture in Changhe Group to HFC-134a as refrigerant and cyclopentane as foam blowing agent | Individual | ASP | CPR | REF | 25 | INV | 251 | N | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 |  | 2001-08-01 |  |  | 2001-12-31 | 1267638 | -1267638 | 0 | 0 | 0 | 0 | 0 |  | 164792.94 | -162321.05 | 2471.89 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Project has been cancelled. |  |  | #NAME? | 0 | 0 | 0 | 0 | CPR/REF/25/INV/251 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | MAC ODS phaseout sector plan | One off phaseout | ASP | CPR | REF | 26 | INV | 255 | N | O | I | CFC | 40 | 40 | 0 | 0 | 1998-11-01 | 1999-05-01 | 2001-12-01 |  | 2001-12-01 | 2003-04-01 | 7700000 | 0 | 7700000 | 7700000 | 100 | 0 | 0 |  | 820000 | 0 | 820000 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. Completion report submitted. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/REF/26/INV/255 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of CFC-12 refrigerant with HCFC-22 in the manufacture of small open type compressors at Wuhan Commercial Machinery Factory | Individual | ASP | CPR | REF | 28 | INV | 298 | N | O | I | CFC | 104.2 | 104.2 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2002-08-01 |  | 2004-09-01 | 2004-09-01 | 1457583 | 0 | 1457583 | 1457583 | 100 | 0 | 0 |  | 170334.13 | 0 | 170334.13 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Project financially completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/REF/28/INV/298 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of CFC-12 refrigerant with HCFC-22 in the manufacture of small and medium sized open type compressors at Zhejiang Commercial Machinery Factory | Individual | ASP | CPR | REF | 28 | INV | 300 | N | O | I | CFC | 251.7 | 251.7 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2002-08-01 |  | 2004-09-01 | 2004-09-01 | 1710295 | 0 | 1710295 | 1710295 | 100 | 0 | 0 |  | 198132.45 | 0 | 198132.45 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Project financially completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/REF/28/INV/300 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of CFC-12 refrigerant with HCFC-22 in the manufacture of semi-hermetic compressors at Yueyang Hengli Air-Cool Equipment Co. Ltd. | Individual | ASP | CPR | REF | 28 | INV | 303 | N | O | I | CFC | 220.2 | 220.2 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2002-08-01 |  | 2004-09-01 | 2004-09-01 | 1951757 | 0 | 1951757 | 1951465.78 | 99.98 | 291.22 | 291.22 |  | 224693.27 | 0 | 224659.74 | 33.53 | 33.53 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Financially completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/REF/28/INV/303 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the commercial refrigeration sub-sector |  | ASP | CPR | REF | 30 | PRP | 351 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2001-12-01 |  | 2001-12-01 | 2001-12-01 | 60000 | 0 | 60000 | 60000 | 100 | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/REF/30/PRP/351 | [7 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the domestic refrigeration subsector |  | ASP | CPR | REF | 30 | PRP | 352 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 20000 | 0 | 20000 | 20000 | 100 | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/REF/30/PRP/352 | [7 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Replacement of CFC-11 foaming agent with cyclopentane and CFC-12 refrigerant with HFC-134a in the manufacture of domestic refrigerators at Shangling Electric Appliance (Group) Co. Ltd. | Individual | ASP | CPR | REF | 34 | INV | 378 | N | O | I | CFC | 174.2 | 0 | 0 | 0 | 2001-07-01 | 2003-05-01 | 2004-08-01 | 2005-10-01 |  |  | 1400000 | 0 | 1400000 | 51524.3 | 3.68 | 1348475.7 | 1348475.7 | 1348475 | 164000 | 0 | 6035.7 | 157964.3 | 157964.3 | 2001 | #NAME? | #NAME? | #NAME? | #NAME? | After consulting with SEPA, CEB cancelled 2nd bidding process and did the re-shopping. Three contracts now signed. C-pentane tank delivered and installation will be done in Jan. 05. Two units of c-pentane foaming equipment will be delivered in early 2005. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/REF/34/INV/378 | [7 empty] | 2000 | INV | 0 | 0 | 0 | 0
ONG | IBRD | Replacement of CFC-12 refrigerant with HCFC-22 in the manufacture of small and medium open compressors at 5 enterprises (Dalian No.2, Shanghai Minhang, Zhejiang Beifeng, Zhejiang Chunlian, Zhejiang Yuhuan) | One off phaseout | ASP | CPR | REF | 36 | INV | 389 | N | O | I | CFC | 764.9 | 0 | 0 | 0 | 2002-03-01 | 2003-02-01 | 2005-03-01 | 2005-12-01 |  |  | 5250852 | 0 | 5250852 | 2950852 | 56.19 | 2300000 | 2300000 | 2300000 | 587593.72 | 0 | 330213.48 | 257380.24 | 257380.24 | 2002 | #NAME? | #NAME? | #NAME? | #NAME? | Conversion for Dalian and Chunhui (which took over the 3 other companies) will be finished by the end of 2005. SEPA is working on necessary policies to be issued when the two phaseout contracts complete. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/REF/36/INV/389 | [7 empty] | 2001 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1991) |  | ASP | CPR | SEV | 4 | PRP | 1 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 184000 | -167746 | 16254 | 16254 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/SEV/4/PRP/1 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme studies | Individual | ASP | CPR | SEV | 6 | CPG | 12 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1992-12-01 |  | 1992-12-01 | 1992-12-01 | 180000 | -73841 | 106159 | 106159 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | CPR/SEV/6/CPG/12 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation advance for developing components of Project I (1992) |  | ASP | CPR | SEV | 7 | PRP | 21 | N | O | D |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | PPA I is complete. These funds were used to support implementation of the China ODS Projects I and II. No money was allocated, however $600,000 from ODS II and $900,000 from ODS I was used. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/SEV/7/PRP/21 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1993) |  | ASP | CPR | SEV | 9 | PRP | 31 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 326000 | -133667 | 192333 | 192333 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/SEV/9/PRP/31 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Financial agent fee for the implementation of approved projects (two aerosols, two foams, two halons) | Individual | ASP | CPR | SEV | 9 | TAS | 29 | N | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-06-01 | 1995-12-01 |  | 1996-12-01 | 1996-12-01 | 185000 | 0 | 185000 | 185000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | The FA completed appraisal reports for all subprojects and all have been cleared by the Bank. PPA I has been fully disbursed. ODS II was disbursed, and its accounts closed in 1997. Project completion report for ODS I& II completed. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | CPR/SEV/9/TAS/29 | 1996-12-01 | [7 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | User-sector pre-investment studies (1993) |  | ASP | CPR | SEV | 10 | PRP | 35 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-06-30 | 1994-06-01 |  | 1993-12-01 | 1993-12-01 | 280000 | -131872 | 148128 | 148128 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/SEV/10/PRP/35 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of projects ODS III (1994) |  | ASP | CPR | SEV | 12 | PRP | 62 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 660000 | -138768 | 521232 | 521232 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/SEV/12/PRP/62 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Supervision of project implementation of China ODS I (1994) |  | ASP | CPR | SEV | 12 | PRP | 63 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 79000 | -35235 | 43765 | 43765 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/SEV/12/PRP/63 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Supervision of project implementation of China ODS II (1994) |  | ASP | CPR | SEV | 12 | PRP | 64 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 110000 | 10949 | 120949 | 120949 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/SEV/12/PRP/64 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects ODS II (1995) |  | ASP | CPR | SEV | 16 | PRP | 120 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 103131 | 0 | 103131 | 103131 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/SEV/16/PRP/120 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects ODS III (1995) |  | ASP | CPR | SEV | 16 | PRP | 139 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 650000 | 0 | 650000 | 650000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Processing of the third ODS Phaseout project for China has been completed. Grant agreement was signed in June 1995. $50,000 was transferred from PPA-IV (China) (CPR/SEV/16/PRP/217) to this project preparation (ODS III - China). Thus, $700,000 was disbursed under this activity. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/SEV/16/PRP/139 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects ODS IV (1995) |  | ASP | CPR | SEV | 16 | PRP | 217 | N | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1996-12-31 | 1997-12-01 |  | 1997-12-31 | 1997-12-01 | 250000 | 0 | 250000 | 250000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Complete. Actual disbursement for PPA IV was $200,000. and the balance of $50,000 was utilized for project preparation under ODS III (CPR/SEV/16/PRP/139). |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/SEV/16/PRP/217 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects ODS I (1995) |  | ASP | CPR | SEV | 16 | PRP | 246 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 68017 | 0 | 68017 | 68017 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/SEV/16/PRP/246 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Development of a cost effective sector based ODS phase out approach | Individual | ASP | CPR | SEV | 17 | TAS | 136 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-07-01 | 1996-10-31 | 1996-12-01 |  | 1996-12-01 | 1996-12-01 | 350000 | -150000 | 200000 | 200000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | $100,000 transferred to PPA-V. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | CPR/SEV/17/TAS/136 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | ASP | CPR | SEV | 18 | PRP | 154 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 30000 | 0 | 30000 | 30000 | 100 | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Complete. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/SEV/18/PRP/154 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | ASP | CPR | SEV | 21 | PRP | 189 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-31 | 1997-12-31 | 250000 | 0 | 250000 | 250000 | 100 | 0 | 0 |  | 32500 | 0 | 32500 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/SEV/21/PRP/189 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the aerosol, foam, MAC and commercial refrigeration sectors |  | ASP | CPR | SEV | 24 | PRP | 243 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1999-06-01 | 1999-06-01 | 600000 | 0 | 600000 | 600000 | 100 | 0 | 0 |  | 78000 | 0 | 78000 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/SEV/24/PRP/243 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of projects in the foam, commercial refrigeration and CFC production sectors |  | ASP | CPR | SEV | 27 | PRP | 273 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-31 | 2001-01-01 |  | 1999-12-31 | 1999-12-31 | 300000 | 0 | 300000 | 300000 | 100 | 0 | 0 |  | 39000 | 0 | 39000 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | CPR/SEV/27/PRP/273 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Project preparation for the conversion of six aerosol plants from CFC-12 to LPG |  | LAC | ECU | ARS | 6 | PRP | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1992-12-01 |  |  | 1992-12-01 | 300000 | -300000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | 0 | 0 | 0 | 0 | ECU/ARS/6/PRP/2 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of 18 aerosol plants to hydrocarbon propellants (Laboratorios Windsor (60 ton CFC/year), Pro Quim (6 ton), Jabonería Nacional (50 ton), Camposa (5 ton) and 14 other plants (169 ton) | Individual | LAC | ECU | ARS | 9 | INV | 12 | N | O | I | CFC | 290 | 82 | 0 | 0 | 1993-03-01 | 1994-04-01 | 1995-03-01 |  | 1995-09-01 | 1995-10-01 | 697000 | -365172 | 331828 | 331828 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | A complete phaseout in the aerosol sector has been achieved through this project component. All small aerosol producers have agreed to have their cans filled by Windsor Laboratories, Ecuador's largest aerosol filler. Balance to be returned to MF by Nov/99. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ECU/ARS/9/INV/12 | [8 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Project preparation for the reduction of CFC-11 use in foam insulation at three refrigerator manufacturing plants (Indurama, Durex, Ecasa) |  | LAC | ECU | FOA | 6 | PRP | 6 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1992-12-01 |  |  | 1992-12-01 | 100000 | -100000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | 0 | 0 | 0 | 0 | ECU/FOA/6/PRP/6 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Reduction of CFC-11 use in foam insulation at three refrigerator manufacturing plants: Indurama, Durex, and Ecasa | Individual | LAC | ECU | FOA | 9 | INV | 10 | N | O | I | CFC | 51 | 126.4 | 0 | 0 | 1993-03-01 | 1994-04-01 | 1994-03-01 |  | 1995-11-01 | 1997-12-01 | 665000 | 0 | 665000 | 665000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Enterprises have used funds to completely phaseout CFC-11 through adoption of HCFC-141b. PCR completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ECU/FOA/9/INV/10 | 1995-07-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 in the fabrication of flexible foams by replacement with methylene chloride at an automobile and furniture component manufacturing plant belonging to Elasto S.A. | Individual | LAC | ECU | FOA | 26 | INV | 24 | N | O | I | CFC | 32 | 32 | 0 | 0 | 1998-11-01 | 2001-12-26 | 2000-06-01 |  | 2002-10-01 | 2002-11-01 | 187286 | 0 | 187286 | 187286 | 100 | 0 | 0 |  | 24347.18 | 0 | 24347.18 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Project successfully completed in both physical and financial terms, and total funding disbursed. PCR under preparation. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ECU/FOA/26/INV/24 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the methyl bromide sector for cut flowers and tobacco |  | LAC | ECU | FUM | 24 | PRP | 21 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-09-30 | 1998-12-01 |  | 1999-06-01 | 1999-06-01 | 20000 | 0 | 20000 | 20000 | 100 | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ECU/FUM/24/PRP/21 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Demonstration project for testing methyl bromide alternatives in soil treatment for the flower growing industry | Individual | LAC | ECU | FUM | 26 | TAS | 23 | N | O | I | MBR | 15 | 0 | 0 | 0 | 1998-11-01 | 2003-12-01 | 2005-11-01 | 2005-07-01 |  |  | 244244 | 0 | 244244 | 97302.75 | 39.83 | 146941.25 | 146941.25 | 146941.25 | 31751.72 | 0 | 12649.36 | 19102.36 | 19102.36 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Soil characterization, biological studies and trials with chemical alternatives completed. With regards to studies on organic matter, research phase is completed and data is currently being compiled for final report. As per steam vaporization trials, physical trials started and currently taking place. Combined studies are expected to start Mar. 05. Workshop to report trial results will be carried out in Jun. 05. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | ECU/FUM/26/TAS/23 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the methyl bromide sector |  | LAC | ECU | FUM | 33 | PRP | 29 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2002-11-01 | 2001-12-01 |  | 2002-11-01 | 2002-11-01 | 35000 | 0 | 35000 | 35000 | 100 | 0 | 0 |  | 4550 | 0 | 4550 | 0 | 0 | 2001 | #NAME? | #NAME? | #NAME? | #NAME? | MeBr phaseout plan for the rose plant nursery sector approved at the 38th ExCom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ECU/FUM/33/PRP/29 | [7 empty] | 2001 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Technology change for the phase-out of methyl bromide in the rose plant nursery sector | Individual | LAC | ECU | FUM | 38 | INV | 31 | N | O | I | MBR | 37.2 | 37.2 | 0 | 0 | 2002-11-01 | 2003-12-01 | 2005-11-01 | 2005-01-01 |  |  | 597945 | 0 | 597945 | 597945 | 100 | 0 | 0 |  | 75774 | 0 | 75774 | 0 | 0 | 2002 | #NAME? | #NAME? | #NAME? | #NAME? | New technology is installed and fully operational as of Aug. 04 and old equipment sealed off. Several additional tests were carried out and the project is expected to be completed in Jan. 05 after destruction of baseline equipment. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ECU/FUM/38/INV/31 | [7 empty] | 2002 | INV | 0 | 0 | 0 | 0
ONG | IBRD | National CFC phase-out plan: first tranche | Multiyear | LAC | ECU | PHA | 41 | INV | 32 | N | O | I | CFC | 11 | 11 | 0 | 0 | 2003-12-01 | 2004-12-01 | 2004-12-01 | 2005-04-01 |  |  | 777326 | 0 | 777326 | 40465.34 | 5.2 | 736860.66 | 736860.66 | 300000 | 58299.45 | 0 | 3034.9 | 55264.55 | 55264.55 | 2003 | #NAME? | #NAME? | #NAME? | #NAME? | SGAs with three enterprises signed and sub-projects fully underway. Two train-the-trainers seminars on good practices in refrigeration completed Sep. 04. Training of refrigeration technicians and customs officers will start early next year. Import quota system that includes all ODS is in place as of May 04. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ECU/PHA/41/INV/32 | [7 empty] | 2003 | INV | 235 | 143 | 0 | 0 | Yes | Yes | Yes
FIN | IBRD | Replacing CFC-12 refrigerant with HFC-134a at a manufacturing plant of domestic refrigerators belonging to Indurama S.A. | Individual | LAC | ECU | REF | 26 | INV | 25 | N | O | I | CFC | 28.38 | 28.38 | 0 | 0 | 1998-11-01 | 2002-09-01 | 2001-06-01 |  | 2002-09-01 | 2002-09-01 | 174792 | 0 | 174792 | 174792 | 100 | 0 | 0 |  | 22722.96 | 0 | 22722.96 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | ODS free production started Jun. 02. Project successfully completed in both physical and financial terms and all funds disbursed. PCR is under preparation. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ECU/REF/26/INV/25 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of CFC-12 refrigerant with HFC-134a at a manufacturing plant of domestic refrigerators belonging to Ecuatoriana de Artefactos S.A. (ECASA) | Individual | LAC | ECU | REF | 26 | INV | 26 | N | O | I | CFC | 15.73 | 15.73 | 0 | 0 | 1998-11-01 | 2001-12-26 | 2000-02-01 |  | 2001-11-30 | 2002-03-01 | 188545 | 0 | 188545 | 188545 | 100 | 0 | 0 |  | 24510.85 | 0 | 24510.85 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Project successfully completed both in physical and financial terms, and all funding disbursed. PCR under preparation. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ECU/REF/26/INV/26 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1991) |  | LAC | ECU | SEV | 4 | PRP | 1 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 92031 | -5365 | 86666 | 86666 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ECU/SEV/4/PRP/1 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation |  | LAC | ECU | SEV | 4 | PRP | 20 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 40386 | -22201 | 18185 | 18185 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ECU/SEV/4/PRP/20 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Country programme preparation | Individual | LAC | ECU | SEV | 6 | CPG | 4 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1993-02-01 |  |  | 1992-12-01 | 76100 | -76100 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | 0 | 0 | 0 | 0 | ECU/SEV/6/CPG/4 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1992) |  | LAC | ECU | SEV | 6 | PRP | 5 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 95026 | 76203 | 171229 | 171229 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ECU/SEV/6/PRP/5 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Institutional strengthening | Individual | LAC | ECU | SEV | 9 | INS | 11 | N | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1994-12-01 | 1996-03-01 |  | 1997-05-01 | 1997-08-01 | 204000 | -33327 | 170673 | 170673 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Public awareness campaign has been successfully carried out. Ozone Team actively supporting project implementation. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | 0 | ECU/SEV/9/INS/11 | 1997-06-01 | [7 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1993) |  | LAC | ECU | SEV | 9 | PRP | 13 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 68000 | 13231 | 81231 | 81231 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ECU/SEV/9/PRP/13 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Supervision of project implementation (approved at the 9th ExCom Meeting) |  | LAC | ECU | SEV | 12 | PRP | 15 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 30000 | 15197 | 45197 | 45197 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Project supervision on-going. Implementation is proceeding satisfactorily. A second phase of the Country Program is expected for CY95. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ECU/SEV/12/PRP/15 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | LAC | ECU | SEV | 16 | PRP | 18 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 56745 | 0 | 56745 | 56745 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project supervision on-going. Implementation is proceeding satisfactorily. A second phase of the Country Program is expected for CY97. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ECU/SEV/16/PRP/18 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | LAC | ECU | SEV | 21 | PRP | 19 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1998-03-31 | 1997-12-01 |  | 1998-12-01 | 1998-12-01 | 15000 | 0 | 15000 | 15000 | 100 | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Ongoing. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ECU/SEV/21/PRP/19 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the foam, refrigeration and halon sectors |  | LAC | ECU | SEV | 24 | PRP | 22 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-03-31 | 1998-12-01 |  | 1998-12-01 | 1998-12-01 | 49000 | 0 | 49000 | 49000 | 100 | 0 | 0 |  | 6370 | 0 | 6370 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ECU/SEV/24/PRP/22 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects in the foam and commercial refrigeration sectors |  | LAC | ECU | SEV | 27 | PRP | 27 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-12-31 | 2001-01-01 |  | 2000-12-01 | 2000-12-01 | 24000 | 0 | 24000 | 24000 | 100 | 0 | 0 |  | 3120 | 0 | 3120 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ECU/SEV/27/PRP/27 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Renewal of institutional strengthening (phase II) |  | LAC | ECU | SEV | 28 | INS | 28 | N | O | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2001-12-01 | 2001-08-01 |  | 2004-04-01 | 2004-04-01 | 97300 | 0 | 97300 | 97300 | 100 | 0 | 0 |  | 12649 | 0 | 12649 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | NOU (MICIP) activities included work on the regulatory side, seeing thru a resolution that sets up import quotas for ODS in order to comply with the Protocol's control measures and additional agreed targets with ExCom. Public awareness activities included a series of seminars in schools in different regions of the country. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | 0 | ECU/SEV/28/INS/28 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation of a national CFC phase-out plan |  | LAC | ECU | SEV | 36 | PRP | 30 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-09-01 |  | 2003-09-01 | 2003-09-01 | 80000 | 0 | 80000 | 80000 | 100 | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0 | 2002 | #NAME? | #NAME? | #NAME? | #NAME? | NCPP submitted and approved at the 41st ExCom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ECU/SEV/36/PRP/30 | [7 empty] | 2002 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Extension of institutional strengthening project (phase III) | Individual | LAC | ECU | SEV | 42 | INS | 33 | N | T | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-12-01 | 2006-04-01 | 2006-04-01 |  |  | 176800 | 0 | 176800 | 21510.18 | 12.16 | 155289.82 | 155289.82 | 45000 | 13260 | 0 | 1613.26 | 11646.74 | 11646.74 | 2004 | #NAME? | #NAME? | #NAME? | #NAME? | An intense public awareness campaign was carried out, including the organization of the Ozone Day Celebration, seminars in more than 30 schools in different regions and the release of brochures and technical sheets on ozone depletion. Follow-up of ongoing projects and enforcement of the quota system proved to be quite effective. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | 0 | ECU/SEV/42/INS/33 | [7 empty] | 2004 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of refrigeration compressor manufacturing to HFC-134a at MISR Compressors Manufacturing Co. (MCMC) | Individual | AFR | EGY | REF | 8 | INV | 8 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1992-10-01 | 1995-11-01 | 1994-03-01 |  | 1997-07-01 | 2000-11-01 | 2800000 | -950000 | 1850000 | 1850000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. Savings of $250,000 to be returned to the 36th ExCom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | EGY/REF/8/INV/8 | 1997-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects in the commercial and industrial refrigeration (1994) |  | AFR | EGY | REF | 12 | PRP | 24 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 25000 | -18884 | 6116 | 6116 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | EGY/REF/12/PRP/24 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation | Individual | AFR | EGY | SEV | 4 | CPG | 1 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-12-01 |  | 1992-12-01 | 1992-12-01 | 68981 | 28539 | 97520 | 97520 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | EGY/SEV/4/CPG/1 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1991) |  | AFR | EGY | SEV | 4 | PRP | 65 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 131065 | -51944 | 79121 | 79121 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | EGY/SEV/4/PRP/65 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1992) |  | AFR | EGY | SEV | 6 | PRP | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 227827 | -219155 | 8672 | 8672 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | EGY/SEV/6/PRP/3 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1993) |  | AFR | EGY | SEV | 9 | PRP | 13 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 112200 | -69976 | 42224 | 42224 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | EGY/SEV/9/PRP/13 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Supervision of project implementation (1994) |  | AFR | EGY | SEV | 12 | PRP | 25 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1995-03-01 |  |  | 1994-12-01 | 50000 | -50000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | 0 | 0 | 0 | 0 | EGY/SEV/12/PRP/25 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1995) |  | AFR | EGY | SEV | 16 | PRP | 47 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 65623 | 0 | 65623 | 65623 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | The reconnaissance mission reported that the scope of refrigeration-sector projects would be limited to recovery and recycling activities. Project identification was then undertaken. This activity is now completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | EGY/SEV/16/PRP/47 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation |  | AFR | GHA | SEV | 4 | PRP | 9 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 29362 | -11448 | 17914 | 17914 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | GHA/SEV/4/PRP/9 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Global aerosol project | Individual | GLO | GLO | ARS | 10 | TAS | 44 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-06-30 | 1994-12-01 |  | 1995-12-01 | 1995-12-01 | 350000 | -196423 | 153577 | 153577 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | The Global Aerosol Phase I report has been received and is under consideration. It is most likely that the Phase II component will be implemented by UNEP. Discussions have been initiated. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | GLO/ARS/10/TAS/44 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Supervision of project implementation (1994) |  | GLO | GLO | ARS | 12 | PRP | 66 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1995-03-01 |  |  | 1994-12-01 | 349931 | -349931 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | 0 | 0 | 0 | 0 | GLO/ARS/12/PRP/66 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Global refrigeration project | Individual | GLO | GLO | REF | 8 | TAS | 29 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-10-01 | 1992-12-31 | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 60000 | -6681 | 53319 | 53319 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | The original Global Refrigeration project is completed. The final activity, the preparation of a template for the domestic refrigeration sector utilizing hydrocarbon refrigerant, has been completed. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | GLO/REF/8/TAS/29 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Supervision of project implementation (1994) |  | GLO | GLO | REF | 12 | PRP | 65 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1995-03-01 |  |  | 1994-12-01 | 156750 | -156750 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | 0 | 0 | 0 | 0 | GLO/REF/12/PRP/65 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Administration, coordination, financial, legal (1991) | Individual | GLO | GLO | SEV | 4 | TAS | 4 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 320000 | -34564 | 285436 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | GLO/SEV/4/TAS/4 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Initial work programme for 1991 | Individual | GLO | GLO | SEV | 4 | TAS | 135 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1991-12-01 |  |  | 1991-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 500000 | -500000 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | 0 | 0 | 0 | 0 | GLO/SEV/4/TAS/135 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Administration, coordination, financial, legal (1992) | Individual | GLO | GLO | SEV | 6 | TAS | 23 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1992-12-01 |  | 1992-12-01 | 1992-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1347550 | -396573 | 950977 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | GLO/SEV/6/TAS/23 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Preparation of investment projects (1993) |  | GLO | GLO | SEV | 9 | PRP | 38 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 |  | 1995-03-01 |  |  | 1993-12-01 | 455000 | -455000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | 0 | 0 | 0 | 0 | GLO/SEV/9/PRP/38 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Administration, coordination, financial, legal and OORG meetings (1993) | Individual | GLO | GLO | SEV | 9 | TAS | 43 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 |  | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1179000 | -309745 | 869355 | -100 | -100 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | GLO/SEV/9/TAS/43 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Administration, coordination, financial, legal and OORG meetings (1994) | Individual | GLO | GLO | SEV | 12 | TAS | 52 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1418963 | -47607 | 1371356 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | GLO/SEV/12/TAS/52 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Administration, coordination, financial, legal (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 212 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 |  | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1450646 | 0 | 1450646 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | GLO/SEV/16/TAS/212 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | OORG workshops and meetings (1995) | Individual | GLO | GLO | SEV | 16 | TAS | 92 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 |  | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 183399 | 0 | 183399 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | GLO/SEV/16/TAS/92 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | IFC concessional financing study |  | GLO | GLO | SEV | 21 | PRP | 117 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-31 | 1997-12-31 | 60000 | 0 | 60000 | 60000 | 100 | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | GLO/SEV/21/PRP/117 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Advance for project preparation as indicated in the 1998 business plan |  | GLO | GLO | SEV | 23 | PRP | 149 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1998-12-01 |  |  | 1998-12-01 | 275600 | -275600 | 0 | 0 | 0 | 0 | 0 |  | 35828 | -35828 | 0 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | The resources allocated for this project were granted to The World Bank as an advance for project preparation for the Year 1998. During the 24th meeting the resources were taken out of the total project prepartion approvals. To indicate this transaction a negative entry with the same ID is created in 24th meeting. |  |  | #NAME? | 0 | 0 | 0 | 0 | GLO/SEV/23/PRP/149 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation advance |  | GLO | GLO | SEV | 26 | PRP | 177 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 | 2000-03-31 | 1999-12-01 |  | 2000-12-01 | 1999-12-01 | 140000 | 0 | 140000 | 140000 | 100 | 0 | 0 |  | 18200 | 0 | 18200 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | GLO/SEV/26/PRP/177 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Unallocated project preparation funds |  | GLO | GLO | SEV | 27 | PRP | 185 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 2000-12-31 | 2001-01-01 |  | 2000-12-01 | 2000-12-01 | 162000 | 0 | 162000 | 162000 | 100 | 0 | 0 |  | 21060 | 0 | 21060 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | GLO/SEV/27/PRP/185 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Project preparation advance for 2000 |  | GLO | GLO | SEV | 29 | PRP | 191 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 |  | 2000-04-01 |  |  | 2000-03-01 | 357450 | -357450 | 0 | 0 | 0 | 0 | 0 |  | 46468.5 | -46468.5 | 0 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | 0 | 0 | 0 | 0 | GLO/SEV/29/PRP/191 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Project preparation (unallocated) |  | GLO | GLO | SEV | 30 | PRP | 203 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 |  | 2000-12-01 |  |  | 2001-12-01 | 70000 | -70000 | 0 | 0 | 0 | 0 | 0 |  | 9100 | -9100 | 0 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | 0 | 0 | 0 | 0 | GLO/SEV/30/PRP/203 | [7 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Project preparation advance (2002) |  | GLO | GLO | SEV | 35 | PRP | 235 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 |  | 2002-03-01 |  |  | 2001-12-01 | 180000 | -180000 | 0 | 0 | 0 | 0 | 0 |  | 23400 | -23400 | 0 | 0 | 0 | 2001 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | 0 | 0 | 0 | 0 | GLO/SEV/35/PRP/235 | [7 empty] | 2001 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Unallocated project preparation |  | GLO | GLO | SEV | 36 | PRP | 239 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 |  | 2003-04-01 |  | 2002-12-01 | 2002-12-01 | 180000 | -180000 | 0 | 0 | 0 | 0 | 0 |  | 23400 | -23400 | 0 | 0 | 0 | 2002 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | GLO/SEV/36/PRP/239 | [7 empty] | 2002 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Core unit (2003) | Individual | GLO | GLO | SEV | 38 | TAS | 245 | A | T | I |  | 0 | 0 | 0 | 0 | 2002-11-01 |  | 2003-12-01 |  | 2003-12-01 | 2003-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1500000 | 0 | 1500000 | 0 | 0 | 2002 | #NAME? | #NAME? | #NAME? | #NAME? | Core unit activities included support/travel of core staff; annual FI workshop and OORG meeting; attendance at ExCom and interagency mtgs; 15th MOP and UNEP regional meetings; and publication of MP case study and flyer. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | GLO/SEV/38/TAS/245 | [7 empty] | 2002 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Core unit (2004) |  | GLO | GLO | SEV | 41 | TAS | 251 | A | T | I |  | 0 | 0 | 0 | 0 | 2003-12-01 |  | 2004-12-01 |  | 2004-12-01 | 2004-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1500000 | 0 | 1500000 | 0 | 0 | 2003 | #NAME? | #NAME? | #NAME? | #NAME? | Core unit activities included travel to MP-related meetings; support of core unit staff; hosting of three MP events and development of select knowledge material. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | GLO/SEV/41/TAS/251 | [7 empty] | 2003 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Core unit (2005) |  | GLO | GLO | SEV | 44 | TAS | 261 | A | T | I |  | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2005-12-01 | 2005-12-01 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1500000 | 0 | 0 | 1500000 | 1500000 | 2004 | #NAME? | #NAME? | #NAME? | #NAME? | Activities will include travel to MP-related meetings; support of core unit staff; hosting of two MP events and development of select knowledge material. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | GLO/SEV/44/TAS/261 | [7 empty] | 2004 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Global solvent project |  | GLO | GLO | SOL | 8 | PRP | 31 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-10-01 | 1992-12-31 | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 260000 | 21754 | 281754 | 281754 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | This activity is completed Final report to be issued shortly. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | GLO/SOL/8/PRP/31 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Supervision of project implementation (1994) |  | GLO | GLO | SOL | 12 | PRP | 64 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1995-03-01 |  |  | 1994-12-01 | 156750 | -156750 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | 0 | 0 | 0 | 0 | GLO/SOL/12/PRP/64 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1992) |  | LAC | GUA | SEV | 8 | PRP | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-10-01 | 1992-12-31 | 1993-10-01 |  | 1992-12-01 | 1992-12-01 | 25000 | -13641 | 11359 | 11359 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | GUA/SEV/8/PRP/2 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1993) |  | LAC | GUA | SEV | 9 | PRP | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 47000 | -13488 | 33512 | 33512 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | GUA/SEV/9/PRP/3 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1994) |  | LAC | GUA | SEV | 12 | PRP | 6 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 55000 | -47098 | 7902 | 7902 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | GUA/SEV/12/PRP/6 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Safety and technical programme to assist manufacturers of hydrocarbon propelled aerosol products | Individual | ASP | IDS | ARS | 11 | TAS | 10 | N | O | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1996-07-01 | 1995-11-01 |  | 1998-11-01 | 1998-11-01 | 238000 | -18915 | 219085 | 219085 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Activities on Work program had been completed. Technical audit has been carried out. Draft PCR has been submitted. Remaining grant returned to trust fund. Project completed and closed. 3% agency fee incl. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | IDS/ARS/11/TAS/10 | 1997-06-01 | [7 empty] | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Conversion and aerosol filling center at PT Candi Swadaya Sentosa | Individual | ASP | IDS | ARS | 22 | INV | 61 | N | O | I | CFC | 460 | 460 | 0 | 0 | 1997-05-01 | 2001-07-01 | 1999-06-01 | 2005-04-01 |  |  | 1175340 | 0 | 1175340 | 1175340 | 100 | 0 | 0 |  | 152794 | 0 | 152794 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed except equipment disposal (which was not a requirement when the project was approved). This is planned for Apr. 05. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/ARS/22/INV/61 |  | 2000-06-01 |  | 2002-06-01 |  |  |  |  | INV | 0 | 0 | 0 | 0
ONG | IBRD | National strategy for phasing out the use of CFC in the aerosol sector: Policies and actions, technical assistance, and enterprise investment initiatives | Individual | ASP | IDS | ARS | 44 | INV | 166 | N | O | I | CFC | 70 | 0 | 0 | 0 | 2004-12-01 |  | 2008-05-01 | 2008-05-01 |  |  | 371910 | 0 | 371910 | 0 | 0 | 371910 | 371910 | 100000 | 27893 | 0 | 0 | 27893 | 27893 | 2004 | #NAME? | #NAME? | #NAME? | #NAME? | The government is currently developing a work plan for this activity. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/ARS/44/INV/166 | [7 empty] | 2003 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11/12 in the manufacture of extruded polystyrene and polyethylene foam sheet at P.T. Tulus Bakti Sempurna | Individual | ASP | IDS | FOA | 11 | INV | 7 | N | O | I | CFC | 95 | 95 | 0 | 0 | 1993-11-01 | 1997-01-01 | 1994-11-01 |  | 1998-09-01 | 1998-12-01 | 416000 | -22725 | 393275 | 393275 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Financial and technical requirements of the project have been completed. PCR had been submitted. Project is closed. 3% agency fee incl. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/FOA/11/INV/7 | 1997-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-12 in the manufacture of extruded polystyrene and polyethylene foam sheet at P.T. Intitri Muliatama | Individual | ASP | IDS | FOA | 11 | INV | 8 | N | O | I | CFC | 119 | 119 | 0 | 0 | 1993-11-01 | 1996-12-01 | 1994-11-01 |  | 1998-09-01 | 1998-09-01 | 387000 | -62963 | 324037 | 324037 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Financial and technical requirements of the project have been completed. PCR had been submitted. Project is closed. 3% agency fee incl. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/FOA/11/INV/8 | 1997-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 in the manufacture of polyurethane foams at P.T. Dasa Windu Agung | Individual | ASP | IDS | FOA | 11 | INV | 9 | N | O | I | CFC | 122 | 122 | 0 | 0 | 1993-11-01 | 1995-12-01 | 1995-04-01 |  | 1998-08-01 | 1998-08-01 | 1733000 | 0 | 1733000 | 1733000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Run commercially. Technical audit had been completed and equipment disposal had been carried out. Project is closed. 3% agency fee incl. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/FOA/11/INV/9 | 1997-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 in the manufacture of polyurethane foams at P.T. Foamindo Industri Uretan | Individual | ASP | IDS | FOA | 11 | INV | 12 | N | O | I | CFC | 80 | 80 | 0 | 0 | 1993-11-01 | 1998-01-01 | 1994-11-01 |  | 2002-04-01 | 2002-04-01 | 176000 | 0 | 176000 | 176000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed in Apr. 02. Draft PCR submitted to WB for review. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/FOA/11/INV/12 | 1997-12-01 |  | 2000-12-01 | [5 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Technical assistance programme for small CFC users in the flexible polyurethane foam sector | Individual | ASP | IDS | FOA | 11 | TAS | 11 | N | O | I | CFC | 100 | 286 | 0 | 0 | 1993-11-01 | 1996-11-01 | 1995-11-01 |  | 1998-05-01 | 1998-05-01 | 1600000 | -1987 | 1598013 | 1598013 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Project technically and financial completed and closed. PCR had been submitted. 3% agency fee incl. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | IDS/FOA/11/TAS/11 | 1997-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 in the manufacture of flexible polyurethane foam at P.T. Erlangga Trimanunggal Kusumah | Individual | ASP | IDS | FOA | 13 | INV | 16 | N | O | I | CFC | 100 | 100 | 0 | 0 | 1994-07-01 | 1997-10-01 | 1995-07-01 |  | 2002-04-01 | 2002-04-01 | 379000 | 0 | 379000 | 379000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Project was completed in April 2002. Draft PCR has been submitted to WB for review. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/FOA/13/INV/16 | 1997-12-01 |  | 2000-12-01 | [5 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 in the manufacture of flexible polyurethane foam at P.T. Royal Abadi Sejahtera | Individual | ASP | IDS | FOA | 13 | INV | 18 | N | O | I | CFC | 120 | 120 | 0 | 0 | 1994-07-01 | 1997-06-01 | 1995-07-01 |  | 1997-06-01 | 1997-06-01 | 237500 | -3846 | 233654 | 233654 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and closed. PCR had been submitted. 3% agency fee incl. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/FOA/13/INV/18 | 1997-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 in the manufacture of polyurethane foam sheet at Positive Foam Industry | Individual | ASP | IDS | FOA | 15 | INV | 19 | N | O | I | CFC | 90 | 90 | 0 | 0 | 1994-12-01 | 1997-10-01 | 1995-12-01 |  | 2002-04-01 | 2002-04-01 | 449000 | 0 | 449000 | 449000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed in April 2002. Draft PCR had been submitted to WB for review. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/FOA/15/INV/19 | 1997-12-01 |  | 2000-12-01 | [5 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 in the manufacture of polyurethane foam sheet at Multi Karya Makmur | Individual | ASP | IDS | FOA | 15 | INV | 20 | N | O | I | CFC | 200 | 200 | 0 | 0 | 1994-12-01 | 1997-03-01 | 1995-12-01 |  | 2003-06-01 | 2003-07-01 | 123700 | -768 | 122932 | 122932.14 | 100 | -0.14 | -0.14 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Project physically and financially completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/FOA/15/INV/20 | 1997-12-01 | 1999-12-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-12 in the manufacture of extruded polyethylene and polystyrene foam sheet at PT Inter Foamindosentra | Individual | ASP | IDS | FOA | 15 | INV | 21 | N | O | I | CFC | 120 | 120 | 0 | 0 | 1994-12-01 | 1997-03-01 | 1995-12-01 |  | 1998-09-01 | 2000-10-01 | 390000 | -154145 | 235855 | 235855 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and PCR submitted. Balance returned to the MLF at the 33rd ExCom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/FOA/15/INV/21 | 1997-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of CFC-11 in the manufacture of polyurethane foam sheet at Musimassejahtera Abadi | Individual | ASP | IDS | FOA | 15 | INV | 30 | N | O | I | CFC | 114 | 50 | 0 | 0 | 1994-12-01 | 1996-11-01 | 1995-12-01 |  |  | 2000-12-01 | 390000 | -356351 | 33649 | 33649 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Project cancelled at 31st meeting and $154,145 returned at the 32nd meeting. |  |  | #NAME? | 0 | 0 | 0 | 0 | IDS/FOA/15/INV/30 | 1997-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of CFC-12 in the manufacture of extruded polyethylene foam sheet at PT. Toha Kencana Mas | Individual | ASP | IDS | FOA | 20 | INV | 45 | N | O | I |  | 0 | 0 | 0 | 0 | 1996-10-01 |  | 1997-10-01 |  |  | 1999-07-01 | 109930 | -109930 | 0 | 0 | 0 | 0 | 0 |  | 14290.9 | -14291 | 0 | -0.1 | -0.1 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Project is cancelled. Funds returned to 28th meeting. |  |  | #NAME? | 0 | 0 | 0 | 0 | IDS/FOA/20/INV/45 | 1997-12-01 | 1997-10-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-12 in the manufacture of extruded polethylene foam sheet at PT. Tara Guna Foam | Individual | ASP | IDS | FOA | 23 | INV | 73 | N | O | I | CFC | 35 | 35 | 0 | 0 | 1997-11-01 | 2001-10-01 | 1999-12-01 |  | 2001-12-01 | 2002-10-01 | 287700 | -34630.97 | 253069.03 | 253069.03 | 100 | 0 | 0 |  | 37401 | -4502.03 | 32898.97 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project technically and financially completed. PCR submitted to WB. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/FOA/23/INV/73 |  |  | 2001-02-01 | [5 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of CFC-11 in the manufacture of flexible polyurethane foam (slabstock) at PT. Irc Inoac Indonesia | Individual | ASP | IDS | FOA | 23 | INV | 75 | N | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1999-12-01 |  |  | 2003-04-01 | 412900 | -412900 | 0 | 0 | 0 | 0 | 0 |  | 53677 | -53677 | 0 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Cancelled - 38th ExCom |  |  | #NAME? | 0 | 0 | 0 | 0 | IDS/FOA/23/INV/75 | [8 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of CFC-11 in the manufacture of flexible polyurethane foam (slabstock) at PT Sea Horse Maspion Indonesia | Individual | ASP | IDS | FOA | 23 | INV | 76 | N | O | I |  | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1999-12-01 |  |  | 2001-12-01 | 532200 | -532200 | 0 | 0 | 0 | 0 | 0 |  | 69186 | -63864 | 5322 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project cancelled at the 35th ExCom and funds to be returned at the 36th ExCom. |  |  | #NAME? | 0 | 0 | 0 | 0 | IDS/FOA/23/INV/76 | [8 empty] | INV | 0 | 0 | 0 | 0
ONG | IBRD | Flexible boxfoam. Technical assistance programme for SMEs at Indonesian Foam Association (AFI) | Individual | ASP | IDS | FOA | 23 | INV | 77 | N | O | I | CFC | 954 | 0 | 0 | 0 | 1997-11-01 | 2002-12-01 | 1999-12-01 | 2005-12-01 |  |  | 4060640 | 0 | 4060640 | 903655.66 | 22.25 | 3156984.34 | 3156984.34 | 3156984.34 | 527883 | 0 | 117475.19 | 410407.81 | 410407.81 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | All 30 units of equipment distributed to foam recipients from Oct. to Dec. 04. Ten of these installed and commissioned; training provided. Due to expiration of visa of technicians, the supplier plans to send two technical teams Feb. 05 to complete commissioning of remaining 18 enterprises in Apr. 05. 2nd batch of equipment comprising of 24 units is to arrive in Feb. 05 and be distributed in Mar. Installation, commissioning and trials for these units planned by AFI in Aug. 05. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/FOA/23/INV/77 |  |  | 2001-02-01 | 2002-12-01 |  |  |  |  | INV | 0 | 0 | 0 | 0
ONG | IBRD | Technical assistance programme for SMEs for flexible polyurethane foam at Indonesian Foam Association (AFI) | Individual | ASP | IDS | FOA | 23 | INV | 78 | N | O | I | CFC | 370 | 370 | 0 | 0 | 1997-11-01 | 2002-12-01 | 1999-12-01 | 2005-01-01 |  |  | 3538400 | 0 | 3538400 | 768108.53 | 21.7 | 2770291.47 | 880704 | 880704 | 459992 | 0 | 99854.11 | 360137.89 | 114491.52 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | 16 units of equipment commissioned. Trials completed. Training conducted at ea. recipient along with distribution of safety thermometer and chemicals for trials. Technical completion of all 16 enterprises Oct. 04. Technical audit of 50% of enterprises conducted and old equipment disposed of for these 8 companies in Dec. 04. MoE planning equipment disposal for other 8 Jan. 05. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/FOA/23/INV/78 |  |  | 2001-02-01 | 2002-12-01 |  |  |  |  | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of projects in the foam sector |  | ASP | IDS | FOA | 27 | PRP | 108 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-06-30 | 2000-01-01 |  | 2000-12-01 | 2000-12-01 | 100000 | 0 | 100000 | 100000 | 100 | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/FOA/27/PRP/108 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase-out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (sprayfoam) at CV Sumber Logam | Individual | ASP | IDS | FOA | 29 | INV | 111 | N | O | I | CFC | 12.1 | 12.1 | 0 | 0 | 1999-11-01 | 2001-09-01 | 2002-12-01 |  | 2001-12-01 | 2002-05-01 | 56118 | -30157 | 25961 | 25961 | 100 | 0 | 0 |  | 7295.34 | -3920.41 | 3374.93 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Project technically and financially completed. PCR submitted to WB. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/FOA/29/INV/111 | [8 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (sprayfoam) at PT Sentra Sukses Selalu | Individual | ASP | IDS | FOA | 29 | INV | 115 | N | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 |  | 2002-12-01 |  |  | 2003-04-01 | 539579 | -539579 | 0 | 0 | 0 | 0 | 0 |  | 69353.69 | -69353.69 | 0 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Cancelled - 38th ExCom |  |  | #NAME? | 0 | 0 | 0 | 0 | IDS/FOA/29/INV/115 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (boxfoam and sprayfoam) at PT Intimas Chemindo | Individual | ASP | IDS | FOA | 29 | INV | 116 | N | O | I | CFC | 74.3 | 74.3 | 0 | 0 | 1999-11-01 | 2003-10-01 | 2002-12-01 |  | 2003-03-01 | 2004-09-01 | 290294 | -163063.56 | 127230.44 | 127230.44 | 100 | 0 | 0 |  | 37738.22 | -21198.04 | 16539.96 | 0.22 | 0.22 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Project technically and financially completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/FOA/29/INV/116 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (panels) at PT Dawamiba Engineering | Individual | ASP | IDS | FOA | 29 | INV | 117 | N | O | I | CFC | 31.6 | 31.6 | 0 | 0 | 1999-11-01 | 2001-11-01 | 2002-12-01 |  | 2003-06-01 | 2003-10-01 | 156500 | -2750 | 153750 | 153750 | 100 | 0 | 0 |  | 20345 | -358 | 19987.5 | -0.5 | -0.5 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Project technically and financially completed. PCR draft being finalized. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/FOA/29/INV/117 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phaseout of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (sprayfoam) at Kimura Fiberglass | Individual | ASP | IDS | FOA | 29 | INV | 118 | N | O | I | CFC | 21.1 | 21.1 | 0 | 0 | 1999-11-01 | 2001-10-01 | 2002-12-01 |  | 2001-12-01 | 2002-07-01 | 69385 | -36556.41 | 32828.59 | 32828.59 | 100 | 0 | 0 |  | 9020.05 | -4752.34 | 4267.71 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Project technically and financially completed. PCR submitted to WB. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/FOA/29/INV/118 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phaseout of CFC-11 by conversion to water based technology and LCD technology in the manufacture of flexible moulded foam and to HCFC-141b in the manufacture of molded integral skin polyurethane foam at Anto Indo Foam | Individual | ASP | IDS | FOA | 31 | INV | 120 | N | O | I | CFC | 54.3 | 54.3 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2003-08-01 |  | 2003-03-01 | 2003-10-01 | 249645 | -244 | 249401 | 249400.86 | 99.99 | 0.14 | 0.14 |  | 32453.85 | -32 | 32422.11 | -0.26 | -0.26 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? | Project technically and financially completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/FOA/31/INV/120 | [7 empty] | 2000 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (steel door) at PT Bostinco | Individual | ASP | IDS | FOA | 35 | INV | 127 | N | O | I | CFC | 11.3 | 11.3 | 0 | 0 | 2001-12-01 | 2003-08-01 | 2004-01-01 |  | 2003-10-01 | 2004-05-01 | 88479 | 0 | 88479 | 88479 | 100 | 0 | 0 |  | 11502.27 | 0 | 11502.27 | 0 | 0 | 2001 | #NAME? | #NAME? | #NAME? | #NAME? | Project physically and financially completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/FOA/35/INV/127 | [7 empty] | 2001 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (cooler box products) at Dua Roda Industrial Co. | Individual | ASP | IDS | FOA | 35 | INV | 128 | N | O | I | CFC | 11.2 | 11.2 | 0 | 0 | 2001-12-01 | 2003-10-01 | 2004-01-01 |  | 2003-05-01 | 2003-10-01 | 52457 | -5800 | 46657 | 46657 | 100 | 0 | 0 |  | 6819.41 | -754 | 6065.41 | 0 | 0 | 2001 | #NAME? | #NAME? | #NAME? | #NAME? | Project physically and financially completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/FOA/35/INV/128 | [7 empty] | 2001 | INV | 0 | 0 | 0 | 0
ONG | IBRD | Phase out of CFC-11 by conversion to 100% water based technology in the manufacture of polyurethane integral skin shoe soles at PT Udapana Swasti | Individual | ASP | IDS | FOA | 35 | INV | 129 | N | O | I | CFC | 28 | 28 | 0 | 0 | 2001-12-01 | 2003-12-01 | 2004-10-01 | 2005-06-01 |  |  | 165201 | 0 | 165201 | 79600 | 48.18 | 85601 | 85601 | 85601 | 21476.13 | 0 | 10348 | 11128.13 | 11128.13 | 2001 | #NAME? | #NAME? | #NAME? | #NAME? | Trials to synchronize work of dry parts (retrofit parts of pumps etc) and wet parts for moulds and mixing heads started in Sep. 04 and completed in Nov. 04, however, enterprise needs to conduct more trials as chemical trials and new retrofitted system (the panel/memory) still did not work to the enterprise's satisfaction. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/FOA/35/INV/129 | [7 empty] | 2001 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 by conversion to HCFC-141b in the manufacture of rigid polyurethane foam (house ware products) at PT Maspion Plastic and Metal Industry | Individual | ASP | IDS | FOA | 35 | INV | 130 | N | O | I | CFC | 18.1 | 18.1 | 0 | 0 | 2001-12-01 | 2003-10-01 | 2004-01-01 |  | 2003-11-01 | 2004-09-01 | 141723 | 0 | 141723 | 141723 | 100 | 0 | 0 |  | 18423.99 | 0 | 18423.99 | 0 | 0 | 2001 | #NAME? | #NAME? | #NAME? | #NAME? | Project physically and financially completed |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/FOA/35/INV/130 | [7 empty] | 2001 | INV | 0 | 0 | 0 | 0
ONG | IBRD | Phase-out of residual CFCs in the foam sector (advancement) | Multiyear | ASP | IDS | FOA | 42 | INV | 160 | N | O | I | CFC | 130 | 0 | 0 | 0 | 2004-04-01 | 2004-12-01 | 2005-04-01 | 2005-04-01 |  |  | 100000 | 1625000 | 1725000 | 10700 | 0.62 | 1714300 | 1714300 | 700000 | 7500 | 121875 | 856 | 128519 | 128519 | 2004 | #NAME? | #NAME? | #NAME? | #NAME? | Subgrant Agreement between Group Coordinator and Ministry of Environment for implementation of foam sector investment activities made in Nov. 04. Confirmation from potential enterprises joining the program expected to be received end of Q12005. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/FOA/42/INV/160 | [7 empty] | 2003 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination in production of halon-1211 fire protection extinguishers at Dahlia Cahaya, Bayu Sentosa Agung and Chubb Lips | Individual | ASP | IDS | HAL | 15 | INV | 27 | N | O | I | HAL | 465 | 682.4 | 0 | 0 | 1994-12-01 | 1996-06-01 | 1995-12-01 |  | 1997-11-01 | 1997-11-01 | 500000 | 0 | 500000 | 500000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | PCR has been submitted. Project is closed. 3% agency fee incl. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/HAL/15/INV/27 | 1997-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the halon recycling sector |  | ASP | IDS | HAL | 24 | PRP | 85 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1999-03-31 | 1998-12-01 |  | 1999-06-01 | 1999-06-01 | 18000 | 0 | 18000 | 18000 | 100 | 0 | 0 |  | 2340 | 0 | 2340 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Complete. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/HAL/24/PRP/85 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Halon management programme, halon recovery, recycling and banking | Halon Banking | ASP | IDS | HAL | 27 | TAS | 107 | N | O | I | HAL | 972 | 0 | 0 | 0 | 1999-03-01 | 2001-05-01 | 2003-04-01 | 2005-12-01 |  |  | 486200 | 0 | 486200 | 351257.22 | 72.24 | 134942.78 | 134942.78 | 134942.78 | 63206 | 0 | 45663.44 | 17542.56 | 17542.56 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Main investment components of Indonesia Halon Bank (IHB) such as REACH Machine, gas chromatographer and storage cylinders installed and put under trial operation. Main activities conducted include: (i) Training of IHB operators (ii) Commissioning of Gas Chromatographer and REACH Machine. Standard Operating Procedures and database for Halon Banking operation being developed. Workshops conducted in Jakarta, Bandung, Denpasar, Palembang, Balikpapan and Batam. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | IDS/HAL/27/TAS/107 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of tobacco expansion process from CFC-11 to carbon dioxide at PT Hanjaya Mandal Sampoerna and P.T. Djarum | Individual | ASP | IDS | OTH | 21 | INV | 51 | N | O | I | CFC | 90 | 54 | 0 | 0 | 1997-02-01 | 1998-08-01 | 1999-02-01 |  | 1997-06-01 | 1998-08-01 | 1214000 | -607000 | 607000 | 607000 | 100 | 0 | 0 |  | 157820 | -78910 | 78910 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | PT Sampoerna - grant was fully disbursed. Completed technical audit and disposal plan. PCR has been submitted and project is closed. PT Djarum - steam-based technology proposed was refused, project cancelled. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/OTH/21/INV/51 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of ODS used in the production of household refrigerators at P.T. Sharp Yasonta, Indonesia | Individual | ASP | IDS | REF | 15 | INV | 22 | N | O | I | CFC | 172.7 | 172.7 | 0 | 0 | 1994-12-01 | 1997-05-01 | 1997-12-01 |  | 1998-05-01 | 1998-05-01 | 346000 | 502910 | 848910 | 848910.25 | 100 | -0.25 | -0.25 |  | 0 | 78000 | 78000 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | PCR has been submitted. Project is physically and financially completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/REF/15/INV/22 | 1997-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of ODS used in the production of household refrigerators at P.T. Lippo Melco Manufacturing | Individual | ASP | IDS | REF | 15 | INV | 23 | N | O | I | CFC | 47.02 | 47.02 | 0 | 0 | 1994-12-01 | 1996-12-01 | 1998-10-01 |  | 1998-06-01 | 1999-03-01 | 382000 | 234452.23 | 616452.23 | 616452.23 | 100 | 0 | 0 |  | 0 | 32455.02 | 32455.42 | -0.4 | -0.4 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Conversion of refrigerant to 134a is finished. Technical audit done on Feb. '98. Completed ODS phaseout in Jun. '98. Disposal plan was carried out in Nov. 19, '98. IOC has been disbursed. Project is technically and financially closed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/REF/15/INV/23 | 1997-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of ODS used in the manufacturing of household refrigerators at P.T. Sanyo Industries Indonesia, Jakarta | Individual | ASP | IDS | REF | 15 | INV | 26 | N | O | I | CFC | 72.3 | 72.3 | 0 | 0 | 1994-12-01 | 1996-04-01 | 1998-12-01 |  | 1998-03-01 | 1998-12-01 | 558000 | -30847.24 | 527152.76 | 527152.76 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Project is completed. PCR had been submitted, project is closed. Unused funds returned to 32nd meeting. 3% agency fee incl. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/REF/15/INV/26 | 1997-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Reduction of CFC-12 emission during service of MAC by use of recycling equipment | Individual | ASP | IDS | REF | 15 | TAS | 29 | N | O | I | CFC | 41 | 41 | 0 | 0 | 1994-12-01 | 2000-03-01 | 1996-12-01 |  | 2002-04-01 | 2002-04-01 | 327000 | -51593.01 | 275406.99 | 275406.99 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. Draft PCR submitted to the Bank. Savings are to be returned to the MLF. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | IDS/REF/15/TAS/29 | 1997-12-01 | 2000-01-01 | 2001-12-01 | [5 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of ODSs used in the production of household refrigerators at P.T. Topjaya Antariksa Electronics | Individual | ASP | IDS | REF | 18 | INV | 36 | N | O | I | CFC | 51 | 69 | 0 | 0 | 1995-11-01 | 1996-11-01 | 2002-12-02 |  | 1998-05-01 | 2000-02-01 | 702000 | -2674 | 699326 | 699326 | 100 | 0 | 0 |  | 91260 | -347 | 90913 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project is completed. PCR has been submitted. Unused fund is returned to 32nd Ex.Com. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/REF/18/INV/36 | 1997-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of ODSs used in the production of household refrigerators at P.T. National Gobel (Nabel) | Individual | ASP | IDS | REF | 18 | INV | 37 | N | O | I | CFC | 90 | 100.57 | 0 | 0 | 1995-11-01 | 1996-07-01 | 2000-12-01 |  | 1998-03-01 | 2000-03-01 | 856500 | 0 | 856500 | 856500 | 100 | 0 | 0 |  | 111345 | 0 | 111345 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project is completed. PCR has been submitted. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/REF/18/INV/37 | 1997-03-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Engineering assistance for the elimination of ODS used in the production of household refrigerators at PT. Goldstar Astra Electronics (GSA) | Individual | ASP | IDS | REF | 20 | INV | 48 | N | O | I | CFC | 38.1 | 35.04 | 0 | 0 | 1996-10-01 | 1998-02-01 | 1999-04-01 |  | 1999-12-01 | 2001-03-01 | 512730 | -163820 | 348910 | 348910.32 | 100 | -0.32 | -0.32 |  | 66654.9 | -21297 | 45358.53 | -0.63 | -0.63 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Project is technically and financially closed. IOC has been disbursed. Balance returned to the MLF at the 35th ExCom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/REF/20/INV/48 | 1999-04-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Engineering assistance for the elimination of ODS used in the production of household refrigerators at PT. Samsung Maspion Indonesia (SMI) | Individual | ASP | IDS | REF | 21 | INV | 52 | N | O | I | CFC | 104.3 | 98.24 | 0 | 0 | 1997-02-01 | 1997-12-01 | 1999-08-01 |  | 2001-10-01 | 2001-11-01 | 537226 | -320243 | 216983 | 216983 | 100 | 0 | 0 |  | 69839.38 | -41632 | 28206.97 | 0.41 | 0.41 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Enterprise decided not to proceed to c-pentane due to current unfavorable economic conditions causing a high upfront investment costs for technology, and stopped at HCFC-141b. Disposal of old equipment done and IOC disbursed. Unused funds returned to the MLF at 35th and 36th Meetings. PCR under preparation. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/REF/21/INV/52 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 commercial refrigeration to HFC-134a at PT Maspion | Individual | ASP | IDS | REF | 23 | INV | 72 | N | O | I | CFC | 9 | 9 | 0 | 0 | 1997-11-01 | 1998-07-01 | 1999-12-01 |  | 1999-12-01 | 2000-11-01 | 136890 | -11703 | 125187 | 125187.38 | 100 | -0.38 | -0.38 |  | 17796 | -1521.39 | 16274.31 | 0.3 | 0.3 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. Disposal of old equipment has been carried out. PCR will be submitted January 2001. Project is closed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/REF/23/INV/72 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 commercial refrigeration to HFC-134a at PT Porkka Indonesia | Individual | ASP | IDS | REF | 23 | INV | 74 | N | O | I | CFC | 3.96 | 3.96 | 0 | 0 | 1997-11-01 | 2000-10-01 | 1999-12-01 |  | 1998-08-01 | 2001-03-01 | 58517 | -9377 | 49140 | 49140 | 100 | 0 | 0 |  | 7607 | -1219.01 | 6387.99 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and PCR to be submitted Mar. 02. Savings returned to the 35th ExCom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/REF/23/INV/74 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 refrigerant to HFC-134a, and CFC-11 to HCFC-141b as the blowing agent for foam insulation in the manufacture of commercial refrigeration units at PT Wahana Derby Sejati | Individual | ASP | IDS | REF | 23 | INV | 79 | N | O | I | CFC | 10.28 | 10.28 | 0 | 0 | 1997-11-01 | 1998-07-01 | 1999-12-01 |  | 1997-11-01 | 1998-07-01 | 139233 | -77613 | 61620 | 61620 | 100 | 0 | 0 |  | 18100 | -10089.69 | 8010.31 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed, PCR submitted Mar. 99 and balance returned to the 32nd ExCom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/REF/23/INV/79 | [8 empty] | INV | 0 | 0 | 0 | 0
COM | IBRD | Refrigeration sector phase-out plan: MAC servicing sector | Multiyear | ASP | IDS | REF | 38 | INV | 153 | N | O | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-12-01 | 2003-12-01 |  | 2003-12-01 |  | 1369800 | 0 | 1369800 | 1364226.64 | 99.59 | 5573.36 | 5573.36 | 5573.36 | 121962 | 0 | 121465.77 | 496.23 | 496.23 | 2002 | #NAME? | #NAME? | #NAME? | #NAME? | 2003 annual plan completed successfully. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/REF/38/INV/153 | [7 empty] | 2002 | INV | 695 | 695 | 0 | 0 | Yes | Yes | Yes
COM | IBRD | Sector phase-out plan for elimination of CFCs in the refrigeration (MAC servicing) sector: 2004 annual programme | Multiyear | ASP | IDS | REF | 41 | INV | 156 | N | O | I | CFC | 110 | 110 | 0 | 0 | 2003-12-01 |  | 2004-12-01 |  | 2004-12-01 |  | 1347300 | 0 | 1347300 | 0 | 0 | 1347300 | 1347300 | 1347300 | 119937 | 0 | 0 | 119937 | 119937 | 2003 | #NAME? | #NAME? | #NAME? | #NAME? | 2004 annual plan completed sucessfully. Disbursement for MAC sector and also non-investment costs expected in 2005. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/REF/41/INV/156 | [7 empty] | 2003 | INV | 585 | 0 | 0 | 0 |  | No | No
ONG | IBRD | Phase-out of CFCs in the refrigeration sector (MAC) (third tranche) | Multiyear | ASP | IDS | REF | 44 | INV | 165 | N | O | I | CFC | 110 | 0 | 0 | 0 | 2004-12-01 |  | 2005-12-01 | 2005-12-01 |  |  | 1347300 | 0 | 1347300 | 0 | 0 | 1347300 | 1347300 | 300 | 119937 | 0 | 0 | 119937 | 119937 | 2004 | #NAME? | #NAME? | #NAME? | #NAME? | Activities are underway to meet 2005 target. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/REF/44/INV/165 | [7 empty] | 2004 | INV | 475 | 0 | 0 | 0 |  | No | No
FIN | IBRD | Country programme preparation | Individual | ASP | IDS | SEV | 8 | CPG | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-10-01 | 1992-12-31 | 1993-10-01 |  | 1992-12-01 | 1992-12-01 | 54000 | -12931 | 41069 | 41069 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | IDS/SEV/8/CPG/2 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation advance I (1993) |  | ASP | IDS | SEV | 9 | PRP | 3 | N | O | D |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-09-30 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 250000 | 0 | 250000 | 250000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Project preparation activities are complete. 14 subproject proposals were prepared. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/SEV/9/PRP/3 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1993) |  | ASP | IDS | SEV | 9 | PRP | 4 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 206000 | 1805 | 207805 | 207805 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/SEV/9/PRP/4 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Completion of processing of investment projects approved at the 11th ExCom Meeting |  | ASP | IDS | SEV | 12 | PRP | 13 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 128899 | 43396 | 172295 | 172295 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Project preparation and processing complete. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/SEV/12/PRP/13 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1994) |  | ASP | IDS | SEV | 12 | PRP | 15 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-09-30 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 117312 | -81569 | 35743 | 35743 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/SEV/12/PRP/15 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Training of the Financial Intermediary on Multilateral Fund and World Bank project processing procedures | Individual | ASP | IDS | SEV | 12 | TRA | 14 | N | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1996-07-01 | 1995-03-01 |  | 1998-08-01 | 1998-08-01 | 50000 | -701 | 49299 | 49299 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | TA Uppindo project is closed. PCR submitted. 3% agency fee incl. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | IDS/SEV/12/TRA/14 | 1997-12-01 | [7 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | ODS phase out investment project preparation (1994) |  | ASP | IDS | SEV | 13 | PRP | 17 | N | O | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1996-08-08 | 1996-08-01 |  | 1996-08-01 | 1996-08-01 | 170000 | 0 | 170000 | 170000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/SEV/13/PRP/17 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | ASP | IDS | SEV | 16 | PRP | 31 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 108824 | 0 | 108824 | 108824 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/SEV/16/PRP/31 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects ODS II (1995) |  | ASP | IDS | SEV | 16 | PRP | 62 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-31 | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 50000 | -32695 | 17305 | 17305 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/SEV/16/PRP/62 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | ASP | IDS | SEV | 18 | PRP | 42 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 30000 | 0 | 30000 | 30000 | 100 | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/SEV/18/PRP/42 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | ASP | IDS | SEV | 21 | PRP | 55 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 179000 | -150000 | 29000 | 29000 | 100 | 0 | 0 |  | 23270 | -19500 | 3770 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | For IDS/SEV/21/PRP/55 $179,000 was approved of which $29,000 was expensed, and the remaining $150,000 was transferred to Indonesia PPA III. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/SEV/21/PRP/55 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation for 3 projects in the foam sector and one in the refrigeration sector |  | ASP | IDS | SEV | 33 | PRP | 125 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-12-01 | 2001-12-01 |  | 2001-12-01 | 2001-12-01 | 10000 | 0 | 10000 | 10000 | 100 | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | 2001 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/SEV/33/PRP/125 | [7 empty] | 2001 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of two sector plans in the aerosol sector and in the foam sector |  | ASP | IDS | SEV | 36 | PRP | 142 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-09-01 |  | 2003-09-01 | 2003-09-01 | 130000 | 0 | 130000 | 130000 | 100 | 0 | 0 |  | 16900 | 0 | 16900 | 0 | 0 | 2002 | #NAME? | #NAME? | #NAME? | #NAME? | Foam and aerosol proposals prepared and submitted to Excom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/SEV/36/PRP/142 | [7 empty] | 2002 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Strengthening of import/export control | Individual | ASP | IDS | SEV | 37 | TAS | 149 | N | O | I | CFC | 9.1 | 9.1 | 0 | 0 | 2002-07-01 | 2003-12-01 | 2004-08-01 | 2005-12-01 |  |  | 110000 | 0 | 110000 | 88780 | 80.7 | 21220 | 21220 | 21220 | 14300 | 0 | 11541.4 | 2758.6 | 2758.6 | 2002 | #NAME? | #NAME? | #NAME? | #NAME? | Government of Indonesia is making some progress in improving the import licensing and quota system to monitor and control ODS import. Legal importers who can obtain ODS import licenses are identified by Decrees No. 789/MPP/KEP/12/2002. The WB (with cooperation of UNDP) has discussed with the Government about the need for legislative measures to control/monitor ODS supply. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | IDS/SEV/37/TAS/149 | [7 empty] | 2002 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of metal cleaning processes from 1.1.1 TCA to aqueous cleaning at PT INTI (Industri Telekomunikasi Indonesia) | Individual | ASP | IDS | SOL | 18 | INV | 38 | N | O | I | TCA | 0.97 | 1 | 0 | 0 | 1995-11-01 | 1996-07-01 | 1996-11-01 |  | 1996-06-01 | 1996-08-01 | 37380 | 0 | 37380 | 37380 | 100 | 0 | 0 |  | 4859.4 | 0 | 4859.4 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project is completed and closed. PCR submitted. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/SOL/18/INV/38 | 1996-08-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of metal cleaning processes from 1,1,1 TCA to aqueous cleaning at PT. Garuda Indonesia | Individual | ASP | IDS | SOL | 18 | INV | 39 | N | O | I | TCA | 0.86 | 2.67 | 0 | 0 | 1995-11-01 | 1997-10-01 | 1996-11-01 |  | 1998-11-01 | 1998-11-01 | 33264 | -169 | 33095 | 33095 | 100 | 0 | 0 |  | 4324.32 | -21.97 | 4302.35 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | The project is completed. Technical audit has been done with satisfactory result. PCR had been submitted. Project is closed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/SOL/18/INV/39 | 1997-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion of metal cleaning processes from 1,1,1 TCA to aqueous cleaning at PT. Markindo Theco | Individual | ASP | IDS | SOL | 18 | INV | 40 | N | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1996-11-01 |  |  | 1999-03-01 | 83200 | -83200 | 0 | 0 | 0 | 0 | 0 |  | 10816 | -10816 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | CANCELLED. Funds returned to 27th meeting. |  |  | #NAME? | 0 | 0 | 0 | 0 | IDS/SOL/18/INV/40 | 1997-12-01 | 1996-11-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of correction fluid manufacturing process from 1,1,1 TCA to non-ODS solvent at PT Cahaya Biru Sakti | Individual | ASP | IDS | SOL | 20 | INV | 50 | N | O | I | TCA | 18.2 | 18.2 | 0 | 0 | 1996-10-01 | 1997-09-01 | 1997-10-01 |  | 1998-06-01 | 2000-10-01 | 700700 | -125383 | 575317 | 575317 | 100 | 0 | 0 |  | 91091 | -16299.79 | 74791.21 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and PCR submitted Jan. 01. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IDS/SOL/20/INV/50 | 1997-12-01 | 1999-06-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Aero Pharma aerosol conversion | Individual | ASP | IND | ARS | 11 | INV | 10 | N | O | I | CFC | 36 | 36 | 0 | 0 | 1993-11-01 | 1996-08-01 | 1994-11-01 |  | 1998-06-01 | 1998-06-01 | 62520 | 0 | 62520 | 62520 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | No change in previous status |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/ARS/11/INV/10 | 1997-03-01 | 1999-06-01 | [6 empty] | INV | 0 | 0 | 0 | 0
TRF | IBRD | Conversion of 5 aerosol filling installations to manual filling equipment using HAP | Individual | ASP | IND | ARS | 17 | DEM | 50 | N | O | I |  | 0 | 0 | 0 | 0 | 1995-07-01 |  | 1996-07-01 |  |  | 1995-07-01 | 181550 | -181550 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project implementation has been transferred to UNDP. |  |  | #NAME? | 0 | 0 | 0 | 0 | IND/ARS/17/DEM/50 | 1996-06-01 | [7 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Stella Industries aerosol conversion | Individual | ASP | IND | ARS | 22 | INV | 113 | N | O | I | CFC | 105 | 105 | 0 | 0 | 1997-05-01 | 1997-08-01 | 1998-06-01 |  | 1998-09-01 | 1998-09-01 | 269175 | 0 | 269175 | 269175 | 100 | 0 | 0 |  | 34992.75 | 0 | 34992.75 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. PCR submitted. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/ARS/22/INV/113 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Accra Pack India Pvt. Ltd. aerosol conversion | Individual | ASP | IND | ARS | 22 | INV | 114 | N | O | I | CFC | 52 | 52 | 0 | 0 | 1997-05-01 | 1999-02-01 | 1998-06-01 |  | 2001-07-01 | 2002-04-01 | 129690 | -7545 | 122145 | 122145 | 100 | 0 | 0 |  | 16859.7 | -980.85 | 15878.85 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | PCR to be finalized and submitted in 2003. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/ARS/22/INV/114 |  | 1999-06-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | My Fair Lady aerosol conversion, Delhi | Individual | ASP | IND | ARS | 22 | INV | 119 | N | O | I | CFC | 59.4 | 59.4 | 0 | 0 | 1997-05-01 | 1999-06-01 | 1998-06-01 |  | 2000-12-01 | 2002-09-01 | 113975 | -16195 | 97780 | 97780.37 | 100 | -0.37 | -0.37 |  | 14816.75 | -2105.35 | 12711.4 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | PCR finalized and submitted to ExCom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/ARS/22/INV/119 |  | 1999-06-01 | [6 empty] | INV | 0 | 0 | 0 | 0
COM | IBRD | Attarwala and Co. Pvt. Ltd. aerosol conversion, Bombay | Individual | ASP | IND | ARS | 22 | INV | 137 | N | O | I | CFC | 30.6 | 30.6 | 0 | 0 | 1997-05-01 | 2001-07-01 | 1998-06-01 |  | 2002-12-01 |  | 134250 | 0 | 134250 | 122148 | 90.98 | 12102 | 0 |  | 17452.5 | 0 | 15879.24 | 1573.26 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. PCR submitted to ExCom. Financial completion expected Feb. 05. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/ARS/22/INV/137 |  | 1999-12-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Aero Industries aerosol conversion, Vapi | Individual | ASP | IND | ARS | 22 | INV | 139 | N | O | I | CFC | 27.6 | 27.6 | 0 | 0 | 1997-05-01 | 1998-05-01 | 1998-06-01 |  | 1999-06-01 | 1999-05-01 | 121735 | -3903 | 117832 | 117832 | 100 | 0 | 0 |  | 15825.55 | -507.39 | 15318.16 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and PCR submitted. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/ARS/22/INV/139 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Aeropres aerosol conversion, Vapi | Individual | ASP | IND | ARS | 22 | INV | 141 | N | O | I | CFC | 50 | 50 | 0 | 0 | 1997-05-01 | 1998-05-01 | 1998-06-01 |  | 1999-06-01 | 2000-10-01 | 146860 | -4040 | 142820 | 142819.81 | 99.99 | 0.19 | 0.19 |  | 19091.8 | -525.2 | 18566.6 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and PCR submitted. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/ARS/22/INV/141 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Application development for the conversion of CFC-11/polyol systems to low non-ODS formulations at UB Petroproducts Ltd. | Individual | ASP | IND | FOA | 11 | INV | 13 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1993-11-01 | 1999-02-01 | 1996-11-01 |  | 1999-08-01 | 2000-08-01 | 200000 | 291817 | 491817 | 491817.37 | 100 | -0.37 | -0.37 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and PCR submitted |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/FOA/11/INV/13 | 1998-04-01 | 1999-03-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Application development for the conversion of CFC-11/polyol systems to low non-ODS formulations at Manali Petrochemical Ltd. | Individual | ASP | IND | FOA | 11 | INV | 14 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1993-11-01 | 1997-02-01 | 1996-11-01 |  | 1998-01-01 | 2000-08-01 | 219000 | 211348 | 430348 | 430347.63 | 99.99 | 0.37 | 0.37 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and PCR submitted |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/FOA/11/INV/14 | 1998-04-01 | 1999-03-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of CFC-11 as blowing agent in polyurethane foam systems with low and non-ODS materials at Expanded Incorporation | Individual | ASP | IND | FOA | 13 | INV | 23 | N | O | I | CFC | 72 | 72 | 0 | 0 | 1994-07-01 | 1997-04-01 | 1998-07-01 |  | 2000-09-01 | 2000-09-01 | 502130 | -8064 | 494066 | 494066 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and PCR submitted |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/FOA/13/INV/23 | 1999-03-01 | 1999-03-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of flexible slabstock PUF at Duroflex Coir Industries P. Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 34 | N | O | I | CFC | 10 | 10 | 0 | 0 | 1995-07-01 | 1996-04-01 | 1997-01-01 |  | 1997-08-01 | 1998-03-01 | 100800 | -7422 | 93378 | 93378 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Complete. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/FOA/17/INV/34 | 1997-03-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of rigid PUF at Industrial Foams Pvt. Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 35 | N | O | I | CFC | 35 | 35 | 0 | 0 | 1995-07-01 | 1996-05-01 | 1997-01-01 |  | 1997-08-01 | 1997-06-01 | 320000 | -9500 | 310500 | 310500 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Complete. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/FOA/17/INV/35 | 1997-03-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of rigid PUF thermoware at Ishwar Arts (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 36 | N | O | I | CFC | 8 | 8 | 0 | 0 | 1995-07-01 | 1996-11-01 | 1997-01-01 |  | 1998-10-01 | 2000-08-01 | 120950 | -29077 | 91873 | 91873 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. PCR submitted. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/FOA/17/INV/36 | 1997-05-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of rigid PUF thermoware at Ishwar Ashish Plastics P. Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 37 | N | O | I | CFC | 8 | 8 | 0 | 0 | 1995-07-01 | 1996-11-01 | 1997-01-01 |  | 1998-10-01 | 2000-08-01 | 120950 | -29077 | 91873 | 91873 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. PCR submitted. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/FOA/17/INV/37 | 1997-04-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of flexible polyurtehane foams at Karnataka Consumer Products Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 38 | N | O | I | CFC | 27 | 27 | 0 | 0 | 1995-07-01 | 1999-06-01 | 1997-01-01 |  | 2000-03-01 | 2001-07-01 | 253200 | -103341 | 149859 | 149859 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. PCR submitted. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/FOA/17/INV/38 | 1998-12-01 | 1999-09-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of moulded PUF at Madras Polymoulds (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 39 | N | O | I | CFC | 10 | 10 | 0 | 0 | 1995-07-01 | 1997-10-01 | 1997-01-01 |  | 1998-10-01 | 2000-07-01 | 167700 | -57255 | 110445 | 110445 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. PCR submitted. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/FOA/17/INV/39 | 1997-12-01 | 1999-01-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of rigid PUF thermoware at Milton Plastics Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 40 | N | O | I | CFC | 30 | 30 | 0 | 0 | 1995-07-01 | 1996-11-01 | 1997-01-01 |  | 1998-10-01 | 2000-07-01 | 456500 | -81683 | 374817 | 374817 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. PCR submitted. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/FOA/17/INV/40 | 1997-04-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of rigid PUF thermoware at Milton Polyplas (India) Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 41 | N | O | I | CFC | 15 | 15 | 0 | 0 | 1995-07-01 | 1996-11-01 | 1997-01-01 |  | 1998-10-01 | 2000-07-01 | 236000 | -52332 | 183668 | 183668 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. PCR submitted. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/FOA/17/INV/41 | 1997-04-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of rigid PUF thermoware at Panorama Plastics (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 42 | N | O | I | CFC | 8 | 8 | 0 | 0 | 1995-07-01 | 1996-11-01 | 1997-01-01 |  | 1998-10-01 | 2000-08-01 | 120950 | -29077 | 91873 | 91873 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. PCR submitted. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/FOA/17/INV/42 | 1997-04-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of PUF sandwich panels at Polynate Foams Pvt. Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 43 | N | O | I | CFC | 20 | 20 | 0 | 0 | 1995-07-01 | 1997-11-01 | 1997-01-01 |  | 2000-02-01 | 2001-10-01 | 278000 | -1057 | 276943 | 276943 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and PCR submitted |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/FOA/17/INV/43 | 1998-01-01 | 1999-02-01 | [6 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Phase out of CFC-11 in the manufacture of PUF sandwich panels at Sree Precoated Steels Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 44 | N | O | I |  | 0 | 0 | 0 | 0 | 1995-07-01 |  | 1997-01-01 |  |  | 1999-11-01 | 224000 | -224000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Cancelled |  |  | #NAME? | 0 | 0 | 0 | 0 | IND/FOA/17/INV/44 | 1998-01-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of rigid PUF thermoware at Vikram Plastics (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 45 | N | O | I | CFC | 15 | 15 | 0 | 0 | 1995-07-01 | 1996-11-01 | 1997-01-01 |  | 1998-10-01 | 2000-08-01 | 236000 | -52312 | 183688 | 183688 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and PCR submitted. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/FOA/17/INV/45 | 1997-04-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of molded PUF at Tranquil Rubber Sales Pvt. Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 46 | N | O | I | CFC | 17 | 17 | 0 | 0 | 1995-07-01 | 1996-05-01 | 1997-01-01 |  | 1998-04-01 | 2000-07-01 | 215250 | -79521 | 135729 | 135729 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and PCR submitted. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/FOA/17/INV/46 | 1997-07-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase-out of CFCs in the manufacture of extruded polyethylene foam at Real Polymers | Individual | ASP | IND | FOA | 17 | INV | 47 | N | O | I | CFC | 35 | 35 | 0 | 0 | 1995-07-01 | 1996-12-01 | 1997-01-01 |  | 1998-09-01 | 1998-07-01 | 276200 | -51275 | 224925 | 224925 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and PCR submitted. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/FOA/17/INV/47 | 1997-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFCs in the manufacture of PUF moldings at Vijayjyot Seats Ltd. | Individual | ASP | IND | FOA | 17 | INV | 48 | N | O | I | CFC | 49 | 49 | 0 | 0 | 1995-07-01 | 1997-07-01 | 1997-01-01 |  | 1998-09-01 | 1999-12-01 | 335500 | -25979 | 309521 | 309521 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Complete. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/FOA/17/INV/48 | 1997-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFCs in the manufacture of molded PUF automotive seats at Polyflex (India) P. Ltd. | Individual | ASP | IND | FOA | 17 | INV | 49 | N | O | I | CFC | 40 | 40 | 0 | 0 | 1995-07-01 | 1998-03-01 | 1997-01-01 |  | 1998-09-01 | 2002-01-01 | 222400 | -6000 | 216400 | 216400 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Complete. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/FOA/17/INV/49 | 1997-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of molded PUF at Alfa Foams (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 51 | N | O | I | CFC | 19 | 19 | 0 | 0 | 1995-07-01 | 1997-07-01 | 1997-01-01 |  | 1997-10-01 | 2000-11-01 | 219900 | -27875 | 192025 | 192025.49 | 100 | -0.49 | -0.49 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and PCR submitted. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/FOA/17/INV/51 | 1997-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of PUF sandwich panels at Blue Star Ltd. (under SPAP) | Individual | ASP | IND | FOA | 17 | INV | 52 | N | O | I | CFC | 13 | 13 | 0 | 0 | 1995-07-01 | 1997-05-01 | 1997-01-01 |  | 1998-06-01 | 2000-12-01 | 224000 | -55898 | 168102 | 168102 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and PCR submitted. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/FOA/17/INV/52 | 1997-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFCs in the manufacture of integral skin PUF moldings at Pfeda Synthetics (P) Ltd. | Individual | ASP | IND | FOA | 18 | INV | 54 | N | O | I | CFC | 30 | 30 | 0 | 0 | 1995-11-01 | 1997-02-01 | 1997-05-01 |  | 1998-04-01 | 1999-09-01 | 335728 | -14893 | 320835 | 320834.93 | 99.99 | 0.07 | 0.07 |  | 43644.64 | -1936.09 | 41708.55 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Complete. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/FOA/18/INV/54 | 1997-09-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFCs in the manufacture of molded PUF at Bharat Seats Ltd. | Individual | ASP | IND | FOA | 18 | INV | 55 | N | O | R | CFC | 55 | 55 | 0 | 0 | 1995-11-01 | 1996-12-01 | 1996-03-01 |  | 1993-07-01 | 1996-12-01 | 514563 | -563 | 514000 | 514000 | 100 | 0 | 0 |  | 66893.19 | -73.19 | 66820 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Complete. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/FOA/18/INV/55 | 1993-07-01 | [7 empty] | INV | 0 | 0 | 0 | 0
COM | IBRD | Phase out of CFCs in the manufacture of molded PUF at PUR Polyurethane Products P. Ltd. | Individual | ASP | IND | FOA | 18 | INV | 56 | N | O | I | CFC | 17 | 17 | 0 | 0 | 1995-11-01 | 1997-12-01 | 1997-05-01 |  | 2002-03-01 |  | 187864 | 0 | 187864 | 146341 | 77.89 | 41523 | 0 |  | 24422.32 | 0 | 19024.33 | 5397.99 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and draft PCR submitted by enterprise. FI has undertaken site visits but enterprise remains non-co-operative in providing more data. Given this long-standing issue, Gov and WB will be discussing the possibiity of submission of the PCR as is. Matter is to be resolved by Mar. 05, given that the ODSII umbrella project is now completed and ICR preparation is in progress. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/FOA/18/INV/56 | 1997-12-01 | 1999-02-01 | 2000-12-01 | [5 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Phase out of CFCs in the manufacture of extruded polyethylene foam at Kunstoff Polymers Ltd. | Individual | ASP | IND | FOA | 18 | INV | 57 | N | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1997-05-01 |  |  | 1997-02-01 | 239320 | -239320 | 0 | 0 | 0 | 0 | 0 |  | 31111.6 | -31111.6 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Cancelled |  |  | #NAME? | 0 | 0 | 0 | 0 | IND/FOA/18/INV/57 | 1997-09-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase-out of CFCs in the manufacture of extruded polyethylene foam at Shroff Textiles Ltd. | Individual | ASP | IND | FOA | 18 | INV | 58 | N | O | I | CFC | 25 | 25 | 0 | 0 | 1995-11-01 | 1998-05-01 | 1997-05-01 |  | 2000-06-01 | 2001-01-01 | 197200 | 0 | 197200 | 197200 | 100 | 0 | 0 |  | 25636 | 0 | 25636 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and PCR submitted |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/FOA/18/INV/58 | 1997-12-01 | 1999-03-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFCs in the manufacture of rigid PUF products at SDC Polyurethane Products Ltd. | Individual | ASP | IND | FOA | 18 | INV | 59 | N | O | I | CFC | 24 | 24 | 0 | 0 | 1995-11-01 | 1998-03-01 | 1997-05-01 |  | 1998-06-01 | 2000-07-01 | 160971 | 0 | 160971 | 160970.73 | 99.99 | 0.27 | 0.27 |  | 20926.23 | 0 | 20926.19 | 0.04 | 0.04 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and PCR submitted. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/FOA/18/INV/59 | 1997-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase-out of CFCs in the manufacture of molded PUF automotive seat cushions at Roloforms Polymer Ltd. | Individual | ASP | IND | FOA | 19 | INV | 77 | N | O | I | CFC | 26 | 26 | 0 | 0 | 1996-05-01 | 1998-03-01 | 1997-11-01 |  | 1999-06-01 | 2000-03-01 | 162400 | -38657 | 123743 | 123743 | 100 | 0 | 0 |  | 21112 | -5025.41 | 16086.59 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and PCR submitted. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/FOA/19/INV/77 | 1998-01-01 | 1999-06-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase-out of CFC-11 in the manufacture of rigid PUF products at Polyproducts | Individual | ASP | IND | FOA | 19 | INV | 84 | N | O | I | CFC | 18.5 | 18.5 | 0 | 0 | 1996-05-01 | 1997-09-01 | 1997-11-01 |  | 1998-09-01 | 2001-03-01 | 140190 | -26 | 140164 | 140164 | 100 | 0 | 0 |  | 18224.7 | -3.38 | 18221.32 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and PCR submitted. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/FOA/19/INV/84 | 1998-01-01 | [7 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Phase-out of CFC-11 in the manufacture of rigid PUF for insulated thermoware at Arihant Thermoware Ltd. | Individual | ASP | IND | FOA | 19 | INV | 85 | N | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1997-11-01 |  |  | 1998-07-01 | 146450 | -146450 | 0 | 0 | 0 | 0 | 0 |  | 19038.5 | -19038.5 | 0 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Cancelled. |  |  | #NAME? | 0 | 0 | 0 | 0 | IND/FOA/19/INV/85 | 1998-01-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase-out of CFC-11 in the manufacture of rigid PUF insulated thermoware at Cello Plast | Individual | ASP | IND | FOA | 19 | INV | 86 | N | O | I | CFC | 21 | 21 | 0 | 0 | 1996-05-01 | 1998-02-01 | 1997-11-01 |  | 1999-06-01 | 2000-09-01 | 141320 | -546 | 140774 | 140773.84 | 99.99 | 0.16 | 0.16 |  | 18372 | -70.98 | 18301.02 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and PCR submitted |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/FOA/19/INV/86 | 1998-01-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase-out of CFC-11 in the manufacture of rigid PUF insulated thermoware at Cello Thermoware Ltd. | Individual | ASP | IND | FOA | 19 | INV | 87 | N | O | I | CFC | 17.4 | 17.4 | 0 | 0 | 1996-05-01 | 1998-02-01 | 1997-11-01 |  | 1999-06-01 | 2000-09-01 | 129420 | 0 | 129420 | 129420 | 100 | 0 | 0 |  | 16824.6 | 0 | 16824.6 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and PCR submitted |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/FOA/19/INV/87 | 1998-01-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase-out of CFC-11 in the manufacture of rigid PUF insulated thermoware at Wimco Pen Co. | Individual | ASP | IND | FOA | 19 | INV | 88 | N | O | I | CFC | 18.5 | 18.5 | 0 | 0 | 1996-05-01 | 1998-03-01 | 1997-11-01 |  | 1999-06-01 | 2000-09-01 | 119290 | -4225 | 115065 | 115065 | 100 | 0 | 0 |  | 15507.7 | -549.25 | 14958.45 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and PCR submitted |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/FOA/19/INV/88 | 1998-01-01 | 1999-03-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of domestic refrigerator manufacture to cyclopentane blowing agent at Godrej - GE Appliances Ltd. (GGEAL) | Individual | ASP | IND | FOA | 20 | INV | 104 | N | O | I | CFC | 568 | 568 | 0 | 0 | 1996-10-01 | 1999-01-01 | 1999-02-01 |  | 1999-07-01 | 2003-10-01 | 2691570 | -27265 | 2664305 | 2664305 | 100 | 0 | 0 |  | 349904.1 | -3544.45 | 346359.55 | 0.1 | 0.1 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/FOA/20/INV/104 |  | 2000-06-01 | [6 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion from halon-1211 to ABC dry chemical power (ABC-DCP) and carbon dioxide (CO2) in portable extinguishers at Real Value Appliances Ltd. | Individual | ASP | IND | HAL | 18 | INV | 60 | N | O | I | HAL | 462 | 462 | 0 | 0 | 1995-11-01 |  | 1997-05-01 |  |  | 2003-07-01 | 251736 | -251736 | 0 | 0 | 0 | 0 | 0 |  | 32725.68 | -32725.68 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project cancelled at the 39th ExCom. |  |  | #NAME? | 0 | 0 | 0 | 0 | IND/HAL/18/INV/60 | 1998-06-01 |  | 2000-12-01 | [5 empty] | INV | 0 | 0 | 0 | 0
COM | IBRD | Halon production and consumption sector phase out plan | One off phaseout | ASP | IND | HAL | 34 | INV | 315 | N | O | I | HAL | 556 | 556 | 321 | 321 | 2001-07-01 | 2003-08-01 | 2002-08-01 |  | 2003-10-01 |  | 2600000 | 0 | 2600000 | 2300000 | 88.46 | 300000 | 300000 | 300000 | 234000 | 0 | 207000 | 27000 | 27000 | 2001 | #NAME? | #NAME? | #NAME? | #NAME? | Completed. Balance of $300,000 to be transferred to UNDP for consumption sector activities - legal process underway. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/HAL/34/INV/315 | [7 empty] | 2000 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phaseout of use of carbon tetrachloride as process agent in the production of endosulphan by Excel Industries Limited | Individual | ASP | IND | PAG | 28 | INV | 217 | N | O | I | CTC | 375 | 375 | 0 | 0 | 1999-07-01 | 2000-11-01 | 2001-08-01 |  | 2001-12-01 | 2002-03-01 | 366000 | 0 | 366000 | 366000 | 100 | 0 | 0 |  | 47580 | 0 | 47580 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | PCR to be finalized and submitted in 2003. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/PAG/28/INV/217 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of a sector plan for the process agent sector |  | ASP | IND | PAG | 33 | PRP | 301 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2001-12-31 | 2001-12-01 |  | 2003-04-01 | 2003-12-01 | 130000 | 0 | 130000 | 130000 | 100 | 0 | 0 |  | 16900 | 0 | 16900 | 0 | 0 | 2001 | #NAME? | #NAME? | #NAME? | #NAME? | Sector Plan completed and project document prepared for submission to the ExCom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/PAG/33/PRP/301 | [7 empty] | 2001 | Non-INV | 0 | 0 | 0 | 0
COM | IBRD | Conversion of chlorinated rubber manufacture from carbon tetrachloride to non-ODS process at Rishiroop Organics Pvt. Ltd. | Individual | ASP | IND | PAG | 34 | INV | 320 | N | O | I | CTC | 248.8 | 248.8 | 0 | 0 | 2001-07-01 | 2002-12-01 | 2004-08-01 |  | 2003-10-01 |  | 2074300 | 0 | 2074300 | 1964315.95 | 94.69 | 109984.05 | 0 |  | 238173 | 0 | 226074.76 | 12098.24 | 0 | 2001 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. PCR submitted and in review process. Finacial completion expected Feb. 05. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/PAG/34/INV/320 | [7 empty] | 2000 | INV | 0 | 0 | 0 | 0
COM | IBRD | CTC phase-out plan for the consumption and production sectors (first tranche) | Multiyear | ASP | IND | PHA | 40 | INV | 363 | N | O | I |  | 0 | 0 | 0 | 0 | 2003-07-01 |  | 2004-07-01 |  | 2004-07-01 |  | 5000000 | 3520843 | 8520843 | 0 | 0 | 8520843 | 8520843 | 1000000 | 375000 | 264063 | 0 | 639063 | 639063 | 2003 | #NAME? | #NAME? | #NAME? | #NAME? | Project appraisal completed in Mar. 04. Negotiations took place in Aug. 04 and project signing was Dec. 04. Some project activities initiated. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/PHA/40/INV/363 | [7 empty] | 2003 | INV | 0 | 0 | 0 | 0
ONG | IBRD | CTC phase-out plan for the consumption and production sectors: 2004 work programme | Multiyear | ASP | IND | PHA | 42 | INV | 373 | N | O | I |  | 0 | 0 | 0 | 0 | 2004-04-01 |  | 2005-04-01 | 2005-04-01 |  |  | 9180112 | 0 | 9180112 | 0 | 0 | 9180112 | 9180112 | 1000000 | 688508 | 0 | 0 | 688508 | 688508 | 2004 | #NAME? | #NAME? | #NAME? | #NAME? | Project appraisal completed in Mar. 04; negotiations in Aug. and GA signing took place in Dec. 04. In 2004, two consumption sector workshops were held as well as two workshops for CTC producers. An informal arrangement regarding production quota distribution and MLF resource allocation among producers was reached and will be formalized in 2005. Verification framework is expected to be completed in 2005, as originally planned. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/PHA/42/INV/373 | [7 empty] | 2003 | INV | 0 | 0 | 0 | 0
COM | IBRD | CFC production sector gradual phase-out project: 1999 annual programme | Multiyear | ASP | IND | PRO | 29 | INV | 238 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1999-11-01 | 2000-08-01 | 2000-11-01 |  | 2000-11-01 |  | 12000000 | 0 | 12000000 | 12000000 | 100 | 0 | 0 |  | 960000 | 0 | 960000 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Implemented |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/PRO/29/INV/238 | [8 empty] | INV | 0 | 0 | 22588 | 22411 | Yes | Yes | Yes
FIN | IBRD | Preparation of projects in halon production sector |  | ASP | IND | PRO | 30 | PRP | 249 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 25000 | 0 | 25000 | 25000 | 100 | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/PRO/30/PRP/249 | [7 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
COM | IBRD | CFC production sector gradual phase-out project: 2000 annual programme | Multiyear | ASP | IND | PRO | 31 | INV | 262 | N | O | I | CFC | 0 | 0 | 1882 | 1882 | 2000-07-01 | 2000-09-01 | 2000-12-01 |  | 2000-12-01 |  | 11000000 | 0 | 11000000 | 11000000 | 100 | 0 | 0 |  | 880000 | 0 | 880000 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? | Annual Programme satisfactorily implemented with achievement of CY2000 CFC production reduction and disbursement targets. ODS (regulation & control) rules established along with quota order for production quota licenses for CFC-producing enterprises. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/PRO/31/INV/262 | [7 empty] | 2000 | INV | 0 | 0 | 20706 | 20407 | Yes | Yes | Yes
COM | IBRD | CFC production sector gradual phase-out project: 2001 annual programme | Multiyear | ASP | IND | PRO | 33 | INV | 295 | N | O | I | CFC | 0 | 0 | 1583 | 1583 | 2001-03-01 | 2001-04-30 | 2001-12-01 |  | 2001-12-01 |  | 11000000 | 0 | 11000000 | 11000000 | 100 | 0 | 0 |  | 880000 | 0 | 880000 | 0 | 0 | 2001 | #NAME? | #NAME? | #NAME? | #NAME? | Annual Programme satisfactorily implemented. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/PRO/33/INV/295 | [7 empty] | 2001 | INV | 0 | 0 | 18824 | 18693 | Yes | Yes | Yes
COM | IBRD | CFC production sector gradual phase-out project: 2002 annual programme | Multiyear | ASP | IND | PRO | 36 | INV | 352 | N | O | I | CFC | 0 | 0 | 1883 | 1883 | 2002-03-01 | 2002-12-01 | 2002-12-01 |  | 2002-12-01 |  | 6000000 | 0 | 6000000 | 6000000 | 100 | 0 | 0 |  | 480000 | 0 | 480000 | 0 | 0 | 2002 | #NAME? | #NAME? | #NAME? | #NAME? | Completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/PRO/36/INV/352 | [7 empty] | 2002 | INV | 0 | 0 | 16941 | 16890 | Yes | Yes | Yes
FIN | IBRD | Project preparation funds for CTC production closure plan |  | ASP | IND | PRO | 38 | PRP | 355 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-12-01 | 2003-12-01 |  | 2003-12-01 | 2003-12-01 | 90000 | 0 | 90000 | 90000 | 100 | 0 | 0 |  | 11700 | 0 | 11700 | 0 | 0 | 2002 | #NAME? | #NAME? | #NAME? | #NAME? | Completed and submitted to ExCom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/PRO/38/PRP/355 | [7 empty] | 2002 | Non-INV | 0 | 0 | 0 | 0
COM | IBRD | CFC production sector gradual phase-out: 2003 annual programme | Multiyear | ASP | IND | PRO | 39 | INV | 361 | N | O | I | CFC | 0 | 0 | 1883 | 1883 | 2003-04-01 | 2003-12-01 | 2004-04-01 |  | 2004-04-01 |  | 6000000 | 0 | 6000000 | 5850000 | 97.5 | 150000 | 150000 | 150000 | 450000 | 0 | 438750 | 11250 | 11250 | 2003 | #NAME? | #NAME? | #NAME? | #NAME? | CY2003 CFC production reduction targets achieved and independently verified. TA component was delayed because of resignation of PMU coordinator. New coordinator recruited in Nov. 04. Coordinator to assess current situation and requirements, in consultation with UNEP, and define new studies. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/PRO/39/INV/361 | [7 empty] | 2003 | INV | 0 | 0 | 15058 | 15014 | Yes | Yes | Yes
ONG | IBRD | CFC production sector gradual phase-out: 2004 annual programme | Multiyear | ASP | IND | PRO | 42 | INV | 372 | N | O | I | CFC | 0 | 0 | 1832 | 0 | 2004-04-01 | 2004-06-01 | 2005-04-01 | 2005-04-01 |  |  | 6000000 | 0 | 6000000 | 5265000 | 87.75 | 735000 | 735000 | 735000 | 450000 | 0 | 394875 | 55125 | 55125 | 2004 | #NAME? | #NAME? | #NAME? | #NAME? | Annual Programme satisfactorily implemented with compliance of CY2004 CFC production targets. Disbursement to CFC producing enterprises on target. Implementation of TA component has been slow primarily due to staffing problems at PMU. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/PRO/42/INV/372 | [7 empty] | 2004 | INV | 0 | 0 | 13176 | 13069 | Yes | Yes | Yes
FIN | IBRD | Substitution of CFC-11 refrigerant by HCFC-123 in centrifugal chillers (Blue Star) | Individual | ASP | IND | REF | 10 | INV | 8 | N | O | I | CFC | 36 | 36 | 0 | 0 | 1993-06-01 | 1995-07-01 | 1996-06-01 |  | 1997-12-01 | 1997-12-01 | 567000 | -146504 | 420496 | 420496 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Complete. (Remaining "balance" has been disbursed to FA.) |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/REF/10/INV/8 | 1997-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of compressor manufacture from CFC-12 to HFC-134a designs at Shriram Industries | Individual | ASP | IND | REF | 10 | INV | 9 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1993-06-01 | 1995-05-01 | 1995-06-01 |  | 1997-12-01 | 1997-07-01 | 685000 | -309549 | 375451 | 375451 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Complete. (Remaining "balance" has been disbursed to FA.) |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/REF/10/INV/9 | 1997-03-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Modification of CFC-12 MAC manufacturing for HFC-134a at Subros Ltd. | Individual | ASP | IND | REF | 11 | INV | 12 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1993-11-01 | 1995-07-01 | 1995-11-01 |  | 1998-11-01 | 2003-05-01 | 1710000 | -55496 | 1654504 | 1654504 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and PCR submitted. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/REF/11/INV/12 | 1997-03-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of compressor designs for refrigeration and appliances from CFC-12 to HFC-134a at Kirloskar Copeland Ltd. | Individual | ASP | IND | REF | 12 | INV | 15 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1994-03-01 | 1996-05-01 | 1998-03-01 |  | 1999-03-01 | 1999-11-01 | 547900 | -16905 | 530995 | 530994.85 | 99.99 | 0.15 | 0.15 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and PCR submitted |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/REF/12/INV/15 | 1998-03-01 | 1999-03-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 open-type compressor designs for use with HCFC-22 refrigerant at Freezeking Industries Pvt., Ltd. | Individual | ASP | IND | REF | 13 | INV | 24 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1994-07-01 | 1996-03-01 | 1997-07-01 |  | 1999-11-01 | 2000-12-01 | 240500 | -25806 | 214694 | 214694.04 | 100 | -0.04 | -0.04 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and PCR submitted |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/REF/13/INV/24 | 1998-07-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Meghdoot Refrigeration Industries | Individual | ASP | IND | REF | 18 | INV | 61 | N | O | I | CFC | 18 | 18 | 0 | 0 | 1995-11-01 | 1997-12-01 | 1997-05-01 |  | 1999-01-01 | 2000-07-01 | 164590 | -5660 | 158930 | 158929.9 | 99.99 | 0.1 | 0.1 |  | 21396.7 | -735.8 | 20660.9 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and PCR submitted. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/REF/18/INV/61 | 1997-08-01 | 1999-05-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at V. Krishna & Co. | Individual | ASP | IND | REF | 18 | INV | 62 | N | O | I | CFC | 14.8 | 14.8 | 0 | 0 | 1995-11-01 | 1997-12-01 | 1997-05-01 |  | 1999-06-01 | 2001-06-01 | 147020 | -11574 | 135446 | 135446 | 100 | 0 | 0 |  | 19112.6 | -1504.62 | 17607.98 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and PCR submitted |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/REF/18/INV/62 | 1997-08-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at V. Krishna Engineers P. Ltd. | Individual | ASP | IND | REF | 18 | INV | 63 | N | O | I | CFC | 17 | 17 | 0 | 0 | 1995-11-01 | 1997-12-01 | 1997-05-01 |  | 2001-04-01 | 2003-10-01 | 202790 | -81830 | 120960 | 120960 | 100 | 0 | 0 |  | 26362.7 | -10637.87 | 15725.13 | -0.3 | -0.3 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/REF/18/INV/63 | 1997-08-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Friz-Tech P. Ltd. | Individual | ASP | IND | REF | 18 | INV | 64 | N | O | I | CFC | 12 | 11.5 | 0 | 0 | 1995-11-01 | 1997-11-01 | 1997-05-01 |  | 2000-03-01 | 2002-07-01 | 132920 | 0 | 132920 | 132920 | 100 | 0 | 0 |  | 17279.6 | 0 | 17279.6 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/REF/18/INV/64 | 1997-08-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Rabi-Run Refrigeration P., Ltd. | Individual | ASP | IND | REF | 19 | INV | 89 | N | O | I | CFC | 14 | 14 | 0 | 0 | 1996-05-01 | 1997-10-01 | 1997-11-01 |  | 2001-01-01 | 2002-09-01 | 142622 | -2428 | 140194 | 140194.28 | 100 | -0.28 | -0.28 |  | 18541 | -315.64 | 18225.36 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | PCR to be finalized and submitted in 2003. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/REF/19/INV/89 | 1998-02-01 |  | 2000-06-01 | [5 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Seepra Refrigeration P., Ltd. | Individual | ASP | IND | REF | 19 | INV | 90 | N | O | I | CFC | 15 | 15 | 0 | 0 | 1996-05-01 | 1997-10-01 | 1997-11-01 |  | 1998-08-01 | 1999-12-01 | 171910 | -10400 | 161510 | 161510 | 100 | 0 | 0 |  | 22348 | -1352 | 20996 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Complete. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/REF/19/INV/90 | 1998-02-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Shakti Fabricators | Individual | ASP | IND | REF | 19 | INV | 91 | N | O | I | CFC | 13.5 | 13.5 | 0 | 0 | 1996-05-01 | 1997-07-01 | 1997-11-01 |  | 2001-09-01 | 2003-10-01 | 159230 | -926 | 158304 | 158304 | 100 | 0 | 0 |  | 20699.9 | -120.42 | 20579.58 | -0.1 | -0.1 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/REF/19/INV/91 | 1998-02-01 | 1999-06-01 | [6 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Chandra Frig Co. P., Ltd. | Individual | ASP | IND | REF | 19 | INV | 92 | N | O | I | CFC | 9.4 | 4.8 | 0 | 0 | 1996-05-01 | 1998-03-01 | 1997-11-01 |  |  | 2004-04-01 | 130984 | -64197 | 66787 | 66787.07 | 100 | -0.07 | -0.07 |  | 17028 | -8346 | 8682.32 | -0.32 | -0.32 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Project cancelled at the 42nd ExCom and balance returned at the 43rd ExCom. Bank has requested FI to examine the SGA to find out appropriate course of action for recuperation of equipment. Process underway. |  |  | #NAME? | 0 | 0 | 0 | 0 | IND/REF/19/INV/92 | 1998-02-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Rockwell Devices P., Ltd. | Individual | ASP | IND | REF | 19 | INV | 93 | N | O | I | CFC | 18 | 18 | 0 | 0 | 1996-05-01 | 1998-06-01 | 1997-11-01 |  | 1999-07-01 | 2000-09-01 | 181004 | -9611 | 171393 | 171392.74 | 99.99 | 0.26 | 0.26 |  | 23530.52 | -1249.43 | 22281.09 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and PCR submitted |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/REF/19/INV/93 | 1998-02-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Sethia Appliances P., Ltd. | Individual | ASP | IND | REF | 19 | INV | 94 | N | O | I | CFC | 16 | 16 | 0 | 0 | 1996-05-01 | 1997-11-01 | 1997-11-01 |  | 1999-06-01 | 2000-08-01 | 173384 | -6586 | 166798 | 166798.3 | 100 | -0.3 | -0.3 |  | 22540 | -856.18 | 21683.82 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and PCR submitted |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/REF/19/INV/94 | 1998-02-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Supercold Refrigeration Systems P. Ltd. | Individual | ASP | IND | REF | 20 | INV | 105 | N | O | I | CFC | 11 | 11 | 0 | 0 | 1996-10-01 | 2000-12-01 | 1998-04-01 |  | 2001-04-01 | 2002-05-01 | 133770 | -3495 | 130275 | 130275 | 100 | 0 | 0 |  | 17390.1 | -454.35 | 16935.75 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Enterprise has submitted the draft PCR which will be sent to the Bank by April 15, 2003. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/REF/20/INV/105 |  | 1999-12-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Murali Refrigeration and Engineering Co. | Individual | ASP | IND | REF | 20 | INV | 106 | N | O | I | CFC | 9 | 9 | 0 | 0 | 1996-10-01 | 1998-03-01 | 1998-04-01 |  | 1999-06-01 | 2000-10-01 | 126485 | -1539 | 124946 | 124945.52 | 99.99 | 0.48 | 0.48 |  | 16443.05 | -200.07 | 16242.98 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and PCR submitted |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/REF/20/INV/106 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the refrigeration sector |  | ASP | IND | REF | 21 | PRP | 108 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1998-06-01 | 1998-06-01 | 243000 | 0 | 243000 | 243000 | 100 | 0 | 0 |  | 31590 | 0 | 31590 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/REF/21/PRP/108 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
COM | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Refrigeration Components and Accessories | Individual | ASP | IND | REF | 22 | INV | 110 | N | O | I | CFC | 9.5 | 9.5 | 0 | 0 | 1997-05-01 | 2001-08-01 | 1999-06-01 |  | 2004-03-01 |  | 125370 | 0 | 125370 | 47993.55 | 38.28 | 77376.45 | 2194 | 2194 | 16298.1 | 0 | 6239.16 | 10058.94 | 285.22 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. FI completed site visit and PCR is in last stage of finalization and signature. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/REF/22/INV/110 |  |  | 2000-12-01 | [5 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to non-CFC technology in the production of MAC systems at Pranav Vikas India Ltd. | Individual | ASP | IND | REF | 22 | INV | 116 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-01-01 | 1999-06-01 |  | 2002-03-01 | 2002-12-01 | 944914 | -90669 | 854245 | 854245 | 100 | 0 | 0 |  | 122838.82 | -11786.97 | 111051.85 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Draft PCR submitted to ExCom Sep. 02. PCR to be finalized and resubmitted in 2003. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/REF/22/INV/116 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Standard Refrigeration Appliances | Individual | ASP | IND | REF | 22 | INV | 120 | N | O | I | CFC | 18.8 | 18.8 | 0 | 0 | 1997-05-01 | 1998-05-01 | 1998-11-01 |  | 2000-08-01 | 2000-12-01 | 170180 | -166 | 170014 | 170014 | 100 | 0 | 0 |  | 22123.4 | -21.58 | 22101.82 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and PCR submitted |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/REF/22/INV/120 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to non-CFC technology in the production of MAC systems at Sanden Vikas India Ltd. | Individual | ASP | IND | REF | 22 | INV | 121 | N | O | I | CFC | 8.36 | 8.36 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1999-06-01 |  | 2002-03-01 | 2002-04-01 | 490820 | -111557 | 379263 | 379263 | 100 | 0 | 0 |  | 63806.6 | -14502.41 | 49304.19 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Draft PCR submitted to the ExCom Sep. 02. PCR to be finalized and resubmitted in 2003. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/REF/22/INV/121 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Sheetal Engineering Works P. Ltd. | Individual | ASP | IND | REF | 22 | INV | 122 | N | O | I | CFC | 8.7 | 8.7 | 0 | 0 | 1997-05-01 | 1998-11-01 | 1999-06-01 |  | 1999-02-01 | 2001-06-01 | 127630 | -28297 | 99333 | 99333 | 100 | 0 | 0 |  | 16591.9 | -3678.61 | 12913.29 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. PCR will be submitted January 2001. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/REF/22/INV/122 | [8 empty] | INV | 0 | 0 | 0 | 0
COM | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Hindustan Refrigeration Industries | Individual | ASP | IND | REF | 22 | INV | 123 | N | O | I | CFC | 10.1 | 10.1 | 0 | 0 | 1997-05-01 | 2002-12-01 | 1999-06-01 |  | 2004-03-01 |  | 132320 | 0 | 132320 | 49000 | 37.03 | 83320 | 1993 | 1993 | 17201.6 | 0 | 6370 | 10831.6 | 259.09 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. FI completed site visit and PCR is in last stage of finalization and signature. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/REF/22/INV/123 | [8 empty] | INV | 0 | 0 | 0 | 0
COM | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Refrigerators and Home Appliances P. Ltd. | Individual | ASP | IND | REF | 22 | INV | 124 | N | O | I | CFC | 11.3 | 11.3 | 0 | 0 | 1997-05-01 | 2001-08-01 | 1999-06-01 |  | 2004-03-01 |  | 147300 | 0 | 147300 | 47993.55 | 32.58 | 99306.45 | 3402 | 3402 | 19149 | 0 | 6239.16 | 12909.84 | 442.26 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. FI completed site visit and PCR is in last stage of finalization and signature. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/REF/22/INV/124 |  |  | 2000-12-01 | [5 empty] | INV | 0 | 0 | 0 | 0
COM | IBRD | Elimination of CFCs in the manufacture of domestic refrigerators at Maharaja International Ltd. | Individual | ASP | IND | REF | 22 | INV | 125 | N | O | I | CFC | 59.8 | 59.8 | 0 | 0 | 1997-05-01 | 2002-12-01 | 1999-11-01 |  | 2004-01-01 |  | 510000 | -242993 | 267007 | 248224.69 | 92.96 | 18782.31 | 0 | 0 | 66300 | -32340 | 31944.02 | 2015.98 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. PCR in process of review. Financial completion expected Feb. 05. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/REF/22/INV/125 |  |  |  | 2001-12-01 |  |  |  |  | INV | 0 | 0 | 0 | 0
COM | IBRD | Conversion of domestic refrigerator manufacture to cyclopentane blowing agent and either R-600a or HCF-134a refrigerant at Voltas Ltd. | Individual | ASP | IND | REF | 22 | INV | 126 | N | O | I | CFC | 379.83 | 379.83 | 0 | 0 | 1997-05-01 | 2000-07-01 | 2001-12-01 |  | 2003-11-01 |  | 2724378 | 454053 | 3178431 | 1630393 | 51.29 | 1548038 | 0 |  | 354169.14 | 59027 | 211951 | 201245.14 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. PCR under review. Financial completion expected Feb. 05. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/REF/22/INV/126 |  | 1999-11-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Polar Enterprises | Individual | ASP | IND | REF | 22 | INV | 131 | N | O | I | CFC | 10.8 | 10.8 | 0 | 0 | 1997-05-01 | 1998-07-01 | 1999-06-01 |  | 1999-09-01 | 2001-07-01 | 138190 | -189 | 138001 | 138001 | 100 | 0 | 0 |  | 17964.7 | -24.57 | 17940.13 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and PCR submitted |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/REF/22/INV/131 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of refrigerator manufacture to cyclopentane foam blowing agent and to HCF-134a refrigerant at Videocon Appliances Ltd. | Individual | ASP | IND | REF | 22 | INV | 134 | N | O | I | CFC | 351.7 | 351.7 | 0 | 0 | 1997-05-01 | 1999-10-01 | 1999-11-01 |  | 2001-12-01 | 2002-08-01 | 1835115 | 524053.41 | 2359168.41 | 2359168.41 | 100 | 0 | 0 |  | 238564.95 | 61500.14 | 300065.09 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project physically completed in 2001, however, was not reported as such by FI in time for the 2001 progress report. Subsequent draft PCR has confirmed correct date of completion. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/REF/22/INV/134 |  | 1999-11-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects for submission in 1997 and 1998 |  | ASP | IND | REF | 22 | PRP | 127 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-03-31 | 1997-12-01 |  | 1998-12-01 | 1998-12-01 | 80000 | 0 | 80000 | 80000 | 100 | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/REF/22/PRP/127 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Aarkay Industries | Individual | ASP | IND | REF | 23 | INV | 144 | N | O | I | CFC | 19.8 | 19.8 | 0 | 0 | 1997-11-01 | 1999-07-01 | 1999-06-01 |  | 2000-09-01 | 2001-01-01 | 135798 | 15128 | 150926 | 150926 | 100 | 0 | 0 |  | 17654 | 1967 | 19621 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | PCR is being finalized for submission in 2003. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/REF/23/INV/144 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Eliminationof CFCs in the manufacture of commercial refrigeration equipment at Saikrupa Industries | Individual | ASP | IND | REF | 23 | INV | 145 | N | O | I | CFC | 14.8 | 14.8 | 0 | 0 | 1997-11-01 | 1999-02-01 | 1999-06-01 |  | 2000-09-01 | 2001-01-01 | 125618 | 10524 | 136142 | 136142 | 100 | 0 | 0 |  | 16330.34 | 1368.12 | 17698.46 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | PCR is being finalized for submission in 2003. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/REF/23/INV/145 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Sarkar Refrigeration Industries | Individual | ASP | IND | REF | 23 | INV | 152 | N | O | I | CFC | 12 | 12 | 0 | 0 | 1997-11-01 | 2000-02-01 | 1999-06-01 |  | 2000-11-01 | 2002-06-01 | 117100 | -1955 | 115145 | 115145 | 100 | 0 | 0 |  | 15223 | -287 | 14936 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | PCR is being finalized for submission in 2003. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/REF/23/INV/152 |  |  | 2000-09-01 | [5 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Eliminationof CFCs in the manufacture of commercial refrigeration equipment at Sidwal Refrigeration Industries P. Ltd. | Individual | ASP | IND | REF | 23 | INV | 160 | N | O | I | CFC | 11.7 | 14.1 | 0 | 0 | 1997-11-01 | 1999-10-01 | 1999-06-01 |  | 2000-09-01 | 2002-05-01 | 169744 | 5038 | 174782 | 174782 | 100 | 0 | 0 |  | 22067 | 655.32 | 22722.32 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/REF/23/INV/160 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFCs in the manufacture of commercial refrigeration equipment at Sandeep Refrigeration | Individual | ASP | IND | REF | 25 | INV | 180 | N | O | I | CFC | 9.9 | 9.9 | 0 | 0 | 1998-07-01 | 1999-08-01 | 2000-08-01 |  | 2000-08-01 | 2001-04-01 | 107684 | -773 | 106911 | 106911 | 100 | 0 | 0 |  | 13998.92 | -100.49 | 13898.43 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and PCR submitted |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/REF/25/INV/180 | [8 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of CFC-11 and CFC-12 converting to HCFC-141b and HFC-134a in the manufacture of commercial refrigeration equipment at Prashant Refrigeration Appliances | Individual | ASP | IND | REF | 25 | INV | 182 | N | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 |  | 2000-08-01 |  |  | 1999-12-01 | 104058 | -104058 | 0 | 0 | 0 | 0 | 0 |  | 13527.54 | -13528 | 0 | -0.46 | -0.46 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Project has been cancelled. |  |  | #NAME? | 0 | 0 | 0 | 0 | IND/REF/25/INV/182 | [8 empty] | INV | 0 | 0 | 0 | 0
COM | IBRD | Elimination of CFC-11 and CFC-12 by converting to HCFC-141b and HFC-134a in the manufacture of domestic refrigerators at BPL Refrigeration Ltd. | Individual | ASP | IND | REF | 25 | INV | 183 | N | O | I | CFC | 136 | 136 | 0 | 0 | 1998-07-01 | 2002-12-01 | 2001-08-01 |  | 2002-12-01 |  | 722906 | 309707 | 1032613 | 1025029.54 | 99.26 | 7583.46 | 7583.46 |  | 93977.78 | 36570 | 129588.97 | 958.81 | 958.81 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. PCR in review process. Financial completion expected Feb. 05. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/REF/25/INV/183 | [8 empty] | INV | 0 | 0 | 0 | 0
COM | IBRD | Elimination of CFCs in the manufacture of domestic refrigerators at Whirlpool of India Ltd. | Individual | ASP | IND | REF | 27 | INV | 204 | N | O | I | CFC | 200.6 | 200.6 | 0 | 0 | 1999-03-01 | 2002-12-01 | 2002-04-01 |  | 2002-12-01 |  | 675165 | -271642 | 403523 | 398409 | 98.73 | 5114 | 0 |  | 84268.15 | -38845 | 44860.61 | 562.54 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. PCR to be submitted Jan. 05. Financial completion expected Feb. 05. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/REF/27/INV/204 | [8 empty] | INV | 0 | 0 | 0 | 0
COM | IBRD | Conversion of domestic refrigerator manufacture to either R600a or HFC-134a refrigerant at Godrej - GE Appliances Ltd. (GGEAL) | Individual | ASP | IND | REF | 30 | INV | 337 | N | O | I | CFC | 71.7 | 71.7 | 0 | 0 | 2000-03-01 | 2003-07-01 | 2002-04-01 |  | 2002-12-01 |  | 2050000 | 0 | 2050000 | 1719046 | 83.85 | 330954 | 330954 |  | 235500 | 0 | 199095.06 | 36404.94 | 36404.94 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. PCR in review process. Financial completion expected Feb. 05. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/REF/30/INV/337 | [7 empty] | 1999 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of projects in the industrial and chiller refrigeration subsectors |  | ASP | IND | REF | 30 | PRP | 255 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2001-12-01 |  | 2001-12-01 | 2001-12-01 | 150000 | 0 | 150000 | 150000 | 100 | 0 | 0 |  | 19500 | 0 | 19500 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/REF/30/PRP/255 | [7 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the MAC sector |  | ASP | IND | REF | 33 | PRP | 300 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2002-09-01 | 2001-12-01 |  | 2002-09-01 | 2002-09-01 | 40000 | 0 | 40000 | 40000 | 100 | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 | 2001 | #NAME? | #NAME? | #NAME? | #NAME? | Project submitted to and approved at the 38th ExCom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/REF/33/PRP/300 | [7 empty] | 2001 | Non-INV | 0 | 0 | 0 | 0
COM | IBRD | Complete phase out of CFC-12 to non-ODS technology (HFC-134a) for manufacturing of mobile air-conditioners (MACs) at Subros Limited (phase II) | Individual | ASP | IND | REF | 38 | INV | 357 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-11-01 | 2003-11-01 |  | 2003-11-01 |  | 1181693 | 0 | 1181693 | 1098416 | 92.95 | 83277 | 83277 |  | 222895 | 0 | 207187.01 | 15707.99 | 15707.99 | 2002 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. PCR in review stage. Financial completion expected Feb. 05. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/REF/38/INV/357 | [7 empty] | 2002 | INV | 0 | 0 | 0 | 0
FIN | IBRD | User-sector pre-investment studies |  | ASP | IND | SEV | 9 | PRP | 4 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 400000 | 11292 | 411292 | 411292 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/SEV/9/PRP/4 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1994) |  | ASP | IND | SEV | 12 | PRP | 20 | N | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-12-31 | 1994-12-01 |  | 1996-12-01 | 1996-12-01 | 430000 | -241165 | 188835 | 188835 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Complete. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/SEV/12/PRP/20 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects for India ODS II (1994) |  | ASP | IND | SEV | 12 | PRP | 21 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 70837 | -6037 | 64800 | 64800 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Complete. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/SEV/12/PRP/21 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Training of the Financial Intermediary on Multilateral Fund and World Bank project processing procedures | Individual | ASP | IND | SEV | 12 | TRA | 22 | N | O | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1995-03-01 | 1995-03-01 |  | 1995-03-01 | 1995-03-01 | 345000 | -239292 | 105708 | 105708 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Project preparation advance of $345,000 to IDBI has been cleared by the Bank to support the preparation of subprojects to be processed thru the umbrella grant agreement. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | IND/SEV/12/TRA/22 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Preparation/supervision of investment projects (1995) |  | ASP | IND | SEV | 16 | PRP | 142 | N | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 |  | 1995-12-01 |  |  | 1995-12-01 | 70000 | -70000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Closed. |  |  | #NAME? | 0 | 0 | 0 | 0 | IND/SEV/16/PRP/142 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects ODS I (1995) |  | ASP | IND | SEV | 16 | PRP | 32 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 24065 | 0 | 24065 | 24065 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Complete. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/SEV/16/PRP/32 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects ODS II (1995) |  | ASP | IND | SEV | 16 | PRP | 33 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 355246 | 0 | 355246 | 355246 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Complete. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/SEV/16/PRP/33 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | ASP | IND | SEV | 18 | PRP | 68 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1997-12-01 | 1997-12-01 | 300000 | 0 | 300000 | 300000 | 100 | 0 | 0 |  | 39000 | 0 | 39000 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Complete. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/SEV/18/PRP/68 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the refrigeration, solvent and halon production sectors |  | ASP | IND | SEV | 24 | PRP | 178 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1999-06-01 | 1999-06-01 | 80000 | 0 | 80000 | 80000 | 100 | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Complete. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/SEV/24/PRP/178 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of projects in the refrigeration, solvent and CFC-halon production sectors |  | ASP | IND | SEV | 27 | PRP | 203 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-06-30 | 2000-01-01 |  | 2000-12-01 | 2000-12-01 | 220000 | 0 | 220000 | 220000 | 100 | 0 | 0 |  | 28600 | 0 | 28600 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/SEV/27/PRP/203 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | ODS phase-out in sterilization and siliconisation of disposable syringes and needle at Hindustan Syringes and Medical Devices Private Ltd., Haryana | Individual | ASP | IND | SOL | 13 | INV | 26 | N | O | I | CFC | 53.2 | 56 | 0 | 0 | 1994-07-01 | 1996-03-01 | 1995-07-01 |  | 1996-12-01 | 1998-09-01 | 481000 | -22298 | 458702 | 458702 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Complete. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/SOL/13/INV/26 | 1996-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of 1,1,1 TCA from the precision cleaning processes at Modi Xerox | Individual | ASP | IND | SOL | 22 | INV | 112 | N | O | I | TCA | 6.07 | 6.07 | 0 | 0 | 1997-05-01 | 1997-12-01 | 1998-06-01 |  | 1998-06-01 | 1998-01-01 | 130819 | -25985 | 104834 | 104834 | 100 | 0 | 0 |  | 17006.47 | -3378.05 | 13628.42 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Complete. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/SOL/22/INV/112 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of projects in the solvent general sector |  | ASP | IND | SOL | 30 | PRP | 247 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 35000 | 0 | 35000 | 35000 | 100 | 0 | 0 |  | 4550 | 0 | 4550 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | IND/SOL/30/PRP/247 | [7 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Country programme preparation | Individual | ASP | IRA | SEV | 6 | CPG | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1992-12-01 |  |  | 1992-12-01 | 150000 | -150000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | 0 | 0 | 0 | 0 | IRA/SEV/6/CPG/2 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Preparation of investment projects (1992) |  | ASP | IRA | SEV | 6 | PRP | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1992-12-01 |  |  | 1992-12-01 | 40000 | -39579 | 421 | 421 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | 0 | 0 | 0 | 0 | IRA/SEV/6/PRP/3 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | LPG purification at Jordan Refinery Company | Individual | ASP | JOR | ARS | 7 | INV | 12 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1992-06-01 | 1997-01-01 | 1995-06-01 |  | 1998-01-01 | 1998-05-01 | 805000 | 0 | 805000 | 805000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. This project is part of the line-of-grant project and was covered by part of the $1.5 million total approved. $1,496,095 disbursed for the line-of-grant - balance returned to the 36th ExCom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | JOR/ARS/7/INV/12 | 1997-07-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC use in aerosol at Household and Toiletries | Individual | ASP | JOR | ARS | 7 | INV | 13 | N | O | I | CFC | 30 | 30 | 0 | 0 | 1992-06-01 | 1996-07-01 | 1995-06-01 |  | 1998-04-01 | 1998-05-01 | 135000 | 0 | 135000 | 135000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. This project is part of the line-of-grant project and was covered by part of the $1.5 million total approved. $1,496,095 disbursed for the line-of-grant - balance returned to the 36th ExCom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | JOR/ARS/7/INV/13 | 1997-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC use in aerosol at Haddad and Sons Inc. | Individual | ASP | JOR | ARS | 7 | INV | 14 | N | O | I | CFC | 85 | 85 | 0 | 0 | 1992-06-01 | 1995-08-01 | 1995-06-01 |  | 1997-12-01 | 1998-05-01 | 214200 | 0 | 214200 | 214200 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. This project is part of the line-of-grant project and was covered by part of the $1.5 million total approved. $1,496,095 disbursed for the line-of-grant - balance returned to the 36th ExCom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | JOR/ARS/7/INV/14 | 1997-07-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Aerosol conversion at Jordan Industrial Petrochemical Co. Ltd. (JIPCO) | Individual | ASP | JOR | ARS | 20 | INV | 26 | N | O | I | CFC | 98 | 98 | 0 | 0 | 1996-10-01 | 2002-12-01 | 1997-10-01 |  | 2003-10-01 | 2003-12-01 | 102855 | 0 | 102855 | 102855 | 100 | 0 | 0 |  | 13371.15 | 0 | 13371.15 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | JOR/ARS/20/INV/26 |  | 2000-12-01 |  | 2002-03-01 |  |  |  |  | INV | 0 | 0 | 0 | 0
FIN | IBRD | Aerosol conversion at Jordan Antiseptics and Detergents Ind. Co. Ltd. (JADICO) | Individual | ASP | JOR | ARS | 20 | INV | 27 | N | O | I | CFC | 20 | 20 | 0 | 0 | 1996-10-01 | 1999-03-01 | 1997-10-01 |  | 1998-12-01 | 1999-05-01 | 65720 | 0 | 65720 | 65720 | 100 | 0 | 0 |  | 8543.6 | 0 | 8543.6 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | JOR/ARS/20/INV/27 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Aerosol conversion at Jordan Chemical Products Co. Ltd. (JCPCO) | Individual | ASP | JOR | ARS | 20 | INV | 28 | N | O | I | CFC | 61 | 61 | 0 | 0 | 1996-10-01 | 1998-01-01 | 1997-10-01 |  | 1998-12-01 | 1999-05-01 | 203328 | 0 | 203328 | 203328 | 100 | 0 | 0 |  | 26432.64 | 0 | 26432.64 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | JOR/ARS/20/INV/28 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation of projects in the aerosol sector |  | ASP | JOR | ARS | 30 | PRP | 59 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100 | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | JOR/ARS/30/PRP/59 | [7 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Substitution of CFC-12 for HAPs for perfumes and cosmetics at the aerosol plant Abu Shakra Factory | Individual | ASP | JOR | ARS | 31 | INV | 63 | N | O | I | CFC | 18 | 18 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2003-01-01 |  | 2003-08-01 | 2003-11-01 | 76676 | 0 | 76676 | 76676 | 100 | 0 | 0 |  | 9967.88 | 0 | 9967.88 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? | Enterprise has ceased using CFCs. Project conversion is completed. Remaining amount of the grant has been requested and payment process initiated. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | JOR/ARS/31/INV/63 | [7 empty] | 2000 | INV | 0 | 0 | 0 | 0
ONG | IBRD | Substitution of CFC-12 for HAPs at the aerosol plant of Arab Chemical Industries | Individual | ASP | JOR | ARS | 31 | INV | 64 | N | O | I | CFC | 13 | 13 | 0 | 0 | 2000-07-01 | 2002-12-01 | 2003-01-01 | 2005-02-01 |  |  | 49539 | 0 | 49539 | 49539 | 100 | 0 | 0 |  | 6440.07 | 0 | 6440.07 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? | Project is technically completed but equipment disposal pending. Use of CFC-12 stopped since 2003. PCR under preparation. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | JOR/ARS/31/INV/64 | [5 empty] | 2003-06-01 |  | 2000 | INV | 0 | 0 | 0 | 0
TRF | IBRD | Reduction of CFC-11 in rigid insulation foams in domestic and commercial refrigerators | Individual | ASP | JOR | FOA | 7 | INV | 5 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1994-06-01 |  |  | 1994-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Transferred project to UNIDO. As it was part of a line-of-grant approval, funding for this item was reallocated to finance other line-of-grant activities in accordance with the ExCom approval. |  |  | #NAME? | 0 | 0 | 0 | 0 | JOR/FOA/7/INV/5 | 1994-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Phase out of CFC use in flexible foam at International Foam Industries Co. Ltd. | Individual | ASP | JOR | FOA | 7 | INV | 6 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1994-06-01 |  |  | 1994-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Closed. Company moved to the Sudan. |  |  | #NAME? | 0 | 0 | 0 | 0 | JOR/FOA/7/INV/6 | 1994-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC use in flexible foam at Kolaghassi Foam and Mattress Factory Co. | Individual | ASP | JOR | FOA | 7 | INV | 8 | N | O | I | CFC | 40 | 40 | 0 | 0 | 1992-06-01 | 1996-07-01 | 1994-06-01 |  | 1997-12-01 | 1998-05-01 | 172800 | -3904.84 | 168895.16 | 168895.16 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. This project is part of the line-of-grant project and was covered by part of the $1.5 million total approved. $1,496,095 disbursed for the line-of-grant - balance returned to the 36th ExCom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | JOR/FOA/7/INV/8 | 1997-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Technology transfer and engineering support | Individual | ASP | JOR | FOA | 7 | TAS | 7 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1995-01-01 | 1994-06-01 |  | 1996-06-01 | 1998-05-01 | 73000 | 0 | 73000 | 73000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Completed for Phase-1 ODS projects. It is part of a line-of-grant approval. The project was carried out as part of IS project. To avoid double counting, disbursement was claimed under the IS project approved at the 7th Meeting. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | JOR/FOA/7/TAS/7 | 1994-06-01 | [7 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Umbrella project for conversion to CFC-free technology at three flexible polyurethane foam factories at Arab Foam, Jordan Plastics, National Foam | Individual | ASP | JOR | FOA | 15 | INV | 22 | N | O | I | CFC | 114 | 114 | 0 | 0 | 1994-12-01 | 1998-08-01 | 1995-09-01 |  | 2002-12-01 | 2003-12-01 | 368500 | 0 | 368500 | 368500 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | JOR/FOA/15/INV/22 | 1997-10-01 | 1999-04-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Umbrella project for conversion to CFC-free technology at Five Star Polyurethane Foam Factory | Individual | ASP | JOR | FOA | 17 | INV | 24 | N | O | I | CFC | 20 | 20 | 0 | 0 | 1995-07-01 | 1997-02-01 | 1996-04-01 |  | 1998-03-01 | 1998-05-01 | 66000 | 0 | 66000 | 66000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | JOR/FOA/17/INV/24 | 1997-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of extruded polysterene at Al Hussam | Individual | ASP | JOR | FOA | 22 | INV | 31 | N | O | I | CFC | 50 | 50 | 0 | 0 | 1997-05-01 | 1999-12-01 | 1999-06-01 |  | 2000-07-01 | 2002-01-01 | 347855 | 0 | 347855 | 347855 | 100 | 0 | 0 |  | 45221.15 | 0 | 45221.15 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | JOR/FOA/22/INV/31 |  | 1999-12-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of flexible slabstock PUF (box foam) at Baybars | Individual | ASP | JOR | FOA | 22 | INV | 32 | N | O | I | CFC | 30 | 30 | 0 | 0 | 1997-05-01 | 2001-12-01 | 1998-11-01 |  | 2002-12-01 | 2003-12-01 | 112500 | 0 | 112500 | 112500 | 100 | 0 | 0 |  | 14625 | 0 | 14625 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | JOR/FOA/22/INV/32 |  | 1999-12-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (miscellaneous applications) at Fathei Abu Arja | Individual | ASP | JOR | FOA | 23 | INV | 37 | N | O | I | CFC | 105.4 | 105.4 | 0 | 0 | 1997-11-01 | 1999-12-01 | 2000-12-01 |  | 1999-12-01 | 2004-08-01 | 824869 | -7968 | 816901 | 816901 | 100 | 0 | 0 |  | 107233 | -1035.84 | 106197.13 | 0.03 | 0.03 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | FAA project is technically and financially completed. There is no more ODS used in production. Baseline equipment modified so as to fit the new alternative of 141-b. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | JOR/FOA/23/INV/37 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the foam general sector |  | ASP | JOR | FOA | 30 | PRP | 60 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100 | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | JOR/FOA/30/PRP/60 | [7 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Halon management programme, halon recovery, recycling and banking | Halon Banking | ASP | JOR | HAL | 29 | TAS | 53 | N | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2002-12-01 | 2003-12-01 | 2005-06-01 |  |  | 382250 | 0 | 382250 | 56000 | 14.65 | 326250 | 326250 | 150000 | 49693 | 0 | 7280.07 | 42412.93 | 42412.93 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Past delay due to rebidding and bid negotiations. Contract for halon recycling equipment signed Nov. 03. Equipment to be delivered, installed and trial-start-up planned by Feb. 05. Date of de-commissioning does not apply; the BCF extinguishers were collected and stored at project failicity for critical users only. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | JOR/HAL/29/TAS/53 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the halon non-recycling |  | ASP | JOR | HAL | 30 | PRP | 61 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 15000 | 0 | 15000 | 15000 | 100 | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | JOR/HAL/30/PRP/61 | [7 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Terminal halon-1211 and halon-1301 phaseout umbrella project for fire equipment manufacturers and suppliers in Jordan converting to ABC powder, CO2, HFC-227ea and inert gases as substitutes | Individual | ASP | JOR | HAL | 32 | INV | 69 | N | O | I | HAL | 421.8 | 421.8 | 0 | 0 | 2000-12-01 | 2002-12-01 | 2004-03-01 | 2005-09-01 |  |  | 563000 | 0 | 563000 | 511570.4 | 90.86 | 51429.6 | 51429.6 | 49000 | 71930 | 0 | 65359.25 | 6570.75 | 6570.75 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? | All contracts signed. All halon fire extinguishing companies completed conversion. Remaining amount of US$49,000 allocated for training is pending. Awaiting names of participants for training. Baseline equipment was destroyed and beneficiaries were compensated to stop using BCF. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | JOR/HAL/32/INV/69 | [5 empty] | 2003-06-01 |  | 2000 | INV | 0 | 0 | 0 | 0
ONG | IBRD | National ODS phase out plan: aerosol, foam, MAC service and solvent sectors | One off phaseout | ASP | JOR | PHA | 38 | INV | 77 | N | O | I |  | 157.4 | 32 | 0 | 0 | 2002-11-01 |  | 2009-11-01 | 2009-11-01 |  |  | 590000 | 0 | 590000 | 0 | 0 | 590000 | 590000 | 59000 | 74900 | 0 | 0 | 74900 | 74900 | 2002 | #NAME? | #NAME? | #NAME? | #NAME? | Specifications prepared, invitation to bid to be made Jan. 05. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | JOR/PHA/38/INV/77 | [7 empty] | 2002 | INV | 0 | 0 | 0 | 0
CLO | IBRD | Recovery and recycling of CFC-12 in refrigeration equipment and maintenance procedures and recycling in halon systems | Individual | ASP | JOR | REF | 7 | DEM | 10 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 |  | 1996-06-01 |  |  | 1994-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Cancelled. UNIDO took over. As it was part of a line-of-grant approval, funding for this item was reallocated to finance other line-of-grant activities in accordance with the ExCom approval. |  |  | #NAME? | 0 | 0 | 0 | 0 | JOR/REF/7/DEM/10 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects in air conditioning, commercial and domestic refrigeration (1992) |  | ASP | JOR | REF | 7 | PRP | 9 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1992-06-30 | 1996-06-01 |  | 1992-12-01 | 1992-12-01 | 500000 | -445139 | 54861 | 54861 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | JOR/REF/7/PRP/9 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1991) |  | ASP | JOR | SEV | 4 | PRP | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 24464 | -21052 | 3412 | 3412 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | JOR/SEV/4/PRP/2 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation |  | ASP | JOR | SEV | 4 | PRP | 34 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 25079 | 47196 | 72275 | 72275 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | JOR/SEV/4/PRP/34 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation | Individual | ASP | JOR | SEV | 6 | CPG | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 70000 | -17005 | 52995 | 52995 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | JOR/SEV/6/CPG/3 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Policy and monitoring measures | Individual | ASP | JOR | SEV | 7 | INS | 11 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1994-06-01 | 1995-12-01 |  | 1997-06-01 | 1997-06-01 | 100000 | 70000 | 170000 | 170000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | PIU fully operational. Total funding of $170,000 was disbursed. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | 0 | JOR/SEV/7/INS/11 | 1997-06-01 | [7 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1993) |  | ASP | JOR | SEV | 9 | PRP | 15 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 123200 | -38647 | 84553 | 84553 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | JOR/SEV/9/PRP/15 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Supervision of project implementation (1994) |  | ASP | JOR | SEV | 12 | PRP | 17 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 72900 | 6579 | 79479 | 79479 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | JOR/SEV/12/PRP/17 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | ASP | JOR | SEV | 16 | PRP | 23 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 64680 | 0 | 64680 | 64680 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | JOR/SEV/16/PRP/23 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | ASP | JOR | SEV | 18 | PRP | 25 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 40000 | 0 | 40000 | 40000 | 100 | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project preparation is completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | JOR/SEV/18/PRP/25 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Renewal of institutional strengthening | Individual | ASP | JOR | SEV | 22 | INS | 30 | N | O | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-06-01 | 1999-05-01 |  | 1999-05-01 | 1999-06-01 | 113333 | 0 | 113333 | 113333 | 100 | 0 | 0 |  | 14733 | 0 | 14733 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | PIU fully operational. Funds were fully disbursed. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | 0 | JOR/SEV/22/INS/30 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation to phase out CFC consumption that is not accounted for in the original country programme |  | ASP | JOR | SEV | 22 | PRP | 33 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-12-31 | 1997-12-01 |  | 1999-06-01 | 1999-06-01 | 30000 | 0 | 30000 | 30000 | 100 | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Completed |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | JOR/SEV/22/PRP/33 |  | 1999-06-01 | [6 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the foam and halon recycling sectors |  | ASP | JOR | SEV | 24 | PRP | 38 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1999-03-31 | 1998-12-01 |  | 1999-12-01 | 1999-12-01 | 30000 | 0 | 30000 | 30000 | 100 | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Completed |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | JOR/SEV/24/PRP/38 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of project in the aerosol and halon recycling sectors |  | ASP | JOR | SEV | 27 | PRP | 44 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-31 | 2000-01-01 |  | 1999-12-01 | 1999-12-01 | 5000 | 0 | 5000 | 5000 | 100 | 0 | 0 |  | 650 | 0 | 650 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Completed |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | JOR/SEV/27/PRP/44 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Renewal of institutional strengthening (phase II) |  | ASP | JOR | SEV | 28 | INS | 51 | N | O | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 1999-08-01 | 1999-08-01 |  | 2001-07-01 | 2001-07-01 | 113333 | 0 | 113333 | 113333 | 100 | 0 | 0 |  | 14733 | 0 | 14733 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | IS tranche completed and full funding dibursed. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | 0 | JOR/SEV/28/INS/51 |  |  | 2000-12-01 | [5 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme update | Individual | ASP | JOR | SEV | 31 | CPG | 67 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-07-01 | 2002-09-01 | 2001-04-01 |  | 2002-09-01 | 2002-09-01 | 50000 | 0 | 50000 | 50000 | 100 | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? | CP update submitted to the 38th ExCom. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | JOR/SEV/31/CPG/67 | [7 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Renewal of the institutional strengthening project |  | ASP | JOR | SEV | 34 | INS | 73 | N | O | I |  | 0 | 0 | 0 | 0 | 2001-07-01 | 2002-12-01 | 2003-08-01 |  | 2004-12-01 | 2004-12-01 | 133333 | 0 | 133333 | 113333 | 84.99 | 20000 | 0 |  | 17333.29 | 0 | 14733.29 | 2600 | 0 | 2001 | #NAME? | #NAME? | #NAME? | #NAME? | Final activities of this IS tranche completed. NOU supervised ongoing projects, organized Ozone Day and conducted public awareness. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | 0 | JOR/SEV/34/INS/73 | [7 empty] | 2001 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Extension of institutional strengthening project | Individual | ASP | JOR | SEV | 40 | INS | 79 | N | T | I | CFC | 12.2 | 0 | 0 | 0 | 2003-07-01 |  | 2005-07-01 | 2005-07-01 |  |  | 147333 | 0 | 147333 | 0 | 0 | 147333 | 147333 | 14700 | 11050 | 0 | 0 | 11050 | 11050 | 2003 | #NAME? | #NAME? | #NAME? | #NAME? | Phase 6 of the IS project focuses primarily on meeting Jordan's 50% CFC/halon consumption reduction targets in 2005 thru targeted activities, including in the aerosol, com. ref and servicing sectors, and coordination of IAs active in the country. Ongoing supervision and public awareness activies. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | 0 | JOR/SEV/40/INS/79 | [7 empty] | 2003 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation |  | AFR | KEN | SEV | 4 | PRP | 13 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 31498 | -22816 | 8682 | 8682 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | KEN/SEV/4/PRP/13 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion project at Argon Malaysia, Sdn. Bhd | Individual | ASP | MAL | ARS | 15 | INV | 53 | N | O | I | CFC | 38 | 38 | 0 | 0 | 1994-12-01 | 1997-04-01 | 1995-12-01 |  | 1997-08-01 | 1997-08-01 | 131200 | 0 | 131200 | 131200 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MAL/ARS/15/INV/53 | 1997-04-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of the aerosol filling plant Kontrak Manufacturing Services Sdn. Bhd. | Individual | ASP | MAL | ARS | 15 | INV | 55 | N | O | I | CFC | 200 | 200 | 0 | 0 | 1994-12-01 | 1997-06-01 | 1995-12-01 |  | 1998-10-01 | 1998-11-01 | 618000 | 0 | 618000 | 618000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MAL/ARS/15/INV/55 | 1997-07-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Tenco Industries Sdn., Bhd., aerosol conversion project | Individual | ASP | MAL | ARS | 18 | INV | 63 | N | O | D | CFC | 18 | 18 | 0 | 0 | 1995-11-01 | 1997-02-01 | 1996-11-01 |  | 1996-03-01 | 1997-03-01 | 79200 | 0 | 79200 | 79200 | 100 | 0 | 0 |  | 10296 | 0 | 10296 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MAL/ARS/18/INV/63 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of ODS in the process of EPE/EPS foam sheet at Star Foam Paper Products Sdn. Bhd. | Individual | ASP | MAL | FOA | 17 | INV | 59 | N | O | I | CFC | 66 | 66 | 0 | 0 | 1995-07-01 | 1997-07-01 | 1996-07-01 |  | 2000-10-01 | 2002-03-01 | 295000 | -43111 | 251889 | 251889 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Safety audit cannot be performed as enterprise out of business due to economic slowdown. Given this subproject was physically completed many years ago and the enterprise cannot recover its business, DOE and the Bank decided safety audit cannot be done and PCR should be sent to ExCom after receiving endorsement letter from the Government. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MAL/FOA/17/INV/59 | 1997-03-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 in the manufacture of polyurethane refrigerator panels at Penang Trading Co. | Individual | ASP | MAL | FOA | 19 | INV | 86 | N | O | I | CFC | 10.5 | 10.5 | 0 | 0 | 1996-05-01 | 2000-02-01 | 2000-05-01 |  | 2001-12-01 | 2000-05-01 | 71500 | -6500 | 65000 | 65000 | 100 | 0 | 0 |  | 9295 | -845 | 8450 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Project is physically and financially completed. Equipment and accessories have been installed and operated with 3-phase electrical supply in its new location. Enterprise has stopped using CFC and converted to alternative blowing agents since Nov. 2001. As no contingency was claimed, financial completion occurred when funding was, in this case, provided directly to supplier for capital costs. PCR to be submitted to the Bank in 02. The Bank is waiting for certificate of destruction from DOE before issuing an approval letter |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MAL/FOA/19/INV/86 | 1997-05-01 | 1999-06-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 in the manufactue of polyurethane cold-room insulation panels/truck container panels at Kejuruteraan Transfreeze Sdn Bhd | Individual | ASP | MAL | FOA | 19 | INV | 87 | N | O | I | CFC | 11.4 | 11.4 | 0 | 0 | 1996-05-01 | 2000-02-01 | 1997-05-01 |  | 2001-11-01 | 2000-05-01 | 71500 | -6500 | 65000 | 65000 | 100 | 0 | 0 |  | 9295 | -845 | 8450 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Project is physically and financially completed. Equipment and accessories have been installed and operated with 3-phrase electrical supply in its new location. Enterprise has stopped using CFC and converted to alternative blowing agents as of Dec. 2001. As no contingency was claimed, financial completion occurred when funding was, in this case, provided directly to supplier for capital costs. PCR to be submitted to the Bank Mar. 02. These both projects has two funding parts that are ICC and contingency. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MAL/FOA/19/INV/87 | 1997-05-01 | 1999-06-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Servicing, maintenance and recovery of portable extinguishers (halon-1211) and training programme | Individual | ASP | MAL | HAL | 6 | INV | 4 | N | O | I | HAL | 900 | 900 | 0 | 0 | 1992-02-01 | 1996-03-01 | 1993-02-01 |  | 1998-09-01 | 2002-04-01 | 720000 | -1150 | 718850 | 718850 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Project physically and financially completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MAL/HAL/6/INV/4 | 1997-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
COM | IBRD | National CFC phaseout plan: 2002 Annual Programme | Multiyear | ASP | MAL | PHA | 35 | INV | 145 | N | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2002-12-01 |  | 2002-12-01 |  | 1799940 | 0 | 1799940 | 1253615 | 69.64 | 546325 | 546325 | 546320 | 140395 | 0 | 97782.14 | 42612.86 | 42612.86 | 2001 | #NAME? | #NAME? | #NAME? | #NAME? | 2002 phaseout targets achieved. Verification report confirming phaseout was submitted to ExCom in advance and 2003 annual report was approved Jul. 03. Last MAC manufacturer in Malaysia (covered under the NCPP)completed its conversion in 2003. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MAL/PHA/35/INV/145 | [7 empty] | 2001 | INV | 0 | 0 | 0 | 0
COM | IBRD | National CFC phase-out plan: release of second tranche for implementation of the 2002 annual plan | Multiyear | ASP | MAL | PHA | 37 | INV | 147 | N | O | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2004-12-01 | 2003-08-01 |  | 2003-08-01 |  | 2969065 | 0 | 2969065 | 1331526 | 44.84 | 1637539 | 1637539 | 1637539 | 259216 | 0 | 116249.68 | 142966.32 | 142966.32 | 2002 | #NAME? | #NAME? | #NAME? | #NAME? | Delays in implementation of activities initially proposed in 2002 AWP were due to various reasons, among which were amendments to the Grant Agreement between Malaysia and the Bank, difficulties in establishing mechanisms for flow of funds and changes in PMU and NOU. However, Government met all its commitments to the MP and achieved required phaseout per Excom agreement. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MAL/PHA/37/INV/147 | [7 empty] | 2002 | INV | 1910.51 | 1671 | 0 | 0 | Yes | Yes | Yes
COM | IBRD | National CFC phase-out plan: 2003 annual work programme | Multiyear | ASP | MAL | PHA | 40 | INV | 149 | N | O | I | CFC | 292 | 292 | 0 | 0 | 2003-07-01 |  | 2004-07-01 |  | 2004-12-01 |  | 2013100 | 0 | 2013100 | 0 | 0 | 2013100 | 2013100 | 1500000 | 169179 | 0 | 0 | 169179 | 169179 | 2003 | #NAME? | #NAME? | #NAME? | #NAME? | Significant progress in NCFCP implementation as planned in AWP for 2004. Country met commitments to the MP as demontrated by its 2003 and 2004 consumption reports. Achievements for the year included near completion of conversion projects in the foam sector, progress in the conversion of the MAC servicing sector, development of final proposals for solvent sector, and completion of multiple public awareness and dissemination activities. Disbursement rates have increased as all parties involved become increasingly proficient in project preparation, appraisal and verification process. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MAL/PHA/40/INV/149 | [7 empty] | 2003 | INV | 1618.51 | 1472 | 0 | 0 | Yes | Yes | Yes
ONG | IBRD | National CFC phase-out plan: 2004 annual programme | Multiyear | ASP | MAL | PHA | 44 | INV | 154 | N | O | I | CFC | 430 | 0 | 0 | 0 | 2004-12-01 |  | 2005-12-01 | 2005-07-01 |  |  | 1688300 | 0 | 1688300 | 0 | 0 | 1688300 | 1688300 | 500000 | 143947 | 0 | 0 | 143947 | 143947 | 2004 | #NAME? | #NAME? | #NAME? | #NAME? | Activities are ongoing and details will be included in the CY05 annual workplan to be submitted for ExCom approval in July 2005. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MAL/PHA/44/INV/154 | [7 empty] | 2004 | INV | 1188.51 | 0 | 0 | 0 | Yes | No | No
FIN | IBRD | Conservation, leakage control and recycling of CFC-12 and demonstration project in MAC sector | Individual | ASP | MAL | REF | 6 | TAS | 5 | N | O | D | CFC | 370 | 370 | 0 | 0 | 1992-02-01 | 1994-03-01 | 1992-12-01 |  | 1997-06-01 | 1997-07-01 | 910000 | -1845 | 908155 | 908155 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | MAL/REF/6/TAS/5 | 1995-08-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Substitution of CFC-12 and CFC-11 with HFC-134a and HCFC-141b respectively and elimination of the use of 1.1.1. TCA in household refrigerator manufacturing at Matsuchita Electric Co. (Melcom) | Individual | ASP | MAL | REF | 15 | INV | 51 | N | O | D |  | 99.73 | 99.73 | 0 | 0 | 1994-12-01 | 1996-04-01 | 1997-12-01 |  | 1996-01-01 | 1997-08-01 | 1276500 | -4307 | 1272193 | 1272193 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. $5,096.82 will be returned. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MAL/REF/15/INV/51 | 1996-01-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-12 MAC system production equipment and conversion to HFC-134a MAC system manufacturing in Nippondenso Capital Sdn. Bhd. | Individual | ASP | MAL | REF | 18 | INV | 75 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1995-11-01 | 1997-03-01 | 1999-11-01 |  | 1998-11-01 | 1998-12-01 | 2232718 | -420628.19 | 1812089.81 | 1812089.81 | 100 | 0 | 0 |  | 290253.34 | -30624.23 | 259629.11 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. Disbursement figure in 1999 and 2000 progress reports is incorrect. Additional balance to be returned to 37th ExCom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MAL/REF/18/INV/75 | 1997-07-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-12 MAC manufacturing equipment and conversion to HFC-134a MAC system manufacturing at APM Air Conditioners Sdn., Bhd. | Individual | ASP | MAL | REF | 18 | INV | 76 | N | O | I |  | 5 | 5 | 0 | 0 | 1995-11-01 | 1998-01-01 | 1999-11-01 |  | 2001-12-01 | 2002-10-01 | 1181553 | -150254.79 | 1031298.21 | 1031298.21 | 100 | 0 | 0 |  | 153601.89 | -19533.15 | 134068.74 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project was physically and financially completed. DOE has endorsed destruction of equipment and disposal plan. PCR submitted. Balance to be returned at the 39th ExCom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MAL/REF/18/INV/76 | 1997-12-01 | 1999-06-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Reduction of the consumption of ODSs in the commercial air-conditioning sector via training, recovery and recycling of CFC-11 and CFC-12 in chillers at Mashrae | Individual | ASP | MAL | REF | 18 | TAS | 77 | N | O | I | CFC | 105 | 4.45 | 0 | 0 | 1995-11-01 | 1998-03-01 | 1996-11-01 |  | 2000-11-01 | 2002-10-01 | 824078 | -118061 | 706017 | 706017 | 100 | 0 | 0 |  | 107130.14 | -15347.93 | 91782.21 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Final PCR not submitted to ExCom as DOE and the Bank requested MASHRAE and CETEC to revise PCR to ensure that information accurately reflects the actual nature of this project including lessons learned. Actual ODP phaseout low because many chiller owners decided to replace the CFC unit with the new non-CFC unit instead of using the facility. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | MAL/REF/18/TAS/77 | 1997-12-01 | 1999-12-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase-out of CFC-12 MAC manufacturing equipment and conversion of HFC-134a MAC manufacturing equipment at UCM Industrial Corporation Berhad | Individual | ASP | MAL | REF | 19 | INV | 90 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1996-05-01 | 1998-05-01 | 2000-05-01 |  | 2000-08-01 | 2002-10-01 | 1468797 | -263251 | 1205546 | 1205546 | 100 | 0 | 0 |  | 190943.61 | -34222.63 | 156720.98 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Project was physically and financially completed. DOE has endorsed destruction of equipment and disposal plan. PCR submitted. Savings to be returned at the 39th ExCom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MAL/REF/19/INV/90 | 1997-12-01 |  | 2000-03-01 | [5 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation for MACs and compressors project category |  | ASP | MAL | REF | 30 | PRP | 132 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2001-12-01 | 2000-12-01 |  | 2001-12-01 | 2001-12-01 | 10000 | 0 | 10000 | 10000 | 100 | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MAL/REF/30/PRP/132 | [7 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of CFC-12 refrigerant with HFC 134a in the manufacturing of MAC system at Sanden International (M) Sdn., Bhd. | Individual | ASP | MAL | REF | 34 | INV | 144 | N | O | R | CFC | 0 | 0 | 0 | 0 | 2001-07-01 | 2003-02-01 | 2003-01-01 |  | 2002-08-01 | 2003-02-01 | 807280 | -15079 | 792201 | 792201 | 100 | 0 | 0 |  | 48440 | -904.74 | 47535.26 | 0 | 0 | 2001 | #NAME? | #NAME? | #NAME? | #NAME? | Project fully completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MAL/REF/34/INV/144 | [7 empty] | 2001 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation | Individual | ASP | MAL | SEV | 4 | CPG | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 16294 | -8287 | 8007 | 8007 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | MAL/SEV/4/CPG/2 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1991) |  | ASP | MAL | SEV | 4 | PRP | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 38289 | 5307 | 43596 | 43596 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MAL/SEV/4/PRP/3 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1992) |  | ASP | MAL | SEV | 6 | PRP | 6 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 120000 | -65592 | 54408 | 54408 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Initially we reported expenditure of $54,408 and expenditure of $35,201 for country program. However, that was due to a coding mistake and the expenditure has been adjusted to $89,609 and entry for country program removed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MAL/SEV/6/PRP/6 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1993) |  | ASP | MAL | SEV | 9 | PRP | 9 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 28200 | 916 | 29116 | 29116 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MAL/SEV/9/PRP/9 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | User-sector pre-investment studies (1993) |  | ASP | MAL | SEV | 10 | PRP | 10 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-06-30 | 1994-06-01 |  | 1993-12-01 | 1993-12-01 | 75000 | -58343 | 16657 | 16657 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MAL/SEV/10/PRP/10 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Up-date country programme | Individual | ASP | MAL | SEV | 12 | CPG | 34 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 25000 | 0 | 25000 | 25000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | The Country Program up-date is complete. Final document submitted to the Bank and the Government on 4/30/95. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | MAL/SEV/12/CPG/34 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Supervision of project implementation (1994) |  | ASP | MAL | SEV | 12 | PRP | 32 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 35815 | 12744 | 48559 | 48559 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MAL/SEV/12/PRP/32 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1994) |  | ASP | MAL | SEV | 12 | PRP | 36 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 66610 | 2803 | 69413 | 69413 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MAL/SEV/12/PRP/36 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects ODS I (1995) |  | ASP | MAL | SEV | 16 | PRP | 57 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 206488 | 0 | 206488 | 206488 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Preparation of subprojects which was initiated in 1994 is complete resulting in 11 proposals. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MAL/SEV/16/PRP/57 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects ODS II (1995) |  | ASP | MAL | SEV | 16 | PRP | 58 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 12258 | 0 | 12258 | 12258 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | This budget is being utilized to supervise the MACs and halon Recover and Recycling projects approved for Malaysia in 1993. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MAL/SEV/16/PRP/58 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | ASP | MAL | SEV | 18 | PRP | 84 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 30000 | 0 | 30000 | 30000 | 100 | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MAL/SEV/18/PRP/84 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | ASP | MAL | SEV | 21 | PRP | 92 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1998-03-01 | 1997-12-01 |  | 1999-06-01 | 1999-06-01 | 27000 | 0 | 27000 | 27000 | 100 | 0 | 0 |  | 3510 | 0 | 3510 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MAL/SEV/21/PRP/92 |  | 1999-06-01 | [6 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of projects in the solvent sector and a national CFC phase out programme |  | ASP | MAL | SEV | 27 | PRP | 135 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-31 | 2001-01-01 |  | 2000-12-01 | 2000-12-01 | 95000 | 0 | 95000 | 95000 | 100 | 0 | 0 |  | 12350 | 0 | 12350 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Ongoing |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MAL/SEV/27/PRP/135 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of metal cleaning process from 1,1,1 TCA to non-ozone depleting organic solvents in Ban Seng Lee Industries Sdn. Bhd. | Individual | ASP | MAL | SOL | 17 | INV | 62 | N | O | D | TCA | 3.36 | 3.36 | 0 | 0 | 1995-07-01 | 1996-09-01 | 1996-07-01 |  | 1996-07-01 | 1996-09-01 | 108400 | 0 | 108400 | 108400 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MAL/SOL/17/INV/62 | 1996-07-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of metal cleaning process from 1,1,1 TCA to hydrocarbons at AE Technology Sdn. Bhd. | Individual | ASP | MAL | SOL | 18 | INV | 79 | N | O | R | TCA | 17 | 16.8 | 0 | 0 | 1995-11-01 | 1996-11-01 | 1997-05-01 |  | 1995-08-01 | 1996-09-01 | 56893 | 0 | 56893 | 56893.2 | 100 | -0.4 | -0.4 |  | 7396.09 | 0 | 7396.12 | -0.03 | -0.03 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MAL/SOL/18/INV/79 | [8 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion of correction fluid manufacturing process from 1,1,1 TCA to non-ODS solvent at Mondial Sdn. Bhd. | Individual | ASP | MAL | SOL | 18 | INV | 80 | N | O | R |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1996-11-01 |  |  | 2001-03-01 | 144447 | -144447 | 0 | 0 | 0 | 0 | 0 |  | 18778.11 | -18778.11 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project cancelled. |  |  | #NAME? | 0 | 0 | 0 | 0 | MAL/SOL/18/INV/80 | 1997-07-01 | 1999-06-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of correction fluid manufacturing process from 1,1,1 TCA to non-ODS solvent at Widetech | Individual | ASP | MAL | SOL | 18 | INV | 81 | N | O | I | TCA | 29 | 29 | 0 | 0 | 1995-11-01 | 1997-09-01 | 1996-11-01 |  | 1997-12-01 | 1997-12-01 | 398418 | 0 | 398418 | 398418 | 100 | 0 | 0 |  | 51794.34 | 0 | 51794.34 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MAL/SOL/18/INV/81 | 1997-07-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of metal cleaning process from 1,1,1 TCA to hydrocarbons at Eng Teknologi Sdn. Bhd. | Individual | ASP | MAL | SOL | 18 | INV | 82 | N | O | I | TCA | 3.4 | 3.36 | 0 | 0 | 1995-11-01 | 1998-07-01 | 1996-11-01 |  | 1998-09-01 | 1999-02-01 | 117379 | 0 | 117379 | 117378.6 | 99.99 | 0.4 | 0.4 |  | 15259.27 | 0 | 15259.22 | 0.05 | 0.05 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MAL/SOL/18/INV/82 | 1997-04-01 | [7 empty] | INV | 0 | 0 | 0 | 0
ONG | IBRD | Umbrella project for the conversion of CFC-11, CFC-12 and CFC-113 into HFC, HCFC, HFE for technical aerosols at Tecnosol, Envatec and Dimmex | Individual | LAC | MEX | ARS | 41 | INV | 116 | N | O | I | CFC | 57.3 | 0 | 0 | 0 | 2003-12-01 |  | 2006-12-01 | 2006-12-01 |  |  | 252340 | 0 | 252340 | 0 | 0 | 252340 | 252340 | 100000 | 18925.5 | 0 | 1455.37 | 17470.13 | 17470.13 | 2003 | #NAME? | #NAME? | #NAME? | #NAME? | SGAs with TECNOSOL and DIMMEX were signed in Dec. 04. A study on how to validate gradual reductions that will take place at both firms has been completed by NAFIN and SEMARNAT. Delay in signing the SGA is explained by the fact that Government was drafting a law regulating the ban of CFCs in the sector, for which the enforcement date had not been clear. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MEX/ARS/41/INV/116 | [7 empty] | 2003 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of CFC-11 with HCFC-141b foam blowing in the manufacturing of commercial refrigeration in Refrigeración Ojeda | Individual | LAC | MEX | FOA | 5 | INV | 10 | N | O | I | CFC | 25 | 25 | 0 | 0 | 1991-11-01 | 1995-01-01 | 1992-11-01 |  | 1995-06-01 | 1995-09-01 | 494500 | 0 | 494500 | 494500 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MEX/FOA/5/INV/10 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | CFC-11 phase out at Refrigeración Ojeda | Individual | LAC | MEX | FOA | 5 | INV | 60 | N | O | I | CFC | 15.6 | 13 | 0 | 0 | 1991-11-01 | 1996-09-01 | 1996-06-01 |  | 1996-12-01 | 1996-12-01 | 390000 | 0 | 390000 | 390000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MEX/FOA/5/INV/60 | 1996-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Safety programme in aerosol plant and recycling training and demonstration project in MAC | Individual | LAC | MEX | MUS | 4 | TRA | 4 | N | O | I | CFC | 0 | 36 | 0 | 0 | 1991-06-01 | 1996-02-01 | 1992-11-01 |  | 1996-04-01 | 1996-04-01 | 180000 | -126208 | 53792 | 53792 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | MEX/MUS/4/TRA/4 | 1995-05-01 | [7 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Implementation of projects identified in the country programme | Individual | LAC | MEX | MUS | 5 | INV | 5 | N | O | I |  | 0 | 0 | 0 | 0 | 1991-11-01 |  | 1996-11-01 |  | 1996-12-01 | 1997-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MEX/MUS/5/INV/5 | 1996-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Demonstration programme in CFC recovery and recycling of the Instituto Mexicano del Seguro Social (IMSS) refrigeration equipment | Individual | LAC | MEX | REF | 5 | DEM | 6 | N | O | I | CFC | 15 | 15 | 0 | 0 | 1991-11-01 | 1996-12-01 | 1992-11-01 |  | 1996-12-01 | 1996-12-01 | 499918 | 0 | 499918 | 499918 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MEX/REF/5/DEM/6 | 1996-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of CFC-12 with HFC-134a refrigerant in the manufacturing of commercial refrigeration in Refrigeración Ojeda | Individual | LAC | MEX | REF | 5 | INV | 9 | N | O | I | CFC | 13 | 13 | 0 | 0 | 1991-11-01 | 1995-08-01 | 1992-11-01 |  | 1995-12-01 | 1995-12-01 | 211543 | 0 | 211543 | 211543 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MEX/REF/5/INV/9 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | ODS phase out at Gigante 1 | Individual | LAC | MEX | REF | 5 | INV | 61 | N | O | I | CFC | 38 | 5 | 0 | 0 | 1991-11-01 | 1996-08-01 | 1996-06-01 |  | 1997-09-01 | 1997-09-01 | 496380 | 0 | 496380 | 496380 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MEX/REF/5/INV/61 | 1997-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | ODS phase out at Aurrera 1 | Individual | LAC | MEX | REF | 5 | INV | 62 | N | O | I | CFC | 44 | 22.2 | 0 | 0 | 1991-11-01 | 1995-04-01 | 1997-01-01 |  | 1998-10-01 | 1998-10-01 | 500000 | 0 | 500000 | 500000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MEX/REF/5/INV/62 | 1997-01-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | ODS phase out at Gigante 2 | Individual | LAC | MEX | REF | 5 | INV | 63 | N | O | I | CFC | 18 | 0 | 0 | 0 | 1991-11-01 | 1996-09-01 | 1997-06-01 |  | 1998-10-01 | 1998-10-01 | 278070 | 0 | 278070 | 278070 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MEX/REF/5/INV/63 | 1997-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | ODS phase out at Chedraui stores | Individual | LAC | MEX | REF | 5 | INV | 64 | N | O | I | CFC | 15 | 15 | 0 | 0 | 1991-11-01 | 1996-08-01 | 1996-06-01 |  | 1996-08-01 | 1996-08-01 | 228120 | 0 | 228120 | 228120 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MEX/REF/5/INV/64 | 1997-03-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | ODS phase out at Aurrera 2 | Individual | LAC | MEX | REF | 5 | INV | 65 | N | O | I | CFC | 22 | 11.8 | 0 | 0 | 1991-11-01 | 1995-04-01 | 1997-01-01 |  | 1998-10-01 | 1998-10-01 | 275000 | 0 | 275000 | 275000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MEX/REF/5/INV/65 | 1997-01-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | CFC recovery and recycling of refrigeration equipment in Monterrey City (Climas Jiménez) | Individual | LAC | MEX | REF | 5 | TAS | 8 | N | O | I | CFC | 4 | 0.3 | 0 | 0 | 1991-11-01 | 1995-10-01 | 1992-11-01 |  | 1994-06-01 | 1995-12-01 | 29328 | 0 | 29328 | 29328 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | MEX/REF/5/TAS/8 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | CFC recovery and recycling programme through Quimobasicos, S.A. | Individual | LAC | MEX | REF | 5 | TAS | 13 | N | O | I | CFC | 140 | 260 | 0 | 0 | 1991-11-01 | 1994-10-01 | 1992-11-01 |  | 1994-07-01 | 1994-12-01 | 222540 | 0 | 222540 | 222540 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? | The annual rate of ODS phaseout has been determined and has exceeded phaseout expectations, resulting in a phase out of 260 tons of CFC phaseout. Project completed. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | MEX/REF/5/TAS/13 | [8 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Training of Quimobasicos personnel in the use of CFC recovery and recycling equipment | Individual | LAC | MEX | REF | 5 | TRA | 7 | N | O | I |  | 0 | 0 | 0 | 0 | 1991-11-01 |  | 1992-11-01 |  |  | 1996-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? | Project cancelled. |  |  | #NAME? | 0 | 0 | 0 | 0 | MEX/REF/5/TRA/7 | 1996-12-01 | [7 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Manufacture of complete heat exchanger systems for air conditioning equipment that use HFC-134a at Climas de Mexico | Individual | LAC | MEX | REF | 24 | INV | 78 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-09-01 | 1999-10-01 |  | 2000-05-01 | 2000-05-01 | 2359812 | 0 | 2359812 | 2359812 | 100 | 0 | 0 |  | 306775.56 | 0 | 306775.56 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. Indirect phaseout of 110.5 MT. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MEX/REF/24/INV/78 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the commercial refrigeration (end users) conversion projects |  | LAC | MEX | REF | 24 | PRP | 77 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1999-03-31 | 1998-12-01 |  | 1999-12-01 | 1999-12-01 | 80000 | 0 | 80000 | 80000 | 100 | 0 | 0 |  | 10400 | 0 | 10400 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MEX/REF/24/PRP/77 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of projects in the commercial refrigeration sector |  | LAC | MEX | REF | 30 | PRP | 93 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2001-12-01 | 2001-12-01 | 20000 | 0 | 20000 | 20000 | 100 | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MEX/REF/30/PRP/93 | [7 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 to HFC-134a technology in the production of MAC systems at Airtemp | Individual | LAC | MEX | REF | 34 | INV | 102 | N | O | I | CFC | 0 | 0 | 0 | 0 | 2001-07-01 | 2001-12-01 | 2003-01-01 |  | 2001-11-30 | 2002-03-01 | 1651430 | 0 | 1651430 | 1651430 | 100 | 0 | 0 |  | 191657.3 | 0 | 191657.3 | 0 | 0 | 2001 | #NAME? | #NAME? | #NAME? | #NAME? | Project successfully completed both physically and financially and all funding disbursed. PCR is under preparation and expected to be submitted in early 2003. Planned and indirect phaseout should be 60 tons on the basis of 1.1 kg installed per unit plus 2 kg of additional service charges (adding up to 3.1 kg per unit). |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MEX/REF/34/INV/102 | [7 empty] | 2001 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the MAC sector |  | LAC | MEX | REF | 36 | PRP | 106 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-04-01 | 2003-07-01 | 25000 | -20000 | 5000 | 5000 | 100 | 0 | 0 |  | 3250 | -2600 | 650 | 0 | 0 | 2002 | #NAME? | #NAME? | #NAME? | #NAME? | Project preparation commenced, however, upon further inspection at the enterprise, enterprise was determined ineligible. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MEX/REF/36/PRP/106 | [7 empty] | 2002 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation | Individual | LAC | MEX | SEV | 4 | CPG | 1 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 36061 | 26194 | 62255 | 62255 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | MEX/SEV/4/CPG/1 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1991) |  | LAC | MEX | SEV | 4 | PRP | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 68164 | 35178 | 103342 | 103342 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MEX/SEV/4/PRP/2 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1992) |  | LAC | MEX | SEV | 6 | PRP | 15 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 292076 | -223980 | 68096 | 68096 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Initially we reported expenditure of $60,082 and expenditure of $8,014 for country program. However, that was due to a coding mistake and the expenditure has been adjusted to $68,096 and entry for country program removed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MEX/SEV/6/PRP/15 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1993) |  | LAC | MEX | SEV | 9 | PRP | 21 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 123400 | -65386 | 58014 | 58014 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MEX/SEV/9/PRP/21 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Supervision of project implementation (1994) |  | LAC | MEX | SEV | 12 | PRP | 23 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 100000 | -35085 | 64915 | 64915 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Activities completed |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MEX/SEV/12/PRP/23 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1994) |  | LAC | MEX | SEV | 12 | PRP | 24 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 52286 | -44858 | 7428 | 7428 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Bank is evaluating its activities in the country. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MEX/SEV/12/PRP/24 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects for ODS I and ODS II (1995) |  | LAC | MEX | SEV | 16 | PRP | 38 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-31 | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 71744 | 0 | 71744 | 71744 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MEX/SEV/16/PRP/38 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | LAC | MEX | SEV | 21 | PRP | 51 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 60000 | 0 | 60000 | 60000 | 100 | 0 | 0 |  | 7800 | 0 | 7800 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MEX/SEV/21/PRP/51 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-113 used as a cleaning agent in the manufacturing of optical frames at Styloptic, S.A. | Individual | LAC | MEX | SOL | 5 | INV | 11 | N | O | I | CFC | 3.2 | 0.72 | 0 | 0 | 1991-11-01 | 1995-01-01 | 1992-11-01 |  | 1995-06-01 | 1995-06-01 | 79299 | 0 | 79299 | 79299 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MEX/SOL/5/INV/11 | 1995-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Recovery, reclaim and recycling of CFC-113 and methylchloroform through Química Omega S.A. plant | Individual | LAC | MEX | SOL | 5 | INV | 12 | N | O | I |  | 183.3 | 183.3 | 0 | 0 | 1991-11-01 | 1995-02-01 | 1992-11-01 |  | 1995-11-01 | 1995-11-01 | 295302 | 0 | 295302 | 295302 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MEX/SOL/5/INV/12 | 1995-11-01 | [7 empty] | INV | 0 | 0 | 0 | 0
ONG | IBRD | Sterilization group project to replace CFC-12 technology-based sterilization equipment by alternative technologies in the hospital medical sterilization sector | Individual | LAC | MEX | STE | 40 | INV | 115 | N | O | I | CFC | 14.5 | 0 | 0 | 0 | 2003-07-01 |  | 2005-07-01 | 2006-12-01 |  |  | 288700 | 0 | 288700 | 0 | 0 | 288700 | 288700 | 100000 | 21653 | 0 | 0 | 21653 | 21653 | 2003 | #NAME? | #NAME? | #NAME? | #NAME? | NAFIN is currently drafting the SGAs with institutions that applied for the assistance program. SGAs are expected to be signed Mar. 05. Delays occured due to verification process covering entire sector, for which a reallocation of funds among existing CFC-based units was prepared, considering that other units were converted at the country's own expense. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | MEX/STE/40/INV/115 | [7 empty] | 2003 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation (1991) | Individual | AFR | NIR | SEV | 4 | CPG | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1993-02-01 |  | 1991-12-01 | 1991-12-01 | 129981 | -44959 | 85022 | 85022 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | NIR/SEV/4/CPG/2 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Preparation of investment projects (1991) |  | AFR | NIR | SEV | 4 | PRP | 20 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1992-06-01 |  |  | 1992-06-01 | 82821 | -82821 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | 0 | 0 | 0 | 0 | NIR/SEV/4/PRP/20 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation (1992) | Individual | AFR | NIR | SEV | 6 | CPG | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 271255 | -214838 | 56417 | 56417 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | NIR/SEV/6/CPG/3 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Preparation of investment projects (1992) |  | AFR | NIR | SEV | 6 | PRP | 4 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 |  | 1993-02-01 |  |  | 1992-12-01 | 144078 | -144078 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | 0 | 0 | 0 | 0 | NIR/SEV/6/PRP/4 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation (1993) | Individual | AFR | NIR | SEV | 9 | CPG | 17 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 35100 | -11028 | 24072 | 24072 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | NIR/SEV/9/CPG/17 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Preparation of investment projects (1993) |  | AFR | NIR | SEV | 9 | PRP | 5 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 |  | 1994-03-01 |  |  | 1993-12-01 | 62500 | -62500 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | 0 | 0 | 0 | 0 | NIR/SEV/9/PRP/5 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation (1994) | Individual | AFR | NIR | SEV | 12 | CPG | 18 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-12-01 |  | 1995-12-01 | 1995-12-01 | 150000 | -143520 | 6480 | 6480 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Completed. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | NIR/SEV/12/CPG/18 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Preparation of investment projects (1994) |  | AFR | NIR | SEV | 12 | PRP | 8 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1995-12-01 |  |  | 1995-12-01 | 100000 | -100000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Completed. |  |  | #NAME? | 0 | 0 | 0 | 0 | NIR/SEV/12/PRP/8 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation (1995) | Individual | AFR | NIR | SEV | 16 | CPG | 19 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-31 | 1996-03-01 |  | 1997-06-01 | 1997-06-01 | 150000 | 0 | 150000 | 150000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Completed. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | NIR/SEV/16/CPG/19 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Halon consumption phase-out through a technical assistance programme and a halon recycling | Halon Banking | ASP | OMA | HAL | 41 | TAS | 8 | N | O | I |  | 0 | 0 | 0 | 0 | 2003-12-01 |  | 2005-12-01 | 2006-12-01 |  |  | 64600 | 0 | 64600 | 0 | 0 | 64600 | 64600 | 6500 | 5814 | 0 | 0 | 5814 | 5814 | 2003 | #NAME? | #NAME? | #NAME? | #NAME? | Implementation start has been delayed. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | OMA/HAL/41/TAS/8 | [7 empty] | 2003 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Phaseout of CFC-11 in the manufacture of flexible PUF molded and integral skin at Master Group: (Master Enterprises Ltd., Durafoam Ltd., Khyber Plastic and Polymer Industries Ltd., Procon En) | Individual | ASP | PAK | FOA | 17 | INV | 6 | N | O | I | CFC | 205 | 205 | 0 | 0 | 1995-07-01 | 1999-08-01 | 1997-01-01 | 2005-02-01 |  |  | 1247330 | 0 | 1247330 | 1246300 | 99.91 | 1030 | 1030 | 1030 | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Conveyors are in operation and the slabstock machine is in commercial production. The project is expected to complete in Feb. 05. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | PAK/FOA/17/INV/6 | 1999-05-01 | 1999-09-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 in the manufacture of molded and rigid PUF at Razi Sons | Individual | ASP | PAK | FOA | 18 | INV | 7 | N | O | I | CFC | 60 | 60 | 0 | 0 | 1995-11-01 | 1999-04-01 | 1997-05-01 |  | 2000-12-01 | 2003-08-01 | 493262 | 0 | 493262 | 493262 | 100 | 0 | 0 |  | 64124.06 | 0 | 64124.06 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project and draft PCR completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | PAK/FOA/18/INV/7 | 1998-12-01 | 1999-09-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation to phase out CFC consumption that is not accounted for in the country programme |  | ASP | PAK | FOA | 22 | PRP | 15 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1997-06-30 | 1998-05-01 |  | 1997-12-01 | 1997-12-01 | 25000 | 0 | 25000 | 25000 | 100 | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | PAK/FOA/22/PRP/15 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of integral skin polyurethane foam at Synthetic Products Enterprises (Pvt) Ltd. (SPEL) | Individual | ASP | PAK | FOA | 23 | INV | 16 | N | O | I | CFC | 13.6 | 13.6 | 0 | 0 | 1997-11-01 | 2000-10-01 | 2000-03-01 |  | 2002-01-01 | 2003-10-01 | 160625 | -23797 | 136828 | 136828.5 | 100 | -0.5 | -0.5 |  | 20881 | -3093.05 | 17787.5 | 0.45 | 0.45 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and PCR submitted. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | PAK/FOA/23/INV/16 | [8 empty] | INV | 0 | 0 | 0 | 0
ONG | IBRD | Umbrella project: Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (thermoware) | Individual | ASP | PAK | FOA | 23 | INV | 20 | N | O | I | CFC | 239.6 | 235.9 | 0 | 0 | 1997-11-01 | 2002-12-01 | 2000-03-01 | 2005-06-01 |  |  | 1600000 | 0 | 1600000 | 1277305.38 | 79.83 | 322694.62 | 322694.62 | 21400 | 208000 | 0 | 166049.7 | 41950.3 | 41950.3 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Issues pertaining to machinery installation and after sale service are being resolved with the supplier. A final visit by supplier for installation of 2 last machines and final training and TA to beneficiaries expected in Mar. 05. CFC is no longer in use. Two enterprises with SGAs have dropped out the project, one of which went bankrupt. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | PAK/FOA/23/INV/20 |  |  |  | 2001-12-01 |  |  |  |  | INV | 0 | 0 | 0 | 0
ONG | IBRD | Conversion to CFC-free technology in the manufacture of polyurethane foam (flexible slabstock, flexible moulded, rigid foam) at Diamond Group of Industries | Individual | ASP | PAK | FOA | 23 | INV | 22 | N | O | I | CFC | 64.1 | 64.1 | 0 | 0 | 1997-11-01 | 2001-09-01 | 2000-03-01 | 2005-02-01 |  |  | 563339 | 0 | 563339 | 506935 | 89.98 | 56404 | 56404 | 50000 | 73234 | 0 | 65901.49 | 7332.51 | 7332.51 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Supplier believes that software problem has been identified and enterprise/supplier have agreed to pursue matter bilaterally. A WB technical consultant will visit the enterprise in Feb. 05 to close the project. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | PAK/FOA/23/INV/22 | [8 empty] | INV | 0 | 0 | 0 | 0
ONG | IBRD | Terminal umbrella: Conversion to HCFC-141b and water blown technology in the manufacture of rigid polyurethane foam (thermoware) | Individual | ASP | PAK | FOA | 25 | INV | 25 | N | O | I | CFC | 105.65 | 105.65 | 0 | 0 | 1998-07-01 | 2002-12-01 | 2000-08-01 | 2005-06-01 |  |  | 718900 | 0 | 718900 | 466957.13 | 64.95 | 251942.87 | 251942.87 | 70000 | 93457 | 0 | 60704.43 | 32752.57 | 32752.57 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Issues pertaining to machinery installation and after sale service are being resolved with the supplier. A final visit by supplier for installation of 2 last machines and final training and TA to beneficiaries expected in Mar. 05. CFC is no longer in use. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | PAK/FOA/25/INV/25 |  |  |  | 2001-12-01 |  |  |  |  | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 through conversion to methylene chloride/LIA technology in the manufacture of flexible polyurethane slabstock foam at United Foam Industries | Individual | ASP | PAK | FOA | 26 | INV | 29 | N | O | I | CFC | 28.6 | 28.6 | 0 | 0 | 1998-11-01 | 2000-12-01 | 2000-12-01 |  | 2001-12-01 | 2002-01-01 | 178200 | 0 | 178200 | 178200 | 100 | 0 | 0 |  | 23166 | 0 | 23166 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and PCR submitted. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | PAK/FOA/26/INV/29 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 through conversion to water based technology in the manufacture of flexible molded polyurethane foam at Saleem Automotive Industries Ltd. | Individual | ASP | PAK | FOA | 26 | INV | 30 | N | O | I | CFC | 2.5 | 2.5 | 0 | 0 | 1998-11-01 | 2000-03-01 | 2000-06-01 |  | 1999-03-01 | 2000-12-01 | 33875 | -2272 | 31603 | 31603 | 100 | 0 | 0 |  | 4403.75 | -295.35 | 4108.4 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed, PCR submitted June 2000. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | PAK/FOA/26/INV/30 | [8 empty] | INV | 0 | 0 | 0 | 0
ONG | IBRD | Conversion from CFC-11 to water-based technology in the manufacture of rigid polyurethane shoe soles at Jaguar Industries | Individual | ASP | PAK | FOA | 29 | INV | 34 | N | O | I | CFC | 40 | 40 | 0 | 0 | 1999-11-01 | 2004-09-01 | 2001-12-01 | 2005-09-01 |  |  | 279280 | 0 | 279280 | 120600 | 43.18 | 158680 | 158680 | 150000 | 36306.4 | 0 | 15678 | 20628.4 | 20628.4 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Delay due to late payment to equipment supplier which involved counterpart funding and issues with exchange rate fluctuations. Baseline equipment dismantled. Equipment expected to be delivered Mar. 05 and installation expected to commence in Apr. 05. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | PAK/FOA/29/INV/34 |  |  |  |  | 2003-12-01 |  |  |  | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the rigid polyurethane foam |  | ASP | PAK | FOA | 30 | PRP | 37 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 12000 | 0 | 12000 | 12000 | 100 | 0 | 0 |  | 1560 | 0 | 1560 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | PAK/FOA/30/PRP/37 | [7 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Phase-out of the use of CFCs in remaining foam enterprises: Pakistan Insulation, Simpson Wire, HEPCO, Indus Plastic, Workman and Thermocraft Engineering | Individual | ASP | PAK | FOA | 41 | INV | 58 | N | O | I | CFC | 106.9 | 0 | 0 | 0 | 2003-12-01 |  | 2006-01-01 | 2006-01-01 |  |  | 658973 | 0 | 658973 | 0 | 0 | 658973 | 658973 | 300000 | 49423 | 0 | 0 | 49423 | 49423 | 2003 | #NAME? | #NAME? | #NAME? | #NAME? | Technical appraisals completed. SGA signing done for two enterprises and 4 remaining expected by Mar. 05. All enterprises have commenced equipment procurement process. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | PAK/FOA/41/INV/58 | [7 empty] | 2003 | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion of refrigerator manufacture from CFC-11 to cyclopentane foam blowing agenct and CFC-12 to R-134a refrigerant at Domestic Appliances Ltd. (DAL) | Individual | ASP | PAK | REF | 19 | INV | 11 | N | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1997-11-01 |  |  | 1999-11-01 | 257650 | -257650 | 0 | 0 | 0 | 0 | 0 |  | 33494.5 | -33494.5 | 0 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Subproject cancelled. |  |  | #NAME? | 0 | 0 | 0 | 0 | PAK/REF/19/INV/11 | 1998-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of polyurethane foam at Kold Kraft Ltd. | Individual | ASP | PAK | REF | 23 | INV | 18 | N | O | I | CFC | 11.5 | 11.5 | 0 | 0 | 1997-11-01 | 2000-10-01 | 2000-03-01 |  | 2002-12-01 | 2003-02-01 | 175000 | 0 | 175000 | 175000 | 100 | 0 | 0 |  | 22750 | 0 | 22750 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and PCR submitted. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | PAK/REF/23/INV/18 | [8 empty] | INV | 0 | 0 | 0 | 0
ONG | IBRD | Conversion to CFC-free technology in the manufacture of polyurethane foam (domestic refrigeration) at Cool Industries Ltd. (Waves) | Individual | ASP | PAK | REF | 23 | INV | 19 | N | O | I | CFC | 117.6 | 27 | 0 | 0 | 1997-11-01 | 2004-07-01 | 2000-03-01 | 2005-10-01 |  |  | 841750 | 0 | 841750 | 48326.92 | 5.74 | 793423.08 | 793423.08 | 700000 | 109428 | 0 | 6282.53 | 103145.47 | 103145.47 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Refrigeration conversion completed and CFC phased out. For foam, LC opened and equipment shipment expected Jan. 05. Delay due to last minute changes requested by Cool for equip. specs. Installation & commissioning expected in Sep. 05 after local works are completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | PAK/REF/23/INV/19 | [8 empty] | INV | 0 | 0 | 0 | 0
COM | IBRD | Conversion to CFC-free technology in the manufacture of polyurethane foam at Singer Pakistan Ltd. | Individual | ASP | PAK | REF | 23 | INV | 21 | N | O | I | CFC | 17.8 | 17.8 | 0 | 0 | 1997-11-01 | 2002-12-01 | 2000-03-01 |  | 2004-07-01 |  | 205893 | 0 | 205893 | 205000 | 99.56 | 893 | 893 | 893 | 26766 | 0 | 26649.91 | 116.09 | 116.09 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project physically completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | PAK/REF/23/INV/21 | [8 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of CFC-11 and CFC-12 by converting to HCFC-141b and HFC-134a in the manufacture of commercial refrigeration equipment at Dawlance P. Ltd. | Individual | ASP | PAK | REF | 25 | INV | 26 | N | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 |  | 2000-08-01 |  |  | 2001-03-01 | 477894 | -477894 | 0 | 0 | 0 | 0 | 0 |  | 62126.22 | -62126.33 | 0 | -0.11 | -0.11 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Project cancelled at the 33rd ExCom Meeting. |  |  | #NAME? | 0 | 0 | 0 | 0 | PAK/REF/25/INV/26 | [8 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of CFC-11 and CFC-12 converting to HCFC-141b and HFC-134a in the manufacture of refrigeration equipment at United Refrigeration Industries Ltd. | Individual | ASP | PAK | REF | 25 | INV | 27 | N | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 |  | 2000-08-01 |  |  | 2001-03-01 | 457815 | -457815 | 0 | 0 | 0 | 0 | 0 |  | 59515.95 | -59515.95 | 0 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Project cancelled at the 33rd ExCom Meeting. |  |  | #NAME? | 0 | 0 | 0 | 0 | PAK/REF/25/INV/27 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of CFC-11 and CFC-12 by converting to HCFC-141b and HFC134a in the manufacture of commercial refrigeration equipment at Shadman Electronic Industries P. Ltd. | Individual | ASP | PAK | REF | 25 | INV | 28 | N | O | I | CFC | 15.53 | 15.53 | 0 | 0 | 1998-07-01 | 2000-10-01 | 2000-08-01 |  | 2002-11-01 | 2003-02-01 | 236936 | 0 | 236936 | 236936 | 100 | 0 | 0 |  | 30801.68 | 0 | 30801.68 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and PCR submitted. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | PAK/REF/25/INV/28 | [8 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Phaseout of CFC-11 and CFC-12 by conversion to HCFC-141b and HFC-134a in the manufacture of domestic refrigeration equipment at Refrigerators Manufacturing Company Pakistan Ltd. | Individual | ASP | PAK | REF | 26 | INV | 31 | N | O | I |  | 0 | 0 | 0 | 0 | 1998-11-01 |  | 2000-12-01 |  |  | 2001-12-31 | 127804 | -127804 | 0 | 0 | 0 | 0 | 0 |  | 16614.52 | -16614.52 | 0 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Project cancelled at the 35th ExCom Meeting. |  |  | #NAME? | 0 | 0 | 0 | 0 | PAK/REF/26/INV/31 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of projects in the foam flexible sub-sector |  | ASP | PAK | REF | 30 | PRP | 35 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 9000 | 0 | 9000 | 9000 | 100 | 0 | 0 |  | 1170 | 0 | 1170 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | PAK/REF/30/PRP/35 | [7 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the refrigeration sector (railway) |  | ASP | PAK | REF | 30 | PRP | 36 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 16000 | 0 | 16000 | 16000 | 100 | 0 | 0 |  | 2080 | 0 | 2080 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | PAK/REF/30/PRP/36 | [7 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Pakistan Airconditioning Engineering Co. P. Ltd., (PAECO) | Individual | ASP | PAK | REF | 32 | INV | 39 | N | O | I | CFC | 19.7 | 19.7 | 0 | 0 | 2000-12-01 | 2004-12-01 | 2004-01-01 | 2005-08-01 |  |  | 176681 | 0 | 176681 | 129382.63 | 73.22 | 47298.37 | 47298.37 | 45000 | 22968.53 | 0 | 16819.74 | 6148.79 | 6148.79 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? | Machinery has been delivered, is partly installed and partly operational. Final installation and commissioning will take place after the return of staff in Feb. 05 from a training trip. No more CFC in use. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | PAK/REF/32/INV/39 | [7 empty] | 2000 | INV | 0 | 0 | 0 | 0
ONG | IBRD | Conversion from CFC-11 to HCFC-141b and from CFC-12 to HFC-134a technology in the manufacture of commercial refrigeration equipment at Mumtaz Engineers | Individual | ASP | PAK | REF | 32 | INV | 40 | N | O | I | CFC | 13.9 | 0 | 0 | 0 | 2000-12-01 | 2004-12-01 | 2004-01-01 | 2005-09-01 |  |  | 204736 | 0 | 204736 | 90720 | 44.31 | 114016 | 114016 | 110000 | 26615.68 | 0 | 11793.6 | 14822.08 | 14822.08 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? | Equipment contracts signed and delivery expected after May 05. To be installed by Aug. 05. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | PAK/REF/32/INV/40 | [7 empty] | 2000 | INV | 0 | 0 | 0 | 0
ONG | IBRD | Phaseout of the use of CFC-11 and CFC-12 in the manufacture of refrigeration equipment at Dawlance, United Refrigeration, Ice Age and at 29 small enterprises | Individual | ASP | PAK | REF | 42 | INV | 59 | N | O | I | CFC | 181.3 | 0 | 0 | 0 | 2004-04-01 |  | 2007-04-01 | 2007-04-01 |  |  | 1126855 | 0 | 1126855 | 0 | 0 | 1126855 | 1126855 | 800000 | 84514 | 0 | 0 | 84514 | 84514 | 2004 | #NAME? | #NAME? | #NAME? | #NAME? | Project appraisals completed for 3 large manufacturers and SGA signing expected by early 2005. Equipment selection process underway. Appraisal for the SME component expected in early 2005. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | PAK/REF/42/INV/59 | [7 empty] | 2003 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project identification and preparation (1993) |  | ASP | PAK | SEV | 11 | PRP | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-11-01 | 1993-12-31 | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 100000 | -91044 | 8956 | 8956 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | PAK/SEV/11/PRP/2 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1994) |  | ASP | PAK | SEV | 12 | PRP | 4 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 133191 | -38871 | 94320 | 94320 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | PAK/SEV/12/PRP/4 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1995) |  | ASP | PAK | SEV | 16 | PRP | 8 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 143009 | 0 | 143009 | 143009 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | PAK/SEV/16/PRP/8 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | ASP | PAK | SEV | 18 | PRP | 38 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 100000 | 0 | 100000 | 100000 | 100 | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | PAK/SEV/18/PRP/38 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the foam and refrigeration sectors |  | ASP | PAK | SEV | 21 | PRP | 12 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 45000 | 0 | 45000 | 45000 | 100 | 0 | 0 |  | 5850 | 0 | 5850 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | PAK/SEV/21/PRP/12 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the foam and refrigeration sectors |  | ASP | PAK | SEV | 24 | PRP | 23 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1998-12-01 | 1998-12-01 | 63000 | 0 | 63000 | 63000 | 100 | 0 | 0 |  | 8190 | 0 | 8190 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | PAK/SEV/24/PRP/23 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of projects in the foam and refrigeration sectors |  | ASP | PAK | SEV | 27 | PRP | 33 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-31 | 2001-01-01 |  | 2000-12-01 | 2000-12-01 | 66000 | 0 | 66000 | 66000 | 100 | 0 | 0 |  | 8580 | 0 | 8580 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | PAK/SEV/27/PRP/33 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Assistance for the country programme update | Individual | ASP | PAK | SEV | 36 | CPG | 46 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2003-04-01 |  | 2003-12-01 | 2003-12-01 | 45000 | 0 | 45000 | 45000 | 100 | 0 | 0 |  | 5850 | 0 | 5850 | 0 | 0 | 2002 | #NAME? | #NAME? | #NAME? | #NAME? | CPU submitted and approved at the 41st ExCom Meeting. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | PAK/SEV/36/CPG/46 | [7 empty] | 2002 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of a methyl bromide phase-out plan |  | ASP | PHI | FUM | 39 | PRP | 70 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2004-12-01 | 2004-09-01 |  | 2004-09-01 | 2004-12-01 | 50000 | 0 | 50000 | 50000 | 100 | 0 | 0 |  | 3750 | 0 | 3750 | 0 | 0 | 2003 | #NAME? | #NAME? | #NAME? | #NAME? | Meetings and workshops with Fertilizer and Pesticide Authority, a TWG and affected groups prior conducted. MBr consumption survey forwarded to Ozone Secretariat to support countrys request to lift potential non-compliance status. Proposed National MBr Strategy approved at the 45th ExCom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | PHI/FUM/39/PRP/70 | [7 empty] | 2003 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Technical assistance for a national methyl bromide phase-out strategy | One off phaseout | ASP | PHI | FUM | 44 | TAS | 76 | N | O | I | MBR | 9 | 0 | 0 | 0 | 2004-12-01 |  | 2008-12-01 | 2008-12-01 |  |  | 330000 | 0 | 330000 | 0 | 0 | 330000 | 330000 | 100000 | 24750 | 0 | 0 | 24750 | 24750 | 2004 | #NAME? | #NAME? | #NAME? | #NAME? | Activities have commenced, including planning of additional Gov. actions to control MBr consumption. Institutional arrangements for project implementation to be finalized in early 2005. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | PHI/FUM/44/TAS/76 | [7 empty] | 2004 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of tobacco fluffing process to carbon dioxide at Fortune Tobacco corporation | Individual | ASP | PHI | OTH | 9 | INV | 18 | N | O | I | CFC | 350 | 350 | 0 | 0 | 1993-03-01 | 1996-05-01 | 1995-03-01 |  | 1999-08-01 | 2000-08-01 | 4720000 | -267640 | 4452360 | 4452360 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Project fully completed on Dec. 30, 1999. Decommissioning of the G -13 Plant was done from Jan. 10 to May 7, 2000. PCR was endorsed to WB on August 2, 2000. Grant fund fully disbursed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | PHI/OTH/9/INV/18 | 1997-09-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of a national CFC phaseout plan |  | ASP | PHI | PHA | 35 | PRP | 65 | A | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2001-12-31 | 2002-12-01 |  | 2002-11-01 | 2002-11-01 | 70000 | 0 | 70000 | 70000 | 100 | 0 | 0 |  | 9100 | 0 | 9100 | 0 | 0 | 2001 | #NAME? | #NAME? | #NAME? | #NAME? | Completed. NCPP approved at the 38th ExCom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | PHI/PHA/35/PRP/65 | [7 empty] | 2001 | Non-INV | 0 | 0 | 0 | 0
COM | IBRD | National CFC phase out plan: manufacturing sector (first tranche) | Multiyear | ASP | PHI | PHA | 38 | INV | 69 | N | O | I |  | 0 | 0 | 0 | 0 | 2002-11-01 | 2003-12-01 | 2003-12-01 |  | 2003-12-01 |  | 2858473 | 0 | 2858473 | 405280.9 | 14.17 | 2453192.1 | 2453192.1 | 2453192.1 | 248663 | 0 | 35256.01 | 213406.99 | 213406.99 | 2002 | #NAME? | #NAME? | #NAME? | #NAME? | PMU established Sep. 03 and completely staffed in 2004. MDI strategy finalized Apr. 04 and corresponding Admin. Order signed Jun. 04. Technical specs for servicing sector equipment identified. Evaluation Committee for Accreditation of Equipment Suppliers created thru a DENR-EMB Special Order and 2 equipment suppliers accredited. Notice of Award issued for equipment procurement for training centers in Dec. 04. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | PHI/PHA/38/INV/69 | [7 empty] | 2002 | INV | 1960 | 1422 | 0 | 0 | Yes | Yes | Yes
COM | IBRD | National CFC phase-out plan (manufacturing sector): 2004 annual programme | Multiyear | ASP | PHI | PHA | 41 | INV | 71 | N | O | I | CFC | 150 | 150 | 0 | 0 | 2003-12-01 |  | 2004-12-01 |  | 2004-12-01 |  | 1877418 | 0 | 1877418 | 0 | 0 | 1877418 | 1877418 | 345419.62 | 160968 | 0 | 0 | 160968 | 160968 | 2003 | #NAME? | #NAME? | #NAME? | #NAME? | Activities underway. For manufacturing, 8 project proposals endorsed by DENR to the FI for appraisal. 2 SGAs signed. FI conducted orientation mtg for enterprises on procurement and disbursement procedures. For servicing, Code of Practice finalized. 222 trainers trained for RAC and MAC. 25 technicians trained to participate in Voucher System pilot. 2003 audit results show that actual CFC imports were 1,422.4 MT (537.6 MT less than NCPP max. allowable consumption level). |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | PHI/PHA/41/INV/71 | [7 empty] | 2003 | INV | 1810 | 0 | 0 | 0 | Yes | No | No
ONG | IBRD | National CFC phase-out plan: 2005 annual programme | Multiyear | ASP | PHI | PHA | 44 | INV | 75 | N | O | I | CFC | 301 | 0 | 0 | 0 | 2004-12-01 |  | 2005-12-01 | 2005-12-01 |  |  | 2160071 | 0 | 2160071 | 0 | 0 | 2160071 | 2160071 | 200000 | 186006 | 0 | 0 | 186006 | 186006 | 2004 | #NAME? | #NAME? | #NAME? | #NAME? | 2005 plan includes commencement of wider servicing sector activities after completion of the pilot phase, additional training of technicians, procurement for pilot reclamation facility and completion of several manufacturing sector projects. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | PHI/PHA/44/INV/75 | [7 empty] | 2004 | INV | 1509 | 0 | 0 | 0 |  | No | No
FIN | IBRD | Application of a reduced CFC blowing agent and non-CFC application preparation at Concepcion Industries | Individual | ASP | PHI | REF | 9 | INV | 7 | N | O | I | CFC | 40.8 | 78.3 | 0 | 0 | 1993-03-01 | 1996-01-01 | 1997-05-01 |  | 1998-10-01 | 1999-02-01 | 790000 | -46000 | 744000 | 744000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Full-production with C-pentane - Oct. 21, 1998. PCR was endorsed to WB on 01/12/99. Grant fund fully disbursed. No ODS eqpt. Dismantled - High pressure foam machine was used even at the start of operation. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | PHI/REF/9/INV/7 | 1997-07-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Application of a reduced CFC blowing agent and non-CFC application preparation at Sanyo Philippines | Individual | ASP | PHI | REF | 9 | INV | 8 | N | O | D | CFC | 12.6 | 23.9 | 0 | 0 | 1993-03-01 | 1996-01-01 | 1997-03-01 |  | 1996-11-01 | 1999-01-01 | 660000 | -37061 | 622939 | 622939 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Phase 2 completed 11/96 - adoption of HCFC 141b foam. PCR was endorsed to WB on 10/12/98. Grant fund fully disbursed. Date ODS Eqpt. Dismantled - 12/19/95 |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | PHI/REF/9/INV/8 | 1997-01-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Application of a reduced CFC blowing agent and non-CFC application preparation at Transunion (formerly called Federal Electric Company) | Individual | ASP | PHI | REF | 9 | INV | 9 | N | O | I | CFC | 6.6 | 26.4 | 0 | 0 | 1993-03-01 | 1997-09-01 | 1997-05-01 |  | 1998-10-01 | 2000-12-01 | 770000 | -204218.75 | 565781.25 | 565781.34 | 100 | -0.09 | -0.09 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Full production with C-pentane - Oct.1, 1998. PCR was endorsed to WB on 2/2/99. Date ODS Eqpt. Dismantled - 12/02/98. All safety equipmpent and other items are installed and operational. Total grant fund disbursed is $547,732.15 only (excluding FI fees). Completed revision of PCR's Table 5. Revised PCR submitted to WB on 10 Jan |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | PHI/REF/9/INV/9 | 1997-07-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Application of a reduced CFC blowing agent and non-CFC application preparation at Philippines Appliance Corporation (Philacor) | Individual | ASP | PHI | REF | 9 | INV | 19 | N | O | I | CFC | 240 | 240 | 0 | 0 | 1993-03-01 | 1995-12-01 | 1997-05-01 |  | 1998-04-01 | 1999-02-01 | 1770000 | 0 | 1770000 | 1770000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. PCR was endorsed to WB on 10/20/98. Date ODS Eqpt. Dismantled - 12/19/95. Grant fund fully disbursed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | PHI/REF/9/INV/19 | 1998-01-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Philacor, Concepcion, Sanyo and Transunion -- Engineering Design and Assistance for the Use of HFC-134a Refrigerant in Household Refrigerators | Individual | ASP | PHI | REF | 19 | INV | 45 | N | O | I | CFC | 91.9 | 27.1 | 0 | 0 | 1996-05-01 | 1997-10-01 | 1998-01-01 |  | 1998-05-01 | 1999-03-01 | 952000 | -485520 | 466480 | 466480 | 100 | 0 | 0 |  | 123760 | -58262.73 | 65497.27 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed - HFC 134a refrigeration systems. PCRs endorsed to WB on 12/1/99. Grant fund fully disbursed. Philacor's Calamba Plant is not covered with grant funding. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | PHI/REF/19/INV/45 | 1998-01-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation | Individual | ASP | PHI | SEV | 4 | CPG | 1 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 19952 | 17415 | 37367 | 37367 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | PHI/SEV/4/CPG/1 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1991) |  | ASP | PHI | SEV | 4 | PRP | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 10826 | 39489 | 50315 | 50315 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | PHI/SEV/4/PRP/3 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Controlled substances engineering project |  | ASP | PHI | SEV | 6 | PRP | 4 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-08-12 | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 400000 | -6325 | 393675 | 393675 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and closed. Balance of funds returned to Multilateral Fund. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | PHI/SEV/6/PRP/4 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1992) |  | ASP | PHI | SEV | 6 | PRP | 5 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 100000 | -57260 | 42740 | 42740 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | PHI/SEV/6/PRP/5 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Instititional strengthening for Ozone Desk Operations | Individual | ASP | PHI | SEV | 9 | INS | 10 | N | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1995-12-01 | 1996-03-01 |  | 1998-12-01 | 2002-05-01 | 209000 | 0 | 209000 | 209000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed physically and financially. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | 0 | PHI/SEV/9/INS/10 | 1998-06-01 | 1999-12-01 | [6 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1993) |  | ASP | PHI | SEV | 9 | PRP | 20 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 194550 | -129221 | 65329 | 65329 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | PHI/SEV/9/PRP/20 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
TRF | IBRD | Information exchange programme | Individual | ASP | PHI | SEV | 9 | TAS | 16 | N | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 |  | 1993-11-01 |  |  | 1993-11-01 | 200000 | -200000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Closed. Funds transferred to UNEP for its implementation at the request of the Govt. |  |  | #NAME? | 0 | 0 | 0 | 0 | PHI/SEV/9/TAS/16 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Technical assistance for the financial institution | Individual | ASP | PHI | SEV | 9 | TAS | 17 | N | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1995-08-01 | 1994-03-01 |  | 2000-04-01 | 2000-04-01 | 100000 | 0 | 100000 | 100000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Project and PCR completed. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | PHI/SEV/9/TAS/17 | 1998-06-01 | 1999-12-01 | [6 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | User-sector project identification and preparation (1993) |  | ASP | PHI | SEV | 11 | PRP | 24 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-11-01 |  | 1994-11-01 |  |  | 1994-12-01 | 150000 | -150000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | 0 | 0 | 0 | 0 | PHI/SEV/11/PRP/24 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Supervision of project implementation (1994) |  | ASP | PHI | SEV | 12 | PRP | 25 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 136027 | -93678 | 42349 | 42349 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | PHI/SEV/12/PRP/25 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Preparation of investment projects (1994) |  | ASP | PHI | SEV | 12 | PRP | 29 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 |  | 1995-03-01 |  |  | 1994-12-01 | 94900 | -94900 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | 0 | 0 | 0 | 0 | PHI/SEV/12/PRP/29 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | ASP | PHI | SEV | 16 | PRP | 36 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1996-12-31 | 1996-12-01 | 169937 | -70000 | 99937 | 99937 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | PHI/SEV/16/PRP/36 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Renewal of institutional strengthening |  | ASP | PHI | SEV | 28 | INS | 63 | N | O | I |  | 0 | 0 | 0 | 0 | 1999-07-01 | 2000-12-01 | 2001-08-01 |  | 2002-05-01 | 2002-05-01 | 139333 | 0 | 139333 | 139333 | 100 | 0 | 0 |  | 18113 | 0 | 18113 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Phase II completed and IS renewal approved at the 36th ExCom. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | 0 | PHI/SEV/28/INS/63 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
COM | IBRD | Renewal of institutional strengthening project (Phase III) |  | ASP | PHI | SEV | 36 | INS | 67 | N | O | I | CFC | 14.97 | 14.97 | 0 | 0 | 2002-03-01 | 2002-12-01 | 2004-04-01 |  | 2004-12-01 |  | 181133 | 0 | 181133 | 179671.86 | 99.19 | 1461.14 | 1461.14 | 1461.14 | 23547.29 | 0 | 23357.34 | 189.95 | 189.95 | 2002 | #NAME? | #NAME? | #NAME? | #NAME? | Revised CCO for ODS approved Apr. 04. Coordinated with Dept. of Foreign Affairs on ratifying the Beijing and Montreal Amendments and request for ratification included in the calendar of activities for 2004 of the Senate Foreign Relations Committee. Monitored investment projects and performed spot verification of shipments. Produced information, education & communication materials for distribution to the general public, industries and gov. agencies. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | 0 | PHI/SEV/36/INS/67 | [7 empty] | 2002 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Extension of institutional strengthening project | Individual | ASP | PHI | SEV | 42 | INS | 73 | N | T | I | CFC | 7.5 | 0 | 0 | 0 | 2004-04-01 | 2004-12-01 | 2005-04-01 | 2005-04-01 |  |  | 90566 | 0 | 90566 | 45160.38 | 49.86 | 45405.62 | 45405.62 | 45405.62 | 6792 | 0 | 3386.8 | 3405.2 | 3405.2 | 2004 | #NAME? | #NAME? | #NAME? | #NAME? | Scheme and forms for registration of dealers, retailers and resellers of ODS prepared and sent for comments to Env. Mgmnt Bureau. Tariff headings assigned for ODS and alternatives under new Tariff and Customs Code. Conducted a meeting with the Bureau of Fire Protection to discuss the formation of a TWG to come up with a mgmnt plan on existing halon stocks. Second half of Phase iV of the IS will be requested at the 45th ExCom. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | 0 | PHI/SEV/42/INS/73 | [7 empty] | 2004 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to semi-aqueous and aqueous cleaning solvents at Ionics Circuits, Inc. | Individual | ASP | PHI | SOL | 9 | INV | 11 | N | O | D |  | 85.7 | 85.7 | 0 | 0 | 1993-03-01 | 1996-08-01 | 1993-09-01 |  | 1995-09-01 | 1998-07-01 | 790000 | 0 | 790000 | 790000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. PCR endorsement to WB - 10/12/98. Grant fund fullly disbursed. Date ODS Eqpt. Dismantled - 8/16/96 |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | PHI/SOL/9/INV/11 | 1995-09-01 | [7 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion to low-emission processing and organic solvents at Pacific Semiconductors, Inc. | Individual | ASP | PHI | SOL | 9 | INV | 12 | N | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 |  | 1993-09-01 |  |  | 1996-10-01 | 710000 | -710000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Enterprise decided not to proceed with project. Project cancelled. |  |  | #NAME? | 0 | 0 | 0 | 0 | PHI/SOL/9/INV/12 | 1993-09-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to aqueous cleaning at Electronic Assemblies, Inc. | Individual | ASP | PHI | SOL | 9 | INV | 13 | N | O | I | CFC | 4 | 4.16 | 0 | 0 | 1993-03-01 | 1996-04-01 | 1993-09-01 |  | 1997-02-01 | 1998-07-01 | 710000 | -34141 | 675859 | 675859 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. PCR endorsement to WB - 10/12/98. Grant fund fully disbursed. Date ODS Eqpt. Dismantled - 6/11/96 |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | PHI/SOL/9/INV/13 | 1997-02-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to high-purity water cleaning at Integrated Microelectronic, Inc. | Individual | ASP | PHI | SOL | 9 | INV | 14 | N | O | D | CFC | 14.6 | 14.6 | 0 | 0 | 1993-03-01 | 1997-08-01 | 1993-09-01 |  | 1997-12-01 | 1998-12-01 | 430000 | -72997.88 | 357002.12 | 357002.12 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. PCR endorsement to WB - 10/20/98. Grant fund fullly disbursed. Date ODS Eqpt. Dismantled - 5/19/98 |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | PHI/SOL/9/INV/14 | 1996-07-01 | [7 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion to semi-aqueous cleaning solvents at Ionics Circuits, Inc. | Individual | ASP | PHI | SOL | 9 | INV | 15 | N | O | I |  | 0 | 0 | 0 | 0 | 1993-03-01 |  | 1993-09-01 |  |  | 1997-02-01 | 70000 | -70000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Enterprise is no longer eligible for grant funding. Project cancelled. |  |  | #NAME? | 0 | 0 | 0 | 0 | PHI/SOL/9/INV/15 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation and user sector pre-investment studies (1993) | Individual | EUR | SLO | SEV | 11 | CPG | 1 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-11-01 |  | 1994-11-01 |  | 1994-12-01 | 1994-12-01 | 50000 | -50000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | SLO/SEV/11/CPG/1 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1993) |  | EUR | SLO | SEV | 11 | PRP | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-11-01 |  | 1995-03-01 |  | 1994-03-01 | 1994-03-01 | 100000 | -100000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | SLO/SEV/11/PRP/2 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation and user sector pre-investment studies (1994) | Individual | EUR | SLO | SEV | 12 | CPG | 4 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 50000 | 0 | 50000 | 50000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | SLO/SEV/12/CPG/4 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1994) |  | EUR | SLO | SEV | 12 | PRP | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 100000 | -22085 | 77915 | 77915 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | A workshop held on project preparation and processing procedures earlier in the year has helped the preparation of 8 subprojects in the refrigeration, foam, aerosol and solvents sectors. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | SLO/SEV/12/PRP/3 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Country programme preparation |  | ASP | SRL | SEV | 4 | PRP | 9 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1992-06-01 |  |  | 1992-06-01 | 23339 | -23339 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | 0 | 0 | 0 | 0 | SRL/SEV/4/PRP/9 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of CFC-11 with HCFC-141b as a foam blowing agent at Technic Foam, Ltd. | Individual | ASP | THA | FOA | 10 | INV | 23 | N | O | I | CFC | 50 | 50 | 0 | 0 | 1993-06-01 | 1999-09-01 | 1993-12-01 |  | 2000-01-01 | 2000-06-01 | 174000 | 0 | 174000 | 174000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. PCR approved by the WB in Jun/2000. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/FOA/10/INV/23 | 1997-12-01 | 1999-08-01 | [6 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (panels) at Alcan Nikkei Thai Aluminum Co. Ltd. | Individual | ASP | THA | FOA | 23 | INV | 72 | N | O | R |  | 0 | 0 | 0 | 0 | 1997-11-01 |  | 1999-11-01 |  |  | 1999-11-01 | 36500 | -36500 | 0 | 0 | 0 | 0 | 0 |  | 4745 | -4745 | 0 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project cancelled. |  |  | #NAME? | 0 | 0 | 0 | 0 | THA/FOA/23/INV/72 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (containers) at Can Asia Products Co. Ltd. | Individual | ASP | THA | FOA | 23 | INV | 73 | N | O | I | CFC | 16.8 | 16.8 | 0 | 0 | 1997-11-01 | 1999-08-01 | 1999-11-01 |  | 1999-10-01 | 2000-06-01 | 84300 | 0 | 84300 | 84300 | 100 | 0 | 0 |  | 10959 | 0 | 10959 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. PCR submitted to the WB in May/2000. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/FOA/23/INV/73 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in rigid sprayfoam applications at Thermobond Co. Ltd. | Individual | ASP | THA | FOA | 23 | INV | 74 | N | O | I | CFC | 10.4 | 10.4 | 0 | 0 | 1997-11-01 | 1999-04-01 | 1999-11-01 |  | 1999-07-01 | 2000-04-01 | 81400 | -4613 | 76787 | 76787 | 100 | 0 | 0 |  | 10582 | -599.69 | 9982.31 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. PCR submitted to the WB in Mar/2000. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/FOA/23/INV/74 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (thermoware) at Siam Chaicharoen Industry Co. Ltd. | Individual | ASP | THA | FOA | 23 | INV | 76 | N | O | I | CFC | 11.3 | 11.3 | 0 | 0 | 1997-11-01 | 1999-12-01 | 1999-11-01 |  | 2000-04-01 | 2000-06-01 | 88500 | 0 | 88500 | 88500 | 100 | 0 | 0 |  | 11505 | 0 | 11505 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. PCR submitted to the MLF Secretariat 30 June 2000. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/FOA/23/INV/76 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (thermoware) at General Injection Co. Ltd. | Individual | ASP | THA | FOA | 23 | INV | 77 | N | O | I | CFC | 15.4 | 15.4 | 0 | 0 | 1997-11-01 | 2000-01-01 | 1999-11-01 |  | 2000-06-01 | 2000-07-01 | 120580 | 0 | 120580 | 120580 | 100 | 0 | 0 |  | 15675 | 0 | 15675 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project Completed. PCR submitted to the WB in Jun/2000. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/FOA/23/INV/77 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (containers) at Viriyakit Plastic Industry Co. Ltd. | Individual | ASP | THA | FOA | 23 | INV | 78 | N | O | I | CFC | 27.5 | 27.5 | 0 | 0 | 1997-11-01 | 1999-01-01 | 1999-11-01 |  | 1999-02-01 | 1999-06-01 | 142700 | 0 | 142700 | 142700 | 100 | 0 | 0 |  | 18551 | 0 | 18551 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/FOA/23/INV/78 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in rigid spray foam applications at P.U. Foam Insulation and Trading Co. Ltd. | Individual | ASP | THA | FOA | 23 | INV | 79 | N | O | I | CFC | 58.1 | 58.1 | 0 | 0 | 1997-11-01 | 1998-12-01 | 1999-11-01 |  | 1999-08-01 | 1999-09-01 | 225400 | 0 | 225400 | 225400 | 100 | 0 | 0 |  | 29302 | 0 | 29302 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/FOA/23/INV/79 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam (containers) at Treathaboon Industry Co. Ltd. | Individual | ASP | THA | FOA | 23 | INV | 86 | N | O | I | CFC | 22.7 | 22.7 | 0 | 0 | 1997-11-01 | 1999-12-01 | 1999-11-01 |  | 1999-02-01 | 1999-12-01 | 177750 | -20563 | 157187 | 157187 | 100 | 0 | 0 |  | 23108 | -2673.19 | 20434.81 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/FOA/23/INV/86 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of cold store polyurethane panels at Somerville | Individual | ASP | THA | FOA | 25 | INV | 95 | N | O | I | CFC | 18.1 | 18.13 | 0 | 0 | 1998-07-01 | 2000-04-01 | 2001-08-01 |  | 2000-03-01 | 2000-04-01 | 141957 | -21957 | 120000 | 120000 | 100 | 0 | 0 |  | 18454.41 | -2854.41 | 15600 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. PCR submitted to the WB in Mar/2000. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/FOA/25/INV/95 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at P.E. Containers Supply Co. Ltd. | Individual | ASP | THA | FOA | 27 | INV | 108 | N | O | I | CFC | 29 | 29 | 0 | 0 | 1999-03-01 | 2000-06-01 | 1999-04-01 |  | 2000-09-01 | 2000-10-01 | 181883 | -8750 | 173133 | 173133 | 100 | 0 | 0 |  | 23644.79 | -1137.5 | 22507.29 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. PCR submitted to the MLF Secretariat January 2001. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/FOA/27/INV/108 | [8 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion from CFC-11 to water blown and HCFC-141b technology in the manufacture of rigid foam (spray) at Bangkok Integrated Trading Co. | Individual | ASP | THA | FOA | 27 | INV | 109 | N | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 |  | 1999-04-01 |  |  | 2001-12-31 | 117923 | -117923 | 0 | 0 | 0 | 0 | 0 |  | 15329.99 | -15329.99 | 0 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Project cancelled July 2000. |  |  | #NAME? | 0 | 0 | 0 | 0 | THA/FOA/27/INV/109 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Siam M.P. Co. Ltd. | Individual | ASP | THA | FOA | 27 | INV | 110 | N | O | I | CFC | 25.4 | 25.4 | 0 | 0 | 1999-03-01 | 2000-09-01 | 1999-04-01 |  | 2000-08-01 | 2000-10-01 | 164366 | -12500 | 151866 | 151866 | 100 | 0 | 0 |  | 21367.58 | -1625 | 19742.58 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. PCR submitted to the MLF Secretariat Nov. 2000. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/FOA/27/INV/110 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Siam Steel International PLC | Individual | ASP | THA | FOA | 27 | INV | 111 | N | O | I | CFC | 27.1 | 27.1 | 0 | 0 | 1999-03-01 | 2001-08-01 | 1999-04-01 |  | 2001-05-01 | 2002-03-01 | 196981 | -200 | 196781 | 196781 | 100 | 0 | 0 |  | 25607.53 | -26 | 25581.53 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Project physically and financially completed. DIW has endorsed destruction of equipment and disposal plan. PCR sent to ENV/WB. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/FOA/27/INV/111 |  |  | 2001-03-01 | [5 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid foam at Willich Sales & Contracting Co. Ltd. | Individual | ASP | THA | FOA | 27 | INV | 112 | N | O | I | CFC | 16.05 | 16.05 | 0 | 0 | 1999-03-01 | 2001-03-01 | 1999-04-01 |  | 2001-08-01 | 2002-11-01 | 58630 | 0 | 58630 | 58630 | 100 | 0 | 0 |  | 7621.9 | 0 | 7621.9 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Project physically and financially completed. DIW has endorsed destruction of equipment and disposal plan. PCR sent to ENV/WB. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/FOA/27/INV/112 |  |  | 2000-06-01 | [5 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 to water based and HCFC-141b technology in the manufacture of integral skin polyurethane foam and rigid moulded foam at Jennings Co. Ltd. | Individual | ASP | THA | FOA | 27 | INV | 113 | N | O | I | CFC | 14.35 | 14.35 | 0 | 0 | 1999-03-01 | 2000-05-01 | 2001-04-01 |  | 2001-02-01 | 2001-10-01 | 125249 | 0 | 125249 | 125249 | 100 | 0 | 0 |  | 16282.37 | 0 | 16282.37 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. PCR submitted to the WB in Sep. 01 |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/FOA/27/INV/113 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam at Plastmate Industry Co. Ltd. | Individual | ASP | THA | FOA | 27 | INV | 115 | N | O | I | CFC | 10.3 | 10.3 | 0 | 0 | 1999-03-01 | 2000-08-01 | 1999-04-01 |  | 2000-11-01 | 2000-11-01 | 80649 | -6500 | 74149 | 74149 | 100 | 0 | 0 |  | 10484.37 | -845 | 9639.37 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/FOA/27/INV/115 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to HCFC-141b technology in the manufacture of commercial refrigerator and display cabinets at Makassan Metal Works | Individual | ASP | THA | FOA | 28 | INV | 116 | N | O | I | CFC | 9.3 | 9.3 | 0 | 0 | 1999-07-01 | 2001-02-01 | 2002-02-01 |  | 2001-05-01 | 2002-07-01 | 72819 | 0 | 72819 | 72819 | 100 | 0 | 0 |  | 9466.47 | 0 | 9466.47 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Project physically and financially completed. DIW has endorsed destruction of equipment and disposal plan. PCR submitted. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/FOA/28/INV/116 |  |  |  | 2004-02-01 |  |  |  |  | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 to HCFC-141b technology in the manufacture of commercial refrigeration equipment at Arco Industry Co., Ltd | Individual | ASP | THA | FOA | 28 | INV | 130 | N | O | I | CFC | 16.8 | 16.32 | 0 | 0 | 1999-07-01 | 2001-12-31 | 2002-02-01 |  | 2001-09-01 | 2002-02-01 | 131544 | -3759 | 127785 | 127785 | 100 | 0 | 0 |  | 17100.72 | -488.67 | 16612.05 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Project physically and financially completed. DIW has endorsed destruction of equipment and disposal plan. PCR submitted. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/FOA/28/INV/130 |  |  |  | 2004-02-01 |  |  |  |  | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of projects in the rigid polyurethane subsector |  | ASP | THA | FOA | 30 | PRP | 127 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 30000 | 0 | 30000 | 30000 | 100 | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/FOA/30/PRP/127 | [7 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
COM | IBRD | Conversion from CFC-11 to water-based technology in the manufacture of integral skin and flexible molded polyurethane foam at Siam Chitose | Individual | ASP | THA | FOA | 31 | INV | 131 | N | O | I | CFC | 11.3 | 11.3 | 0 | 0 | 2000-07-01 | 2002-03-01 | 2003-08-01 |  | 2004-05-01 |  | 51795 | 0 | 51795 | 36893 | 71.22 | 14902 | 14902 | 14902 | 6733.35 | 0 | 4796.09 | 1937.26 | 1937.26 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? | Destruction of baseline equipment completed in Feb. 04. Commissioning and trial runs and start of ODS-free production completed in May 04. PCR under review by the WB. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/FOA/31/INV/131 | [7 empty] | 2000 | INV | 0 | 0 | 0 | 0
COM | IBRD | Conversion from CFC-11 to water-based technology in the manufacture of rigid polyurethane foam at Siam Cargo Containers | Individual | ASP | THA | FOA | 31 | INV | 132 | N | O | I | CFC | 22.7 | 22.7 | 0 | 0 | 2000-07-01 |  | 2003-08-01 |  | 2004-08-01 |  | 177741 | 0 | 177741 | 0 | 0 | 177741 | 98119 | 98119 | 23106.33 | 0 | 0 | 23106.33 | 12755.47 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? | Delays of equipment delivery by supplier caused significant overall project delays. However, final delivery and trial runs were conducted in Aug. 04. PCR submitted to ExCom Dec. 04. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/FOA/31/INV/132 | [7 empty] | 2000 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 to HCFC-141b technology in the manufacture of rigid polyurethane foam (sprayfoam and blocks) at Isotech | Individual | ASP | THA | FOA | 32 | INV | 133 | N | O | I | CFC | 22.7 | 22.7 | 0 | 0 | 2000-12-01 | 2001-10-01 | 2004-01-01 |  | 2001-11-01 | 2002-01-01 | 144943 | 0 | 144943 | 144943 | 100 | 0 | 0 |  | 18842.59 | 0 | 18842.59 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? | Project physically and financially completed. DIW has endorsed destruction of equipment and disposal plan. PCR sent to ENV/World Bank. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/FOA/32/INV/133 | [7 empty] | 2000 | INV | 0 | 0 | 0 | 0
COM | IBRD | Preparation of a methyl bromide phaseout strategy | Individual | ASP | THA | FUM | 33 | TAS | 135 | N | O | I |  | 0 | 0 | 0 | 0 | 2001-03-01 | 2003-12-01 | 2002-09-01 |  | 2004-12-01 |  | 80000 | 0 | 80000 | 68000 | 85 | 12000 | 12000 | 12000 | 10400 | 0 | 8840 | 1560 | 1560 | 2001 | #NAME? | #NAME? | #NAME? | #NAME? | Final National MeBr strategy prepared with input from natonal and international consultants. Strategy presented and approved at the 44th ExCom. Final payment to NC is expected in early 2005. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | THA/FUM/33/TAS/135 | [7 empty] | 2001 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | National methyl bromide phase-out plan (first tranche) | Multiyear | ASP | THA | FUM | 44 | INV | 143 | N | O | I | MBR | 58.7 | 0 | 0 | 0 | 2004-12-01 |  | 2006-12-01 | 2006-12-01 |  |  | 546991 | 0 | 546991 | 0 | 0 | 546991 | 546991 | 100000 | 41024 | 0 | 0 | 41024 | 41024 | 2004 | #NAME? | #NAME? | #NAME? | #NAME? | Consultation workshop will be held early in 2005 to present final strategy to stakeholders. Grant Agreement between the WB and Thailand needs to be amended before implementation starts and this is expected to happen in the first semester of 2005. Talks between the Bank, DOA and DIW have started, and the mechanisms for project implementation are being put into place. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/FUM/44/INV/143 | [7 empty] | 2004 | INV | 183 | 0 | 0 | 0
ONG | IBRD | Halon management programme, halon recovery, recycling and banking | Halon Banking | ASP | THA | HAL | 29 | TAS | 121 | N | O | I |  | 0 | 0 | 0 | 0 | 1999-11-01 | 2003-12-01 | 2003-12-01 | 2006-05-01 |  |  | 220750 | 0 | 220750 | 48360.15 | 21.9 | 172389.85 | 172389.85 | 101613 | 28697.5 | 0 | 6286.82 | 22410.68 | 22410.68 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Data analysis completed. According to the National Consultant's survey and report, it is not feasible to establish a physical halon bank in Thailand. Halon Steering Committee has proposed that an Electronic Clearing House be established. Bank review of updated consultant reports, as well as discussions with the Government are on-going. A final report will be prepared by FI and sent by early Feb. 05. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | THA/HAL/29/TAS/121 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of projects in halon non-recycling |  | ASP | THA | HAL | 30 | PRP | 125 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 8000 | 0 | 8000 | 8000 | 100 | 0 | 0 |  | 1040 | 0 | 1040 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/HAL/30/PRP/125 | [7 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Terminal halon-1211 and halon-1301 phaseout project for fire equipment manufacturers and suppliers converting to ABC powder, CO2, HFC-227ea and inert gases | Individual | ASP | THA | HAL | 32 | INV | 134 | N | O | I | HAL | 436 | 717.4 | 0 | 0 | 2000-12-01 | 2003-10-01 | 2004-02-01 | 2005-10-01 |  |  | 568000 | 0 | 568000 | 143768.61 | 25.31 | 424231.39 | 86360 | 86360 | 72480 | 0 | 18345.68 | 54134.32 | 11226.8 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? | Last appraisal report of Antifire Ltd. is expected to be approved by Bank in early 2005. Delays due to revisions and information needed to be confirmed with enterprise. Commissioning and trial runs expected to be completed by Jun. 05. Conversion of Nippon Chemical expected in Oct. 04 but delivery and installation of equipment delayed due to supplier. Installation of equipment and destruction of baseline equipment expected by early 2005. Green Cross Safety, Siam Sophon and Antifire Import Co,. Ltd have completed PCRs. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/HAL/32/INV/134 | [7 empty] | 2000 | INV | 0 | 0 | 0 | 0
COM | IBRD | National CFC phaseout plan: 2002 Annual Programme | Multiyear | ASP | THA | PHA | 35 | INV | 137 | N | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2003-12-01 | 2002-12-01 |  | 2002-12-01 |  | 540000 | 0 | 540000 | 540000 | 100 | 0 | 0 |  | 27000 | 0 | 27000 | 0 | 0 | 2001 | #NAME? | #NAME? | #NAME? | #NAME? | Implementation of initial project activities, as outlined in the 2002 AWP conducted. PMU carried out activities under three major components in 2004: (i) public awareness; (ii) investment activities; and (iii)policy related activities. PMU has been working actively to provide the Government with necessary support to carry out all activities proposed under the NCFCP. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/PHA/35/INV/137 | [7 empty] | 2001 | INV | 0 | 0 | 0 | 0
COM | IBRD | National CFC phase-out plan: release of second tranche for implementation of the 2002 annual plan | Multiyear | ASP | THA | PHA | 37 | INV | 138 | N | O | I |  | 0 | 0 | 0 | 0 | 2002-07-01 | 2003-12-01 | 2003-08-01 |  | 2003-12-01 |  | 5194380 | 0 | 5194380 | 188779 | 3.63 | 5005601 | 5005601 | 5005601 | 459494 | 0 | 16699.36 | 442794.64 | 442794.64 | 2002 | #NAME? | #NAME? | #NAME? | #NAME? | Delays in implementation of activities in the 2002 AWP were due to reasons including required amendments to the Grant Agreement between Thailand and the Bank, difficulties in establishing mechanisms for the flow of funds, and trouble signing agreements with beneficiary enterprises. However, the Government achieved the ODS phaseout required per the Excom agreement and funds from the approved 2002 AWP will be used to complete activities initially planned for 2002. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/PHA/37/INV/138 | [7 empty] | 2002 | INV | 3107.52 | 3103 | 0 | 0 | Yes | Yes | Yes
COM | IBRD | National CFC phase-out plan: 2003 annual programme | Multiyear | ASP | THA | PHA | 41 | INV | 140 | N | O | I | CFC | 486 | 486 | 0 | 0 | 2003-12-01 |  | 2004-12-01 |  | 2004-03-01 |  | 4011846 | 0 | 4011846 | 0 | 0 | 4011846 | 4011846 | 1900000 | 353066 | 0 | 0 | 353066 | 353066 | 2003 | #NAME? | #NAME? | #NAME? | #NAME? | Funding from this tranche was mainly allocated for investment projects in the TCA, solvent and foam sectors. With regards to phaseout activities in the solvent sector, SGA signed with one enterprise and baseline equipment disposed of. PCR will be submitted to PMU by Q105. For 1,1,1-TCA, disbursement to 2 enterprises will be made by Q105. EGAT is the final enterprise that will be converted in this sector. SGA signed and project expected to be completed in 2005. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/PHA/41/INV/140 | [7 empty] | 2003 | INV | 2818.52 | 1848 | 0 | 0 | Yes | Yes | Yes
ONG | IBRD | National CFC phase-out plan: 2004 annual programme | Multiyear | ASP | THA | PHA | 42 | INV | 141 | N | O | I | CFC | 486 | 0 | 0 | 0 | 2004-04-01 |  | 2005-04-01 | 2005-04-01 |  |  | 1315400 | 0 | 1315400 | 0 | 0 | 1315400 | 1315400 | 200000 | 118386 | 0 | 0 | 118386 | 118386 | 2004 | #NAME? | #NAME? | #NAME? | #NAME? | Funding from this tranche is planned to cover part of the MAC servicing equipment, fees for the MAC project Group Coordinator(GC), and for PMU. PMU developed a group sub-project proposal for the MAC service sector. As of Dec. 04, approximately 600 vouchers were hand-on certified MAC service shops. Vouchers for the rest will be continuing in 2005. Three GCs will be assigned to facilitate provision of equipment thru the voucher scheme. Contract signing between GCs and FI is expected by Feb. 05. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/PHA/42/INV/141 | [7 empty] | 2004 | INV | 2332.52 | 1358 | 0 | 0 | Yes | No | No
FIN | IBRD | CFC recycling in MAC | Individual | ASP | THA | REF | 7 | TAS | 7 | N | O | I | CFC | 250 | 86.93 | 0 | 0 | 1992-06-01 | 1999-01-01 | 1994-12-01 |  | 2003-12-01 | 2004-03-01 | 900000 | 0 | 900000 | 801085.63 | 89 | 98914.37 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | THA/REF/7/TAS/7 | 1999-05-01 | 1999-12-01 | 2001-12-01 | [5 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of ODS used in the production of household refrigerators at Thai Toshiba Electric Industries Co. Ltd. (Phase I) | Individual | ASP | THA | REF | 10 | INV | 17 | N | O | D |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1997-12-01 | 1996-06-01 |  | 1997-01-01 | 1998-02-01 | 823000 | -131273 | 691727 | 691727 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/REF/10/INV/17 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of ODS used in the production of household refrigerators at Kang Yong Electric Co. Ltd. (Kye) | Individual | ASP | THA | REF | 10 | INV | 18 | N | O | R | CFC | 109 | 109 | 0 | 0 | 1993-06-01 | 1997-12-01 | 1996-06-01 |  | 1997-01-01 | 1997-12-01 | 1140000 | -256628 | 883372 | 883372 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/REF/10/INV/18 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of ODS used in the production of household refrigerators at Sanyo Universal Electric Co. Ltd. (Phase I) | Individual | ASP | THA | REF | 10 | INV | 19 | N | O | D | CFC | 0 | 0 | 0 | 0 | 1993-06-01 | 1997-12-01 | 1996-06-01 |  | 1997-01-01 | 1998-01-01 | 1864000 | -1269071 | 594929 | 594929 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/REF/10/INV/19 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of ODS used in the production of household refrigerators at Hitachi Consumer Products Co. Ltd. | Individual | ASP | THA | REF | 10 | INV | 20 | N | O | D | CFC | 132 | 132 | 0 | 0 | 1993-06-01 | 1997-08-01 | 1996-06-01 |  | 1996-12-01 | 1998-10-01 | 553000 | 128861 | 681861 | 681861 | 100 | 0 | 0 |  | 0 | 32939.53 | 32939.53 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. Phase I was financially completed in Aug '97. Phase II was financially completed in Oct. '98. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/REF/10/INV/20 | 1996-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of compressor manufacture from CFC-12 to HFC-134a designs at Sanyo Universal Electric Co. Ltd. (Phase I) | Individual | ASP | THA | REF | 10 | INV | 21 | N | O | D | CFC | 0 | 0 | 0 | 0 | 1993-06-01 | 1996-09-01 | 1996-06-01 |  | 1997-01-01 | 1996-11-01 | 989000 | -330207 | 658793 | 658793 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/REF/10/INV/21 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of compressor manufacture from CFC-12 to HFC-134a designs at Kulthorn Kirby Co. Ltd. (Phase I) | Individual | ASP | THA | REF | 10 | INV | 22 | N | O | D | CFC | 0 | 0 | 0 | 0 | 1993-06-01 | 1997-01-01 | 1996-06-01 |  | 1995-12-01 | 1997-01-01 | 686000 | -85630 | 600370 | 600370 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/REF/10/INV/22 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Production of HFC-134a MAC parts at Nippodenso | Individual | ASP | THA | REF | 13 | INV | 37 | N | O | R | CFC | 0 | 0 | 0 | 0 | 1994-07-01 | 1997-03-01 | 1995-07-01 |  | 1993-12-01 | 1997-03-01 | 141500 | 0 | 141500 | 141500 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/REF/13/INV/37 | [8 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Phase out of CFC-11 in the manufacturing of equipment for the food and beverage industry at Siam Stainless Steel Co. Ltd. | Individual | ASP | THA | REF | 19 | INV | 52 | N | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1996-09-01 |  |  | 1999-03-01 | 212900 | -212900 | 0 | 0 | 0 | 0 | 0 |  | 27677 | -27677 | 0 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Project cancelled. Funds returned to 27th meeting. |  |  | #NAME? | 0 | 0 | 0 | 0 | THA/REF/19/INV/52 | 1997-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of compressor manufacture from CFC-12 to HFC-134a designs at Sanyo Universal Electric Co. Ltd. (Phase II) | Individual | ASP | THA | REF | 20 | INV | 58 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-12-01 | 1997-04-01 |  | 1997-01-01 | 1998-05-01 | 673680 | 224477 | 898157 | 898157 | 100 | 0 | 0 |  | 87578.4 | 29181.85 | 116760.25 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/REF/20/INV/58 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of compressor manufacture from CFC-12 to HFC-134a designs at Kulthorn Kirby Co. Ltd. (Phase II) | Individual | ASP | THA | REF | 20 | INV | 60 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1996-10-01 | 1997-10-01 | 1997-10-01 |  | 1997-01-01 | 1997-10-01 | 808234 | -94003 | 714231 | 714231 | 100 | 0 | 0 |  | 105070.42 | 10323.11 | 115393.53 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/REF/20/INV/60 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of ozone depleting substances used in the production of household refrigerators at A.P. National Co. Ltd. | Individual | ASP | THA | REF | 21 | INV | 57 | N | O | R | CFC | 54 | 54 | 0 | 0 | 1997-02-01 | 1997-12-01 | 1998-02-01 |  | 1997-01-01 | 1997-12-01 | 311150 | 0 | 311150 | 311150 | 100 | 0 | 0 |  | 40449.5 | 0 | 40449.5 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/REF/21/INV/57 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of ODS used in the production of household refrigerators at Sanyo Universal Electric Co. Ltd. (Phase II) | Individual | ASP | THA | REF | 21 | INV | 61 | N | O | R | CFC | 436 | 436 | 0 | 0 | 1997-02-01 | 1998-08-01 | 1997-08-01 |  | 1997-01-01 | 1998-08-01 | 1467055 | -84285 | 1382770 | 1382770 | 100 | 0 | 0 |  | 190717.15 | -5722.05 | 184995.1 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/REF/21/INV/61 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of ODS used in the production of household refrigerators at Thai Toshiba Electric Industries Co. Ltd. (Phase II) | Individual | ASP | THA | REF | 21 | INV | 62 | N | O | R | CFC | 89 | 89 | 0 | 0 | 1997-02-01 | 1998-05-01 | 1998-02-01 |  | 1997-01-01 | 1998-05-01 | 316957 | -19224 | 297733 | 297733 | 100 | 0 | 0 |  | 41204.41 | -1236.1 | 39968.31 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/REF/21/INV/62 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 refrigerant to HFC-134a and CFC-11 to HCFC-141b as the blowing agent for foam insulation in the manufacture of water coolers at Sirithana | Individual | ASP | THA | REF | 23 | INV | 80 | N | O | I | CFC | 8.06 | 8.06 | 0 | 0 | 1997-11-01 | 1999-07-01 | 1999-05-01 |  | 1999-08-01 | 1999-12-01 | 122593 | 0 | 122593 | 122593 | 100 | 0 | 0 |  | 15937 | 0 | 15937 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. PCR submitted to the WB in Dec/1999. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/REF/23/INV/80 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 commercial refrigeration to HC-134a, and CFC-11 to HCFC-141b as the blowing agent for foam insulation at Padriew Co. Ltd. | Individual | ASP | THA | REF | 23 | INV | 81 | N | O | I | CFC | 10.24 | 10.24 | 0 | 0 | 1997-11-01 | 1999-05-01 | 1999-05-01 |  | 1999-07-01 | 1999-08-01 | 135954 | 0 | 135954 | 135954 | 100 | 0 | 0 |  | 17674 | 0 | 17674 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/REF/23/INV/81 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 refrigerant to HFC-134a, and CFC-11 to HCFC-141b as the blowing agent for foam insulation in the manufacture of Water Coolers at Siam Cooler | Individual | ASP | THA | REF | 23 | INV | 82 | N | O | I | CFC | 26.38 | 12.38 | 0 | 0 | 1997-11-01 | 2000-04-01 | 1999-05-01 |  | 2000-08-01 | 2000-09-01 | 186545 | -8258 | 178287 | 178286.83 | 99.99 | 0.17 | 0.17 |  | 24251 | -1073.54 | 23177.46 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. PCR submitted to the World Bank 4 September 2000. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/REF/23/INV/82 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 commercial refrigeration to HFC-134a, and CFC-11 to HCFC-141b as the blowing agent for foam insulation at Sahakarn Intercool Co. Ltd. | Individual | ASP | THA | REF | 23 | INV | 85 | N | O | I | CFC | 5.7 | 5.7 | 0 | 0 | 1997-11-01 | 2000-03-01 | 1999-05-01 |  | 2000-07-01 | 2001-12-31 | 86697 | 0 | 86697 | 86697 | 100 | 0 | 0 |  | 11271 | 0 | 11271 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. PCR submitted to the MLF Secretariat January 2001. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/REF/23/INV/85 | [8 empty] | INV | 0 | 0 | 0 | 0
COM | IBRD | Terminal umbrella project to convert CFC-12 commercial refrigeration to HFC-134a, and CFC-11 to HCFC-141b as the blowing agent for foam insulation at 224 small and medium sized enterprises | Individual | ASP | THA | REF | 25 | INV | 92 | N | O | I | CFC | 173 | 200.3 | 0 | 0 | 1998-07-01 | 1999-04-01 | 2002-12-01 |  | 2004-12-01 |  | 750000 | 1881486 | 2631486 | 2265174.37 | 86.07 | 366311.63 | 366311.63 | 202140 | 97500 | 226963 | 279296.67 | 45166.33 | 45166.33 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Project physically completed at the end of 2004. Financial completion expected in 2005 along with submissio of the PCR. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/REF/25/INV/92 | [8 empty] | INV | 0 | 0 | 0 | 0
COM | IBRD | Programme to reduce the usage of CFC-11 and CFC-12 in chiller servicing by replacing CFC-based chillers with HFC-134a and HCFC-123 chillers at Electricity Generating Authority (EGAT) | Individual | ASP | THA | REF | 26 | INV | 104 | N | O | I | CFC | 13.2 | 13.2 | 0 | 0 | 1998-11-01 | 2003-10-01 | 2002-12-01 |  | 2003-09-01 |  | 2475000 | 0 | 2475000 | 1198946.93 | 48.44 | 1276053.07 | 0 |  | 282250 | 0 | 136729.17 | 145520.83 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Upon request from the Ministry of Finance, the Bank canceled, as of Nov. 15, 2004, $1,276,053.07 from the OTF Trust Fund Agreement. This amount is to be returned to the MLF in Apr. 05. PCR under preparation and expected to be completed in Mar. 05. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/REF/26/INV/104 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation | Individual | ASP | THA | SEV | 4 | CPG | 1 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-12-01 |  | 1992-12-01 | 1992-12-01 | 30909 | 220344 | 251253 | 251253 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | THA/SEV/4/CPG/1 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1991) |  | ASP | THA | SEV | 4 | PRP | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 32476 | 11678 | 44154 | 44154 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/SEV/4/PRP/3 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Controlled substances engineering project |  | ASP | THA | SEV | 6 | PRP | 4 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-12-08 | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 390000 | -40 | 389960 | 389960 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Completed and closed. Balance returned to Multilateral Fund. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/SEV/6/PRP/4 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1992) |  | ASP | THA | SEV | 6 | PRP | 5 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 120000 | 12195 | 132195 | 132195 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/SEV/6/PRP/5 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1993) |  | ASP | THA | SEV | 9 | PRP | 10 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 190000 | -10781 | 179219 | 179219 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/SEV/9/PRP/10 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | User-sector pre-investment studies (1993) |  | ASP | THA | SEV | 10 | PRP | 24 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-06-01 | 1993-06-30 | 1994-06-01 |  | 1993-12-01 | 1993-12-01 | 150000 | -104309 | 45691 | 45691 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/SEV/10/PRP/24 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Supervision of project implementation (1994) |  | ASP | THA | SEV | 12 | PRP | 28 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 129433 | 3256 | 132689 | 132689 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Umbrella Grant Agreement signed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/SEV/12/PRP/28 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1994) |  | ASP | THA | SEV | 12 | PRP | 32 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 81302 | -68062 | 13240 | 13240 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/SEV/12/PRP/32 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | ASP | THA | SEV | 16 | PRP | 43 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1997-12-01 | 1997-12-01 | 267138 | 0 | 267138 | 267138 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/SEV/16/PRP/43 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | ASP | THA | SEV | 18 | PRP | 50 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-01 | 1996-12-01 | 20000 | 0 | 20000 | 20000 | 100 | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/SEV/18/PRP/50 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | ASP | THA | SEV | 21 | PRP | 129 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 125000 | 0 | 125000 | 125000 | 100 | 0 | 0 |  | 16250 | 0 | 16250 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/SEV/21/PRP/129 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the foam, halon, commercial refrigeration (end users), and solvent sectors |  | ASP | THA | SEV | 24 | PRP | 88 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1999-06-01 | 1999-06-01 | 110000 | 0 | 110000 | 110000 | 100 | 0 | 0 |  | 14300 | 0 | 14300 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Completed |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/SEV/24/PRP/88 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of projects in the foam, halon, commercial refrigeration end-use and solvent sectors |  | ASP | THA | SEV | 27 | PRP | 107 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-06-30 | 2001-01-01 |  | 2000-12-01 | 2000-12-01 | 141000 | 0 | 141000 | 141000 | 100 | 0 | 0 |  | 18330 | 0 | 18330 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Ongoing |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/SEV/27/PRP/107 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Renewal of institutional strengthening project for the phaseout of ODS under the Montreal Protocol |  | ASP | THA | SEV | 35 | INS | 136 | N | O | I |  | 0 | 0 | 0 | 0 | 2001-12-01 | 2004-12-31 | 2003-07-01 |  | 2003-07-01 | 2004-12-01 | 0 | 225128 | 225128 | 225128 | 100 | 0 | 0 |  | 0 | 29267 | 29267 | 0 | 0 | 2001 | #NAME? | #NAME? | #NAME? | #NAME? | Project was completed and a terminal report and extension request was submitted to ExCom in Jul. 03. Funding was advanced to cover costs which was not received until 43rd ExCom. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | 0 | THA/SEV/35/INS/136 | [7 empty] | 2001 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Extension of institutional strengthening project | Individual | ASP | THA | SEV | 40 | INS | 139 | N | T | I | CFC | 28.6 | 18 | 0 | 0 | 2003-07-01 | 2003-12-01 | 2005-07-01 | 2005-11-01 |  |  | 346667 | 0 | 346667 | 204669.36 | 59.03 | 141997.64 | 141997.64 | 141997.64 | 26000 | 0 | 15350.19 | 10649.81 | 10649.81 | 2003 | #NAME? | #NAME? | #NAME? | #NAME? | NOU completed activities including, among others, data reporting, promoting and ensuring sustainable ODS phaseout, enhancing control of ODS imports, supporting implementation of ongoing individual conversion activities and collaborating with PMU in the implementation of the policy components of the NCFCP. In 2004, the NOU was instrumental in the development of the National MB Phaseout Plan. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | 0 | THA/SEV/40/INS/139 | [7 empty] | 2003 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Thai-Airways non-ODS metal cleaning |  | ASP | THA | SOL | 7 | PRP | 6 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1993-12-01 | 1994-06-01 |  | 1994-12-01 | 1994-12-01 | 100000 | 0 | 100000 | 100000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/SOL/7/PRP/6 | 1994-12-01 | [7 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to wet media blasting and aqueous cleaning solvents at Hana (BKK) Co., Ltd. | Individual | ASP | THA | SOL | 10 | INV | 12 | N | O | D |  | 16.1 | 16.1 | 0 | 0 | 1993-06-01 | 1996-07-01 | 1994-03-01 |  | 1993-12-01 | 1997-08-01 | 1010000 | -232835 | 777165 | 777165 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/SOL/10/INV/12 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to high-purity water cleaning at GSS Array | Individual | ASP | THA | SOL | 10 | INV | 13 | N | O | D | CFC | 16.1 | 16.1 | 0 | 0 | 1993-06-01 | 1996-03-01 | 1994-03-01 |  | 1993-12-01 | 1997-05-01 | 316000 | -41204 | 274796 | 274796 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/SOL/10/INV/13 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to high-purity water cleaning at Saha Union's Sriracha facility | Individual | ASP | THA | SOL | 10 | INV | 14 | N | O | R | CFC | 27.2 | 21.76 | 0 | 0 | 1993-06-01 | 1996-06-01 | 1994-03-01 |  | 1993-05-01 | 1997-05-01 | 2573000 | -472605 | 2100395 | 2100395 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/SOL/10/INV/14 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to aqueous cleaning at Thai Heat Exchange Co. Ltd. | Individual | ASP | THA | SOL | 10 | INV | 15 | N | O | I | TCA | 11 | 11 | 0 | 0 | 1993-06-01 | 1998-08-01 | 1994-03-01 |  | 1998-08-01 | 1998-08-01 | 268000 | -14000 | 254000 | 254000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/SOL/10/INV/15 | 1997-08-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to aqueous cleaning at C.I. Group Co. Ltd. | Individual | ASP | THA | SOL | 10 | INV | 16 | N | O | R | TCA | 12.7 | 12.7 | 0 | 0 | 1993-06-01 | 1998-05-01 | 1994-03-01 |  | 1995-12-01 | 1998-05-01 | 277000 | 0 | 277000 | 277000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/SOL/10/INV/16 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of electronic cleaning processes from CFC-113 to high-purity water cleaning at Team Tronics, Co. Ltd. | Individual | ASP | THA | SOL | 13 | INV | 34 | N | O | I | CFC | 12 | 11.5 | 0 | 0 | 1994-07-01 | 1998-05-01 | 1995-01-01 |  | 1999-08-01 | 1999-09-01 | 221760 | 0 | 221760 | 221760 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/SOL/13/INV/34 | 1997-12-01 | 1999-02-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase-out of ODS solvents at Thai Airways | Individual | ASP | THA | SOL | 15 | INV | 40 | N | O | I | CFC | 6 | 0 | 0 | 0 | 1994-12-01 | 1998-12-01 | 1996-06-01 |  | 1999-12-01 | 1999-12-01 | 463900 | -32600 | 431300 | 431300 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/SOL/15/INV/40 | 1997-12-01 | 1999-04-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of plastic lens cleaning processes from CFC-113 and 1,1,1 TCA to aqueous cleaning at Crystal Lens Corporation Ltd. | Individual | ASP | THA | SOL | 18 | INV | 48 | N | O | R |  | 1.86 | 1.86 | 0 | 0 | 1995-11-01 | 1998-08-01 | 1996-05-01 |  | 1996-12-01 | 1998-08-01 | 39830 | 0 | 39830 | 39830 | 100 | 0 | 0 |  | 5177.9 | 0 | 5177.9 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/SOL/18/INV/48 | 1996-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion of metal cleaning processes from 1,1,1 TCA to aqueous cleaning at BKJ Engineering Co. Ltd. (BKJ) | Individual | ASP | THA | SOL | 19 | INV | 53 | N | O | I |  | 0 | 0 | 0 | 0 | 1996-05-01 |  | 1997-02-01 |  |  | 1998-07-01 | 186487 | -186487 | 0 | 0 | 0 | 0 | 0 |  | 24243.31 | -24243 | 0 | 0.31 | 0.31 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Project cancellation |  |  | #NAME? | 0 | 0 | 0 | 0 | THA/SOL/19/INV/53 | 1997-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of precision cleaning processes from CFC-113 to aqueous and alternative solvent cleaning and conversion of insulator applications from CFC-113 to perfluorocarbons at Thai CRT Co. Ltd. | Individual | ASP | THA | SOL | 19 | INV | 54 | N | O | R | CFC | 5 | 5 | 0 | 0 | 1996-05-01 | 1997-05-01 | 1996-05-01 |  | 1995-09-01 | 1997-05-01 | 99440 | 0 | 99440 | 99440 | 100 | 0 | 0 |  | 12927.2 | 0 | 12927.2 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/SOL/19/INV/54 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of projects in the solvent (TCA) sector |  | ASP | THA | SOL | 30 | PRP | 128 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100 | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | THA/SOL/30/PRP/128 | [7 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Preparation of investment projects (1991) |  | LAC | TRI | SEV | 4 | PRP | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1991-12-01 |  |  | 1991-12-01 | 86843 | -86843 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | 0 | 0 | 0 | 0 | TRI/SEV/4/PRP/2 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Country programme preparation |  | LAC | TRI | SEV | 4 | PRP | 6 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1992-06-01 |  |  | 1992-06-01 | 107561 | -107561 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | 0 | 0 | 0 | 0 | TRI/SEV/4/PRP/6 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Technical seminar and conversion to non-CFC technology in aerosol sector | Individual | AFR | TUN | ARS | 7 | INV | 4 | N | O | I | CFC | 50 | 50 | 0 | 0 | 1992-06-01 | 1996-07-01 | 1993-06-01 |  | 1998-03-01 | 1998-06-01 | 239995 | 50000 | 289995 | 289995 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. Completion report provided in June 1998 |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUN/ARS/7/INV/4 | 1997-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Technical assistance and demonstration of non-CFC technology in rigid and flexible foam production | Individual | AFR | TUN | FOA | 7 | INV | 5 | N | O | I | CFC | 45 | 45 | 0 | 0 | 1992-06-01 | 1995-11-01 | 1993-02-01 |  | 1998-03-01 | 1998-06-01 | 218354.28 | 0 | 218354.28 | 218354.28 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. Completion report provided in June 1998. This project is part of a line-of-grant approval. The total expenditure was covered by the $1.79 million approval. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUN/FOA/7/INV/5 | 1997-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Introduction of low-CFC and non-CFC in rigid foams in refrigeration insulation at Tabrid | Individual | AFR | TUN | FOA | 7 | INV | 6 | N | O | I | CFC | 60 | 60 | 0 | 0 | 1992-06-01 | 1995-11-01 | 1993-06-01 |  | 1997-07-01 | 1998-06-01 | 258844 | 0 | 258844 | 258844 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. Final PCR provided in June 1998 |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUN/FOA/7/INV/6 | 1997-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the foam sector |  | AFR | TUN | FOA | 24 | PRP | 28 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1998-12-01 | 1998-12-01 | 25000 | 0 | 25000 | 25000 | 100 | 0 | 0 |  | 3250 | 0 | 3250 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUN/FOA/24/PRP/28 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
COM | IBRD | Conversion to LCD technology in the manufacture of polyurethane flexible foam and HCFC-141b with water in polyurethane rigid foam at Sotim | Individual | AFR | TUN | FOA | 25 | INV | 32 | N | O | I | CFC | 95.3 | 95.3 | 0 | 0 | 1998-07-01 | 2000-11-01 | 2000-08-01 |  | 2004-12-01 |  | 553400 | 0 | 553400 | 422036.9 | 76.26 | 131363.1 | 131363.1 | 131363.1 | 71942 | 0 | 54864.8 | 17077.2 | 17077.2 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Project is completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUN/FOA/25/INV/32 | [8 empty] | INV | 0 | 0 | 0 | 0
COM | IBRD | Phaseout of CFC-11 by conversion to liquid carbon dioxide technology in the manufacture of flexible polyurethane foam at Supermousse | Individual | AFR | TUN | FOA | 26 | INV | 33 | N | O | I | CFC | 93.5 | 93.5 | 0 | 0 | 1998-11-01 | 2000-01-01 | 2000-12-01 |  | 2004-12-01 |  | 529490 | 0 | 529490 | 422036.9 | 79.7 | 107453.1 | 107453.1 | 107453.1 | 68243.9 | 0 | 54394.69 | 13849.21 | 13849.21 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUN/FOA/26/INV/33 | [8 empty] | INV | 0 | 0 | 0 | 0
ONG | IBRD | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam at Coldeq by conversion to a combination of water and HCFC-141b based systems | Individual | AFR | TUN | FOA | 32 | INV | 36 | N | O | I | CFC | 8.8 | 0 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 | 2005-01-01 |  |  | 68917 | 0 | 68917 | 64525 | 93.62 | 4392 | 4392 | 4392 | 8959.21 | 0 | 8388.25 | 570.96 | 570.96 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? | Baseline equipment destroyed. Non-CFC production start-up expected Jan. 05. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUN/FOA/32/INV/36 | [7 empty] | 2000 | INV | 0 | 0 | 0 | 0
ONG | IBRD | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam at Bafes by conversion to a combination of water and HCFC-141b based systems | Individual | AFR | TUN | FOA | 32 | INV | 37 | N | O | I | CFC | 11.7 | 0 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 | 2005-01-01 |  |  | 91477 | 0 | 91477 | 86329 | 94.37 | 5148 | 5148 | 5148 | 11892.01 | 0 | 11222.77 | 669.24 | 669.24 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? | Baseline equipment destroyed. Non-CFC production start-up expected Jan. 05. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUN/FOA/32/INV/37 | [7 empty] | 2000 | INV | 0 | 0 | 0 | 0
ONG | IBRD | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam at Societe de Construction Industrialisee (SCI) by conversion to a combination of water and HCFC-141b based systems | Individual | AFR | TUN | FOA | 32 | INV | 38 | N | O | I | CFC | 8.3 | 0 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 | 2005-01-01 |  |  | 64700 | 0 | 64700 | 58730 | 90.77 | 5970 | 5970 | 5970 | 8411 | 0 | 7634.9 | 776.1 | 776.1 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? | Baseline equipment destroyed. Non-CFC production start-up expected Jan. 05. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUN/FOA/32/INV/38 | [7 empty] | 2000 | INV | 0 | 0 | 0 | 0
ONG | IBRD | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam at Societe Nouvelle de Coupe Industrielle (SNCI) by conversion to a combination of water and HCFC-141b based systems | Individual | AFR | TUN | FOA | 32 | INV | 39 | N | O | I | CFC | 20.3 | 0 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 | 2005-01-01 |  |  | 156235 | 0 | 156235 | 140611.5 | 90 | 15623.5 | 15623.5 | 15623.5 | 20310.55 | 0 | 18279.5 | 2031.05 | 2031.05 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? | Baseline equipment destroyed. Non-CFC production start-up expected Jan. 05. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUN/FOA/32/INV/39 | [7 empty] | 2000 | INV | 0 | 0 | 0 | 0
ONG | IBRD | Phasing out of CFC-11 in the manufacture of rigid polyurethane foam at Soften by conversion to a combination of water and HCFC-141b based systems | Individual | AFR | TUN | FOA | 32 | INV | 40 | N | O | I | CFC | 7.5 | 0 | 0 | 0 | 2000-12-01 | 2001-12-01 | 2004-01-01 | 2005-01-01 |  |  | 59079 | 0 | 59079 | 58083.1 | 98.31 | 995.9 | 995.9 | 995.9 | 7680.27 | 0 | 7550.8 | 129.47 | 129.47 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? | Baseline equipment destroyed. Non-CFC production start-up expected Jan. 05. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUN/FOA/32/INV/40 | [7 empty] | 2000 | INV | 0 | 0 | 0 | 0
CLO | IBRD | Project preparation in the foam sector |  | AFR | TUN | FOA | 36 | PRP | 42 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 |  | 2003-04-01 |  |  | 2003-07-01 | 10000 | -10000 | 0 | 0 | 0 | 0 | 0 |  | 1300 | -1300 | 0 | 0 | 0 | 2002 | #NAME? | #NAME? | #NAME? | #NAME? | Project prep. cancelled at the 41st ExCom. |  |  | #NAME? | 0 | 0 | 0 | 0 | TUN/FOA/36/PRP/42 | [7 empty] | 2002 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Maintenance of domestic, commercial and industrial refrigeration systems | Individual | AFR | TUN | REF | 7 | TAS | 7 | N | O | I | CFC | 42 | 42 | 0 | 0 | 1992-06-01 | 1996-07-01 | 1997-06-01 |  | 1997-12-01 | 1998-06-01 | 32836 | 300000 | 332836 | 332836 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. PCR provided in June 1998 |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | TUN/REF/7/TAS/7 | 1997-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Technical assistance for development of HFC-134a-based domestic refrigerators | Individual | AFR | TUN | REF | 8 | TAS | 8 | N | O | I | CFC | 30 | 30 | 0 | 0 | 1992-10-01 | 1995-11-01 | 1995-04-01 |  | 1997-06-01 | 1998-06-01 | 404658.6 | 0 | 404658.6 | 404658.6 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. Final completion report provided in June 1998. This project is part of a line-of-grant approval. The total expenditure was covered by the $1.79 million approval. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | TUN/REF/8/TAS/8 | 1997-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation | Individual | AFR | TUN | SEV | 4 | CPG | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-12-01 |  | 1992-12-01 | 1992-12-01 | 58363 | 105240 | 163603 | 163603 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | TUN/SEV/4/CPG/2 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1991) |  | AFR | TUN | SEV | 4 | PRP | 1 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 64748 | -33533 | 31215 | 31215 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUN/SEV/4/PRP/1 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1992) |  | AFR | TUN | SEV | 6 | PRP | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 50000 | -27623 | 22377 | 22377 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUN/SEV/6/PRP/3 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Implementation of Governmnet actions (institutional strengthening) | Individual | AFR | TUN | SEV | 8 | INS | 9 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-10-01 | 1996-07-01 | 1995-10-01 |  | 1998-06-01 | 1998-06-01 | 285312 | 0 | 285312 | 285312 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Project complete. Final completion report provided in June 1998. This project is part of a line-of-grant approval. The total expenditure was covered by the $1.79 million approval. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | 0 | TUN/SEV/8/INS/9 | 1997-06-01 | [7 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation | Individual | AFR | TUN | SEV | 9 | CPG | 22 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1993-12-01 |  | 1993-12-01 | 1993-12-01 | 8200 | 0 | 8200 | 8200 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | TUN/SEV/9/CPG/22 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1993) |  | AFR | TUN | SEV | 9 | PRP | 10 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 165800 | -3866 | 161934 | 161934 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUN/SEV/9/PRP/10 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Supervision of project implementation (1994) |  | AFR | TUN | SEV | 12 | PRP | 11 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 76296 | -26955 | 49341 | 49341 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUN/SEV/12/PRP/11 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | AFR | TUN | SEV | 16 | PRP | 12 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 35000 | -3418 | 31582 | 31582 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project supervision completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUN/SEV/16/PRP/12 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of ozone depleting substances (renewal of institutional strengthening) | Individual | AFR | TUN | SEV | 25 | INS | 31 | N | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1998-07-01 | 2000-07-01 |  | 2003-12-01 | 2003-12-01 | 186700 | 0 | 186700 | 186700 | 100 | 0 | 0 |  | 24271 | 0 | 24271 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Legislation was drafted, ongoing and completed projects monitored and public awareness campaign was continued. IS renewal requested and approved at the 39th ExCom. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | 0 | TUN/SEV/25/INS/31 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Renewal of institutional strengthening project | Individual | AFR | TUN | SEV | 39 | INS | 43 | N | T | I | CFC | 20.2 | 0 | 0 | 0 | 2003-04-01 | 2003-12-01 | 2005-04-01 | 2006-04-01 |  |  | 242667 | 0 | 242667 | 108479.89 | 44.7 | 134187.11 | 134187.11 | 85000 | 18200.03 | 0 | 8135.99 | 10064.04 | 10064.04 | 2003 | #NAME? | #NAME? | #NAME? | #NAME? | Awareness activities continue and ODS use and import data updated. ANPE is in the process of starting an awareness campaign (including conferences, seminars and production of a film on ODS phase-out. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | 0 | TUN/SEV/39/INS/43 | [7 empty] | 2003 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Preparation of the country programme update | Individual | AFR | TUN | SEV | 42 | CPG | 44 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-04-01 | 2004-12-01 | 2004-12-01 | 2005-06-01 |  |  | 80000 | 0 | 80000 | 5500 | 6.87 | 74500 | 74500 | 74500 | 7200 | 0 | 495 | 6705 | 6705 | 2004 | #NAME? | #NAME? | #NAME? | #NAME? | Contract signed with two consultants, one local and one international. Mission planned in Mar. 05 and a first draft will then be circulated. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | TUN/SEV/42/CPG/44 | [7 empty] | 2004 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of a project in the solvent sector |  | AFR | TUN | SOL | 27 | PRP | 34 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-31 | 2001-01-01 |  | 2000-12-01 | 2000-12-01 | 15000 | 0 | 15000 | 15000 | 100 | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUN/SOL/27/PRP/34 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects in the aerosol sector |  | EUR | TUR | ARS | 30 | PRP | 60 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 8000 | 0 | 8000 | 8000 | 100 | 0 | 0 |  | 1040 | 0 | 1040 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/ARS/30/PRP/60 | [7 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFCs and MCF into HAPs and CO2 for technical aerosols at Beta | Individual | EUR | TUR | ARS | 31 | INV | 66 | N | O | I |  | 31.2 | 31.2 | 0 | 0 | 2000-07-01 | 2001-02-01 | 2002-01-01 |  | 2001-01-01 | 2001-10-01 | 137456 | 0 | 137456 | 137456 | 100 | 0 | 0 |  | 8247 | 0 | 8247 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? | Project fully implemented and 100% non-CFC production started. Awaiting PCR. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/ARS/31/INV/66 | [7 empty] | 2000 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the manufacture of rigid polyurethane foam insulation panels at Assan Demir ve Sac Sanayi A.S., Tuzla-Istanbul | Individual | EUR | TUR | FOA | 15 | INV | 14 | N | O | I | CFC | 180 | 250 | 0 | 0 | 1994-12-01 | 1996-04-01 | 1995-12-01 |  | 1998-04-01 | 1998-12-01 | 925000 | 0 | 925000 | 925000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and fully disbursed in CY98. PCR submitted. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/FOA/15/INV/14 | 1996-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to CFC-free technology in the mnufacture of rigid polyurethane foam isulation panels at Tek-iz Izolasyon ve Yapi Elemanlari Sanayii, Umnariye-Istanbul | Individual | EUR | TUR | FOA | 18 | INV | 17 | N | O | I | CFC | 155 | 177 | 0 | 0 | 1995-11-01 | 1996-11-01 | 1996-11-01 |  | 1998-04-01 | 1998-07-01 | 729650 | 0 | 729650 | 729650 | 100 | 0 | 0 |  | 94854.5 | 0 | 94854.5 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed and fully disbursed in CY98. PCR submitted. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/FOA/18/INV/17 | 1996-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 into carbon dioxide and water for flexible molded foam at Suntas Foam and Mattress Industry and Commerce, Inc. | Individual | EUR | TUR | FOA | 22 | INV | 24 | N | O | I | CFC | 9.05 | 12.06 | 0 | 0 | 1997-05-01 | 1997-11-01 | 1999-06-01 |  | 1996-09-01 | 1998-07-01 | 148613 | -5177 | 143436 | 143436 | 100 | 0 | 0 |  | 19319.69 | -579.54 | 18740.15 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | The project (retroactive) was fully implemented. 100% non-CFC production started. The project is completed and the final report has been submitted to the World Bank. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/FOA/22/INV/24 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 into HCFC-141b at Teba | Individual | EUR | TUR | FOA | 22 | INV | 28 | N | O | I | CFC | 3.51 | 3.51 | 0 | 0 | 1997-05-01 | 1998-07-01 | 1998-06-01 |  | 1998-11-01 | 1999-02-01 | 27468 | -104 | 27364 | 27364 | 100 | 0 | 0 |  | 3570.84 | -13.52 | 3557.32 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | The project had been fully implemented. 100% non-CFC production started. The project is completed and the PCR has been submitted. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/FOA/22/INV/28 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 into LCD for flexible slabstock foam at Safas | Individual | EUR | TUR | FOA | 23 | INV | 29 | N | O | I | CFC | 93.83 | 93.83 | 0 | 0 | 1997-11-01 | 1998-05-01 | 1999-03-01 |  | 1999-09-01 | 1999-12-01 | 530000 | 0 | 530000 | 530000 | 100 | 0 | 0 |  | 68900 | 0 | 68900 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project fully implemented, 100% non-CFC production started. Draft PCR submitted to the Bank. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/FOA/23/INV/29 | [8 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Conversion from CFC-11 into all-water and HCFC-141b for integral skin foam at Polifleks Sentetik Maddeler Sanayii Ve Ticaret A.S. | Individual | EUR | TUR | FOA | 24 | INV | 33 | N | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 |  | 2000-04-01 |  |  | 1999-11-01 | 252558 | -252558 | 0 | 0 | 0 | 0 | 0 |  | 32832.54 | -32832.54 | 0 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Project was canceled. Ownership of the enterprise had changed to 100 % foreign before signing sub-agreement. Funds will be returned at 34th Meeting. |  |  | #NAME? | 0 | 0 | 0 | 0 | TUR/FOA/24/INV/33 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 into all-water for flexible slabstock foam at IDAS | Individual | EUR | TUR | FOA | 24 | INV | 38 | N | O | I | CFC | 37 | 37 | 0 | 0 | 1998-03-01 | 1999-02-01 | 2000-04-01 |  | 1998-11-01 | 1999-07-01 | 230510 | -373 | 230137 | 230137 | 100 | 0 | 0 |  | 29966.3 | -48.49 | 29917.81 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | The project had been fully implemented. 100% non-CFC production started. The project is completed and the PCR has been submitted. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/FOA/24/INV/38 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phaseout of CFC-11 for flexible molded, integral skin and rigid foam at Purplast | Individual | EUR | TUR | FOA | 24 | INV | 39 | N | O | I | CFC | 54 | 54 | 0 | 0 | 1998-03-01 | 1998-12-01 | 2000-04-01 |  | 1999-11-01 | 2000-11-01 | 551101 | 0 | 551101 | 551101 | 100 | 0 | 0 |  | 71643.13 | 0 | 71643.13 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Project fully implemented, 100% non-CFC production started. PCR submitted Jan. 01. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/FOA/24/INV/39 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 into LCD for flexible moulded foam at Elele Doseme Sanayii Ve Ticaret A.S. | Individual | EUR | TUR | FOA | 24 | INV | 40 | N | O | I | CFC | 41.36 | 41.36 | 0 | 0 | 1998-03-01 | 1999-04-01 | 2000-10-01 |  | 1999-04-01 | 1999-07-01 | 311768 | 0 | 311768 | 311768 | 100 | 0 | 0 |  | 40529.84 | 0 | 40529.84 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | 100% non-CFC production started. Draft PCR prepared. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/FOA/24/INV/40 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion to non-CFC foam blowing agents in the production of polyurethane (PU) insulation panels, spray/in situ foam and one component foams at Izopoli Yapi Elemantari Taahhuet Sanayii ve Ticaret Lt | Individual | EUR | TUR | FOA | 24 | INV | 41 | N | O | I | CFC | 274 | 274 | 0 | 0 | 1998-03-01 | 1998-12-01 | 2001-04-01 |  | 2000-05-01 | 2000-05-01 | 1141500 | 0 | 1141500 | 1141500 | 100 | 0 | 0 |  | 148395 | 0 | 148395 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/FOA/24/INV/41 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 into all-water for flexible moulded and HCFC-141b for integral skin foam at EPS Entegre Poliuretan Sunger Ve Koltuk San Tic. Ltd. Sti. | Individual | EUR | TUR | FOA | 24 | INV | 42 | N | O | I | CFC | 11.2 | 11.2 | 0 | 0 | 1998-03-01 | 1999-01-01 | 2000-04-01 |  | 1999-12-01 | 1999-12-01 | 188280 | -270 | 188010 | 188010 | 100 | 0 | 0 |  | 24476.4 | -35.12 | 24441.28 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | 100% non-CFC production started. Waiting for PCR. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/FOA/24/INV/42 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Phase out of CFC-11 for flexible moulded, integral skin and rigid foam at Pimsa Poliuretan Imalat Sanayii Ve Ticaret A.S. | Individual | EUR | TUR | FOA | 24 | INV | 43 | N | O | I | CFC | 57.9 | 57.9 | 0 | 0 | 1998-03-01 | 1998-07-01 | 2000-04-01 |  | 1999-07-01 | 2000-11-01 | 551501 | 0 | 551501 | 551501 | 100 | 0 | 0 |  | 71695.13 | 0 | 71695.13 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Installation completed. 100% non-CFC production started. PCR submitted. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/FOA/24/INV/43 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 into methylene chloride and dop for flexible molded hot cured foam at Teknik Malzeme | Individual | EUR | TUR | FOA | 24 | INV | 44 | N | O | I | CFC | 17.2 | 17.2 | 0 | 0 | 1998-03-01 | 1998-09-01 | 1999-10-01 |  | 1998-06-01 | 1999-08-01 | 122443 | -22079 | 100364 | 100364 | 100 | 0 | 0 |  | 15917.59 | -2870.27 | 13047.32 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | The project had been fully implemented. 100% non-CFC production started. The project is completed and the final report has been submitted to the World Bank. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/FOA/24/INV/44 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 to isobutane in the manufacture of polyethylene foam tubing at Thermaflex-Form | Individual | EUR | TUR | FOA | 26 | INV | 51 | N | O | R | CFC | 37.5 | 37.5 | 0 | 0 | 1998-11-01 | 1999-06-01 | 2000-12-01 |  | 1996-08-01 | 1999-06-01 | 124219 | 0 | 124219 | 124219 | 100 | 0 | 0 |  | 16148.47 | 0 | 16148.47 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Company started non-CFC production in mid-1996. Subgrant agreement signed in Feb/99. PCR submitted Jan. 01. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/FOA/26/INV/51 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 into low index additive (LIA) technology for flexible slabstock foam at Elta | Individual | EUR | TUR | FOA | 28 | INV | 55 | N | O | I | CFC | 21.3 | 21.3 | 0 | 0 | 1999-07-01 | 2001-02-01 | 2001-08-01 |  | 2001-06-01 | 2001-10-01 | 130597 | -20000 | 110597 | 110597 | 100 | 0 | 0 |  | 16977.61 | -2600 | 14377.61 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Project fully implemented. 100% non-CFC production started. Awaiting PCR. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/FOA/28/INV/55 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of project proposal in the foam general sector |  | EUR | TUR | FOA | 30 | PRP | 61 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 15000 | 0 | 15000 | 15000 | 100 | 0 | 0 |  | 1950 | 0 | 1950 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/FOA/30/PRP/61 | [7 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of projects in the rigid polyurethane foam subsector |  | EUR | TUR | FOA | 30 | PRP | 63 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2000-12-01 |  | 2000-12-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100 | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/FOA/30/PRP/63 | [7 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 into all-water technology for flexible molded and integral skin foams at Urosan | Individual | EUR | TUR | FOA | 32 | INV | 70 | N | O | I | CFC | 39.5 | 39.5 | 0 | 0 | 2000-12-01 | 2002-12-01 | 2004-01-01 |  | 2003-03-01 | 2004-12-01 | 291641 | -815.56 | 290825.44 | 290825.44 | 100 | 0 | 0 |  | 37913.33 | -106.02 | 37807.31 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/FOA/32/INV/70 | [5 empty] | 2004-01-01 |  | 2000 | INV | 0 | 0 | 0 | 0
COM | IBRD | Conversion from CFC-11 into all-water technology for flexible molded and HCFC-141b for integral skin foams at 11 enterprises (Erdogan Rurmenler; KarakayaCelik; Una Polyuretan; Iksan Ltd; Ak-Kom; Karsan; Goldsit; Buoflex; Gervener; Yaris Kabin; Hisarlar) | Individual | EUR | TUR | FOA | 32 | INV | 71 | N | O | I | CFC | 48.5 | 48.5 | 0 | 0 | 2000-12-01 | 2002-12-01 | 2004-01-01 |  | 2003-06-01 |  | 398378 | 0 | 398378 | 120932.48 | 30.35 | 277445.52 | 277445.52 |  | 51789.14 | 0 | 15721.22 | 36067.92 | 36067.92 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? | Investment part of project completed and non-ODS production at all 5 participating companies is underway. As per the given guidance to enterprises IOC disb. also completed in 2004. Financial completion expected Jan. 05. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/FOA/32/INV/71 | [5 empty] | 2004-01-01 |  | 2000 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation for methy bromide |  | EUR | TUR | FUM | 25 | PRP | 48 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-03-31 | 1999-08-01 |  | 1999-08-01 | 1999-08-01 | 50000 | 0 | 50000 | 50000 | 100 | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Completed |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/FUM/25/PRP/48 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Introduction of alternatives to methyl bromide in protected strawberry, pepper and eggplant in East Mediterranean region and in strawberry in Aydm province of Turkey | Individual | EUR | TUR | FUM | 29 | INV | 56 | N | O | I | MBR | 50 | 50 | 0 | 0 | 1999-11-01 | 2000-10-01 | 2002-12-01 |  | 2003-07-01 | 2003-08-01 | 366440 | 0 | 366440 | 366440 | 100 | 0 | 0 |  | 47637.2 | 0 | 47637.2 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Project fully implemented. Alternatives to MeBr use in strawberry, pepper and eggplant production determined and results published. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/FUM/29/INV/56 | [8 empty] | INV | 0 | 0 | 0 | 0
ONG | IBRD | Phase-out methyl bromide in the dried fig sector | Individual | EUR | TUR | FUM | 31 | INV | 69 | N | O | I | MBR | 30 | 0 | 0 | 0 | 2000-07-01 | 2001-06-02 | 2002-10-01 | 2005-06-01 |  |  | 479040 | 0 | 479040 | 418175.33 | 87.29 | 60864.67 | 60864.67 | 60864.67 | 62275.2 | 0 | 54362.79 | 7912.41 | 7912.41 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed except the installation of CO2 tanks. Company has decided to install the tanks at the current plant location in Izmir. It will move the tanks when new plant is constructed. Project manager and TARIS managers have declared that they will finish tank installation by May 05. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/FUM/31/INV/69 | [7 empty] | 2000 | INV | 0 | 0 | 0 | 0
CLO | IBRD | Project preparation in the methyl bromide sector (storage of hazelnut) |  | EUR | TUR | FUM | 36 | PRP | 77 | A | O | I |  | 0 | 0 | 0 | 0 | 2002-03-01 |  | 2003-04-01 |  |  | 2004-12-01 | 40000 | -40000 | 0 | 0 | 0 | 0 | 0 |  | 5200 | -5200 | 0 | 0 | 0 | 2002 | #NAME? | #NAME? | #NAME? | #NAME? | Due to reorganization of MARA and personnel changes following a newly elected government funding is returned while Gov. weighs its options on a way forward. |  |  | #NAME? | 0 | 0 | 0 | 0 | TUR/FUM/36/PRP/77 | [7 empty] | 2002 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of projects for the halon recycling |  | EUR | TUR | HAL | 30 | PRP | 62 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2001-12-01 |  | 2001-12-01 | 2001-12-01 | 15000 | -5000 | 10000 | 10000 | 100 | 0 | 0 |  | 1950 | -650 | 1300 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/HAL/30/PRP/62 | [7 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Halon management programme, halon recovery, recycling and banking | Halon Banking | EUR | TUR | HAL | 38 | TAS | 80 | N | O | I | HAL | 118 | 0 | 0 | 0 | 2002-11-01 |  | 2005-11-01 | 2007-01-01 |  |  | 439250 | 0 | 439250 | 0 | 0 | 439250 | 439250 | 146666.67 | 57102.5 | 0 | 0 | 57102.5 | 57102.5 | 2002 | #NAME? | #NAME? | #NAME? | #NAME? | Negotiations continued into Q2 of 2004. In 2004, MoEF & TTGV met with several groups who in the end were not interested in implementation. In Dec. 04, Environmental Engineering Department, Environmental Research Center of Middle East Technical University (METU) confirmed its interest and will get necessary approval from METU & finalize procedures for Halon Bank site & operations by Feb. 05. After finalizing arrangements with the WB, project is planned to start in Mar. 05. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | TUR/HAL/38/TAS/80 | [7 empty] | 2001 | INV | 0 | 0 | 0 | 0
COM | IBRD | Total phase out of CFCs plan: 2001 and 2002 annual programmes | Multiyear | EUR | TUR | PHA | 35 | INV | 75 | N | O | I | CFC | 97 | 97 | 0 | 0 | 2001-12-01 | 2002-12-01 | 2002-12-01 |  | 2002-12-01 |  | 3500000 | 0 | 3500000 | 3455782.32 | 98.73 | 44217.68 | 44217.68 | 44217.68 | 295000 | 0 | 291273.08 | 3726.92 | 3726.92 | 2001 | #NAME? | #NAME? | #NAME? | #NAME? | Conversion of 61 SMEs has been completed. First phase of training part is completed. Second phase of training to begin. R&R part is under implementation. For chillers, chiller conversion of 2 companies has been completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/PHA/35/INV/75 | [7 empty] | 2001 | INV | 977 | 699 | 0 | 0 | Yes | Yes | Yes
COM | IBRD | Total phase out of CFCs plan: 2003 annual programme | Multiyear | EUR | TUR | PHA | 38 | INV | 79 | N | O | I | CFC | 375 | 375 | 0 | 0 | 2002-11-01 | 2003-12-01 | 2003-12-01 |  | 2003-12-01 |  | 2500000 | 0 | 2500000 | 1793539.76 | 71.74 | 706460.24 | 706460.24 | 706460.24 | 175000 | 0 | 125547.78 | 49452.22 | 49452.22 | 2002 | #NAME? | #NAME? | #NAME? | #NAME? | Conversion of 13 SMEs completed. Training part of RSP and customs training planned and implementation started in 2003. Installation of R&R part started in 2003. Chiller conversion of 3 companies has been completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/PHA/38/INV/79 | [7 empty] | 2002 | INV | 534 | 457 | 0 | 0 | Yes | Yes | Yes
COM | IBRD | Total phase-out of CFCs plan: 2004 annual programme | Multiyear | EUR | TUR | PHA | 41 | INV | 81 | N | O | I | CFC | 218 | 218 | 0 | 0 | 2003-12-01 | 2004-12-01 | 2004-12-01 |  | 2004-12-01 |  | 1000000 | 0 | 1000000 | 636757.85 | 63.67 | 363242.15 | 363242.15 | 363242.15 | 150000 | 0 | 95513.68 | 54486.32 | 54486.32 | 2003 | #NAME? | #NAME? | #NAME? | #NAME? | Country met obligations under AP and it is completed. For activities under this AP, 3 SME contracts signed in 2004. Second phase of training is planned to continue along with implementation of R&R and customs training. 4 companies contracted for chiller conversion in 04. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/PHA/41/INV/81 | [7 empty] | 2003 | INV | 316 | 258 | 0 | 0 | Yes | Yes | Yes
ONG | IBRD | Total phase-out of CFCs plan: 2005 annual programme | Multiyear | EUR | TUR | PHA | 44 | INV | 85 | N | O | I | CFC | 150 | 0 | 0 | 0 | 2004-12-01 |  | 2005-12-01 | 2005-12-01 |  |  | 750000 | 0 | 750000 | 0 | 0 | 750000 | 750000 | 501764.82 | 45000 | 0 | 0 | 45000 | 45000 | 2004 | #NAME? | #NAME? | #NAME? | #NAME? | Tranche newly approved and implementation underway. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/PHA/44/INV/85 | [7 empty] | 2004 | INV | 150 | 0 | 0 | 0 |  | No | No
FIN | IBRD | Recovery and recycling of CFC-12 at a refrigeration production plant | Individual | EUR | TUR | REF | 7 | TAS | 3 | N | O | I | CFC | 4 | 4 | 0 | 0 | 1992-06-01 | 1994-05-01 | 1993-06-01 |  | 1994-12-01 | 1997-12-01 | 65000 | 0 | 65000 | 65000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | The project had been fully implemented, 100% non-CFC production started. The project is completed and the final report has been submitted to the World Bank. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | TUR/REF/7/TAS/3 | 1994-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Recovery and reclamation of CFC-12 from household refrigerators | Individual | EUR | TUR | REF | 7 | TAS | 4 | N | O | I | CFC | 1 | 0 | 0 | 0 | 1992-06-01 | 1996-10-01 | 1994-06-01 |  | 1996-12-01 | 1997-03-01 | 400000 | -82919.94 | 317080.06 | 317080.06 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | The project had been fully implemented, 100% non-CFC production started. The project is completed and the final report has been submitted to the World Bank. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | TUR/REF/7/TAS/4 | 1996-06-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Introduction of non-ODS technologies in the production of domestic refrigerators at Arcelik A.S. | Individual | EUR | TUR | REF | 8 | INV | 7 | N | O | I | CFC | 750 | 750 | 0 | 0 | 1992-10-01 | 1994-05-01 | 1995-10-01 |  | 1996-06-01 | 1997-03-01 | 4900000 | -10484 | 4889516 | 4889516.31 | 100 | -0.62 | -0.62 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | The project had been fully implemented, 100% non-CFC production started. The project is completed and the final report has been submitted to the World Bank. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/REF/8/INV/7 | 1996-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Engineering assistance for the elimination of ODS used in the production of freezers and coolers at Klimasan Klima Sanayi ve Ticaret A.S. | Individual | EUR | TUR | REF | 15 | INV | 12 | N | O | I |  | 36.9 | 36.9 | 0 | 0 | 1994-12-01 | 1996-04-01 | 1995-12-01 |  | 1997-01-01 | 1996-12-01 | 690903 | 110665 | 801568 | 801568 | 100 | 0 | 0 |  | 0 | 16669.9 | 16669.9 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | The project had been fully implemented, 100% non-CFC production started. The project is completed and the final report has been submitted to the world Bank. Additional funds approved for IOC fully disbursed Mar. 01 ($128,230). |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/REF/15/INV/12 | 1996-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Engineering assistance for the elimination of ODS used in the production of household refrigerators at PEG Profilo Elektrikli Gerecler Sanayii A.S. | Individual | EUR | TUR | REF | 15 | INV | 13 | N | O | I | CFC | 290 | 290 | 0 | 0 | 1994-12-01 | 1996-02-01 | 1995-12-01 |  | 1996-04-01 | 1996-03-01 | 1578000 | 257747 | 1835747 | 1835747.02 | 100 | -0.02 | -0.02 |  | 0 | 34340.02 | 34340 | 0.02 | 0.02 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | The company has achieved 100% non-ODS production. The project is completed and the final report has been submitted to the World Bank. Additional funds approved for IOC fully disbursed Mar. 01 ($264,154). |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/REF/15/INV/13 | 1996-04-01 | [7 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of the use of CFCs in the manufacture of domestic refrigerators at Pekel Teknik Sanyi ve Ticaret A.S. | Individual | EUR | TUR | REF | 18 | INV | 19 | N | O | R |  | 0 | 0 | 0 | 0 | 1995-11-01 |  | 1996-05-01 |  |  | 1996-10-01 | 500664 | -500664 | 0 | 0 | 0 | 0 | 0 |  | 65086.32 | -65086.32 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project was canceled. Ownership of the enterprise had changed to 100 % foreign before signing sub-agreement. |  |  | #NAME? | 0 | 0 | 0 | 0 | TUR/REF/18/INV/19 | 1996-05-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Engineering assistance for the elimination of ODS used in the production of freezers, coolers, ice makers, and ice cream machines at UGUR Makinalari Sanayi ve Ticaret, A.S. | Individual | EUR | TUR | REF | 19 | INV | 21 | N | O | I | CFC | 64.3 | 64.3 | 0 | 0 | 1996-05-01 | 1997-04-01 | 1997-11-01 |  | 1999-03-01 | 1999-07-01 | 1166455 | 0 | 1166455 | 1166455 | 100 | 0 | 0 |  | 151639.15 | 0 | 151639.15 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | 100% non-CFC production started. Waiting for PCR. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/REF/19/INV/21 | 1998-09-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11, CFC-12 into cyclopentane and HFC-134a for commercial refrigeration at S.F.A. Sogutma Urunleri Sanayi Ve Tekstil Pazariama Ltd. Sti. | Individual | EUR | TUR | REF | 22 | INV | 25 | N | O | I |  | 25.9 | 25.9 | 0 | 0 | 1997-05-01 | 1998-04-01 | 1999-02-01 |  | 1999-03-01 | 1999-12-01 | 389832 | 0 | 389832 | 389832 | 100 | 0 | 0 |  | 50678.16 | 0 | 50678.16 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | 100% non-CFC production started. Waiting for PCR. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/REF/22/INV/25 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 and CFC-12 into HCFC-141b and HFC-134a at Gumaksan | Individual | EUR | TUR | REF | 22 | INV | 26 | N | O | I | CFC | 2.3 | 2.3 | 0 | 0 | 1997-05-01 | 1998-04-01 | 1998-06-01 |  | 1998-11-01 | 1999-01-01 | 35195 | 0 | 35195 | 35195 | 100 | 0 | 0 |  | 4575.35 | 0 | 4575.35 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project fully implemented, 100% non-CFC production started. Draft PCR submitted to the Bank. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/REF/22/INV/26 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion from CFC-11 and CFC-12 into HCFC-141b and HFC-134a at Kulahcioglu | Individual | EUR | TUR | REF | 22 | INV | 27 | N | O | I | CFC | 4 | 4 | 0 | 0 | 1997-05-01 | 1998-06-01 | 1998-06-01 |  | 1999-03-01 | 1999-06-01 | 60840 | 0 | 60840 | 60840 | 100 | 0 | 0 |  | 7909.2 | 0 | 7909.2 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | The project is completed 100% non-CFC production started. Waiting for PCR. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/REF/22/INV/27 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation for commercial refrigeration terminal umbrella project |  | EUR | TUR | REF | 25 | PRP | 45 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-07-01 | 1999-03-31 | 1999-08-01 |  | 1999-08-01 | 1999-08-01 | 120000 | 0 | 120000 | 120000 | 100 | 0 | 0 |  | 15600 | 0 | 15600 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Completed |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/REF/25/PRP/45 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation | Individual | EUR | TUR | SEV | 6 | CPG | 1 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1991-06-30 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 13515 | 55074 | 68589 | 68589 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | TUR/SEV/6/CPG/1 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1992) |  | EUR | TUR | SEV | 6 | PRP | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 217687 | -67459 | 150228 | 150228 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/SEV/6/PRP/2 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Demonstration activities in several sectors |  | EUR | TUR | SEV | 7 | PRP | 5 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-06-01 | 1994-10-01 | 1993-06-01 |  | 1999-12-01 | 2000-03-01 | 500000 | -18877 | 481123 | 481123 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | 3 demo projects in solvent sector are implemented. 8 demo projects in refrigeration sector completed as of December 31, 1998. 6 demo projects in foam sector is completed as of March 31, 1999. Individual PCRs submitted separately per project code. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/SEV/7/PRP/5 | 1997-07-01 | 1999-03-01 | [6 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Institutional strengthening | Individual | EUR | TUR | SEV | 8 | INS | 6 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-10-01 | 1995-06-01 | 1997-06-01 |  | 2000-04-01 | 2000-04-01 | 300000 | -33157 | 266843 | 266843 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | IS project extended to accommodate additional work program of ozone unit. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | 0 | TUR/SEV/8/INS/6 | 1997-06-01 | 1999-12-01 | [6 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1993) |  | EUR | TUR | SEV | 9 | PRP | 8 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 140400 | 42164 | 182564 | 182564 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/SEV/9/PRP/8 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Supervision of project implementation (1994) |  | EUR | TUR | SEV | 12 | PRP | 9 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 30000 | -8823 | 21177 | 21177 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Funds utilized for supervision on project implementation. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/SEV/12/PRP/9 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1994) |  | EUR | TUR | SEV | 13 | PRP | 10 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-07-01 | 1994-09-30 | 1995-07-01 |  | 1994-12-01 | 1994-12-01 | 100000 | -79142 | 20858 | 20858 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Project preparation completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/SEV/13/PRP/10 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects ODS I (1995) |  | EUR | TUR | SEV | 16 | PRP | 15 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 43966 | 0 | 43966 | 43966 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project preparation completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/SEV/16/PRP/15 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects ODS II (1995) |  | EUR | TUR | SEV | 16 | PRP | 16 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-31 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 80000 | -7373 | 72627 | 72627 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project preparation completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/SEV/16/PRP/16 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | EUR | TUR | SEV | 18 | PRP | 20 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-31 | 1996-12-01 | 100000 | 0 | 100000 | 100000 | 100 | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project preparation completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/SEV/18/PRP/20 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | EUR | TUR | SEV | 21 | PRP | 23 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 96000 | 0 | 96000 | 96000 | 100 | 0 | 0 |  | 12480 | 0 | 12480 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project preparation completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/SEV/21/PRP/23 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation in the aerosol, foam and recycling sectors |  | EUR | TUR | SEV | 24 | PRP | 34 | A | O | I |  | 0 | 0 | 0 | 0 | 1998-03-01 | 1998-06-30 | 1998-12-01 |  | 1999-06-01 | 1999-06-01 | 100000 | 0 | 100000 | 100000 | 100 | 0 | 0 |  | 13000 | 0 | 13000 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Completed |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/SEV/24/PRP/34 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects in the foam, commercial refrigeration, refrigeration/ recycling, halon, methyl bromide and a demonstration project for a national phase-out. |  | EUR | TUR | SEV | 27 | PRP | 54 | A | O | I |  | 0 | 0 | 0 | 0 | 1999-03-01 | 1999-03-31 | 2001-01-01 |  | 1999-12-31 | 1999-12-01 | 8000 | 0 | 8000 | 8000 | 100 | 0 | 0 |  | 1040 | 0 | 1040 | 0 | 0 | 1999 | #NAME? | #NAME? | #NAME? | #NAME? | Completed |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/SEV/27/PRP/54 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Renewal of institutional strengthening |  | EUR | TUR | SEV | 32 | INS | 73 | N | O | I |  | 0 | 0 | 0 | 0 | 2000-12-01 | 2002-12-01 | 2003-01-01 | 2005-12-01 |  |  | 200000 | 0 | 200000 | 130157.73 | 65.07 | 69842.27 | 69842.27 | 69842.27 | 26000 | 0 | 16920.5 | 9079.5 | 9079.5 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? | Due to additional management changes and bureaucratic procedures, project continues to run slowly. MARA is revising its business plan to complete the project in 2005. Nonetheless, in 2004, MARA conducted meetings to: organize a training program on MeBr alternatives for extension staff stationed in 48 provinces; for production of awareness / training materials on MeBr alternatives, the MeBr strategy and Turkeys MP compliance responsibilities; and on training programs for extension staff from 27 provinces. MARA also worked on improving country-wide data collection and control activities. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | 0 | TUR/SEV/32/INS/73 | [7 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Extension of institutional strengthening project (phase III) | Individual | EUR | TUR | SEV | 44 | INS | 86 | N | T | I | CFC | 21.5 | 0 | 0 | 0 | 2004-12-01 |  | 2006-12-01 | 2007-06-01 |  |  | 260000 | 0 | 260000 | 0 | 0 | 260000 | 260000 | 90000 | 19500 | 0 | 0 | 19500 | 19500 | 2004 | #NAME? | #NAME? | #NAME? | #NAME? | IS renewal newly approved. Project covers MoEF and MARA components. Implementation will commence in 2005. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | 0 | TUR/SEV/44/INS/86 | [7 empty] | 2004 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Umbrella project for 17 enterprises for phaseout of ODS used as solvents | Individual | EUR | TUR | SOL | 25 | INV | 49 | N | O | I |  | 11.97 | 11.97 | 0 | 0 | 1998-07-01 | 2000-03-01 | 1999-08-01 |  | 2000-10-01 | 2000-10-01 | 415312 | -20098 | 395214 | 395214 | 100 | 0 | 0 |  | 53990.56 | -2612.77 | 51377.79 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Project implemented and 100% non-CFC production started. Awaiting PCR. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/SOL/25/INV/49 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of an electronic defluxing process from ODS-solvent cleaning to hydrocarbon/surfactant (semi-aqueous) cleaning at Aselsan AS | Individual | EUR | TUR | SOL | 25 | INV | 50 | N | O | R | CFC | 3.9 | 3.9 | 0 | 0 | 1998-07-01 | 1999-02-01 | 1999-08-01 |  | 1995-10-01 | 1999-02-01 | 58517 | 0 | 58517 | 58517 | 100 | 0 | 0 |  | 7607.21 | 0 | 7607.21 | 0 | 0 | 1998 | #NAME? | #NAME? | #NAME? | #NAME? | Company has achieved 100% non-ODS production. Project is completed and draft report submitted to the Bank. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/SOL/25/INV/50 | [8 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of projects in the solvent (TCA) sector |  | EUR | TUR | SOL | 30 | PRP | 64 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2001-12-01 |  | 2000-12-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100 | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/SOL/30/PRP/64 | [7 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Umbrella project for the phase-out of MCF used as solvent by water cleaning at 21 enterprises | Individual | EUR | TUR | SOL | 35 | INV | 76 | N | O | I | TCA | 15.4 | 9.4 | 0 | 0 | 2001-12-01 | 2003-11-01 | 2004-01-01 | 2005-03-01 |  |  | 518693 | 0 | 518693 | 261082.48 | 50.33 | 257610.52 | 257610.52 | 173580 | 67056.23 | 0 | 33752.54 | 33303.69 | 33303.69 | 2001 | #NAME? | #NAME? | #NAME? | #NAME? | 16 enterprises are taking part in the project. 15 have completed their conversion-one enterprise plans to finalize the subproject by Feb. 05. Subproject was delayed because of adaptation of the cleaning machine system to existing production system required a software program which is hard to obtain. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | TUR/SOL/35/INV/76 | [7 empty] | 2001 | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of the use of CFC-11 as blowing agent in rigid polyurethane foams used as insulation in thermal tanks at Tem, S.A. | Individual | LAC | URU | FOA | 15 | INV | 10 | N | O | I |  | 0 | 0 | 0 | 0 | 1994-12-01 |  | 1995-08-01 |  |  | 1996-04-01 | 220300 | -220300 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Tem S.A. has closed down. The project was cancelled by the government on 4/29/96. Funds returned to Multilateral Fund 20th Meeting. |  |  | #NAME? | 0 | 0 | 0 | 0 | URU/FOA/15/INV/10 | 1997-01-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of the use of CFC-11 as a blowing agent in rigid polyurethane foam used as insulation in thermal tanks at Etchepare-Gil S.A. | Individual | LAC | URU | FOA | 15 | INV | 14 | N | O | I | CFC | 3 | 3 | 0 | 0 | 1994-12-01 | 1998-08-01 | 1995-08-01 |  | 1999-09-01 | 2000-01-01 | 235050 | 0 | 235050 | 235050 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | The project was technically completed by September 99 and financially completed in January 00. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | URU/FOA/15/INV/14 | 1997-09-01 | 1999-11-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Terminal programme for the elimination of CFC-11 in the manufacture of polyurethane foam through the use of HCFC-141b technology in the foam sector in Uruguay by means of technical assistance and conversion to different companies | Individual | LAC | URU | FOA | 31 | INV | 34 | N | O | I | CFC | 4.35 | 4.35 | 0 | 0 | 2000-07-01 | 2001-11-01 | 2002-01-01 |  | 2003-05-01 | 2003-05-01 | 91300 | -80 | 91220 | 91220 | 100 | 0 | 0 |  | 11869 | -10 | 11858.6 | 0.4 | 0.4 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | URU/FOA/31/INV/34 | [7 empty] | 2000 | INV | 0 | 0 | 0 | 0
FIN | IBRD | Elimination of the use of CFC-11 as blowing agent in rigid polyurethane foams used as insulation in cold storage and substitution of CFC-12 used as refrigerant with HFC-134a at Colder S.R.L. | Individual | LAC | URU | REF | 15 | INV | 11 | N | O | I | CFC | 10.8 | 10.8 | 0 | 0 | 1994-12-01 | 1997-06-01 | 1995-08-01 |  | 1997-09-01 | 1998-08-01 | 325070 | 0 | 325070 | 325070 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Company signed Subgrant Agreement in November '96. Implementation began in Fall /96. Product testing started in Fall /97. The project was completed in August 98. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | URU/REF/15/INV/11 | 1997-12-01 | 1999-04-01 | [6 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Elimination of the use of CFC-11 as a blowing agent in rigid polyurethane foams used as insulation for refrigerators and substitution of CFC-12 used as refrigerant at Indurnor S.A. | Individual | LAC | URU | REF | 15 | INV | 12 | N | O | I |  | 0 | 0 | 0 | 0 | 1994-12-01 |  | 1995-12-01 |  |  | 1999-07-01 | 448140 | -448140 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Indunor S.A. has closed down. The funds were returned to the Multilateral Fund on July 99 at the 28th Ex Com meeting |  |  | #NAME? | 0 | 0 | 0 | 0 | URU/REF/15/INV/12 | 1998-06-01 | 2000-01-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Recovery and recycling of CFC-12 in maintenance workshops for industrial refrigeration equipment | Individual | LAC | URU | REF | 18 | TAS | 19 | N | O | I | CFC | 4 | 0 | 0 | 0 | 1995-11-01 | 1998-07-01 | 1996-05-01 |  | 1999-10-01 | 2000-01-01 | 87647 | 0 | 87647 | 87647 | 100 | 0 | 0 |  | 11394.11 | 0 | 11394.11 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Implementation began in Fall'96. The funds were transferred to local UNDP office in September'97. During 1998 the equipment was purchased and the consultantwas paid. The equipment were distributed on March 99 . The project was completed by October 99. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | URU/REF/18/TAS/19 | 1997-06-01 | 1999-12-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Completing the elimination of CFC use in domestic refrigeration manufacturing by adoption of HCFC-141b as blowing agent and HFC-134a as refrigerant at Nevol S.A. | Individual | LAC | URU | REF | 19 | INV | 21 | N | O | I | CFC | 10.5 | 10.5 | 0 | 0 | 1996-05-01 | 1997-08-01 | 1997-07-01 |  | 1998-10-01 | 1999-07-01 | 141512 | 0 | 141512 | 141512 | 100 | 0 | 0 |  | 18396.56 | 0 | 18396.56 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | The project was completed in July 99 |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | URU/REF/19/INV/21 | 1997-07-01 | 1999-07-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of an investment project in the domestic refrigeration sector |  | LAC | URU | REF | 30 | PRP | 32 | A | O | I |  | 0 | 0 | 0 | 0 | 2000-03-01 | 2000-03-31 | 2001-12-01 |  | 2000-12-01 | 2000-12-01 | 10000 | 0 | 10000 | 10000 | 100 | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | 2000 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | URU/REF/30/PRP/32 | [7 empty] | 2000 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1994) |  | LAC | URU | SEV | 12 | PRP | 5 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 100000 | -41688 | 58312 | 58312 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | URU/SEV/12/PRP/5 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects (1995) |  | LAC | URU | SEV | 16 | PRP | 15 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 81278 | 0 | 81278 | 81278 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Preparation is complete. Project is now under supervision. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | URU/SEV/16/PRP/15 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | LAC | URU | SEV | 18 | PRP | 20 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-31 | 1996-12-01 | 30000 | 0 | 30000 | 30000 | 100 | 0 | 0 |  | 3900 | 0 | 3900 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project preparation completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | URU/SEV/18/PRP/20 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | LAC | URU | SEV | 21 | PRP | 23 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 20000 | 0 | 20000 | 20000 | 100 | 0 | 0 |  | 2600 | 0 | 2600 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project preparation completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | URU/SEV/21/PRP/23 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Market survey to develop a country-wide scheme to phase out remaining ODS | Individual | LAC | URU | SEV | 22 | TAS | 24 | N | O | I |  | 0 | 0 | 0 | 0 | 1997-05-01 | 1998-06-01 | 1998-12-01 |  | 1998-07-01 | 1998-07-01 | 23000 | 0 | 23000 | 23000 | 100 | 0 | 0 |  | 2990 | 0 | 2990 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Time required for collecting and verifying consumption data was longer than originally anticipated. All disbursements have been made (US$ 23,000). Project completed. |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | URU/SEV/22/TAS/24 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of a CFC-12 polystyrene foam production facility to use hydrocarbons as blowing agent at Plásticos Molanca | Individual | LAC | VEN | FOA | 7 | INV | 5 | N | O | I | CFC | 259 | 259 | 0 | 0 | 1992-06-01 | 1993-06-01 | 1993-06-01 |  | 1995-12-01 | 1996-04-01 | 1300000 | -38322 | 1261678 | 1261678.18 | 100 | -0.36 | -0.36 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | ICR issued in May/96. The final project cost amounted to about US$2 million. The overrun was absorbed by enterprise. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | VEN/FOA/7/INV/5 | 1995-03-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation for the CFC production phase out project |  | LAC | VEN | PRO | 41 | PRP | 97 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-12-01 | 2003-12-01 | 2004-12-01 |  | 2004-04-01 | 2004-04-01 | 40000 | 0 | 40000 | 40000 | 100 | 0 | 0 |  | 3000 | 0 | 3000 | 0 | 0 | 2003 | #NAME? | #NAME? | #NAME? | #NAME? | Project was prepared and subsequently approved at the 44th ExCom in Dec. 04. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | VEN/PRO/41/PRP/97 | [7 empty] | 2003 | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Phased reduction and closure of the entire CFC production: 2004 annual programme | Multiyear | LAC | VEN | PRO | 44 | INV | 101 | N | O | I | CFC | 0 | 0 | 1487 | 0 | 2004-12-01 |  | 2005-12-01 | 2005-12-01 |  |  | 3300000 | 0 | 3300000 | 0 | 0 | 3300000 | 3300000 | 3300000 | 247500 | 0 | 0 | 247500 | 247500 | 2004 | #NAME? | #NAME? | #NAME? | #NAME? | TOR for the verification audit of 2004 production are ready and the audit will take place in Feb. 05. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | VEN/PRO/44/INV/101 | [7 empty] | 2004 | INV | 0 | 0 | 4400 | 3564 | Yes | No | No
CLO | IBRD | Replacement of CFC by HFC-134a as a refrigerant in central air conditioning units at Instituto Venezolano de los Seguros Sociales | Individual | LAC | VEN | REF | 8 | INV | 8 | N | O | I |  | 0 | 0 | 0 | 0 | 1992-10-01 |  | 1994-04-01 |  |  | 1995-07-01 | 851000 | -851000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Project Cancelled. |  |  | #NAME? | 0 | 0 | 0 | 0 | VEN/REF/8/INV/8 | 1994-04-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of CFC by HFC-134a as a refrigerant in central air conditioning units at Clínica Atias, Hospitalización y Servicios | Individual | LAC | VEN | REF | 8 | INV | 9 | N | O | I | CFC | 4 | 4 | 0 | 0 | 1992-10-01 | 1996-12-01 | 1994-04-01 |  | 1997-01-01 | 1997-02-01 | 115000 | 0 | 115000 | 115000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Project Completed |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | VEN/REF/8/INV/9 | 1997-01-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Replacement of CFC by HFC-134a as a refrigerant in central air conditioning units at Instituto de Prevencion Social del Médico | Individual | LAC | VEN | REF | 8 | INV | 10 | N | O | D | CFC | 2 | 2 | 0 | 0 | 1992-10-01 | 1995-12-01 | 1994-04-01 |  | 1995-09-01 | 1997-02-01 | 69000 | 0 | 69000 | 69000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | VEN/REF/8/INV/10 | 1995-09-01 | [7 empty] | INV | 0 | 0 | 0 | 0
CLO | IBRD | Replacement of CFC by HFC-134a as a refrigerant in central air conditioning units at Congreso de la Republica | Individual | LAC | VEN | REF | 8 | INV | 11 | N | O | D |  | 0 | 0 | 0 | 0 | 1992-10-01 |  | 1994-04-01 |  |  | 1998-05-01 | 65000 | -65000 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? | Retroactive project physically completed, but enterprise chose not to utilize MLF funds. Funds returned to MLF. |  |  | #NAME? | 0 | 0 | 0 | 0 | VEN/REF/8/INV/11 | 1995-12-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | MAC factory conversion for fabrication of HFC-134a heat exchangers at Fabrica de Aparatos de Aire Acondicionado, S.A. (Faaca) | Individual | LAC | VEN | REF | 11 | INV | 19 | N | O | I | CFC | 0 | 0 | 0 | 0 | 1993-11-01 | 1995-06-01 | 1995-11-01 |  | 1998-02-01 | 1998-02-01 | 3480000 | -380000 | 3100000 | 3100000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Project Completed |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | VEN/REF/11/INV/19 | 1997-09-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | MAC factory conversion for fabrication of HFC-134a compressors and heat exchangers at Aire Acondicionado Integral, S.A. (Aaisa) | Individual | LAC | VEN | REF | 11 | INV | 20 | N | O | I | CFC | 11 | 11 | 0 | 0 | 1993-11-01 | 1995-12-01 | 1996-09-01 |  | 1998-06-01 | 1998-10-01 | 620000 | 3800000 | 4420000 | 4420000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? | Complete. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | VEN/REF/11/INV/20 | 1997-09-01 | [7 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation | Individual | LAC | VEN | SEV | 4 | CPG | 59 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 30313 | -27612 | 2701 | 2701 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | VEN/SEV/4/CPG/59 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1991) |  | LAC | VEN | SEV | 4 | PRP | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1992-06-01 |  | 1991-12-01 | 1991-12-01 | 70419 | -57546 | 12873 | 12873 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | VEN/SEV/4/PRP/2 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation | Individual | LAC | VEN | SEV | 6 | CPG | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1994-03-31 | 1994-12-01 |  | 1994-12-01 | 1994-12-01 | 61591 | -36591 | 25000 | 25000 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | #NAME? | #NAME? | VEN/SEV/6/CPG/3 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1992) |  | LAC | VEN | SEV | 6 | PRP | 4 | A | T | I |  | 0 | 0 | 0 | 0 | 1992-02-01 | 1992-03-31 | 1993-02-01 |  | 1992-12-01 | 1992-12-01 | 107058 | 69729 | 176787 | 176787 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1992 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | VEN/SEV/6/PRP/4 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of investment projects (1993) |  | LAC | VEN | SEV | 9 | PRP | 14 | A | T | I |  | 0 | 0 | 0 | 0 | 1993-03-01 | 1993-03-31 | 1994-03-01 |  | 1993-12-01 | 1993-12-01 | 156200 | 23305 | 179505 | 179505 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1993 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | VEN/SEV/9/PRP/14 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Supervision of Faaca project implementation (1994) |  | LAC | VEN | SEV | 12 | PRP | 22 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 47190 | -26845 | 20345 | 20345 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Technical mission completed project preparation during 1994. Project submitted and approved by the E.C. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | VEN/SEV/12/PRP/22 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Supervision of Aaisa project implementation (1994) |  | LAC | VEN | SEV | 12 | PRP | 23 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 47190 | -28772 | 18418 | 18418 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Technical mission completed project preparation during 1994. Project submitted and approved by the E.C. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | VEN/SEV/12/PRP/23 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Supervision of Plásticos Molanca project implementation (1994) |  | LAC | VEN | SEV | 12 | PRP | 24 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 83236 | 9685 | 92921 | 92921 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? | Funds utilized for finalizing project preparation and for project supervision. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | VEN/SEV/12/PRP/24 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Supervision of air conditioners project implementation (1994) |  | LAC | VEN | SEV | 12 | PRP | 25 | A | T | I |  | 0 | 0 | 0 | 0 | 1994-03-01 | 1994-03-31 | 1995-03-01 |  | 1994-12-01 | 1994-12-01 | 28665 | -22792 | 5873 | 5873 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1994 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | VEN/SEV/12/PRP/25 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects ODS V (Aaisa) (1995) |  | LAC | VEN | SEV | 16 | PRP | 33 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 22455 | 0 | 22455 | 22455 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | This activity is now complete. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | VEN/SEV/16/PRP/33 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects ODS IV (Faaca) (1995) |  | LAC | VEN | SEV | 16 | PRP | 34 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 19121 | 0 | 19121 | 19121 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | VEN/SEV/16/PRP/34 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects ODS I and II (1995) |  | LAC | VEN | SEV | 16 | PRP | 35 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 36430 | 0 | 36430 | 36430 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | VEN/SEV/16/PRP/35 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation/supervision of investment projects (central air chillers) (1995) |  | LAC | VEN | SEV | 16 | PRP | 36 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-03-01 | 1995-03-01 | 1996-03-01 |  | 1995-12-01 | 1995-12-01 | 23966 | 0 | 23966 | 23966 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | VEN/SEV/16/PRP/36 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | LAC | VEN | SEV | 18 | PRP | 41 | A | O | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-12-31 |  | 1996-12-31 | 1996-12-31 | 40000 | 0 | 40000 | 40000 | 100 | 0 | 0 |  | 5200 | 0 | 5200 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? | Project has been dropped in FY97. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | VEN/SEV/18/PRP/41 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | LAC | VEN | SEV | 21 | PRP | 53 | A | O | I |  | 0 | 0 | 0 | 0 | 1997-02-01 | 1997-03-31 | 1997-12-01 |  | 1997-12-01 | 1997-12-01 | 10000 | 0 | 10000 | 10000 | 100 | 0 | 0 |  | 1300 | 0 | 1300 | 0 | 0 | 1997 | #NAME? | #NAME? | #NAME? | #NAME? | Project has been dropped in FY97. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | VEN/SEV/21/PRP/53 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
ONG | IBRD | Project preparation for methyl bromide phase-out plan |  | ASP | VIE | FUM | 44 | PRP | 44 | A | O | I |  | 0 | 0 | 0 | 0 | 2004-12-01 |  | 2005-12-01 | 2005-12-01 |  |  | 65000 | 0 | 65000 | 0 | 0 | 65000 | 65000 | 65000 | 4875 | 0 | 0 | 4875 | 4875 | 2004 | #NAME? | #NAME? | #NAME? | #NAME? | National consulting team is being recruited. It is expected that the selection process and contract award will take place within the first quarter of 2005. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | VIE/FUM/44/PRP/44 | [7 empty] | 2004 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Preparation of a national CFC phase-out plan |  | ASP | VIE | PHA | 39 | PRP | 41 | A | O | I |  | 0 | 0 | 0 | 0 | 2003-04-01 | 2003-12-01 | 2004-09-01 |  | 2004-09-01 | 2004-11-01 | 60000 | 0 | 60000 | 60000 | 100 | 0 | 0 |  | 4500 | 0 | 4500 | 0 | 0 | 2003 | #NAME? | #NAME? | #NAME? | #NAME? | Project preparation completed and proposal considered at the 44th ExCom. Project approval expected in Apr. 05. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | VIE/PHA/39/PRP/41 | [7 empty] | 2003 | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Country programme preparation |  | EUR | YUG | SEV | 4 | PRP | 2 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 | 1991-06-30 | 1991-12-01 |  | 1991-12-01 | 1991-12-01 | 20302 | -14877 | 5425 | 5425 | 100 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | YUG/SEV/4/PRP/2 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
CLO | IBRD | Preparation of investment projects (1991) |  | EUR | YUG | SEV | 4 | PRP | 3 | A | T | I |  | 0 | 0 | 0 | 0 | 1991-06-01 |  | 1992-06-01 |  |  | 1992-06-01 | 21432 | -21432 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 1991 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | 0 | 0 | 0 | 0 | YUG/SEV/4/PRP/3 | [8 empty] | Non-INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 commercial refrigeration equipment production to HFC-134a and HCFC-22 refrigerant, and CFC-11 to HCFC-141b as the blowing agent for foam insulation at Ref-air Refrigeration | Individual | AFR | ZIM | REF | 20 | INV | 6 | N | O | I | CFC | 5.3 | 5.3 | 0 | 0 | 1996-10-01 | 1999-03-01 | 2000-10-01 |  | 2000-11-01 | 2000-11-01 | 43382 | 0 | 43382 | 43382 | 100 | 0 | 0 |  | 5639.66 | 0 | 5639.66 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Because of economic difficulties in Zimbabwe (including significant local currency devaluation and unavailability of forex), not much progress was made until CY00 and the project was completed by 11/00. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ZIM/REF/20/INV/6 |  | 1999-12-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 commercial refrigeration equipment production to HFC-134a and HCFC-22 refrigerant, and CFC-11 to HCFC-141b as the blowing agent for foam insulation at Commercial Refrigeration | Individual | AFR | ZIM | REF | 20 | INV | 7 | N | O | I | CFC | 6.9 | 6.9 | 0 | 0 | 1996-10-01 | 1999-03-01 | 2000-10-01 |  | 2001-08-01 | 2001-08-01 | 156636 | -15061 | 141575 | 141575 | 100 | 0 | 0 |  | 20363 | -1957.93 | 18405.07 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ZIM/REF/20/INV/7 |  | 1999-12-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 refrigerator production to HFC-134a refrigerant and CFC-11 to HCFC-141b as the blowing agent for foam insulation at Capri Refrigeration | Individual | AFR | ZIM | REF | 20 | INV | 8 | N | O | I | CFC | 5.9 | 5.9 | 0 | 0 | 1996-10-01 | 1998-05-01 | 1998-10-01 |  | 1999-11-01 | 1999-11-01 | 106695 | 0 | 106695 | 106695 | 100 | 0 | 0 |  | 13870 | 0 | 13870 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | CFC-11 portion completed 2/97 and CFC-12 portion completed 6/99, but because of the economic difficulties in Zimbabwe (including significant local currency devaluation) and the change of ownership of the company, not much progress was made during CY98. The project was completed in 08/99. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ZIM/REF/20/INV/8 |  | 1999-12-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 refrigerator production to HFC-134a refrigerant and CFC-11 to cyclopentane as the blowing agent for foam insulation at Imperial Derby Refrigeration Ltd. | Individual | AFR | ZIM | REF | 20 | INV | 9 | N | O | I | CFC | 14 | 12.85 | 0 | 0 | 1996-10-01 | 1998-01-01 | 1997-12-01 |  | 1996-03-01 | 2001-05-01 | 310000 | -88275 | 221725 | 221725 | 100 | 0 | 0 |  | 40300 | -11476 | 28824.25 | -0.25 | -0.25 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Project completed. Funds returned at the 35th ExCom. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ZIM/REF/20/INV/9 |  | 1999-12-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Conversion of CFC-12 commercial refrigeration equipment production to HFC-134a and HCFC-22 refrigerant, and CFC-11 to HCFC-141b as the blowing agent for foam insulation at Ajax Refrigeration | Individual | AFR | ZIM | REF | 20 | INV | 10 | N | O | I | CFC | 3.5 | 3.5 | 0 | 0 | 1996-10-01 | 1999-03-01 | 2001-10-01 |  | 1997-01-01 | 2001-08-01 | 61966 | 0 | 61966 | 61966 | 100 | 0 | 0 |  | 8056 | 0 | 8056 | 0 | 0 | 1996 | #NAME? | #NAME? | #NAME? | #NAME? | Company taken over by Commercial Refrigeration and now treated as 2nd production line at Commercial. Project combined with that of Commercial Refrigeration as approved. Financial completion date is the same as Commercial. |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ZIM/REF/20/INV/10 |  | 1999-12-01 | [6 empty] | INV | 0 | 0 | 0 | 0
FIN | IBRD | Project preparation |  | AFR | ZIM | SEV | 18 | PRP | 5 | A | T | I |  | 0 | 0 | 0 | 0 | 1995-11-01 | 1996-03-31 | 1996-11-01 |  | 1996-12-31 | 1996-12-31 | 50000 | 0 | 50000 | 50000 | 100 | 0 | 0 |  | 6500 | 0 | 6500 | 0 | 0 | 1995 | #NAME? | #NAME? | #NAME? | #NAME? |  |  |  | #NAME? | #NAME? | #NAME? | 0 | 0 | ZIM/SEV/18/PRP/5 | [8 empty] | Non-INV | 0 | 0 | 0 | 0

## Multi-Year
Country | Sector Plan/National ODS Phase-Out Plan | Date Approved | Planned Date of Completion | Funds Committed by ExCom (US$) | Funds Released including Present Year by ExCom (US$) | Funds Disbursed to the Country (US$) | Total ODP Consumption to be Phase-out for the Plan | ODP Counsumption Allowed for the Reporting Year | Actual ODP Consumption for Reporting Year | Total ODP Production to be Phase-out for the Plan | ODP Production Allowed for the Reporting Year | Actual ODP Production for Reporting Year | Remarks (Achievement of Conditions of Approval, Milestones, Relevant Issues concerning next Targets)
Antigua Barbuda | CFC phase-out management plan | 2004-12-02 | 2008-12-02 | 97300 | 69400 | 0 | 1.8 | 1.8 | 0 | 0 | 0 | 0 | WB is working closely with the Government to establish a legal agreement for channelling funding to the country. WB will work closely with the country on ground work required for supporting implementation. This includes development of TORs for all PMU staff, TORs for technical experts to update training manuals, and TORs for consultants to undertake surveys of refrigerators and MACs in the country.
Argentina | CFC production closure plan | 2002-11-02 | 2009-12-01 | 8300000 | 4300000 | 500000 | 0 | 0 | 0 | 3020 | 3016 | 3016 | Project underway and production targets met for 2002, 2003 and 2004. Sub-grant Agreement signed between the GOA and FIASA in November 2004. Comprehensive study on conditions of the market for FIASA undertaken. Three monitoring activities were implemented during 2004, in order to verify FIASA’a compliance with the 2004 CFC production agreed caps. Equipment to be procured for UEPRO in order to facilitate monitoring activities related to CFC production of CFC in 2005.
Bahamas | Terminal CFC Phaseout Plan for The Bahamas | 2001-12-01 | 2009-12-01 | 560000 | 440000 | 240000 | 66 | 36 |  | 0 | 0 | 0 | Grant Agreement between Bank and the Bahamas effective as of Jun. 04. Disbursement of funds from first tranche made on a retroactive basis upon approval of Progress Report and CFC consumption verification report. Audited account of expenditures and verification report confirmed that the Bahamas met all commitments, as per Excom agreement. Implementation of activities is ongoing as per 2004-2005 Biennial Work Plan. These include, among others, training of customs officials, training of technicians of refrigeration servicing centers, public awareness activities, and policy and regulatory montitoring and control. Disbursement of funds for 2nd tranche will take place once all activities in biennial work plan are completed and verified, and once CFC consumption verification report approved by Excom.
China | Halon Sector | 1997-12-01 | 2010-12-01 | 62000000 | 49800000 | 45786000 | 24480 | 7170 | 3912 | 30060 | 11970 | 5053 | From the initial number of 14 Halon plants, 12 halon 1211 production plants were closed and dismantled completely, and production and capacity was reduced at 2 remaining halon 1211 production plants. Out of a total of 72 halon fire fighting extinguisher manufacturers originally identified as potential beneficiaries, 14 enterprises signed contracts to close extinguisher production, and 44 enterprises signed contracts to convert manufacturing lines for fire extinguishers from halon to non-ODS extinguishers. 52 of the 58 enterprises completed closure/conversions projects, and the rest are presently implementing closure/conversions. Four additional equipment manufacturers were found to be operating without valid licenses and were shut down in 2001 without funding. Out of a total of 22 originally identified halon fire fighting systems manufacturers, 13 enterprises signed contracts to convert manufacturing of halon fire extinguishing systems; 4 of these are completed, and the rest are presently implementing conversions. There are currently 14 remaining fire extinguisher manufacturing enterprises and 9 fire extinguishing system enterprises who have not yet been addressed. A total of 45 TA activities were taken up, including activities for strengthening implementation capacity, and preparation of standards to ensure quality and reliability of halon substitute fire extinguishers and fire extinguishing systems. 28 out of these projects are completed.
China | CFC Production Sector | 1999-03-01 | 2010-12-01 | 150000000 | 98000000 | 69400000 | 0 | 0 | 0 | 44931 | 25300 | 25285 | Annual Program completed. CFC production verified and confirmed to be within target. 2005 Annual Programme approved at the 45th ExCom.
China | Foam Sector | 2001-12-01 | 2010-12-01 | 53846000 | 44316000 | 25650500 | 14143 | 11666 | 11666 | 0 | 0 | 0 | For the 2002AP, three ODS conversion projects will be completed by Jun. 05 and all associated TA activities have completed. Three conversion projects are expected to be completed by Jun. 06 under the 2003AP. All TA activities completed. Six conversion contracts under the 2004AP signed within 2004 and are expected to be completed by Dec. 07. Conversion contracts are under preparation for the 2005AP. According to the newly approved CFC/Halon accelerated phaseout plan, all remaining conversion contracts will be signed within 2005 to meet the zero phaseout target by Dec. 31, 2007 in the foam sector.
China | TCA Sector | 2004-07-01 | 2015-07-01 | 2100000 | 1400000 | 0 | 0 | 0 | 0 | 113 | 113 | 105.6 | Sector plan will be implemented in two stages (2004-08 and 2009-15). Scope of first stage includes: complete dismantling of production facilities of TCA 1 and TCA 3 upon sector plan approval; closure of TCA production in TCA 2 once sector plan approved, dismantling of production facility; control of TCA production in TCA 4 to reduce TCA production to 79 tonnes ODP by 2005; and various policy measures and TA activities along with production phase-out. Policy actions include: banning newly-built equipment which produce TCA; production quota license for TCA; import quota license; and sales registration license for TCA. TA activities will concentrate on strengthening overall institutional framework and management, M&E capabilities of participating institutions. Current activities include preparation of Project Implementation Manual and TORs for TA activities by SEPA. TCA production in 2004 has been verified.
China | CTC/PA Sector | 2002-11-02 | 2010-12-01 | 65000000 | 38000000 | 30400000 | 11160.2 | 5063 | 5063 | 52162 | 54857 | 52353 | CTC production: So far, of the 17 original CTC producers, 11 CTC producers remain. For PA companies, of the 8 CR companies, 4 have been closed in 2004, 1 will be closed in 2005 and 3 will modify their production lines to reduce emission. Closure contracts have been signed with 10 CP-70 producers and all of them have been closed by the end of January 2005. CTC production and consumption as PA in 2004 has been verified and confirmed to be within targets.
Ecuador | National CFC phase-out plan | 2003-12-02 | 2008-12-31 | 1689800 | 1216645 | 40465.34 | 246 | 235 | 143 | 0 | 0 | 0 | SGAs with two enterprises signed and sub-projects fully underway. Two train-the-trainers seminars on good practices in refrigeration completed Sep. 04. Training of refrigeration technicians and customs officers will start early next year. Import quota system for all ODS is in place as of May 04.
India | CFC production sector gradual phase-out project | 1999-11-01 | 2010-01-01 | 82000000 | 57850000 | 50710000 | 0 | 0 | 0 | 22588 | 13176 | 13069 | Annual Programme satisfactorily implemented with compliance of CY2004 CFC production targets. Disbursement to the CFC producing enterprises on target. Implementation of TA component has been slow primarily due to staffing problems at the PMU and Ozone Cell and disconnected oversight by UNEP. In November 2004, a new Coordinator was hired and provided initital training by the Bank and by UNEP. There have been a number of discussions between the Bank and UNEP and it was agreed that Performance Indicators would need to be re-worded to clearly define specific outputs and outcomes and UNEP's oversight role under this project.
India | CTC phase-out plan for the consumption and production sectors | 2003-07-01 | 2010-01-01 | 38100954 | 18100000 | 0 | 11505 | 11505 |  | 11553 | 11553 |  | There were no targets or limits for CTC consumption and production for 2003 and 2004. Activities under the PA sector and chemical solvents are to be implemented through the Bank. Project appraisal was completed in Mar.; negotiations in Aug. and project signing took place in Dec. 04. Some preliminary project activities were initiated. In 2004, two consumption sector workshops were held. Enterprises were informed of the eligibility criteria, procedures, and other requirements for accessing grant resources provided by the MLF and project proposals were submitted to the Ozone Cell for review. Similarly, two workshops for the CTC producers were held in 2004. An informal arrangement regarding production quota distribution and MLF resource allocation among producers was reached and will be formalized in 2005. Preparation of the draft verification framework is on track and verification framework is expected to be completed in 2005.
Indonesia | Phase-out of residual CFCs in the foam sector | 2004-04-01 | 2007-12-01 | 2957564 | 1725000 | 100000 | 352 | 352 |  | 0 | 0 | 0 | Subgrant Agreement between Group Coordinator and Ministry of Environment for implementation of foam sector investment activities signed in Nov. 04. Confirmation from potential enterprises joining the program expected to be received in early 2005. Sector Plan Management and Coordination Unit will coordinate policy and regulatory activities. For the non-investment component (public awareness and technical assistance), MoE will request 3 qualified firms to send expressions of interest.
Indonesia | Refrigeration sector phase-out plan: MAC servicing sector | 2002-11-02 | 2008-12-31 | 4317000 | 4064400 | 2717100 | 915 | 585 |  | 0 | 0 | 0 | 2003 AP completed sucessfully.TA activities under 2004 AP concentrate on: (a) strengthening overall institutional framework for phase-out; (b) regulatory support; (c) public awareness, (d) management, monitoring and evaluation and enhancement of capabilities of participating institutions under PMU; (e) project implementation that will be subcontracted to an independent institution, and, (f) information exchange. Activities carried out in the first implementation program are as follow: (i) Workshops to MAC service shop personnel involved in implementation of phase-out activities. (ii) National Workshop. (iii) Promotional program was launched during the commemoration of International Ozone Day (iv) Train the trainer program. (v) Development of Standard Inspection Manual. (vi) Development and printing of pamphlets. (vii) Training.
Malaysia | National CFC phaseout plan | 2001-12-01 | 2009-12-01 | 11517005 | 8470405 | 2585141 | 1910.51 | 1188.51 |  | 0 | 0 | 0 | Significant progress in the implementation of NCPP. Country met its commitments to the Montreal Protocol, as demontrated by its 2003 and 2004 consumption reports. Achievements for 2004included near completion of conversion projects in the foam sector, significant progress in the conversion of the MAC servicing sector, development of final proposals for the solvent sector, and completion of multiple public awareness and dissemination activities. Disbursement rates have increased as all parties involved become increasingly proficient in the process of project preparation, appraisal and verification.
Philippines | National CFC phase out plan | 2002-11-01 | 2010-11-01 | 10216876 | 6895962 | 649984.69 | 2017.6 | 1810 |  | 0 | 0 | 0 | PMU completely staffed in 2004. MDI strategy finalized Apr. 04 and corresponding admin. order signed Jun. 04. Technical specs for servicing sector equipment identified and equipment suppliers accredited. Notice of Award issued for equipment procurement for training centers in Dec. 04. Activities underway. For manufacturing, 8 project proposals endorsed by DENR to the FI for appraisal. 2 SGAs signed. FI conducted orientation mtg for enterprises on procurement and disbursement procedures. Code of Practice finalized. 222 trainers trained for RAC/MAC. 25 technicians trained to participate in Voucher System pilot. 2005 plan includes commencement of wider servicing sector activities after completion of pilot phase, training of technicians, procurement for pilot reclamation facility and completion of several manufacturing sector projects.
Thailand | National CFC phaseout plan | 2001-12-01 | 2009-12-01 | 14728626 | 12392026 | 1774795.53 | 3107.52 | 2332.52 | 1358 | 0 | 0 | 0 | Delays in implementation of initial activities were due to required amendments to the Grant Agreement between Thailand and the Bank, difficulties in establishing mechanisms for the flow of funds, and trouble signing agreements with beneficiary enterprises. With regards to phaseout activities in the solvent sector, SGA signed with one enterprise and baseline equipment disposed of. EGAT is the final enterprise that will be converted in this sector. SGA signed. PMU developed a group sub-project proposal for the MAC service sector. As of Dec. 04, approximately 600 vouchers were hand-on certified MAC service shops. Vouchers for the rest will be continuing in 2005.
Thailand | National methyl bromide phase-out plan | 2004-12-01 | 2012-12-01 | 2901600 | 546991 | 0 | 241.8 | 183.1 |  | 0 | 0 | 0 | Consultation workshop will be held early in 2005 to present final strategy to stakeholders. Grant Agreement between the WB and Thailand expected to be amended in the first semester of 2005. Talks between the Bank, DOA and DIW have started, and mechanisms for project implementation are being put into place.
Turkey | CFC Phase-out plan for Turkey | 2001-12-01 | 2009-12-01 | 9000000 | 7750000 | 5957273.46 | 977 | 316 | 258 | 0 | 0 | 0 | Under the first tranche, conversion of 61 SMEs and first phase of training part completed. Second phase of training is to begin. R&R part is under implementation. For chillers, chiller conversion of 2 companies completed. Conversion of 13 SMEs completed under the 2003 AP and training part of RSP and customs training implementation started in 2003. Installation of R&R part started in 2003. Chiller conversion of 3 companies completed. For activities under the 2004 AP, 3 SME contracts signed in 2004. Second phase of training is planned to continue along with implementation of R&R and customs training. 4 companies contracted for chiller conversion in 04.
Venezuela | Phased reduction and closure of the entire CFC production | 2004-12-02 | 2008-12-31 | 16500000 | 3300000 | 0 | 0 | 0 | 0 | 4400 | 4400 | 3564 | TOR for the verification audit of 2004 production prepared, audit completed in May 2005 and Grant Agreement signed with PRODUVEN and FONDOIN in May 2005.

## CLO and TRF
Agency | Number of Projects | Approved Funding (US$) | Adjustments (USS) | Approved Funding Plus Adjustment (US$) | Funds Disbursed (US$) | Balances (US$) | Percent of Funds Disbursed | Consumption ODP to Be Phased Out | Consumption ODP Phased Out | Production ODP to Be Phased Out | Production ODP Phased Out | Estimated Disbursement in Current Year (US$)
Closed Projects
UNDP | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
UNEP | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
UNIDO | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
World Bank | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Bilaterals | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Total | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Transferred Projects
UNDP | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
UNEP | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
UNIDO | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
World Bank | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Bilaterals | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Total | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!

## Total Funds
Item | UNDP (US$) | UNEP (US$) | UNIDO (US$) | World Bank (US$)* | Bilaterals (US$) | Grand Total (US$)*
Sector
Aerosol | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Foam | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Halon | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Fumigants | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Multiple Sectors | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Other | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Phaseout Plan | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Process Agent | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Production | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Refrigeration | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Several | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Solvents | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Sterilant | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Sub-Total | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Agency fees/administrative costs | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
GRAND TOTAL | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
*13 per cent agency fees were charged starting in July 1995, prior to which actual administrative costs were charged as project preparation or technical assistance.
Region
Africa | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Asia & Pacific | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Europe | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Latin America and Caribbean | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Global | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Implementation Characteristics
Agency Implementation | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
National Implementation | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Time or Objective-sensitive Accounts
Time-Sensitive | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Objective-Sensitive | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Disbursement Method
During Implementation | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
After Implementation | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Retroactive Funding | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Note: The sum of each section (Region, Sector, etc.) equals the Grand Total.

## Annual Summary detail
Year Approved/Implementation Characteristic | Number of Approvals* | Number Completed | Per Cent Completed | Consumption ODP to be Phased Out* | Consumption ODP Phased Out | Per Cent of Consumption ODP Phased Out | Production ODP to be Phased Out* | Production ODP Phased Out | Per Cent of Production ODP Phased Out | Approved Funding (US $) | Adjustment (US $) | Funds Disbursed (US $) | Per Cent of Funds Disbursed | Balance (US $) | Estimated Disbursement in Current Year (US $) | Support Costs Approved (US$) | Support Cost Adjustments (US$)
Disbursement during Implementation
1991 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1992 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1993 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1994 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1995 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1996 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1997 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1998 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1999 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2000 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2001 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2002 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2003 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2004 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Sub-Total | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Disbursement after Completion**
1991 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1992 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1993 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1994 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1995 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1996 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1997 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1998 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1999 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2000 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2001 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2002 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2003 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2004 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Sub-Total | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Retroactively Funded | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Time-sensitive Accounts | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
GRAND TOTAL | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
* Does not include the __ transferred and __ closed projects included in the database.
** Does not include projects that were implemented before Executive Committee approval.
Note 1: Agency and National implementation is not distinguished in this table.
Note 2: Retroactive projects and time-sensitive accounts are provided for all years as one cumulative figure (not included in annual data).

## Annual Summary
Year Approv-ed | Number of Ap-prov-als* | Number Com-pleted | Per Cent Com-pleted | Consumption ODP to be Phased Out* | Consumption ODP Phased Out* | Per Cent of Consumption ODP Phased Out | Production ODP to be Phased Out* | Production ODP Phased Out* | Per Cent of Production ODP Phased Out | Approved Funding plus Adjustment (US$) | Funds Disbursed (US$) | Per Cent of Funds Dis-burs-ed | Balance (US$) | Estimated Disbursement in Current Year (US$) | Support Costs Approved (US$) | Support Cost Adjustments (US$)
1991 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1992 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1993 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1994 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1995 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1996 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1997 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1998 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1999 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2000 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2001 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2002 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2003 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
2004 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Total | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
*Excludes Closed and Transferred Projects
Includes Project Preparation

## Agency Comparisons
Item | UNDP | UNEP | UNIDO | World Bank | Bilaterals | Grand Total
Investment Projects
Number of completed projects | #VALUE! | n/a | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Number of ongoing projects | #VALUE! | n/a | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Total ongoing and completed* | #VALUE! | n/a | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Per cent completed | #VALUE! | n/a | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Consumption ODP phased out | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Consumption ODP to be phased out | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Consumption Per cent phased out | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Production ODP phased out | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Production ODP to be phased out | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Production Per cent phased out | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Funds disbursed through 2004 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Estimated disbursements in 2005 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Total funds approved through 2004*** | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Estimated of disbursements through 2005 as percentage of total funds approved through 2004*** | #VALUE! | n/a | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Non-Investment Projects**
Number of completed projects | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Number of ongoing projects | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Total ongoing and completed* | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Per cent completed | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
All Projects
Total funds disbursed | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Total funds approved*** | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Per cent disbursed | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Estimated disbursement in Current Year | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Balance of Funds | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Per cent of 2004 balance committed in 2005 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
* The total number of ongoing and completed projects does not include closed projects and projects that were transferred.
**Does not include project preparation.
*** Includes adjustments.

## Summary Data by Project Type
Type | Number of Approvals* | Number Completed | Per Cent Completed | Approved Funding (US$) | Adjustment (US $) | Funds Disbursed (US $) | Per Cent of Funds Disbursed | Balance (US$) | Estimated Disbursement In Currrent Year (US $)
Country Programme Preparation | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Demonstration Projects | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Institutional Strengthening Projects | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Investment Projects | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Project Preparation | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Technical Assistance Projects | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Training Projects | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
GRAND TOTAL | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
*Excludes Closed and Transferred Projects.

## Cumulative Completed Investment
Item | Number of Projects | Approved Funds plus Adjustment (US $) | Per Cent of Funds Disbursed | Consumption ODP Phased Out** | Production ODP Phased Out** | Average Number of Months from Approval to First Disbursement | Average Number of Months from Approval to Completion | Overall Cost-Effectiveness to the Fund (US$/kg.)
GRAND TOTAL | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Region
Africa | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Asia & Pacific | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Europe | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Latin America and Caribbean | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Global | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Sector
Aerosol | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Foam | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Fumigants | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Halon | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Multiple Sectors* | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Other | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Phaseout Plan | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Process Agent | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Production | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Refrigeration | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Solvents | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Sterilant | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Implementation Characteristics
Agency Implementation | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
National Implementation | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Time or Objective-sensitive Accounts
Time-Sensitive | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Objective-Sensitive | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Disbursement Method
During Implementation | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
After Implementation | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Retroactive Funding | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
* No funds are listed for the multiple sector investment project, but are recorded in appropriate sector.
** Total phased out for the Fund is ____ includes ____ from completed non-investment projects and ____ from ongoing projects.
Note: The sum of each section (Region, Sector, etc.) equals the Grand Total.

## Cumulative Ongoing Investment
Item | Number of Projects | Approved Funds plus Adjustment (US$) | Per Cent of Funds Dis-bursed | Number of Projects Disburs-ing | Per Cent of Projects Disburs-ing | Estimated Disbursement plus Funds Disbursed | Per Cent Funds Expected to be Disbursed by End of 2004 | Average Number of Months from Approval to First Disburse-ment | Average Number of Months from Approval to Planned Completion | Average Length of Delay in Project Planned Comple-tion | Overall Cost-Effective-ness to the Fund (US$/kg.)*
GRAND TOTAL | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Region
Africa | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Asia & Pacific | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Europe | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Latin America and Caribbean | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Global | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Sector
Aerosol | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Foam | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Fumigants | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Halon | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Multiple Sectors | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Other | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Phaseout Plan | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Process Agent | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Production | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Refrigeration | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Solvents | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Sterilant | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Implementation Characteristics
Agency Implementation | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
National Implementation | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Time or Objective-sensitive Accounts
Time-Sensitive | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Objective-Sensitive | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Disbursement Method
During Implementation | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
After Implementation | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Retroactive Funding | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Note: The sum of each section (Region, Sector, etc.) equals the Grand Total.
*Based on the ODS to be phased out according to the proposal.

## Cumulative Completed Non-Invest
Item | Number of Projects | Approved Funds plus Adjustment (US $) | Per Cent of Funds Disbursed | Average Number of Months from Approval to First Disbursement | Average Number of Months from Approval to Completion
GRAND TOTAL | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Region
Africa | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Asia & Pacific | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Europe | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Latin America and Caribbean | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Global | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Sector
Aerosol | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Foam | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Fumigants | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Halon | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Multiple Sectors | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Other | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Phaseout Plan | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Process Agent | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Production | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Refrigeration | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Several | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Solvents | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Sterilant | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Implementation Characteristics
Agency Implementation | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
National Implementation | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Time or Objective-sensitive Accounts
Time-Sensitive | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Objective-Sensitive | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Disbursement Method
During Implementation | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
After Implementation | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Retroactive Funding | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Note:
(1) Per decision 22/11(a)(vi), project preparation is not included as a non-investment project.
(2) The sum of each section (Region, Sector, etc.) equals the Grand Total.

## Cumulative Ongoing Non-Invest
Item | Number of Projects | Approved Funds plus Adjustment (US$) | Per Cent of Funds Disbursed | Number of Projects Disbursing | Per Cent of Projects Disbursing | Estimated Disbursements plus Funds Disbursed | Per Cent Funds Expected to be Disbursed by End of 2004 | Average Number of Months from Approval to First Disbursement | Average Number of Months from Approval to Planned Completion | Average Length of Delay in Project Planned Completion
GRAND TOTAL | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Region
Africa | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Asia & Pacific | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Europe | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Latin America and Caribbean | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Global | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Sector
Aerosol | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Foam | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Fumigants | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Halon | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Multiple Sectors | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Other | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Phaseout Plan | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Process Agent | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Production | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Refrigeration | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Several | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Solvents | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Sterilant | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Implementation Characteristics
Agency Implementation | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
National Implementation | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Time or Objective-sensitive Accounts
Time-Sensitive | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Objective-Sensitive | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Disbursement Method
During Implementation | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
After Implementation | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Retroactive Funding | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Note:
(1) Per decision 22/11(a)(vi), project preparation is not included as a non-investment project.
(2) The sum of each section (Region, Sector, etc.) equals the Grand Total.

## Project Preparation
| COMPLETED PROJECT PREPARATION |  |  |  |  | ONGOING PROJECT PREPARATION
Item | Num-ber of Pro-jects | Approved Funds plus Adjustment (US$) | Per Cent of Funds Dis-bursed | Aver-age Num-ber of Months from Ap-proval to First Dis-burse-ment | Average Number of Months from Approval to Completion | Num-ber of Pro-jects | Approved Funds plus Adjust-ment (US$) | Funds Disbursed (US$) | Per Cent of Funds Dis-burs-ed | Average Number of Months from Ap-proval to First Dis-burse-ment | Average Number of Months from Ap-proval to Planned Com-pletion | Balance (US$) | Estimated Disbursement in Current Year (US$)
GRAND TOTAL | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Agency
UNDP | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
UNEP | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
UNIDO | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
WORLD BANK | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Bilaterals | #VALUE! | #VALUE! | n/a | n/a | n/a | #VALUE! | #VALUE! | #VALUE! | #VALUE! | n/a | n/a | #VALUE! | #VALUE!
Region
Africa | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Asia & Pacific | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Europe | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Latin Amer./Car. | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Global | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Sector
Aerosol | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Foam | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Fumigants | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Halon | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Multiple Sectors | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Other | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Phaseout Plan | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Process Agent | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Production | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Refrigeration | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Several | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Solvents | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Sterilant | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Implementation Type
Agency | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
National | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Time/Objective Accounts
Time | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Objective | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Disbursement
During Imp. | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
After Imp. | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Retroactive | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Note: The sum of each section (Region, Sector, etc.) equals the Grand Total.

## Speed of Delivery Indicators
INVESTMENT PROJECTS
Approval to First Disbursement
| Average | UNDP | [11 empty] | UNIDO | [11 empty] | IBRD
|  | 91-93 | 94 | 95 | 96 | 97 | 98 | 99 | 00 | 01 | 02 | 03 | 04 | 91-93 | 94 | 95 | 96 | 97 | 98 | 99 | 00 | 01 | 02 | 03 | 04 | 91-93 | 94 | 95 | 96 | 97 | 98 | 99 | 00 | 01 | 02 | 03 | 04
Aerosol | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Foam | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Halon | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Refrigeration | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Solvent | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Overall | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Approval to Completion
| Average | UNDP 91-93: UNDP; UNIDO 91-93: UNIDO; IBRD 91-93: IBRD
|  | 91-93 | 94 | 95 | 96 | 97 | 98 | 99 | 00 | 01 | 02 | 03 | 04 | 91-93 | 94 | 95 | 96 | 97 | 98 | 99 | 00 | 01 | 02 | 03 | 04 | 91-93 | 94 | 95 | 96 | 97 | 98 | 99 | 00 | 01 | 02 | 03 | 04
Aerosol | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Foam | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Halon | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Refrigeration | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Solvent | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Overall | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
NON-INVESTMENT PROJECTS
Approval to First Disbursement
| Average | UNDP 91-93: UNDP; UNIDO 91-93: UNIDO; IBRD 91-93: IBRD | UNEP
|  | 91-93 | 94 | 95 | 96 | 97 | 98 | 99 | 00 | 01 | 02 | 03 | 04 | 91-93 | 94 | 95 | 96 | 97 | 98 | 99 | 00 | 01 | 02 | 03 | 04 | 91-93 | 94 | 95 | 96 | 97 | 98 | 99 | 00 | 01 | 02 | 03 | 04 | 91-93 | 94 | 95 | 96 | 97 | 98 | 99 | 00 | 01 | 02 | 03 | 04
CPG | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
TAS | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
TRA | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
INS | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Overall | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Approval to Completion
| Average | UNDP 91-93: UNDP; UNIDO 91-93: UNIDO; IBRD 91-93: IBRD; UNEP 91-93: UNEP
|  | 91-93 | 94 | 95 | 96 | 97 | 98 | 99 | 00 | 01 | 02 | 03 | 04 | 91-93 | 94 | 95 | 96 | 97 | 98 | 99 | 00 | 01 | 02 | 03 | 04 | 91-93 | 94 | 95 | 96 | 97 | 98 | 99 | 00 | 01 | 02 | 03 | 04 | 91-93 | 94 | 95 | 96 | 97 | 98 | 99 | 00 | 01 | 02 | 03 | 04
CPG | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
TAS | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
TRA | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Overall | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!