EXECUTIVE COMMITTEE OF
  THE MULTILATERAL FUND FOR THE
  IMPLEMENTATION OF THE MONTREAL PROTOCOL
Fifty-seventh Meeting
Montreal, 30 March - 3 April 2009

DRAFT DECISION ON THE NATIONAL CFC PHASE-OUT PLAN IN

THE BOLIVARIAN REPUBLIC OF VENEZUELA

(2009 WORK PROGRAMME)

1.	Following the discussion, the Executive Committee decided:

- To noted the progress report on the implementation of the national phase-out plan (NPP) in the Bolivarian Republic of Venezuela during the years 2007 and 2008;

- To note that the Bolivarian Republic of Venezuela was in non-compliance with the Agreement between the Executive Committee and the Government of the Bolivarian Republic of Venezuela for the year 2006;

- To note that the Bolivarian Republic of Venezuela had taken action to effectively return to compliance with the Agreement, mentioned in paragraph (b) above, for the year 2007;

- To note the commitment of the Government of the Bolivarian Republic of Venezuela, as reported by UNIDO, to export or destroy any remaining stockpiled CFCs;

- To apply the penalty clause in the Agreement mentioned in paragraph (b) above. calculated at 20 per cent of the amount of the tranche being submitted to the Executive Committee for approval for non-compliance with the Agreement, on the basis of the following considerations:

  - That it was the first time that the country had been in non-compliance with the Agreement;

  - That non-compliance with the Agreement did not lead to aggregated consumption for all years of the Agreement being larger than the aggregated values of the agreed consumption for those years;

  - The country had returned to compliance without additional assistance from the Fund;

- To use the method outlined in sub-paragraph (e) above and to apply a US $128,366 penalty to the fourth tranche of the NPP for the Bolivarian Republic of Venezuela;

- To approve the fourth tranche of the NPP for the Bolivarian Republic of Venezuela at the amount of US $513,465, plus agency support costs of US $38,510, which took into account a penalty using the method outlined in sub-paragraph (e) above;

- To approve the implementation programme for 2009, with the flexibility to foresee the need for additional verification efforts; and

- To request UNIDO to submit, no later than eight weeks prior to the 61st Meeting of the Executive Committee, a verification of the level of stockpiles of CFCs at the end of  the years 2008 and 2009, any export of CFCs during 2008 and 2009, and the destruction of any remaining CFCs, that were not exported prior to December 2009

-----