Annex III

Table 1

ANNUAL TRANCHES NOT SUBMITTED TO TWO OR MORE CONSECUTIVE MEETINGS

| Agency | Country | Sector | Tranche | Reason for delay | Planned Submission |
| --- | --- | --- | --- | --- | --- |
| World Bank | Antigua and Barbuda | CFC Phase Out Plan | 2006 | Funds not advance to NOU due to the financial crisis as per the reimbursement approach agreed in the signed grant agreement. | 61st Meeting |
| UNEP | Democratic People's Republic of Korea (the) | CFC Phase Out Plan | 2009 | Deferred consideration by decision until 61st Meeting. | 61st Meeting |
| UNDP | Dominica | CFC Phase Out Plan | 2009 | Low disbursement of funds from approved tranches. | 61st Meeting |
| UNEP | Dominica | CFC Phase Out Plan | 2009 | Low disbursement of funds from approved tranches. Country received 2nd and 3rd annual tranches. Sufficient funding at this stage. | 62nd Meeting |
| UNEP | Eritrea | ODS Phase Out Plan | 2009 | Licensing system not in place. | 61st Meeting |
| UNIDO | Eritrea | ODS Phase Out Plan | 2009 | ODS legislation not in place. | 62nd Meeting |
| UNEP | Guatemala | CFC Phase Out Plan | 2009 | Low disbursement of funds from approved tranche and sufficient funding at this stage. | 62nd Meeting |
| UNEP | Kuwait | ODS Phase Out Plan | 2008 | Verification audit had not been completed in time. | 61st Meeting |
| UNIDO | Kuwait | ODS Phase Out Plan | 2008 | Verification audit had not been completed in time. | 61st Meeting |
| France | Lao People's Democratic Republic (the) | CFC Phase Out Plan | 2009 | Insufficient rate of disbursement. | 61st Meeting |
| UNDP | Peru | CFC Phase Out Plan | 2009 | Delay in the first tranche due to institutional changes. | 61st Meeting |
| UNEP | Peru | CFC Phase Out Plan | 2009 | Low disbursement of funds from approved tranche. Sufficient funding at this stage. | 62nd Meeting |
| UNDP | Saint Kitts and Nevis | CFC Phase Out Plan | 2009 | Low disbursement. | 61st Meeting |
| UNEP | Saint Kitts and Nevis | CFC Phase-out Plan | 2009 | Country received 2nd and 3rd annual tranches. Sufficient funding at this stage. | 62nd Meeting |
| UNEP | Saint Vincent and the Grenadines | CFC Phase-out Plan | 2009 | Insufficient progress made with respect to the implementation of the approved tranches. | 62nd Meeting |
| UNEP | Suriname | CFC Phase Out Plan | 2009 | Insufficient progress made with respect to the implementation of the approved tranches and sufficient funding at this stage. | 62nd Meeting |
| World Bank | Turkey | CFC Phase Out Plan | 2008 | Verification audits (2007 and 2008) not completed and annual programme incomplete. | 61st Meeting |

# Table 2

ANNUAL TRANCHES NOT SUBMITTED THAT WERE DUE FOR THE FIRST TIME

FOR SUBMISSION TO THE 60TH MEETING

| Agency | Country | Sector | Tranche | Reason for Delay | Planned Submission |
| --- | --- | --- | --- | --- | --- |
| UNEP | Burundi | CFC Phase Out Plan | 2009 | Low disbursement and slow implementation. | 61st Meeting |
| UNIDO | Burundi | CFC Phase Out Plan | 2009 | Sufficient funds available on existing tranche. | 61st Meeting |
| France | Central African Republic (the) | CFC Phase Out Plan | 2009 | Insufficient rate of disbursement of the 1st tranche. | 61st Meeting |
| UNEP | Central African Republic (the) | CFC Phase Out Plan | 2009 | Low disbursement and slow start-up of first tranche. | 61st Meeting |
| UNDP | Democratic Republic of the Congo (the) | CFC Phase Out Plan | 2008 | Low disbursements. | 61st Meeting |
| UNEP | Democratic Republic of the Congo (the) | CFC Phase-Out Plan | 2008 | Insufficient progress made with respect to the implementation of the approved tranche due to structural and administrative changes in the Ministry. | 61st Meeting |
| UNEP | Equatorial Guinea | ODS Phase Out Plan | 2010 | Delays to start implementation of first tranche but sufficient funds available at this stage. | 61st Meeting |
| UNEP | Haiti | CFC Phase Out Plan | 2010 | Sufficient funding at this stage. | 63rd Meeting |
| UNEP | Saudi Arabia | ODS Phase Out Plan | 2010 | Verification audit had not been completed. | 61st Meeting |
| UNIDO | Saudi Arabia | ODS Phase Out Plan | 2010 | Verification audit had not been completed. | 61st Meeting |
| UNDP | Sierra Leone | ODS Phase Out Plan | 2010 | Low disbursements. | 61st Meeting |
| UNEP | Sierra Leone | ODS Phase Out Plan | 2010 | Delays at the start of implementation of first tranche bit sufficient funds available at this stage. | 61st Meeting |
| World Bank | Tunisia | ODS Phase Out Plan | 2008 | Delays in the procurement of servicing sector equipment and low disbursement. | 61st Meeting |

-----